## Dashboard
PS2 EIT Backlog
Discipline Scope | Total ITRS | Total closed | Total Open | Backlog from Construction Team | Backlog from Precom Team | Construction Not yet started
E - Electrical | 1194 | 244 | 950 | 4 | 12 | 882
I - Instrumentation | 1029 | 180 | 849 | 12 | 0 | 832
T - Telecom | 6 | 0 | 6 | 0 | 0 | 6

## CMT Data
Task ID | Asset - Tag | Description | Category (Summary) | Discipline (Summary) | Asset - Description | Responsible Company | Documents | Systemization - Subsystem (Summary) | Closed By | Construction update/Issue | ITR closeout plan (Planned date) | Remarks 2 | Remarks | RFI Number
T-00005-0046 | PS2-61-IJ-0001 | CPX04 - HV switchboard | PCOM - Precommissioning | E - Electrical | MV Switchgear | EITS |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) | ardila, ardila |  | Closed | Closed
T-00005-0047 | PS2-61-IJ-0010 | CPX04 - HV switchboard | PCOM - Precommissioning | E - Electrical | MV Switchgear | EITS |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) | ardila, ardila |  | Closed | Closed
T-00005-0048 | PS2-61-IJ-0011 | CPX04 - HV switchboard | PCOM - Precommissioning | E - Electrical | MV Switchgear | EITS |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) | ardila, ardila |  | Closed | Closed
T-00005-0092 | PS2-61-IJ-0001_busbar | CPX04 - HV switchboard | PCOM - Precommissioning | E - Electrical | MV Switchgear | EITS |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | Not CPP EIT Scope |  | Construction not yet started |  | #N/A
T-00018-0063 | PS2-61-ISR-0101 | CPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | Shunt Reactor | CPP AGI | UG-MID-65-SSF1-150257 | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | Transformer installed at site, Cable termination and earthing to be completed | Vendor Scope | Vendor Scope |  | #NAME?
T-00018-0064 | PS2-61-IU-0010 | CPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | LLHT Oil Transformer | CPP AGI | UG-MID-65-SSF1-150257 | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  | Transformer installed at site, Cable termination and earthing to be completed | Vendor Scope | Vendor Scope | ETA- 15th JULY 2026 | #NAME?
T-00018-0065 | PS2-61-IU-0011 | CPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | LLHT Oil Transformer | CPP AGI | UG-MID-65-SSF1-150257 | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  | Transformer installed at site, Cable termination and earthing to be completed | Vendor Scope | Vendor Scope |  | #NAME?
T-00018-0066 | PS2-61-IV-0001A | CPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | Distribution Transformer | CPP AGI | UG-MID-65-SSF1-150257 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Transformer installed at site, Cable termination and earthing to be completed | Vendor Scope | Vendor Scope |  | #NAME?
T-00018-0067 | PS2-61-IV-0001B | CPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | Distribution Transformer | CPP AGI | UG-MID-65-SSF1-150257 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Transformer installed at site, Cable termination and earthing to be completed | Vendor Scope | Vendor Scope |  | #NAME?
T-00018-0068 | PS2-63-IV-0010 | CPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | Earthing Transformer | CPP AGI | UG-MID-65-SSF1-150257 | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | Transformer not availabe (CPY action) | Vendor Scope | Vendor Scope | Not Available | #NAME?
T-00018-0170 | PS2-61-IU-3100C | CPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | 33kV VSD Transformer | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Transformer installed at site, Cable termination and earthing to be completed | Vendor Scope | Vendor Scope |  | #NAME?
T-00018-0180 | PS2-61-IU-3100A | CPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | VSD Transformer | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Transformer installed at site, Cable termination and earthing to be completed | Vendor Scope | Vendor Scope |  | #NAME?
T-00018-0181 | PS2-61-IU-3100B | CPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | VSD Transformer | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Transformer installed at site, Cable termination and earthing to be completed | Vendor Scope | Vendor Scope |  | #NAME?
T-00018-0211 | PS2-79-IV-0001 | CPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | Feeder to EHT Transformer / DB 1 | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  | Transformer installed at site, Cable termination and earthing to be completed | Vendor Scope | Vendor Scope |  | #NAME?
T-00018-0212 | PS2-79-IV-0002 | CPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | Feeder to EHT Transformer / DB 2 | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  | Transformer installed at site, Cable termination and earthing to be completed | Vendor Scope | Vendor Scope |  | #NAME?
T-00018-0213 | PS2-79-IV-0003 | CPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | Feeder to EHT Transformer / DB 3 | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  | Transformer installed at site, Cable termination and earthing to be completed | Vendor Scope | Vendor Scope |  | #NAME?
T-00018-0214 | PS2-79-IV-0004 | CPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | Feeder to EHT Transformer / DB 4 | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  | Transformer installed at site, Cable termination and earthing to be completed | Vendor Scope | Vendor Scope |  | #NAME?
T-00018-0215 | PS2-79-IV-0005 | CPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | Feeder to EHT Transformer / DB 5 | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  | Transformer installed at site, Cable termination and earthing to be completed | Vendor Scope | Vendor Scope |  | #NAME?
T-00019-0022 | PS2-61-IK-0001 | CPX05 - LV switchboard | PCOM - Precommissioning | E - Electrical | Main LV MCC SWGR | EITS |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) | sari, indera | Not CPP EIT Scope | Closed | Closed |  | N/A
T-00022-0001 | PS2-79-BH-0001-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0010 TO PS2-79-BH-0001 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-0002 | PS2-79-BH-0001-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0010 TO PS2-79-BH-0001 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-0003 | PS2-79-BH-0001-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0010 TO PS2-79-BH-0001 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-0004 | PS2-79-BH-0002-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0011 TO PS2-79-BH-0002 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-0005 | PS2-79-BH-0002-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0011 TO PS2-79-BH-0002 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-0006 | PS2-79-BH-0002-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0011 TO PS2-79-BH-0002 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2864 | PS2-25-DM-3100A-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2865 | PS2-25-DM-3100A-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2866 | PS2-25-DM-3100A-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2867 | PS2-25-DM-3100A-CH04 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2868 | PS2-25-DM-3100A-CH05 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2869 | PS2-25-DM-3100A-CH06 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2870 | PS2-25-DM-3100B-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2871 | PS2-25-DM-3100B-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2872 | PS2-25-DM-3100B-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2873 | PS2-25-DM-3100B-CH04 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2874 | PS2-25-DM-3100B-CH05 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2875 | PS2-25-DM-3100B-CH06 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2876 | PS2-25-DM-3100C-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2877 | PS2-25-DM-3100C-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2878 | PS2-25-DM-3100C-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2879 | PS2-25-DM-3100C-CH04 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2880 | PS2-25-DM-3100C-CH05 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2881 | PS2-25-DM-3100C-CH06 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2882 | PS2-61-IDH-3100A-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2883 | PS2-61-IDH-3100A-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2884 | PS2-61-IDH-3100A-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2885 | PS2-61-IDH-3100A-CH04 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2886 | PS2-61-IDH-3100A-CH05 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2887 | PS2-61-IDH-3100A-CH06 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2888 | PS2-61-IDH-3100A-CH07 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2889 | PS2-61-IDH-3100A-CH08 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2890 | PS2-61-IDH-3100A-CH09 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2891 | PS2-61-IDH-3100A-CH10 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2892 | PS2-61-IDH-3100A-CH11 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2893 | PS2-61-IDH-3100A-CH12 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2894 | PS2-61-IDH-3100B-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2895 | PS2-61-IDH-3100B-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2896 | PS2-61-IDH-3100B-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2897 | PS2-61-IDH-3100B-CH04 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2898 | PS2-61-IDH-3100B-CH05 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2899 | PS2-61-IDH-3100B-CH06 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2900 | PS2-61-IDH-3100B-CH07 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2901 | PS2-61-IDH-3100B-CH08 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2902 | PS2-61-IDH-3100B-CH09 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2903 | PS2-61-IDH-3100B-CH10 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2904 | PS2-61-IDH-3100B-CH11 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2905 | PS2-61-IDH-3100B-CH12 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2906 | PS2-61-IDH-3100C-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2907 | PS2-61-IDH-3100C-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2908 | PS2-61-IDH-3100C-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2909 | PS2-61-IDH-3100C-CH04 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2910 | PS2-61-IDH-3100C-CH05 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2911 | PS2-61-IDH-3100C-CH06 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2912 | PS2-61-IDH-3100C-CH07 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2913 | PS2-61-IDH-3100C-CH08 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2914 | PS2-61-IDH-3100C-CH09 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2915 | PS2-61-IDH-3100C-CH10 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2916 | PS2-61-IDH-3100C-CH11 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2917 | PS2-61-IDH-3100C-CH12 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | 35m cable pulled, cable coiled near VSD transformer and Beneath Ehouse | Closed | Closed |  | #NAME?
T-00022-2918 | PS2-61-IJ-0010-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IJ-0010 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) | rajeev, manu | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2919 | PS2-61-IJ-0010-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IJ-0010 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) | rajeev, manu | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2920 | PS2-61-IJ-0010-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IJ-0010 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) | rajeev, manu | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2921 | PS2-61-IJ-0011-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IJ-0011 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) | rajeev, manu | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2922 | PS2-61-IJ-0011-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IJ-0011 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) | rajeev, manu | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2923 | PS2-61-IJ-0011-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IJ-0011 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) | rajeev, manu | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2924 | PS2-61-ISR-0101-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-ISR-0101 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2925 | PS2-61-ISR-0101-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-ISR-0101 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2926 | PS2-61-ISR-0101-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-ISR-0101 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2927 | PS2-61-IU-0010-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0010 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) | rajeev, manu | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2928 | PS2-61-IU-0010-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0010 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) | rajeev, manu | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2929 | PS2-61-IU-0010-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0010 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) | rajeev, manu | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2930 | PS2-61-IU-0011-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0011 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) | rajeev, manu | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2931 | PS2-61-IU-0011-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0011 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) | rajeev, manu | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2932 | PS2-61-IU-0011-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0011 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) | rajeev, manu | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2933 | PS2-61-IU-3100A-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | 90m cable laying completed | Closed | Closed | 2026-06-19 | #NAME?
T-00022-2934 | PS2-61-IU-3100A-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | 90m cable pulled, coiled below EITS building, The coiled cable to be routed to the cubicle | Closed | Closed | 2026-06-19 | #NAME?
T-00022-2935 | PS2-61-IU-3100A-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | 90m cable pulled, coiled below EITS building, The coiled cable to be routed to the cubicle | Closed | Closed | 2026-06-19 | #NAME?
T-00022-2936 | PS2-61-IU-3100A-CH04 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0006A TO PS2-61-IU-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  |  | Closed | Closed |  | #NAME?
T-00022-2937 | PS2-61-IU-3100B-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | 100m cable pulled, coiled below EITS building, The coiled cable to be routed to the cubicle | Closed | Closed | 2026-06-19 | #NAME?
T-00022-2938 | PS2-61-IU-3100B-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | 100m cable pulled, coiled below EITS building, The coiled cable to be routed to the cubicle | Closed | Closed | 2026-06-19 | #NAME?
T-00022-2939 | PS2-61-IU-3100B-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | 100m cable pulled, coiled below EITS building, The coiled cable to be routed to the cubicle | Closed | Closed | 2026-06-19 | #NAME?
T-00022-2940 | PS2-61-IU-3100B-CH04 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0006B TO PS2-61-IU-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  |  | Closed | Closed |  | #NAME?
T-00022-2941 | PS2-61-IU-3100C-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | 110m cable pulled, coiled below EITS building, The coiled cable to be routed to the cubicle | Closed | Closed | 2026-06-19 | #NAME?
T-00022-2942 | PS2-61-IU-3100C-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | 110m cable pulled, coiled below EITS building, The coiled cable to be routed to the cubicle | Closed | Closed | 2026-06-19 | #NAME?
T-00022-2943 | PS2-61-IU-3100C-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | 110m cable pulled, coiled below EITS building, The coiled cable to be routed to the cubicle | Closed | Closed | 2026-06-19 | #NAME?
T-00022-2944 | PS2-61-IU-3100C-CH04 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0006C TO PS2-61-IU-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  |  | Closed | Closed |  | #NAME?
T-00022-2945 | PS2-61-IV-0001A-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2946 | PS2-61-IV-0001A-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2947 | PS2-61-IV-0001A-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2948 | PS2-61-IV-0001B-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2949 | PS2-61-IV-0001B-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2950 | PS2-61-IV-0001B-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) | Kumar, Vimlesh | HV cable laying done, conformity ITR closed | Closed | Closed |  | #NAME?
T-00022-2951 | PS2-61-NER-0010-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-NER-0010 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  | Work front not available |  | Construction not yet started | Cable drum not available | #NAME?
T-00022-2952 | PS2-61-NER-0011-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-NER-0011 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  | Work front not available |  | Construction not yet started | Cable drum not available | #NAME?
T-00022-2953 | PS2-63-IV-0010-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-63-IV-0010 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | Work front not available |  | Construction not yet started | Cable drum not available | #NAME?
T-00022-2954 | PS2-63-IV-0010-CH02 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-63-IV-0010 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | Work front not available |  | Construction not yet started | Cable drum not available | #NAME?
T-00022-2955 | PS2-63-IV-0010-CH03 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-63-IV-0010 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | Work front not available |  | Construction not yet started | Cable drum not available | #NAME?
T-00022-2956 | PS2-63-NER-0010-CH01 | CPX08 - HV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-63-IV-0010 TO PS2-63-NER-0010 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | Work front not available |  | Construction not yet started | Cable drum not available | #NAME?
T-00023-10506 | PS2-08-85CP-1001-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-85CP-1001 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00023-10515 | PS2-25-DM-3100A-CG01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-10516 | PS2-25-DM-3100A-CG02 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | 205m cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-10517 | PS2-25-DM-3100B-CG01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-10518 | PS2-25-DM-3100B-CG02 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-10519 | PS2-25-DM-3100C-CG01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | 200m cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-10520 | PS2-25-DM-3100C-CG02 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | 200m cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-10844 | PS2-01-LA-0001-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | From PS2-06-IG-0001A To PS2-01-LA-0001 | EITS |  | PS2-0H-01 - HIPPS | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00023-10845 | PS2-01-LA-0001-CS02 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | From PS2-61-IG-0008 To PS2-01-LA-0001 | EITS |  | PS2-0H-01 - HIPPS | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00023-10846 | PS2-01-LA-0001-CS03 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | From PS2-06-IG-0001B To PS2-01-LA-0001 | EITS |  | PS2-0H-01 - HIPPS | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00023-2921 | PS2-08-01FB-0701-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-01FB-0701 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0080
T-00023-2922 | PS2-08-01FB-0702-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-01FB-0701 TO PS2-08-01FB-0702 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00023-2923 | PS2-08-01FB-0703-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-01FB-0702 TO PS2-08-01FB-0703 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00023-2924 | PS2-08-01FB-0704-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-01FB-0703 TO PS2-08-01FB-0704 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0093
T-00023-2925 | PS2-08-01FB-0704-CS02 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-01FB-0704 TO PS2-08-11CB-1001 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0093
T-00023-2926 | PS2-08-01FB-0801-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-01FB-0801 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00023-2927 | PS2-08-01FB-0802-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-01FB-0801 TO PS2-08-01FB-0802 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00023-2928 | PS2-08-01FB-0803-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-01FB-0802 TO PS2-08-01FB-0803 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00023-2929 | PS2-08-01FB-0804-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-01FB-0803 TO PS2-08-01FB-0804 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00023-2930 | PS2-08-01FB-0804-CS02 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-01FB-0804 TO PS2-08-11CB-1001 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00023-2931 | PS2-08-03FB-0001-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-03FB-0001 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00023-2932 | PS2-08-03FB-0002-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-03FB-0002 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00023-2933 | PS2-08-03FB-0101-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-03FB-0101 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00023-2934 | PS2-08-03FB-0102-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-03FB-0102 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00023-2935 | PS2-08-03FB-0103-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-03FB-0103 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0104
T-00023-2936 | PS2-08-03FB-0104-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-03FB-0104 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00023-2937 | PS2-08-12BT-0101-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0101 | EITS | UG-MID-65-WPR2-150100 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0104
T-00023-2938 | PS2-08-12BT-0102-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0102 | EITS | UG-MID-65-WPR2-150100 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00023-2939 | PS2-08-12BT-0104-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0104 | EITS | UG-MID-65-WPR2-150100 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0080
T-00023-2940 | PS2-08-12BT-0105-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0105 | EITS | UG-MID-65-WPR2-150100 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00023-2941 | PS2-08-12BT-0107-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0107 | EITS | UG-MID-65-WPR2-150100 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00023-2942 | PS2-08-15CP-0001-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0001 | EITS | UG-MID-65-WPR2-150100 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0193
T-00023-2943 | PS2-08-15CP-0002-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0002 | EITS | UG-MID-65-WPR2-150100 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0193
T-00023-2944 | PS2-08-15CP-0003-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0003 | EITS | UG-MID-65-WPR2-150100 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0052
T-00023-2945 | PS2-08-15CP-0004-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0004 | EITS | UG-MID-65-WPR2-150100 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0052
T-00023-2946 | PS2-08-15CP-0005-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0005 | EITS | UG-MID-65-WPR2-150100 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00023-2947 | PS2-08-15CP-0006-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0006 | EITS | UG-MID-65-WPR2-150100 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00023-2948 | PS2-08-15CP-0007-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0007 | EITS | UG-MID-65-WPR2-150100 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0087_01
T-00023-2949 | PS2-08-15CP-0008-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0008 | EITS | UG-MID-65-WPR2-150100 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0087_01
T-00023-2950 | PS2-08-52BT-0131-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-52BT-0131 | EITS | UG-MID-65-WPR2-150100 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0104
T-00023-2951 | PS2-08-52BT-0132-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-52BT-0132 | EITS | UG-MID-65-WPR2-150100 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00023-2952 | PS2-08-52BT-0133-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-52BT-0133 | EITS | UG-MID-65-WPR2-150100 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00023-2953 | PS2-08-52BT-0134-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-52BT-0134 | EITS | UG-MID-65-WPR2-150100 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00023-2954 | PS2-08-52BT-0931-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1601 TO PS2-08-52BT-0931 | EITS | UG-MID-65-WPR2-150100 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00023-2955 | PS2-08-61BT-0002-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-14CB-1601 TO PS2-08-61BT-0002 | EITS | UG-MID-65-WPR2-150100 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00023-2956 | PS2-08-85CP-0021-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-85CP-0021 | EITS | UG-MID-65-WPR2-150100 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00023-2957 | PS2-08-85CP-0022-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-85CP-0022 | EITS | UG-MID-65-WPR2-150100 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00023-2958 | PS2-08-85CP-1501-CS01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1501 TO PS2-08-85CP-1501 | EITS | UG-MID-65-WPR2-150100 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00023-2965 | PS2-25-DM-3100A-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-2966 | PS2-25-DM-3100A-CL02 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0014 TO PS2-25-DM-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-2973 | PS2-25-DM-3100B-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-2974 | PS2-25-DM-3100B-CL02 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0014 TO PS2-25-DM-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-2981 | PS2-25-DM-3100C-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-2982 | PS2-25-DM-3100C-CL02 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0014 TO PS2-25-DM-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-2995 | PS2-25-ESDV-0021-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-ESDV-0021 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-01 - Export Pipeline Pig Receiver |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-2996 | PS2-25-ESDV-0023-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-ESDV-0023 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-2997 | PS2-25-FCV-0003A-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-FCV-0003A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-2998 | PS2-25-FCV-0003B-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-FCV-0003B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-2999 | PS2-25-FCV-0003C-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-FCV-0003C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3000 | PS2-25-FCV-0004-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-FCV-0004 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-06 - Crude Oil Export Pumps Discharge |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3009 | PS2-25-MOV-0001-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0001 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-01 - Export Pipeline Pig Receiver |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3010 | PS2-25-MOV-0002-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0002 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-01 - Export Pipeline Pig Receiver |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3011 | PS2-25-MOV-0003-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0003 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-01 - Export Pipeline Pig Receiver |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3012 | PS2-25-MOV-0008-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0008 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3013 | PS2-25-MOV-0011-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0011 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3014 | PS2-25-MOV-0012-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0012 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3015 | PS2-25-MOV-0025-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0025 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-01 - Export Pipeline Pig Receiver |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3016 | PS2-25-MOV-0026-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0026 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-01 - Export Pipeline Pig Receiver |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3017 | PS2-25-MOV-0027-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0027 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-06 - Crude Oil Export Pumps Discharge |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3018 | PS2-25-MOV-0028-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0028 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3019 | PS2-25-SDV-0035A-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0035A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3020 | PS2-25-SDV-0035B-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0035B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3021 | PS2-25-SDV-0035C-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0035C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3022 | PS2-25-SDV-0036A-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0036A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3023 | PS2-25-SDV-0036B-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0036B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3024 | PS2-25-SDV-0036C-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0036C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3025 | PS2-25-SDV-0046-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0046 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-05 - Crude Oil Export Pumps Bypass |  | 100m cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3026 | PS2-25-SDV-0052-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0052 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3027 | PS2-25-SDV-0054A-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0054A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3028 | PS2-25-SDV-0054B-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0054B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3029 | PS2-25-SDV-0054C-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0054C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3031 | PS2-25-XV-0053-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-XV-0053 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-05 - Crude Oil Export Pumps Bypass |  | 125m cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3032 | PS2-25-XV-0070-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-XV-0070 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-05 - Crude Oil Export Pumps Bypass |  | 135m cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3034 | PS2-28-BE-0001-CL02 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0014 TO PS2-28-BE-0001 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | #NAME?
T-00023-3041 | PS2-28-HE-2100-CL02 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0014 TO PS2-28-HE-2100 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-28-03 - Closed Drain Drum & Pump |  | 242 M cable pulled, G&T to be completed |  | Construction not yet started | ETA- 30TH JULY 2026 | #NAME?
T-00023-3042 | PS2-28-LB-8200-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0014 TO PS2-28-LB-8200 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-28-09 - Open Drain Interceptor |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 15th JULY 2026 | #NAME?
T-00023-3043 | PS2-28-SDV-0053A-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-28-SDV-0053A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3044 | PS2-28-SDV-0053B-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-28-SDV-0053B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3045 | PS2-28-SDV-0053C-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-28-SDV-0053C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3046 | PS2-28-SDV-0065-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-28-SDV-0065 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-28-04 - Reinjection Pump |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 15th JULY 2026 | #NAME?
T-00023-3170 | PS2-61-IU-3100A-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-61-IU-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3175 | PS2-61-IU-3100B-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-61-IU-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3180 | PS2-61-IU-3100C-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-61-IU-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3196 | PS2-62-IE-0001-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0004 TO PS2-62-IE-0001 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #NAME?
T-00023-3197 | PS2-62-IE-0002-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0006 TO PS2-62-IE-0002 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00023-3208 | PS2-75-MOV-0001-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-75-MOV-0001 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-28-08 - Open Drains (OD2) |  | 150m cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00023-3209 | PS2-75-UI-6200-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0001A TO PS2-75-UI-6200 | #N/A | UG-MID-65-WPR2-150100 | PS2-75-01 - DRA Injection Package |  | cable not found in cable schedule | Cable not found in Electrical cable schedule | Construction work pending |  | #NAME?
T-00023-3210 | PS2-75-UI-6200-CL02 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0001B TO PS2-75-UI-6200 | #N/A | UG-MID-65-WPR2-150100 | PS2-75-01 - DRA Injection Package |  | cable not found in cable schedule | Cable not found in Electrical cable schedule | Construction work pending |  | #NAME?
T-00023-8583 | PS2-79-IG-0001-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0001 TO PS2-79-IG-0001 | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00023-8584 | PS2-79-IG-0002-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0002 TO PS2-79-IG-0002 | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00023-8585 | PS2-79-IG-0003-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0003 TO PS2-79-IG-0003 | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #NAME?
T-00023-8586 | PS2-79-IG-0004-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0004 TO PS2-79-IG-0004 | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #NAME?
T-00023-8587 | PS2-79-IG-0005-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0005 TO PS2-79-IG-0005 | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #NAME?
T-00023-8600 | PS2-05-IG-0003-CP01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-62-IK-0001 TO PS2-05-IG-0003 | EITS |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 | sari, indera | Closed | Closed | Closed |  | #N/A
T-00023-8601 | PS2-61-IG-0003-CP01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-62-IK-0001 TO PS2-61-IG-0003 | EITS |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 | sari, indera | Closed | Closed | Closed |  | #N/A
T-00023-8973 | PS2-02-SWSI-0002-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0006 TO PS2-02-SWSI-0002 | CPP AGI |  | PS2-02-01 - Miscellaneous Safety equipment |  |  |  | Construction not yet started |  | #NAME?
T-00023-8974 | PS2-03-SEA-0002-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0006 TO PS2-03-SEA-0002 | CPP AGI |  | PS2-03-05 - FZ-G1 - Guard House |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #NAME?
T-00023-8975 | PS2-06-GU-0004-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0007 TO PS2-06-GU-0004 | CPP AGI |  | PS2-06-02 - AC UPS - Guard House |  |  |  | Construction not yet started |  | #NAME?
T-00023-8976 | PS2-08-11CB-1501-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0006 TO PS2-08-11CB-1501 | CPP AGI |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #NAME?
T-00023-8977 | PS2-09-LB-7001-CL01 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0007 TO PS2-09-LB-7001 | CPP AGI |  | PS2-09-02 - HVAC for Guard House |  |  |  | Construction not yet started |  | #NAME?
T-00023-9932 | PS2-62-IE-0001-CL02 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0005 TO PS2-62-IE-0001 | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #NAME?
T-00023-9933 | PS2-62-IE-0001-CL03 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0005 TO PS2-62-IE-0001 | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #NAME?
T-00023-9934 | PS2-62-IE-0001-CL04 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0005 TO PS2-62-IE-0001 | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #NAME?
T-00023-9935 | PS2-62-IE-0001-CL05 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0004 TO PS2-62-IE-0001 | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #NAME?
T-00023-9936 | PS2-62-IE-0001-CL06 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0004 TO PS2-62-IE-0001 | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #NAME?
T-00023-9937 | PS2-62-IE-0001-CL07 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0004 TO PS2-62-IE-0001 | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #NAME?
T-00023-9938 | PS2-62-IE-0002-CL02 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0007 TO PS2-62-IE-0002 | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00023-9939 | PS2-62-IE-0002-CL03 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0007 TO PS2-62-IE-0002 | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00023-9940 | PS2-62-IE-0002-CL04 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0006 TO PS2-62-IE-0002 | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00023-9941 | PS2-62-IE-0002-CL05 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0006 TO PS2-62-IE-0002 | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00023-9942 | PS2-62-IE-0002-CL06 | CPX09 - LV Power Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0006 TO PS2-62-IE-0002 | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00024-1188 | PS2-25-IES-3100A-CD01 | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-IES-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00024-1189 | PS2-25-IES-3100B-CD01 | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-IES-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00024-1190 | PS2-25-IES-3100C-CD01 | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-IES-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00024-1212 | PS2-61-IDH-3100A-CD03 | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00024-1214 | PS2-61-IDH-3100A-CD05 | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-25-DM-3100A TO PS2-61-IDH-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00024-1217 | PS2-61-IDH-3100B-CD03 | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00024-1219 | PS2-61-IDH-3100B-CD05 | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-25-DM-3100B TO PS2-61-IDH-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00024-1222 | PS2-61-IDH-3100C-CD03 | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00024-1224 | PS2-61-IDH-3100C-CD05 | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-25-DM-3100C TO PS2-61-IDH-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00024-1246 | PS2-62-IE-0002-CD01 | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-62-IE-0001 TO PS2-62-IE-0002 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00024-3019 | PS2-79-IG-0001-CD01 | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0001 TO PS2-79-IG-0001 | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00024-3020 | PS2-79-IG-0002-CD01 | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0002 TO PS2-79-IG-0002 | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00024-3021 | PS2-79-IG-0003-CD01 | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0003 TO PS2-79-IG-0003 | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #NAME?
T-00024-3022 | PS2-79-IG-0004-CD01 | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0004 TO PS2-79-IG-0004 | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #NAME?
T-00024-3023 | PS2-79-IG-0005-CD01 | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0005 TO PS2-79-IG-0005 | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #NAME?
T-00025-0004 | PS2-25-DM-3100A | CPX12 - HV Motor | PCOM - Precommissioning | E - Electrical | CRUDE OIL EXPORT PUMP A MOTOR | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Equipment installed |  | Construction not yet started |  | #NAME?
T-00025-0005 | PS2-25-DM-3100B | CPX12 - HV Motor | PCOM - Precommissioning | E - Electrical | CRUDE OIL EXPORT PUMP B MOTOR | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Equipment installed |  | Construction not yet started |  | #NAME?
T-00025-0006 | PS2-25-DM-3100C | CPX12 - HV Motor | PCOM - Precommissioning | E - Electrical | CRUDE OIL EXPORT PUMP C MOTOR | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Equipment installed |  | Construction not yet started |  | #NAME?
T-00026-0074 | PS2-28-DM-3100 | CPX13 - LV Motor | PCOM - Precommissioning | E - Electrical | Closed Drain Drum Pump | CPP AGI |  | PS2-28-03 - Closed Drain Drum & Pump |  | Equipment installed, Cable G&T, Earthing to be completed |  | Construction not yet started | ETA- 30TH JULY 2026 | #NAME?
T-00026-0075 | PS2-28-DM-3800A | CPX13 - LV Motor | PCOM - Precommissioning | E - Electrical | Seal Oil Drain Drum Pump Motor A | CPP AGI |  | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00026-0076 | PS2-28-DM-3800B | CPX13 - LV Motor | PCOM - Precommissioning | E - Electrical | Seal Oil Drain Drum Pump Motor B | CPP AGI |  | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00026-0077 | PS2-28-DM-3800C | CPX13 - LV Motor | PCOM - Precommissioning | E - Electrical | Seal Oil Drain Drum Pump Motor C | CPP AGI |  | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00026-0078 | PS2-28-DM-3900 | CPX13 - LV Motor | PCOM - Precommissioning | E - Electrical | Reinjection Pump Motor | CPP AGI |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | #NAME?
T-00026-0079 | PS2-53-DM-3100 | CPX13 - LV Motor | PCOM - Precommissioning | E - Electrical | Water Distribution Pump Motor | CPP AGI |  | PS2-53-02 - Water Distribution Pump |  | Equipment installed |  | Construction not yet started |  | #NAME?
T-00028-0262 | PS2-05-IG-0003 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | Emergency Lighting and Small power Distribution Panel | EITS |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00028-0264 | PS2-06-IG-0001A | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | AC UPS Distribution Board | EITS |  | PS2-06-01 - AC UPS - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00028-0265 | PS2-06-IG-0001B | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | AC UPS Distribution Board | EITS |  | PS2-06-01 - AC UPS - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00028-0266 | PS2-06-IG-0002 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | AC UPS Distribution Board | EITS |  | PS2-06-01 - AC UPS - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00028-0267 | PS2-61-IG-0003 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | Normal Lighting and Small power Distribution Panel | EITS |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00028-0268 | PS2-61-IG-0008 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | Normal Auxiliary Distribution Panel | EITS |  | PS2-61-08 - EITS 33kV Bld. Normal Auxiliary DP - PS2-61-IG-0008 | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00028-0405 | PS2-05-IG-0002 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | Feeder to Office & Facilities Building SWGR Emergency Section | CPP AGI |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started | Inside office building | #NAME?
T-00028-0406 | PS2-05-IG-0004 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | Outdoor Emergency Lighting Distribution Board PS-2 | CPP AGI |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  | Foundation for DB support to be done by civil, DB support to be fabricated and erected, |  | Construction not yet started |  | #NAME?
T-00028-0407 | PS2-05-IG-0006 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | Outdoor Emergency Lighting Distribution Board PS-2 | CPP AGI |  | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  | Foundation for DB support to be done by civil, DB support to be fabricated and erected, |  | Construction not yet started |  | #NAME?
T-00028-0408 | PS2-05-IG-0007 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | Guard House Emergency L&SP Distribution Board | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  | Foundation for DB support to be done by civil, DB support to be fabricated and erected, |  | Construction not yet started |  | #NAME?
T-00028-0409 | PS2-61-IG-0002 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | Normal feeder to Office and other EPC buildings | CPP AGI |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00028-0410 | PS2-61-IG-0005 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | Outdoor Normal Lighting Distribution Board PS-2 | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  | Foundation for DB support to be done by civil, DB support to be fabricated and erected, |  | Construction not yet started |  | #NAME?
T-00028-0411 | PS2-61-IG-0007 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | Outdoor Normal Lighting Distribution Board PS-2 | CPP AGI |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  | Foundation for DB support to be done by civil, DB support to be fabricated and erected, |  | Construction not yet started |  | #NAME?
T-00028-0412 | PS2-61-IG-0014 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | Outdoor Power Distribution Board PS-2 | CPP AGI |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  | Foundation for DB support to be done by civil, DB support to be fabricated and erected, |  | Construction not yet started | Not Available | #NAME?
T-00028-0413 | PS2-61-IG-0015 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | Outdoor Valves Distribution Board PS-2 | CPP AGI |  | PS2-61-07 - Outdoor Valves Distribution Board - PS2-61-IG-0015 |  | DB installation completed |  | Construction not yet started | ETA- 15th JULY 2026 | #NAME?
T-00028-0414 | PS2-79-IG-0001 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | EHT Distribution Board 1 | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00028-0415 | PS2-79-IG-0002 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | EHT Distribution Board 2 | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00028-0416 | PS2-79-IG-0003 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | EHT Distribution Board 3 | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #NAME?
T-00028-0417 | PS2-79-IG-0004 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | EHT Distribution Board 4 | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #NAME?
T-00028-0418 | PS2-79-IG-0005 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | EHT Distribution Board 5 | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #NAME?
T-00028-0582 | PS2-06-GU-0101 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | UPS DISTRIBUTION PANEL | CPP AGI |  | PS2-06-03 - AC DB - Office Building |  |  |  | Construction not yet started |  | #NAME?
T-00028-0583 | PS2-61-IG-0004 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | LIGHTING AND SMALL POWER DISTRIBUTION | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00028-0584 | PS2-05-IG-0101 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | EMERGENCY POWER DISTRIBUTION BOARD | CPP AGI |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | #NAME?
T-00028-0585 | PS2-06-IG-0004 | CPX15 - Distribution Board | PCOM - Precommissioning | E - Electrical | UPS POWER DISTRIBUTION BOARD | CPP AGI |  | PS2-06-04 - AC DB - Workshop & Warehouse |  |  |  | Construction not yet started |  | #NAME?
T-00029-0218 | PS2-06-GU-0001 | CPX16 - Charger/Inverter | PCOM - Precommissioning | E - Electrical | AC UPS 100kVA | EITS |  | PS2-06-01 - AC UPS - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00030-0361 |  | CPX17 - Battery | PCOM - Precommissioning | E - Electrical |  | EITS | UT-MID-60-SSF1-150308 | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #NAME?
T-00030-0362 |  | CPX17 - Battery | PCOM - Precommissioning | E - Electrical |  | EITS | UT-MID-60-SSF1-150308 | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | 0
T-00031-0666 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 | dwi, dwi | Closed | Closed | Closed |  | 0
T-00031-0667 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 | dwi, dwi | Closed | Closed | Closed |  | 0
T-00031-0668 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 | dwi, dwi | Closed | Closed | Closed |  | 0
T-00031-0669 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 | sari, indera | Closed | Closed | Closed |  | 0
T-00031-0670 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 | sari, indera | Closed | Closed | Closed |  | 0
T-00031-0671 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 | sari, indera | Closed | Closed | Closed |  | 0
T-00031-0672 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 | sari, indera | Closed | Closed | Closed |  | 0
T-00031-0673 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 | sari, indera | Closed | Closed | Closed |  | 0
T-00031-0867 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0868 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0869 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0870 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0871 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0872 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0873 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0874 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0875 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0876 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0877 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0878 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0879 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0880 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0881 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0882 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0883 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0884 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0885 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0886 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0887 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0888 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0889 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0890 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0891 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0892 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0893 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0894 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0895 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0896 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0897 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0898 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0899 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0900 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0901 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0902 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0903 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0904 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0905 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0906 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0907 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0908 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0909 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0910 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0911 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00031-0912 |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0161 | PS2-25-UD-3100A | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical | 5 pin 32A plug and socket for Oil Purifier Control Panel(Portable Load) | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00032-0175 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 | sari, indera | Closed | Closed | Closed |  | 0
T-00032-0176 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 | sari, indera | Closed | Closed | Closed |  | 0
T-00032-0282 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0283 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0284 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0285 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0286 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0287 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-06-03 - AC DB - Office Building |  |  |  | Construction not yet started |  | #NAME?
T-00032-0288 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-06-03 - AC DB - Office Building |  |  |  | Construction not yet started |  | #NAME?
T-00032-0289 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-06-04 - AC DB - Workshop & Warehouse |  |  |  | Construction not yet started |  | #NAME?
T-00032-0290 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0291 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0292 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0293 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0294 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0295 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0296 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0297 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0298 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0299 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0300 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0301 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0302 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0303 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0304 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0305 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0306 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0307 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0308 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0309 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0310 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0311 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | #NAME?
T-00032-0312 |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | #NAME?
T-00033-0015 | PS2-09-HE-2700 | CPX20 - Heater | PCOM - Precommissioning | E - Electrical | ELECTRICAL HEATER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00033-0041 | PS2-28-HE-2100 | CPX20 - Heater | PCOM - Precommissioning | E - Electrical | CLOSED DRAIN DRUM HEATER | CPP AGI | UG-MID-65-WPR2-135401 | PS2-28-03 - Closed Drain Drum & Pump |  | Vendor installed Package equipment |  | Construction not yet started | ETA- 30TH JULY 2026 | #NAME?
T-00033-0059 | PS2-25-HE-2100 | CPX20 - Heater | PCOM - Precommissioning | E - Electrical | Crude Oil Export Pump Motor A - Lube Oil System Oil Reservoir Heater | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  | Vendor Scope | Vendor Scope |  | #NAME?
T-00033-0060 | PS2-25-HE-2200 | CPX20 - Heater | PCOM - Precommissioning | E - Electrical | Crude Oil Export Pump Motor B - Lube Oil System Oil Reservoir Heater | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00033-0061 | PS2-25-HE-2300 | CPX20 - Heater | PCOM - Precommissioning | E - Electrical | Crude Oil Export Pump Motor C - Lube Oil System Oil Reservoir Heater | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00034-0026 | PS2-61-NER-0010 | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E - Electrical | LLHT Transformer NER | CPP AGI | UG-MID-65-SSF1-150257 | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started | Not Available | #NAME?
T-00034-0027 | PS2-61-NER-0011 | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E - Electrical | LLHT Transformer NER | CPP AGI | UG-MID-65-SSF1-150257 | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started | Not Available | #NAME?
T-00034-0028 | PS2-63-NER-0010 | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E - Electrical | Earthing Transformer NER | CPP AGI | UG-MID-65-SSF1-150257 | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  | Vendor Scope | Vendor Scope | Not Available | #NAME?
T-00035-0683 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0684 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0685 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0686 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0687 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0688 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0689 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0690 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0691 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0692 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0693 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0694 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0695 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0696 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0697 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0698 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0699 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0700 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0701 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0702 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0703 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0704 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0705 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0706 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0707 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0708 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0709 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0710 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0711 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0712 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0713 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0714 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0715 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0716 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0717 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0718 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0719 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0720 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0721 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0722 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0723 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0724 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0725 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0726 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0727 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0728 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0729 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0730 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0731 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0732 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0733 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0734 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0735 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0736 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0737 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0738 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0739 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0740 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #NAME?
T-00035-0741 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started
T-00035-0742 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started
T-00035-0743 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started
T-00035-0744 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started
T-00035-0745 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started
T-00035-0746 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started
T-00035-0747 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started
T-00035-0748 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0749 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0750 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0751 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0752 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0753 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0754 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0755 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0756 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0757 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0758 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0759 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0760 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0761 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0762 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0763 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0764 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0765 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0766 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0767 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0768 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0769 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0770 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0771 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0772 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0773 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0774 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0775 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00035-0776 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0777 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0778 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0779 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0780 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0781 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0782 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0783 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0784 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0785 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0786 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0787 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0788 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0789 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0790 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0791 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0792 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0793 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0794 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0795 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0796 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0797 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0798 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0799 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0800 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0801 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0802 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0803 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0804 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0805 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00035-0806 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00035-0807 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0808 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0809 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0810 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0811 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0812 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0813 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0814 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0815 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0816 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0817 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0818 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0819 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0820 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0821 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0822 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0823 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0824 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0825 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0826 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0827 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0828 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0829 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0830 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0831 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0832 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0833 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0834 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0835 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00035-0836 |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00039-0218 | PS2 - EITS BUILDING AREA_Earthing | CPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151138 | PS2-63-01 - Electrical Earthing |  | Installation complete | Closed | Closed | 2026-07-06 | RFI-23,39,47
T-00039-0219 | PS2 - EXPORT PUMP AREA_Earthing | CPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151137 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00039-0220 | PS2 - EXPORT PUMP VSD AREA_Earthing | CPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151135 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00039-0221 | PS2 - FENCE EAST AREA_Earthing | CPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151139 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00039-0222 | PS2 - FENCE SOUTH AREA_Earthing | CPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151140 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00039-0223 | PS2 - FENCE WEST AREA_Earthing | CPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151132 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00039-0224 | PS2 - MAIN ENTRANCE GATE & OFFICE BUILDING AREA_Earthing | CPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151131 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00039-0225 | PS2 - OPERATIONS AND MAINTENANCE AREA_Earthing | CPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151133 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00039-0226 | PS2 - PIGGING MECHANICAL HANDLING AREA_Earthing | CPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151134 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00039-0227 | PS2 - PUMP DISCHARGE CONTROL AREA_Earthing | CPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151136 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00039-0228 | PS2-82-OB-0001_Earthing | CPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing for Office building | CPP AGI | UG-MID-65-CPP1-150005 | PS2-63-02 - Electrical Earthing - Office Building |  |  |  | Construction not yet started |  | #N/A
T-00039-0229 | PS2-82-OB-0005_Earthing | CPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing for Guard House | CPP AGI | UG-MID-65-WPR2-151176 | PS2-63-05 - Electrical Earthing - Guard House |  |  |  | Construction not yet started | Guard house civil work ongoing | #N/A
T-00039-0230 | PS2-83-OB-0001_Earthing | CPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | EITS | UG-MID-65-SSF1-150004 | PS2-63-03 - Electrical Earthing - EITS Building | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00039-0231 | PS2-84-OB-0001_Earthing | CPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing for Workshop & Warehouse | CPP AGI | UG-MID-65-CPP1-150012 | PS2-63-04 - Electrical Earthing - Workshop and Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00039-0232 | PS2-84-OB-0003_Earthing | CPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing for Chemical Storage Shelter | CPP AGI | UG-MID-65-WPR2-151177 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00039-0233 | PS2-84-OB-0004_Earthing | CPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing for Waste Storage Shelter | CPP AGI | UG-MID-65-WPR2-151177 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00039-0234 | PS2-86-OB-0001_Earthing | CPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing for Closed Drain Drum Shelter | CPP AGI | UG-MID-65-WPR2-151175 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00040-0024 | PS2 - LAUNCHER AND RECEIVER AREA_Lightning | CPX28 - Lightning protection system | PCOM - Precommissioning | E - Electrical | Lightning | CPP AGI | UG-MID-65-WPR2-151185 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00040-0025 | PS2-82-OB-0001_Lightning | CPX28 - Lightning protection system | PCOM - Precommissioning | E - Electrical | Lightning for Office building | CPP AGI | UG-MID-65-CPP1-150006 | PS2-63-02 - Electrical Earthing - Office Building |  |  |  | Construction not yet started |  | #N/A
T-00040-0026 | PS2-82-OB-0005_Lightning | CPX28 - Lightning protection system | PCOM - Precommissioning | E - Electrical | Lightning for Guard House | CPP AGI | UG-MID-65-WPR2-151141 | PS2-63-05 - Electrical Earthing - Guard House |  |  |  | Construction not yet started | Guard house civil work ongoing | #N/A
T-00040-0027 | PS2-84-OB-0001_Lightning | CPX28 - Lightning protection system | PCOM - Precommissioning | E - Electrical | Lightning for Workshop & Warehouse | CPP AGI | UG-MID-65-CPP1-150013 | PS2-63-04 - Electrical Earthing - Workshop and Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00040-0028 | PS2-84-OB-0003_Lightning | CPX28 - Lightning protection system | PCOM - Precommissioning | E - Electrical | Lightning for Chemical Storage Shelter | CPP AGI | UG-MID-65-WPR2-151143 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00040-0029 | PS2-84-OB-0004_Lightning | CPX28 - Lightning protection system | PCOM - Precommissioning | E - Electrical | Lightning for Waste Storage Shelter | CPP AGI | UG-MID-65-WPR2-151142 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00040-0030 | PS2-86-OB-0001_Lightning | CPX28 - Lightning protection system | PCOM - Precommissioning | E - Electrical | Lightning for Closed Drain Drum Shelter | CPP AGI | UG-MID-65-WPR2-151144 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00041-0012 | PS2-83-OB-0001 | CPX29 - MCT cabling | PCOM - Precommissioning | E - Electrical | EITS Building | EITS |  | PS2-83-01 - EITS Building | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00041-0019 | PS2-82-OB-0001 | CPX29 - MCT cabling | PCOM - Precommissioning | E - Electrical | Office building | CPP AGI |  | PS2-82-01 - Office building |  |  |  | Construction not yet started |  | #N/A
T-00041-0020 | PS2-82-OB-0005 | CPX29 - MCT cabling | PCOM - Precommissioning | E - Electrical | Guard House | CPP AGI |  | PS2-82-02 - Guard House |  |  |  | Construction not yet started |  | #N/A
T-00042-0088 | PS2-83-OB-0001 | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E - Electrical | EITS Building | EITS |  | PS2-83-01 - EITS Building | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00042-0122 | PS2_AREA_COMPLETION_FOR_BUILDING_AREA_EAST | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E - Electrical | Area completion | CPP AGI |  | PS2-99-02 - Area Completion for Building Area East |  |  |  | Construction not yet started |  | #N/A
T-00042-0123 | PS2_AREA_COMPLETION_FOR_BUILDING_AREA_WEST | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E - Electrical | Area completion | CPP AGI |  | PS2-99-01 - Area Completion for Building Area West |  |  |  | Construction not yet started |  | #N/A
T-00042-0124 | PS2_AREA_COMPLETION_FOR_POWER_DISTRIBUTION_AREA | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E - Electrical | Area completion | CPP AGI |  | PS2-99-04 - Area Completion for Power Distribution Area |  | Tray work, CTS installation not completed |  | Construction not yet started |  | #N/A
T-00042-0125 | PS2_AREA_COMPLETION_FOR_PROCESS_AREA | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E - Electrical | Area completion | CPP AGI |  | PS2-99-05 - Area Completion for Process Area |  |  |  | Construction not yet started |  | #N/A
T-00042-0126 | PS2_AREA_COMPLETION_FOR_UTILITY_AREA | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E - Electrical | Area completion | CPP AGI |  | PS2-99-03 - Area Completion for Utility Area |  |  |  | Construction not yet started |  | #N/A
T-00042-0160 | PS2-82-OB-0001 | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E - Electrical | Office building | CPP AGI |  | PS2-82-01 - Office building |  |  |  | Construction not yet started |  | #N/A
T-00042-0161 | PS2-82-OB-0005 | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E - Electrical | Guard House | CPP AGI |  | PS2-82-02 - Guard House |  |  |  | Construction not yet started |  | #N/A
T-00042-0206 | PS2-83-OB-0001_Installation | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E - Electrical | EITS Building | CPP AGI |  | PS2-83-01 - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00043-0039 | PS2-79-BH-0001 | CPX31 - Junction and marshalling box | PCOM - Precommissioning | E - Electrical | LLHT High Voltage Power Junction Box | CPP AGI |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started | Not Available
T-00043-0040 | PS2-79-BH-0002 | CPX31 - Junction and marshalling box | PCOM - Precommissioning | E - Electrical | LLHT High Voltage Power Junction Box | CPP AGI |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started | Not Available
T-00044-0023 | PS2-61-IE-0001 | CPX32 - Console / control panel | PCOM - Precommissioning | E - Electrical | ECS 1 Panelboard | EITS |  | PS2-61-05 - Electrical Control System | ardila, ardila | Closed | Closed | Closed |  | CPP-RFI-65-33/1-07-0215
T-00044-0024 | PS2-61-IE-0002 | CPX32 - Console / control panel | PCOM - Precommissioning | E - Electrical | ECS 2 Panelboard | EITS |  | PS2-61-05 - Electrical Control System | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00044-0051 | PS2-05-IE-8100 | CPX32 - Console / control panel | PCOM - Precommissioning | E - Electrical | Unit Control Panel for Emergency Diesel Generator | EITS | UG-MID-65-SSF1-240000 | PS2-05-02 - Emergency Diesel Generator Package (UCP) | sari, indera | Closed | Closed | Closed |  | #N/A
T-00044-0121 | PS2-62-IE-0001 | CPX32 - Console / control panel | PCOM - Precommissioning | E - Electrical | Lighting Control panel 1 | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started
T-00044-0122 | PS2-62-IE-0002 | CPX32 - Console / control panel | PCOM - Precommissioning | E - Electrical | Lighting Control panel 2 | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started | After bridge , near tray turns towards Export pump | #N/A
T-00044-0277 | PS2-09-LB-7001 | CPX32 - Console / control panel | PCOM - Precommissioning | E - Electrical | HVAC UCP - Guard House | CPP AGI |  | PS2-09-02 - HVAC for Guard House |  |  |  | Construction not yet started |  | #N/A
T-00045-0002 | PS2-53-TR-4100 | CPX33 - Cathodic protection | PCOM - Precommissioning | E - Electrical | UTILITY WATER STORAGE TANK | CPP AGI | UG-MID-65-FZC2-180010 | PS2-53-01 - Utility Water Storage Tank |  |  | Not CPP EITScope | Vendor Scope | Not Available | #N/A
T-00046-0060 | PS2-06-JY-0001 | CZX01E - Package | PCOM - Precommissioning | E - Electrical | Battery lifter PS0415 | EITS |  | PS2-78-01 - Lifting and handling equipment | sari, indera | Closed | Closed | Closed |  | #N/A
T-00046-0061 | PS2-61-JY-0001 | CZX01E - Package | PCOM - Precommissioning | E - Electrical | Maintenance trolley for BlokSet | EITS |  | PS2-78-01 - Lifting and handling equipment |  |  |  | Construction not yet started |  | #N/A
T-00046-0166 | PS2-01-UB-6100 | CZX01E - Package | PCOM - Precommissioning | E - Electrical | Fire suppression skid | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | #N/A
T-00046-0280 | PS2-05-UR-8100 | CZX01E - Package | PCOM - Precommissioning | E - Electrical | EMERGENCY DIESEL ENGINE GENERATOR PACKAGE | CPP AGI | UG-MID-65-WPR2-135200 | PS2-05-01 - Emergency Diesel Generator Package |  |  | Vendor Scope | Vendor Scope |  | #N/A
T-00046-0281 | PS2-53-UT-8200 | CZX01E - Package | PCOM - Precommissioning | E - Electrical | WATER TREATMENT/ PURIFICATION PACKAGE | CPP AGI | UG-MID-65-WPR2-135502 | PS2-53-03 - Water Treatment Purification Package |  |  | Vendor Scope | Vendor Scope | Not Available | #N/A
T-00046-0282 | PS2-75-UI-6100 | CZX01E - Package | PCOM - Precommissioning | E - Electrical | BIOCIDE INJECTION PACKAGE | CPP AGI | UG-MID-65-WPR2-135300 | PS2-75-02 - Biocide Injection Package |  |  | Vendor Scope | Vendor Scope |  | #N/A
T-00046-0283 | PS2-75-UI-6200 | CZX01E - Package | PCOM - Precommissioning | E - Electrical | DRA PACKAGE | CPP AGI | UG-MID-65-WPR2-135300 | PS2-75-01 - DRA Injection Package |  |  | Vendor Scope | Vendor Scope | Not Available | #N/A
T-00046-0533 | PS2-83-EHO-0001A | CZX01E - Package | PCOM - Precommissioning | E - Electrical | VSD E-HOUSE | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Equipment installed | Vendor Scope | Vendor Scope
T-00046-0534 | PS2-83-EHO-0001B | CZX01E - Package | PCOM - Precommissioning | E - Electrical | VSD E-HOUSE | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Equipment installed | Vendor Scope | Vendor Scope
T-00046-0535 | PS2-83-EHO-0001C | CZX01E - Package | PCOM - Precommissioning | E - Electrical | VSD E-HOUSE | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Equipment installed | Vendor Scope | Vendor Scope
T-00050-0263 | PS2-09-RF-6600B | CKX02 - HVAC Fan | PCOM - Precommissioning | H - HVAC | EXTRACT FAN B | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00050-0280 | PS2-09-RF-6600A | CKX02 - HVAC Fan | PCOM - Precommissioning | H - HVAC | EXTRACT FAN A | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00052-0047 | PS2-09-ACU-0007_OUTDOOR_INSTALLATION | CNX01 - HVAC Ducting | PCOM - Precommissioning | H - HVAC | Outdoor installation scope | CPP AGI |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00053-0024 | PS2-09-AB-0004 | CNX02 - HVAC Manual damper | PCOM - Precommissioning | H - HVAC | AIR BALANCING DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00053-0041 | PS2-09-AP-0002 | CNX02 - HVAC Manual damper | PCOM - Precommissioning | H - HVAC | PRESSURE RELIEF DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00053-0122 | PS2-09-AS-0004B | CNX02 - HVAC Manual damper | PCOM - Precommissioning | H - HVAC | SHUT-OFF DAMPER (MANUAL) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00053-0127 | PS2-09-AB-0006 | CNX02 - HVAC Manual damper | PCOM - Precommissioning | H - HVAC | AIR BALANCING DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00053-0160 | PS2-09-AB-0005 | CNX02 - HVAC Manual damper | PCOM - Precommissioning | H - HVAC | AIR BALANCING DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00053-0165 | PS2-09-AP-0001 | CNX02 - HVAC Manual damper | PCOM - Precommissioning | H - HVAC | PRESSURE RELIEF DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00053-0185 | PS2-09-AJ-0001 | CNX02 - HVAC Manual damper | PCOM - Precommissioning | H - HVAC | NON RETURN DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00053-0186 | PS2-09-AP-0003 | CNX02 - HVAC Manual damper | PCOM - Precommissioning | H - HVAC | PRESSURE RELIEF DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00053-0188 | PS2-09-AS-0004A | CNX02 - HVAC Manual damper | PCOM - Precommissioning | H - HVAC | SHUT-OFF DAMPER (MANUAL) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00053-0251 | PS2-09-AB-0001 | CNX02 - HVAC Manual damper | PCOM - Precommissioning | H - HVAC | AIR BALANCING DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00053-0289 | PS2-09-AB-0007 | CNX02 - HVAC Manual damper | PCOM - Precommissioning | H - HVAC | AIR BALANCING DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00053-0291 | PS2-09-AB-0003 | CNX02 - HVAC Manual damper | PCOM - Precommissioning | H - HVAC | AIR BALANCING DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00053-0308 | PS2-09-AP-0004 | CNX02 - HVAC Manual damper | PCOM - Precommissioning | H - HVAC | PRESSURE RELIEF DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00053-0351 | PS2-09-AP-0005 | CNX02 - HVAC Manual damper | PCOM - Precommissioning | H - HVAC | PRESSURE RELIEF DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00053-0353 | PS2-09-AB-0008 | CNX02 - HVAC Manual damper | PCOM - Precommissioning | H - HVAC | AIR BALANCING DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00053-0378 | PS2-09-AB-0002 | CNX02 - HVAC Manual damper | PCOM - Precommissioning | H - HVAC | AIR BALANCING DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00054-0053 | PS2-09-AS-0003A | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | SHUT-OFF DAMPER (AUTOMATIC) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00054-0137 | PS2-09-AS-0003B | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | SHUT-OFF DAMPER (AUTOMATIC) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00054-0344 | PS2-09-FD-0107 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | FIRE DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00054-0351 | PS2-09-FD-0101 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | FIRE DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00054-0380 | PS2-09-FD-0106 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | FIRE DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00054-0382 | PS2-09-FD-0105 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | FIRE DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00054-0399 | PS2-09-FD-0104 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | FIRE DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00054-0402 | PS2-09-FD-0108 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | FIRE DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00054-0423 | PS2-09-FD-0102 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | FIRE DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00054-0445 | PS2-09-FD-0103 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | FIRE DAMPER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00054-0519 | PS2-09-FD-0001 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00054-0520 | PS2-09-FD-0002 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00054-0521 | PS2-09-FD-0003 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00054-0522 | PS2-09-FD-0004 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00054-0523 | PS2-09-FD-0005 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00054-0524 | PS2-09-FD-0006 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00054-0525 | PS2-09-FD-0007 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00054-0526 | PS2-09-FD-0008 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00054-0527 | PS2-09-FD-0009 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00054-0528 | PS2-09-FD-0010 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00054-0529 | PS2-09-FD-0011 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00054-0530 | PS2-09-FD-0012 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00054-0531 | PS2-09-FD-0013 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00054-0532 | PS2-09-FD-0014 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00054-0533 | PS2-09-FD-0015 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #N/A
T-00054-0534 | PS2-09-FD-0016 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #N/A
T-00054-0535 | PS2-09-FD-0017 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #N/A
T-00054-0536 | PS2-09-FD-0018 | CNX03 - HVAC Automatic damper | PCOM - Precommissioning | H - HVAC | Fire Damper | CPP AGI |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #N/A
T-00055-0009 | PS2-09-AN-0001 | CNX04 - HVAC Sound attenuator | PCOM - Precommissioning | H - HVAC | SOUND ATTENUATOR | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00057-0029 | PS2-09-ACU-0007A | CNX06 - HVAC Air handling unit | PCOM - Precommissioning | H - HVAC | AIR CONDITIONING UNIT A | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00057-0036 | PS2-09-ACU-0007B | CNX06 - HVAC Air handling unit | PCOM - Precommissioning | H - HVAC | AIR CONDITIONING UNIT B | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00061-0040 | PS2-09-LB-0001 | CNX10 - HVAC Fire damper control panel | PCOM - Precommissioning | H - HVAC | HVAC CONTROL PANEL | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00062-0400 | PS2-09-AR-0014 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | RECIRCULATION / EXHAUST AIR GRILLE | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0414 | PS2-09-AD-0005 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | AIR DIFFUSER (GRILLES) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0475 | PS2-09-AR-0013 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | RECIRCULATION / EXHAUST AIR GRILLE | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0478 | PS2-09-AD-0007 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | AIR DIFFUSER (GRILLES) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0489 | PS2-09-AR-0007 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | RECIRCULATION / EXHAUST AIR GRILLE | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0510 | PS2-09-AR-0003 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | RECIRCULATION / EXHAUST AIR GRILLE | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0520 | PS2-09-AD-0001 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | AIR DIFFUSER (GRILLES) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0523 | PS2-09-AR-0004 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | RECIRCULATION / EXHAUST AIR GRILLE | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0527 | PS2-09-AR-0011 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | RECIRCULATION / EXHAUST AIR GRILLE | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0561 | PS2-09-AD-0013 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | AIR DIFFUSER (GRILLES) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0567 | PS2-09-AD-0006 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | AIR DIFFUSER (GRILLES) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0570 | PS2-09-AD-0010 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | AIR DIFFUSER (GRILLES) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0575 | PS2-09-AD-0002 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | AIR DIFFUSER (GRILLES) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0652 | PS2-09-AD-0004 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | AIR DIFFUSER (GRILLES) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0653 | PS2-09-AR-0015 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | RECIRCULATION / EXHAUST AIR GRILLE | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0677 | PS2-09-AR-0008 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | RECIRCULATION / EXHAUST AIR GRILLE | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0678 | PS2-09-AD-0008 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | AIR DIFFUSER (GRILLES) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0704 | PS2-09-AR-0016 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | RECIRCULATION / EXHAUST AIR GRILLE | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0712 | PS2-09-AD-0009 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | AIR DIFFUSER (GRILLES) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0725 | PS2-09-AR-0012 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | RECIRCULATION / EXHAUST AIR GRILLE | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0739 | PS2-09-AD-0014 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | AIR DIFFUSER (GRILLES) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0774 | PS2-09-AR-0005 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | RECIRCULATION / EXHAUST AIR GRILLE | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0798 | PS2-09-AR-0006 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | RECIRCULATION / EXHAUST AIR GRILLE | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0824 | PS2-09-AR-0010 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | RECIRCULATION / EXHAUST AIR GRILLE | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0831 | PS2-09-AD-0012 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | AIR DIFFUSER (GRILLES) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0857 | PS2-09-AR-0001 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | RECIRCULATION / EXHAUST AIR GRILLE | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0860 | PS2-09-AR-0009 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | RECIRCULATION / EXHAUST AIR GRILLE | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0875 | PS2-09-AR-0002 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | RECIRCULATION / EXHAUST AIR GRILLE | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0883 | PS2-09-AD-0011 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | AIR DIFFUSER (GRILLES) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0893 | PS2-09-AD-0003 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | AIR DIFFUSER (GRILLES) | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00062-0908 | PS2-09-AR-0017 | CNX11 - HVAC Weather louver | PCOM - Precommissioning | H - HVAC | RECIRCULATION / EXHAUST AIR GRILLE | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00064-0175 | PS2-61-QE-0001 | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Tool Box | EITS | UG-MID-65-SSF1-240000 | PS2-02-01 - Miscellaneous Safety equipment | sari, indera | Closed | Closed | Closed |  | #N/A
T-00064-0214 | PS2-03-RAA-E110 | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Fire Audible Alarm | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00064-0215 | PS2-03-RAA-E111 | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Fire Audible Alarm | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00064-0216 | PS2-03-RAB-E106 | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Combined Beacon Sounder | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00064-0217 | PS2-03-RAB-E204 | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Combined Beacon Sounder | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00064-0218 | PS2-03-RAB-E305 | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Combined Beacon Sounder | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00064-0219 | PS2-03-RAL-E108 | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Fire Visual Alarm | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00064-0220 | PS2-03-RAL-E109 | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Fire Visual Alarm | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00064-0314 | PS2-03-NALP-E101 | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Warning sign | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00064-0315 | PS2-03-NALP-E101A | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Warning sign | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00064-0316 | PS2-03-NALP-E102 | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Warning sign | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00064-0317 | PS2-03-NALP-E201 | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Warning sign | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen | sari, indera | Closed | Closed | Closed |  | #N/A
T-00064-0318 | PS2-03-NALP-E202 | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Warning sign | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00064-0319 | PS2-03-NALP-E303 | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Warning sign | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00064-0320 | PS2-03-NALP-E303A | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Warning sign | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00064-0321 | PS2-03-NALP-E304 | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Warning sign | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00064-0425 | PS2-03-RAB-B103 | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Combined Beacon Sounder | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00064-0430 | PS2-03-RAB-W103 | CJX00 - Miscellaneous | PCOM - Precommissioning | I - Instrumentation | Combined Beacon Sounder | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00065-0025 | PS2-25-PSV-1103 | CJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Pressure Safety Relief Valve | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00065-0026 | PS2-25-PSV-1203 | CJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Pressure Safety Relief Valve | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00065-0027 | PS2-25-PSV-3901 | CJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Pressure Safety Relief Valve | CPP AGI | UG-MID-65-WPR2-134008 | PS2-28-04 - Reinjection Pump |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00065-0028 | PS2-28-PRV-0047A | CJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Self-Actuating / Regulating Press Valve | CPP AGI | UG-MID-65-WPR2-135403 | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00065-0029 | PS2-28-PRV-0047B | CJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Self-Actuating / Regulating Press Valve | CPP AGI | UG-MID-65-WPR2-135404 | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00065-0030 | PS2-28-PRV-0047C | CJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Self-Actuating / Regulating Press Valve | CPP AGI | UG-MID-65-WPR2-135405 | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00065-0031 | PS2-28-PRV-0048A | CJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Self-Actuating / Regulating Press Valve | CPP AGI | UG-MID-65-WPR2-135403 | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00065-0032 | PS2-28-PRV-0048B | CJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Self-Actuating / Regulating Press Valve | CPP AGI | UG-MID-65-WPR2-135404 | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00065-0033 | PS2-28-PRV-0048C | CJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Self-Actuating / Regulating Press Valve | CPP AGI | UG-MID-65-WPR2-135405 | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00065-0034 | PS2-28-PSV-0064A | CJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Pressure Safety Relief Valve | CPP AGI | UG-MID-65-WPR2-135403 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00065-0035 | PS2-28-PSV-0064B | CJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Pressure Safety Relief Valve | CPP AGI | UG-MID-65-WPR2-135404 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00065-0036 | PS2-28-PSV-0064C | CJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Pressure Safety Relief Valve | CPP AGI | UG-MID-65-WPR2-135405 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00066-0015 | PS2-25-FCV-0003A | CJX06 - Tubing Hydraulic | PCOM - Precommissioning | I - Instrumentation | Flow Control Valve | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  | Piping Scope | Construction work pending | Instrument installation - Piping (CPP2) Scope | #N/A
T-00066-0016 | PS2-25-FCV-0003B | CJX06 - Tubing Hydraulic | PCOM - Precommissioning | I - Instrumentation | Flow Control Valve | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  | Piping Scope | Construction work pending | Instrument installation - Piping (CPP2) Scope | #N/A
T-00066-0017 | PS2-25-FCV-0003C | CJX06 - Tubing Hydraulic | PCOM - Precommissioning | I - Instrumentation | Flow Control Valve | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  | Piping Scope | Construction work pending | Instrument installation - Piping (CPP2) Scope
T-00066-0018 | PS2-25-FCV-0004 | CJX06 - Tubing Hydraulic | PCOM - Precommissioning | I - Instrumentation | Flow Control Valve | CPP AGI |  | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  | Piping Scope | Construction work pending | Instrument installation - Piping (CPP2) Scope
T-00067-0009 | PS2-03-RMAC-0114 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | MANUAL CALL POINT | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00067-0010 | PS2-03-RMAC-0115 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | MANUAL CALL POINT | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00067-0011 | PS2-03-RMAC-0116 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | MANUAL CALL POINT | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00067-0012 | PS2-03-RMAC-0117 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | MANUAL CALL POINT | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00067-0013 | PS2-03-RMAC-0206 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | MANUAL CALL POINT | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | Foundation for stanchion to be done by Civil |  | Construction not yet started | ETA- 20TH JULY 2026
T-00067-0014 | PS2-03-RMAC-0207 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | MANUAL CALL POINT | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | Foundation for stanchion to be done by Civil |  | Construction not yet started | ETA- 20TH JULY 2026 | #N/A
T-00067-0443 | PS2-03-RMAC-0301 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | MANUAL CALL POINT | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-03 - FZ-03 - Buildings Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 5TH AUGUST 2026
T-00067-0830 | PS2-09-IES-0001 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | EMERGENCY PUSH BUTTON | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00067-0842 | PS2-09-TT-0003 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | TEMPERATURE TRANSMITTER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00067-0887 | PS2-09-PDT-0004 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | PRESSURE DIFFERENTIEL TRANSMITTER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00067-0929 | PS2-09-PDT-0001 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | PRESSURE DIFFERENTIEL TRANSMITTER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00067-0977 | PS2-09-PDT-0003 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | PRESSURE DIFFERENTIEL TRANSMITTER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00067-1065 | PS2-09-TT-0001 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | TEMPERATURE TRANSMITTER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00067-1123 | PS2-09-TT-0002 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | TEMPERATURE TRANSMITTER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00067-1131 | PS2-09-PDT-0002 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | PRESSURE DIFFERENTIEL TRANSMITTER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00067-1134 | PS2-09-PDT-0005 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | PRESSURE DIFFERENTIEL TRANSMITTER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00067-1162 | PS2-03-RMAC-E103 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Manual Call Point | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00067-1163 | PS2-03-RMAC-E104 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Manual Call Point | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00067-1164 | PS2-03-RMAC-E203 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Manual Call Point | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00067-1165 | PS2-03-RMAC-E303 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Manual Call Point | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00067-1166 | PS2-03-RMAC-E304 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Manual Call Point | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00067-1288 | PS2-01-PSH-6105 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Discharge Pressure Switch | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen | sari, indera | Closed | Closed | Closed |  | #N/A
T-00067-1289 | PS2-01-PSH-6106 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Discharge Pressure Switch | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen | sari, indera | Closed | Closed | Closed |  | #N/A
T-00067-1290 | PS2-01-PSH-6107 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Discharge Pressure Switch | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen | sari, indera | Closed | Closed | Closed |  | #N/A
T-00067-1294 | PS2-03-NMR-E104 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Manual Release | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00067-1295 | PS2-03-NMR-E204 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Manual Release | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00067-1296 | PS2-03-NMR-E302 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Manual Release | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00067-1297 | PS2-03-XS-E106A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Select switch Auto/Manu | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | #N/A
T-00067-1299 | PS2-03-XS-E201A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Select switch Auto/Manu | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | #N/A
T-00067-1301 | PS2-03-XS-E301A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Select switch Auto/Manu | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | #N/A
T-00067-1615 | PS2-03-HS-7002 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Hand Switch | CPP AGI |  | PS2-03-03 - FZ-03 - Buildings Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 5TH AUGUST 2026
T-00067-1616 | PS2-25-ZIT-0001 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Position transmitter | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  | STANCHION IN FABRICATION |  | Construction not yet started |  | #N/A
T-00067-1617 | PS2-25-ZIT-0002 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Position transmitter | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  | STANCHION IN FABRICATION |  | Construction not yet started |  | #N/A
T-00067-1618 | PS2-25-ZS-1201 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Position Switch | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  |  | Piping Scope | Construction work pending | Instrument installation - Piping (CPP2) Scope
T-00067-1619 | PS2-25-ZS-1101 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Position Switch | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  |  | Piping Scope | Construction work pending | Instrument installation - Piping (CPP2) Scope
T-00067-1620 | PS2-25-PDIT-0034A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Diff Press Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-02 - Crude Oil Export Pump A |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1621 | PS2-25-PDIT-0034B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Diff Press Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134004 | PS2-25-03 - Crude Oil Export Pump B |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1622 | PS2-25-PDIT-0034C | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Diff Press Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134005 | PS2-25-04 - Crude Oil Export Pump C |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1623 | PS2-25-PDIT-0050 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Diff Press Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134006 | PS2-25-06 - Crude Oil Export Pumps Discharge |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1624 | PS2-25-PIT-0001 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started |  | #N/A
T-00067-1625 | PS2-25-PIT-0004A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-02 - Crude Oil Export Pump A |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1626 | PS2-25-PIT-0004B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134004 | PS2-25-03 - Crude Oil Export Pump B |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1627 | PS2-25-PIT-0004C | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134005 | PS2-25-04 - Crude Oil Export Pump C |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1628 | PS2-25-PIT-0005A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-02 - Crude Oil Export Pump A |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1629 | PS2-25-PIT-0005B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134004 | PS2-25-03 - Crude Oil Export Pump B |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1630 | PS2-25-PIT-0005C | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134005 | PS2-25-04 - Crude Oil Export Pump C |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1631 | PS2-25-PIT-0007A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-02 - Crude Oil Export Pump A |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1632 | PS2-25-PIT-0007B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134004 | PS2-25-03 - Crude Oil Export Pump B |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1633 | PS2-25-PIT-0007C | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134005 | PS2-25-04 - Crude Oil Export Pump C |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1634 | PS2-25-PIT-0008A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1635 | PS2-25-PIT-0008B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1636 | PS2-25-PIT-0008C | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1637 | PS2-25-PIT-0013 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134006 | PS2-25-06 - Crude Oil Export Pumps Discharge |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started |  | #N/A
T-00067-1638 | PS2-25-PIT-0018 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-01 - Export Pipeline Pig Receiver |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started |  | #N/A
T-00067-1639 | PS2-25-PIT-0071A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1640 | PS2-25-PIT-0071B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1641 | PS2-25-PIT-0071C | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1642 | PS2-25-PIT-1102 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started |  | #N/A
T-00067-1643 | PS2-25-PIT-1202 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started |  | #N/A
T-00067-1644 | PS2-25-TIT-0001 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Temperature Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started |  | #N/A
T-00067-1645 | PS2-25-TIT-0002A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Temperature Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-02 - Crude Oil Export Pump A |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1646 | PS2-25-TIT-0002B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Temperature Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134004 | PS2-25-03 - Crude Oil Export Pump B |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1647 | PS2-25-TIT-0002C | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Temperature Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134005 | PS2-25-04 - Crude Oil Export Pump C |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1648 | PS2-25-TIT-0003A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Temperature Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-02 - Crude Oil Export Pump A |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1649 | PS2-25-TIT-0003B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Temperature Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134004 | PS2-25-03 - Crude Oil Export Pump B |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1650 | PS2-25-TIT-0003C | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Temperature Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134005 | PS2-25-04 - Crude Oil Export Pump C |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1651 | PS2-25-TIT-0004 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Temperature Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-06 - Crude Oil Export Pumps Discharge |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started |  | #N/A
T-00067-1652 | PS2-25-TIT-1101 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Temperature Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started |  | #N/A
T-00067-1653 | PS2-25-TIT-1201 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Temperature Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started |  | #N/A
T-00067-1654 | PS2-28-LIT-1101 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | GWR Level Ind Transmitter | CPP AGI | UG-MID-65-WPR2-135401 | PS2-28-03 - Closed Drain Drum & Pump |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started | ETA- 30TH JULY 2026 | #N/A
T-00067-1655 | PS2-28-LIT-1102 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | GWR Level Ind Transmitter | CPP AGI | UG-MID-65-WPR2-135401 | PS2-28-03 - Closed Drain Drum & Pump |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started | ETA- 30TH JULY 2026 | #N/A
T-00067-1656 | PS2-28-LIT-1301A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | GWR Level Ind Transmitter | CPP AGI | UG-MID-65-WPR2-135403 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1657 | PS2-28-LIT-1301B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | GWR Level Ind Transmitter | CPP AGI | UG-MID-65-WPR2-135404 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1658 | PS2-28-LIT-1301C | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | GWR Level Ind Transmitter | CPP AGI | UG-MID-65-WPR2-135405 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1659 | PS2-28-PIT-0015 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134008 | PS2-28-04 - Reinjection Pump |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started | ETA- 15th JULY 2026 | #N/A
T-00067-1660 | PS2-28-PIT-0041 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-135401 | PS2-28-03 - Closed Drain Drum & Pump |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started | ETA- 30TH JULY 2026 | #N/A
T-00067-1661 | PS2-28-PIT-0066 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-134000 | PS2-28-04 - Reinjection Pump |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started | ETA- 15th JULY 2026 | #N/A
T-00067-1662 | PS2-28-TIT-1101 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Temperature Ind Transmitter | CPP AGI | UG-MID-65-WPR2-135401 | PS2-28-03 - Closed Drain Drum & Pump |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started | ETA- 30TH JULY 2026 | #N/A
T-00067-1663 | PS2-28-TIT-1102 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Temperature Ind Transmitter | CPP AGI | UG-MID-65-WPR2-135401 | PS2-28-03 - Closed Drain Drum & Pump |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started | ETA- 30TH JULY 2026 | #N/A
T-00067-1664 | PS2-53-LIT-4101 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | DP Level Ind Transmitter | CPP AGI | UG-MID-65-WPR2-135501 | PS2-53-01 - Utility Water Storage Tank |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1665 | PS2-53-LIT-4102 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | DP Level Ind Transmitter | CPP AGI | UG-MID-65-WPR2-135501 | PS2-53-01 - Utility Water Storage Tank |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1666 | PS2-53-PIT-0005 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Pressure Transmitter | CPP AGI | UG-MID-65-WPR2-135501 | PS2-53-02 - Water Distribution Pump |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1787 | PS2-25-FIT-0001 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Ultrasonic Flow Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started | OSD - Follow up | #N/A
T-00067-1788 | PS2-25-FIT-0003A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Ultrasonic Flow Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-02 - Crude Oil Export Pump A |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1789 | PS2-25-FIT-0003B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Ultrasonic Flow Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134004 | PS2-25-03 - Crude Oil Export Pump B |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1790 | PS2-25-FIT-0003C | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Ultrasonic Flow Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134005 | PS2-25-04 - Crude Oil Export Pump C |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started
T-00067-1791 | PS2-25-FIT-0004 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | Ultrasonic Flow Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134006 | PS2-25-06 - Crude Oil Export Pumps Discharge |  | WAITING FOR PIPING REINSTATEMENT |  | Construction not yet started | OSD - Follow up
T-00067-2350 | PS2-25-IES-3200A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Crude Oil Export Pump Motor A - Lube OilPump 1 Motor | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | INSTRUMENT INSTALLED, G&T TO BE DONE |  | Construction not yet started
T-00067-2351 | PS2-25-IES-3200B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Crude Oil Export Pump Motor A - Lube OilPump 2 Motor | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | INSTRUMENT INSTALLED, G&T TO BE DONE |  | Construction not yet started
T-00067-2352 | PS2-25-IES-3300A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Crude Oil Export Pump Motor B - Lube OilPump 1 Motor | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | INSTRUMENT INSTALLED, G&T TO BE DONE |  | Construction not yet started
T-00067-2353 | PS2-25-IES-3300B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Crude Oil Export Pump Motor B - Lube OilPump 2 Motor | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | INSTRUMENT INSTALLED, G&T TO BE DONE |  | Construction not yet started
T-00067-2354 | PS2-25-IES-3400A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Crude Oil Export Pump C - Lube OilPump 1 Motor | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | INSTRUMENT INSTALLED, G&T TO BE DONE |  | Construction not yet started
T-00067-2355 | PS2-25-IES-3400B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Crude Oil Export Pump C - Lube OilPump 2 Motor | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | INSTRUMENT INSTALLED, G&T TO BE DONE |  | Construction not yet started
T-00067-2356 | PS2-25-IES-6400A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Crude Oil Export Pump Motor A - Lube Oil Heat Exchanger Fan Motor 1 | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | INSTRUMENT INSTALLED, G&T TO BE DONE |  | Construction not yet started
T-00067-2357 | PS2-25-IES-6400B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Crude Oil Export Pump Motor A - Lube Oil Heat Exchanger Fan Motor 2 | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | INSTRUMENT INSTALLED, G&T TO BE DONE |  | Construction not yet started
T-00067-2358 | PS2-25-IES-6500A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Crude Oil Export Pump Motor B - Lube Oil Heat Exchanger Fan Motor 1 | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | INSTRUMENT INSTALLED, G&T TO BE DONE |  | Construction not yet started
T-00067-2359 | PS2-25-IES-6500B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Crude Oil Export Pump Motor B- Lube Oil Heat Exchanger Fan Motor 2 | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | INSTRUMENT INSTALLED, G&T TO BE DONE |  | Construction not yet started
T-00067-2360 | PS2-25-IES-6600A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Crude Oil Export Pump C - Lube Oil Heat Exchanger Fan Motor 1 | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | INSTRUMENT INSTALLED, G&T TO BE DONE |  | Construction not yet started
T-00067-2361 | PS2-25-IES-6600B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Crude Oil Export Pump C - Lube Oil Heat Exchanger Fan Motor 2 | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | INSTRUMENT INSTALLED, G&T TO BE DONE |  | Construction not yet started
T-00067-2362 | PS2-28-IES-3100 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Closed Drain Drum Pump | CPP AGI |  | PS2-28-03 - Closed Drain Drum & Pump |  | Not Installed |  | Construction not yet started | ETA- 30TH JULY 2026
T-00067-2363 | PS2-28-IES-3800A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Seal Oil Drain Drum Pump Motor A | CPP AGI |  | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started
T-00067-2364 | PS2-28-IES-3800B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Seal Oil Drain Drum Pump Motor B | CPP AGI |  | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started
T-00067-2365 | PS2-28-IES-3800C | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Seal Oil Drain Drum Pump Motor C | CPP AGI |  | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started
T-00067-2366 | PS2-28-IES-3900 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Reinjection Pump Motor | CPP AGI |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026
T-00067-2367 | PS2-53-IES-3100 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | LCS for Water Distribution Pump Motor | CPP AGI |  | PS2-53-02 - Water Distribution Pump |  |  |  | Construction not yet started
T-00067-2597 | PS2-03-RMAC-B102 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | MANUAL CALL POINT | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00067-2636 | PS2-03-RMAC-W102 | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | MANUAL CALL POINT | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00067-2905 | PS2-23-SPZM-0007A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | CORROSION PROBE INTRUSIVE FLUSH TYPE - Corrosion coupon [CP] | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  |  | Piping Scope | Construction work pending | Instrument installation - Piping (CPP2) Scope | #N/A
T-00067-2906 | PS2-23-SPZM-0007B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | CORROSION PROBE INTRUSIVE FLUSH TYPE - Bio-coupon [BP] | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  |  | Piping Scope | Construction work pending | Instrument installation - Piping (CPP2) Scope | #N/A
T-00067-2907 | PS2-23-SPZM-0007C | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | CORROSION PROBE INTRUSIVE FLUSH TYPE - Electrical Resistance Probe [ ER] | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  |  | Piping Scope | Construction work pending | Instrument installation - Piping (CPP2) Scope | #N/A
T-00067-2908 | PS2-23-SPZM-0007D | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | ULTRASONIC THICKNESS SENSORS NON INTRUSIVE. ultrasonic wall thickness [UT] sensors | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00067-2909 | PS2-23-SPZM-0008A | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | CORROSION PROBE INTRUSIVE FLUSH TYPE - Corrosion coupon [CP] | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  |  | Piping Scope | Construction work pending | Instrument installation - Piping (CPP2) Scope | #N/A
T-00067-2910 | PS2-23-SPZM-0008B | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | CORROSION PROBE INTRUSIVE FLUSH TYPE - Bio-coupon [BP] | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  |  | Piping Scope | Construction work pending | Instrument installation - Piping (CPP2) Scope | #N/A
T-00067-2911 | PS2-23-SPZM-0008C | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | CORROSION PROBE INTRUSIVE FLUSH TYPE - Electrical Resistance Probe [ ER] | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  |  | Piping Scope | Construction work pending | Instrument installation - Piping (CPP2) Scope | #N/A
T-00067-2912 | PS2-23-SPZM-0008D | CJX08 - Electrical instrument | PCOM - Precommissioning | I - Instrumentation | ULTRASONIC THICKNESS SENSORS NON INTRUSIVE - ultrasonic wall thickness [UT] sensors | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00068-1635 | PS2-03-SFSC-0001-CZ01 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0001 TO PS2-03-SFMC-0001 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1636 | PS2-03-SFSC-0001-CZ02 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0001 TO PS2-03-SFMC-0002 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1637 | PS2-03-SFSC-0001-CZ03 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0001 TO PS2-03-SFMC-0002 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1638 | PS2-03-SFSC-0001-CZ04 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0001 TO PS2-03-SFMC-0002 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1639 | PS2-03-SFSC-0001-CZ05 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0001 TO PS2-03-SFMC-0001 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1640 | PS2-03-SFSC-0001-CZ06 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0001 TO PS2-03-SFMC-0001 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1641 | PS2-03-SFSC-0001-CZ07 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0001 TO PS2-03-SFMC-0002 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1642 | PS2-03-SFSC-0001-CZ08 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0001 TO PS2-03-SFMC-0003 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1643 | PS2-03-SFSC-0001-CZ09 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0001 TO PS2-03-SFMC-0004 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1644 | PS2-03-SFSC-0001-CZ10 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0001 TO PS2-03-SFMC-0004 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1645 | PS2-03-SFSC-0002-CZ01 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0001 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1646 | PS2-03-SFSC-0002-CZ02 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0003 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1647 | PS2-03-SFSC-0002-CZ03 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0003 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1648 | PS2-03-SFSC-0002-CZ04 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0004 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1649 | PS2-03-SFSC-0002-CZ05 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0004 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1650 | PS2-03-SFSC-0002-CZ06 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0004 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1651 | PS2-03-SFSC-0002-CZ07 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0004 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1652 | PS2-03-SFSC-0002-CZ08 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0005 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1653 | PS2-03-SFSC-0002-CZ09 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0006 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1654 | PS2-03-SFSC-0002-CZ10 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0006 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1655 | PS2-03-SFSC-0002-CZ11 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0005 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1656 | PS2-03-SFSC-0002-CZ12 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0005 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1657 | PS2-03-SFSC-0002-CZ13 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0005 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1658 | PS2-03-SFSC-0002-CZ14 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0006 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1659 | PS2-03-SFSC-0002-CZ15 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0007 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1660 | PS2-03-SFSC-0002-CZ16 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0007 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1661 | PS2-03-SFSC-0002-CZ17 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0007 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1662 | PS2-03-SFSC-0002-CZ18 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0002 TO PS2-03-SFMC-0007 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1663 | PS2-03-SFSC-0003-CZ01 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0003 TO PS2-03-SFMC-0005 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1664 | PS2-03-SFSC-0003-CZ02 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0003 TO PS2-03-SFMC-0006 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1665 | PS2-03-SFSC-0003-CZ03 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0003 TO PS2-03-SFMC-0007 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1666 | PS2-03-SFSC-0003-CZ04 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFSC-0003 TO PS2-03-SFMC-0007 | EITS |  | PS2-04-05 - EITS Building SIS/FGS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1667 | PS2-04-PSC-0001-CZ01 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0001 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1668 | PS2-04-PSC-0001-CZ02 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0001 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1669 | PS2-04-PSC-0001-CZ03 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0001 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1670 | PS2-04-PSC-0001-CZ04 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0002 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1671 | PS2-04-PSC-0001-CZ05 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0002 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1672 | PS2-04-PSC-0001-CZ06 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0001 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1673 | PS2-04-PSC-0001-CZ07 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0003 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1674 | PS2-04-PSC-0001-CZ08 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0004 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1675 | PS2-04-PSC-0001-CZ09 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0005 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1676 | PS2-04-PSC-0001-CZ10 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0003 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1677 | PS2-04-PSC-0001-CZ11 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0005 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1678 | PS2-04-PSC-0001-CZ12 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0001 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1679 | PS2-04-PSC-0001-CZ13 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0001 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1680 | PS2-04-PSC-0001-CZ14 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0001 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1681 | PS2-04-PSC-0001-CZ15 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0002 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1682 | PS2-04-PSC-0001-CZ16 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0002 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1683 | PS2-04-PSC-0001-CZ17 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0001 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1684 | PS2-04-PSC-0001-CZ18 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0003 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1685 | PS2-04-PSC-0001-CZ19 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0004 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1686 | PS2-04-PSC-0001-CZ20 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0003 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1687 | PS2-04-PSC-0001-CZ21 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0004 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1688 | PS2-04-PSC-0001-CZ22 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0001 TO PS2-04-PMC-0005 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1689 | PS2-04-PSC-0002-CZ01 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0002 TO PS2-04-PMC-0001 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1690 | PS2-04-PSC-0002-CZ02 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0002 TO PS2-04-PMC-0001 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1691 | PS2-04-PSC-0002-CZ03 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0002 TO PS2-04-PMC-0002 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1692 | PS2-04-PSC-0002-CZ04 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0002 TO PS2-04-PMC-0002 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1693 | PS2-04-PSC-0002-CZ05 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0002 TO PS2-04-PMC-0001 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1694 | PS2-04-PSC-0002-CZ06 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0002 TO PS2-04-PMC-0004 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1695 | PS2-04-PSC-0002-CZ07 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0002 TO PS2-04-PMC-0005 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1696 | PS2-04-PSC-0002-CZ08 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0002 TO PS2-04-PMC-0003 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1697 | PS2-04-PSC-0002-CZ09 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0002 TO PS2-04-PMC-0004 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00068-1698 | PS2-04-PSC-0002-CZ10 | CJX09 - Instrument power cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PSC-0002 TO PS2-04-PMC-0005 | EITS |  | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00069-10433 | PS2-03-RAB-B103-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SEA-0005 TO PS2-03-RAB-B103 | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #NAME?
T-00069-10434 | PS2-03-RDOS-B101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDOS-B101B TO PS2-03-RDOS-B101A | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #NAME?
T-00069-10435 | PS2-03-RDOS-B101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDOS-B101C TO PS2-03-RDOS-B101B | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #NAME?
T-00069-10436 | PS2-03-RDOS-B101C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDOS-B101D TO PS2-03-RDOS-B101C | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #NAME?
T-00069-10437 | PS2-03-RDOS-B101D-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDOS-B101E TO PS2-03-RDOS-B101D | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #NAME?
T-00069-10438 | PS2-03-RDOS-B101E-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDOS-B101F TO PS2-03-RDOS-B101E | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #NAME?
T-00069-10439 | PS2-03-RDOS-B101F-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RMAC-B102 TO PS2-03-RDOS-B101F | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #NAME?
T-00069-10440 | PS2-03-RDOS-B101G-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SEA-0005 TO PS2-03-RDOS-B101G | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #NAME?
T-00069-10441 | PS2-03-RMAC-B102-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDOS-B101G TO PS2-03-RMAC-B102 | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #NAME?
T-00069-10530 | PS2-03-RAB-W103-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SEA-0003 TO PS2-03-RAB-W103 | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10531 | PS2-03-RDHR-W101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101B TO PS2-03-RDHR-W101A | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10532 | PS2-03-RDHR-W101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101C TO PS2-03-RDHR-W101B | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10533 | PS2-03-RDHR-W101C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101D TO PS2-03-RDHR-W101C | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10534 | PS2-03-RDHR-W101D-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101E TO PS2-03-RDHR-W101D | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10535 | PS2-03-RDHR-W101E-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101F TO PS2-03-RDHR-W101E | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10536 | PS2-03-RDHR-W101F-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101L TO PS2-03-RDHR-W101F | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10537 | PS2-03-RDHR-W101G-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101R TO PS2-03-RDHR-W101G | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10538 | PS2-03-RDHR-W101H-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101G TO PS2-03-RDHR-W101H | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10539 | PS2-03-RDHR-W101I-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101H TO PS2-03-RDHR-W101I | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10540 | PS2-03-RDHR-W101J-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101I TO PS2-03-RDHR-W101J | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10541 | PS2-03-RDHR-W101K-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101J TO PS2-03-RDHR-W101K | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10542 | PS2-03-RDHR-W101L-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101K TO PS2-03-RDHR-W101L | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10543 | PS2-03-RDHR-W101M-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RMAC-W102 TO PS2-03-RDHR-W101M | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10544 | PS2-03-RDHR-W101N-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101M TO PS2-03-RDHR-W101N | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10545 | PS2-03-RDHR-W101O-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101N TO PS2-03-RDHR-W101O | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10546 | PS2-03-RDHR-W101P-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101O TO PS2-03-RDHR-W101P | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10547 | PS2-03-RDHR-W101Q-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101P TO PS2-03-RDHR-W101Q | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10548 | PS2-03-RDHR-W101R-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101Q TO PS2-03-RDHR-W101R | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-10549 | PS2-03-RMAC-W102-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SEA-0003 TO PS2-03-RMAC-W102 | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-12879 | PS2-01-LA-0001-CC52 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | From PS2-61-IJ-0001 To PS2-01-LA-0001 | EITS |  | PS2-0H-01 - HIPPS |  |  |  | Construction not yet started |  | #N/A
T-00069-12880 | PS2-01-LA-0001-CC53 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | From PS2-61-IJ-0001 To PS2-01-LA-0001 | EITS |  | PS2-0H-01 - HIPPS |  |  |  | Construction not yet started |  | #N/A
T-00069-12881 | PS2-01-LA-0001-CC54 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | From PS2-61-IJ-0001 To PS2-01-LA-0001 | EITS |  | PS2-0H-01 - HIPPS |  |  |  | Construction not yet started |  | #N/A
T-00069-12882 | PS2-01-LA-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | From PS2-03-SFMC-0002 To PS2-01-LA-0001 | EITS |  | PS2-0H-01 - HIPPS | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00069-12894 | PS2-25-BI-1802A-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-61-IDH-3100A TO PS2-25-BI-1802A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00069-2561 | PS2-03-GDLHP-0105-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2505 TO PS2-03-GDLHP-0105 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2562 | PS2-03-GDLHP-0106-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2505 TO PS2-03-GDLHP-0106 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2563 | PS2-03-RDH-0201-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2501 TO PS2-03-RDH-0201 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 20TH JULY 2026 | #NAME?
T-00069-2564 | PS2-03-RDH-0202-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2501 TO PS2-03-RDH-0202 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 20TH JULY 2026 | #NAME?
T-00069-2565 | PS2-03-RDH-0203-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2501 TO PS2-03-RDH-0203 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 20TH JULY 2026 | #NAME?
T-00069-2566 | PS2-03-RDH-0204-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2501 TO PS2-03-RDH-0204 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 20TH JULY 2026 | #NAME?
T-00069-2567 | PS2-03-RDH-0205-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2501 TO PS2-03-RDH-0205 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 20TH JULY 2026 | #NAME?
T-00069-2568 | PS2-03-RDH-0211-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2502 TO PS2-03-RDH-0211 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 20TH JULY 2026 | #NAME?
T-00069-2569 | PS2-03-RDH-0212-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2502 TO PS2-03-RDH-0212 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 20TH JULY 2026 | #NAME?
T-00069-2570 | PS2-03-RDH-0213-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2502 TO PS2-03-RDH-0213 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 20TH JULY 2026 | #NAME?
T-00069-2571 | PS2-03-RDIR-0101-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1503 TO PS2-03-RDIR-0101 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2572 | PS2-03-RDIR-0102-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1501 TO PS2-03-RDIR-0102 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2573 | PS2-03-RDIR-0103-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1501 TO PS2-03-RDIR-0103 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2574 | PS2-03-RDIR-0104-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1501 TO PS2-03-RDIR-0104 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2575 | PS2-03-RDIR-0105-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0105 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2576 | PS2-03-RDIR-0106-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0106 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2577 | PS2-03-RDIR-0107-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0107 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2578 | PS2-03-RDIR-0108-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0108 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2579 | PS2-03-RDIR-0109-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0109 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2580 | PS2-03-RDIR-0110-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0110 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2581 | PS2-03-RDIR-0111-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1503 TO PS2-03-RDIR-0111 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2582 | PS2-03-RDIR-0112-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1503 TO PS2-03-RDIR-0112 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2583 | PS2-03-RDIR-0113-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1503 TO PS2-03-RDIR-0113 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2584 | PS2-03-RDIR-0118-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0118 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2585 | PS2-03-RDIR-0119-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0119 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2586 | PS2-03-RDIR-0120-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0120 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2587 | PS2-03-RDIR-0121-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1503 TO PS2-03-RDIR-0121 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2588 | PS2-03-RMAC-0114-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2503 TO PS2-03-RMAC-0114 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2589 | PS2-03-RMAC-0115-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2503 TO PS2-03-RMAC-0115 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2590 | PS2-03-RMAC-0116-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2504 TO PS2-03-RMAC-0116 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2591 | PS2-03-RMAC-0117-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2504 TO PS2-03-RMAC-0117 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2592 | PS2-03-RMAC-0206-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2502 TO PS2-03-RMAC-0206 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 20TH JULY 2026 | #NAME?
T-00069-2593 | PS2-03-RMAC-0207-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2501 TO PS2-03-RMAC-0207 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started | ETA- 20TH JULY 2026 | #NAME?
T-00069-2596 | PS2-03-GDLHP-0107-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2505 TO PS2-03-GDLHP-0107 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2597 | PS2-03-GDLHP-0109-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2505 TO PS2-03-GDLHP-0109 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2598 | PS2-03-GDLHP-0111-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2505 TO PS2-03-GDLHP-0111 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2606 | PS2-03-RDH-0214-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2501 TO PS2-03-RDH-0214 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started | ETA- 20TH JULY 2026 | #NAME?
T-00069-2607 | PS2-03-RDH-0215-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2501 TO PS2-03-RDH-0215 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started | ETA- 20TH JULY 2026 | #NAME?
T-00069-2608 | PS2-03-RDIR-0124-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1501 TO PS2-03-RDIR-0124 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2609 | PS2-03-RDIR-0125-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1501 TO PS2-03-RDIR-0125 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00069-2610 | PS2-03-RDOS-G101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDOS-G101B TO PS2-03-RDOS-G101A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-05 - FZ-G1 - Guard House |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #NAME?
T-00069-2611 | PS2-03-RDOS-G101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SEA-0002 TO PS2-03-RDOS-G101B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-05 - FZ-G1 - Guard House |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #NAME?
T-00069-2660 | PS2-25-BI-1802B-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-61-IDH-3100B TO PS2-25-BI-1802B | CPP AGI | UT-MID-63-SLZ1-160005 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00069-2662 | PS2-25-BI-1802C-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-61-IDH-3100C TO PS2-25-BI-1802C | CPP AGI | UT-MID-63-SLZ1-160005 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00069-2690 | PS2-25-ESDV-0021-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1201 TO PS2-25-ESDV-0021 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2691 | PS2-25-ESDV-0021-CC02 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2201 TO PS2-25-ESDV-0021 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2692 | PS2-25-ESDV-0021-CC03 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2202 TO PS2-25-ESDV-0021 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2693 | PS2-25-ESDV-0023-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1201 TO PS2-25-ESDV-0023 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2694 | PS2-25-ESDV-0023-CC02 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2201 TO PS2-25-ESDV-0023 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2695 | PS2-25-ESDV-0023-CC03 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2202 TO PS2-25-ESDV-0023 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2696 | PS2-25-ESY-0021A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2203 TO PS2-25-ESDV-0021 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2697 | PS2-25-ESY-0021B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2305 TO PS2-25-ESDV-0021 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2698 | PS2-25-ESY-0023A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2203 TO PS2-25-ESDV-0023 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2699 | PS2-25-ESY-0023B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2305 TO PS2-25-ESDV-0023 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2700 | PS2-25-FCV-0003A-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-FCV-0003A TO PS2-25-FCV-0003A-HPU | CPP AGI | UT-MID-60-EPM2-160008 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00069-2701 | PS2-25-FCV-0003B-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-FCV-0003B TO PS2-25-FCV-0003B-HPU | CPP AGI | UT-MID-60-EPM2-160008 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2702 | PS2-25-FCV-0003C-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-FCV-0003C TO PS2-25-FCV-0003C-HPU | CPP AGI | UT-MID-60-EPM2-160008 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2703 | PS2-25-FCV-0004-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-FCV-0004 TO PS2-25-FCV-0004-HPU | CPP AGI | UT-MID-60-EPM2-160008 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #NAME?
T-00069-2704 | PS2-25-FIT-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-FIT-0001 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2705 | PS2-25-FIT-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1102 TO PS2-25-FIT-0003A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00069-2706 | PS2-25-FIT-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1106 TO PS2-25-FIT-0003B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2707 | PS2-25-FIT-0003C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1107 TO PS2-25-FIT-0003C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2708 | PS2-25-FIT-0004-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1108 TO PS2-25-FIT-0004 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #NAME?
T-00069-2709 | PS2-25-FXS-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2105 TO PS2-25-FCV-0003A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2710 | PS2-25-FXS-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2105 TO PS2-25-FCV-0003B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2711 | PS2-25-FXS-0003C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2105 TO PS2-25-FCV-0003C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2712 | PS2-25-FXS-0004-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2104 TO PS2-25-FCV-0004 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #NAME?
T-00069-2713 | PS2-25-FY-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1102 TO PS2-25-FCV-0003A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00069-2714 | PS2-25-FY-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1106 TO PS2-25-FCV-0003B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2715 | PS2-25-FY-0003C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1107 TO PS2-25-FCV-0003C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2716 | PS2-25-FY-0004-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1108 TO PS2-25-FCV-0004 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #NAME?
T-00069-2717 | PS2-25-HS-8101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2315 TO PS2-25-HS-8101A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00069-2718 | PS2-25-HS-8101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2315 TO PS2-25-HS-8101B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2719 | PS2-25-HS-8101C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2315 TO PS2-25-HS-8101C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2720 | PS2-25-HS-8102A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2315 TO PS2-25-HS-8102A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00069-2721 | PS2-25-HS-8102B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2315 TO PS2-25-HS-8102B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2722 | PS2-25-HS-8102C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2315 TO PS2-25-HS-8102C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2723 | PS2-25-MOV-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2101 TO PS2-25-MOV-0001 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2724 | PS2-25-MOV-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2101 TO PS2-25-MOV-0002 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2725 | PS2-25-MOV-0003-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2101 TO PS2-25-MOV-0003 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2726 | PS2-25-MOV-0008-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2103 TO PS2-25-MOV-0008 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2727 | PS2-25-MOV-0011-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2103 TO PS2-25-MOV-0011 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2728 | PS2-25-MOV-0012-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2103 TO PS2-25-MOV-0012 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2729 | PS2-25-MOV-0025-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2101 TO PS2-25-MOV-0025 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2730 | PS2-25-MOV-0026-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2102 TO PS2-25-MOV-0026 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2731 | PS2-25-MOV-0026-CC02 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-MOV-0026 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2732 | PS2-25-MOV-0027-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2102 TO PS2-25-MOV-0027 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #NAME?
T-00069-2733 | PS2-25-MOV-0027-CC02 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-MOV-0027 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #NAME?
T-00069-2734 | PS2-25-MOV-0028-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2103 TO PS2-25-MOV-0028 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2735 | PS2-25-MXS-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2101 TO PS2-25-MOV-0001 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2736 | PS2-25-MXS-0008-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2103 TO PS2-25-MOV-0008 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2737 | PS2-25-MXS-0025-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2101 TO PS2-25-MOV-0025 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2738 | PS2-25-MXS-0028-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2103 TO PS2-25-MOV-0028 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2742 | PS2-25-PDIT-0034A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1102 TO PS2-25-PDIT-0034A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00069-2743 | PS2-25-PDIT-0034B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1106 TO PS2-25-PDIT-0034B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2744 | PS2-25-PDIT-0034C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1107 TO PS2-25-PDIT-0034C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2745 | PS2-25-PDIT-0050-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-PDIT-0050 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2746 | PS2-25-PI-1102B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-PIT-1102 TO PS2-25-PI-1102B | CPP AGI | UT-MID-60-ACP2-160006 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2747 | PS2-25-PI-1202B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-PIT-1202 TO PS2-25-PI-1202B | CPP AGI | UT-MID-60-ACP2-160006 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2748 | PS2-25-PIT-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-PIT-0001 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2749 | PS2-25-PIT-0003AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1102 TO PS2-25-FCV-0003A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00069-2750 | PS2-25-PIT-0003BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1106 TO PS2-25-FCV-0003B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2751 | PS2-25-PIT-0003CA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1107 TO PS2-25-FCV-0003C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2752 | PS2-25-PIT-0004AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1108 TO PS2-25-FCV-0004 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #NAME?
T-00069-2753 | PS2-25-PIT-0004A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-25-PIT-0004A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00069-2754 | PS2-25-PIT-0004B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-25-PIT-0004B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2755 | PS2-25-PIT-0004C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-PIT-0004C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2756 | PS2-25-PIT-0005A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1102 TO PS2-25-PIT-0005A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00069-2757 | PS2-25-PIT-0005B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1106 TO PS2-25-PIT-0005B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2758 | PS2-25-PIT-0005C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1107 TO PS2-25-PIT-0005C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2759 | PS2-25-PIT-0007A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1102 TO PS2-25-PIT-0007A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00069-2760 | PS2-25-PIT-0007B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1106 TO PS2-25-PIT-0007B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2761 | PS2-25-PIT-0007C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1107 TO PS2-25-PIT-0007C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2762 | PS2-25-PIT-0008A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1301 TO PS2-25-PIT-0008A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2763 | PS2-25-PIT-0008B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1301 TO PS2-25-PIT-0008B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2764 | PS2-25-PIT-0008C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1301 TO PS2-25-PIT-0008C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2765 | PS2-25-PIT-0013-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1108 TO PS2-25-PIT-0013 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #NAME?
T-00069-2766 | PS2-25-PIT-0018-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-PIT-0018 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2767 | PS2-25-PIT-0035A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-25-SDV-0035A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00069-2768 | PS2-25-PIT-0035B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-25-SDV-0035B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2769 | PS2-25-PIT-0035C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-SDV-0035C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2770 | PS2-25-PIT-0036A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-25-SDV-0036A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00069-2771 | PS2-25-PIT-0036B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-SDV-0036B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2772 | PS2-25-PIT-0036C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-SDV-0036C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2773 | PS2-25-PIT-0046-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-SDV-0046 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2775 | PS2-25-PIT-0053-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1108 TO PS2-25-XV-0053 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #NAME?
T-00069-2776 | PS2-25-PIT-0054A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-25-SDV-0054A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00069-2777 | PS2-25-PIT-0054B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-SDV-0054B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2778 | PS2-25-PIT-0054C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-SDV-0054C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2779 | PS2-25-PIT-0070-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1108 TO PS2-25-XV-0070 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #NAME?
T-00069-2783 | PS2-25-PIT-1102-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-PIT-1102 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2784 | PS2-25-PIT-1202-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-PIT-1202 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2785 | PS2-25-SDV-0035A-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2302 TO PS2-25-SDV-0035A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started
T-00069-2786 | PS2-25-SDV-0035B-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2307 TO PS2-25-SDV-0035B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2787 | PS2-25-SDV-0035C-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2308 TO PS2-25-SDV-0035C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2788 | PS2-25-SDV-0036A-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2302 TO PS2-25-SDV-0036A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started
T-00069-2789 | PS2-25-SDV-0036B-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2307 TO PS2-25-SDV-0036B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2790 | PS2-25-SDV-0036C-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2308 TO PS2-25-SDV-0036C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2791 | PS2-25-SDV-0046-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2308 TO PS2-25-SDV-0046 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #NAME?
T-00069-2794 | PS2-25-SDV-0053C-CC02 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-SDV-0053C TO PS2-25-SDV-0053C-HPU | CPP AGI | UT-MID-60-NBV3-160008 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2795 | PS2-25-SDV-0054A-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2302 TO PS2-25-SDV-0054A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started
T-00069-2796 | PS2-25-SDV-0054B-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2307 TO PS2-25-SDV-0054B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2797 | PS2-25-SDV-0054C-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2308 TO PS2-25-SDV-0054C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2799 | PS2-25-SXS-0035A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2301 TO PS2-25-SDV-0035A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started
T-00069-2800 | PS2-25-SXS-0035B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2301 TO PS2-25-SDV-0035B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started
T-00069-2801 | PS2-25-SXS-0035C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2306 TO PS2-25-SDV-0035C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2802 | PS2-25-SXS-0036A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2301 TO PS2-25-SDV-0036A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started
T-00069-2803 | PS2-25-SXS-0036B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2306 TO PS2-25-SDV-0036B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2804 | PS2-25-SXS-0036C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2306 TO PS2-25-SDV-0036C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2805 | PS2-25-SXS-0046-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2306 TO PS2-25-SDV-0046 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #NAME?
T-00069-2807 | PS2-25-SXS-0054A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2301 TO PS2-25-SDV-0054A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started
T-00069-2808 | PS2-25-SXS-0054B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2306 TO PS2-25-SDV-0054B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2809 | PS2-25-SXS-0054C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2306 TO PS2-25-SDV-0054C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2810 | PS2-25-SY-0035AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2303 TO PS2-25-SDV-0035A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started
T-00069-2811 | PS2-25-SY-0035AB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2107 TO PS2-25-SDV-0035A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started
T-00069-2812 | PS2-25-SY-0035BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-25-SDV-0035B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2813 | PS2-25-SY-0035BB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2108 TO PS2-25-SDV-0035B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2814 | PS2-25-SY-0035CA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-25-SDV-0035C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2815 | PS2-25-SY-0035CB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2108 TO PS2-25-SDV-0035C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2816 | PS2-25-SY-0036AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2303 TO PS2-25-SDV-0036A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started
T-00069-2817 | PS2-25-SY-0036AB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2107 TO PS2-25-SDV-0036A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started
T-00069-2818 | PS2-25-SY-0036BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-25-SDV-0036B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2819 | PS2-25-SY-0036BB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2108 TO PS2-25-SDV-0036B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2820 | PS2-25-SY-0036CA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-25-SDV-0036C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2821 | PS2-25-SY-0036CB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2108 TO PS2-25-SDV-0036C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2822 | PS2-25-SY-0046A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-25-SDV-0046 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #NAME?
T-00069-2823 | PS2-25-SY-0046B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2109 TO PS2-25-SDV-0046 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #NAME?
T-00069-2825 | PS2-25-SY-0052B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2305 TO PS2-25-SDV-0052 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2826 | PS2-25-SY-0054AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2303 TO PS2-25-SDV-0054A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started
T-00069-2827 | PS2-25-SY-0054AB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2107 TO PS2-25-SDV-0054A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started
T-00069-2828 | PS2-25-SY-0054BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-25-SDV-0054B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2829 | PS2-25-SY-0054BB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2108 TO PS2-25-SDV-0054B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2830 | PS2-25-SY-0054CA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-25-SDV-0054C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2831 | PS2-25-SY-0054CB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2108 TO PS2-25-SDV-0054C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2832 | PS2-25-TI-1101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-TIT-1101 TO PS2-25-TI-1101B | CPP AGI | UT-MID-60-ACP2-160008 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2833 | PS2-25-TI-1201B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-TIT-1201 TO PS2-25-TI-1201B | CPP AGI | UT-MID-60-ACP2-160008 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2834 | PS2-25-TIT-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-TIT-0001 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2835 | PS2-25-TIT-0002A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-25-TIT-0002A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started
T-00069-2836 | PS2-25-TIT-0002B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-25-TIT-0002B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started
T-00069-2837 | PS2-25-TIT-0002C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-TIT-0002C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2838 | PS2-25-TIT-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1102 TO PS2-25-TIT-0003A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00069-2839 | PS2-25-TIT-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1106 TO PS2-25-TIT-0003B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2840 | PS2-25-TIT-0003C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1107 TO PS2-25-TIT-0003C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2841 | PS2-25-TIT-0004-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-TIT-0004 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #NAME?
T-00069-2842 | PS2-25-TIT-1101-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-TIT-1101 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2843 | PS2-25-TIT-1201-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-TIT-1201 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2844 | PS2-25-XV-0053-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2106 TO PS2-25-XV-0053 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #NAME?
T-00069-2845 | PS2-25-XV-0053-CC02 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-XV-0053 TO PS2-25-XV-0053-HPU | CPP AGI | UT-MID-60-NBV3-160008 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #NAME?
T-00069-2846 | PS2-25-XV-0070-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2106 TO PS2-25-XV-0070 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #NAME?
T-00069-2847 | PS2-25-XXS-0053-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2104 TO PS2-25-XV-0053 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #NAME?
T-00069-2848 | PS2-25-XXS-0070-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2104 TO PS2-25-XV-0070 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #NAME?
T-00069-2849 | PS2-25-XY-0053-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2109 TO PS2-25-XV-0053 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #NAME?
T-00069-2850 | PS2-25-XY-0070-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2109 TO PS2-25-XV-0070 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #NAME?
T-00069-2851 | PS2-25-ZIT-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-ZIT-0001 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #NAME?
T-00069-2852 | PS2-25-ZIT-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-ZIT-0002 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #NAME?
T-00069-2853 | PS2-25-ZS-1101-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2105 TO PS2-25-ZS-1101 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2854 | PS2-25-ZS-1201-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2105 TO PS2-25-ZS-1201 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2858 | PS2-28-HY-3901-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1103 TO PS2-28-HY-3901 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | #NAME?
T-00069-2861 | PS2-28-LI-1101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-LIT-1101 TO PS2-28-LI-1101B | CPP AGI | UT-MID-60-ACP2-160007 | PS2-28-03 - Closed Drain Drum & Pump |  | Secondary cable to be pulled after JBsupport installation and secondary cable tray installation |  | Construction not yet started | ETA- 30TH JULY 2026 | #NAME?
T-00069-2862 | PS2-28-LI-1101C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-LI-1101B TO PS2-28-LI-1101C | CPP AGI | UT-MID-60-ACP2-160007 | PS2-28-03 - Closed Drain Drum & Pump |  | Secondary cable to be pulled after JBsupport installation and secondary cable tray installation |  | Construction not yet started | ETA- 30TH JULY 2026 | #NAME?
T-00069-2863 | PS2-28-LIT-1101-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1103 TO PS2-28-LIT-1101 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-03 - Closed Drain Drum & Pump |  | Secondary cable to be pulled after JBsupport installation and secondary cable tray installation |  | Construction not yet started | ETA- 30TH JULY 2026 | #NAME?
T-00069-2864 | PS2-28-LIT-1102-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1303 TO PS2-28-LIT-1102 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-03 - Closed Drain Drum & Pump |  | Secondary cable to be pulled after JBsupport installation and secondary cable tray installation |  | Construction not yet started | ETA- 30TH JULY 2026 | #NAME?
T-00069-2865 | PS2-28-LIT-1301A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1102 TO PS2-28-LIT-1301A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00069-2866 | PS2-28-LIT-1301B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1106 TO PS2-28-LIT-1301B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2867 | PS2-28-LIT-1301C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1107 TO PS2-28-LIT-1301C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2868 | PS2-28-PIT-0015-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1103 TO PS2-28-PIT-0015 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | #NAME?
T-00069-2869 | PS2-28-PIT-0041-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1103 TO PS2-28-PIT-0041 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-03 - Closed Drain Drum & Pump |  | Secondary cable to be pulled after JBsupport installation and secondary cable tray installation |  | Construction not yet started | ETA- 30TH JULY 2026 | #NAME?
T-00069-2870 | PS2-28-PIT-0053A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-28-SDV-0053A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started
T-00069-2871 | PS2-28-PIT-0053B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-28-SDV-0053B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2872 | PS2-28-PIT-0053C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-28-SDV-0053C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #NAME?
T-00069-2873 | PS2-28-PIT-0065-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1303 TO PS2-28-SDV-0065 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | #NAME?
T-00069-2874 | PS2-28-PIT-0066-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1303 TO PS2-28-PIT-0066 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | #NAME?
T-00069-2875 | PS2-28-PIT-3901-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1303 TO PS2-28-PIT-3901 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | #NAME?
T-00069-2876 | PS2-28-SDV-0053A-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2302 TO PS2-28-SDV-0053A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00069-2877 | PS2-28-SDV-0053A-CC02 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-SDV-0053A TO PS2-28-SDV-0053A-HPU | CPP AGI | UT-MID-60-NBV3-160008 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | #NAME?
T-00069-2878 | PS2-28-SDV-0053B-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2307 TO PS2-28-SDV-0053B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2879 | PS2-28-SDV-0053B-CC02 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-SDV-0053B TO PS2-28-SDV-0053B-HPU | CPP AGI | UT-MID-60-NBV3-160008 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2880 | PS2-28-SDV-0053C-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2308 TO PS2-28-SDV-0053C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2881 | PS2-28-SDV-0065-CC01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2302 TO PS2-28-SDV-0065 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026
T-00069-2882 | PS2-28-SDV-0065-CC02 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-SDV-0065 TO PS2-28-SDV-0065-HPU | CPP AGI | UT-MID-60-NBV3-160008 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | #NAME?
T-00069-2883 | PS2-28-SXS-0053A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2301 TO PS2-28-SDV-0053A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started
T-00069-2884 | PS2-28-SXS-0053B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2306 TO PS2-28-SDV-0053B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2885 | PS2-28-SXS-0053C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2306 TO PS2-28-SDV-0053C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2886 | PS2-28-SXS-0065-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2301 TO PS2-28-SDV-0065 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026
T-00069-2887 | PS2-28-SY-0053AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2303 TO PS2-28-SDV-0053A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started
T-00069-2888 | PS2-28-SY-0053AB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2107 TO PS2-28-SDV-0053A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started
T-00069-2889 | PS2-28-SY-0053BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-28-SDV-0053B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2890 | PS2-28-SY-0053BB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2108 TO PS2-28-SDV-0053B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | #NAME?
T-00069-2891 | PS2-28-SY-0053CA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-28-SDV-0053C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2892 | PS2-28-SY-0053CB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2108 TO PS2-28-SDV-0053C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | #NAME?
T-00069-2893 | PS2-28-SY-0065A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2303 TO PS2-28-SDV-0065 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026
T-00069-2894 | PS2-28-SY-0065B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2107 TO PS2-28-SDV-0065 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026
T-00069-2895 | PS2-28-TIT-1101-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1103 TO PS2-28-TIT-1101 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-03 - Closed Drain Drum & Pump |  | Secondary cable to be pulled after JBsupport installation and secondary cable tray installation |  | Construction not yet started | ETA- 30TH JULY 2026 | #NAME?
T-00069-2896 | PS2-28-TIT-1102-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1303 TO PS2-28-TIT-1102 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-03 - Closed Drain Drum & Pump |  | Secondary cable to be pulled after JBsupport installation and secondary cable tray installation |  | Construction not yet started | ETA- 30TH JULY 2026 | #NAME?
T-00069-2897 | PS2-28-TIT-2101-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1303 TO PS2-28-TIT-2101 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-03 - Closed Drain Drum & Pump |  | Secondary cable to be pulled after JBsupport installation and secondary cable tray installation |  | Construction not yet started | ETA- 30TH JULY 2026 | #NAME?
T-00069-2900 | PS2-53-LIT-4101-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-53-BI-1105 TO PS2-53-LIT-4101 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-53-01 - Utility Water Storage Tank |  |  |  | Construction not yet started |  | #NAME?
T-00069-2902 | PS2-53-PIT-0005-CJ01 | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-53-BI-1105 TO PS2-53-PIT-0005 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-53-02 - Water Distribution Pump |  |  |  | Construction not yet started |  | #NAME?
T-00070-0020 | PS2-25-FO-0008 | CJX11 - Orifice plate | PCOM - Precommissioning | I - Instrumentation | Flow Restriction Orifice | CPP AGI | UG-MID-65-WPR2-134006 | PS2-25-05 - Crude Oil Export Pumps Bypass |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00070-0021 | PS2-28-FO-0001 | CJX11 - Orifice plate | PCOM - Precommissioning | I - Instrumentation | Flow Restriction Orifice | CPP AGI | UG-MID-65-WPR2-135401 | PS2-28-03 - Closed Drain Drum & Pump |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00070-0022 | PS2-28-FO-0003 | CJX11 - Orifice plate | PCOM - Precommissioning | I - Instrumentation | Flow Restriction Orifice | CPP AGI | UG-MID-65-WPR2-135400 | PS2-28-02 - Relief Header |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00070-0023 | PS2-28-FO-0009 | CJX11 - Orifice plate | PCOM - Precommissioning | I - Instrumentation | Flow Restriction Orifice | CPP AGI | UG-MID-65-WPR2-135403 | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00071-0083 | PS2-75-LA-6200-CX01 | CJX12 - Optical fiber cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PNC-0001 TO PS2-75-LA-6200 | CPP AGI |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | #NAME?
T-00072-0032 | PS2-25-TW-0001 | CJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00072-0033 | PS2-25-TW-0002A | CJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-02 - Crude Oil Export Pump A |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00072-0034 | PS2-25-TW-0002B | CJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-134004 | PS2-25-03 - Crude Oil Export Pump B |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00072-0035 | PS2-25-TW-0002C | CJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-134005 | PS2-25-04 - Crude Oil Export Pump C |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00072-0036 | PS2-25-TW-0003A | CJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-02 - Crude Oil Export Pump A |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00072-0037 | PS2-25-TW-0003B | CJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-134004 | PS2-25-03 - Crude Oil Export Pump B |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00072-0038 | PS2-25-TW-0003C | CJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-134005 | PS2-25-04 - Crude Oil Export Pump C |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00072-0039 | PS2-25-TW-0004 | CJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-06 - Crude Oil Export Pumps Discharge |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00072-0040 | PS2-28-TW-0001 | CJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-135400 | PS2-28-02 - Relief Header |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00072-0041 | PS2-28-TW-0002 | CJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-135403 | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00072-0042 | PS2-28-TW-1101 | CJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-135401 | PS2-28-03 - Closed Drain Drum & Pump |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00072-0043 | PS2-28-TW-1102 | CJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-135401 | PS2-28-03 - Closed Drain Drum & Pump |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00075-0053 | PS2-25-PG-0002 | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I - Instrumentation | Pressure Gauge | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00075-0054 | PS2-25-PG-0010 | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I - Instrumentation | Pressure Gauge | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #N/A
T-00075-0055 | PS2-25-PG-1101A | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I - Instrumentation | Pressure Gauge | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00075-0056 | PS2-25-PG-1101B | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I - Instrumentation | Pressure Gauge | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00075-0057 | PS2-25-PG-1201A | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I - Instrumentation | Pressure Gauge | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00075-0058 | PS2-25-PG-1201B | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I - Instrumentation | Pressure Gauge | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00075-0059 | PS2-28-PG-0014 | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I - Instrumentation | Pressure Gauge | CPP AGI | UG-MID-65-WPR2-134008 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | #N/A
T-00075-0060 | PS2-28-PG-0049A | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I - Instrumentation | Pressure Gauge | CPP AGI | UG-MID-65-WPR2-135403 | PS2-28-11 - Nitrogen for Seal Oil Drain |  |  |  | Construction not yet started |  | #N/A
T-00075-0061 | PS2-28-PG-0049B | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I - Instrumentation | Pressure Gauge | CPP AGI | UG-MID-65-WPR2-135404 | PS2-28-11 - Nitrogen for Seal Oil Drain |  |  |  | Construction not yet started |  | #N/A
T-00075-0062 | PS2-28-PG-0049C | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I - Instrumentation | Pressure Gauge | CPP AGI | UG-MID-65-WPR2-135405 | PS2-28-11 - Nitrogen for Seal Oil Drain |  |  |  | Construction not yet started |  | #N/A
T-00075-0063 | PS2-28-PG-1101 | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I - Instrumentation | Pressure Gauge | CPP AGI | UG-MID-65-WPR2-135401 | PS2-28-03 - Closed Drain Drum & Pump |  | Instrument installed , |  | Construction not yet started | ETA- 30TH JULY 2026 | #N/A
T-00075-0064 | PS2-28-TG-0001 | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I - Instrumentation | Temperature Gauge | CPP AGI | UG-MID-65-WPR2-135400 | PS2-28-02 - Relief Header |  | Not Installed |  | Construction not yet started | ETA- 15th JULY 2026 | #N/A
T-00075-0065 | PS2-28-TG-0002 | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I - Instrumentation | Temperature Gauge | CPP AGI | UG-MID-65-WPR2-135403 | PS2-28-11 - Nitrogen for Seal Oil Drain |  |  |  | Construction not yet started |  | #N/A
T-00075-0066 | PS2-53-PG-0022 | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I - Instrumentation | Pressure Gauge | CPP AGI | UG-MID-65-WPR2-135501 | PS2-53-02 - Water Distribution Pump |  |  |  | Construction not yet started |  | #N/A
T-00075-0067 | PS2-71-LG-1301 | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I - Instrumentation | Magnetic Level Gauge | CPP AGI | UG-MID-65-WPR2-135200 | PS2-05-01 - Emergency Diesel Generator Package |  | Installed by Piping | Closed | Closed | installation completed by CPP2 | #N/A
T-00077-0116 | PS2-25-SDV-0035A | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Shutdown Valve | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-02 - Crude Oil Export Pump A |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00077-0117 | PS2-25-SDV-0035B | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Shutdown Valve | CPP AGI | UG-MID-65-WPR2-134004 | PS2-25-03 - Crude Oil Export Pump B |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00077-0118 | PS2-25-SDV-0035C | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Shutdown Valve | CPP AGI | UG-MID-65-WPR2-134005 | PS2-25-04 - Crude Oil Export Pump C |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00077-0119 | PS2-25-SDV-0036A | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Shutdown Valve | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-02 - Crude Oil Export Pump A |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00077-0120 | PS2-25-SDV-0036B | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Shutdown Valve | CPP AGI | UG-MID-65-WPR2-134004 | PS2-25-03 - Crude Oil Export Pump B |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00077-0121 | PS2-25-SDV-0036C | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Shutdown Valve | CPP AGI | UG-MID-65-WPR2-134005 | PS2-25-04 - Crude Oil Export Pump C |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00077-0122 | PS2-25-SDV-0046 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Shutdown Valve | CPP AGI | UG-MID-65-WPR2-134006 | PS2-25-05 - Crude Oil Export Pumps Bypass |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00077-0123 | PS2-25-SDV-0052 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Shutdown Valve | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00077-0124 | PS2-25-SDV-0054A | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Shutdown Valve | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-02 - Crude Oil Export Pump A |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00077-0125 | PS2-25-SDV-0054B | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Shutdown Valve | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-03 - Crude Oil Export Pump B |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00077-0126 | PS2-25-SDV-0054C | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Shutdown Valve | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-04 - Crude Oil Export Pump C |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00077-0127 | PS2-25-XV-0053 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I - Instrumentation | On / Off Valve | CPP AGI | UG-MID-65-WPR2-134006 | PS2-25-05 - Crude Oil Export Pumps Bypass |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00077-0128 | PS2-25-XV-0070 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I - Instrumentation | On / Off Valve | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-05 - Crude Oil Export Pumps Bypass |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00077-0129 | PS2-28-SDV-0053A | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Shutdown Valve | CPP AGI | UG-MID-65-WPR2-135403 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00077-0130 | PS2-28-SDV-0053B | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Shutdown Valve | CPP AGI | UG-MID-65-WPR2-135404 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00077-0131 | PS2-28-SDV-0053C | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Shutdown Valve | CPP AGI | UG-MID-65-WPR2-135405 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00077-0132 | PS2-28-SDV-0065 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Shutdown Valve | CPP AGI | UG-MID-65-WPR2-134000 | PS2-28-04 - Reinjection Pump |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00078-0042 | PS2-25-MOV-0025 | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I - Instrumentation | Motor Operated Valve | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00078-0043 | PS2-25-MOV-0001 | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I - Instrumentation | Motor Operated Valve | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00078-0044 | PS2-25-MOV-0008 | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I - Instrumentation | Motor Operated Valve | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00078-0045 | PS2-25-MOV-0028 | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I - Instrumentation | Motor Operated Valve | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00078-0046 | PS2-25-MOV-0026 | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I - Instrumentation | Motor Operated Valve | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00078-0047 | PS2-25-MOV-0027 | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I - Instrumentation | Motor Operated Valve | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-06 - Crude Oil Export Pumps Discharge |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00078-0048 | PS2-25-MOV-0002 | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I - Instrumentation | Motor Operated Valve | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00078-0049 | PS2-25-MOV-0003 | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I - Instrumentation | Motor Operated Valve | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00078-0050 | PS2-25-MOV-0011 | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I - Instrumentation | Motor Operated Valve | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00078-0051 | PS2-25-MOV-0012 | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I - Instrumentation | Motor Operated Valve | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-07 - Export Pipeline Pig Launcher |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00078-0052 | PS2-75-MOV-0001 | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I - Instrumentation | Motor Operated Valve | CPP AGI | UG-MID-65-WPR2-135300 | PS2-28-08 - Open Drains (OD2) |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00079-0018 | PS2-25-FCV-0003A | CJX27 - Control valve - Pneumatic / Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Flow Control Valve | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-02 - Crude Oil Export Pump A |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00079-0019 | PS2-25-FCV-0003B | CJX27 - Control valve - Pneumatic / Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Flow Control Valve | CPP AGI | UG-MID-65-WPR2-134004 | PS2-25-03 - Crude Oil Export Pump B |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00079-0020 | PS2-25-FCV-0003C | CJX27 - Control valve - Pneumatic / Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Flow Control Valve | CPP AGI | UG-MID-65-WPR2-134005 | PS2-25-04 - Crude Oil Export Pump C |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00079-0021 | PS2-25-FCV-0004 | CJX27 - Control valve - Pneumatic / Hydraulic type | PCOM - Precommissioning | I - Instrumentation | Flow Control Valve | CPP AGI | UG-MID-65-WPR2-134006 | PS2-25-06 - Crude Oil Export Pumps Discharge |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00082-0014 | PS2-03-BI-1501 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-05-0194-01
T-00082-0015 | PS2-03-BI-1502 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0016 | PS2-03-BI-1503 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0017 | PS2-03-BI-2501 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | Foundation for JB support to be done by civil |  | Construction not yet started | ETA- 20TH JULY 2026 | #N/A
T-00082-0018 | PS2-03-BI-2502 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | Foundation for JB support to be done by civil |  | Construction not yet started | ETA- 20TH JULY 2026 | CPP-RFI-65-33/1-05-0090
T-00082-0019 | PS2-03-BI-2503 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0020 | PS2-03-BI-2504 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0172 | PS2-03-BI-1504 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0173 | PS2-03-BI-2505 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0174 | PS2-05-BI-0002 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-05-01 - Emergency Diesel Generator Package |  | Vendor installed JB | Closed | Closed | 2026-07-05 | CPP-RFI-65-16-11-0180
T-00082-0175 | PS2-09-BI-2501 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-09-03 - HVAC for Workshop & Warehouse |  | Foundation for JB support to be done by civil |  | Construction not yet started |  | CPP-RFI-65-16-04-0206
T-00082-0176 | PS2-09-BI-2502 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-09-01 - HVAC for Office building |  | Foundation for JB support to be done by civil |  | Construction not yet started |  | #N/A
T-00082-0177 | PS2-25-BI-1101 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  |  |  | Construction not yet started | ETA- 25th JULY 2026 | #N/A
T-00082-0178 | PS2-25-BI-1102 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0179 | PS2-25-BI-1106 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0180 | PS2-25-BI-1107 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0181 | PS2-25-BI-1108 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB installed, Earthing to be done |  | Construction not yet started | ETA- 25th JULY 2026 | CPP-RFI-65-33/1-05-0073
T-00082-0182 | PS2-25-BI-1174A | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A | Kumar, Vimlesh | Vendor installed JB | Closed | Closed | Export pump A
T-00082-0183 | PS2-25-BI-1174B | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B | Kumar, Vimlesh | Vendor installed JB | Closed | Closed | Export pump B
T-00082-0184 | PS2-25-BI-1174C | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C | Kumar, Vimlesh | Vendor installed JB | Closed | Closed | Export pump C
T-00082-0185 | PS2-25-BI-1201 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB installed, Earthing to be done |  | Construction not yet started | ETA- 25th JULY 2026 | CPP-RFI-65-33/1-05-0072
T-00082-0186 | PS2-25-BI-1274A | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A | Kumar, Vimlesh | Vendor installed JB | Closed | Closed | Export pump A
T-00082-0187 | PS2-25-BI-1274B | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B | Kumar, Vimlesh | Vendor installed JB | Closed | Closed | Export pump B
T-00082-0188 | PS2-25-BI-1274C | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C | Kumar, Vimlesh | Vendor installed JB | Closed | Closed | Export pump C
T-00082-0189 | PS2-25-BI-1301 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0190 | PS2-25-BI-1302 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0191 | PS2-25-BI-1305 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0192 | PS2-25-BI-1801A | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A | Kumar, Vimlesh | Vendor installed JB | Closed | Closed | Export pump A
T-00082-0193 | PS2-25-BI-1801B | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B | Kumar, Vimlesh | Vendor installed JB | Closed | Closed | Export pump B
T-00082-0194 | PS2-25-BI-1801C | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C | Kumar, Vimlesh | Vendor installed JB | Closed | Closed | Export pump C
T-00082-0195 | PS2-25-BI-1802A | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A | Kumar, Vimlesh | Vendor installed JB | Closed | Closed | Export pump A
T-00082-0196 | PS2-25-BI-1802B | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B | Kumar, Vimlesh | Vendor installed JB | Closed | Closed | Export pump B
T-00082-0197 | PS2-25-BI-1802C | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C | Kumar, Vimlesh | Vendor installed JB | Closed | Closed | Export pump C
T-00082-0198 | PS2-25-BI-1803A | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A | Kumar, Vimlesh | Vendor installed JB | Closed | Closed | Export pump A
T-00082-0199 | PS2-25-BI-1803B | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B | Kumar, Vimlesh | Vendor installed JB | Closed | Closed | Export pump B
T-00082-0200 | PS2-25-BI-1803C | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C | Kumar, Vimlesh | Vendor installed JB | Closed | Closed | Export pump C
T-00082-0201 | PS2-25-BI-2101 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  | Foundation for JB support to be done by civil |  | Construction not yet started | Mechanical handling area | CPP-RFI-65-33/1-05-0072
T-00082-0202 | PS2-25-BI-2102 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB installed, Earthing to be done |  | Construction not yet started | ETA- 25th JULY 2026 | CPP-RFI-65-33/1-05-0074
T-00082-0203 | PS2-25-BI-2103 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  | Foundation for JB support to be done by civil |  | Construction not yet started | Mechanical handling area | CPP-RFI-65-33/1-05-0072
T-00082-0204 | PS2-25-BI-2104 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB installed, Earthing to be done |  | Construction not yet started | ETA- 25th JULY 2026 | CPP-RFI-65-16-04-0096
T-00082-0205 | PS2-25-BI-2105 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0206 | PS2-25-BI-2106 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  | Foundation for JB support to be done by civil |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0073
T-00082-0207 | PS2-25-BI-2107 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0208 | PS2-25-BI-2108 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB installed, Earthing to be done |  | Construction not yet started | ETA- 25th JULY 2026 | CPP-RFI-65-33/1-05-0073
T-00082-0209 | PS2-25-BI-2109 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  | Foundation for JB support to be done by civil |  | Construction not yet started |  | CPP-RFI-65-16-04-0096
T-00082-0210 | PS2-25-BI-2201 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB installed, Earthing to be done |  | Construction not yet started | ETA- 25th JULY 2026 | CPP-RFI-65-16-04-0095
T-00082-0211 | PS2-25-BI-2202 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB installed, Earthing to be done |  | Construction not yet started | ETA- 25th JULY 2026 | CPP-RFI-65-33/1-05-0074
T-00082-0212 | PS2-25-BI-2203 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB installed, Earthing to be done |  | Construction not yet started | ETA- 25th JULY 2026 | CPP-RFI-65-16-04-0095
T-00082-0213 | PS2-25-BI-2301 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0214 | PS2-25-BI-2303 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0215 | PS2-25-BI-2304 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0216 | PS2-25-BI-2305 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB installed, Earthing to be done |  | Construction not yet started | ETA- 25th JULY 2026 | CPP-RFI-65-33/1-05-0074
T-00082-0217 | PS2-25-BI-2306 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0218 | PS2-25-BI-2307 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0219 | PS2-25-BI-2308 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0220 | PS2-25-BI-2315 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00082-0221 | PS2-28-BI-1103 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB installed, Earthing to be done |  | Construction not yet started | ETA- 25th JULY 2026 | CPP-RFI-65-33/1-05-0072
T-00082-0222 | PS2-28-BI-1303 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB installed, Earthing to be done |  | Construction not yet started | ETA- 25th JULY 2026 | CPP-RFI-65-33/1-05-0072
T-00082-0223 | PS2-53-BI-1105 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI | UG-MID-65-WPR2-161503 | PS2-91-01 - Multicore cables & JB |  | JB installed, Earthing to be done |  | Construction not yet started | ETA- 25th JULY 2026 | CPP-RFI-65-16-03-0101
T-00082-1310 | PS2-25-BI-2302 | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I - Instrumentation | Junction Box | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | JB INSTALLATION AND INSPECTION DONE | Closed | Closed | 2026-07-04 | CPP-RFI-65-16-05-0194-01
T-00083-0007 | PS2-03-GDLHP-0105 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | TRACE TAPE TYPE LIQUID HYDROCARBON LEAK DETECTOR | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00083-0008 | PS2-03-GDLHP-0106 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | TRACE TAPE TYPE LIQUID HYDROCARBON LEAK DETECTOR | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00083-0009 | PS2-03-RDH-0201 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) (Hc) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 20TH JULY 2026
T-00083-0010 | PS2-03-RDH-0202 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) (Hc) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 20TH JULY 2026
T-00083-0011 | PS2-03-RDH-0203 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) (Hc) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 20TH JULY 2026
T-00083-0012 | PS2-03-RDH-0204 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) (Hc) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 20TH JULY 2026
T-00083-0013 | PS2-03-RDH-0205 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) (Hc) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 20TH JULY 2026
T-00083-0014 | PS2-03-RDH-0211 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) (Hc) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 20TH JULY 2026
T-00083-0015 | PS2-03-RDH-0212 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) (Hc) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 20TH JULY 2026
T-00083-0016 | PS2-03-RDH-0213 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) (Hc) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 20TH JULY 2026
T-00083-0288 | PS2-03-GDLHP-0107 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | POINT TYPE LIQUID HYDROCARBON DETECTOR | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00083-0289 | PS2-03-GDLHP-0109 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | POINT TYPE LIQUID HYDROCARBON DETECTOR | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00083-0290 | PS2-03-GDLHP-0111 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | POINT TYPE LIQUID HYDROCARBON DETECTOR | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00083-0291 | PS2-03-RDOS-G101A | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | SMOKE DETECTOR | CPP AGI | UG-MID-65-WPR2-121113 | PS2-03-05 - FZ-G1 - Guard House |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00083-0292 | PS2-03-RDOS-G101B | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | SMOKE DETECTOR | CPP AGI | UG-MID-65-WPR2-121113 | PS2-03-05 - FZ-G1 - Guard House |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00083-0924 | PS2-03-RDH-0214 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 20TH JULY 2026 | #N/A
T-00083-0925 | PS2-03-RDH-0215 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 20TH JULY 2026
T-00083-0965 | PS2-03-GDH-E201 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Hydrogen gas detector | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00083-0966 | PS2-03-GDH-E202 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Hydrogen gas detector | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00083-0967 | PS2-03-RDOS-E101 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Smoke Detector - Optical | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00083-0968 | PS2-03-RDOS-E102 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Smoke Detector - Optical | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00083-0969 | PS2-03-RDOS-E107 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Smoke Detector - Optical | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00083-0970 | PS2-03-RDOS-E201 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Smoke Detector - Optical | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00083-0971 | PS2-03-RDOS-E202 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Smoke Detector - Optical | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00083-0972 | PS2-03-RDOS-E301 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Smoke Detector - Optical | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00083-0973 | PS2-03-RDOS-E302 | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Smoke Detector - Optical | EITS | UG-MID-65-SSF1-160031 | PS2-03-06 - FZ-E1 to E3 - EITS Building | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00083-1419 | PS2-03-RDOS-B101A | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Smoke Detector - Optical | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00083-1420 | PS2-03-RDOS-B101B | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Smoke Detector - Optical | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00083-1421 | PS2-03-RDOS-B101C | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Smoke Detector - Optical | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00083-1422 | PS2-03-RDOS-B101D | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Smoke Detector - Optical | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00083-1423 | PS2-03-RDOS-B101E | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Smoke Detector - Optical | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00083-1424 | PS2-03-RDOS-B101F | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Smoke Detector - Optical | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00083-1425 | PS2-03-RDOS-B101G | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Smoke Detector - Optical | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00083-1506 | PS2-03-RDHR-W101A | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00083-1507 | PS2-03-RDHR-W101B | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00083-1508 | PS2-03-RDHR-W101C | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00083-1509 | PS2-03-RDHR-W101D | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00083-1510 | PS2-03-RDHR-W101E | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00083-1511 | PS2-03-RDHR-W101F | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00083-1512 | PS2-03-RDHR-W101G | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00083-1513 | PS2-03-RDHR-W101H | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00083-1514 | PS2-03-RDHR-W101I | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00083-1515 | PS2-03-RDHR-W101J | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00083-1516 | PS2-03-RDHR-W101K | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00083-1517 | PS2-03-RDHR-W101L | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00083-1518 | PS2-03-RDHR-W101M | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00083-1519 | PS2-03-RDHR-W101N | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00083-1520 | PS2-03-RDHR-W101O | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00083-1521 | PS2-03-RDHR-W101P | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00083-1522 | PS2-03-RDHR-W101Q | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00083-1523 | PS2-03-RDHR-W101R | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I - Instrumentation | Heat Detector | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00084-0012 | PS2-03-RDIR-0101 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00084-0013 | PS2-03-RDIR-0102 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00084-0014 | PS2-03-RDIR-0103 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026 | CPP-RFI-65-16-12-0214
T-00084-0015 | PS2-03-RDIR-0104 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026 | CPP-RFI-65-16-12-0214
T-00084-0016 | PS2-03-RDIR-0105 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00084-0017 | PS2-03-RDIR-0106 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00084-0018 | PS2-03-RDIR-0107 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00084-0019 | PS2-03-RDIR-0108 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00084-0020 | PS2-03-RDIR-0109 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00084-0021 | PS2-03-RDIR-0110 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00084-0022 | PS2-03-RDIR-0111 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00084-0023 | PS2-03-RDIR-0112 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00084-0024 | PS2-03-RDIR-0113 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00084-0025 | PS2-03-RDIR-0118 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00084-0026 | PS2-03-RDIR-0119 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00084-0027 | PS2-03-RDIR-0120 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00084-0028 | PS2-03-RDIR-0121 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00084-0353 | PS2-03-RDIR-0124 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00084-0354 | PS2-03-RDIR-0125 | CJX43 - Fire detector | PCOM - Precommissioning | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | CPP AGI | UG-MID-65-WPR2-121110 | PS2-03-01 - FZ-01 - Process Area |  | STANCHION IN FABRICATION |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00087-0106 | PS2-03-SEA-0002 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | FIRE ALARM CONTROL PANEL | CPP AGI | UG-MID-65-WPR2-121113 | PS2-03-05 - FZ-G1 - Guard House |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 5TH AUGUST 2026
T-00087-0172 | PS2-01-LA-0001 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | HIPPS (OPPS) CABINET | EITS | UG-MID-65-SSF1-240000 | PS2-0H-01 - HIPPS | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00087-0248 | PS2-03-MTX-0001 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | SIS/FGS Matrix Panel | CPP AGI |  | PS2-04-02 - Office Building SIS/FGS System |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 15th August 2026
T-00087-0249 | PS2-03-SFMC-0001 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | SIS/FGS Marshalling Cabinet 1 | EITS | UG-MID-65-SSF1-240000 | PS2-04-05 - EITS Building SIS/FGS System | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00087-0250 | PS2-03-SFMC-0002 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | SIS/FGS Marshalling Cabinet 2 | EITS | UG-MID-65-SSF1-240000 | PS2-04-05 - EITS Building SIS/FGS System | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00087-0251 | PS2-03-SFMC-0003 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | SIS/FGS Marshalling Cabinet 3 | EITS | UG-MID-65-SSF1-240000 | PS2-04-05 - EITS Building SIS/FGS System | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00087-0252 | PS2-03-SFMC-0004 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | SIS/FGS Marshalling Cabinet 4 | EITS | UG-MID-65-SSF1-240000 | PS2-04-05 - EITS Building SIS/FGS System | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00087-0253 | PS2-03-SFMC-0005 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | SIS/FGS Marshalling Cabinet 5 | EITS | UG-MID-65-SSF1-240000 | PS2-04-05 - EITS Building SIS/FGS System | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00087-0254 | PS2-03-SFMC-0006 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | SIS/FGS Marshalling Cabinet 6 | EITS | UG-MID-65-SSF1-240000 | PS2-04-05 - EITS Building SIS/FGS System | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00087-0255 | PS2-03-SFMC-0007 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | SIS/FGS Marshalling Cabinet 7 | EITS | UG-MID-65-SSF1-240000 | PS2-04-05 - EITS Building SIS/FGS System | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00087-0256 | PS2-03-SFSC-0001 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | SIS/FGS System Cabinet 1 | EITS | UG-MID-65-SSF1-240000 | PS2-04-05 - EITS Building SIS/FGS System | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00087-0257 | PS2-03-SFSC-0002 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | SIS/FGS System Cabinet 2 | EITS | UG-MID-65-SSF1-240000 | PS2-04-05 - EITS Building SIS/FGS System | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00087-0258 | PS2-03-SFSC-0003 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | SIS/FGS System Cabinet 3 | EITS | UG-MID-65-SSF1-240000 | PS2-04-05 - EITS Building SIS/FGS System | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00087-0259 | PS2-04-PMC-0001 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | PCS Marshalling Cabinet 1 | EITS | UG-MID-65-SSF1-240000 | PS2-04-04 - EITS Building PCS System | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00087-0260 | PS2-04-PMC-0002 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | PCS Marshalling Cabinet 2 | EITS | UG-MID-65-SSF1-240000 | PS2-04-04 - EITS Building PCS System | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00087-0261 | PS2-04-PMC-0003 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | PCS Marshalling Cabinet 3 | EITS | UG-MID-65-SSF1-240000 | PS2-04-04 - EITS Building PCS System | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00087-0262 | PS2-04-PMC-0004 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | PCS Marshalling Cabinet 4 | EITS | UG-MID-65-SSF1-240000 | PS2-04-04 - EITS Building PCS System | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00087-0263 | PS2-04-PMC-0005 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | PCS Marshalling Cabinet 5 | EITS | UG-MID-65-SSF1-240000 | PS2-04-04 - EITS Building PCS System | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00087-0264 | PS2-04-PNC-0001 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | ICSS Network Cabinet 1 | EITS | UG-MID-65-SSF1-240000 | PS2-04-03 - EITS Building ICSS System |  |  |  | Construction not yet started |  | #N/A
T-00087-0265 | PS2-04-PSC-0001 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | PCS System Cabinet 1 | EITS | UG-MID-65-SSF1-240000 | PS2-04-04 - EITS Building PCS System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00087-0266 | PS2-04-PSC-0002 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | PCS System Cabinet 2 | EITS | UG-MID-65-SSF1-240000 | PS2-04-04 - EITS Building PCS System | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00087-0463 | PS2-25-IE-0001 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | VTMS Cabinet for Export Pump cabinet | EITS | UG-MID-65-SSF1-240000 | PS2-25-02 - Crude Oil Export Pump A | ardila, ardila | Closed | Closed | Closed |  | #N/A
T-00087-0505 | PS2-03-SEA-0005 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | FIRE ALARM CONTROL PANEL | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00087-0509 | PS2-03-SEA-0003 | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I - Instrumentation | FIRE ALARM CONTROL PANEL | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 10TH AUGUST 2026
T-00090-0049 | PS2-01-UB-6100 | CZX01I - Package | PCOM - Precommissioning | I - Instrumentation | Fire suppression skid | EITS | UG-MID-65-SSF1-160003 | PS2-01-01 - Inergen | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00090-0168 | PS2-05-UR-8100 | CZX01I - Package | PCOM - Precommissioning | I - Instrumentation | EMERGENCY DIESEL ENGINE GENERATOR PACKAGE | CPP AGI | UG-MID-65-WPR2-135200 | PS2-05-01 - Emergency Diesel Generator Package |  |  | Vendor Scope | Vendor Scope |  | #N/A
T-00090-0169 | PS2-53-UT-8200 | CZX01I - Package | PCOM - Precommissioning | I - Instrumentation | WATER TREATMENT/ PURIFICATION PACKAGE | CPP AGI | UG-MID-65-WPR2-135502 | PS2-53-03 - Water Treatment Purification Package |  |  | Vendor Scope | Vendor Scope |  | #N/A
T-00090-0170 | PS2-75-UI-6100 | CZX01I - Package | PCOM - Precommissioning | I - Instrumentation | BIOCIDE INJECTION PACKAGE | CPP AGI | UG-MID-65-WPR2-135300 | PS2-75-02 - Biocide Injection Package |  |  | Vendor Scope | Vendor Scope |  | #N/A
T-00090-0171 | PS2-75-UI-6200 | CZX01I - Package | PCOM - Precommissioning | I - Instrumentation | DRA PACKAGE | CPP AGI | UG-MID-65-WPR2-135300 | PS2-75-01 - DRA Injection Package |  |  | Vendor Scope | Vendor Scope |  | #N/A
T-00090-0450 | PR1-03-SEA-0001 | CZX01I - Package | PCOM - Precommissioning | I - Instrumentation | FACP | #N/A |  | PS2-03-04 - FZ-04 - Emergency Diesel Generator Enclosure |  |  | Vendor Scope | Vendor Scope |  | #N/A
T-00090-0452 | PS2-03-SEA-0001 | CZX01I - Package | PCOM - Precommissioning | I - Instrumentation | FACP | CPP AGI |  | PS2-03-04 - FZ-04 - Emergency Diesel Generator Enclosure |  |  | Vendor Scope | Vendor Scope
T-00091-0500 | PS2-06-IER-0001A | CPX00 - Miscellaneous electrical equipment | PCOM - Precommissioning | E - Electrical | Battery MCCB box A | EITS |  | PS2-06-01 - AC UPS - EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00091-0501 | PS2-06-IER-0001B | CPX00 - Miscellaneous electrical equipment | PCOM - Precommissioning | E - Electrical | Battery MCCB box B | EITS |  | PS2-06-01 - AC UPS - EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00154-0170 | PS2-02-SCA-0001 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | CARBON DIOXIDE EXTINGUISHER, 7 KG | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0171 | PS2-02-SCA-0005 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | CARBON DIOXIDE EXTINGUISHER, 7 KG | CPP AGI | UG-MID-65-WPR2-121112 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0172 | PS2-02-SCE-0001 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER IN WEATHERPROOF CABINET CLASS: BC; 12 KG | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0173 | PS2-02-SCE-0002 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER IN WEATHERPROOF CABINET CLASS: BC; 12 KG | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0174 | PS2-02-SCE-0004 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER IN WEATHERPROOF CABINET CLASS: BC; 12 KG | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0175 | PS2-02-SCE-0007 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER IN WEATHERPROOF CABINET CLASS: BC; 12 KG | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0176 | PS2-02-SCE-0010 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER IN WEATHERPROOF CABINET CLASS: BC; 12 KG | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0177 | PS2-02-SCE-0016 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER IN WEATHERPROOF CABINET CLASS: BC; 12 KG | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0178 | PS2-02-SCE-0018 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | MOBILE DRY POWDER EXTINGUISHER CLASS: BC; 60 KG | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0179 | PS2-02-SCE-0019 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER IN WEATHERPROOF CABINET CLASS: BC; 12 KG | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0180 | PS2-02-SCE-0022 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER CLASS: ABC; 9 KG | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0181 | PS2-02-SCE-0024 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER IN WEATHERPROOF CABINET CLASS: BC; 12 KG | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0182 | PS2-02-SCE-0025 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER IN WEATHERPROOF CABINET CLASS: BC; 12 KG | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0183 | PS2-02-SCE-0027 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | MOBILE DRY POWDER EXTINGUISHER CLASS: BC; 60 KG | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0184 | PS2-02-SCE-0028 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER CLASS: ABC; 5 KG | CPP AGI | UG-MID-65-WPR2-121112 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0185 | PS2-02-SFD-0001 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | FOAM MOBILE WHEELED 100 L FIRE EXTINGUISHER | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0186 | PS2-02-SFD-0002 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | FOAM MOBILE WHEELED 100 L FIRE EXTINGUISHER | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0187 | PS2-02-SFD-0003 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | 9 L FOAM PORTABLE FIRE EXTINGUISHER | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0188 | PS2-02-SFD-0004 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | 9 L FOAM PORTABLE FIRE EXTINGUISHER | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0189 | PS2-02-SFD-0005 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | 9 L FOAM PORTABLE FIRE EXTINGUISHER | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0190 | PS2-02-SFD-0006 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | FOAM MOBIL CART 82 KG FIRE EXTINGUISHER | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0424 | PS2-02-SCE-0100 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | Portable fire extinguishers CO2 5kg | EITS | UG-MID-65-SSF1-240000 | PS2-02-02 - Portable Fire Fighting Equipments | sari, indera | Closed | Closed | Closed |  | #N/A
T-00154-0425 | PS2-02-SCE-0101 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | Portable fire extinguishers CO2 5kg | EITS | UG-MID-65-SSF1-240000 | PS2-02-02 - Portable Fire Fighting Equipments | sari, indera | Closed | Closed | Closed |  | #N/A
T-00154-0426 | PS2-02-SCE-0102 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | Portable fire extinguishers CO2 5kg | EITS | UG-MID-65-SSF1-240000 | PS2-02-02 - Portable Fire Fighting Equipments | sari, indera | Closed | Closed | Closed |  | #N/A
T-00154-0427 | PS2-02-SCE-0103 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | Portable fire extinguishers CO2 5kg | EITS | UG-MID-65-SSF1-240000 | PS2-02-02 - Portable Fire Fighting Equipments | sari, indera | Closed | Closed | Closed |  | #N/A
T-00154-0428 | PS2-02-SCE-0104 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | Portable fire extinguishers CO2 5kg | EITS | UG-MID-65-SSF1-240000 | PS2-02-02 - Portable Fire Fighting Equipments | sari, indera | Closed | Closed | Closed |  | #N/A
T-00154-0511 | PS2-02-SCA-0006 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | CARBON DIOXIDE EXTINGUISHER, 7 KG | CPP AGI | UG-MID-65-CPP1-120004 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0512 | PS2-02-SCA-0008 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | CARBON DIOXIDE EXTINGUISHER, 7 KG | CPP AGI | UG-MID-65-CPP1-120000 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0513 | PS2-02-SCB-0001 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER CLASS: ABC; 5 KG | CPP AGI | UG-MID-65-CPP1-120004 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0514 | PS2-02-SCB-0002 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER CLASS: ABC; 9 KG | CPP AGI | UG-MID-65-CPP1-120000 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0515 | PS2-02-SCB-0003 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER CLASS: ABC; 9 KG | CPP AGI | UG-MID-65-CPP1-120000 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0516 | PS2-02-SCB-0004 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER CLASS: ABC; 9 KG | CPP AGI | UG-MID-65-CPP1-120000 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0517 | PS2-02-SCB-0005 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER CLASS: ABC; 9 KG | CPP AGI | UG-MID-65-CPP1-120000 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0518 | PS2-02-SCB-0006 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER CLASS: ABC; 5 KG | CPP AGI | UG-MID-65-CPP1-120004 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0519 | PS2-02-SCB-0007 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER CLASS: ABC; 5 KG | CPP AGI | UG-MID-65-CPP1-120004 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0520 | PS2-02-SCB-0008 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | PORTABLE DRY POWDER EXTINGUISHER CLASS: ABC; 5 KG | CPP AGI | UG-MID-65-CPP1-120004 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0521 | PS2-02-SCE-0106 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | MOBILE DRY POWDER EXTINGUISHER CLASS: BC; 60 KG | CPP AGI | UG-MID-65-CPP1-120000 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00154-0522 | PS2-02-SCE-0107 | CYX08 - Portable fire extinguisher | PCOM - Precommissioning | S - Safety | MOBILE DRY POWDER EXTINGUISHER CLASS: BC; 60 KG | CPP AGI | UG-MID-65-CPP1-120000 | PS2-02-02 - Portable Fire Fighting Equipments |  |  |  | Construction not yet started |  | #N/A
T-00155-0092 | PS2-02-SCSK-0001 | CYX09 - Survival equipment | PCOM - Precommissioning | S - Safety | CHEMICAL SPILL KIT | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-01 - Miscellaneous Safety equipment |  |  |  | Construction not yet started |  | #N/A
T-00155-0093 | PS2-02-SCSK-0002 | CYX09 - Survival equipment | PCOM - Precommissioning | S - Safety | CHEMICAL SPILL KIT | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-01 - Miscellaneous Safety equipment |  |  |  | Construction not yet started |  | #N/A
T-00155-0094 | PS2-02-SES-0002 | CYX09 - Survival equipment | PCOM - Precommissioning | S - Safety | EMERGENCY STRETCHER | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-01 - Miscellaneous Safety equipment |  |  |  | Construction not yet started |  | #N/A
T-00155-0095 | PS2-02-SFAB-0002 | CYX09 - Survival equipment | PCOM - Precommissioning | S - Safety | FIRST AID BOX | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-01 - Miscellaneous Safety equipment |  |  |  | Construction not yet started |  | #N/A
T-00155-0096 | PS2-02-SFP-0001 | CYX09 - Survival equipment | PCOM - Precommissioning | S - Safety | FIRE POINT | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-01 - Miscellaneous Safety equipment |  |  |  | Construction not yet started |  | #N/A
T-00155-0097 | PS2-02-SRA-0002 | CYX09 - Survival equipment | PCOM - Precommissioning | S - Safety | FIRE BLANKET | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-01 - Miscellaneous Safety equipment |  |  |  | Construction not yet started |  | #N/A
T-00155-0098 | PS2-02-SWSI-0002 | CYX09 - Survival equipment | PCOM - Precommissioning | S - Safety | ILLUMINATED WINDSOCK | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-01 - Miscellaneous Safety equipment |  |  |  | Construction not yet started |  | #N/A
T-00155-0200 | PS2-02-SGF-0010 | CYX09 - Survival equipment | PCOM - Precommissioning | S - Safety | Safety Kit | EITS | UG-MID-65-SSF1-240000 | PS2-02-01 - Miscellaneous Safety equipment | sari, indera | Closed | Closed | Closed |  | #N/A
T-00156-0128 | PS2-02-SAB-0001 | CYX10 - First aid equipment | PCOM - Precommissioning | S - Safety | PORTABLE EYE WASH STATION | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-01 - Miscellaneous Safety equipment |  |  |  | Construction not yet started |  | #N/A
T-00156-0129 | PS2-02-SAS-0001 | CYX10 - First aid equipment | PCOM - Precommissioning | S - Safety | COMBINED SAFETY SHOWER AND EYEWASH - EXTERNAL USE | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-01 - Miscellaneous Safety equipment |  |  |  | Construction not yet started |  | #N/A
T-00156-0130 | PS2-02-SAS-0002 | CYX10 - First aid equipment | PCOM - Precommissioning | S - Safety | COMBINED SAFETY SHOWER AND EYEWASH - EXTERNAL USE | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-01 - Miscellaneous Safety equipment |  |  |  | Construction not yet started |  | #N/A
T-00156-0131 | PS2-02-SAS-0003 | CYX10 - First aid equipment | PCOM - Precommissioning | S - Safety | COMBINED SAFETY SHOWER AND EYEWASH - EXTERNAL USE | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-01 - Miscellaneous Safety equipment |  |  |  | Construction not yet started |  | #N/A
T-00156-0132 | PS2-02-SAS-0004 | CYX10 - First aid equipment | PCOM - Precommissioning | S - Safety | COMBINED SAFETY SHOWER AND EYEWASH - EXTERNAL USE | CPP AGI | UG-MID-65-WPR2-121100 | PS2-02-01 - Miscellaneous Safety equipment |  |  |  | Construction not yet started |  | #N/A
T-00156-0216 | PS2-02-SAB-0010 | CYX10 - First aid equipment | PCOM - Precommissioning | S - Safety | Eye Wash Unit | EITS | UG-MID-65-SSF1-240000 | PS2-02-01 - Miscellaneous Safety equipment | sari, indera | Closed | Closed | Closed |  | #N/A
T-00163-0035 | PS2-08-06AH-0001 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EITS | UT-MID-60-SSF1-170602 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00163-0036 | PS2-08-06AH-0002 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EITS | UT-MID-60-SSF1-170602 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00163-0037 | PS2-08-06AH-0003 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EITS | UT-MID-60-SSF1-170602 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00163-0038 | PS2-08-06AH-0004 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EITS | UT-MID-60-SSF1-170602 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00163-0039 | PS2-08-06AH-0005 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EITS | UT-MID-60-SSF1-170602 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00163-0040 | PS2-08-06AH-0006 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EITS | UT-MID-60-SSF1-170602 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00163-0041 | PS2-08-06AH-0007 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EITS | UT-MID-60-SSF1-170602 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00163-0042 | PS2-08-06AH-0008 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EITS | UT-MID-60-SSF1-170602 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00163-0043 | PS2-08-06AH-0009 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EITS | UT-MID-60-SSF1-170602 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00163-0495 | PS2-08-01LS-0103 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00163-0496 | PS2-08-01LS-0605 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 6 - Adressable Hazardous area addressable wall-mounted speaker (Ex rated) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0497 | PS2-08-01LS-0209 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 2 - Adressable Safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0498 | PS2-08-01LS-0402 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 4 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00163-0499 | PS2-08-01LS-0602 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 6 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started | Column mounted | #N/A
T-00163-0500 | PS2-08-01LS-0504 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 5 - Adressable Hazardous area addressable wall-mounted speaker (Ex rated) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0501 | PS2-08-01LS-0214 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 2 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0502 | PS2-08-01LS-0106 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable Safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0503 | PS2-08-01LS-0405 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 4 - Adressable Hazardous area addressable wall-mounted speaker (Ex rated) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0504 | PS2-08-01LS-0212 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 2 - Adressable safe area addressable ceiling speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0505 | PS2-08-01LS-0203 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 2 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0506 | PS2-08-01LS-0301 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 3 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0507 | PS2-08-01LS-0503 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 5 - Adressable Hazardous area addressable wall-mounted speaker (Ex rated) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0508 | PS2-08-01LS-0406 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 4 - Adressable Hazardous area addressable wall-mounted speaker (Ex rated) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0509 | PS2-08-01LS-0207 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable Safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0510 | PS2-08-01LS-0216 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 2 - Adressable safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00163-0511 | PS2-08-01LS-0306 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 3 - Adressable Hazardous area addressable wall-mounted speaker (Ex rated) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0512 | PS2-08-01LS-0218 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 2 - Adressable safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00163-0513 | PS2-08-01LS-0104 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable Safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0514 | PS2-08-01LS-0502 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 5 - Adressable Hazardous area addressable wall-mounted speaker (Ex rated) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0515 | PS2-08-01LS-0210 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 2 - Adressable safe area addressable ceiling speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0516 | PS2-08-01LS-0116 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable Safe area addressable wall-mounted speaker (including LTD) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00163-0517 | PS2-08-01LS-0221 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 2 - Adressable safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00163-0518 | PS2-08-01LS-0505 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 5 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started | Column mounted | #N/A
T-00163-0519 | PS2-08-01LS-0113 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0520 | PS2-08-01LS-0305 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 3 - Adressable Hazardous area addressable wall-mounted speaker (Ex rated) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0521 | PS2-08-01LS-0108 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable Safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0522 | PS2-08-01LS-0303 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 3 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0523 | PS2-08-01LS-0122 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable Safe area addressable wall-mounted speaker (Ex rated) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00163-0524 | PS2-08-01LS-0120 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00163-0525 | PS2-08-01LS-0114 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0526 | PS2-08-01LS-0220 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 2 - Adressable safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00163-0527 | PS2-08-01LS-0606 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 6 - Adressable weatherproof Horn Speaker (including LTD) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0528 | PS2-08-01LS-0506 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 5 - Adressable Hazardous area addressable wall-mounted speaker (Ex rated) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0529 | PS2-08-01LS-0202 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 2 - Adressable safe area addressable ceiling speaker (including LTD) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0530 | PS2-08-01LS-0304 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 3 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0184
T-00163-0531 | PS2-08-01LS-0204 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable Safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0532 | PS2-08-01LS-0217 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 2 - Adressable Safe area addressable wall-mounted speaker (including LTD) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00163-0533 | PS2-08-01LS-0208 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable Safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0534 | PS2-08-01LS-0206 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable Safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0535 | PS2-08-01LS-0607 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 6 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0536 | PS2-08-01LS-0109 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable safe area addressable ceiling speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0537 | PS2-08-01LS-0307 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 3 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started | Column mounted | #N/A
T-00163-0538 | PS2-08-01LS-0401 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 4 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00163-0539 | PS2-08-01LS-0211 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 2 - Adressable safe area addressable ceiling speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0540 | PS2-08-01LS-0110 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable safe area addressable ceiling speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0541 | PS2-08-01LS-0213 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 2 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0542 | PS2-08-01LS-0302 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 3 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0543 | PS2-08-01LS-0115 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00163-0544 | PS2-08-01LS-0219 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 2 - Adressable safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00163-0545 | PS2-08-01LS-0117 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00163-0546 | PS2-08-01LS-0112 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable safe area addressable ceiling speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0547 | PS2-08-01LS-0205 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable Safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0548 | PS2-08-01LS-0101 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable weatherproof Horn Speaker (including LTD) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0549 | PS2-08-01LS-0121 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00163-0550 | PS2-08-01LS-0404 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 4 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0551 | PS2-08-01LS-0501 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 5 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0552 | PS2-08-01LS-0222 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 2 - Adressable Hazardous area addressable wall-mounted speaker (Ex rated) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00163-0553 | PS2-08-01LS-0119 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00163-0554 | PS2-08-01LS-0604 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 6 - Adressable Hazardous area addressable wall-mounted speaker (Ex rated) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0555 | PS2-08-01LS-0215 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 2 - Adressable safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00163-0556 | PS2-08-01LS-0102 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable safe area addressable ceiling speaker (including LTD) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0557 | PS2-08-01LS-0111 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable safe area addressable ceiling speaker (including LTD) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0558 | PS2-08-01LS-0118 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00163-0559 | PS2-08-01LS-0107 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable Safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0560 | PS2-08-01LS-0603 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 6 - Adressable Hazardous area addressable wall-mounted speaker (Ex rated) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0561 | PS2-08-01LS-0403 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 4 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0184
T-00163-0562 | PS2-08-01LS-0201 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 2 - Adressable weatherproof Horn Speaker (including LTD) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0563 | PS2-08-01LS-0601 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 6 - Adressable weatherproof Horn Speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0564 | PS2-08-01LS-0507 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 5 - Adressable weatherproof Horn Speaker (including LTD) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00163-0565 | PS2-08-01LS-0105 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | PCOM - Precommissioning | T - Telecom | Loop 1 - Adressable Safe area addressable wall-mounted speaker | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00164-0056 | PS2-08-01FB-0804 | CIX02 - PA/GA flashing beacon + JB | PCOM - Precommissioning | T - Telecom | Loop 8 - SAFE AREA FLASHING BEACON | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00164-0057 | PS2-08-01FB-0702 | CIX02 - PA/GA flashing beacon + JB | PCOM - Precommissioning | T - Telecom | Loop 7 - HAZARDOUS AREA FLASHING BEACON | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00164-0058 | PS2-08-01FB-0803 | CIX02 - PA/GA flashing beacon + JB | PCOM - Precommissioning | T - Telecom | Loop 8 - HAZARDOUS AREA FLASHING BEACON | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00164-0059 | PS2-08-01FB-0802 | CIX02 - PA/GA flashing beacon + JB | PCOM - Precommissioning | T - Telecom | Loop 8 - HAZARDOUS AREA FLASHING BEACON | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00164-0060 | PS2-08-01FB-0701 | CIX02 - PA/GA flashing beacon + JB | PCOM - Precommissioning | T - Telecom | Loop 7 - HAZARDOUS AREA FLASHING BEACON | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0080
T-00164-0061 | PS2-08-01FB-0703 | CIX02 - PA/GA flashing beacon + JB | PCOM - Precommissioning | T - Telecom | Loop 7 - HAZARDOUS AREA FLASHING BEACON | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00164-0062 | PS2-08-01FB-0704 | CIX02 - PA/GA flashing beacon + JB | PCOM - Precommissioning | T - Telecom | Loop 7 - SAFE AREA FLASHING BEACON | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0093
T-00164-0063 | PS2-08-01FB-0801 | CIX02 - PA/GA flashing beacon + JB | PCOM - Precommissioning | T - Telecom | Loop 8 - HAZARDOUS AREA FLASHING BEACON | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00165-0021 | PS2-08-01OC-0002 | CIX03 - P.A. Access and Override control unit | PCOM - Precommissioning | T - Telecom | OVERRIDE CONTROL UNIT (OCU) - Secondary muster point | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00165-0022 | PS2-08-01PA-1201 | CIX03 - P.A. Access and Override control unit | PCOM - Precommissioning | T - Telecom | VIRTUAL PC PAGA ACCESS UNIT | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00165-0023 | PS2-08-01PA-1501 | CIX03 - P.A. Access and Override control unit | PCOM - Precommissioning | T - Telecom | VIRTUAL PC PAGA ACCESS UNIT | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00165-0024 | PS2-08-01OC-0001 | CIX03 - P.A. Access and Override control unit | PCOM - Precommissioning | T - Telecom | OVERRIDE CONTROL UNIT (OCU) - Primary muster point | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00166-0006 | PS2-08-01MP-0001 | CIX04 - PA/GA Central System and Marshalling Cabinet | PCOM - Precommissioning | T - Telecom | Outdoor Marshalling enclosure (IDF) | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00170-0387 | PS2-08-03FB-0001 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Safe Area FB+Sounder Outdoor 230Vca | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00170-0388 | PS2-08-03FB-0002 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Safe Area FB+Sounder Outdoor 230Vca | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00170-0389 | PS2-08-03FB-0101 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Safe Area FB+Sounder Outdoor 230Vca | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00170-0390 | PS2-08-03FB-0102 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Safe Area FB+Sounder Outdoor 230Vca | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00170-0391 | PS2-08-03FB-0103 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Safe Area FB+Sounder Outdoor 230Vca | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0104
T-00170-0392 | PS2-08-03FB-0104 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Safe Area FB+Sounder Outdoor 230Vca | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00170-0393 | PS2-08-03HO-0001 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Accoustic Hood | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00170-0394 | PS2-08-03HO-0002 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Accoustic Hood | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00170-0395 | PS2-08-03HO-0101 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Accoustic Hood | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started | Foundation to be provided by civil | #N/A
T-00170-0396 | PS2-08-03HO-0102 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Accoustic Hood | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00170-0397 | PS2-08-03HO-0103 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Accoustic Hood | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00170-0398 | PS2-08-03HO-0104 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Accoustic Hood | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00170-0399 | PS2-08-03TP-0001 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Outdoor Weather Proof Analog Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00170-0400 | PS2-08-03TP-0002 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Outdoor Weather Proof Analog Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00170-0401 | PS2-08-03TP-0101 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Outdoor Weather Proof Analog Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00170-0402 | PS2-08-03TP-0102 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Outdoor Weather Proof Analog Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00170-0403 | PS2-08-03TP-0103 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Outdoor Weather Proof Analog Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0184
T-00170-0404 | PS2-08-03TP-0104 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | PCOM - Precommissioning | T - Telecom | Outdoor Weather Proof Analog Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00171-10208 | PS2-08-01IO-1001-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10209 | PS2-08-01IO-1001-CC02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10210 | PS2-08-01LS-0115-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-01LS-0115 | EITS |  | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10211 | PS2-08-01LS-0116-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0115 TO PS2-08-01LS-0116 | EITS |  | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10212 | PS2-08-01LS-0117-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-01LS-0117 | EITS |  | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10213 | PS2-08-01LS-0118-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0117 TO PS2-08-01LS-0118 | EITS |  | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10214 | PS2-08-01LS-0119-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0118 TO PS2-08-01LS-0119 | EITS |  | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10215 | PS2-08-01LS-0120-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0119 TO PS2-08-01LS-0120 | EITS |  | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10216 | PS2-08-01LS-0121-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0120 TO PS2-08-01LS-0121 | EITS |  | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10217 | PS2-08-01LS-0122-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0121 TO PS2-08-01LS-0122 | EITS |  | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10218 | PS2-08-01LS-0216-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0215 TO PS2-08-01LS-0216 | EITS |  | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10219 | PS2-08-01LS-0217-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0216 TO PS2-08-01LS-0217 | EITS |  | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10220 | PS2-08-01LS-0218-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-01LS-0218 | EITS |  | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10221 | PS2-08-01LS-0219-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0218 TO PS2-08-01LS-0219 | EITS |  | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10222 | PS2-08-01LS-0220-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0219 TO PS2-08-01LS-0220 | EITS |  | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10223 | PS2-08-01LS-0221-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0220 TO PS2-08-01LS-0221 | EITS |  | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10224 | PS2-08-01LS-0222-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0221 TO PS2-08-01LS-0222 | EITS |  | PS2-08-01 - PAGA | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10225 | PS2-08-03GY-1001-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-03 - Telephone | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10226 | PS2-08-11CB-1001-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10227 | PS2-08-11CB-1001-CA02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10228 | PS2-08-11CB-1001-CA03 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10229 | PS2-08-11CB-1001-CA04 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10230 | PS2-08-11CB-1001-CA05 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10231 | PS2-08-11CB-1001-CA06 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10232 | PS2-08-11CB-1001-CA07 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10233 | PS2-08-11CB-1001-CA08 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10234 | PS2-08-11CB-1001-CA09 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10235 | PS2-08-11CB-1001-CA10 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10236 | PS2-08-11CB-1001-CA11 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10237 | PS2-08-11CB-1001-CA12 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10238 | PS2-08-12AP-1001-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12AP-1001 | EITS |  | PS2-08-12 - Corporate Wireless LAN (SIE) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10239 | PS2-08-12AP-1002-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12AP-1002 | EITS |  | PS2-08-12 - Corporate Wireless LAN (SIE) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10240 | PS2-08-13CB-1001-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10241 | PS2-08-13CB-1001-CA02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10242 | PS2-08-13CB-1001-CA03 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10243 | PS2-08-13CB-1001-CA04 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10244 | PS2-08-13CB-1001-CA05 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10245 | PS2-08-13CB-1001-CA06 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10246 | PS2-08-13CB-1001-CA07 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10247 | PS2-08-13CB-1001-CA08 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10248 | PS2-08-13CB-1001-CA09 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10249 | PS2-08-13CB-1001-CA10 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10250 | PS2-08-13CB-1001-CA11 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10251 | PS2-08-13CB-1001-CA12 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10252 | PS2-08-13CB-1001-CA13 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10253 | PS2-08-13CB-1001-CA14 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10254 | PS2-08-13CB-1001-CA15 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10255 | PS2-08-13CB-1001-CA16 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10256 | PS2-08-13CB-1001-CA17 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10257 | PS2-08-13CB-1001-CA18 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10258 | PS2-08-13CB-1001-CA19 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10259 | PS2-08-13CB-1001-CA20 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10260 | PS2-08-13CB-1001-CA21 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10261 | PS2-08-13CB-1001-CA22 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10262 | PS2-08-13CB-1001-CA23 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10263 | PS2-08-13CB-1001-CA24 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10264 | PS2-08-13CB-1001-CC02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-93 - Telecom Monitoring System | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10265 | PS2-08-15CB-1001-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10266 | PS2-08-15CB-1001-CA02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00171-10267 | PS2-08-15CB-1001-CA03 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10268 | PS2-08-15CB-1001-CA04 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00171-10269 | PS2-08-15CB-1001-CA05 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00171-10270 | PS2-08-15CB-1001-CA06 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10271 | PS2-08-15CB-1001-CA07 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00171-10272 | PS2-08-15CB-1001-CA08 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10273 | PS2-08-15CB-1001-CA09 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10274 | PS2-08-15CB-1001-CA10 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10275 | PS2-08-15CB-1001-CA11 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00171-10276 | PS2-08-15CB-1001-CA12 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00171-10277 | PS2-08-15CB-1001-CA13 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10278 | PS2-08-15CB-1001-CA14 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00171-10279 | PS2-08-15CB-1001-CA15 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00171-10280 | PS2-08-15CB-1001-CA16 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00171-10281 | PS2-08-15CB-1001-CA17 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00171-10282 | PS2-08-15CB-1001-CA18 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00171-10283 | PS2-08-23AN-0003-CV01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23AN-0003 TO PS2-08-23LA-1001 | EITS |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00171-10284 | PS2-08-23AN-1001-CV01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23SL-1001 TO PS2-08-23AN-1001 | EITS |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00171-10285 | PS2-08-23AN-1001-CV02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23SL-1001 TO PS2-08-23AN-1002 | EITS |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00171-10286 | PS2-08-23LA-1001-CV01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23LA-1001 TO PS2-08-23SL-1001 | EITS |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00171-10287 | PS2-08-35CB-1001-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00171-10288 | PS2-08-35CB-1001-CA02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00171-10289 | PS2-08-35CB-1001-CA03 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00171-10290 | PS2-08-35CB-1001-CA04 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00171-10291 | PS2-08-35CB-1001-CA05 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00171-10292 | PS2-08-35CB-1001-CA06 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10293 | PS2-08-35CB-1001-CA07 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10294 | PS2-08-35CB-1001-CA08 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00171-10295 | PS2-08-35CB-1001-CA09 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00171-10296 | PS2-08-35CB-1001-CA10 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00171-10297 | PS2-08-35CB-1001-CA11 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00171-10298 | PS2-08-35CB-1001-CA12 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00171-10299 | PS2-08-35CB-1001-CA13 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00171-10300 | PS2-08-35CB-1001-CA14 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00171-10301 | PS2-08-35CB-1001-CA15 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00171-10302 | PS2-08-35CB-1001-CA16 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00171-10303 | PS2-08-35CB-1001-CA17 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network | hadji, tahar | Closed | Closed | Closed |  | #N/A
T-00171-10304 | PS2-08-35CB-1001-CA18 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00171-10305 | PS2-08-35CB-1001-CA19 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00171-10306 | PS2-08-52CM-1001-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1001 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-10307 | PS2-08-52CM-1002-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1002 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-10308 | PS2-08-52CM-1003-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1003 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-10309 | PS2-08-52CM-1004-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1004 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-10310 | PS2-08-52CM-1011-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1011 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-10311 | PS2-08-52CM-1012-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1012 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-10312 | PS2-08-52CM-1013-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1013 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-10313 | PS2-08-52CM-1014-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1014 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-10314 | PS2-08-52CM-1015-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1015 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-10315 | PS2-08-52CM-1016-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1016 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-10316 | PS2-08-71SK-1001A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1001A | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-10317 | PS2-08-71SK-1001B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1001B | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-10318 | PS2-08-71SK-1002A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1002A | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-10319 | PS2-08-71SK-1002B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1002B | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-10320 | PS2-08-71SK-1003A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1003A | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-10321 | PS2-08-71SK-1003B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1003B | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-10322 | PS2-08-71SK-1004A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1004A | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-10323 | PS2-08-71SK-1004B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1004B | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-10324 | PS2-08-71SK-1005A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1005A | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-10325 | PS2-08-71SK-1005B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1005B | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-10326 | PS2-08-71SK-1006A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1006A | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-10327 | PS2-08-71SK-1006B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1006B | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-10328 | PS2-08-85BR-1001-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1001 TO PS2-08-85BR-1002 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10329 | PS2-08-85BR-1002-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1001 TO PS2-08-85BR-1002 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10330 | PS2-08-85BT-1001-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1001 TO PS2-08-85BT-1001 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10331 | PS2-08-85BT-1001-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10332 | PS2-08-85BT-1002-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1001 TO PS2-08-85BT-1002 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10333 | PS2-08-85BT-1003-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1001 TO PS2-08-85BT-1003 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10334 | PS2-08-85BT-1003-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1003 TO PS2-08-15CB-1001 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10335 | PS2-08-85BT-1004-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1001 TO PS2-08-85BT-1004 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10336 | PS2-08-85BT-1005-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1001 TO PS2-08-85BT-1005 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10337 | PS2-08-85CP-1001-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-85CP-1001 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10338 | PS2-08-85DC-1001-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1001 TO PS2-08-85DC-1001 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10339 | PS2-08-85DC-1002-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1001 TO PS2-08-85DC-1002 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10340 | PS2-08-85DC-1003-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1002 TO PS2-08-85DC-1003 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10341 | PS2-08-85DC-1004-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1003 TO PS2-08-85DC-1004 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10342 | PS2-08-85DC-1005-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1003 TO PS2-08-85DC-1005 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10343 | PS2-08-85DC-1006-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1004 TO PS2-08-85DC-1006 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10344 | PS2-08-85DC-1007-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1005 TO PS2-08-85DC-1007 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10345 | PS2-08-85ML-1001-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1001 TO PS2-08-85ML-1001 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10346 | PS2-08-85ML-1002-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1003 TO PS2-08-85ML-1002 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10347 | PS2-08-85PB-1001-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1001 TO PS2-08-85PB-1001 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-10348 | PS2-08-85PB-1002-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1003 TO PS2-08-85PB-1002 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3605 | PS2-08-01BT-0001-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01BT-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3606 | PS2-08-01BT-0001-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01OC-0001 TO PS2-08-01BT-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3607 | PS2-08-01BT-0002-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01BT-0002 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3608 | PS2-08-01BT-0002-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01OC-0001 TO PS2-08-01BT-0002 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3609 | PS2-08-01BT-0003-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0506 TO PS2-08-01BT-0003 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3610 | PS2-08-01BT-0003-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01BT-0003 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3611 | PS2-08-01BT-0003-CR03 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01OC-0002 TO PS2-08-01BT-0003 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3612 | PS2-08-01BT-0004-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0605 TO PS2-08-01BT-0004 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3613 | PS2-08-01BT-0004-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01OC-0002 TO PS2-08-01BT-0004 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3614 | PS2-08-01BT-1201-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1601 TO PS2-08-01BT-1201 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3615 | PS2-08-01BT-1201-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1201 TO PS2-08-01BT-1203 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3616 | PS2-08-01BT-1202-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1602 TO PS2-08-01BT-1202 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3617 | PS2-08-01BT-1202-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1202 TO PS2-08-01BT-1203 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3618 | PS2-08-01BT-1203-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01BT-1203 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3619 | PS2-08-01BT-1203-CJ02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01BT-1203 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3620 | PS2-08-01BT-1203-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-01BT-1203 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3621 | PS2-08-01BT-1203-CN02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-01BT-1203 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3622 | PS2-08-01BT-1501-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0103 TO PS2-08-01BT-1501 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3623 | PS2-08-01BT-1501-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1501 TO PS2-08-01BT-1503 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3624 | PS2-08-01BT-1502-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-0002 TO PS2-08-01BT-1502 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3625 | PS2-08-01BT-1502-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1502 TO PS2-08-01BT-1503 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3626 | PS2-08-01BT-1503-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01BT-1503 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3627 | PS2-08-01BT-1503-CJ02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01BT-1503 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3628 | PS2-08-01BT-1503-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-01BT-1503 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3629 | PS2-08-01BT-1503-CN02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-01BT-1503 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3630 | PS2-08-01BT-1601-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1501 TO PS2-08-01BT-1601 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3631 | PS2-08-01BT-1602-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0203 TO PS2-08-01BT-1602 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3632 | PS2-08-01LS-0101-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01OC-0001 TO PS2-08-01LS-0101 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3633 | PS2-08-01LS-0102-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1501 TO PS2-08-01LS-0102 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3634 | PS2-08-01LS-0103-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-0001 TO PS2-08-01LS-0103 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3635 | PS2-08-01LS-0104-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1601 TO PS2-08-01LS-0104 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3636 | PS2-08-01LS-0105-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0104 TO PS2-08-01LS-0105 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3637 | PS2-08-01LS-0106-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0105 TO PS2-08-01LS-0106 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3638 | PS2-08-01LS-0107-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0106 TO PS2-08-01LS-0107 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3639 | PS2-08-01LS-0108-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0107 TO PS2-08-01LS-0108 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3640 | PS2-08-01LS-0108-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1601 TO PS2-08-01LS-0108 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3641 | PS2-08-01LS-0109-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0109 TO PS2-08-01LS-0110 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3642 | PS2-08-01LS-0109-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1201 TO PS2-08-01LS-0109 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3643 | PS2-08-01LS-0110-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0110 TO PS2-08-01LS-0112 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3644 | PS2-08-01LS-0111-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1201 TO PS2-08-01LS-0111 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3645 | PS2-08-01LS-0112-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1201 TO PS2-08-01LS-0112 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3646 | PS2-08-01LS-0113-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1201 TO PS2-08-01LS-0113 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3647 | PS2-08-01LS-0114-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0113 TO PS2-08-01LS-0114 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3648 | PS2-08-01LS-0114-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0114 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3649 | PS2-08-01LS-0122-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0122 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3650 | PS2-08-01LS-0201-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01OC-0001 TO PS2-08-01LS-0201 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3651 | PS2-08-01LS-0202-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1502 TO PS2-08-01LS-0202 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3652 | PS2-08-01LS-0203-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1502 TO PS2-08-01LS-0203 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3653 | PS2-08-01LS-0204-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1602 TO PS2-08-01LS-0204 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3654 | PS2-08-01LS-0205-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0204 TO PS2-08-01LS-0205 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3655 | PS2-08-01LS-0206-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0205 TO PS2-08-01LS-0206 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3656 | PS2-08-01LS-0207-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0206 TO PS2-08-01LS-0207 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3657 | PS2-08-01LS-0208-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0207 TO PS2-08-01LS-0208 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3658 | PS2-08-01LS-0209-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0208 TO PS2-08-01LS-0209 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3659 | PS2-08-01LS-0209-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1602 TO PS2-08-01LS-0209 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3660 | PS2-08-01LS-0210-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1202 TO PS2-08-01LS-0210 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3661 | PS2-08-01LS-0211-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0210 TO PS2-08-01LS-0211 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3662 | PS2-08-01LS-0212-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0211 TO PS2-08-01LS-0212 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3663 | PS2-08-01LS-0213-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1202 TO PS2-08-01LS-0213 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3664 | PS2-08-01LS-0214-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0213 TO PS2-08-01LS-0214 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3665 | PS2-08-01LS-0214-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0214 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3666 | PS2-08-01LS-0215-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0212 TO PS2-08-01LS-0215 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA | sari, indera | Closed | Closed | Closed |  | #N/A
T-00171-3667 | PS2-08-01LS-0215-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1202 TO PS2-08-01LS-0215 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3668 | PS2-08-01LS-0222-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0222 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3669 | PS2-08-01LS-0301-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0301 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3670 | PS2-08-01LS-0302-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0301 TO PS2-08-01LS-0302 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3671 | PS2-08-01LS-0303-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0302 TO PS2-08-01LS-0303 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3672 | PS2-08-01LS-0304-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0303 TO PS2-08-01LS-0304 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0184
T-00171-3673 | PS2-08-01LS-0305-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0304 TO PS2-08-01LS-0305 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3674 | PS2-08-01LS-0306-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0305 TO PS2-08-01LS-0306 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3675 | PS2-08-01LS-0307-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0306 TO PS2-08-01LS-0307 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3676 | PS2-08-01LS-0307-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0307 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3677 | PS2-08-01LS-0401-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0401 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3678 | PS2-08-01LS-0402-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0401 TO PS2-08-01LS-0402 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3679 | PS2-08-01LS-0403-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0402 TO PS2-08-01LS-0403 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0184
T-00171-3680 | PS2-08-01LS-0404-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0403 TO PS2-08-01LS-0404 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3681 | PS2-08-01LS-0405-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0404 TO PS2-08-01LS-0405 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3682 | PS2-08-01LS-0406-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0405 TO PS2-08-01LS-0406 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3683 | PS2-08-01LS-0406-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0406 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3684 | PS2-08-01LS-0501-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0501 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3685 | PS2-08-01LS-0502-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0501 TO PS2-08-01LS-0502 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3686 | PS2-08-01LS-0503-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0502 TO PS2-08-01LS-0503 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3687 | PS2-08-01LS-0504-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0503 TO PS2-08-01LS-0504 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3688 | PS2-08-01LS-0505-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0504 TO PS2-08-01LS-0505 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3689 | PS2-08-01LS-0506-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0505 TO PS2-08-01LS-0506 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3690 | PS2-08-01LS-0507-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01OC-0002 TO PS2-08-01LS-0507 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3691 | PS2-08-01LS-0601-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0601 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3692 | PS2-08-01LS-0602-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0601 TO PS2-08-01LS-0602 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3693 | PS2-08-01LS-0603-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0602 TO PS2-08-01LS-0603 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3694 | PS2-08-01LS-0604-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0603 TO PS2-08-01LS-0604 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3695 | PS2-08-01LS-0605-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0604 TO PS2-08-01LS-0605 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3696 | PS2-08-01LS-0606-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01OC-0002 TO PS2-08-01LS-0606 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3697 | PS2-08-01LS-0607-CR01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-0004 TO PS2-08-01LS-0607 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3698 | PS2-08-01LS-0607-CR02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0607 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3699 | PS2-08-01MP-0001-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-01MP-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3700 | PS2-08-01MP-0001-CC02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-01MP-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3701 | PS2-08-01MP-0001-CC03 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-01MP-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3702 | PS2-08-01MP-0001-CC04 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-01MP-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3703 | PS2-08-01OC-0001-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01OC-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3704 | PS2-08-01OC-0001-CJ02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01OC-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3705 | PS2-08-01OC-0001-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01OC-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3706 | PS2-08-01OC-0001-CN02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01OC-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3707 | PS2-08-01OC-0002-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01OC-0002 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3708 | PS2-08-01OC-0002-CJ02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01OC-0002 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3709 | PS2-08-01OC-0002-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01OC-0002 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3710 | PS2-08-01OC-0002-CN02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01OC-0002 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3711 | PS2-08-01PA-1201-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-01PA-1201 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3712 | PS2-08-01PA-1201-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1203 TO PS2-08-01PA-1201 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3713 | PS2-08-01PA-1501-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-01PA-1501 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3714 | PS2-08-01PA-1501-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1503 TO PS2-08-01PA-1501 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00171-3715 | PS2-08-03TP-0001-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-03TP-0001 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00171-3716 | PS2-08-03TP-0001-CJ02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-03FB-0001 TO PS2-08-03TP-0001 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00171-3717 | PS2-08-03TP-0002-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-03TP-0002 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3718 | PS2-08-03TP-0002-CJ02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-03FB-0002 TO PS2-08-03TP-0002 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00171-3719 | PS2-08-03TP-0101-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-03TP-0101 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00171-3720 | PS2-08-03TP-0101-CJ02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-03FB-0101 TO PS2-08-03TP-0101 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00171-3721 | PS2-08-03TP-0102-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-03TP-0102 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00171-3722 | PS2-08-03TP-0102-CJ02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-03FB-0102 TO PS2-08-03TP-0102 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00171-3723 | PS2-08-03TP-0103-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-03TP-0103 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0184
T-00171-3724 | PS2-08-03TP-0103-CJ02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-03FB-0103 TO PS2-08-03TP-0103 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00171-3725 | PS2-08-03TP-0104-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-03TP-0104 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00171-3726 | PS2-08-03TP-0104-CJ02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-03FB-0104 TO PS2-08-03TP-0104 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00171-3727 | PS2-08-05IN-0001-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-05IN-0001 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3728 | PS2-08-06AH-0001-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0001 TO PS2-08-06AH-0001 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00171-3729 | PS2-08-06AH-0002-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0002 TO PS2-08-06AH-0002 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00171-3730 | PS2-08-06AH-0003-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-06AH-0003 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00171-3731 | PS2-08-06AH-0004-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0004 TO PS2-08-06AH-0004 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00171-3732 | PS2-08-06AH-0005-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0005 TO PS2-08-06AH-0005 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00171-3733 | PS2-08-06AH-0006-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0005 TO PS2-08-06AH-0006 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00171-3734 | PS2-08-06AH-0007-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0006 TO PS2-08-06AH-0007 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00171-3735 | PS2-08-06AH-0008-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0007 TO PS2-08-06AH-0008 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00171-3736 | PS2-08-06AH-0009-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-06AH-0009 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00171-3737 | PS2-08-12AP-0101-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-12BT-0101 TO PS2-08-12AP-0101 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00171-3738 | PS2-08-12AP-0102-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-12BT-0102 TO PS2-08-12AP-0102 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00171-3739 | PS2-08-12AP-0103-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-12BT-0103 TO PS2-08-12AP-0103 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00171-3740 | PS2-08-12AP-0104-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-12BT-0104 TO PS2-08-12AP-0104 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00171-3741 | PS2-08-12AP-0105-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-12BT-0105 TO PS2-08-12AP-0105 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00171-3742 | PS2-08-12AP-0106-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-12BT-0106 TO PS2-08-12AP-0106 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00171-3743 | PS2-08-12AP-0107-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-12BT-0107 TO PS2-08-12AP-0107 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00171-3744 | PS2-08-12BT-0103-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0103 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00171-3745 | PS2-08-12BT-0106-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0106 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00171-3746 | PS2-08-13CB-1601-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-14CB-1601 TO PS2-08-13CB-1601 | #N/A | UG-MID-65-SSF1-179320 | PS2-08-93 - Telecom Monitoring System |  |  |  | Construction not yet started |  | #N/A
T-00171-3747 | PS2-08-13CB-1601-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-04-PMC-0003 TO PS2-08-13CB-1601 | #N/A | UG-MID-65-SSF1-171320 | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00171-3748 | PS2-08-14CB-1601-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-14CB-1601 | #N/A | UG-MID-65-SSF1-171420 | PS2-08-14 - Industrial Data Network (SII SP1) |  |  |  | Construction not yet started |  | #N/A
T-00171-3749 | PS2-08-14CB-1601-CA02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-14CB-1601 | #N/A | UG-MID-65-SSF1-171420 | PS2-08-14 - Industrial Data Network (SII SP1) |  |  |  | Construction not yet started |  | #N/A
T-00171-3750 | PS2-08-14CB-1601-CA03 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-14CB-1601 | #N/A | UG-MID-65-SSF1-171420 | PS2-08-14 - Industrial Data Network (SII SP1) |  |  |  | Construction not yet started |  | #N/A
T-00171-3751 | PS2-08-14CB-1601-CA04 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-14CB-1601 | #N/A | UG-MID-65-SSF1-171420 | PS2-08-14 - Industrial Data Network (SII SP1) |  |  |  | Construction not yet started |  | #N/A
T-00171-3752 | PS2-08-14CB-1601-CA05 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-14CB-1601 | #N/A | UG-MID-65-SSF1-171420 | PS2-08-14 - Industrial Data Network (SII SP1) |  |  |  | Construction not yet started |  | #N/A
T-00171-3753 | PS2-08-14CB-1601-CA06 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-14CB-1601 | #N/A | UG-MID-65-SSF1-171420 | PS2-08-14 - Industrial Data Network (SII SP1) |  |  |  | Construction not yet started |  | #N/A
T-00171-3754 | PS2-08-23AN-0001-CV01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23LA-1202 TO PS2-08-23AN-0001 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00171-3755 | PS2-08-23AN-0002-CV01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23LA-1501 TO PS2-08-23AN-0002 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00171-3756 | PS2-08-23AN-0901-CV01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23LA-1602 TO PS2-08-23AN-0901 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00171-3757 | PS2-08-23AN-1201-CV01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23LA-1201 TO PS2-08-23AN-1201 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00171-3758 | PS2-08-23LA-1202-CV01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23BS-1201 TO PS2-08-23LA-1202 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00171-3759 | PS2-08-23LA-1501-CV01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23BS-1501 TO PS2-08-23LA-1501 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00171-3760 | PS2-08-23LA-1602-CV01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1601 TO PS2-08-23LA-1602 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00171-3761 | PS2-08-23SL-1601-CV01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1601 TO PS2-08-23SL-1601 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00171-3762 | PS2-08-23SL-1601-CV02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23AN-1601 TO PS2-08-23SL-1601 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00171-3763 | PS2-08-23SL-1601-CV03 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23LA-1201 TO PS2-08-23SL-1601 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00171-3764 | PS2-08-34AN-0001-CV01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-34LA-1201 TO PS2-08-34AN-0001 | #N/A | UG-MID-65-SSF1-173420 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00171-3765 | PS2-08-34AN-0002-CV01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-34LA-1501 TO PS2-08-34AN-0002 | #N/A | UG-MID-65-SSF1-173420 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00171-3766 | PS2-08-34LA-1201-CV01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-34DS-1201 TO PS2-08-34LA-1201 | #N/A | UG-MID-65-SSF1-173420 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00171-3767 | PS2-08-34LA-1501-CV01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-34DS-1501 TO PS2-08-34LA-1501 | #N/A | UG-MID-65-SSF1-173420 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00171-3768 | PS2-08-52CM-0001-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-52CM-0001 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3769 | PS2-08-52CM-0002-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-52CM-0002 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3770 | PS2-08-52CM-0003-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-52CM-0003 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3771 | PS2-08-52CM-0031-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-52CM-0031 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3772 | PS2-08-52CM-0032-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0002 TO PS2-08-52CM-0032 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3773 | PS2-08-52CM-0033-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0006 TO PS2-08-52CM-0033 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3774 | PS2-08-52CM-0034-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-52CM-0034 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3775 | PS2-08-52CM-0071-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0001 TO PS2-08-52CM-0071 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3776 | PS2-08-52CM-0072-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0002 TO PS2-08-52CM-0072 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3777 | PS2-08-52CM-0073-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-52CM-0073 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3778 | PS2-08-52CM-0074-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0004 TO PS2-08-52CM-0074 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3779 | PS2-08-52CM-0075-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0005 TO PS2-08-52CM-0075 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3780 | PS2-08-52CM-0076-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0006 TO PS2-08-52CM-0076 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3781 | PS2-08-52CM-0077-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0007 TO PS2-08-52CM-0077 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3782 | PS2-08-52CM-0078-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-52CM-0078 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3783 | PS2-08-52CM-0131-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-0131 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3784 | PS2-08-52CM-0931-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-52CM-0931 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3785 | PS2-08-52CM-1201-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-52CM-1201 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3786 | PS2-08-52CM-1501-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-52CM-1501 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3787 | PS2-08-52CM-1601-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-52CM-1601 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3788 | PS2-08-52TK-0032-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-52CM-0032 TO PS2-08-52TK-0032 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3789 | PS2-08-52TK-0033-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-52CM-0033 TO PS2-08-52TK-0033 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3790 | PS2-08-52TK-0034-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-52CM-0034 TO PS2-08-52TK-0034 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3791 | PS2-08-52TK-0131-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-52CM-0131 TO PS2-08-52TK-0131 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3792 | PS2-08-52TK-0132-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-52CM-0132 TO PS2-08-52TK-0132 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3793 | PS2-08-52TK-0133-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-52CM-0133 TO PS2-08-52TK-0133 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3794 | PS2-08-52TK-0134-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-52CM-0134 TO PS2-08-52TK-0134 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3795 | PS2-08-52TK-0931-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-52CM-0931 TO PS2-08-52TK-0931 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00171-3796 | PS2-08-61BT-0001-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-14CB-1601 TO PS2-08-61BT-0001 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00171-3797 | PS2-08-61BT-0001-CC02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-14CB-1601 TO PS2-08-61BT-0001 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00171-3798 | PS2-08-61BT-0001-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-14CB-1601 TO PS2-08-61BT-0001 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00171-3799 | PS2-08-61BT-0002-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-14CB-1601 TO PS2-08-61BT-0002 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00171-3800 | PS2-08-61BT-0901-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-61BT-0001 TO PS2-08-61BT-0901 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00171-3801 | PS2-08-61SN-0003-CZ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-61BT-0001 TO PS2-08-61SN-0003 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00171-3802 | PS2-08-61SN-0004-CZ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-61BT-0001 TO PS2-08-61SN-0004 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00171-3803 | PS2-08-61SN-0005-CZ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-61BT-0002 TO PS2-08-61SN-0005 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00171-3804 | PS2-08-61SN-0005-CZ02 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-61BT-0002 TO PS2-08-61SN-0005 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00171-3805 | PS2-08-61SN-0901-CZ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-61BT-0901 TO PS2-08-61SN-0901 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00171-3806 | PS2-08-71SK-1201-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1201 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3807 | PS2-08-71SK-1202-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1202 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3808 | PS2-08-71SK-1203A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1203A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3809 | PS2-08-71SK-1203B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1203B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3810 | PS2-08-71SK-1204A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1204A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3811 | PS2-08-71SK-1204B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1204B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3812 | PS2-08-71SK-1205A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1205A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3813 | PS2-08-71SK-1205B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1205B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3814 | PS2-08-71SK-1206A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1206A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3815 | PS2-08-71SK-1206B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1206B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3816 | PS2-08-71SK-1207A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1207A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3817 | PS2-08-71SK-1207B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1207B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3818 | PS2-08-71SK-1208A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1208A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3819 | PS2-08-71SK-1208B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1208B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3820 | PS2-08-71SK-1209A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1209A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3821 | PS2-08-71SK-1209B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1209B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3822 | PS2-08-71SK-1210-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1210 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3823 | PS2-08-71SK-1211A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1211A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3824 | PS2-08-71SK-1211B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1211B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3825 | PS2-08-71SK-1211C-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1211C | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3826 | PS2-08-71SK-1211D-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1211D | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3827 | PS2-08-71SK-1212A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1212A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3828 | PS2-08-71SK-1212B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1212B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3829 | PS2-08-71SK-1213A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1213A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3830 | PS2-08-71SK-1213B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1213B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3831 | PS2-08-71SK-1214A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1214A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3832 | PS2-08-71SK-1214B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1214B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3833 | PS2-08-71SK-1215-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1215 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3834 | PS2-08-71SK-1216-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1216 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3835 | PS2-08-71SK-1217A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1217A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3836 | PS2-08-71SK-1217B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1217B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3837 | PS2-08-71SK-1217C-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1217C | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3838 | PS2-08-71SK-1217D-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1217D | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3839 | PS2-08-71SK-1501A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1501A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3840 | PS2-08-71SK-1501B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1501B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3841 | PS2-08-71SK-1502A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1502A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3842 | PS2-08-71SK-1502B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1502B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3843 | PS2-08-71SK-1503A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1503A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3844 | PS2-08-71SK-1503B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1503B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3845 | PS2-08-71SK-1504-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1504 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3846 | PS2-08-71SK-1505-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1505 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3847 | PS2-08-71SK-1506A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1506A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3848 | PS2-08-71SK-1506B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1506B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3849 | PS2-08-71SK-1507-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1507 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3850 | PS2-08-71SK-1601A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-71SK-1601A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3851 | PS2-08-71SK-1601B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-71SK-1601B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3852 | PS2-08-71SK-1602A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-71SK-1602A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3853 | PS2-08-71SK-1602B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-71SK-1602B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3854 | PS2-08-71SK-1603-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-71SK-1603 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3855 | PS2-08-71SK-1604-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-71SK-1604 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3856 | PS2-08-71SK-1605-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-71SK-1605 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00171-3857 | PS2-08-85AP-0001-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0023 TO PS2-08-85AP-0001 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3858 | PS2-08-85AP-0002-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0024 TO PS2-08-85AP-0002 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3859 | PS2-08-85AP-0003-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-0021 TO PS2-08-85AP-0003 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3860 | PS2-08-85AP-0004-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-0022 TO PS2-08-85AP-0004 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3861 | PS2-08-85BG-1201-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1202 TO PS2-08-85BG-1201 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3862 | PS2-08-85BG-1601-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1601 TO PS2-08-85BG-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3863 | PS2-08-85BG-1602-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1602 TO PS2-08-85BG-1602 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3864 | PS2-08-85BR-0001-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1202 TO PS2-08-85BR-0001 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3865 | PS2-08-85BR-0002-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1201 TO PS2-08-85BR-0002 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3866 | PS2-08-85BR-0003-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-0021 TO PS2-08-85BR-0003 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3867 | PS2-08-85BR-0004-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-0022 TO PS2-08-85BR-0004 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3868 | PS2-08-85BR-0005-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1501 TO PS2-08-85BR-0005 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3869 | PS2-08-85BR-0006-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1501 TO PS2-08-85BR-0006 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3870 | PS2-08-85BR-1201-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1201 TO PS2-08-85BR-1201 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3871 | PS2-08-85BR-1202-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1202 TO PS2-08-85BR-1202 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3872 | PS2-08-85BR-1203-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1201 TO PS2-08-85BR-1203 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3873 | PS2-08-85BR-1501-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1501 TO PS2-08-85BR-1501 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3874 | PS2-08-85BR-1601-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1601 TO PS2-08-85BR-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3875 | PS2-08-85BR-1602-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1601 TO PS2-08-85BR-1602 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3876 | PS2-08-85BT-0001-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-85BT-0001 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3877 | PS2-08-85BT-0002-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-85BT-0002 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3878 | PS2-08-85BT-0003-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-85BT-0003 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3879 | PS2-08-85BT-0004-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0005 TO PS2-08-85BT-0004 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3880 | PS2-08-85BT-0005-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0005 TO PS2-08-85BT-0005 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3881 | PS2-08-85BT-0006-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0005 TO PS2-08-85BT-0006 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3882 | PS2-08-85BT-0007-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0005 TO PS2-08-85BT-0007 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3883 | PS2-08-85BT-0008-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-85BT-0008 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3884 | PS2-08-85BT-0009-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-85BT-0009 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3885 | PS2-08-85BT-0010-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-85BT-0010 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3886 | PS2-08-85BT-0011-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-85BT-0011 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3887 | PS2-08-85BT-0012-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-85BT-0012 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3888 | PS2-08-85BT-0013-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0002 TO PS2-08-85BT-0013 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3889 | PS2-08-85BT-0014-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0002 TO PS2-08-85BT-0014 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3890 | PS2-08-85BT-0015-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0002 TO PS2-08-85BT-0015 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3891 | PS2-08-85BT-0016-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0002 TO PS2-08-85BT-0016 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3892 | PS2-08-85BT-0017-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1501 TO PS2-08-85BT-0017 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3893 | PS2-08-85BT-0017-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-85BT-0017 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3894 | PS2-08-85BT-0018-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-85BT-0018 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3895 | PS2-08-85BT-0019-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1501 TO PS2-08-85BT-0019 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3896 | PS2-08-85BT-0020-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-85BT-0020 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3897 | PS2-08-85BT-0023-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-85BT-0023 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3898 | PS2-08-85BT-0024-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-85BT-0024 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00171-3899 | PS2-08-85BT-0025-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-85BT-0025 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3900 | PS2-08-85BT-1201-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1201 TO PS2-08-85BT-1201 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3901 | PS2-08-85BT-1202-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1201 TO PS2-08-85BT-1202 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3902 | PS2-08-85BT-1202-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-85BT-1202 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3903 | PS2-08-85BT-1203-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1201 TO PS2-08-85BT-1203 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3904 | PS2-08-85BT-1501-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1501 TO PS2-08-85BT-1501 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3905 | PS2-08-85BT-1501-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-85BT-1501 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3906 | PS2-08-85BT-1601-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1601 TO PS2-08-85BT-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3907 | PS2-08-85BT-1601-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1601 TO PS2-08-11CB-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3908 | PS2-08-85BT-1602-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1601 TO PS2-08-85BT-1602 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3909 | PS2-08-85BT-1602-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1602 TO PS2-08-11CB-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3910 | PS2-08-85BT-1603-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1601 TO PS2-08-85BT-1603 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3911 | PS2-08-85BT-1604-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1601 TO PS2-08-85BT-1604 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3912 | PS2-08-85BT-1605-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1601 TO PS2-08-85BT-1605 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3913 | PS2-08-85CP-1201-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-85CP-1201 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3914 | PS2-08-85CP-1202-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-85CP-1202 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3915 | PS2-08-85CP-1501-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-85CP-1501 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3916 | PS2-08-85CP-1601-CA01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1601 TO PS2-08-85CP-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3917 | PS2-08-85DC-0001-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0001 TO PS2-08-85DC-0001 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3918 | PS2-08-85DC-0002-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0002 TO PS2-08-85DC-0002 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3919 | PS2-08-85DC-0003-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0003 TO PS2-08-85DC-0003 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3920 | PS2-08-85DC-0004-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0004 TO PS2-08-85DC-0004 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3921 | PS2-08-85DC-0005-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0005 TO PS2-08-85DC-0005 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3922 | PS2-08-85DC-0006-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0006 TO PS2-08-85DC-0006 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3923 | PS2-08-85DC-0007-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0008 TO PS2-08-85DC-0007 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3924 | PS2-08-85DC-0008-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0010 TO PS2-08-85DC-0008 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3925 | PS2-08-85DC-0009-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0008 TO PS2-08-85DC-0009 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3926 | PS2-08-85DC-0010-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0009 TO PS2-08-85DC-0010 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3927 | PS2-08-85DC-0011-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0011 TO PS2-08-85DC-0011 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3928 | PS2-08-85DC-0012-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0012 TO PS2-08-85DC-0012 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3929 | PS2-08-85DC-0013-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0014 TO PS2-08-85DC-0013 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3930 | PS2-08-85DC-0014-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0013 TO PS2-08-85DC-0014 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3931 | PS2-08-85DC-0015-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0015 TO PS2-08-85DC-0015 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3932 | PS2-08-85DC-0016-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0016 TO PS2-08-85DC-0016 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3933 | PS2-08-85DC-0017-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0017 TO PS2-08-85DC-0017 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3934 | PS2-08-85DC-0018-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0018 TO PS2-08-85DC-0018 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3935 | PS2-08-85DC-0019-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0019 TO PS2-08-85DC-0019 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3936 | PS2-08-85DC-0020-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0020 TO PS2-08-85DC-0020 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3937 | PS2-08-85DC-0021-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0001 TO PS2-08-85DC-0021 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3938 | PS2-08-85DC-0022-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0020 TO PS2-08-85DC-0022 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3939 | PS2-08-85DC-0023-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0009 TO PS2-08-85DC-0023 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3940 | PS2-08-85DC-0024-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0025 TO PS2-08-85DC-0024 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3941 | PS2-08-85DC-0025-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0025 TO PS2-08-85DC-0025 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3942 | PS2-08-85DC-1201-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1202 TO PS2-08-85DC-1201 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3943 | PS2-08-85DC-1202-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1201 TO PS2-08-85DC-1202 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3944 | PS2-08-85DC-1203-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1203 TO PS2-08-85DC-1203 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3945 | PS2-08-85DC-1501-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1501 TO PS2-08-85DC-1501 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3946 | PS2-08-85DC-1601-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1601 TO PS2-08-85DC-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3947 | PS2-08-85DC-1602-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1602 TO PS2-08-85DC-1602 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3948 | PS2-08-85DC-1603-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1603 TO PS2-08-85DC-1603 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3949 | PS2-08-85DC-1604-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1604 TO PS2-08-85DC-1604 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3950 | PS2-08-85DC-1605-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1605 TO PS2-08-85DC-1605 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3951 | PS2-08-85ML-0001-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0017 TO PS2-08-85ML-0001 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3952 | PS2-08-85ML-1201-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1202 TO PS2-08-85ML-1201 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3953 | PS2-08-85ML-1501-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1501 TO PS2-08-85ML-1501 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3954 | PS2-08-85ML-1601-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1601 TO PS2-08-85ML-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3955 | PS2-08-85ML-1602-CN01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1602 TO PS2-08-85ML-1602 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3956 | PS2-08-85PB-0001-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0017 TO PS2-08-85PB-0001 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3957 | PS2-08-85PB-1201-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1202 TO PS2-08-85PB-1201 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3958 | PS2-08-85PB-1501-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1501 TO PS2-08-85PB-1501 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3959 | PS2-08-85PB-1502-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1501 TO PS2-08-85PB-1502 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3960 | PS2-08-85PB-1601-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1601 TO PS2-08-85PB-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3961 | PS2-08-85PB-1602-CJ01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1602 TO PS2-08-85PB-1602 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-3962 | PS2-82-MGV-0003-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0019 TO PS2-82-MGV-0003 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00171-9459 | PS2-08-13CB-1001-CC01 | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-13CB-1001 | EITS | UG-MID-65-SSF1-179320 | PS2-08-93 - Telecom Monitoring System |  |  |  | Construction not yet started |  | #N/A
T-00173-0352 | PS2-08-83SP-1001 | CIX11 - Fiber Optic Patch Panel | PCOM - Precommissioning | T - Telecom | Rack Fiber Connection Module | EITS | UT-MID-60-SSF1-178302 | PS2-08-83 - Perimeter & Pipeline intrusion detection system |  |  |  | Construction not yet started |  | #N/A
T-00173-0353 | PS2-08-83SP-0001 | CIX11 - Fiber Optic Patch Panel | PCOM - Precommissioning | T - Telecom | OUTDOOR SPLICE ENCLOSURE | EITS | UT-MID-60-SSF1-178302 | PS2-08-83 - Perimeter & Pipeline intrusion detection system |  |  |  | Construction not yet started |  | #N/A
T-00174-0008 | PS2-08-15CB-1001 | CIX12 - System Cabinet | PCOM - Precommissioning | T - Telecom | Cabinet | EITS | UT-MID-60-SSF1-171502 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00174-0131 | PS2-08-35CB-1001 | CIX12 - System Cabinet | PCOM - Precommissioning | T - Telecom | OTN cabinet | EITS | UT-MID-60-SSF1-173502 | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00174-0135 | PS2-08-14CB-1601 | CIX12 - System Cabinet | PCOM - Precommissioning | T - Telecom | Cabinet | EITS | UT-MID-60-SSF1-171402 | PS2-08-14 - Industrial Data Network (SII SP1) |  |  |  | Construction not yet started |  | #N/A
T-00174-0232 | PS2-08-13CB-1601 | CIX12 - System Cabinet | PCOM - Precommissioning | T - Telecom | Cabinet | EITS | UT-MID-60-SSF1-171302 | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00174-0233 | PS2-08-13CB-1001 | CIX12 - System Cabinet | PCOM - Precommissioning | T - Telecom | Cabinet | EITS | UT-MID-60-SSF1-171302 | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00174-0288 | PS2-08-11CB-1001 | CIX12 - System Cabinet | PCOM - Precommissioning | T - Telecom | Telecom cabinet | EITS | UT-MID-60-SSF1-171102 | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00174-0289 | PS2-08-11CB-1201 | CIX12 - System Cabinet | PCOM - Precommissioning | T - Telecom | Telecom cabinet | EITS | UT-MID-60-SSF1-171102 | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00174-0290 | PS2-08-11CB-1501 | CIX12 - System Cabinet | PCOM - Precommissioning | T - Telecom | Telecom cabinet | EITS | UT-MID-60-SSF1-171102 | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0184
T-00174-0291 | PS2-08-11CB-1601 | CIX12 - System Cabinet | PCOM - Precommissioning | T - Telecom | Telecom cabinet | EITS | UT-MID-60-SSF1-171102 | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00176-0002 | PS2-08-61SN-0001 | CIX14 - Meteorological Sensor / Cable Equipment / Display | PCOM - Precommissioning | T - Telecom | PRESSURE SENSOR | EITS | UT-MID-60-SSF1-176102 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00176-0003 | PS2-08-61SN-0002 | CIX14 - Meteorological Sensor / Cable Equipment / Display | PCOM - Precommissioning | T - Telecom | BAROMETER SENSOR | EITS | UT-MID-60-SSF1-176102 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00176-0004 | PS2-08-61SN-0003 | CIX14 - Meteorological Sensor / Cable Equipment / Display | PCOM - Precommissioning | T - Telecom | TEMPERATURE / HUMIDITY SENSOR | EITS | UT-MID-60-SSF1-176102 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00176-0005 | PS2-08-61SN-0004 | CIX14 - Meteorological Sensor / Cable Equipment / Display | PCOM - Precommissioning | T - Telecom | PRECIPITATION SENSOR | EITS | UT-MID-60-SSF1-176102 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00176-0006 | PS2-08-61SN-0005 | CIX14 - Meteorological Sensor / Cable Equipment / Display | PCOM - Precommissioning | T - Telecom | CLOUD SENSOR | EITS | UT-MID-60-SSF1-176102 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00176-0007 | PS2-08-61SN-0901 | CIX14 - Meteorological Sensor / Cable Equipment / Display | PCOM - Precommissioning | T - Telecom | WIND SENSOR | EITS | UT-MID-60-SSF1-176102 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00176-0040 | PS2-08-61BT-0003 | CIX14 - Meteorological Sensor / Cable Equipment / Display | PCOM - Precommissioning | T - Telecom | SOLAR RADIATION SHIELD | EITS | UT-MID-60-SSF1-176102 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00180-0006 | PS2-08-55TV-1201 | CIX18 - Monitor/Screen/Projector | PCOM - Precommissioning | T - Telecom | TV set | EITS | UT-MID-60-SSF1-170302 | PS2-08-55 - Videoconference |  |  |  | Construction not yet started |  | #N/A
T-00180-0147 | PS2-08-86DY-1201A | CIX18 - Monitor/Screen/Projector | PCOM - Precommissioning | T - Telecom | DISPLAY 24" | EITS | UT-MID-60-SSF1-178602 | PS2-08-86 - Integrated Security Management System |  |  |  | Construction not yet started |  | #N/A
T-00180-0148 | PS2-08-86DY-1201B | CIX18 - Monitor/Screen/Projector | PCOM - Precommissioning | T - Telecom | DISPLAY 24" | EITS | UT-MID-60-SSF1-178602 | PS2-08-86 - Integrated Security Management System |  |  |  | Construction not yet started |  | #N/A
T-00180-0149 | PS2-08-86DY-1501A | CIX18 - Monitor/Screen/Projector | PCOM - Precommissioning | T - Telecom | DISPLAY 24" | EITS | UT-MID-60-SSF1-178602 | PS2-08-86 - Integrated Security Management System |  |  |  | Construction not yet started |  | #N/A
T-00180-0150 | PS2-08-86DY-1501B | CIX18 - Monitor/Screen/Projector | PCOM - Precommissioning | T - Telecom | DISPLAY 24" | EITS | UT-MID-60-SSF1-178602 | PS2-08-86 - Integrated Security Management System |  |  |  | Construction not yet started |  | #N/A
T-00180-0151 | PS2-08-86DY-1501C | CIX18 - Monitor/Screen/Projector | PCOM - Precommissioning | T - Telecom | DISPLAY 24" | EITS | UT-MID-60-SSF1-178602 | PS2-08-86 - Integrated Security Management System |  |  |  | Construction not yet started |  | #N/A
T-00180-0152 | PS2-08-86DY-1502A | CIX18 - Monitor/Screen/Projector | PCOM - Precommissioning | T - Telecom | DISPLAY 24" | EITS | UT-MID-60-SSF1-178602 | PS2-08-86 - Integrated Security Management System |  |  |  | Construction not yet started |  | #N/A
T-00180-0153 | PS2-08-86DY-1502B | CIX18 - Monitor/Screen/Projector | PCOM - Precommissioning | T - Telecom | DISPLAY 24" | EITS | UT-MID-60-SSF1-178602 | PS2-08-86 - Integrated Security Management System |  |  |  | Construction not yet started |  | #N/A
T-00180-0154 | PS2-08-86DY-1502C | CIX18 - Monitor/Screen/Projector | PCOM - Precommissioning | T - Telecom | DISPLAY 24" | EITS | UT-MID-60-SSF1-178602 | PS2-08-86 - Integrated Security Management System |  |  |  | Construction not yet started |  | #N/A
T-00182-0277 | PS2-08-52CM-1014 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | INDOOR DOME CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0278 | PS2-08-52CM-0034 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | SAFE AREA PTZ CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0279 | PS2-08-52CM-1001 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | OUTDOOR DUAL DOME CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0280 | PS2-08-52CM-1002 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | OUTDOOR DOME CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0281 | PS2-08-52CM-0078 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | THERMAL CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0282 | PS2-08-52CM-0033 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | SAFE AREA PTZ CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0283 | PS2-08-52CM-1016 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | INDOOR DOME CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0284 | PS2-08-52CM-0073 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | THERMAL CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0285 | PS2-08-52CM-1013 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | INDOOR DOME CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0286 | PS2-08-52CM-0001 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | FIXED OPTICAL CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0287 | PS2-08-52CM-1004 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | OUTDOOR DOME CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0288 | PS2-08-52TK-0034 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | WATER TANK 23L | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0289 | PS2-08-52CM-0131 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | PROCESS PTZ CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0290 | PS2-08-52TK-0931 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | WATER TANK 23L | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0291 | PS2-08-52CM-0077 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | THERMAL CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0292 | PS2-08-52CM-0002 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | FIXED OPTICAL CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0293 | PS2-08-52CM-0032 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | SAFE AREA PTZ CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0294 | PS2-08-52CM-1012 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | INDOOR DOME CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0295 | PS2-08-52CM-1501 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | OUTDOOR DOME CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0296 | PS2-08-52CM-0134 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | PROCESS PTZ CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0297 | PS2-08-52CM-0031 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | PANORAMIC CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0298 | PS2-08-52TK-0134 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | WATER TANK 23L | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0299 | PS2-08-52CM-1011 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | INDOOR DOME CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0300 | PS2-08-52CM-0133 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | PROCESS PTZ CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0301 | PS2-08-52CM-1201 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | OUTDOOR DOME CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0302 | PS2-08-52CM-0072 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | THERMAL CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0303 | PS2-08-52TK-0033 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | WATER TANK 23L | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0304 | PS2-08-52CM-0132 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | PROCESS PTZ CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0305 | PS2-08-52CM-0075 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | THERMAL CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0306 | PS2-08-52TK-0131 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | WATER TANK 23L | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0307 | PS2-08-52CM-1015 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | INDOOR DOME CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0308 | PS2-08-52CM-0074 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | THERMAL CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0309 | PS2-08-52TK-0032 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | WATER TANK 23L | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0310 | PS2-08-52CM-1601 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | OUTDOOR DOME CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0311 | PS2-08-52CM-0076 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | THERMAL CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0312 | PS2-08-52TK-0133 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | WATER TANK 23L | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0313 | PS2-08-52CM-1003 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | OUTDOOR DOME CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0314 | PS2-08-52TK-0132 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | WATER TANK 23L | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0315 | PS2-08-52CM-0003 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | FIXED OPTICAL CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0316 | PS2-08-52CM-0071 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | THERMAL CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00182-0317 | PS2-08-52CM-0931 | CIX20 - CCTV Camera and housing | PCOM - Precommissioning | T - Telecom | SAFE AREA PTZ CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00183-0029 | PS2-08-23AN-0001 | CIX21 - Radio Antenna | PCOM - Precommissioning | T - Telecom | Antenna | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00183-0030 | PS2-08-23AN-0002 | CIX21 - Radio Antenna | PCOM - Precommissioning | T - Telecom | Antenna | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00183-0031 | PS2-08-23AN-0003 | CIX21 - Radio Antenna | PCOM - Precommissioning | T - Telecom | Yagi Donor Antenna | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00183-0032 | PS2-08-23AN-0901 | CIX21 - Radio Antenna | PCOM - Precommissioning | T - Telecom | Antenna | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00183-0033 | PS2-08-23AN-1001 | CIX21 - Radio Antenna | PCOM - Precommissioning | T - Telecom | Flat Panel Antenna | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00183-0034 | PS2-08-23AN-1002 | CIX21 - Radio Antenna | PCOM - Precommissioning | T - Telecom | Flat Panel Antenna | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00183-0035 | PS2-08-23AN-1201 | CIX21 - Radio Antenna | PCOM - Precommissioning | T - Telecom | Flat Panel Antenna | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00183-0036 | PS2-08-23AN-1601 | CIX21 - Radio Antenna | PCOM - Precommissioning | T - Telecom | Flat Panel Antenna | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00183-0242 | PS2-08-34AN-0001 | CIX21 - Radio Antenna | PCOM - Precommissioning | T - Telecom | Marine IRIDIUM Antenna | EITS | UT-MID-60-SSF1-173402 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00183-0243 | PS2-08-34AN-0002 | CIX21 - Radio Antenna | PCOM - Precommissioning | T - Telecom | Marine IRIDIUM Antenna | EITS | UT-MID-60-SSF1-173402 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00185-0015 | PS2-08-23SL-1001 | CIX23 - Radio Antenna Feeder Distribution | PCOM - Precommissioning | T - Telecom | Splitter (RF) | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00185-0016 | PS2-08-23SL-1601 | CIX23 - Radio Antenna Feeder Distribution | PCOM - Precommissioning | T - Telecom | Splitter (RF) | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00187-0024 | PS2-08-34DS-1201 | CIX25 - Radio Remote Control Unit / Station / Console | PCOM - Precommissioning | T - Telecom | Docking station | EITS | UT-MID-60-SSF1-173402 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00187-0025 | PS2-08-34DS-1211 | CIX25 - Radio Remote Control Unit / Station / Console | PCOM - Precommissioning | T - Telecom | BIAS Box | EITS | UT-MID-60-SSF1-173402 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00187-0026 | PS2-08-34DS-1501 | CIX25 - Radio Remote Control Unit / Station / Console | PCOM - Precommissioning | T - Telecom | Docking station | EITS | UT-MID-60-SSF1-173402 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00187-0027 | PS2-08-34DS-1511 | CIX25 - Radio Remote Control Unit / Station / Console | PCOM - Precommissioning | T - Telecom | BIAS Box | EITS | UT-MID-60-SSF1-173402 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00188-0007 | PS2-08-23BS-1201 | CIX26 - Radio Base Station | PCOM - Precommissioning | T - Telecom | Fixed Base station | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00188-0008 | PS2-08-23BS-1501 | CIX26 - Radio Base Station | PCOM - Precommissioning | T - Telecom | Fixed Base station | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00189-0063 | PS2-08-23CH-1601 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | Multiway Charger | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00189-0064 | PS2-08-23HP-3001 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | ATEX handheld portable Radio | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00189-0065 | PS2-08-23HP-3002 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | ATEX handheld portable Radio | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00189-0066 | PS2-08-23HP-3003 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | ATEX handheld portable Radio | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00189-0067 | PS2-08-23HP-3004 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | ATEX handheld portable Radio | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00189-0068 | PS2-08-23HP-3005 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | ATEX handheld portable Radio | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00189-0069 | PS2-08-23HP-3006 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | ATEX handheld portable Radio | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00189-0070 | PS2-08-23HP-3007 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | ATEX handheld portable Radio | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00189-0071 | PS2-08-23HP-3008 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | ATEX handheld portable Radio | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00189-0072 | PS2-08-23HP-3009 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | ATEX handheld portable Radio | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00189-0073 | PS2-08-23HP-3010 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | ATEX handheld portable Radio | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00189-0074 | PS2-08-23HP-3011 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | ATEX handheld portable Radio | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00189-0075 | PS2-08-23HP-3012 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | ATEX handheld portable Radio | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00189-0076 | PS2-08-23HP-3013 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | ATEX handheld portable Radio | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00189-0077 | PS2-08-23HP-3014 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | ATEX handheld portable Radio | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00189-0258 | PS2-08-34MB-3001 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | SATPHONE | EITS | UT-MID-60-SSF1-173402 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00189-0259 | PS2-08-34MB-3002 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | SATPHONE | EITS | UT-MID-60-SSF1-173402 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00189-0313 | PS2-08-85DS-1201 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | Muster Tablet Docking Station | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00189-0314 | PS2-08-85MT-1201 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | Muster Tablet - 1 | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00189-0315 | PS2-08-85MT-1202 | CIX27 - Radio Handheld, Pager and Battery Charger | PCOM - Precommissioning | T - Telecom | Muster Tablet - 2 | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00190-0002 | PS2-08-92MT-0001 | CIX28 - Radio Mast / Tower | PCOM - Precommissioning | T - Telecom | Telecom Mast lattice structure, 4legs / Square base, - 10.5m high (AGL) | EITS | UT-MID-60-SSF1-179202 | PS2-08-92 - Telecom Mast |  |  |  | Construction not yet started |  | #N/A
T-00200-0682 | PS2-08-71SK-1001A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0683 | PS2-08-71SK-1001B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0684 | PS2-08-71SK-1002A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0685 | PS2-08-71SK-1002B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0686 | PS2-08-71SK-1003A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0687 | PS2-08-71SK-1003B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0688 | PS2-08-71SK-1004A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0689 | PS2-08-71SK-1004B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0690 | PS2-08-71SK-1005A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0691 | PS2-08-71SK-1005B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0692 | PS2-08-71SK-1006A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0693 | PS2-08-71SK-1006B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0694 | PS2-08-71SK-1201 | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Single RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0695 | PS2-08-71SK-1202 | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Single RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0696 | PS2-08-71SK-1203A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0697 | PS2-08-71SK-1203B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0698 | PS2-08-71SK-1204A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0699 | PS2-08-71SK-1204B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0700 | PS2-08-71SK-1205A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0701 | PS2-08-71SK-1205B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0702 | PS2-08-71SK-1206A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0703 | PS2-08-71SK-1206B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0704 | PS2-08-71SK-1207A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0705 | PS2-08-71SK-1207B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0706 | PS2-08-71SK-1208A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0707 | PS2-08-71SK-1208B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0708 | PS2-08-71SK-1209A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0709 | PS2-08-71SK-1209B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0710 | PS2-08-71SK-1210 | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Single RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0711 | PS2-08-71SK-1211A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Quad RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0712 | PS2-08-71SK-1211B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Quad RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0713 | PS2-08-71SK-1211C | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Quad RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0714 | PS2-08-71SK-1211D | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Quad RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0715 | PS2-08-71SK-1212A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0716 | PS2-08-71SK-1212B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0717 | PS2-08-71SK-1213A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0718 | PS2-08-71SK-1213B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0719 | PS2-08-71SK-1214A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0720 | PS2-08-71SK-1214B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0721 | PS2-08-71SK-1215 | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Single RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0722 | PS2-08-71SK-1216 | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Single RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0723 | PS2-08-71SK-1217A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Quad RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0724 | PS2-08-71SK-1217B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Quad RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0725 | PS2-08-71SK-1217C | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Quad RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0726 | PS2-08-71SK-1217D | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Quad RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0727 | PS2-08-71SK-1501A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0728 | PS2-08-71SK-1501B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0729 | PS2-08-71SK-1502A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0730 | PS2-08-71SK-1502B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0731 | PS2-08-71SK-1503A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0732 | PS2-08-71SK-1503B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0733 | PS2-08-71SK-1504 | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Single RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0734 | PS2-08-71SK-1505 | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Single RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0735 | PS2-08-71SK-1506A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0736 | PS2-08-71SK-1506B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0737 | PS2-08-71SK-1507 | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Single RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0738 | PS2-08-71SK-1601A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0739 | PS2-08-71SK-1601B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0740 | PS2-08-71SK-1602A | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0741 | PS2-08-71SK-1602B | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Dual RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0742 | PS2-08-71SK-1603 | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Single RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0743 | PS2-08-71SK-1604 | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Single RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00200-0744 | PS2-08-71SK-1605 | CIX38 - RJ45 Socket | PCOM - Precommissioning | T - Telecom | Single RJ45 socket | EITS | UT-MID-60-SSF1-177102 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00202-0080 | PS2-08-86PR-1201 | CIX40 - PC workstation | PCOM - Precommissioning | T - Telecom | PAPER PRINTER | EITS | UT-MID-60-SSF1-178602 | PS2-08-86 - Integrated Security Management System |  |  |  | Construction not yet started |  | #N/A
T-00202-0081 | PS2-08-86WK-1201 | CIX40 - PC workstation | PCOM - Precommissioning | T - Telecom | WORKSTATION | EITS | UT-MID-60-SSF1-178602 | PS2-08-86 - Integrated Security Management System |  |  |  | Construction not yet started |  | #N/A
T-00202-0082 | PS2-08-86WK-1501 | CIX40 - PC workstation | PCOM - Precommissioning | T - Telecom | WORKSTATION | EITS | UT-MID-60-SSF1-178602 | PS2-08-86 - Integrated Security Management System |  |  |  | Construction not yet started |  | #N/A
T-00202-0083 | PS2-08-86WK-1502 | CIX40 - PC workstation | PCOM - Precommissioning | T - Telecom | WORKSTATION | EITS | UT-MID-60-SSF1-178602 | PS2-08-86 - Integrated Security Management System |  |  |  | Construction not yet started |  | #N/A
T-00202-0101 | PS2-04-OWS-0001 | CIX40 - PC workstation | PCOM - Precommissioning | T - Telecom | PCS Operator Workstation (65OWS1) | EITS |  | PS2-04-01 - Office Building PCS System |  |  |  | Construction not yet started |  | #N/A
T-00203-0004 | PS2-08-81DS-1501 | CIX41 - Server | PCOM - Precommissioning | T - Telecom | Data Collector Station | EITS | UT-MID-60-SSF1-178102 | PS2-08-81 - Guard tour |  |  |  | Construction not yet started |  | #N/A
T-00203-0005 | PS2-08-81DS-1502 | CIX41 - Server | PCOM - Precommissioning | T - Telecom | Data Collector Station | EITS | UT-MID-60-SSF1-178102 | PS2-08-81 - Guard tour |  |  |  | Construction not yet started |  | #N/A
T-00204-0007 | PS2-04-PR-0001 | CIX42 - Data Network Equipment | PCOM - Precommissioning | T - Telecom | Alarm Report Printer | EITS |  | PS2-04-01 - Office Building PCS System |  |  |  | Construction not yet started |  | #N/A
T-00206-0001 | PS2-08-61BT-0001 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | JUNCTION BOX | EITS | UT-MID-60-SSF1-176102 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00206-0002 | PS2-08-61BT-0002 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | JUNCTION BOX | EITS | UT-MID-60-SSF1-176102 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00206-0003 | PS2-08-61BT-0901 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | JUNCTION BOX | EITS | UT-MID-60-SSF1-176102 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00206-0459 | PS2-08-01BT-1501 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Building LS junction box with muting arrangement | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00206-0460 | PS2-08-01BT-0002 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | OCU junction box #2 at Primary muster point | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00206-0461 | PS2-08-01BT-1503 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | ACCESS UNIT junction box | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00206-0462 | PS2-08-01BT-1602 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Building LS junction box without muting arrangement | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00206-0463 | PS2-08-01BT-1502 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Building LS junction box with muting arrangement | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00206-0464 | PS2-08-01BT-1203 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | ACCESS UNIT junction box | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00206-0465 | PS2-08-01BT-1202 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Building LS junction box with muting arrangement | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00206-0466 | PS2-08-01BT-1601 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Building LS junction box without muting arrangement | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00206-0467 | PS2-08-01BT-0003 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | OCU junction box #1 at Secondary muster point | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00206-0468 | PS2-08-01BT-1201 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Building LS junction box with muting arrangement | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00206-0469 | PS2-08-01BT-0001 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | OCU junction box #1 at Primary muster point | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00206-0470 | PS2-08-01BT-0004 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | OCU junction box #2 at Secondary muster point | EITS | UT-MID-60-SSF1-170102 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00206-0499 | PS2-08-52BT-0132 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | JUNCTION BOX PTZ CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00206-0500 | PS2-08-52BT-0131 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | JUNCTION BOX PTZ CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0104
T-00206-0501 | PS2-08-52BT-0133 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | JUNCTION BOX PTZ CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00206-0502 | PS2-08-52BT-0931 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | JUNCTION BOX PTZ CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00206-0503 | PS2-08-52BT-0134 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | JUNCTION BOX PTZ CAMERA | EITS | UT-MID-60-SSF1-175202 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00206-0700 | PS2-08-12BT-0101 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00206-0701 | PS2-08-12BT-0102 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00206-0702 | PS2-08-12BT-0103 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started | column mounted JB | #N/A
T-00206-0703 | PS2-08-12BT-0104 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started | column mounted JB | CPP-RFI-65-33/1-05-0080
T-00206-0704 | PS2-08-12BT-0105 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | ATEX Junction Box | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00206-0705 | PS2-08-12BT-0106 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00206-0706 | PS2-08-12BT-0107 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00206-0863 | PS2-08-15CP-0001 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Control Panel | EITS | UT-MID-60-SSF1-171502 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0193
T-00206-0864 | PS2-08-15CP-0002 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Control Panel | EITS | UT-MID-60-SSF1-171502 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0193
T-00206-0865 | PS2-08-15CP-0003 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Control Panel | EITS | UT-MID-60-SSF1-171502 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0052
T-00206-0866 | PS2-08-15CP-0004 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Control Panel | EITS | UT-MID-60-SSF1-171502 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0052
T-00206-0867 | PS2-08-15CP-0005 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Control Panel | EITS | UT-MID-60-SSF1-171502 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00206-0868 | PS2-08-15CP-0006 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Control Panel | EITS | UT-MID-60-SSF1-171502 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00206-0869 | PS2-08-15CP-0007 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Control Panel | EITS | UT-MID-60-SSF1-171502 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0087_01
T-00206-0870 | PS2-08-15CP-0008 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Control Panel | EITS | UT-MID-60-SSF1-171502 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0087_01
T-00206-0965 | PS2-08-85BT-0021 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | WiFi Access Point A - Junction Box | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0966 | PS2-08-85BT-0022 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | WiFi Access Point B - Junction Box | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0967 | PS2-08-85BT-0023 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Outdoor Junction Box - 23 | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00206-0968 | PS2-08-85BT-0024 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Outdoor Junction Box - 24 | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00206-0969 | PS2-08-85BT-1001 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box - ITR Access | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0970 | PS2-08-85BT-1002 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box - ITR Emergency Escape | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0971 | PS2-08-85BT-1004 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box - ED Room Emergency Escape | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0972 | PS2-08-85BT-1005 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box - Battery Room | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00206-0973 | PS2-08-85BT-1201 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box - Main Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0974 | PS2-08-85BT-1202 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box -Emergency Escape | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0975 | PS2-08-85BT-1203 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box - Emergency Escape | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0976 | PS2-08-85BT-1501 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box - GH Access | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0977 | PS2-08-85BT-1601 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box - Warehouse Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0978 | PS2-08-85BT-1602 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box - Workshop Emergency Escape | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0979 | PS2-08-85BT-1603 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box - Workshop Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0980 | PS2-08-85BT-1604 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box 1 - Workshop Emergency Escape | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0981 | PS2-08-85BT-1605 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Junction Box 2 - Workshop Emergency Escape | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0982 | PS2-08-85CP-0021 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Outdoor Muster Enclosure A | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00206-0983 | PS2-08-85CP-0022 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Outdoor Muster Enclosure B | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00206-0984 | PS2-08-85CP-1001 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Controller Enclosure | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0985 | PS2-08-85CP-1201 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Controller Enclosure A | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0986 | PS2-08-85CP-1202 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Controller Enclosure B | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0987 | PS2-08-85CP-1501 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Controller Enclosure A | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00206-0988 | PS2-08-85CP-1601 | CIX44 - Telecom Junction Box | PCOM - Precommissioning | T - Telecom | Controller Enclosure | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1258 | PS2-08-81RF-0001 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | DALLAS Check point | EITS | UT-MID-60-SSF1-178102 | PS2-08-81 - Guard tour |  |  |  | Construction not yet started |  | #N/A
T-00207-1259 | PS2-08-81RF-0002 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | DALLAS Check point | EITS | UT-MID-60-SSF1-178102 | PS2-08-81 - Guard tour |  |  |  | Construction not yet started |  | #N/A
T-00207-1260 | PS2-08-81RF-0003 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | DALLAS Check point | EITS | UT-MID-60-SSF1-178102 | PS2-08-81 - Guard tour |  |  |  | Construction not yet started |  | #N/A
T-00207-1261 | PS2-08-81RF-0004 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | DALLAS Check point | EITS | UT-MID-60-SSF1-178102 | PS2-08-81 - Guard tour |  |  |  | Construction not yet started |  | #N/A
T-00207-1262 | PS2-08-81RF-0005 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | DALLAS Check point | EITS | UT-MID-60-SSF1-178102 | PS2-08-81 - Guard tour |  |  |  | Construction not yet started |  | #N/A
T-00207-1263 | PS2-08-81RF-0006 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | DALLAS Check point | EITS | UT-MID-60-SSF1-178102 | PS2-08-81 - Guard tour |  |  |  | Construction not yet started |  | #N/A
T-00207-1264 | PS2-08-81RF-0007 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | DALLAS Check point | EITS | UT-MID-60-SSF1-178102 | PS2-08-81 - Guard tour |  |  |  | Construction not yet started |  | #N/A
T-00207-1445 | PS2-08-85BG-1201 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Emergency Break Glass - Main Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1446 | PS2-08-85BG-1601 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Emergency Break Glass - Warehouse Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1447 | PS2-08-85BG-1602 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Emergency Break Glass - Workshop Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1448 | PS2-08-85BR-0001 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Standard Badge Reader A - Primary Muster Point | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00207-1449 | PS2-08-85BR-0002 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Standard Badge Reader B - Primary Muster Point | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00207-1450 | PS2-08-85BR-0003 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Standard Badge Reader A - Secondary Muster Point | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1451 | PS2-08-85BR-0004 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Standard Badge Reader B - Secondary Muster Point | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1452 | PS2-08-85BR-0005 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Standard Badge Reader IN - Personnel Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1453 | PS2-08-85BR-0006 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Standard Badge Reader OUT - Personnel Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1454 | PS2-08-85BR-1001 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Biometric Badge Reader - ITR Access | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1455 | PS2-08-85BR-1002 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Biometric Badge Reader - ED Room Access | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1456 | PS2-08-85BR-1201 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Standard Badge Reader A - Safe Haven | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1457 | PS2-08-85BR-1202 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Standard Badge Reader B - Safe Haven | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1458 | PS2-08-85BR-1203 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Standard Badge Reader - Main Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1459 | PS2-08-85BR-1501 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Biometric Badge Reader - GH Access | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1460 | PS2-08-85BR-1601 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Standard Badge Reader - Warehouse Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1461 | PS2-08-85BR-1602 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Standard Badge Reader - Workshop Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1462 | PS2-08-85BT-1003 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Junction Box - ED Room Access | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1463 | PS2-08-85DC-1001 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door Contact 1 - ITR Access | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1464 | PS2-08-85DC-1002 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door Contact 2 - ITR Access | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1465 | PS2-08-85DC-1003 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door Contact - ITR Emergency Escape | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1466 | PS2-08-85DC-1004 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door Contact 1 - ED Room Access | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1467 | PS2-08-85DC-1005 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door Contact 2 - ED Room Access | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1468 | PS2-08-85DC-1006 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door Contact - ED Room Emergency Escape | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1469 | PS2-08-85DC-1007 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door Contact 1 - Battery Room Access | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1470 | PS2-08-85DC-1008 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door Contact 2 - Battery Room Access | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1471 | PS2-08-85DC-1201 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door Contact - Main Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1472 | PS2-08-85DC-1202 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door Contact - Emergency Escape | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1473 | PS2-08-85DC-1203 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door Contact - Emergency Escape | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1474 | PS2-08-85DC-1501 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door Contact 1 - GH Access | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1475 | PS2-08-85DC-1601 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door Contact - Warehouse Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1476 | PS2-08-85DC-1602 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door Contact - Warehouse Emergency Escape | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1477 | PS2-08-85DC-1603 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door Contact -Workshop Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1478 | PS2-08-85DC-1604 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door Contact 1 - Workshop Emergency Escape | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1479 | PS2-08-85DC-1605 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door Contact 1 - Workshop Emergency Escape | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1480 | PS2-08-85ML-1001 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Magnetic Lock Fail Secure - ITR Access | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1481 | PS2-08-85ML-1002 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Magnetic Lock Fail Secure - ED Room Access | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1482 | PS2-08-85ML-1201 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Magnetic Lock Fail Safe - Main Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1483 | PS2-08-85ML-1501 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Magnetic Lock Fail Secure - GH Access | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1484 | PS2-08-85ML-1601 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Magnetic Lock Fail Safe - Warehouse Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1485 | PS2-08-85ML-1602 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Magnetic Lock Fail Safe - Workshop Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1486 | PS2-08-85PB-1001 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door PushBar | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1487 | PS2-08-85PB-1002 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door PushBar | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1488 | PS2-08-85PB-1201 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Exit PushButton - Main Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1489 | PS2-08-85PB-1501 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Door PushBar | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1490 | PS2-08-85PB-1502 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Panic Button | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1491 | PS2-08-85PB-1601 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Exit PushButton - Warehouse Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00207-1492 | PS2-08-85PB-1602 | CIX45 - Access Control Device & Field enclosure | PCOM - Precommissioning | T - Telecom | Exit PushButton - Workshop Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00208-0505 | PS2-08-03AF-1201 | CIX46 - IP/Digital/ Analogue Phone | PCOM - Precommissioning | T - Telecom | Audio Conference Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00208-0506 | PS2-08-03TP-1001 | CIX46 - IP/Digital/ Analogue Phone | PCOM - Precommissioning | T - Telecom | IP Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00208-0507 | PS2-08-03TP-1002 | CIX46 - IP/Digital/ Analogue Phone | PCOM - Precommissioning | T - Telecom | IP Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00208-0508 | PS2-08-03TP-1201 | CIX46 - IP/Digital/ Analogue Phone | PCOM - Precommissioning | T - Telecom | IP Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00208-0509 | PS2-08-03TP-1202 | CIX46 - IP/Digital/ Analogue Phone | PCOM - Precommissioning | T - Telecom | IP Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00208-0510 | PS2-08-03TP-1203 | CIX46 - IP/Digital/ Analogue Phone | PCOM - Precommissioning | T - Telecom | IP Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00208-0511 | PS2-08-03TP-1204 | CIX46 - IP/Digital/ Analogue Phone | PCOM - Precommissioning | T - Telecom | IP Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00208-0512 | PS2-08-03TP-1205 | CIX46 - IP/Digital/ Analogue Phone | PCOM - Precommissioning | T - Telecom | IP Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00208-0513 | PS2-08-03TP-1206 | CIX46 - IP/Digital/ Analogue Phone | PCOM - Precommissioning | T - Telecom | IP Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00208-0514 | PS2-08-03TP-1207 | CIX46 - IP/Digital/ Analogue Phone | PCOM - Precommissioning | T - Telecom | IP Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00208-0515 | PS2-08-03TP-1208 | CIX46 - IP/Digital/ Analogue Phone | PCOM - Precommissioning | T - Telecom | IP Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00208-0516 | PS2-08-03TP-1209 | CIX46 - IP/Digital/ Analogue Phone | PCOM - Precommissioning | T - Telecom | IP Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00208-0517 | PS2-08-03TP-1501 | CIX46 - IP/Digital/ Analogue Phone | PCOM - Precommissioning | T - Telecom | IP Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00208-0518 | PS2-08-03TP-1601 | CIX46 - IP/Digital/ Analogue Phone | PCOM - Precommissioning | T - Telecom | IP Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00208-0519 | PS2-08-03TP-1602 | CIX46 - IP/Digital/ Analogue Phone | PCOM - Precommissioning | T - Telecom | IP Phone | EITS | UT-MID-60-SSF1-170302 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00208-0520 | PS2-08-55VF-1201 | CIX46 - IP/Digital/ Analogue Phone | PCOM - Precommissioning | T - Telecom | Video Conference Unit | EITS | UT-MID-60-SSF1-170302 | PS2-08-55 - Videoconference |  |  |  | Construction not yet started |  | #N/A
T-00225-0500 | PS2-06-IER-0001A | TPX00 - Miscellaneous electrical equipment | PCOM - Precommissioning | E - Electrical | Battery MCCB box A | EITS |  | PS2-06-01 - AC UPS - EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00225-0501 | PS2-06-IER-0001B | TPX00 - Miscellaneous electrical equipment | PCOM - Precommissioning | E - Electrical | Battery MCCB box B | EITS |  | PS2-06-01 - AC UPS - EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00227-0043 | PS2-61-ISR-0101 | TPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | Shunt Reactor | CPP AGI | UG-MID-65-SSF1-150257 | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  | Vendor Scope | Vendor Scope
T-00227-0044 | PS2-61-IU-0010 | TPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | LLHT Oil Transformer | CPP AGI | UG-MID-65-SSF1-150257 | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  | Vendor Scope | Vendor Scope | ETA- 15th JULY 2026
T-00227-0045 | PS2-61-IU-0011 | TPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | LLHT Oil Transformer | CPP AGI | UG-MID-65-SSF1-150257 | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  | Vendor Scope | Vendor Scope | Not in CPP-EITScope
T-00227-0046 | PS2-63-IV-0010 | TPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | Earthing Transformer | CPP AGI | UG-MID-65-SSF1-150257 | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  | Vendor Scope | Vendor Scope |  | #N/A
T-00227-0111 | PS2-61-IU-3100C | TPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | 33kV VSD Transformer | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  | Vendor Scope | Vendor Scope
T-00227-0121 | PS2-61-IU-3100A | TPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | VSD Transformer | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  | Vendor Scope | Vendor Scope
T-00227-0122 | PS2-61-IU-3100B | TPX02 - Power transformer | PCOM - Precommissioning | E - Electrical | VSD Transformer | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  | Vendor Scope | Vendor Scope
T-00228-0021 | PS2-61-IV-0001A | TPX03 - LV transformer | PCOM - Precommissioning | E - Electrical | Distribution Transformer | #N/A | UG-MID-65-SSF1-150257 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  | Vendor Scope | Vendor Scope
T-00228-0022 | PS2-61-IV-0001B | TPX03 - LV transformer | PCOM - Precommissioning | E - Electrical | Distribution Transformer | #N/A | UG-MID-65-SSF1-150257 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  | Vendor Scope | Vendor Scope
T-00228-0070 | PS2-79-IV-0001 | TPX03 - LV transformer | PCOM - Precommissioning | E - Electrical | Feeder to EHT Transformer / DB 1 | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  | Vendor Scope | Vendor Scope
T-00228-0071 | PS2-79-IV-0002 | TPX03 - LV transformer | PCOM - Precommissioning | E - Electrical | Feeder to EHT Transformer / DB 2 | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  | Vendor Scope | Vendor Scope
T-00228-0072 | PS2-79-IV-0003 | TPX03 - LV transformer | PCOM - Precommissioning | E - Electrical | Feeder to EHT Transformer / DB 3 | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  | Vendor Scope | Vendor Scope |  | #N/A
T-00228-0073 | PS2-79-IV-0004 | TPX03 - LV transformer | PCOM - Precommissioning | E - Electrical | Feeder to EHT Transformer / DB 4 | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  | Vendor Scope | Vendor Scope |  | #N/A
T-00228-0074 | PS2-79-IV-0005 | TPX03 - LV transformer | PCOM - Precommissioning | E - Electrical | Feeder to EHT Transformer / DB 5 | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  | Vendor Scope | Vendor Scope |  | #N/A
T-00229-0044 | PS2-61-IJ-0001 | TPX04 - HV switchboard | PCOM - Precommissioning | E - Electrical | MV Switchgear | EITS |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) | dwi, dwi | Closed | Closed | Closed |  | CPP-RFI-65-33/1-07-0215
T-00229-0045 | PS2-61-IJ-0010 | TPX04 - HV switchboard | PCOM - Precommissioning | E - Electrical | MV Switchgear | EITS |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) | dwi, dwi | Closed | Closed | Closed |  | CPP-RFI-65-33/1-07-0215
T-00229-0046 | PS2-61-IJ-0011 | TPX04 - HV switchboard | PCOM - Precommissioning | E - Electrical | MV Switchgear | EITS |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) | sari, indera | Closed | Closed | Closed |  | CPP-RFI-65-33/1-07-0215
T-00229-0090 | PS2-61-IJ-0001_busbar | TPX04 - HV switchboard | PCOM - Precommissioning | E - Electrical | MV Switchgear | EITS |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00230-0022 | PS2-61-IK-0001 | TPX05 - LV switchboard | PCOM - Precommissioning | E - Electrical | Main LV MCC SWGR | EITS |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) | sari, indera | Closed | Closed | Closed |  | CPP-RFI-65-33/1-07-0202
T-00232-0001 | PS2-79-BH-0001-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0010 TO PS2-79-BH-0001 | CPP AGI |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  | HV cable testing done, static test ITR closed | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0163
T-00232-0002 | PS2-79-BH-0001-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0010 TO PS2-79-BH-0001 | CPP AGI |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  | 250m cable pulled, Cable is coiled near Export pump CTS (one end), and near EITS area (other end), cable to be reached to cubicle | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0163
T-00232-0003 | PS2-79-BH-0001-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0010 TO PS2-79-BH-0001 | CPP AGI |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  | 250m cable pulled, Cable is coiled near Export pump CTS (one end), and near EITS area (other end), cable to be reached to cubicle | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0163
T-00232-0004 | PS2-79-BH-0002-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0011 TO PS2-79-BH-0002 | CPP AGI |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  | 240m cable pulled, Cable is coiled near Export pump CTS (one end), and near EITS area (other end), cable to be reached to cubicle | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0163
T-00232-0005 | PS2-79-BH-0002-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0011 TO PS2-79-BH-0002 | CPP AGI |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  | 240m cable pulled, Cable is coiled near Export pump CTS (one end), and near EITS area (other end), cable to be reached to cubicle | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0163
T-00232-0006 | PS2-79-BH-0002-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0011 TO PS2-79-BH-0002 | CPP AGI |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  | 240m cable pulled, Cable is coiled near Export pump CTS (one end), and near EITS area (other end), cable to be reached to cubicle | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0163
T-00232-0500 | PS2-25-DM-3100A-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-29 | CPP-RFI-65-33/1-07-145
T-00232-0501 | PS2-25-DM-3100A-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-26 | CPP-RFI-65-33/1-07-0209
T-00232-0502 | PS2-25-DM-3100A-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-29 | CPP-RFI-65-33/1-07-145
T-00232-0503 | PS2-25-DM-3100A-CH04 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-29 | CPP-RFI-65-33/1-07-145
T-00232-0504 | PS2-25-DM-3100A-CH05 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-29 | CPP-RFI-65-33/1-07-145
T-00232-0505 | PS2-25-DM-3100A-CH06 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-29 | CPP-RFI-65-33/1-07-145
T-00232-0506 | PS2-25-DM-3100B-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-06-26 | CPP-RFI-65-33/1-07-0209
T-00232-0507 | PS2-25-DM-3100B-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable laying and testing completed | Closed | Closed | 2026-05-29 | CPP-RFI-65-33/1-07-145
T-00232-0508 | PS2-25-DM-3100B-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable laying and testing completed | Closed | Closed | 2026-05-29 | CPP-RFI-65-33/1-07-145
T-00232-0509 | PS2-25-DM-3100B-CH04 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable laying and testing completed | Closed | Closed | 2026-05-29 | CPP-RFI-65-33/1-07-145
T-00232-0510 | PS2-25-DM-3100B-CH05 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable laying and testing completed | Closed | Closed | 2026-05-29 | CPP-RFI-65-33/1-07-145
T-00232-0511 | PS2-25-DM-3100B-CH06 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-04 | CPP-RFI-65-33/1-07-0219
T-00232-0512 | PS2-25-DM-3100C-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | Closed | Closed | 2026-05-29 | CPP-RFI-65-33/1-07-145
T-00232-0513 | PS2-25-DM-3100C-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | Closed | Closed | 2026-05-29 | CPP-RFI-65-33/1-07-145
T-00232-0514 | PS2-25-DM-3100C-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | Closed | Closed | 2026-05-29 | CPP-RFI-65-33/1-07-145
T-00232-0515 | PS2-25-DM-3100C-CH04 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-06-26 | CPP-RFI-65-33/1-07-0209
T-00232-0516 | PS2-25-DM-3100C-CH05 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | Closed | Closed | 2026-05-29 | CPP-RFI-65-33/1-07-145
T-00232-0517 | PS2-25-DM-3100C-CH06 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | Closed | Closed | 2026-06-26 | CPP-RFI-65-33/1-07-0209
T-00232-0518 | PS2-61-IDH-3100A-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-147
T-00232-0519 | PS2-61-IDH-3100A-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-147
T-00232-0520 | PS2-61-IDH-3100A-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-147
T-00232-0521 | PS2-61-IDH-3100A-CH04 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-147
T-00232-0522 | PS2-61-IDH-3100A-CH05 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-147
T-00232-0523 | PS2-61-IDH-3100A-CH06 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-147
T-00232-0524 | PS2-61-IDH-3100A-CH07 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-147
T-00232-0525 | PS2-61-IDH-3100A-CH08 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-147
T-00232-0526 | PS2-61-IDH-3100A-CH09 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-147
T-00232-0527 | PS2-61-IDH-3100A-CH10 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-147
T-00232-0528 | PS2-61-IDH-3100A-CH11 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-147
T-00232-0529 | PS2-61-IDH-3100A-CH12 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-147
T-00232-0530 | PS2-61-IDH-3100B-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-04 | CPP-RFI-65-33/1-07-0219
T-00232-0531 | PS2-61-IDH-3100B-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-146
T-00232-0532 | PS2-61-IDH-3100B-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-146
T-00232-0533 | PS2-61-IDH-3100B-CH04 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-146
T-00232-0534 | PS2-61-IDH-3100B-CH05 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-146
T-00232-0535 | PS2-61-IDH-3100B-CH06 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-04 | CPP-RFI-65-33/1-07-0219
T-00232-0536 | PS2-61-IDH-3100B-CH07 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-146
T-00232-0537 | PS2-61-IDH-3100B-CH08 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-146
T-00232-0538 | PS2-61-IDH-3100B-CH09 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-146
T-00232-0539 | PS2-61-IDH-3100B-CH10 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-146
T-00232-0540 | PS2-61-IDH-3100B-CH11 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-04 | CPP-RFI-65-33/1-07-0219
T-00232-0541 | PS2-61-IDH-3100B-CH12 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-146
T-00232-0542 | PS2-61-IDH-3100C-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | closed | Closed | 2026-05-26 | CPP-RFI-65-33/1-07-144
T-00232-0543 | PS2-61-IDH-3100C-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | closed | Closed | 2026-05-26 | CPP-RFI-65-33/1-07-144
T-00232-0544 | PS2-61-IDH-3100C-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | closed | Closed | 2026-05-26 | CPP-RFI-65-33/1-07-144
T-00232-0545 | PS2-61-IDH-3100C-CH04 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | closed | Closed | 2026-05-26 | CPP-RFI-65-33/1-07-144
T-00232-0546 | PS2-61-IDH-3100C-CH05 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | closed | Closed | 2026-05-26 | CPP-RFI-65-33/1-07-144
T-00232-0547 | PS2-61-IDH-3100C-CH06 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | closed | Closed | 2026-05-26 | CPP-RFI-65-33/1-07-144
T-00232-0548 | PS2-61-IDH-3100C-CH07 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | closed | Closed | 2026-05-26 | CPP-RFI-65-33/1-07-144
T-00232-0549 | PS2-61-IDH-3100C-CH08 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | closed | Closed | 2026-05-26 | CPP-RFI-65-33/1-07-144
T-00232-0550 | PS2-61-IDH-3100C-CH09 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | closed | Closed | 2026-05-26 | CPP-RFI-65-33/1-07-144
T-00232-0551 | PS2-61-IDH-3100C-CH10 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | closed | Closed | 2026-05-26 | CPP-RFI-65-33/1-07-144
T-00232-0552 | PS2-61-IDH-3100C-CH11 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | closed | Closed | 2026-05-26 | CPP-RFI-65-33/1-07-144
T-00232-0553 | PS2-61-IDH-3100C-CH12 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | closed | Closed | 2026-05-26 | CPP-RFI-65-33/1-07-144
T-00232-0554 | PS2-61-IJ-0010-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IJ-0010 | CPP AGI |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0164
T-00232-0555 | PS2-61-IJ-0010-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IJ-0010 | CPP AGI |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0164
T-00232-0556 | PS2-61-IJ-0010-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IJ-0010 | CPP AGI |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0164
T-00232-0557 | PS2-61-IJ-0011-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IJ-0011 | CPP AGI |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0165
T-00232-0558 | PS2-61-IJ-0011-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IJ-0011 | CPP AGI |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0165
T-00232-0559 | PS2-61-IJ-0011-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IJ-0011 | CPP AGI |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0165
T-00232-0560 | PS2-61-ISR-0101-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-ISR-0101 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | 70m cable pulled, Cable is coiled near EITS, cable to be reached to cubicle |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0168
T-00232-0561 | PS2-61-ISR-0101-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-ISR-0101 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | HV cable testing done, static test ITR closed | Closed | Closed | 2026-06-06 | CPP-RFI-65-33/1-07-0168
T-00232-0562 | PS2-61-ISR-0101-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-ISR-0101 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | HV cable testing done, static test ITR closed | Closed | Closed | 2026-06-06 | CPP-RFI-65-33/1-07-0168
T-00232-0563 | PS2-61-IU-0010-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0010 | CPP AGI |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0164
T-00232-0564 | PS2-61-IU-0010-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0010 | CPP AGI |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0164
T-00232-0565 | PS2-61-IU-0010-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0010 | CPP AGI |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0164
T-00232-0566 | PS2-61-IU-0011-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0011 | CPP AGI |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0165
T-00232-0567 | PS2-61-IU-0011-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0011 | CPP AGI |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0165
T-00232-0568 | PS2-61-IU-0011-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0011 | CPP AGI |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-03 | CPP-RFI-65-33/1-07-0165
T-00232-0569 | PS2-61-IU-3100A-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-06-19 | CPP-RFI-65-33/1-07-0191
T-00232-0570 | PS2-61-IU-3100A-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-06-19 | CPP-RFI-65-33/1-07-0191
T-00232-0571 | PS2-61-IU-3100A-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-06-19 | CPP-RFI-65-33/1-07-0191
T-00232-0572 | PS2-61-IU-3100A-CH04 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0006A TO PS2-61-IU-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-147
T-00232-0573 | PS2-61-IU-3100B-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable laying and testing completed | Closed | Closed | 2026-06-19 | CPP-RFI-65-33/1-07-0191
T-00232-0574 | PS2-61-IU-3100B-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable laying and testing completed | Closed | Closed | 2026-06-19 | CPP-RFI-65-33/1-07-0191
T-00232-0575 | PS2-61-IU-3100B-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable laying and testing completed | Closed | Closed | 2026-06-19 | CPP-RFI-65-33/1-07-0191
T-00232-0576 | PS2-61-IU-3100B-CH04 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0006B TO PS2-61-IU-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Cable laying and testing completed | Closed | Closed | 2026-05-27 | CPP-RFI-65-33/1-07-146
T-00232-0577 | PS2-61-IU-3100C-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | Closed | Closed | 2026-06-19 | CPP-RFI-65-33/1-07-0191
T-00232-0578 | PS2-61-IU-3100C-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | Closed | Closed | 2026-06-19 | CPP-RFI-65-33/1-07-0191
T-00232-0579 | PS2-61-IU-3100C-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | Closed | Closed | 2026-06-19 | CPP-RFI-65-33/1-07-0191
T-00232-0580 | PS2-61-IU-3100C-CH04 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0006C TO PS2-61-IU-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Cable laying and testing completed | closed | Closed | 2026-05-26 | CPP-RFI-65-33/1-07-144
T-00232-0581 | PS2-61-IV-0001A-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001A | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | HV cable testing done, static test ITR closed | Closed | Closed | 2026-06-06 | CPP-RFI-65-33/1-07-0168
T-00232-0582 | PS2-61-IV-0001A-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001A | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | 70m cable pulled, coiled below EITS building, cable to be reached to cubicle and IR test to be done | HV cable outer sheath damaged | Construction work pending |  | CPP-RFI-65-33/1-07-0168
T-00232-0583 | PS2-61-IV-0001A-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001A | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | HV cable testing done, static test ITR closed | HV cable outer sheath damaged | Construction work pending |  | CPP-RFI-65-33/1-07-0168
T-00232-0584 | PS2-61-IV-0001B-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001B | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | 65m cable pulled, coiled below EITS building, cable to be reached to cubicle and IR test to be done | HV cable outer sheath damaged | Construction work pending |  | CPP-RFI-65-33/1-07-0168
T-00232-0585 | PS2-61-IV-0001B-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001B | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | 65m cable pulled, coiled below EITS building, cable to be reached to cubicle and IR test to be done | HV cable outer sheath damaged | Construction work pending |  | CPP-RFI-65-33/1-07-0168
T-00232-0586 | PS2-61-IV-0001B-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001B | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | 65m cable pulled, coiled below EITS building, cable to be reached to cubicle and IR test to be done | Closed | Closed | 2026-06-10 | CPP-RFI-65-33/1-07-0168
T-00232-0587 | PS2-61-NER-0010-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-NER-0010 | CPP AGI |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started | Not Available
T-00232-0588 | PS2-61-NER-0011-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-NER-0011 | CPP AGI |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started | Not Available
T-00232-0589 | PS2-63-IV-0010-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-63-IV-0010 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started | Cable drum not available
T-00232-0590 | PS2-63-IV-0010-CH02 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-63-IV-0010 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started | Cable drum not available
T-00232-0591 | PS2-63-IV-0010-CH03 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-63-IV-0010 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started | Cable drum not available
T-00232-0592 | PS2-63-NER-0010-CH01 | TPX08 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-63-IV-0010 TO PS2-63-NER-0010 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started | Cable drum not available
T-00233-10506 | PS2-08-85CP-1001-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-85CP-1001 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00233-10515 | PS2-25-DM-3100A-CG01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00233-10516 | PS2-25-DM-3100A-CG02 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00233-10517 | PS2-25-DM-3100B-CG01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00233-10518 | PS2-25-DM-3100B-CG02 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00233-10519 | PS2-25-DM-3100C-CG01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00233-10520 | PS2-25-DM-3100C-CG02 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00233-10847 | PS2-01-LA-0001-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | From PS2-06-IG-0001A To PS2-01-LA-0001 | EITS |  | PS2-0H-01 - HIPPS | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00233-10848 | PS2-01-LA-0001-CS02 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | From PS2-61-IG-0008 To PS2-01-LA-0001 | EITS |  | PS2-0H-01 - HIPPS | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00233-10849 | PS2-01-LA-0001-CS03 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | From PS2-06-IG-0001B To PS2-01-LA-0001 | EITS |  | PS2-0H-01 - HIPPS | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00233-2921 | PS2-08-01FB-0701-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-01FB-0701 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0080
T-00233-2922 | PS2-08-01FB-0702-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-01FB-0701 TO PS2-08-01FB-0702 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00233-2923 | PS2-08-01FB-0703-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-01FB-0702 TO PS2-08-01FB-0703 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00233-2924 | PS2-08-01FB-0704-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-01FB-0703 TO PS2-08-01FB-0704 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0093
T-00233-2925 | PS2-08-01FB-0704-CS02 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-01FB-0704 TO PS2-08-11CB-1001 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0093
T-00233-2926 | PS2-08-01FB-0801-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-01FB-0801 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00233-2927 | PS2-08-01FB-0802-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-01FB-0801 TO PS2-08-01FB-0802 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00233-2928 | PS2-08-01FB-0803-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-01FB-0802 TO PS2-08-01FB-0803 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00233-2929 | PS2-08-01FB-0804-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-01FB-0803 TO PS2-08-01FB-0804 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00233-2930 | PS2-08-01FB-0804-CS02 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-01FB-0804 TO PS2-08-11CB-1001 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00233-2931 | PS2-08-03FB-0001-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-03FB-0001 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00233-2932 | PS2-08-03FB-0002-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-03FB-0002 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00233-2933 | PS2-08-03FB-0101-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-03FB-0101 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00233-2934 | PS2-08-03FB-0102-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-03FB-0102 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00233-2935 | PS2-08-03FB-0103-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-03FB-0103 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0104
T-00233-2936 | PS2-08-03FB-0104-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-03FB-0104 | EITS | UG-MID-65-WPR2-150100 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00233-2937 | PS2-08-12BT-0101-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0101 | EITS | UG-MID-65-WPR2-150100 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0104
T-00233-2938 | PS2-08-12BT-0102-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0102 | EITS | UG-MID-65-WPR2-150100 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00233-2939 | PS2-08-12BT-0104-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0104 | EITS | UG-MID-65-WPR2-150100 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0080
T-00233-2940 | PS2-08-12BT-0105-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0105 | EITS | UG-MID-65-WPR2-150100 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00233-2941 | PS2-08-12BT-0107-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0107 | EITS | UG-MID-65-WPR2-150100 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00233-2942 | PS2-08-15CP-0001-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0001 | EITS | UG-MID-65-WPR2-150100 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0193
T-00233-2943 | PS2-08-15CP-0002-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0002 | EITS | UG-MID-65-WPR2-150100 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0193
T-00233-2944 | PS2-08-15CP-0003-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0003 | EITS | UG-MID-65-WPR2-150100 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0052
T-00233-2945 | PS2-08-15CP-0004-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0004 | EITS | UG-MID-65-WPR2-150100 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0052
T-00233-2946 | PS2-08-15CP-0005-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0005 | EITS | UG-MID-65-WPR2-150100 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00233-2947 | PS2-08-15CP-0006-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0006 | EITS | UG-MID-65-WPR2-150100 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00233-2948 | PS2-08-15CP-0007-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0007 | EITS | UG-MID-65-WPR2-150100 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0087_01
T-00233-2949 | PS2-08-15CP-0008-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0008 | EITS | UG-MID-65-WPR2-150100 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0087_01
T-00233-2950 | PS2-08-52BT-0131-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-52BT-0131 | EITS | UG-MID-65-WPR2-150100 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0104
T-00233-2951 | PS2-08-52BT-0132-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-52BT-0132 | EITS | UG-MID-65-WPR2-150100 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00233-2952 | PS2-08-52BT-0133-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-52BT-0133 | EITS | UG-MID-65-WPR2-150100 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00233-2953 | PS2-08-52BT-0134-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-08-52BT-0134 | EITS | UG-MID-65-WPR2-150100 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00233-2954 | PS2-08-52BT-0931-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1601 TO PS2-08-52BT-0931 | EITS | UG-MID-65-WPR2-150100 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00233-2955 | PS2-08-61BT-0002-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-14CB-1601 TO PS2-08-61BT-0002 | EITS | UG-MID-65-WPR2-150100 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00233-2956 | PS2-08-85CP-0021-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-85CP-0021 | EITS | UG-MID-65-WPR2-150100 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00233-2957 | PS2-08-85CP-0022-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1001 TO PS2-08-85CP-0022 | EITS | UG-MID-65-WPR2-150100 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0091_01
T-00233-2958 | PS2-08-85CP-1501-CS01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-11CB-1501 TO PS2-08-85CP-1501 | EITS | UG-MID-65-WPR2-150100 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00233-2965 | PS2-25-DM-3100A-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00233-2966 | PS2-25-DM-3100A-CL02 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0014 TO PS2-25-DM-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00233-2973 | PS2-25-DM-3100B-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00233-2974 | PS2-25-DM-3100B-CL02 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0014 TO PS2-25-DM-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00233-2981 | PS2-25-DM-3100C-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0082
T-00233-2982 | PS2-25-DM-3100C-CL02 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0014 TO PS2-25-DM-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00233-2995 | PS2-25-ESDV-0021-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-ESDV-0021 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-01 - Export Pipeline Pig Receiver |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0081
T-00233-2996 | PS2-25-ESDV-0023-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-ESDV-0023 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0081
T-00233-2997 | PS2-25-FCV-0003A-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-FCV-0003A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #N/A
T-00233-2998 | PS2-25-FCV-0003B-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-FCV-0003B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #N/A
T-00233-2999 | PS2-25-FCV-0003C-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-FCV-0003C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | #N/A
T-00233-3000 | PS2-25-FCV-0004-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-FCV-0004 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-06 - Crude Oil Export Pumps Discharge |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00233-3009 | PS2-25-MOV-0001-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0001 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-01 - Export Pipeline Pig Receiver |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0097-01
T-00233-3010 | PS2-25-MOV-0002-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0002 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-01 - Export Pipeline Pig Receiver |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0097-01
T-00233-3011 | PS2-25-MOV-0003-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0003 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-01 - Export Pipeline Pig Receiver |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0097-01
T-00233-3012 | PS2-25-MOV-0008-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0008 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0097-01
T-00233-3013 | PS2-25-MOV-0011-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0011 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0097-01
T-00233-3014 | PS2-25-MOV-0012-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0012 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0097-01
T-00233-3015 | PS2-25-MOV-0025-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0025 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-01 - Export Pipeline Pig Receiver |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0097-01
T-00233-3016 | PS2-25-MOV-0026-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0026 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-01 - Export Pipeline Pig Receiver |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0097-01
T-00233-3017 | PS2-25-MOV-0027-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0027 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-06 - Crude Oil Export Pumps Discharge |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0097-01
T-00233-3018 | PS2-25-MOV-0028-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-MOV-0028 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0097-01
T-00233-3019 | PS2-25-SDV-0035A-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0035A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0081
T-00233-3020 | PS2-25-SDV-0035B-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0035B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0081
T-00233-3021 | PS2-25-SDV-0035C-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0035C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0081
T-00233-3022 | PS2-25-SDV-0036A-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0036A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0081
T-00233-3023 | PS2-25-SDV-0036B-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0036B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0081
T-00233-3024 | PS2-25-SDV-0036C-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0036C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0081
T-00233-3025 | PS2-25-SDV-0046-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0046 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-05 - Crude Oil Export Pumps Bypass |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0097-01
T-00233-3026 | PS2-25-SDV-0052-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0052 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0081
T-00233-3027 | PS2-25-SDV-0054A-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0054A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0081
T-00233-3028 | PS2-25-SDV-0054B-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0054B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0081
T-00233-3029 | PS2-25-SDV-0054C-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-SDV-0054C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0081
T-00233-3031 | PS2-25-XV-0053-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-XV-0053 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-05 - Crude Oil Export Pumps Bypass |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0097-01
T-00233-3032 | PS2-25-XV-0070-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-25-XV-0070 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-05 - Crude Oil Export Pumps Bypass |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0097-01
T-00233-3034 | PS2-28-BE-0001-CL02 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0014 TO PS2-28-BE-0001 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-28-04 - Reinjection Pump |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 15th JULY 2026 | #N/A
T-00233-3041 | PS2-28-HE-2100-CL02 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0014 TO PS2-28-HE-2100 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-28-03 - Closed Drain Drum & Pump |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 30TH JULY 2026 | CPP-RFI-65-33/1-05-0082
T-00233-3042 | PS2-28-LB-8200-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0014 TO PS2-28-LB-8200 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-28-09 - Open Drain Interceptor |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 15th JULY 2026 | CPP-RFI-65-33/1-05-0119
T-00233-3043 | PS2-28-SDV-0053A-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-28-SDV-0053A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0081
T-00233-3044 | PS2-28-SDV-0053B-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-28-SDV-0053B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0081
T-00233-3045 | PS2-28-SDV-0053C-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-28-SDV-0053C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0081
T-00233-3046 | PS2-28-SDV-0065-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-28-SDV-0065 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-28-04 - Reinjection Pump |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 15th JULY 2026 | CPP-RFI-65-33/1-05-0081
T-00233-3170 | PS2-61-IU-3100A-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-61-IU-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0107
T-00233-3175 | PS2-61-IU-3100B-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-61-IU-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0107
T-00233-3180 | PS2-61-IU-3100C-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-61-IU-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0107
T-00233-3196 | PS2-62-IE-0001-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0004 TO PS2-62-IE-0001 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00233-3197 | PS2-62-IE-0002-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0006 TO PS2-62-IE-0002 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00233-3208 | PS2-75-MOV-0001-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0015 TO PS2-75-MOV-0001 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-28-08 - Open Drains (OD2) |  | cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0097-01
T-00233-3209 | PS2-75-UI-6200-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0001A TO PS2-75-UI-6200 | #N/A | UG-MID-65-WPR2-150100 | PS2-75-01 - DRA Injection Package |  | cable not found in cable schedule | Cable not found in Electrical cable schedule | Construction work pending |  | #N/A
T-00233-3210 | PS2-75-UI-6200-CL02 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0001B TO PS2-75-UI-6200 | #N/A | UG-MID-65-WPR2-150100 | PS2-75-01 - DRA Injection Package |  | cable not found in cable schedule | Cable not found in Electrical cable schedule | Construction work pending |  | #N/A
T-00233-8583 | PS2-79-IG-0001-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0001 TO PS2-79-IG-0001 | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00233-8584 | PS2-79-IG-0002-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0002 TO PS2-79-IG-0002 | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00233-8585 | PS2-79-IG-0003-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0003 TO PS2-79-IG-0003 | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00233-8586 | PS2-79-IG-0004-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0004 TO PS2-79-IG-0004 | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00233-8587 | PS2-79-IG-0005-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0005 TO PS2-79-IG-0005 | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00233-8600 | PS2-05-IG-0003-CP01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-62-IK-0001 TO PS2-05-IG-0003 | EITS |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 | sari, indera | Closed | Closed | Closed |  | #N/A
T-00233-8601 | PS2-61-IG-0003-CP01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-62-IK-0001 TO PS2-61-IG-0003 | EITS |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 | sari, indera | Closed | Closed | Closed |  | #N/A
T-00233-8973 | PS2-02-SWSI-0002-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0006 TO PS2-02-SWSI-0002 | CPP AGI |  | PS2-02-01 - Miscellaneous Safety equipment |  |  |  | Construction not yet started |  | #N/A
T-00233-8974 | PS2-03-SEA-0002-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0006 TO PS2-03-SEA-0002 | CPP AGI |  | PS2-03-05 - FZ-G1 - Guard House |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00233-8975 | PS2-06-GU-0004-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0007 TO PS2-06-GU-0004 | CPP AGI |  | PS2-06-02 - AC UPS - Guard House |  |  |  | Construction not yet started |  | #N/A
T-00233-8976 | PS2-08-11CB-1501-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0006 TO PS2-08-11CB-1501 | CPP AGI |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00233-8977 | PS2-09-LB-7001-CL01 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0007 TO PS2-09-LB-7001 | CPP AGI |  | PS2-09-02 - HVAC for Guard House |  |  |  | Construction not yet started |  | #N/A
T-00233-9932 | PS2-62-IE-0001-CL02 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0005 TO PS2-62-IE-0001 | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00233-9933 | PS2-62-IE-0001-CL03 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0005 TO PS2-62-IE-0001 | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00233-9934 | PS2-62-IE-0001-CL04 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0005 TO PS2-62-IE-0001 | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00233-9935 | PS2-62-IE-0001-CL05 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0004 TO PS2-62-IE-0001 | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00233-9936 | PS2-62-IE-0001-CL06 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0004 TO PS2-62-IE-0001 | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00233-9937 | PS2-62-IE-0001-CL07 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0004 TO PS2-62-IE-0001 | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00233-9938 | PS2-62-IE-0002-CL02 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0007 TO PS2-62-IE-0002 | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00233-9939 | PS2-62-IE-0002-CL03 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0007 TO PS2-62-IE-0002 | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00233-9940 | PS2-62-IE-0002-CL04 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0006 TO PS2-62-IE-0002 | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00233-9941 | PS2-62-IE-0002-CL05 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0006 TO PS2-62-IE-0002 | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00233-9942 | PS2-62-IE-0002-CL06 | TPX09 - LV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-IG-0006 TO PS2-62-IE-0002 | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00234-1188 | PS2-25-IES-3100A-CD01 | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-IES-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00234-1189 | PS2-25-IES-3100B-CD01 | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-IES-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00234-1190 | PS2-25-IES-3100C-CD01 | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-IES-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00234-1212 | PS2-61-IDH-3100A-CD03 | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0107
T-00234-1214 | PS2-61-IDH-3100A-CD05 | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-25-DM-3100A TO PS2-61-IDH-3100A | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-16-12-0208
T-00234-1217 | PS2-61-IDH-3100B-CD03 | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0107
T-00234-1219 | PS2-61-IDH-3100B-CD05 | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-25-DM-3100B TO PS2-61-IDH-3100B | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-16-12-0208
T-00234-1222 | PS2-61-IDH-3100C-CD03 | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0107
T-00234-1224 | PS2-61-IDH-3100C-CD05 | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-25-DM-3100C TO PS2-61-IDH-3100C | CPP AGI | UG-MID-65-WPR2-150100 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-16-12-0208
T-00234-1246 | PS2-62-IE-0002-CD01 | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-62-IE-0001 TO PS2-62-IE-0002 | CPP AGI | UG-MID-65-WPR2-150100 | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00234-3019 | PS2-79-IG-0001-CD01 | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0001 TO PS2-79-IG-0001 | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00234-3020 | PS2-79-IG-0002-CD01 | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0002 TO PS2-79-IG-0002 | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00234-3021 | PS2-79-IG-0003-CD01 | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0003 TO PS2-79-IG-0003 | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00234-3022 | PS2-79-IG-0004-CD01 | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0004 TO PS2-79-IG-0004 | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00234-3023 | PS2-79-IG-0005-CD01 | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-79-IV-0005 TO PS2-79-IG-0005 | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00235-0004 | PS2-25-DM-3100A | TPX12 - Motor HV | PCOM - Precommissioning | E - Electrical | CRUDE OIL EXPORT PUMP A MOTOR | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Equipment installed | Vendor Scope | Vendor Scope
T-00235-0005 | PS2-25-DM-3100B | TPX12 - Motor HV | PCOM - Precommissioning | E - Electrical | CRUDE OIL EXPORT PUMP B MOTOR | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Equipment installed | Vendor Scope | Vendor Scope
T-00235-0006 | PS2-25-DM-3100C | TPX12 - Motor HV | PCOM - Precommissioning | E - Electrical | CRUDE OIL EXPORT PUMP C MOTOR | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Equipment installed | Vendor Scope | Vendor Scope
T-00236-0074 | PS2-28-DM-3100 | TPX13 - Motor LV | PCOM - Precommissioning | E - Electrical | Closed Drain Drum Pump | CPP AGI |  | PS2-28-03 - Closed Drain Drum & Pump |  |  | Vendor Scope | Vendor Scope | ETA- 30TH JULY 2026
T-00236-0075 | PS2-28-DM-3800A | TPX13 - Motor LV | PCOM - Precommissioning | E - Electrical | Seal Oil Drain Drum Pump Motor A | CPP AGI |  | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  | Vendor Scope | Vendor Scope
T-00236-0076 | PS2-28-DM-3800B | TPX13 - Motor LV | PCOM - Precommissioning | E - Electrical | Seal Oil Drain Drum Pump Motor B | CPP AGI |  | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  | Vendor Scope | Vendor Scope
T-00236-0077 | PS2-28-DM-3800C | TPX13 - Motor LV | PCOM - Precommissioning | E - Electrical | Seal Oil Drain Drum Pump Motor C | CPP AGI |  | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  | Vendor Scope | Vendor Scope
T-00236-0078 | PS2-28-DM-3900 | TPX13 - Motor LV | PCOM - Precommissioning | E - Electrical | Reinjection Pump Motor | CPP AGI |  | PS2-28-04 - Reinjection Pump |  |  | Vendor Scope | Vendor Scope | ETA- 15th JULY 2026
T-00236-0079 | PS2-53-DM-3100 | TPX13 - Motor LV | PCOM - Precommissioning | E - Electrical | Water Distribution Pump Motor | CPP AGI |  | PS2-53-02 - Water Distribution Pump |  |  | Vendor Scope | Vendor Scope
T-00238-0262 | PS2-05-IG-0003 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | Emergency Lighting and Small power Distribution Panel | EITS |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 | sari, indera | Closed | Closed | Closed |  | #N/A
T-00238-0264 | PS2-06-IG-0001A | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | AC UPS Distribution Board | EITS |  | PS2-06-01 - AC UPS - EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00238-0265 | PS2-06-IG-0001B | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | AC UPS Distribution Board | EITS |  | PS2-06-01 - AC UPS - EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00238-0266 | PS2-06-IG-0002 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | AC UPS Distribution Board | EITS |  | PS2-06-01 - AC UPS - EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00238-0267 | PS2-61-IG-0003 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | Normal Lighting and Small power Distribution Panel | EITS |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 | sari, indera | Closed | Closed | Closed |  | #N/A
T-00238-0268 | PS2-61-IG-0008 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | Normal Auxiliary Distribution Panel | EITS |  | PS2-61-08 - EITS 33kV Bld. Normal Auxiliary DP - PS2-61-IG-0008 | sari, indera | Closed | Closed | Closed |  | #N/A
T-00238-0385 | PS2-61-IE-0001 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | ECS 1 Panelboard | EITS |  | PS2-61-05 - Electrical Control System | sari, indera | Closed | Closed | Closed |  | CPP-RFI-65-33/1-07-0215
T-00238-0386 | PS2-61-IE-0002 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | ECS 2 Panelboard | EITS |  | PS2-61-05 - Electrical Control System | sari, indera | Closed | Closed | Closed |  | #N/A
T-00238-0410 | PS2-05-IE-8100 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | Unit Control Panel for Emergency Diesel Generator | EITS |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) | sari, indera | Closed | Closed | Closed |  | #N/A
T-00238-0488 | PS2-62-IE-0001 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | Lighting Control panel 1 | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started | After bridge , near tray turns towards Export pump
T-00238-0489 | PS2-62-IE-0002 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | Lighting Control panel 2 | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started | After bridge , near tray turns towards Export pump | #N/A
T-00238-0657 | PS2-05-IG-0002 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | Feeder to Office & Facilities Building SWGR Emergency Section | CPP AGI |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00238-0658 | PS2-05-IG-0004 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | Outdoor Emergency Lighting Distribution Board PS-2 | CPP AGI |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started
T-00238-0659 | PS2-05-IG-0006 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | Outdoor Emergency Lighting Distribution Board PS-2 | CPP AGI |  | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  |  |  | Construction not yet started
T-00238-0660 | PS2-05-IG-0007 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | Guard House Emergency L&SP Distribution Board | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00238-0661 | PS2-61-IG-0002 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | Normal feeder to Office and other EPC buildings | CPP AGI |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00238-0662 | PS2-61-IG-0005 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | Outdoor Normal Lighting Distribution Board PS-2 | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started
T-00238-0663 | PS2-61-IG-0007 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | Outdoor Normal Lighting Distribution Board PS-2 | CPP AGI |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started
T-00238-0664 | PS2-61-IG-0014 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | Outdoor Power Distribution Board PS-2 | CPP AGI |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started | Not Available
T-00238-0665 | PS2-61-IG-0015 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | Outdoor Valves Distribution Board PS-2 | CPP AGI |  | PS2-61-07 - Outdoor Valves Distribution Board - PS2-61-IG-0015 |  | DB installation completed |  | Construction not yet started | ETA- 15th JULY 2026
T-00238-0666 | PS2-79-IG-0001 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | EHT Distribution Board 1 | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started
T-00238-0667 | PS2-79-IG-0002 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | EHT Distribution Board 2 | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started
T-00238-0668 | PS2-79-IG-0003 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | EHT Distribution Board 3 | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started
T-00238-0669 | PS2-79-IG-0004 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | EHT Distribution Board 4 | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started
T-00238-0670 | PS2-79-IG-0005 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | EHT Distribution Board 5 | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started
T-00238-0843 | PS2-06-GU-0101 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | UPS DISTRIBUTION PANEL | CPP AGI |  | PS2-06-03 - AC DB - Office Building |  |  |  | Construction not yet started |  | #N/A
T-00238-0844 | PS2-61-IG-0004 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | LIGHTING AND SMALL POWER DISTRIBUTION | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00238-0845 | PS2-05-IG-0101 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | EMERGENCY POWER DISTRIBUTION BOARD | CPP AGI |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | #N/A
T-00238-0846 | PS2-06-IG-0004 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | UPS POWER DISTRIBUTION BOARD | CPP AGI |  | PS2-06-04 - AC DB - Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00238-0856 | PS2-09-LB-7001 | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E - Electrical | HVAC UCP - Guard House | CPP AGI |  | PS2-09-02 - HVAC for Guard House |  |  |  | Construction not yet started |  | #N/A
T-00239-0218 | PS2-06-GU-0001 | TPX16 - Charger / inverter | PCOM - Precommissioning | E - Electrical | AC UPS 100kVA | EITS |  | PS2-06-01 - AC UPS - EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00240-0666 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 | dwi, dwi | Closed | Closed | Closed |  | 0
T-00240-0667 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 | dwi, dwi | Closed | Closed | Closed |  | 0
T-00240-0668 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 | dwi, dwi | Closed | Closed | Closed |  | 0
T-00240-0669 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 | sari, indera | Closed | Closed | Closed |  | 0
T-00240-0670 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 | sari, indera | Closed | Closed | Closed |  | 0
T-00240-0671 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 | sari, indera | Closed | Closed | Closed |  | 0
T-00240-0672 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 | sari, indera | Closed | Closed | Closed |  | 0
T-00240-0673 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 | sari, indera | Closed | Closed | Closed |  | 0
T-00240-0867 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | 0
T-00240-0868 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | 0
T-00240-0869 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | 0
T-00240-0870 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | 0
T-00240-0871 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00240-0872 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | 0
T-00240-0873 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | 0
T-00240-0874 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | 0
T-00240-0875 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | 0
T-00240-0876 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | 0
T-00240-0877 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | 0
T-00240-0878 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | 0
T-00240-0879 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | 0
T-00240-0880 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | 0
T-00240-0881 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | 0
T-00240-0882 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | 0
T-00240-0883 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | 0
T-00240-0884 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | 0
T-00240-0885 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00240-0886 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00240-0887 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00240-0888 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00240-0889 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00240-0890 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | 0
T-00240-0891 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | 0
T-00240-0892 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | 0
T-00240-0893 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | 0
T-00240-0894 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | 0
T-00240-0895 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | 0
T-00240-0896 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | 0
T-00240-0897 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | 0
T-00240-0898 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | 0
T-00240-0899 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | 0
T-00240-0900 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | 0
T-00240-0901 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | 0
T-00240-0902 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | 0
T-00240-0903 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | 0
T-00240-0904 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | 0
T-00240-0905 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | 0
T-00240-0906 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | 0
T-00240-0907 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | 0
T-00240-0908 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | 0
T-00240-0909 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | 0
T-00240-0910 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | 0
T-00240-0911 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | 0
T-00240-0912 |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | 0
T-00241-0161 | PS2-25-UD-3100A | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical | 5 pin 32A plug and socket for Oil Purifier Control Panel(Portable Load) | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started
T-00241-0175 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 | sari, indera | Closed | Closed | Closed |  | 0
T-00241-0176 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | EITS |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 | sari, indera | Closed | Closed | Closed |  | 0
T-00241-0282 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | 0
T-00241-0283 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | 0
T-00241-0284 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | 0
T-00241-0285 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | 0
T-00241-0286 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | 0
T-00241-0287 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-06-03 - AC DB - Office Building |  |  |  | Construction not yet started |  | 0
T-00241-0288 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-06-03 - AC DB - Office Building |  |  |  | Construction not yet started |  | 0
T-00241-0289 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-06-04 - AC DB - Workshop & Warehouse |  |  |  | Construction not yet started |  | 0
T-00241-0290 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | 0
T-00241-0291 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | 0
T-00241-0292 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | 0
T-00241-0293 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00241-0294 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00241-0295 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00241-0296 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00241-0297 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00241-0298 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00241-0299 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00241-0300 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00241-0301 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00241-0302 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00241-0303 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00241-0304 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00241-0305 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00241-0306 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00241-0307 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00241-0308 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | 0
T-00241-0309 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | 0
T-00241-0310 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | 0
T-00241-0311 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | 0
T-00241-0312 |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | 0
T-00242-0015 | PS2-09-HE-2700 | TPX20 - Heater | PCOM - Precommissioning | E - Electrical | ELECTRICAL HEATER | EITS | UT-MID-63-SSF1-220011 | PS2-09-04 - HVAC for EITS Building | sari, indera | Closed | Closed | Closed |  | #N/A
T-00242-0041 | PS2-28-HE-2100 | TPX20 - Heater | PCOM - Precommissioning | E - Electrical | CLOSED DRAIN DRUM HEATER | CPP AGI | UG-MID-65-WPR2-135401 | PS2-28-03 - Closed Drain Drum & Pump |  | Vendor installed Package equipment | Vendor Scope | Vendor Scope | ETA- 30TH JULY 2026
T-00242-0059 | PS2-25-HE-2100 | TPX20 - Heater | PCOM - Precommissioning | E - Electrical | Crude Oil Export Pump Motor A - Lube Oil System Oil Reservoir Heater | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  | Vendor Scope | Vendor Scope
T-00242-0060 | PS2-25-HE-2200 | TPX20 - Heater | PCOM - Precommissioning | E - Electrical | Crude Oil Export Pump Motor B - Lube Oil System Oil Reservoir Heater | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  | Vendor Scope | Vendor Scope
T-00242-0061 | PS2-25-HE-2300 | TPX20 - Heater | PCOM - Precommissioning | E - Electrical | Crude Oil Export Pump Motor C - Lube Oil System Oil Reservoir Heater | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  | Vendor Scope | Vendor Scope
T-00243-0026 | PS2-61-NER-0010 | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E - Electrical | LLHT Transformer NER | CPP AGI | UG-MID-65-SSF1-150257 | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  | Vendor Scope | Vendor Scope | ETA- 15th JULY 2026
T-00243-0027 | PS2-61-NER-0011 | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E - Electrical | LLHT Transformer NER | CPP AGI | UG-MID-65-SSF1-150257 | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  | Vendor Scope | Vendor Scope
T-00243-0028 | PS2-63-NER-0010 | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E - Electrical | Earthing Transformer NER | CPP AGI | UG-MID-65-SSF1-150257 | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  | Vendor Scope | Vendor Scope |  | #N/A
T-00244-0683 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0684 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0685 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0686 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0687 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0688 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0689 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0690 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0691 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0692 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0693 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0694 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0695 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0696 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0697 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0698 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0699 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0700 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0701 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0702 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0703 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0704 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0705 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0706 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0707 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0708 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0709 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0710 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0711 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0712 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0713 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0714 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0715 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0716 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0717 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00244-0718 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0719 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0720 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0721 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0722 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0723 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0724 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0725 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0726 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0727 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0728 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0729 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0730 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0731 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0732 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0733 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0734 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0735 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0736 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0737 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0738 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0739 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0740 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0741 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0742 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0743 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0744 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0745 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0746 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0747 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00244-0748 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0749 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0750 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0751 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0752 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0753 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0754 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0755 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0756 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0757 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0758 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0759 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0760 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0761 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0762 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0763 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0764 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0765 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0766 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0767 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0768 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0769 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0770 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0771 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0772 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0773 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0774 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0775 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00244-0776 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0777 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0778 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0779 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0780 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0781 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0782 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0783 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0784 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0785 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0786 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0787 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0788 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0789 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0790 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0791 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0792 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0793 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0794 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0795 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0796 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0797 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0798 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0799 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0800 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0801 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0802 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0803 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0804 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0805 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0806 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00244-0807 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0808 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0809 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0810 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0811 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0812 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0813 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0814 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0815 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0816 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0817 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0818 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0819 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0820 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0821 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0822 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0823 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0824 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0825 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0826 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0827 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0828 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0829 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0830 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0831 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0832 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0833 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0834 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0835 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00244-0836 |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E - Electrical |  | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00247-0069 | PS2 - EITS BUILDING AREA_Earthing | TPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151138 | PS2-63-01 - Electrical Earthing |  | Installation complete | Closed | Closed | 2026-07-06 | #N/A
T-00247-0070 | PS2 - EXPORT PUMP AREA_Earthing | TPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151137 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00247-0071 | PS2 - EXPORT PUMP VSD AREA_Earthing | TPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151135 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00247-0072 | PS2 - FENCE EAST AREA_Earthing | TPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151139 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00247-0073 | PS2 - FENCE SOUTH AREA_Earthing | TPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151140 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00247-0074 | PS2 - FENCE WEST AREA_Earthing | TPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151132 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00247-0075 | PS2 - MAIN ENTRANCE GATE & OFFICE BUILDING AREA_Earthing | TPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151131 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00247-0076 | PS2 - OPERATIONS AND MAINTENANCE AREA_Earthing | TPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151133 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00247-0077 | PS2 - PIGGING MECHANICAL HANDLING AREA_Earthing | TPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151134 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00247-0078 | PS2 - PUMP DISCHARGE CONTROL AREA_Earthing | TPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | CPP AGI | UG-MID-65-WPR2-151136 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00247-0079 | PS2-82-OB-0001_Earthing | TPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing for Office building | CPP AGI | UG-MID-65-CPP1-150005 | PS2-63-02 - Electrical Earthing - Office Building |  |  |  | Construction not yet started |  | #N/A
T-00247-0080 | PS2-82-OB-0005_Earthing | TPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing for Guard House | CPP AGI | UG-MID-65-WPR2-151176 | PS2-63-05 - Electrical Earthing - Guard House |  |  |  | Construction not yet started | Guard house civil work ongoing | #N/A
T-00247-0081 | PS2-83-OB-0001_Earthing | TPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing | EITS | UG-MID-65-SSF1-150004 | PS2-63-03 - Electrical Earthing - EITS Building | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00247-0082 | PS2-84-OB-0001_Earthing | TPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing for Workshop & Warehouse | CPP AGI | UG-MID-65-CPP1-150012 | PS2-63-04 - Electrical Earthing - Workshop and Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00247-0083 | PS2-84-OB-0003_Earthing | TPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing for Chemical Storage Shelter | CPP AGI | UG-MID-65-WPR2-151177 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00247-0084 | PS2-84-OB-0004_Earthing | TPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing for Waste Storage Shelter | CPP AGI | UG-MID-65-WPR2-151177 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00247-0085 | PS2-86-OB-0001_Earthing | TPX26 - Earthing system | PCOM - Precommissioning | E - Electrical | Earthing for Closed Drain Drum Shelter | CPP AGI | UG-MID-65-WPR2-151175 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00248-0024 | PS2 - LAUNCHER AND RECEIVER AREA_Lightning | TPX28 - Lightning protection system | PCOM - Precommissioning | E - Electrical | Lightning | CPP AGI | UG-MID-65-WPR2-151185 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00248-0025 | PS2-82-OB-0001_Lightning | TPX28 - Lightning protection system | PCOM - Precommissioning | E - Electrical | Lightning for Office building | CPP AGI | UG-MID-65-CPP1-150006 | PS2-63-02 - Electrical Earthing - Office Building |  |  |  | Construction not yet started |  | #N/A
T-00248-0026 | PS2-82-OB-0005_Lightning | TPX28 - Lightning protection system | PCOM - Precommissioning | E - Electrical | Lightning for Guard House | CPP AGI | UG-MID-65-WPR2-151141 | PS2-63-05 - Electrical Earthing - Guard House |  |  |  | Construction not yet started | Guard house civil work ongoing | #N/A
T-00248-0027 | PS2-84-OB-0001_Lightning | TPX28 - Lightning protection system | PCOM - Precommissioning | E - Electrical | Lightning for Workshop & Warehouse | CPP AGI | UG-MID-65-CPP1-150013 | PS2-63-04 - Electrical Earthing - Workshop and Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00248-0028 | PS2-84-OB-0003_Lightning | TPX28 - Lightning protection system | PCOM - Precommissioning | E - Electrical | Lightning for Chemical Storage Shelter | CPP AGI | UG-MID-65-WPR2-151143 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00248-0029 | PS2-84-OB-0004_Lightning | TPX28 - Lightning protection system | PCOM - Precommissioning | E - Electrical | Lightning for Waste Storage Shelter | CPP AGI | UG-MID-65-WPR2-151142 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00248-0030 | PS2-86-OB-0001_Lightning | TPX28 - Lightning protection system | PCOM - Precommissioning | E - Electrical | Lightning for Closed Drain Drum Shelter | CPP AGI | UG-MID-65-WPR2-151144 | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00249-0002 | PS2-53-TR-4100 | TPX33 - Cathodic protection | PCOM - Precommissioning | E - Electrical | UTILITY WATER STORAGE TANK | CPP AGI | UG-MID-65-FZC2-180010 | PS2-53-01 - Utility Water Storage Tank |  |  |  | Construction not yet started |  | #N/A
T-00251-0025 | PS2-25-PSV-1103 | TJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Pressure Safety Relief Valve | CPP AGI |  | PS2-25-01 - Export Pipeline Pig Receiver |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00251-0026 | PS2-25-PSV-1203 | TJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Pressure Safety Relief Valve | CPP AGI |  | PS2-25-07 - Export Pipeline Pig Launcher |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00251-0027 | PS2-25-PSV-3901 | TJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Pressure Safety Relief Valve | CPP AGI |  | PS2-28-04 - Reinjection Pump |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00251-0028 | PS2-28-PRV-0047A | TJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Self-Actuating / Regulating Press Valve | CPP AGI |  | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00251-0029 | PS2-28-PRV-0047B | TJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Self-Actuating / Regulating Press Valve | CPP AGI |  | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00251-0030 | PS2-28-PRV-0047C | TJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Self-Actuating / Regulating Press Valve | CPP AGI |  | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00251-0031 | PS2-28-PRV-0048A | TJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Self-Actuating / Regulating Press Valve | CPP AGI |  | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00251-0032 | PS2-28-PRV-0048B | TJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Self-Actuating / Regulating Press Valve | CPP AGI |  | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00251-0033 | PS2-28-PRV-0048C | TJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Self-Actuating / Regulating Press Valve | CPP AGI |  | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00251-0034 | PS2-28-PSV-0064A | TJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Pressure Safety Relief Valve | CPP AGI |  | PS2-28-05 - Seal Oil Drain Drum & Pump A |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00251-0035 | PS2-28-PSV-0064B | TJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Pressure Safety Relief Valve | CPP AGI |  | PS2-28-06 - Seal Oil Drain Drum & Pump B |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00251-0036 | PS2-28-PSV-0064C | TJX03 - Relief valve | PCOM - Precommissioning | I - Instrumentation | Pressure Safety Relief Valve | CPP AGI |  | PS2-28-07 - Seal Oil Drain Drum & Pump C |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00254-10445 | PS2-03-RAB-B103-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SEA-0005 TO PS2-03-RAB-B103 | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00254-10446 | PS2-03-RDOS-B101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDOS-B101B TO PS2-03-RDOS-B101A | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00254-10447 | PS2-03-RDOS-B101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDOS-B101C TO PS2-03-RDOS-B101B | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00254-10448 | PS2-03-RDOS-B101C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDOS-B101D TO PS2-03-RDOS-B101C | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00254-10449 | PS2-03-RDOS-B101D-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDOS-B101E TO PS2-03-RDOS-B101D | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00254-10450 | PS2-03-RDOS-B101E-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDOS-B101F TO PS2-03-RDOS-B101E | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00254-10451 | PS2-03-RDOS-B101F-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RMAC-B102 TO PS2-03-RDOS-B101F | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00254-10452 | PS2-03-RDOS-B101G-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SEA-0005 TO PS2-03-RDOS-B101G | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00254-10453 | PS2-03-RMAC-B102-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDOS-B101G TO PS2-03-RMAC-B102 | CPP AGI | UG-MID-65-CPP1-160002 | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00254-10542 | PS2-03-RAB-W103-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SEA-0003 TO PS2-03-RAB-W103 | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10543 | PS2-03-RDHR-W101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101B TO PS2-03-RDHR-W101A | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10544 | PS2-03-RDHR-W101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101C TO PS2-03-RDHR-W101B | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10545 | PS2-03-RDHR-W101C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101D TO PS2-03-RDHR-W101C | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10546 | PS2-03-RDHR-W101D-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101E TO PS2-03-RDHR-W101D | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10547 | PS2-03-RDHR-W101E-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101F TO PS2-03-RDHR-W101E | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10548 | PS2-03-RDHR-W101F-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101L TO PS2-03-RDHR-W101F | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10549 | PS2-03-RDHR-W101G-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101R TO PS2-03-RDHR-W101G | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10550 | PS2-03-RDHR-W101H-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101G TO PS2-03-RDHR-W101H | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10551 | PS2-03-RDHR-W101I-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101H TO PS2-03-RDHR-W101I | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10552 | PS2-03-RDHR-W101J-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101I TO PS2-03-RDHR-W101J | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10553 | PS2-03-RDHR-W101K-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101J TO PS2-03-RDHR-W101K | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10554 | PS2-03-RDHR-W101L-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101K TO PS2-03-RDHR-W101L | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10555 | PS2-03-RDHR-W101M-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RMAC-W102 TO PS2-03-RDHR-W101M | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10556 | PS2-03-RDHR-W101N-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101M TO PS2-03-RDHR-W101N | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10557 | PS2-03-RDHR-W101O-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101N TO PS2-03-RDHR-W101O | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10558 | PS2-03-RDHR-W101P-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101O TO PS2-03-RDHR-W101P | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10559 | PS2-03-RDHR-W101Q-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101P TO PS2-03-RDHR-W101Q | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10560 | PS2-03-RDHR-W101R-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDHR-W101Q TO PS2-03-RDHR-W101R | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-10561 | PS2-03-RMAC-W102-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SEA-0003 TO PS2-03-RMAC-W102 | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #N/A
T-00254-12891 | PS2-01-LA-0001-CC52 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | From PS2-61-IJ-0001 To PS2-01-LA-0001 | EITS |  | PS2-0H-01 - HIPPS |  |  |  | Construction not yet started |  | #N/A
T-00254-12892 | PS2-01-LA-0001-CC53 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | From PS2-61-IJ-0001 To PS2-01-LA-0001 | EITS |  | PS2-0H-01 - HIPPS |  |  |  | Construction not yet started |  | #N/A
T-00254-12893 | PS2-01-LA-0001-CC54 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | From PS2-61-IJ-0001 To PS2-01-LA-0001 | EITS |  | PS2-0H-01 - HIPPS |  |  |  | Construction not yet started |  | #N/A
T-00254-12894 | PS2-01-LA-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | From PS2-03-SFMC-0002 To PS2-01-LA-0001 | EITS |  | PS2-0H-01 - HIPPS | dwi, dwi | Closed | Closed | Closed |  | #N/A
T-00254-12906 | PS2-25-BI-1802A-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-61-IDH-3100A TO PS2-25-BI-1802A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | CPP-RFI-65-16-12-0208
T-00254-2573 | PS2-03-GDLHP-0105-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2505 TO PS2-03-GDLHP-0105 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2574 | PS2-03-GDLHP-0106-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2505 TO PS2-03-GDLHP-0106 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2575 | PS2-03-RDH-0201-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2501 TO PS2-03-RDH-0201 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | Cable laying and testing completed | Closed | Closed | 2026-06-18 | CPP-RFI-65-16-12-0158
T-00254-2576 | PS2-03-RDH-0202-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2501 TO PS2-03-RDH-0202 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | Cable laying and testing completed | Closed | Closed | 2026-06-19 | CPP-RFI-65-16-12-0158
T-00254-2577 | PS2-03-RDH-0203-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2501 TO PS2-03-RDH-0203 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | Cable laying and testing completed | Closed | Closed | 2026-06-19 | CPP-RFI-65-16-12-0158
T-00254-2578 | PS2-03-RDH-0204-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2501 TO PS2-03-RDH-0204 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | Cable laying and testing completed | Closed | Closed | 2026-06-19 | CPP-RFI-65-16-12-0158
T-00254-2579 | PS2-03-RDH-0205-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2501 TO PS2-03-RDH-0205 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | Cable laying and testing completed | Closed | Closed | 2026-06-19 | CPP-RFI-65-16-12-0158
T-00254-2580 | PS2-03-RDH-0211-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2502 TO PS2-03-RDH-0211 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started | ETA- 20TH JULY 2026 | CPP-RFI-65-16-04-0131
T-00254-2581 | PS2-03-RDH-0212-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2502 TO PS2-03-RDH-0212 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started | ETA- 20TH JULY 2026 | CPP-RFI-65-16-04-0131
T-00254-2582 | PS2-03-RDH-0213-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2502 TO PS2-03-RDH-0213 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started | ETA- 20TH JULY 2026 | CPP-RFI-65-16-04-0131
T-00254-2583 | PS2-03-RDIR-0101-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1503 TO PS2-03-RDIR-0101 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2584 | PS2-03-RDIR-0102-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1501 TO PS2-03-RDIR-0102 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2585 | PS2-03-RDIR-0103-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1501 TO PS2-03-RDIR-0103 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2586 | PS2-03-RDIR-0104-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1501 TO PS2-03-RDIR-0104 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2587 | PS2-03-RDIR-0105-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0105 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2588 | PS2-03-RDIR-0106-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0106 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2589 | PS2-03-RDIR-0107-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0107 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2590 | PS2-03-RDIR-0108-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0108 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2591 | PS2-03-RDIR-0109-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0109 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2592 | PS2-03-RDIR-0110-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0110 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2593 | PS2-03-RDIR-0111-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1503 TO PS2-03-RDIR-0111 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2594 | PS2-03-RDIR-0112-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1503 TO PS2-03-RDIR-0112 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2595 | PS2-03-RDIR-0113-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1503 TO PS2-03-RDIR-0113 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2596 | PS2-03-RDIR-0118-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0118 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2597 | PS2-03-RDIR-0119-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0119 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2598 | PS2-03-RDIR-0120-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1502 TO PS2-03-RDIR-0120 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2599 | PS2-03-RDIR-0121-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1503 TO PS2-03-RDIR-0121 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2600 | PS2-03-RMAC-0114-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2503 TO PS2-03-RMAC-0114 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2601 | PS2-03-RMAC-0115-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2503 TO PS2-03-RMAC-0115 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2602 | PS2-03-RMAC-0116-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2504 TO PS2-03-RMAC-0116 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2603 | PS2-03-RMAC-0117-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2504 TO PS2-03-RMAC-0117 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2604 | PS2-03-RMAC-0206-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2502 TO PS2-03-RMAC-0206 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started | ETA- 20TH JULY 2026 | CPP-RFI-65-16-03-0101
T-00254-2605 | PS2-03-RMAC-0207-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2501 TO PS2-03-RMAC-0207 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started | ETA- 20TH JULY 2026 | #N/A
T-00254-2608 | PS2-03-GDLHP-0107-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2505 TO PS2-03-GDLHP-0107 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2609 | PS2-03-GDLHP-0109-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2505 TO PS2-03-GDLHP-0109 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2610 | PS2-03-GDLHP-0111-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2505 TO PS2-03-GDLHP-0111 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2618 | PS2-03-RDH-0214-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2501 TO PS2-03-RDH-0214 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started | ETA- 20TH JULY 2026 | #N/A
T-00254-2619 | PS2-03-RDH-0215-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-2501 TO PS2-03-RDH-0215 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | Cable intallation and testing completed | Closed | Closed | 2026-06-18 | CPP-RFI-65-16-12-0158
T-00254-2620 | PS2-03-RDIR-0124-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1501 TO PS2-03-RDIR-0124 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2621 | PS2-03-RDIR-0125-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-BI-1501 TO PS2-03-RDIR-0125 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-01 - FZ-01 - Process Area |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2622 | PS2-03-RDOS-G101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-RDOS-G101B TO PS2-03-RDOS-G101A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-05 - FZ-G1 - Guard House |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00254-2623 | PS2-03-RDOS-G101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SEA-0002 TO PS2-03-RDOS-G101B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-03-05 - FZ-G1 - Guard House |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #N/A
T-00254-2672 | PS2-25-BI-1802B-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-61-IDH-3100B TO PS2-25-BI-1802B | CPP AGI | UT-MID-63-SLZ1-160005 | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | CPP-RFI-65-16-12-0208
T-00254-2674 | PS2-25-BI-1802C-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-61-IDH-3100C TO PS2-25-BI-1802C | CPP AGI | UT-MID-63-SLZ1-160005 | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | CPP-RFI-65-16-12-0208
T-00254-2702 | PS2-25-ESDV-0021-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1201 TO PS2-25-ESDV-0021 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2703 | PS2-25-ESDV-0021-CC02 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2201 TO PS2-25-ESDV-0021 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2704 | PS2-25-ESDV-0021-CC03 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2202 TO PS2-25-ESDV-0021 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2705 | PS2-25-ESDV-0023-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1201 TO PS2-25-ESDV-0023 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00254-2706 | PS2-25-ESDV-0023-CC02 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2201 TO PS2-25-ESDV-0023 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00254-2707 | PS2-25-ESDV-0023-CC03 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2202 TO PS2-25-ESDV-0023 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00254-2708 | PS2-25-ESY-0021A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2203 TO PS2-25-ESDV-0021 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2709 | PS2-25-ESY-0021B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2305 TO PS2-25-ESDV-0021 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2710 | PS2-25-ESY-0023A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2203 TO PS2-25-ESDV-0023 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00254-2711 | PS2-25-ESY-0023B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2305 TO PS2-25-ESDV-0023 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00254-2712 | PS2-25-FCV-0003A-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-FCV-0003A TO PS2-25-FCV-0003A-HPU | CPP AGI | UT-MID-60-EPM2-160008 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00254-2713 | PS2-25-FCV-0003B-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-FCV-0003B TO PS2-25-FCV-0003B-HPU | CPP AGI | UT-MID-60-EPM2-160008 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00254-2714 | PS2-25-FCV-0003C-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-FCV-0003C TO PS2-25-FCV-0003C-HPU | CPP AGI | UT-MID-60-EPM2-160008 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2715 | PS2-25-FCV-0004-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-FCV-0004 TO PS2-25-FCV-0004-HPU | CPP AGI | UT-MID-60-EPM2-160008 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #N/A
T-00254-2716 | PS2-25-FIT-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-FIT-0001 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2717 | PS2-25-FIT-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1102 TO PS2-25-FIT-0003A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2718 | PS2-25-FIT-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1106 TO PS2-25-FIT-0003B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00254-2719 | PS2-25-FIT-0003C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1107 TO PS2-25-FIT-0003C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2720 | PS2-25-FIT-0004-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1108 TO PS2-25-FIT-0004 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #N/A
T-00254-2721 | PS2-25-FXS-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2105 TO PS2-25-FCV-0003A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2722 | PS2-25-FXS-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2105 TO PS2-25-FCV-0003B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2723 | PS2-25-FXS-0003C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2105 TO PS2-25-FCV-0003C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2724 | PS2-25-FXS-0004-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2104 TO PS2-25-FCV-0004 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #N/A
T-00254-2725 | PS2-25-FY-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1102 TO PS2-25-FCV-0003A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2726 | PS2-25-FY-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1106 TO PS2-25-FCV-0003B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-16-04-0131
T-00254-2727 | PS2-25-FY-0003C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1107 TO PS2-25-FCV-0003C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2728 | PS2-25-FY-0004-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1108 TO PS2-25-FCV-0004 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #N/A
T-00254-2729 | PS2-25-HS-8101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2315 TO PS2-25-HS-8101A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-16-12-0208
T-00254-2730 | PS2-25-HS-8101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2315 TO PS2-25-HS-8101B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-16-12-0208
T-00254-2731 | PS2-25-HS-8101C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2315 TO PS2-25-HS-8101C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-16-12-0208
T-00254-2732 | PS2-25-HS-8102A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2315 TO PS2-25-HS-8102A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-16-12-0208
T-00254-2733 | PS2-25-HS-8102B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2315 TO PS2-25-HS-8102B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-16-12-0208
T-00254-2734 | PS2-25-HS-8102C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2315 TO PS2-25-HS-8102C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-16-12-0208
T-00254-2735 | PS2-25-MOV-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2101 TO PS2-25-MOV-0001 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2736 | PS2-25-MOV-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2101 TO PS2-25-MOV-0002 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2737 | PS2-25-MOV-0003-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2101 TO PS2-25-MOV-0003 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2738 | PS2-25-MOV-0008-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2103 TO PS2-25-MOV-0008 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00254-2739 | PS2-25-MOV-0011-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2103 TO PS2-25-MOV-0011 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00254-2740 | PS2-25-MOV-0012-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2103 TO PS2-25-MOV-0012 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00254-2741 | PS2-25-MOV-0025-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2101 TO PS2-25-MOV-0025 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2742 | PS2-25-MOV-0026-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2102 TO PS2-25-MOV-0026 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2743 | PS2-25-MOV-0026-CC02 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-MOV-0026 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2744 | PS2-25-MOV-0027-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2102 TO PS2-25-MOV-0027 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #N/A
T-00254-2745 | PS2-25-MOV-0027-CC02 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-MOV-0027 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #N/A
T-00254-2746 | PS2-25-MOV-0028-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2103 TO PS2-25-MOV-0028 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00254-2747 | PS2-25-MXS-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2101 TO PS2-25-MOV-0001 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2748 | PS2-25-MXS-0008-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2103 TO PS2-25-MOV-0008 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00254-2749 | PS2-25-MXS-0025-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2101 TO PS2-25-MOV-0025 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2750 | PS2-25-MXS-0028-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2103 TO PS2-25-MOV-0028 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00254-2754 | PS2-25-PDIT-0034A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1102 TO PS2-25-PDIT-0034A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2755 | PS2-25-PDIT-0034B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1106 TO PS2-25-PDIT-0034B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2756 | PS2-25-PDIT-0034C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1107 TO PS2-25-PDIT-0034C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2757 | PS2-25-PDIT-0050-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-PDIT-0050 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2758 | PS2-25-PI-1102B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-PIT-1102 TO PS2-25-PI-1102B | CPP AGI | UT-MID-60-ACP2-160006 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2759 | PS2-25-PI-1202B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-PIT-1202 TO PS2-25-PI-1202B | CPP AGI | UT-MID-60-ACP2-160006 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00254-2760 | PS2-25-PIT-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-PIT-0001 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2761 | PS2-25-PIT-0003AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1102 TO PS2-25-FCV-0003A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2762 | PS2-25-PIT-0003BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1106 TO PS2-25-FCV-0003B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2763 | PS2-25-PIT-0003CA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1107 TO PS2-25-FCV-0003C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2764 | PS2-25-PIT-0004AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1108 TO PS2-25-FCV-0004 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #N/A
T-00254-2765 | PS2-25-PIT-0004A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-25-PIT-0004A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2766 | PS2-25-PIT-0004B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-25-PIT-0004B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2767 | PS2-25-PIT-0004C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-PIT-0004C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2768 | PS2-25-PIT-0005A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1102 TO PS2-25-PIT-0005A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2769 | PS2-25-PIT-0005B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1106 TO PS2-25-PIT-0005B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2770 | PS2-25-PIT-0005C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1107 TO PS2-25-PIT-0005C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2771 | PS2-25-PIT-0007A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1102 TO PS2-25-PIT-0007A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2772 | PS2-25-PIT-0007B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1106 TO PS2-25-PIT-0007B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2773 | PS2-25-PIT-0007C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1107 TO PS2-25-PIT-0007C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2774 | PS2-25-PIT-0008A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1301 TO PS2-25-PIT-0008A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2775 | PS2-25-PIT-0008B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1301 TO PS2-25-PIT-0008B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2776 | PS2-25-PIT-0008C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1301 TO PS2-25-PIT-0008C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2777 | PS2-25-PIT-0013-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1108 TO PS2-25-PIT-0013 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #N/A
T-00254-2778 | PS2-25-PIT-0018-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-PIT-0018 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2779 | PS2-25-PIT-0035A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-25-SDV-0035A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2780 | PS2-25-PIT-0035B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-25-SDV-0035B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2781 | PS2-25-PIT-0035C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-SDV-0035C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2782 | PS2-25-PIT-0036A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-25-SDV-0036A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2783 | PS2-25-PIT-0036B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-SDV-0036B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2784 | PS2-25-PIT-0036C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-SDV-0036C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2785 | PS2-25-PIT-0046-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-SDV-0046 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2787 | PS2-25-PIT-0053-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1108 TO PS2-25-XV-0053 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #N/A
T-00254-2788 | PS2-25-PIT-0054A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-25-SDV-0054A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2789 | PS2-25-PIT-0054B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-SDV-0054B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2790 | PS2-25-PIT-0054C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-SDV-0054C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2791 | PS2-25-PIT-0070-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1108 TO PS2-25-XV-0070 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #N/A
T-00254-2795 | PS2-25-PIT-1102-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-PIT-1102 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2796 | PS2-25-PIT-1202-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-PIT-1202 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00254-2797 | PS2-25-SDV-0035A-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2302 TO PS2-25-SDV-0035A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-30 | CPP-RFI-65-16-12-0210
T-00254-2798 | PS2-25-SDV-0035B-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2307 TO PS2-25-SDV-0035B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2799 | PS2-25-SDV-0035C-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2308 TO PS2-25-SDV-0035C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2800 | PS2-25-SDV-0036A-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2302 TO PS2-25-SDV-0036A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-30 | CPP-RFI-65-16-12-0210
T-00254-2801 | PS2-25-SDV-0036B-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2307 TO PS2-25-SDV-0036B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2802 | PS2-25-SDV-0036C-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2308 TO PS2-25-SDV-0036C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2803 | PS2-25-SDV-0046-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2308 TO PS2-25-SDV-0046 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2806 | PS2-25-SDV-0053C-CC02 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-SDV-0053C TO PS2-25-SDV-0053C-HPU | CPP AGI | UT-MID-60-NBV3-160008 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2807 | PS2-25-SDV-0054A-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2302 TO PS2-25-SDV-0054A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-30 | CPP-RFI-65-16-12-0210
T-00254-2808 | PS2-25-SDV-0054B-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2307 TO PS2-25-SDV-0054B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2809 | PS2-25-SDV-0054C-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2308 TO PS2-25-SDV-0054C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2811 | PS2-25-SXS-0035A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2301 TO PS2-25-SDV-0035A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-30 | CPP-RFI-65-16-12-0210
T-00254-2812 | PS2-25-SXS-0035B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2301 TO PS2-25-SDV-0035B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-06-30 | CPP-RFI-65-16-12-0210
T-00254-2813 | PS2-25-SXS-0035C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2306 TO PS2-25-SDV-0035C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2814 | PS2-25-SXS-0036A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2301 TO PS2-25-SDV-0036A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-30 | CPP-RFI-65-16-12-0210
T-00254-2815 | PS2-25-SXS-0036B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2306 TO PS2-25-SDV-0036B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2816 | PS2-25-SXS-0036C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2306 TO PS2-25-SDV-0036C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2817 | PS2-25-SXS-0046-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2306 TO PS2-25-SDV-0046 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2819 | PS2-25-SXS-0054A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2301 TO PS2-25-SDV-0054A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-30 | CPP-RFI-65-16-12-0210
T-00254-2820 | PS2-25-SXS-0054B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2306 TO PS2-25-SDV-0054B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2821 | PS2-25-SXS-0054C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2306 TO PS2-25-SDV-0054C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2822 | PS2-25-SY-0035AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2303 TO PS2-25-SDV-0035A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-30 | CPP-RFI-65-16-12-0210
T-00254-2823 | PS2-25-SY-0035AB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2107 TO PS2-25-SDV-0035A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-16-12-0210
T-00254-2824 | PS2-25-SY-0035BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-25-SDV-0035B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2825 | PS2-25-SY-0035BB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2108 TO PS2-25-SDV-0035B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2826 | PS2-25-SY-0035CA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-25-SDV-0035C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2827 | PS2-25-SY-0035CB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2108 TO PS2-25-SDV-0035C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2828 | PS2-25-SY-0036AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2303 TO PS2-25-SDV-0036A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-30 | CPP-RFI-65-16-12-0210
T-00254-2829 | PS2-25-SY-0036AB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2107 TO PS2-25-SDV-0036A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-16-12-0210
T-00254-2830 | PS2-25-SY-0036BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-25-SDV-0036B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2831 | PS2-25-SY-0036BB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2108 TO PS2-25-SDV-0036B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2832 | PS2-25-SY-0036CA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-25-SDV-0036C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2833 | PS2-25-SY-0036CB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2108 TO PS2-25-SDV-0036C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2834 | PS2-25-SY-0046A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-25-SDV-0046 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2835 | PS2-25-SY-0046B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2109 TO PS2-25-SDV-0046 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #N/A
T-00254-2837 | PS2-25-SY-0052B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2305 TO PS2-25-SDV-0052 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00254-2838 | PS2-25-SY-0054AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2303 TO PS2-25-SDV-0054A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-30 | CPP-RFI-65-16-12-0210
T-00254-2839 | PS2-25-SY-0054AB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2107 TO PS2-25-SDV-0054A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-16-12-0210
T-00254-2840 | PS2-25-SY-0054BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-25-SDV-0054B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2841 | PS2-25-SY-0054BB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2108 TO PS2-25-SDV-0054B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2842 | PS2-25-SY-0054CA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-25-SDV-0054C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2843 | PS2-25-SY-0054CB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2108 TO PS2-25-SDV-0054C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2844 | PS2-25-TI-1101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-TIT-1101 TO PS2-25-TI-1101B | CPP AGI | UT-MID-60-ACP2-160008 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2845 | PS2-25-TI-1201B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-TIT-1201 TO PS2-25-TI-1201B | CPP AGI | UT-MID-60-ACP2-160008 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00254-2846 | PS2-25-TIT-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-TIT-0001 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2847 | PS2-25-TIT-0002A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-25-TIT-0002A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-16-12-0210
T-00254-2848 | PS2-25-TIT-0002B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-25-TIT-0002B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-16-12-0210
T-00254-2849 | PS2-25-TIT-0002C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-25-TIT-0002C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2850 | PS2-25-TIT-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1102 TO PS2-25-TIT-0003A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-02 - Crude Oil Export Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2851 | PS2-25-TIT-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1106 TO PS2-25-TIT-0003B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-03 - Crude Oil Export Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2852 | PS2-25-TIT-0003C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1107 TO PS2-25-TIT-0003C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-04 - Crude Oil Export Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2853 | PS2-25-TIT-0004-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-TIT-0004 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #N/A
T-00254-2854 | PS2-25-TIT-1101-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-TIT-1101 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2855 | PS2-25-TIT-1201-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-TIT-1201 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00254-2856 | PS2-25-XV-0053-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2106 TO PS2-25-XV-0053 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #N/A
T-00254-2857 | PS2-25-XV-0053-CC02 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-XV-0053 TO PS2-25-XV-0053-HPU | CPP AGI | UT-MID-60-NBV3-160008 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #N/A
T-00254-2858 | PS2-25-XV-0070-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2106 TO PS2-25-XV-0070 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #N/A
T-00254-2859 | PS2-25-XXS-0053-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2104 TO PS2-25-XV-0053 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #N/A
T-00254-2860 | PS2-25-XXS-0070-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2104 TO PS2-25-XV-0070 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #N/A
T-00254-2861 | PS2-25-XY-0053-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2109 TO PS2-25-XV-0053 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #N/A
T-00254-2862 | PS2-25-XY-0070-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2109 TO PS2-25-XV-0070 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #N/A
T-00254-2863 | PS2-25-ZIT-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-ZIT-0001 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00254-2864 | PS2-25-ZIT-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1101 TO PS2-25-ZIT-0002 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00254-2865 | PS2-25-ZS-1101-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2105 TO PS2-25-ZS-1101 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-01 - Export Pipeline Pig Receiver |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2866 | PS2-25-ZS-1201-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2105 TO PS2-25-ZS-1201 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-25-07 - Export Pipeline Pig Launcher |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2870 | PS2-28-HY-3901-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1103 TO PS2-28-HY-3901 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | #N/A
T-00254-2873 | PS2-28-LI-1101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-LIT-1101 TO PS2-28-LI-1101B | CPP AGI | UT-MID-60-ACP2-160007 | PS2-28-03 - Closed Drain Drum & Pump |  | Secondary cable to be pulled after JBsupport installation and secondary cable tray installation |  | Construction not yet started | ETA- 30TH JULY 2026 | #N/A
T-00254-2874 | PS2-28-LI-1101C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-LI-1101B TO PS2-28-LI-1101C | CPP AGI | UT-MID-60-ACP2-160007 | PS2-28-03 - Closed Drain Drum & Pump |  | Secondary cable to be pulled after JBsupport installation and secondary cable tray installation |  | Construction not yet started | ETA- 30TH JULY 2026 | #N/A
T-00254-2875 | PS2-28-LIT-1101-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1103 TO PS2-28-LIT-1101 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-03 - Closed Drain Drum & Pump |  | Secondary cable to be pulled after JBsupport installation and secondary cable tray installation |  | Construction not yet started | ETA- 30TH JULY 2026 | #N/A
T-00254-2876 | PS2-28-LIT-1102-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1303 TO PS2-28-LIT-1102 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-03 - Closed Drain Drum & Pump |  | Secondary cable to be pulled after JBsupport installation and secondary cable tray installation |  | Construction not yet started | ETA- 30TH JULY 2026 | #N/A
T-00254-2877 | PS2-28-LIT-1301A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1102 TO PS2-28-LIT-1301A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2878 | PS2-28-LIT-1301B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1106 TO PS2-28-LIT-1301B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-01 | CPP-RFI-65-16-12-0211
T-00254-2879 | PS2-28-LIT-1301C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1107 TO PS2-28-LIT-1301C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2880 | PS2-28-PIT-0015-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1103 TO PS2-28-PIT-0015 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | #N/A
T-00254-2881 | PS2-28-PIT-0041-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1103 TO PS2-28-PIT-0041 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-03 - Closed Drain Drum & Pump |  | Secondary cable to be pulled after JBsupport installation and secondary cable tray installation |  | Construction not yet started | ETA- 30TH JULY 2026 | #N/A
T-00254-2882 | PS2-28-PIT-0053A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1302 TO PS2-28-SDV-0053A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-16-12-0210
T-00254-2883 | PS2-28-PIT-0053B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-28-SDV-0053B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2884 | PS2-28-PIT-0053C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-1305 TO PS2-28-SDV-0053C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-02 | CPP-RFI-65-16-12-0213
T-00254-2885 | PS2-28-PIT-0065-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1303 TO PS2-28-SDV-0065 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | #N/A
T-00254-2886 | PS2-28-PIT-0066-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1303 TO PS2-28-PIT-0066 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | #N/A
T-00254-2887 | PS2-28-PIT-3901-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1303 TO PS2-28-PIT-3901 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | #N/A
T-00254-2888 | PS2-28-SDV-0053A-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2302 TO PS2-28-SDV-0053A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-16-04-0133
T-00254-2889 | PS2-28-SDV-0053A-CC02 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-SDV-0053A TO PS2-28-SDV-0053A-HPU | CPP AGI | UT-MID-60-NBV3-160008 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | #N/A
T-00254-2890 | PS2-28-SDV-0053B-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2307 TO PS2-28-SDV-0053B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2891 | PS2-28-SDV-0053B-CC02 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-SDV-0053B TO PS2-28-SDV-0053B-HPU | CPP AGI | UT-MID-60-NBV3-160008 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | #N/A
T-00254-2892 | PS2-28-SDV-0053C-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2308 TO PS2-28-SDV-0053C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2893 | PS2-28-SDV-0065-CC01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2302 TO PS2-28-SDV-0065 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-16-12-0210
T-00254-2894 | PS2-28-SDV-0065-CC02 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-SDV-0065 TO PS2-28-SDV-0065-HPU | CPP AGI | UT-MID-60-NBV3-160008 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | #N/A
T-00254-2895 | PS2-28-SXS-0053A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2301 TO PS2-28-SDV-0053A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-30 | CPP-RFI-65-16-12-0210
T-00254-2896 | PS2-28-SXS-0053B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2306 TO PS2-28-SDV-0053B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2897 | PS2-28-SXS-0053C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2306 TO PS2-28-SDV-0053C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2898 | PS2-28-SXS-0065-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2301 TO PS2-28-SDV-0065 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  | Cable intallation and testing completed | Closed | Closed | 2026-06-30 | CPP-RFI-65-16-12-0210
T-00254-2899 | PS2-28-SY-0053AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2303 TO PS2-28-SDV-0053A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-30 | CPP-RFI-65-16-12-0210
T-00254-2900 | PS2-28-SY-0053AB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2107 TO PS2-28-SDV-0053A | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-16-12-0210
T-00254-2901 | PS2-28-SY-0053BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-28-SDV-0053B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2902 | PS2-28-SY-0053BB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2108 TO PS2-28-SDV-0053B | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2903 | PS2-28-SY-0053CA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2304 TO PS2-28-SDV-0053C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2904 | PS2-28-SY-0053CB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2108 TO PS2-28-SDV-0053C | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  | Cable intallation and testing completed | Closed | Closed | 2026-07-03 | CPP-RFI-65-16-12-0214
T-00254-2905 | PS2-28-SY-0065A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2303 TO PS2-28-SDV-0065 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  | Cable intallation and testing completed | Closed | Closed | 2026-06-30 | CPP-RFI-65-16-12-0210
T-00254-2906 | PS2-28-SY-0065B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-BI-2107 TO PS2-28-SDV-0065 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-04 - Reinjection Pump |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-16-12-0210
T-00254-2907 | PS2-28-TIT-1101-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1103 TO PS2-28-TIT-1101 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-03 - Closed Drain Drum & Pump |  | Secondary cable to be pulled after JBsupport installation and secondary cable tray installation |  | Construction not yet started | ETA- 30TH JULY 2026 | #N/A
T-00254-2908 | PS2-28-TIT-1102-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1303 TO PS2-28-TIT-1102 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-03 - Closed Drain Drum & Pump |  | Secondary cable to be pulled after JBsupport installation and secondary cable tray installation |  | Construction not yet started | ETA- 30TH JULY 2026 | #N/A
T-00254-2909 | PS2-28-TIT-2101-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-28-BI-1303 TO PS2-28-TIT-2101 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-28-03 - Closed Drain Drum & Pump |  | Secondary cable to be pulled after JBsupport installation and secondary cable tray installation |  | Construction not yet started | ETA- 30TH JULY 2026 | #N/A
T-00254-2912 | PS2-53-LIT-4101-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-53-BI-1105 TO PS2-53-LIT-4101 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-53-01 - Utility Water Storage Tank |  |  |  | Construction not yet started |  | CPP-RFI-65-16-04-0131
T-00254-2914 | PS2-53-PIT-0005-CJ01 | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-53-BI-1105 TO PS2-53-PIT-0005 | CPP AGI | UG-MID-65-WPR2-161503 | PS2-53-02 - Water Distribution Pump |  |  |  | Construction not yet started |  | CPP-RFI-65-16-04-0131
T-00255-0020 | PS2-25-FO-0008 | TJX11 - Orifice plate | PCOM - Precommissioning | I - Instrumentation | Flow Restriction Orifice | CPP AGI | UG-MID-65-WPR2-134006 | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00255-0021 | PS2-28-FO-0001 | TJX11 - Orifice plate | PCOM - Precommissioning | I - Instrumentation | Flow Restriction Orifice | CPP AGI | UG-MID-65-WPR2-135401 | PS2-28-03 - Closed Drain Drum & Pump |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00255-0022 | PS2-28-FO-0003 | TJX11 - Orifice plate | PCOM - Precommissioning | I - Instrumentation | Flow Restriction Orifice | CPP AGI | UG-MID-65-WPR2-135400 | PS2-28-02 - Relief Header |  |  |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00255-0023 | PS2-28-FO-0009 | TJX11 - Orifice plate | PCOM - Precommissioning | I - Instrumentation | Flow Restriction Orifice | CPP AGI | UG-MID-65-WPR2-135403 | PS2-28-11 - Nitrogen for Seal Oil Drain |  |  |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00256-0083 | PS2-75-LA-6200-CX01 | TJX12 - Optical fiber cable | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PNC-0001 TO PS2-75-LA-6200 | CPP AGI |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | #N/A
T-00257-0032 | PS2-25-TW-0001 | TJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-134000 | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00257-0033 | PS2-25-TW-0002A | TJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00257-0034 | PS2-25-TW-0002B | TJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-134004 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00257-0035 | PS2-25-TW-0002C | TJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-134005 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00257-0036 | PS2-25-TW-0003A | TJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00257-0037 | PS2-25-TW-0003B | TJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-134004 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00257-0038 | PS2-25-TW-0003C | TJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-134005 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00257-0039 | PS2-25-TW-0004 | TJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-134007 | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00257-0040 | PS2-28-TW-0001 | TJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-135400 | PS2-28-02 - Relief Header |  |  |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00257-0041 | PS2-28-TW-0002 | TJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-135403 | PS2-28-11 - Nitrogen for Seal Oil Drain |  |  |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00257-0042 | PS2-28-TW-1101 | TJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-135401 | PS2-28-03 - Closed Drain Drum & Pump |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00257-0043 | PS2-28-TW-1102 | TJX13 - Thermowell | PCOM - Precommissioning | I - Instrumentation | Thermowell | CPP AGI | UG-MID-65-WPR2-135401 | PS2-28-03 - Closed Drain Drum & Pump |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00275-1739 | PS2-08-01PA-1201-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-01PA-1201 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00275-1740 | PS2-08-01PA-1501-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-01PA-1501 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00275-1741 | PS2-08-05IN-0001-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-05IN-0001 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00275-1742 | PS2-08-06AH-0001-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0001 TO PS2-08-06AH-0001 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00275-1743 | PS2-08-06AH-0002-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0002 TO PS2-08-06AH-0002 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00275-1744 | PS2-08-06AH-0003-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-06AH-0003 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00275-1745 | PS2-08-06AH-0004-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0004 TO PS2-08-06AH-0004 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00275-1746 | PS2-08-06AH-0005-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0005 TO PS2-08-06AH-0005 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00275-1747 | PS2-08-06AH-0006-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0005 TO PS2-08-06AH-0006 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00275-1748 | PS2-08-06AH-0007-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0006 TO PS2-08-06AH-0007 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00275-1749 | PS2-08-06AH-0008-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0007 TO PS2-08-06AH-0008 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00275-1750 | PS2-08-06AH-0009-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-06AH-0009 | #N/A | UG-MID-65-SSF1-170620 | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00275-1751 | PS2-08-12AP-0103-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-12BT-0103 TO PS2-08-12AP-0103 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-1752 | PS2-08-12AP-0106-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-12BT-0106 TO PS2-08-12AP-0106 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-1753 | PS2-08-12BT-0103-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0103 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-1754 | PS2-08-12BT-0106-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0106 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-1755 | PS2-08-14CB-1601-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-14CB-1601 | #N/A | UG-MID-65-SSF1-171420 | PS2-08-14 - Industrial Data Network (SII SP1) |  |  |  | Construction not yet started |  | #N/A
T-00275-1756 | PS2-08-14CB-1601-CA02 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-14CB-1601 | #N/A | UG-MID-65-SSF1-171420 | PS2-08-14 - Industrial Data Network (SII SP1) |  |  |  | Construction not yet started |  | #N/A
T-00275-1757 | PS2-08-14CB-1601-CA03 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-14CB-1601 | #N/A | UG-MID-65-SSF1-171420 | PS2-08-14 - Industrial Data Network (SII SP1) |  |  |  | Construction not yet started |  | #N/A
T-00275-1758 | PS2-08-14CB-1601-CA04 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-14CB-1601 | #N/A | UG-MID-65-SSF1-171420 | PS2-08-14 - Industrial Data Network (SII SP1) |  |  |  | Construction not yet started |  | #N/A
T-00275-1759 | PS2-08-14CB-1601-CA05 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-14CB-1601 | #N/A | UG-MID-65-SSF1-171420 | PS2-08-14 - Industrial Data Network (SII SP1) |  |  |  | Construction not yet started |  | #N/A
T-00275-1760 | PS2-08-14CB-1601-CA06 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-14CB-1601 | #N/A | UG-MID-65-SSF1-171420 | PS2-08-14 - Industrial Data Network (SII SP1) |  |  |  | Construction not yet started |  | #N/A
T-00275-1761 | PS2-08-52CM-0001-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-52CM-0001 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1762 | PS2-08-52CM-0002-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-52CM-0002 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1763 | PS2-08-52CM-0003-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-52CM-0003 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1764 | PS2-08-52CM-0031-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-52CM-0031 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1765 | PS2-08-52CM-0032-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0002 TO PS2-08-52CM-0032 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1766 | PS2-08-52CM-0033-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0006 TO PS2-08-52CM-0033 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1767 | PS2-08-52CM-0034-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-52CM-0034 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1768 | PS2-08-52CM-0071-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0001 TO PS2-08-52CM-0071 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1769 | PS2-08-52CM-0072-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0002 TO PS2-08-52CM-0072 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1770 | PS2-08-52CM-0073-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-52CM-0073 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1771 | PS2-08-52CM-0074-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0004 TO PS2-08-52CM-0074 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1772 | PS2-08-52CM-0075-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0005 TO PS2-08-52CM-0075 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1773 | PS2-08-52CM-0076-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0006 TO PS2-08-52CM-0076 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1774 | PS2-08-52CM-0077-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0007 TO PS2-08-52CM-0077 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1775 | PS2-08-52CM-0078-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-52CM-0078 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1776 | PS2-08-52CM-0131-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-0131 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1777 | PS2-08-52CM-0931-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-52CM-0931 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1778 | PS2-08-52CM-1201-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-52CM-1201 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1779 | PS2-08-52CM-1501-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-52CM-1501 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1780 | PS2-08-52CM-1601-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-52CM-1601 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-1781 | PS2-08-71SK-1201-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1201 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1782 | PS2-08-71SK-1202-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1202 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1783 | PS2-08-71SK-1203A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1203A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1784 | PS2-08-71SK-1203B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1203B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1785 | PS2-08-71SK-1204A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1204A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1786 | PS2-08-71SK-1204B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1204B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1787 | PS2-08-71SK-1205A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1205A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1788 | PS2-08-71SK-1205B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1205B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1789 | PS2-08-71SK-1206A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1206A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1790 | PS2-08-71SK-1206B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1206B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1791 | PS2-08-71SK-1207A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1207A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1792 | PS2-08-71SK-1207B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1207B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1793 | PS2-08-71SK-1208A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1208A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1794 | PS2-08-71SK-1208B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1208B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1795 | PS2-08-71SK-1209A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1209A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1796 | PS2-08-71SK-1209B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1209B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1797 | PS2-08-71SK-1210-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1210 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1798 | PS2-08-71SK-1211A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1211A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1799 | PS2-08-71SK-1211B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1211B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1800 | PS2-08-71SK-1211C-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1211C | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1801 | PS2-08-71SK-1211D-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1211D | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1802 | PS2-08-71SK-1212A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1212A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1803 | PS2-08-71SK-1212B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1212B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1804 | PS2-08-71SK-1213A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1213A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1805 | PS2-08-71SK-1213B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1213B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1806 | PS2-08-71SK-1214A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1214A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1807 | PS2-08-71SK-1214B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1214B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1808 | PS2-08-71SK-1215-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1215 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1809 | PS2-08-71SK-1216-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1216 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1810 | PS2-08-71SK-1217A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1217A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1811 | PS2-08-71SK-1217B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1217B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1812 | PS2-08-71SK-1217C-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1217C | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1813 | PS2-08-71SK-1217D-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-71SK-1217D | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1814 | PS2-08-71SK-1501A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1501A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1815 | PS2-08-71SK-1501B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1501B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1816 | PS2-08-71SK-1502A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1502A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1817 | PS2-08-71SK-1502B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1502B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1818 | PS2-08-71SK-1503A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1503A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1819 | PS2-08-71SK-1503B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1503B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1820 | PS2-08-71SK-1504-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1504 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1821 | PS2-08-71SK-1505-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1505 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1822 | PS2-08-71SK-1506A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1506A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1823 | PS2-08-71SK-1506B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1506B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1824 | PS2-08-71SK-1507-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-71SK-1507 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1825 | PS2-08-71SK-1601A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-71SK-1601A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1826 | PS2-08-71SK-1601B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-71SK-1601B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1827 | PS2-08-71SK-1602A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-71SK-1602A | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1828 | PS2-08-71SK-1602B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-71SK-1602B | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1829 | PS2-08-71SK-1603-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-71SK-1603 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1830 | PS2-08-71SK-1604-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-71SK-1604 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1831 | PS2-08-71SK-1605-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1601 TO PS2-08-71SK-1605 | #N/A | UG-MID-65-SSF1-177120 | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-1832 | PS2-08-85AP-0001-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0023 TO PS2-08-85AP-0001 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00275-1833 | PS2-08-85AP-0002-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0024 TO PS2-08-85AP-0002 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00275-1834 | PS2-08-85AP-0003-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-0021 TO PS2-08-85AP-0003 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00275-1835 | PS2-08-85AP-0004-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-0022 TO PS2-08-85AP-0004 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00275-1836 | PS2-08-85BT-0023-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-85BT-0023 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00275-1837 | PS2-08-85BT-0024-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-85BT-0024 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00275-1838 | PS2-08-85CP-1201-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-85CP-1201 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00275-1839 | PS2-08-85CP-1202-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-85CP-1202 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00275-1840 | PS2-08-85CP-1501-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-85CP-1501 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00275-1841 | PS2-08-85CP-1601-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1601 TO PS2-08-85CP-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00275-4643 | PS2-08-11CB-1001-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-4644 | PS2-08-11CB-1001-CA02 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-4645 | PS2-08-11CB-1001-CA03 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-4646 | PS2-08-11CB-1001-CA04 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-4647 | PS2-08-11CB-1001-CA05 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-4648 | PS2-08-11CB-1001-CA06 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-4649 | PS2-08-11CB-1001-CA07 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-4650 | PS2-08-11CB-1001-CA08 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-4651 | PS2-08-11CB-1001-CA09 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-4652 | PS2-08-11CB-1001-CA10 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-4653 | PS2-08-11CB-1001-CA11 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-4654 | PS2-08-11CB-1001-CA12 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-4655 | PS2-08-12AP-1001-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12AP-1001 | EITS |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-4656 | PS2-08-12AP-1002-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12AP-1002 | EITS |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00275-4657 | PS2-08-13CB-1001-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4658 | PS2-08-13CB-1001-CA02 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4659 | PS2-08-13CB-1001-CA03 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4660 | PS2-08-13CB-1001-CA04 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4661 | PS2-08-13CB-1001-CA05 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4662 | PS2-08-13CB-1001-CA06 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4663 | PS2-08-13CB-1001-CA07 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4664 | PS2-08-13CB-1001-CA08 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4665 | PS2-08-13CB-1001-CA09 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4666 | PS2-08-13CB-1001-CA10 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4667 | PS2-08-13CB-1001-CA11 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4668 | PS2-08-13CB-1001-CA12 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4669 | PS2-08-13CB-1001-CA13 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4670 | PS2-08-13CB-1001-CA14 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4671 | PS2-08-13CB-1001-CA15 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4672 | PS2-08-13CB-1001-CA16 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4673 | PS2-08-13CB-1001-CA17 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4674 | PS2-08-13CB-1001-CA18 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4675 | PS2-08-13CB-1001-CA19 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4676 | PS2-08-13CB-1001-CA20 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4677 | PS2-08-13CB-1001-CA21 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4678 | PS2-08-13CB-1001-CA22 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4679 | PS2-08-13CB-1001-CA23 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4680 | PS2-08-13CB-1001-CA24 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00275-4681 | PS2-08-15CB-1001-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4682 | PS2-08-15CB-1001-CA02 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4683 | PS2-08-15CB-1001-CA03 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4684 | PS2-08-15CB-1001-CA04 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4685 | PS2-08-15CB-1001-CA05 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4686 | PS2-08-15CB-1001-CA06 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4687 | PS2-08-15CB-1001-CA07 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4688 | PS2-08-15CB-1001-CA08 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4689 | PS2-08-15CB-1001-CA09 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4690 | PS2-08-15CB-1001-CA10 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4691 | PS2-08-15CB-1001-CA11 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4692 | PS2-08-15CB-1001-CA12 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4693 | PS2-08-15CB-1001-CA13 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4694 | PS2-08-15CB-1001-CA14 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4695 | PS2-08-15CB-1001-CA15 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4696 | PS2-08-15CB-1001-CA16 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4697 | PS2-08-15CB-1001-CA17 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4698 | PS2-08-15CB-1001-CA18 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00275-4699 | PS2-08-35CB-1001-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4700 | PS2-08-35CB-1001-CA02 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4701 | PS2-08-35CB-1001-CA03 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4702 | PS2-08-35CB-1001-CA04 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4703 | PS2-08-35CB-1001-CA05 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4704 | PS2-08-35CB-1001-CA06 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4705 | PS2-08-35CB-1001-CA07 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4706 | PS2-08-35CB-1001-CA08 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4707 | PS2-08-35CB-1001-CA09 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4708 | PS2-08-35CB-1001-CA10 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4709 | PS2-08-35CB-1001-CA11 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4710 | PS2-08-35CB-1001-CA12 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4711 | PS2-08-35CB-1001-CA13 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4712 | PS2-08-35CB-1001-CA14 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4713 | PS2-08-35CB-1001-CA15 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4714 | PS2-08-35CB-1001-CA16 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4715 | PS2-08-35CB-1001-CA17 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4716 | PS2-08-35CB-1001-CA18 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4717 | PS2-08-35CB-1001-CA19 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-04-PNC-0001 | EITS |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00275-4718 | PS2-08-52CM-1001-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1001 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-4719 | PS2-08-52CM-1002-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1002 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-4720 | PS2-08-52CM-1003-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1003 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-4721 | PS2-08-52CM-1004-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1004 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-4722 | PS2-08-52CM-1011-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1011 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-4723 | PS2-08-52CM-1012-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1012 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-4724 | PS2-08-52CM-1013-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1013 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-4725 | PS2-08-52CM-1014-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1014 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-4726 | PS2-08-52CM-1015-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1015 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-4727 | PS2-08-52CM-1016-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-1016 | EITS |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00275-4728 | PS2-08-71SK-1001A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1001A | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-4729 | PS2-08-71SK-1001B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1001B | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-4730 | PS2-08-71SK-1002A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1002A | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-4731 | PS2-08-71SK-1002B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1002B | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-4732 | PS2-08-71SK-1003A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1003A | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-4733 | PS2-08-71SK-1003B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1003B | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-4734 | PS2-08-71SK-1004A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1004A | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-4735 | PS2-08-71SK-1004B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1004B | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-4736 | PS2-08-71SK-1005A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1005A | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-4737 | PS2-08-71SK-1005B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1005B | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-4738 | PS2-08-71SK-1006A-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1006A | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-4739 | PS2-08-71SK-1006B-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-71SK-1006B | EITS |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00275-4740 | PS2-08-85CP-1001-CA01 | TIX01 - RJ45 Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-85CP-1001 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00276-1168 | PS2-09-LB-0006-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-04-PNC-0001 TO PS2-09-LB-0006 | CPP AGI | UG-MID-65-WPR2-160500 | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | CPP-RFI-65-16-04-0206
T-00276-1169 | PS2-09-LB-0008-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-04-PNC-0001 TO PS2-09-LB-0008 | CPP AGI | UG-MID-65-WPR2-160500 | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #N/A
T-00276-1170 | PS2-53-LA-0001-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-04-PNC-0001 TO PS2-53-LA-0001 | CPP AGI | UG-MID-65-WPR2-160500 | PS2-53-03 - Water Treatment Purification Package |  |  |  | Construction not yet started |  | #N/A
T-00276-1263 | PS2-08-11CB-1201-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-11CB-1201 | #N/A | UG-MID-65-SSF1-171120 | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00276-1264 | PS2-08-11CB-1501-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-11CB-1501 | #N/A | UG-MID-65-SSF1-171120 | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0184
T-00276-1265 | PS2-08-11CB-1601-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-11CB-1601 | #N/A | UG-MID-65-SSF1-171120 | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00276-1266 | PS2-08-12BT-0101-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0101 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00276-1267 | PS2-08-12BT-0102-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0102 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00276-1268 | PS2-08-12BT-0104-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0104 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00276-1269 | PS2-08-12BT-0105-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0105 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00276-1270 | PS2-08-12BT-0107-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0107 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00276-1271 | PS2-08-15CP-0001-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-15CP-0001 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00276-1272 | PS2-08-15CP-0002-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0001 TO PS2-08-15CP-0002 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00276-1273 | PS2-08-15CP-0003-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0002 TO PS2-08-15CP-0003 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00276-1274 | PS2-08-15CP-0004-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-15CP-0004 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00276-1275 | PS2-08-15CP-0004-CX02 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0004 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00276-1276 | PS2-08-15CP-0005-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0005 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00276-1277 | PS2-08-15CP-0006-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0005 TO PS2-08-15CP-0006 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00276-1278 | PS2-08-15CP-0007-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0006 TO PS2-08-15CP-0007 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00276-1279 | PS2-08-15CP-0008-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0007 TO PS2-08-15CP-0008 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00276-1280 | PS2-08-36SP-0101-CX02 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-36SP-0101 | #N/A | UG-MID-65-SSF1-173620 | PS2-08-36 - Pipeline FO Cable & EPRS |  |  |  | Construction not yet started |  | #N/A
T-00276-1281 | PS2-08-36SP-0102-CX02 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-36SP-0102 | #N/A | UG-MID-65-SSF1-173620 | PS2-08-36 - Pipeline FO Cable & EPRS |  |  |  | Construction not yet started |  | #N/A
T-00276-1282 | PS2-08-52CM-0132-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-0132 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00276-1283 | PS2-08-52CM-0133-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-0133 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00276-1284 | PS2-08-52CM-0134-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-0134 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00276-1285 | PS2-08-83SP-1001-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CB-1001 | #N/A | UG-MID-65-SSF1-178320 | PS2-08-83 - Perimeter & Pipeline intrusion detection system |  |  |  | Construction not yet started |  | #N/A
T-00276-1286 | PS2-08-85CP-0021-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-85CP-0021 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00276-1287 | PS2-08-85CP-0021-CX02 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-85CP-0021 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00276-1288 | PS2-08-85CP-0022-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-85CP-0022 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00276-1289 | PS2-08-85CP-0022-CX02 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-85CP-0022 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00276-1581 | PS2-08-13CB-1001-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00276-1582 | PS2-08-15CB-1001-CX01 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00276-1583 | PS2-08-15CB-1001-CX02 | TIX02 - Fiber Optic cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00278-0029 | PS2-08-23AN-0001-CV01 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23LA-1202 TO PS2-08-23AN-0001 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00278-0030 | PS2-08-23AN-0002-CV01 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23LA-1501 TO PS2-08-23AN-0002 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00278-0031 | PS2-08-23AN-0901-CV01 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23LA-1602 TO PS2-08-23AN-0901 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00278-0032 | PS2-08-23AN-1201-CV01 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23LA-1201 TO PS2-08-23AN-1201 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00278-0033 | PS2-08-23LA-1202-CV01 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23BS-1201 TO PS2-08-23LA-1202 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00278-0034 | PS2-08-23LA-1501-CV01 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23BS-1501 TO PS2-08-23LA-1501 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00278-0035 | PS2-08-23LA-1602-CV01 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1601 TO PS2-08-23LA-1602 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00278-0036 | PS2-08-23SL-1601-CV01 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1601 TO PS2-08-23SL-1601 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00278-0037 | PS2-08-23SL-1601-CV02 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23AN-1601 TO PS2-08-23SL-1601 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00278-0038 | PS2-08-23SL-1601-CV03 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23LA-1201 TO PS2-08-23SL-1601 | #N/A | UG-MID-65-SSF1-172320 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00278-0039 | PS2-08-34AN-0001-CV01 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-34LA-1201 TO PS2-08-34AN-0001 | #N/A | UG-MID-65-SSF1-173420 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00278-0040 | PS2-08-34AN-0002-CV01 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-34LA-1501 TO PS2-08-34AN-0002 | #N/A | UG-MID-65-SSF1-173420 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00278-0041 | PS2-08-34LA-1201-CV01 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-34DS-1201 TO PS2-08-34LA-1201 | #N/A | UG-MID-65-SSF1-173420 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00278-0042 | PS2-08-34LA-1501-CV01 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-34DS-1501 TO PS2-08-34LA-1501 | #N/A | UG-MID-65-SSF1-173420 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00278-0253 | PS2-08-23AN-0003-CV01 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23AN-0003 TO PS2-08-23LA-1001 | EITS |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00278-0254 | PS2-08-23AN-1001-CV01 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23SL-1001 TO PS2-08-23AN-1001 | EITS |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00278-0255 | PS2-08-23AN-1001-CV02 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23SL-1001 TO PS2-08-23AN-1002 | EITS |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00278-0256 | PS2-08-23LA-1001-CV01 | TIX04 - Coaxial Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-23LA-1001 TO PS2-08-23SL-1001 | EITS |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00279-1717 | PS2-08-01BT-0001-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01BT-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00279-1718 | PS2-08-01BT-0001-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01OC-0001 TO PS2-08-01BT-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1719 | PS2-08-01BT-0002-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01BT-0002 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1720 | PS2-08-01BT-0002-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01OC-0001 TO PS2-08-01BT-0002 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1721 | PS2-08-01BT-0003-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0506 TO PS2-08-01BT-0003 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1722 | PS2-08-01BT-0003-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01BT-0003 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1723 | PS2-08-01BT-0003-CR03 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01OC-0002 TO PS2-08-01BT-0003 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1724 | PS2-08-01BT-0004-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0605 TO PS2-08-01BT-0004 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1725 | PS2-08-01BT-0004-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01OC-0002 TO PS2-08-01BT-0004 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1726 | PS2-08-01BT-1201-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1601 TO PS2-08-01BT-1201 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1727 | PS2-08-01BT-1201-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1201 TO PS2-08-01BT-1203 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1728 | PS2-08-01BT-1202-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1602 TO PS2-08-01BT-1202 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1729 | PS2-08-01BT-1202-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1202 TO PS2-08-01BT-1203 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1730 | PS2-08-01BT-1203-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01BT-1203 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1731 | PS2-08-01BT-1203-CJ02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01BT-1203 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1732 | PS2-08-01BT-1203-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-01BT-1203 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1733 | PS2-08-01BT-1203-CN02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-01BT-1203 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1734 | PS2-08-01BT-1501-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0103 TO PS2-08-01BT-1501 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00279-1735 | PS2-08-01BT-1501-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1501 TO PS2-08-01BT-1503 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1736 | PS2-08-01BT-1502-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-0002 TO PS2-08-01BT-1502 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1737 | PS2-08-01BT-1502-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1502 TO PS2-08-01BT-1503 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1738 | PS2-08-01BT-1503-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01BT-1503 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00279-1739 | PS2-08-01BT-1503-CJ02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01BT-1503 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00279-1740 | PS2-08-01BT-1503-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-01BT-1503 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1741 | PS2-08-01BT-1503-CN02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-01BT-1503 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1742 | PS2-08-01BT-1601-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1501 TO PS2-08-01BT-1601 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00279-1743 | PS2-08-01BT-1602-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0203 TO PS2-08-01BT-1602 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00279-1744 | PS2-08-01LS-0101-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01OC-0001 TO PS2-08-01LS-0101 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1745 | PS2-08-01LS-0102-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1501 TO PS2-08-01LS-0102 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1746 | PS2-08-01LS-0103-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-0001 TO PS2-08-01LS-0103 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00279-1747 | PS2-08-01LS-0104-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1601 TO PS2-08-01LS-0104 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1748 | PS2-08-01LS-0105-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0104 TO PS2-08-01LS-0105 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1749 | PS2-08-01LS-0106-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0105 TO PS2-08-01LS-0106 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1750 | PS2-08-01LS-0107-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0106 TO PS2-08-01LS-0107 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1751 | PS2-08-01LS-0108-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0107 TO PS2-08-01LS-0108 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1752 | PS2-08-01LS-0108-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1601 TO PS2-08-01LS-0108 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1753 | PS2-08-01LS-0109-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0109 TO PS2-08-01LS-0110 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1754 | PS2-08-01LS-0109-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1201 TO PS2-08-01LS-0109 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1755 | PS2-08-01LS-0110-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0110 TO PS2-08-01LS-0112 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1756 | PS2-08-01LS-0111-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1201 TO PS2-08-01LS-0111 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1757 | PS2-08-01LS-0112-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1201 TO PS2-08-01LS-0112 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1758 | PS2-08-01LS-0113-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1201 TO PS2-08-01LS-0113 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1759 | PS2-08-01LS-0114-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0113 TO PS2-08-01LS-0114 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1760 | PS2-08-01LS-0114-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0114 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1761 | PS2-08-01LS-0122-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0122 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1762 | PS2-08-01LS-0201-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01OC-0001 TO PS2-08-01LS-0201 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1763 | PS2-08-01LS-0202-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1502 TO PS2-08-01LS-0202 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1764 | PS2-08-01LS-0203-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1502 TO PS2-08-01LS-0203 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1765 | PS2-08-01LS-0204-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1602 TO PS2-08-01LS-0204 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1766 | PS2-08-01LS-0205-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0204 TO PS2-08-01LS-0205 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1767 | PS2-08-01LS-0206-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0205 TO PS2-08-01LS-0206 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1768 | PS2-08-01LS-0207-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0206 TO PS2-08-01LS-0207 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1769 | PS2-08-01LS-0208-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0207 TO PS2-08-01LS-0208 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1770 | PS2-08-01LS-0209-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0208 TO PS2-08-01LS-0209 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1771 | PS2-08-01LS-0209-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1602 TO PS2-08-01LS-0209 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1772 | PS2-08-01LS-0210-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1202 TO PS2-08-01LS-0210 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1773 | PS2-08-01LS-0211-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0210 TO PS2-08-01LS-0211 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1774 | PS2-08-01LS-0212-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0211 TO PS2-08-01LS-0212 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1775 | PS2-08-01LS-0213-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1202 TO PS2-08-01LS-0213 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1776 | PS2-08-01LS-0214-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0213 TO PS2-08-01LS-0214 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1777 | PS2-08-01LS-0214-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0214 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1778 | PS2-08-01LS-0215-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0212 TO PS2-08-01LS-0215 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1779 | PS2-08-01LS-0215-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1202 TO PS2-08-01LS-0215 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1780 | PS2-08-01LS-0222-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0222 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1781 | PS2-08-01LS-0301-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0301 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1782 | PS2-08-01LS-0302-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0301 TO PS2-08-01LS-0302 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1783 | PS2-08-01LS-0303-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0302 TO PS2-08-01LS-0303 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1784 | PS2-08-01LS-0304-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0303 TO PS2-08-01LS-0304 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0184
T-00279-1785 | PS2-08-01LS-0305-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0304 TO PS2-08-01LS-0305 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1786 | PS2-08-01LS-0306-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0305 TO PS2-08-01LS-0306 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1787 | PS2-08-01LS-0307-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0306 TO PS2-08-01LS-0307 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1788 | PS2-08-01LS-0307-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0307 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1789 | PS2-08-01LS-0401-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0401 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00279-1790 | PS2-08-01LS-0402-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0401 TO PS2-08-01LS-0402 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00279-1791 | PS2-08-01LS-0403-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0402 TO PS2-08-01LS-0403 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0184
T-00279-1792 | PS2-08-01LS-0404-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0403 TO PS2-08-01LS-0404 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1793 | PS2-08-01LS-0405-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0404 TO PS2-08-01LS-0405 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1794 | PS2-08-01LS-0406-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0405 TO PS2-08-01LS-0406 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1795 | PS2-08-01LS-0406-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0406 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1796 | PS2-08-01LS-0501-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0501 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1797 | PS2-08-01LS-0502-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0501 TO PS2-08-01LS-0502 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1798 | PS2-08-01LS-0503-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0502 TO PS2-08-01LS-0503 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1799 | PS2-08-01LS-0504-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0503 TO PS2-08-01LS-0504 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1800 | PS2-08-01LS-0505-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0504 TO PS2-08-01LS-0505 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1801 | PS2-08-01LS-0506-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0505 TO PS2-08-01LS-0506 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1802 | PS2-08-01LS-0507-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01OC-0002 TO PS2-08-01LS-0507 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1803 | PS2-08-01LS-0601-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0601 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1804 | PS2-08-01LS-0602-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0601 TO PS2-08-01LS-0602 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1805 | PS2-08-01LS-0603-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0602 TO PS2-08-01LS-0603 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1806 | PS2-08-01LS-0604-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0603 TO PS2-08-01LS-0604 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1807 | PS2-08-01LS-0605-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0604 TO PS2-08-01LS-0605 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1808 | PS2-08-01LS-0606-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01OC-0002 TO PS2-08-01LS-0606 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1809 | PS2-08-01LS-0607-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-0004 TO PS2-08-01LS-0607 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1810 | PS2-08-01LS-0607-CR02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01LS-0607 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1811 | PS2-08-01OC-0001-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01OC-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00279-1812 | PS2-08-01OC-0001-CJ02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01OC-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00279-1813 | PS2-08-01OC-0001-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01OC-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00279-1814 | PS2-08-01OC-0001-CN02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01OC-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00279-1815 | PS2-08-01OC-0002-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01OC-0002 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1816 | PS2-08-01OC-0002-CJ02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01OC-0002 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1817 | PS2-08-01OC-0002-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01OC-0002 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1818 | PS2-08-01OC-0002-CN02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01MP-0001 TO PS2-08-01OC-0002 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-1819 | PS2-08-03TP-0001-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-03TP-0001 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00279-1820 | PS2-08-03TP-0001-CJ02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-03FB-0001 TO PS2-08-03TP-0001 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00279-1821 | PS2-08-03TP-0002-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-03TP-0002 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00279-1822 | PS2-08-03TP-0002-CJ02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-03FB-0002 TO PS2-08-03TP-0002 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00279-1823 | PS2-08-03TP-0101-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-03TP-0101 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00279-1824 | PS2-08-03TP-0101-CJ02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-03FB-0101 TO PS2-08-03TP-0101 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00279-1825 | PS2-08-03TP-0102-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-03TP-0102 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00279-1826 | PS2-08-03TP-0102-CJ02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-03FB-0102 TO PS2-08-03TP-0102 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00279-1827 | PS2-08-03TP-0103-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-03TP-0103 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0184
T-00279-1828 | PS2-08-03TP-0103-CJ02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-03FB-0103 TO PS2-08-03TP-0103 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00279-1829 | PS2-08-03TP-0104-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-03TP-0104 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00279-1830 | PS2-08-03TP-0104-CJ02 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-03FB-0104 TO PS2-08-03TP-0104 | #N/A | UG-MID-65-SSF1-170320 | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00279-1831 | PS2-08-12AP-0101-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-12BT-0101 TO PS2-08-12AP-0101 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00279-1832 | PS2-08-12AP-0102-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-12BT-0102 TO PS2-08-12AP-0102 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00279-1833 | PS2-08-12AP-0104-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-12BT-0104 TO PS2-08-12AP-0104 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00279-1834 | PS2-08-12AP-0105-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-12BT-0105 TO PS2-08-12AP-0105 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00279-1835 | PS2-08-12AP-0107-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-12BT-0107 TO PS2-08-12AP-0107 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00279-1836 | PS2-08-13CB-1601-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-04-PMC-0003 TO PS2-08-13CB-1601 | #N/A | UG-MID-65-SSF1-171320 | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00279-1837 | PS2-08-61BT-0001-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-14CB-1601 TO PS2-08-61BT-0001 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00279-1838 | PS2-08-85BT-0001-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-85BT-0001 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1839 | PS2-08-85BT-0002-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-85BT-0002 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1840 | PS2-08-85BT-0003-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-85BT-0003 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1841 | PS2-08-85BT-0004-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0005 TO PS2-08-85BT-0004 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1842 | PS2-08-85BT-0005-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0005 TO PS2-08-85BT-0005 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1843 | PS2-08-85BT-0006-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0005 TO PS2-08-85BT-0006 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1844 | PS2-08-85BT-0007-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0005 TO PS2-08-85BT-0007 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1845 | PS2-08-85BT-0008-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-85BT-0008 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1846 | PS2-08-85BT-0009-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-85BT-0009 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1847 | PS2-08-85BT-0010-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-85BT-0010 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1848 | PS2-08-85BT-0011-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-85BT-0011 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1849 | PS2-08-85BT-0012-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-85BT-0012 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1850 | PS2-08-85BT-0013-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0002 TO PS2-08-85BT-0013 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1851 | PS2-08-85BT-0014-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0002 TO PS2-08-85BT-0014 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1852 | PS2-08-85BT-0015-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0002 TO PS2-08-85BT-0015 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1853 | PS2-08-85BT-0016-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0002 TO PS2-08-85BT-0016 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1854 | PS2-08-85BT-0017-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-85BT-0017 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1855 | PS2-08-85BT-0018-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-85BT-0018 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1856 | PS2-08-85BT-0020-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-85BT-0020 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1857 | PS2-08-85BT-0025-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-85BT-0025 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1858 | PS2-08-85BT-1201-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1201 TO PS2-08-85BT-1201 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1859 | PS2-08-85BT-1202-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1201 TO PS2-08-85BT-1202 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1860 | PS2-08-85BT-1203-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1201 TO PS2-08-85BT-1203 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1861 | PS2-08-85BT-1501-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1501 TO PS2-08-85BT-1501 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1862 | PS2-08-85BT-1601-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1601 TO PS2-08-11CB-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1863 | PS2-08-85BT-1602-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1602 TO PS2-08-11CB-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1864 | PS2-08-85BT-1603-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1601 TO PS2-08-85BT-1603 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1865 | PS2-08-85BT-1604-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1601 TO PS2-08-85BT-1604 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1866 | PS2-08-85BT-1605-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1601 TO PS2-08-85BT-1605 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1867 | PS2-08-85DC-0001-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0001 TO PS2-08-85DC-0001 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1868 | PS2-08-85DC-0002-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0002 TO PS2-08-85DC-0002 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1869 | PS2-08-85DC-0003-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0003 TO PS2-08-85DC-0003 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1870 | PS2-08-85DC-0004-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0004 TO PS2-08-85DC-0004 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1871 | PS2-08-85DC-0005-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0005 TO PS2-08-85DC-0005 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1872 | PS2-08-85DC-0006-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0006 TO PS2-08-85DC-0006 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1873 | PS2-08-85DC-0007-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0008 TO PS2-08-85DC-0007 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1874 | PS2-08-85DC-0008-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0010 TO PS2-08-85DC-0008 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1875 | PS2-08-85DC-0009-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0008 TO PS2-08-85DC-0009 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1876 | PS2-08-85DC-0010-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0009 TO PS2-08-85DC-0010 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1877 | PS2-08-85DC-0011-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0011 TO PS2-08-85DC-0011 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1878 | PS2-08-85DC-0012-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0012 TO PS2-08-85DC-0012 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1879 | PS2-08-85DC-0013-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0014 TO PS2-08-85DC-0013 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1880 | PS2-08-85DC-0014-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0013 TO PS2-08-85DC-0014 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1881 | PS2-08-85DC-0015-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0015 TO PS2-08-85DC-0015 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1882 | PS2-08-85DC-0016-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0016 TO PS2-08-85DC-0016 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1883 | PS2-08-85DC-0017-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0017 TO PS2-08-85DC-0017 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1884 | PS2-08-85DC-0018-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0018 TO PS2-08-85DC-0018 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1885 | PS2-08-85DC-0019-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0019 TO PS2-08-85DC-0019 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1886 | PS2-08-85DC-0020-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0020 TO PS2-08-85DC-0020 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1887 | PS2-08-85DC-0021-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0001 TO PS2-08-85DC-0021 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1888 | PS2-08-85DC-0022-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0020 TO PS2-08-85DC-0022 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1889 | PS2-08-85DC-0023-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0009 TO PS2-08-85DC-0023 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1890 | PS2-08-85DC-0024-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0025 TO PS2-08-85DC-0024 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1891 | PS2-08-85DC-0025-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0025 TO PS2-08-85DC-0025 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1892 | PS2-08-85DC-1201-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1202 TO PS2-08-85DC-1201 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1893 | PS2-08-85DC-1202-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1201 TO PS2-08-85DC-1202 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1894 | PS2-08-85DC-1203-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1203 TO PS2-08-85DC-1203 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1895 | PS2-08-85DC-1501-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1501 TO PS2-08-85DC-1501 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1896 | PS2-08-85DC-1601-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1601 TO PS2-08-85DC-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1897 | PS2-08-85DC-1602-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1602 TO PS2-08-85DC-1602 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1898 | PS2-08-85DC-1603-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1603 TO PS2-08-85DC-1603 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1899 | PS2-08-85DC-1604-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1604 TO PS2-08-85DC-1604 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1900 | PS2-08-85DC-1605-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1605 TO PS2-08-85DC-1605 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1901 | PS2-08-85ML-0001-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0017 TO PS2-08-85ML-0001 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1902 | PS2-08-85ML-1201-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1202 TO PS2-08-85ML-1201 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1903 | PS2-08-85ML-1501-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1501 TO PS2-08-85ML-1501 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1904 | PS2-08-85ML-1601-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1601 TO PS2-08-85ML-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1905 | PS2-08-85ML-1602-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1602 TO PS2-08-85ML-1602 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1906 | PS2-08-85PB-0001-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0017 TO PS2-08-85PB-0001 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1907 | PS2-08-85PB-1201-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1202 TO PS2-08-85PB-1201 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1908 | PS2-08-85PB-1501-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1501 TO PS2-08-85PB-1501 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1909 | PS2-08-85PB-1502-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1501 TO PS2-08-85PB-1502 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1910 | PS2-08-85PB-1601-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1601 TO PS2-08-85PB-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-1911 | PS2-08-85PB-1602-CJ01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1602 TO PS2-08-85PB-1602 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-4172 | PS2-08-01LS-0115-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-01LS-0115 | EITS |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-4173 | PS2-08-01LS-0116-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0115 TO PS2-08-01LS-0116 | EITS |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-4174 | PS2-08-01LS-0117-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-01LS-0117 | EITS |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-4175 | PS2-08-01LS-0118-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0117 TO PS2-08-01LS-0118 | EITS |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-4176 | PS2-08-01LS-0119-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0118 TO PS2-08-01LS-0119 | EITS |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-4177 | PS2-08-01LS-0120-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0119 TO PS2-08-01LS-0120 | EITS |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-4178 | PS2-08-01LS-0121-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0120 TO PS2-08-01LS-0121 | EITS |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-4179 | PS2-08-01LS-0122-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0121 TO PS2-08-01LS-0122 | EITS |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-4180 | PS2-08-01LS-0216-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0215 TO PS2-08-01LS-0216 | EITS |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-4181 | PS2-08-01LS-0217-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0216 TO PS2-08-01LS-0217 | EITS |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-4182 | PS2-08-01LS-0218-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-01LS-0218 | EITS |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-4183 | PS2-08-01LS-0219-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0218 TO PS2-08-01LS-0219 | EITS |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-4184 | PS2-08-01LS-0220-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0219 TO PS2-08-01LS-0220 | EITS |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-4185 | PS2-08-01LS-0221-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0220 TO PS2-08-01LS-0221 | EITS |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-4186 | PS2-08-01LS-0222-CR01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01LS-0221 TO PS2-08-01LS-0222 | EITS |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00279-4187 | PS2-08-85BT-1001-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-4188 | PS2-08-85BT-1003-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1003 TO PS2-08-15CB-1001 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-4189 | PS2-08-85ML-1001-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1001 TO PS2-08-85ML-1001 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00279-4190 | PS2-08-85ML-1002-CN01 | TIX09 - Telecom power and control cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1003 TO PS2-08-85ML-1002 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0123 | PS2-08-01MP-0001-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-01MP-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00280-0124 | PS2-08-01MP-0001-CC02 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-01MP-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00280-0125 | PS2-08-01MP-0001-CC03 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-01MP-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00280-0126 | PS2-08-01MP-0001-CC04 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-01MP-0001 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00280-0127 | PS2-08-01PA-1201-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1203 TO PS2-08-01PA-1201 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00280-0128 | PS2-08-01PA-1501-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-01BT-1503 TO PS2-08-01PA-1501 | #N/A | UG-MID-65-SSF1-170120 | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00280-0129 | PS2-08-13CB-1601-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-14CB-1601 TO PS2-08-13CB-1601 | #N/A | UG-MID-65-SSF1-179320 | PS2-08-93 - Telecom Monitoring System |  |  |  | Construction not yet started |  | #N/A
T-00280-0130 | PS2-08-52TK-0032-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-52CM-0032 TO PS2-08-52TK-0032 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00280-0131 | PS2-08-52TK-0033-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-52CM-0033 TO PS2-08-52TK-0033 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00280-0132 | PS2-08-52TK-0034-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-52CM-0034 TO PS2-08-52TK-0034 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00280-0133 | PS2-08-52TK-0131-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-52CM-0131 TO PS2-08-52TK-0131 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00280-0134 | PS2-08-52TK-0132-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-52CM-0132 TO PS2-08-52TK-0132 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00280-0135 | PS2-08-52TK-0133-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-52CM-0133 TO PS2-08-52TK-0133 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00280-0136 | PS2-08-52TK-0134-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-52CM-0134 TO PS2-08-52TK-0134 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00280-0137 | PS2-08-52TK-0931-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-52CM-0931 TO PS2-08-52TK-0931 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00280-0138 | PS2-08-61BT-0001-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-14CB-1601 TO PS2-08-61BT-0001 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00280-0139 | PS2-08-61BT-0001-CC02 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-14CB-1601 TO PS2-08-61BT-0001 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00280-0140 | PS2-08-61BT-0002-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-14CB-1601 TO PS2-08-61BT-0002 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00280-0141 | PS2-08-61BT-0901-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-61BT-0001 TO PS2-08-61BT-0901 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00280-0142 | PS2-08-61SN-0003-CZ01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-61BT-0001 TO PS2-08-61SN-0003 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00280-0143 | PS2-08-61SN-0004-CZ01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-61BT-0001 TO PS2-08-61SN-0004 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00280-0144 | PS2-08-61SN-0005-CZ01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-61BT-0002 TO PS2-08-61SN-0005 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00280-0145 | PS2-08-61SN-0005-CZ02 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-61BT-0002 TO PS2-08-61SN-0005 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00280-0146 | PS2-08-61SN-0901-CZ01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-61BT-0901 TO PS2-08-61SN-0901 | #N/A | UG-MID-65-SSF1-176120 | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00280-0147 | PS2-08-85BG-1201-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1202 TO PS2-08-85BG-1201 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0148 | PS2-08-85BG-1601-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1601 TO PS2-08-85BG-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0149 | PS2-08-85BG-1602-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1602 TO PS2-08-85BG-1602 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0150 | PS2-08-85BR-0001-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1202 TO PS2-08-85BR-0001 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00280-0151 | PS2-08-85BR-0002-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1201 TO PS2-08-85BR-0002 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00280-0152 | PS2-08-85BR-0003-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-0021 TO PS2-08-85BR-0003 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0153 | PS2-08-85BR-0004-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-0022 TO PS2-08-85BR-0004 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0154 | PS2-08-85BR-0005-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1501 TO PS2-08-85BR-0005 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0155 | PS2-08-85BR-0006-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1501 TO PS2-08-85BR-0006 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0156 | PS2-08-85BR-1201-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1201 TO PS2-08-85BR-1201 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0157 | PS2-08-85BR-1202-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1202 TO PS2-08-85BR-1202 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0158 | PS2-08-85BR-1203-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1201 TO PS2-08-85BR-1203 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0159 | PS2-08-85BR-1501-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1501 TO PS2-08-85BR-1501 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0160 | PS2-08-85BR-1601-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1601 TO PS2-08-85BR-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0161 | PS2-08-85BR-1602-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1601 TO PS2-08-85BR-1602 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0162 | PS2-08-85BT-0017-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1501 TO PS2-08-85BT-0017 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0163 | PS2-08-85BT-0019-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1501 TO PS2-08-85BT-0019 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0164 | PS2-08-85BT-1202-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1201 TO PS2-08-85BT-1202 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0165 | PS2-08-85BT-1501-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1501 TO PS2-08-85BT-1501 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0166 | PS2-08-85BT-1601-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1601 TO PS2-08-85BT-1601 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0167 | PS2-08-85BT-1602-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1601 TO PS2-08-85BT-1602 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-0168 | PS2-82-MGV-0003-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-0019 TO PS2-82-MGV-0003 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-1113 | PS2-08-13CB-1001-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-13CB-1001 | EITS | UG-MID-65-SSF1-179320 | PS2-08-93 - Telecom Monitoring System |  |  |  | Construction not yet started |  | #N/A
T-00280-1143 | PS2-08-01IO-1001-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00280-1144 | PS2-08-01IO-1001-CC02 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00280-1145 | PS2-08-03GY-1001-CJ01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-11CB-1001 | EITS |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00280-1146 | PS2-08-13CB-1001-CC02 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-13CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-93 - Telecom Monitoring System |  |  |  | Construction not yet started |  | #N/A
T-00280-1147 | PS2-08-85BR-1001-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1001 TO PS2-08-85BR-1002 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-1148 | PS2-08-85BR-1002-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1001 TO PS2-08-85BR-1002 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-1149 | PS2-08-85BT-1001-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1001 TO PS2-08-85BT-1001 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-1150 | PS2-08-85BT-1002-CJ01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1001 TO PS2-08-85BT-1002 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-1151 | PS2-08-85BT-1003-CC01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1001 TO PS2-08-85BT-1003 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-1152 | PS2-08-85BT-1004-CJ01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1001 TO PS2-08-85BT-1004 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-1153 | PS2-08-85BT-1005-CJ01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85CP-1001 TO PS2-08-85BT-1005 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-1154 | PS2-08-85DC-1001-CJ01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1001 TO PS2-08-85DC-1001 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-1155 | PS2-08-85DC-1002-CJ01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1001 TO PS2-08-85DC-1002 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-1156 | PS2-08-85DC-1003-CJ01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1002 TO PS2-08-85DC-1003 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-1157 | PS2-08-85DC-1004-CJ01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1003 TO PS2-08-85DC-1004 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-1158 | PS2-08-85DC-1005-CJ01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1003 TO PS2-08-85DC-1005 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-1159 | PS2-08-85DC-1006-CJ01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1004 TO PS2-08-85DC-1006 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-1160 | PS2-08-85DC-1007-CJ01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1005 TO PS2-08-85DC-1007 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-1161 | PS2-08-85PB-1001-CJ01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1001 TO PS2-08-85PB-1001 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00280-1162 | PS2-08-85PB-1002-CJ01 | TIX10 - Multicore cable telecom | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-85BT-1003 TO PS2-08-85PB-1002 | EITS |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00281-0362 |  | TPX17 - Battery | PCOM - Precommissioning | E - Electrical |  | EITS | UT-MID-60-SSF1-150308 | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | 0
T-00281-0363 |  | TPX17 - Battery | PCOM - Precommissioning | E - Electrical |  | EITS | UT-MID-60-SSF1-150308 | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | 0
T-00284-0011 | PS2-25-PDIT-0034A | TJX06 - Tubing pressure test | PCOM - Precommissioning | I - Instrumentation | Diff Press Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134003 | PS2-25-02 - Crude Oil Export Pump A |  | STANCHION IN FABRICATION |  | Construction not yet started
T-00284-0012 | PS2-25-PDIT-0034B | TJX06 - Tubing pressure test | PCOM - Precommissioning | I - Instrumentation | Diff Press Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134004 | PS2-25-03 - Crude Oil Export Pump B |  | STANCHION IN FABRICATION |  | Construction not yet started
T-00284-0013 | PS2-25-PDIT-0034C | TJX06 - Tubing pressure test | PCOM - Precommissioning | I - Instrumentation | Diff Press Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134005 | PS2-25-04 - Crude Oil Export Pump C |  | STANCHION IN FABRICATION |  | Construction not yet started
T-00284-0014 | PS2-25-PDIT-0050 | TJX06 - Tubing pressure test | PCOM - Precommissioning | I - Instrumentation | Diff Press Ind Transmitter | CPP AGI | UG-MID-65-WPR2-134006 | PS2-25-06 - Crude Oil Export Pumps Discharge |  | STANCHION IN FABRICATION |  | Construction not yet started
T-00284-0015 | PS2-53-LIT-4101 | TJX06 - Tubing pressure test | PCOM - Precommissioning | I - Instrumentation | DP Level Ind Transmitter | CPP AGI | UG-MID-65-WPR2-135501 | PS2-53-01 - Utility Water Storage Tank |  | STANCHION IN FABRICATION |  | Construction not yet started
T-00284-0016 | PS2-53-LIT-4102 | TJX06 - Tubing pressure test | PCOM - Precommissioning | I - Instrumentation | DP Level Ind Transmitter | CPP AGI | UG-MID-65-WPR2-135501 | PS2-53-01 - Utility Water Storage Tank |  | STANCHION IN FABRICATION |  | Construction not yet started
T-00284-0135 | PS2-25-FCV-0003A | TJX06 - Tubing pressure test | PCOM - Precommissioning | I - Instrumentation | Flow Control Valve | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00284-0136 | PS2-25-FCV-0003B | TJX06 - Tubing pressure test | PCOM - Precommissioning | I - Instrumentation | Flow Control Valve | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope | #N/A
T-00284-0137 | PS2-25-FCV-0003C | TJX06 - Tubing pressure test | PCOM - Precommissioning | I - Instrumentation | Flow Control Valve | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00284-0138 | PS2-25-FCV-0004 | TJX06 - Tubing pressure test | PCOM - Precommissioning | I - Instrumentation | Flow Control Valve | CPP AGI |  | PS2-25-06 - Crude Oil Export Pumps Discharge |  | Piping Scope |  | Construction not yet started | Instrument installation - Piping (CPP2) Scope
T-00291-0119 | PS2-63-01_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-63-01 - Electrical Earthing |  |  |  | Construction not yet started |  | #N/A
T-00291-0120 | PS2-63-02_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-63-02 - Electrical Earthing - Office Building |  |  |  | Construction not yet started |  | #N/A
T-00291-0121 | PS2-63-03_PRC-ELECTRICAL-EITS | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-63-03 - Electrical Earthing - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00291-0122 | PS2-63-04_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-63-04 - Electrical Earthing - Workshop and Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00291-0123 | PS2-63-05_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-63-05 - Electrical Earthing - Guard House |  |  |  | Construction not yet started |  | #N/A
T-00291-0920 | PS2-01-01_PRC-ELECTRICAL-EITS | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | #N/A
T-00291-0921 | PS2-02-01_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-02-01 - Miscellaneous Safety equipment |  |  |  | Construction not yet started |  | #N/A
T-00291-0922 | PS2-03-01_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | #N/A
T-00291-0923 | PS2-03-05_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-03-05 - FZ-G1 - Guard House |  |  |  | Construction not yet started |  | #N/A
T-00291-0924 | PS2-05-01_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-05-01 - Emergency Diesel Generator Package |  |  |  | Construction not yet started |  | #N/A
T-00291-0925 | PS2-05-02_PRC-ELECTRICAL-EITS | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | #N/A
T-00291-0926 | PS2-06-01_PRC-ELECTRICAL-EITS | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00291-0927 | PS2-06-02_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-06-02 - AC UPS - Guard House |  |  |  | Construction not yet started |  | #N/A
T-00291-0928 | PS2-06-03_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-06-03 - AC DB - Office Building |  |  |  | Construction not yet started |  | #N/A
T-00291-0929 | PS2-06-04_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-06-04 - AC DB - Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00291-0930 | PS2-08-01_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00291-0931 | PS2-08-11_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00291-0932 | PS2-08-12_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00291-0933 | PS2-08-15_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00291-0934 | PS2-08-52_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00291-0935 | PS2-08-61_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00291-0936 | PS2-08-85_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00291-0937 | PS2-09-02_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-09-02 - HVAC for Guard House |  |  |  | Construction not yet started |  | #N/A
T-00291-0938 | PS2-09-04_PRC-ELECTRICAL-EITS | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00291-0939 | PS2-25-01_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00291-0940 | PS2-25-02_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00291-0941 | PS2-25-03_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00291-0942 | PS2-25-04_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00291-0943 | PS2-25-05_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #N/A
T-00291-0944 | PS2-25-06_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #N/A
T-00291-0945 | PS2-25-07_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00291-0946 | PS2-28-03_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | #N/A
T-00291-0947 | PS2-28-04_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started |  | #N/A
T-00291-0948 | PS2-28-05_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | #N/A
T-00291-0949 | PS2-28-06_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | #N/A
T-00291-0950 | PS2-28-07_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | #N/A
T-00291-0951 | PS2-28-08_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-28-08 - Open Drains (OD2) |  |  |  | Construction not yet started |  | #N/A
T-00291-0952 | PS2-28-09_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-28-09 - Open Drain Interceptor |  |  |  | Construction not yet started |  | #N/A
T-00291-0953 | PS2-53-01_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-53-01 - Utility Water Storage Tank |  |  |  | Construction not yet started |  | #N/A
T-00291-0954 | PS2-53-02_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-53-02 - Water Distribution Pump |  |  |  | Construction not yet started |  | #N/A
T-00291-0955 | PS2-53-03_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-53-03 - Water Treatment Purification Package |  |  |  | Construction not yet started |  | #N/A
T-00291-0956 | PS2-61-01_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00291-0957 | PS2-61-01_PRC-ELECTRICAL-EITS | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00291-0958 | PS2-61-02_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00291-0959 | PS2-61-02_PRC-ELECTRICAL-EITS | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00291-0960 | PS2-61-03_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00291-0961 | PS2-61-03_PRC-ELECTRICAL-EITS | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00291-0962 | PS2-61-04_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00291-0963 | PS2-61-04_PRC-ELECTRICAL-EITS | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00291-0964 | PS2-61-05_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-61-05 - Electrical Control System |  |  |  | Construction not yet started |  | #N/A
T-00291-0965 | PS2-61-05_PRC-ELECTRICAL-EITS | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-61-05 - Electrical Control System |  |  |  | Construction not yet started |  | #N/A
T-00291-0966 | PS2-61-06_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | #N/A
T-00291-0967 | PS2-61-07_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-61-07 - Outdoor Valves Distribution Board - PS2-61-IG-0015 |  |  |  | Construction not yet started |  | #N/A
T-00291-0968 | PS2-61-08_PRC-ELECTRICAL-EITS | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-61-08 - EITS 33kV Bld. Normal Auxiliary DP - PS2-61-IG-0008 |  |  |  | Construction not yet started |  | #N/A
T-00291-0969 | PS2-62-01_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00291-0970 | PS2-62-02_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00291-0971 | PS2-62-03_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00291-0972 | PS2-62-04_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  |  |  | Construction not yet started |  | #N/A
T-00291-0973 | PS2-62-05_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00291-0974 | PS2-62-06_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #N/A
T-00291-0975 | PS2-62-07_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00291-0976 | PS2-62-08_PRC-ELECTRICAL-EITS | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00291-0977 | PS2-62-09_PRC-ELECTRICAL-EITS | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00291-0978 | PS2-62-10_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00291-0979 | PS2-62-11_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00291-0980 | PS2-62-12_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00291-0981 | PS2-62-13_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | #N/A
T-00291-0982 | PS2-75-01_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | #N/A
T-00291-0983 | PS2-75-02_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | #N/A
T-00291-0984 | PS2-78-01_PRC-ELECTRICAL-EITS | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-78-01 - Lifting and handling equipment |  |  |  | Construction not yet started |  | #N/A
T-00291-0985 | PS2-79-01_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00291-0986 | PS2-79-02_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00291-0987 | PS2-79-03_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00291-0988 | PS2-79-04_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00291-0989 | PS2-79-05_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00291-0990 | PS2-82-01_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-82-01 - Office building |  |  |  | Construction not yet started |  | #N/A
T-00291-0991 | PS2-82-02_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-82-02 - Guard House |  |  |  | Construction not yet started |  | #N/A
T-00291-0992 | PS2-83-01_PRC-ELECTRICAL-EITS | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-83-01 - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00291-0993 | PS2-99-01_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-99-01 - Area Completion for Building Area West |  |  |  | Construction not yet started |  | #N/A
T-00291-0994 | PS2-99-02_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-99-02 - Area Completion for Building Area East |  |  |  | Construction not yet started |  | #N/A
T-00291-0995 | PS2-99-03_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-99-03 - Area Completion for Utility Area |  |  |  | Construction not yet started |  | #N/A
T-00291-0996 | PS2-99-04_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-99-04 - Area Completion for Power Distribution Area |  |  |  | Construction not yet started |  | #N/A
T-00291-0997 | PS2-99-05_PRC-ELECTRICAL-CPP | 2621E - Electrical | COM - Commissioning | E - Electrical | PRC Electrical | EACOP |  | PS2-99-05 - Area Completion for Process Area |  |  |  | Construction not yet started |  | #N/A
T-00292-0628 | PS2-01-01_PRC-INSTRUMENTATION-EITS | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | #N/A
T-00292-0629 | PS2-02-01_PRC-INSTRUMENTATION-EITS | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-02-01 - Miscellaneous Safety equipment |  |  |  | Construction not yet started |  | #N/A
T-00292-0630 | PS2-03-01_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | #N/A
T-00292-0631 | PS2-03-01_PRC-INSTRUMENTATION-EITS | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | #N/A
T-00292-0632 | PS2-03-02_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started |  | #N/A
T-00292-0633 | PS2-03-02_PRC-INSTRUMENTATION-EITS | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started |  | #N/A
T-00292-0634 | PS2-03-03_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-03-03 - FZ-03 - Buildings Area |  |  |  | Construction not yet started |  | #N/A
T-00292-0635 | PS2-03-05_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-03-05 - FZ-G1 - Guard House |  |  |  | Construction not yet started |  | #N/A
T-00292-0636 | PS2-03-06_PRC-INSTRUMENTATION-EITS | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00292-0637 | PS2-03-07_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started |  | #N/A
T-00292-0638 | PS2-03-08_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00292-0639 | PS2-04-02_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00292-0640 | PS2-04-03_PRC-INSTRUMENTATION-EITS | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-04-03 - EITS Building ICSS System |  |  |  | Construction not yet started |  | #N/A
T-00292-0641 | PS2-04-04_PRC-INSTRUMENTATION-EITS | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | #N/A
T-00292-0642 | PS2-04-05_PRC-INSTRUMENTATION-EITS | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00292-0643 | PS2-05-01_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-05-01 - Emergency Diesel Generator Package |  |  |  | Construction not yet started |  | #N/A
T-00292-0644 | PS2-09-01_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #N/A
T-00292-0645 | PS2-09-03_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00292-0646 | PS2-09-04_PRC-INSTRUMENTATION-EITS | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00292-0647 | PS2-0H-01_PRC-INSTRUMENTATION-EITS | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-0H-01 - HIPPS |  |  |  | Construction not yet started |  | #N/A
T-00292-0648 | PS2-25-01_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00292-0649 | PS2-25-02_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00292-0650 | PS2-25-02_PRC-INSTRUMENTATION-EITS | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00292-0651 | PS2-25-03_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00292-0652 | PS2-25-04_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00292-0653 | PS2-25-05_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #N/A
T-00292-0654 | PS2-25-06_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #N/A
T-00292-0655 | PS2-25-07_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00292-0656 | PS2-28-02_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-28-02 - Relief Header |  |  |  | Construction not yet started |  | #N/A
T-00292-0657 | PS2-28-03_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | #N/A
T-00292-0658 | PS2-28-04_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started |  | #N/A
T-00292-0659 | PS2-28-05_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | #N/A
T-00292-0660 | PS2-28-06_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | #N/A
T-00292-0661 | PS2-28-07_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | #N/A
T-00292-0662 | PS2-28-08_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-28-08 - Open Drains (OD2) |  |  |  | Construction not yet started |  | #N/A
T-00292-0663 | PS2-28-09_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-28-09 - Open Drain Interceptor |  |  |  | Construction not yet started |  | #N/A
T-00292-0664 | PS2-28-11_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-28-11 - Nitrogen for Seal Oil Drain |  |  |  | Construction not yet started |  | #N/A
T-00292-0665 | PS2-53-01_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-53-01 - Utility Water Storage Tank |  |  |  | Construction not yet started |  | #N/A
T-00292-0666 | PS2-53-02_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-53-02 - Water Distribution Pump |  |  |  | Construction not yet started |  | #N/A
T-00292-0667 | PS2-53-03_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-53-03 - Water Treatment Purification Package |  |  |  | Construction not yet started |  | #N/A
T-00292-0668 | PS2-75-01_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | #N/A
T-00292-0669 | PS2-75-02_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | #N/A
T-00292-0670 | PS2-79-01_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00292-0671 | PS2-79-02_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00292-0672 | PS2-79-03_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00292-0673 | PS2-79-04_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00292-0674 | PS2-79-05_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00292-0675 | PS2-91-01_PRC-INSTRUMENTATION-CPP | 2621I - Instrumentation | COM - Commissioning | I - Instrumentation | PRC Instrumentation | EACOP |  | PS2-91-01 - Multicore cables & JB |  |  |  | Construction not yet started |  | #N/A
T-00295-0280 | PS2-04-01_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-04-01 - Office Building PCS System |  |  |  | Construction not yet started |  | #N/A
T-00295-0281 | PS2-08-01_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00295-0282 | PS2-08-03_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00295-0283 | PS2-08-06_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00295-0284 | PS2-08-11_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00295-0285 | PS2-08-12_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00295-0286 | PS2-08-13_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00295-0287 | PS2-08-14_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-14 - Industrial Data Network (SII SP1) |  |  |  | Construction not yet started |  | #N/A
T-00295-0288 | PS2-08-15_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00295-0289 | PS2-08-23_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00295-0290 | PS2-08-34_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00295-0291 | PS2-08-35_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00295-0292 | PS2-08-36_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-36 - Pipeline FO Cable & EPRS |  |  |  | Construction not yet started |  | #N/A
T-00295-0293 | PS2-08-52_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00295-0294 | PS2-08-55_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-55 - Videoconference |  |  |  | Construction not yet started |  | #N/A
T-00295-0295 | PS2-08-61_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-61 - Meteocean |  |  |  | Construction not yet started |  | #N/A
T-00295-0296 | PS2-08-71_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-71 - Structured Cabling (CAT6) |  |  |  | Construction not yet started |  | #N/A
T-00295-0297 | PS2-08-81_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-81 - Guard tour |  |  |  | Construction not yet started |  | #N/A
T-00295-0298 | PS2-08-83_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-83 - Perimeter & Pipeline intrusion detection system |  |  |  | Construction not yet started |  | #N/A
T-00295-0299 | PS2-08-85_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00295-0300 | PS2-08-86_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-86 - Integrated Security Management System |  |  |  | Construction not yet started |  | #N/A
T-00295-0301 | PS2-08-92_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-92 - Telecom Mast |  |  |  | Construction not yet started |  | #N/A
T-00295-0302 | PS2-08-93_PRC-TELECOM-EITS | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-08-93 - Telecom Monitoring System |  |  |  | Construction not yet started |  | #N/A
T-00295-0303 | PS2-09-01_PRC-TELECOM-CPP | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #N/A
T-00295-0304 | PS2-09-03_PRC-TELECOM-CPP | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00295-0305 | PS2-53-03_PRC-TELECOM-CPP | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-53-03 - Water Treatment Purification Package |  |  |  | Construction not yet started |  | #N/A
T-00295-0306 | PS2-75-01_PRC-TELECOM-CPP | 2621T - Telecommunications | COM - Commissioning | T - Telecom | PRC Telecom | EACOP |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | #N/A
T-00296-0149 | BF_PS2-05-IE-8100 | FP00 - Miscellaneous Electrical Consumer | COM - Commissioning | E - Electrical | Unit Control Panel for Emergency Diesel Generator | EACOP |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | #N/A
T-00296-0150 | BF_PS2-06-IER-0001A | FP00 - Miscellaneous Electrical Consumer | COM - Commissioning | E - Electrical | Battery MCCB box A | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00296-0151 | BF_PS2-06-IER-0001B | FP00 - Miscellaneous Electrical Consumer | COM - Commissioning | E - Electrical | Battery MCCB box B | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00296-0152 | BF_PS2-61-IE-0001 | FP00 - Miscellaneous Electrical Consumer | COM - Commissioning | E - Electrical | ECS 1 Panelboard | EACOP |  | PS2-61-05 - Electrical Control System |  |  |  | Construction not yet started |  | #N/A
T-00296-0153 | BF_PS2-61-IE-0002 | FP00 - Miscellaneous Electrical Consumer | COM - Commissioning | E - Electrical | ECS 2 Panelboard | EACOP |  | PS2-61-05 - Electrical Control System |  |  |  | Construction not yet started |  | #N/A
T-00337-0083 | BF_PS2-61-ISR-0101 | FP02 - Power Transformer | COM - Commissioning | E - Electrical | Shunt Reactor | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00337-0084 | BF_PS2-61-IU-0010 | FP02 - Power Transformer | COM - Commissioning | E - Electrical | LLHT Oil Transformer | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00337-0085 | BF_PS2-61-IU-0011 | FP02 - Power Transformer | COM - Commissioning | E - Electrical | LLHT Oil Transformer | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00337-0086 | BF_PS2-61-IU-3100A | FP02 - Power Transformer | COM - Commissioning | E - Electrical | VSD Transformer | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00337-0087 | BF_PS2-61-IU-3100B | FP02 - Power Transformer | COM - Commissioning | E - Electrical | VSD Transformer | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00337-0088 | BF_PS2-61-IU-3100C | FP02 - Power Transformer | COM - Commissioning | E - Electrical | 33kV VSD Transformer | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00337-0089 | BF_PS2-63-IV-0010 | FP02 - Power Transformer | COM - Commissioning | E - Electrical | Earthing Transformer | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00338-0016 | BF_PS2-61-IV-0001A | FP03 - Small Power Transformer | COM - Commissioning | E - Electrical | Distribution Transformer | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00338-0017 | BF_PS2-61-IV-0001B | FP03 - Small Power Transformer | COM - Commissioning | E - Electrical | Distribution Transformer | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00338-0018 | BF_PS2-79-IV-0001 | FP03 - Small Power Transformer | COM - Commissioning | E - Electrical | Feeder to EHT Transformer / DB 1 | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00338-0019 | BF_PS2-79-IV-0002 | FP03 - Small Power Transformer | COM - Commissioning | E - Electrical | Feeder to EHT Transformer / DB 2 | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00338-0020 | BF_PS2-79-IV-0003 | FP03 - Small Power Transformer | COM - Commissioning | E - Electrical | Feeder to EHT Transformer / DB 3 | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00338-0021 | BF_PS2-79-IV-0004 | FP03 - Small Power Transformer | COM - Commissioning | E - Electrical | Feeder to EHT Transformer / DB 4 | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00338-0022 | BF_PS2-79-IV-0005 | FP03 - Small Power Transformer | COM - Commissioning | E - Electrical | Feeder to EHT Transformer / DB 5 | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00339-0010 | BF_PS2-61-IJ-0001 | FP04 - HV Switchboard /MCC | COM - Commissioning | E - Electrical | MV Switchgear | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00339-0011 | BF_PS2-61-IJ-0010 | FP04 - HV Switchboard /MCC | COM - Commissioning | E - Electrical | MV Switchgear | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00339-0012 | BF_PS2-61-IJ-0011 | FP04 - HV Switchboard /MCC | COM - Commissioning | E - Electrical | MV Switchgear | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00339-0030 | BF_PS2-61-IJ-0001_busbar | FP04 - HV Switchboard /MCC | COM - Commissioning | E - Electrical | MV Switchgear | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00340-0005 | BF_PS2-61-IK-0001 | FP05 - LV Switchboard /MCC | COM - Commissioning | E - Electrical | LV SWGR | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00341-0004 | BF_PS2-25-DM-3100A | FP12 - HV Motor | COM - Commissioning | E - Electrical | CRUDE OIL EXPORT PUMP A MOTOR | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00341-0005 | BF_PS2-25-DM-3100B | FP12 - HV Motor | COM - Commissioning | E - Electrical | CRUDE OIL EXPORT PUMP B MOTOR | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00341-0006 | BF_PS2-25-DM-3100C | FP12 - HV Motor | COM - Commissioning | E - Electrical | CRUDE OIL EXPORT PUMP C MOTOR | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00342-0025 | BF_PS2-28-DM-3100 | FP13 - LV Motor | COM - Commissioning | E - Electrical | Closed Drain Drum Pump | EACOP |  | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | #N/A
T-00342-0026 | BF_PS2-28-DM-3800A | FP13 - LV Motor | COM - Commissioning | E - Electrical | Seal Oil Drain Drum Pump Motor A | EACOP |  | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | #N/A
T-00342-0027 | BF_PS2-28-DM-3800B | FP13 - LV Motor | COM - Commissioning | E - Electrical | Seal Oil Drain Drum Pump Motor B | EACOP |  | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | #N/A
T-00342-0028 | BF_PS2-28-DM-3800C | FP13 - LV Motor | COM - Commissioning | E - Electrical | Seal Oil Drain Drum Pump Motor C | EACOP |  | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | #N/A
T-00342-0029 | BF_PS2-28-DM-3900 | FP13 - LV Motor | COM - Commissioning | E - Electrical | Reinjection Pump Motor | EACOP |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started |  | #N/A
T-00342-0030 | BF_PS2-53-DM-3100 | FP13 - LV Motor | COM - Commissioning | E - Electrical | Water Distribution Pump Motor | EACOP |  | PS2-53-02 - Water Distribution Pump |  |  |  | Construction not yet started |  | #N/A
T-00344-0042 | BF_PS2-05-IG-0003 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | Emergency Lighting and Small power Distribution Panel | EACOP |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00344-0043 | BF_PS2-06-IG-0001A | FP15 - Distribution Board | COM - Commissioning | E - Electrical | AC UPS Distribution Board | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00344-0044 | BF_PS2-06-IG-0001B | FP15 - Distribution Board | COM - Commissioning | E - Electrical | AC UPS Distribution Board | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00344-0045 | BF_PS2-06-IG-0002 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | AC UPS Distribution Board | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00344-0046 | BF_PS2-61-IG-0003 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | Normal Lighting and Small power Distribution Panel | EACOP |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00344-0047 | BF_PS2-61-IG-0008 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | Normal Auxiliary Distribution Panel | EACOP |  | PS2-61-08 - EITS 33kV Bld. Normal Auxiliary DP - PS2-61-IG-0008 |  |  |  | Construction not yet started |  | #N/A
T-00344-0128 | BF_PS2-05-IG-0002 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | Feeder to Office & Facilities Building SWGR Emergency Section | EACOP |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00344-0129 | BF_PS2-05-IG-0004 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | Outdoor Emergency Lighting Distribution Board PS-2 | EACOP |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00344-0130 | BF_PS2-05-IG-0006 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | Outdoor Emergency Lighting Distribution Board PS-2 | EACOP |  | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  |  |  | Construction not yet started |  | #N/A
T-00344-0131 | BF_PS2-05-IG-0007 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | Guard House Emergency L&SP Distribution Board | EACOP |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00344-0132 | BF_PS2-05-IG-0101 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | EMERGENCY POWER DISTRIBUTION BOARD | EACOP |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | #N/A
T-00344-0133 | BF_PS2-06-GU-0101 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | UPS DISTRIBUTION PANEL | EACOP |  | PS2-06-03 - AC DB - Office Building |  |  |  | Construction not yet started |  | #N/A
T-00344-0134 | BF_PS2-06-IG-0004 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | UPS POWER DISTRIBUTION BOARD | EACOP |  | PS2-06-04 - AC DB - Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00344-0135 | BF_PS2-61-IG-0002 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | Normal feeder to Office and other EPC buildings | EACOP |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00344-0136 | BF_PS2-61-IG-0004 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | LIGHTING AND SMALL POWER DISTRIBUTION | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00344-0137 | BF_PS2-61-IG-0005 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | Outdoor Normal Lighting Distribution Board PS-2 | EACOP |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #N/A
T-00344-0138 | BF_PS2-61-IG-0007 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | Outdoor Normal Lighting Distribution Board PS-2 | EACOP |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00344-0139 | BF_PS2-61-IG-0014 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | Outdoor Power Distribution Board PS-2 | EACOP |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | #N/A
T-00344-0140 | BF_PS2-61-IG-0015 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | Outdoor Valves Distribution Board PS-2 | EACOP |  | PS2-61-07 - Outdoor Valves Distribution Board - PS2-61-IG-0015 |  |  |  | Construction not yet started |  | #N/A
T-00344-0141 | BF_PS2-79-IG-0001 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | EHT Distribution Board 1 | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00344-0142 | BF_PS2-79-IG-0002 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | EHT Distribution Board 2 | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00344-0143 | BF_PS2-79-IG-0003 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | EHT Distribution Board 3 | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00344-0144 | BF_PS2-79-IG-0004 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | EHT Distribution Board 4 | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00344-0145 | BF_PS2-79-IG-0005 | FP15 - Distribution Board | COM - Commissioning | E - Electrical | EHT Distribution Board 5 | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00345-0011 | BF_PS2-06-GU-0001 | FP16A - AC UPS | COM - Commissioning | E - Electrical | AC UPS 100kVA | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-0661 | BF_PS2-05-IG-0002_CKT01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0662 | BF_PS2-05-IG-0002_CKT02 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0663 | BF_PS2-05-IG-0002_CKT03 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0664 | BF_PS2-05-IG-0002_CKT04 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0665 | BF_PS2-05-IG-0003_CKT01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00347-0666 | BF_PS2-05-IG-0003_CKT02 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00347-0667 | BF_PS2-05-IG-0003_CKT03 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00347-0668 | BF_PS2-05-IG-0003_CKT04 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00347-0669 | BF_PS2-05-IG-0004_CKT01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0670 | BF_PS2-05-IG-0004_CKT02 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0671 | BF_PS2-05-IG-0004_CKT03 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting circuit | EACOP |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0672 | BF_PS2-05-IG-0004_CKT04 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0673 | BF_PS2-05-IG-0004_CKT05 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting circuit | EACOP |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00347-0674 | BF_PS2-05-IG-0004_CKT06 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0675 | BF_PS2-05-IG-0004_CKT07 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting circuit | EACOP |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00347-0676 | BF_PS2-05-IG-0004_CKT08 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0677 | BF_PS2-05-IG-0004_CKT09 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-62-IE-0001 - Lighting Control Panel 1 - Control supply | EACOP |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0678 | BF_PS2-05-IG-0004_CKT10 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0679 | BF_PS2-05-IG-0004_CKT11 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0680 | BF_PS2-05-IG-0004_CKT12 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0681 | BF_PS2-05-IG-0004_CKT13 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0682 | BF_PS2-05-IG-0004_CKT14 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0683 | BF_PS2-05-IG-0006_CKT01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  |  |  | Construction not yet started |  | #N/A
T-00347-0684 | BF_PS2-05-IG-0006_CKT02 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  |  |  | Construction not yet started |  | #N/A
T-00347-0685 | BF_PS2-05-IG-0006_CKT03 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting circuit | EACOP |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0686 | BF_PS2-05-IG-0006_CKT04 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  |  |  | Construction not yet started |  | #N/A
T-00347-0687 | BF_PS2-05-IG-0006_CKT05 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting circuit | EACOP |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0688 | BF_PS2-05-IG-0006_CKT06 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  |  |  | Construction not yet started |  | #N/A
T-00347-0689 | BF_PS2-05-IG-0006_CKT07 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting circuit | EACOP |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0690 | BF_PS2-05-IG-0006_CKT08 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-02-SWSI-0002 - Illuminated Windsock JB - Power supply | EACOP |  | PS2-02-01 - Miscellaneous Safety equipment |  |  |  | Construction not yet started |  | #N/A
T-00347-0691 | BF_PS2-05-IG-0006_CKT09 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-62-IE-0002 - Lighting Control Panel 2 - Control supply | EACOP |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0692 | BF_PS2-05-IG-0006_CKT10 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  |  |  | Construction not yet started |  | #N/A
T-00347-0693 | BF_PS2-05-IG-0006_CKT11 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  |  |  | Construction not yet started |  | #N/A
T-00347-0694 | BF_PS2-05-IG-0006_CKT12 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  |  |  | Construction not yet started |  | #N/A
T-00347-0695 | BF_PS2-05-IG-0006_CKT13 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  |  |  | Construction not yet started |  | #N/A
T-00347-0696 | BF_PS2-05-IG-0006_CKT14 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  |  |  | Construction not yet started |  | #N/A
T-00347-0697 | BF_PS2-05-IG-0007_CKT01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0698 | BF_PS2-05-IG-0007_CKT02 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0699 | BF_PS2-05-IG-0007_CKT03 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0700 | BF_PS2-05-IG-0007_CKT04 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0701 | BF_PS2-05-IG-0007_CKT05 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0702 | BF_PS2-05-IG-0007_CKT06 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0703 | BF_PS2-05-IG-0007_CKT07 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0704 | BF_PS2-05-IG-0007_CKT08 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0705 | BF_PS2-05-IG-0007_CKT09 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0706 | BF_PS2-05-IG-0007_CKT10 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0707 | BF_PS2-05-IG-0007_CKT11 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-06-GU-0004 - GUARD HOUSE UPS (4kVA) | EACOP |  | PS2-06-02 - AC UPS - Guard House |  |  |  | Construction not yet started |  | #N/A
T-00347-0708 | BF_PS2-05-IG-0007_CKT12 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0709 | BF_PS2-05-IG-0007_CKT13 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0710 | BF_PS2-05-IG-0007_CKT14 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0711 | BF_PS2-05-IG-0007_CKT15 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0712 | BF_PS2-05-IG-0101_CKT01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | #N/A
T-00347-0713 | BF_PS2-05-IG-0101_CKT02 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | #N/A
T-00347-0714 | BF_PS2-05-IG-0101_CKT03 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | #N/A
T-00347-0715 | BF_PS2-05-IG-0101_CKT04 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | #N/A
T-00347-0716 | BF_PS2-05-IG-0101_CKT05 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | #N/A
T-00347-0717 | BF_PS2-05-IG-0101_CKT06 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-13 - Workshop & Warehouse Emergency L&SP DB - PS2-05-IG-0101 |  |  |  | Construction not yet started |  | #N/A
T-00347-0718 | BF_PS2-06-GU-0101_CKT01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-06-03 - AC DB - Office Building |  |  |  | Construction not yet started |  | #N/A
T-00347-0719 | BF_PS2-06-GU-0101_CKT02 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-06-03 - AC DB - Office Building |  |  |  | Construction not yet started |  | #N/A
T-00347-0720 | BF_PS2-06-IG-0004_CKT19 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-06-04 - AC DB - Workshop & Warehouse |  |  |  | Construction not yet started |  | #N/A
T-00347-0721 | BF_PS2-61-IG-0002_CKT01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0722 | BF_PS2-61-IG-0002_CKT02 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0723 | BF_PS2-61-IG-0002_CKT03 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0724 | BF_PS2-61-IG-0002_CKT04 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0725 | BF_PS2-61-IG-0002_CKT05 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0726 | BF_PS2-61-IG-0002_CKT06 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0727 | BF_PS2-61-IG-0003_CKT01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00347-0728 | BF_PS2-61-IG-0003_CKT02 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00347-0729 | BF_PS2-61-IG-0003_CKT03 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00347-0730 | BF_PS2-61-IG-0003_CKT04 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00347-0731 | BF_PS2-61-IG-0003_CKT05 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00347-0732 | BF_PS2-61-IG-0003_CKT06 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00347-0733 | BF_PS2-61-IG-0004_CKT01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0734 | BF_PS2-61-IG-0004_CKT02 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0735 | BF_PS2-61-IG-0004_CKT03 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0736 | BF_PS2-61-IG-0004_CKT04 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0737 | BF_PS2-61-IG-0004_CKT05 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0738 | BF_PS2-61-IG-0004_CKT07 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0739 | BF_PS2-61-IG-0004_CKT08 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0740 | BF_PS2-61-IG-0004_CKT09 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0741 | BF_PS2-61-IG-0004_CKT10 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0742 | BF_PS2-61-IG-0004_CKT11 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0743 | BF_PS2-61-IG-0004_CKT12 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0744 | BF_PS2-61-IG-0004_CKT13 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0745 | BF_PS2-61-IG-0004_CKT14 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0746 | BF_PS2-61-IG-0004_CKT15 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0747 | BF_PS2-61-IG-0004_CKT16 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0748 | BF_PS2-61-IG-0004_CKT17 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0749 | BF_PS2-61-IG-0004_CKT18 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0750 | BF_PS2-61-IG-0004_CKT19 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0751 | BF_PS2-61-IG-0004_CKT21 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0752 | BF_PS2-61-IG-0004_CKT22 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0753 | BF_PS2-61-IG-0004_CKT23 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-62-12 - Workshop & Warehouse Normal L&SP DB - PS2-61-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00347-0754 | BF_PS2-61-IG-0005_CKT01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting circuit | EACOP |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00347-0755 | BF_PS2-61-IG-0005_CKT02 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting circuit | EACOP |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00347-0756 | BF_PS2-61-IG-0005_CKT03 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #N/A
T-00347-0757 | BF_PS2-61-IG-0005_CKT04 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting circuit | EACOP |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00347-0758 | BF_PS2-61-IG-0005_CKT05 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #N/A
T-00347-0759 | BF_PS2-61-IG-0005_CKT06 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #N/A
T-00347-0760 | BF_PS2-61-IG-0005_CKT07 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #N/A
T-00347-0761 | BF_PS2-61-IG-0005_CKT08 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #N/A
T-00347-0762 | BF_PS2-61-IG-0005_CKT09 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #N/A
T-00347-0763 | BF_PS2-61-IG-0005_CKT10 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #N/A
T-00347-0764 | BF_PS2-61-IG-0005_CKT11 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #N/A
T-00347-0765 | BF_PS2-61-IG-0005_CKT12 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #N/A
T-00347-0766 | BF_PS2-61-IG-0005_CKT13 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #N/A
T-00347-0767 | BF_PS2-61-IG-0005_CKT14 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #N/A
T-00347-0768 | BF_PS2-61-IG-0007_CKT01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting circuit | EACOP |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0769 | BF_PS2-61-IG-0007_CKT02 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting circuit | EACOP |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0770 | BF_PS2-61-IG-0007_CKT03 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0771 | BF_PS2-61-IG-0007_CKT04 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0772 | BF_PS2-61-IG-0007_CKT05 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0773 | BF_PS2-61-IG-0007_CKT06 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0774 | BF_PS2-61-IG-0007_CKT07 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0775 | BF_PS2-61-IG-0007_CKT08 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0776 | BF_PS2-61-IG-0007_CKT09 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0777 | BF_PS2-61-IG-0007_CKT10 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0778 | BF_PS2-61-IG-0007_CKT11 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0779 | BF_PS2-61-IG-0007_CKT12 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0780 | BF_PS2-61-IG-0007_CKT13 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0781 | BF_PS2-61-IG-0007_CKT14 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00347-0782 | BF_PS2-61-IG-0014_CKT01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | #N/A
T-00347-0783 | BF_PS2-61-IG-0014_CKT02 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-28-BE-0001 - Actuator Power - reciprocating pump | EACOP |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started |  | #N/A
T-00347-0784 | BF_PS2-61-IG-0014_CKT03 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | #N/A
T-00347-0785 | BF_PS2-61-IG-0014_CKT04 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | #N/A
T-00347-0786 | BF_PS2-61-IG-0014_CKT05 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | #N/A
T-00347-0787 | BF_PS2-61-IG-0014_CKT06 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Socket Circuit | EACOP |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | #N/A
T-00347-0788 | BF_PS2-61-IG-0014_CKT07 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-DM-3100A - Motor Main TB Anti Condensation Heater | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00347-0789 | BF_PS2-61-IG-0014_CKT08 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-28-LB-8200 - Open Drain Interceptor Panel | EACOP |  | PS2-28-09 - Open Drain Interceptor |  |  |  | Construction not yet started |  | #N/A
T-00347-0790 | BF_PS2-61-IG-0014_CKT09 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | #N/A
T-00347-0791 | BF_PS2-61-IG-0014_CKT10 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-DM-3100B - Motor Main TB Anti Condensation Heater | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00347-0792 | BF_PS2-61-IG-0014_CKT11 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-28-HE-2100 - Closed Drain Drum Heater_Terminal Box Anti-condensation Heater | EACOP |  | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | #N/A
T-00347-0793 | BF_PS2-61-IG-0014_CKT12 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-DM-3100C - Motor Main TB Anti Condensation Heater | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00347-0794 | BF_PS2-61-IG-0015_CKT01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-ESDV-0021 - Emergency Shut Down Valve | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00347-0795 | BF_PS2-61-IG-0015_CKT02 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-MOV-0026 - Motor Operated Valve | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00347-0796 | BF_PS2-61-IG-0015_CKT03 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-ESDV-0023 - Emergency Shut Down Valve | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00347-0797 | BF_PS2-61-IG-0015_CKT04 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-MOV-0027 - Motor Operated Valve | EACOP |  | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #N/A
T-00347-0798 | BF_PS2-61-IG-0015_CKT05 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-MOV-0001 - Motor Operated Valve | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00347-0799 | BF_PS2-61-IG-0015_CKT06 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-SDV-0046 - Shutdown Valve | EACOP |  | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #N/A
T-00347-0800 | BF_PS2-61-IG-0015_CKT07 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-MOV-0008 - Motor Operated Valve | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00347-0801 | BF_PS2-61-IG-0015_CKT08 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-SDV-0035A - Shutdown Valve | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00347-0802 | BF_PS2-61-IG-0015_CKT09 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-MOV-0003 - Motor Operated Valve | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00347-0803 | BF_PS2-61-IG-0015_CKT10 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-SDV-0035B - Shutdown Valve | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00347-0804 | BF_PS2-61-IG-0015_CKT11 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-MOV-0002 - Motor Operated Valve | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00347-0805 | BF_PS2-61-IG-0015_CKT12 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-SDV-0035C - Shutdown Valve | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00347-0806 | BF_PS2-61-IG-0015_CKT13 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-MOV-0011 - Motor Operated Valve | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00347-0807 | BF_PS2-61-IG-0015_CKT14 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-SDV-0036A - Shutdown Valve | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00347-0808 | BF_PS2-61-IG-0015_CKT15 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-MOV-0012 - Motor Operated Valve | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00347-0809 | BF_PS2-61-IG-0015_CKT16 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-SDV-0036B - Shutdown Valve | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00347-0810 | BF_PS2-61-IG-0015_CKT17 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-MOV-0025 - Motor Operated Valve | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00347-0811 | BF_PS2-61-IG-0015_CKT18 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-SDV-0036C - Shutdown Valve | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00347-0812 | BF_PS2-61-IG-0015_CKT19 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-MOV-0028 - Motor Operated Valve | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00347-0813 | BF_PS2-61-IG-0015_CKT20 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-28-SDV-0053A - Shutdown Valve | EACOP |  | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | #N/A
T-00347-0814 | BF_PS2-61-IG-0015_CKT21 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-SDV-0052 - Shutdown Valve | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | #N/A
T-00347-0815 | BF_PS2-61-IG-0015_CKT22 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-28-SDV-0053B - Shutdown Valve | EACOP |  | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | #N/A
T-00347-0816 | BF_PS2-61-IG-0015_CKT23 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-FCV-0003A - Flow Control Valve | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00347-0817 | BF_PS2-61-IG-0015_CKT24 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-28-SDV-0053C - Shutdown Valve | EACOP |  | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | #N/A
T-00347-0818 | BF_PS2-61-IG-0015_CKT25 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-FCV-0003B - Flow Control Valve | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00347-0819 | BF_PS2-61-IG-0015_CKT26 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-28-SDV-0065 - Shutdown Valve | EACOP |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started |  | #N/A
T-00347-0820 | BF_PS2-61-IG-0015_CKT27 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-FCV-0003C - Flow Control Valve | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00347-0821 | BF_PS2-61-IG-0015_CKT28 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-SDV-0054C - Shutdown Valve | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00347-0822 | BF_PS2-61-IG-0015_CKT29 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-FCV-0004 - Flow Control Valve | EACOP |  | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #N/A
T-00347-0823 | BF_PS2-61-IG-0015_CKT30 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-XV-0053 - On / Off Valve | EACOP |  | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #N/A
T-00347-0824 | BF_PS2-61-IG-0015_CKT31 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-SDV-0054A - Shutdown Valve | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00347-0825 | BF_PS2-61-IG-0015_CKT32 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-XV-0070 - On / Off Valve | EACOP |  | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | #N/A
T-00347-0826 | BF_PS2-61-IG-0015_CKT33 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-SDV-0054B - Shutdown Valve | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00347-0827 | BF_PS2-61-IG-0015_CKT34 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-75-MOV-0001 - Motor Operated Valve | EACOP |  | PS2-28-08 - Open Drains (OD2) |  |  |  | Construction not yet started |  | #N/A
T-00347-0828 | BF_PS2-61-IG-0015_CKT35 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-07 - Outdoor Valves Distribution Board - PS2-61-IG-0015 |  |  |  | Construction not yet started |  | #N/A
T-00347-0829 | BF_PS2-61-IG-0015_CKT36 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-07 - Outdoor Valves Distribution Board - PS2-61-IG-0015 |  |  |  | Construction not yet started |  | #N/A
T-00347-0830 | BF_PS2-61-IG-0015_CKT37 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-07 - Outdoor Valves Distribution Board - PS2-61-IG-0015 |  |  |  | Construction not yet started |  | #N/A
T-00347-0831 | BF_PS2-61-IG-0015_CKT38 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-07 - Outdoor Valves Distribution Board - PS2-61-IG-0015 |  |  |  | Construction not yet started |  | #N/A
T-00347-0832 | BF_PS2-61-IG-0015_CKT39 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-07 - Outdoor Valves Distribution Board - PS2-61-IG-0015 |  |  |  | Construction not yet started |  | #N/A
T-00347-0833 | BF_PS2-62-IE-0001_CKT-KA01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00347-0834 | BF_PS2-62-IE-0001_CKT-KA02 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00347-0835 | BF_PS2-62-IE-0001_CKT-KA03 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00347-0836 | BF_PS2-62-IE-0001_CKT-KA07 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00347-0837 | BF_PS2-62-IE-0001_CKT-KB01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00347-0838 | BF_PS2-62-IE-0001_CKT-KB03 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | #N/A
T-00347-0839 | BF_PS2-62-IE-0002_CKT-KA01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0840 | BF_PS2-62-IE-0002_CKT-KA02 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0841 | BF_PS2-62-IE-0002_CKT-KA03 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0842 | BF_PS2-62-IE-0002_CKT-KB01 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-0843 | BF_PS2-62-IE-0002_CKT-KB03 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Lighting Circuit | EACOP |  | PS2-62-02 - Lighting Control Panel - PS2-62-IE-0002 |  |  |  | Construction not yet started |  | #N/A
T-00347-4605 | BF_PS2-06-IG-0001A_CKT1Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4606 | BF_PS2-06-IG-0001A_CKT1Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4607 | BF_PS2-06-IG-0001A_CKT1Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-04-PNC-0001 - ICSS Network Cabinet 1 UPS A Pwr Supply | EACOP |  | PS2-04-03 - EITS Building ICSS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4608 | BF_PS2-06-IG-0001A_CKT1Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4609 | BF_PS2-06-IG-0001A_CKT1Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-04-PSC-0001 - PCS System Cab 1 UPS A Pwr Supply | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4610 | BF_PS2-06-IG-0001A_CKT1Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-04-PSC-0002 - PCS System Cab 2 UPS A Pwr Supply | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4611 | BF_PS2-06-IG-0001A_CKT1Q7 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4612 | BF_PS2-06-IG-0001A_CKT1Q8 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4613 | BF_PS2-06-IG-0001A_CKT1Q9 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-04-PMC-0003 - PCS Marsh Cab 3 UPS A Pwr Supply | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4614 | BF_PS2-06-IG-0001A_CKT2Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFSC-0001 - SIS/FGS System Cab 1 UPS A Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4615 | BF_PS2-06-IG-0001A_CKT2Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFSC-0002 - SIS/FGS System Cab 2 UPS A Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4616 | BF_PS2-06-IG-0001A_CKT2Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFSC-0003 - SIS/FGS System Cab 3 UPS A Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4617 | BF_PS2-06-IG-0001A_CKT2Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0001 - SIS/FGS Marsh Cab 1 UPS A Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4618 | BF_PS2-06-IG-0001A_CKT2Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0002 - SIS/FGS Marsh Cab 2 UPS A Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4619 | BF_PS2-06-IG-0001A_CKT2Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0003 - SIS/FGS Marsh Cab 3 UPS A Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4620 | BF_PS2-06-IG-0001A_CKT2Q7 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0004 - SIS/FGS Marsh Cab 4 UPS A Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4621 | BF_PS2-06-IG-0001A_CKT2Q8 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0005 - SIS/FGS Marsh Cab 5 UPS A Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4622 | BF_PS2-06-IG-0001A_CKT2Q9 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0006 - SIS/FGS Marsh Cab 6 UPS A Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4623 | BF_PS2-06-IG-0001A_CKT3Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0007 - SIS/FGS Marsh Cab 7 UPS A Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4624 | BF_PS2-06-IG-0001A_CKT3Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IE-0001 - ECS 1 Panelboard UPS A Pwr Supply | EACOP |  | PS2-61-05 - Electrical Control System |  |  |  | Construction not yet started |  | #N/A
T-00347-4625 | BF_PS2-06-IG-0001A_CKT3Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IE-0002 - ECS 2 Panelboard UPS A Pwr Supply | EACOP |  | PS2-61-05 - Electrical Control System |  |  |  | Construction not yet started |  | #N/A
T-00347-4626 | BF_PS2-06-IG-0001A_CKT3Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-08-35CB-1001 - TEL OTN Cabinet UPS A Pwr Supply | EACOP |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00347-4627 | BF_PS2-06-IG-0001A_CKT3Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-08-13CB-1001 - TEL SII SP3 SAF Cabinet UPS A Pwr Supply | EACOP |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00347-4628 | BF_PS2-06-IG-0001A_CKT3Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-08-15CB-1001 - TEL SII SP3 SEC Cabinet UPS A Pwr Supply | EACOP |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00347-4629 | BF_PS2-06-IG-0001A_CKT3Q7 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-08-11CB-1001 - TEL SIE & SII SP1 Cabinet UPS A Pwr Supply | EACOP |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00347-4630 | BF_PS2-06-IG-0001A_CKT3Q8 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-IE-0001 - VTMS Export loading Pumps UPS A Pwr Supply | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00347-4631 | BF_PS2-06-IG-0001A_CKT3Q9 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-01-LA-0001 - OPPS Cabinet UPS A Pwr Supply | EACOP |  | PS2-0H-01 - HIPPS |  |  |  | Construction not yet started |  | #N/A
T-00347-4632 | BF_PS2-06-IG-0001A_CKT4Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-05-IE-8100 - EDG UCP UPS A Pwr Supply | EACOP |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | #N/A
T-00347-4633 | BF_PS2-06-IG-0001A_CKT4Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-53-IN-0001 - Water Treat UCP UPS A Pwr Supply | EACOP |  | PS2-53-03 - Water Treatment Purification Package |  |  |  | Construction not yet started |  | #N/A
T-00347-4634 | BF_PS2-06-IG-0001A_CKT4Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IDH-3100A - VSD-A Control UPS Pwr Supply | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00347-4635 | BF_PS2-06-IG-0001A_CKT4Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4636 | BF_PS2-06-IG-0001A_CKT4Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4637 | BF_PS2-06-IG-0001A_CKT4Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4638 | BF_PS2-06-IG-0001A_CKT4Q7 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4639 | BF_PS2-06-IG-0001A_CKT4Q8 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4640 | BF_PS2-06-IG-0001A_CKT4Q9 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4641 | BF_PS2-06-IG-0001A_CKT5Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4642 | BF_PS2-06-IG-0001A_CKT5Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4643 | BF_PS2-06-IG-0001B_CKT1Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4644 | BF_PS2-06-IG-0001B_CKT1Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4645 | BF_PS2-06-IG-0001B_CKT1Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-04-PNC-0001 - ICSS Network Cabinet 1 UPS B Pwr Supply | EACOP |  | PS2-04-03 - EITS Building ICSS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4646 | BF_PS2-06-IG-0001B_CKT1Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4647 | BF_PS2-06-IG-0001B_CKT1Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-04-PSC-0001 - PCS System Cab 1 UPS B Pwr Supply | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4648 | BF_PS2-06-IG-0001B_CKT1Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-04-PSC-0002 - PCS System Cab 2 UPS B Pwr Supply | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4649 | BF_PS2-06-IG-0001B_CKT1Q7 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4650 | BF_PS2-06-IG-0001B_CKT1Q8 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4651 | BF_PS2-06-IG-0001B_CKT1Q9 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-04-PMC-0003 - PCS Marsh Cab 3 UPS B Pwr Supply | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4652 | BF_PS2-06-IG-0001B_CKT2Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFSC-0001 - SIS/FGS System Cab 1 UPS B Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4653 | BF_PS2-06-IG-0001B_CKT2Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFSC-0002 - SIS/FGS System Cab 2 UPS B Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4654 | BF_PS2-06-IG-0001B_CKT2Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFSC-0003 - SIS/FGS System Cab 3 UPS B Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4655 | BF_PS2-06-IG-0001B_CKT2Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0001 - SIS/FGS Marsh Cab 1 UPS B Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4656 | BF_PS2-06-IG-0001B_CKT2Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0002 - SIS/FGS Marsh Cab 2 UPS B Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4657 | BF_PS2-06-IG-0001B_CKT2Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0003 - SIS/FGS Marsh Cab 3 UPS B Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4658 | BF_PS2-06-IG-0001B_CKT2Q7 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0004 - SIS/FGS Marsh Cab 4 UPS B Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4659 | BF_PS2-06-IG-0001B_CKT2Q8 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0005 - SIS/FGS Marsh Cab 5 UPS B Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4660 | BF_PS2-06-IG-0001B_CKT2Q9 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0006 - SIS/FGS Marsh Cab 6 UPS B Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4661 | BF_PS2-06-IG-0001B_CKT3Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0007 - SIS/FGS Marsh Cab 7 UPS B Pwr Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4662 | BF_PS2-06-IG-0001B_CKT3Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IE-0001 - ECS 1 Panelboard UPS B Pwr Supply | EACOP |  | PS2-61-05 - Electrical Control System |  |  |  | Construction not yet started |  | #N/A
T-00347-4663 | BF_PS2-06-IG-0001B_CKT3Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IE-0002 - ECS 2 Panelboard UPS B Pwr Supply | EACOP |  | PS2-61-05 - Electrical Control System |  |  |  | Construction not yet started |  | #N/A
T-00347-4664 | BF_PS2-06-IG-0001B_CKT3Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-08-35CB-1001 - TEL OTN Cabinet UPS B Pwr Supply | EACOP |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00347-4665 | BF_PS2-06-IG-0001B_CKT3Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-08-13CB-1001 - TEL SII SP3 SAF Cabinet UPS B Pwr Supply | EACOP |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00347-4666 | BF_PS2-06-IG-0001B_CKT3Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-08-15CB-1001 - TEL SII SP3 SEC Cabinet UPS B Pwr Supply | EACOP |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00347-4667 | BF_PS2-06-IG-0001B_CKT3Q7 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-08-11CB-1001 - TEL SIE & SII SP1 Cabinet UPS B Pwr Supply | EACOP |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00347-4668 | BF_PS2-06-IG-0001B_CKT3Q8 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-IE-0001 - VTMS Export loading Pumps UPS B Pwr Supply | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00347-4669 | BF_PS2-06-IG-0001B_CKT3Q9 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-01-LA-0001 - OPPS Cabinet UPS B Pwr Supply | EACOP |  | PS2-0H-01 - HIPPS |  |  |  | Construction not yet started |  | #N/A
T-00347-4670 | BF_PS2-06-IG-0001B_CKT4Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-05-IE-8100 - EDG UCP UPS B Pwr Supply | EACOP |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | #N/A
T-00347-4671 | BF_PS2-06-IG-0001B_CKT4Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-53-IN-0001 - Water Treat UCP UPS B Pwr Supply | EACOP |  | PS2-53-03 - Water Treatment Purification Package |  |  |  | Construction not yet started |  | #N/A
T-00347-4672 | BF_PS2-06-IG-0001B_CKT4Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IDH-3100B - VSD-B Control UPS Pwr Supply | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00347-4673 | BF_PS2-06-IG-0001B_CKT4Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IDH-3100C - VSD-C Control UPS Pwr Supply | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00347-4674 | BF_PS2-06-IG-0001B_CKT4Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4675 | BF_PS2-06-IG-0001B_CKT4Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4676 | BF_PS2-06-IG-0001B_CKT4Q7 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4677 | BF_PS2-06-IG-0001B_CKT4Q8 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4678 | BF_PS2-06-IG-0001B_CKT4Q9 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4679 | BF_PS2-06-IG-0001B_CKT5Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4680 | BF_PS2-06-IG-0001B_CKT5Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4681 | BF_PS2-06-IG-0002_CKT1Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IJ-0010 - LLHT MV SWGR UPS C Ctrl Supply | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00347-4682 | BF_PS2-06-IG-0002_CKT1Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IJ-0011 - LLHT MV SWGR UPS C Ctrl Supply | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00347-4683 | BF_PS2-06-IG-0002_CKT1Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IK-0001 - LV MCC SWGR_SEC.C UPS C Ctrl Supply | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00347-4684 | BF_PS2-06-IG-0002_CKT1Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-08-35CB-1001 - TEL OTN Cabinet UPS C Pwr Supply | EACOP |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00347-4685 | BF_PS2-06-IG-0002_CKT1Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-08-13CB-1001 - TEL SII SP3 SAF Cabinet UPS C Pwr Supply | EACOP |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00347-4686 | BF_PS2-06-IG-0002_CKT1Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-08-15CB-1001 - TEL SII SP3 SEC Cabinet UPS C Pwr Supply | EACOP |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00347-4687 | BF_PS2-06-IG-0002_CKT1Q7 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-08-11CB-1001 - TEL SIE & SII SP1 Cabinet UPS C Pwr Supply | EACOP |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00347-4688 | BF_PS2-06-IG-0002_CKT1Q8 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-09-LB-0001 - HVAC Control Panel UPS Ctrl Supply | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4689 | BF_PS2-06-IG-0002_CKT1Q9 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-05-IG-0009 - EDG PDP UPS Pwr Supply | EACOP |  | PS2-05-01 - Emergency Diesel Generator Package |  |  |  | Construction not yet started |  | #N/A
T-00347-4690 | BF_PS2-06-IG-0002_CKT2Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-FIT-0001 - Ultrasonic Flow Ind TRM UPS Pwr Supply | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00347-4691 | BF_PS2-06-IG-0002_CKT2Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-FIT-0003A - Ultrasonic Flow Ind TRM UPS Pwr Supply | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00347-4692 | BF_PS2-06-IG-0002_CKT2Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-FIT-0003B - Ultrasonic Flow Ind TRM UPS Pwr Supply | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00347-4693 | BF_PS2-06-IG-0002_CKT2Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-FIT-0003C - Ultrasonic Flow Ind TRM UPS Pwr Supply | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00347-4694 | BF_PS2-06-IG-0002_CKT2Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-FIT-0004 - Ultrasonic Flow Ind TRM UPS Pwr Supply | EACOP |  | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | #N/A
T-00347-4695 | BF_PS2-06-IG-0002_CKT2Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-GDLHP-0105 - Liquid Hydro Detector UPS Pwr Supply | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | #N/A
T-00347-4696 | BF_PS2-06-IG-0002_CKT2Q7 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-GDLHP-0106 - Liquid Hydro Detector UPS Pwr Supply | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | #N/A
T-00347-4697 | BF_PS2-06-IG-0002_CKT2Q8 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-GDLHP-0107 - Liquid Hydro Detector UPS Pwr Supply | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | #N/A
T-00347-4698 | BF_PS2-06-IG-0002_CKT2Q9 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-GDLHP-0109 - Liquid Hydro Detector UPS Pwr Supply | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | #N/A
T-00347-4699 | BF_PS2-06-IG-0002_CKT3Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-GDLHP-0111 - Liquid Hydro Detector UPS Pwr Supply | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | #N/A
T-00347-4700 | BF_PS2-06-IG-0002_CKT3Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4701 | BF_PS2-06-IG-0002_CKT3Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4702 | BF_PS2-06-IG-0002_CKT3Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4703 | BF_PS2-06-IG-0002_CKT3Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IJ-0001 - 33kV MV SWGR_SEC.A UPS C Ctrl Supply | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00347-4704 | BF_PS2-06-IG-0002_CKT3Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IJ-0001 - 33kV MV SWGR_SEC.B UPS C Ctrl Supply | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00347-4705 | BF_PS2-06-IG-0002_CKT3Q7 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IK-0001 - LV MCC SWGR_SEC.A UPS C Ctrl Supply | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00347-4706 | BF_PS2-06-IG-0002_CKT3Q8 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IK-0001 - LV MCC SWGR_SEC.B UPS C Ctrl Supply | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00347-4707 | BF_PS2-61-IG-0008_CKT1Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IJ-0001 - 33kV MV SWGR_SEC.A Heater & light Supply | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00347-4708 | BF_PS2-61-IG-0008_CKT1Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IJ-0001 - 33kV MV SWGR_SEC.B Heater & light Supply | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00347-4709 | BF_PS2-61-IG-0008_CKT1Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IJ-0010 - LLHT MV SWGR Heater & light Supply | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00347-4710 | BF_PS2-61-IG-0008_CKT1Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IJ-0011 - LLHT MV SWGR Heater & light Supply | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00347-4711 | BF_PS2-61-IG-0008_CKT1Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IK-0001 - LV MCC SWGR_SEC.A Heater & light Supply | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00347-4712 | BF_PS2-61-IG-0008_CKT1Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IK-0001 - LV MCC SWGR_SEC.B Heater & light Supply | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00347-4713 | BF_PS2-61-IG-0008_CKT1Q7 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IK-0001 - LV MCC SWGR_SEC.C Heater & light Supply | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00347-4714 | BF_PS2-61-IG-0008_CKT1Q8 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-06-GU-0001 - AC UPS Cabinet Heater & light Supply | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4715 | BF_PS2-61-IG-0008_CKT1Q9 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IU-0010 - LLHT OT Motorised Marshalling box supply | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00347-4716 | BF_PS2-61-IG-0008_CKT2Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IU-0011 - LLHT OT Motorised Marshalling box supply | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00347-4717 | BF_PS2-61-IG-0008_CKT2Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IU-0010 - LLHT OT Motorised MDU supply | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00347-4718 | BF_PS2-61-IG-0008_CKT2Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IU-0011 - LLHT OT Motorised MDU supply | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00347-4719 | BF_PS2-61-IG-0008_CKT2Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IV-0001A - Oil Distr. Trf Marshalling box supply | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00347-4720 | BF_PS2-61-IG-0008_CKT2Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IV-0001B - Oil Distr. Trf Marshalling box supply | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00347-4721 | BF_PS2-61-IG-0008_CKT2Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-63-IV-0010 - Earthing Transformer Marshalling box supply | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00347-4722 | BF_PS2-61-IG-0008_CKT3Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-ISR-0101 - Shunt Reactor Heater & light Supply | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00347-4723 | BF_PS2-61-IG-0008_CKT3Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-08 - EITS 33kV Bld. Normal Auxiliary DP - PS2-61-IG-0008 |  |  |  | Construction not yet started |  | #N/A
T-00347-4724 | BF_PS2-61-IG-0008_CKT3Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-63-NER-0010 - Earthing Transformer NER Heater & light Supply | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00347-4725 | BF_PS2-61-IG-0008_CKT3Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-NER-0010 - LLHT Transformer NER Heater & light Supply | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00347-4726 | BF_PS2-61-IG-0008_CKT3Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-NER-0011 - LLHT Transformer NER Heater & light Supply | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00347-4727 | BF_PS2-61-IG-0008_CKT3Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-04-PNC-0001 - ICSS Network Cabinet 1 Heater & light Supply | EACOP |  | PS2-04-03 - EITS Building ICSS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4728 | BF_PS2-61-IG-0008_CKT3Q7 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-08 - EITS 33kV Bld. Normal Auxiliary DP - PS2-61-IG-0008 |  |  |  | Construction not yet started |  | #N/A
T-00347-4729 | BF_PS2-61-IG-0008_CKT3Q8 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-04-PSC-0001 - PCS System Cab 1 Heater & light Supply | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4730 | BF_PS2-61-IG-0008_CKT3Q9 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-04-PSC-0002 - PCS System Cab 2 Heater & light Supply | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4731 | BF_PS2-61-IG-0008_CKT4Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-04-PMC-0001 - PCS Marsh Cab 1 Heater & light Supply | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4732 | BF_PS2-61-IG-0008_CKT4Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-04-PMC-0002 - PCS Marsh Cab 2 Heater & light Supply | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4733 | BF_PS2-61-IG-0008_CKT4Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-04-PMC-0003 - PCS Marsh Cab 3 Heater & light Supply | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4734 | BF_PS2-61-IG-0008_CKT4Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-04-PMC-0004 - PCS Marsh Cab 4 Heater & light Supply | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4735 | BF_PS2-61-IG-0008_CKT4Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-04-PMC-0005 - PCS Marsh Cab 5 Heater & light Supply | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4736 | BF_PS2-61-IG-0008_CKT4Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFSC-0001 - SIS/FGS System Cab 1 Heater & light Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4737 | BF_PS2-61-IG-0008_CKT4Q7 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFSC-0002 - SIS/FGS System Cab 2 Heater & light Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4738 | BF_PS2-61-IG-0008_CKT4Q8 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFSC-0003 - SIS/FGS System Cab 3 Heater & light Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4739 | BF_PS2-61-IG-0008_CKT4Q9 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0001 - SIS/FGS Marsh Cab 1 Heater & light Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4740 | BF_PS2-61-IG-0008_CKT5Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0002 - SIS/FGS Marsh Cab 2 Heater & light Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4741 | BF_PS2-61-IG-0008_CKT5Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0003 - SIS/FGS Marsh Cab 3 Heater & light Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4742 | BF_PS2-61-IG-0008_CKT5Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0004 - SIS/FGS Marsh Cab 4 Heater & light Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4743 | BF_PS2-61-IG-0008_CKT5Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0005 - SIS/FGS Marsh Cab 5 Heater & light Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4744 | BF_PS2-61-IG-0008_CKT5Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0006 - SIS/FGS Marsh Cab 6 Heater & light Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4745 | BF_PS2-61-IG-0008_CKT5Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-03-SFMC-0007 - SIS/FGS Marsh Cab 7 Heater & light Supply | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00347-4746 | BF_PS2-61-IG-0008_CKT5Q7 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IE-0001 - ECS 1 Panelboard Heater & light Supply | EACOP |  | PS2-61-05 - Electrical Control System |  |  |  | Construction not yet started |  | #N/A
T-00347-4747 | BF_PS2-61-IG-0008_CKT5Q8 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IE-0002 - ECS 2 Panelboard Heater & light Supply | EACOP |  | PS2-61-05 - Electrical Control System |  |  |  | Construction not yet started |  | #N/A
T-00347-4748 | BF_PS2-61-IG-0008_CKT5Q9 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-08-35CB-1001 - TEL OTN Cabinet Heater & light Supply | EACOP |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00347-4749 | BF_PS2-61-IG-0008_CKT6Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-08-13CB-1001 - TEL SII SP3 SAF Cabinet Heater & light Supply | EACOP |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00347-4750 | BF_PS2-61-IG-0008_CKT6Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-08-15CB-1001 - TEL SII SP3 SEC Cabinet Heater & light Supply | EACOP |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00347-4751 | BF_PS2-61-IG-0008_CKT6Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-08-11CB-1001 - TEL SIE & SII SP1 Cabinet Heater & light Supply | EACOP |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00347-4752 | BF_PS2-61-IG-0008_CKT6Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-61-IG-0003 - Normal L& small power DB Heater & light Supply | EACOP |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00347-4753 | BF_PS2-61-IG-0008_CKT6Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-05-IG-0003 - Emergency Lighting DB Heater & light Supply | EACOP |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00347-4754 | BF_PS2-61-IG-0008_CKT6Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-08 - EITS 33kV Bld. Normal Auxiliary DP - PS2-61-IG-0008 |  |  |  | Construction not yet started |  | #N/A
T-00347-4755 | BF_PS2-61-IG-0008_CKT6Q7 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-09-LB-0001 - HVAC Control Panel Heater & light Supply | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00347-4756 | BF_PS2-61-IG-0008_CKT6Q8 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-08 - EITS 33kV Bld. Normal Auxiliary DP - PS2-61-IG-0008 |  |  |  | Construction not yet started |  | #N/A
T-00347-4757 | BF_PS2-61-IG-0008_CKT6Q9 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-08 - EITS 33kV Bld. Normal Auxiliary DP - PS2-61-IG-0008 |  |  |  | Construction not yet started |  | #N/A
T-00347-4758 | BF_PS2-61-IG-0008_CKT7Q1 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-25-IE-0001 - VTMS Export loading Pumps Heater & light Supply | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00347-4759 | BF_PS2-61-IG-0008_CKT7Q2 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | PS2-01-LA-0001 - OPPS Cabinet Heater & light Supply | EACOP |  | PS2-0H-01 - HIPPS |  |  |  | Construction not yet started |  | #N/A
T-00347-4760 | BF_PS2-61-IG-0008_CKT7Q3 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-08 - EITS 33kV Bld. Normal Auxiliary DP - PS2-61-IG-0008 |  |  |  | Construction not yet started |  | #N/A
T-00347-4761 | BF_PS2-61-IG-0008_CKT7Q4 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-08 - EITS 33kV Bld. Normal Auxiliary DP - PS2-61-IG-0008 |  |  |  | Construction not yet started |  | #N/A
T-00347-4762 | BF_PS2-61-IG-0008_CKT7Q5 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-08 - EITS 33kV Bld. Normal Auxiliary DP - PS2-61-IG-0008 |  |  |  | Construction not yet started |  | #N/A
T-00347-4763 | BF_PS2-61-IG-0008_CKT7Q6 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-08 - EITS 33kV Bld. Normal Auxiliary DP - PS2-61-IG-0008 |  |  |  | Construction not yet started |  | #N/A
T-00347-4764 | BF_PS2-61-IG-0008_CKT7Q7 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-08 - EITS 33kV Bld. Normal Auxiliary DP - PS2-61-IG-0008 |  |  |  | Construction not yet started |  | #N/A
T-00347-4765 | BF_PS2-61-IG-0008_CKT7Q8 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-08 - EITS 33kV Bld. Normal Auxiliary DP - PS2-61-IG-0008 |  |  |  | Construction not yet started |  | #N/A
T-00347-4766 | BF_PS2-61-IG-0008_CKT7Q9 | FP18 - Lighting & Small Power | COM - Commissioning | E - Electrical | Spare | EACOP |  | PS2-61-08 - EITS 33kV Bld. Normal Auxiliary DP - PS2-61-IG-0008 |  |  |  | Construction not yet started |  | #N/A
T-00349-0005 | BF_PS2-09-HE-2700 | FP20 - Power Heater | COM - Commissioning | E - Electrical | ELECTRICAL HEATER | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00349-0020 | BF_PS2-25-HE-2100 | FP20 - Power Heater | COM - Commissioning | E - Electrical | Crude Oil Export Pump Motor A - Lube Oil System Oil Reservoir Heater | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00349-0021 | BF_PS2-25-HE-2200 | FP20 - Power Heater | COM - Commissioning | E - Electrical | Crude Oil Export Pump Motor B - Lube Oil System Oil Reservoir Heater | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00349-0022 | BF_PS2-25-HE-2300 | FP20 - Power Heater | COM - Commissioning | E - Electrical | Crude Oil Export Pump Motor C - Lube Oil System Oil Reservoir Heater | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00349-0023 | BF_PS2-28-HE-2100 | FP20 - Power Heater | COM - Commissioning | E - Electrical | CLOSED DRAIN DRUM HEATER | EACOP |  | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | #N/A
T-00350-0485 | BF_PS2-79-IG-0001_CKT01 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0486 | BF_PS2-79-IG-0001_CKT02 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0487 | BF_PS2-79-IG-0001_CKT03 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0488 | BF_PS2-79-IG-0001_CKT04 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0489 | BF_PS2-79-IG-0001_CKT05 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0490 | BF_PS2-79-IG-0001_CKT06 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0491 | BF_PS2-79-IG-0001_CKT07 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0492 | BF_PS2-79-IG-0001_CKT08 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0493 | BF_PS2-79-IG-0001_CKT09 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0494 | BF_PS2-79-IG-0001_CKT10 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0495 | BF_PS2-79-IG-0001_CKT11 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0496 | BF_PS2-79-IG-0001_CKT12 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0497 | BF_PS2-79-IG-0001_CKT13 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0498 | BF_PS2-79-IG-0001_CKT14 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0499 | BF_PS2-79-IG-0001_CKT15 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0500 | BF_PS2-79-IG-0001_CKT16 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0501 | BF_PS2-79-IG-0001_CKT17 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0502 | BF_PS2-79-IG-0001_CKT18 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0503 | BF_PS2-79-IG-0001_CKT19 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0504 | BF_PS2-79-IG-0001_CKT20 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0505 | BF_PS2-79-IG-0001_CKT21 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0506 | BF_PS2-79-IG-0001_CKT22 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0507 | BF_PS2-79-IG-0001_CKT23 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0508 | BF_PS2-79-IG-0001_CKT24 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0509 | BF_PS2-79-IG-0001_CKT25 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0510 | BF_PS2-79-IG-0001_CKT26 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0511 | BF_PS2-79-IG-0001_CKT27 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0512 | BF_PS2-79-IG-0001_CKT28 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0513 | BF_PS2-79-IG-0001_CKT29 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0514 | BF_PS2-79-IG-0001_CKT30 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0515 | BF_PS2-79-IG-0001_CKT31 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0516 | BF_PS2-79-IG-0001_CKT32 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0517 | BF_PS2-79-IG-0001_CKT33 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0518 | BF_PS2-79-IG-0001_CKT34 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0519 | BF_PS2-79-IG-0001_CKT36 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00350-0520 | BF_PS2-79-IG-0002_CKT01 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0521 | BF_PS2-79-IG-0002_CKT02 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0522 | BF_PS2-79-IG-0002_CKT03 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0523 | BF_PS2-79-IG-0002_CKT04 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0524 | BF_PS2-79-IG-0002_CKT05 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0525 | BF_PS2-79-IG-0002_CKT06 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0526 | BF_PS2-79-IG-0002_CKT07 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0527 | BF_PS2-79-IG-0002_CKT08 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0528 | BF_PS2-79-IG-0002_CKT09 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0529 | BF_PS2-79-IG-0002_CKT10 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0530 | BF_PS2-79-IG-0002_CKT11 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0531 | BF_PS2-79-IG-0002_CKT12 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0532 | BF_PS2-79-IG-0002_CKT13 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0533 | BF_PS2-79-IG-0002_CKT14 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0534 | BF_PS2-79-IG-0002_CKT15 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0535 | BF_PS2-79-IG-0002_CKT16 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0536 | BF_PS2-79-IG-0002_CKT17 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0537 | BF_PS2-79-IG-0002_CKT18 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0538 | BF_PS2-79-IG-0002_CKT19 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0539 | BF_PS2-79-IG-0002_CKT20 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0540 | BF_PS2-79-IG-0002_CKT21 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0541 | BF_PS2-79-IG-0002_CKT22 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0542 | BF_PS2-79-IG-0002_CKT23 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0543 | BF_PS2-79-IG-0002_CKT24 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0544 | BF_PS2-79-IG-0002_CKT25 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0545 | BF_PS2-79-IG-0002_CKT26 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0546 | BF_PS2-79-IG-0002_CKT27 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0547 | BF_PS2-79-IG-0002_CKT28 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0548 | BF_PS2-79-IG-0002_CKT29 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0549 | BF_PS2-79-IG-0002_CKT31 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00350-0550 | BF_PS2-79-IG-0003_CKT01 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0551 | BF_PS2-79-IG-0003_CKT02 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0552 | BF_PS2-79-IG-0003_CKT03 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0553 | BF_PS2-79-IG-0003_CKT04 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0554 | BF_PS2-79-IG-0003_CKT05 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0555 | BF_PS2-79-IG-0003_CKT06 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0556 | BF_PS2-79-IG-0003_CKT07 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0557 | BF_PS2-79-IG-0003_CKT08 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0558 | BF_PS2-79-IG-0003_CKT09 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0559 | BF_PS2-79-IG-0003_CKT10 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0560 | BF_PS2-79-IG-0003_CKT11 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0561 | BF_PS2-79-IG-0003_CKT12 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0562 | BF_PS2-79-IG-0003_CKT13 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0563 | BF_PS2-79-IG-0003_CKT14 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0564 | BF_PS2-79-IG-0003_CKT15 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0565 | BF_PS2-79-IG-0003_CKT16 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0566 | BF_PS2-79-IG-0003_CKT17 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0567 | BF_PS2-79-IG-0003_CKT18 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0568 | BF_PS2-79-IG-0003_CKT19 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0569 | BF_PS2-79-IG-0003_CKT20 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0570 | BF_PS2-79-IG-0003_CKT21 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0571 | BF_PS2-79-IG-0003_CKT22 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0572 | BF_PS2-79-IG-0003_CKT23 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0573 | BF_PS2-79-IG-0003_CKT24 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0574 | BF_PS2-79-IG-0003_CKT25 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0575 | BF_PS2-79-IG-0003_CKT26 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0576 | BF_PS2-79-IG-0003_CKT27 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0577 | BF_PS2-79-IG-0003_CKT40 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00350-0578 | BF_PS2-79-IG-0004_CKT01 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0579 | BF_PS2-79-IG-0004_CKT02 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0580 | BF_PS2-79-IG-0004_CKT03 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0581 | BF_PS2-79-IG-0004_CKT04 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0582 | BF_PS2-79-IG-0004_CKT05 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0583 | BF_PS2-79-IG-0004_CKT06 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0584 | BF_PS2-79-IG-0004_CKT07 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0585 | BF_PS2-79-IG-0004_CKT08 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0586 | BF_PS2-79-IG-0004_CKT09 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0587 | BF_PS2-79-IG-0004_CKT10 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0588 | BF_PS2-79-IG-0004_CKT11 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0589 | BF_PS2-79-IG-0004_CKT12 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0590 | BF_PS2-79-IG-0004_CKT13 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0591 | BF_PS2-79-IG-0004_CKT14 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0592 | BF_PS2-79-IG-0004_CKT15 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0593 | BF_PS2-79-IG-0004_CKT16 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0594 | BF_PS2-79-IG-0004_CKT17 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0595 | BF_PS2-79-IG-0004_CKT18 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0596 | BF_PS2-79-IG-0004_CKT19 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0597 | BF_PS2-79-IG-0004_CKT20 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0598 | BF_PS2-79-IG-0004_CKT21 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0599 | BF_PS2-79-IG-0004_CKT22 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0600 | BF_PS2-79-IG-0004_CKT23 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0601 | BF_PS2-79-IG-0004_CKT24 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0602 | BF_PS2-79-IG-0004_CKT25 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0603 | BF_PS2-79-IG-0004_CKT26 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0604 | BF_PS2-79-IG-0004_CKT28 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0605 | BF_PS2-79-IG-0004_CKT29 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0606 | BF_PS2-79-IG-0004_CKT30 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0607 | BF_PS2-79-IG-0004_CKT33 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0608 | BF_PS2-79-IG-0004_CKT40 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00350-0609 | BF_PS2-79-IG-0005_CKT01 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0610 | BF_PS2-79-IG-0005_CKT02 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0611 | BF_PS2-79-IG-0005_CKT03 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0612 | BF_PS2-79-IG-0005_CKT04 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0613 | BF_PS2-79-IG-0005_CKT05 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0614 | BF_PS2-79-IG-0005_CKT06 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0615 | BF_PS2-79-IG-0005_CKT07 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0616 | BF_PS2-79-IG-0005_CKT08 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0617 | BF_PS2-79-IG-0005_CKT09 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0618 | BF_PS2-79-IG-0005_CKT10 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0619 | BF_PS2-79-IG-0005_CKT11 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0620 | BF_PS2-79-IG-0005_CKT12 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0621 | BF_PS2-79-IG-0005_CKT13 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0622 | BF_PS2-79-IG-0005_CKT14 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0623 | BF_PS2-79-IG-0005_CKT15 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0624 | BF_PS2-79-IG-0005_CKT16 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0625 | BF_PS2-79-IG-0005_CKT17 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0626 | BF_PS2-79-IG-0005_CKT18 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0627 | BF_PS2-79-IG-0005_CKT19 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0628 | BF_PS2-79-IG-0005_CKT20 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0629 | BF_PS2-79-IG-0005_CKT21 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0630 | BF_PS2-79-IG-0005_CKT22 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0631 | BF_PS2-79-IG-0005_CKT23 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0632 | BF_PS2-79-IG-0005_CKT24 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0633 | BF_PS2-79-IG-0005_CKT25 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0634 | BF_PS2-79-IG-0005_CKT26 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0635 | BF_PS2-79-IG-0005_CKT27 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0636 | BF_PS2-79-IG-0005_CKT29 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0637 | BF_PS2-79-IG-0005_CKT30 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00350-0638 | BF_PS2-79-IG-0005_CKT40 | FP22 - Heat Tracing | COM - Commissioning | E - Electrical | Heat Tracing circuit | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00352-0076 | BF_PS2-61-IJ-0001 | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | MV Switchgear | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00352-0077 | BF_PS2-61-IJ-0010 | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | MV Switchgear | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00352-0078 | BF_PS2-61-IJ-0011 | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | MV Switchgear | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00352-0079 | BF_PS2-61-IK-0001 | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | LV SWGR | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00352-0142 | BF_PS2-61-IJ-0001_busbar | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | MV Switchgear | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00352-0143 | BF_PS2-61-ISR-0101 | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | Shunt Reactor | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00352-0144 | BF_PS2-61-IU-0010 | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | LLHT Oil Transformer | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00352-0145 | BF_PS2-61-IU-0011 | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | LLHT Oil Transformer | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00352-0146 | BF_PS2-61-IU-3100A | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | VSD Transformer | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00352-0147 | BF_PS2-61-IU-3100B | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | VSD Transformer | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00352-0148 | BF_PS2-61-IU-3100C | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | 33kV VSD Transformer | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00352-0149 | BF_PS2-61-IV-0001A | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | Distribution Transformer | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00352-0150 | BF_PS2-61-IV-0001B | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | Distribution Transformer | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00352-0151 | BF_PS2-63-IV-0010 | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | Earthing Transformer | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00352-0152 | BF_PS2-79-IV-0001 | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | Feeder to EHT Transformer / DB 1 | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00352-0153 | BF_PS2-79-IV-0002 | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | Feeder to EHT Transformer / DB 2 | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00352-0154 | BF_PS2-79-IV-0003 | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | Feeder to EHT Transformer / DB 3 | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00352-0155 | BF_PS2-79-IV-0004 | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | Feeder to EHT Transformer / DB 4 | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00352-0156 | BF_PS2-79-IV-0005 | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | Feeder to EHT Transformer / DB 5 | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00352-0319 | BF_PS2-25-DM-3100A | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | CRUDE OIL EXPORT PUMP A MOTOR | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00352-0320 | BF_PS2-25-DM-3100B | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | CRUDE OIL EXPORT PUMP B MOTOR | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00352-0321 | BF_PS2-25-DM-3100C | FTR-1 - Miscellaneous | COM - Commissioning | E - Electrical | CRUDE OIL EXPORT PUMP C MOTOR | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00353-0032 | PS2-61-IK-0001_A01 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | INCOMER A | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00353-0033 | PS2-61-IK-0001_AB | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | Bus-Coupler-1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00353-0034 | PS2-61-IK-0001_B01 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | INCOMER B | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00353-0035 | PS2-61-IK-0001_BC | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | Bus-Coupler-2 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00353-0036 | PS2-61-IK-0001_C01 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | INCOMER C | EACOP | UG-MID-65-SSF1-150214 | PS2-05-01 - Emergency Diesel Generator Package |  |  |  | Construction not yet started |  | #N/A
T-00353-0297 | PS2-61-IJ-0001_A02 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | MVC012A: 33/5.5kV<2MVA TFO FEEDER | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00353-0298 | PS2-61-IJ-0001_A03 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | MVC009 : 33/0.42kV/>2MVA TFO FEEDER | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00353-0299 | PS2-61-IJ-0001_A04 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | MVC016A : EARTHING TRANSFORMER | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00353-0300 | PS2-61-IJ-0001_A05 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | MVC014A : SHUNT REACTOR FEEDER | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00353-0301 | PS2-61-IJ-0001_A06 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | MVC015 : MOTOR FEEDER WITH VSD | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00353-0302 | PS2-61-IJ-0001_A07 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | MVC017 : SPARE WITH BB VTS | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00353-0303 | PS2-61-IJ-0001_AB01 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | MVC018A : COUPLER AND RISER | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00353-0304 | PS2-61-IJ-0001_AB02 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | MVC018A: RISER | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00353-0305 | PS2-61-IJ-0001_B01 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | MVC044 : GRID TFO INCOMER | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00353-0306 | PS2-61-IJ-0001_B02 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | MVC012A: 33/5.5kV<2MVA TFO FEEDER | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00353-0307 | PS2-61-IJ-0001_B03 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | MVC009 : 33/0.42kV/>2MVA TFO FEEDER | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00353-0308 | PS2-61-IJ-0001_B04 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | MVC016A : EARTHING TRANSFORMER | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00353-0309 | PS2-61-IJ-0001_B05 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | MVC015 : MOTOR FEEDER WITH VSD | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00353-0310 | PS2-61-IJ-0001_B06 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | MVC015 : MOTOR FEEDER WITH VSD | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00353-0312 | PS2-61-IJ-0001_B08 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | MVC014D : SHUNT REACTOR FEEDER | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00353-0313 | PS2-61-IJ-0010_A01 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | LLHT001A: LLHT Circuit Breaker Incomer with V.T's (1 MVA TFO) | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00353-0314 | PS2-61-IJ-0010_A02 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | LLHT001B : LLHT FEEDER (GAM / 1MVA TFO) | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00353-0315 | PS2-61-IJ-0011_A01 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | LLHT001A: LLHT Circuit Breaker Incomer with V.T's (1 MVA TFO) | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00353-0316 | PS2-61-IJ-0011_A02 | FTR-2 - Protection relay | COM - Commissioning | E - Electrical | LLHT001B : LLHT FEEDER (GAM / 1MVA TFO) | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00354-0019 | BF_PS2-06-GB-0001A | FTR-3 - Battery autonomy | COM - Commissioning | E - Electrical | Battery Rack A | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00354-0020 | BF_PS2-06-GB-0001B | FTR-3 - Battery autonomy | COM - Commissioning | E - Electrical | Battery Rack B | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00355-0019 | BF_PS2-06-GB-0001A | FTR-4 - Battery charge/discharge | COM - Commissioning | E - Electrical | Battery Rack A | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00355-0020 | BF_PS2-06-GB-0001B | FTR-4 - Battery charge/discharge | COM - Commissioning | E - Electrical | Battery Rack B | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00428-0565 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | 0
T-00428-0566 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | 0
T-00428-0567 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | 0
T-00428-0568 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | 0
T-00428-0569 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | 0
T-00428-0570 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | 0
T-00428-0571 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | 0
T-00428-0572 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | 0
T-00428-0573 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | 0
T-00428-0574 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | 0
T-00428-0575 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | 0
T-00428-0576 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | 0
T-00428-0577 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | 0
T-00428-0578 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | 0
T-00428-0579 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | 0
T-00428-0580 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | 0
T-00428-0581 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | 0
T-00428-0582 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | 0
T-00428-0583 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | 0
T-00428-0584 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | 0
T-00428-0585 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | 0
T-00428-0586 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | 0
T-00428-0587 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | 0
T-00428-0588 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | 0
T-00428-0589 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | 0
T-00428-0590 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | 0
T-00428-0591 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | 0
T-00428-0592 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | 0
T-00428-0593 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | 0
T-00428-0594 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | 0
T-00428-0595 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | 0
T-00428-0596 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | 0
T-00428-0597 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | 0
T-00428-0598 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | 0
T-00428-0599 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | 0
T-00428-0600 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | 0
T-00428-0601 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | 0
T-00428-0602 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | 0
T-00428-0603 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | 0
T-00428-0604 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | 0
T-00428-0605 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | 0
T-00428-0606 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | 0
T-00428-0607 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | 0
T-00428-0608 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | 0
T-00428-0609 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | 0
T-00428-0610 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | #N/A |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | 0
T-00428-0611 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | 0
T-00428-0612 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | 0
T-00428-0613 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | 0
T-00428-0614 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | 0
T-00428-0615 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-05 - Crude Oil Export Pumps Bypass |  |  |  | Construction not yet started |  | 0
T-00428-0616 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | 0
T-00428-0617 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | 0
T-00428-0618 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | 0
T-00428-0619 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started |  | 0
T-00428-0620 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-08 - Open Drains (OD2) |  |  |  | Construction not yet started |  | 0
T-00428-0621 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | 0
T-00428-0622 |  | FJ01F - ON/OFF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | 0
T-00429-1168 | PS2-09-LB-0006-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-04-PNC-0001 TO PS2-09-LB-0006 | CPP AGI | UG-MID-65-WPR2-160500 | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | CPP-RFI-65-16-04-0206
T-00429-1169 | PS2-09-LB-0008-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-04-PNC-0001 TO PS2-09-LB-0008 | CPP AGI | UG-MID-65-WPR2-160500 | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #N/A
T-00429-1170 | PS2-53-LA-0001-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-04-PNC-0001 TO PS2-53-LA-0001 | CPP AGI | UG-MID-65-WPR2-160500 | PS2-53-03 - Water Treatment Purification Package |  |  |  | Construction not yet started |  | #N/A
T-00429-1263 | PS2-08-11CB-1201-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-11CB-1201 | #N/A | UG-MID-65-SSF1-171120 | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00429-1264 | PS2-08-11CB-1501-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-11CB-1501 | #N/A | UG-MID-65-SSF1-171120 | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0184
T-00429-1265 | PS2-08-11CB-1601-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-11CB-1601 | #N/A | UG-MID-65-SSF1-171120 | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00429-1266 | PS2-08-12BT-0101-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0101 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/3-05-0179
T-00429-1267 | PS2-08-12BT-0102-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0102 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00429-1268 | PS2-08-12BT-0104-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0104 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00429-1269 | PS2-08-12BT-0105-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0105 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00429-1270 | PS2-08-12BT-0107-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-12BT-0107 | #N/A | UG-MID-65-SSF1-171220 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00429-1271 | PS2-08-15CP-0001-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0008 TO PS2-08-15CP-0001 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00429-1272 | PS2-08-15CP-0002-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0001 TO PS2-08-15CP-0002 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00429-1273 | PS2-08-15CP-0003-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0002 TO PS2-08-15CP-0003 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00429-1274 | PS2-08-15CP-0004-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0003 TO PS2-08-15CP-0004 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00429-1275 | PS2-08-15CP-0004-CX02 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0004 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00429-1276 | PS2-08-15CP-0005-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CP-0005 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00429-1277 | PS2-08-15CP-0006-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0005 TO PS2-08-15CP-0006 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00429-1278 | PS2-08-15CP-0007-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0006 TO PS2-08-15CP-0007 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00429-1279 | PS2-08-15CP-0008-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CP-0007 TO PS2-08-15CP-0008 | #N/A | UG-MID-65-SSF1-171520 | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00429-1280 | PS2-08-36SP-0101-CX02 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-36SP-0101 | #N/A | UG-MID-65-SSF1-173620 | PS2-08-36 - Pipeline FO Cable & EPRS |  |  |  | Construction not yet started |  | #N/A
T-00429-1281 | PS2-08-36SP-0102-CX02 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-35CB-1001 TO PS2-08-36SP-0102 | #N/A | UG-MID-65-SSF1-173620 | PS2-08-36 - Pipeline FO Cable & EPRS |  |  |  | Construction not yet started |  | #N/A
T-00429-1282 | PS2-08-52CM-0132-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-0132 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00429-1283 | PS2-08-52CM-0133-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-0133 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00429-1284 | PS2-08-52CM-0134-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-52CM-0134 | #N/A | UG-MID-65-SSF1-175220 | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00429-1285 | PS2-08-83SP-1001-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-15CB-1001 | #N/A | UG-MID-65-SSF1-178320 | PS2-08-83 - Perimeter & Pipeline intrusion detection system |  |  |  | Construction not yet started |  | #N/A
T-00429-1286 | PS2-08-85CP-0021-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-85CP-0021 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00429-1287 | PS2-08-85CP-0021-CX02 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-85CP-0021 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00429-1288 | PS2-08-85CP-0022-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-85CP-0022 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00429-1289 | PS2-08-85CP-0022-CX02 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-15CB-1001 TO PS2-08-85CP-0022 | #N/A | UG-MID-65-SSF1-178520 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00429-1581 | PS2-08-13CB-1001-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-13CB-1001 | EITS |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00429-1582 | PS2-08-15CB-1001-CX01 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00429-1583 | PS2-08-15CB-1001-CX02 | CIX55 - Fiber Optic Cable | PCOM - Precommissioning | T - Telecom | Cable FROM PS2-08-11CB-1001 TO PS2-08-15CB-1001 | EITS |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00431-0017 | PS2-08-23LA-1001 | CIX52 - Lighting Arrestor | PCOM - Precommissioning | T - Telecom | Lightning arrestor | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00431-0018 | PS2-08-23LA-1201 | CIX52 - Lighting Arrestor | PCOM - Precommissioning | T - Telecom | Lightning arrestor | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00431-0019 | PS2-08-23LA-1202 | CIX52 - Lighting Arrestor | PCOM - Precommissioning | T - Telecom | Lightning arrestor | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00431-0020 | PS2-08-23LA-1501 | CIX52 - Lighting Arrestor | PCOM - Precommissioning | T - Telecom | Lightning arrestor | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00431-0021 | PS2-08-23LA-1601 | CIX52 - Lighting Arrestor | PCOM - Precommissioning | T - Telecom | Lightning arrestor | EITS | UT-MID-60-SSF1-172302 | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00431-0084 | PS2-08-34LA-1201 | CIX52 - Lighting Arrestor | PCOM - Precommissioning | T - Telecom | Lightning Arrestors | EITS | UT-MID-60-SSF1-173402 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00431-0085 | PS2-08-34LA-1501 | CIX52 - Lighting Arrestor | PCOM - Precommissioning | T - Telecom | Lightning Arrestors | EITS | UT-MID-60-SSF1-173402 | PS2-08-34 - Satphone |  |  |  | Construction not yet started |  | #N/A
T-00432-0051 | PS2-08-12AP-0101 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | Outdoor Access Point | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00432-0052 | PS2-08-12AP-0102 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | Outdoor Access Point | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00432-0053 | PS2-08-12AP-0103 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | Outdoor Access Point | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00432-0054 | PS2-08-12AP-0104 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | Outdoor Access Point | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started | Column mounted | #N/A
T-00432-0055 | PS2-08-12AP-0105 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | ATEX Outdoor Access Point | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00432-0056 | PS2-08-12AP-0106 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | Outdoor Access Point | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00432-0057 | PS2-08-12AP-0107 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | Outdoor Access Point | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00432-0058 | PS2-08-12AP-1001 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | Indoor Access Point | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00432-0059 | PS2-08-12AP-1002 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | Indoor Access Point | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00432-0060 | PS2-08-12AP-1201 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | Indoor Access Point | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00432-0061 | PS2-08-12AP-1202 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | Indoor Access Point | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00432-0062 | PS2-08-12AP-1501 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | Indoor Access Point | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00432-0063 | PS2-08-12AP-1601 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | Indoor Access Point | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00432-0064 | PS2-08-12AP-1602 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | Indoor Access Point | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00432-0065 | PS2-08-12AP-1603 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | Indoor Access Point | EITS | UT-MID-60-SSF1-171202 | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00432-0233 | PS2-08-05IN-0001 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | Field Intercom - Personnel Entrance | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00432-0234 | PS2-08-05IN-1501 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | Master Intercom | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00432-0235 | PS2-08-85AP-0001 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | WiFi Access Point A - Primary Muster Point | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00432-0236 | PS2-08-85AP-0002 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | WiFi Access Point B - Primary Muster Point | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00432-0237 | PS2-08-85AP-0003 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | WiFi Access Point A - Secondary Muster Point | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00432-0238 | PS2-08-85AP-0004 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | WiFi Access Point B - Secondary Muster Point | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00432-0239 | PS2-08-85AP-1201 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | WiFi Access Point A - Safe Haven | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00432-0240 | PS2-08-85AP-1202 | CIX53 - WIFI Access Point | PCOM - Precommissioning | T - Telecom | WiFi Access Point B - Safe Haven | EITS | UT-MID-60-SSF1-178502 | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00439-0014 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00439-0015 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00439-0016 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00439-0895 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00439-0896 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00439-0923 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | 0
T-00439-0933 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | 0
T-00439-0934 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | 0
T-00439-0935 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | 0
T-00439-0936 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | 0
T-00439-0937 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | 0
T-00439-0938 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | 0
T-00439-0939 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | 0
T-00439-0940 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | 0
T-00439-0941 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | 0
T-00439-0942 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | 0
T-00439-0943 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | 0
T-00439-0944 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | 0
T-00439-0945 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | 0
T-00439-0946 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | 0
T-00439-0947 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | 0
T-00439-0948 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | 0
T-00439-0949 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | 0
T-00439-0950 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | 0
T-00439-0951 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | 0
T-00439-0952 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | 0
T-00439-0953 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | 0
T-00439-0954 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | 0
T-00439-0973 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | 0
T-00439-0974 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | 0
T-00439-0975 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | 0
T-00439-0976 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | 0
T-00439-0977 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | 0
T-00439-0978 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | 0
T-00439-0979 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | 0
T-00439-0980 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | 0
T-00439-0981 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | 0
T-00439-0982 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | 0
T-00439-0989 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | 0
T-00439-0990 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | 0
T-00439-0991 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | 0
T-00439-0992 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | 0
T-00439-0993 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | 0
T-00439-0994 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | 0
T-00439-0995 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | 0
T-00439-0996 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started |  | 0
T-00439-0997 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | 0
T-00439-0998 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started |  | 0
T-00439-0999 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started |  | 0
T-00439-1000 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | 0
T-00439-1001 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | 0
T-00439-1002 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | 0
T-00439-1003 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-53-01 - Utility Water Storage Tank |  |  |  | Construction not yet started |  | 0
T-00439-1004 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-53-01 - Utility Water Storage Tank |  |  |  | Construction not yet started |  | 0
T-00439-1005 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-53-02 - Water Distribution Pump |  |  |  | Construction not yet started |  | 0
T-00439-1006 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | 0
T-00439-1007 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | 0
T-00439-1008 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | 0
T-00439-1009 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | 0
T-00439-1010 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | 0
T-00439-1011 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | 0
T-00439-1012 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | 0
T-00439-1013 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | 0
T-00439-1014 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | 0
T-00439-1015 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | 0
T-00439-1016 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | 0
T-00439-1017 |  | FJ01A1 - ANALOG INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | 0
T-00441-0057 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00441-0058 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00441-0059 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00441-0060 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00441-0061 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00441-0062 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00441-0063 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00441-0064 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00441-0065 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00441-1762 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00441-1768 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00441-1769 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00441-1770 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00441-1771 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00441-1772 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-03 - FZ-03 - Buildings Area |  |  |  | Construction not yet started |  | 0
T-00441-1773 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00441-1774 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00441-1775 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00441-1776 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00441-1777 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00441-1778 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00441-1779 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00441-1780 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00441-1781 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00441-1787 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started |  | 0
T-00441-1788 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started |  | 0
T-00441-1794 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-03 - FZ-03 - Buildings Area |  |  |  | Construction not yet started |  | 0
T-00441-1795 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00441-1796 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00441-1797 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00441-1798 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00441-1799 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00441-1800 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-05 - FZ-G1 - Guard House |  |  |  | Construction not yet started |  | 0
T-00441-1801 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-05 - FZ-G1 - Guard House |  |  |  | Construction not yet started |  | 0
T-00441-1802 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-05 - FZ-G1 - Guard House |  |  |  | Construction not yet started |  | 0
T-00441-1803 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started |  | 0
T-00441-1804 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started |  | 0
T-00441-1805 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started |  | 0
T-00441-1806 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started |  | 0
T-00441-1807 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started |  | 0
T-00441-1808 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started |  | 0
T-00441-1809 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1810 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1811 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1812 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1813 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1814 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00441-1815 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1816 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1817 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-53-03 - Water Treatment Purification Package |  |  |  | Construction not yet started |  | 0
T-00441-1818 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1819 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1820 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1821 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1822 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | 0
T-00441-1823 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | 0
T-00441-1824 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | 0
T-00441-1825 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | 0
T-00441-1826 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | 0
T-00441-1827 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | 0
T-00441-1828 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | 0
T-00441-1829 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | 0
T-00441-1830 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | 0
T-00441-1831 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | 0
T-00441-1832 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00441-1833 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00441-1834 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1835 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1836 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1837 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1838 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1839 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1840 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1841 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1842 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1843 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1844 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | 0
T-00441-1851 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-0H-01 - HIPPS |  |  |  | Construction not yet started |  | 0
T-00441-1854 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | 0
T-00441-1855 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | 0
T-00441-1857 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-09 - Open Drain Interceptor |  |  |  | Construction not yet started |  | 0
T-00441-1858 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-09 - Open Drain Interceptor |  |  |  | Construction not yet started |  | 0
T-00441-1859 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-09 - Open Drain Interceptor |  |  |  | Construction not yet started |  | 0
T-00441-1860 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-53-03 - Water Treatment Purification Package |  |  |  | Construction not yet started |  | 0
T-00441-1861 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00441-1862 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | 0
T-00441-1863 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | 0
T-00441-1864 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | 0
T-00441-1865 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | 0
T-00441-1866 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | 0
T-00441-1867 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | 0
T-00441-1868 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | 0
T-00441-1869 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | 0
T-00441-1984 |  | FJ01A2 - DIGITAL INPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | 0
T-00442-0063 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00442-0064 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00442-0065 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00442-0066 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00442-0067 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00442-0068 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00442-0069 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00442-0070 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00442-0071 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-01-01 - Inergen |  |  |  | Construction not yet started |  | 0
T-00442-0798 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0799 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00442-0800 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00442-0801 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00442-0802 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00442-0803 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00442-0804 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00442-0805 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00442-0806 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-05 - FZ-G1 - Guard House |  |  |  | Construction not yet started |  | 0
T-00442-0807 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started |  | 0
T-00442-0808 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started |  | 0
T-00442-0809 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0810 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0811 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0812 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0813 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0814 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0815 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0816 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0817 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0818 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0819 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0820 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0821 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0822 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0823 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0824 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0825 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0826 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0827 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0828 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0829 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0830 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0831 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0832 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0833 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0834 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0835 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0836 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0837 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0838 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0839 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-05 - EITS Building SIS/FGS System |  |  |  | Construction not yet started |  | 0
T-00442-0840 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | 0
T-00442-0841 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00442-0843 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | 0
T-00442-0845 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | 0
T-00442-0846 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | 0
T-00442-0847 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00442-0848 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00442-0849 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00442-0850 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00442-0851 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | 0
T-00442-0852 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | 0
T-00442-0853 |  | FJ01A3 - DIGITAL OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | 0
T-00444-0028 |  | FJ01A4 - ANALOG OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started |  | 0
T-00444-0029 |  | FJ01A4 - ANALOG OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-04-04 - EITS Building PCS System |  |  |  | Construction not yet started |  | 0
T-00444-0030 |  | FJ01A4 - ANALOG OUTPUT | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | 0
T-00445-0068 |  | FJ01C - CONTROL LOOP | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | 0
T-00445-0069 |  | FJ01C - CONTROL LOOP | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | 0
T-00445-0070 |  | FJ01C - CONTROL LOOP | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | 0
T-00445-0071 |  | FJ01C - CONTROL LOOP | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | 0
T-00446-0185 |  | FJ01D1 - HEAT SMOKE DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started |  | 0
T-00446-0186 |  | FJ01D1 - HEAT SMOKE DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started |  | 0
T-00446-0187 |  | FJ01D1 - HEAT SMOKE DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started |  | 0
T-00446-0188 |  | FJ01D1 - HEAT SMOKE DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started |  | 0
T-00446-0189 |  | FJ01D1 - HEAT SMOKE DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started |  | 0
T-00446-0190 |  | FJ01D1 - HEAT SMOKE DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started |  | 0
T-00446-0191 |  | FJ01D1 - HEAT SMOKE DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started |  | 0
T-00446-0192 |  | FJ01D1 - HEAT SMOKE DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started |  | 0
T-00446-0193 |  | FJ01D1 - HEAT SMOKE DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started |  | 0
T-00446-0194 |  | FJ01D1 - HEAT SMOKE DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started |  | 0
T-00446-0195 |  | FJ01D1 - HEAT SMOKE DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00446-0196 |  | FJ01D1 - HEAT SMOKE DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00446-0197 |  | FJ01D1 - HEAT SMOKE DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00446-0198 |  | FJ01D1 - HEAT SMOKE DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00446-0199 |  | FJ01D1 - HEAT SMOKE DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00446-0200 |  | FJ01D1 - HEAT SMOKE DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00446-0201 |  | FJ01D1 - HEAT SMOKE DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-06 - FZ-E1 to E3 - EITS Building |  |  |  | Construction not yet started |  | 0
T-00447-0249 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0250 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0251 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0252 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0253 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0254 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0255 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0256 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0257 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0258 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0259 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0260 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0261 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0262 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0263 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0264 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0265 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0266 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00447-0267 |  | FJ01D2 - FLAME DETECTION | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00448-0078 |  | FJ01E - GAS DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00448-0079 |  | FJ01E - GAS DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00448-0080 |  | FJ01E - GAS DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00448-0081 |  | FJ01E - GAS DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00448-0082 |  | FJ01E - GAS DETECTOR | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | 0
T-00450-0120 |  | FJ03 - Data Communication Link | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | 0
T-00450-0124 |  | FJ03 - Data Communication Link | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | 0
T-00450-0126 |  | FJ03 - Data Communication Link | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | 0
T-00450-0128 |  | FJ03 - Data Communication Link | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | 0
T-00450-0131 |  | FJ03 - Data Communication Link | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-0H-01 - HIPPS |  |  |  | Construction not yet started |  | 0
T-00451-0161 |  | FJ04 - Single Machine Control Logic | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | 0
T-00451-0162 |  | FJ04 - Single Machine Control Logic | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | 0
T-00451-0163 |  | FJ04 - Single Machine Control Logic | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | 0
T-00451-0164 |  | FJ04 - Single Machine Control Logic | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | 0
T-00451-0165 |  | FJ04 - Single Machine Control Logic | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started |  | 0
T-00451-0166 |  | FJ04 - Single Machine Control Logic | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-53-02 - Water Distribution Pump |  |  |  | Construction not yet started |  | 0
T-00451-0197 |  | FJ04 - Single Machine Control Logic | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | 0
T-00454-0006 |  | FJ11A - 2oo3 LOGIC | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  |  |  | Construction not yet started |  | 0
T-00457-0095 |  | FJ13 - RELIEF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-01 - Export Pipeline Pig Receiver |  | Piping Scope |  | Construction not yet started |  | 0
T-00457-0096 |  | FJ13 - RELIEF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-07 - Export Pipeline Pig Launcher |  | Piping Scope |  | Construction not yet started |  | 0
T-00457-0097 |  | FJ13 - RELIEF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started |  | 0
T-00457-0098 |  | FJ13 - RELIEF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started |  | 0
T-00457-0099 |  | FJ13 - RELIEF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started |  | 0
T-00457-0100 |  | FJ13 - RELIEF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started |  | 0
T-00457-0101 |  | FJ13 - RELIEF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started |  | 0
T-00457-0102 |  | FJ13 - RELIEF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-11 - Nitrogen for Seal Oil Drain |  | Piping Scope |  | Construction not yet started |  | 0
T-00457-0103 |  | FJ13 - RELIEF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-05 - Seal Oil Drain Drum & Pump A |  | Piping Scope |  | Construction not yet started |  | 0
T-00457-0104 |  | FJ13 - RELIEF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-06 - Seal Oil Drain Drum & Pump B |  | Piping Scope |  | Construction not yet started |  | 0
T-00457-0105 |  | FJ13 - RELIEF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-07 - Seal Oil Drain Drum & Pump C |  | Piping Scope |  | Construction not yet started |  | 0
T-00457-0106 |  | FJ13 - RELIEF VALVE | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-28-04 - Reinjection Pump |  | Piping Scope |  | Construction not yet started |  | 0
T-00475-0103 |  | FJ19 - ADDRESS PANEL | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-05 - FZ-G1 - Guard House |  |  |  | Construction not yet started |  | 0
T-00475-0118 |  | FJ19 - ADDRESS PANEL | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-03-04 - FZ-04 - Emergency Diesel Generator Enclosure |  |  |  | Construction not yet started |  | 0
T-00545-0017 | BF_PS2-08-01LS-01 | FI01L - Loudspeaker Test | COM - Commissioning | T - Telecom | PS2-Loop 1 -Loudspeaker | EACOP |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00545-0018 | BF_PS2-08-01LS-02 | FI01L - Loudspeaker Test | COM - Commissioning | T - Telecom | PS2-Loop 2 -Loudspeaker | EACOP |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00545-0019 | BF_PS2-08-01LS-03 | FI01L - Loudspeaker Test | COM - Commissioning | T - Telecom | PS2-Loop 3 -Loudspeaker | EACOP |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00545-0020 | BF_PS2-08-01LS-04 | FI01L - Loudspeaker Test | COM - Commissioning | T - Telecom | PS2-Loop 4 -Loudspeaker | EACOP |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00545-0021 | BF_PS2-08-01LS-05 | FI01L - Loudspeaker Test | COM - Commissioning | T - Telecom | PS2-Loop 5 -Loudspeaker | EACOP |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00545-0022 | BF_PS2-08-01LS-06 | FI01L - Loudspeaker Test | COM - Commissioning | T - Telecom | PS2-Loop 6 -Loudspeaker | EACOP |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00546-0007 | BF_PS2-08-01FB-07 | FI01L2 - Beacon Loop Test | COM - Commissioning | T - Telecom | PS2-Loop 7 -Flashing Beacon | EACOP |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00546-0008 | BF_PS2-08-01FB-08 | FI01L2 - Beacon Loop Test | COM - Commissioning | T - Telecom | PS2-Loop 8 -Flashing Beacon | EACOP |  | PS2-08-01 - PAGA |  |  |  | Construction not yet started |  | #N/A
T-00548-0048 | BF_PS2-08-03TP-1001 | FI03IPT - IP Telephone Test | COM - Commissioning | T - Telecom | IP Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00548-0049 | BF_PS2-08-03TP-1002 | FI03IPT - IP Telephone Test | COM - Commissioning | T - Telecom | IP Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00548-0050 | BF_PS2-08-03TP-1201 | FI03IPT - IP Telephone Test | COM - Commissioning | T - Telecom | IP Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00548-0051 | BF_PS2-08-03TP-1202 | FI03IPT - IP Telephone Test | COM - Commissioning | T - Telecom | IP Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00548-0052 | BF_PS2-08-03TP-1203 | FI03IPT - IP Telephone Test | COM - Commissioning | T - Telecom | IP Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00548-0053 | BF_PS2-08-03TP-1204 | FI03IPT - IP Telephone Test | COM - Commissioning | T - Telecom | IP Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00548-0054 | BF_PS2-08-03TP-1205 | FI03IPT - IP Telephone Test | COM - Commissioning | T - Telecom | IP Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00548-0055 | BF_PS2-08-03TP-1206 | FI03IPT - IP Telephone Test | COM - Commissioning | T - Telecom | IP Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00548-0056 | BF_PS2-08-03TP-1207 | FI03IPT - IP Telephone Test | COM - Commissioning | T - Telecom | IP Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00548-0057 | BF_PS2-08-03TP-1208 | FI03IPT - IP Telephone Test | COM - Commissioning | T - Telecom | IP Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00548-0058 | BF_PS2-08-03TP-1209 | FI03IPT - IP Telephone Test | COM - Commissioning | T - Telecom | IP Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00548-0059 | BF_PS2-08-03TP-1501 | FI03IPT - IP Telephone Test | COM - Commissioning | T - Telecom | IP Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00548-0060 | BF_PS2-08-03TP-1601 | FI03IPT - IP Telephone Test | COM - Commissioning | T - Telecom | IP Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00548-0061 | BF_PS2-08-03TP-1602 | FI03IPT - IP Telephone Test | COM - Commissioning | T - Telecom | IP Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00549-0096 | BF_PS2-08-03TP-0001 | FI03T - Telephone Hazardous Area Test | COM - Commissioning | T - Telecom | Outdoor Weather Proof Analog Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00549-0097 | BF_PS2-08-03TP-0002 | FI03T - Telephone Hazardous Area Test | COM - Commissioning | T - Telecom | Outdoor Weather Proof Analog Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00549-0098 | BF_PS2-08-03TP-0101 | FI03T - Telephone Hazardous Area Test | COM - Commissioning | T - Telecom | Outdoor Weather Proof Analog Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00549-0099 | BF_PS2-08-03TP-0102 | FI03T - Telephone Hazardous Area Test | COM - Commissioning | T - Telecom | Outdoor Weather Proof Analog Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00549-0100 | BF_PS2-08-03TP-0103 | FI03T - Telephone Hazardous Area Test | COM - Commissioning | T - Telecom | Outdoor Weather Proof Analog Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00549-0101 | BF_PS2-08-03TP-0104 | FI03T - Telephone Hazardous Area Test | COM - Commissioning | T - Telecom | Outdoor Weather Proof Analog Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00550-0002 | BF_PS2-08-55VF-1201 | FI03VC - Video Conferencing system Test | COM - Commissioning | T - Telecom | Video Conference Unit | EACOP |  | PS2-08-55 - Videoconference |  |  |  | Construction not yet started |  | #N/A
T-00551-0041 | BF_PS2-08-11CB-1001 | FI00CAB1 - AC Power up cabinet | COM - Commissioning | T - Telecom | telecom cabinet - 230VAC | EACOP |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00551-0042 | BF_PS2-08-11CB-1201 | FI00CAB1 - AC Power up cabinet | COM - Commissioning | T - Telecom | telecom cabinet - 230VAC | EACOP |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00551-0043 | BF_PS2-08-11CB-1501 | FI00CAB1 - AC Power up cabinet | COM - Commissioning | T - Telecom | telecom cabinet - 230VAC | EACOP |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00551-0044 | BF_PS2-08-11CB-1601 | FI00CAB1 - AC Power up cabinet | COM - Commissioning | T - Telecom | telecom cabinet - 230VAC | EACOP |  | PS2-08-11 - Corporate LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00551-0045 | BF_PS2-08-13CB-1001 | FI00CAB1 - AC Power up cabinet | COM - Commissioning | T - Telecom | telecom cabinet - 230VAC | EACOP |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00551-0046 | BF_PS2-08-13CB-1601 | FI00CAB1 - AC Power up cabinet | COM - Commissioning | T - Telecom | telecom cabinet - 230VAC | EACOP |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00551-0047 | BF_PS2-08-14CB-1601 | FI00CAB1 - AC Power up cabinet | COM - Commissioning | T - Telecom | telecom cabinet - 230VAC | EACOP |  | PS2-08-14 - Industrial Data Network (SII SP1) |  |  |  | Construction not yet started |  | #N/A
T-00551-0048 | BF_PS2-08-15CB-1001 | FI00CAB1 - AC Power up cabinet | COM - Commissioning | T - Telecom | telecom cabinet - 230VAC | EACOP |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00551-0049 | BF_PS2-08-35CB-1001 | FI00CAB1 - AC Power up cabinet | COM - Commissioning | T - Telecom | telecom cabinet - 230VAC | EACOP |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00553-0060 | BF_PS2-08-12AP-0101 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | Outdoor Access Point | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00553-0061 | BF_PS2-08-12AP-0102 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | Outdoor Access Point | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00553-0062 | BF_PS2-08-12AP-0103 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | Outdoor Access Point | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00553-0063 | BF_PS2-08-12AP-0104 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | Outdoor Access Point | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00553-0064 | BF_PS2-08-12AP-0105 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | Outdoor Access Point | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00553-0065 | BF_PS2-08-12AP-0106 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | Outdoor Access Point | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00553-0066 | BF_PS2-08-12AP-0107 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | Outdoor Access Point | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00553-0067 | BF_PS2-08-12AP-1001 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | Indoor Access Point | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00553-0068 | BF_PS2-08-12AP-1002 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | Indoor Access Point | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00553-0069 | BF_PS2-08-12AP-1201 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | Indoor Access Point | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00553-0070 | BF_PS2-08-12AP-1202 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | Indoor Access Point | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00553-0071 | BF_PS2-08-12AP-1501 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | Indoor Access Point | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00553-0072 | BF_PS2-08-12AP-1601 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | Indoor Access Point | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00553-0073 | BF_PS2-08-12AP-1602 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | Indoor Access Point | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00553-0074 | BF_PS2-08-12AP-1603 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | Indoor Access Point | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00553-0075 | BF_PS2-08-85AP-0001 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | WiFi Access Point A - Primary Muster Point | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00553-0076 | BF_PS2-08-85AP-0002 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | WiFi Access Point B - Primary Muster Point | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00553-0077 | BF_PS2-08-85AP-0003 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | WiFi Access Point A - Secondary Muster Point | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00553-0078 | BF_PS2-08-85AP-0004 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | WiFi Access Point B - Secondary Muster Point | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00553-0079 | BF_PS2-08-85AP-1201 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | WiFi Access Point A - Safe Haven | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00553-0080 | BF_PS2-08-85AP-1202 | FI12AP - WIFI AP | COM - Commissioning | T - Telecom | WiFi Access Point B - Safe Haven | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00557-0404 | PS2-61-IK-0001_A01 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | INCOMER A | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0405 | PS2-61-IK-0001_A0201 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - M1A.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0406 | PS2-61-IK-0001_A0208 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-61-IG-0015 - Outdoor Valves Distribution Board PS2 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-07 - Outdoor Valves Distribution Board - PS2-61-IG-0015 |  |  |  | Construction not yet started |  | #N/A
T-00557-0407 | PS2-61-IK-0001_A0212 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-25-UD-3100A - 5 pin 32A plug and socket for Oil Purifier Control Panel(Portable Load) | EACOP | UG-MID-65-SSF1-150214 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00557-0408 | PS2-61-IK-0001_A0216 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - M1A.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0409 | PS2-61-IK-0001_A0218 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-25-HE-2200 - Crude Oil Export Pump B - Lube Oil System Oil Reservoir Heater | EACOP | UG-MID-65-SSF1-150214 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00557-0410 | PS2-61-IK-0001_A0221 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-53-DM-3100 - Water Distribution pump motor | EACOP | UG-MID-65-SSF1-150214 | PS2-53-02 - Water Distribution Pump |  |  |  | Construction not yet started |  | #N/A
T-00557-0411 | PS2-61-IK-0001_A0223 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-28-DM-3800B - Seal Oil Drain Drum Pump B | EACOP | UG-MID-65-SSF1-150214 | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | #N/A
T-00557-0412 | PS2-61-IK-0001_A0227 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - M1A.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0413 | PS2-61-IK-0001_A0229 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-25-DM-6600A - Crude Oil Export Pump C - Lube Oil Heat Exchanger Fan Motor 1 | EACOP | UG-MID-65-SSF1-150214 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00557-0414 | PS2-61-IK-0001_A0231 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-25-DM-6500A - Crude Oil Export Pump B - Lube Oil Heat Exchanger Fan Motor 1 | EACOP | UG-MID-65-SSF1-150214 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00557-0415 | PS2-61-IK-0001_A0233 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-25-DM-6400A - Crude Oil Export Pump A - Lube Oil Heat Exchanger Fan Motor 1 | EACOP | UG-MID-65-SSF1-150214 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00557-0416 | PS2-61-IK-0001_A0301 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - CB1.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0417 | PS2-61-IK-0001_A0308 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-28-DM-3800A - Seal Oil Drain Drum Pump A | EACOP | UG-MID-65-SSF1-150214 | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | #N/A
T-00557-0418 | PS2-61-IK-0001_A0310 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-75-DM-3100A - Biocide injection Pump Motor A | EACOP | UG-MID-65-SSF1-150214 | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | #N/A
T-00557-0419 | PS2-61-IK-0001_A0312 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - M1A.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0420 | PS2-61-IK-0001_A0316 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-25-HE-2100 - Crude Oil Export Pump A - Lube Oil System Oil Reservoir Heater | EACOP | UG-MID-65-SSF1-150214 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00557-0421 | PS2-61-IK-0001_A0319 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - M1A.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0422 | PS2-61-IK-0001_A0323 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - M1A.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0423 | PS2-61-IK-0001_A0325 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-25-DM-3400A - Crude Oil Export Pump C - Lube Oil Pump 1 Motor | EACOP | UG-MID-65-SSF1-150214 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00557-0424 | PS2-61-IK-0001_A0327 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-25-DM-3300A - Crude Oil Export Pump B - Lube Oil Pump 1 Motor | EACOP | UG-MID-65-SSF1-150214 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00557-0425 | PS2-61-IK-0001_A0329 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-25-DM-3200A - Crude Oil Export Pump A - Lube Oil Pump 1 Motor | EACOP | UG-MID-65-SSF1-150214 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00557-0426 | PS2-61-IK-0001_A0331 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - M1A.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0427 | PS2-61-IK-0001_A0333 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - M1A.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0428 | PS2-61-IK-0001_A0406 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-28-DM-3900 - Reinjection Pump | EACOP | UG-MID-65-SSF1-150214 | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started |  | #N/A
T-00557-0429 | PS2-61-IK-0001_A0411 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-28-HE-2100 - Closed Drain Drum Heater 01 | EACOP | UG-MID-65-SSF1-150214 | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | #N/A
T-00557-0430 | PS2-61-IK-0001_A0414 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - H_SW.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0431 | PS2-61-IK-0001_A0417 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - M1A.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0432 | PS2-61-IK-0001_A0419 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-61-IG-0002 - Normal feeder to Office and other EPC buildings | EACOP | UG-MID-65-SSF1-150214 | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00557-0433 | PS2-61-IK-0001_A0423 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-75-ISO-0001 - DRA Injection Pck. - Socket for MCC | EACOP | UG-MID-65-SSF1-150214 | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | #N/A
T-00557-0434 | PS2-61-IK-0001_A0427 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-61-IG-0014 - Outdoor Power Distribution Board PS2 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | #N/A
T-00557-0435 | PS2-61-IK-0001_A0431 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-61-IG-0005 - Outdoor Normal Lighting Distribution Board PS2 | EACOP | UG-MID-65-SSF1-150214 | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | #N/A
T-00557-0436 | PS2-61-IK-0001_A0509 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - CB1.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0437 | PS2-61-IK-0001_A0513 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - CB1.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0438 | PS2-61-IK-0001_A0517 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - CB1.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0439 | PS2-61-IK-0001_A0521 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - CB1.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0440 | PS2-61-IK-0001_A0525 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-61-IG-0012A - VSD E-house aux. DB - PS2-83-EHO-0001A | EACOP | UG-MID-65-SSF1-150214 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00557-0441 | PS2-61-IK-0001_A0529 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-79-IV-0002 - Feeder to EHT Transformer / DB 2 | EACOP | UG-MID-65-SSF1-150214 | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | #N/A
T-00557-0442 | PS2-61-IK-0001_A0533 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-28-DM-3100 - Closed Drain Drum Pump motor | EACOP | UG-MID-65-SSF1-150214 | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | #N/A
T-00557-0443 | PS2-61-IK-0001_A0607 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-79-IV-0003 - Feeder to EHT Transformer / DB 3 | EACOP | UG-MID-65-SSF1-150214 | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00557-0444 | PS2-61-IK-0001_A0611 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - CB1.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0445 | PS2-61-IK-0001_A0623 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-61-IV-0006A - Pre-Magnetisation VSD Transformer (PS2-61-IU-3100A) Supply via VSD | EACOP | UG-MID-65-SSF1-150214 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00557-0446 | PS2-61-IK-0001_A0627 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-79-IV-0001 - Feeder to EHT Transformer / DB 1 | EACOP | UG-MID-65-SSF1-150214 | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0447 | PS2-61-IK-0001_A0631 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - CB1.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0448 | PS2-61-IK-0001_AB | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Bus-Coupler-1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0449 | PS2-61-IK-0001_B01 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | INCOMER B | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0450 | PS2-61-IK-0001_B0205 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - CB1.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0451 | PS2-61-IK-0001_B0209 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-61-IV-0006C - Pre-Magnetisation VSD Transformer (PS2-61-IU-3100C) Supply via VSD | EACOP | UG-MID-65-SSF1-150214 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00557-0452 | PS2-61-IK-0001_B0213 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-61-IV-0006B - Pre-Magnetisation VSD Transformer (PS2-61-IU-3100B) Supply via VSD | EACOP | UG-MID-65-SSF1-150214 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00557-0453 | PS2-61-IK-0001_B0217 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - CB1.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0454 | PS2-61-IK-0001_B0221 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - CB1.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0455 | PS2-61-IK-0001_B0225 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-61-IG-0007 - Outdoor Normal Lighting Distribution Board PS2 | EACOP | UG-MID-65-SSF1-150214 | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00557-0456 | PS2-61-IK-0001_B0229 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-25-DM-3300B - Crude Oil Export Pump B - Lube Oil Pump 2 Motor | EACOP | UG-MID-65-SSF1-150214 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00557-0457 | PS2-61-IK-0001_B0231 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-79-IV-0005 - Feeder to EHT Transformer / DB 5 | EACOP | UG-MID-65-SSF1-150214 | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00557-0458 | PS2-61-IK-0001_B0309 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-79-IV-0004 - Feeder to EHT Transformer / DB 4 | EACOP | UG-MID-65-SSF1-150214 | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00557-0459 | PS2-61-IK-0001_B0313 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-61-IG-0012B - VSD E-house aux. DB - PS2-83-EHO-0001B | EACOP | UG-MID-65-SSF1-150214 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00557-0460 | PS2-61-IK-0001_B0317 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-61-IG-0012C - VSD E-house aux. DB - PS2-83-EHO-0001B | EACOP | UG-MID-65-SSF1-150214 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00557-0461 | PS2-61-IK-0001_B0321 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-75-ISO-0002 - DRA Injection Pck. - Socket for Portable Recirculation Pump Motor | EACOP | UG-MID-65-SSF1-150214 | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | #N/A
T-00557-0462 | PS2-61-IK-0001_B0325 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - CB1.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0463 | PS2-61-IK-0001_B0331 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - M1A.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0464 | PS2-61-IK-0001_B0333 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - M1A.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0465 | PS2-61-IK-0001_B0401 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - CB1.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0466 | PS2-61-IK-0001_B0410 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - M1A.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0467 | PS2-61-IK-0001_B0412 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-25-DM-3400B - Crude Oil Export Pump C - Lube Oil Pump 2 Motor | EACOP | UG-MID-65-SSF1-150214 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00557-0468 | PS2-61-IK-0001_B0416 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-25-HE-2300 - Crude Oil Export Pump C - Lube Oil System Oil Reservoir Heater | EACOP | UG-MID-65-SSF1-150214 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00557-0469 | PS2-61-IK-0001_B0418 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-75-DM-3100B - Biocide injection Pump Motor B | EACOP | UG-MID-65-SSF1-150214 | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | #N/A
T-00557-0470 | PS2-61-IK-0001_B0420 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - M1A.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0471 | PS2-61-IK-0001_B0422 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-28-DM-3800C - Seal Oil Drain Drum Pump C | EACOP | UG-MID-65-SSF1-150214 | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | #N/A
T-00557-0472 | PS2-61-IK-0001_B0426 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - M1A.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0473 | PS2-61-IK-0001_B0428 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-25-DM-6600B - Crude Oil Export Pump C - Lube Oil Heat Exchanger Fan Motor 2 | EACOP | UG-MID-65-SSF1-150214 | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00557-0474 | PS2-61-IK-0001_B0430 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-25-DM-6500B - Crude Oil Export Pump B - Lube Oil Heat Exchanger Fan Motor 2 | EACOP | UG-MID-65-SSF1-150214 | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00557-0475 | PS2-61-IK-0001_B0432 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-25-DM-6400B - Crude Oil Export Pump A - Lube Oil Heat Exchanger Fan Motor 2 | EACOP | UG-MID-65-SSF1-150214 | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00557-0476 | PS2-61-IK-0001_BC | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Bus-Coupler-2 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0477 | PS2-61-IK-0001_C01 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | INCOMER C | EACOP | UG-MID-65-SSF1-150214 | PS2-05-01 - Emergency Diesel Generator Package |  |  |  | Construction not yet started |  | #N/A
T-00557-0478 | PS2-61-IK-0001_C0201 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - M1A.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0479 | PS2-61-IK-0001_C0203 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - CB1.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0480 | PS2-61-IK-0001_C0219 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - CB1.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0481 | PS2-61-IK-0001_C0227 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-05-IG-0009 - EDG - Power Distribution Panel | EACOP | UG-MID-65-SSF1-150214 | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | #N/A
T-00557-0482 | PS2-61-IK-0001_C0231 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-05-IG-0002 - Emergency feeder to Office and other EPC buildings | EACOP | UG-MID-65-SSF1-150214 | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00557-0483 | PS2-61-IK-0001_C0315 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-05-IG-0007 - Guard House Emergency L&SP Distribution Board | EACOP | UG-MID-65-SSF1-150214 | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00557-0484 | PS2-61-IK-0001_C0319 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-53-IN-0001 - Water Treatment Package MCC | EACOP | UG-MID-65-SSF1-150214 | PS2-53-03 - Water Treatment Purification Package |  |  |  | Construction not yet started |  | #N/A
T-00557-0485 | PS2-61-IK-0001_C0323 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | Spare - CB1.1 | EACOP | UG-MID-65-SSF1-150214 | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-0486 | PS2-61-IK-0001_C0327 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-05-IG-0004 - Outdoor Emergency Lighting Distribution Board PS2 | EACOP | UG-MID-65-SSF1-150214 | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | #N/A
T-00557-0487 | PS2-61-IK-0001_C0331 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-05-IG-0006 - Outdoor Emergency Lighting Distribution Board PS2 | EACOP | UG-MID-65-SSF1-150214 | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  |  |  | Construction not yet started |  | #N/A
T-00557-1403 | PS2-61-IJ-0001_A02 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | MVC012A: 33/5.5kV<2MVA TFO FEEDER | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00557-1404 | PS2-61-IJ-0001_A03 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | MVC009 : 33/0.42kV/>2MVA TFO FEEDER | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-1405 | PS2-61-IJ-0001_A04 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | MVC016A : EARTHING TRANSFORMER | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-1406 | PS2-61-IJ-0001_A05 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | MVC014A : SHUNT REACTOR FEEDER | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-1407 | PS2-61-IJ-0001_A06 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | MVC015 : MOTOR FEEDER WITH VSD | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00557-1408 | PS2-61-IJ-0001_A07 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | MVC017 : SPARE WITH BB VTS | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-1409 | PS2-61-IJ-0001_AB01 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | MVC018A : COUPLER AND RISER | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-1410 | PS2-61-IJ-0001_AB02 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | MVC018A: RISER | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-1411 | PS2-61-IJ-0001_B01 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | MVC044 : GRID TFO INCOMER | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-1412 | PS2-61-IJ-0001_B02 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | MVC012A: 33/5.5kV<2MVA TFO FEEDER | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00557-1413 | PS2-61-IJ-0001_B03 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | MVC009 : 33/0.42kV/>2MVA TFO FEEDER | EACOP |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-1414 | PS2-61-IJ-0001_B04 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | MVC016A : EARTHING TRANSFORMER | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-1415 | PS2-61-IJ-0001_B05 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | MVC015 : MOTOR FEEDER WITH VSD | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | #N/A
T-00557-1416 | PS2-61-IJ-0001_B06 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | MVC015 : MOTOR FEEDER WITH VSD | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | #N/A
T-00557-1418 | PS2-61-IJ-0001_B08 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | MVC014D : SHUNT REACTOR FEEDER | EACOP |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00557-1419 | PS2-61-IJ-0010_A01 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | LLHT001A: LLHT Circuit Breaker Incomer with V.T's (1 MVA TFO) | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00557-1420 | PS2-61-IJ-0010_A02 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | LLHT001B : LLHT FEEDER (GAM / 1MVA TFO) | EACOP |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00557-1421 | PS2-61-IJ-0011_A01 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | LLHT001A: LLHT Circuit Breaker Incomer with V.T's (1 MVA TFO) | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00557-1422 | PS2-61-IJ-0011_A02 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | LLHT001B : LLHT FEEDER (GAM / 1MVA TFO) | EACOP |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00557-1693 | PS2-61-IK-0001_A0305 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-09-RF-6600A - EITS Building - Battery extract Fan-01A | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00557-1694 | PS2-61-IK-0001_A0401 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-61-IG-0003 - Normal Lighting and Small power Distribution Panel | EACOP |  | PS2-62-09 - EITS 33kV Bld. Normal L&SP DP - PS2-61-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00557-1695 | PS2-61-IK-0001_A0501 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-09-ACU-0007A - EITS Building - Package unit-01A | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00557-1696 | PS2-61-IK-0001_A0601 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-06-GU-0001A - AC UPS A - Main Feed | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00557-1697 | PS2-61-IK-0001_B0201 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-61-IG-0008 - Normal Auxiliary DB | EACOP |  | PS2-61-08 - EITS 33kV Bld. Normal Auxiliary DP - PS2-61-IG-0008 |  |  |  | Construction not yet started |  | #N/A
T-00557-1698 | PS2-61-IK-0001_B0301 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-09-ACU-0007B - EITS Building - Package unit-01B | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00557-1699 | PS2-61-IK-0001_B0329 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-25-DM-3200B - Crude Oil Export Pump A - Lube Oil Pump 2 Motor | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | #N/A
T-00557-1700 | PS2-61-IK-0001_C0207 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-06-GU-0001B - AC UPS B - Main Feed | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00557-1701 | PS2-61-IK-0001_C0301 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-05-IG-0003 - Emergency Lighting and Small power Distribution Panel | EACOP |  | PS2-62-08 - EITS 33kV Bld. Emergency L&SP DP - PS2-05-IG-0003 |  |  |  | Construction not yet started |  | #N/A
T-00557-1702 | PS2-61-IK-0001_C0305 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-06-GU-0001C - AC UPS - Bypass | EACOP |  | PS2-06-01 - AC UPS - EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00557-1703 | PS2-61-IK-0001_C0310 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-09-RF-6600B - EITS Building - Battery extract Fan-01B | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00557-1704 | PS2-61-IK-0001_C0312 | FTR-8 - Circuit breaker | COM - Commissioning | E - Electrical | PS2-09-HE-2700 - EITS Building - Electrical duct heater | EACOP |  | PS2-09-04 - HVAC for EITS Building |  |  |  | Construction not yet started |  | #N/A
T-00566-0026 | BF_PS2-08-85BR-1001 | FI85GAD - ACS controlled Door | COM - Commissioning | T - Telecom | Biometric Badge Reader - ITR Access | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00566-0027 | BF_PS2-08-85BR-1002 | FI85GAD - ACS controlled Door | COM - Commissioning | T - Telecom | Biometric Badge Reader - ED Room Access | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00566-0028 | BF_PS2-08-85BR-1201 | FI85GAD - ACS controlled Door | COM - Commissioning | T - Telecom | Standard Badge Reader - Main Entrance | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00566-0029 | BF_PS2-08-85BR-1501 | FI85GAD - ACS controlled Door | COM - Commissioning | T - Telecom | Biometric Badge Reader - GH Access | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00566-0030 | BF_PS2-08-85BR-1601 | FI85GAD - ACS controlled Door | COM - Commissioning | T - Telecom | Standard Badge Reader - Warehouse Entrance | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00566-0031 | BF_PS2-08-85BR-1602 | FI85GAD - ACS controlled Door | COM - Commissioning | T - Telecom | Standard Badge Reader - Workshop Entrance | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00566-0032 | BF_PS2-08-85BT-0017 | FI85GAD - ACS controlled Door | COM - Commissioning | T - Telecom | Outdoor Junction Box - 17 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00572-0077 |  | FJ05 - Data Hardwire Package | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | 0
T-00572-0078 |  | FJ05 - Data Hardwire Package | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | 0
T-00572-0088 |  | FJ05 - Data Hardwire Package | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-05-02 - Emergency Diesel Generator Package (UCP) |  |  |  | Construction not yet started |  | 0
T-00572-0092 |  | FJ05 - Data Hardwire Package | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-0H-01 - HIPPS |  |  |  | Construction not yet started |  | 0
T-00572-0093 |  | FJ05 - Data Hardwire Package | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | 0
T-00572-0104 |  | FJ05 - Data Hardwire Package | COM - Commissioning | I - Instrumentation |  | EACOP |  | PS2-53-03 - Water Treatment Purification Package |  |  |  | Construction not yet started |  | 0
T-00579-0002 | BF_PS2-08-03AF-1201 | FI03CONF - IP Conference phone Test | COM - Commissioning | T - Telecom | Audio Conference Phone | EACOP |  | PS2-08-03 - Telephone |  |  |  | Construction not yet started |  | #N/A
T-00581-0029 | BF_PS2-08-52CM-0032 | FI52PCM - Outdoor PTZ Camera | COM - Commissioning | T - Telecom | SAFE AREA PTZ CAMERA | EACOP |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00581-0030 | BF_PS2-08-52CM-0033 | FI52PCM - Outdoor PTZ Camera | COM - Commissioning | T - Telecom | SAFE AREA PTZ CAMERA | EACOP |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00581-0031 | BF_PS2-08-52CM-0034 | FI52PCM - Outdoor PTZ Camera | COM - Commissioning | T - Telecom | SAFE AREA PTZ CAMERA | EACOP |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00581-0032 | BF_PS2-08-52CM-0131 | FI52PCM - Outdoor PTZ Camera | COM - Commissioning | T - Telecom | PROCESS PTZ CAMERA | EACOP |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00581-0033 | BF_PS2-08-52CM-0132 | FI52PCM - Outdoor PTZ Camera | COM - Commissioning | T - Telecom | PROCESS PTZ CAMERA | EACOP |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00581-0034 | BF_PS2-08-52CM-0133 | FI52PCM - Outdoor PTZ Camera | COM - Commissioning | T - Telecom | PROCESS PTZ CAMERA | EACOP |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00581-0035 | BF_PS2-08-52CM-0134 | FI52PCM - Outdoor PTZ Camera | COM - Commissioning | T - Telecom | PROCESS PTZ CAMERA | EACOP |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00581-0036 | BF_PS2-08-52CM-0931 | FI52PCM - Outdoor PTZ Camera | COM - Commissioning | T - Telecom | SAFE AREA PTZ CAMERA | EACOP |  | PS2-08-52 - Process & Security CCTV |  |  |  | Construction not yet started |  | #N/A
T-00582-0226 | BF_PS2-08-85BT-0001 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 1 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0227 | BF_PS2-08-85BT-0002 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 2 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0228 | BF_PS2-08-85BT-0003 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 3 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0229 | BF_PS2-08-85BT-0004 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 4 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0230 | BF_PS2-08-85BT-0005 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 5 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0231 | BF_PS2-08-85BT-0006 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 6 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0232 | BF_PS2-08-85BT-0007 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 7 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0233 | BF_PS2-08-85BT-0008 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 8 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0234 | BF_PS2-08-85BT-0009 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 9 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0235 | BF_PS2-08-85BT-0010 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 10 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0236 | BF_PS2-08-85BT-0011 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 11 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0237 | BF_PS2-08-85BT-0012 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 12 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0238 | BF_PS2-08-85BT-0013 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 13 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0239 | BF_PS2-08-85BT-0014 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 14 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0240 | BF_PS2-08-85BT-0015 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 15 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0241 | BF_PS2-08-85BT-0016 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 16 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0242 | BF_PS2-08-85BT-0018 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 18 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0243 | BF_PS2-08-85BT-0020 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 20 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0244 | BF_PS2-08-85BT-0025 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Outdoor Junction Box - 25 | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0245 | BF_PS2-08-85BT-1002 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Junction Box - ITR Emergency Escape | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0246 | BF_PS2-08-85BT-1004 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Junction Box - ED Room Emergency Escape | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0247 | BF_PS2-08-85BT-1005 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Junction Box - Battery Room | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0248 | BF_PS2-08-85BT-1201 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Junction Box -Emergency Escape | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0249 | BF_PS2-08-85BT-1203 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Junction Box - Emergency Escape | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0250 | BF_PS2-08-85BT-1603 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Junction Box - Workshop Emergency Escape | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0251 | BF_PS2-08-85BT-1604 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Junction Box 1 - Workshop Emergency Escape | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00582-0252 | BF_PS2-08-85BT-1605 | FI85DC - ACS uncontrolled door & Gates | COM - Commissioning | T - Telecom | Junction Box 2 - Workshop Emergency Escape | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00583-0007 | BF_PS2-08-13CB-1001_TMS | FI93M - TMS Intercabinet test | COM - Commissioning | T - Telecom | telecom cabinet - 230VAC | EACOP |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00583-0008 | BF_PS2-08-13CB-1601_TMS | FI93M - TMS Intercabinet test | COM - Commissioning | T - Telecom | telecom cabinet - 230VAC | EACOP |  | PS2-08-13 - Safety Data Network (SII SP3 SAF) |  |  |  | Construction not yet started |  | #N/A
T-00586-0002 | BF_PS2-82-MGV-0003 | FI81GAG - ACS - Rolling Gate | COM - Commissioning | T - Telecom | Main Sliding gate | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00589-0005 | BF_PS2-08-23BS-1201 | FI23VTM - VHF Trunk Handheld Radios | COM - Commissioning | T - Telecom | Fixed Base station | EACOP |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00589-0006 | BF_PS2-08-23BS-1501 | FI23VTM - VHF Trunk Handheld Radios | COM - Commissioning | T - Telecom | Fixed Base station | EACOP |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00590-0021 | BF_PS2-08-23HP-3001 | FI23VTM1 - VHF Trunk Radios | COM - Commissioning | T - Telecom | ATEX handheld portable Radio | EACOP |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00590-0022 | BF_PS2-08-23HP-3002 | FI23VTM1 - VHF Trunk Radios | COM - Commissioning | T - Telecom | ATEX handheld portable Radio | EACOP |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00590-0023 | BF_PS2-08-23HP-3003 | FI23VTM1 - VHF Trunk Radios | COM - Commissioning | T - Telecom | ATEX handheld portable Radio | EACOP |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00590-0024 | BF_PS2-08-23HP-3004 | FI23VTM1 - VHF Trunk Radios | COM - Commissioning | T - Telecom | ATEX handheld portable Radio | EACOP |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00590-0025 | BF_PS2-08-23HP-3005 | FI23VTM1 - VHF Trunk Radios | COM - Commissioning | T - Telecom | ATEX handheld portable Radio | EACOP |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00590-0026 | BF_PS2-08-23HP-3006 | FI23VTM1 - VHF Trunk Radios | COM - Commissioning | T - Telecom | ATEX handheld portable Radio | EACOP |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00590-0027 | BF_PS2-08-23HP-3007 | FI23VTM1 - VHF Trunk Radios | COM - Commissioning | T - Telecom | ATEX handheld portable Radio | EACOP |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00590-0028 | BF_PS2-08-23HP-3008 | FI23VTM1 - VHF Trunk Radios | COM - Commissioning | T - Telecom | ATEX handheld portable Radio | EACOP |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00590-0029 | BF_PS2-08-23HP-3009 | FI23VTM1 - VHF Trunk Radios | COM - Commissioning | T - Telecom | ATEX handheld portable Radio | EACOP |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00590-0030 | BF_PS2-08-23HP-3010 | FI23VTM1 - VHF Trunk Radios | COM - Commissioning | T - Telecom | ATEX handheld portable Radio | EACOP |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00590-0031 | BF_PS2-08-23HP-3011 | FI23VTM1 - VHF Trunk Radios | COM - Commissioning | T - Telecom | ATEX handheld portable Radio | EACOP |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00590-0032 | BF_PS2-08-23HP-3012 | FI23VTM1 - VHF Trunk Radios | COM - Commissioning | T - Telecom | ATEX handheld portable Radio | EACOP |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00590-0033 | BF_PS2-08-23HP-3013 | FI23VTM1 - VHF Trunk Radios | COM - Commissioning | T - Telecom | ATEX handheld portable Radio | EACOP |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00590-0034 | BF_PS2-08-23HP-3014 | FI23VTM1 - VHF Trunk Radios | COM - Commissioning | T - Telecom | ATEX handheld portable Radio | EACOP |  | PS2-08-23 - VHF Trunk Radio System |  |  |  | Construction not yet started |  | #N/A
T-00596-0186 | BF_PS2-08-06AH-0001 | FI06AH - Audio challenge speaker Test | COM - Commissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EACOP |  | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00596-0187 | BF_PS2-08-06AH-0002 | FI06AH - Audio challenge speaker Test | COM - Commissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EACOP |  | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00596-0188 | BF_PS2-08-06AH-0003 | FI06AH - Audio challenge speaker Test | COM - Commissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EACOP |  | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00596-0189 | BF_PS2-08-06AH-0004 | FI06AH - Audio challenge speaker Test | COM - Commissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EACOP |  | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00596-0190 | BF_PS2-08-06AH-0005 | FI06AH - Audio challenge speaker Test | COM - Commissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EACOP |  | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00596-0191 | BF_PS2-08-06AH-0006 | FI06AH - Audio challenge speaker Test | COM - Commissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EACOP |  | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00596-0192 | BF_PS2-08-06AH-0007 | FI06AH - Audio challenge speaker Test | COM - Commissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EACOP |  | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00596-0193 | BF_PS2-08-06AH-0008 | FI06AH - Audio challenge speaker Test | COM - Commissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EACOP |  | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00596-0194 | BF_PS2-08-06AH-0009 | FI06AH - Audio challenge speaker Test | COM - Commissioning | T - Telecom | Audio Challenge Loudspeaker Unit | EACOP |  | PS2-08-06 - Audio Challenge |  |  |  | Construction not yet started |  | #N/A
T-00597-0099 | BF_PS2-08-35ON-1001 | FI35ON - OTN Node | COM - Commissioning | T - Telecom | Non-SIL3 node A (note 3) | EACOP |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00597-0100 | BF_PS2-08-35ON-1002 | FI35ON - OTN Node | COM - Commissioning | T - Telecom | Non-SIL3 node B (note 3) | EACOP |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00597-0101 | BF_PS2-08-35ON-1003 | FI35ON - OTN Node | COM - Commissioning | T - Telecom | SIL3 node A (note 3) | EACOP |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00597-0102 | BF_PS2-08-35ON-1004 | FI35ON - OTN Node | COM - Commissioning | T - Telecom | SIL3 node B (note 3) | EACOP |  | PS2-08-35 - Optical Transport Network |  |  |  | Construction not yet started |  | #N/A
T-00599-0048 | BF_PS2-08-12BT-0101 | FI00JB - Active Junction Box | COM - Commissioning | T - Telecom | Junction Box | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00599-0049 | BF_PS2-08-12BT-0102 | FI00JB - Active Junction Box | COM - Commissioning | T - Telecom | Junction Box | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00599-0050 | BF_PS2-08-12BT-0104 | FI00JB - Active Junction Box | COM - Commissioning | T - Telecom | Junction Box | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00599-0051 | BF_PS2-08-12BT-0105 | FI00JB - Active Junction Box | COM - Commissioning | T - Telecom | Junction Box | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00599-0052 | BF_PS2-08-12BT-0107 | FI00JB - Active Junction Box | COM - Commissioning | T - Telecom | Junction Box | EACOP |  | PS2-08-12 - Corporate Wireless LAN (SIE) |  |  |  | Construction not yet started |  | #N/A
T-00599-0053 | BF_PS2-08-15CP-0001 | FI00JB - Active Junction Box | COM - Commissioning | T - Telecom | Control Panel | EACOP |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00599-0054 | BF_PS2-08-15CP-0002 | FI00JB - Active Junction Box | COM - Commissioning | T - Telecom | Control Panel | EACOP |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00599-0055 | BF_PS2-08-15CP-0003 | FI00JB - Active Junction Box | COM - Commissioning | T - Telecom | Control Panel | EACOP |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00599-0056 | BF_PS2-08-15CP-0004 | FI00JB - Active Junction Box | COM - Commissioning | T - Telecom | Control Panel | EACOP |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00599-0057 | BF_PS2-08-15CP-0005 | FI00JB - Active Junction Box | COM - Commissioning | T - Telecom | Control Panel | EACOP |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00599-0058 | BF_PS2-08-15CP-0006 | FI00JB - Active Junction Box | COM - Commissioning | T - Telecom | Control Panel | EACOP |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00599-0059 | BF_PS2-08-15CP-0007 | FI00JB - Active Junction Box | COM - Commissioning | T - Telecom | Control Panel | EACOP |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00599-0060 | BF_PS2-08-15CP-0008 | FI00JB - Active Junction Box | COM - Commissioning | T - Telecom | Control Panel | EACOP |  | PS2-08-15 - Security Data Network (SII SP3 SEC) |  |  |  | Construction not yet started |  | #N/A
T-00599-0061 | BF_PS2-08-85CP-0021 | FI00JB - Active Junction Box | COM - Commissioning | T - Telecom | Outdoor Muster Enclosure A | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00599-0062 | BF_PS2-08-85CP-0022 | FI00JB - Active Junction Box | COM - Commissioning | T - Telecom | Outdoor Muster Enclosure B | EACOP |  | PS2-08-85 - Access Control, POB & e-Mustering |  |  |  | Construction not yet started |  | #N/A
T-00600-0014 | BF_PS2-08-83IU-1003 | FI83PID - PIDS | COM - Commissioning | T - Telecom | Pipeline Interrogator x2 Channels (Processor Unit) | EACOP |  | PS2-08-83 - Perimeter & Pipeline intrusion detection system |  |  |  | Construction not yet started |  | #N/A
T-00602-0004 | PS2-25-DM-3100A-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0145
T-00602-0005 | PS2-25-DM-3100A-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0209
T-00602-0006 | PS2-25-DM-3100A-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0145
T-00602-0007 | PS2-25-DM-3100A-CH04 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0145
T-00602-0008 | PS2-25-DM-3100A-CH05 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0145
T-00602-0009 | PS2-25-DM-3100A-CH06 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100A TO PS2-25-DM-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0145
T-00602-0010 | PS2-25-DM-3100B-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0209
T-00602-0011 | PS2-25-DM-3100B-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0145
T-00602-0012 | PS2-25-DM-3100B-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0145
T-00602-0013 | PS2-25-DM-3100B-CH04 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0145
T-00602-0014 | PS2-25-DM-3100B-CH05 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0145
T-00602-0015 | PS2-25-DM-3100B-CH06 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100B TO PS2-25-DM-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0219
T-00602-0016 | PS2-25-DM-3100C-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0145
T-00602-0017 | PS2-25-DM-3100C-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0145
T-00602-0018 | PS2-25-DM-3100C-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0145
T-00602-0019 | PS2-25-DM-3100C-CH04 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0209
T-00602-0020 | PS2-25-DM-3100C-CH05 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0145
T-00602-0021 | PS2-25-DM-3100C-CH06 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IDH-3100C TO PS2-25-DM-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0209
T-00602-0022 | PS2-61-IDH-3100A-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0147
T-00602-0023 | PS2-61-IDH-3100A-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0147
T-00602-0024 | PS2-61-IDH-3100A-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0147
T-00602-0025 | PS2-61-IDH-3100A-CH04 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0147
T-00602-0026 | PS2-61-IDH-3100A-CH05 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0147
T-00602-0027 | PS2-61-IDH-3100A-CH06 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0147
T-00602-0028 | PS2-61-IDH-3100A-CH07 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0147
T-00602-0029 | PS2-61-IDH-3100A-CH08 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0147
T-00602-0030 | PS2-61-IDH-3100A-CH09 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0147
T-00602-0031 | PS2-61-IDH-3100A-CH10 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0147
T-00602-0032 | PS2-61-IDH-3100A-CH11 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0147
T-00602-0033 | PS2-61-IDH-3100A-CH12 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100A TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0147
T-00602-0034 | PS2-61-IDH-3100B-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0219
T-00602-0035 | PS2-61-IDH-3100B-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0146
T-00602-0036 | PS2-61-IDH-3100B-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0146
T-00602-0037 | PS2-61-IDH-3100B-CH04 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0146
T-00602-0038 | PS2-61-IDH-3100B-CH05 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0146
T-00602-0039 | PS2-61-IDH-3100B-CH06 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0219
T-00602-0040 | PS2-61-IDH-3100B-CH07 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0146
T-00602-0041 | PS2-61-IDH-3100B-CH08 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0146
T-00602-0042 | PS2-61-IDH-3100B-CH09 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0146
T-00602-0043 | PS2-61-IDH-3100B-CH10 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0146
T-00602-0044 | PS2-61-IDH-3100B-CH11 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0219
T-00602-0045 | PS2-61-IDH-3100B-CH12 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100B TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0146
T-00602-0046 | PS2-61-IDH-3100C-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0144
T-00602-0047 | PS2-61-IDH-3100C-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0144
T-00602-0048 | PS2-61-IDH-3100C-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0144
T-00602-0049 | PS2-61-IDH-3100C-CH04 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0144
T-00602-0050 | PS2-61-IDH-3100C-CH05 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0144
T-00602-0051 | PS2-61-IDH-3100C-CH06 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0144
T-00602-0052 | PS2-61-IDH-3100C-CH07 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0144
T-00602-0053 | PS2-61-IDH-3100C-CH08 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0144
T-00602-0054 | PS2-61-IDH-3100C-CH09 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0144
T-00602-0055 | PS2-61-IDH-3100C-CH10 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0144
T-00602-0056 | PS2-61-IDH-3100C-CH11 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0144
T-00602-0057 | PS2-61-IDH-3100C-CH12 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-3100C TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0144
T-00602-0058 | PS2-61-IJ-0010-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IJ-0010 | KENT |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0164
T-00602-0059 | PS2-61-IJ-0010-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IJ-0010 | KENT |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0164
T-00602-0060 | PS2-61-IJ-0010-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IJ-0010 | KENT |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0164
T-00602-0061 | PS2-61-IJ-0011-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IJ-0011 | KENT |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0165
T-00602-0062 | PS2-61-IJ-0011-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IJ-0011 | KENT |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0165
T-00602-0063 | PS2-61-IJ-0011-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IJ-0011 | KENT |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0165
T-00602-0064 | PS2-61-ISR-0101-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-ISR-0101 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0168
T-00602-0065 | PS2-61-ISR-0101-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-ISR-0101 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0168
T-00602-0066 | PS2-61-ISR-0101-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-ISR-0101 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0168
T-00602-0067 | PS2-61-IU-0010-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0010 | KENT |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0164
T-00602-0068 | PS2-61-IU-0010-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0010 | KENT |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0164
T-00602-0069 | PS2-61-IU-0010-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0010 | KENT |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0164
T-00602-0070 | PS2-61-IU-0011-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0011 | KENT |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0165
T-00602-0071 | PS2-61-IU-0011-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0011 | KENT |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0085
T-00602-0072 | PS2-61-IU-0011-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-0011 | KENT |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0085
T-00602-0073 | PS2-61-IU-3100A-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0191
T-00602-0074 | PS2-61-IU-3100A-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0191
T-00602-0075 | PS2-61-IU-3100A-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0191
T-00602-0076 | PS2-61-IU-3100A-CH04 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0006A TO PS2-61-IU-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0147
T-00602-0077 | PS2-61-IU-3100B-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0191
T-00602-0078 | PS2-61-IU-3100B-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0191
T-00602-0079 | PS2-61-IU-3100B-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0191
T-00602-0080 | PS2-61-IU-3100B-CH04 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0006B TO PS2-61-IU-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0146
T-00602-0081 | PS2-61-IU-3100C-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0191
T-00602-0082 | PS2-61-IU-3100C-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0191
T-00602-0083 | PS2-61-IU-3100C-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IU-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0191
T-00602-0084 | PS2-61-IU-3100C-CH04 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0006C TO PS2-61-IU-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0144
T-00602-0085 | PS2-61-IV-0001A-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001A | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  | Waiting for EITS building installation | Construction work pending |  | CPP-RFI-65-33/1-07-0168
T-00602-0086 | PS2-61-IV-0001A-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001A | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  | Waiting for EITS building installation | Construction work pending |  | CPP-RFI-65-33/1-07-0168
T-00602-0087 | PS2-61-IV-0001A-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001A | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  | Waiting for EITS building installation | Construction work pending |  | CPP-RFI-65-33/1-07-0168
T-00602-0088 | PS2-61-IV-0001B-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001B | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  | Waiting for EITS building installation | Construction work pending |  | CPP-RFI-65-33/1-07-0168
T-00602-0089 | PS2-61-IV-0001B-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001B | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  | Waiting for EITS building installation | Construction work pending |  | CPP-RFI-65-33/1-07-0168
T-00602-0090 | PS2-61-IV-0001B-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IV-0001B | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  | Waiting for EITS building installation | Construction work pending |  | CPP-RFI-65-33/1-07-0168
T-00602-0091 | PS2-61-NER-0010-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-NER-0010 | KENT |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | #N/A
T-00602-0092 | PS2-61-NER-0011-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-NER-0011 | KENT |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | #N/A
T-00602-0093 | PS2-63-IV-0010-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-63-IV-0010 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00602-0094 | PS2-63-IV-0010-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-63-IV-0010 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00602-0095 | PS2-63-IV-0010-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-63-IV-0010 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00602-0096 | PS2-63-NER-0010-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-63-IV-0010 TO PS2-63-NER-0010 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00602-0097 | PS2-79-BH-0001-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0010 TO PS2-79-BH-0001 | KENT |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0163
T-00602-0098 | PS2-79-BH-0001-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0010 TO PS2-79-BH-0001 | KENT |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0163
T-00602-0099 | PS2-79-BH-0001-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0010 TO PS2-79-BH-0001 | KENT |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0163
T-00602-0100 | PS2-79-BH-0002-CH01 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0011 TO PS2-79-BH-0002 | KENT |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0163
T-00602-0101 | PS2-79-BH-0002-CH02 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0011 TO PS2-79-BH-0002 | KENT |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0163
T-00602-0102 | PS2-79-BH-0002-CH03 | TPX08-02 - HV power cable | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0011 TO PS2-79-BH-0002 | KENT |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0163
T-00604-0001 | PS2-61-IJ-0001-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-63-NER-0010 TO PS2-61-IJ-0001 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00604-0002 | PS2-61-IJ-0010-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-NER-0010 TO PS2-61-IJ-0010 | CPP AGI |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  | Cable intallation and testing completed | Closed | Closed | 2026-07-05 | CPP-RFI-65-33/1-07-0215
T-00604-0003 | PS2-61-IJ-0011-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-NER-0011 TO PS2-61-IJ-0011 | CPP AGI |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  | Cable intallation and testing completed | Closed | Closed | 2026-07-06 | CPP-RFI-65-33/1-07-0215
T-00604-0004 | PS2-61-IK-0001-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0005 | PS2-61-IK-0001-CL02 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0006 | PS2-61-IK-0001-CL03 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0007 | PS2-61-IK-0001-CL04 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0008 | PS2-61-IK-0001-CL05 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0009 | PS2-61-IK-0001-CL06 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0010 | PS2-61-IK-0001-CL07 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0011 | PS2-61-IK-0001-CL08 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0012 | PS2-61-IK-0001-CL09 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0013 | PS2-61-IK-0001-CL10 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0014 | PS2-61-IK-0001-CL11 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0015 | PS2-61-IK-0001-CL12 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0016 | PS2-61-IK-0001-CL13 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0017 | PS2-61-IK-0001-CL14 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0018 | PS2-61-IK-0001-CL15 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0019 | PS2-61-IK-0001-CL16 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0020 | PS2-61-IK-0001-CL17 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0021 | PS2-61-IK-0001-CL18 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0022 | PS2-61-IK-0001-CL19 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0201
T-00604-0023 | PS2-61-IK-0001-CL20 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0201
T-00604-0024 | PS2-61-IK-0001-CL21 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-28 | CPP-RFI-65-33/1-07-0201
T-00604-0025 | PS2-61-IK-0001-CL22 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-28 | CPP-RFI-65-33/1-07-0201
T-00604-0026 | PS2-61-IK-0001-CL23 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-28 | CPP-RFI-65-33/1-07-0201
T-00604-0027 | PS2-61-IK-0001-CL24 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-28 | CPP-RFI-65-33/1-07-0201
T-00604-0028 | PS2-61-IK-0001-CL25 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-28 | CPP-RFI-65-33/1-07-0201
T-00604-0029 | PS2-61-IK-0001-CL26 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-28 | CPP-RFI-65-33/1-07-0201
T-00604-0030 | PS2-61-IK-0001-CL27 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-28 | CPP-RFI-65-33/1-07-0201
T-00604-0031 | PS2-61-IK-0001-CL28 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-28 | CPP-RFI-65-33/1-07-0201
T-00604-0032 | PS2-61-IK-0001-CL29 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-33/1-07-0201
T-00604-0033 | PS2-61-IK-0001-CL30 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable testing RFI awaiting | ITR started-waiting for cable testing RFI | Construction Completed , Pre Com work pending |  | CPP-RFI-65-33/1-05-0083
T-00604-0034 | PS2-61-IK-0001-CL31 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-33/1-07-0201
T-00604-0035 | PS2-61-IK-0001-CL32 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-33/1-07-0201
T-00604-0036 | PS2-61-IK-0001-CL33 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-33/1-07-0201
T-00604-0037 | PS2-61-IK-0001-CL34 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-33/1-07-0201
T-00604-0038 | PS2-61-IK-0001-CL35 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-33/1-07-0201
T-00604-0039 | PS2-61-IK-0001-CL36 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-33/1-07-0201
T-00604-0040 | PS2-61-IK-0001-CL44 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-07-0202
T-00604-0041 | PS2-61-IK-0001-CL45 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-33/1-05-0083
T-00604-0042 | PS2-61-ISR-0101-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-ISR-0101 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | 70m cable pulled, coiled below EITS building, cable to be reached to cubicle , G&T to be done and IR test to be completed | ITR started-waiting for cable testing RFI | Construction Completed , Pre Com work pending |  | CPP-RFI-65-33/1-05-0085
T-00604-0043 | PS2-61-IU-0010-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-IU-0010 | CPP AGI |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  | Cable intallation and testing completed | Closed | Closed | 2026-07-06 | CPP-RFI-65-33/1-07-0215
T-00604-0044 | PS2-61-IU-0010-CL02 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-IU-0010 | CPP AGI |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  | Cable intallation and testing completed | Closed | Closed | 2026-07-06 | CPP-RFI-65-33/1-07-0215
T-00604-0045 | PS2-61-IU-0011-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-IU-0011 | CPP AGI |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  | 75m cable pulled, coiled below EITS building, cable to be reached to cubicle , G&T to be done and IR test to be completed | ITR started-waiting for cable testing RFI | Construction Completed , Pre Com work pending |  | CPP-RFI-65-33/1-05-0106
T-00604-0046 | PS2-61-IU-0011-CL02 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-IU-0011 | CPP AGI |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  | 75m cable pulled, coiled below EITS building, cable to be reached to cubicle , G&T to be done and IR test to be completed | Closed | Closed | 2026-07-06 | CPP-RFI-65-33/1-07-0215
T-00604-0047 | PS2-61-IV-0001A-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-IV-0001A | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-05-0086
T-00604-0048 | PS2-61-IV-0001B-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-IV-0001B | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-33/1-05-0083
T-00604-0049 | PS2-61-NER-0010-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-NER-0010 | CPP AGI |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  | Cable intallation and testing completed | Closed | Closed | 2026-07-06 | CPP-RFI-65-33/1-07-0215
T-00604-0050 | PS2-61-NER-0011-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-NER-0011 | CPP AGI |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  | Cable intallation and testing completed | Closed | Closed | 2026-07-06 | CPP-RFI-65-33/1-07-0215
T-00604-0051 | PS2-63-IV-0010-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-63-IV-0010 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started | Cable drum not available | #N/A
T-00604-0052 | PS2-63-NER-0010-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-63-NER-0010 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started | Cable drum not available | #N/A
T-00604-0546 | PS2-61-IK-0001-CG05 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable drum theft from Hoima Warehouse |  | Construction not yet started | Cable drum not available | #N/A
T-00604-0547 | PS2-61-IK-0001-CG06 | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable drum theft from Hoima Warehouse |  | Construction not yet started | Cable drum not available | #N/A
T-00605-0001 | PS2-61-IJ-0001-CL01 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-63-NER-0010 TO PS2-61-IJ-0001 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00605-0002 | PS2-61-IJ-0010-CL01 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-NER-0010 TO PS2-61-IJ-0010 | KENT |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00605-0003 | PS2-61-IJ-0011-CL01 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-NER-0011 TO PS2-61-IJ-0011 | KENT |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00605-0004 | PS2-61-IK-0001-CL01 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0005 | PS2-61-IK-0001-CL02 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0006 | PS2-61-IK-0001-CL03 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0007 | PS2-61-IK-0001-CL04 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0008 | PS2-61-IK-0001-CL05 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0009 | PS2-61-IK-0001-CL06 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0010 | PS2-61-IK-0001-CL07 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0011 | PS2-61-IK-0001-CL08 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0012 | PS2-61-IK-0001-CL09 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0013 | PS2-61-IK-0001-CL10 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0014 | PS2-61-IK-0001-CL11 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0015 | PS2-61-IK-0001-CL12 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0016 | PS2-61-IK-0001-CL13 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0017 | PS2-61-IK-0001-CL14 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0018 | PS2-61-IK-0001-CL15 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0019 | PS2-61-IK-0001-CL16 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0020 | PS2-61-IK-0001-CL17 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0021 | PS2-61-IK-0001-CL18 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0022 | PS2-61-IK-0001-CL19 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0201
T-00605-0023 | PS2-61-IK-0001-CL20 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0201
T-00605-0024 | PS2-61-IK-0001-CL21 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0201
T-00605-0025 | PS2-61-IK-0001-CL22 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0201
T-00605-0026 | PS2-61-IK-0001-CL23 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0201
T-00605-0027 | PS2-61-IK-0001-CL24 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0201
T-00605-0028 | PS2-61-IK-0001-CL25 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0201
T-00605-0029 | PS2-61-IK-0001-CL26 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0201
T-00605-0030 | PS2-61-IK-0001-CL27 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0201
T-00605-0031 | PS2-61-IK-0001-CL28 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0201
T-00605-0032 | PS2-61-IK-0001-CL29 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0201
T-00605-0033 | PS2-61-IK-0001-CL30 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0083
T-00605-0034 | PS2-61-IK-0001-CL31 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0201
T-00605-0035 | PS2-61-IK-0001-CL32 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0201
T-00605-0036 | PS2-61-IK-0001-CL33 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0201
T-00605-0037 | PS2-61-IK-0001-CL34 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0201
T-00605-0038 | PS2-61-IK-0001-CL35 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0201
T-00605-0039 | PS2-61-IK-0001-CL36 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0201
T-00605-0040 | PS2-61-IK-0001-CL44 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0202
T-00605-0041 | PS2-61-IK-0001-CL45 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0083
T-00605-0042 | PS2-61-ISR-0101-CL01 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-ISR-0101 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0085
T-00605-0043 | PS2-61-IU-0010-CL01 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-IU-0010 | KENT |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00605-0044 | PS2-61-IU-0010-CL02 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-IU-0010 | KENT |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00605-0045 | PS2-61-IU-0011-CL01 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-IU-0011 | KENT |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0106
T-00605-0046 | PS2-61-IU-0011-CL02 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-IU-0011 | KENT |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00605-0047 | PS2-61-IV-0001A-CL01 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-IV-0001A | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0086
T-00605-0048 | PS2-61-IV-0001B-CL01 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-IV-0001B | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0083
T-00605-0049 | PS2-61-NER-0010-CL01 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-NER-0010 | KENT |  | PS2-61-02 - 6.6kV Switchboards and Transformer LLHT North - EITS Building (PS2-61-IJ-0010) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00605-0050 | PS2-61-NER-0011-CL01 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-61-NER-0011 | KENT |  | PS2-61-03 - 6.6kV Switchboards and Transformer LLHT South - EITS Building (PS2-61-IJ-0011) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00605-0051 | PS2-63-IV-0010-CL01 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-63-IV-0010 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00605-0052 | PS2-63-NER-0010-CL01 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IG-0008 TO PS2-63-NER-0010 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00605-0546 | PS2-61-IK-0001-CG05 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00605-0547 | PS2-61-IK-0001-CG06 | TPX09a - LV power cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | #N/A
T-00606-0002 | PS2-61-IE-0001-CD01 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IE-0001 | CPP AGI |  | PS2-61-05 - Electrical Control System |  | Cable intallation and testing completed | Closed | Closed | 2026-07-05 | CPP-RFI-65-33/1-07-0215
T-00606-0003 | PS2-61-IE-0001-CD02 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IE-0001 | CPP AGI |  | PS2-61-05 - Electrical Control System |  | Cable intallation and testing completed | Closed | Closed | 2026-07-05 | CPP-RFI-65-33/1-07-0215
T-00606-0004 | PS2-61-IE-0001-CD03 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IE-0001 | CPP AGI |  | PS2-61-05 - Electrical Control System |  | Cable intallation and testing completed | Closed | Closed | 2026-07-05 | CPP-RFI-65-33/1-07-0215
T-00606-0005 | PS2-61-IE-0001-CD04 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IE-0001 | CPP AGI |  | PS2-61-05 - Electrical Control System |  | Cable intallation and testing completed | Closed | Closed | 2026-07-05 | CPP-RFI-65-33/1-07-0215
T-00606-0006 | PS2-61-IE-0001-CD05 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IE-0001 | CPP AGI |  | PS2-61-05 - Electrical Control System |  | Cable intallation and testing completed | Closed | Closed | 2026-07-05 | CPP-RFI-65-33/1-07-0215
T-00606-0007 | PS2-61-IE-0001-CD06 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IE-0001 | CPP AGI |  | PS2-61-05 - Electrical Control System |  | Cable intallation and testing completed | Closed | Closed | 2026-07-05 | CPP-RFI-65-33/1-07-0215
T-00606-0008 | PS2-61-IJ-0001-CD01 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-ISR-0101 TO PS2-61-IJ-0001 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-07-05 | CPP-RFI-65-33/1-07-0215
T-00606-0009 | PS2-61-IJ-0001-CD02 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IJ-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-27 | CPP-RFI-65-33/1-05-0086
T-00606-0010 | PS2-61-IJ-0001-CD03 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IJ-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-06-29 | CPP-RFI-65-33/1-05-0083
T-00606-0011 | PS2-61-IJ-0001-CD04 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IJ-0001 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-07-05 | CPP-RFI-65-33/1-07-0215
T-00606-0012 | PS2-61-IJ-0001-CD05 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IJ-0001 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-07-06 | CPP-RFI-65-33/1-07-0215
T-00606-0013 | PS2-61-IJ-0001-CD06 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IJ-0001 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-07-06 | CPP-RFI-65-33/1-07-0215
T-00606-0014 | PS2-61-IJ-0001-CD07 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IJ-0001 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-07-06 | CPP-RFI-65-33/1-07-0215
T-00606-0015 | PS2-61-IJ-0001-CD08 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IJ-0001 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-07-06 | CPP-RFI-65-33/1-07-0215
T-00606-0016 | PS2-61-IJ-0001-CD09 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IJ-0001 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | Cable intallation and testing completed | Closed | Closed | 2026-07-06 | CPP-RFI-65-33/1-07-0215
T-00606-0017 | PS2-61-IJ-0001-CD10 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-63-IV-0010 TO PS2-61-IJ-0001 | CPP AGI |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  | Waiting for RFI clearance |  | Construction not yet started | Cable drum not available | #N/A
T-00607-0002 | PS2-61-IE-0001-CD01 | TPX10a - Multicore electrical control cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IE-0001 | KENT |  | PS2-61-05 - Electrical Control System |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00607-0003 | PS2-61-IE-0001-CD02 | TPX10a - Multicore electrical control cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IE-0001 | KENT |  | PS2-61-05 - Electrical Control System |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00607-0004 | PS2-61-IE-0001-CD03 | TPX10a - Multicore electrical control cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IE-0001 | KENT |  | PS2-61-05 - Electrical Control System |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00607-0005 | PS2-61-IE-0001-CD04 | TPX10a - Multicore electrical control cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IE-0001 | KENT |  | PS2-61-05 - Electrical Control System |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00607-0006 | PS2-61-IE-0001-CD05 | TPX10a - Multicore electrical control cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IE-0001 | KENT |  | PS2-61-05 - Electrical Control System |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00607-0007 | PS2-61-IE-0001-CD06 | TPX10a - Multicore electrical control cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IE-0001 | KENT |  | PS2-61-05 - Electrical Control System |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00607-0008 | PS2-61-IJ-0001-CD01 | TPX10a - Multicore electrical control cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-ISR-0101 TO PS2-61-IJ-0001 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00607-0009 | PS2-61-IJ-0001-CD02 | TPX10a - Multicore electrical control cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001A TO PS2-61-IJ-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0086
T-00607-0010 | PS2-61-IJ-0001-CD03 | TPX10a - Multicore electrical control cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IV-0001B TO PS2-61-IJ-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0083
T-00607-0011 | PS2-61-IJ-0001-CD04 | TPX10a - Multicore electrical control cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IJ-0001 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00607-0012 | PS2-61-IJ-0001-CD05 | TPX10a - Multicore electrical control cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IJ-0001 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00607-0013 | PS2-61-IJ-0001-CD06 | TPX10a - Multicore electrical control cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0010 TO PS2-61-IJ-0001 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00607-0014 | PS2-61-IJ-0001-CD07 | TPX10a - Multicore electrical control cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IJ-0001 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00607-0015 | PS2-61-IJ-0001-CD08 | TPX10a - Multicore electrical control cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IJ-0001 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00607-0016 | PS2-61-IJ-0001-CD09 | TPX10a - Multicore electrical control cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IU-0011 TO PS2-61-IJ-0001 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0215
T-00607-0017 | PS2-61-IJ-0001-CD10 | TPX10a - Multicore electrical control cable (both end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-63-IV-0010 TO PS2-61-IJ-0001 | KENT |  | PS2-61-01 - 33kV Switchboard EITS Building (PS2-61-IJ-0001) |  |  |  | Construction not yet started |  | #N/A
T-00608-0034 | PS2-03-GDLHP-0105-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-03-GDLHP-0105 | CPP AGI |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | CPP-RFI-65-33/1-07-0205
T-00608-0035 | PS2-03-GDLHP-0106-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-03-GDLHP-0106 | CPP AGI |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | CPP-RFI-65-33/1-07-0204
T-00608-0036 | PS2-03-GDLHP-0107-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-03-GDLHP-0107 | CPP AGI |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | CPP-RFI-65-33/1-05-0119
T-00608-0037 | PS2-03-GDLHP-0109-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-03-GDLHP-0109 | CPP AGI |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | CPP-RFI-65-33/1-05-0071
T-00608-0038 | PS2-03-GDLHP-0111-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-03-GDLHP-0111 | CPP AGI |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | CPP-RFI-65-33/1-07-0205
T-00608-0039 | PS2-05-IG-0002-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-05-IG-0002 | CPP AGI |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00608-0040 | PS2-05-IG-0004-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-05-IG-0004 | CPP AGI |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00608-0041 | PS2-05-IG-0006-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-05-IG-0006 | CPP AGI |  | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00608-0042 | PS2-05-IG-0007-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-05-IG-0007 | CPP AGI |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00608-0043 | PS2-05-IG-0009-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-05-IG-0009 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | CPP-RFI-65-33/1-06-0181
T-00608-0044 | PS2-05-IG-0009-CL02 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-05-IG-0009 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | CPP-RFI-65-33/1-06-0181
T-00608-0045 | PS2-25-DM-3200A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-3200A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00608-0046 | PS2-25-DM-3200B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-3200B | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00608-0047 | PS2-25-DM-3300A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-3300A | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00608-0048 | PS2-25-DM-3300B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-3300B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0063
T-00608-0049 | PS2-25-DM-3400A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-3400A | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00608-0050 | PS2-25-DM-3400B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-3400B | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00608-0051 | PS2-25-DM-6400A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-6400A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00608-0052 | PS2-25-DM-6400B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-6400B | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00608-0053 | PS2-25-DM-6500A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-6500A | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00608-0054 | PS2-25-DM-6500B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-6500B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00608-0055 | PS2-25-DM-6600A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-6600A | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00608-0056 | PS2-25-DM-6600B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-6600B | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00608-0057 | PS2-25-FIT-0001-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-25-FIT-0001 | CPP AGI |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00608-0058 | PS2-25-FIT-0003A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-25-FIT-0003A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0080
T-00608-0059 | PS2-25-FIT-0003B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-25-FIT-0003B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0080
T-00608-0060 | PS2-25-FIT-0003C-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-25-FIT-0003C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0080
T-00608-0061 | PS2-25-FIT-0004-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-25-FIT-0004 | CPP AGI |  | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00608-0062 | PS2-25-HE-2100-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-HE-2100 | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00608-0063 | PS2-25-HE-2200-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-HE-2200 | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00608-0064 | PS2-25-HE-2300-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-HE-2300 | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00608-0065 | PS2-25-UD-3100A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-UD-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0080
T-00608-0066 | PS2-28-BE-0001-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-BE-0001 | CPP AGI |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | CPP-RFI-65-33/1-05-0119
T-00608-0067 | PS2-28-DM-3100-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-DM-3100 | CPP AGI |  | PS2-28-03 - Closed Drain Drum & Pump |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 30TH JULY 2026 | CPP-RFI-65-33/1-05-0119
T-00608-0068 | PS2-28-DM-3800A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-DM-3800A | CPP AGI |  | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00608-0069 | PS2-28-DM-3800B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-DM-3800B | CPP AGI |  | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00608-0070 | PS2-28-DM-3800C-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-DM-3800C | CPP AGI |  | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00608-0071 | PS2-28-DM-3900-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-DM-3900 | CPP AGI |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | CPP-RFI-65-33/1-05-0119
T-00608-0072 | PS2-28-HE-2100-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-HE-2100 | CPP AGI |  | PS2-28-03 - Closed Drain Drum & Pump |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 30TH JULY 2026 | CPP-RFI-65-33/1-05-0119
T-00608-0073 | PS2-53-DM-3100-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-53-DM-3100 | CPP AGI |  | PS2-53-02 - Water Distribution Pump |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0104
T-00608-0074 | PS2-53-IN-0001-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-53-IN-0001 | CPP AGI |  | PS2-53-03 - Water Treatment Purification Package |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0104
T-00608-0075 | PS2-61-IDH-3100A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0001A TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00608-0076 | PS2-61-IDH-3100B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0001B TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00608-0077 | PS2-61-IDH-3100C-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0001B TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00608-0078 | PS2-61-IG-0002-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IG-0002 | CPP AGI |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00608-0079 | PS2-61-IG-0005-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IG-0005 | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00608-0080 | PS2-61-IG-0007-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IG-0007 | CPP AGI |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00608-0081 | PS2-61-IG-0012A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IG-0012A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00608-0082 | PS2-61-IG-0012B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IG-0012B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00608-0083 | PS2-61-IG-0012C-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IG-0012C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00608-0084 | PS2-61-IG-0014-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IG-0014 | CPP AGI |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00608-0085 | PS2-61-IG-0015-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IG-0015 | CPP AGI |  | PS2-61-07 - Outdoor Valves Distribution Board - PS2-61-IG-0015 |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | #N/A
T-00608-0086 | PS2-61-IK-0001-CL37 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | ITR started-waiting for cable G&T RFI | Construction Completed , Pre Com work pending | 2026-06-29 | CPP-RFI-65-33/1-06-0181
T-00608-0087 | PS2-61-IK-0001-CL38 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | ITR started-waiting for cable G&T RFI | Construction Completed , Pre Com work pending | 2026-06-29 | CPP-RFI-65-33/1-06-0181
T-00608-0088 | PS2-61-IK-0001-CL39 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | ITR started-waiting for cable G&T RFI | Construction Completed , Pre Com work pending | 2026-06-29 | CPP-RFI-65-33/1-06-0181
T-00608-0089 | PS2-61-IK-0001-CL40 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | ITR started-waiting for cable G&T RFI | Construction Completed , Pre Com work pending | 2026-06-29 | CPP-RFI-65-33/1-06-0181
T-00608-0090 | PS2-61-IK-0001-CL41 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | ITR started-waiting for cable G&T RFI | Construction Completed , Pre Com work pending | 2026-06-29 | CPP-RFI-65-33/1-06-0181
T-00608-0091 | PS2-61-IK-0001-CL42 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | ITR started-waiting for cable G&T RFI | Construction Completed , Pre Com work pending | 2026-06-29 | CPP-RFI-65-33/1-06-0181
T-00608-0092 | PS2-61-IK-0001-CL43 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | ITR started-waiting for cable G&T RFI | Construction Completed , Pre Com work pending | 2026-06-29 | CPP-RFI-65-33/1-06-0181
T-00608-0093 | PS2-61-IV-0006A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IV-0006A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00608-0094 | PS2-61-IV-0006B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IV-0006B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00608-0095 | PS2-61-IV-0006C-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IV-0006C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00608-0096 | PS2-75-DM-3100A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-75-DM-3100A | CPP AGI |  | PS2-75-02 - Biocide Injection Package |  | 260m cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00608-0097 | PS2-75-DM-3100B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-75-DM-3100B | CPP AGI |  | PS2-75-02 - Biocide Injection Package |  | 336m cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00608-0098 | PS2-75-ISO-0001-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-75-ISO-0001 | CPP AGI |  | PS2-75-01 - DRA Injection Package |  | 230m cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0071
T-00608-0099 | PS2-75-ISO-0002-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-75-ISO-0002 | CPP AGI |  | PS2-75-01 - DRA Injection Package |  | 230m cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0071
T-00608-0100 | PS2-79-IV-0001-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-79-IV-0001 | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00608-0101 | PS2-79-IV-0002-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-79-IV-0002 | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00608-0102 | PS2-79-IV-0003-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-79-IV-0003 | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00608-0103 | PS2-79-IV-0004-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-79-IV-0004 | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00608-0104 | PS2-79-IV-0005-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-79-IV-0005 | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00608-0937 | PS2-53-IN-0001-CL02 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0001A TO PS2-53-IN-0001 | CPP AGI |  | PS2-53-03 - Water Treatment Purification Package |  |  |  | Construction not yet started |  | #N/A
T-00608-0938 | PS2-53-IN-0001-CL03 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0001B TO PS2-53-IN-0001 | CPP AGI |  | PS2-53-03 - Water Treatment Purification Package |  |  |  | Construction not yet started |  | #N/A
T-00608-0963 | PS2-61-IK-0001-CG03 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | ITR started-waiting for cable G&T RFI | Construction Completed , Pre Com work pending | 2026-06-29 | CPP-RFI-65-33/1-06-0181
T-00608-0964 | PS2-61-IK-0001-CG04 | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | CPP AGI |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  | Cable intallation and testing completed | ITR started-waiting for cable G&T RFI | Construction Completed , Pre Com work pending | 2026-06-29 | CPP-RFI-65-33/1-06-0181
T-00609-0034 | PS2-03-GDLHP-0105-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-03-GDLHP-0105 | KENT |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00609-0035 | PS2-03-GDLHP-0106-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-03-GDLHP-0106 | KENT |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00609-0036 | PS2-03-GDLHP-0107-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-03-GDLHP-0107 | KENT |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00609-0037 | PS2-03-GDLHP-0109-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-03-GDLHP-0109 | KENT |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0071
T-00609-0038 | PS2-03-GDLHP-0111-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-03-GDLHP-0111 | KENT |  | PS2-03-01 - FZ-01 - Process Area |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00609-0039 | PS2-05-IG-0002-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-05-IG-0002 | KENT |  | PS2-62-10 - Office Building Emergency L&SP DB - PS2-05-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00609-0040 | PS2-05-IG-0004-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-05-IG-0004 | KENT |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00609-0041 | PS2-05-IG-0006-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-05-IG-0006 | KENT |  | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00609-0042 | PS2-05-IG-0007-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-05-IG-0007 | KENT |  | PS2-62-05 - Guard House Emergency L&SP DB - PS2-05-IG-0007 |  |  |  | Construction not yet started |  | #N/A
T-00609-0043 | PS2-05-IG-0009-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-05-IG-0009 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-06-0181
T-00609-0044 | PS2-05-IG-0009-CL02 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-05-IG-0009 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-06-0181
T-00609-0045 | PS2-25-DM-3200A-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-3200A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00609-0046 | PS2-25-DM-3200B-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-3200B | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00609-0047 | PS2-25-DM-3300A-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-3300A | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00609-0048 | PS2-25-DM-3300B-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-3300B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0063
T-00609-0049 | PS2-25-DM-3400A-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-3400A | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00609-0050 | PS2-25-DM-3400B-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-3400B | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00609-0051 | PS2-25-DM-6400A-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-6400A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00609-0052 | PS2-25-DM-6400B-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-6400B | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00609-0053 | PS2-25-DM-6500A-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-6500A | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00609-0054 | PS2-25-DM-6500B-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-6500B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00609-0055 | PS2-25-DM-6600A-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-6600A | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00609-0056 | PS2-25-DM-6600B-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-DM-6600B | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00609-0057 | PS2-25-FIT-0001-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-25-FIT-0001 | KENT |  | PS2-25-01 - Export Pipeline Pig Receiver |  |  |  | Construction not yet started |  | #N/A
T-00609-0058 | PS2-25-FIT-0003A-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-25-FIT-0003A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0080
T-00609-0059 | PS2-25-FIT-0003B-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-25-FIT-0003B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0080
T-00609-0060 | PS2-25-FIT-0003C-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-25-FIT-0003C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0080
T-00609-0061 | PS2-25-FIT-0004-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0002 TO PS2-25-FIT-0004 | KENT |  | PS2-25-06 - Crude Oil Export Pumps Discharge |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00609-0062 | PS2-25-HE-2100-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-HE-2100 | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00609-0063 | PS2-25-HE-2200-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-HE-2200 | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00609-0064 | PS2-25-HE-2300-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-HE-2300 | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00609-0065 | PS2-25-UD-3100A-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-UD-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0080
T-00609-0066 | PS2-28-BE-0001-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-BE-0001 | KENT |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00609-0067 | PS2-28-DM-3100-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-DM-3100 | KENT |  | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00609-0068 | PS2-28-DM-3800A-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-DM-3800A | KENT |  | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00609-0069 | PS2-28-DM-3800B-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-DM-3800B | KENT |  | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00609-0070 | PS2-28-DM-3800C-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-DM-3800C | KENT |  | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00609-0071 | PS2-28-DM-3900-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-DM-3900 | KENT |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00609-0072 | PS2-28-HE-2100-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-HE-2100 | KENT |  | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00609-0073 | PS2-53-DM-3100-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-53-DM-3100 | KENT |  | PS2-53-02 - Water Distribution Pump |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0104
T-00609-0074 | PS2-53-IN-0001-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-53-IN-0001 | KENT |  | PS2-53-03 - Water Treatment Purification Package |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0104
T-00609-0075 | PS2-61-IDH-3100A-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0001A TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00609-0076 | PS2-61-IDH-3100B-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0001B TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00609-0077 | PS2-61-IDH-3100C-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0001B TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00609-0078 | PS2-61-IG-0002-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IG-0002 | KENT |  | PS2-62-11 - Office Building Normal L&SP DB - PS2-61-IG-0002 |  |  |  | Construction not yet started |  | #N/A
T-00609-0079 | PS2-61-IG-0005-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IG-0005 | KENT |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00609-0080 | PS2-61-IG-0007-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IG-0007 | KENT |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00609-0081 | PS2-61-IG-0012A-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IG-0012A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00609-0082 | PS2-61-IG-0012B-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IG-0012B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00609-0083 | PS2-61-IG-0012C-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IG-0012C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00609-0084 | PS2-61-IG-0014-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IG-0014 | KENT |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00609-0085 | PS2-61-IG-0015-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IG-0015 | KENT |  | PS2-61-07 - Outdoor Valves Distribution Board - PS2-61-IG-0015 |  |  |  | Construction not yet started |  | #N/A
T-00609-0086 | PS2-61-IK-0001-CL37 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-06-0181
T-00609-0087 | PS2-61-IK-0001-CL38 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-06-0181
T-00609-0088 | PS2-61-IK-0001-CL39 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-06-0181
T-00609-0089 | PS2-61-IK-0001-CL40 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-06-0181
T-00609-0090 | PS2-61-IK-0001-CL41 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-06-0181
T-00609-0091 | PS2-61-IK-0001-CL42 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-06-0181
T-00609-0092 | PS2-61-IK-0001-CL43 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-06-0181
T-00609-0093 | PS2-61-IV-0006A-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IV-0006A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00609-0094 | PS2-61-IV-0006B-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IV-0006B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00609-0095 | PS2-61-IV-0006C-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-61-IV-0006C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00609-0096 | PS2-75-DM-3100A-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-75-DM-3100A | KENT |  | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00609-0097 | PS2-75-DM-3100B-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-75-DM-3100B | KENT |  | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00609-0098 | PS2-75-ISO-0001-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-75-ISO-0001 | KENT |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0071
T-00609-0099 | PS2-75-ISO-0002-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-75-ISO-0002 | KENT |  | PS2-75-01 - DRA Injection Package |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0071
T-00609-0100 | PS2-79-IV-0001-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-79-IV-0001 | KENT |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00609-0101 | PS2-79-IV-0002-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-79-IV-0002 | KENT |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00609-0102 | PS2-79-IV-0003-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-79-IV-0003 | KENT |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00609-0103 | PS2-79-IV-0004-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-79-IV-0004 | KENT |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  |  |  | Construction not yet started |  | #N/A
T-00609-0104 | PS2-79-IV-0005-CL01 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-79-IV-0005 | KENT |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  |  |  | Construction not yet started |  | #N/A
T-00609-0937 | PS2-53-IN-0001-CL02 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0001A TO PS2-53-IN-0001 | KENT |  | PS2-53-03 - Water Treatment Purification Package |  |  |  | Construction not yet started |  | #N/A
T-00609-0938 | PS2-53-IN-0001-CL03 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-06-IG-0001B TO PS2-53-IN-0001 | KENT |  | PS2-53-03 - Water Treatment Purification Package |  |  |  | Construction not yet started |  | #N/A
T-00609-0963 | PS2-61-IK-0001-CG03 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-06-0181
T-00609-0964 | PS2-61-IK-0001-CG04 | TPX09b - LV power cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-05-DG-8100 TO PS2-61-IK-0001 | KENT |  | PS2-61-04 - 0.4kV Switchboard EITS Building (PS2-61-IK-0001) |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-06-0181
T-00610-0006 | PS2-05-IG-0004-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0002 TO PS2-05-IG-0004 | CPP AGI |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00610-0007 | PS2-05-IG-0006-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0002 TO PS2-05-IG-0006 | CPP AGI |  | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00610-0008 | PS2-25-HE-2100-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-HE-2100 | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00610-0009 | PS2-25-HE-2200-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-HE-2200 | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00610-0010 | PS2-25-HE-2300-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-HE-2300 | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00610-0011 | PS2-25-IES-3200A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-3200A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00610-0012 | PS2-25-IES-3200B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-3200B | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00610-0013 | PS2-25-IES-3300A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-3300A | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00610-0014 | PS2-25-IES-3300B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-3300B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00610-0015 | PS2-25-IES-3400A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-3400A | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00610-0016 | PS2-25-IES-3400B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-3400B | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00610-0017 | PS2-25-IES-6400A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-6400A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00610-0018 | PS2-25-IES-6400B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-6400B | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00610-0019 | PS2-25-IES-6500A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-6500A | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00610-0020 | PS2-25-IES-6500B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-6500B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00610-0021 | PS2-25-IES-6600A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-6600A | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00610-0022 | PS2-25-IES-6600B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-6600B | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00610-0023 | PS2-28-HE-2100-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-HE-2100 | CPP AGI |  | PS2-28-03 - Closed Drain Drum & Pump |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 30TH JULY 2026 | CPP-RFI-65-33/1-05-0119
T-00610-0024 | PS2-28-IES-3100-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-IES-3100 | CPP AGI |  | PS2-28-03 - Closed Drain Drum & Pump |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 30TH JULY 2026 | CPP-RFI-65-33/1-05-0119
T-00610-0025 | PS2-28-IES-3800A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-IES-3800A | CPP AGI |  | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00610-0026 | PS2-28-IES-3800B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-IES-3800B | CPP AGI |  | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00610-0027 | PS2-28-IES-3800C-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-IES-3800C | CPP AGI |  | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00610-0028 | PS2-28-IES-3900-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-IES-3900 | CPP AGI |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started | ETA- 15th JULY 2026 | CPP-RFI-65-33/1-05-0119
T-00610-0029 | PS2-53-IES-3100-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-53-IES-3100 | CPP AGI |  | PS2-53-02 - Water Distribution Pump |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0104
T-00610-0030 | PS2-61-IDH-3100A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00610-0031 | PS2-61-IDH-3100A-CD02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00610-0032 | PS2-61-IDH-3100A-CD04 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0001 TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00610-0033 | PS2-61-IDH-3100B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00610-0034 | PS2-61-IDH-3100B-CD02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00610-0035 | PS2-61-IDH-3100B-CD04 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0001 TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00610-0036 | PS2-61-IDH-3100C-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00610-0037 | PS2-61-IDH-3100C-CD02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00610-0038 | PS2-61-IDH-3100C-CD04 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0001 TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00610-0039 | PS2-61-IG-0005-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0002 TO PS2-61-IG-0005 | CPP AGI |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00610-0040 | PS2-61-IG-0007-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0002 TO PS2-61-IG-0007 | CPP AGI |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00610-0041 | PS2-61-IG-0014-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0002 TO PS2-61-IG-0014 | CPP AGI |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00610-0042 | PS2-61-IG-0015-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0002 TO PS2-61-IG-0015 | CPP AGI |  | PS2-61-07 - Outdoor Valves Distribution Board - PS2-61-IG-0015 |  | 144m cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started | ETA- 15th JULY 2026 | CPP-RFI-65-33/1-05-0064
T-00610-0043 | PS2-62-IE-0001-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-62-IE-0001 | CPP AGI |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0080
T-00610-0044 | PS2-75-IES-3100A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-75-IES-3100A | CPP AGI |  | PS2-75-02 - Biocide Injection Package |  | 280m cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00610-0045 | PS2-75-IES-3100B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-75-IES-3100B | CPP AGI |  | PS2-75-02 - Biocide Injection Package |  | 280m cable pulled, glanding & termination, earthing, to be completed |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00611-0006 | PS2-05-IG-0004-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0002 TO PS2-05-IG-0004 | KENT |  | PS2-62-03 - Outdoor Emergency Lighting DB - PS2-05-IG-0004 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00611-0007 | PS2-05-IG-0006-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0002 TO PS2-05-IG-0006 | KENT |  | PS2-62-04 - Outdoor Emergency Lighting DB - PS2-05-IG-0006 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00611-0008 | PS2-25-HE-2100-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-HE-2100 | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00611-0009 | PS2-25-HE-2200-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-HE-2200 | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00611-0010 | PS2-25-HE-2300-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-HE-2300 | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00611-0011 | PS2-25-IES-3200A-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-3200A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00611-0012 | PS2-25-IES-3200B-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-3200B | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00611-0013 | PS2-25-IES-3300A-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-3300A | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00611-0014 | PS2-25-IES-3300B-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-3300B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00611-0015 | PS2-25-IES-3400A-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-3400A | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00611-0016 | PS2-25-IES-3400B-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-3400B | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00611-0017 | PS2-25-IES-6400A-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-6400A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00611-0018 | PS2-25-IES-6400B-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-6400B | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00611-0019 | PS2-25-IES-6500A-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-6500A | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00611-0020 | PS2-25-IES-6500B-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-6500B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00611-0021 | PS2-25-IES-6600A-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-6600A | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00611-0022 | PS2-25-IES-6600B-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-25-IES-6600B | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00611-0023 | PS2-28-HE-2100-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-HE-2100 | KENT |  | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00611-0024 | PS2-28-IES-3100-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-IES-3100 | KENT |  | PS2-28-03 - Closed Drain Drum & Pump |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00611-0025 | PS2-28-IES-3800A-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-IES-3800A | KENT |  | PS2-28-05 - Seal Oil Drain Drum & Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0203
T-00611-0026 | PS2-28-IES-3800B-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-IES-3800B | KENT |  | PS2-28-06 - Seal Oil Drain Drum & Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0204
T-00611-0027 | PS2-28-IES-3800C-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-IES-3800C | KENT |  | PS2-28-07 - Seal Oil Drain Drum & Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-07-0205
T-00611-0028 | PS2-28-IES-3900-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-28-IES-3900 | KENT |  | PS2-28-04 - Reinjection Pump |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00611-0029 | PS2-53-IES-3100-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-53-IES-3100 | KENT |  | PS2-53-02 - Water Distribution Pump |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0104
T-00611-0030 | PS2-61-IDH-3100A-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00611-0031 | PS2-61-IDH-3100A-CD02 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00611-0032 | PS2-61-IDH-3100A-CD04 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0001 TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00611-0033 | PS2-61-IDH-3100B-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00611-0034 | PS2-61-IDH-3100B-CD02 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00611-0035 | PS2-61-IDH-3100B-CD04 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0001 TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00611-0036 | PS2-61-IDH-3100C-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00611-0037 | PS2-61-IDH-3100C-CD02 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IJ-0001 TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00611-0038 | PS2-61-IDH-3100C-CD04 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0001 TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-08-0100
T-00611-0039 | PS2-61-IG-0005-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0002 TO PS2-61-IG-0005 | KENT |  | PS2-62-06 - Outdoor Normal Lighting DB - PS2-61-IG-0005 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00611-0040 | PS2-61-IG-0007-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0002 TO PS2-61-IG-0007 | KENT |  | PS2-62-07 - Outdoor Normal Lighting DB - PS2-61-IG-0007 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00611-0041 | PS2-61-IG-0014-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0002 TO PS2-61-IG-0014 | KENT |  | PS2-61-06 - Outdoor Power Distribution Board - PS2-61-IG-0014 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00611-0042 | PS2-61-IG-0015-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IE-0002 TO PS2-61-IG-0015 | KENT |  | PS2-61-07 - Outdoor Valves Distribution Board - PS2-61-IG-0015 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0064
T-00611-0043 | PS2-62-IE-0001-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-08-15CB-1001 TO PS2-62-IE-0001 | KENT |  | PS2-62-01 - Lighting Control Panel - PS2-62-IE-0001 |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0080
T-00611-0044 | PS2-75-IES-3100A-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-75-IES-3100A | KENT |  | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00611-0045 | PS2-75-IES-3100B-CD01 | TPX10b - Multicore electrical control cable (One end by HU CTR) | PCOM - Precommissioning | E - Electrical | Cable FROM PS2-61-IK-0001 TO PS2-75-IES-3100B | KENT |  | PS2-75-02 - Biocide Injection Package |  |  |  | Construction not yet started |  | CPP-RFI-65-33/1-05-0119
T-00614-0004 | PS2-03-BI-1501-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0005 TO PS2-03-BI-1501 | CPP AGI |  | PS2-03-01 - FZ-01 - Process Area |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started | ETA- 10TH AUGUST 2026 | CPP-RFI-65-33/1-05-0072
T-00614-0005 | PS2-03-BI-1502-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0005 TO PS2-03-BI-1502 | CPP AGI |  | PS2-03-01 - FZ-01 - Process Area |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started | ETA- 10TH AUGUST 2026 | CPP-RFI-65-33/1-05-0072
T-00614-0006 | PS2-03-BI-1503-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0005 TO PS2-03-BI-1503 | CPP AGI |  | PS2-03-01 - FZ-01 - Process Area |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started | ETA- 10TH AUGUST 2026 | CPP-RFI-65-33/1-05-0073
T-00614-0007 | PS2-03-BI-2501-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-BI-2501 | CPP AGI |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started | ETA- 20TH JULY 2026 | #N/A
T-00614-0008 | PS2-03-BI-2502-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-BI-2502 | CPP AGI |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started | ETA- 20TH JULY 2026 | CPP-RFI-65-33/1-05-0090
T-00614-0009 | PS2-03-BI-2503-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-BI-2503 | CPP AGI |  | PS2-03-01 - FZ-01 - Process Area |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started | ETA- 10TH AUGUST 2026 | CPP-RFI-65-16-04-0096
T-00614-0010 | PS2-03-BI-2504-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-BI-2504 | CPP AGI |  | PS2-03-01 - FZ-01 - Process Area |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started | ETA- 10TH AUGUST 2026 | CPP-RFI-65-33/1-05-0072
T-00614-0217 | PS2-03-BI-1504-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0005 TO PS2-03-BI-1504 | CPP AGI |  | PS2-03-01 - FZ-01 - Process Area |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started | ETA- 10TH AUGUST 2026 | CPP-RFI-65-33/1-05-0072
T-00614-0218 | PS2-03-BI-2505-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-BI-2505 | CPP AGI |  | PS2-03-01 - FZ-01 - Process Area |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started | ETA- 10TH AUGUST 2026 | CPP-RFI-65-33/1-05-0072
T-00614-0219 | PS2-03-HS-7002-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0002 TO PS2-03-HS-7002 | CPP AGI |  | PS2-03-03 - FZ-03 - Buildings Area |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | CPP-RFI-65-16-04-0206
T-00614-0220 | PS2-03-MTX-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0002 TO PS2-03-MTX-0001 | CPP AGI |  | PS2-04-02 - Office Building SIS/FGS System |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 15th August 2026
T-00614-0221 | PS2-03-MTX-0001-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0002 TO PS2-03-MTX-0001 | CPP AGI |  | PS2-04-02 - Office Building SIS/FGS System |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 15th August 2026
T-00614-0222 | PS2-03-MTX-0001-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0002 TO PS2-03-MTX-0001 | CPP AGI |  | PS2-04-02 - Office Building SIS/FGS System |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 15th August 2026
T-00614-0223 | PS2-03-MTX-0001-CC04 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0004 TO PS2-03-MTX-0001 | CPP AGI |  | PS2-04-02 - Office Building SIS/FGS System |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 15th August 2026
T-00614-0224 | PS2-03-MTX-0001-CC05 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-MTX-0001 | CPP AGI |  | PS2-04-02 - Office Building SIS/FGS System |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 15th August 2026
T-00614-0225 | PS2-03-MTX-0001-CC06 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0007 TO PS2-03-MTX-0001 | CPP AGI |  | PS2-04-02 - Office Building SIS/FGS System |  | CIVIL WORK NOT COMPLETED |  | Construction not yet started | ETA- 15th August 2026
T-00614-0226 | PS2-03-RMAC-0301-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-RMAC-0301 | CPP AGI |  | PS2-03-03 - FZ-03 - Buildings Area |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #NAME?
T-00614-0227 | PS2-03-SEA-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-03-04 - FZ-04 - Emergency Diesel Generator Enclosure |  | Cable laying, glanding & termination completed, |  | Construction not yet started | ETA- 5TH JULY 2026
T-00614-0228 | PS2-03-SEA-0002-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-SEA-0002 | CPP AGI |  | PS2-03-05 - FZ-G1 - Guard House |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #NAME?
T-00614-0229 | PS2-03-SEA-0002-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-03-SEA-0002 | CPP AGI |  | PS2-03-05 - FZ-G1 - Guard House |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #NAME?
T-00614-0230 | PS2-03-SEA-0003-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-SEA-0003 | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00614-0231 | PS2-03-SEA-0003-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-03-SEA-0003 | CPP AGI |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started | ETA- 10TH AUGUST 2026 | #NAME?
T-00614-0232 | PS2-03-SEA-0005-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-SEA-0005 | CPP AGI |  | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #NAME?
T-00614-0233 | PS2-03-SEA-0005-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-03-SEA-0005 | CPP AGI |  | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started | ETA- 5TH AUGUST 2026 | #NAME?
T-00614-0234 | PS2-05-BI-0002-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | #NAME?
T-00614-0235 | PS2-05-BI-0002-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | #NAME?
T-00614-0236 | PS2-05-BI-0002-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | #NAME?
T-00614-0237 | PS2-05-BI-0002-CC04 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | #NAME?
T-00614-0238 | PS2-05-BI-0002-CC05 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | #NAME?
T-00614-0239 | PS2-05-BI-0002-CC06 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | #NAME?
T-00614-0240 | PS2-05-BI-0002-CC11 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-05-BI-0002 | CPP AGI |  | PS2-03-04 - FZ-04 - Emergency Diesel Generator Enclosure |  | Cable laying, glanding & termination completed, |  | Construction not yet started | ETA- 5TH JULY 2026 | #NAME?
T-00614-0241 | PS2-05-BI-0002-CC12 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0007 TO PS2-05-BI-0002 | CPP AGI |  | PS2-03-04 - FZ-04 - Emergency Diesel Generator Enclosure |  | Cable laying, glanding & termination completed, |  | Construction not yet started | ETA- 5TH JULY 2026 | #NAME?
T-00614-0242 | PS2-05-BI-0002-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | #NAME?
T-00614-0243 | PS2-05-BI-0002-CJ02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | #NAME?
T-00614-0244 | PS2-05-BI-0002-CJ03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | #NAME?
T-00614-0245 | PS2-05-GC-8100-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | #NAME?
T-00614-0246 | PS2-05-IE-8101-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | #NAME?
T-00614-0247 | PS2-05-IG-0009-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | #NAME?
T-00614-0248 | PS2-05-IG-0009-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | #NAME?
T-00614-0249 | PS2-05-IG-0009-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | #NAME?
T-00614-0250 | PS2-05-LIT-4101-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | #NAME?
T-00614-0251 | PS2-05-UH-8100-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | #NAME?
T-00614-0252 | PS2-05-UH-8100-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | CPP AGI |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, glanding & termination completed, |  | Construction not yet started | Final RFI for G&T awaiting | #NAME?
T-00614-0253 | PS2-09-BI-2501-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0007 TO PS2-09-BI-2501 | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #NAME?
T-00614-0254 | PS2-09-BI-2502-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0007 TO PS2-09-BI-2502 | CPP AGI |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #NAME?
T-00614-0255 | PS2-09-LB-0006-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-09-LB-0006 | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #NAME?
T-00614-0256 | PS2-09-LB-0006-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-09-LB-0006 | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #NAME?
T-00614-0257 | PS2-09-LB-0006-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0007 TO PS2-09-LB-0006 | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #NAME?
T-00614-0258 | PS2-09-LB-0006-CC04 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-09-LB-0006 | CPP AGI |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | #NAME?
T-00614-0259 | PS2-09-LB-0008-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-09-LB-0008 | CPP AGI |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #NAME?
T-00614-0260 | PS2-09-LB-0008-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-09-LB-0008 | CPP AGI |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #NAME?
T-00614-0261 | PS2-09-LB-0008-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0007 TO PS2-09-LB-0008 | CPP AGI |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #NAME?
T-00614-0262 | PS2-09-LB-0008-CC04 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0004 TO PS2-09-LB-0008 | CPP AGI |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #NAME?
T-00614-0263 | PS2-25-BI-1101-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-25-BI-1101 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  |  |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0264 | PS2-25-BI-1102-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-25-BI-1102 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0265 | PS2-25-BI-1106-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-25-BI-1106 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0266 | PS2-25-BI-1107-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-25-BI-1107 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0267 | PS2-25-BI-1108-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-25-BI-1108 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0268 | PS2-25-BI-1201-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-25-BI-1201 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0269 | PS2-25-BI-1301-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-25-BI-1301 | CPP AGI |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0270 | PS2-25-BI-1302-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-25-BI-1302 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0271 | PS2-25-BI-1305-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-25-BI-1305 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0272 | PS2-25-BI-1801B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1801B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0273 | PS2-25-BI-1801C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1801C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0274 | PS2-25-BI-1802B-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1802B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0275 | PS2-25-BI-1802C-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1802C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0276 | PS2-25-BI-1803A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1803A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0277 | PS2-25-BI-1803A-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1803A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0278 | PS2-25-BI-1803B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1803B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0279 | PS2-25-BI-1803B-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1803B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0280 | PS2-25-BI-1803C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1803C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0281 | PS2-25-BI-1803C-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1803C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0282 | PS2-25-BI-2101-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-25-BI-2101 | CPP AGI |  | PS2-25-01 - Export Pipeline Pig Receiver |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0283 | PS2-25-BI-2102-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0004 TO PS2-25-BI-2102 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0284 | PS2-25-BI-2103-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0004 TO PS2-25-BI-2103 | CPP AGI |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0285 | PS2-25-BI-2104-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-25-BI-2104 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0286 | PS2-25-BI-2105-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-25-BI-2105 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0287 | PS2-25-BI-2106-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-25-BI-2106 | CPP AGI |  | PS2-25-05 - Crude Oil Export Pumps Bypass |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0288 | PS2-25-BI-2107-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-25-BI-2107 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0289 | PS2-25-BI-2108-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-25-BI-2108 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0290 | PS2-25-BI-2109-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-25-BI-2109 | CPP AGI |  | PS2-25-05 - Crude Oil Export Pumps Bypass |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0291 | PS2-25-BI-2201-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0002 TO PS2-25-BI-2201 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0292 | PS2-25-BI-2202-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0002 TO PS2-25-BI-2202 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0293 | PS2-25-BI-2203-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0002 TO PS2-25-BI-2203 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0294 | PS2-25-BI-2301-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0003 TO PS2-25-BI-2301 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0295 | PS2-25-BI-2303-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0004 TO PS2-25-BI-2303 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0296 | PS2-25-BI-2304-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0004 TO PS2-25-BI-2304 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0297 | PS2-25-BI-2305-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0004 TO PS2-25-BI-2305 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0298 | PS2-25-BI-2306-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0003 TO PS2-25-BI-2306 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0299 | PS2-25-BI-2307-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0003 TO PS2-25-BI-2307 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0300 | PS2-25-BI-2308-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0003 TO PS2-25-BI-2308 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0301 | PS2-25-BI-2315-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0003 TO PS2-25-BI-2315 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0302 | PS2-25-MXS-3101AB-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0303 | PS2-25-MXS-3101BB-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0304 | PS2-25-MXS-3101CB-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0305 | PS2-25-PIT-0052-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-25-SDV-0052 | CPP AGI |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0306 | PS2-25-PIT-0071A-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-25-PIT-0071A | CPP AGI |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0307 | PS2-25-PIT-0071B-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-25-PIT-0071B | CPP AGI |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0308 | PS2-25-PIT-0071C-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-25-PIT-0071C | CPP AGI |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0309 | PS2-25-SDV-0052-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-25-SDV-0052 | CPP AGI |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0310 | PS2-25-SDV-0052-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-25-SDV-0052 IDC24 | CPP AGI |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0311 | PS2-25-SHSR-0052-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0003 TO PS2-25-SDV-0052 | CPP AGI |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0312 | PS2-25-SXS-0052-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-25-SDV-0052 | CPP AGI |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0313 | PS2-25-SY-0052A-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-25-SDV-0052 | CPP AGI |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0314 | PS2-28-BI-1103-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-28-BI-1103 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0315 | PS2-28-BI-1303-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-28-BI-1303 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0316 | PS2-28-HXA-1101-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-28-HXA-1101 | CPP AGI |  | PS2-28-03 - Closed Drain Drum & Pump |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 30TH JULY 2026 | #NAME?
T-00614-0317 | PS2-28-LB-8200-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-28-LB-8200 | CPP AGI |  | PS2-28-09 - Open Drain Interceptor |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started | ETA- 15th JULY 2026 | #NAME?
T-00614-0318 | PS2-28-LB-8200-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-28-LB-8200 | CPP AGI |  | PS2-28-09 - Open Drain Interceptor |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started | ETA- 15th JULY 2026 | #NAME?
T-00614-0319 | PS2-53-BI-1105-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0002 TO PS2-53-BI-1105 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-0320 | PS2-53-LA-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-53-LA-0001 | CPP AGI |  | PS2-53-03 - Water Treatment Purification Package |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0321 | PS2-53-LIT-4102-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-53-LIT-4102 | CPP AGI |  | PS2-53-01 - Utility Water Storage Tank |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0322 | PS2-75-BI-1177-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0002 TO PS2-75-BI-1177 | CPP AGI |  | PS2-75-02 - Biocide Injection Package |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0323 | PS2-75-BI-1371-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-75-BI-1371 | CPP AGI |  | PS2-75-02 - Biocide Injection Package |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0324 | PS2-75-BI-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-75-BI-0001 | CPP AGI |  | PS2-75-01 - DRA Injection Package |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0325 | PS2-75-BI-0002-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-75-BI-0002 | CPP AGI |  | PS2-75-01 - DRA Injection Package |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0326 | PS2-75-BI-0002-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-75-BI-0002 | CPP AGI |  | PS2-75-01 - DRA Injection Package |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0327 | PS2-75-BI-0002-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0004 TO PS2-75-BI-0002 | CPP AGI |  | PS2-75-01 - DRA Injection Package |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0328 | PS2-75-MOV-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-75-MOV-0001 | CPP AGI |  | PS2-28-08 - Open Drains (OD2) |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0329 | PS2-75-MOV-0001-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0004 TO PS2-75-MOV-0001 | CPP AGI |  | PS2-28-08 - Open Drains (OD2) |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0330 | PS2-79-IG-0001-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-79-IG-0001 | CPP AGI |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0331 | PS2-79-IG-0002-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-79-IG-0002 | CPP AGI |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0332 | PS2-79-IG-0003-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-79-IG-0003 | CPP AGI |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0333 | PS2-79-IG-0004-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-79-IG-0004 | CPP AGI |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-0334 | PS2-79-IG-0005-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-79-IG-0005 | CPP AGI |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1566 | PS2-25-BI-1174A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0002 TO PS2-25-BI-1174A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1567 | PS2-25-BI-1174B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0002 TO PS2-25-BI-1174B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1568 | PS2-25-BI-1174C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0002 TO PS2-25-BI-1174C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1569 | PS2-25-BI-1274A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-25-BI-1274A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1570 | PS2-25-BI-1274B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-25-BI-1274B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1571 | PS2-25-BI-1274C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-25-BI-1274C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1572 | PS2-25-BI-1801A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1801A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1573 | PS2-25-BI-1802A-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1802A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1574 | PS2-25-BI-2302-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0002 TO PS2-25-BI-2302 | CPP AGI |  | PS2-91-01 - Multicore cables & JB |  | cable pulled, G&T to be completed |  | Construction not yet started | ETA- 25th JULY 2026 | #NAME?
T-00614-1575 | PS2-25-MXS-3101AA-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0004 TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1576 | PS2-25-MXS-3101BA-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0004 TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1577 | PS2-25-MXS-3101CA-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0004 TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1578 | PS2-61-IDH-3100A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1579 | PS2-61-IDH-3100A-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1580 | PS2-61-IDH-3100A-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-61-IDH-3100A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1581 | PS2-61-IDH-3100B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1582 | PS2-61-IDH-3100B-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1583 | PS2-61-IDH-3100B-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-61-IDH-3100B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1584 | PS2-61-IDH-3100C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1585 | PS2-61-IDH-3100C-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0004 TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1586 | PS2-61-IDH-3100C-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-61-IDH-3100C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1587 | PS2-83-EHO-0001A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-83-EHO-0001A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1588 | PS2-83-EHO-0001A-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-83-EHO-0001A | CPP AGI |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1589 | PS2-83-EHO-0001B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-83-EHO-0001B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1590 | PS2-83-EHO-0001B-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-83-EHO-0001B | CPP AGI |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1591 | PS2-83-EHO-0001C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-83-EHO-0001C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00614-1592 | PS2-83-EHO-0001C-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-83-EHO-0001C | CPP AGI |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done |  | Construction not yet started |  | #NAME?
T-00615-0004 | PS2-03-BI-1501-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0005 TO PS2-03-BI-1501 | KENT |  | PS2-03-01 - FZ-01 - Process Area |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0072
T-00615-0005 | PS2-03-BI-1502-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0005 TO PS2-03-BI-1502 | KENT |  | PS2-03-01 - FZ-01 - Process Area |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0072
T-00615-0006 | PS2-03-BI-1503-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0005 TO PS2-03-BI-1503 | KENT |  | PS2-03-01 - FZ-01 - Process Area |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0073
T-00615-0007 | PS2-03-BI-2501-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-BI-2501 | KENT |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  |  |  | Construction not yet started |  | #N/A
T-00615-0008 | PS2-03-BI-2502-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-BI-2502 | KENT |  | PS2-03-02 - FZ-02 - Transformer And Operations & Maintenance Areas |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-0009 | PS2-03-BI-2503-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-BI-2503 | KENT |  | PS2-03-01 - FZ-01 - Process Area |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0096
T-00615-0010 | PS2-03-BI-2504-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-BI-2504 | KENT |  | PS2-03-01 - FZ-01 - Process Area |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0072
T-00615-0217 | PS2-03-BI-1504-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0005 TO PS2-03-BI-1504 | KENT |  | PS2-03-01 - FZ-01 - Process Area |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0072
T-00615-0218 | PS2-03-BI-2505-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-BI-2505 | KENT |  | PS2-03-01 - FZ-01 - Process Area |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0072
T-00615-0219 | PS2-03-HS-7002-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0002 TO PS2-03-HS-7002 | KENT |  | PS2-03-03 - FZ-03 - Buildings Area |  |  |  | Construction not yet started |  | CPP-RFI-65-16-04-0206
T-00615-0220 | PS2-03-MTX-0001-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0002 TO PS2-03-MTX-0001 | KENT |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00615-0221 | PS2-03-MTX-0001-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0002 TO PS2-03-MTX-0001 | KENT |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00615-0222 | PS2-03-MTX-0001-CC03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0002 TO PS2-03-MTX-0001 | KENT |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00615-0223 | PS2-03-MTX-0001-CC04 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0004 TO PS2-03-MTX-0001 | KENT |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00615-0224 | PS2-03-MTX-0001-CC05 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-MTX-0001 | KENT |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00615-0225 | PS2-03-MTX-0001-CC06 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0007 TO PS2-03-MTX-0001 | KENT |  | PS2-04-02 - Office Building SIS/FGS System |  |  |  | Construction not yet started |  | #N/A
T-00615-0226 | PS2-03-RMAC-0301-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-RMAC-0301 | KENT |  | PS2-03-03 - FZ-03 - Buildings Area |  |  |  | Construction not yet started |  | CPP-RFI-65-16-04-0206
T-00615-0227 | PS2-03-SEA-0001-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-03-04 - FZ-04 - Emergency Diesel Generator Enclosure |  | Cable laying, glanding & termination completed, | Planned By 10th June 2026 | Construction Completed , Pre Com work pending | Final RFI for G&T awaiting
T-00615-0228 | PS2-03-SEA-0002-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-SEA-0002 | KENT |  | PS2-03-05 - FZ-G1 - Guard House |  |  |  | Construction not yet started |  | CPP-RFI-65-16-04-0206
T-00615-0229 | PS2-03-SEA-0002-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-03-SEA-0002 | KENT |  | PS2-03-05 - FZ-G1 - Guard House |  |  |  | Construction not yet started |  | CPP-RFI-65-16-04-0206
T-00615-0230 | PS2-03-SEA-0003-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-SEA-0003 | KENT |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started |  | CPP-RFI-65-16-04-0206
T-00615-0231 | PS2-03-SEA-0003-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-03-SEA-0003 | KENT |  | PS2-03-08 - FZ - Workshop and Warehouse |  |  |  | Construction not yet started |  | CPP-RFI-65-16-04-0206
T-00615-0232 | PS2-03-SEA-0005-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-03-SEA-0005 | KENT |  | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started |  | #N/A
T-00615-0233 | PS2-03-SEA-0005-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-03-SEA-0005 | KENT |  | PS2-03-07 - FZ - Office Building |  |  |  | Construction not yet started |  | #N/A
T-00615-0234 | PS2-05-BI-0002-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, G&T and testing completed. Gland earthing/bonding to be completed |  | Construction not yet started | CPP-EITscope- only EDG side | CPP-RFI-65-16-11-0180
T-00615-0235 | PS2-05-BI-0002-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, G&T and testing completed. Gland earthing/bonding to be completed |  | Construction not yet started | CPP-EITscope- only EDG side | CPP-RFI-65-16-11-0180
T-00615-0236 | PS2-05-BI-0002-CC03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, G&T and testing completed. Gland earthing/bonding to be completed |  | Construction not yet started | CPP-EITscope- only EDG side | CPP-RFI-65-16-11-0180
T-00615-0237 | PS2-05-BI-0002-CC04 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, G&T and testing completed. Gland earthing/bonding to be completed |  | Construction not yet started | CPP-EITscope- only EDG side | CPP-RFI-65-16-11-0180
T-00615-0238 | PS2-05-BI-0002-CC05 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, G&T and testing completed. Gland earthing/bonding to be completed |  | Construction not yet started | CPP-EITscope- only EDG side | CPP-RFI-65-16-11-0180
T-00615-0239 | PS2-05-BI-0002-CC06 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, G&T and testing completed. Gland earthing/bonding to be completed |  | Construction not yet started | CPP-EITscope- only EDG side | CPP-RFI-65-16-11-0180
T-00615-0240 | PS2-05-BI-0002-CC11 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-05-BI-0002 | KENT |  | PS2-03-04 - FZ-04 - Emergency Diesel Generator Enclosure |  | Cable laying, G&T and testing completed. Gland earthing/bonding to be completed |  | Construction not yet started | CPP-EITscope- only EDG side
T-00615-0241 | PS2-05-BI-0002-CC12 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0007 TO PS2-05-BI-0002 | KENT |  | PS2-03-04 - FZ-04 - Emergency Diesel Generator Enclosure |  | Cable laying, G&T and testing completed. Gland earthing/bonding to be completed |  | Construction not yet started | CPP-EITscope- only EDG side
T-00615-0242 | PS2-05-BI-0002-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, G&T and testing completed. Gland earthing/bonding to be completed |  | Construction not yet started | CPP-EITscope- only EDG side | CPP-RFI-65-16-11-0180
T-00615-0243 | PS2-05-BI-0002-CJ02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, G&T and testing completed. Gland earthing/bonding to be completed |  | Construction not yet started | CPP-EITscope- only EDG side | CPP-RFI-65-16-11-0180
T-00615-0244 | PS2-05-BI-0002-CJ03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  | Cable laying, G&T and testing completed. Gland earthing/bonding to be completed |  | Construction not yet started | CPP-EITscope- only EDG side | CPP-RFI-65-16-11-0180
T-00615-0245 | PS2-05-GC-8100-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  |  |  | Construction not yet started |  | CPP-RFI-65-16-11-0180
T-00615-0246 | PS2-05-IE-8101-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  |  |  | Construction not yet started |  | CPP-RFI-65-16-11-0180
T-00615-0247 | PS2-05-IG-0009-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  |  |  | Construction not yet started |  | CPP-RFI-65-16-11-0180
T-00615-0248 | PS2-05-IG-0009-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  |  |  | Construction not yet started |  | CPP-RFI-65-16-11-0180
T-00615-0249 | PS2-05-IG-0009-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  |  |  | Construction not yet started |  | CPP-RFI-65-16-11-0180
T-00615-0250 | PS2-05-LIT-4101-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  |  |  | Construction not yet started |  | CPP-RFI-65-16-11-0180
T-00615-0251 | PS2-05-UH-8100-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  |  |  | Construction not yet started |  | CPP-RFI-65-16-11-0180
T-00615-0252 | PS2-05-UH-8100-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-05-IE-8100 TO PS2-05-BI-0002 | KENT |  | PS2-05-01 - Emergency Diesel Generator Package |  |  |  | Construction not yet started |  | CPP-RFI-65-16-11-0180
T-00615-0253 | PS2-09-BI-2501-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0007 TO PS2-09-BI-2501 | KENT |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | CPP-RFI-65-16-04-0206
T-00615-0254 | PS2-09-BI-2502-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0007 TO PS2-09-BI-2502 | KENT |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #N/A
T-00615-0255 | PS2-09-LB-0006-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-09-LB-0006 | KENT |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | CPP-RFI-65-16-04-0206
T-00615-0256 | PS2-09-LB-0006-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-09-LB-0006 | KENT |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | CPP-RFI-65-16-04-0206
T-00615-0257 | PS2-09-LB-0006-CC03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0007 TO PS2-09-LB-0006 | KENT |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | CPP-RFI-65-16-04-0206
T-00615-0258 | PS2-09-LB-0006-CC04 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-09-LB-0006 | KENT |  | PS2-09-03 - HVAC for Workshop & Warehouse |  |  |  | Construction not yet started |  | CPP-RFI-65-16-04-0206
T-00615-0259 | PS2-09-LB-0008-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-09-LB-0008 | KENT |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #N/A
T-00615-0260 | PS2-09-LB-0008-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-09-LB-0008 | KENT |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #N/A
T-00615-0261 | PS2-09-LB-0008-CC03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0007 TO PS2-09-LB-0008 | KENT |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #N/A
T-00615-0262 | PS2-09-LB-0008-CC04 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0004 TO PS2-09-LB-0008 | KENT |  | PS2-09-01 - HVAC for Office building |  |  |  | Construction not yet started |  | #N/A
T-00615-0263 | PS2-25-BI-1101-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-25-BI-1101 | KENT |  | PS2-91-01 - Multicore cables & JB |  |  |  | Construction not yet started |  | #N/A
T-00615-0264 | PS2-25-BI-1102-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-25-BI-1102 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0096
T-00615-0265 | PS2-25-BI-1106-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-25-BI-1106 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0072
T-00615-0266 | PS2-25-BI-1107-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-25-BI-1107 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0073
T-00615-0267 | PS2-25-BI-1108-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-25-BI-1108 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0073
T-00615-0268 | PS2-25-BI-1201-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-25-BI-1201 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0072
T-00615-0269 | PS2-25-BI-1301-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-25-BI-1301 | KENT |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0096
T-00615-0270 | PS2-25-BI-1302-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-25-BI-1302 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0096
T-00615-0271 | PS2-25-BI-1305-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-25-BI-1305 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0073
T-00615-0272 | PS2-25-BI-1801B-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1801B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-0273 | PS2-25-BI-1801C-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1801C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-0274 | PS2-25-BI-1802B-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1802B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-0275 | PS2-25-BI-1802C-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1802C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-0276 | PS2-25-BI-1803A-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1803A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-0277 | PS2-25-BI-1803A-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1803A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-0278 | PS2-25-BI-1803B-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1803B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-0279 | PS2-25-BI-1803B-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1803B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-0280 | PS2-25-BI-1803C-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1803C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-0281 | PS2-25-BI-1803C-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1803C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-0282 | PS2-25-BI-2101-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-25-BI-2101 | KENT |  | PS2-25-01 - Export Pipeline Pig Receiver |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0072
T-00615-0283 | PS2-25-BI-2102-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0004 TO PS2-25-BI-2102 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0074
T-00615-0284 | PS2-25-BI-2103-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0004 TO PS2-25-BI-2103 | KENT |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0072
T-00615-0285 | PS2-25-BI-2104-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-25-BI-2104 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0096
T-00615-0286 | PS2-25-BI-2105-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-25-BI-2105 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0072
T-00615-0287 | PS2-25-BI-2106-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-25-BI-2106 | KENT |  | PS2-25-05 - Crude Oil Export Pumps Bypass |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0073
T-00615-0288 | PS2-25-BI-2107-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-25-BI-2107 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0096
T-00615-0289 | PS2-25-BI-2108-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-25-BI-2108 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0073
T-00615-0290 | PS2-25-BI-2109-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-25-BI-2109 | KENT |  | PS2-25-05 - Crude Oil Export Pumps Bypass |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0096
T-00615-0291 | PS2-25-BI-2201-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0002 TO PS2-25-BI-2201 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0095
T-00615-0292 | PS2-25-BI-2202-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0002 TO PS2-25-BI-2202 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0074
T-00615-0293 | PS2-25-BI-2203-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0002 TO PS2-25-BI-2203 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0095
T-00615-0294 | PS2-25-BI-2301-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0003 TO PS2-25-BI-2301 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0072
T-00615-0295 | PS2-25-BI-2303-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0004 TO PS2-25-BI-2303 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0096
T-00615-0296 | PS2-25-BI-2304-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0004 TO PS2-25-BI-2304 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0073
T-00615-0297 | PS2-25-BI-2305-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0004 TO PS2-25-BI-2305 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0074
T-00615-0298 | PS2-25-BI-2306-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0003 TO PS2-25-BI-2306 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0072
T-00615-0299 | PS2-25-BI-2307-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0003 TO PS2-25-BI-2307 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0072
T-00615-0300 | PS2-25-BI-2308-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0003 TO PS2-25-BI-2308 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0073
T-00615-0301 | PS2-25-BI-2315-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0003 TO PS2-25-BI-2315 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0072
T-00615-0302 | PS2-25-MXS-3101AB-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-0303 | PS2-25-MXS-3101BB-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-0304 | PS2-25-MXS-3101CB-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-0305 | PS2-25-PIT-0052-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-25-SDV-0052 | KENT |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0074
T-00615-0306 | PS2-25-PIT-0071A-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-25-PIT-0071A | KENT |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0074
T-00615-0307 | PS2-25-PIT-0071B-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-25-PIT-0071B | KENT |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0074
T-00615-0308 | PS2-25-PIT-0071C-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-25-PIT-0071C | KENT |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0074
T-00615-0309 | PS2-25-SDV-0052-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-25-SDV-0052 | KENT |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0074
T-00615-0310 | PS2-25-SDV-0052-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-25-SDV-0052 IDC24 | KENT |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0074
T-00615-0311 | PS2-25-SHSR-0052-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0003 TO PS2-25-SDV-0052 | KENT |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0095
T-00615-0312 | PS2-25-SXS-0052-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-25-SDV-0052 | KENT |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0074
T-00615-0313 | PS2-25-SY-0052A-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-01-LA-0001 TO PS2-25-SDV-0052 | KENT |  | PS2-25-07 - Export Pipeline Pig Launcher |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0074
T-00615-0314 | PS2-28-BI-1103-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-28-BI-1103 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0072
T-00615-0315 | PS2-28-BI-1303-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-28-BI-1303 | KENT |  | PS2-91-01 - Multicore cables & JB |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0072
T-00615-0316 | PS2-28-HXA-1101-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-28-HXA-1101 | KENT |  | PS2-28-03 - Closed Drain Drum & Pump |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0074
T-00615-0317 | PS2-28-LB-8200-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-28-LB-8200 | KENT |  | PS2-28-09 - Open Drain Interceptor |  |  |  | Construction not yet started |  | CPP-RFI-65-16-03-0101
T-00615-0318 | PS2-28-LB-8200-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-28-LB-8200 | KENT |  | PS2-28-09 - Open Drain Interceptor |  |  |  | Construction not yet started |  | CPP-RFI-65-16-03-0101
T-00615-0319 | PS2-53-BI-1105-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0002 TO PS2-53-BI-1105 | KENT |  | PS2-91-01 - Multicore cables & JB |  |  |  | Construction not yet started |  | CPP-RFI-65-16-03-0101
T-00615-0320 | PS2-53-LA-0001-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-53-LA-0001 | KENT |  | PS2-53-03 - Water Treatment Purification Package |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0095
T-00615-0321 | PS2-53-LIT-4102-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-53-LIT-4102 | KENT |  | PS2-53-01 - Utility Water Storage Tank |  |  |  | Construction not yet started |  | CPP-RFI-65-16-03-0101
T-00615-0322 | PS2-75-BI-1177-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0002 TO PS2-75-BI-1177 | KENT |  | PS2-75-02 - Biocide Injection Package |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0095
T-00615-0323 | PS2-75-BI-1371-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-75-BI-1371 | KENT |  | PS2-75-02 - Biocide Injection Package |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0095
T-00615-0324 | PS2-75-BI-0001-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-75-BI-0001 | KENT |  | PS2-75-01 - DRA Injection Package |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0095
T-00615-0325 | PS2-75-BI-0002-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-75-BI-0002 | KENT |  | PS2-75-01 - DRA Injection Package |  | Cable laying, G&T and testing completed. Gland earthing/bonding to be completed |  | Construction not yet started | CPP-EITscope- only EDG side | CPP-RFI-65-16-04-0095
T-00615-0326 | PS2-75-BI-0002-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-75-BI-0002 | KENT |  | PS2-75-01 - DRA Injection Package |  | Cable laying, G&T and testing completed. Gland earthing/bonding to be completed |  | Construction not yet started | CPP-EITscope- only EDG side | CPP-RFI-65-16-04-0095
T-00615-0327 | PS2-75-BI-0002-CC03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0004 TO PS2-75-BI-0002 | KENT |  | PS2-75-01 - DRA Injection Package |  | Cable laying, G&T and testing completed. Gland earthing/bonding to be completed |  | Construction not yet started | CPP-EITscope- only EDG side | CPP-RFI-65-16-04-0095
T-00615-0328 | PS2-75-MOV-0001-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-75-MOV-0001 | KENT |  | PS2-28-08 - Open Drains (OD2) |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0095
T-00615-0329 | PS2-75-MOV-0001-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0004 TO PS2-75-MOV-0001 | KENT |  | PS2-28-08 - Open Drains (OD2) |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0074
T-00615-0330 | PS2-79-IG-0001-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-79-IG-0001 | KENT |  | PS2-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS2-79-IG-0001) |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0074
T-00615-0331 | PS2-79-IG-0002-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-79-IG-0002 | KENT |  | PS2-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS2-79-IG-0002) |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0074
T-00615-0332 | PS2-79-IG-0003-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-79-IG-0003 | KENT |  | PS2-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS2-79-IG-0003) |  |  |  | Construction not yet started |  | #N/A
T-00615-0333 | PS2-79-IG-0004-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-79-IG-0004 | KENT |  | PS2-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS2-79-IG-0004) |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0096
T-00615-0334 | PS2-79-IG-0005-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0003 TO PS2-79-IG-0005 | KENT |  | PS2-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS2-79-IG-0005) |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-04-0096
T-00615-1566 | PS2-25-BI-1174A-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0002 TO PS2-25-BI-1174A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-1567 | PS2-25-BI-1174B-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0002 TO PS2-25-BI-1174B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-1568 | PS2-25-BI-1174C-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0002 TO PS2-25-BI-1174C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-1569 | PS2-25-BI-1274A-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-25-BI-1274A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-1570 | PS2-25-BI-1274B-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-25-BI-1274B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-1571 | PS2-25-BI-1274C-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0001 TO PS2-25-BI-1274C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-1572 | PS2-25-BI-1801A-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1801A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-1573 | PS2-25-BI-1802A-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-25-IE-0001 TO PS2-25-BI-1802A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-16-12-0208
T-00615-1574 | PS2-25-BI-2302-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0002 TO PS2-25-BI-2302 | KENT |  | PS2-91-01 - Multicore cables & JB |  |  |  | Construction not yet started |  | #N/A
T-00615-1575 | PS2-25-MXS-3101AA-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0004 TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-1576 | PS2-25-MXS-3101BA-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0004 TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-1577 | PS2-25-MXS-3101CA-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0004 TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-1578 | PS2-61-IDH-3100A-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-1579 | PS2-61-IDH-3100A-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-1580 | PS2-61-IDH-3100A-CC03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-61-IDH-3100A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-1581 | PS2-61-IDH-3100B-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-1582 | PS2-61-IDH-3100B-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-1583 | PS2-61-IDH-3100B-CC03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-61-IDH-3100B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-1584 | PS2-61-IDH-3100C-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0001 TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-1585 | PS2-61-IDH-3100C-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0004 TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-1586 | PS2-61-IDH-3100C-CC03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-61-IDH-3100C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-1587 | PS2-83-EHO-0001A-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-83-EHO-0001A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-1588 | PS2-83-EHO-0001A-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-83-EHO-0001A | KENT |  | PS2-25-02 - Crude Oil Export Pump A |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-1589 | PS2-83-EHO-0001B-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-83-EHO-0001B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-1590 | PS2-83-EHO-0001B-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-83-EHO-0001B | KENT |  | PS2-25-03 - Crude Oil Export Pump B |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-1591 | PS2-83-EHO-0001C-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-03-SFMC-0006 TO PS2-83-EHO-0001C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090
T-00615-1592 | PS2-83-EHO-0001C-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I - Instrumentation | Cable FROM PS2-04-PMC-0005 TO PS2-83-EHO-0001C | KENT |  | PS2-25-04 - Crude Oil Export Pump C |  | cable pulled coiled near VSD area , to be routed inside EITS, G&Tto be done | JB and marshalling cabinet not available for termination | Construction work pending |  | CPP-RFI-65-33/1-05-0090