## ITR SUMMARY
Responsible Company : CPP AGI
Physical Area : PS5 - Tanzania
Pre-commissioning ITRs
Discipline | Total | Closed | % | Open | CUT OFF DATE-19 AUGUST 2026
CPP
Building | 71 | 41 | 0.5775 | 30
HVAC | 123 | 9 | 0.0732 | 114
Mechanical | 422 | 276 | 0.654 | 146
Piping & Vessel | 2911 | 1210 | 0.4157 | 1701
Safety | 172 | 81 | 0.4709 | 91
Total | 3699 | 1617 | 0.4371 | 2082
EIT
Electrical | 4627 | 174 | 0.0376 | 4453
Instrumentation | 4595 | 1005 | 0.2187 | 3590
Telecom | 1078 | 27 | 0.025 | 1051
Total | 10300 | 1206 | 0.1171 | 9094
Grand Total | 13999 | 2823 | 0.2017 | 11176
*Note: This report was generated based on Hexagon data as of- 19 AUGUST 2026 at 7.00 AM

## PUNCH SUMMERY
PS5 Punch Summary
| A Punch Summary |  |  |  | B Punch Summary |  |  |  | C Punch Summary |  |  |  | 0 Punch Summary
| Discipline | Total | Closed | Open | Discipline | Total | Closed | Open | Discipline | Total | Closed | Open | Discipline | Total | Closed | Open
| Building | 543 | 141 | 402 | Building | 575 | 279 | 296 | Building | 183 | 101 | 82 | Building | 72 | 52 | 20
| Electrical | 179 | 10 | 169 | Electrical | 591 | 527 | 64 | Electrical | 453 | 308 | 145 | Electrical | 413 | 244 | 169
| HVAC | 342 | 315 | 27 | HVAC | 419 | 52 | 367 | HVAC | 135 | 97 | 38 | HVAC | 59 | 35 | 24
| Instrumentation | 468 | 12 | 456 | Instrumentation | 165 | 5 | 160 | Instrumentation | 598 | 150 | 448 | Instrumentation | 568 | 201 | 367
| Mechanical | 31 | 17 | 14 | Mechanical | 487 | 40 | 447 | Mechanical | 404 | 333 | 71 | Mechanical | 154 | 117 | 37
| Piping & Vessel | 544 | 124 | 420 | Piping & Vessel | 195 | 67 | 128 | Piping & Vessel | 156 | 134 | 22 | Piping & Vessel | 397 | 196 | 201
| Safety | 83 | 22 | 61 | Safety | 535 | 358 | 177 | Safety | 409 | 172 | 237 | Safety | 328 | 209 | 119
| Telecom | 456 | 378 | 78 | Telecom | 162 | 19 | 143 | Telecom | 318 | 150 | 168 | Telecom | 399 | 77 | 322
| Miscellaneous | 0 | 0 | 0 | Miscellaneous | 0 | 0 | 0 | Miscellaneous | 0 | 0 | 0 | Miscellaneous | 0 | 0 | 0
| Grand Total | 2646 | 1019 | 1627 | Grand Total | 3129 | 1347 | 1782 | Grand Total | 2656 | 1445 | 1211 | Grand Total | 2390 | 1131 | 1259
*Note: This report was generated based on Hexagon data as of - 19 AUGUST 2026 at 7.00 AM

## DETAILED PUNCH LIST
Punchlist ID | Asset (Name/Tag) | Asset Pack | CAT | Discipline (Name) | Description | Scheduling - Responsible Company (Name) | Systemization - Subsystem (Summary) | Workflow - Closing Date | Status | Originated by | PRIORITY | PRIORITY_NUM
PL-00001 | PS5-04-UR-4582A |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-01-04 - Fire Water Ring Main | 2026-12-14 | Closed | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-00002 | PS5-98-IK-7924B |  | I | I | Missing loop diagram | CPP AGI | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Jean, Pierre | PS5 - Milestone D | 3
PL-00003 | PS5-34-UR-8527C |  | P | P | Insulation damaged | KENT | PS5-03-02 - Fire & Gas Detection |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00004 | PS5-11-IK-2654B |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-12-02 - Water Treatment |  | In Progress | Wang, Li | PS5 - Milestone D | 3
PL-00005 | PS5-10-NI-3803C |  | P | P | Pipe support missing | KENT | PS5-05-01 - Telecom Network |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-00006 | PS5-30-UR-6168B |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-60-01 - Power Generation Package A |  | On Hold | Jean, Pierre | PS5 - Milestone E | 4
PL-00007 | PS5-32-NI-9830B |  | P | P | Missing pipe stress label | CPP AGI | PS5-07-02 - Chiller System B |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-00008 | PS5-97-UR-2796A |  | S | S | Emergency shower not tested | CPP AGI | PS5-12-02 - Water Treatment |  | On Hold | Wang, Li | PS5 - Milestone D | 3
PL-00009 | PS5-02-UR-9797D |  | S | S | Deluge valve not primed | KENT | PS5-01-09 - Inergen for EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-00010 | PS5-65-UR-5889D |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-10-02 - Utility Pipe Rack | 2026-12-25 | Closed | Kumar, Raj | PS5 - Milestone G | 6
PL-00011 | PS5-03-UR-6947D |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-04-04 - 33kV PCS System |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-00012 | PS5-99-IK-3103C |  | B | B | Cracked wall plaster | KENT | PS5-08-01 - Compressor Air System |  | Originated | Jean, Pierre | PS5 - Milestone B | 1.1
PL-00013 | PS5-86-OB-8177D |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building |  | On Hold | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-00014 | PS5-10-UR-4750A |  | I | I | Transmitter not calibrated | CPP AGI | PS5-07-03 - AHU System |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00015 | PS5-74-NI-8744A |  | E | E | Incomplete cable termination | KENT | PS5-08-01 - Compressor Air System |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-00016 | PS5-94-UR-2612A |  | I | I | Missing instrument tag | EPS UNATRAC | PS5-03-01 - ESD System |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00017 | PS5-10-NER-2604A |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-08-02 - Nitrogen Generator | 2026-10-15 | Closed | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-00018 | PS5-08-IK-7209A |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-08-01 - Compressor Air System |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-00019 | PS5-28-UR-9883A |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-10-01 - Main Pipe Rack |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00020 | PS5-24-UR-2113C |  | B | B | Incomplete floor tiling | CPP AGI | PS5-82-07 - Guard Huts |  | On Hold | Smith, John | PS5 - Milestone I | 8
PL-00021 | PS5-67-OB-5272A |  | E | E | Outgoing breaker not labeled | KENT | PS5-08-02 - Nitrogen Generator |  | In Progress | Mohamed, Ali | PS5 - Milestone A | 1
PL-00022 | PS5-73-UR-2200C |  | I | I | Control valve actuator fault | KENT | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-08-15 | Closed | Mohamed, Ali | PS5 - Milestone G | 6
PL-00023 | PS5-70-OB-9666A |  | H | H | FCU drain pipe not connected | EPS UNATRAC | PS5-11-03 - Admin Building |  | On Hold | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00024 | PS5-27-OB-4335C |  | E | E | Wrong cable glanding | KENT | PS5-04-02 - SIS System | 2026-10-10 | Closed | Kumar, Raj | PS5 - Milestone E | 4
PL-00025 | PS5-01-OB-3143C |  | T | T | CAT6 cable untidied | CPP AGI | PS5-09-01 - Transformer 33kV/6.6kV |  | Originated | Jean, Pierre | PS5 - Milestone A | 1
PL-00026 | PS5-05-OB-3426B |  | T | T | Fiber patch panel unorganized | KENT | PS5-61-07 - 0.4kV Switchboard EITS Building |  | Originated | Mohamed, Ali | PS5 - Milestone I | 8
PL-00027 | PS5-80-IK-4878D |  | P | P | Pipe support missing | EPS UNATRAC | PS5-01-06 - Deluge System | 2026-12-28 | Closed | Smith, John | PS5 - Milestone F | 5
PL-00028 | PS5-32-OB-3608D |  | B | B | Missing fire extinguisher signage | KENT | PS5-05-03 - CCTV System |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-00029 | PS5-25-NER-6378B |  | B | B | Missing fire extinguisher signage | KENT | PS5-82-02 - Structural Steel B | 2026-09-01 | Closed | Mohamed, Ali | PS5 - Milestone D | 3
PL-00030 | PS5-75-OB-1626A |  | P | P | Insulation damaged | CPP AGI | PS5-60-10 - Power Generation Package D |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-00031 | PS5-88-IK-6967B |  | P | P | Gasket protruding from flange | KENT | PS5-62-01 - Cable Tray Main | 2026-08-17 | Closed | Mohamed, Ali | PS5 - Milestone I | 8
PL-00032 | PS5-38-NI-3085A |  | P | P | Gasket protruding from flange | KENT | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-00033 | PS5-56-NI-6279B |  | H | H | AHU filter not installed | CPP AGI | PS5-10-03 - Process piping A |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-00034 | PS5-80-OB-2530D |  | I | I | Missing loop diagram | KENT | PS5-82-02 - Structural Steel B |  | In Progress | Wang, Li | PS5 - Milestone C | 2
PL-00035 | PS5-74-IK-7291B |  | M | M | Missing rotation arrow | KENT | PS5-07-03 - AHU System | 2026-11-14 | Closed | Jean, Pierre | PS5 - Milestone D | 3
PL-00036 | PS5-60-NI-6198D |  | B | B | Missing door closer | CPP AGI | PS5-03-02 - Fire & Gas Detection | 2026-08-15 | Closed | Kumar, Raj | PS5 - Milestone G | 6
PL-00037 | PS5-82-OB-9540B |  | S | S | Emergency shower not tested | CPP AGI | PS5-63-01 - Electrical Earthing |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-00038 | PS5-50-IK-4505A |  | T | T | PA speaker not tested | CPP AGI | PS5-02-01 - Diesel Storage Tank | 2026-09-05 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-00039 | PS5-01-OB-5892D |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-12-13 | Closed | Kumar, Raj | PS5 - Milestone A | 1
PL-00040 | PS5-60-IK-9751A |  | I | I | Pressure gauge reads zero | CPP AGI | PS5-99-01 - Area Completion Building Area | 2026-11-24 | Closed | Kumar, Raj | PS5 - Milestone D | 3
PL-00041 | PS5-59-OB-6529D |  | B | B | Missing door closer | CPP AGI | PS5-02-02 - Diesel Transfer Pump | 2026-11-11 | Closed | Mohamed, Ali | PS5 - Milestone G | 6
PL-00042 | PS5-09-UR-1508D |  | S | S | Emergency shower not tested | KENT | PS5-09-01 - Transformer 33kV/6.6kV |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00043 | PS5-90-OB-7043A |  | H | H | FCU drain pipe not connected | EPS UNATRAC | PS5-08-01 - Compressor Air System |  | In Progress | Wang, Li | PS5 - Milestone C | 2
PL-00044 | PS5-10-NI-4978A |  | E | E | Wrong cable glanding | CPP AGI | PS5-05-01 - Telecom Network | 2026-11-23 | Closed | Wang, Li | PS5 - Milestone E | 4
PL-00045 | PS5-44-UR-7882D |  | E | E | Cable tray not properly supported | KENT | PS5-01-06 - Deluge System |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-00046 | PS5-62-NER-8136D |  | P | P | Missing pipe stress label | KENT | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-00047 | PS5-49-OB-1470B |  | P | P | Valve handwheel stiff | KENT | PS5-08-02 - Nitrogen Generator | 2026-12-20 | Closed | Jean, Pierre | PS5 - Milestone B | 1.1
PL-00048 | PS5-36-NI-1166C |  | T | T | Missing cable label | KENT | PS5-07-02 - Chiller System B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00049 | PS5-92-NER-8342D |  | I | I | Transmitter not calibrated | KENT | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-00050 | PS5-45-NER-6419B |  | I | I | Pressure gauge reads zero | KENT | PS5-60-10 - Power Generation Package D |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-00051 | PS5-62-OB-9595C |  | M | M | Pump alignment required | KENT | PS5-09-01 - Transformer 33kV/6.6kV | 2026-09-07 | Closed | Jean, Pierre | PS5 - Milestone D | 3
PL-00052 | PS5-71-OB-3068C |  | M | M | Bearing temperature high | CPP AGI | PS5-07-04 - FCU System | 2026-10-02 | Closed | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00053 | PS5-62-UR-2070B |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-10-01 - Main Pipe Rack |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-00054 | PS5-72-NER-4697D |  | B | B | Missing door closer | CPP AGI | PS5-04-04 - 33kV PCS System |  | On Hold | Smith, John | PS5 - Milestone C | 2
PL-00055 | PS5-98-IK-4457B |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-10-03 - Process piping A |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-00056 | PS5-77-NER-5771A |  | I | I | Instrument tubing leak | KENT | PS5-05-03 - CCTV System |  | Originated | Wang, Li | PS5 - Milestone I | 8
PL-00057 | PS5-76-IK-7965A |  | M | M | Missing rotation arrow | KENT | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-00058 | PS5-96-NI-5728B |  | H | H | AHU filter not installed | KENT | PS5-09-03 - Motor Control Center |  | Originated | Wang, Li | PS5 - Milestone C | 2
PL-00059 | PS5-06-NER-6280C |  | M | M | Pump alignment required | KENT | PS5-60-10 - Power Generation Package D |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-00060 | PS5-57-OB-3973D |  | I | I | Pressure gauge reads zero | KENT | PS5-01-03 - Fire Water Pump B |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-00061 | PS5-21-OB-7744C |  | T | T | CAT6 cable untidied | CPP AGI | PS5-02-03 - Fuel Gas System |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-00062 | PS5-66-UR-9889B |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-01-05 - Foam System |  | Originated | Jean, Pierre | PS5 - Milestone H | 7
PL-00063 | PS5-37-NER-8941A |  | P | P | Gasket protruding from flange | CPP AGI | PS5-99-02 - Area Completion Process Area |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-00064 | PS5-60-UR-3522B |  | I | I | Missing instrument tag | CPP AGI | PS5-05-01 - Telecom Network |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-00065 | PS5-50-IK-9327C |  | M | M | Missing rotation arrow | CPP AGI | PS5-61-02 - 6.6kV Switchboard LLHT North |  | On Hold | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00066 | PS5-93-OB-9022D |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-61-02 - 6.6kV Switchboard LLHT North |  | On Hold | Kumar, Raj | PS5 - Milestone F | 5
PL-00067 | PS5-90-IK-7274A |  | T | T | PA speaker not tested | CPP AGI | PS5-11-03 - Admin Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00068 | PS5-65-NI-6439D |  | P | P | Insulation damaged | CPP AGI | PS5-82-02 - Structural Steel B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00069 | PS5-44-NI-7512C |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-01-02 - Fire Water Pump A |  | In Progress | Wang, Li | PS5 - Milestone C | 2
PL-00070 | PS5-81-OB-4727C |  | S | S | Missing safety sign | CPP AGI | PS5-10-05 - Drain System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00071 | PS5-38-OB-7141B |  | E | E | Missing earth continuity label | CPP AGI | PS5-62-02 - Cable Tray Secondary |  | In Progress | Kumar, Raj | PS5 - Milestone C | 2
PL-00072 | PS5-30-NER-5161B |  | S | S | Deluge valve not primed | CPP AGI | PS5-06-01 - AC UPS - EITS Building | 2026-11-19 | Closed | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00073 | PS5-59-OB-4263D |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-10-01 - Main Pipe Rack | 2026-11-23 | Closed | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-00074 | PS5-51-OB-1132C |  | I | I | Missing instrument tag | KENT | PS5-60-01 - Power Generation Package A |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-00075 | PS5-29-IK-5106C |  | B | B | Incomplete paint touch-up | EPS UNATRAC | PS5-99-02 - Area Completion Process Area |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-00076 | PS5-94-IK-2476D |  | H | H | Missing insulation on duct | EPS UNATRAC | PS5-03-01 - ESD System |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-00077 | PS5-38-OB-2886B |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-05-03 - CCTV System | 2026-09-09 | Closed | Jean, Pierre | PS5 - Milestone D | 3
PL-00078 | PS5-16-NER-7038C |  | I | I | Missing instrument tag | KENT | PS5-60-07 - Power Generation Package C |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-00079 | PS5-42-NI-4626C |  | S | S | Deluge valve not primed | KENT | PS5-13-01 - Flare System |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-00080 | PS5-18-NER-8432B |  | M | M | Motor fan guard missing | KENT | PS5-61-01 - 33kV Switchboard EITS Building | 2026-08-08 | Closed | Wang, Li | PS5 - Milestone B | 1.1
PL-00081 | PS5-05-OB-4559B |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-04-04 - 33kV PCS System |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-00082 | PS5-25-UR-8450A |  | E | E | Missing earth continuity label | EPS UNATRAC | PS5-13-01 - Flare System |  | On Hold | Wang, Li | PS5 - Milestone I | 8
PL-00083 | PS5-27-NI-4538D |  | B | B | Incomplete floor tiling | KENT | PS5-01-07 - Hydrant System | 2026-08-27 | Closed | Mohamed, Ali | PS5 - Milestone F | 5
PL-00084 | PS5-23-UR-1422A |  | H | H | Missing insulation on duct | EPS UNATRAC | PS5-01-01 - Fire Water Jockey Pump A/B |  | On Hold | Jean, Pierre | PS5 - Milestone E | 4
PL-00085 | PS5-47-NI-2786B |  | P | P | Pipe support missing | EPS UNATRAC | PS5-01-03 - Fire Water Pump B | 2026-08-16 | Closed | Kumar, Raj | PS5 - Milestone C | 2
PL-00086 | PS5-55-UR-9032C |  | B | B | Missing door closer | EPS UNATRAC | PS5-10-03 - Process piping A |  | In Progress | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00087 | PS5-71-OB-7240D |  | E | E | Missing electrical hazard sign | KENT | PS5-10-06 - Vent System |  | Originated | Mohamed, Ali | PS5 - Milestone C | 2
PL-00088 | PS5-99-NI-4522B |  | T | T | Missing cable label | KENT | PS5-99-03 - Area Completion Utilities Area |  | Originated | Smith, John | PS5 - Milestone G | 6
PL-00089 | PS5-86-OB-7132D |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-00090 | PS5-17-NI-1982C |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-02-03 - Fuel Gas System |  | Originated | Kumar, Raj | PS5 - Milestone B | 1.1
PL-00091 | PS5-37-NI-6119B |  | P | P | Missing pipe stress label | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-00092 | PS5-74-IK-8030D |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-04-04 - 33kV PCS System | 2026-08-25 | Closed | Kumar, Raj | PS5 - Milestone H | 7
PL-00093 | PS5-73-NER-2140A |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-09-03 - Motor Control Center | 2026-09-28 | Closed | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-00094 | PS5-93-OB-2391D |  | E | E | Missing earth continuity label | EPS UNATRAC | PS5-07-02 - Chiller System B |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-00095 | PS5-54-OB-4531D |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-00096 | PS5-06-IK-7475D |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-03-03 - Flame Detector System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-00097 | PS5-01-NER-8055A |  | I | I | Pressure gauge reads zero | CPP AGI | PS5-10-03 - Process piping A |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-00098 | PS5-06-NER-1307B |  | I | I | Transmitter not calibrated | KENT | PS5-99-03 - Area Completion Utilities Area |  | On Hold | Mohamed, Ali | PS5 - Milestone I | 8
PL-00099 | PS5-47-UR-8155D |  | S | S | Emergency shower not tested | KENT | PS5-60-10 - Power Generation Package D | 2026-12-15 | Closed | Smith, John | PS5 - Milestone G | 6
PL-00100 | PS5-10-NI-2868C |  | S | S | Emergency shower not tested | CPP AGI | PS5-02-02 - Diesel Transfer Pump |  | On Hold | Mohamed, Ali | PS5 - Milestone G | 6
PL-00101 | PS5-64-NER-8354C |  | P | P | Missing pipe stress label | KENT | PS5-04-03 - 33kV ICSS System | 2026-08-06 | Closed | Wang, Li | PS5 - Milestone D | 3
PL-00102 | PS5-36-NI-1920B |  | P | P | Flange bolt torque incomplete | EPS UNATRAC | PS5-10-05 - Drain System |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-00103 | PS5-79-NI-9307B |  | T | T | CCTV camera not focused | CPP AGI | PS5-63-01 - Electrical Earthing |  | Originated | Kumar, Raj | PS5 - Milestone A | 1
PL-00104 | PS5-58-UR-6626D |  | B | B | Missing fire extinguisher signage | CPP AGI | PS5-63-01 - Electrical Earthing |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-00105 | PS5-21-OB-7108D |  | H | H | AHU filter not installed | KENT | PS5-01-06 - Deluge System |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-00106 | PS5-37-OB-3463B |  | P | P | Missing pipe stress label | EPS UNATRAC | PS5-01-07 - Hydrant System |  | Originated | Wang, Li | PS5 - Milestone F | 5
PL-00107 | PS5-11-OB-7171C |  | H | H | Missing insulation on duct | KENT | PS5-11-03 - Admin Building |  | On Hold | Jean, Pierre | PS5 - Milestone E | 4
PL-00108 | PS5-44-NER-4145A |  | E | E | Missing earth continuity label | CPP AGI | PS5-61-07 - 0.4kV Switchboard EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-00109 | PS5-17-NI-7172A |  | E | E | Missing earth continuity label | KENT | PS5-10-02 - Utility Pipe Rack |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-00110 | PS5-97-NER-4833C |  | H | H | Missing insulation on duct | EPS UNATRAC | PS5-62-02 - Cable Tray Secondary |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-00111 | PS5-68-NER-3655D |  | I | I | Control valve actuator fault | KENT | PS5-13-01 - Flare System |  | In Progress | Jean, Pierre | PS5 - Milestone H | 7
PL-00112 | PS5-16-OB-2374D |  | M | M | Coupling guard loose | KENT | PS5-01-07 - Hydrant System |  | On Hold | Smith, John | PS5 - Milestone H | 7
PL-00113 | PS5-04-NER-1872B |  | H | H | Missing insulation on duct | EPS UNATRAC | PS5-62-01 - Cable Tray Main |  | On Hold | Jean, Pierre | PS5 - Milestone B | 1.1
PL-00114 | PS5-37-NER-3273D |  | S | S | Missing safety sign | CPP AGI | PS5-02-02 - Diesel Transfer Pump | 2026-09-05 | Closed | Smith, John | PS5 - Milestone F | 5
PL-00115 | PS5-31-OB-2996A |  | B | B | Missing door closer | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump | 2026-08-25 | Closed | Wang, Li | PS5 - Milestone A | 1
PL-00116 | PS5-81-NI-4963C |  | T | T | CAT6 cable untidied | CPP AGI | PS5-01-09 - Inergen for EITS Building |  | On Hold | Smith, John | PS5 - Milestone B | 1.1
PL-00117 | PS5-68-OB-2108D |  | B | B | Cracked wall plaster | CPP AGI | PS5-12-01 - Cooling Tower |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-00118 | PS5-03-OB-2106B |  | B | B | Incomplete paint touch-up | KENT | PS5-60-04 - Power Generation Package B |  | Originated | Wang, Li | PS5 - Milestone H | 7
PL-00119 | PS5-88-NER-8840C |  | E | E | Missing earth continuity label | CPP AGI | PS5-11-01 - Guard Hut A |  | Originated | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00120 | PS5-61-OB-1599D |  | T | T | Missing cable label | KENT | PS5-01-05 - Foam System | 2026-12-13 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-00121 | PS5-64-NER-7018D |  | P | P | Missing pipe stress label | CPP AGI | PS5-01-07 - Hydrant System | 2026-11-11 | Closed | Mohamed, Ali | PS5 - Milestone F | 5
PL-00122 | PS5-14-UR-6372C |  | E | E | Wrong cable glanding | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-00123 | PS5-79-NER-5498C |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-05-02 - PA/GA System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00124 | PS5-87-NER-1570A |  | S | S | Emergency shower not tested | KENT | PS5-12-02 - Water Treatment |  | On Hold | Wang, Li | PS5 - Milestone I | 8
PL-00125 | PS5-58-OB-7095B |  | P | P | Flange bolt torque incomplete | KENT | PS5-12-02 - Water Treatment |  | On Hold | Kumar, Raj | PS5 - Milestone G | 6
PL-00126 | PS5-95-IK-9176C |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-12-02 - Water Treatment |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00127 | PS5-58-IK-8292D |  | M | M | Motor fan guard missing | CPP AGI | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-08-05 | Closed | Mohamed, Ali | PS5 - Milestone H | 7
PL-00128 | PS5-91-IK-6922C |  | P | P | Flange bolt torque incomplete | KENT | PS5-01-09 - Inergen for EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-00129 | PS5-17-NI-2412A |  | H | H | AHU filter not installed | KENT | PS5-08-01 - Compressor Air System |  | Originated | Wang, Li | PS5 - Milestone H | 7
PL-00130 | PS5-10-NER-8632C |  | T | T | CAT6 cable untidied | KENT | PS5-61-01 - 33kV Switchboard EITS Building |  | On Hold | Jean, Pierre | PS5 - Milestone G | 6
PL-00131 | PS5-20-OB-3697A |  | H | H | Thermostat calibration needed | KENT | PS5-04-01 - DCS System |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-00132 | PS5-65-IK-3526A |  | P | P | Missing pipe stress label | CPP AGI | PS5-10-01 - Main Pipe Rack | 2026-12-18 | Closed | Wang, Li | PS5 - Milestone B | 1.1
PL-00133 | PS5-54-NI-1496B |  | P | P | Gasket protruding from flange | KENT | PS5-01-06 - Deluge System |  | Originated | Kumar, Raj | PS5 - Milestone A | 1
PL-00134 | PS5-54-NER-8609A |  | M | M | Vibration level exceeded | EPS UNATRAC | PS5-10-03 - Process piping A | 2026-08-06 | Closed | Jean, Pierre | PS5 - Milestone H | 7
PL-00135 | PS5-72-UR-6228A |  | P | P | Flange bolt torque incomplete | KENT | PS5-10-05 - Drain System |  | On Hold | Mohamed, Ali | PS5 - Milestone F | 5
PL-00136 | PS5-54-IK-3616D |  | T | T | CCTV camera not focused | KENT | PS5-08-02 - Nitrogen Generator |  | Originated | Wang, Li | PS5 - Milestone C | 2
PL-00137 | PS5-03-UR-7442C |  | P | P | Pipe support missing | EPS UNATRAC | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-00138 | PS5-34-OB-7606B |  | P | P | Insulation damaged | CPP AGI | PS5-01-07 - Hydrant System | 2026-08-14 | Closed | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-00139 | PS5-16-IK-2584B |  | I | I | Instrument tubing leak | KENT | PS5-12-02 - Water Treatment | 2026-12-22 | Closed | Kumar, Raj | PS5 - Milestone I | 8
PL-00140 | PS5-05-IK-6456D |  | P | P | Missing pipe stress label | CPP AGI | PS5-04-03 - 33kV ICSS System |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-00141 | PS5-95-OB-6511C |  | H | H | FCU drain pipe not connected | KENT | PS5-04-02 - SIS System |  | On Hold | Kumar, Raj | PS5 - Milestone F | 5
PL-00142 | PS5-54-NI-6040D |  | T | T | Intercom not functioning | CPP AGI | PS5-10-03 - Process piping A |  | On Hold | Wang, Li | PS5 - Milestone H | 7
PL-00143 | PS5-62-IK-9589C |  | B | B | Cracked wall plaster | KENT | PS5-82-02 - Structural Steel B |  | On Hold | Smith, John | PS5 - Milestone E | 4
PL-00144 | PS5-41-NER-3481B |  | H | H | Damper not operational | EPS UNATRAC | PS5-08-02 - Nitrogen Generator |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-00145 | PS5-49-OB-3837B |  | T | T | CCTV camera not focused | KENT | PS5-01-08 - Drencher System |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-00146 | PS5-91-IK-9011B |  | P | P | Valve handwheel stiff | EPS UNATRAC | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-09-10 | Closed | Kumar, Raj | PS5 - Milestone H | 7
PL-00147 | PS5-99-IK-5758A |  | M | M | Motor fan guard missing | EPS UNATRAC | PS5-10-01 - Main Pipe Rack |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00148 | PS5-35-NI-5450A |  | P | P | Missing pipe stress label | KENT | PS5-62-02 - Cable Tray Secondary |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-00149 | PS5-13-NER-6411C |  | I | I | Transmitter not calibrated | CPP AGI | PS5-08-02 - Nitrogen Generator |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-00150 | PS5-62-IK-5706B |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-01-01 - Fire Water Jockey Pump A/B |  | On Hold | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-00151 | PS5-05-NER-9116A |  | E | E | Outgoing breaker not labeled | CPP AGI | PS5-07-04 - FCU System |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-00152 | PS5-83-NI-9590B |  | B | B | Incomplete floor tiling | EPS UNATRAC | PS5-01-02 - Fire Water Pump A |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-00153 | PS5-83-OB-4050A |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-09-03 - Motor Control Center |  | On Hold | Mohamed, Ali | PS5 - Milestone D | 3
PL-00154 | PS5-13-IK-3303B |  | I | I | Missing loop diagram | KENT | PS5-05-03 - CCTV System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00155 | PS5-93-NI-1187B |  | M | M | Coupling guard loose | KENT | PS5-60-04 - Power Generation Package B |  | In Progress | Wang, Li | PS5 - Milestone D | 3
PL-00156 | PS5-91-OB-2923C |  | I | I | Instrument tubing leak | KENT | PS5-01-08 - Drencher System |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00157 | PS5-54-NI-8714D |  | I | I | Missing instrument tag | EPS UNATRAC | PS5-07-03 - AHU System |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-00158 | PS5-08-NI-9281A |  | I | I | Control valve actuator fault | CPP AGI | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-00159 | PS5-12-NI-8298D |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-10-06 - Vent System |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-00160 | PS5-33-UR-4570C |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-00161 | PS5-53-IK-3218D |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-01-09 - Inergen for EITS Building |  | On Hold | Wang, Li | PS5 - Milestone I | 8
PL-00162 | PS5-85-NI-3178C |  | S | S | Eye wash station blocked | KENT | PS5-13-01 - Flare System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00163 | PS5-93-NI-7948C |  | H | H | Damper not operational | KENT | PS5-60-07 - Power Generation Package C | 2026-10-15 | Closed | Jean, Pierre | PS5 - Milestone I | 8
PL-00164 | PS5-31-IK-2102A |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-11-03 - Admin Building | 2026-12-25 | Closed | Smith, John | PS5 - Milestone C | 2
PL-00165 | PS5-18-NI-5739A |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-08-02 - Nitrogen Generator |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-00166 | PS5-53-OB-5508A |  | P | P | Missing pipe stress label | CPP AGI | PS5-10-06 - Vent System |  | In Progress | Wang, Li | PS5 - Milestone D | 3
PL-00167 | PS5-68-OB-7821B |  | H | H | Missing insulation on duct | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-00168 | PS5-60-UR-7761D |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-82-02 - Structural Steel B |  | On Hold | Kumar, Raj | PS5 - Milestone D | 3
PL-00169 | PS5-93-IK-1844B |  | H | H | Thermostat calibration needed | KENT | PS5-60-04 - Power Generation Package B | 2026-10-03 | Closed | Kumar, Raj | PS5 - Milestone D | 3
PL-00170 | PS5-39-UR-4470D |  | B | B | Incomplete paint touch-up | EPS UNATRAC | PS5-02-01 - Diesel Storage Tank |  | On Hold | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-00171 | PS5-49-NER-9743C |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-08-02 - Nitrogen Generator |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-00172 | PS5-27-OB-6126B |  | P | P | Missing pipe stress label | EPS UNATRAC | PS5-99-02 - Area Completion Process Area |  | Originated | Jean, Pierre | PS5 - Milestone H | 7
PL-00173 | PS5-43-IK-7223C |  | H | H | Damper not operational | CPP AGI | PS5-01-03 - Fire Water Pump B |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-00174 | PS5-46-IK-3293C |  | P | P | Insulation damaged | KENT | PS5-09-01 - Transformer 33kV/6.6kV |  | On Hold | Jean, Pierre | PS5 - Milestone H | 7
PL-00175 | PS5-18-IK-2113C |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-01-05 - Foam System |  | On Hold | Jean, Pierre | PS5 - Milestone B | 1.1
PL-00176 | PS5-01-NI-7739A |  | T | T | CCTV camera not focused | CPP AGI | PS5-13-01 - Flare System |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-00177 | PS5-13-NI-3439A |  | M | M | Vibration level exceeded | CPP AGI | PS5-10-01 - Main Pipe Rack |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-00178 | PS5-73-IK-4700B |  | M | M | Pump alignment required | EPS UNATRAC | PS5-12-01 - Cooling Tower |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-00179 | PS5-90-IK-2354B |  | B | B | Missing door closer | CPP AGI | PS5-02-03 - Fuel Gas System |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-00180 | PS5-73-NER-5441A |  | P | P | Flange bolt torque incomplete | KENT | PS5-03-01 - ESD System |  | On Hold | Wang, Li | PS5 - Milestone I | 8
PL-00181 | PS5-19-NER-2260B |  | M | M | Vibration level exceeded | KENT | PS5-01-05 - Foam System |  | On Hold | Jean, Pierre | PS5 - Milestone C | 2
PL-00182 | PS5-11-NI-6666A |  | S | S | Missing safety sign | KENT | PS5-11-01 - Guard Hut A |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-00183 | PS5-58-NER-4737B |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-11-02 - Guard Hut B |  | On Hold | Smith, John | PS5 - Milestone G | 6
PL-00184 | PS5-10-UR-5390A |  | H | H | Thermostat calibration needed | KENT | PS5-60-01 - Power Generation Package A |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-00185 | PS5-47-OB-2674A |  | H | H | Damper not operational | EPS UNATRAC | PS5-60-04 - Power Generation Package B |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-00186 | PS5-77-OB-7311A |  | T | T | PA speaker not tested | KENT | PS5-61-01 - 33kV Switchboard EITS Building |  | Originated | Smith, John | PS5 - Milestone B | 1.1
PL-00187 | PS5-19-UR-3739B |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-08-02 - Nitrogen Generator | 2026-10-09 | Closed | Mohamed, Ali | PS5 - Milestone I | 8
PL-00188 | PS5-59-UR-3219B |  | T | T | PA speaker not tested | CPP AGI | PS5-02-01 - Diesel Storage Tank | 2026-12-20 | Closed | Mohamed, Ali | PS5 - Milestone F | 5
PL-00189 | PS5-89-IK-8848B |  | S | S | Missing safety sign | KENT | PS5-11-01 - Guard Hut A |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-00190 | PS5-47-UR-4273C |  | M | M | Vibration level exceeded | EPS UNATRAC | PS5-99-01 - Area Completion Building Area |  | In Progress | Jean, Pierre | PS5 - Milestone D | 3
PL-00191 | PS5-53-NER-3280C |  | B | B | Incomplete floor tiling | CPP AGI | PS5-82-01 - Structural Steel A |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-00192 | PS5-65-NER-9907A |  | H | H | Missing insulation on duct | KENT | PS5-61-07 - 0.4kV Switchboard EITS Building |  | Originated | Wang, Li | PS5 - Milestone G | 6
PL-00193 | PS5-06-NI-7547D |  | E | E | Wrong cable glanding | KENT | PS5-03-02 - Fire & Gas Detection |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-00194 | PS5-76-NI-3469B |  | E | E | Cable tray not properly supported | KENT | PS5-01-02 - Fire Water Pump A | 2026-11-25 | Closed | Smith, John | PS5 - Milestone B | 1.1
PL-00195 | PS5-19-OB-6110B |  | E | E | Missing earth continuity label | KENT | PS5-10-02 - Utility Pipe Rack |  | On Hold | Kumar, Raj | PS5 - Milestone G | 6
PL-00196 | PS5-06-UR-1370D |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-11-03 - Admin Building |  | Originated | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00197 | PS5-81-IK-4053C |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-08-02 - Nitrogen Generator | 2026-11-08 | Closed | Smith, John | PS5 - Milestone I | 8
PL-00198 | PS5-27-OB-2025C |  | B | B | Cracked wall plaster | CPP AGI | PS5-06-03 - Lightning Protection |  | In Progress | Jean, Pierre | PS5 - Milestone H | 7
PL-00199 | PS5-68-OB-7367C |  | P | P | Missing pipe stress label | EPS UNATRAC | PS5-10-06 - Vent System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-00200 | PS5-87-IK-6131A |  | P | P | Valve handwheel stiff | CPP AGI | PS5-12-01 - Cooling Tower |  | In Progress | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00201 | PS5-50-NER-4043B |  | H | H | FCU drain pipe not connected | KENT | PS5-13-01 - Flare System |  | In Progress | Wang, Li | PS5 - Milestone C | 2
PL-00202 | PS5-02-NER-3236A |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-05-02 - PA/GA System | 2026-12-02 | Closed | Kumar, Raj | PS5 - Milestone H | 7
PL-00203 | PS5-73-UR-4613B |  | T | T | CAT6 cable untidied | CPP AGI | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone H | 7
PL-00204 | PS5-74-UR-5389D |  | M | M | Coupling guard loose | CPP AGI | PS5-05-02 - PA/GA System |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-00205 | PS5-58-OB-6711D |  | B | B | Missing fire extinguisher signage | CPP AGI | PS5-62-02 - Cable Tray Secondary | 2026-10-28 | Closed | Smith, John | PS5 - Milestone I | 8
PL-00206 | PS5-81-NER-3719C |  | E | E | Missing earth continuity label | KENT | PS5-08-01 - Compressor Air System |  | On Hold | Jean, Pierre | PS5 - Milestone D | 3
PL-00207 | PS5-66-UR-3221D |  | B | B | Missing door closer | EPS UNATRAC | PS5-11-03 - Admin Building | 2026-10-19 | Closed | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-00208 | PS5-81-OB-7786B |  | M | M | Pump alignment required | KENT | PS5-04-01 - DCS System | 2026-11-05 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-00209 | PS5-75-UR-2526C |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-60-10 - Power Generation Package D |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-00210 | PS5-35-OB-5646B |  | P | P | Missing pipe stress label | EPS UNATRAC | PS5-01-09 - Inergen for EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-00211 | PS5-57-NER-1011D |  | T | T | PA speaker not tested | CPP AGI | PS5-11-02 - Guard Hut B |  | Originated | Jean, Pierre | PS5 - Milestone A | 1
PL-00212 | PS5-33-UR-7092C |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-10-03 - Process piping A |  | On Hold | Jean, Pierre | PS5 - Milestone C | 2
PL-00213 | PS5-91-UR-1017A |  | B | B | Missing fire extinguisher signage | CPP AGI | PS5-60-07 - Power Generation Package C |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-00214 | PS5-89-IK-8826A |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-62-02 - Cable Tray Secondary |  | Originated | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-00215 | PS5-83-IK-2120C |  | E | E | Cable tray not properly supported | CPP AGI | PS5-03-02 - Fire & Gas Detection |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-00216 | PS5-57-IK-2420D |  | H | H | Damper not operational | KENT | PS5-62-02 - Cable Tray Secondary |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00217 | PS5-11-IK-5668D |  | S | S | Deluge valve not primed | KENT | PS5-11-03 - Admin Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00218 | PS5-83-UR-4921B |  | M | M | Pump alignment required | EPS UNATRAC | PS5-07-01 - Chiller System A |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-00219 | PS5-50-NI-7895B |  | T | T | Intercom not functioning | CPP AGI | PS5-02-01 - Diesel Storage Tank |  | On Hold | Jean, Pierre | PS5 - Milestone I | 8
PL-00220 | PS5-08-NER-9300B |  | T | T | Intercom not functioning | CPP AGI | PS5-02-01 - Diesel Storage Tank |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-00221 | PS5-11-NI-4329D |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building |  | Originated | Kumar, Raj | PS5 - Milestone G | 6
PL-00222 | PS5-08-IK-2412D |  | P | P | Flange bolt torque incomplete | CPP AGI | PS5-60-07 - Power Generation Package C |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-00223 | PS5-67-OB-3735B |  | B | B | Incomplete paint touch-up | KENT | PS5-10-04 - Process piping B | 2026-11-12 | Closed | Mohamed, Ali | PS5 - Milestone C | 2
PL-00224 | PS5-92-NI-2262B |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-01-04 - Fire Water Ring Main |  | On Hold | Mohamed, Ali | PS5 - Milestone F | 5
PL-00225 | PS5-87-UR-4742C |  | B | B | Missing fire extinguisher signage | KENT | PS5-99-02 - Area Completion Process Area |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00226 | PS5-71-NER-4678B |  | B | B | Missing door closer | CPP AGI | PS5-08-02 - Nitrogen Generator |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-00227 | PS5-23-IK-9450D |  | P | P | Insulation damaged | CPP AGI | PS5-09-03 - Motor Control Center |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00228 | PS5-38-NI-5979C |  | T | T | Missing cable label | CPP AGI | PS5-10-01 - Main Pipe Rack |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-00229 | PS5-04-IK-9872B |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-99-02 - Area Completion Process Area |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-00230 | PS5-31-NER-9061D |  | P | P | Pipe support missing | KENT | PS5-01-01 - Fire Water Jockey Pump A/B |  | On Hold | Wang, Li | PS5 - Milestone G | 6
PL-00231 | PS5-96-UR-2565C |  | M | M | Motor fan guard missing | EPS UNATRAC | PS5-02-03 - Fuel Gas System |  | On Hold | Smith, John | PS5 - Milestone A | 1
PL-00232 | PS5-41-NER-6345B |  | E | E | Wrong cable glanding | EPS UNATRAC | PS5-01-08 - Drencher System |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-00233 | PS5-58-NER-6145B |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-06-03 - Lightning Protection |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-00234 | PS5-39-NI-1660A |  | I | I | Instrument tubing leak | KENT | PS5-63-01 - Electrical Earthing |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-00235 | PS5-23-UR-7625D |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-08-02 - Nitrogen Generator |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-00236 | PS5-52-OB-2376C |  | I | I | Instrument tubing leak | CPP AGI | PS5-03-01 - ESD System | 2026-09-05 | Closed | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00237 | PS5-43-UR-1699D |  | B | B | Missing fire extinguisher signage | CPP AGI | PS5-01-09 - Inergen for EITS Building |  | On Hold | Jean, Pierre | PS5 - Milestone D | 3
PL-00238 | PS5-24-OB-5585B |  | S | S | Emergency shower not tested | CPP AGI | PS5-60-07 - Power Generation Package C |  | Originated | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00239 | PS5-50-IK-7868A |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-10-02 - Utility Pipe Rack |  | In Progress | Jean, Pierre | PS5 - Milestone H | 7
PL-00240 | PS5-42-NER-5430A |  | B | B | Damaged ceiling panel | KENT | PS5-60-01 - Power Generation Package A |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-00241 | PS5-30-IK-2640A |  | I | I | Missing loop diagram | KENT | PS5-01-04 - Fire Water Ring Main |  | Originated | Mohamed, Ali | PS5 - Milestone E | 4
PL-00242 | PS5-41-OB-1462C |  | B | B | Damaged ceiling panel | KENT | PS5-07-03 - AHU System |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-00243 | PS5-08-IK-4584A |  | H | H | AHU filter not installed | CPP AGI | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00244 | PS5-08-UR-3420C |  | P | P | Pipe support missing | EPS UNATRAC | PS5-06-03 - Lightning Protection |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00245 | PS5-39-OB-3235D |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-02-01 - Diesel Storage Tank |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-00246 | PS5-23-NER-6026C |  | T | T | CAT6 cable untidied | KENT | PS5-10-05 - Drain System |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-00247 | PS5-79-IK-2705D |  | H | H | Damper not operational | EPS UNATRAC | PS5-01-01 - Fire Water Jockey Pump A/B |  | On Hold | Mohamed, Ali | PS5 - Milestone G | 6
PL-00248 | PS5-86-OB-8317A |  | E | E | Missing earth continuity label | KENT | PS5-08-01 - Compressor Air System |  | On Hold | Jean, Pierre | PS5 - Milestone F | 5
PL-00249 | PS5-94-NER-3725D |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-11-03 - Admin Building |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-00250 | PS5-05-OB-1328B |  | P | P | Flange bolt torque incomplete | CPP AGI | PS5-60-01 - Power Generation Package A |  | On Hold | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00251 | PS5-91-UR-8066D |  | P | P | Pipe support missing | EPS UNATRAC | PS5-05-02 - PA/GA System | 2026-12-20 | Closed | Kumar, Raj | PS5 - Milestone G | 6
PL-00252 | PS5-13-UR-7437C |  | S | S | Missing safety sign | CPP AGI | PS5-05-01 - Telecom Network | 2026-10-10 | Closed | Jean, Pierre | PS5 - Milestone A | 1
PL-00253 | PS5-77-NER-4271A |  | B | B | Incomplete floor tiling | KENT | PS5-12-02 - Water Treatment |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-00254 | PS5-63-OB-2493C |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | On Hold | Jean, Pierre | PS5 - Milestone H | 7
PL-00255 | PS5-73-UR-3476D |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-60-01 - Power Generation Package A | 2026-10-08 | Closed | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00256 | PS5-67-NER-9773C |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-11-03 - Admin Building |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-00257 | PS5-74-NI-3415A |  | I | I | Pressure gauge reads zero | KENT | PS5-82-02 - Structural Steel B |  | Originated | Jean, Pierre | PS5 - Milestone E | 4
PL-00258 | PS5-19-NI-5225B |  | H | H | Thermostat calibration needed | KENT | PS5-07-02 - Chiller System B | 2026-09-27 | Closed | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-00259 | PS5-59-UR-9561D |  | E | E | Cable tray not properly supported | KENT | PS5-60-04 - Power Generation Package B |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-00260 | PS5-45-NER-5327B |  | H | H | AHU filter not installed | KENT | PS5-04-03 - 33kV ICSS System |  | On Hold | Kumar, Raj | PS5 - Milestone B | 1.1
PL-00261 | PS5-89-IK-1807C |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-01-05 - Foam System | 2026-08-13 | Closed | Mohamed, Ali | PS5 - Milestone C | 2
PL-00262 | PS5-13-IK-3201B |  | B | B | Incomplete paint touch-up | KENT | PS5-11-02 - Guard Hut B |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-00263 | PS5-53-NER-9462D |  | P | P | Flange bolt torque incomplete | CPP AGI | PS5-09-03 - Motor Control Center |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-00264 | PS5-73-UR-3846A |  | H | H | Damper not operational | KENT | PS5-01-09 - Inergen for EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-00265 | PS5-48-NER-9275B |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-01-05 - Foam System |  | Originated | Wang, Li | PS5 - Milestone H | 7
PL-00266 | PS5-76-NI-6730B |  | B | B | Damaged ceiling panel | EPS UNATRAC | PS5-08-01 - Compressor Air System |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-00267 | PS5-29-IK-4387B |  | E | E | Incomplete cable termination | CPP AGI | PS5-10-01 - Main Pipe Rack |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-00268 | PS5-29-OB-6004C |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-01-02 - Fire Water Pump A |  | On Hold | Wang, Li | PS5 - Milestone H | 7
PL-00269 | PS5-39-NI-7506C |  | M | M | Pump alignment required | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building |  | On Hold | Kumar, Raj | PS5 - Milestone G | 6
PL-00270 | PS5-82-OB-5536B |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-10-01 - Main Pipe Rack |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-00271 | PS5-52-OB-3292C |  | M | M | Motor fan guard missing | KENT | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-00272 | PS5-25-OB-4643C |  | M | M | Motor fan guard missing | KENT | PS5-09-02 - Transformer 6.6kV/0.4kV |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-00273 | PS5-17-OB-3999D |  | P | P | Valve handwheel stiff | EPS UNATRAC | PS5-99-03 - Area Completion Utilities Area |  | On Hold | Wang, Li | PS5 - Milestone E | 4
PL-00274 | PS5-38-NER-2929B |  | E | E | Outgoing breaker not labeled | KENT | PS5-07-03 - AHU System | 2026-10-09 | Closed | Kumar, Raj | PS5 - Milestone F | 5
PL-00275 | PS5-07-IK-3250D |  | E | E | Wrong cable glanding | EPS UNATRAC | PS5-82-02 - Structural Steel B |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-00276 | PS5-43-IK-6134C |  | T | T | Fiber patch panel unorganized | EPS UNATRAC | PS5-04-03 - 33kV ICSS System |  | On Hold | Smith, John | PS5 - Milestone F | 5
PL-00277 | PS5-17-NI-8105C |  | M | M | Bearing temperature high | CPP AGI | PS5-07-01 - Chiller System A |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-00278 | PS5-42-NI-4122A |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-60-04 - Power Generation Package B |  | Originated | Wang, Li | PS5 - Milestone A | 1
PL-00279 | PS5-40-IK-2069D |  | I | I | Instrument tubing leak | KENT | PS5-07-03 - AHU System |  | In Progress | Mohamed, Ali | PS5 - Milestone F | 5
PL-00280 | PS5-97-IK-3701D |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-11-02 - Guard Hut B |  | On Hold | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00281 | PS5-84-UR-7147D |  | I | I | Instrument tubing leak | KENT | PS5-07-03 - AHU System | 2026-08-12 | Closed | Kumar, Raj | PS5 - Milestone C | 2
PL-00282 | PS5-54-NER-7230A |  | B | B | Damaged ceiling panel | CPP AGI | PS5-01-07 - Hydrant System |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-00283 | PS5-80-NI-3247B |  | H | H | Duct leakage at joint | EPS UNATRAC | PS5-07-01 - Chiller System A |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-00284 | PS5-34-NI-4304B |  | E | E | Incomplete cable termination | CPP AGI | PS5-10-01 - Main Pipe Rack |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00285 | PS5-31-UR-1208C |  | H | H | Duct leakage at joint | EPS UNATRAC | PS5-01-06 - Deluge System |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-00286 | PS5-33-IK-8483D |  | T | T | CAT6 cable untidied | CPP AGI | PS5-04-04 - 33kV PCS System |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00287 | PS5-87-OB-7979C |  | T | T | Fiber patch panel unorganized | EPS UNATRAC | PS5-01-07 - Hydrant System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00288 | PS5-12-OB-6615A |  | B | B | Missing door closer | KENT | PS5-04-02 - SIS System |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-00289 | PS5-22-UR-3171C |  | T | T | Fiber patch panel unorganized | KENT | PS5-09-03 - Motor Control Center |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-00290 | PS5-46-NI-1472D |  | E | E | Outgoing breaker not labeled | EPS UNATRAC | PS5-61-02 - 6.6kV Switchboard LLHT North |  | On Hold | Jean, Pierre | PS5 - Milestone H | 7
PL-00291 | PS5-84-OB-1202C |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-99-01 - Area Completion Building Area |  | On Hold | Kumar, Raj | PS5 - Milestone B | 1.1
PL-00292 | PS5-32-NER-6664C |  | I | I | Missing instrument tag | KENT | PS5-11-02 - Guard Hut B |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-00293 | PS5-64-IK-2226D |  | H | H | Missing insulation on duct | EPS UNATRAC | PS5-01-07 - Hydrant System |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-00294 | PS5-11-NER-8277D |  | P | P | Insulation damaged | CPP AGI | PS5-09-04 - 0.4kV Switchboard |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-00295 | PS5-05-NI-9996A |  | T | T | Fiber patch panel unorganized | EPS UNATRAC | PS5-63-01 - Electrical Earthing | 2026-08-13 | Closed | Kumar, Raj | PS5 - Milestone F | 5
PL-00296 | PS5-59-OB-8751C |  | M | M | Coupling guard loose | CPP AGI | PS5-07-01 - Chiller System A |  | On Hold | Wang, Li | PS5 - Milestone H | 7
PL-00297 | PS5-82-OB-9973C |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-03-03 - Flame Detector System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00298 | PS5-28-NER-4122C |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-05-02 - PA/GA System | 2026-09-04 | Closed | Smith, John | PS5 - Milestone H | 7
PL-00299 | PS5-95-UR-8091D |  | B | B | Missing door closer | KENT | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-00300 | PS5-36-NER-6617D |  | H | H | AHU filter not installed | CPP AGI | PS5-05-03 - CCTV System | 2026-12-23 | Closed | Jean, Pierre | PS5 - Milestone C | 2
PL-00301 | PS5-92-OB-6657D |  | H | H | Damper not operational | KENT | PS5-61-01 - 33kV Switchboard EITS Building | 2026-09-07 | Closed | Wang, Li | PS5 - Milestone I | 8
PL-00302 | PS5-72-NER-7839C |  | H | H | FCU drain pipe not connected | EPS UNATRAC | PS5-99-03 - Area Completion Utilities Area |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-00303 | PS5-37-OB-3399D |  | S | S | Deluge valve not primed | CPP AGI | PS5-01-02 - Fire Water Pump A | 2026-09-09 | Closed | Mohamed, Ali | PS5 - Milestone I | 8
PL-00304 | PS5-95-NI-4675C |  | I | I | Control valve actuator fault | KENT | PS5-01-05 - Foam System |  | On Hold | Smith, John | PS5 - Milestone F | 5
PL-00305 | PS5-41-NI-1881A |  | I | I | Instrument tubing leak | KENT | PS5-10-01 - Main Pipe Rack |  | On Hold | Jean, Pierre | PS5 - Milestone A | 1
PL-00306 | PS5-38-NER-3906D |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-07-03 - AHU System |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-00307 | PS5-21-NI-5178A |  | H | H | AHU filter not installed | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | Originated | Wang, Li | PS5 - Milestone G | 6
PL-00308 | PS5-85-OB-9037D |  | H | H | FCU drain pipe not connected | KENT | PS5-01-06 - Deluge System |  | On Hold | Mohamed, Ali | PS5 - Milestone C | 2
PL-00309 | PS5-52-UR-6724A |  | E | E | Missing earth continuity label | KENT | PS5-10-05 - Drain System | 2026-11-18 | Closed | Wang, Li | PS5 - Milestone I | 8
PL-00310 | PS5-58-IK-4994D |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-11-01 - Guard Hut A | 2026-08-22 | Closed | Mohamed, Ali | PS5 - Milestone F | 5
PL-00311 | PS5-58-NER-1718B |  | S | S | Deluge valve not primed | KENT | PS5-03-03 - Flame Detector System | 2026-12-26 | Closed | Jean, Pierre | PS5 - Milestone G | 6
PL-00312 | PS5-55-UR-4368C |  | P | P | Gasket protruding from flange | KENT | PS5-02-02 - Diesel Transfer Pump | 2026-09-28 | Closed | Wang, Li | PS5 - Milestone B | 1.1
PL-00313 | PS5-07-IK-5127C |  | S | S | Fire alarm panel fault | CPP AGI | PS5-02-01 - Diesel Storage Tank |  | Originated | Jean, Pierre | PS5 - Milestone C | 2
PL-00314 | PS5-50-UR-9762A |  | M | M | Motor fan guard missing | CPP AGI | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-00315 | PS5-39-NI-2417B |  | E | E | Incomplete cable termination | KENT | PS5-01-06 - Deluge System |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-00316 | PS5-19-OB-7113D |  | S | S | Fire extinguisher expired | KENT | PS5-01-04 - Fire Water Ring Main | 2026-12-10 | Closed | Kumar, Raj | PS5 - Milestone H | 7
PL-00317 | PS5-40-IK-6633A |  | H | H | Thermostat calibration needed | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | Originated | Kumar, Raj | PS5 - Milestone A | 1
PL-00318 | PS5-97-NI-8557C |  | H | H | Duct leakage at joint | CPP AGI | PS5-05-01 - Telecom Network | 2026-12-28 | Closed | Mohamed, Ali | PS5 - Milestone C | 2
PL-00319 | PS5-80-UR-4170B |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-09-01 - Transformer 33kV/6.6kV | 2026-09-04 | Closed | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00320 | PS5-32-IK-8145B |  | M | M | Coupling guard loose | EPS UNATRAC | PS5-04-04 - 33kV PCS System |  | On Hold | Jean, Pierre | PS5 - Milestone F | 5
PL-00321 | PS5-23-NI-2343D |  | P | P | Pipe support missing | CPP AGI | PS5-82-07 - Guard Huts |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-00322 | PS5-04-NI-7637D |  | I | I | Missing loop diagram | KENT | PS5-09-02 - Transformer 6.6kV/0.4kV |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00323 | PS5-38-IK-8613C |  | M | M | Pump alignment required | KENT | PS5-82-02 - Structural Steel B |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-00324 | PS5-58-IK-3935C |  | P | P | Missing pipe stress label | CPP AGI | PS5-99-03 - Area Completion Utilities Area |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-00325 | PS5-48-IK-1701C |  | H | H | FCU drain pipe not connected | EPS UNATRAC | PS5-82-07 - Guard Huts |  | Originated | Mohamed, Ali | PS5 - Milestone F | 5
PL-00326 | PS5-91-NI-5480D |  | S | S | Eye wash station blocked | CPP AGI | PS5-82-02 - Structural Steel B |  | On Hold | Kumar, Raj | PS5 - Milestone H | 7
PL-00327 | PS5-29-NI-7649B |  | H | H | Missing insulation on duct | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-00328 | PS5-66-OB-4465A |  | T | T | Missing cable label | CPP AGI | PS5-01-01 - Fire Water Jockey Pump A/B |  | On Hold | Mohamed, Ali | PS5 - Milestone I | 8
PL-00329 | PS5-62-IK-3641C |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-07-04 - FCU System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00330 | PS5-06-NI-3406A |  | I | I | Instrument tubing leak | KENT | PS5-01-06 - Deluge System |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-00331 | PS5-62-IK-4594D |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-01-03 - Fire Water Pump B |  | On Hold | Jean, Pierre | PS5 - Milestone E | 4
PL-00332 | PS5-09-IK-7196B |  | H | H | Duct leakage at joint | KENT | PS5-09-02 - Transformer 6.6kV/0.4kV |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00333 | PS5-77-UR-9706C |  | I | I | Transmitter not calibrated | KENT | PS5-99-03 - Area Completion Utilities Area |  | On Hold | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00334 | PS5-06-NI-8028A |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-04-01 - DCS System |  | On Hold | Smith, John | PS5 - Milestone I | 8
PL-00335 | PS5-53-OB-4096A |  | P | P | Gasket protruding from flange | KENT | PS5-03-01 - ESD System | 2026-10-20 | Closed | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00336 | PS5-20-NER-5155B |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-00337 | PS5-62-IK-7065C |  | P | P | Insulation damaged | KENT | PS5-09-04 - 0.4kV Switchboard |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-00338 | PS5-90-IK-2642A |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-11-03 - Admin Building |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-00339 | PS5-61-NI-8133A |  | B | B | Damaged ceiling panel | CPP AGI | PS5-05-01 - Telecom Network |  | On Hold | Jean, Pierre | PS5 - Milestone G | 6
PL-00340 | PS5-37-NI-1941D |  | P | P | Pipe support missing | KENT | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-00341 | PS5-05-OB-4919C |  | T | T | Missing cable label | KENT | PS5-62-02 - Cable Tray Secondary | 2026-12-06 | Closed | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-00342 | PS5-02-UR-2477C |  | M | M | Motor fan guard missing | KENT | PS5-60-10 - Power Generation Package D |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-00343 | PS5-65-UR-2185C |  | P | P | Valve handwheel stiff | EPS UNATRAC | PS5-11-03 - Admin Building | 2026-10-06 | Closed | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-00344 | PS5-59-NER-1448B |  | M | M | Coupling guard loose | EPS UNATRAC | PS5-09-01 - Transformer 33kV/6.6kV |  | On Hold | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00345 | PS5-02-OB-5067B |  | S | S | Missing safety sign | KENT | PS5-07-03 - AHU System |  | On Hold | Wang, Li | PS5 - Milestone D | 3
PL-00346 | PS5-74-OB-3994D |  | P | P | Gasket protruding from flange | CPP AGI | PS5-02-01 - Diesel Storage Tank |  | On Hold | Jean, Pierre | PS5 - Milestone I | 8
PL-00347 | PS5-32-NI-6833A |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-06-03 - Lightning Protection |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-00348 | PS5-80-OB-9066D |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-99-02 - Area Completion Process Area |  | In Progress | Mohamed, Ali | PS5 - Milestone A | 1
PL-00349 | PS5-62-NI-1533C |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-06-01 - AC UPS - EITS Building | 2026-08-17 | Closed | Wang, Li | PS5 - Milestone I | 8
PL-00350 | PS5-02-IK-7216C |  | H | H | Missing insulation on duct | CPP AGI | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00351 | PS5-55-IK-7866C |  | M | M | Coupling guard loose | EPS UNATRAC | PS5-06-01 - AC UPS - EITS Building | 2026-10-06 | Closed | Mohamed, Ali | PS5 - Milestone I | 8
PL-00352 | PS5-31-NI-8081D |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-09-04 - 0.4kV Switchboard | 2026-08-24 | Closed | Jean, Pierre | PS5 - Milestone H | 7
PL-00353 | PS5-72-NI-1781B |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-82-02 - Structural Steel B | 2026-11-10 | Closed | Jean, Pierre | PS5 - Milestone A | 1
PL-00354 | PS5-34-OB-6903C |  | B | B | Damaged ceiling panel | EPS UNATRAC | PS5-07-02 - Chiller System B |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-00355 | PS5-84-NI-3859D |  | B | B | Damaged ceiling panel | KENT | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00356 | PS5-81-IK-3745C |  | P | P | Valve handwheel stiff | EPS UNATRAC | PS5-99-01 - Area Completion Building Area |  | On Hold | Smith, John | PS5 - Milestone H | 7
PL-00357 | PS5-51-OB-8289D |  | S | S | Eye wash station blocked | KENT | PS5-02-01 - Diesel Storage Tank | 2026-10-20 | Closed | Wang, Li | PS5 - Milestone B | 1.1
PL-00358 | PS5-96-UR-4450A |  | T | T | Fiber patch panel unorganized | KENT | PS5-61-01 - 33kV Switchboard EITS Building | 2026-10-24 | Closed | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00359 | PS5-14-OB-3544A |  | E | E | Incomplete cable termination | CPP AGI | PS5-82-02 - Structural Steel B |  | Originated | Mohamed, Ali | PS5 - Milestone I | 8
PL-00360 | PS5-04-UR-6846D |  | I | I | Instrument tubing leak | CPP AGI | PS5-08-02 - Nitrogen Generator |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-00361 | PS5-81-NI-8126C |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-09-03 - Motor Control Center |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-00362 | PS5-53-OB-3551B |  | M | M | Pump alignment required | EPS UNATRAC | PS5-11-03 - Admin Building |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-00363 | PS5-39-UR-8052D |  | H | H | FCU drain pipe not connected | EPS UNATRAC | PS5-11-03 - Admin Building |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-00364 | PS5-92-NER-7199A |  | B | B | Missing fire extinguisher signage | CPP AGI | PS5-13-01 - Flare System |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-00365 | PS5-24-IK-5744A |  | I | I | Pressure gauge reads zero | CPP AGI | PS5-09-03 - Motor Control Center |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-00366 | PS5-35-IK-8183C |  | T | T | Missing cable label | EPS UNATRAC | PS5-09-03 - Motor Control Center | 2026-09-04 | Closed | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00367 | PS5-05-OB-2314D |  | H | H | Damper not operational | KENT | PS5-01-02 - Fire Water Pump A | 2026-10-15 | Closed | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00368 | PS5-49-UR-2998D |  | M | M | Motor fan guard missing | EPS UNATRAC | PS5-60-07 - Power Generation Package C |  | In Progress | Jean, Pierre | PS5 - Milestone B | 1.1
PL-00369 | PS5-99-UR-9538C |  | S | S | Emergency shower not tested | KENT | PS5-62-02 - Cable Tray Secondary |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-00370 | PS5-39-IK-6905D |  | S | S | Deluge valve not primed | KENT | PS5-10-04 - Process piping B | 2026-10-16 | Closed | Jean, Pierre | PS5 - Milestone F | 5
PL-00371 | PS5-16-NER-4982A |  | E | E | Cable tray not properly supported | KENT | PS5-08-01 - Compressor Air System |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-00372 | PS5-88-NI-6544D |  | T | T | Intercom not functioning | CPP AGI | PS5-04-04 - 33kV PCS System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00373 | PS5-41-NI-6690D |  | B | B | Missing door closer | CPP AGI | PS5-12-01 - Cooling Tower |  | In Progress | Wang, Li | PS5 - Milestone C | 2
PL-00374 | PS5-91-NER-5828C |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-01-03 - Fire Water Pump B |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-00375 | PS5-71-IK-2128C |  | H | H | AHU filter not installed | KENT | PS5-11-03 - Admin Building |  | In Progress | Mohamed, Ali | PS5 - Milestone F | 5
PL-00376 | PS5-80-OB-4912B |  | M | M | Pump alignment required | CPP AGI | PS5-12-02 - Water Treatment |  | Originated | Wang, Li | PS5 - Milestone H | 7
PL-00377 | PS5-53-OB-2809A |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-00378 | PS5-13-UR-7366C |  | B | B | Cracked wall plaster | CPP AGI | PS5-04-01 - DCS System |  | On Hold | Kumar, Raj | PS5 - Milestone C | 2
PL-00379 | PS5-08-OB-7814D |  | M | M | Motor fan guard missing | KENT | PS5-01-07 - Hydrant System | 2026-08-15 | Closed | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00380 | PS5-13-IK-9710B |  | M | M | Missing rotation arrow | CPP AGI | PS5-01-06 - Deluge System |  | On Hold | Kumar, Raj | PS5 - Milestone B | 1.1
PL-00381 | PS5-74-OB-8515C |  | I | I | Pressure gauge reads zero | KENT | PS5-05-03 - CCTV System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-00382 | PS5-77-NER-6772D |  | H | H | FCU drain pipe not connected | KENT | PS5-06-01 - AC UPS - EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-00383 | PS5-70-IK-7145D |  | P | P | Gasket protruding from flange | KENT | PS5-61-01 - 33kV Switchboard EITS Building |  | On Hold | Mohamed, Ali | PS5 - Milestone G | 6
PL-00384 | PS5-77-UR-9480A |  | P | P | Valve handwheel stiff | EPS UNATRAC | PS5-63-01 - Electrical Earthing |  | On Hold | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00385 | PS5-36-NI-9376C |  | M | M | Vibration level exceeded | KENT | PS5-07-03 - AHU System |  | On Hold | Jean, Pierre | PS5 - Milestone D | 3
PL-00386 | PS5-32-IK-5198D |  | E | E | Cable tray not properly supported | KENT | PS5-01-05 - Foam System |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-00387 | PS5-90-NI-2562C |  | S | S | Eye wash station blocked | KENT | PS5-07-02 - Chiller System B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00388 | PS5-54-UR-4714C |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | On Hold | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-00389 | PS5-42-NI-4617A |  | S | S | Deluge valve not primed | CPP AGI | PS5-01-07 - Hydrant System |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-00390 | PS5-19-IK-6507A |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-63-01 - Electrical Earthing |  | Originated | Wang, Li | PS5 - Milestone I | 8
PL-00391 | PS5-98-IK-8879C |  | B | B | Missing door closer | CPP AGI | PS5-60-10 - Power Generation Package D |  | Originated | Smith, John | PS5 - Milestone E | 4
PL-00392 | PS5-12-UR-7776B |  | I | I | Instrument tubing leak | KENT | PS5-08-02 - Nitrogen Generator |  | Originated | Jean, Pierre | PS5 - Milestone D | 3
PL-00393 | PS5-80-IK-8216A |  | P | P | Pipe support missing | EPS UNATRAC | PS5-11-03 - Admin Building |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-00394 | PS5-89-UR-5999B |  | P | P | Flange bolt torque incomplete | EPS UNATRAC | PS5-04-04 - 33kV PCS System | 2026-10-01 | Closed | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00395 | PS5-94-IK-1301B |  | I | I | Missing instrument tag | KENT | PS5-07-02 - Chiller System B |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-00396 | PS5-35-UR-8617C |  | B | B | Missing fire extinguisher signage | KENT | PS5-09-01 - Transformer 33kV/6.6kV |  | Originated | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00397 | PS5-50-IK-7237C |  | S | S | Deluge valve not primed | KENT | PS5-09-03 - Motor Control Center |  | On Hold | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00398 | PS5-92-UR-1651A |  | P | P | Missing pipe stress label | KENT | PS5-99-01 - Area Completion Building Area |  | Originated | Mohamed, Ali | PS5 - Milestone I | 8
PL-00399 | PS5-46-OB-4869D |  | P | P | Missing pipe stress label | EPS UNATRAC | PS5-99-01 - Area Completion Building Area |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-00400 | PS5-20-OB-7436C |  | B | B | Missing fire extinguisher signage | CPP AGI | PS5-09-01 - Transformer 33kV/6.6kV |  | On Hold | Wang, Li | PS5 - Milestone G | 6
PL-00401 | PS5-27-IK-9869C |  | S | S | Emergency shower not tested | CPP AGI | PS5-07-04 - FCU System | 2026-11-18 | Closed | Jean, Pierre | PS5 - Milestone G | 6
PL-00402 | PS5-41-UR-9732D |  | M | M | Pump alignment required | CPP AGI | PS5-04-02 - SIS System |  | On Hold | Jean, Pierre | PS5 - Milestone G | 6
PL-00403 | PS5-96-OB-3489D |  | P | P | Flange bolt torque incomplete | EPS UNATRAC | PS5-04-03 - 33kV ICSS System |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-00404 | PS5-88-UR-6886A |  | H | H | AHU filter not installed | CPP AGI | PS5-01-04 - Fire Water Ring Main |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-00405 | PS5-25-IK-1528B |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-13-01 - Flare System |  | On Hold | Mohamed, Ali | PS5 - Milestone C | 2
PL-00406 | PS5-63-OB-8496D |  | S | S | Missing safety sign | KENT | PS5-07-03 - AHU System |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-00407 | PS5-59-UR-5025C |  | B | B | Missing door closer | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-00408 | PS5-51-OB-5684B |  | B | B | Missing door closer | EPS UNATRAC | PS5-60-04 - Power Generation Package B |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-00409 | PS5-15-IK-9952A |  | B | B | Missing door closer | KENT | PS5-04-03 - 33kV ICSS System |  | On Hold | Mohamed, Ali | PS5 - Milestone H | 7
PL-00410 | PS5-42-IK-3024A |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-01-04 - Fire Water Ring Main |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-00411 | PS5-06-IK-6491C |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-00412 | PS5-94-NER-5731C |  | H | H | Duct leakage at joint | EPS UNATRAC | PS5-04-03 - 33kV ICSS System |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-00413 | PS5-01-NI-9084A |  | I | I | Control valve actuator fault | KENT | PS5-01-01 - Fire Water Jockey Pump A/B |  | Originated | Wang, Li | PS5 - Milestone E | 4
PL-00414 | PS5-80-NI-4401A |  | T | T | Missing cable label | EPS UNATRAC | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00415 | PS5-14-NER-3920A |  | P | P | Valve handwheel stiff | CPP AGI | PS5-01-05 - Foam System |  | On Hold | Kumar, Raj | PS5 - Milestone C | 2
PL-00416 | PS5-48-NER-2108D |  | H | H | FCU drain pipe not connected | EPS UNATRAC | PS5-63-04 - Electrical Earthing EITS Building |  | On Hold | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00417 | PS5-27-NI-1953A |  | M | M | Motor fan guard missing | KENT | PS5-82-02 - Structural Steel B | 2026-12-07 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-00418 | PS5-80-OB-3125C |  | E | E | Incomplete cable termination | KENT | PS5-82-07 - Guard Huts |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-00419 | PS5-01-UR-1392B |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-99-02 - Area Completion Process Area |  | On Hold | Wang, Li | PS5 - Milestone C | 2
PL-00420 | PS5-28-UR-4296C |  | I | I | Instrument tubing leak | KENT | PS5-61-02 - 6.6kV Switchboard LLHT North |  | Originated | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00421 | PS5-44-NER-1477D |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-10-03 - Process piping A |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-00422 | PS5-59-NI-6490B |  | P | P | Insulation damaged | KENT | PS5-82-07 - Guard Huts |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-00423 | PS5-43-OB-2084D |  | B | B | Damaged ceiling panel | KENT | PS5-10-03 - Process piping A |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00424 | PS5-97-OB-6152C |  | P | P | Valve handwheel stiff | CPP AGI | PS5-60-01 - Power Generation Package A |  | On Hold | Smith, John | PS5 - Milestone I | 8
PL-00425 | PS5-23-UR-7131D |  | E | E | Missing earth continuity label | EPS UNATRAC | PS5-99-02 - Area Completion Process Area |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-00426 | PS5-94-NI-6084D |  | T | T | Missing cable label | EPS UNATRAC | PS5-99-03 - Area Completion Utilities Area |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-00427 | PS5-88-NI-2426B |  | H | H | Duct leakage at joint | CPP AGI | PS5-07-01 - Chiller System A |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-00428 | PS5-37-OB-9720B |  | M | M | Bearing temperature high | CPP AGI | PS5-01-03 - Fire Water Pump B |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-00429 | PS5-71-OB-5440A |  | E | E | Outgoing breaker not labeled | EPS UNATRAC | PS5-09-03 - Motor Control Center | 2026-09-18 | Closed | Mohamed, Ali | PS5 - Milestone C | 2
PL-00430 | PS5-17-UR-8712D |  | I | I | Transmitter not calibrated | CPP AGI | PS5-05-02 - PA/GA System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00431 | PS5-81-NER-6826B |  | S | S | Emergency shower not tested | KENT | PS5-01-07 - Hydrant System |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-00432 | PS5-88-NER-8709A |  | E | E | Missing earth continuity label | EPS UNATRAC | PS5-82-01 - Structural Steel A |  | Originated | Jean, Pierre | PS5 - Milestone C | 2
PL-00433 | PS5-09-NER-2849B |  | M | M | Bearing temperature high | CPP AGI | PS5-12-02 - Water Treatment | 2026-11-16 | Closed | Jean, Pierre | PS5 - Milestone G | 6
PL-00434 | PS5-42-NI-2162D |  | M | M | Vibration level exceeded | CPP AGI | PS5-11-03 - Admin Building |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-00435 | PS5-44-IK-8063D |  | S | S | Missing safety sign | CPP AGI | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-00436 | PS5-63-UR-8584B |  | P | P | Flange bolt torque incomplete | KENT | PS5-08-01 - Compressor Air System |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-00437 | PS5-99-NER-6364B |  | H | H | Thermostat calibration needed | KENT | PS5-10-04 - Process piping B |  | Originated | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00438 | PS5-20-NER-9704B |  | E | E | Missing electrical hazard sign | KENT | PS5-07-02 - Chiller System B |  | On Hold | Kumar, Raj | PS5 - Milestone C | 2
PL-00439 | PS5-39-NER-6640D |  | T | T | CCTV camera not focused | KENT | PS5-06-03 - Lightning Protection |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-00440 | PS5-46-UR-5623D |  | S | S | Emergency shower not tested | KENT | PS5-04-01 - DCS System |  | Originated | Smith, John | PS5 - Milestone E | 4
PL-00441 | PS5-23-NER-3278A |  | S | S | Missing safety sign | KENT | PS5-10-05 - Drain System |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-00442 | PS5-83-UR-3359C |  | S | S | Missing safety sign | CPP AGI | PS5-04-04 - 33kV PCS System |  | On Hold | Wang, Li | PS5 - Milestone E | 4
PL-00443 | PS5-66-NER-8373B |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-04-02 - SIS System | 2026-12-06 | Closed | Jean, Pierre | PS5 - Milestone B | 1.1
PL-00444 | PS5-53-NI-7012A |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-01-01 - Fire Water Jockey Pump A/B |  | On Hold | Kumar, Raj | PS5 - Milestone H | 7
PL-00445 | PS5-68-OB-8617C |  | T | T | CCTV camera not focused | KENT | PS5-13-01 - Flare System |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-00446 | PS5-75-OB-1864D |  | E | E | Missing electrical hazard sign | KENT | PS5-08-02 - Nitrogen Generator |  | In Progress | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00447 | PS5-38-IK-1578C |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-63-04 - Electrical Earthing EITS Building |  | On Hold | Wang, Li | PS5 - Milestone I | 8
PL-00448 | PS5-38-NI-1447B |  | M | M | Pump alignment required | KENT | PS5-09-02 - Transformer 6.6kV/0.4kV |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-00449 | PS5-78-IK-3476C |  | E | E | Wrong cable glanding | CPP AGI | PS5-09-04 - 0.4kV Switchboard | 2026-08-24 | Closed | Jean, Pierre | PS5 - Milestone E | 4
PL-00450 | PS5-64-NER-7277A |  | M | M | Bearing temperature high | CPP AGI | PS5-08-01 - Compressor Air System | 2026-12-27 | Closed | Wang, Li | PS5 - Milestone H | 7
PL-00451 | PS5-07-IK-8602B |  | H | H | Missing insulation on duct | CPP AGI | PS5-07-01 - Chiller System A |  | Originated | Smith, John | PS5 - Milestone F | 5
PL-00452 | PS5-02-OB-8353B |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-00453 | PS5-43-OB-5375D |  | B | B | Damaged ceiling panel | EPS UNATRAC | PS5-03-01 - ESD System |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-00454 | PS5-89-IK-6132C |  | S | S | Deluge valve not primed | KENT | PS5-82-01 - Structural Steel A |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-00455 | PS5-29-OB-5127A |  | E | E | Cable tray not properly supported | EPS UNATRAC | PS5-01-02 - Fire Water Pump A |  | Originated | Kumar, Raj | PS5 - Milestone G | 6
PL-00456 | PS5-78-IK-7159C |  | E | E | Outgoing breaker not labeled | CPP AGI | PS5-01-08 - Drencher System |  | On Hold | Kumar, Raj | PS5 - Milestone D | 3
PL-00457 | PS5-89-OB-5216A |  | H | H | Duct leakage at joint | EPS UNATRAC | PS5-03-03 - Flame Detector System | 2026-10-25 | Closed | Mohamed, Ali | PS5 - Milestone C | 2
PL-00458 | PS5-23-NER-2137B |  | B | B | Incomplete floor tiling | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-00459 | PS5-14-UR-2194A |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-05-03 - CCTV System | 2026-11-23 | Closed | Mohamed, Ali | PS5 - Milestone H | 7
PL-00460 | PS5-43-NER-1060C |  | T | T | PA speaker not tested | KENT | PS5-01-03 - Fire Water Pump B | 2026-10-05 | Closed | Smith, John | PS5 - Milestone H | 7
PL-00461 | PS5-16-NI-9770D |  | S | S | Eye wash station blocked | EPS UNATRAC | PS5-60-10 - Power Generation Package D |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00462 | PS5-11-NER-5750C |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-60-10 - Power Generation Package D |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-00463 | PS5-57-IK-3292A |  | B | B | Missing fire extinguisher signage | KENT | PS5-60-04 - Power Generation Package B | 2026-11-03 | Closed | Wang, Li | PS5 - Milestone D | 3
PL-00464 | PS5-03-UR-6558A |  | I | I | Missing instrument tag | EPS UNATRAC | PS5-99-01 - Area Completion Building Area |  | Originated | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00465 | PS5-20-NI-4817D |  | S | S | Fire extinguisher expired | KENT | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | On Hold | Wang, Li | PS5 - Milestone D | 3
PL-00466 | PS5-17-UR-3822C |  | H | H | Missing insulation on duct | KENT | PS5-99-01 - Area Completion Building Area |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-00467 | PS5-79-IK-2033D |  | T | T | PA speaker not tested | KENT | PS5-05-02 - PA/GA System |  | On Hold | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00468 | PS5-98-UR-3841B |  | S | S | Fire extinguisher expired | CPP AGI | PS5-10-06 - Vent System |  | On Hold | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00469 | PS5-06-IK-2637D |  | H | H | Thermostat calibration needed | KENT | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Kumar, Raj | PS5 - Milestone C | 2
PL-00470 | PS5-12-NI-5648B |  | S | S | Missing safety sign | CPP AGI | PS5-05-01 - Telecom Network |  | On Hold | Wang, Li | PS5 - Milestone A | 1
PL-00471 | PS5-79-UR-3949C |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-07-01 - Chiller System A |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00472 | PS5-13-NI-6929D |  | M | M | Vibration level exceeded | KENT | PS5-11-03 - Admin Building |  | Originated | Kumar, Raj | PS5 - Milestone G | 6
PL-00473 | PS5-21-UR-1885C |  | I | I | Instrument tubing leak | CPP AGI | PS5-82-01 - Structural Steel A | 2026-11-16 | Closed | Jean, Pierre | PS5 - Milestone D | 3
PL-00474 | PS5-07-NI-3881A |  | S | S | Fire extinguisher expired | KENT | PS5-09-01 - Transformer 33kV/6.6kV |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-00475 | PS5-87-OB-4769D |  | E | E | Wrong cable glanding | KENT | PS5-02-01 - Diesel Storage Tank |  | In Progress | Jean, Pierre | PS5 - Milestone D | 3
PL-00476 | PS5-75-NER-1890D |  | E | E | Missing earth continuity label | EPS UNATRAC | PS5-08-01 - Compressor Air System |  | On Hold | Jean, Pierre | PS5 - Milestone G | 6
PL-00477 | PS5-46-OB-4313B |  | T | T | Fiber patch panel unorganized | KENT | PS5-05-03 - CCTV System |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-00478 | PS5-78-IK-3784C |  | B | B | Cracked wall plaster | EPS UNATRAC | PS5-09-04 - 0.4kV Switchboard | 2026-10-08 | Closed | Jean, Pierre | PS5 - Milestone C | 2
PL-00479 | PS5-36-UR-8014C |  | E | E | Missing earth continuity label | EPS UNATRAC | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-00480 | PS5-06-UR-8711C |  | P | P | Missing pipe stress label | EPS UNATRAC | PS5-62-01 - Cable Tray Main |  | On Hold | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-00481 | PS5-11-NI-1203C |  | S | S | Missing safety sign | CPP AGI | PS5-60-07 - Power Generation Package C |  | On Hold | Jean, Pierre | PS5 - Milestone H | 7
PL-00482 | PS5-74-NI-1399D |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-12-01 - Cooling Tower | 2026-09-23 | Closed | Jean, Pierre | PS5 - Milestone E | 4
PL-00483 | PS5-50-OB-9698A |  | S | S | Missing safety sign | CPP AGI | PS5-06-01 - AC UPS - EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone F | 5
PL-00484 | PS5-07-UR-7274B |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00485 | PS5-18-OB-4909C |  | P | P | Gasket protruding from flange | CPP AGI | PS5-12-02 - Water Treatment |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-00486 | PS5-36-UR-2038B |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-07-03 - AHU System |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-00487 | PS5-87-UR-4085D |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-82-02 - Structural Steel B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-00488 | PS5-64-IK-4346C |  | E | E | Outgoing breaker not labeled | CPP AGI | PS5-60-07 - Power Generation Package C | 2026-08-23 | Closed | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00489 | PS5-95-UR-5776A |  | M | M | Pump alignment required | EPS UNATRAC | PS5-61-02 - 6.6kV Switchboard LLHT North |  | On Hold | Jean, Pierre | PS5 - Milestone I | 8
PL-00490 | PS5-90-NI-9986B |  | P | P | Valve handwheel stiff | KENT | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-00491 | PS5-99-UR-3430B |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-10-04 - Process piping B |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-00492 | PS5-06-OB-3072B |  | H | H | Missing insulation on duct | CPP AGI | PS5-10-01 - Main Pipe Rack |  | On Hold | Jean, Pierre | PS5 - Milestone C | 2
PL-00493 | PS5-21-NI-5940A |  | I | I | Transmitter not calibrated | KENT | PS5-01-05 - Foam System |  | On Hold | Smith, John | PS5 - Milestone F | 5
PL-00494 | PS5-65-OB-5842B |  | T | T | CAT6 cable untidied | KENT | PS5-04-03 - 33kV ICSS System |  | On Hold | Kumar, Raj | PS5 - Milestone H | 7
PL-00495 | PS5-71-UR-6047A |  | H | H | FCU drain pipe not connected | KENT | PS5-62-02 - Cable Tray Secondary |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-00496 | PS5-99-OB-4206A |  | T | T | CCTV camera not focused | CPP AGI | PS5-12-01 - Cooling Tower |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-00497 | PS5-19-NER-7056B |  | E | E | Cable tray not properly supported | EPS UNATRAC | PS5-60-07 - Power Generation Package C |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-00498 | PS5-95-NER-8249B |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-11-03 - Admin Building |  | On Hold | Smith, John | PS5 - Milestone E | 4
PL-00499 | PS5-12-UR-7708C |  | S | S | Eye wash station blocked | EPS UNATRAC | PS5-04-02 - SIS System | 2026-08-19 | Closed | Smith, John | PS5 - Milestone B | 1.1
PL-00500 | PS5-75-OB-9095C |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-82-01 - Structural Steel A | 2026-08-27 | Closed | Jean, Pierre | PS5 - Milestone C | 2
PL-00501 | PS5-89-IK-1466A |  | B | B | Damaged ceiling panel | EPS UNATRAC | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-11-06 | Closed | Smith, John | PS5 - Milestone C | 2
PL-00502 | PS5-89-UR-7114C |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-12-02 - Water Treatment |  | In Progress | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00503 | PS5-47-NER-6832A |  | M | M | Coupling guard loose | EPS UNATRAC | PS5-05-01 - Telecom Network | 2026-09-02 | Closed | Kumar, Raj | PS5 - Milestone A | 1
PL-00504 | PS5-88-OB-5447C |  | E | E | Outgoing breaker not labeled | EPS UNATRAC | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-00505 | PS5-53-OB-3671A |  | E | E | Missing earth continuity label | EPS UNATRAC | PS5-12-01 - Cooling Tower |  | Originated | Kumar, Raj | PS5 - Milestone C | 2
PL-00506 | PS5-15-IK-1284B |  | I | I | Instrument tubing leak | CPP AGI | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-00507 | PS5-04-UR-4643A |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-04-02 - SIS System |  | On Hold | Jean, Pierre | PS5 - Milestone H | 7
PL-00508 | PS5-97-NER-1696A |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-10-04 - Process piping B | 2026-08-01 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-00509 | PS5-02-UR-3028D |  | B | B | Incomplete floor tiling | KENT | PS5-82-02 - Structural Steel B |  | On Hold | Kumar, Raj | PS5 - Milestone B | 1.1
PL-00510 | PS5-75-OB-6770A |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-06-01 - AC UPS - EITS Building |  | Originated | Wang, Li | PS5 - Milestone F | 5
PL-00511 | PS5-25-OB-3814D |  | I | I | Control valve actuator fault | KENT | PS5-99-03 - Area Completion Utilities Area |  | Originated | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00512 | PS5-24-NER-2758A |  | E | E | Wrong cable glanding | KENT | PS5-07-02 - Chiller System B |  | On Hold | Smith, John | PS5 - Milestone I | 8
PL-00513 | PS5-18-NER-6918C |  | S | S | Fire alarm panel fault | KENT | PS5-07-02 - Chiller System B | 2026-11-04 | Closed | Wang, Li | PS5 - Milestone I | 8
PL-00514 | PS5-95-OB-8273A |  | B | B | Missing door closer | KENT | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Mohamed, Ali | PS5 - Milestone F | 5
PL-00515 | PS5-02-NER-2723B |  | S | S | Fire alarm panel fault | CPP AGI | PS5-06-02 - DC UPS - EITS Building |  | On Hold | Wang, Li | PS5 - Milestone B | 1.1
PL-00516 | PS5-47-IK-6548A |  | E | E | Incomplete cable termination | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00517 | PS5-78-NER-8938C |  | I | I | Missing loop diagram | KENT | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-10-16 | Closed | Smith, John | PS5 - Milestone H | 7
PL-00518 | PS5-13-UR-2117B |  | E | E | Cable tray not properly supported | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-00519 | PS5-97-NI-9064D |  | S | S | Emergency shower not tested | KENT | PS5-10-06 - Vent System |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-00520 | PS5-50-NER-6153D |  | T | T | PA speaker not tested | CPP AGI | PS5-99-01 - Area Completion Building Area | 2026-08-14 | Closed | Smith, John | PS5 - Milestone I | 8
PL-00521 | PS5-56-IK-6119C |  | B | B | Missing door closer | EPS UNATRAC | PS5-01-05 - Foam System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00522 | PS5-34-NER-7189C |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-82-02 - Structural Steel B |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-00523 | PS5-95-NI-1440D |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-01-08 - Drencher System |  | In Progress | Mohamed, Ali | PS5 - Milestone A | 1
PL-00524 | PS5-85-IK-5056A |  | S | S | Eye wash station blocked | CPP AGI | PS5-03-01 - ESD System |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-00525 | PS5-55-NI-9433D |  | E | E | Wrong cable glanding | KENT | PS5-01-09 - Inergen for EITS Building | 2026-08-15 | Closed | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-00526 | PS5-63-UR-4373B |  | T | T | CCTV camera not focused | CPP AGI | PS5-01-03 - Fire Water Pump B |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-00527 | PS5-10-NI-4507B |  | P | P | Flange bolt torque incomplete | KENT | PS5-05-02 - PA/GA System |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-00528 | PS5-09-NI-9700B |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-07-03 - AHU System |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00529 | PS5-26-NER-7591B |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-10-03 - Process piping A |  | On Hold | Smith, John | PS5 - Milestone I | 8
PL-00530 | PS5-60-OB-9728D |  | H | H | AHU filter not installed | KENT | PS5-01-03 - Fire Water Pump B |  | On Hold | Kumar, Raj | PS5 - Milestone I | 8
PL-00531 | PS5-98-OB-8133B |  | B | B | Missing fire extinguisher signage | KENT | PS5-06-03 - Lightning Protection |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-00532 | PS5-31-NER-4907A |  | I | I | Missing loop diagram | KENT | PS5-61-01 - 33kV Switchboard EITS Building |  | On Hold | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-00533 | PS5-26-IK-5468A |  | I | I | Instrument tubing leak | CPP AGI | PS5-10-04 - Process piping B |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-00534 | PS5-78-OB-2041D |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-01-06 - Deluge System |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-00535 | PS5-77-UR-6134B |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-60-07 - Power Generation Package C | 2026-11-03 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-00536 | PS5-76-UR-9034C |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-08-01 - Compressor Air System | 2026-11-14 | Closed | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00537 | PS5-61-OB-6049A |  | P | P | Missing pipe stress label | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00538 | PS5-88-UR-9763D |  | B | B | Missing door closer | EPS UNATRAC | PS5-08-01 - Compressor Air System |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-00539 | PS5-57-OB-7656D |  | B | B | Damaged ceiling panel | CPP AGI | PS5-60-07 - Power Generation Package C |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-00540 | PS5-21-OB-9295A |  | T | T | PA speaker not tested | CPP AGI | PS5-82-02 - Structural Steel B |  | On Hold | Kumar, Raj | PS5 - Milestone G | 6
PL-00541 | PS5-18-UR-7564A |  | P | P | Valve handwheel stiff | KENT | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone A | 1
PL-00542 | PS5-95-IK-5270A |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-03-03 - Flame Detector System | 2026-10-15 | Closed | Mohamed, Ali | PS5 - Milestone C | 2
PL-00543 | PS5-29-UR-1376D |  | M | M | Motor fan guard missing | KENT | PS5-06-03 - Lightning Protection |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-00544 | PS5-12-OB-3787D |  | I | I | Transmitter not calibrated | CPP AGI | PS5-02-03 - Fuel Gas System | 2026-12-09 | Closed | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00545 | PS5-49-IK-8066D |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-63-04 - Electrical Earthing EITS Building | 2026-10-24 | Closed | Jean, Pierre | PS5 - Milestone H | 7
PL-00546 | PS5-32-OB-8506A |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-06-02 - DC UPS - EITS Building | 2026-09-20 | Closed | Jean, Pierre | PS5 - Milestone G | 6
PL-00547 | PS5-10-UR-1962A |  | P | P | Pipe support missing | EPS UNATRAC | PS5-60-07 - Power Generation Package C |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-00548 | PS5-75-IK-5264A |  | P | P | Insulation damaged | CPP AGI | PS5-01-06 - Deluge System | 2026-09-18 | Closed | Mohamed, Ali | PS5 - Milestone A | 1
PL-00549 | PS5-41-UR-3095B |  | T | T | CAT6 cable untidied | CPP AGI | PS5-04-01 - DCS System |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-00550 | PS5-67-OB-8139D |  | P | P | Valve handwheel stiff | EPS UNATRAC | PS5-62-01 - Cable Tray Main |  | On Hold | Wang, Li | PS5 - Milestone E | 4
PL-00551 | PS5-07-IK-4000A |  | T | T | CAT6 cable untidied | CPP AGI | PS5-04-04 - 33kV PCS System |  | On Hold | Jean, Pierre | PS5 - Milestone I | 8
PL-00552 | PS5-91-NI-8949B |  | T | T | Fiber patch panel unorganized | EPS UNATRAC | PS5-62-01 - Cable Tray Main |  | On Hold | Wang, Li | PS5 - Milestone B | 1.1
PL-00553 | PS5-96-NI-5469C |  | H | H | Thermostat calibration needed | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | Originated | Kumar, Raj | PS5 - Milestone F | 5
PL-00554 | PS5-99-NER-2545D |  | I | I | Transmitter not calibrated | CPP AGI | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-00555 | PS5-04-UR-8540D |  | E | E | Outgoing breaker not labeled | CPP AGI | PS5-60-07 - Power Generation Package C |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-00556 | PS5-42-NI-3118A |  | T | T | Fiber patch panel unorganized | EPS UNATRAC | PS5-09-03 - Motor Control Center |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-00557 | PS5-23-IK-7535A |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-10-06 - Vent System |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-00558 | PS5-56-OB-3151B |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-60-10 - Power Generation Package D |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-00559 | PS5-55-UR-7922D |  | I | I | Control valve actuator fault | KENT | PS5-99-01 - Area Completion Building Area |  | On Hold | Jean, Pierre | PS5 - Milestone H | 7
PL-00560 | PS5-83-IK-9115C |  | S | S | Deluge valve not primed | CPP AGI | PS5-61-07 - 0.4kV Switchboard EITS Building |  | Originated | Kumar, Raj | PS5 - Milestone B | 1.1
PL-00561 | PS5-88-OB-5073C |  | E | E | Wrong cable glanding | CPP AGI | PS5-10-02 - Utility Pipe Rack |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-00562 | PS5-85-NI-5151B |  | B | B | Cracked wall plaster | EPS UNATRAC | PS5-02-01 - Diesel Storage Tank |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-00563 | PS5-39-OB-8454D |  | B | B | Missing door closer | KENT | PS5-03-03 - Flame Detector System | 2026-08-14 | Closed | Kumar, Raj | PS5 - Milestone H | 7
PL-00564 | PS5-03-UR-7470A |  | M | M | Missing rotation arrow | KENT | PS5-11-02 - Guard Hut B | 2026-08-14 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-00565 | PS5-47-NER-5958A |  | T | T | Missing cable label | KENT | PS5-63-04 - Electrical Earthing EITS Building |  | On Hold | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00566 | PS5-62-IK-4961B |  | I | I | Missing instrument tag | CPP AGI | PS5-03-03 - Flame Detector System |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-00567 | PS5-15-IK-3497C |  | I | I | Pressure gauge reads zero | CPP AGI | PS5-02-03 - Fuel Gas System |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-00568 | PS5-07-OB-1129A |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-01-03 - Fire Water Pump B |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-00569 | PS5-66-NI-8993A |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-99-02 - Area Completion Process Area |  | On Hold | Kumar, Raj | PS5 - Milestone I | 8
PL-00570 | PS5-15-NER-6681B |  | B | B | Missing door closer | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00571 | PS5-76-OB-8675A |  | H | H | Missing insulation on duct | CPP AGI | PS5-10-01 - Main Pipe Rack |  | In Progress | Wang, Li | PS5 - Milestone D | 3
PL-00572 | PS5-89-UR-8911A |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-00573 | PS5-72-UR-1297B |  | T | T | CAT6 cable untidied | CPP AGI | PS5-03-01 - ESD System |  | On Hold | Mohamed, Ali | PS5 - Milestone G | 6
PL-00574 | PS5-80-IK-2977C |  | H | H | AHU filter not installed | CPP AGI | PS5-05-03 - CCTV System |  | Originated | Mohamed, Ali | PS5 - Milestone I | 8
PL-00575 | PS5-66-NI-2706C |  | P | P | Insulation damaged | KENT | PS5-12-01 - Cooling Tower |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-00576 | PS5-81-UR-4365D |  | E | E | Missing earth continuity label | CPP AGI | PS5-03-02 - Fire & Gas Detection |  | On Hold | Wang, Li | PS5 - Milestone B | 1.1
PL-00577 | PS5-43-IK-3014D |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-62-02 - Cable Tray Secondary |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-00578 | PS5-92-NER-6908C |  | B | B | Incomplete floor tiling | EPS UNATRAC | PS5-08-02 - Nitrogen Generator |  | In Progress | Jean, Pierre | PS5 - Milestone H | 7
PL-00579 | PS5-88-OB-1487B |  | S | S | Fire extinguisher expired | KENT | PS5-07-04 - FCU System |  | On Hold | Wang, Li | PS5 - Milestone C | 2
PL-00580 | PS5-98-UR-3473D |  | E | E | Cable tray not properly supported | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-00581 | PS5-45-UR-5583D |  | M | M | Vibration level exceeded | EPS UNATRAC | PS5-61-02 - 6.6kV Switchboard LLHT North |  | On Hold | Jean, Pierre | PS5 - Milestone G | 6
PL-00582 | PS5-52-IK-5940A |  | S | S | Fire alarm panel fault | KENT | PS5-63-01 - Electrical Earthing |  | On Hold | Mohamed, Ali | PS5 - Milestone D | 3
PL-00583 | PS5-71-OB-9541B |  | S | S | Deluge valve not primed | KENT | PS5-04-01 - DCS System |  | On Hold | Jean, Pierre | PS5 - Milestone I | 8
PL-00584 | PS5-93-NER-9278A |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-01-04 - Fire Water Ring Main |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-00585 | PS5-96-NI-9737D |  | M | M | Missing rotation arrow | CPP AGI | PS5-99-03 - Area Completion Utilities Area | 2026-11-11 | Closed | Mohamed, Ali | PS5 - Milestone F | 5
PL-00586 | PS5-75-IK-6919B |  | M | M | Missing rotation arrow | KENT | PS5-10-01 - Main Pipe Rack |  | In Progress | Wang, Li | PS5 - Milestone C | 2
PL-00587 | PS5-58-UR-7050C |  | S | S | Missing safety sign | CPP AGI | PS5-61-01 - 33kV Switchboard EITS Building |  | Originated | Kumar, Raj | PS5 - Milestone B | 1.1
PL-00588 | PS5-54-IK-3364C |  | S | S | Missing safety sign | KENT | PS5-09-02 - Transformer 6.6kV/0.4kV |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-00589 | PS5-61-UR-3569D |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-04-01 - DCS System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-00590 | PS5-16-OB-5995D |  | S | S | Eye wash station blocked | CPP AGI | PS5-03-03 - Flame Detector System |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00591 | PS5-63-UR-3004C |  | T | T | Fiber patch panel unorganized | KENT | PS5-01-04 - Fire Water Ring Main | 2026-09-06 | Closed | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00592 | PS5-93-NI-3175D |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-82-07 - Guard Huts |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-00593 | PS5-44-NI-1750D |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-63-01 - Electrical Earthing | 2026-11-08 | Closed | Wang, Li | PS5 - Milestone H | 7
PL-00594 | PS5-83-NI-2395A |  | M | M | Vibration level exceeded | CPP AGI | PS5-02-03 - Fuel Gas System |  | In Progress | Kumar, Raj | PS5 - Milestone C | 2
PL-00595 | PS5-24-UR-5504D |  | B | B | Incomplete floor tiling | KENT | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-00596 | PS5-03-OB-8160A |  | T | T | Fiber patch panel unorganized | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-00597 | PS5-19-IK-5187D |  | P | P | Pipe support missing | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | Originated | Mohamed, Ali | PS5 - Milestone E | 4
PL-00598 | PS5-08-OB-7388A |  | S | S | Emergency shower not tested | KENT | PS5-05-02 - PA/GA System |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-00599 | PS5-97-NI-4874B |  | P | P | Missing pipe stress label | CPP AGI | PS5-09-02 - Transformer 6.6kV/0.4kV |  | On Hold | Smith, John | PS5 - Milestone G | 6
PL-00600 | PS5-53-IK-1305B |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-09-03 - Motor Control Center |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-00601 | PS5-58-UR-9199A |  | E | E | Missing earth continuity label | EPS UNATRAC | PS5-08-02 - Nitrogen Generator |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-00602 | PS5-80-OB-3742A |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-08-02 - Nitrogen Generator |  | On Hold | Mohamed, Ali | PS5 - Milestone I | 8
PL-00603 | PS5-37-UR-3644C |  | M | M | Vibration level exceeded | KENT | PS5-60-01 - Power Generation Package A |  | On Hold | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00604 | PS5-56-IK-9270D |  | M | M | Coupling guard loose | EPS UNATRAC | PS5-02-03 - Fuel Gas System |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-00605 | PS5-89-IK-1033C |  | P | P | Flange bolt torque incomplete | CPP AGI | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-12-11 | Closed | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00606 | PS5-11-UR-9825A |  | H | H | Thermostat calibration needed | KENT | PS5-61-01 - 33kV Switchboard EITS Building |  | On Hold | Smith, John | PS5 - Milestone I | 8
PL-00607 | PS5-02-UR-8580B |  | E | E | Missing earth continuity label | KENT | PS5-12-01 - Cooling Tower |  | On Hold | Smith, John | PS5 - Milestone G | 6
PL-00608 | PS5-81-OB-4623A |  | B | B | Missing door closer | KENT | PS5-07-03 - AHU System |  | In Progress | Mohamed, Ali | PS5 - Milestone A | 1
PL-00609 | PS5-51-UR-5544C |  | B | B | Missing door closer | KENT | PS5-09-04 - 0.4kV Switchboard |  | On Hold | Jean, Pierre | PS5 - Milestone H | 7
PL-00610 | PS5-30-NI-5494A |  | I | I | Missing instrument tag | KENT | PS5-05-03 - CCTV System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00611 | PS5-53-OB-2994C |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-63-04 - Electrical Earthing EITS Building |  | On Hold | Smith, John | PS5 - Milestone A | 1
PL-00612 | PS5-01-NER-4188B |  | P | P | Missing pipe stress label | EPS UNATRAC | PS5-01-06 - Deluge System |  | Originated | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-00613 | PS5-09-UR-1456B |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building |  | On Hold | Kumar, Raj | PS5 - Milestone B | 1.1
PL-00614 | PS5-10-NI-8184D |  | P | P | Gasket protruding from flange | CPP AGI | PS5-09-01 - Transformer 33kV/6.6kV | 2026-10-17 | Closed | Smith, John | PS5 - Milestone D | 3
PL-00615 | PS5-09-IK-2015D |  | E | E | Incomplete cable termination | KENT | PS5-02-02 - Diesel Transfer Pump |  | On Hold | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-00616 | PS5-80-NER-4819D |  | M | M | Motor fan guard missing | CPP AGI | PS5-62-01 - Cable Tray Main | 2026-11-13 | Closed | Kumar, Raj | PS5 - Milestone B | 1.1
PL-00617 | PS5-44-UR-8439C |  | B | B | Cracked wall plaster | CPP AGI | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-00618 | PS5-74-IK-9337B |  | E | E | Incomplete cable termination | CPP AGI | PS5-03-02 - Fire & Gas Detection |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-00619 | PS5-84-OB-6098C |  | T | T | CCTV camera not focused | KENT | PS5-06-01 - AC UPS - EITS Building | 2026-12-14 | Closed | Jean, Pierre | PS5 - Milestone D | 3
PL-00620 | PS5-76-IK-1939A |  | H | H | FCU drain pipe not connected | KENT | PS5-82-02 - Structural Steel B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-00621 | PS5-25-NER-8657C |  | S | S | Eye wash station blocked | EPS UNATRAC | PS5-11-03 - Admin Building |  | On Hold | Kumar, Raj | PS5 - Milestone D | 3
PL-00622 | PS5-64-IK-1060C |  | P | P | Gasket protruding from flange | CPP AGI | PS5-10-03 - Process piping A |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-00623 | PS5-27-NER-4018D |  | T | T | Fiber patch panel unorganized | EPS UNATRAC | PS5-07-02 - Chiller System B |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-00624 | PS5-25-NI-6896A |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-02-01 - Diesel Storage Tank |  | Originated | Jean, Pierre | PS5 - Milestone F | 5
PL-00625 | PS5-26-UR-3884D |  | I | I | Transmitter not calibrated | CPP AGI | PS5-10-01 - Main Pipe Rack | 2026-12-08 | Closed | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00626 | PS5-48-OB-3807D |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-60-01 - Power Generation Package A |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-00627 | PS5-69-NER-7131B |  | E | E | Incomplete cable termination | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | On Hold | Wang, Li | PS5 - Milestone C | 2
PL-00628 | PS5-32-UR-5588D |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-01-06 - Deluge System |  | On Hold | Kumar, Raj | PS5 - Milestone D | 3
PL-00629 | PS5-97-NI-7131B |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-07-01 - Chiller System A |  | In Progress | Jean, Pierre | PS5 - Milestone B | 1.1
PL-00630 | PS5-52-NI-1599A |  | P | P | Pipe support missing | KENT | PS5-13-01 - Flare System |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-00631 | PS5-33-NI-2388A |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-60-07 - Power Generation Package C |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-00632 | PS5-55-NER-8660B |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-12-01 - Cooling Tower |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-00633 | PS5-10-OB-2350B |  | P | P | Missing pipe stress label | KENT | PS5-09-03 - Motor Control Center |  | Originated | Kumar, Raj | PS5 - Milestone G | 6
PL-00634 | PS5-26-OB-4221C |  | E | E | Wrong cable glanding | KENT | PS5-09-04 - 0.4kV Switchboard |  | Originated | Mohamed, Ali | PS5 - Milestone D | 3
PL-00635 | PS5-37-OB-7616D |  | M | M | Vibration level exceeded | EPS UNATRAC | PS5-06-02 - DC UPS - EITS Building |  | On Hold | Wang, Li | PS5 - Milestone C | 2
PL-00636 | PS5-30-IK-8773A |  | B | B | Cracked wall plaster | CPP AGI | PS5-82-02 - Structural Steel B |  | On Hold | Kumar, Raj | PS5 - Milestone I | 8
PL-00637 | PS5-99-NER-4433B |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-82-01 - Structural Steel A |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00638 | PS5-46-OB-4694B |  | P | P | Gasket protruding from flange | KENT | PS5-04-02 - SIS System |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-00639 | PS5-73-NI-7404D |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-10-06 - Vent System |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-00640 | PS5-39-UR-3808A |  | E | E | Missing electrical hazard sign | KENT | PS5-60-04 - Power Generation Package B |  | In Progress | Jean, Pierre | PS5 - Milestone D | 3
PL-00641 | PS5-68-UR-8449A |  | B | B | Cracked wall plaster | KENT | PS5-99-01 - Area Completion Building Area | 2026-09-10 | Closed | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-00642 | PS5-62-UR-7373D |  | H | H | Damper not operational | EPS UNATRAC | PS5-10-06 - Vent System |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-00643 | PS5-40-NI-4325C |  | I | I | Missing instrument tag | KENT | PS5-10-04 - Process piping B |  | On Hold | Smith, John | PS5 - Milestone G | 6
PL-00644 | PS5-78-IK-9615B |  | M | M | Vibration level exceeded | EPS UNATRAC | PS5-06-03 - Lightning Protection |  | On Hold | Smith, John | PS5 - Milestone A | 1
PL-00645 | PS5-90-OB-7407C |  | T | T | Missing cable label | EPS UNATRAC | PS5-82-01 - Structural Steel A |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-00646 | PS5-51-UR-4927D |  | I | I | Missing loop diagram | CPP AGI | PS5-05-03 - CCTV System |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-00647 | PS5-48-UR-2723C |  | M | M | Coupling guard loose | CPP AGI | PS5-01-09 - Inergen for EITS Building |  | On Hold | Smith, John | PS5 - Milestone D | 3
PL-00648 | PS5-96-NER-4185B |  | T | T | Fiber patch panel unorganized | EPS UNATRAC | PS5-05-02 - PA/GA System | 2026-11-13 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-00649 | PS5-11-NI-4969C |  | E | E | Incomplete cable termination | CPP AGI | PS5-04-02 - SIS System |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-00650 | PS5-95-NER-3759A |  | T | T | Fiber patch panel unorganized | KENT | PS5-09-04 - 0.4kV Switchboard | 2026-10-04 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-00651 | PS5-69-IK-8242C |  | M | M | Motor fan guard missing | KENT | PS5-04-04 - 33kV PCS System |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-00652 | PS5-99-IK-5091B |  | E | E | Missing earth continuity label | EPS UNATRAC | PS5-60-04 - Power Generation Package B |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-00653 | PS5-88-UR-4613D |  | E | E | Cable tray not properly supported | CPP AGI | PS5-01-03 - Fire Water Pump B |  | Originated | Wang, Li | PS5 - Milestone G | 6
PL-00654 | PS5-72-IK-4393D |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-05-02 - PA/GA System |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-00655 | PS5-28-NER-4606A |  | E | E | Wrong cable glanding | EPS UNATRAC | PS5-07-04 - FCU System | 2026-10-01 | Closed | Wang, Li | PS5 - Milestone D | 3
PL-00656 | PS5-64-UR-9784D |  | P | P | Missing pipe stress label | KENT | PS5-01-06 - Deluge System |  | On Hold | Jean, Pierre | PS5 - Milestone B | 1.1
PL-00657 | PS5-18-OB-3872C |  | M | M | Motor fan guard missing | KENT | PS5-03-01 - ESD System |  | On Hold | Mohamed, Ali | PS5 - Milestone F | 5
PL-00658 | PS5-95-IK-9248C |  | T | T | Fiber patch panel unorganized | KENT | PS5-01-09 - Inergen for EITS Building |  | Originated | Jean, Pierre | PS5 - Milestone F | 5
PL-00659 | PS5-64-OB-4309A |  | B | B | Incomplete floor tiling | EPS UNATRAC | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-08-05 | Closed | Wang, Li | PS5 - Milestone E | 4
PL-00660 | PS5-83-UR-9533D |  | B | B | Missing door closer | EPS UNATRAC | PS5-08-01 - Compressor Air System |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-00661 | PS5-70-UR-5068D |  | M | M | Motor fan guard missing | CPP AGI | PS5-01-04 - Fire Water Ring Main |  | On Hold | Wang, Li | PS5 - Milestone D | 3
PL-00662 | PS5-63-UR-4153A |  | I | I | Missing loop diagram | CPP AGI | PS5-60-01 - Power Generation Package A |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-00663 | PS5-55-NER-6103A |  | H | H | Damper not operational | CPP AGI | PS5-02-03 - Fuel Gas System |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-00664 | PS5-62-UR-6891B |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-05-03 - CCTV System |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-00665 | PS5-03-NER-8002D |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-00666 | PS5-72-NI-8878A |  | H | H | Damper not operational | EPS UNATRAC | PS5-05-03 - CCTV System |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-00667 | PS5-94-OB-9051B |  | T | T | PA speaker not tested | KENT | PS5-06-03 - Lightning Protection |  | On Hold | Smith, John | PS5 - Milestone C | 2
PL-00668 | PS5-50-NI-3660A |  | P | P | Insulation damaged | CPP AGI | PS5-60-04 - Power Generation Package B |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-00669 | PS5-32-NER-1565D |  | P | P | Valve handwheel stiff | CPP AGI | PS5-99-01 - Area Completion Building Area |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-00670 | PS5-75-IK-1202A |  | B | B | Missing fire extinguisher signage | KENT | PS5-04-03 - 33kV ICSS System |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-00671 | PS5-33-OB-9202D |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-60-07 - Power Generation Package C |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-00672 | PS5-90-OB-1105D |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-61-01 - 33kV Switchboard EITS Building | 2026-09-24 | Closed | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00673 | PS5-23-OB-4053C |  | E | E | Missing earth continuity label | CPP AGI | PS5-01-09 - Inergen for EITS Building |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-00674 | PS5-96-IK-4143B |  | H | H | AHU filter not installed | CPP AGI | PS5-99-03 - Area Completion Utilities Area |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-00675 | PS5-31-NER-8949C |  | E | E | Cable tray not properly supported | KENT | PS5-05-02 - PA/GA System | 2026-10-01 | Closed | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00676 | PS5-01-NER-9520D |  | B | B | Damaged ceiling panel | KENT | PS5-09-03 - Motor Control Center |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-00677 | PS5-47-NER-7200C |  | T | T | CAT6 cable untidied | CPP AGI | PS5-11-02 - Guard Hut B |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-00678 | PS5-04-NI-3013D |  | E | E | Wrong cable glanding | CPP AGI | PS5-01-01 - Fire Water Jockey Pump A/B |  | On Hold | Wang, Li | PS5 - Milestone H | 7
PL-00679 | PS5-25-UR-6278A |  | I | I | Instrument tubing leak | KENT | PS5-13-01 - Flare System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00680 | PS5-45-NER-8800D |  | P | P | Gasket protruding from flange | CPP AGI | PS5-62-02 - Cable Tray Secondary |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-00681 | PS5-39-NI-8648A |  | S | S | Missing safety sign | CPP AGI | PS5-10-02 - Utility Pipe Rack |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-00682 | PS5-99-OB-4610C |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-08-01 - Compressor Air System | 2026-09-11 | Closed | Smith, John | PS5 - Milestone D | 3
PL-00683 | PS5-43-IK-2059C |  | E | E | Incomplete cable termination | KENT | PS5-04-02 - SIS System |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-00684 | PS5-76-IK-2902C |  | S | S | Emergency shower not tested | KENT | PS5-62-01 - Cable Tray Main | 2026-08-11 | Closed | Mohamed, Ali | PS5 - Milestone D | 3
PL-00685 | PS5-41-OB-3069C |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-01-01 - Fire Water Jockey Pump A/B |  | Originated | Kumar, Raj | PS5 - Milestone E | 4
PL-00686 | PS5-29-NER-8467A |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-03-02 - Fire & Gas Detection |  | Originated | Jean, Pierre | PS5 - Milestone G | 6
PL-00687 | PS5-74-NER-4534B |  | B | B | Incomplete paint touch-up | KENT | PS5-10-05 - Drain System |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-00688 | PS5-90-UR-3933D |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-11-01 - Guard Hut A |  | On Hold | Smith, John | PS5 - Milestone C | 2
PL-00689 | PS5-45-NER-7407A |  | M | M | Motor fan guard missing | EPS UNATRAC | PS5-05-01 - Telecom Network |  | In Progress | Mohamed, Ali | PS5 - Milestone A | 1
PL-00690 | PS5-07-OB-8496C |  | M | M | Vibration level exceeded | KENT | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-00691 | PS5-26-UR-6934C |  | T | T | CCTV camera not focused | KENT | PS5-82-07 - Guard Huts |  | On Hold | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-00692 | PS5-61-IK-1859A |  | H | H | FCU drain pipe not connected | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-00693 | PS5-31-NER-9005B |  | P | P | Missing pipe stress label | CPP AGI | PS5-62-01 - Cable Tray Main |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-00694 | PS5-57-OB-1190A |  | S | S | Fire extinguisher expired | KENT | PS5-02-03 - Fuel Gas System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00695 | PS5-13-NI-3967B |  | T | T | Intercom not functioning | KENT | PS5-07-03 - AHU System |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-00696 | PS5-24-NER-1323B |  | S | S | Fire alarm panel fault | KENT | PS5-10-03 - Process piping A |  | Originated | Kumar, Raj | PS5 - Milestone C | 2
PL-00697 | PS5-85-UR-3960D |  | T | T | Intercom not functioning | CPP AGI | PS5-01-09 - Inergen for EITS Building |  | On Hold | Jean, Pierre | PS5 - Milestone I | 8
PL-00698 | PS5-97-UR-2386D |  | B | B | Cracked wall plaster | EPS UNATRAC | PS5-63-01 - Electrical Earthing | 2026-08-18 | Closed | Mohamed, Ali | PS5 - Milestone F | 5
PL-00699 | PS5-67-OB-9750B |  | P | P | Missing pipe stress label | CPP AGI | PS5-05-02 - PA/GA System |  | On Hold | Smith, John | PS5 - Milestone G | 6
PL-00700 | PS5-31-UR-4081A |  | P | P | Pipe support missing | CPP AGI | PS5-12-01 - Cooling Tower |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-00701 | PS5-21-NER-8472A |  | I | I | Instrument tubing leak | KENT | PS5-12-01 - Cooling Tower | 2026-10-13 | Closed | Wang, Li | PS5 - Milestone E | 4
PL-00702 | PS5-83-NI-3687B |  | S | S | Emergency shower not tested | KENT | PS5-04-03 - 33kV ICSS System | 2026-10-19 | Closed | Mohamed, Ali | PS5 - Milestone I | 8
PL-00703 | PS5-69-UR-9984B |  | S | S | Eye wash station blocked | CPP AGI | PS5-60-01 - Power Generation Package A |  | On Hold | Wang, Li | PS5 - Milestone A | 1
PL-00704 | PS5-36-UR-2604B |  | E | E | Missing earth continuity label | CPP AGI | PS5-12-02 - Water Treatment |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-00705 | PS5-13-NI-6716C |  | E | E | Wrong cable glanding | EPS UNATRAC | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone C | 2
PL-00706 | PS5-34-UR-9414C |  | M | M | Motor fan guard missing | CPP AGI | PS5-03-01 - ESD System | 2026-11-19 | Closed | Jean, Pierre | PS5 - Milestone A | 1
PL-00707 | PS5-87-NI-7852C |  | H | H | Damper not operational | CPP AGI | PS5-60-01 - Power Generation Package A |  | Originated | Smith, John | PS5 - Milestone E | 4
PL-00708 | PS5-40-NER-6123D |  | P | P | Gasket protruding from flange | CPP AGI | PS5-82-01 - Structural Steel A | 2026-10-21 | Closed | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-00709 | PS5-55-NI-3235B |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-08-01 - Compressor Air System | 2026-12-16 | Closed | Wang, Li | PS5 - Milestone B | 1.1
PL-00710 | PS5-69-OB-5001D |  | E | E | Outgoing breaker not labeled | KENT | PS5-60-10 - Power Generation Package D |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-00711 | PS5-18-NI-6788D |  | B | B | Missing door closer | EPS UNATRAC | PS5-63-01 - Electrical Earthing |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-00712 | PS5-99-UR-5752B |  | S | S | Eye wash station blocked | KENT | PS5-05-02 - PA/GA System |  | On Hold | Mohamed, Ali | PS5 - Milestone F | 5
PL-00713 | PS5-08-OB-1096C |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-11-20 | Closed | Mohamed, Ali | PS5 - Milestone G | 6
PL-00714 | PS5-13-NER-9061A |  | P | P | Missing pipe stress label | CPP AGI | PS5-03-02 - Fire & Gas Detection |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-00715 | PS5-33-IK-8711B |  | H | H | Missing insulation on duct | KENT | PS5-61-01 - 33kV Switchboard EITS Building |  | On Hold | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00716 | PS5-21-IK-6795C |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-06-01 - AC UPS - EITS Building |  | On Hold | Mohamed, Ali | PS5 - Milestone I | 8
PL-00717 | PS5-26-NER-5354A |  | I | I | Pressure gauge reads zero | KENT | PS5-03-03 - Flame Detector System | 2026-08-06 | Closed | Kumar, Raj | PS5 - Milestone D | 3
PL-00718 | PS5-50-IK-2797D |  | T | T | Fiber patch panel unorganized | KENT | PS5-04-01 - DCS System |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-00719 | PS5-55-NI-1131B |  | H | H | Missing insulation on duct | EPS UNATRAC | PS5-11-03 - Admin Building |  | Originated | Mohamed, Ali | PS5 - Milestone I | 8
PL-00720 | PS5-34-IK-8031A |  | T | T | Intercom not functioning | CPP AGI | PS5-02-02 - Diesel Transfer Pump | 2026-09-09 | Closed | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00721 | PS5-03-NI-4270A |  | H | H | Duct leakage at joint | EPS UNATRAC | PS5-06-02 - DC UPS - EITS Building | 2026-09-05 | Closed | Smith, John | PS5 - Milestone C | 2
PL-00722 | PS5-35-OB-5596D |  | S | S | Deluge valve not primed | CPP AGI | PS5-10-04 - Process piping B | 2026-08-10 | Closed | Smith, John | PS5 - Milestone D | 3
PL-00723 | PS5-36-NI-2650B |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-10-05 - Drain System | 2026-09-10 | Closed | Smith, John | PS5 - Milestone A | 1
PL-00724 | PS5-47-NI-9664C |  | P | P | Pipe support missing | KENT | PS5-11-01 - Guard Hut A | 2026-10-12 | Closed | Wang, Li | PS5 - Milestone E | 4
PL-00725 | PS5-78-UR-1672C |  | M | M | Motor fan guard missing | KENT | PS5-07-01 - Chiller System A |  | Originated | Jean, Pierre | PS5 - Milestone G | 6
PL-00726 | PS5-98-IK-9741C |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-63-01 - Electrical Earthing |  | Originated | Jean, Pierre | PS5 - Milestone B | 1.1
PL-00727 | PS5-92-UR-8145A |  | I | I | Pressure gauge reads zero | KENT | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-00728 | PS5-08-IK-7512B |  | B | B | Cracked wall plaster | KENT | PS5-05-02 - PA/GA System |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-00729 | PS5-52-NI-5448A |  | E | E | Cable tray not properly supported | EPS UNATRAC | PS5-05-02 - PA/GA System |  | In Progress | Jean, Pierre | PS5 - Milestone H | 7
PL-00730 | PS5-38-OB-2951A |  | I | I | Transmitter not calibrated | CPP AGI | PS5-01-02 - Fire Water Pump A |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-00731 | PS5-83-IK-4440C |  | I | I | Transmitter not calibrated | CPP AGI | PS5-10-02 - Utility Pipe Rack |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-00732 | PS5-79-OB-6318D |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-13-01 - Flare System |  | Originated | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00733 | PS5-81-NI-4377D |  | P | P | Pipe support missing | EPS UNATRAC | PS5-07-03 - AHU System | 2026-11-21 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-00734 | PS5-12-NER-3973B |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-07-01 - Chiller System A | 2026-10-05 | Closed | Jean, Pierre | PS5 - Milestone G | 6
PL-00735 | PS5-88-NI-4077A |  | T | T | Fiber patch panel unorganized | EPS UNATRAC | PS5-06-01 - AC UPS - EITS Building |  | Originated | Smith, John | PS5 - Milestone E | 4
PL-00736 | PS5-50-UR-2802D |  | I | I | Missing instrument tag | EPS UNATRAC | PS5-63-04 - Electrical Earthing EITS Building | 2026-12-04 | Closed | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00737 | PS5-91-UR-4314A |  | H | H | FCU drain pipe not connected | EPS UNATRAC | PS5-08-02 - Nitrogen Generator | 2026-12-24 | Closed | Smith, John | PS5 - Milestone B | 1.1
PL-00738 | PS5-35-NI-3016A |  | H | H | Duct leakage at joint | KENT | PS5-10-04 - Process piping B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00739 | PS5-04-IK-7998B |  | M | M | Coupling guard loose | CPP AGI | PS5-03-02 - Fire & Gas Detection |  | On Hold | Wang, Li | PS5 - Milestone I | 8
PL-00740 | PS5-29-UR-5617B |  | M | M | Vibration level exceeded | CPP AGI | PS5-07-03 - AHU System |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-00741 | PS5-43-NI-3971C |  | E | E | Missing earth continuity label | KENT | PS5-12-02 - Water Treatment |  | On Hold | Wang, Li | PS5 - Milestone B | 1.1
PL-00742 | PS5-34-UR-1035D |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-10-01 - Main Pipe Rack |  | On Hold | Wang, Li | PS5 - Milestone F | 5
PL-00743 | PS5-74-NER-5562A |  | H | H | Missing insulation on duct | CPP AGI | PS5-10-05 - Drain System |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-00744 | PS5-78-OB-3264D |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-60-04 - Power Generation Package B |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-00745 | PS5-50-UR-7911C |  | S | S | Deluge valve not primed | CPP AGI | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-00746 | PS5-72-NER-3188D |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-02-03 - Fuel Gas System |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-00747 | PS5-08-IK-2920D |  | P | P | Gasket protruding from flange | CPP AGI | PS5-04-02 - SIS System |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-00748 | PS5-62-NI-3591A |  | S | S | Eye wash station blocked | CPP AGI | PS5-01-04 - Fire Water Ring Main |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-00749 | PS5-61-IK-9641C |  | E | E | Wrong cable glanding | CPP AGI | PS5-08-02 - Nitrogen Generator |  | Originated | Smith, John | PS5 - Milestone B | 1.1
PL-00750 | PS5-08-UR-3843C |  | S | S | Fire extinguisher expired | CPP AGI | PS5-11-02 - Guard Hut B |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-00751 | PS5-91-IK-7941D |  | S | S | Eye wash station blocked | EPS UNATRAC | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-00752 | PS5-96-NI-2264D |  | S | S | Missing safety sign | CPP AGI | PS5-04-01 - DCS System |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-00753 | PS5-10-OB-6496A |  | P | P | Valve handwheel stiff | CPP AGI | PS5-60-10 - Power Generation Package D | 2026-10-04 | Closed | Jean, Pierre | PS5 - Milestone G | 6
PL-00754 | PS5-82-UR-4937B |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-01-09 - Inergen for EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-00755 | PS5-97-OB-7523C |  | B | B | Damaged ceiling panel | EPS UNATRAC | PS5-82-07 - Guard Huts |  | Originated | Smith, John | PS5 - Milestone A | 1
PL-00756 | PS5-04-NI-7260B |  | P | P | Flange bolt torque incomplete | CPP AGI | PS5-04-01 - DCS System |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00757 | PS5-88-IK-3638D |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-04-04 - 33kV PCS System |  | Originated | Kumar, Raj | PS5 - Milestone H | 7
PL-00758 | PS5-06-NER-4917A |  | P | P | Missing pipe stress label | EPS UNATRAC | PS5-63-01 - Electrical Earthing |  | In Progress | Kumar, Raj | PS5 - Milestone C | 2
PL-00759 | PS5-71-UR-9174A |  | E | E | Wrong cable glanding | EPS UNATRAC | PS5-04-04 - 33kV PCS System |  | Originated | Jean, Pierre | PS5 - Milestone H | 7
PL-00760 | PS5-34-NER-5194D |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-05-01 - Telecom Network | 2026-09-23 | Closed | Wang, Li | PS5 - Milestone B | 1.1
PL-00761 | PS5-88-IK-8222B |  | H | H | FCU drain pipe not connected | KENT | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | Originated | Mohamed, Ali | PS5 - Milestone H | 7
PL-00762 | PS5-83-UR-5011C |  | P | P | Missing pipe stress label | KENT | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00763 | PS5-50-NER-2531B |  | H | H | AHU filter not installed | CPP AGI | PS5-03-02 - Fire & Gas Detection |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-00764 | PS5-09-OB-6610D |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-03-02 - Fire & Gas Detection | 2026-09-13 | Closed | Jean, Pierre | PS5 - Milestone B | 1.1
PL-00765 | PS5-28-OB-1513D |  | T | T | PA speaker not tested | KENT | PS5-03-03 - Flame Detector System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-00766 | PS5-23-UR-3322A |  | P | P | Insulation damaged | KENT | PS5-62-01 - Cable Tray Main | 2026-10-09 | Closed | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00767 | PS5-12-NER-6603D |  | M | M | Coupling guard loose | CPP AGI | PS5-63-01 - Electrical Earthing |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-00768 | PS5-89-NI-7375D |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-11-03 - Admin Building |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-00769 | PS5-19-NER-6184A |  | I | I | Missing instrument tag | EPS UNATRAC | PS5-02-01 - Diesel Storage Tank |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-00770 | PS5-75-UR-1597A |  | M | M | Missing rotation arrow | KENT | PS5-01-01 - Fire Water Jockey Pump A/B |  | On Hold | Smith, John | PS5 - Milestone H | 7
PL-00771 | PS5-48-OB-1265B |  | H | H | Missing insulation on duct | CPP AGI | PS5-60-01 - Power Generation Package A |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-00772 | PS5-55-NI-6502A |  | E | E | Missing earth continuity label | KENT | PS5-99-02 - Area Completion Process Area |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-00773 | PS5-37-NER-5640C |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-13-01 - Flare System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00774 | PS5-97-NI-9924A |  | E | E | Incomplete cable termination | KENT | PS5-02-03 - Fuel Gas System |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-00775 | PS5-16-OB-8601B |  | B | B | Incomplete paint touch-up | EPS UNATRAC | PS5-10-02 - Utility Pipe Rack | 2026-09-28 | Closed | Wang, Li | PS5 - Milestone G | 6
PL-00776 | PS5-40-NER-4957A |  | S | S | Missing safety sign | EPS UNATRAC | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00777 | PS5-56-IK-7412A |  | B | B | Incomplete paint touch-up | KENT | PS5-01-04 - Fire Water Ring Main |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-00778 | PS5-41-NI-3595B |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building |  | On Hold | Wang, Li | PS5 - Milestone C | 2
PL-00779 | PS5-34-NI-3605D |  | H | H | Damper not operational | KENT | PS5-99-03 - Area Completion Utilities Area |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00780 | PS5-70-UR-7265A |  | E | E | Outgoing breaker not labeled | KENT | PS5-01-04 - Fire Water Ring Main |  | Originated | Jean, Pierre | PS5 - Milestone G | 6
PL-00781 | PS5-85-UR-5505A |  | T | T | Missing cable label | EPS UNATRAC | PS5-12-01 - Cooling Tower | 2026-11-25 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-00782 | PS5-34-IK-2520A |  | B | B | Damaged ceiling panel | EPS UNATRAC | PS5-03-02 - Fire & Gas Detection |  | In Progress | Jean, Pierre | PS5 - Milestone B | 1.1
PL-00783 | PS5-10-IK-7879B |  | S | S | Eye wash station blocked | KENT | PS5-03-01 - ESD System |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-00784 | PS5-62-NI-9953A |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-05-01 - Telecom Network | 2026-08-11 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-00785 | PS5-28-OB-2880D |  | M | M | Pump alignment required | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-00786 | PS5-26-UR-6710C |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-07-03 - AHU System |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00787 | PS5-26-OB-7436A |  | T | T | CCTV camera not focused | CPP AGI | PS5-99-02 - Area Completion Process Area |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-00788 | PS5-35-OB-2762C |  | H | H | AHU filter not installed | KENT | PS5-07-01 - Chiller System A |  | In Progress | Jean, Pierre | PS5 - Milestone H | 7
PL-00789 | PS5-53-OB-9691B |  | P | P | Flange bolt torque incomplete | KENT | PS5-13-01 - Flare System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00790 | PS5-85-OB-7094A |  | H | H | Missing insulation on duct | CPP AGI | PS5-10-06 - Vent System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00791 | PS5-30-NI-2085B |  | B | B | Cracked wall plaster | EPS UNATRAC | PS5-10-05 - Drain System |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-00792 | PS5-26-IK-1813D |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-03-02 - Fire & Gas Detection | 2026-11-11 | Closed | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-00793 | PS5-37-UR-1076D |  | M | M | Coupling guard loose | CPP AGI | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-09-19 | Closed | Jean, Pierre | PS5 - Milestone B | 1.1
PL-00794 | PS5-09-NER-2558D |  | S | S | Missing safety sign | CPP AGI | PS5-01-05 - Foam System |  | On Hold | Wang, Li | PS5 - Milestone I | 8
PL-00795 | PS5-64-NI-1771B |  | M | M | Motor fan guard missing | EPS UNATRAC | PS5-09-04 - 0.4kV Switchboard |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-00796 | PS5-02-IK-2722D |  | T | T | Intercom not functioning | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | On Hold | Wang, Li | PS5 - Milestone F | 5
PL-00797 | PS5-89-UR-5254D |  | S | S | Fire extinguisher expired | CPP AGI | PS5-07-03 - AHU System |  | Originated | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00798 | PS5-16-IK-6231D |  | B | B | Cracked wall plaster | EPS UNATRAC | PS5-10-03 - Process piping A | 2026-09-19 | Closed | Smith, John | PS5 - Milestone B | 1.1
PL-00799 | PS5-42-NER-4700A |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-00800 | PS5-27-UR-2231D |  | E | E | Cable tray not properly supported | KENT | PS5-12-01 - Cooling Tower |  | On Hold | Jean, Pierre | PS5 - Milestone I | 8
PL-00801 | PS5-27-NI-9644C |  | B | B | Damaged ceiling panel | EPS UNATRAC | PS5-07-02 - Chiller System B |  | On Hold | Mohamed, Ali | PS5 - Milestone H | 7
PL-00802 | PS5-66-IK-7556A |  | T | T | CAT6 cable untidied | KENT | PS5-04-04 - 33kV PCS System | 2026-11-28 | Closed | Smith, John | PS5 - Milestone I | 8
PL-00803 | PS5-35-UR-8802C |  | H | H | AHU filter not installed | CPP AGI | PS5-10-04 - Process piping B | 2026-08-15 | Closed | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00804 | PS5-65-NER-9321B |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | Originated | Mohamed, Ali | PS5 - Milestone I | 8
PL-00805 | PS5-52-IK-5520C |  | P | P | Insulation damaged | CPP AGI | PS5-03-01 - ESD System |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-00806 | PS5-05-NI-5361A |  | S | S | Fire alarm panel fault | CPP AGI | PS5-03-02 - Fire & Gas Detection |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-00807 | PS5-35-NER-4370A |  | M | M | Missing rotation arrow | KENT | PS5-07-03 - AHU System |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-00808 | PS5-31-IK-6162C |  | M | M | Missing rotation arrow | KENT | PS5-10-01 - Main Pipe Rack |  | Originated | Jean, Pierre | PS5 - Milestone A | 1
PL-00809 | PS5-23-OB-2261A |  | P | P | Flange bolt torque incomplete | CPP AGI | PS5-63-04 - Electrical Earthing EITS Building |  | On Hold | Kumar, Raj | PS5 - Milestone C | 2
PL-00810 | PS5-03-NI-5762D |  | P | P | Missing pipe stress label | CPP AGI | PS5-82-02 - Structural Steel B |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-00811 | PS5-45-NI-5216C |  | H | H | Missing insulation on duct | KENT | PS5-04-03 - 33kV ICSS System |  | Originated | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00812 | PS5-77-NER-2847B |  | T | T | CCTV camera not focused | KENT | PS5-01-02 - Fire Water Pump A |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-00813 | PS5-32-NI-8056B |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-04-03 - 33kV ICSS System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00814 | PS5-87-OB-6426B |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | On Hold | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00815 | PS5-56-NER-6685B |  | M | M | Pump alignment required | CPP AGI | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-00816 | PS5-21-OB-8976B |  | H | H | Missing insulation on duct | KENT | PS5-82-01 - Structural Steel A |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00817 | PS5-85-UR-1817B |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-01-06 - Deluge System | 2026-08-14 | Closed | Mohamed, Ali | PS5 - Milestone D | 3
PL-00818 | PS5-61-OB-5075D |  | H | H | Thermostat calibration needed | CPP AGI | PS5-02-03 - Fuel Gas System | 2026-10-08 | Closed | Smith, John | PS5 - Milestone E | 4
PL-00819 | PS5-73-NER-6283D |  | S | S | Emergency shower not tested | CPP AGI | PS5-60-10 - Power Generation Package D |  | On Hold | Wang, Li | PS5 - Milestone B | 1.1
PL-00820 | PS5-39-NI-8555C |  | I | I | Pressure gauge reads zero | CPP AGI | PS5-09-01 - Transformer 33kV/6.6kV |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-00821 | PS5-46-NER-6803B |  | E | E | Incomplete cable termination | KENT | PS5-04-02 - SIS System |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-00822 | PS5-79-OB-4975C |  | T | T | CAT6 cable untidied | CPP AGI | PS5-01-04 - Fire Water Ring Main |  | Originated | Jean, Pierre | PS5 - Milestone I | 8
PL-00823 | PS5-35-UR-6463C |  | M | M | Coupling guard loose | CPP AGI | PS5-01-07 - Hydrant System | 2026-08-03 | Closed | Kumar, Raj | PS5 - Milestone G | 6
PL-00824 | PS5-18-IK-3535B |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-11-01 - Guard Hut A | 2026-12-24 | Closed | Wang, Li | PS5 - Milestone A | 1
PL-00825 | PS5-27-UR-8761A |  | B | B | Cracked wall plaster | CPP AGI | PS5-99-01 - Area Completion Building Area | 2026-12-04 | Closed | Smith, John | PS5 - Milestone D | 3
PL-00826 | PS5-88-NER-3018B |  | S | S | Deluge valve not primed | KENT | PS5-01-08 - Drencher System | 2026-12-09 | Closed | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00827 | PS5-76-NER-7018C |  | H | H | AHU filter not installed | CPP AGI | PS5-04-03 - 33kV ICSS System | 2026-10-22 | Closed | Smith, John | PS5 - Milestone D | 3
PL-00828 | PS5-16-NI-7380A |  | E | E | Wrong cable glanding | EPS UNATRAC | PS5-82-01 - Structural Steel A |  | On Hold | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00829 | PS5-02-IK-6861C |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-01-06 - Deluge System |  | On Hold | Jean, Pierre | PS5 - Milestone F | 5
PL-00830 | PS5-73-OB-8528C |  | P | P | Pipe support missing | KENT | PS5-60-04 - Power Generation Package B |  | Originated | Mohamed, Ali | PS5 - Milestone I | 8
PL-00831 | PS5-85-IK-9306D |  | M | M | Vibration level exceeded | KENT | PS5-60-07 - Power Generation Package C |  | On Hold | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00832 | PS5-94-IK-4796A |  | H | H | Duct leakage at joint | CPP AGI | PS5-10-06 - Vent System |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-00833 | PS5-50-NER-2054A |  | T | T | CAT6 cable untidied | KENT | PS5-10-06 - Vent System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-00834 | PS5-90-NER-7187A |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-02-01 - Diesel Storage Tank |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-00835 | PS5-21-NER-9659D |  | I | I | Missing loop diagram | KENT | PS5-06-03 - Lightning Protection |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-00836 | PS5-73-NI-2179B |  | B | B | Incomplete paint touch-up | EPS UNATRAC | PS5-03-01 - ESD System |  | Originated | Wang, Li | PS5 - Milestone D | 3
PL-00837 | PS5-80-NI-3258D |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-00838 | PS5-70-OB-1369A |  | S | S | Eye wash station blocked | KENT | PS5-02-01 - Diesel Storage Tank | 2026-09-02 | Closed | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00839 | PS5-74-IK-9482D |  | S | S | Fire alarm panel fault | KENT | PS5-12-01 - Cooling Tower |  | On Hold | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00840 | PS5-84-UR-1528B |  | S | S | Eye wash station blocked | EPS UNATRAC | PS5-01-08 - Drencher System |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-00841 | PS5-73-NI-1579B |  | P | P | Flange bolt torque incomplete | CPP AGI | PS5-01-08 - Drencher System | 2026-09-16 | Closed | Smith, John | PS5 - Milestone C | 2
PL-00842 | PS5-45-NER-8824B |  | E | E | Missing earth continuity label | KENT | PS5-82-07 - Guard Huts | 2026-12-08 | Closed | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00843 | PS5-03-NI-8899A |  | B | B | Missing door closer | KENT | PS5-01-04 - Fire Water Ring Main |  | In Progress | Wang, Li | PS5 - Milestone D | 3
PL-00844 | PS5-48-OB-4172B |  | H | H | Duct leakage at joint | KENT | PS5-62-01 - Cable Tray Main |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-00845 | PS5-17-NER-3958B |  | I | I | Instrument tubing leak | CPP AGI | PS5-02-03 - Fuel Gas System | 2026-08-03 | Closed | Mohamed, Ali | PS5 - Milestone A | 1
PL-00846 | PS5-10-UR-5099D |  | I | I | Missing loop diagram | KENT | PS5-10-02 - Utility Pipe Rack |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-00847 | PS5-84-IK-9631D |  | P | P | Valve handwheel stiff | EPS UNATRAC | PS5-07-03 - AHU System |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-00848 | PS5-18-NI-4777B |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-01-07 - Hydrant System |  | On Hold | Jean, Pierre | PS5 - Milestone F | 5
PL-00849 | PS5-98-NER-2871A |  | E | E | Cable tray not properly supported | KENT | PS5-13-01 - Flare System |  | Originated | Mohamed, Ali | PS5 - Milestone C | 2
PL-00850 | PS5-50-NER-1308D |  | M | M | Bearing temperature high | KENT | PS5-60-04 - Power Generation Package B |  | On Hold | Smith, John | PS5 - Milestone E | 4
PL-00851 | PS5-40-UR-9872D |  | B | B | Missing fire extinguisher signage | KENT | PS5-07-03 - AHU System |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-00852 | PS5-56-NER-1935D |  | P | P | Missing pipe stress label | KENT | PS5-09-02 - Transformer 6.6kV/0.4kV |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-00853 | PS5-96-IK-3160D |  | M | M | Coupling guard loose | EPS UNATRAC | PS5-82-01 - Structural Steel A |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-00854 | PS5-05-NI-5493B |  | M | M | Motor fan guard missing | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-00855 | PS5-57-NER-1282B |  | B | B | Missing door closer | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-00856 | PS5-09-NER-3945B |  | P | P | Valve handwheel stiff | EPS UNATRAC | PS5-82-07 - Guard Huts | 2026-12-18 | Closed | Mohamed, Ali | PS5 - Milestone I | 8
PL-00857 | PS5-07-IK-2875C |  | T | T | Missing cable label | KENT | PS5-04-01 - DCS System |  | In Progress | Wang, Li | PS5 - Milestone D | 3
PL-00858 | PS5-33-UR-6789C |  | T | T | Fiber patch panel unorganized | EPS UNATRAC | PS5-10-05 - Drain System |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-00859 | PS5-31-IK-6337C |  | I | I | Missing instrument tag | CPP AGI | PS5-11-03 - Admin Building |  | Originated | Smith, John | PS5 - Milestone B | 1.1
PL-00860 | PS5-48-NER-5817C |  | E | E | Missing earth continuity label | KENT | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-10-14 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-00861 | PS5-41-NI-9326D |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-10-02 - Utility Pipe Rack |  | On Hold | Mohamed, Ali | PS5 - Milestone C | 2
PL-00862 | PS5-11-UR-4679C |  | I | I | Control valve actuator fault | KENT | PS5-60-01 - Power Generation Package A |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-00863 | PS5-57-OB-5410A |  | S | S | Fire alarm panel fault | KENT | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-00864 | PS5-96-UR-4949B |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-11-01 - Guard Hut A |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-00865 | PS5-30-NER-7862A |  | E | E | Missing earth continuity label | KENT | PS5-12-01 - Cooling Tower |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-00866 | PS5-11-NER-7898C |  | I | I | Missing loop diagram | CPP AGI | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone C | 2
PL-00867 | PS5-34-NI-8698C |  | T | T | Missing cable label | EPS UNATRAC | PS5-06-03 - Lightning Protection |  | On Hold | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00868 | PS5-50-NER-6805A |  | S | S | Deluge valve not primed | KENT | PS5-01-04 - Fire Water Ring Main |  | On Hold | Kumar, Raj | PS5 - Milestone C | 2
PL-00869 | PS5-14-UR-2208C |  | I | I | Instrument tubing leak | KENT | PS5-10-02 - Utility Pipe Rack |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-00870 | PS5-11-IK-1127C |  | S | S | Eye wash station blocked | KENT | PS5-63-01 - Electrical Earthing | 2026-12-27 | Closed | Wang, Li | PS5 - Milestone G | 6
PL-00871 | PS5-39-NER-6588A |  | T | T | CCTV camera not focused | CPP AGI | PS5-60-01 - Power Generation Package A |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-00872 | PS5-94-IK-8053C |  | S | S | Fire alarm panel fault | KENT | PS5-10-01 - Main Pipe Rack |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-00873 | PS5-37-OB-2738D |  | P | P | Gasket protruding from flange | CPP AGI | PS5-03-01 - ESD System | 2026-11-08 | Closed | Mohamed, Ali | PS5 - Milestone F | 5
PL-00874 | PS5-70-NI-4197A |  | H | H | Duct leakage at joint | CPP AGI | PS5-03-01 - ESD System |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-00875 | PS5-15-UR-8281D |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-10-01 - Main Pipe Rack |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-00876 | PS5-96-IK-2218B |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-04-02 - SIS System |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-00877 | PS5-05-NER-2645D |  | M | M | Vibration level exceeded | EPS UNATRAC | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-00878 | PS5-63-IK-9138B |  | I | I | Missing loop diagram | CPP AGI | PS5-01-05 - Foam System | 2026-10-16 | Closed | Wang, Li | PS5 - Milestone A | 1
PL-00879 | PS5-91-IK-1635B |  | E | E | Wrong cable glanding | CPP AGI | PS5-07-02 - Chiller System B |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-00880 | PS5-38-NER-9031D |  | S | S | Missing safety sign | CPP AGI | PS5-08-01 - Compressor Air System |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-00881 | PS5-54-NER-6331A |  | P | P | Insulation damaged | EPS UNATRAC | PS5-82-07 - Guard Huts |  | Originated | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-00882 | PS5-17-NER-9014C |  | H | H | Thermostat calibration needed | KENT | PS5-82-01 - Structural Steel A |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-00883 | PS5-34-OB-7737B |  | B | B | Missing door closer | EPS UNATRAC | PS5-10-02 - Utility Pipe Rack |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-00884 | PS5-29-NI-3728C |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-10-15 | Closed | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-00885 | PS5-91-OB-6778D |  | P | P | Missing pipe stress label | CPP AGI | PS5-04-01 - DCS System |  | Originated | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-00886 | PS5-92-IK-5754D |  | B | B | Damaged ceiling panel | EPS UNATRAC | PS5-07-01 - Chiller System A |  | In Progress | Mohamed, Ali | PS5 - Milestone F | 5
PL-00887 | PS5-97-NI-2679C |  | S | S | Missing safety sign | CPP AGI | PS5-07-02 - Chiller System B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-00888 | PS5-16-NER-7565A |  | H | H | Thermostat calibration needed | KENT | PS5-10-01 - Main Pipe Rack |  | Originated | Mohamed, Ali | PS5 - Milestone E | 4
PL-00889 | PS5-70-NI-3487A |  | E | E | Missing electrical hazard sign | KENT | PS5-02-01 - Diesel Storage Tank |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-00890 | PS5-26-UR-5329D |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-10-04 - Process piping B |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-00891 | PS5-37-NI-9300A |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-10-02 - Utility Pipe Rack |  | Originated | Smith, John | PS5 - Milestone G | 6
PL-00892 | PS5-51-IK-8325B |  | S | S | Fire alarm panel fault | CPP AGI | PS5-13-01 - Flare System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-00893 | PS5-27-NER-5095A |  | M | M | Bearing temperature high | CPP AGI | PS5-11-01 - Guard Hut A |  | On Hold | Kumar, Raj | PS5 - Milestone C | 2
PL-00894 | PS5-44-IK-1598B |  | T | T | CCTV camera not focused | KENT | PS5-07-04 - FCU System |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-00895 | PS5-84-IK-6272B |  | S | S | Missing safety sign | EPS UNATRAC | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-00896 | PS5-21-NI-2990A |  | E | E | Incomplete cable termination | CPP AGI | PS5-03-02 - Fire & Gas Detection |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00897 | PS5-16-NER-5820C |  | B | B | Incomplete paint touch-up | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-11-01 | Closed | Mohamed, Ali | PS5 - Milestone H | 7
PL-00898 | PS5-61-NER-4450D |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-13-01 - Flare System | 2026-12-20 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-00899 | PS5-23-IK-8708A |  | H | H | Duct leakage at joint | EPS UNATRAC | PS5-05-02 - PA/GA System |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-00900 | PS5-60-NI-3563A |  | I | I | Missing instrument tag | KENT | PS5-06-03 - Lightning Protection |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-00901 | PS5-75-OB-7017C |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-11-03 - Admin Building |  | On Hold | Mohamed, Ali | PS5 - Milestone A | 1
PL-00902 | PS5-67-NI-7274B |  | I | I | Control valve actuator fault | CPP AGI | PS5-02-01 - Diesel Storage Tank | 2026-12-04 | Closed | Kumar, Raj | PS5 - Milestone C | 2
PL-00903 | PS5-01-OB-2274D |  | M | M | Pump alignment required | EPS UNATRAC | PS5-82-02 - Structural Steel B | 2026-09-06 | Closed | Jean, Pierre | PS5 - Milestone D | 3
PL-00904 | PS5-49-NER-8773B |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-00905 | PS5-72-NER-9029C |  | E | E | Wrong cable glanding | EPS UNATRAC | PS5-07-02 - Chiller System B |  | On Hold | Wang, Li | PS5 - Milestone C | 2
PL-00906 | PS5-72-IK-7266B |  | E | E | Outgoing breaker not labeled | KENT | PS5-62-01 - Cable Tray Main | 2026-11-07 | Closed | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-00907 | PS5-13-OB-5157C |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-62-02 - Cable Tray Secondary |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-00908 | PS5-33-OB-1937D |  | M | M | Pump alignment required | KENT | PS5-01-05 - Foam System |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-00909 | PS5-91-IK-3156A |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-63-04 - Electrical Earthing EITS Building | 2026-12-23 | Closed | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00910 | PS5-79-UR-6450D |  | T | T | CAT6 cable untidied | KENT | PS5-01-08 - Drencher System |  | Originated | Wang, Li | PS5 - Milestone F | 5
PL-00911 | PS5-86-UR-2064A |  | H | H | FCU drain pipe not connected | KENT | PS5-12-02 - Water Treatment |  | Originated | Jean, Pierre | PS5 - Milestone I | 8
PL-00912 | PS5-65-NER-3833C |  | M | M | Pump alignment required | KENT | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-00913 | PS5-15-UR-3990C |  | M | M | Missing rotation arrow | CPP AGI | PS5-11-03 - Admin Building |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00914 | PS5-83-IK-3174B |  | B | B | Missing door closer | KENT | PS5-05-02 - PA/GA System | 2026-10-27 | Closed | Wang, Li | PS5 - Milestone A | 1
PL-00915 | PS5-38-OB-8202B |  | M | M | Bearing temperature high | CPP AGI | PS5-05-03 - CCTV System | 2026-10-07 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-00916 | PS5-50-IK-9813C |  | P | P | Gasket protruding from flange | KENT | PS5-11-03 - Admin Building |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-00917 | PS5-34-IK-8662B |  | P | P | Flange bolt torque incomplete | CPP AGI | PS5-10-01 - Main Pipe Rack |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-00918 | PS5-85-NI-1554B |  | H | H | Duct leakage at joint | EPS UNATRAC | PS5-82-02 - Structural Steel B |  | In Progress | Wang, Li | PS5 - Milestone C | 2
PL-00919 | PS5-24-OB-6018A |  | P | P | Missing pipe stress label | CPP AGI | PS5-01-02 - Fire Water Pump A |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-00920 | PS5-32-OB-7114C |  | B | B | Missing door closer | EPS UNATRAC | PS5-62-02 - Cable Tray Secondary |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-00921 | PS5-54-NER-5413D |  | S | S | Missing safety sign | CPP AGI | PS5-10-03 - Process piping A |  | On Hold | Kumar, Raj | PS5 - Milestone A | 1
PL-00922 | PS5-17-OB-1881D |  | B | B | Damaged ceiling panel | CPP AGI | PS5-05-01 - Telecom Network | 2026-12-25 | Closed | Jean, Pierre | PS5 - Milestone I | 8
PL-00923 | PS5-11-IK-4869D |  | P | P | Insulation damaged | EPS UNATRAC | PS5-63-04 - Electrical Earthing EITS Building | 2026-09-10 | Closed | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00924 | PS5-45-UR-8713C |  | I | I | Pressure gauge reads zero | CPP AGI | PS5-04-04 - 33kV PCS System |  | On Hold | Wang, Li | PS5 - Milestone I | 8
PL-00925 | PS5-17-OB-3187B |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-82-02 - Structural Steel B |  | On Hold | Mohamed, Ali | PS5 - Milestone G | 6
PL-00926 | PS5-04-IK-3918D |  | S | S | Eye wash station blocked | KENT | PS5-60-07 - Power Generation Package C |  | Originated | Mohamed, Ali | PS5 - Milestone I | 8
PL-00927 | PS5-18-NER-4079A |  | P | P | Valve handwheel stiff | CPP AGI | PS5-99-03 - Area Completion Utilities Area |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-00928 | PS5-50-NER-1570B |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-11-02 - Guard Hut B |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-00929 | PS5-88-UR-7626D |  | H | H | Duct leakage at joint | EPS UNATRAC | PS5-60-07 - Power Generation Package C |  | On Hold | Jean, Pierre | PS5 - Milestone I | 8
PL-00930 | PS5-86-NER-7921D |  | P | P | Valve handwheel stiff | KENT | PS5-04-01 - DCS System |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-00931 | PS5-47-UR-3930D |  | M | M | Vibration level exceeded | KENT | PS5-03-03 - Flame Detector System |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-00932 | PS5-94-NER-8125A |  | E | E | Wrong cable glanding | KENT | PS5-04-04 - 33kV PCS System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-00933 | PS5-87-OB-1385C |  | E | E | Missing earth continuity label | EPS UNATRAC | PS5-99-01 - Area Completion Building Area |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-00934 | PS5-15-OB-1599C |  | P | P | Insulation damaged | KENT | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-00935 | PS5-36-OB-8504C |  | H | H | Damper not operational | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | Originated | Wang, Li | PS5 - Milestone I | 8
PL-00936 | PS5-82-UR-7257C |  | T | T | Intercom not functioning | KENT | PS5-01-06 - Deluge System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00937 | PS5-84-UR-8101D |  | P | P | Pipe support missing | KENT | PS5-10-03 - Process piping A |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-00938 | PS5-48-NI-8748A |  | M | M | Bearing temperature high | CPP AGI | PS5-10-03 - Process piping A |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-00939 | PS5-35-UR-7671A |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-09-04 - 0.4kV Switchboard |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-00940 | PS5-03-OB-4621A |  | H | H | Missing insulation on duct | CPP AGI | PS5-09-04 - 0.4kV Switchboard |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-00941 | PS5-44-OB-6674D |  | T | T | Missing cable label | EPS UNATRAC | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-00942 | PS5-85-NI-2287C |  | T | T | CCTV camera not focused | CPP AGI | PS5-07-01 - Chiller System A |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-00943 | PS5-87-NER-1484A |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-07-01 - Chiller System A |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-00944 | PS5-96-NER-4845B |  | P | P | Missing pipe stress label | KENT | PS5-62-01 - Cable Tray Main |  | On Hold | Jean, Pierre | PS5 - Milestone G | 6
PL-00945 | PS5-23-IK-7571C |  | S | S | Eye wash station blocked | EPS UNATRAC | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone B | 1.1
PL-00946 | PS5-98-OB-9229C |  | S | S | Missing safety sign | KENT | PS5-09-04 - 0.4kV Switchboard |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-00947 | PS5-69-OB-8602C |  | S | S | Deluge valve not primed | CPP AGI | PS5-99-02 - Area Completion Process Area | 2026-11-10 | Closed | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-00948 | PS5-79-NI-9247D |  | S | S | Fire alarm panel fault | CPP AGI | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-00949 | PS5-88-UR-7066A |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-01-03 - Fire Water Pump B |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-00950 | PS5-26-OB-3173B |  | S | S | Fire extinguisher expired | KENT | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-00951 | PS5-60-NI-2821D |  | T | T | CAT6 cable untidied | CPP AGI | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone D | 3
PL-00952 | PS5-67-NER-7313A |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-82-01 - Structural Steel A |  | Originated | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-00953 | PS5-93-UR-6953B |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-01-04 - Fire Water Ring Main |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-00954 | PS5-85-OB-3325D |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-09-12 | Closed | Jean, Pierre | PS5 - Milestone B | 1.1
PL-00955 | PS5-97-IK-5259B |  | M | M | Motor fan guard missing | EPS UNATRAC | PS5-03-01 - ESD System |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-00956 | PS5-67-OB-1425A |  | P | P | Valve handwheel stiff | CPP AGI | PS5-63-01 - Electrical Earthing |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-00957 | PS5-61-NER-5831A |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-10-02 - Utility Pipe Rack |  | On Hold | Jean, Pierre | PS5 - Milestone E | 4
PL-00958 | PS5-75-UR-5250B |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-10-02 - Utility Pipe Rack | 2026-12-10 | Closed | Wang, Li | PS5 - Milestone G | 6
PL-00959 | PS5-41-NI-7133B |  | S | S | Missing safety sign | KENT | PS5-82-07 - Guard Huts |  | On Hold | Wang, Li | PS5 - Milestone C | 2
PL-00960 | PS5-44-IK-6067A |  | H | H | Damper not operational | CPP AGI | PS5-82-07 - Guard Huts |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-00961 | PS5-30-IK-6956C |  | E | E | Incomplete cable termination | KENT | PS5-06-03 - Lightning Protection |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-00962 | PS5-73-NI-5062A |  | E | E | Outgoing breaker not labeled | EPS UNATRAC | PS5-11-01 - Guard Hut A |  | Originated | Jean, Pierre | PS5 - Milestone I | 8
PL-00963 | PS5-17-NI-5960A |  | I | I | Missing loop diagram | CPP AGI | PS5-07-04 - FCU System | 2026-09-24 | Closed | Jean, Pierre | PS5 - Milestone H | 7
PL-00964 | PS5-10-IK-8836A |  | T | T | Fiber patch panel unorganized | KENT | PS5-82-01 - Structural Steel A |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-00965 | PS5-75-NER-2827C |  | I | I | Pressure gauge reads zero | CPP AGI | PS5-03-01 - ESD System |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-00966 | PS5-62-NI-5649D |  | I | I | Instrument tubing leak | KENT | PS5-63-04 - Electrical Earthing EITS Building | 2026-09-11 | Closed | Mohamed, Ali | PS5 - Milestone A | 1
PL-00967 | PS5-97-IK-8988A |  | I | I | Control valve actuator fault | CPP AGI | PS5-11-02 - Guard Hut B |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-00968 | PS5-57-OB-9824D |  | T | T | Missing cable label | CPP AGI | PS5-05-01 - Telecom Network |  | Originated | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-00969 | PS5-14-OB-4445C |  | I | I | Missing loop diagram | EPS UNATRAC | PS5-07-02 - Chiller System B |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-00970 | PS5-42-NI-8762C |  | H | H | AHU filter not installed | CPP AGI | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-00971 | PS5-43-OB-6166B |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-07-04 - FCU System |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-00972 | PS5-83-IK-8485D |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-00973 | PS5-72-IK-4522C |  | I | I | Pressure gauge reads zero | KENT | PS5-07-01 - Chiller System A | 2026-11-11 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-00974 | PS5-50-NER-5093B |  | E | E | Missing electrical hazard sign | KENT | PS5-02-01 - Diesel Storage Tank | 2026-08-25 | Closed | Kumar, Raj | PS5 - Milestone D | 3
PL-00975 | PS5-57-OB-2819B |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-01-08 - Drencher System |  | Originated | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00976 | PS5-12-NER-5017B |  | P | P | Missing pipe stress label | KENT | PS5-61-01 - 33kV Switchboard EITS Building |  | On Hold | Wang, Li | PS5 - Milestone C | 2
PL-00977 | PS5-96-IK-4016B |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-10-02 - Utility Pipe Rack | 2026-10-25 | Closed | Smith, John | PS5 - Milestone A | 1
PL-00978 | PS5-03-IK-2952C |  | P | P | Insulation damaged | KENT | PS5-11-01 - Guard Hut A |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-00979 | PS5-05-NI-6358D |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-01-07 - Hydrant System |  | Originated | Mohamed, Ali | PS5 - Milestone I | 8
PL-00980 | PS5-12-NI-8675C |  | P | P | Pipe support missing | KENT | PS5-01-09 - Inergen for EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-00981 | PS5-24-NI-6567B |  | S | S | Deluge valve not primed | CPP AGI | PS5-09-04 - 0.4kV Switchboard |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-00982 | PS5-03-UR-4690B |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-01-03 - Fire Water Pump B |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-00983 | PS5-46-NI-3500A |  | I | I | Missing loop diagram | KENT | PS5-10-06 - Vent System |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-00984 | PS5-45-UR-6365D |  | M | M | Missing rotation arrow | KENT | PS5-06-01 - AC UPS - EITS Building |  | Originated | Wang, Li | PS5 - Milestone B | 1.1
PL-00985 | PS5-16-NER-1416B |  | I | I | Missing instrument tag | EPS UNATRAC | PS5-06-03 - Lightning Protection | 2026-08-05 | Closed | Wang, Li | PS5 - Milestone E | 4
PL-00986 | PS5-76-UR-2521D |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-00987 | PS5-27-UR-9305B |  | E | E | Wrong cable glanding | CPP AGI | PS5-05-01 - Telecom Network | 2026-10-14 | Closed | Kumar, Raj | PS5 - Milestone D | 3
PL-00988 | PS5-46-OB-6078D |  | E | E | Incomplete cable termination | CPP AGI | PS5-63-04 - Electrical Earthing EITS Building |  | Originated | Wang, Li | PS5 - Milestone A | 1
PL-00989 | PS5-94-OB-1743A |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-07-04 - FCU System |  | In Progress | Jean, Pierre | PS5 - Milestone B | 1.1
PL-00990 | PS5-95-OB-7089C |  | B | B | Incomplete floor tiling | CPP AGI | PS5-04-01 - DCS System | 2026-12-26 | Closed | Smith, John | PS5 - Milestone I | 8
PL-00991 | PS5-04-NER-4343B |  | H | H | Thermostat calibration needed | CPP AGI | PS5-05-03 - CCTV System |  | On Hold | Mohamed, Ali | PS5 - Milestone I | 8
PL-00992 | PS5-95-IK-7679A |  | M | M | Bearing temperature high | CPP AGI | PS5-10-06 - Vent System |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-00993 | PS5-15-NER-8609D |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-05-01 - Telecom Network |  | Originated | Smith, John | PS5 - Milestone B | 1.1
PL-00994 | PS5-70-OB-2579B |  | H | H | Thermostat calibration needed | KENT | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-00995 | PS5-96-UR-7616B |  | I | I | Control valve actuator fault | CPP AGI | PS5-04-01 - DCS System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-00996 | PS5-74-OB-3157B |  | I | I | Instrument tubing leak | KENT | PS5-07-03 - AHU System | 2026-12-17 | Closed | Wang, Li | PS5 - Milestone E | 4
PL-00997 | PS5-82-UR-4896A |  | H | H | Missing insulation on duct | CPP AGI | PS5-01-05 - Foam System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-00998 | PS5-57-UR-5576C |  | T | T | CCTV camera not focused | KENT | PS5-82-07 - Guard Huts | 2026-12-09 | Closed | Mohamed, Ali | PS5 - Milestone F | 5
PL-00999 | PS5-85-UR-6609D |  | P | P | Valve handwheel stiff | EPS UNATRAC | PS5-06-01 - AC UPS - EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01000 | PS5-15-UR-5844A |  | P | P | Valve handwheel stiff | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building |  | On Hold | Mohamed, Ali | PS5 - Milestone A | 1
PL-01001 | PS5-51-NI-4192A |  | T | T | Intercom not functioning | CPP AGI | PS5-62-01 - Cable Tray Main |  | On Hold | Jean, Pierre | PS5 - Milestone I | 8
PL-01002 | PS5-68-UR-9735B |  | B | B | Incomplete floor tiling | KENT | PS5-06-03 - Lightning Protection |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-01003 | PS5-55-IK-5561A |  | H | H | AHU filter not installed | KENT | PS5-13-01 - Flare System | 2026-09-18 | Closed | Mohamed, Ali | PS5 - Milestone C | 2
PL-01004 | PS5-10-OB-6105A |  | S | S | Deluge valve not primed | CPP AGI | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-01005 | PS5-83-NER-7406C |  | E | E | Missing earth continuity label | CPP AGI | PS5-01-08 - Drencher System | 2026-11-26 | Closed | Mohamed, Ali | PS5 - Milestone G | 6
PL-01006 | PS5-87-OB-6365A |  | E | E | Cable tray not properly supported | CPP AGI | PS5-07-03 - AHU System | 2026-09-15 | Closed | Kumar, Raj | PS5 - Milestone E | 4
PL-01007 | PS5-59-IK-2153D |  | M | M | Motor fan guard missing | KENT | PS5-03-02 - Fire & Gas Detection | 2026-12-24 | Closed | Mohamed, Ali | PS5 - Milestone H | 7
PL-01008 | PS5-55-NI-3759D |  | M | M | Motor fan guard missing | EPS UNATRAC | PS5-01-06 - Deluge System |  | On Hold | Smith, John | PS5 - Milestone G | 6
PL-01009 | PS5-82-UR-5590D |  | M | M | Motor fan guard missing | CPP AGI | PS5-07-03 - AHU System | 2026-11-14 | Closed | Mohamed, Ali | PS5 - Milestone I | 8
PL-01010 | PS5-13-NER-4977C |  | M | M | Missing rotation arrow | CPP AGI | PS5-11-01 - Guard Hut A |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-01011 | PS5-49-NI-9502D |  | S | S | Deluge valve not primed | KENT | PS5-09-03 - Motor Control Center |  | On Hold | Smith, John | PS5 - Milestone B | 1.1
PL-01012 | PS5-75-NI-7911D |  | B | B | Incomplete paint touch-up | EPS UNATRAC | PS5-03-02 - Fire & Gas Detection |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-01013 | PS5-96-NER-1420A |  | B | B | Incomplete floor tiling | KENT | PS5-11-03 - Admin Building |  | On Hold | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01014 | PS5-46-OB-6773D |  | P | P | Pipe support missing | EPS UNATRAC | PS5-03-01 - ESD System |  | On Hold | Mohamed, Ali | PS5 - Milestone E | 4
PL-01015 | PS5-27-NI-9966C |  | T | T | Intercom not functioning | CPP AGI | PS5-01-07 - Hydrant System |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-01016 | PS5-95-IK-6186D |  | P | P | Flange bolt torque incomplete | KENT | PS5-05-03 - CCTV System |  | On Hold | Wang, Li | PS5 - Milestone H | 7
PL-01017 | PS5-34-NER-6744B |  | E | E | Incomplete cable termination | CPP AGI | PS5-60-10 - Power Generation Package D |  | In Progress | Mohamed, Ali | PS5 - Milestone F | 5
PL-01018 | PS5-90-NI-5853D |  | H | H | FCU drain pipe not connected | KENT | PS5-05-02 - PA/GA System |  | Originated | Jean, Pierre | PS5 - Milestone F | 5
PL-01019 | PS5-92-OB-9729B |  | S | S | Emergency shower not tested | CPP AGI | PS5-02-01 - Diesel Storage Tank |  | Originated | Smith, John | PS5 - Milestone D | 3
PL-01020 | PS5-32-NI-3539C |  | E | E | Wrong cable glanding | CPP AGI | PS5-10-02 - Utility Pipe Rack |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01021 | PS5-32-UR-8917D |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-07-03 - AHU System | 2026-09-01 | Closed | Kumar, Raj | PS5 - Milestone D | 3
PL-01022 | PS5-96-OB-6963D |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-61-01 - 33kV Switchboard EITS Building |  | On Hold | Smith, John | PS5 - Milestone C | 2
PL-01023 | PS5-42-IK-9819C |  | P | P | Flange bolt torque incomplete | CPP AGI | PS5-12-02 - Water Treatment |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-01024 | PS5-90-NI-4669B |  | T | T | CCTV camera not focused | KENT | PS5-10-05 - Drain System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01025 | PS5-58-NI-1942D |  | T | T | PA speaker not tested | KENT | PS5-62-02 - Cable Tray Secondary |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-01026 | PS5-04-NI-9041B |  | H | H | Damper not operational | KENT | PS5-01-09 - Inergen for EITS Building |  | Originated | Smith, John | PS5 - Milestone F | 5
PL-01027 | PS5-66-NER-3363D |  | I | I | Missing instrument tag | KENT | PS5-63-01 - Electrical Earthing |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-01028 | PS5-79-UR-9679B |  | P | P | Pipe support missing | CPP AGI | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-01029 | PS5-16-OB-2459A |  | I | I | Pressure gauge reads zero | KENT | PS5-08-02 - Nitrogen Generator |  | On Hold | Kumar, Raj | PS5 - Milestone C | 2
PL-01030 | PS5-13-OB-6818A |  | S | S | Missing safety sign | CPP AGI | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-01031 | PS5-68-OB-1334D |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-02-03 - Fuel Gas System | 2026-10-15 | Closed | Kumar, Raj | PS5 - Milestone C | 2
PL-01032 | PS5-73-OB-2136D |  | B | B | Incomplete floor tiling | KENT | PS5-13-01 - Flare System | 2026-10-01 | Closed | Wang, Li | PS5 - Milestone B | 1.1
PL-01033 | PS5-23-NER-3908C |  | T | T | PA speaker not tested | KENT | PS5-06-01 - AC UPS - EITS Building | 2026-12-12 | Closed | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01034 | PS5-76-NI-3742D |  | B | B | Missing door closer | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | On Hold | Jean, Pierre | PS5 - Milestone E | 4
PL-01035 | PS5-86-NI-2072B |  | H | H | Missing insulation on duct | CPP AGI | PS5-11-02 - Guard Hut B |  | On Hold | Jean, Pierre | PS5 - Milestone H | 7
PL-01036 | PS5-85-NI-2618D |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-99-01 - Area Completion Building Area |  | In Progress | Wang, Li | PS5 - Milestone D | 3
PL-01037 | PS5-98-IK-5799D |  | P | P | Insulation damaged | EPS UNATRAC | PS5-60-07 - Power Generation Package C |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-01038 | PS5-62-NI-7370B |  | S | S | Eye wash station blocked | KENT | PS5-60-01 - Power Generation Package A |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-01039 | PS5-70-IK-6138C |  | B | B | Cracked wall plaster | KENT | PS5-01-06 - Deluge System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01040 | PS5-66-OB-1732D |  | B | B | Missing fire extinguisher signage | CPP AGI | PS5-10-03 - Process piping A | 2026-12-17 | Closed | Smith, John | PS5 - Milestone G | 6
PL-01041 | PS5-82-NI-1255A |  | H | H | AHU filter not installed | KENT | PS5-07-03 - AHU System |  | Originated | Jean, Pierre | PS5 - Milestone F | 5
PL-01042 | PS5-48-NER-1733A |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-10-02 - Utility Pipe Rack |  | On Hold | Jean, Pierre | PS5 - Milestone A | 1
PL-01043 | PS5-49-OB-4104D |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-11-27 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-01044 | PS5-29-UR-2874A |  | B | B | Missing door closer | KENT | PS5-60-07 - Power Generation Package C |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01045 | PS5-51-OB-9786B |  | H | H | FCU drain pipe not connected | KENT | PS5-10-06 - Vent System |  | On Hold | Mohamed, Ali | PS5 - Milestone C | 2
PL-01046 | PS5-26-IK-9490D |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | On Hold | Smith, John | PS5 - Milestone G | 6
PL-01047 | PS5-09-IK-8142C |  | E | E | Incomplete cable termination | KENT | PS5-03-03 - Flame Detector System |  | Originated | Wang, Li | PS5 - Milestone D | 3
PL-01048 | PS5-41-UR-1232D |  | H | H | Missing insulation on duct | KENT | PS5-62-02 - Cable Tray Secondary |  | In Progress | Mohamed, Ali | PS5 - Milestone A | 1
PL-01049 | PS5-29-IK-4184B |  | H | H | Thermostat calibration needed | CPP AGI | PS5-11-03 - Admin Building | 2026-10-17 | Closed | Smith, John | PS5 - Milestone H | 7
PL-01050 | PS5-71-OB-1929A |  | B | B | Missing fire extinguisher signage | CPP AGI | PS5-62-02 - Cable Tray Secondary |  | On Hold | Smith, John | PS5 - Milestone B | 1.1
PL-01051 | PS5-01-NER-1056C |  | B | B | Missing door closer | CPP AGI | PS5-05-02 - PA/GA System |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-01052 | PS5-74-NER-5627C |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-07-03 - AHU System |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-01053 | PS5-69-OB-4667A |  | I | I | Missing instrument tag | EPS UNATRAC | PS5-99-01 - Area Completion Building Area |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-01054 | PS5-39-IK-1697B |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-60-04 - Power Generation Package B |  | On Hold | Kumar, Raj | PS5 - Milestone E | 4
PL-01055 | PS5-54-NER-8410B |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-60-10 - Power Generation Package D |  | On Hold | Smith, John | PS5 - Milestone C | 2
PL-01056 | PS5-32-IK-4128C |  | P | P | Gasket protruding from flange | CPP AGI | PS5-11-02 - Guard Hut B |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-01057 | PS5-28-NER-3315B |  | P | P | Missing pipe stress label | EPS UNATRAC | PS5-82-01 - Structural Steel A |  | On Hold | Wang, Li | PS5 - Milestone I | 8
PL-01058 | PS5-85-NER-9478B |  | T | T | PA speaker not tested | CPP AGI | PS5-10-03 - Process piping A |  | Originated | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01059 | PS5-60-IK-3139D |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-60-04 - Power Generation Package B | 2026-09-14 | Closed | Mohamed, Ali | PS5 - Milestone C | 2
PL-01060 | PS5-43-UR-6133D |  | B | B | Damaged ceiling panel | CPP AGI | PS5-03-01 - ESD System |  | Originated | Jean, Pierre | PS5 - Milestone B | 1.1
PL-01061 | PS5-58-NER-6547C |  | H | H | Missing insulation on duct | KENT | PS5-07-02 - Chiller System B |  | On Hold | Mohamed, Ali | PS5 - Milestone E | 4
PL-01062 | PS5-81-NER-5607C |  | E | E | Missing earth continuity label | KENT | PS5-05-01 - Telecom Network | 2026-09-18 | Closed | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-01063 | PS5-62-IK-1326C |  | H | H | Missing insulation on duct | EPS UNATRAC | PS5-62-02 - Cable Tray Secondary |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-01064 | PS5-09-IK-3210C |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-63-01 - Electrical Earthing |  | On Hold | Smith, John | PS5 - Milestone A | 1
PL-01065 | PS5-46-NI-9105A |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-03-03 - Flame Detector System |  | On Hold | Smith, John | PS5 - Milestone D | 3
PL-01066 | PS5-84-IK-6023B |  | H | H | AHU filter not installed | CPP AGI | PS5-12-02 - Water Treatment | 2026-10-06 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-01067 | PS5-80-UR-1314B |  | B | B | Incomplete floor tiling | CPP AGI | PS5-09-03 - Motor Control Center |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-01068 | PS5-47-NI-7955B |  | S | S | Eye wash station blocked | EPS UNATRAC | PS5-60-04 - Power Generation Package B |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-01069 | PS5-41-NI-2859A |  | P | P | Pipe support missing | KENT | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-08-26 | Closed | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01070 | PS5-12-UR-1158C |  | I | I | Missing instrument tag | CPP AGI | PS5-02-01 - Diesel Storage Tank |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-01071 | PS5-79-UR-1920C |  | E | E | Missing earth continuity label | CPP AGI | PS5-04-04 - 33kV PCS System |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-01072 | PS5-30-IK-1819C |  | E | E | Incomplete cable termination | KENT | PS5-06-01 - AC UPS - EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01073 | PS5-61-OB-2003B |  | I | I | Control valve actuator fault | CPP AGI | PS5-82-02 - Structural Steel B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01074 | PS5-97-IK-3661B |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-05-03 - CCTV System | 2026-09-06 | Closed | Mohamed, Ali | PS5 - Milestone D | 3
PL-01075 | PS5-88-OB-5611D |  | S | S | Fire extinguisher expired | KENT | PS5-99-03 - Area Completion Utilities Area | 2026-12-01 | Closed | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01076 | PS5-11-NER-1196D |  | E | E | Outgoing breaker not labeled | EPS UNATRAC | PS5-99-02 - Area Completion Process Area |  | On Hold | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-01077 | PS5-62-OB-9187B |  | P | P | Insulation damaged | KENT | PS5-12-02 - Water Treatment |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01078 | PS5-42-NER-8596D |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-07-04 - FCU System |  | Originated | Smith, John | PS5 - Milestone C | 2
PL-01079 | PS5-49-IK-7544B |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-04-03 - 33kV ICSS System |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-01080 | PS5-03-NER-7426A |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-04-04 - 33kV PCS System | 2026-10-11 | Closed | Mohamed, Ali | PS5 - Milestone C | 2
PL-01081 | PS5-63-UR-6789D |  | I | I | Transmitter not calibrated | CPP AGI | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-01082 | PS5-81-IK-6547C |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-10-02 - Utility Pipe Rack | 2026-11-01 | Closed | Kumar, Raj | PS5 - Milestone C | 2
PL-01083 | PS5-17-OB-8758A |  | S | S | Missing safety sign | KENT | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-01084 | PS5-61-OB-6582C |  | S | S | Eye wash station blocked | KENT | PS5-08-02 - Nitrogen Generator |  | On Hold | Wang, Li | PS5 - Milestone D | 3
PL-01085 | PS5-31-IK-9005C |  | I | I | Transmitter not calibrated | KENT | PS5-04-01 - DCS System |  | In Progress | Mohamed, Ali | PS5 - Milestone F | 5
PL-01086 | PS5-78-OB-2096B |  | E | E | Missing earth continuity label | EPS UNATRAC | PS5-60-04 - Power Generation Package B |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-01087 | PS5-46-NI-8906C |  | H | H | Missing insulation on duct | EPS UNATRAC | PS5-12-02 - Water Treatment |  | In Progress | Mohamed, Ali | PS5 - Milestone A | 1
PL-01088 | PS5-95-IK-9577D |  | T | T | CAT6 cable untidied | CPP AGI | PS5-10-05 - Drain System | 2026-10-24 | Closed | Jean, Pierre | PS5 - Milestone I | 8
PL-01089 | PS5-98-NER-2289B |  | S | S | Emergency shower not tested | KENT | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-08-21 | Closed | Smith, John | PS5 - Milestone A | 1
PL-01090 | PS5-26-NI-8427B |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-05-01 - Telecom Network |  | In Progress | Jean, Pierre | PS5 - Milestone H | 7
PL-01091 | PS5-19-OB-7144C |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-01-03 - Fire Water Pump B |  | Originated | Smith, John | PS5 - Milestone B | 1.1
PL-01092 | PS5-73-NI-1645D |  | P | P | Flange bolt torque incomplete | EPS UNATRAC | PS5-60-07 - Power Generation Package C |  | In Progress | Wang, Li | PS5 - Milestone C | 2
PL-01093 | PS5-21-IK-2505D |  | H | H | Missing insulation on duct | KENT | PS5-99-02 - Area Completion Process Area |  | On Hold | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01094 | PS5-68-NER-7487C |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-01095 | PS5-83-IK-8842A |  | I | I | Missing loop diagram | CPP AGI | PS5-63-01 - Electrical Earthing | 2026-12-01 | Closed | Jean, Pierre | PS5 - Milestone C | 2
PL-01096 | PS5-51-UR-9359D |  | H | H | AHU filter not installed | KENT | PS5-04-02 - SIS System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01097 | PS5-11-NI-7031C |  | S | S | Emergency shower not tested | KENT | PS5-01-09 - Inergen for EITS Building | 2026-08-12 | Closed | Smith, John | PS5 - Milestone A | 1
PL-01098 | PS5-66-NER-3619D |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-04-04 - 33kV PCS System |  | Originated | Mohamed, Ali | PS5 - Milestone I | 8
PL-01099 | PS5-58-UR-8299C |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-06-03 - Lightning Protection |  | On Hold | Wang, Li | PS5 - Milestone F | 5
PL-01100 | PS5-95-OB-4511D |  | S | S | Eye wash station blocked | KENT | PS5-07-01 - Chiller System A | 2026-09-25 | Closed | Mohamed, Ali | PS5 - Milestone C | 2
PL-01101 | PS5-40-UR-4545D |  | T | T | CAT6 cable untidied | CPP AGI | PS5-01-07 - Hydrant System |  | In Progress | Jean, Pierre | PS5 - Milestone D | 3
PL-01102 | PS5-63-NER-5675D |  | T | T | Intercom not functioning | CPP AGI | PS5-60-04 - Power Generation Package B |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-01103 | PS5-01-OB-8291B |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-03-02 - Fire & Gas Detection |  | On Hold | Jean, Pierre | PS5 - Milestone A | 1
PL-01104 | PS5-84-UR-5873D |  | E | E | Cable tray not properly supported | EPS UNATRAC | PS5-01-07 - Hydrant System | 2026-08-09 | Closed | Mohamed, Ali | PS5 - Milestone F | 5
PL-01105 | PS5-88-UR-8807A |  | H | H | Duct leakage at joint | KENT | PS5-09-02 - Transformer 6.6kV/0.4kV |  | On Hold | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01106 | PS5-20-IK-2067B |  | I | I | Pressure gauge reads zero | KENT | PS5-63-04 - Electrical Earthing EITS Building | 2026-08-24 | Closed | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01107 | PS5-06-UR-5601C |  | B | B | Incomplete paint touch-up | KENT | PS5-99-02 - Area Completion Process Area |  | On Hold | Smith, John | PS5 - Milestone G | 6
PL-01108 | PS5-01-UR-8132C |  | I | I | Missing instrument tag | EPS UNATRAC | PS5-09-03 - Motor Control Center |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-01109 | PS5-70-IK-7115C |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-01-07 - Hydrant System |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-01110 | PS5-99-OB-3418D |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-10-06 - Vent System |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-01111 | PS5-83-NER-8385D |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-12-02 - Water Treatment |  | Originated | Jean, Pierre | PS5 - Milestone G | 6
PL-01112 | PS5-81-IK-3285D |  | B | B | Incomplete floor tiling | KENT | PS5-11-02 - Guard Hut B |  | On Hold | Wang, Li | PS5 - Milestone I | 8
PL-01113 | PS5-01-OB-3698C |  | S | S | Deluge valve not primed | KENT | PS5-02-02 - Diesel Transfer Pump |  | On Hold | Wang, Li | PS5 - Milestone G | 6
PL-01114 | PS5-85-NER-4589C |  | P | P | Gasket protruding from flange | KENT | PS5-99-01 - Area Completion Building Area |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-01115 | PS5-89-OB-4962D |  | E | E | Wrong cable glanding | CPP AGI | PS5-07-03 - AHU System | 2026-11-05 | Closed | Jean, Pierre | PS5 - Milestone H | 7
PL-01116 | PS5-88-UR-2098B |  | E | E | Cable tray not properly supported | CPP AGI | PS5-06-02 - DC UPS - EITS Building |  | Originated | Smith, John | PS5 - Milestone A | 1
PL-01117 | PS5-27-OB-8020C |  | P | P | Insulation damaged | EPS UNATRAC | PS5-60-10 - Power Generation Package D |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-01118 | PS5-61-NER-9831D |  | B | B | Missing door closer | KENT | PS5-99-01 - Area Completion Building Area |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-01119 | PS5-33-NI-2508A |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-99-01 - Area Completion Building Area |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-01120 | PS5-42-OB-8392A |  | E | E | Incomplete cable termination | CPP AGI | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01121 | PS5-60-OB-7359D |  | B | B | Cracked wall plaster | CPP AGI | PS5-04-01 - DCS System |  | On Hold | Wang, Li | PS5 - Milestone A | 1
PL-01122 | PS5-21-UR-5756C |  | B | B | Missing door closer | EPS UNATRAC | PS5-09-01 - Transformer 33kV/6.6kV |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01123 | PS5-84-IK-7172A |  | H | H | Damper not operational | KENT | PS5-02-01 - Diesel Storage Tank |  | In Progress | Jean, Pierre | PS5 - Milestone D | 3
PL-01124 | PS5-17-NI-1387B |  | P | P | Valve handwheel stiff | CPP AGI | PS5-99-02 - Area Completion Process Area |  | In Progress | Wang, Li | PS5 - Milestone D | 3
PL-01125 | PS5-54-NER-1549B |  | S | S | Fire alarm panel fault | CPP AGI | PS5-01-03 - Fire Water Pump B |  | On Hold | Wang, Li | PS5 - Milestone I | 8
PL-01126 | PS5-32-IK-2982A |  | S | S | Fire extinguisher expired | KENT | PS5-01-09 - Inergen for EITS Building |  | Originated | Kumar, Raj | PS5 - Milestone B | 1.1
PL-01127 | PS5-09-IK-7770A |  | H | H | Duct leakage at joint | EPS UNATRAC | PS5-06-03 - Lightning Protection |  | In Progress | Jean, Pierre | PS5 - Milestone H | 7
PL-01128 | PS5-15-NI-5356C |  | I | I | Transmitter not calibrated | CPP AGI | PS5-04-03 - 33kV ICSS System | 2026-12-26 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-01129 | PS5-62-NER-4508A |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-10-05 - Drain System |  | On Hold | Kumar, Raj | PS5 - Milestone D | 3
PL-01130 | PS5-62-NI-2189C |  | E | E | Missing earth continuity label | CPP AGI | PS5-04-03 - 33kV ICSS System |  | On Hold | Wang, Li | PS5 - Milestone C | 2
PL-01131 | PS5-06-OB-7465A |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-12-02 - Water Treatment |  | On Hold | Wang, Li | PS5 - Milestone D | 3
PL-01132 | PS5-79-NI-7660C |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-60-07 - Power Generation Package C |  | In Progress | Jean, Pierre | PS5 - Milestone H | 7
PL-01133 | PS5-09-NI-2390C |  | I | I | Missing loop diagram | EPS UNATRAC | PS5-10-01 - Main Pipe Rack |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-01134 | PS5-39-NI-6359D |  | B | B | Missing door closer | EPS UNATRAC | PS5-13-01 - Flare System |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-01135 | PS5-89-NER-6610C |  | T | T | CCTV camera not focused | CPP AGI | PS5-60-04 - Power Generation Package B |  | On Hold | Wang, Li | PS5 - Milestone I | 8
PL-01136 | PS5-41-OB-4922C |  | E | E | Wrong cable glanding | CPP AGI | PS5-09-01 - Transformer 33kV/6.6kV |  | On Hold | Mohamed, Ali | PS5 - Milestone E | 4
PL-01137 | PS5-86-IK-3281D |  | I | I | Missing instrument tag | EPS UNATRAC | PS5-11-01 - Guard Hut A |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-01138 | PS5-67-IK-2920C |  | I | I | Instrument tubing leak | KENT | PS5-12-02 - Water Treatment |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-01139 | PS5-73-NER-9804B |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-07-01 - Chiller System A | 2026-11-23 | Closed | Kumar, Raj | PS5 - Milestone F | 5
PL-01140 | PS5-33-NER-8450D |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-09-01 - Transformer 33kV/6.6kV |  | On Hold | Kumar, Raj | PS5 - Milestone B | 1.1
PL-01141 | PS5-41-UR-3289A |  | M | M | Coupling guard loose | EPS UNATRAC | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-11-14 | Closed | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01142 | PS5-85-NI-1981A |  | B | B | Damaged ceiling panel | CPP AGI | PS5-01-09 - Inergen for EITS Building | 2026-11-07 | Closed | Kumar, Raj | PS5 - Milestone E | 4
PL-01143 | PS5-20-UR-6189D |  | M | M | Missing rotation arrow | CPP AGI | PS5-10-01 - Main Pipe Rack | 2026-12-12 | Closed | Smith, John | PS5 - Milestone G | 6
PL-01144 | PS5-13-IK-7658A |  | I | I | Pressure gauge reads zero | CPP AGI | PS5-01-03 - Fire Water Pump B |  | Originated | Kumar, Raj | PS5 - Milestone C | 2
PL-01145 | PS5-50-NER-4496A |  | H | H | Duct leakage at joint | KENT | PS5-05-03 - CCTV System | 2026-11-19 | Closed | Smith, John | PS5 - Milestone D | 3
PL-01146 | PS5-03-NI-5451A |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-62-02 - Cable Tray Secondary |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-01147 | PS5-27-OB-3367C |  | S | S | Fire alarm panel fault | KENT | PS5-11-02 - Guard Hut B |  | Originated | Wang, Li | PS5 - Milestone F | 5
PL-01148 | PS5-30-NER-8695D |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-05-02 - PA/GA System | 2026-09-23 | Closed | Kumar, Raj | PS5 - Milestone G | 6
PL-01149 | PS5-47-NER-1335B |  | I | I | Missing instrument tag | EPS UNATRAC | PS5-01-09 - Inergen for EITS Building |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-01150 | PS5-29-NI-9473C |  | S | S | Emergency shower not tested | CPP AGI | PS5-02-03 - Fuel Gas System | 2026-11-06 | Closed | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01151 | PS5-79-NI-1820B |  | S | S | Fire alarm panel fault | CPP AGI | PS5-12-02 - Water Treatment |  | In Progress | Mohamed, Ali | PS5 - Milestone A | 1
PL-01152 | PS5-22-NI-2094A |  | T | T | Fiber patch panel unorganized | EPS UNATRAC | PS5-04-04 - 33kV PCS System | 2026-09-14 | Closed | Kumar, Raj | PS5 - Milestone E | 4
PL-01153 | PS5-26-NI-2262A |  | B | B | Missing fire extinguisher signage | CPP AGI | PS5-05-03 - CCTV System |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-01154 | PS5-69-IK-5024D |  | H | H | Missing insulation on duct | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone H | 7
PL-01155 | PS5-07-NER-3554D |  | M | M | Missing rotation arrow | CPP AGI | PS5-01-03 - Fire Water Pump B |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-01156 | PS5-97-UR-2098D |  | P | P | Pipe support missing | KENT | PS5-09-04 - 0.4kV Switchboard | 2026-09-21 | Closed | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01157 | PS5-52-NI-8645D |  | M | M | Vibration level exceeded | KENT | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-01158 | PS5-17-UR-4389A |  | S | S | Eye wash station blocked | EPS UNATRAC | PS5-09-01 - Transformer 33kV/6.6kV |  | On Hold | Mohamed, Ali | PS5 - Milestone I | 8
PL-01159 | PS5-26-UR-4531B |  | E | E | Outgoing breaker not labeled | EPS UNATRAC | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-01160 | PS5-33-NER-7541B |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-04-02 - SIS System |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-01161 | PS5-13-OB-7128A |  | I | I | Pressure gauge reads zero | KENT | PS5-82-01 - Structural Steel A |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-01162 | PS5-09-OB-6430A |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-02-01 - Diesel Storage Tank |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-01163 | PS5-28-NI-7082A |  | B | B | Missing door closer | KENT | PS5-03-01 - ESD System |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-01164 | PS5-56-NI-1592C |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-11-03 - Admin Building | 2026-11-25 | Closed | Wang, Li | PS5 - Milestone F | 5
PL-01165 | PS5-35-IK-3329D |  | E | E | Missing earth continuity label | KENT | PS5-04-04 - 33kV PCS System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01166 | PS5-25-NER-3484B |  | S | S | Fire alarm panel fault | KENT | PS5-09-04 - 0.4kV Switchboard | 2026-09-14 | Closed | Mohamed, Ali | PS5 - Milestone G | 6
PL-01167 | PS5-22-NER-2871A |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-08-08 | Closed | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01168 | PS5-68-IK-9520C |  | P | P | Missing pipe stress label | EPS UNATRAC | PS5-82-02 - Structural Steel B |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-01169 | PS5-93-NER-1840D |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-01-03 - Fire Water Pump B |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-01170 | PS5-65-OB-7760C |  | E | E | Incomplete cable termination | KENT | PS5-04-03 - 33kV ICSS System | 2026-08-23 | Closed | Kumar, Raj | PS5 - Milestone I | 8
PL-01171 | PS5-56-IK-7786B |  | P | P | Flange bolt torque incomplete | EPS UNATRAC | PS5-10-03 - Process piping A | 2026-08-14 | Closed | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01172 | PS5-37-IK-3701B |  | P | P | Missing pipe stress label | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-11-14 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-01173 | PS5-64-UR-3488D |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | Originated | Smith, John | PS5 - Milestone B | 1.1
PL-01174 | PS5-22-OB-6409A |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-01-05 - Foam System | 2026-12-03 | Closed | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-01175 | PS5-35-NI-5774C |  | B | B | Cracked wall plaster | CPP AGI | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01176 | PS5-66-UR-9133C |  | M | M | Motor fan guard missing | KENT | PS5-04-02 - SIS System |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01177 | PS5-66-OB-5811C |  | B | B | Missing door closer | EPS UNATRAC | PS5-60-07 - Power Generation Package C |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-01178 | PS5-76-UR-3419A |  | I | I | Pressure gauge reads zero | CPP AGI | PS5-10-04 - Process piping B | 2026-08-03 | Closed | Jean, Pierre | PS5 - Milestone F | 5
PL-01179 | PS5-62-NER-7715A |  | H | H | Thermostat calibration needed | KENT | PS5-02-01 - Diesel Storage Tank |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-01180 | PS5-45-UR-1801A |  | M | M | Coupling guard loose | CPP AGI | PS5-07-01 - Chiller System A |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-01181 | PS5-58-IK-6356C |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-99-02 - Area Completion Process Area |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-01182 | PS5-63-OB-3427A |  | P | P | Pipe support missing | CPP AGI | PS5-06-01 - AC UPS - EITS Building |  | On Hold | Jean, Pierre | PS5 - Milestone A | 1
PL-01183 | PS5-81-OB-6619D |  | T | T | CAT6 cable untidied | CPP AGI | PS5-09-04 - 0.4kV Switchboard |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-01184 | PS5-88-NI-5480C |  | B | B | Cracked wall plaster | EPS UNATRAC | PS5-03-02 - Fire & Gas Detection |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-01185 | PS5-06-OB-6449A |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-62-01 - Cable Tray Main |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-01186 | PS5-29-NER-5336B |  | E | E | Outgoing breaker not labeled | KENT | PS5-82-02 - Structural Steel B |  | On Hold | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01187 | PS5-56-UR-2246D |  | I | I | Instrument tubing leak | CPP AGI | PS5-09-01 - Transformer 33kV/6.6kV | 2026-09-13 | Closed | Kumar, Raj | PS5 - Milestone G | 6
PL-01188 | PS5-07-NER-4496C |  | S | S | Fire alarm panel fault | KENT | PS5-01-03 - Fire Water Pump B |  | On Hold | Mohamed, Ali | PS5 - Milestone I | 8
PL-01189 | PS5-26-UR-8036A |  | E | E | Outgoing breaker not labeled | KENT | PS5-08-01 - Compressor Air System |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-01190 | PS5-55-IK-3685B |  | T | T | CAT6 cable untidied | CPP AGI | PS5-01-03 - Fire Water Pump B | 2026-10-14 | Closed | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01191 | PS5-23-UR-8393B |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-02-01 - Diesel Storage Tank |  | On Hold | Kumar, Raj | PS5 - Milestone C | 2
PL-01192 | PS5-12-OB-3890B |  | T | T | Missing cable label | EPS UNATRAC | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-01193 | PS5-67-NI-4181B |  | M | M | Motor fan guard missing | CPP AGI | PS5-01-03 - Fire Water Pump B |  | On Hold | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01194 | PS5-52-IK-3744A |  | B | B | Incomplete paint touch-up | KENT | PS5-11-02 - Guard Hut B |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-01195 | PS5-48-IK-1687A |  | E | E | Missing earth continuity label | KENT | PS5-07-04 - FCU System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01196 | PS5-41-NER-2396A |  | P | P | Flange bolt torque incomplete | CPP AGI | PS5-01-03 - Fire Water Pump B |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-01197 | PS5-82-OB-5031B |  | E | E | Incomplete cable termination | CPP AGI | PS5-04-02 - SIS System |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-01198 | PS5-20-OB-6569D |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-03-02 - Fire & Gas Detection |  | On Hold | Kumar, Raj | PS5 - Milestone A | 1
PL-01199 | PS5-37-OB-4027C |  | P | P | Pipe support missing | CPP AGI | PS5-02-01 - Diesel Storage Tank |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-01200 | PS5-16-IK-4478C |  | E | E | Cable tray not properly supported | EPS UNATRAC | PS5-12-02 - Water Treatment |  | Originated | Jean, Pierre | PS5 - Milestone B | 1.1
PL-01201 | PS5-74-NI-5869D |  | B | B | Incomplete paint touch-up | KENT | PS5-09-04 - 0.4kV Switchboard |  | On Hold | Mohamed, Ali | PS5 - Milestone E | 4
PL-01202 | PS5-35-UR-3242A |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-60-10 - Power Generation Package D |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01203 | PS5-34-IK-5056A |  | E | E | Missing earth continuity label | CPP AGI | PS5-82-07 - Guard Huts |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-01204 | PS5-67-OB-4072B |  | E | E | Missing earth continuity label | KENT | PS5-01-03 - Fire Water Pump B | 2026-11-01 | Closed | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01205 | PS5-37-OB-5080C |  | S | S | Fire extinguisher expired | KENT | PS5-07-02 - Chiller System B | 2026-12-14 | Closed | Wang, Li | PS5 - Milestone G | 6
PL-01206 | PS5-96-OB-3100C |  | S | S | Deluge valve not primed | CPP AGI | PS5-09-01 - Transformer 33kV/6.6kV |  | Originated | Kumar, Raj | PS5 - Milestone H | 7
PL-01207 | PS5-94-UR-7467A |  | E | E | Missing earth continuity label | CPP AGI | PS5-08-02 - Nitrogen Generator |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-01208 | PS5-27-NER-3365A |  | E | E | Outgoing breaker not labeled | EPS UNATRAC | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01209 | PS5-82-IK-4387B |  | P | P | Pipe support missing | CPP AGI | PS5-10-06 - Vent System |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-01210 | PS5-56-NER-3598A |  | I | I | Transmitter not calibrated | CPP AGI | PS5-99-01 - Area Completion Building Area |  | On Hold | Wang, Li | PS5 - Milestone H | 7
PL-01211 | PS5-23-NER-1225B |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-10-02 - Utility Pipe Rack |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01212 | PS5-62-NER-5417A |  | T | T | Missing cable label | EPS UNATRAC | PS5-11-03 - Admin Building |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-01213 | PS5-83-IK-2799B |  | H | H | Missing insulation on duct | KENT | PS5-01-03 - Fire Water Pump B |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-01214 | PS5-09-NI-2755A |  | M | M | Coupling guard loose | CPP AGI | PS5-03-01 - ESD System |  | On Hold | Mohamed, Ali | PS5 - Milestone E | 4
PL-01215 | PS5-99-NI-7876C |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-06-01 - AC UPS - EITS Building |  | On Hold | Smith, John | PS5 - Milestone H | 7
PL-01216 | PS5-76-IK-7585C |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-06-01 - AC UPS - EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-01217 | PS5-44-OB-8723D |  | P | P | Missing pipe stress label | CPP AGI | PS5-03-01 - ESD System |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-01218 | PS5-73-IK-4789B |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-07-04 - FCU System |  | On Hold | Jean, Pierre | PS5 - Milestone G | 6
PL-01219 | PS5-57-IK-4616C |  | T | T | Missing cable label | KENT | PS5-61-01 - 33kV Switchboard EITS Building |  | On Hold | Mohamed, Ali | PS5 - Milestone I | 8
PL-01220 | PS5-76-NER-4425A |  | E | E | Missing earth continuity label | KENT | PS5-01-05 - Foam System |  | Originated | Kumar, Raj | PS5 - Milestone E | 4
PL-01221 | PS5-36-NI-3736C |  | E | E | Outgoing breaker not labeled | KENT | PS5-02-03 - Fuel Gas System |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-01222 | PS5-75-IK-5549A |  | B | B | Incomplete paint touch-up | KENT | PS5-99-01 - Area Completion Building Area |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-01223 | PS5-74-UR-5509A |  | P | P | Pipe support missing | KENT | PS5-63-01 - Electrical Earthing |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-01224 | PS5-08-NER-4696C |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-05-03 - CCTV System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01225 | PS5-21-NER-7194A |  | I | I | Instrument tubing leak | CPP AGI | PS5-12-02 - Water Treatment |  | On Hold | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01226 | PS5-54-UR-8120A |  | H | H | Damper not operational | CPP AGI | PS5-61-02 - 6.6kV Switchboard LLHT North |  | Originated | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01227 | PS5-79-NER-5574B |  | P | P | Missing pipe stress label | CPP AGI | PS5-63-01 - Electrical Earthing |  | On Hold | Jean, Pierre | PS5 - Milestone C | 2
PL-01228 | PS5-95-NI-2854C |  | B | B | Missing door closer | CPP AGI | PS5-06-03 - Lightning Protection | 2026-09-02 | Closed | Wang, Li | PS5 - Milestone G | 6
PL-01229 | PS5-70-UR-4956C |  | H | H | Duct leakage at joint | KENT | PS5-01-07 - Hydrant System | 2026-08-17 | Closed | Mohamed, Ali | PS5 - Milestone I | 8
PL-01230 | PS5-55-NER-4363A |  | E | E | Missing earth continuity label | CPP AGI | PS5-09-02 - Transformer 6.6kV/0.4kV |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-01231 | PS5-59-IK-5527D |  | E | E | Wrong cable glanding | EPS UNATRAC | PS5-04-03 - 33kV ICSS System |  | Originated | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01232 | PS5-04-UR-6283A |  | B | B | Incomplete paint touch-up | KENT | PS5-01-02 - Fire Water Pump A |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-01233 | PS5-83-OB-1937D |  | E | E | Outgoing breaker not labeled | KENT | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-01234 | PS5-38-OB-5273A |  | B | B | Cracked wall plaster | KENT | PS5-04-04 - 33kV PCS System |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-01235 | PS5-65-NI-1695B |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-10-01 - Main Pipe Rack |  | In Progress | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01236 | PS5-32-NER-6658C |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-82-01 - Structural Steel A |  | Originated | Mohamed, Ali | PS5 - Milestone A | 1
PL-01237 | PS5-35-NI-4733D |  | M | M | Coupling guard loose | CPP AGI | PS5-04-04 - 33kV PCS System |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-01238 | PS5-92-UR-8696A |  | B | B | Incomplete floor tiling | KENT | PS5-12-02 - Water Treatment |  | On Hold | Jean, Pierre | PS5 - Milestone E | 4
PL-01239 | PS5-68-IK-3060A |  | S | S | Eye wash station blocked | KENT | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-01240 | PS5-01-OB-5237D |  | E | E | Outgoing breaker not labeled | KENT | PS5-60-07 - Power Generation Package C |  | On Hold | Jean, Pierre | PS5 - Milestone E | 4
PL-01241 | PS5-68-UR-7548B |  | T | T | Missing cable label | CPP AGI | PS5-99-02 - Area Completion Process Area |  | In Progress | Wang, Li | PS5 - Milestone D | 3
PL-01242 | PS5-74-OB-7678B |  | E | E | Cable tray not properly supported | KENT | PS5-04-03 - 33kV ICSS System |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-01243 | PS5-33-UR-8568D |  | S | S | Missing safety sign | EPS UNATRAC | PS5-04-01 - DCS System |  | In Progress | Mohamed, Ali | PS5 - Milestone F | 5
PL-01244 | PS5-24-NER-4753C |  | S | S | Eye wash station blocked | CPP AGI | PS5-05-01 - Telecom Network |  | On Hold | Mohamed, Ali | PS5 - Milestone F | 5
PL-01245 | PS5-49-OB-7736D |  | H | H | Missing insulation on duct | EPS UNATRAC | PS5-10-02 - Utility Pipe Rack |  | On Hold | Kumar, Raj | PS5 - Milestone D | 3
PL-01246 | PS5-93-IK-8629C |  | B | B | Incomplete paint touch-up | EPS UNATRAC | PS5-07-03 - AHU System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01247 | PS5-27-IK-4423D |  | P | P | Valve handwheel stiff | CPP AGI | PS5-01-05 - Foam System |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-01248 | PS5-12-UR-8450C |  | M | M | Motor fan guard missing | CPP AGI | PS5-10-05 - Drain System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01249 | PS5-52-OB-4698A |  | B | B | Missing door closer | CPP AGI | PS5-06-03 - Lightning Protection |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01250 | PS5-65-NER-9592D |  | E | E | Cable tray not properly supported | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-01251 | PS5-71-IK-9583D |  | I | I | Missing loop diagram | CPP AGI | PS5-01-04 - Fire Water Ring Main |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-01252 | PS5-77-UR-7807D |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-11-01 - Guard Hut A |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-01253 | PS5-40-NI-2161D |  | I | I | Control valve actuator fault | CPP AGI | PS5-60-07 - Power Generation Package C |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-01254 | PS5-76-IK-7672A |  | M | M | Motor fan guard missing | CPP AGI | PS5-03-02 - Fire & Gas Detection | 2026-10-27 | Closed | Jean, Pierre | PS5 - Milestone I | 8
PL-01255 | PS5-54-UR-2511B |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-99-03 - Area Completion Utilities Area |  | Originated | Wang, Li | PS5 - Milestone C | 2
PL-01256 | PS5-03-OB-4893B |  | M | M | Bearing temperature high | KENT | PS5-04-01 - DCS System |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-01257 | PS5-03-UR-4161D |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-01-06 - Deluge System |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-01258 | PS5-50-IK-8465A |  | I | I | Missing instrument tag | CPP AGI | PS5-12-02 - Water Treatment |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-01259 | PS5-56-NI-2782B |  | E | E | Incomplete cable termination | CPP AGI | PS5-05-03 - CCTV System | 2026-12-18 | Closed | Smith, John | PS5 - Milestone D | 3
PL-01260 | PS5-31-OB-1081D |  | H | H | AHU filter not installed | CPP AGI | PS5-07-01 - Chiller System A |  | On Hold | Jean, Pierre | PS5 - Milestone I | 8
PL-01261 | PS5-30-OB-3033A |  | P | P | Gasket protruding from flange | CPP AGI | PS5-10-03 - Process piping A |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-01262 | PS5-74-IK-1258C |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-01-03 - Fire Water Pump B |  | In Progress | Mohamed, Ali | PS5 - Milestone A | 1
PL-01263 | PS5-38-NI-8474A |  | H | H | FCU drain pipe not connected | KENT | PS5-60-10 - Power Generation Package D |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-01264 | PS5-14-OB-1348D |  | H | H | Missing insulation on duct | KENT | PS5-12-02 - Water Treatment |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-01265 | PS5-72-UR-7681C |  | I | I | Transmitter not calibrated | KENT | PS5-05-03 - CCTV System | 2026-11-13 | Closed | Kumar, Raj | PS5 - Milestone D | 3
PL-01266 | PS5-83-NER-3849C |  | T | T | CAT6 cable untidied | CPP AGI | PS5-04-04 - 33kV PCS System |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-01267 | PS5-18-NI-1286D |  | I | I | Instrument tubing leak | KENT | PS5-07-03 - AHU System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-01268 | PS5-19-NER-6877C |  | P | P | Pipe support missing | KENT | PS5-61-01 - 33kV Switchboard EITS Building |  | On Hold | Smith, John | PS5 - Milestone B | 1.1
PL-01269 | PS5-10-IK-1244C |  | M | M | Bearing temperature high | KENT | PS5-02-03 - Fuel Gas System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01270 | PS5-25-OB-7531C |  | H | H | Damper not operational | EPS UNATRAC | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-01271 | PS5-01-UR-9419B |  | M | M | Bearing temperature high | CPP AGI | PS5-09-03 - Motor Control Center |  | On Hold | Smith, John | PS5 - Milestone A | 1
PL-01272 | PS5-11-IK-6486D |  | E | E | Cable tray not properly supported | CPP AGI | PS5-01-08 - Drencher System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01273 | PS5-78-UR-6265A |  | E | E | Incomplete cable termination | KENT | PS5-60-01 - Power Generation Package A |  | Originated | Jean, Pierre | PS5 - Milestone I | 8
PL-01274 | PS5-82-OB-5425A |  | I | I | Pressure gauge reads zero | CPP AGI | PS5-62-02 - Cable Tray Secondary |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-01275 | PS5-77-IK-6645A |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-10-01 - Main Pipe Rack | 2026-11-22 | Closed | Wang, Li | PS5 - Milestone G | 6
PL-01276 | PS5-09-OB-1372B |  | T | T | CCTV camera not focused | KENT | PS5-82-02 - Structural Steel B |  | On Hold | Wang, Li | PS5 - Milestone G | 6
PL-01277 | PS5-22-IK-6648D |  | M | M | Bearing temperature high | KENT | PS5-01-09 - Inergen for EITS Building | 2026-10-12 | Closed | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01278 | PS5-78-IK-1007B |  | T | T | Missing cable label | CPP AGI | PS5-02-02 - Diesel Transfer Pump |  | Originated | Smith, John | PS5 - Milestone H | 7
PL-01279 | PS5-28-NER-2217D |  | I | I | Control valve actuator fault | CPP AGI | PS5-10-05 - Drain System |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-01280 | PS5-07-IK-7481B |  | M | M | Pump alignment required | EPS UNATRAC | PS5-09-02 - Transformer 6.6kV/0.4kV |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01281 | PS5-33-UR-7526B |  | S | S | Fire extinguisher expired | KENT | PS5-09-04 - 0.4kV Switchboard |  | On Hold | Jean, Pierre | PS5 - Milestone E | 4
PL-01282 | PS5-69-IK-2676C |  | T | T | CAT6 cable untidied | KENT | PS5-99-02 - Area Completion Process Area | 2026-08-16 | Closed | Kumar, Raj | PS5 - Milestone I | 8
PL-01283 | PS5-78-NER-4831D |  | S | S | Emergency shower not tested | KENT | PS5-05-02 - PA/GA System |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-01284 | PS5-95-UR-9074D |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-03-03 - Flame Detector System | 2026-09-19 | Closed | Kumar, Raj | PS5 - Milestone I | 8
PL-01285 | PS5-31-NER-9491D |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-60-10 - Power Generation Package D |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01286 | PS5-24-IK-6722B |  | P | P | Pipe support missing | CPP AGI | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01287 | PS5-52-NI-3463C |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-12-02 - Water Treatment |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-01288 | PS5-06-NI-9753D |  | H | H | Missing insulation on duct | KENT | PS5-02-01 - Diesel Storage Tank |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-01289 | PS5-05-NI-4765C |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-10-01 - Main Pipe Rack |  | On Hold | Smith, John | PS5 - Milestone I | 8
PL-01290 | PS5-79-NI-2081C |  | M | M | Coupling guard loose | KENT | PS5-99-03 - Area Completion Utilities Area |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-01291 | PS5-12-OB-3933A |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-99-03 - Area Completion Utilities Area |  | On Hold | Smith, John | PS5 - Milestone H | 7
PL-01292 | PS5-79-UR-8559B |  | T | T | CCTV camera not focused | CPP AGI | PS5-60-04 - Power Generation Package B | 2026-10-13 | Closed | Smith, John | PS5 - Milestone H | 7
PL-01293 | PS5-41-NI-4213B |  | S | S | Deluge valve not primed | CPP AGI | PS5-04-04 - 33kV PCS System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01294 | PS5-35-UR-6904D |  | P | P | Insulation damaged | KENT | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-01295 | PS5-23-OB-7136B |  | P | P | Pipe support missing | KENT | PS5-63-04 - Electrical Earthing EITS Building |  | Originated | Kumar, Raj | PS5 - Milestone A | 1
PL-01296 | PS5-82-IK-9727C |  | S | S | Eye wash station blocked | CPP AGI | PS5-63-04 - Electrical Earthing EITS Building | 2026-09-21 | Closed | Smith, John | PS5 - Milestone G | 6
PL-01297 | PS5-34-UR-6371A |  | I | I | Instrument tubing leak | CPP AGI | PS5-06-02 - DC UPS - EITS Building |  | On Hold | Wang, Li | PS5 - Milestone I | 8
PL-01298 | PS5-89-IK-6625C |  | T | T | Intercom not functioning | CPP AGI | PS5-05-03 - CCTV System |  | In Progress | Mohamed, Ali | PS5 - Milestone F | 5
PL-01299 | PS5-50-NI-6314A |  | E | E | Wrong cable glanding | EPS UNATRAC | PS5-07-03 - AHU System | 2026-11-17 | Closed | Smith, John | PS5 - Milestone I | 8
PL-01300 | PS5-87-NI-2220D |  | M | M | Pump alignment required | CPP AGI | PS5-09-02 - Transformer 6.6kV/0.4kV |  | Originated | Smith, John | PS5 - Milestone D | 3
PL-01301 | PS5-27-NER-6039A |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-05-02 - PA/GA System | 2026-08-03 | Closed | Smith, John | PS5 - Milestone A | 1
PL-01302 | PS5-61-NI-2595A |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-10-06 - Vent System | 2026-12-07 | Closed | Smith, John | PS5 - Milestone F | 5
PL-01303 | PS5-83-UR-5644D |  | P | P | Flange bolt torque incomplete | KENT | PS5-01-06 - Deluge System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01304 | PS5-61-NI-1985C |  | P | P | Pipe support missing | KENT | PS5-05-03 - CCTV System |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-01305 | PS5-54-UR-6315D |  | B | B | Cracked wall plaster | EPS UNATRAC | PS5-09-03 - Motor Control Center | 2026-10-18 | Closed | Kumar, Raj | PS5 - Milestone F | 5
PL-01306 | PS5-64-OB-9359B |  | S | S | Deluge valve not primed | CPP AGI | PS5-63-01 - Electrical Earthing |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-01307 | PS5-37-IK-9225A |  | M | M | Vibration level exceeded | KENT | PS5-11-02 - Guard Hut B |  | On Hold | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01308 | PS5-40-OB-4761C |  | E | E | Missing earth continuity label | CPP AGI | PS5-61-07 - 0.4kV Switchboard EITS Building |  | Originated | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-01309 | PS5-42-OB-8872A |  | I | I | Missing loop diagram | CPP AGI | PS5-04-01 - DCS System |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-01310 | PS5-92-NER-3360B |  | S | S | Deluge valve not primed | KENT | PS5-06-01 - AC UPS - EITS Building | 2026-11-19 | Closed | Jean, Pierre | PS5 - Milestone B | 1.1
PL-01311 | PS5-96-UR-3125B |  | S | S | Fire alarm panel fault | CPP AGI | PS5-63-01 - Electrical Earthing |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-01312 | PS5-95-IK-4119D |  | H | H | Damper not operational | CPP AGI | PS5-13-01 - Flare System | 2026-12-26 | Closed | Jean, Pierre | PS5 - Milestone E | 4
PL-01313 | PS5-12-NI-5009B |  | H | H | AHU filter not installed | CPP AGI | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-01314 | PS5-67-UR-8471A |  | I | I | Missing loop diagram | EPS UNATRAC | PS5-82-01 - Structural Steel A |  | Originated | Mohamed, Ali | PS5 - Milestone F | 5
PL-01315 | PS5-20-NI-1535B |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-82-01 - Structural Steel A | 2026-11-05 | Closed | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-01316 | PS5-61-IK-2037B |  | T | T | Missing cable label | KENT | PS5-60-01 - Power Generation Package A | 2026-11-04 | Closed | Jean, Pierre | PS5 - Milestone I | 8
PL-01317 | PS5-20-NI-4507C |  | T | T | Missing cable label | CPP AGI | PS5-07-02 - Chiller System B |  | On Hold | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-01318 | PS5-31-IK-6326C |  | S | S | Deluge valve not primed | CPP AGI | PS5-10-06 - Vent System |  | In Progress | Jean, Pierre | PS5 - Milestone B | 1.1
PL-01319 | PS5-93-NER-9078A |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-10-05 - Drain System |  | On Hold | Mohamed, Ali | PS5 - Milestone I | 8
PL-01320 | PS5-15-IK-8320C |  | I | I | Control valve actuator fault | KENT | PS5-01-03 - Fire Water Pump B | 2026-12-23 | Closed | Smith, John | PS5 - Milestone F | 5
PL-01321 | PS5-86-NI-8676D |  | B | B | Missing door closer | CPP AGI | PS5-06-01 - AC UPS - EITS Building |  | In Progress | Wang, Li | PS5 - Milestone C | 2
PL-01322 | PS5-67-IK-3140A |  | E | E | Outgoing breaker not labeled | KENT | PS5-07-02 - Chiller System B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01323 | PS5-05-UR-5346D |  | H | H | AHU filter not installed | CPP AGI | PS5-12-02 - Water Treatment |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-01324 | PS5-89-OB-9426B |  | T | T | Missing cable label | CPP AGI | PS5-99-03 - Area Completion Utilities Area |  | On Hold | Wang, Li | PS5 - Milestone I | 8
PL-01325 | PS5-74-OB-2793B |  | S | S | Eye wash station blocked | KENT | PS5-01-08 - Drencher System | 2026-08-27 | Closed | Jean, Pierre | PS5 - Milestone A | 1
PL-01326 | PS5-96-OB-1393A |  | I | I | Missing loop diagram | KENT | PS5-02-03 - Fuel Gas System |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-01327 | PS5-61-UR-4447C |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01328 | PS5-27-IK-2934D |  | E | E | Outgoing breaker not labeled | CPP AGI | PS5-04-03 - 33kV ICSS System |  | Originated | Smith, John | PS5 - Milestone G | 6
PL-01329 | PS5-52-UR-3121D |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-82-01 - Structural Steel A |  | Originated | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-01330 | PS5-96-IK-1606B |  | B | B | Incomplete floor tiling | KENT | PS5-63-01 - Electrical Earthing |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-01331 | PS5-39-NI-2697A |  | S | S | Eye wash station blocked | KENT | PS5-11-02 - Guard Hut B |  | In Progress | Jean, Pierre | PS5 - Milestone D | 3
PL-01332 | PS5-44-UR-6351D |  | E | E | Missing earth continuity label | CPP AGI | PS5-02-03 - Fuel Gas System |  | Originated | Kumar, Raj | PS5 - Milestone E | 4
PL-01333 | PS5-45-NER-2081D |  | M | M | Motor fan guard missing | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | Originated | Wang, Li | PS5 - Milestone C | 2
PL-01334 | PS5-19-OB-4125B |  | B | B | Damaged ceiling panel | CPP AGI | PS5-07-02 - Chiller System B | 2026-09-15 | Closed | Kumar, Raj | PS5 - Milestone F | 5
PL-01335 | PS5-34-UR-3558A |  | P | P | Insulation damaged | CPP AGI | PS5-12-02 - Water Treatment |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01336 | PS5-36-UR-3725C |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-01337 | PS5-17-OB-9700C |  | E | E | Cable tray not properly supported | CPP AGI | PS5-62-01 - Cable Tray Main |  | On Hold | Mohamed, Ali | PS5 - Milestone G | 6
PL-01338 | PS5-37-UR-5091A |  | P | P | Flange bolt torque incomplete | KENT | PS5-09-02 - Transformer 6.6kV/0.4kV |  | On Hold | Kumar, Raj | PS5 - Milestone C | 2
PL-01339 | PS5-80-UR-7076B |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-60-10 - Power Generation Package D |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-01340 | PS5-18-OB-8565B |  | P | P | Flange bolt torque incomplete | CPP AGI | PS5-10-01 - Main Pipe Rack |  | On Hold | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01341 | PS5-58-NER-5524D |  | B | B | Missing fire extinguisher signage | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-12-08 | Closed | Smith, John | PS5 - Milestone I | 8
PL-01342 | PS5-86-OB-8336A |  | H | H | FCU drain pipe not connected | KENT | PS5-61-07 - 0.4kV Switchboard EITS Building |  | Originated | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01343 | PS5-58-UR-5038A |  | E | E | Outgoing breaker not labeled | EPS UNATRAC | PS5-11-02 - Guard Hut B |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-01344 | PS5-63-OB-4268D |  | P | P | Pipe support missing | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | On Hold | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01345 | PS5-87-OB-8320B |  | I | I | Pressure gauge reads zero | KENT | PS5-01-04 - Fire Water Ring Main |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-01346 | PS5-57-OB-8167D |  | M | M | Bearing temperature high | CPP AGI | PS5-99-02 - Area Completion Process Area | 2026-12-13 | Closed | Jean, Pierre | PS5 - Milestone A | 1
PL-01347 | PS5-03-UR-1943D |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-12-01 - Cooling Tower |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-01348 | PS5-07-NER-8956C |  | S | S | Fire extinguisher expired | CPP AGI | PS5-03-01 - ESD System |  | On Hold | Mohamed, Ali | PS5 - Milestone E | 4
PL-01349 | PS5-97-OB-1049B |  | B | B | Incomplete paint touch-up | KENT | PS5-01-03 - Fire Water Pump B |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-01350 | PS5-83-NI-9141D |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-10-05 - Drain System |  | Originated | Kumar, Raj | PS5 - Milestone C | 2
PL-01351 | PS5-96-OB-2672B |  | T | T | PA speaker not tested | KENT | PS5-07-03 - AHU System | 2026-11-20 | Closed | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01352 | PS5-98-OB-8158A |  | H | H | Thermostat calibration needed | CPP AGI | PS5-07-02 - Chiller System B | 2026-09-08 | Closed | Wang, Li | PS5 - Milestone H | 7
PL-01353 | PS5-22-NER-3286A |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-03-03 - Flame Detector System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01354 | PS5-86-UR-5251A |  | T | T | CCTV camera not focused | KENT | PS5-05-02 - PA/GA System |  | Originated | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01355 | PS5-57-UR-9806C |  | I | I | Control valve actuator fault | CPP AGI | PS5-13-01 - Flare System |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-01356 | PS5-21-UR-8393D |  | B | B | Damaged ceiling panel | CPP AGI | PS5-02-01 - Diesel Storage Tank |  | On Hold | Kumar, Raj | PS5 - Milestone I | 8
PL-01357 | PS5-04-OB-9848A |  | I | I | Pressure gauge reads zero | CPP AGI | PS5-62-02 - Cable Tray Secondary |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-01358 | PS5-77-NER-2499D |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-02-03 - Fuel Gas System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-01359 | PS5-60-NER-8817C |  | H | H | Duct leakage at joint | CPP AGI | PS5-99-02 - Area Completion Process Area |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-01360 | PS5-55-UR-6809B |  | B | B | Missing door closer | KENT | PS5-12-01 - Cooling Tower |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-01361 | PS5-75-NER-3977B |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-05-03 - CCTV System | 2026-10-04 | Closed | Kumar, Raj | PS5 - Milestone H | 7
PL-01362 | PS5-55-UR-5352B |  | S | S | Eye wash station blocked | KENT | PS5-10-01 - Main Pipe Rack |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-01363 | PS5-98-IK-7662B |  | E | E | Missing electrical hazard sign | KENT | PS5-62-02 - Cable Tray Secondary | 2026-09-12 | Closed | Jean, Pierre | PS5 - Milestone A | 1
PL-01364 | PS5-18-OB-7474B |  | B | B | Cracked wall plaster | EPS UNATRAC | PS5-99-03 - Area Completion Utilities Area | 2026-12-02 | Closed | Smith, John | PS5 - Milestone D | 3
PL-01365 | PS5-28-UR-5067B |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-61-07 - 0.4kV Switchboard EITS Building |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-01366 | PS5-32-UR-5169B |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-07-01 - Chiller System A | 2026-08-11 | Closed | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01367 | PS5-64-IK-5295A |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-11-01 - Guard Hut A |  | On Hold | Smith, John | PS5 - Milestone A | 1
PL-01368 | PS5-54-NER-2035B |  | P | P | Gasket protruding from flange | KENT | PS5-01-05 - Foam System |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-01369 | PS5-01-NER-8564D |  | E | E | Missing earth continuity label | KENT | PS5-04-01 - DCS System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01370 | PS5-81-NER-5342C |  | M | M | Vibration level exceeded | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump | 2026-12-06 | Closed | Wang, Li | PS5 - Milestone H | 7
PL-01371 | PS5-12-OB-6575C |  | I | I | Instrument tubing leak | KENT | PS5-60-07 - Power Generation Package C |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-01372 | PS5-62-OB-5036C |  | B | B | Missing door closer | KENT | PS5-03-03 - Flame Detector System |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-01373 | PS5-08-IK-9811D |  | B | B | Cracked wall plaster | KENT | PS5-11-03 - Admin Building |  | Originated | Smith, John | PS5 - Milestone B | 1.1
PL-01374 | PS5-08-NER-8954A |  | I | I | Transmitter not calibrated | KENT | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-10-12 | Closed | Kumar, Raj | PS5 - Milestone F | 5
PL-01375 | PS5-49-NER-5488D |  | M | M | Motor fan guard missing | EPS UNATRAC | PS5-04-02 - SIS System |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-01376 | PS5-21-UR-6091B |  | S | S | Eye wash station blocked | EPS UNATRAC | PS5-62-01 - Cable Tray Main |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-01377 | PS5-29-IK-9297D |  | T | T | Fiber patch panel unorganized | EPS UNATRAC | PS5-11-02 - Guard Hut B |  | On Hold | Smith, John | PS5 - Milestone I | 8
PL-01378 | PS5-44-OB-1887A |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-08-02 - Nitrogen Generator | 2026-09-25 | Closed | Mohamed, Ali | PS5 - Milestone F | 5
PL-01379 | PS5-16-IK-3492B |  | P | P | Insulation damaged | CPP AGI | PS5-07-04 - FCU System |  | Originated | Smith, John | PS5 - Milestone A | 1
PL-01380 | PS5-04-UR-2295A |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-82-02 - Structural Steel B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01381 | PS5-82-NER-1982A |  | E | E | Missing electrical hazard sign | KENT | PS5-13-01 - Flare System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01382 | PS5-17-IK-2296A |  | E | E | Missing electrical hazard sign | KENT | PS5-82-02 - Structural Steel B |  | On Hold | Mohamed, Ali | PS5 - Milestone I | 8
PL-01383 | PS5-82-NER-2247A |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-01-02 - Fire Water Pump A |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-01384 | PS5-94-NER-9721A |  | B | B | Cracked wall plaster | KENT | PS5-07-01 - Chiller System A | 2026-10-23 | Closed | Mohamed, Ali | PS5 - Milestone I | 8
PL-01385 | PS5-86-NI-4810C |  | H | H | Missing insulation on duct | CPP AGI | PS5-13-01 - Flare System |  | On Hold | Mohamed, Ali | PS5 - Milestone E | 4
PL-01386 | PS5-48-OB-8654B |  | M | M | Missing rotation arrow | KENT | PS5-01-07 - Hydrant System |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-01387 | PS5-99-NI-9048C |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-03-03 - Flame Detector System |  | On Hold | Wang, Li | PS5 - Milestone C | 2
PL-01388 | PS5-86-OB-3725B |  | E | E | Cable tray not properly supported | CPP AGI | PS5-63-01 - Electrical Earthing |  | On Hold | Jean, Pierre | PS5 - Milestone H | 7
PL-01389 | PS5-70-UR-2102C |  | S | S | Missing safety sign | KENT | PS5-05-02 - PA/GA System |  | On Hold | Jean, Pierre | PS5 - Milestone B | 1.1
PL-01390 | PS5-30-OB-9934C |  | B | B | Incomplete floor tiling | KENT | PS5-09-01 - Transformer 33kV/6.6kV |  | In Progress | Mohamed, Ali | PS5 - Milestone F | 5
PL-01391 | PS5-82-UR-9432A |  | I | I | Pressure gauge reads zero | KENT | PS5-11-01 - Guard Hut A |  | On Hold | Smith, John | PS5 - Milestone D | 3
PL-01392 | PS5-23-OB-5163B |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-99-03 - Area Completion Utilities Area |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-01393 | PS5-89-UR-8784C |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-09-02 - Transformer 6.6kV/0.4kV |  | Originated | Smith, John | PS5 - Milestone G | 6
PL-01394 | PS5-33-NI-7324D |  | E | E | Missing electrical hazard sign | KENT | PS5-01-02 - Fire Water Pump A | 2026-12-17 | Closed | Kumar, Raj | PS5 - Milestone F | 5
PL-01395 | PS5-18-NER-2714B |  | S | S | Missing safety sign | KENT | PS5-04-04 - 33kV PCS System |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-01396 | PS5-17-IK-4709C |  | H | H | Damper not operational | EPS UNATRAC | PS5-09-01 - Transformer 33kV/6.6kV | 2026-10-06 | Closed | Kumar, Raj | PS5 - Milestone G | 6
PL-01397 | PS5-73-IK-3824C |  | I | I | Control valve actuator fault | CPP AGI | PS5-08-01 - Compressor Air System | 2026-08-13 | Closed | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01398 | PS5-09-NI-7323B |  | I | I | Pressure gauge reads zero | CPP AGI | PS5-05-02 - PA/GA System | 2026-09-01 | Closed | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-01399 | PS5-02-NI-2369D |  | B | B | Incomplete floor tiling | CPP AGI | PS5-01-04 - Fire Water Ring Main |  | On Hold | Mohamed, Ali | PS5 - Milestone I | 8
PL-01400 | PS5-84-IK-2393C |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-02-03 - Fuel Gas System |  | Originated | Smith, John | PS5 - Milestone E | 4
PL-01401 | PS5-76-OB-2600A |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-01402 | PS5-43-NI-7212B |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-63-04 - Electrical Earthing EITS Building |  | On Hold | Mohamed, Ali | PS5 - Milestone G | 6
PL-01403 | PS5-10-UR-7438D |  | B | B | Damaged ceiling panel | CPP AGI | PS5-01-06 - Deluge System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01404 | PS5-52-NI-5405D |  | E | E | Incomplete cable termination | CPP AGI | PS5-07-03 - AHU System |  | Originated | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01405 | PS5-38-NI-3307B |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-13-01 - Flare System |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-01406 | PS5-56-NI-9520D |  | S | S | Fire alarm panel fault | KENT | PS5-05-01 - Telecom Network |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01407 | PS5-24-OB-8430D |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-99-01 - Area Completion Building Area |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-01408 | PS5-67-NI-4060B |  | S | S | Eye wash station blocked | KENT | PS5-01-03 - Fire Water Pump B | 2026-11-28 | Closed | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01409 | PS5-41-UR-8545B |  | B | B | Damaged ceiling panel | KENT | PS5-13-01 - Flare System |  | On Hold | Wang, Li | PS5 - Milestone C | 2
PL-01410 | PS5-71-IK-5592A |  | E | E | Outgoing breaker not labeled | KENT | PS5-04-02 - SIS System | 2026-12-22 | Closed | Kumar, Raj | PS5 - Milestone H | 7
PL-01411 | PS5-10-NER-1874D |  | S | S | Eye wash station blocked | KENT | PS5-04-02 - SIS System | 2026-10-17 | Closed | Wang, Li | PS5 - Milestone G | 6
PL-01412 | PS5-41-NER-9286A |  | P | P | Missing pipe stress label | CPP AGI | PS5-09-03 - Motor Control Center | 2026-11-27 | Closed | Jean, Pierre | PS5 - Milestone C | 2
PL-01413 | PS5-81-NER-4597D |  | H | H | Missing insulation on duct | CPP AGI | PS5-12-02 - Water Treatment |  | On Hold | Smith, John | PS5 - Milestone H | 7
PL-01414 | PS5-72-NI-6375D |  | M | M | Coupling guard loose | CPP AGI | PS5-01-07 - Hydrant System | 2026-09-17 | Closed | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01415 | PS5-92-NER-4938A |  | B | B | Missing door closer | EPS UNATRAC | PS5-02-03 - Fuel Gas System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01416 | PS5-83-UR-2498A |  | S | S | Eye wash station blocked | KENT | PS5-13-01 - Flare System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01417 | PS5-11-UR-6942A |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-82-01 - Structural Steel A |  | On Hold | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01418 | PS5-41-UR-1075D |  | H | H | Missing insulation on duct | KENT | PS5-06-03 - Lightning Protection |  | Originated | Wang, Li | PS5 - Milestone A | 1
PL-01419 | PS5-83-IK-9550B |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-99-03 - Area Completion Utilities Area |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-01420 | PS5-12-NI-9432D |  | I | I | Pressure gauge reads zero | KENT | PS5-61-01 - 33kV Switchboard EITS Building | 2026-11-27 | Closed | Jean, Pierre | PS5 - Milestone F | 5
PL-01421 | PS5-06-IK-6763D |  | M | M | Motor fan guard missing | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | On Hold | Kumar, Raj | PS5 - Milestone D | 3
PL-01422 | PS5-47-NER-5194C |  | S | S | Emergency shower not tested | KENT | PS5-07-03 - AHU System |  | Originated | Mohamed, Ali | PS5 - Milestone C | 2
PL-01423 | PS5-96-NER-8336A |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-61-02 - 6.6kV Switchboard LLHT North |  | Originated | Jean, Pierre | PS5 - Milestone I | 8
PL-01424 | PS5-49-OB-7650D |  | M | M | Vibration level exceeded | CPP AGI | PS5-10-03 - Process piping A |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01425 | PS5-51-OB-8356C |  | P | P | Valve handwheel stiff | CPP AGI | PS5-11-01 - Guard Hut A |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01426 | PS5-43-OB-2755A |  | P | P | Gasket protruding from flange | KENT | PS5-60-07 - Power Generation Package C | 2026-12-02 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-01427 | PS5-65-NER-2552C |  | M | M | Motor fan guard missing | EPS UNATRAC | PS5-01-04 - Fire Water Ring Main |  | On Hold | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01428 | PS5-88-IK-3755C |  | H | H | AHU filter not installed | CPP AGI | PS5-11-01 - Guard Hut A |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-01429 | PS5-23-UR-2354C |  | P | P | Pipe support missing | KENT | PS5-07-04 - FCU System |  | On Hold | Smith, John | PS5 - Milestone F | 5
PL-01430 | PS5-07-UR-6234A |  | P | P | Pipe support missing | KENT | PS5-12-01 - Cooling Tower |  | Originated | Wang, Li | PS5 - Milestone A | 1
PL-01431 | PS5-06-NER-2636D |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-11-03 - Admin Building |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-01432 | PS5-87-OB-1459D |  | H | H | Thermostat calibration needed | KENT | PS5-82-01 - Structural Steel A |  | Originated | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01433 | PS5-16-UR-5545B |  | B | B | Missing fire extinguisher signage | KENT | PS5-01-02 - Fire Water Pump A | 2026-09-23 | Closed | Jean, Pierre | PS5 - Milestone G | 6
PL-01434 | PS5-39-NI-2536D |  | S | S | Deluge valve not primed | KENT | PS5-01-06 - Deluge System |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-01435 | PS5-44-IK-1748B |  | H | H | Duct leakage at joint | KENT | PS5-12-01 - Cooling Tower |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-01436 | PS5-74-NER-9970A |  | B | B | Cracked wall plaster | EPS UNATRAC | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-01437 | PS5-89-IK-4568C |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-82-07 - Guard Huts |  | Originated | Mohamed, Ali | PS5 - Milestone E | 4
PL-01438 | PS5-98-IK-6475B |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-13-01 - Flare System |  | Originated | Jean, Pierre | PS5 - Milestone D | 3
PL-01439 | PS5-51-IK-5683A |  | P | P | Missing pipe stress label | CPP AGI | PS5-01-02 - Fire Water Pump A |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01440 | PS5-40-OB-2560A |  | H | H | Thermostat calibration needed | CPP AGI | PS5-01-08 - Drencher System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-01441 | PS5-72-NER-9362B |  | B | B | Missing fire extinguisher signage | KENT | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-01442 | PS5-01-OB-6480D |  | E | E | Incomplete cable termination | KENT | PS5-02-03 - Fuel Gas System |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-01443 | PS5-06-IK-4936B |  | T | T | Missing cable label | EPS UNATRAC | PS5-10-06 - Vent System |  | Originated | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-01444 | PS5-60-UR-3065A |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-01445 | PS5-78-IK-2106B |  | E | E | Missing electrical hazard sign | KENT | PS5-11-03 - Admin Building | 2026-09-04 | Closed | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-01446 | PS5-65-NER-4464C |  | T | T | CAT6 cable untidied | CPP AGI | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-01447 | PS5-13-NER-9466A |  | E | E | Cable tray not properly supported | KENT | PS5-10-05 - Drain System |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-01448 | PS5-78-IK-9331D |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-82-07 - Guard Huts |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-01449 | PS5-93-NER-3662A |  | M | M | Missing rotation arrow | CPP AGI | PS5-11-01 - Guard Hut A |  | On Hold | Kumar, Raj | PS5 - Milestone E | 4
PL-01450 | PS5-36-OB-8983D |  | I | I | Missing instrument tag | CPP AGI | PS5-10-02 - Utility Pipe Rack | 2026-08-09 | Closed | Jean, Pierre | PS5 - Milestone I | 8
PL-01451 | PS5-26-UR-3073C |  | H | H | Thermostat calibration needed | KENT | PS5-03-03 - Flame Detector System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01452 | PS5-29-IK-3139C |  | H | H | AHU filter not installed | CPP AGI | PS5-01-05 - Foam System |  | On Hold | Mohamed, Ali | PS5 - Milestone D | 3
PL-01453 | PS5-65-UR-7847B |  | H | H | Duct leakage at joint | CPP AGI | PS5-03-02 - Fire & Gas Detection |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-01454 | PS5-30-NER-8486B |  | M | M | Bearing temperature high | KENT | PS5-60-07 - Power Generation Package C |  | Originated | Kumar, Raj | PS5 - Milestone D | 3
PL-01455 | PS5-12-NER-2212B |  | E | E | Incomplete cable termination | KENT | PS5-07-03 - AHU System |  | In Progress | Kumar, Raj | PS5 - Milestone C | 2
PL-01456 | PS5-51-IK-3471C |  | B | B | Incomplete floor tiling | EPS UNATRAC | PS5-05-01 - Telecom Network | 2026-08-20 | Closed | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01457 | PS5-54-NER-8544D |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-99-01 - Area Completion Building Area |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-01458 | PS5-39-NI-5701D |  | I | I | Instrument tubing leak | CPP AGI | PS5-60-07 - Power Generation Package C |  | Originated | Mohamed, Ali | PS5 - Milestone C | 2
PL-01459 | PS5-99-IK-4681C |  | B | B | Damaged ceiling panel | KENT | PS5-62-02 - Cable Tray Secondary |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01460 | PS5-18-NER-2924A |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-01461 | PS5-42-OB-3478A |  | I | I | Control valve actuator fault | KENT | PS5-61-01 - 33kV Switchboard EITS Building |  | On Hold | Kumar, Raj | PS5 - Milestone C | 2
PL-01462 | PS5-93-OB-2386C |  | B | B | Cracked wall plaster | CPP AGI | PS5-99-02 - Area Completion Process Area |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-01463 | PS5-47-UR-6974C |  | S | S | Emergency shower not tested | CPP AGI | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-10-15 | Closed | Jean, Pierre | PS5 - Milestone D | 3
PL-01464 | PS5-47-NI-9183B |  | M | M | Coupling guard loose | KENT | PS5-06-03 - Lightning Protection |  | On Hold | Wang, Li | PS5 - Milestone A | 1
PL-01465 | PS5-35-NER-6420D |  | M | M | Bearing temperature high | KENT | PS5-13-01 - Flare System |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-01466 | PS5-61-OB-7439B |  | M | M | Motor fan guard missing | KENT | PS5-11-01 - Guard Hut A |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-01467 | PS5-03-NI-1129C |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-01-09 - Inergen for EITS Building | 2026-10-10 | Closed | Mohamed, Ali | PS5 - Milestone G | 6
PL-01468 | PS5-74-NER-7505B |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-11-02 - Guard Hut B |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-01469 | PS5-92-NI-2944B |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-08-01 - Compressor Air System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01470 | PS5-54-UR-5931D |  | M | M | Coupling guard loose | CPP AGI | PS5-01-07 - Hydrant System |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-01471 | PS5-88-UR-9121D |  | B | B | Damaged ceiling panel | KENT | PS5-63-01 - Electrical Earthing | 2026-08-18 | Closed | Jean, Pierre | PS5 - Milestone G | 6
PL-01472 | PS5-41-IK-4426B |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01473 | PS5-84-NER-1796A |  | H | H | Damper not operational | KENT | PS5-62-01 - Cable Tray Main |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-01474 | PS5-29-NER-8582B |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-01-04 - Fire Water Ring Main |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-01475 | PS5-98-OB-3498D |  | S | S | Fire alarm panel fault | CPP AGI | PS5-10-06 - Vent System | 2026-08-21 | Closed | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01476 | PS5-62-IK-3097A |  | B | B | Incomplete floor tiling | CPP AGI | PS5-13-01 - Flare System |  | In Progress | Mohamed, Ali | PS5 - Milestone F | 5
PL-01477 | PS5-16-IK-7520C |  | T | T | Intercom not functioning | KENT | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-01478 | PS5-80-OB-6751C |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-99-02 - Area Completion Process Area |  | On Hold | Smith, John | PS5 - Milestone C | 2
PL-01479 | PS5-17-OB-6771D |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-01-04 - Fire Water Ring Main |  | In Progress | Wang, Li | PS5 - Milestone C | 2
PL-01480 | PS5-23-UR-5707B |  | I | I | Pressure gauge reads zero | KENT | PS5-08-01 - Compressor Air System | 2026-12-20 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-01481 | PS5-12-UR-8522A |  | I | I | Missing loop diagram | EPS UNATRAC | PS5-12-01 - Cooling Tower | 2026-08-16 | Closed | Smith, John | PS5 - Milestone D | 3
PL-01482 | PS5-02-NER-3042A |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | On Hold | Mohamed, Ali | PS5 - Milestone I | 8
PL-01483 | PS5-56-OB-9751D |  | I | I | Pressure gauge reads zero | KENT | PS5-06-01 - AC UPS - EITS Building |  | On Hold | Smith, John | PS5 - Milestone B | 1.1
PL-01484 | PS5-89-IK-3320D |  | I | I | Missing instrument tag | CPP AGI | PS5-10-06 - Vent System |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-01485 | PS5-46-NER-1936B |  | B | B | Cracked wall plaster | KENT | PS5-03-02 - Fire & Gas Detection | 2026-09-06 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-01486 | PS5-62-IK-2092D |  | I | I | Transmitter not calibrated | KENT | PS5-13-01 - Flare System |  | On Hold | Kumar, Raj | PS5 - Milestone A | 1
PL-01487 | PS5-01-NER-6165A |  | B | B | Cracked wall plaster | CPP AGI | PS5-09-03 - Motor Control Center |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-01488 | PS5-23-NER-1939C |  | E | E | Wrong cable glanding | EPS UNATRAC | PS5-10-06 - Vent System |  | Originated | Wang, Li | PS5 - Milestone C | 2
PL-01489 | PS5-36-NER-1737B |  | S | S | Eye wash station blocked | KENT | PS5-07-04 - FCU System |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-01490 | PS5-10-NI-6606B |  | E | E | Wrong cable glanding | CPP AGI | PS5-05-03 - CCTV System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01491 | PS5-24-UR-8817D |  | E | E | Missing earth continuity label | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01492 | PS5-64-UR-3227C |  | M | M | Pump alignment required | KENT | PS5-05-02 - PA/GA System |  | On Hold | Jean, Pierre | PS5 - Milestone G | 6
PL-01493 | PS5-69-NI-8436B |  | M | M | Vibration level exceeded | EPS UNATRAC | PS5-02-01 - Diesel Storage Tank |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-01494 | PS5-17-NER-7379C |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-07-02 - Chiller System B | 2026-12-25 | Closed | Smith, John | PS5 - Milestone B | 1.1
PL-01495 | PS5-81-NI-6058A |  | P | P | Missing pipe stress label | CPP AGI | PS5-82-02 - Structural Steel B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01496 | PS5-16-NI-2134B |  | S | S | Fire extinguisher expired | CPP AGI | PS5-11-01 - Guard Hut A | 2026-09-02 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-01497 | PS5-01-UR-1019A |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | On Hold | Smith, John | PS5 - Milestone E | 4
PL-01498 | PS5-74-NER-8375D |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-10-04 - Process piping B |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-01499 | PS5-05-UR-7663A |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-60-04 - Power Generation Package B |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-01500 | PS5-79-IK-8608B |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-82-02 - Structural Steel B |  | Originated | Wang, Li | PS5 - Milestone D | 3
PL-01501 | PS5-02-IK-7029B |  | P | P | Pipe support missing | KENT | PS5-04-02 - SIS System | 2026-12-15 | Closed | Kumar, Raj | PS5 - Milestone G | 6
PL-01502 | PS5-41-NI-5751D |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-82-01 - Structural Steel A |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-01503 | PS5-39-OB-5288D |  | P | P | Valve handwheel stiff | CPP AGI | PS5-60-07 - Power Generation Package C |  | On Hold | Wang, Li | PS5 - Milestone F | 5
PL-01504 | PS5-73-NI-5007D |  | I | I | Missing loop diagram | EPS UNATRAC | PS5-10-04 - Process piping B |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-01505 | PS5-85-NI-3807A |  | M | M | Pump alignment required | KENT | PS5-09-04 - 0.4kV Switchboard | 2026-12-25 | Closed | Kumar, Raj | PS5 - Milestone H | 7
PL-01506 | PS5-14-UR-8299A |  | P | P | Gasket protruding from flange | CPP AGI | PS5-99-03 - Area Completion Utilities Area | 2026-08-08 | Closed | Jean, Pierre | PS5 - Milestone G | 6
PL-01507 | PS5-25-OB-7763B |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-82-07 - Guard Huts |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-01508 | PS5-19-NI-4660C |  | H | H | Duct leakage at joint | CPP AGI | PS5-04-01 - DCS System | 2026-10-13 | Closed | Jean, Pierre | PS5 - Milestone A | 1
PL-01509 | PS5-43-NER-6836C |  | P | P | Missing pipe stress label | EPS UNATRAC | PS5-03-02 - Fire & Gas Detection |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-01510 | PS5-11-NI-4578D |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-11-01 - Guard Hut A |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-01511 | PS5-70-NI-7078A |  | P | P | Pipe support missing | CPP AGI | PS5-10-03 - Process piping A | 2026-08-03 | Closed | Mohamed, Ali | PS5 - Milestone D | 3
PL-01512 | PS5-38-IK-5343B |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-06-02 - DC UPS - EITS Building | 2026-09-10 | Closed | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01513 | PS5-87-NER-9851D |  | B | B | Missing fire extinguisher signage | KENT | PS5-10-03 - Process piping A |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-01514 | PS5-12-NER-8178D |  | P | P | Flange bolt torque incomplete | KENT | PS5-04-03 - 33kV ICSS System |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-01515 | PS5-69-OB-1768A |  | M | M | Vibration level exceeded | CPP AGI | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-01516 | PS5-97-IK-4259A |  | M | M | Vibration level exceeded | KENT | PS5-61-07 - 0.4kV Switchboard EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-01517 | PS5-28-IK-1163A |  | I | I | Missing loop diagram | CPP AGI | PS5-01-02 - Fire Water Pump A |  | Originated | Jean, Pierre | PS5 - Milestone C | 2
PL-01518 | PS5-47-UR-8168D |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-01519 | PS5-48-IK-1918A |  | P | P | Pipe support missing | KENT | PS5-10-05 - Drain System |  | On Hold | Jean, Pierre | PS5 - Milestone D | 3
PL-01520 | PS5-38-NER-2115D |  | M | M | Vibration level exceeded | KENT | PS5-99-01 - Area Completion Building Area | 2026-08-05 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-01521 | PS5-38-UR-7116A |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-02-03 - Fuel Gas System |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-01522 | PS5-64-OB-5267B |  | M | M | Vibration level exceeded | KENT | PS5-82-01 - Structural Steel A |  | On Hold | Kumar, Raj | PS5 - Milestone B | 1.1
PL-01523 | PS5-20-NER-3430B |  | H | H | Duct leakage at joint | EPS UNATRAC | PS5-09-02 - Transformer 6.6kV/0.4kV |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-01524 | PS5-37-OB-9308C |  | H | H | Damper not operational | KENT | PS5-10-05 - Drain System |  | On Hold | Jean, Pierre | PS5 - Milestone A | 1
PL-01525 | PS5-17-UR-2408D |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-08-02 - Nitrogen Generator |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-01526 | PS5-07-UR-8445D |  | T | T | PA speaker not tested | KENT | PS5-01-06 - Deluge System |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-01527 | PS5-77-OB-2792B |  | B | B | Incomplete floor tiling | CPP AGI | PS5-07-03 - AHU System |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-01528 | PS5-24-IK-1351B |  | H | H | Missing insulation on duct | EPS UNATRAC | PS5-99-02 - Area Completion Process Area |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-01529 | PS5-25-IK-1024C |  | H | H | Damper not operational | EPS UNATRAC | PS5-03-03 - Flame Detector System | 2026-12-21 | Closed | Jean, Pierre | PS5 - Milestone G | 6
PL-01530 | PS5-64-NI-6416A |  | M | M | Bearing temperature high | KENT | PS5-10-02 - Utility Pipe Rack |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01531 | PS5-45-UR-6131A |  | H | H | Thermostat calibration needed | KENT | PS5-01-02 - Fire Water Pump A |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-01532 | PS5-41-NER-4820B |  | T | T | PA speaker not tested | KENT | PS5-09-01 - Transformer 33kV/6.6kV |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-01533 | PS5-45-NI-2371A |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-10-05 - Drain System | 2026-11-03 | Closed | Jean, Pierre | PS5 - Milestone C | 2
PL-01534 | PS5-20-NI-6205B |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-13-01 - Flare System | 2026-11-07 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-01535 | PS5-86-IK-1700B |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-07-04 - FCU System | 2026-12-24 | Closed | Mohamed, Ali | PS5 - Milestone G | 6
PL-01536 | PS5-29-NI-1662A |  | M | M | Vibration level exceeded | CPP AGI | PS5-01-04 - Fire Water Ring Main |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-01537 | PS5-13-IK-2249B |  | I | I | Instrument tubing leak | CPP AGI | PS5-05-01 - Telecom Network |  | On Hold | Kumar, Raj | PS5 - Milestone B | 1.1
PL-01538 | PS5-14-NI-2797C |  | E | E | Wrong cable glanding | CPP AGI | PS5-13-01 - Flare System | 2026-11-10 | Closed | Kumar, Raj | PS5 - Milestone I | 8
PL-01539 | PS5-01-UR-7361A |  | B | B | Cracked wall plaster | KENT | PS5-60-04 - Power Generation Package B |  | On Hold | Smith, John | PS5 - Milestone E | 4
PL-01540 | PS5-82-NER-5616D |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-82-07 - Guard Huts |  | On Hold | Wang, Li | PS5 - Milestone D | 3
PL-01541 | PS5-15-NI-3308C |  | M | M | Bearing temperature high | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-01542 | PS5-33-NI-4554D |  | H | H | Duct leakage at joint | KENT | PS5-02-01 - Diesel Storage Tank | 2026-10-06 | Closed | Mohamed, Ali | PS5 - Milestone D | 3
PL-01543 | PS5-76-NI-5549C |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-03-03 - Flame Detector System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01544 | PS5-55-NER-1343C |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-06-03 - Lightning Protection |  | In Progress | Jean, Pierre | PS5 - Milestone B | 1.1
PL-01545 | PS5-44-IK-9912B |  | B | B | Missing fire extinguisher signage | KENT | PS5-01-08 - Drencher System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01546 | PS5-71-UR-6820C |  | P | P | Pipe support missing | CPP AGI | PS5-01-06 - Deluge System |  | On Hold | Smith, John | PS5 - Milestone F | 5
PL-01547 | PS5-97-NER-4998D |  | H | H | Damper not operational | EPS UNATRAC | PS5-01-08 - Drencher System |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-01548 | PS5-53-UR-9284B |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-99-03 - Area Completion Utilities Area |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-01549 | PS5-14-UR-2218A |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-05-03 - CCTV System |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-01550 | PS5-66-IK-6723D |  | H | H | AHU filter not installed | KENT | PS5-06-03 - Lightning Protection |  | In Progress | Wang, Li | PS5 - Milestone D | 3
PL-01551 | PS5-50-UR-1711B |  | E | E | Outgoing breaker not labeled | EPS UNATRAC | PS5-82-07 - Guard Huts |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-01552 | PS5-32-UR-3087B |  | P | P | Insulation damaged | EPS UNATRAC | PS5-05-02 - PA/GA System |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-01553 | PS5-69-IK-9864C |  | E | E | Wrong cable glanding | KENT | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-01554 | PS5-48-NER-9746B |  | T | T | Missing cable label | EPS UNATRAC | PS5-05-03 - CCTV System |  | On Hold | Kumar, Raj | PS5 - Milestone A | 1
PL-01555 | PS5-76-NI-3662B |  | P | P | Pipe support missing | KENT | PS5-03-01 - ESD System |  | In Progress | Kumar, Raj | PS5 - Milestone C | 2
PL-01556 | PS5-03-NER-5392C |  | M | M | Missing rotation arrow | KENT | PS5-62-01 - Cable Tray Main |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-01557 | PS5-63-UR-1063C |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building |  | Originated | Smith, John | PS5 - Milestone E | 4
PL-01558 | PS5-66-IK-9258D |  | M | M | Pump alignment required | CPP AGI | PS5-99-02 - Area Completion Process Area |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-01559 | PS5-75-NI-9736A |  | T | T | PA speaker not tested | KENT | PS5-08-02 - Nitrogen Generator |  | On Hold | Mohamed, Ali | PS5 - Milestone E | 4
PL-01560 | PS5-51-UR-6352D |  | B | B | Missing fire extinguisher signage | KENT | PS5-09-02 - Transformer 6.6kV/0.4kV |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01561 | PS5-71-NI-2002A |  | H | H | FCU drain pipe not connected | EPS UNATRAC | PS5-60-10 - Power Generation Package D |  | On Hold | Jean, Pierre | PS5 - Milestone C | 2
PL-01562 | PS5-74-NI-4112D |  | M | M | Pump alignment required | KENT | PS5-09-01 - Transformer 33kV/6.6kV |  | In Progress | Mohamed, Ali | PS5 - Milestone F | 5
PL-01563 | PS5-14-NI-6695B |  | T | T | Missing cable label | KENT | PS5-10-04 - Process piping B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01564 | PS5-87-OB-7395D |  | H | H | AHU filter not installed | CPP AGI | PS5-63-01 - Electrical Earthing |  | On Hold | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-01565 | PS5-72-OB-4138D |  | P | P | Missing pipe stress label | CPP AGI | PS5-07-01 - Chiller System A |  | On Hold | Wang, Li | PS5 - Milestone A | 1
PL-01566 | PS5-16-NI-8734A |  | M | M | Motor fan guard missing | KENT | PS5-62-01 - Cable Tray Main |  | In Progress | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01567 | PS5-38-OB-5129A |  | B | B | Cracked wall plaster | EPS UNATRAC | PS5-03-03 - Flame Detector System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01568 | PS5-22-OB-1632B |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-82-07 - Guard Huts |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01569 | PS5-24-IK-3046C |  | P | P | Valve handwheel stiff | CPP AGI | PS5-11-03 - Admin Building |  | On Hold | Jean, Pierre | PS5 - Milestone G | 6
PL-01570 | PS5-50-OB-9866B |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-10-02 - Utility Pipe Rack |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-01571 | PS5-18-OB-6456C |  | I | I | Missing loop diagram | CPP AGI | PS5-62-01 - Cable Tray Main | 2026-08-16 | Closed | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-01572 | PS5-12-UR-8738A |  | H | H | Thermostat calibration needed | CPP AGI | PS5-01-08 - Drencher System |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-01573 | PS5-94-IK-6677C |  | T | T | Intercom not functioning | KENT | PS5-99-02 - Area Completion Process Area |  | In Progress | Wang, Li | PS5 - Milestone C | 2
PL-01574 | PS5-13-NER-2894D |  | P | P | Valve handwheel stiff | EPS UNATRAC | PS5-10-06 - Vent System | 2026-09-23 | Closed | Smith, John | PS5 - Milestone C | 2
PL-01575 | PS5-07-OB-6054C |  | P | P | Valve handwheel stiff | KENT | PS5-02-02 - Diesel Transfer Pump |  | Originated | Smith, John | PS5 - Milestone H | 7
PL-01576 | PS5-99-IK-5875B |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-10-04 - Process piping B |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-01577 | PS5-78-IK-1600B |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-03-03 - Flame Detector System | 2026-09-09 | Closed | Kumar, Raj | PS5 - Milestone H | 7
PL-01578 | PS5-67-NI-3985B |  | B | B | Missing fire extinguisher signage | KENT | PS5-07-03 - AHU System | 2026-09-08 | Closed | Kumar, Raj | PS5 - Milestone D | 3
PL-01579 | PS5-62-NI-8785A |  | T | T | CAT6 cable untidied | CPP AGI | PS5-99-03 - Area Completion Utilities Area |  | On Hold | Kumar, Raj | PS5 - Milestone I | 8
PL-01580 | PS5-89-OB-7694B |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-06-01 - AC UPS - EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-01581 | PS5-14-OB-7960C |  | P | P | Pipe support missing | KENT | PS5-07-03 - AHU System |  | On Hold | Mohamed, Ali | PS5 - Milestone H | 7
PL-01582 | PS5-21-NI-7512C |  | M | M | Pump alignment required | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | Originated | Mohamed, Ali | PS5 - Milestone H | 7
PL-01583 | PS5-79-NI-1475C |  | I | I | Transmitter not calibrated | CPP AGI | PS5-07-01 - Chiller System A | 2026-10-11 | Closed | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01584 | PS5-44-IK-2559C |  | P | P | Missing pipe stress label | KENT | PS5-82-07 - Guard Huts |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-01585 | PS5-79-NER-7073B |  | S | S | Fire alarm panel fault | KENT | PS5-10-02 - Utility Pipe Rack | 2026-12-25 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-01586 | PS5-76-UR-3935A |  | T | T | PA speaker not tested | CPP AGI | PS5-11-01 - Guard Hut A |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-01587 | PS5-43-NI-9669B |  | T | T | CAT6 cable untidied | CPP AGI | PS5-02-01 - Diesel Storage Tank | 2026-08-15 | Closed | Mohamed, Ali | PS5 - Milestone C | 2
PL-01588 | PS5-14-UR-3985C |  | E | E | Outgoing breaker not labeled | KENT | PS5-09-03 - Motor Control Center |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01589 | PS5-32-NI-9055D |  | I | I | Transmitter not calibrated | KENT | PS5-99-03 - Area Completion Utilities Area |  | In Progress | Mohamed, Ali | PS5 - Milestone F | 5
PL-01590 | PS5-60-NI-1769B |  | P | P | Pipe support missing | EPS UNATRAC | PS5-01-02 - Fire Water Pump A |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-01591 | PS5-97-NER-1194D |  | S | S | Deluge valve not primed | CPP AGI | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-12-18 | Closed | Mohamed, Ali | PS5 - Milestone D | 3
PL-01592 | PS5-75-UR-1170A |  | I | I | Control valve actuator fault | CPP AGI | PS5-04-01 - DCS System |  | Originated | Jean, Pierre | PS5 - Milestone G | 6
PL-01593 | PS5-93-NER-1692C |  | T | T | Intercom not functioning | CPP AGI | PS5-10-04 - Process piping B |  | In Progress | Kumar, Raj | PS5 - Milestone C | 2
PL-01594 | PS5-18-OB-4476C |  | P | P | Pipe support missing | CPP AGI | PS5-03-01 - ESD System |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-01595 | PS5-57-UR-4555C |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-11-02 - Guard Hut B |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-01596 | PS5-43-NI-6271D |  | S | S | Missing safety sign | KENT | PS5-08-02 - Nitrogen Generator |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01597 | PS5-49-IK-8984C |  | P | P | Valve handwheel stiff | EPS UNATRAC | PS5-10-02 - Utility Pipe Rack |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-01598 | PS5-31-NER-8965A |  | E | E | Cable tray not properly supported | KENT | PS5-03-01 - ESD System | 2026-09-27 | Closed | Jean, Pierre | PS5 - Milestone G | 6
PL-01599 | PS5-11-NER-5176B |  | S | S | Deluge valve not primed | KENT | PS5-60-01 - Power Generation Package A |  | Originated | Wang, Li | PS5 - Milestone G | 6
PL-01600 | PS5-43-NI-5908B |  | S | S | Eye wash station blocked | CPP AGI | PS5-02-01 - Diesel Storage Tank |  | On Hold | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01601 | PS5-63-NER-4416B |  | P | P | Missing pipe stress label | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-08-09 | Closed | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01602 | PS5-03-NI-7746C |  | M | M | Pump alignment required | CPP AGI | PS5-09-02 - Transformer 6.6kV/0.4kV |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-01603 | PS5-65-NI-5558D |  | T | T | CCTV camera not focused | CPP AGI | PS5-60-10 - Power Generation Package D |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-01604 | PS5-18-NER-3019B |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-10-05 - Drain System | 2026-12-24 | Closed | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-01605 | PS5-26-OB-4412C |  | S | S | Fire alarm panel fault | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01606 | PS5-30-IK-7630B |  | T | T | PA speaker not tested | KENT | PS5-07-01 - Chiller System A |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-01607 | PS5-82-NER-1379A |  | B | B | Incomplete floor tiling | KENT | PS5-09-01 - Transformer 33kV/6.6kV | 2026-10-07 | Closed | Smith, John | PS5 - Milestone B | 1.1
PL-01608 | PS5-22-IK-2392C |  | H | H | Thermostat calibration needed | KENT | PS5-11-03 - Admin Building |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-01609 | PS5-89-NER-5458A |  | P | P | Pipe support missing | KENT | PS5-63-01 - Electrical Earthing | 2026-08-02 | Closed | Jean, Pierre | PS5 - Milestone H | 7
PL-01610 | PS5-92-NI-6071A |  | M | M | Motor fan guard missing | EPS UNATRAC | PS5-13-01 - Flare System |  | On Hold | Jean, Pierre | PS5 - Milestone D | 3
PL-01611 | PS5-72-NER-3474C |  | H | H | Missing insulation on duct | KENT | PS5-09-04 - 0.4kV Switchboard |  | On Hold | Kumar, Raj | PS5 - Milestone I | 8
PL-01612 | PS5-02-OB-4505A |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-07-01 - Chiller System A | 2026-09-06 | Closed | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-01613 | PS5-28-UR-8780A |  | B | B | Cracked wall plaster | EPS UNATRAC | PS5-01-05 - Foam System |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-01614 | PS5-77-OB-4873B |  | T | T | PA speaker not tested | CPP AGI | PS5-05-02 - PA/GA System |  | On Hold | Wang, Li | PS5 - Milestone A | 1
PL-01615 | PS5-04-UR-2569B |  | H | H | Damper not operational | EPS UNATRAC | PS5-01-09 - Inergen for EITS Building | 2026-11-20 | Closed | Mohamed, Ali | PS5 - Milestone F | 5
PL-01616 | PS5-12-UR-4345C |  | B | B | Missing door closer | CPP AGI | PS5-01-04 - Fire Water Ring Main | 2026-11-06 | Closed | Kumar, Raj | PS5 - Milestone H | 7
PL-01617 | PS5-04-OB-6180D |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-82-02 - Structural Steel B |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01618 | PS5-59-OB-6019A |  | S | S | Fire extinguisher expired | CPP AGI | PS5-03-03 - Flame Detector System | 2026-11-27 | Closed | Jean, Pierre | PS5 - Milestone H | 7
PL-01619 | PS5-12-NER-1252A |  | I | I | Missing loop diagram | CPP AGI | PS5-10-03 - Process piping A |  | On Hold | Jean, Pierre | PS5 - Milestone E | 4
PL-01620 | PS5-95-NER-8773D |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | On Hold | Kumar, Raj | PS5 - Milestone C | 2
PL-01621 | PS5-17-NER-7700A |  | B | B | Missing door closer | CPP AGI | PS5-07-01 - Chiller System A |  | In Progress | Kumar, Raj | PS5 - Milestone C | 2
PL-01622 | PS5-15-NER-1607A |  | M | M | Pump alignment required | EPS UNATRAC | PS5-01-04 - Fire Water Ring Main | 2026-12-18 | Closed | Kumar, Raj | PS5 - Milestone C | 2
PL-01623 | PS5-70-NER-5678C |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-10-05 - Drain System |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-01624 | PS5-49-UR-1158C |  | M | M | Coupling guard loose | EPS UNATRAC | PS5-82-07 - Guard Huts |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-01625 | PS5-72-UR-2794C |  | T | T | PA speaker not tested | KENT | PS5-09-02 - Transformer 6.6kV/0.4kV |  | In Progress | Mohamed, Ali | PS5 - Milestone A | 1
PL-01626 | PS5-93-NI-4303B |  | H | H | Thermostat calibration needed | KENT | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-01627 | PS5-56-OB-8357D |  | H | H | Duct leakage at joint | KENT | PS5-06-03 - Lightning Protection |  | On Hold | Kumar, Raj | PS5 - Milestone F | 5
PL-01628 | PS5-24-IK-1159A |  | H | H | Damper not operational | EPS UNATRAC | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone D | 3
PL-01629 | PS5-01-UR-1337A |  | T | T | CCTV camera not focused | CPP AGI | PS5-04-03 - 33kV ICSS System |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-01630 | PS5-67-NI-2474A |  | I | I | Transmitter not calibrated | CPP AGI | PS5-10-02 - Utility Pipe Rack |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-01631 | PS5-88-NER-4302D |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-01-03 - Fire Water Pump B |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-01632 | PS5-71-NER-8864D |  | T | T | PA speaker not tested | CPP AGI | PS5-01-06 - Deluge System |  | Originated | Jean, Pierre | PS5 - Milestone G | 6
PL-01633 | PS5-56-UR-2585C |  | B | B | Incomplete floor tiling | CPP AGI | PS5-01-07 - Hydrant System |  | On Hold | Smith, John | PS5 - Milestone A | 1
PL-01634 | PS5-72-OB-5245B |  | E | E | Missing earth continuity label | KENT | PS5-03-01 - ESD System |  | On Hold | Kumar, Raj | PS5 - Milestone I | 8
PL-01635 | PS5-42-IK-5550B |  | M | M | Pump alignment required | CPP AGI | PS5-04-04 - 33kV PCS System | 2026-08-12 | Closed | Smith, John | PS5 - Milestone A | 1
PL-01636 | PS5-07-UR-1959C |  | P | P | Valve handwheel stiff | KENT | PS5-60-01 - Power Generation Package A | 2026-11-05 | Closed | Wang, Li | PS5 - Milestone E | 4
PL-01637 | PS5-66-NER-5734D |  | B | B | Incomplete floor tiling | CPP AGI | PS5-04-02 - SIS System |  | On Hold | Smith, John | PS5 - Milestone I | 8
PL-01638 | PS5-42-IK-8660A |  | H | H | Missing insulation on duct | KENT | PS5-01-05 - Foam System |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-01639 | PS5-21-NI-2551D |  | I | I | Control valve actuator fault | CPP AGI | PS5-61-01 - 33kV Switchboard EITS Building | 2026-08-10 | Closed | Jean, Pierre | PS5 - Milestone E | 4
PL-01640 | PS5-03-OB-7513A |  | P | P | Flange bolt torque incomplete | KENT | PS5-03-02 - Fire & Gas Detection | 2026-10-12 | Closed | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01641 | PS5-11-IK-4969C |  | T | T | PA speaker not tested | CPP AGI | PS5-05-03 - CCTV System |  | Originated | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01642 | PS5-17-UR-5333D |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-02-03 - Fuel Gas System | 2026-08-12 | Closed | Mohamed, Ali | PS5 - Milestone C | 2
PL-01643 | PS5-97-OB-6112B |  | B | B | Missing fire extinguisher signage | KENT | PS5-99-02 - Area Completion Process Area |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-01644 | PS5-50-UR-2754C |  | H | H | Missing insulation on duct | EPS UNATRAC | PS5-04-03 - 33kV ICSS System |  | In Progress | Jean, Pierre | PS5 - Milestone H | 7
PL-01645 | PS5-20-OB-4848B |  | B | B | Missing door closer | EPS UNATRAC | PS5-12-02 - Water Treatment |  | In Progress | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01646 | PS5-51-NER-1062C |  | T | T | PA speaker not tested | CPP AGI | PS5-61-01 - 33kV Switchboard EITS Building | 2026-11-22 | Closed | Wang, Li | PS5 - Milestone I | 8
PL-01647 | PS5-57-NER-9942B |  | S | S | Eye wash station blocked | KENT | PS5-11-03 - Admin Building |  | On Hold | Kumar, Raj | PS5 - Milestone G | 6
PL-01648 | PS5-27-OB-1246A |  | M | M | Pump alignment required | KENT | PS5-82-02 - Structural Steel B |  | On Hold | Kumar, Raj | PS5 - Milestone H | 7
PL-01649 | PS5-35-IK-6039A |  | M | M | Motor fan guard missing | EPS UNATRAC | PS5-99-03 - Area Completion Utilities Area |  | On Hold | Smith, John | PS5 - Milestone H | 7
PL-01650 | PS5-97-OB-3680B |  | S | S | Fire alarm panel fault | KENT | PS5-04-04 - 33kV PCS System | 2026-10-20 | Closed | Jean, Pierre | PS5 - Milestone B | 1.1
PL-01651 | PS5-86-NI-9078D |  | B | B | Cracked wall plaster | CPP AGI | PS5-60-10 - Power Generation Package D |  | On Hold | Kumar, Raj | PS5 - Milestone E | 4
PL-01652 | PS5-37-NI-9236D |  | E | E | Outgoing breaker not labeled | KENT | PS5-04-03 - 33kV ICSS System | 2026-10-22 | Closed | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01653 | PS5-45-UR-2650D |  | M | M | Missing rotation arrow | CPP AGI | PS5-61-02 - 6.6kV Switchboard LLHT North |  | Originated | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01654 | PS5-16-NER-1834B |  | H | H | Thermostat calibration needed | CPP AGI | PS5-13-01 - Flare System | 2026-09-28 | Closed | Kumar, Raj | PS5 - Milestone E | 4
PL-01655 | PS5-65-NER-1866D |  | S | S | Emergency shower not tested | KENT | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Jean, Pierre | PS5 - Milestone D | 3
PL-01656 | PS5-05-UR-4438B |  | B | B | Missing door closer | EPS UNATRAC | PS5-06-03 - Lightning Protection |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01657 | PS5-54-UR-2719D |  | I | I | Pressure gauge reads zero | KENT | PS5-03-02 - Fire & Gas Detection |  | In Progress | Jean, Pierre | PS5 - Milestone H | 7
PL-01658 | PS5-02-UR-2262A |  | P | P | Insulation damaged | EPS UNATRAC | PS5-01-07 - Hydrant System | 2026-12-11 | Closed | Mohamed, Ali | PS5 - Milestone I | 8
PL-01659 | PS5-57-NI-1056B |  | I | I | Pressure gauge reads zero | KENT | PS5-11-02 - Guard Hut B | 2026-12-17 | Closed | Kumar, Raj | PS5 - Milestone I | 8
PL-01660 | PS5-15-NI-8700D |  | B | B | Incomplete floor tiling | KENT | PS5-07-04 - FCU System | 2026-12-23 | Closed | Jean, Pierre | PS5 - Milestone H | 7
PL-01661 | PS5-44-IK-1660B |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-60-04 - Power Generation Package B |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-01662 | PS5-71-OB-6765B |  | E | E | Missing electrical hazard sign | KENT | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-01663 | PS5-28-NER-4051A |  | B | B | Missing fire extinguisher signage | CPP AGI | PS5-05-02 - PA/GA System |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-01664 | PS5-61-UR-7372D |  | B | B | Incomplete paint touch-up | KENT | PS5-60-04 - Power Generation Package B |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-01665 | PS5-90-IK-2465B |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-01-09 - Inergen for EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01666 | PS5-26-OB-1760D |  | S | S | Deluge valve not primed | CPP AGI | PS5-10-03 - Process piping A |  | In Progress | Kumar, Raj | PS5 - Milestone C | 2
PL-01667 | PS5-74-IK-5727C |  | M | M | Coupling guard loose | CPP AGI | PS5-05-01 - Telecom Network |  | On Hold | Kumar, Raj | PS5 - Milestone E | 4
PL-01668 | PS5-10-UR-6183D |  | E | E | Cable tray not properly supported | KENT | PS5-07-03 - AHU System |  | Originated | Jean, Pierre | PS5 - Milestone A | 1
PL-01669 | PS5-71-NER-5764B |  | E | E | Missing earth continuity label | KENT | PS5-13-01 - Flare System |  | In Progress | Jean, Pierre | PS5 - Milestone B | 1.1
PL-01670 | PS5-16-OB-9170B |  | P | P | Pipe support missing | CPP AGI | PS5-07-04 - FCU System |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-01671 | PS5-18-NI-2251D |  | S | S | Missing safety sign | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone F | 5
PL-01672 | PS5-47-OB-3535B |  | E | E | Outgoing breaker not labeled | EPS UNATRAC | PS5-04-02 - SIS System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01673 | PS5-56-OB-5590B |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-05-01 - Telecom Network |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-01674 | PS5-08-NI-8599A |  | H | H | AHU filter not installed | CPP AGI | PS5-01-05 - Foam System |  | Originated | Mohamed, Ali | PS5 - Milestone F | 5
PL-01675 | PS5-41-OB-4739C |  | T | T | Missing cable label | EPS UNATRAC | PS5-07-04 - FCU System |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-01676 | PS5-24-NER-1816A |  | M | M | Missing rotation arrow | KENT | PS5-02-01 - Diesel Storage Tank |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-01677 | PS5-67-OB-1748B |  | M | M | Bearing temperature high | KENT | PS5-60-07 - Power Generation Package C |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-01678 | PS5-62-UR-4383D |  | H | H | Damper not operational | CPP AGI | PS5-01-02 - Fire Water Pump A |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-01679 | PS5-68-NER-9256D |  | S | S | Fire alarm panel fault | CPP AGI | PS5-82-02 - Structural Steel B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01680 | PS5-23-UR-6482D |  | S | S | Emergency shower not tested | CPP AGI | PS5-01-04 - Fire Water Ring Main |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-01681 | PS5-54-UR-6363C |  | B | B | Missing door closer | KENT | PS5-11-03 - Admin Building |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-01682 | PS5-60-NER-6554B |  | M | M | Missing rotation arrow | KENT | PS5-01-02 - Fire Water Pump A | 2026-11-17 | Closed | Smith, John | PS5 - Milestone F | 5
PL-01683 | PS5-62-IK-7593C |  | E | E | Missing earth continuity label | CPP AGI | PS5-01-04 - Fire Water Ring Main |  | On Hold | Smith, John | PS5 - Milestone D | 3
PL-01684 | PS5-14-UR-2228D |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-06-01 - AC UPS - EITS Building |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-01685 | PS5-38-IK-9899B |  | T | T | CAT6 cable untidied | CPP AGI | PS5-61-07 - 0.4kV Switchboard EITS Building |  | On Hold | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01686 | PS5-02-IK-3935A |  | S | S | Emergency shower not tested | KENT | PS5-07-04 - FCU System |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-01687 | PS5-35-NER-2268A |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-01-02 - Fire Water Pump A |  | On Hold | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01688 | PS5-52-IK-8301D |  | E | E | Cable tray not properly supported | CPP AGI | PS5-63-01 - Electrical Earthing |  | On Hold | Mohamed, Ali | PS5 - Milestone H | 7
PL-01689 | PS5-24-OB-5581B |  | B | B | Incomplete floor tiling | EPS UNATRAC | PS5-01-05 - Foam System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01690 | PS5-70-IK-1532C |  | T | T | CAT6 cable untidied | CPP AGI | PS5-05-01 - Telecom Network |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-01691 | PS5-29-NI-4684A |  | B | B | Incomplete paint touch-up | KENT | PS5-05-01 - Telecom Network |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-01692 | PS5-29-OB-1782B |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-06-01 - AC UPS - EITS Building |  | On Hold | Smith, John | PS5 - Milestone I | 8
PL-01693 | PS5-22-NER-3723C |  | B | B | Damaged ceiling panel | EPS UNATRAC | PS5-04-01 - DCS System |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-01694 | PS5-01-NI-9947B |  | I | I | Transmitter not calibrated | KENT | PS5-99-01 - Area Completion Building Area |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-01695 | PS5-02-UR-3814C |  | T | T | Missing cable label | KENT | PS5-12-02 - Water Treatment |  | On Hold | Jean, Pierre | PS5 - Milestone G | 6
PL-01696 | PS5-34-NI-1566C |  | E | E | Missing earth continuity label | EPS UNATRAC | PS5-13-01 - Flare System |  | On Hold | Jean, Pierre | PS5 - Milestone E | 4
PL-01697 | PS5-48-OB-6636D |  | P | P | Flange bolt torque incomplete | CPP AGI | PS5-06-02 - DC UPS - EITS Building | 2026-08-02 | Closed | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01698 | PS5-75-NI-5666C |  | I | I | Missing loop diagram | EPS UNATRAC | PS5-11-02 - Guard Hut B |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-01699 | PS5-21-NI-7991A |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-08-02 - Nitrogen Generator |  | On Hold | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01700 | PS5-57-OB-7435B |  | P | P | Missing pipe stress label | CPP AGI | PS5-07-04 - FCU System | 2026-09-19 | Closed | Kumar, Raj | PS5 - Milestone B | 1.1
PL-01701 | PS5-76-OB-5552A |  | H | H | Duct leakage at joint | EPS UNATRAC | PS5-01-08 - Drencher System | 2026-11-15 | Closed | Smith, John | PS5 - Milestone B | 1.1
PL-01702 | PS5-76-IK-3962B |  | H | H | Duct leakage at joint | CPP AGI | PS5-09-03 - Motor Control Center |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-01703 | PS5-61-OB-3476C |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-03-01 - ESD System |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-01704 | PS5-04-UR-3594C |  | S | S | Fire alarm panel fault | CPP AGI | PS5-09-01 - Transformer 33kV/6.6kV | 2026-08-15 | Closed | Mohamed, Ali | PS5 - Milestone G | 6
PL-01705 | PS5-46-IK-6437B |  | P | P | Valve handwheel stiff | CPP AGI | PS5-04-02 - SIS System |  | Originated | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01706 | PS5-63-NI-8552C |  | M | M | Coupling guard loose | EPS UNATRAC | PS5-07-01 - Chiller System A | 2026-12-28 | Closed | Smith, John | PS5 - Milestone C | 2
PL-01707 | PS5-31-OB-6264C |  | H | H | FCU drain pipe not connected | KENT | PS5-13-01 - Flare System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01708 | PS5-64-NER-4248D |  | H | H | Damper not operational | EPS UNATRAC | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-01709 | PS5-92-NI-5748D |  | S | S | Eye wash station blocked | EPS UNATRAC | PS5-12-01 - Cooling Tower |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01710 | PS5-22-OB-8163C |  | P | P | Insulation damaged | KENT | PS5-99-03 - Area Completion Utilities Area |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-01711 | PS5-85-NI-3757B |  | S | S | Emergency shower not tested | CPP AGI | PS5-05-03 - CCTV System |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-01712 | PS5-23-IK-6740A |  | P | P | Flange bolt torque incomplete | CPP AGI | PS5-13-01 - Flare System |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-01713 | PS5-24-UR-2485D |  | H | H | Damper not operational | EPS UNATRAC | PS5-12-01 - Cooling Tower | 2026-09-19 | Closed | Jean, Pierre | PS5 - Milestone G | 6
PL-01714 | PS5-54-NER-3789D |  | I | I | Pressure gauge reads zero | KENT | PS5-09-04 - 0.4kV Switchboard | 2026-12-23 | Closed | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01715 | PS5-75-OB-8050A |  | H | H | Duct leakage at joint | CPP AGI | PS5-61-01 - 33kV Switchboard EITS Building |  | Originated | Smith, John | PS5 - Milestone G | 6
PL-01716 | PS5-74-IK-5024B |  | M | M | Missing rotation arrow | CPP AGI | PS5-01-06 - Deluge System |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-01717 | PS5-89-UR-7879D |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-04-02 - SIS System | 2026-11-28 | Closed | Jean, Pierre | PS5 - Milestone C | 2
PL-01718 | PS5-96-NER-1899B |  | T | T | PA speaker not tested | KENT | PS5-99-01 - Area Completion Building Area |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-01719 | PS5-42-IK-8586A |  | S | S | Eye wash station blocked | KENT | PS5-10-01 - Main Pipe Rack |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-01720 | PS5-26-NER-2878A |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-62-02 - Cable Tray Secondary |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-01721 | PS5-15-IK-8532A |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-02-03 - Fuel Gas System | 2026-10-09 | Closed | Wang, Li | PS5 - Milestone G | 6
PL-01722 | PS5-27-OB-5789A |  | S | S | Fire extinguisher expired | KENT | PS5-12-02 - Water Treatment |  | On Hold | Mohamed, Ali | PS5 - Milestone H | 7
PL-01723 | PS5-57-UR-2417D |  | S | S | Missing safety sign | KENT | PS5-01-09 - Inergen for EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-01724 | PS5-29-NER-6040B |  | I | I | Instrument tubing leak | KENT | PS5-05-03 - CCTV System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01725 | PS5-74-OB-8350C |  | T | T | Fiber patch panel unorganized | EPS UNATRAC | PS5-05-02 - PA/GA System | 2026-12-27 | Closed | Jean, Pierre | PS5 - Milestone D | 3
PL-01726 | PS5-54-NI-1679B |  | P | P | Insulation damaged | CPP AGI | PS5-10-02 - Utility Pipe Rack |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-01727 | PS5-30-NI-6524C |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-62-01 - Cable Tray Main |  | Originated | Smith, John | PS5 - Milestone E | 4
PL-01728 | PS5-78-UR-1532C |  | M | M | Missing rotation arrow | KENT | PS5-05-03 - CCTV System |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-01729 | PS5-53-UR-5810A |  | E | E | Missing electrical hazard sign | KENT | PS5-09-02 - Transformer 6.6kV/0.4kV |  | Originated | Kumar, Raj | PS5 - Milestone G | 6
PL-01730 | PS5-70-NER-6757D |  | M | M | Coupling guard loose | CPP AGI | PS5-09-04 - 0.4kV Switchboard |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-01731 | PS5-48-OB-2427C |  | T | T | CCTV camera not focused | CPP AGI | PS5-04-01 - DCS System |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-01732 | PS5-02-NI-6047B |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-01-08 - Drencher System |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-01733 | PS5-05-OB-1598A |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-01-03 - Fire Water Pump B |  | On Hold | Smith, John | PS5 - Milestone E | 4
PL-01734 | PS5-61-UR-9978D |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-09-01 | Closed | Wang, Li | PS5 - Milestone I | 8
PL-01735 | PS5-11-NI-1264D |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-61-02 - 6.6kV Switchboard LLHT North |  | On Hold | Kumar, Raj | PS5 - Milestone G | 6
PL-01736 | PS5-50-NER-4362C |  | S | S | Emergency shower not tested | CPP AGI | PS5-11-01 - Guard Hut A |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-01737 | PS5-82-OB-1358D |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-99-03 - Area Completion Utilities Area |  | On Hold | Mohamed, Ali | PS5 - Milestone H | 7
PL-01738 | PS5-55-UR-9930D |  | H | H | Thermostat calibration needed | KENT | PS5-04-02 - SIS System |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-01739 | PS5-52-IK-1242B |  | T | T | CCTV camera not focused | CPP AGI | PS5-01-04 - Fire Water Ring Main |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-01740 | PS5-54-OB-4343D |  | H | H | Damper not operational | CPP AGI | PS5-02-02 - Diesel Transfer Pump |  | On Hold | Smith, John | PS5 - Milestone I | 8
PL-01741 | PS5-52-NI-5783A |  | E | E | Missing earth continuity label | CPP AGI | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-01742 | PS5-89-UR-2850B |  | I | I | Control valve actuator fault | KENT | PS5-02-03 - Fuel Gas System |  | On Hold | Kumar, Raj | PS5 - Milestone D | 3
PL-01743 | PS5-69-NER-4110A |  | S | S | Eye wash station blocked | EPS UNATRAC | PS5-63-01 - Electrical Earthing |  | On Hold | Kumar, Raj | PS5 - Milestone A | 1
PL-01744 | PS5-07-IK-2234B |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-09-03 - Motor Control Center |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01745 | PS5-83-OB-4633C |  | S | S | Eye wash station blocked | EPS UNATRAC | PS5-82-02 - Structural Steel B |  | On Hold | Wang, Li | PS5 - Milestone I | 8
PL-01746 | PS5-85-IK-9372A |  | B | B | Missing fire extinguisher signage | KENT | PS5-03-02 - Fire & Gas Detection |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-01747 | PS5-06-NER-1785A |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-01-06 - Deluge System |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-01748 | PS5-99-OB-5901D |  | B | B | Damaged ceiling panel | KENT | PS5-01-09 - Inergen for EITS Building | 2026-12-06 | Closed | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01749 | PS5-83-NER-5515A |  | B | B | Missing door closer | KENT | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone C | 2
PL-01750 | PS5-61-NER-7421A |  | B | B | Cracked wall plaster | CPP AGI | PS5-61-07 - 0.4kV Switchboard EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01751 | PS5-54-IK-5334B |  | H | H | Damper not operational | CPP AGI | PS5-01-03 - Fire Water Pump B |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-01752 | PS5-02-OB-3336B |  | S | S | Deluge valve not primed | CPP AGI | PS5-06-01 - AC UPS - EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-01753 | PS5-32-UR-3992C |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-01754 | PS5-32-NER-6214A |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-60-10 - Power Generation Package D | 2026-08-05 | Closed | Mohamed, Ali | PS5 - Milestone A | 1
PL-01755 | PS5-48-OB-1266D |  | B | B | Missing door closer | EPS UNATRAC | PS5-12-01 - Cooling Tower | 2026-12-27 | Closed | Wang, Li | PS5 - Milestone F | 5
PL-01756 | PS5-48-OB-7554B |  | M | M | Missing rotation arrow | KENT | PS5-04-03 - 33kV ICSS System |  | In Progress | Jean, Pierre | PS5 - Milestone B | 1.1
PL-01757 | PS5-68-NER-5648C |  | I | I | Missing loop diagram | KENT | PS5-61-07 - 0.4kV Switchboard EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone A | 1
PL-01758 | PS5-73-NI-3110A |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-99-01 - Area Completion Building Area | 2026-09-06 | Closed | Smith, John | PS5 - Milestone C | 2
PL-01759 | PS5-94-NI-5062A |  | E | E | Missing electrical hazard sign | KENT | PS5-63-04 - Electrical Earthing EITS Building | 2026-12-24 | Closed | Wang, Li | PS5 - Milestone G | 6
PL-01760 | PS5-48-NER-1202B |  | T | T | Missing cable label | CPP AGI | PS5-60-10 - Power Generation Package D |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-01761 | PS5-13-OB-4279C |  | H | H | Thermostat calibration needed | CPP AGI | PS5-01-07 - Hydrant System |  | On Hold | Jean, Pierre | PS5 - Milestone I | 8
PL-01762 | PS5-39-UR-8641D |  | E | E | Missing earth continuity label | EPS UNATRAC | PS5-04-04 - 33kV PCS System |  | In Progress | Kumar, Raj | PS5 - Milestone C | 2
PL-01763 | PS5-28-OB-2936A |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-10-04 - Process piping B |  | On Hold | Kumar, Raj | PS5 - Milestone D | 3
PL-01764 | PS5-79-NI-8123C |  | T | T | Intercom not functioning | KENT | PS5-10-06 - Vent System |  | On Hold | Smith, John | PS5 - Milestone C | 2
PL-01765 | PS5-30-OB-4803A |  | M | M | Bearing temperature high | CPP AGI | PS5-05-01 - Telecom Network | 2026-08-17 | Closed | Smith, John | PS5 - Milestone C | 2
PL-01766 | PS5-05-OB-7591C |  | S | S | Fire extinguisher expired | KENT | PS5-03-02 - Fire & Gas Detection |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01767 | PS5-53-UR-9621B |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-12-02 - Water Treatment |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-01768 | PS5-91-IK-6209A |  | H | H | Duct leakage at joint | CPP AGI | PS5-10-02 - Utility Pipe Rack |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-01769 | PS5-63-NER-4218C |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-82-07 - Guard Huts |  | On Hold | Smith, John | PS5 - Milestone F | 5
PL-01770 | PS5-43-NI-2162C |  | P | P | Missing pipe stress label | KENT | PS5-01-08 - Drencher System |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-01771 | PS5-40-OB-8349B |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-07-01 - Chiller System A |  | Originated | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01772 | PS5-41-UR-1084C |  | M | M | Bearing temperature high | CPP AGI | PS5-99-02 - Area Completion Process Area |  | Originated | Smith, John | PS5 - Milestone G | 6
PL-01773 | PS5-12-NER-4914D |  | P | P | Pipe support missing | EPS UNATRAC | PS5-02-01 - Diesel Storage Tank |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-01774 | PS5-10-NI-6800C |  | P | P | Valve handwheel stiff | KENT | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-01775 | PS5-80-NER-6992A |  | E | E | Outgoing breaker not labeled | KENT | PS5-03-01 - ESD System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-01776 | PS5-76-IK-1206C |  | S | S | Eye wash station blocked | CPP AGI | PS5-01-07 - Hydrant System |  | On Hold | Mohamed, Ali | PS5 - Milestone H | 7
PL-01777 | PS5-70-IK-3919A |  | E | E | Missing electrical hazard sign | KENT | PS5-09-04 - 0.4kV Switchboard |  | On Hold | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01778 | PS5-70-NI-7542C |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-01779 | PS5-78-OB-2483D |  | B | B | Missing door closer | CPP AGI | PS5-62-02 - Cable Tray Secondary |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-01780 | PS5-26-UR-4110C |  | S | S | Missing safety sign | CPP AGI | PS5-07-01 - Chiller System A |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-01781 | PS5-63-UR-9283C |  | M | M | Vibration level exceeded | EPS UNATRAC | PS5-01-03 - Fire Water Pump B |  | On Hold | Kumar, Raj | PS5 - Milestone I | 8
PL-01782 | PS5-12-NI-5622D |  | T | T | Fiber patch panel unorganized | KENT | PS5-01-06 - Deluge System |  | Originated | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-01783 | PS5-71-OB-1770B |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-04-03 - 33kV ICSS System |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-01784 | PS5-88-IK-3404A |  | H | H | Damper not operational | EPS UNATRAC | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-01785 | PS5-38-NER-1929D |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-01786 | PS5-10-NI-6553C |  | H | H | FCU drain pipe not connected | KENT | PS5-06-03 - Lightning Protection |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01787 | PS5-32-OB-7159D |  | S | S | Eye wash station blocked | CPP AGI | PS5-99-01 - Area Completion Building Area |  | On Hold | Jean, Pierre | PS5 - Milestone G | 6
PL-01788 | PS5-63-NI-8346A |  | B | B | Missing door closer | EPS UNATRAC | PS5-04-02 - SIS System |  | Originated | Kumar, Raj | PS5 - Milestone G | 6
PL-01789 | PS5-51-NER-4910B |  | S | S | Fire extinguisher expired | CPP AGI | PS5-01-07 - Hydrant System |  | On Hold | Mohamed, Ali | PS5 - Milestone F | 5
PL-01790 | PS5-35-UR-9929C |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-04-01 - DCS System |  | On Hold | Jean, Pierre | PS5 - Milestone I | 8
PL-01791 | PS5-47-IK-1381C |  | B | B | Damaged ceiling panel | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | Originated | Jean, Pierre | PS5 - Milestone C | 2
PL-01792 | PS5-74-IK-7429A |  | I | I | Control valve actuator fault | CPP AGI | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-01793 | PS5-38-OB-5223D |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-01-06 - Deluge System |  | On Hold | Kumar, Raj | PS5 - Milestone C | 2
PL-01794 | PS5-16-NI-1266C |  | H | H | Duct leakage at joint | CPP AGI | PS5-01-06 - Deluge System | 2026-09-17 | Closed | Wang, Li | PS5 - Milestone F | 5
PL-01795 | PS5-98-OB-7523D |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-11-03 - Admin Building |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-01796 | PS5-53-NER-1197A |  | P | P | Insulation damaged | KENT | PS5-04-04 - 33kV PCS System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01797 | PS5-58-IK-7907D |  | S | S | Missing safety sign | EPS UNATRAC | PS5-04-02 - SIS System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01798 | PS5-04-UR-7135D |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-06-03 - Lightning Protection |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-01799 | PS5-41-NER-1884B |  | E | E | Incomplete cable termination | CPP AGI | PS5-62-02 - Cable Tray Secondary |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-01800 | PS5-57-NI-5347A |  | B | B | Missing door closer | EPS UNATRAC | PS5-13-01 - Flare System | 2026-12-11 | Closed | Mohamed, Ali | PS5 - Milestone C | 2
PL-01801 | PS5-07-OB-8540A |  | P | P | Gasket protruding from flange | KENT | PS5-07-02 - Chiller System B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01802 | PS5-43-NER-3016C |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-62-01 - Cable Tray Main |  | On Hold | Mohamed, Ali | PS5 - Milestone E | 4
PL-01803 | PS5-07-IK-4979D |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-09-02 - Transformer 6.6kV/0.4kV |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-01804 | PS5-04-NI-6896B |  | T | T | Missing cable label | CPP AGI | PS5-02-03 - Fuel Gas System | 2026-12-06 | Closed | Jean, Pierre | PS5 - Milestone I | 8
PL-01805 | PS5-24-NI-3185B |  | I | I | Missing loop diagram | CPP AGI | PS5-04-03 - 33kV ICSS System | 2026-10-09 | Closed | Smith, John | PS5 - Milestone H | 7
PL-01806 | PS5-44-IK-1765A |  | T | T | Intercom not functioning | KENT | PS5-60-01 - Power Generation Package A | 2026-09-24 | Closed | Jean, Pierre | PS5 - Milestone C | 2
PL-01807 | PS5-25-IK-3870C |  | B | B | Damaged ceiling panel | KENT | PS5-03-01 - ESD System |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-01808 | PS5-62-OB-6260D |  | I | I | Instrument tubing leak | KENT | PS5-10-03 - Process piping A |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-01809 | PS5-89-NI-2137A |  | P | P | Pipe support missing | KENT | PS5-04-01 - DCS System |  | Originated | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01810 | PS5-24-NER-3466D |  | B | B | Missing door closer | CPP AGI | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-01811 | PS5-94-NER-1463D |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-82-01 - Structural Steel A | 2026-11-13 | Closed | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01812 | PS5-39-IK-5713A |  | I | I | Transmitter not calibrated | KENT | PS5-12-02 - Water Treatment | 2026-09-20 | Closed | Wang, Li | PS5 - Milestone A | 1
PL-01813 | PS5-65-IK-8012B |  | T | T | Missing cable label | EPS UNATRAC | PS5-10-03 - Process piping A | 2026-11-26 | Closed | Mohamed, Ali | PS5 - Milestone A | 1
PL-01814 | PS5-25-NI-6846C |  | B | B | Missing door closer | EPS UNATRAC | PS5-62-01 - Cable Tray Main |  | Originated | Mohamed, Ali | PS5 - Milestone C | 2
PL-01815 | PS5-83-NI-4422A |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-02-01 - Diesel Storage Tank |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-01816 | PS5-77-IK-3341D |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-09-04 - 0.4kV Switchboard | 2026-10-01 | Closed | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01817 | PS5-13-IK-9979C |  | I | I | Control valve actuator fault | CPP AGI | PS5-04-01 - DCS System |  | In Progress | Wang, Li | PS5 - Milestone C | 2
PL-01818 | PS5-01-UR-3989C |  | E | E | Incomplete cable termination | CPP AGI | PS5-03-02 - Fire & Gas Detection |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-01819 | PS5-82-IK-6587B |  | H | H | AHU filter not installed | CPP AGI | PS5-04-02 - SIS System |  | On Hold | Wang, Li | PS5 - Milestone D | 3
PL-01820 | PS5-68-NI-8914A |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-01-09 - Inergen for EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-01821 | PS5-26-OB-7063B |  | M | M | Bearing temperature high | KENT | PS5-01-09 - Inergen for EITS Building |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-01822 | PS5-57-NI-5412C |  | M | M | Bearing temperature high | KENT | PS5-60-07 - Power Generation Package C |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-01823 | PS5-19-NER-2370B |  | I | I | Missing loop diagram | KENT | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-12-02 | Closed | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01824 | PS5-65-NER-5551B |  | E | E | Outgoing breaker not labeled | KENT | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-01825 | PS5-23-OB-8704B |  | S | S | Fire extinguisher expired | CPP AGI | PS5-10-06 - Vent System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-01826 | PS5-38-UR-6855A |  | B | B | Missing door closer | CPP AGI | PS5-60-04 - Power Generation Package B |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-01827 | PS5-76-NI-8738D |  | M | M | Pump alignment required | KENT | PS5-10-06 - Vent System | 2026-08-25 | Closed | Jean, Pierre | PS5 - Milestone B | 1.1
PL-01828 | PS5-41-NER-1686C |  | I | I | Pressure gauge reads zero | CPP AGI | PS5-06-03 - Lightning Protection |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01829 | PS5-28-NI-7737A |  | I | I | Transmitter not calibrated | CPP AGI | PS5-61-01 - 33kV Switchboard EITS Building |  | Originated | Wang, Li | PS5 - Milestone D | 3
PL-01830 | PS5-96-UR-4483B |  | P | P | Missing pipe stress label | EPS UNATRAC | PS5-01-07 - Hydrant System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01831 | PS5-44-IK-5402A |  | S | S | Eye wash station blocked | EPS UNATRAC | PS5-01-09 - Inergen for EITS Building |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-01832 | PS5-97-NER-9063B |  | M | M | Vibration level exceeded | EPS UNATRAC | PS5-01-02 - Fire Water Pump A |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01833 | PS5-98-NI-1739A |  | P | P | Insulation damaged | KENT | PS5-99-02 - Area Completion Process Area |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01834 | PS5-98-IK-6441C |  | H | H | FCU drain pipe not connected | KENT | PS5-09-01 - Transformer 33kV/6.6kV | 2026-10-17 | Closed | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01835 | PS5-69-NER-8541B |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-06-02 - DC UPS - EITS Building | 2026-11-16 | Closed | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01836 | PS5-21-IK-1060C |  | M | M | Motor fan guard missing | KENT | PS5-01-09 - Inergen for EITS Building |  | On Hold | Jean, Pierre | PS5 - Milestone I | 8
PL-01837 | PS5-21-IK-4600A |  | P | P | Insulation damaged | EPS UNATRAC | PS5-60-07 - Power Generation Package C |  | On Hold | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01838 | PS5-57-IK-1040B |  | P | P | Pipe support missing | CPP AGI | PS5-60-01 - Power Generation Package A | 2026-12-07 | Closed | Kumar, Raj | PS5 - Milestone E | 4
PL-01839 | PS5-20-OB-3403D |  | I | I | Instrument tubing leak | KENT | PS5-02-03 - Fuel Gas System |  | Originated | Mohamed, Ali | PS5 - Milestone F | 5
PL-01840 | PS5-18-NER-3366A |  | M | M | Bearing temperature high | CPP AGI | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-01841 | PS5-74-UR-1588C |  | T | T | PA speaker not tested | KENT | PS5-99-03 - Area Completion Utilities Area |  | On Hold | Mohamed, Ali | PS5 - Milestone A | 1
PL-01842 | PS5-75-OB-5251A |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-63-01 - Electrical Earthing |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-01843 | PS5-60-NI-2086B |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-10-05 - Drain System | 2026-11-24 | Closed | Mohamed, Ali | PS5 - Milestone F | 5
PL-01844 | PS5-81-NER-3746B |  | T | T | CCTV camera not focused | KENT | PS5-01-08 - Drencher System |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-01845 | PS5-20-IK-7539C |  | M | M | Missing rotation arrow | CPP AGI | PS5-62-02 - Cable Tray Secondary | 2026-11-13 | Closed | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01846 | PS5-70-NI-7340D |  | B | B | Missing fire extinguisher signage | KENT | PS5-11-01 - Guard Hut A |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-01847 | PS5-05-UR-1771B |  | H | H | Damper not operational | KENT | PS5-01-04 - Fire Water Ring Main |  | Originated | Jean, Pierre | PS5 - Milestone H | 7
PL-01848 | PS5-06-IK-6180A |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-04-03 - 33kV ICSS System | 2026-10-20 | Closed | Mohamed, Ali | PS5 - Milestone I | 8
PL-01849 | PS5-89-NER-1217D |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-01850 | PS5-05-OB-3080C |  | E | E | Missing electrical hazard sign | KENT | PS5-05-02 - PA/GA System | 2026-10-15 | Closed | Smith, John | PS5 - Milestone D | 3
PL-01851 | PS5-09-OB-8919D |  | I | I | Missing instrument tag | EPS UNATRAC | PS5-09-04 - 0.4kV Switchboard | 2026-08-03 | Closed | Wang, Li | PS5 - Milestone E | 4
PL-01852 | PS5-52-NI-8273A |  | E | E | Outgoing breaker not labeled | CPP AGI | PS5-04-04 - 33kV PCS System |  | On Hold | Smith, John | PS5 - Milestone D | 3
PL-01853 | PS5-07-IK-4803C |  | E | E | Wrong cable glanding | KENT | PS5-01-05 - Foam System |  | On Hold | Wang, Li | PS5 - Milestone H | 7
PL-01854 | PS5-38-UR-4799D |  | M | M | Bearing temperature high | KENT | PS5-12-01 - Cooling Tower |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-01855 | PS5-62-IK-9169C |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-10-03 - Process piping A |  | Originated | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01856 | PS5-19-NER-4826A |  | P | P | Insulation damaged | KENT | PS5-99-02 - Area Completion Process Area |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-01857 | PS5-91-OB-3681D |  | I | I | Missing loop diagram | EPS UNATRAC | PS5-01-05 - Foam System |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-01858 | PS5-81-OB-9807A |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-10-03 - Process piping A |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-01859 | PS5-16-OB-6844C |  | B | B | Incomplete paint touch-up | KENT | PS5-82-01 - Structural Steel A | 2026-11-06 | Closed | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01860 | PS5-21-IK-2260C |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-09-03 - Motor Control Center |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-01861 | PS5-91-NI-5180D |  | E | E | Missing earth continuity label | CPP AGI | PS5-10-01 - Main Pipe Rack | 2026-11-23 | Closed | Wang, Li | PS5 - Milestone B | 1.1
PL-01862 | PS5-17-NI-7636B |  | T | T | Intercom not functioning | KENT | PS5-63-01 - Electrical Earthing |  | Originated | Jean, Pierre | PS5 - Milestone E | 4
PL-01863 | PS5-93-NI-7299C |  | I | I | Missing loop diagram | KENT | PS5-01-04 - Fire Water Ring Main |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-01864 | PS5-54-NER-8135D |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-01865 | PS5-29-OB-9916A |  | P | P | Pipe support missing | KENT | PS5-60-07 - Power Generation Package C | 2026-09-22 | Closed | Wang, Li | PS5 - Milestone D | 3
PL-01866 | PS5-79-UR-6364A |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-08-16 | Closed | Mohamed, Ali | PS5 - Milestone I | 8
PL-01867 | PS5-51-OB-8115D |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-08-15 | Closed | Smith, John | PS5 - Milestone E | 4
PL-01868 | PS5-28-UR-6844C |  | B | B | Incomplete paint touch-up | EPS UNATRAC | PS5-03-03 - Flame Detector System |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-01869 | PS5-34-UR-5892C |  | P | P | Flange bolt torque incomplete | EPS UNATRAC | PS5-12-01 - Cooling Tower |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-01870 | PS5-93-IK-5441D |  | P | P | Gasket protruding from flange | KENT | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-01871 | PS5-30-UR-5140D |  | S | S | Eye wash station blocked | CPP AGI | PS5-82-07 - Guard Huts | 2026-11-25 | Closed | Smith, John | PS5 - Milestone C | 2
PL-01872 | PS5-76-NER-9617C |  | E | E | Missing electrical hazard sign | KENT | PS5-13-01 - Flare System | 2026-08-09 | Closed | Mohamed, Ali | PS5 - Milestone H | 7
PL-01873 | PS5-42-OB-4995B |  | I | I | Missing instrument tag | KENT | PS5-01-09 - Inergen for EITS Building |  | On Hold | Smith, John | PS5 - Milestone C | 2
PL-01874 | PS5-69-NER-4984A |  | S | S | Emergency shower not tested | KENT | PS5-03-01 - ESD System | 2026-08-24 | Closed | Kumar, Raj | PS5 - Milestone I | 8
PL-01875 | PS5-69-NER-3798C |  | E | E | Cable tray not properly supported | EPS UNATRAC | PS5-10-06 - Vent System |  | On Hold | Smith, John | PS5 - Milestone B | 1.1
PL-01876 | PS5-55-OB-3111B |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-63-04 - Electrical Earthing EITS Building |  | Originated | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01877 | PS5-10-OB-5313A |  | S | S | Deluge valve not primed | KENT | PS5-01-01 - Fire Water Jockey Pump A/B |  | On Hold | Jean, Pierre | PS5 - Milestone C | 2
PL-01878 | PS5-56-OB-6490D |  | B | B | Missing fire extinguisher signage | KENT | PS5-60-10 - Power Generation Package D |  | Originated | Wang, Li | PS5 - Milestone A | 1
PL-01879 | PS5-62-UR-2689B |  | P | P | Valve handwheel stiff | EPS UNATRAC | PS5-04-02 - SIS System | 2026-08-13 | Closed | Mohamed, Ali | PS5 - Milestone C | 2
PL-01880 | PS5-95-NI-3304A |  | H | H | Damper not operational | CPP AGI | PS5-01-03 - Fire Water Pump B |  | On Hold | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01881 | PS5-18-UR-2566D |  | B | B | Incomplete paint touch-up | EPS UNATRAC | PS5-01-05 - Foam System | 2026-08-12 | Closed | Kumar, Raj | PS5 - Milestone F | 5
PL-01882 | PS5-29-NI-2655A |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-02-01 - Diesel Storage Tank |  | In Progress | Jean, Pierre | PS5 - Milestone B | 1.1
PL-01883 | PS5-32-NI-5164B |  | P | P | Insulation damaged | CPP AGI | PS5-06-01 - AC UPS - EITS Building |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-01884 | PS5-55-UR-3838B |  | M | M | Vibration level exceeded | EPS UNATRAC | PS5-11-01 - Guard Hut A | 2026-10-20 | Closed | Smith, John | PS5 - Milestone C | 2
PL-01885 | PS5-82-NER-4973B |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-06-02 - DC UPS - EITS Building | 2026-09-14 | Closed | Kumar, Raj | PS5 - Milestone E | 4
PL-01886 | PS5-43-IK-7285D |  | P | P | Insulation damaged | CPP AGI | PS5-05-03 - CCTV System |  | On Hold | Mohamed, Ali | PS5 - Milestone H | 7
PL-01887 | PS5-82-NI-1992C |  | P | P | Insulation damaged | CPP AGI | PS5-01-09 - Inergen for EITS Building |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-01888 | PS5-75-OB-3609B |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-03-02 - Fire & Gas Detection |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-01889 | PS5-90-NER-3085D |  | S | S | Fire alarm panel fault | KENT | PS5-62-01 - Cable Tray Main |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-01890 | PS5-61-UR-3566C |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-08-02 - Nitrogen Generator | 2026-10-04 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-01891 | PS5-37-NER-9987B |  | S | S | Deluge valve not primed | KENT | PS5-06-03 - Lightning Protection |  | On Hold | Smith, John | PS5 - Milestone I | 8
PL-01892 | PS5-38-NI-8706C |  | I | I | Missing loop diagram | CPP AGI | PS5-01-04 - Fire Water Ring Main |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-01893 | PS5-13-NER-9442C |  | E | E | Outgoing breaker not labeled | CPP AGI | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-01894 | PS5-08-NER-3720D |  | E | E | Cable tray not properly supported | EPS UNATRAC | PS5-01-04 - Fire Water Ring Main |  | Originated | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01895 | PS5-94-OB-4407A |  | M | M | Pump alignment required | EPS UNATRAC | PS5-61-07 - 0.4kV Switchboard EITS Building |  | On Hold | Mohamed, Ali | PS5 - Milestone H | 7
PL-01896 | PS5-83-OB-3361C |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-06-03 - Lightning Protection |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-01897 | PS5-14-NER-3272C |  | S | S | Fire alarm panel fault | KENT | PS5-10-02 - Utility Pipe Rack |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-01898 | PS5-11-UR-3974C |  | M | M | Motor fan guard missing | KENT | PS5-01-02 - Fire Water Pump A |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-01899 | PS5-88-NI-4673A |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-01900 | PS5-04-UR-7575D |  | E | E | Missing earth continuity label | KENT | PS5-01-05 - Foam System |  | On Hold | Kumar, Raj | PS5 - Milestone B | 1.1
PL-01901 | PS5-62-IK-5483C |  | M | M | Pump alignment required | EPS UNATRAC | PS5-01-05 - Foam System | 2026-11-22 | Closed | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01902 | PS5-77-IK-1617A |  | B | B | Damaged ceiling panel | EPS UNATRAC | PS5-09-02 - Transformer 6.6kV/0.4kV |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-01903 | PS5-76-UR-1408A |  | E | E | Wrong cable glanding | KENT | PS5-03-02 - Fire & Gas Detection |  | Originated | Wang, Li | PS5 - Milestone G | 6
PL-01904 | PS5-52-NI-1540C |  | H | H | Duct leakage at joint | CPP AGI | PS5-01-05 - Foam System |  | In Progress | Kumar, Raj | PS5 - Milestone C | 2
PL-01905 | PS5-20-UR-4432B |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-08-02 - Nitrogen Generator | 2026-10-18 | Closed | Smith, John | PS5 - Milestone E | 4
PL-01906 | PS5-08-UR-6307D |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-82-07 - Guard Huts |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-01907 | PS5-03-IK-5971D |  | E | E | Outgoing breaker not labeled | EPS UNATRAC | PS5-99-02 - Area Completion Process Area | 2026-12-22 | Closed | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-01908 | PS5-81-OB-6195A |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-02-03 - Fuel Gas System |  | Originated | Wang, Li | PS5 - Milestone E | 4
PL-01909 | PS5-55-IK-2175A |  | E | E | Cable tray not properly supported | EPS UNATRAC | PS5-07-02 - Chiller System B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01910 | PS5-37-IK-5087C |  | T | T | Fiber patch panel unorganized | KENT | PS5-10-03 - Process piping A |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-01911 | PS5-07-NER-8099D |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-01-07 - Hydrant System |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-01912 | PS5-64-OB-2229A |  | E | E | Outgoing breaker not labeled | KENT | PS5-61-01 - 33kV Switchboard EITS Building | 2026-09-25 | Closed | Mohamed, Ali | PS5 - Milestone I | 8
PL-01913 | PS5-91-NI-5520C |  | M | M | Coupling guard loose | KENT | PS5-99-01 - Area Completion Building Area |  | On Hold | Smith, John | PS5 - Milestone B | 1.1
PL-01914 | PS5-14-NI-6582B |  | S | S | Eye wash station blocked | EPS UNATRAC | PS5-10-01 - Main Pipe Rack |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-01915 | PS5-58-UR-8465A |  | S | S | Missing safety sign | CPP AGI | PS5-07-01 - Chiller System A |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-01916 | PS5-03-UR-2359B |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-60-10 - Power Generation Package D |  | Originated | Mohamed, Ali | PS5 - Milestone F | 5
PL-01917 | PS5-24-OB-1663D |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-07-03 - AHU System |  | On Hold | Smith, John | PS5 - Milestone A | 1
PL-01918 | PS5-08-OB-2643B |  | E | E | Missing electrical hazard sign | KENT | PS5-01-01 - Fire Water Jockey Pump A/B |  | On Hold | Jean, Pierre | PS5 - Milestone A | 1
PL-01919 | PS5-71-IK-3965A |  | B | B | Incomplete floor tiling | CPP AGI | PS5-82-02 - Structural Steel B | 2026-09-08 | Closed | Mohamed, Ali | PS5 - Milestone G | 6
PL-01920 | PS5-78-NI-5868A |  | B | B | Damaged ceiling panel | EPS UNATRAC | PS5-09-04 - 0.4kV Switchboard |  | In Progress | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01921 | PS5-91-UR-5034B |  | B | B | Missing fire extinguisher signage | CPP AGI | PS5-09-03 - Motor Control Center |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-01922 | PS5-76-IK-1125D |  | I | I | Pressure gauge reads zero | KENT | PS5-10-05 - Drain System |  | On Hold | Mohamed, Ali | PS5 - Milestone H | 7
PL-01923 | PS5-68-IK-1478A |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-12-02 - Water Treatment |  | In Progress | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-01924 | PS5-79-OB-3068D |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-01-04 - Fire Water Ring Main | 2026-09-10 | Closed | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01925 | PS5-17-NI-1596A |  | M | M | Motor fan guard missing | KENT | PS5-10-01 - Main Pipe Rack |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-01926 | PS5-75-UR-3390A |  | I | I | Missing instrument tag | KENT | PS5-01-03 - Fire Water Pump B | 2026-09-15 | Closed | Kumar, Raj | PS5 - Milestone G | 6
PL-01927 | PS5-41-OB-6294D |  | T | T | PA speaker not tested | CPP AGI | PS5-09-01 - Transformer 33kV/6.6kV |  | On Hold | Mohamed, Ali | PS5 - Milestone D | 3
PL-01928 | PS5-54-NI-8043C |  | M | M | Pump alignment required | CPP AGI | PS5-01-03 - Fire Water Pump B |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-01929 | PS5-94-UR-7365B |  | M | M | Bearing temperature high | CPP AGI | PS5-12-01 - Cooling Tower |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-01930 | PS5-19-NER-7789A |  | I | I | Missing loop diagram | EPS UNATRAC | PS5-63-01 - Electrical Earthing |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-01931 | PS5-66-OB-4185B |  | E | E | Incomplete cable termination | CPP AGI | PS5-10-03 - Process piping A |  | Originated | Kumar, Raj | PS5 - Milestone I | 8
PL-01932 | PS5-69-OB-4017A |  | H | H | Damper not operational | CPP AGI | PS5-60-07 - Power Generation Package C | 2026-09-11 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-01933 | PS5-91-IK-6043A |  | H | H | Missing insulation on duct | EPS UNATRAC | PS5-07-02 - Chiller System B |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-01934 | PS5-75-UR-7294A |  | I | I | Pressure gauge reads zero | EPS UNATRAC | PS5-60-07 - Power Generation Package C |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-01935 | PS5-19-NI-6536C |  | S | S | Eye wash station blocked | KENT | PS5-01-02 - Fire Water Pump A | 2026-09-08 | Closed | Mohamed, Ali | PS5 - Milestone C | 2
PL-01936 | PS5-06-OB-1331D |  | H | H | Damper not operational | CPP AGI | PS5-07-03 - AHU System |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-01937 | PS5-63-OB-3571C |  | S | S | Emergency shower not tested | CPP AGI | PS5-60-07 - Power Generation Package C |  | On Hold | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-01938 | PS5-31-NI-3885D |  | M | M | Bearing temperature high | KENT | PS5-02-03 - Fuel Gas System |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-01939 | PS5-28-UR-4778C |  | I | I | Control valve actuator fault | CPP AGI | PS5-82-02 - Structural Steel B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01940 | PS5-83-IK-4467B |  | M | M | Missing rotation arrow | CPP AGI | PS5-12-01 - Cooling Tower | 2026-08-19 | Closed | Smith, John | PS5 - Milestone A | 1
PL-01941 | PS5-83-OB-8049A |  | T | T | Missing cable label | KENT | PS5-02-02 - Diesel Transfer Pump |  | Originated | Jean, Pierre | PS5 - Milestone A | 1
PL-01942 | PS5-46-NI-6064A |  | P | P | Insulation damaged | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-01943 | PS5-11-NER-8679B |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-07-04 - FCU System | 2026-09-24 | Closed | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01944 | PS5-16-NI-5844D |  | M | M | Coupling guard loose | KENT | PS5-11-01 - Guard Hut A | 2026-08-26 | Closed | Jean, Pierre | PS5 - Milestone G | 6
PL-01945 | PS5-44-UR-6645A |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | On Hold | Wang, Li | PS5 - Milestone H | 7
PL-01946 | PS5-83-OB-8811C |  | S | S | Missing safety sign | KENT | PS5-01-09 - Inergen for EITS Building |  | Originated | Wang, Li | PS5 - Milestone C | 2
PL-01947 | PS5-88-NER-1393B |  | E | E | Incomplete cable termination | KENT | PS5-01-08 - Drencher System | 2026-11-21 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-01948 | PS5-75-IK-2173D |  | S | S | Missing safety sign | EPS UNATRAC | PS5-07-01 - Chiller System A | 2026-08-18 | Closed | Wang, Li | PS5 - Milestone F | 5
PL-01949 | PS5-25-UR-1656A |  | M | M | Motor fan guard missing | EPS UNATRAC | PS5-13-01 - Flare System | 2026-09-20 | Closed | Jean, Pierre | PS5 - Milestone G | 6
PL-01950 | PS5-90-UR-4394A |  | T | T | PA speaker not tested | KENT | PS5-11-02 - Guard Hut B |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-01951 | PS5-71-IK-9141B |  | S | S | Fire alarm panel fault | KENT | PS5-60-01 - Power Generation Package A | 2026-08-16 | Closed | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01952 | PS5-46-IK-8011B |  | P | P | Pipe support missing | EPS UNATRAC | PS5-07-01 - Chiller System A | 2026-08-27 | Closed | Smith, John | PS5 - Milestone I | 8
PL-01953 | PS5-41-OB-4614D |  | T | T | Missing cable label | EPS UNATRAC | PS5-07-03 - AHU System |  | Originated | Smith, John | PS5 - Milestone F | 5
PL-01954 | PS5-34-NI-8230C |  | P | P | Missing pipe stress label | EPS UNATRAC | PS5-60-07 - Power Generation Package C |  | On Hold | Smith, John | PS5 - Milestone F | 5
PL-01955 | PS5-03-OB-7664C |  | H | H | Missing insulation on duct | CPP AGI | PS5-05-02 - PA/GA System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-01956 | PS5-87-UR-7909D |  | S | S | Missing safety sign | CPP AGI | PS5-04-01 - DCS System |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-01957 | PS5-28-OB-5412D |  | T | T | Fiber patch panel unorganized | KENT | PS5-05-03 - CCTV System |  | In Progress | Jean, Pierre | PS5 - Milestone D | 3
PL-01958 | PS5-26-OB-9084B |  | E | E | Outgoing breaker not labeled | CPP AGI | PS5-10-03 - Process piping A |  | On Hold | Wang, Li | PS5 - Milestone G | 6
PL-01959 | PS5-15-NI-5772C |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-10-01 - Main Pipe Rack |  | On Hold | Smith, John | PS5 - Milestone F | 5
PL-01960 | PS5-72-IK-4981A |  | B | B | Incomplete paint touch-up | EPS UNATRAC | PS5-07-01 - Chiller System A |  | In Progress | Wang, Li | PS5 - Milestone D | 3
PL-01961 | PS5-57-UR-7478A |  | H | H | Thermostat calibration needed | KENT | PS5-01-08 - Drencher System |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-01962 | PS5-04-UR-9486B |  | H | H | Missing insulation on duct | CPP AGI | PS5-61-07 - 0.4kV Switchboard EITS Building |  | Originated | Jean, Pierre | PS5 - Milestone D | 3
PL-01963 | PS5-66-IK-9851C |  | S | S | Missing safety sign | CPP AGI | PS5-09-01 - Transformer 33kV/6.6kV | 2026-12-13 | Closed | Wang, Li | PS5 - Milestone I | 8
PL-01964 | PS5-78-OB-8124D |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-07-01 - Chiller System A |  | Originated | Jean, Pierre | PS5 - Milestone G | 6
PL-01965 | PS5-48-UR-4525B |  | B | B | Incomplete paint touch-up | KENT | PS5-13-01 - Flare System | 2026-09-09 | Closed | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01966 | PS5-68-NI-1585B |  | E | E | Outgoing breaker not labeled | CPP AGI | PS5-03-02 - Fire & Gas Detection | 2026-12-02 | Closed | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-01967 | PS5-88-IK-6409A |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-10-01 - Main Pipe Rack | 2026-12-11 | Closed | Wang, Li | PS5 - Milestone A | 1
PL-01968 | PS5-46-NI-1818A |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-09-04 - 0.4kV Switchboard |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-01969 | PS5-15-NER-8385C |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-03-02 - Fire & Gas Detection |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01970 | PS5-89-NI-4345B |  | B | B | Missing fire extinguisher signage | KENT | PS5-04-04 - 33kV PCS System |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-01971 | PS5-55-UR-2395C |  | E | E | Incomplete cable termination | KENT | PS5-03-02 - Fire & Gas Detection |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-01972 | PS5-93-OB-1460B |  | T | T | CCTV camera not focused | CPP AGI | PS5-12-01 - Cooling Tower | 2026-11-28 | Closed | Jean, Pierre | PS5 - Milestone I | 8
PL-01973 | PS5-42-NER-3456C |  | P | P | Pipe support missing | EPS UNATRAC | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-01974 | PS5-62-OB-1709A |  | I | I | Instrument tubing leak | KENT | PS5-08-02 - Nitrogen Generator | 2026-08-15 | Closed | Kumar, Raj | PS5 - Milestone I | 8
PL-01975 | PS5-01-IK-9444B |  | M | M | Missing rotation arrow | CPP AGI | PS5-61-07 - 0.4kV Switchboard EITS Building |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-01976 | PS5-82-OB-2003A |  | H | H | Damper not operational | CPP AGI | PS5-82-07 - Guard Huts |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-01977 | PS5-73-NER-3049D |  | P | P | Flange bolt torque incomplete | KENT | PS5-10-03 - Process piping A | 2026-09-01 | Closed | Wang, Li | PS5 - Milestone G | 6
PL-01978 | PS5-61-NER-2899A |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-07-03 - AHU System |  | On Hold | Mohamed, Ali | PS5 - Milestone I | 8
PL-01979 | PS5-26-UR-2007A |  | H | H | Duct leakage at joint | EPS UNATRAC | PS5-10-05 - Drain System |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-01980 | PS5-87-OB-9009A |  | E | E | Outgoing breaker not labeled | EPS UNATRAC | PS5-01-07 - Hydrant System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-01981 | PS5-55-UR-8778A |  | P | P | Valve handwheel stiff | KENT | PS5-82-07 - Guard Huts |  | On Hold | Wang, Li | PS5 - Milestone H | 7
PL-01982 | PS5-78-NI-7187C |  | S | S | Emergency shower not tested | CPP AGI | PS5-11-03 - Admin Building |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-01983 | PS5-18-NER-6972A |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-09-03 - Motor Control Center |  | Originated | Kumar, Raj | PS5 - Milestone A | 1
PL-01984 | PS5-80-UR-8514A |  | I | I | Missing instrument tag | CPP AGI | PS5-06-01 - AC UPS - EITS Building |  | On Hold | Mohamed, Ali | PS5 - Milestone C | 2
PL-01985 | PS5-76-UR-2353D |  | T | T | CAT6 cable untidied | KENT | PS5-08-02 - Nitrogen Generator |  | Originated | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-01986 | PS5-65-UR-3204B |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-01-06 - Deluge System |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-01987 | PS5-29-OB-5735C |  | I | I | Missing instrument tag | CPP AGI | PS5-09-02 - Transformer 6.6kV/0.4kV |  | On Hold | Jean, Pierre | PS5 - Milestone H | 7
PL-01988 | PS5-61-NI-2495D |  | P | P | Insulation damaged | EPS UNATRAC | PS5-99-01 - Area Completion Building Area |  | In Progress | Jean, Pierre | PS5 - Milestone B | 1.1
PL-01989 | PS5-27-UR-9107C |  | S | S | Deluge valve not primed | CPP AGI | PS5-60-04 - Power Generation Package B |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-01990 | PS5-43-OB-3727D |  | S | S | Missing safety sign | KENT | PS5-12-02 - Water Treatment |  | In Progress | Wang, Li | PS5 - Milestone C | 2
PL-01991 | PS5-85-IK-1340C |  | H | H | Thermostat calibration needed | KENT | PS5-10-02 - Utility Pipe Rack |  | Originated | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01992 | PS5-72-OB-5584A |  | E | E | Missing earth continuity label | CPP AGI | PS5-10-03 - Process piping A |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-01993 | PS5-84-IK-7248C |  | E | E | Missing earth continuity label | EPS UNATRAC | PS5-60-10 - Power Generation Package D |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-01994 | PS5-76-IK-2080C |  | E | E | Missing electrical hazard sign | KENT | PS5-01-08 - Drencher System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-01995 | PS5-43-OB-2056B |  | B | B | Cracked wall plaster | CPP AGI | PS5-10-04 - Process piping B |  | On Hold | Jean, Pierre | PS5 - Milestone I | 8
PL-01996 | PS5-55-UR-4972D |  | B | B | Missing door closer | EPS UNATRAC | PS5-07-04 - FCU System |  | On Hold | Jean, Pierre | PS5 - Milestone A | 1
PL-01997 | PS5-98-NI-5965D |  | B | B | Incomplete paint touch-up | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | On Hold | Mohamed, Ali | PS5 - Milestone C | 2
PL-01998 | PS5-05-OB-9986D |  | T | T | Intercom not functioning | CPP AGI | PS5-01-01 - Fire Water Jockey Pump A/B |  | On Hold | Wang, Li | PS5 - Milestone F | 5
PL-01999 | PS5-65-OB-3285A |  | I | I | Control valve actuator fault | KENT | PS5-01-02 - Fire Water Pump A |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-02000 | PS5-83-UR-2701B |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-04-02 - SIS System |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-02001 | PS5-68-NI-4551B |  | T | T | Missing cable label | KENT | PS5-03-01 - ESD System |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-02002 | PS5-21-NER-7578A |  | P | P | Pipe support missing | KENT | PS5-01-04 - Fire Water Ring Main |  | In Progress | Jean, Pierre | PS5 - Milestone B | 1.1
PL-02003 | PS5-25-NER-7505A |  | S | S | Missing safety sign | KENT | PS5-62-01 - Cable Tray Main |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-02004 | PS5-75-IK-6209C |  | H | H | Duct leakage at joint | KENT | PS5-06-01 - AC UPS - EITS Building |  | On Hold | Jean, Pierre | PS5 - Milestone I | 8
PL-02005 | PS5-64-NER-5855A |  | P | P | Pipe support missing | KENT | PS5-11-02 - Guard Hut B |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-02006 | PS5-99-NER-2791D |  | P | P | Insulation damaged | CPP AGI | PS5-01-04 - Fire Water Ring Main |  | Originated | Mohamed, Ali | PS5 - Milestone F | 5
PL-02007 | PS5-51-OB-2520C |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-06-02 - DC UPS - EITS Building |  | On Hold | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-02008 | PS5-06-UR-4008B |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-10-04 - Process piping B |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-02009 | PS5-07-IK-1272D |  | H | H | FCU drain pipe not connected | EPS UNATRAC | PS5-63-01 - Electrical Earthing |  | On Hold | Jean, Pierre | PS5 - Milestone I | 8
PL-02010 | PS5-09-NI-7413D |  | B | B | Missing fire extinguisher signage | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-02011 | PS5-30-IK-7685C |  | M | M | Pump alignment required | CPP AGI | PS5-05-02 - PA/GA System |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-02012 | PS5-26-UR-3229D |  | B | B | Incomplete floor tiling | KENT | PS5-60-04 - Power Generation Package B |  | On Hold | Smith, John | PS5 - Milestone C | 2
PL-02013 | PS5-95-OB-1407C |  | S | S | Eye wash station blocked | EPS UNATRAC | PS5-04-02 - SIS System |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-02014 | PS5-33-UR-7232C |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-09-04 - 0.4kV Switchboard |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-02015 | PS5-09-OB-7239C |  | P | P | Missing pipe stress label | KENT | PS5-10-03 - Process piping A |  | On Hold | Kumar, Raj | PS5 - Milestone E | 4
PL-02016 | PS5-85-OB-9962D |  | S | S | Deluge valve not primed | CPP AGI | PS5-12-01 - Cooling Tower | 2026-12-24 | Closed | Jean, Pierre | PS5 - Milestone I | 8
PL-02017 | PS5-41-IK-3527A |  | S | S | Deluge valve not primed | KENT | PS5-99-02 - Area Completion Process Area |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-02018 | PS5-53-NI-4578C |  | T | T | Intercom not functioning | KENT | PS5-12-02 - Water Treatment |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-02019 | PS5-46-UR-6006B |  | M | M | Pump alignment required | CPP AGI | PS5-08-02 - Nitrogen Generator |  | On Hold | Mohamed, Ali | PS5 - Milestone G | 6
PL-02020 | PS5-36-IK-4213C |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-05-03 - CCTV System | 2026-08-15 | Closed | Smith, John | PS5 - Milestone I | 8
PL-02021 | PS5-86-UR-4959C |  | T | T | Fiber patch panel unorganized | EPS UNATRAC | PS5-07-04 - FCU System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-02022 | PS5-87-IK-1079B |  | S | S | Eye wash station blocked | CPP AGI | PS5-04-02 - SIS System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-02023 | PS5-88-IK-4666D |  | H | H | FCU drain pipe not connected | KENT | PS5-03-01 - ESD System | 2026-12-09 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-02024 | PS5-52-OB-4025D |  | I | I | Instrument tubing leak | CPP AGI | PS5-02-02 - Diesel Transfer Pump | 2026-10-28 | Closed | Jean, Pierre | PS5 - Milestone B | 1.1
PL-02025 | PS5-68-OB-9124A |  | S | S | Emergency shower not tested | CPP AGI | PS5-60-01 - Power Generation Package A |  | On Hold | Kumar, Raj | PS5 - Milestone C | 2
PL-02026 | PS5-06-NI-2324C |  | P | P | Valve handwheel stiff | EPS UNATRAC | PS5-11-03 - Admin Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-02027 | PS5-29-NER-1512D |  | E | E | Incomplete cable termination | KENT | PS5-82-07 - Guard Huts |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-02028 | PS5-57-OB-7312A |  | T | T | Missing cable label | CPP AGI | PS5-06-01 - AC UPS - EITS Building |  | On Hold | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-02029 | PS5-13-IK-7951A |  | P | P | Valve handwheel stiff | EPS UNATRAC | PS5-82-02 - Structural Steel B |  | On Hold | Kumar, Raj | PS5 - Milestone F | 5
PL-02030 | PS5-31-UR-4848D |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-62-02 - Cable Tray Secondary | 2026-08-20 | Closed | Mohamed, Ali | PS5 - Milestone G | 6
PL-02031 | PS5-43-NI-9844A |  | E | E | Missing earth continuity label | KENT | PS5-62-01 - Cable Tray Main |  | On Hold | Wang, Li | PS5 - Milestone H | 7
PL-02032 | PS5-36-IK-9700D |  | S | S | Fire alarm panel fault | CPP AGI | PS5-62-02 - Cable Tray Secondary |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-02033 | PS5-20-UR-3379B |  | M | M | Missing rotation arrow | KENT | PS5-99-03 - Area Completion Utilities Area |  | On Hold | Smith, John | PS5 - Milestone F | 5
PL-02034 | PS5-31-UR-5035B |  | M | M | Bearing temperature high | KENT | PS5-12-02 - Water Treatment |  | On Hold | Mohamed, Ali | PS5 - Milestone A | 1
PL-02035 | PS5-38-NI-1397C |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-62-02 - Cable Tray Secondary |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-02036 | PS5-56-NI-7103A |  | I | I | Transmitter not calibrated | CPP AGI | PS5-02-02 - Diesel Transfer Pump |  | On Hold | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-02037 | PS5-15-NER-3072B |  | H | H | Missing insulation on duct | KENT | PS5-82-07 - Guard Huts | 2026-09-22 | Closed | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-02038 | PS5-11-UR-9248B |  | T | T | CCTV camera not focused | KENT | PS5-07-02 - Chiller System B |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-02039 | PS5-56-NER-2866D |  | H | H | Missing insulation on duct | EPS UNATRAC | PS5-03-01 - ESD System | 2026-09-22 | Closed | Jean, Pierre | PS5 - Milestone I | 8
PL-02040 | PS5-95-NI-2326B |  | T | T | Missing cable label | KENT | PS5-99-01 - Area Completion Building Area |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-02041 | PS5-49-NI-4998C |  | M | M | Vibration level exceeded | KENT | PS5-09-04 - 0.4kV Switchboard |  | Originated | Kumar, Raj | PS5 - Milestone F | 5
PL-02042 | PS5-65-NER-8415D |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-07-02 - Chiller System B |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-02043 | PS5-89-NER-6701B |  | B | B | Missing fire extinguisher signage | KENT | PS5-09-03 - Motor Control Center |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-02044 | PS5-71-IK-8313A |  | H | H | Duct leakage at joint | CPP AGI | PS5-08-01 - Compressor Air System |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-02045 | PS5-13-IK-9772C |  | E | E | Missing earth continuity label | CPP AGI | PS5-08-02 - Nitrogen Generator | 2026-09-05 | Closed | Mohamed, Ali | PS5 - Milestone D | 3
PL-02046 | PS5-97-NER-9568A |  | I | I | Missing instrument tag | CPP AGI | PS5-05-03 - CCTV System |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-02047 | PS5-77-UR-8632C |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-09-24 | Closed | Wang, Li | PS5 - Milestone A | 1
PL-02048 | PS5-17-UR-5210C |  | M | M | Pump alignment required | EPS UNATRAC | PS5-99-01 - Area Completion Building Area |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-02049 | PS5-86-NI-6253A |  | T | T | Missing cable label | KENT | PS5-01-02 - Fire Water Pump A | 2026-08-26 | Closed | Smith, John | PS5 - Milestone H | 7
PL-02050 | PS5-39-OB-5252D |  | B | B | Missing door closer | KENT | PS5-13-01 - Flare System |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-02051 | PS5-24-NER-8008B |  | T | T | Missing cable label | KENT | PS5-04-03 - 33kV ICSS System |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-02052 | PS5-75-OB-7566A |  | T | T | Intercom not functioning | CPP AGI | PS5-03-03 - Flame Detector System |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-02053 | PS5-26-NI-9597B |  | S | S | Eye wash station blocked | CPP AGI | PS5-62-02 - Cable Tray Secondary | 2026-09-15 | Closed | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-02054 | PS5-39-OB-7405D |  | H | H | Damper not operational | CPP AGI | PS5-04-02 - SIS System |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-02055 | PS5-54-UR-5885A |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-07-01 - Chiller System A |  | Originated | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-02056 | PS5-95-NER-4394D |  | P | P | Insulation damaged | KENT | PS5-06-01 - AC UPS - EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-02057 | PS5-76-NI-8914D |  | T | T | Missing cable label | EPS UNATRAC | PS5-01-04 - Fire Water Ring Main |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-02058 | PS5-89-UR-6644C |  | I | I | Missing loop diagram | CPP AGI | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-11-24 | Closed | Wang, Li | PS5 - Milestone A | 1
PL-02059 | PS5-29-OB-2055A |  | H | H | Missing insulation on duct | KENT | PS5-03-03 - Flame Detector System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-02060 | PS5-21-OB-8861A |  | S | S | Emergency shower not tested | KENT | PS5-04-03 - 33kV ICSS System |  | Originated | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-02061 | PS5-43-NER-9615C |  | E | E | Outgoing breaker not labeled | EPS UNATRAC | PS5-03-03 - Flame Detector System |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-02062 | PS5-41-IK-3208A |  | M | M | Pump alignment required | CPP AGI | PS5-82-07 - Guard Huts |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-02063 | PS5-71-NI-9757C |  | M | M | Pump alignment required | CPP AGI | PS5-61-01 - 33kV Switchboard EITS Building |  | On Hold | Smith, John | PS5 - Milestone F | 5
PL-02064 | PS5-13-NER-4278D |  | E | E | Missing earth continuity label | CPP AGI | PS5-99-02 - Area Completion Process Area |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-02065 | PS5-14-NER-5998C |  | T | T | Missing cable label | EPS UNATRAC | PS5-12-02 - Water Treatment |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-02066 | PS5-90-UR-2864D |  | E | E | Outgoing breaker not labeled | CPP AGI | PS5-02-03 - Fuel Gas System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-02067 | PS5-90-IK-2882B |  | T | T | Intercom not functioning | KENT | PS5-02-01 - Diesel Storage Tank |  | On Hold | Jean, Pierre | PS5 - Milestone G | 6
PL-02068 | PS5-97-UR-6086C |  | S | S | Fire extinguisher expired | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | Originated | Jean, Pierre | PS5 - Milestone D | 3
PL-02069 | PS5-65-IK-6599C |  | T | T | Missing cable label | EPS UNATRAC | PS5-05-01 - Telecom Network |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-02070 | PS5-19-OB-6603A |  | E | E | Wrong cable glanding | CPP AGI | PS5-04-04 - 33kV PCS System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-02071 | PS5-64-NER-3940D |  | H | H | Duct leakage at joint | EPS UNATRAC | PS5-10-06 - Vent System |  | On Hold | Wang, Li | PS5 - Milestone I | 8
PL-02072 | PS5-30-NI-5278B |  | H | H | Duct leakage at joint | EPS UNATRAC | PS5-06-02 - DC UPS - EITS Building |  | On Hold | Jean, Pierre | PS5 - Milestone G | 6
PL-02073 | PS5-78-IK-1142D |  | M | M | Bearing temperature high | CPP AGI | PS5-10-05 - Drain System |  | Originated | Kumar, Raj | PS5 - Milestone D | 3
PL-02074 | PS5-47-NI-9820B |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-11-02 - Guard Hut B |  | In Progress | Mohamed, Ali | PS5 - Milestone A | 1
PL-02075 | PS5-54-NER-9326A |  | B | B | Incomplete floor tiling | CPP AGI | PS5-05-03 - CCTV System |  | In Progress | Jean, Pierre | PS5 - Milestone B | 1.1
PL-02076 | PS5-62-IK-5812D |  | T | T | Intercom not functioning | CPP AGI | PS5-06-02 - DC UPS - EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-02077 | PS5-68-IK-2004B |  | M | M | Missing rotation arrow | KENT | PS5-04-01 - DCS System |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-02078 | PS5-84-OB-5754B |  | I | I | Instrument tubing leak | CPP AGI | PS5-62-01 - Cable Tray Main |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-02079 | PS5-40-NER-7739B |  | M | M | Pump alignment required | KENT | PS5-04-04 - 33kV PCS System | 2026-08-23 | Closed | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-02080 | PS5-37-UR-6061B |  | S | S | Emergency shower not tested | KENT | PS5-01-09 - Inergen for EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-02081 | PS5-39-OB-2529C |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-06-02 - DC UPS - EITS Building |  | Originated | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-02082 | PS5-41-NER-6235C |  | H | H | Damper not operational | CPP AGI | PS5-60-04 - Power Generation Package B |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-02083 | PS5-77-IK-3750C |  | H | H | Damper not operational | EPS UNATRAC | PS5-01-05 - Foam System | 2026-12-22 | Closed | Jean, Pierre | PS5 - Milestone C | 2
PL-02084 | PS5-97-IK-1266D |  | S | S | Emergency shower not tested | KENT | PS5-02-03 - Fuel Gas System |  | Originated | Mohamed, Ali | PS5 - Milestone E | 4
PL-02085 | PS5-35-NER-4134A |  | H | H | Missing insulation on duct | CPP AGI | PS5-09-04 - 0.4kV Switchboard | 2026-12-24 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-02086 | PS5-94-UR-9318B |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-08-01 - Compressor Air System | 2026-11-20 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-02087 | PS5-71-OB-6628A |  | H | H | Missing insulation on duct | CPP AGI | PS5-10-01 - Main Pipe Rack |  | In Progress | Jean, Pierre | PS5 - Milestone D | 3
PL-02088 | PS5-55-NI-7913B |  | P | P | Pipe support missing | KENT | PS5-01-03 - Fire Water Pump B | 2026-08-08 | Closed | Mohamed, Ali | PS5 - Milestone F | 5
PL-02089 | PS5-67-IK-1074A |  | E | E | Missing electrical hazard sign | KENT | PS5-82-02 - Structural Steel B |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-02090 | PS5-95-NI-7585C |  | P | P | Missing pipe stress label | EPS UNATRAC | PS5-09-04 - 0.4kV Switchboard |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-02091 | PS5-90-UR-8496C |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-63-01 - Electrical Earthing |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-02092 | PS5-98-IK-9578B |  | S | S | Deluge valve not primed | CPP AGI | PS5-01-07 - Hydrant System |  | On Hold | Smith, John | PS5 - Milestone B | 1.1
PL-02093 | PS5-42-UR-6549A |  | E | E | Outgoing breaker not labeled | KENT | PS5-11-02 - Guard Hut B |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-02094 | PS5-88-IK-4349B |  | S | S | Emergency shower not tested | KENT | PS5-01-03 - Fire Water Pump B |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-02095 | PS5-83-OB-7700B |  | S | S | Deluge valve not primed | CPP AGI | PS5-10-06 - Vent System |  | On Hold | Kumar, Raj | PS5 - Milestone A | 1
PL-02096 | PS5-34-IK-8121A |  | I | I | Missing instrument tag | KENT | PS5-99-01 - Area Completion Building Area |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-02097 | PS5-31-NI-6303D |  | H | H | AHU filter not installed | KENT | PS5-11-01 - Guard Hut A | 2026-08-28 | Closed | Smith, John | PS5 - Milestone H | 7
PL-02098 | PS5-67-OB-5005D |  | H | H | AHU filter not installed | CPP AGI | PS5-60-01 - Power Generation Package A |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-02099 | PS5-11-UR-2301D |  | B | B | Incomplete floor tiling | KENT | PS5-60-04 - Power Generation Package B |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-02100 | PS5-83-NI-7043A |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-11-01 - Guard Hut A |  | On Hold | Smith, John | PS5 - Milestone B | 1.1
PL-02101 | PS5-42-NER-3403A |  | T | T | Missing cable label | EPS UNATRAC | PS5-11-03 - Admin Building |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-02102 | PS5-34-NER-9334D |  | S | S | Missing safety sign | KENT | PS5-07-02 - Chiller System B |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-02103 | PS5-57-NER-2454B |  | I | I | Missing instrument tag | EPS UNATRAC | PS5-07-04 - FCU System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-02104 | PS5-60-NER-8012A |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-07-03 - AHU System |  | On Hold | Jean, Pierre | PS5 - Milestone B | 1.1
PL-02105 | PS5-79-NI-9001D |  | S | S | Eye wash station blocked | KENT | PS5-08-02 - Nitrogen Generator |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-02106 | PS5-43-IK-6802D |  | P | P | Insulation damaged | KENT | PS5-09-03 - Motor Control Center |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-02107 | PS5-54-NI-8787B |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-09-01 - Transformer 33kV/6.6kV |  | On Hold | Jean, Pierre | PS5 - Milestone A | 1
PL-02108 | PS5-45-IK-5883A |  | B | B | Damaged ceiling panel | EPS UNATRAC | PS5-82-07 - Guard Huts |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-02109 | PS5-92-UR-5550C |  | I | I | Pressure gauge reads zero | KENT | PS5-07-01 - Chiller System A |  | In Progress | Mohamed, Ali | PS5 - Milestone A | 1
PL-02110 | PS5-84-NER-6987A |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-12-01 - Cooling Tower | 2026-09-17 | Closed | Jean, Pierre | PS5 - Milestone I | 8
PL-02111 | PS5-60-UR-2289A |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-61-01 - 33kV Switchboard EITS Building |  | On Hold | Jean, Pierre | PS5 - Milestone G | 6
PL-02112 | PS5-12-NI-2667C |  | M | M | Coupling guard loose | CPP AGI | PS5-12-02 - Water Treatment |  | Originated | Kumar, Raj | PS5 - Milestone G | 6
PL-02113 | PS5-61-NER-7964D |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-63-01 - Electrical Earthing |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-02114 | PS5-50-NI-3412C |  | S | S | Fire extinguisher expired | KENT | PS5-99-01 - Area Completion Building Area | 2026-11-22 | Closed | Wang, Li | PS5 - Milestone A | 1
PL-02115 | PS5-80-UR-5525C |  | P | P | Gasket protruding from flange | KENT | PS5-04-02 - SIS System |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-02116 | PS5-03-OB-5558D |  | I | I | Missing instrument tag | EPS UNATRAC | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-02117 | PS5-12-NI-7365B |  | S | S | Eye wash station blocked | CPP AGI | PS5-05-03 - CCTV System |  | Originated | Smith, John | PS5 - Milestone C | 2
PL-02118 | PS5-39-OB-3100A |  | M | M | Coupling guard loose | EPS UNATRAC | PS5-63-01 - Electrical Earthing | 2026-09-09 | Closed | Kumar, Raj | PS5 - Milestone D | 3
PL-02119 | PS5-62-IK-6854D |  | M | M | Vibration level exceeded | KENT | PS5-10-01 - Main Pipe Rack |  | Originated | Wang, Li | PS5 - Milestone B | 1.1
PL-02120 | PS5-27-UR-4335D |  | S | S | Fire extinguisher expired | CPP AGI | PS5-61-01 - 33kV Switchboard EITS Building |  | On Hold | Kumar, Raj | PS5 - Milestone E | 4
PL-02121 | PS5-99-OB-9757D |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-01-02 - Fire Water Pump A |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-02122 | PS5-08-NI-9560B |  | P | P | Gasket protruding from flange | KENT | PS5-05-02 - PA/GA System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-02123 | PS5-98-NI-3913A |  | H | H | Damper not operational | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-02124 | PS5-94-UR-4212D |  | I | I | Transmitter not calibrated | CPP AGI | PS5-10-04 - Process piping B |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-02125 | PS5-60-IK-1852D |  | S | S | Deluge valve not primed | KENT | PS5-06-02 - DC UPS - EITS Building | 2026-12-12 | Closed | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-02126 | PS5-12-OB-7579A |  | H | H | Damper not operational | CPP AGI | PS5-01-09 - Inergen for EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-02127 | PS5-40-OB-1168B |  | P | P | Missing pipe stress label | CPP AGI | PS5-12-01 - Cooling Tower | 2026-08-07 | Closed | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-02128 | PS5-41-NER-7664C |  | E | E | Outgoing breaker not labeled | EPS UNATRAC | PS5-01-07 - Hydrant System |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-02129 | PS5-95-IK-2610A |  | I | I | Control valve actuator fault | KENT | PS5-10-04 - Process piping B |  | On Hold | Kumar, Raj | PS5 - Milestone F | 5
PL-02130 | PS5-94-UR-1375B |  | M | M | Pump alignment required | KENT | PS5-11-02 - Guard Hut B |  | Originated | Wang, Li | PS5 - Milestone C | 2
PL-02131 | PS5-18-UR-7627C |  | S | S | Missing safety sign | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | Originated | Kumar, Raj | PS5 - Milestone B | 1.1
PL-02132 | PS5-22-NER-7249D |  | H | H | Duct leakage at joint | EPS UNATRAC | PS5-04-04 - 33kV PCS System |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-02133 | PS5-45-NI-4774A |  | I | I | Missing instrument tag | CPP AGI | PS5-09-03 - Motor Control Center |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-02134 | PS5-21-IK-1499A |  | P | P | Gasket protruding from flange | CPP AGI | PS5-99-02 - Area Completion Process Area |  | In Progress | Wang, Li | PS5 - Milestone C | 2
PL-02135 | PS5-25-NI-8587D |  | T | T | Missing cable label | EPS UNATRAC | PS5-09-03 - Motor Control Center |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-02136 | PS5-83-UR-3415D |  | P | P | Missing pipe stress label | KENT | PS5-02-03 - Fuel Gas System |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-02137 | PS5-46-OB-8816B |  | B | B | Missing door closer | EPS UNATRAC | PS5-60-01 - Power Generation Package A | 2026-10-01 | Closed | Wang, Li | PS5 - Milestone A | 1
PL-02138 | PS5-34-IK-1577A |  | P | P | Insulation damaged | KENT | PS5-01-06 - Deluge System | 2026-11-13 | Closed | Mohamed, Ali | PS5 - Milestone A | 1
PL-02139 | PS5-90-NI-4893A |  | P | P | Insulation damaged | EPS UNATRAC | PS5-62-01 - Cable Tray Main | 2026-11-12 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-02140 | PS5-12-UR-4170C |  | B | B | Missing fire extinguisher signage | CPP AGI | PS5-61-02 - 6.6kV Switchboard LLHT North |  | On Hold | Mohamed, Ali | PS5 - Milestone C | 2
PL-02141 | PS5-02-IK-9338A |  | T | T | CAT6 cable untidied | KENT | PS5-09-04 - 0.4kV Switchboard |  | On Hold | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-02142 | PS5-92-UR-5253B |  | M | M | Vibration level exceeded | KENT | PS5-10-06 - Vent System |  | In Progress | Wang, Li | PS5 - Milestone D | 3
PL-02143 | PS5-46-UR-7698B |  | B | B | Incomplete paint touch-up | KENT | PS5-12-02 - Water Treatment |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-02144 | PS5-33-NI-9471B |  | P | P | Gasket protruding from flange | KENT | PS5-07-03 - AHU System |  | In Progress | Kumar, Raj | PS5 - Milestone C | 2
PL-02145 | PS5-85-NI-4040D |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-11-01 - Guard Hut A |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-02146 | PS5-06-NER-9355C |  | H | H | AHU filter not installed | CPP AGI | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-02147 | PS5-52-OB-6307D |  | M | M | Missing rotation arrow | KENT | PS5-61-07 - 0.4kV Switchboard EITS Building |  | On Hold | Smith, John | PS5 - Milestone H | 7
PL-02148 | PS5-30-OB-4287A |  | M | M | Bearing temperature high | CPP AGI | PS5-09-04 - 0.4kV Switchboard |  | On Hold | Mohamed, Ali | PS5 - Milestone F | 5
PL-02149 | PS5-59-OB-2425D |  | P | P | Flange bolt torque incomplete | KENT | PS5-11-01 - Guard Hut A |  | On Hold | Wang, Li | PS5 - Milestone C | 2
PL-02150 | PS5-84-UR-9077B |  | M | M | Coupling guard loose | KENT | PS5-60-04 - Power Generation Package B |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-02151 | PS5-56-OB-2828C |  | M | M | Bearing temperature high | KENT | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-02152 | PS5-95-NI-4009A |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-08-01 - Compressor Air System |  | On Hold | Smith, John | PS5 - Milestone A | 1
PL-02153 | PS5-82-IK-3827D |  | I | I | Missing loop diagram | KENT | PS5-01-05 - Foam System |  | In Progress | Jean, Pierre | PS5 - Milestone B | 1.1
PL-02154 | PS5-71-UR-9518D |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-07-02 - Chiller System B |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-02155 | PS5-26-OB-1082A |  | B | B | Damaged ceiling panel | CPP AGI | PS5-02-02 - Diesel Transfer Pump |  | On Hold | Jean, Pierre | PS5 - Milestone I | 8
PL-02156 | PS5-14-OB-6346B |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-08-01 - Compressor Air System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-02157 | PS5-35-NER-3257B |  | P | P | Flange bolt torque incomplete | EPS UNATRAC | PS5-08-02 - Nitrogen Generator |  | On Hold | Wang, Li | PS5 - Milestone C | 2
PL-02158 | PS5-14-NI-3509C |  | P | P | Valve handwheel stiff | CPP AGI | PS5-07-01 - Chiller System A |  | On Hold | Smith, John | PS5 - Milestone G | 6
PL-02159 | PS5-42-IK-5028D |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-04-04 - 33kV PCS System |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-02160 | PS5-54-OB-4564D |  | T | T | CAT6 cable untidied | CPP AGI | PS5-11-02 - Guard Hut B |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-02161 | PS5-03-NER-6626A |  | T | T | CCTV camera not focused | KENT | PS5-09-03 - Motor Control Center |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-02162 | PS5-74-OB-5897A |  | E | E | Wrong cable glanding | CPP AGI | PS5-99-03 - Area Completion Utilities Area |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-02163 | PS5-23-NI-5006C |  | H | H | Thermostat calibration needed | KENT | PS5-11-02 - Guard Hut B |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-02164 | PS5-75-UR-8887A |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-09-03 - Motor Control Center |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-02165 | PS5-73-IK-3307C |  | M | M | Vibration level exceeded | EPS UNATRAC | PS5-07-01 - Chiller System A | 2026-08-11 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-02166 | PS5-45-IK-6897C |  | B | B | Missing door closer | CPP AGI | PS5-99-01 - Area Completion Building Area |  | On Hold | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-02167 | PS5-99-OB-5306A |  | B | B | Missing fire extinguisher signage | CPP AGI | PS5-01-07 - Hydrant System | 2026-11-28 | Closed | Wang, Li | PS5 - Milestone B | 1.1
PL-02168 | PS5-29-OB-5429C |  | M | M | Motor fan guard missing | CPP AGI | PS5-82-07 - Guard Huts | 2026-11-09 | Closed | Wang, Li | PS5 - Milestone C | 2
PL-02169 | PS5-28-NI-6145A |  | T | T | Missing cable label | EPS UNATRAC | PS5-10-04 - Process piping B |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-02170 | PS5-39-NER-6933D |  | P | P | Flange bolt torque incomplete | KENT | PS5-13-01 - Flare System |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-02171 | PS5-31-IK-5947B |  | S | S | Eye wash station blocked | CPP AGI | PS5-60-10 - Power Generation Package D | 2026-09-14 | Closed | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-02172 | PS5-33-NER-9014C |  | T | T | Intercom not functioning | CPP AGI | PS5-03-02 - Fire & Gas Detection |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-02173 | PS5-67-IK-9180D |  | M | M | Coupling guard loose | CPP AGI | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-02174 | PS5-13-UR-2275B |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-01-05 - Foam System |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-02175 | PS5-83-OB-1547B |  | B | B | Missing door closer | KENT | PS5-01-06 - Deluge System |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-02176 | PS5-96-OB-4872C |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-10-05 - Drain System |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-02177 | PS5-31-OB-6833C |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-60-10 - Power Generation Package D |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-02178 | PS5-35-UR-4500A |  | B | B | Damaged ceiling panel | CPP AGI | PS5-99-01 - Area Completion Building Area |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-02179 | PS5-40-NI-4714B |  | I | I | Missing instrument tag | KENT | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-09-16 | Closed | Jean, Pierre | PS5 - Milestone B | 1.1
PL-02180 | PS5-03-IK-1180C |  | P | P | Insulation damaged | KENT | PS5-82-07 - Guard Huts |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-02181 | PS5-66-IK-6614A |  | I | I | Missing instrument tag | CPP AGI | PS5-12-02 - Water Treatment |  | On Hold | Smith, John | PS5 - Milestone G | 6
PL-02182 | PS5-50-NER-2698A |  | I | I | Missing loop diagram | KENT | PS5-82-02 - Structural Steel B |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-02183 | PS5-49-UR-2772C |  | H | H | Thermostat calibration needed | CPP AGI | PS5-06-03 - Lightning Protection |  | Originated | Kumar, Raj | PS5 - Milestone C | 2
PL-02184 | PS5-81-OB-7185D |  | H | H | Thermostat calibration needed | KENT | PS5-11-01 - Guard Hut A |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-02185 | PS5-44-UR-4503B |  | H | H | AHU filter not installed | KENT | PS5-13-01 - Flare System | 2026-12-22 | Closed | Jean, Pierre | PS5 - Milestone F | 5
PL-02186 | PS5-57-NER-9404B |  | B | B | Missing fire extinguisher signage | CPP AGI | PS5-11-02 - Guard Hut B |  | Originated | Kumar, Raj | PS5 - Milestone C | 2
PL-02187 | PS5-32-IK-4980B |  | M | M | Pump alignment required | KENT | PS5-99-02 - Area Completion Process Area | 2026-10-22 | Closed | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-02188 | PS5-51-OB-8679D |  | E | E | Cable tray not properly supported | EPS UNATRAC | PS5-06-01 - AC UPS - EITS Building | 2026-08-17 | Closed | Wang, Li | PS5 - Milestone H | 7
PL-02189 | PS5-19-NI-7114A |  | B | B | Missing door closer | EPS UNATRAC | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-02190 | PS5-67-NER-1808C |  | T | T | Fiber patch panel unorganized | KENT | PS5-01-09 - Inergen for EITS Building | 2026-10-18 | Closed | Kumar, Raj | PS5 - Milestone G | 6
PL-02191 | PS5-33-NI-8035B |  | S | S | Fire extinguisher expired | EPS UNATRAC | PS5-07-03 - AHU System | 2026-10-26 | Closed | Kumar, Raj | PS5 - Milestone A | 1
PL-02192 | PS5-50-OB-1543D |  | E | E | Outgoing breaker not labeled | CPP AGI | PS5-60-10 - Power Generation Package D |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-02193 | PS5-07-UR-2132C |  | T | T | CAT6 cable untidied | KENT | PS5-01-02 - Fire Water Pump A | 2026-12-15 | Closed | Kumar, Raj | PS5 - Milestone D | 3
PL-02194 | PS5-02-NER-5542A |  | E | E | Wrong cable glanding | EPS UNATRAC | PS5-06-02 - DC UPS - EITS Building |  | On Hold | Jean, Pierre | PS5 - Milestone G | 6
PL-02195 | PS5-18-IK-2852B |  | E | E | Outgoing breaker not labeled | CPP AGI | PS5-08-02 - Nitrogen Generator |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-02196 | PS5-30-IK-7030C |  | T | T | CCTV camera not focused | KENT | PS5-12-02 - Water Treatment |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-02197 | PS5-11-NER-6103B |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-02198 | PS5-07-UR-3466D |  | I | I | Missing loop diagram | EPS UNATRAC | PS5-11-03 - Admin Building |  | Originated | Jean, Pierre | PS5 - Milestone B | 1.1
PL-02199 | PS5-29-OB-8434A |  | E | E | Incomplete cable termination | CPP AGI | PS5-11-01 - Guard Hut A |  | In Progress | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-02200 | PS5-74-OB-2207A |  | T | T | Intercom not functioning | CPP AGI | PS5-01-04 - Fire Water Ring Main |  | Originated | Smith, John | PS5 - Milestone D | 3
PL-02201 | PS5-98-NI-6255A |  | B | B | Missing door closer | CPP AGI | PS5-11-01 - Guard Hut A |  | On Hold | Smith, John | PS5 - Milestone B | 1.1
PL-02202 | PS5-56-UR-1153B |  | M | M | Missing rotation arrow | KENT | PS5-03-03 - Flame Detector System |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-02203 | PS5-30-IK-3900B |  | P | P | Insulation damaged | CPP AGI | PS5-63-04 - Electrical Earthing EITS Building |  | On Hold | Wang, Li | PS5 - Milestone D | 3
PL-02204 | PS5-01-OB-9893B |  | T | T | CCTV camera not focused | CPP AGI | PS5-11-01 - Guard Hut A |  | On Hold | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-02205 | PS5-44-OB-3657B |  | M | M | Bearing temperature high | CPP AGI | PS5-62-02 - Cable Tray Secondary |  | On Hold | Kumar, Raj | PS5 - Milestone D | 3
PL-02206 | PS5-62-NI-8744B |  | P | P | Insulation damaged | CPP AGI | PS5-10-03 - Process piping A |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-02207 | PS5-20-IK-7347C |  | M | M | Missing rotation arrow | EPS UNATRAC | PS5-11-03 - Admin Building |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-02208 | PS5-88-NER-9657D |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-09-03 - Motor Control Center |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-02209 | PS5-53-UR-4579C |  | B | B | Missing door closer | KENT | PS5-62-01 - Cable Tray Main |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-02210 | PS5-60-UR-4360C |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-01-05 - Foam System |  | On Hold | Jean, Pierre | PS5 - Milestone H | 7
PL-02211 | PS5-09-UR-1903D |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-07-03 - AHU System |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-02212 | PS5-53-NI-3751B |  | E | E | Missing earth continuity label | CPP AGI | PS5-04-01 - DCS System |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-02213 | PS5-33-OB-7210A |  | I | I | Pressure gauge reads zero | CPP AGI | PS5-08-01 - Compressor Air System |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-02214 | PS5-84-IK-4124B |  | B | B | Cracked wall plaster | EPS UNATRAC | PS5-60-01 - Power Generation Package A |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-02215 | PS5-07-UR-7267D |  | P | P | Valve handwheel stiff | KENT | PS5-04-02 - SIS System |  | Originated | Mohamed, Ali | PS5 - Milestone E | 4
PL-02216 | PS5-75-NI-1160B |  | P | P | Valve handwheel stiff | CPP AGI | PS5-10-01 - Main Pipe Rack |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-02217 | PS5-98-OB-3162B |  | M | M | Pump alignment required | EPS UNATRAC | PS5-04-03 - 33kV ICSS System |  | On Hold | Smith, John | PS5 - Milestone I | 8
PL-02218 | PS5-76-IK-3765A |  | S | S | Fire extinguisher expired | KENT | PS5-63-01 - Electrical Earthing |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-02219 | PS5-85-IK-9846D |  | B | B | Cracked wall plaster | KENT | PS5-02-03 - Fuel Gas System |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-02220 | PS5-40-NI-6935D |  | T | T | Missing cable label | CPP AGI | PS5-05-01 - Telecom Network |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-02221 | PS5-25-IK-9878C |  | E | E | Cable tray not properly supported | CPP AGI | PS5-82-02 - Structural Steel B |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-02222 | PS5-40-OB-2299A |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-01-03 - Fire Water Pump B |  | Originated | Jean, Pierre | PS5 - Milestone F | 5
PL-02223 | PS5-35-UR-7526B |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-02224 | PS5-60-OB-1293D |  | H | H | Missing insulation on duct | CPP AGI | PS5-01-09 - Inergen for EITS Building |  | On Hold | Jean, Pierre | PS5 - Milestone A | 1
PL-02225 | PS5-99-OB-5789C |  | S | S | Emergency shower not tested | KENT | PS5-63-01 - Electrical Earthing | 2026-08-16 | Closed | Jean, Pierre | PS5 - Milestone E | 4
PL-02226 | PS5-28-NER-9763C |  | B | B | Missing fire extinguisher signage | KENT | PS5-13-01 - Flare System |  | On Hold | Smith, John | PS5 - Milestone I | 8
PL-02227 | PS5-63-UR-5389C |  | B | B | Cracked wall plaster | EPS UNATRAC | PS5-02-03 - Fuel Gas System |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-02228 | PS5-56-NER-8919C |  | E | E | Cable tray not properly supported | KENT | PS5-63-04 - Electrical Earthing EITS Building |  | Originated | Kumar, Raj | PS5 - Milestone A | 1
PL-02229 | PS5-20-NI-6780A |  | H | H | Damper not operational | KENT | PS5-11-03 - Admin Building |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-02230 | PS5-44-NI-3646C |  | H | H | Duct leakage at joint | KENT | PS5-63-01 - Electrical Earthing |  | On Hold | Mohamed, Ali | PS5 - Milestone A | 1
PL-02231 | PS5-57-UR-5627C |  | P | P | Flange bolt torque incomplete | KENT | PS5-10-06 - Vent System |  | Originated | Smith, John | PS5 - Milestone B | 1.1
PL-02232 | PS5-39-NI-8663D |  | P | P | Missing pipe stress label | CPP AGI | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-02233 | PS5-89-UR-3913B |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-60-04 - Power Generation Package B |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-02234 | PS5-39-IK-6008A |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-08-01 - Compressor Air System |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-02235 | PS5-44-NER-6036A |  | T | T | CCTV camera not focused | CPP AGI | PS5-99-02 - Area Completion Process Area |  | In Progress | Wang, Li | PS5 - Milestone C | 2
PL-02236 | PS5-03-OB-3053B |  | B | B | Cracked wall plaster | KENT | PS5-05-01 - Telecom Network |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-02237 | PS5-90-OB-8912A |  | B | B | Missing door closer | EPS UNATRAC | PS5-01-04 - Fire Water Ring Main |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-02238 | PS5-77-IK-1541A |  | M | M | Vibration level exceeded | EPS UNATRAC | PS5-05-02 - PA/GA System |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-02239 | PS5-19-NER-4960A |  | B | B | Incomplete paint touch-up | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | On Hold | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-02240 | PS5-54-NI-1208D |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-06-01 - AC UPS - EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-02241 | PS5-21-IK-9826C |  | M | M | Motor fan guard missing | EPS UNATRAC | PS5-04-01 - DCS System | 2026-11-26 | Closed | Mohamed, Ali | PS5 - Milestone D | 3
PL-02242 | PS5-03-IK-3722B |  | S | S | Emergency shower not tested | KENT | PS5-61-02 - 6.6kV Switchboard LLHT North |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-02243 | PS5-19-NI-1260C |  | M | M | Motor fan guard missing | CPP AGI | PS5-82-01 - Structural Steel A |  | In Progress | Wang, Li | PS5 - Milestone D | 3
PL-02244 | PS5-40-OB-3386B |  | B | B | Missing door closer | KENT | PS5-62-01 - Cable Tray Main |  | On Hold | Jean, Pierre | PS5 - Milestone E | 4
PL-02245 | PS5-83-IK-3047B |  | P | P | Insulation damaged | CPP AGI | PS5-10-05 - Drain System |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-02246 | PS5-74-IK-4218B |  | H | H | Damper not operational | EPS UNATRAC | PS5-01-08 - Drencher System |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-02247 | PS5-76-IK-6681A |  | S | S | Missing safety sign | KENT | PS5-01-03 - Fire Water Pump B |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-02248 | PS5-44-IK-4411A |  | I | I | Missing loop diagram | EPS UNATRAC | PS5-11-01 - Guard Hut A | 2026-11-08 | Closed | Smith, John | PS5 - Milestone H | 7
PL-02249 | PS5-21-UR-4960A |  | M | M | Pump alignment required | EPS UNATRAC | PS5-03-01 - ESD System | 2026-09-23 | Closed | Mohamed, Ali | PS5 - Milestone C | 2
PL-02250 | PS5-47-OB-6312C |  | E | E | Incomplete cable termination | CPP AGI | PS5-60-10 - Power Generation Package D | 2026-11-23 | Closed | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-02251 | PS5-80-IK-7083D |  | M | M | Pump alignment required | KENT | PS5-01-07 - Hydrant System | 2026-08-03 | Closed | Jean, Pierre | PS5 - Milestone E | 4
PL-02252 | PS5-10-NI-2493D |  | P | P | Gasket protruding from flange | KENT | PS5-07-04 - FCU System |  | On Hold | Mohamed, Ali | PS5 - Milestone I | 8
PL-02253 | PS5-79-NER-2803B |  | B | B | Missing door closer | CPP AGI | PS5-11-03 - Admin Building |  | In Progress | Mohamed, Ali | PS5 - Milestone D | 3
PL-02254 | PS5-23-NI-3153D |  | P | P | Insulation damaged | CPP AGI | PS5-99-02 - Area Completion Process Area |  | On Hold | Jean, Pierre | PS5 - Milestone B | 1.1
PL-02255 | PS5-86-NI-6974D |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-62-01 - Cable Tray Main |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-02256 | PS5-41-UR-5737A |  | I | I | Instrument tubing leak | CPP AGI | PS5-10-05 - Drain System |  | Originated | Kumar, Raj | PS5 - Milestone C | 2
PL-02257 | PS5-10-OB-4110C |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-99-03 - Area Completion Utilities Area |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-02258 | PS5-37-NER-2573D |  | B | B | Incomplete paint touch-up | CPP AGI | PS5-99-03 - Area Completion Utilities Area |  | In Progress | Jean, Pierre | PS5 - Milestone A | 1
PL-02259 | PS5-05-OB-7401C |  | H | H | AHU filter not installed | CPP AGI | PS5-99-01 - Area Completion Building Area |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-02260 | PS5-46-NER-1749D |  | E | E | Outgoing breaker not labeled | KENT | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-02261 | PS5-68-UR-1197B |  | S | S | Emergency shower not tested | CPP AGI | PS5-11-01 - Guard Hut A |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-02262 | PS5-58-IK-4164B |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-05-01 - Telecom Network |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-02263 | PS5-99-NER-8265D |  | M | M | Vibration level exceeded | CPP AGI | PS5-01-03 - Fire Water Pump B |  | In Progress | Kumar, Raj | PS5 - Milestone H | 7
PL-02264 | PS5-53-NER-2301B |  | P | P | Insulation damaged | CPP AGI | PS5-03-02 - Fire & Gas Detection |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-02265 | PS5-72-OB-9051D |  | B | B | Missing fire extinguisher signage | CPP AGI | PS5-62-01 - Cable Tray Main |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-02266 | PS5-39-IK-2464C |  | M | M | Motor fan guard missing | CPP AGI | PS5-12-01 - Cooling Tower |  | Originated | Wang, Li | PS5 - Milestone G | 6
PL-02267 | PS5-45-NER-6427D |  | T | T | Missing cable label | KENT | PS5-07-01 - Chiller System A |  | Originated | Jean, Pierre | PS5 - Milestone C | 2
PL-02268 | PS5-49-NER-8881A |  | T | T | Missing cable label | CPP AGI | PS5-82-07 - Guard Huts |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-02269 | PS5-19-OB-1943A |  | E | E | Wrong cable glanding | CPP AGI | PS5-13-01 - Flare System |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-02270 | PS5-65-UR-4420C |  | P | P | Insulation damaged | CPP AGI | PS5-10-06 - Vent System |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-02271 | PS5-51-IK-1216A |  | T | T | CAT6 cable untidied | CPP AGI | PS5-08-01 - Compressor Air System |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-02272 | PS5-21-NI-6033C |  | I | I | Missing loop diagram | EPS UNATRAC | PS5-01-08 - Drencher System |  | Originated | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-02273 | PS5-97-NER-3500C |  | T | T | PA speaker not tested | EPS UNATRAC | PS5-09-04 - 0.4kV Switchboard |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-02274 | PS5-20-NER-6362C |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-12-01 - Cooling Tower |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-02275 | PS5-49-NER-8399D |  | H | H | Duct leakage at joint | EPS UNATRAC | PS5-04-01 - DCS System |  | Originated | Jean, Pierre | PS5 - Milestone D | 3
PL-02276 | PS5-67-IK-9304D |  | P | P | Flange bolt torque incomplete | CPP AGI | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Mohamed, Ali | PS5 - Milestone F | 5
PL-02277 | PS5-75-IK-8992C |  | E | E | Wrong cable glanding | CPP AGI | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-02278 | PS5-18-NER-7404C |  | T | T | CCTV camera not focused | EPS UNATRAC | PS5-01-05 - Foam System |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-02279 | PS5-72-IK-5113C |  | M | M | Bearing temperature high | KENT | PS5-10-03 - Process piping A |  | Originated | Jean, Pierre | PS5 - Milestone C | 2
PL-02280 | PS5-69-UR-3498B |  | E | E | Incomplete cable termination | CPP AGI | PS5-08-02 - Nitrogen Generator | 2026-09-03 | Closed | Wang, Li | PS5 - Milestone H | 7
PL-02281 | PS5-01-NER-2397A |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-09-02 - Transformer 6.6kV/0.4kV |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-02282 | PS5-19-OB-8965B |  | E | E | Missing electrical hazard sign | KENT | PS5-03-02 - Fire & Gas Detection |  | In Progress | Wang, Li | PS5 - Milestone C | 2
PL-02283 | PS5-12-IK-2142C |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-10-02 - Utility Pipe Rack |  | On Hold | Kumar, Raj | PS5 - Milestone B | 1.1
PL-02284 | PS5-30-IK-6158C |  | E | E | Incomplete cable termination | KENT | PS5-10-04 - Process piping B |  | On Hold | Kumar, Raj | PS5 - Milestone A | 1
PL-02285 | PS5-96-OB-1782D |  | B | B | Missing door closer | KENT | PS5-10-04 - Process piping B |  | In Progress | Smith, John | PS5 - Milestone E | 4
PL-02286 | PS5-14-OB-6794D |  | E | E | Incomplete cable termination | CPP AGI | PS5-10-02 - Utility Pipe Rack |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-02287 | PS5-61-NI-5403D |  | P | P | Insulation damaged | KENT | PS5-82-02 - Structural Steel B |  | On Hold | Wang, Li | PS5 - Milestone C | 2
PL-02288 | PS5-32-NI-2745C |  | M | M | Bearing temperature high | CPP AGI | PS5-01-04 - Fire Water Ring Main | 2026-08-20 | Closed | Wang, Li | PS5 - Milestone D | 3
PL-02289 | PS5-50-UR-4672A |  | M | M | Bearing temperature high | CPP AGI | PS5-02-03 - Fuel Gas System |  | On Hold | Mohamed, Ali | PS5 - Milestone C | 2
PL-02290 | PS5-88-UR-2330A |  | I | I | Control valve actuator fault | CPP AGI | PS5-01-09 - Inergen for EITS Building |  | Originated | Kumar, Raj | PS5 - Milestone I | 8
PL-02291 | PS5-51-UR-7365D |  | S | S | Fire extinguisher expired | CPP AGI | PS5-11-01 - Guard Hut A |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-02292 | PS5-72-NER-9500C |  | M | M | Vibration level exceeded | EPS UNATRAC | PS5-62-02 - Cable Tray Secondary |  | On Hold | Mohamed, Ali | PS5 - Milestone E | 4
PL-02293 | PS5-04-UR-8471D |  | E | E | Cable tray not properly supported | CPP AGI | PS5-82-01 - Structural Steel A |  | On Hold | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-02294 | PS5-26-IK-1605B |  | T | T | Fiber patch panel unorganized | KENT | PS5-99-01 - Area Completion Building Area |  | In Progress | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-02295 | PS5-36-NI-1387A |  | E | E | Cable tray not properly supported | CPP AGI | PS5-62-02 - Cable Tray Secondary |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-02296 | PS5-55-NER-5576A |  | M | M | Missing rotation arrow | KENT | PS5-10-02 - Utility Pipe Rack |  | On Hold | Wang, Li | PS5 - Milestone B | 1.1
PL-02297 | PS5-62-UR-4458C |  | M | M | Coupling guard loose | CPP AGI | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-02298 | PS5-45-IK-7322C |  | B | B | Incomplete paint touch-up | EPS UNATRAC | PS5-01-08 - Drencher System |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-02299 | PS5-35-NI-9115C |  | T | T | Missing cable label | CPP AGI | PS5-63-04 - Electrical Earthing EITS Building | 2026-11-23 | Closed | Jean, Pierre | PS5 - Milestone D | 3
PL-02300 | PS5-62-NER-8425C |  | P | P | Valve handwheel stiff | CPP AGI | PS5-60-01 - Power Generation Package A |  | On Hold | Wang, Li | PS5 - Milestone F | 5
PL-02301 | PS5-50-NER-1546B |  | E | E | Wrong cable glanding | KENT | PS5-08-01 - Compressor Air System |  | In Progress | Mohamed, Ali | PS5 - Milestone E | 4
PL-02302 | PS5-92-UR-7366A |  | E | E | Cable tray not properly supported | CPP AGI | PS5-82-07 - Guard Huts |  | On Hold | Smith, John | PS5 - Milestone D | 3
PL-02303 | PS5-69-NI-8337A |  | I | I | Instrument tubing leak | KENT | PS5-13-01 - Flare System |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-02304 | PS5-33-IK-8789C |  | P | P | Flange bolt torque incomplete | CPP AGI | PS5-12-02 - Water Treatment |  | Originated | Wang, Li | PS5 - Milestone H | 7
PL-02305 | PS5-08-OB-1390C |  | S | S | Emergency shower not tested | KENT | PS5-60-07 - Power Generation Package C |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-02306 | PS5-08-UR-6352B |  | B | B | Missing door closer | KENT | PS5-01-01 - Fire Water Jockey Pump A/B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-02307 | PS5-01-UR-9388A |  | T | T | Missing cable label | CPP AGI | PS5-06-02 - DC UPS - EITS Building | 2026-09-03 | Closed | Kumar, Raj | PS5 - Milestone I | 8
PL-02308 | PS5-87-IK-2205A |  | M | M | Motor fan guard missing | CPP AGI | PS5-60-01 - Power Generation Package A |  | In Progress | Mohamed, Ali | PS5 - Milestone A | 1
PL-02309 | PS5-41-NER-2150C |  | E | E | Missing earth continuity label | EPS UNATRAC | PS5-99-02 - Area Completion Process Area |  | On Hold | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-02310 | PS5-37-UR-8875B |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-04-02 - SIS System |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-02311 | PS5-65-IK-6191D |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-01-04 - Fire Water Ring Main | 2026-12-08 | Closed | Kumar, Raj | PS5 - Milestone C | 2
PL-02312 | PS5-29-NI-2109C |  | E | E | Outgoing breaker not labeled | CPP AGI | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone H | 7
PL-02313 | PS5-59-UR-3864B |  | H | H | FCU drain pipe not connected | EPS UNATRAC | PS5-11-02 - Guard Hut B |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-02314 | PS5-79-NER-5214B |  | T | T | Intercom not functioning | CPP AGI | PS5-09-02 - Transformer 6.6kV/0.4kV |  | On Hold | Kumar, Raj | PS5 - Milestone F | 5
PL-02315 | PS5-10-OB-4646A |  | M | M | Bearing temperature high | CPP AGI | PS5-08-02 - Nitrogen Generator |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-02316 | PS5-41-OB-1914D |  | B | B | Missing door closer | EPS UNATRAC | PS5-01-04 - Fire Water Ring Main |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-02317 | PS5-13-IK-1259C |  | H | H | Missing insulation on duct | KENT | PS5-82-07 - Guard Huts |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-02318 | PS5-25-OB-9334B |  | I | I | Control valve actuator fault | CPP AGI | PS5-82-01 - Structural Steel A | 2026-08-07 | Closed | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-02319 | PS5-93-NER-4204C |  | H | H | Missing insulation on duct | CPP AGI | PS5-10-05 - Drain System |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-02320 | PS5-35-UR-2204A |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-11-03 - Admin Building |  | In Progress | Jean, Pierre | PS5 - Milestone B | 1.1
PL-02321 | PS5-14-UR-3626B |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-63-04 - Electrical Earthing EITS Building | 2026-11-28 | Closed | Mohamed, Ali | PS5 - Milestone A | 1
PL-02322 | PS5-51-IK-1525C |  | H | H | FCU drain pipe not connected | EPS UNATRAC | PS5-07-01 - Chiller System A |  | Originated | Wang, Li | PS5 - Milestone D | 3
PL-02323 | PS5-22-UR-1644D |  | H | H | Thermostat calibration needed | CPP AGI | PS5-05-02 - PA/GA System |  | On Hold | Wang, Li | PS5 - Milestone E | 4
PL-02324 | PS5-98-OB-9925B |  | I | I | Missing loop diagram | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-02325 | PS5-38-IK-9925B |  | T | T | Intercom not functioning | KENT | PS5-04-02 - SIS System |  | Originated | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-02326 | PS5-51-OB-2084A |  | S | S | Deluge valve not primed | KENT | PS5-05-01 - Telecom Network |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-02327 | PS5-05-NI-2881C |  | P | P | Gasket protruding from flange | CPP AGI | PS5-12-01 - Cooling Tower |  | Originated | Kumar, Raj | PS5 - Milestone F | 5
PL-02328 | PS5-02-IK-7854A |  | M | M | Bearing temperature high | CPP AGI | PS5-04-01 - DCS System |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-02329 | PS5-86-OB-3332D |  | H | H | Thermostat calibration needed | CPP AGI | PS5-08-01 - Compressor Air System |  | Originated | Mohamed, Ali | PS5 - Milestone F | 5
PL-02330 | PS5-19-NI-1493D |  | I | I | Transmitter not calibrated | KENT | PS5-63-04 - Electrical Earthing EITS Building |  | On Hold | Smith, John | PS5 - Milestone F | 5
PL-02331 | PS5-61-OB-1151A |  | S | S | Fire extinguisher expired | KENT | PS5-07-03 - AHU System |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-02332 | PS5-51-OB-8607A |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-09-04 - 0.4kV Switchboard |  | Originated | Kumar, Raj | PS5 - Milestone E | 4
PL-02333 | PS5-13-NER-7671B |  | M | M | Vibration level exceeded | KENT | PS5-10-02 - Utility Pipe Rack |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-02334 | PS5-53-NI-7810A |  | H | H | Thermostat calibration needed | KENT | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-08-21 | Closed | Jean, Pierre | PS5 - Milestone C | 2
PL-02335 | PS5-90-IK-3181C |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-11-01 - Guard Hut A |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-02336 | PS5-95-UR-6014B |  | P | P | Insulation damaged | EPS UNATRAC | PS5-99-03 - Area Completion Utilities Area | 2026-09-12 | Closed | Jean, Pierre | PS5 - Milestone I | 8
PL-02337 | PS5-21-OB-6232C |  | P | P | Insulation damaged | EPS UNATRAC | PS5-06-03 - Lightning Protection |  | Originated | Jean, Pierre | PS5 - Milestone F | 5
PL-02338 | PS5-11-NER-5527C |  | T | T | Fiber patch panel unorganized | CPP AGI | PS5-63-01 - Electrical Earthing |  | In Progress | Jean, Pierre | PS5 - Milestone I | 8
PL-02339 | PS5-61-UR-9905B |  | B | B | Damaged ceiling panel | KENT | PS5-09-01 - Transformer 33kV/6.6kV |  | On Hold | Jean, Pierre | PS5 - Milestone F | 5
PL-02340 | PS5-85-OB-3966A |  | H | H | Thermostat calibration needed | EPS UNATRAC | PS5-07-03 - AHU System |  | On Hold | Mohamed, Ali | PS5 - Milestone F | 5
PL-02341 | PS5-58-NI-9982A |  | S | S | Deluge valve not primed | CPP AGI | PS5-62-02 - Cable Tray Secondary |  | In Progress | Mohamed, Ali | PS5 - Milestone F | 5
PL-02342 | PS5-99-UR-2437D |  | P | P | Flange bolt torque incomplete | EPS UNATRAC | PS5-82-01 - Structural Steel A |  | On Hold | Kumar, Raj | PS5 - Milestone G | 6
PL-02343 | PS5-24-UR-4360A |  | P | P | Gasket protruding from flange | CPP AGI | PS5-82-01 - Structural Steel A |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-02344 | PS5-88-UR-3128C |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-01-08 - Drencher System |  | On Hold | Kumar, Raj | PS5 - Milestone A | 1
PL-02345 | PS5-62-NI-3074B |  | I | I | Missing instrument tag | KENT | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-12-20 | Closed | Mohamed, Ali | PS5 - Milestone H | 7
PL-02346 | PS5-94-NI-9390B |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-01-07 - Hydrant System | 2026-09-17 | Closed | Thao-my, Alexandre | PS5 - Milestone D | 3
PL-02347 | PS5-02-UR-8704A |  | M | M | Vibration level exceeded | KENT | PS5-08-01 - Compressor Air System |  | In Progress | Mohamed, Ali | PS5 - Milestone H | 7
PL-02348 | PS5-36-UR-1708B |  | M | M | Vibration level exceeded | EPS UNATRAC | PS5-09-04 - 0.4kV Switchboard |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-02349 | PS5-39-NER-6810D |  | S | S | Fire extinguisher expired | CPP AGI | PS5-04-02 - SIS System |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-02350 | PS5-60-NI-8031B |  | S | S | Eye wash station blocked | CPP AGI | PS5-01-04 - Fire Water Ring Main | 2026-12-24 | Closed | Smith, John | PS5 - Milestone E | 4
PL-02351 | PS5-40-IK-6023C |  | I | I | Pressure gauge reads zero | KENT | PS5-99-02 - Area Completion Process Area |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-02352 | PS5-60-NER-2538D |  | I | I | Missing instrument tag | EPS UNATRAC | PS5-01-08 - Drencher System |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-02353 | PS5-28-NER-3567A |  | I | I | Missing loop diagram | KENT | PS5-10-05 - Drain System |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-02354 | PS5-88-UR-4068A |  | P | P | Pipe support missing | EPS UNATRAC | PS5-10-01 - Main Pipe Rack | 2026-09-18 | Closed | Wang, Li | PS5 - Milestone A | 1
PL-02355 | PS5-58-IK-5300C |  | S | S | Fire extinguisher expired | KENT | PS5-10-05 - Drain System | 2026-08-10 | Closed | Jean, Pierre | PS5 - Milestone D | 3
PL-02356 | PS5-75-IK-6848B |  | H | H | Missing insulation on duct | CPP AGI | PS5-04-01 - DCS System | 2026-12-11 | Closed | Wang, Li | PS5 - Milestone D | 3
PL-02357 | PS5-10-IK-7850D |  | T | T | CAT6 cable untidied | EPS UNATRAC | PS5-01-06 - Deluge System |  | Originated | Mohamed, Ali | PS5 - Milestone C | 2
PL-02358 | PS5-19-NER-1233D |  | M | M | Coupling guard loose | KENT | PS5-82-02 - Structural Steel B | 2026-12-03 | Closed | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-02359 | PS5-84-IK-1432B |  | T | T | CAT6 cable untidied | KENT | PS5-60-10 - Power Generation Package D |  | On Hold | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-02360 | PS5-44-NI-6455A |  | S | S | Missing safety sign | EPS UNATRAC | PS5-12-01 - Cooling Tower |  | In Progress | Jean, Pierre | PS5 - Milestone D | 3
PL-02361 | PS5-87-OB-4545A |  | P | P | Pipe support missing | KENT | PS5-61-07 - 0.4kV Switchboard EITS Building |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-02362 | PS5-49-IK-7948D |  | S | S | Fire alarm panel fault | KENT | PS5-06-02 - DC UPS - EITS Building | 2026-09-13 | Closed | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-02363 | PS5-03-NER-2706B |  | H | H | FCU drain pipe not connected | KENT | PS5-06-01 - AC UPS - EITS Building |  | Originated | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-02364 | PS5-23-UR-1914A |  | S | S | Emergency shower not tested | CPP AGI | PS5-82-01 - Structural Steel A |  | On Hold | Mohamed, Ali | PS5 - Milestone A | 1
PL-02365 | PS5-24-UR-4172C |  | M | M | Motor fan guard missing | EPS UNATRAC | PS5-01-05 - Foam System |  | In Progress | Jean, Pierre | PS5 - Milestone H | 7
PL-02366 | PS5-29-UR-8870A |  | E | E | Missing earth continuity label | EPS UNATRAC | PS5-05-01 - Telecom Network |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-02367 | PS5-24-NER-1887B |  | B | B | Cracked wall plaster | EPS UNATRAC | PS5-01-08 - Drencher System | 2026-11-24 | Closed | Kumar, Raj | PS5 - Milestone I | 8
PL-02368 | PS5-19-UR-7557A |  | P | P | Pipe support missing | KENT | PS5-99-01 - Area Completion Building Area |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-02369 | PS5-91-NER-6991C |  | B | B | Damaged ceiling panel | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump |  | In Progress | Jean, Pierre | PS5 - Milestone C | 2
PL-02370 | PS5-83-NER-5346B |  | M | M | Motor fan guard missing | CPP AGI | PS5-99-01 - Area Completion Building Area |  | Originated | Wang, Li | PS5 - Milestone G | 6
PL-02371 | PS5-89-OB-8688B |  | M | M | Vibration level exceeded | EPS UNATRAC | PS5-11-02 - Guard Hut B |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-02372 | PS5-60-NER-1866D |  | B | B | Missing fire extinguisher signage | EPS UNATRAC | PS5-62-02 - Cable Tray Secondary |  | On Hold | Jean, Pierre | PS5 - Milestone A | 1
PL-02373 | PS5-18-NI-3402D |  | T | T | Intercom not functioning | KENT | PS5-04-04 - 33kV PCS System |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-02374 | PS5-67-NER-1545B |  | E | E | Outgoing breaker not labeled | KENT | PS5-60-01 - Power Generation Package A | 2026-11-03 | Closed | Wang, Li | PS5 - Milestone E | 4
PL-02375 | PS5-74-OB-2050A |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-01-02 - Fire Water Pump A |  | Originated | Kumar, Raj | PS5 - Milestone D | 3
PL-02376 | PS5-47-IK-7112C |  | I | I | Instrument tubing leak | KENT | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-02377 | PS5-34-NI-1323C |  | S | S | Fire extinguisher expired | KENT | PS5-01-03 - Fire Water Pump B |  | In Progress | Wang, Li | PS5 - Milestone B | 1.1
PL-02378 | PS5-47-IK-1645B |  | E | E | Outgoing breaker not labeled | CPP AGI | PS5-82-02 - Structural Steel B |  | In Progress | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-02379 | PS5-75-OB-8252C |  | B | B | Missing door closer | KENT | PS5-82-02 - Structural Steel B |  | Originated | Wang, Li | PS5 - Milestone E | 4
PL-02380 | PS5-05-NI-1008A |  | H | H | AHU filter not installed | CPP AGI | PS5-10-02 - Utility Pipe Rack |  | Originated | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-02381 | PS5-48-UR-3434B |  | E | E | Wrong cable glanding | CPP AGI | PS5-99-02 - Area Completion Process Area |  | In Progress | Kumar, Raj | PS5 - Milestone I | 8
PL-02382 | PS5-87-IK-8711B |  | T | T | CCTV camera not focused | CPP AGI | PS5-05-01 - Telecom Network |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-02383 | PS5-55-OB-8394C |  | T | T | CAT6 cable untidied | KENT | PS5-09-03 - Motor Control Center |  | In Progress | Jean, Pierre | PS5 - Milestone H | 7
PL-02384 | PS5-08-OB-2366B |  | P | P | Flange bolt torque incomplete | CPP AGI | PS5-04-04 - 33kV PCS System |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-02385 | PS5-59-NI-4764D |  | I | I | Pressure gauge reads zero | CPP AGI | PS5-62-02 - Cable Tray Secondary |  | Originated | Smith, John | PS5 - Milestone E | 4
PL-02386 | PS5-59-OB-1760D |  | T | T | CCTV camera not focused | CPP AGI | PS5-60-01 - Power Generation Package A | 2026-10-16 | Closed | Mohamed, Ali | PS5 - Milestone I | 8
PL-02387 | PS5-22-OB-1739C |  | S | S | Missing safety sign | EPS UNATRAC | PS5-02-02 - Diesel Transfer Pump | 2026-10-17 | Closed | Mohamed, Ali | PS5 - Milestone E | 4
PL-02388 | PS5-48-IK-6199A |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-11-01 - Guard Hut A |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-02389 | PS5-89-UR-9752B |  | E | E | Outgoing breaker not labeled | EPS UNATRAC | PS5-03-01 - ESD System |  | Originated | Smith, John | PS5 - Milestone B | 1.1
PL-02390 | PS5-16-NI-4434A |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-07-03 - AHU System |  | Originated | Smith, John | PS5 - Milestone C | 2
PL-02391 | PS5-54-OB-3537B |  | I | I | Pressure gauge reads zero | KENT | PS5-09-04 - 0.4kV Switchboard |  | Originated | Wang, Li | PS5 - Milestone I | 8
PL-02392 | PS5-74-NI-8934D |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-01-02 - Fire Water Pump A |  | On Hold | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-02393 | PS5-36-NER-5997B |  | H | H | Missing insulation on duct | KENT | PS5-01-09 - Inergen for EITS Building |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-02394 | PS5-11-OB-8041A |  | I | I | Missing loop diagram | CPP AGI | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Smith, John | PS5 - Milestone B | 1.1
PL-02395 | PS5-55-NER-8010C |  | P | P | Missing pipe stress label | CPP AGI | PS5-01-07 - Hydrant System |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-02396 | PS5-58-OB-2134A |  | T | T | Fiber patch panel unorganized | EPS UNATRAC | PS5-82-01 - Structural Steel A |  | In Progress | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-02397 | PS5-56-IK-8433B |  | H | H | Duct leakage at joint | KENT | PS5-07-02 - Chiller System B |  | On Hold | Wang, Li | PS5 - Milestone G | 6
PL-02398 | PS5-68-OB-5826B |  | I | I | Missing loop diagram | EPS UNATRAC | PS5-09-01 - Transformer 33kV/6.6kV |  | On Hold | Smith, John | PS5 - Milestone G | 6
PL-02399 | PS5-52-IK-3167C |  | P | P | Pipe support missing | KENT | PS5-61-01 - 33kV Switchboard EITS Building |  | On Hold | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-02400 | PS5-30-UR-7205A |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-01-04 - Fire Water Ring Main |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-02401 | PS5-53-IK-5657B |  | T | T | CAT6 cable untidied | KENT | PS5-10-03 - Process piping A | 2026-11-03 | Closed | Smith, John | PS5 - Milestone D | 3
PL-02402 | PS5-72-NER-9840D |  | I | I | Transmitter not calibrated | CPP AGI | PS5-01-09 - Inergen for EITS Building | 2026-11-18 | Closed | Smith, John | PS5 - Milestone B | 1.1
PL-02403 | PS5-43-NI-7575B |  | S | S | Eye wash station blocked | KENT | PS5-02-01 - Diesel Storage Tank |  | In Progress | Smith, John | PS5 - Milestone F | 5
PL-02404 | PS5-88-NI-3883B |  | P | P | Flange bolt torque incomplete | KENT | PS5-10-02 - Utility Pipe Rack |  | In Progress | Jean, Pierre | PS5 - Milestone B | 1.1
PL-02405 | PS5-50-NI-9617D |  | S | S | Emergency shower not tested | EPS UNATRAC | PS5-62-01 - Cable Tray Main |  | On Hold | Kumar, Raj | PS5 - Milestone A | 1
PL-02406 | PS5-11-IK-3745D |  | H | H | FCU drain pipe not connected | CPP AGI | PS5-10-01 - Main Pipe Rack |  | On Hold | Kumar, Raj | PS5 - Milestone H | 7
PL-02407 | PS5-38-IK-8250D |  | T | T | Intercom not functioning | EPS UNATRAC | PS5-02-03 - Fuel Gas System | 2026-11-17 | Closed | Smith, John | PS5 - Milestone C | 2
PL-02408 | PS5-68-NER-7204D |  | S | S | Deluge valve not primed | CPP AGI | PS5-04-02 - SIS System |  | On Hold | Jean, Pierre | PS5 - Milestone G | 6
PL-02409 | PS5-35-NER-2310D |  | H | H | Duct leakage at joint | CPP AGI | PS5-01-01 - Fire Water Jockey Pump A/B |  | On Hold | Smith, John | PS5 - Milestone I | 8
PL-02410 | PS5-55-IK-4160D |  | H | H | Damper not operational | EPS UNATRAC | PS5-07-04 - FCU System | 2026-11-08 | Closed | Smith, John | PS5 - Milestone D | 3
PL-02411 | PS5-08-IK-8574A |  | T | T | Intercom not functioning | CPP AGI | PS5-01-05 - Foam System | 2026-12-16 | Closed | Wang, Li | PS5 - Milestone A | 1
PL-02412 | PS5-21-OB-1684D |  | H | H | Damper not operational | KENT | PS5-05-02 - PA/GA System |  | In Progress | Mohamed, Ali | PS5 - Milestone I | 8
PL-02413 | PS5-59-UR-5803A |  | P | P | Insulation damaged | EPS UNATRAC | PS5-11-02 - Guard Hut B |  | On Hold | Smith, John | PS5 - Milestone E | 4
PL-02414 | PS5-59-IK-9644B |  | E | E | Wrong cable glanding | KENT | PS5-12-02 - Water Treatment |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-02415 | PS5-64-IK-4395A |  | B | B | Incomplete floor tiling | EPS UNATRAC | PS5-10-03 - Process piping A |  | In Progress | Kumar, Raj | PS5 - Milestone E | 4
PL-02416 | PS5-89-NER-1475A |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-05-01 - Telecom Network |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-02417 | PS5-05-NER-7759A |  | I | I | Control valve actuator fault | EPS UNATRAC | PS5-09-02 - Transformer 6.6kV/0.4kV |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-02418 | PS5-74-NI-1474C |  | P | P | Pipe support missing | CPP AGI | PS5-07-01 - Chiller System A |  | Originated | Wang, Li | PS5 - Milestone A | 1
PL-02419 | PS5-42-NI-2240A |  | T | T | Intercom not functioning | CPP AGI | PS5-02-03 - Fuel Gas System | 2026-12-20 | Closed | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-02420 | PS5-03-IK-8370B |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-12-02 - Water Treatment | 2026-10-13 | Closed | Smith, John | PS5 - Milestone D | 3
PL-02421 | PS5-60-NI-5846B |  | E | E | Incomplete cable termination | EPS UNATRAC | PS5-10-05 - Drain System |  | In Progress | Mohamed, Ali | PS5 - Milestone G | 6
PL-02422 | PS5-89-NER-3195C |  | P | P | Gasket protruding from flange | CPP AGI | PS5-13-01 - Flare System |  | Originated | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-02423 | PS5-80-OB-3628C |  | T | T | Missing cable label | CPP AGI | PS5-03-03 - Flame Detector System |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-02424 | PS5-51-OB-2577D |  | P | P | Missing pipe stress label | CPP AGI | PS5-04-03 - 33kV ICSS System |  | On Hold | Wang, Li | PS5 - Milestone A | 1
PL-02425 | PS5-38-OB-3440A |  | H | H | Damper not operational | KENT | PS5-02-03 - Fuel Gas System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-02426 | PS5-66-NI-3318B |  | H | H | Duct leakage at joint | CPP AGI | PS5-82-02 - Structural Steel B |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-02427 | PS5-37-OB-1157C |  | P | P | Pipe support missing | KENT | PS5-08-01 - Compressor Air System |  | In Progress | Kumar, Raj | PS5 - Milestone C | 2
PL-02428 | PS5-12-NI-1635B |  | I | I | Missing instrument tag | KENT | PS5-62-01 - Cable Tray Main | 2026-09-26 | Closed | Jean, Pierre | PS5 - Milestone D | 3
PL-02429 | PS5-62-NI-5143A |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-82-07 - Guard Huts |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-02430 | PS5-15-IK-5957C |  | H | H | Thermostat calibration needed | CPP AGI | PS5-10-06 - Vent System |  | In Progress | Jean, Pierre | PS5 - Milestone E | 4
PL-02431 | PS5-80-NER-3881D |  | M | M | Bearing temperature high | KENT | PS5-99-03 - Area Completion Utilities Area |  | In Progress | Kumar, Raj | PS5 - Milestone F | 5
PL-02432 | PS5-99-UR-3469A |  | S | S | Emergency shower not tested | CPP AGI | PS5-02-03 - Fuel Gas System |  | In Progress | Kumar, Raj | PS5 - Milestone C | 2
PL-02433 | PS5-76-OB-1563A |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-07-01 - Chiller System A |  | Originated | Kumar, Raj | PS5 - Milestone I | 8
PL-02434 | PS5-25-UR-2764C |  | B | B | Cracked wall plaster | CPP AGI | PS5-01-09 - Inergen for EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone G | 6
PL-02435 | PS5-30-NER-7532B |  | H | H | Missing insulation on duct | CPP AGI | PS5-01-09 - Inergen for EITS Building | 2026-08-15 | Closed | Wang, Li | PS5 - Milestone D | 3
PL-02436 | PS5-12-NI-2886D |  | E | E | Incomplete cable termination | KENT | PS5-82-07 - Guard Huts |  | Originated | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-02437 | PS5-76-OB-8042A |  | B | B | Missing door closer | EPS UNATRAC | PS5-10-06 - Vent System | 2026-09-09 | Closed | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-02438 | PS5-20-OB-8524A |  | M | M | Pump alignment required | KENT | PS5-82-02 - Structural Steel B |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-02439 | PS5-65-UR-2520C |  | I | I | Missing instrument tag | KENT | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | Originated | Wang, Li | PS5 - Milestone G | 6
PL-02440 | PS5-79-NER-4371A |  | B | B | Missing door closer | KENT | PS5-10-05 - Drain System |  | On Hold | Smith, John | PS5 - Milestone H | 7
PL-02441 | PS5-51-NI-5023D |  | B | B | Incomplete floor tiling | EPS UNATRAC | PS5-01-02 - Fire Water Pump A |  | In Progress | Jean, Pierre | PS5 - Milestone F | 5
PL-02442 | PS5-67-UR-1432C |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-82-01 - Structural Steel A |  | Originated | Mohamed, Ali | PS5 - Milestone A | 1
PL-02443 | PS5-63-OB-5674D |  | B | B | Cracked wall plaster | KENT | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-11-11 | Closed | Wang, Li | PS5 - Milestone D | 3
PL-02444 | PS5-24-IK-9595D |  | I | I | Instrument tubing leak | EPS UNATRAC | PS5-05-02 - PA/GA System |  | In Progress | Kumar, Raj | PS5 - Milestone D | 3
PL-02445 | PS5-28-NI-2873D |  | H | H | AHU filter not installed | CPP AGI | PS5-13-01 - Flare System |  | On Hold | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-02446 | PS5-72-IK-9975C |  | I | I | Missing loop diagram | KENT | PS5-10-04 - Process piping B |  | On Hold | Smith, John | PS5 - Milestone I | 8
PL-02447 | PS5-53-OB-8192B |  | I | I | Instrument tubing leak | CPP AGI | PS5-04-03 - 33kV ICSS System |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-02448 | PS5-51-IK-9046D |  | S | S | Emergency shower not tested | CPP AGI | PS5-09-04 - 0.4kV Switchboard |  | In Progress | Thao-my, Alexandre | PS5 - Milestone I | 8
PL-02449 | PS5-62-NER-1611A |  | S | S | Eye wash station blocked | EPS UNATRAC | PS5-07-04 - FCU System |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-02450 | PS5-70-UR-6105C |  | M | M | Motor fan guard missing | CPP AGI | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-10-15 | Closed | Smith, John | PS5 - Milestone I | 8
PL-02451 | PS5-04-IK-7144A |  | E | E | Missing electrical hazard sign | EPS UNATRAC | PS5-02-01 - Diesel Storage Tank |  | In Progress | Kumar, Raj | PS5 - Milestone G | 6
PL-02452 | PS5-35-NER-6744D |  | H | H | Damper not operational | KENT | PS5-60-10 - Power Generation Package D |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-02453 | PS5-64-NER-2466D |  | S | S | Fire extinguisher expired | CPP AGI | PS5-99-03 - Area Completion Utilities Area |  | In Progress | Jean, Pierre | PS5 - Milestone D | 3
PL-02454 | PS5-04-UR-4782D |  | M | M | Pump alignment required | EPS UNATRAC | PS5-09-03 - Motor Control Center | 2026-11-26 | Closed | Thao-my, Alexandre | PS5 - Milestone F | 5
PL-02455 | PS5-76-NER-5375C |  | S | S | Deluge valve not primed | EPS UNATRAC | PS5-04-02 - SIS System |  | In Progress | Thao-my, Alexandre | PS5 - Milestone C | 2
PL-02456 | PS5-08-NI-6322D |  | T | T | Intercom not functioning | KENT | PS5-07-01 - Chiller System A |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-02457 | PS5-05-NI-2859A |  | B | B | Missing door closer | EPS UNATRAC | PS5-06-02 - DC UPS - EITS Building |  | Originated | Wang, Li | PS5 - Milestone E | 4
PL-02458 | PS5-05-UR-7880A |  | M | M | Bearing temperature high | EPS UNATRAC | PS5-01-03 - Fire Water Pump B | 2026-11-27 | Closed | Kumar, Raj | PS5 - Milestone D | 3
PL-02459 | PS5-37-NI-7343B |  | P | P | Valve handwheel stiff | EPS UNATRAC | PS5-11-01 - Guard Hut A |  | In Progress | Mohamed, Ali | PS5 - Milestone B | 1.1
PL-02460 | PS5-61-OB-3761C |  | H | H | Duct leakage at joint | CPP AGI | PS5-02-02 - Diesel Transfer Pump |  | On Hold | Thao-my, Alexandre | PS5 - Milestone H | 7
PL-02461 | PS5-30-OB-2925D |  | S | S | Deluge valve not primed | CPP AGI | PS5-01-09 - Inergen for EITS Building | 2026-10-19 | Closed | Jean, Pierre | PS5 - Milestone H | 7
PL-02462 | PS5-02-NER-2694A |  | I | I | Missing instrument tag | EPS UNATRAC | PS5-05-01 - Telecom Network | 2026-08-03 | Closed | Kumar, Raj | PS5 - Milestone G | 6
PL-02463 | PS5-06-OB-5943C |  | M | M | Pump alignment required | CPP AGI | PS5-11-02 - Guard Hut B |  | In Progress | Wang, Li | PS5 - Milestone H | 7
PL-02464 | PS5-26-IK-8919A |  | M | M | Vibration level exceeded | KENT | PS5-05-03 - CCTV System |  | In Progress | Smith, John | PS5 - Milestone D | 3
PL-02465 | PS5-18-NER-6336B |  | P | P | Gasket protruding from flange | CPP AGI | PS5-60-10 - Power Generation Package D |  | In Progress | Smith, John | PS5 - Milestone H | 7
PL-02466 | PS5-68-NER-1614C |  | T | T | CCTV camera not focused | CPP AGI | PS5-03-01 - ESD System |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-02467 | PS5-10-OB-7575B |  | M | M | Bearing temperature high | CPP AGI | PS5-02-01 - Diesel Storage Tank |  | In Progress | Wang, Li | PS5 - Milestone A | 1
PL-02468 | PS5-63-IK-9457D |  | E | E | Outgoing breaker not labeled | EPS UNATRAC | PS5-03-02 - Fire & Gas Detection | 2026-09-24 | Closed | Mohamed, Ali | PS5 - Milestone I | 8
PL-02469 | PS5-94-NER-8511A |  | H | H | AHU filter not installed | KENT | PS5-08-01 - Compressor Air System |  | On Hold | Kumar, Raj | PS5 - Milestone H | 7
PL-02470 | PS5-71-IK-3719B |  | E | E | Missing electrical hazard sign | CPP AGI | PS5-04-03 - 33kV ICSS System | 2026-12-27 | Closed | Kumar, Raj | PS5 - Milestone F | 5
PL-02471 | PS5-47-IK-9999D |  | B | B | Cracked wall plaster | EPS UNATRAC | PS5-61-01 - 33kV Switchboard EITS Building |  | In Progress | Wang, Li | PS5 - Milestone G | 6
PL-02472 | PS5-68-IK-2776D |  | P | P | Flange bolt torque incomplete | KENT | PS5-63-04 - Electrical Earthing EITS Building |  | In Progress | Thao-my, Alexandre | PS5 - Milestone B | 1.1
PL-02473 | PS5-63-NI-1995C |  | I | I | Control valve actuator fault | CPP AGI | PS5-82-02 - Structural Steel B |  | On Hold | Wang, Li | PS5 - Milestone A | 1
PL-02474 | PS5-35-NI-5445C |  | S | S | Deluge valve not primed | CPP AGI | PS5-62-01 - Cable Tray Main | 2026-12-17 | Closed | Wang, Li | PS5 - Milestone D | 3
PL-02475 | PS5-53-OB-1971D |  | S | S | Eye wash station blocked | KENT | PS5-99-01 - Area Completion Building Area |  | In Progress | Wang, Li | PS5 - Milestone E | 4
PL-02476 | PS5-47-OB-2471D |  | M | M | Vibration level exceeded | EPS UNATRAC | PS5-11-02 - Guard Hut B |  | In Progress | Jean, Pierre | PS5 - Milestone G | 6
PL-02477 | PS5-25-OB-6469D |  | E | E | Missing earth continuity label | CPP AGI | PS5-63-01 - Electrical Earthing |  | In Progress | Thao-my, Alexandre | PS5 - Milestone E | 4
PL-02478 | PS5-96-NER-5189B |  | H | H | Missing insulation on duct | CPP AGI | PS5-62-01 - Cable Tray Main |  | In Progress | Smith, John | PS5 - Milestone C | 2
PL-02479 | PS5-98-UR-7243A |  | I | I | Transmitter not calibrated | EPS UNATRAC | PS5-08-01 - Compressor Air System |  | In Progress | Smith, John | PS5 - Milestone A | 1
PL-02480 | PS5-91-NI-4278B |  | P | P | Gasket protruding from flange | EPS UNATRAC | PS5-04-03 - 33kV ICSS System | 2026-08-05 | Closed | Kumar, Raj | PS5 - Milestone C | 2
PL-02481 | PS5-77-IK-4180A |  | B | B | Missing door closer | EPS UNATRAC | PS5-01-08 - Drencher System |  | On Hold | Jean, Pierre | PS5 - Milestone F | 5
PL-02482 | PS5-18-IK-9147C |  | I | I | Missing loop diagram | EPS UNATRAC | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-12-08 | Closed | Mohamed, Ali | PS5 - Milestone C | 2
PL-02483 | PS5-75-OB-3335C |  | I | I | Instrument tubing leak | KENT | PS5-03-02 - Fire & Gas Detection | 2026-08-18 | Closed | Thao-my, Alexandre | PS5 - Milestone A | 1
PL-02484 | PS5-69-NI-4449C |  | I | I | Instrument tubing leak | KENT | PS5-63-01 - Electrical Earthing | 2026-08-21 | Closed | Smith, John | PS5 - Milestone A | 1
PL-02485 | PS5-57-UR-9581D |  | E | E | Outgoing breaker not labeled | CPP AGI | PS5-04-01 - DCS System |  | In Progress | Wang, Li | PS5 - Milestone F | 5
PL-02486 | PS5-81-NER-5846B |  | P | P | Gasket protruding from flange | KENT | PS5-03-03 - Flame Detector System |  | On Hold | Mohamed, Ali | PS5 - Milestone H | 7
PL-02487 | PS5-29-NER-3577B |  | M | M | Pump alignment required | KENT | PS5-10-03 - Process piping A |  | Originated | Mohamed, Ali | PS5 - Milestone C | 2
PL-02488 | PS5-93-IK-9620D |  | I | I | Missing loop diagram | EPS UNATRAC | PS5-04-03 - 33kV ICSS System | 2026-12-07 | Closed | Wang, Li | PS5 - Milestone H | 7
PL-02489 | PS5-28-IK-2315C |  | B | B | Missing fire extinguisher signage | KENT | PS5-07-03 - AHU System |  | In Progress | Jean, Pierre | PS5 - Milestone H | 7
PL-02490 | PS5-11-UR-3093B |  | H | H | AHU filter not installed | EPS UNATRAC | PS5-03-01 - ESD System |  | In Progress | Smith, John | PS5 - Milestone I | 8
PL-02491 | PS5-54-NER-2533D |  | S | S | Fire alarm panel fault | EPS UNATRAC | PS5-60-10 - Power Generation Package D |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-02492 | PS5-94-UR-4786C |  | S | S | Emergency shower not tested | CPP AGI | PS5-08-02 - Nitrogen Generator |  | In Progress | Mohamed, Ali | PS5 - Milestone C | 2
PL-02493 | PS5-38-IK-7793A |  | H | H | FCU drain pipe not connected | EPS UNATRAC | PS5-82-02 - Structural Steel B | 2026-09-22 | Closed | Mohamed, Ali | PS5 - Milestone G | 6
PL-02494 | PS5-85-OB-4250A |  | P | P | Flange bolt torque incomplete | EPS UNATRAC | PS5-10-01 - Main Pipe Rack | 2026-11-12 | Closed | Kumar, Raj | PS5 - Milestone A | 1
PL-02495 | PS5-95-NER-4342B |  | T | T | PA speaker not tested | CPP AGI | PS5-07-02 - Chiller System B |  | Originated | Jean, Pierre | PS5 - Milestone A | 1
PL-02496 | PS5-24-IK-4350B |  | H | H | FCU drain pipe not connected | KENT | PS5-11-03 - Admin Building |  | In Progress | Smith, John | PS5 - Milestone G | 6
PL-02497 | PS5-75-UR-1546C |  | M | M | Coupling guard loose | CPP AGI | PS5-07-02 - Chiller System B |  | In Progress | Kumar, Raj | PS5 - Milestone B | 1.1
PL-02498 | PS5-53-OB-5984D |  | S | S | Missing safety sign | CPP AGI | PS5-60-07 - Power Generation Package C |  | In Progress | Kumar, Raj | PS5 - Milestone A | 1
PL-02499 | PS5-62-NER-1954D |  | I | I | Control valve actuator fault | CPP AGI | PS5-82-02 - Structural Steel B |  | In Progress | Wang, Li | PS5 - Milestone I | 8
PL-02500 | PS5-85-OB-2760A |  | B | B | Damaged ceiling panel | KENT | PS5-06-03 - Lightning Protection |  | Originated | Smith, John | PS5 - Milestone H | 7

## DETAILED ITR LIST
Task ID | Asset - Tag | Description | Category (Summary) | Discipline | Task Type (Name) | Discipline (Summary) | Responsible Company (Summary) | Physical Location - Area (Summary) | Systemization - Subsystem (Summary) | Closing Date | Subsystem ID | Priority | Priority_NUM | Task State | Actual MH | Planned MH | MONTH
T-555-0001 | PS5-57-OB-6334A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone G | 6 | On hold |  | 5 | NOVEMBER
T-456-0002 | PS5-12-UR-8291B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone G | 6 | On hold |  | 26 | NOVEMBER
T-248-0003 | PS5-06-OB-5594B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-07-06 | PS5-60-10 | PS5 - Milestone I | 8 | Closed | 44 | 14 | JULY
T-194-0004 | PS5-14-IK-7371A | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone E | 4 | In progress |  | 32 | DECEMBER
T-440-0005 | PS5-01-IK-1960A | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone I | 8 | To be completed |  | 32 | NOVEMBER
T-834-0006 | PS5-44-OB-4895C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone G | 6 | To be completed |  | 29 | AUGUST
T-128-0007 | PS5-41-UR-4520A | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-11-19 | PS5-11-03 | PS5 - Milestone I | 8 | Closed | 38 | 30 | NOVEMBER
T-807-0008 | PS5-62-UR-9497A | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-12-01 | PS5-01-01 | PS5 - Milestone B | 1.1 | Closed | 5 | 8 | DECEMBER
T-768-0009 | PS5-84-OB-5836C | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone F | 5 | To be completed |  | 11 | OCTOBER
T-548-0010 | PS5-57-OB-9219B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-02-19 | PS5-60-10 | PS5 - Milestone F | 5 | Closed | 8 | 34 | FEBRUARY
T-505-0011 | PS5-90-OB-7923A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone E | 4 | On hold |  | 18 | SEPTEMBER
T-684-0012 | PS5-07-UR-8831D | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | To be completed |  | 34 | SEPTEMBER
T-412-0013 | PS5-14-OB-3970D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | In progress |  | 12 | OCTOBER
T-175-0014 | PS5-15-OB-8071A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-02-14 | PS5-07-04 | PS5 - Milestone A | 1 | Closed | 38 | 9 | FEBRUARY
T-600-0015 | PS5-96-OB-3222A | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-04-02 | PS5-04-01 | PS5 - Milestone D | 3 | Closed | 18 | 11 | APRIL
T-784-0016 | PS5-52-OB-5721B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-01-19 | PS5-11-02 | PS5 - Milestone G | 6 | Closed | 9 | 8 | JANUARY
T-262-0017 | PS5-33-OB-1696D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone D | 3 | To be completed |  | 48 | OCTOBER
T-290-0018 | PS5-73-IK-1488D | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-05-14 | PS5-03-02 | PS5 - Milestone E | 4 | Closed | 47 | 25 | MAY
T-588-0019 | PS5-84-OB-8980B | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone C | 2 | To be completed |  | 21 | DECEMBER
T-186-0020 | PS5-41-UR-9743B | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-10-12 | PS5-10-04 | PS5 - Milestone C | 2 | Closed | 28 | 42 | OCTOBER
T-483-0021 | PS5-38-OB-9499B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | To be completed |  | 12 | SEPTEMBER
T-011-0022 | PS5-99-UR-6053C | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone H | 7 | To be completed |  | 29 | SEPTEMBER
T-048-0023 | PS5-21-OB-6962D | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | In progress |  | 12 | NOVEMBER
T-854-0024 | PS5-05-OB-9536B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone C | 2 | To be completed |  | 43 | OCTOBER
T-643-0025 | PS5-47-UR-6414A | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone B | 1.1 | To be completed |  | 11 | OCTOBER
T-156-0026 | PS5-17-OB-1108C | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone G | 6 | In progress |  | 41 | OCTOBER
T-829-0027 | PS5-69-OB-9388A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-12-21 | PS5-09-02 | PS5 - Milestone D | 3 | Closed | 16 | 47 | DECEMBER
T-440-0028 | PS5-68-UR-4736A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-01-25 | PS5-82-07 | PS5 - Milestone I | 8 | Closed | 40 | 47 | JANUARY
T-999-0029 | PS5-53-IK-8588C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone B | 1.1 | On hold |  | 31 | SEPTEMBER
T-517-0030 | PS5-67-UR-4201C | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone F | 5 | In progress |  | 44 | SEPTEMBER
T-072-0031 | PS5-60-UR-1413B | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-11-11 | PS5-10-05 | PS5 - Milestone E | 4 | Closed | 20 | 25 | NOVEMBER
T-487-0032 | PS5-56-OB-7207C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone I | 8 | To be completed |  | 38 | AUGUST
T-703-0033 | PS5-28-OB-6896C | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone F | 5 | In progress |  | 12 | NOVEMBER
T-006-0034 | PS5-82-OB-1249D | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone B | 1.1 | In progress |  | 22 | OCTOBER
T-612-0035 | PS5-79-OB-2584D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone G | 6 | In progress |  | 27 | OCTOBER
T-097-0036 | PS5-04-OB-4375D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-03-20 | PS5-07-04 | PS5 - Milestone D | 3 | Closed | 22 | 23 | MARCH
T-527-0037 | PS5-52-OB-3143A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-11-03 | PS5-12-02 | PS5 - Milestone I | 8 | Closed | 13 | 35 | NOVEMBER
T-222-0038 | PS5-16-UR-3742A | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | On hold |  | 24 | NOVEMBER
T-571-0039 | PS5-60-IK-8533B | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone H | 7 | To be completed |  | 20 | OCTOBER
T-389-0040 | PS5-92-UR-3655D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | In progress |  | 13 | NOVEMBER
T-812-0041 | PS5-34-OB-3189B | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone I | 8 | To be completed |  | 17 | DECEMBER
T-924-0042 | PS5-52-OB-7505A | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-11-19 | PS5-06-03 | PS5 - Milestone A | 1 | Closed | 26 | 18 | NOVEMBER
T-902-0043 | PS5-72-OB-2842D | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-04-11 | PS5-06-01 | PS5 - Milestone D | 3 | Closed | 31 | 26 | APRIL
T-778-0044 | PS5-91-OB-6028C | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone E | 4 | To be completed |  | 18 | NOVEMBER
T-589-0045 | PS5-34-UR-2200C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone I | 8 | To be completed |  | 16 | DECEMBER
T-412-0046 | PS5-60-OB-9514B | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone G | 6 | On hold |  | 40 | DECEMBER
T-228-0047 | PS5-72-OB-9973C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | To be completed |  | 15 | NOVEMBER
T-375-0048 | PS5-04-OB-2539A | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone C | 2 | To be completed |  | 10 | NOVEMBER
T-163-0049 | PS5-98-OB-5285D | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | In progress |  | 9 | NOVEMBER
T-862-0050 | PS5-81-OB-6613D | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-08-23 | PS5-60-07 | PS5 - Milestone B | 1.1 | Closed | 37 | 46 | AUGUST
T-040-0051 | PS5-75-OB-2936A | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone H | 7 | On hold |  | 16 | SEPTEMBER
T-165-0052 | PS5-35-IK-8683A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone G | 6 | To be completed |  | 45 | OCTOBER
T-318-0053 | PS5-87-OB-8643C | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone H | 7 | To be completed |  | 15 | AUGUST
T-208-0054 | PS5-45-OB-8845D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone G | 6 | In progress |  | 41 | AUGUST
T-504-0055 | PS5-51-OB-7951D | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone D | 3 | To be completed |  | 26 | SEPTEMBER
T-765-0056 | PS5-11-IK-6793D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone F | 5 | In progress |  | 19 | DECEMBER
T-510-0057 | PS5-22-OB-5471C | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-05-01 | PS5-62-02 | PS5 - Milestone E | 4 | Closed | 43 | 29 | MAY
T-890-0058 | PS5-05-OB-9601A | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-08-26 | PS5-07-04 | PS5 - Milestone E | 4 | Closed | 17 | 16 | AUGUST
T-761-0059 | PS5-68-OB-5533D | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-14 | PS5-60-10 | PS5 - Milestone D | 3 | Closed | 18 | 33 | APRIL
T-324-0060 | PS5-14-OB-3312B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | In progress |  | 38 | SEPTEMBER
T-887-0061 | PS5-56-OB-5057A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-08-09 | PS5-62-01 | PS5 - Milestone D | 3 | Closed | 12 | 35 | AUGUST
T-901-0062 | PS5-12-OB-3933C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone E | 4 | In progress |  | 34 | DECEMBER
T-652-0063 | PS5-61-UR-9492A | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone B | 1.1 | To be completed |  | 5 | DECEMBER
T-878-0064 | PS5-44-OB-6635C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone E | 4 | To be completed |  | 47 | OCTOBER
T-446-0065 | PS5-97-OB-1990B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-12-13 | PS5-61-01 | PS5 - Milestone A | 1 | Closed | 48 | 38 | DECEMBER
T-195-0066 | PS5-63-OB-5154B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-02-28 | PS5-05-01 | PS5 - Milestone C | 2 | Closed | 37 | 23 | FEBRUARY
T-595-0067 | PS5-09-OB-7626D | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone D | 3 | In progress |  | 5 | AUGUST
T-546-0068 | PS5-94-IK-9393D | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone A | 1 | To be completed |  | 18 | DECEMBER
T-638-0069 | PS5-17-OB-4026C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone H | 7 | In progress |  | 16 | AUGUST
T-507-0070 | PS5-96-IK-9234D | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone I | 8 | To be completed |  | 21 | SEPTEMBER
T-008-0071 | PS5-92-IK-3531B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone D | 3 | To be completed |  | 7 | NOVEMBER
T-203-0072 | PS5-29-OB-3705D | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-03-20 | PS5-12-02 | PS5 - Milestone C | 2 | Closed | 29 | 26 | MARCH
T-702-0073 | PS5-60-UR-3676A | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone D | 3 | In progress |  | 44 | OCTOBER
T-083-0074 | PS5-86-UR-1638D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone B | 1.1 | On hold |  | 28 | AUGUST
T-546-0075 | PS5-37-OB-4563D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-10-08 | PS5-01-08 | PS5 - Milestone E | 4 | Closed | 35 | 42 | OCTOBER
T-881-0076 | PS5-11-UR-8962A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone I | 8 | To be completed |  | 36 | SEPTEMBER
T-665-0077 | PS5-60-OB-9648D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-09-11 | PS5-62-01 | PS5 - Milestone E | 4 | Closed | 9 | 25 | SEPTEMBER
T-762-0078 | PS5-65-OB-7351A | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | On hold |  | 4 | DECEMBER
T-045-0079 | PS5-31-IK-1438B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-11-09 | PS5-10-01 | PS5 - Milestone B | 1.1 | Closed | 42 | 27 | NOVEMBER
T-452-0080 | PS5-43-IK-8324D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-01-17 | PS5-12-01 | PS5 - Milestone D | 3 | Closed | 35 | 35 | JANUARY
T-874-0081 | PS5-37-UR-8905C | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | To be completed |  | 5 | SEPTEMBER
T-920-0082 | PS5-34-OB-8149B | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-09-27 | PS5-01-08 | PS5 - Milestone E | 4 | Closed | 40 | 25 | SEPTEMBER
T-444-0083 | PS5-58-IK-1341B | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone B | 1.1 | In progress |  | 13 | OCTOBER
T-713-0084 | PS5-81-UR-5526A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone C | 2 | In progress |  | 44 | OCTOBER
T-912-0085 | PS5-47-OB-4069D | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | On hold |  | 39 | OCTOBER
T-311-0086 | PS5-96-OB-1491C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-07-17 | PS5-07-01 | PS5 - Milestone F | 5 | Closed | 7 | 22 | JULY
T-643-0087 | PS5-92-OB-4793A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone H | 7 | In progress |  | 6 | DECEMBER
T-380-0088 | PS5-48-UR-2282A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-11-22 | PS5-01-09 | PS5 - Milestone G | 6 | Closed | 17 | 15 | NOVEMBER
T-251-0089 | PS5-64-OB-4030D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone G | 6 | To be completed |  | 19 | SEPTEMBER
T-773-0090 | PS5-97-OB-8418B | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-09-10 | PS5-05-02 | PS5 - Milestone B | 1.1 | Closed | 21 | 12 | SEPTEMBER
T-495-0091 | PS5-36-UR-7767B | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-05-06 | PS5-07-04 | PS5 - Milestone E | 4 | Closed | 20 | 33 | MAY
T-702-0092 | PS5-89-OB-8268D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-04-15 | PS5-05-02 | PS5 - Milestone H | 7 | Closed | 43 | 40 | APRIL
T-258-0093 | PS5-12-IK-6411D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | In progress |  | 45 | OCTOBER
T-787-0094 | PS5-76-OB-7397B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone E | 4 | On hold |  | 37 | DECEMBER
T-576-0095 | PS5-63-UR-4043D | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-04-22 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 17 | 18 | APRIL
T-726-0096 | PS5-67-IK-9122C | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-04-17 | PS5-09-03 | PS5 - Milestone A | 1 | Closed | 20 | 25 | APRIL
T-910-0097 | PS5-46-IK-2099D | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-08-17 | PS5-60-04 | PS5 - Milestone F | 5 | Closed | 29 | 44 | AUGUST
T-040-0098 | PS5-48-OB-2759B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone E | 4 | On hold |  | 16 | NOVEMBER
T-469-0099 | PS5-92-OB-7040A | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone C | 2 | To be completed |  | 9 | DECEMBER
T-559-0100 | PS5-12-IK-4072D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone A | 1 | In progress |  | 40 | SEPTEMBER
T-564-0101 | PS5-13-OB-7589A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone G | 6 | To be completed |  | 36 | OCTOBER
T-924-0102 | PS5-84-IK-7658B | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone A | 1 | In progress |  | 25 | DECEMBER
T-327-0103 | PS5-65-UR-1733B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone A | 1 | In progress |  | 44 | AUGUST
T-114-0104 | PS5-52-OB-5710B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | To be completed |  | 33 | AUGUST
T-132-0105 | PS5-57-IK-5078D | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone H | 7 | On hold |  | 31 | OCTOBER
T-525-0106 | PS5-03-OB-3384B | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone G | 6 | To be completed |  | 25 | AUGUST
T-468-0107 | PS5-93-IK-2847A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-07-21 | PS5-61-02 | PS5 - Milestone H | 7 | Closed | 26 | 47 | JULY
T-717-0108 | PS5-67-OB-7276B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-08-03 | PS5-99-01 | PS5 - Milestone A | 1 | Closed | 16 | 15 | AUGUST
T-754-0109 | PS5-75-IK-2341D | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-01-21 | PS5-12-02 | PS5 - Milestone D | 3 | Closed | 34 | 7 | JANUARY
T-702-0110 | PS5-34-OB-9656D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-01-05 | PS5-10-02 | PS5 - Milestone D | 3 | Closed | 47 | 25 | JANUARY
T-103-0111 | PS5-07-UR-4118B | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone C | 2 | In progress |  | 19 | OCTOBER
T-005-0112 | PS5-74-IK-2958B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone D | 3 | To be completed |  | 18 | OCTOBER
T-841-0113 | PS5-24-IK-3779C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone A | 1 | To be completed |  | 18 | OCTOBER
T-622-0114 | PS5-57-IK-1603B | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-07-17 | PS5-82-02 | PS5 - Milestone B | 1.1 | Closed | 19 | 48 | JULY
T-737-0115 | PS5-84-OB-8997C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-10-03 | PS5-01-04 | PS5 - Milestone B | 1.1 | Closed | 28 | 22 | OCTOBER
T-724-0116 | PS5-92-IK-6815D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-12-10 | PS5-01-04 | PS5 - Milestone I | 8 | Closed | 25 | 40 | DECEMBER
T-187-0117 | PS5-02-OB-9814D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-06-01 | PS5-13-01 | PS5 - Milestone H | 7 | Closed | 13 | 45 | JUNE
T-127-0118 | PS5-72-OB-9397D | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-07-01 | PS5-63-01 | PS5 - Milestone B | 1.1 | Closed | 11 | 5 | JULY
T-053-0119 | PS5-07-UR-3227B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-10-01 | PS5-62-01 | PS5 - Milestone A | 1 | Closed | 14 | 37 | OCTOBER
T-140-0120 | PS5-90-OB-9298A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone I | 8 | In progress |  | 10 | AUGUST
T-373-0121 | PS5-50-OB-3740A | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone G | 6 | In progress |  | 11 | SEPTEMBER
T-048-0122 | PS5-07-OB-6847A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-05-24 | PS5-13-01 | PS5 - Milestone G | 6 | Closed | 21 | 37 | MAY
T-524-0123 | PS5-58-IK-9177B | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-12-04 | PS5-82-02 | PS5 - Milestone D | 3 | Closed | 43 | 43 | DECEMBER
T-794-0124 | PS5-05-OB-4279A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone D | 3 | To be completed |  | 20 | AUGUST
T-218-0125 | PS5-48-UR-1615A | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-10-03 | PS5-03-23 | PS5 - Milestone C | 2 | Closed | 39 | 34 | OCTOBER
T-185-0126 | PS5-55-UR-1872A | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-06-08 | PS5-01-06 | PS5 - Milestone F | 5 | Closed | 39 | 35 | JUNE
T-766-0127 | PS5-48-OB-8406A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | To be completed |  | 12 | NOVEMBER
T-385-0128 | PS5-98-OB-6181B | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-06-01 | PS5-07-03 | PS5 - Milestone B | 1.1 | Closed | 46 | 35 | JUNE
T-361-0129 | PS5-32-OB-2125C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone H | 7 | To be completed |  | 6 | SEPTEMBER
T-464-0130 | PS5-83-IK-7843A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-12-26 | PS5-63-04 | PS5 - Milestone C | 2 | Closed | 16 | 16 | DECEMBER
T-019-0131 | PS5-52-IK-4732D | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-01-26 | PS5-61-01 | PS5 - Milestone I | 8 | Closed | 21 | 21 | JANUARY
T-288-0132 | PS5-75-UR-2879D | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone B | 1.1 | To be completed |  | 37 | OCTOBER
T-462-0133 | PS5-42-UR-9661B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone I | 8 | In progress |  | 44 | SEPTEMBER
T-057-0134 | PS5-83-OB-7750B | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-04-10 | PS5-03-01 | PS5 - Milestone B | 1.1 | Closed | 47 | 14 | APRIL
T-853-0135 | PS5-30-IK-5106D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone E | 4 | On hold |  | 48 | SEPTEMBER
T-285-0136 | PS5-50-OB-2016D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone D | 3 | To be completed |  | 25 | NOVEMBER
T-403-0137 | PS5-25-IK-3186A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone A | 1 | In progress |  | 9 | AUGUST
T-529-0138 | PS5-06-IK-8145B | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone C | 2 | To be completed |  | 37 | OCTOBER
T-533-0139 | PS5-44-OB-6386D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone B | 1.1 | To be completed |  | 24 | NOVEMBER
T-609-0140 | PS5-23-UR-2403D | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-10-02 | PS5-62-02 | PS5 - Milestone B | 1.1 | Closed | 45 | 47 | OCTOBER
T-010-0141 | PS5-97-OB-4545D | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-09-04 | PS5-10-01 | PS5 - Milestone C | 2 | Closed | 48 | 29 | SEPTEMBER
T-113-0142 | PS5-58-IK-1703A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone E | 4 | In progress |  | 36 | AUGUST
T-078-0143 | PS5-89-UR-8591A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | On hold |  | 11 | NOVEMBER
T-198-0144 | PS5-20-OB-1416D | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone H | 7 | On hold |  | 7 | OCTOBER
T-259-0145 | PS5-92-OB-3054A | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone D | 3 | In progress |  | 20 | SEPTEMBER
T-962-0146 | PS5-97-IK-3603A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-03-01 | PS5-05-03 | PS5 - Milestone G | 6 | Closed | 6 | 32 | MARCH
T-728-0147 | PS5-51-OB-5954A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-11-21 | PS5-60-04 | PS5 - Milestone A | 1 | Closed | 35 | 35 | NOVEMBER
T-855-0148 | PS5-28-OB-7068D | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-05-27 | PS5-02-01 | PS5 - Milestone A | 1 | Closed | 47 | 42 | MAY
T-299-0149 | PS5-09-OB-9713C | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-06-09 | PS5-04-03 | PS5 - Milestone E | 4 | Closed | 15 | 35 | JUNE
T-932-0150 | PS5-49-UR-3726D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-09-22 | PS5-07-04 | PS5 - Milestone I | 8 | Closed | 45 | 31 | SEPTEMBER
T-536-0151 | PS5-79-IK-4854A | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | To be completed |  | 31 | NOVEMBER
T-510-0152 | PS5-62-IK-1100C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone D | 3 | To be completed |  | 23 | OCTOBER
T-562-0153 | PS5-02-IK-6872A | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone D | 3 | In progress |  | 20 | NOVEMBER
T-727-0154 | PS5-05-IK-2102B | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone E | 4 | To be completed |  | 30 | OCTOBER
T-884-0155 | PS5-55-UR-7584D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | To be completed |  | 4 | OCTOBER
T-432-0156 | PS5-90-OB-9230D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone E | 4 | In progress |  | 6 | SEPTEMBER
T-970-0157 | PS5-40-OB-6245D | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone D | 3 | To be completed |  | 11 | NOVEMBER
T-092-0158 | PS5-40-UR-4909D | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone H | 7 | On hold |  | 5 | NOVEMBER
T-836-0159 | PS5-69-OB-9346D | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-10-09 | PS5-05-01 | PS5 - Milestone D | 3 | Closed | 30 | 23 | OCTOBER
T-560-0160 | PS5-12-OB-1746A | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone A | 1 | To be completed |  | 31 | OCTOBER
T-624-0161 | PS5-74-OB-1176A | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-03-25 | PS5-61-07 | PS5 - Milestone I | 8 | Closed | 5 | 21 | MARCH
T-424-0162 | PS5-47-OB-1737D | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone H | 7 | To be completed |  | 29 | OCTOBER
T-587-0163 | PS5-39-UR-1775C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone A | 1 | To be completed |  | 13 | OCTOBER
T-816-0164 | PS5-10-OB-8437B | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-03-22 | PS5-07-04 | PS5 - Milestone F | 5 | Closed | 32 | 27 | MARCH
T-997-0165 | PS5-74-UR-8478C | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone I | 8 | In progress |  | 6 | SEPTEMBER
T-760-0166 | PS5-65-OB-9352D | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone H | 7 | To be completed |  | 33 | DECEMBER
T-256-0167 | PS5-81-OB-6698D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-08-19 | PS5-09-04 | PS5 - Milestone B | 1.1 | Closed | 36 | 25 | AUGUST
T-618-0168 | PS5-25-UR-3993B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone I | 8 | To be completed |  | 24 | AUGUST
T-989-0169 | PS5-82-OB-6818A | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-08-01 | PS5-01-04 | PS5 - Milestone G | 6 | Closed | 21 | 15 | AUGUST
T-463-0170 | PS5-98-OB-8471B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-11-11 | PS5-11-03 | PS5 - Milestone F | 5 | Closed | 37 | 38 | NOVEMBER
T-790-0171 | PS5-97-IK-9101D | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-03-22 | PS5-04-02 | PS5 - Milestone B | 1.1 | Closed | 11 | 15 | MARCH
T-568-0172 | PS5-55-OB-8921A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone B | 1.1 | In progress |  | 21 | OCTOBER
T-087-0173 | PS5-15-OB-2924C | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | In progress |  | 4 | OCTOBER
T-253-0174 | PS5-18-IK-7163C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone C | 2 | In progress |  | 40 | OCTOBER
T-455-0175 | PS5-80-UR-5278B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-05-26 | PS5-09-01 | PS5 - Milestone A | 1 | Closed | 22 | 33 | MAY
T-253-0176 | PS5-18-UR-2371D | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone I | 8 | To be completed |  | 48 | AUGUST
T-061-0177 | PS5-03-UR-5443A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-08-12 | PS5-13-01 | PS5 - Milestone B | 1.1 | Closed | 21 | 16 | AUGUST
T-899-0178 | PS5-84-UR-4366A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone G | 6 | To be completed |  | 20 | NOVEMBER
T-503-0179 | PS5-14-UR-7586C | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-11-05 | PS5-01-09 | PS5 - Milestone B | 1.1 | Closed | 6 | 27 | NOVEMBER
T-576-0180 | PS5-34-UR-6176D | CQH02 - AHU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone B | 1.1 | To be completed |  | 30 | SEPTEMBER
T-325-0181 | PS5-27-OB-6189C | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-12-03 | PS5-10-05 | PS5 - Milestone E | 4 | Closed | 37 | 12 | DECEMBER
T-202-0182 | PS5-45-IK-4768D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone I | 8 | To be completed |  | 48 | AUGUST
T-896-0183 | PS5-64-OB-8390D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-01-26 | PS5-11-01 | PS5 - Milestone C | 2 | Closed | 22 | 12 | JANUARY
T-402-0184 | PS5-34-UR-1555B | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone E | 4 | In progress |  | 7 | OCTOBER
T-986-0185 | PS5-95-OB-6966D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-07-10 | PS5-62-01 | PS5 - Milestone A | 1 | Closed | 35 | 33 | JULY
T-482-0186 | PS5-21-IK-5149D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone E | 4 | To be completed |  | 16 | AUGUST
T-034-0187 | PS5-57-UR-7506D | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | To be completed |  | 10 | SEPTEMBER
T-770-0188 | PS5-88-IK-5039C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-04-05 | PS5-10-02 | PS5 - Milestone D | 3 | Closed | 37 | 20 | APRIL
T-608-0189 | PS5-34-OB-5301B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-11-08 | PS5-04-04 | PS5 - Milestone H | 7 | Closed | 42 | 48 | NOVEMBER
T-729-0190 | PS5-37-UR-8199C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-08-24 | PS5-12-01 | PS5 - Milestone H | 7 | Closed | 12 | 13 | AUGUST
T-107-0191 | PS5-60-OB-5433C | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-07-28 | PS5-01-04 | PS5 - Milestone C | 2 | Closed | 21 | 6 | JULY
T-990-0192 | PS5-03-IK-1107D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone F | 5 | To be completed |  | 12 | SEPTEMBER
T-801-0193 | PS5-54-OB-8889D | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-10-12 | PS5-01-05 | PS5 - Milestone H | 7 | Closed | 43 | 17 | OCTOBER
T-989-0194 | PS5-28-OB-4065A | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-04-24 | PS5-09-02 | PS5 - Milestone D | 3 | Closed | 11 | 6 | APRIL
T-982-0195 | PS5-73-OB-6624A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | In progress |  | 27 | OCTOBER
T-572-0196 | PS5-59-UR-1496C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone D | 3 | On hold |  | 27 | AUGUST
T-913-0197 | PS5-36-OB-6101C | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone D | 3 | In progress |  | 14 | SEPTEMBER
T-157-0198 | PS5-23-OB-8824A | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone A | 1 | To be completed |  | 11 | AUGUST
T-217-0199 | PS5-10-IK-9455C | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-10-14 | PS5-11-03 | PS5 - Milestone C | 2 | Closed | 11 | 33 | OCTOBER
T-292-0200 | PS5-09-OB-6508A | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone A | 1 | To be completed |  | 21 | NOVEMBER
T-720-0201 | PS5-63-IK-6581C | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone A | 1 | In progress |  | 4 | NOVEMBER
T-639-0202 | PS5-38-OB-3096B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone E | 4 | To be completed |  | 25 | SEPTEMBER
T-152-0203 | PS5-14-OB-7325B | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone E | 4 | To be completed |  | 22 | OCTOBER
T-580-0204 | PS5-66-IK-9731B | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-08-09 | PS5-10-01 | PS5 - Milestone B | 1.1 | Closed | 8 | 9 | AUGUST
T-671-0205 | PS5-75-OB-9814C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-05-03 | PS5-60-07 | PS5 - Milestone G | 6 | Closed | 33 | 34 | MAY
T-951-0206 | PS5-34-UR-8185C | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-07-24 | PS5-02-01 | PS5 - Milestone C | 2 | Closed | 4 | 22 | JULY
T-924-0207 | PS5-90-UR-1822D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone D | 3 | In progress |  | 18 | OCTOBER
T-077-0208 | PS5-20-UR-1079A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-03-12 | PS5-82-02 | PS5 - Milestone D | 3 | Closed | 33 | 46 | MARCH
T-023-0209 | PS5-01-OB-6466D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone F | 5 | To be completed |  | 17 | OCTOBER
T-672-0210 | PS5-25-UR-9447B | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | To be completed |  | 38 | SEPTEMBER
T-964-0211 | PS5-49-OB-5554D | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-07-02 | PS5-62-02 | PS5 - Milestone H | 7 | Closed | 32 | 6 | JULY
T-679-0212 | PS5-94-OB-4905C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone B | 1.1 | On hold |  | 31 | NOVEMBER
T-856-0213 | PS5-65-OB-8030A | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-01-24 | PS5-02-02 | PS5 - Milestone F | 5 | Closed | 38 | 35 | JANUARY
T-518-0214 | PS5-65-OB-3836B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone E | 4 | In progress |  | 47 | AUGUST
T-475-0215 | PS5-90-OB-4467D | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone C | 2 | To be completed |  | 48 | AUGUST
T-375-0216 | PS5-86-IK-2809C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone E | 4 | To be completed |  | 48 | NOVEMBER
T-705-0217 | PS5-95-IK-7071B | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone A | 1 | In progress |  | 46 | DECEMBER
T-050-0218 | PS5-72-IK-3059A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-07-28 | PS5-60-10 | PS5 - Milestone F | 5 | Closed | 25 | 45 | JULY
T-589-0219 | PS5-80-OB-9670A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-02-16 | PS5-62-01 | PS5 - Milestone E | 4 | Closed | 35 | 13 | FEBRUARY
T-427-0220 | PS5-78-UR-9785B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone E | 4 | To be completed |  | 45 | AUGUST
T-601-0221 | PS5-05-UR-3657D | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone A | 1 | In progress |  | 19 | OCTOBER
T-946-0222 | PS5-15-IK-1351B | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-04-27 | PS5-06-02 | PS5 - Milestone B | 1.1 | Closed | 38 | 24 | APRIL
T-354-0223 | PS5-10-IK-4159B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone F | 5 | To be completed |  | 20 | SEPTEMBER
T-339-0224 | PS5-45-OB-7950D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone I | 8 | In progress |  | 19 | DECEMBER
T-970-0225 | PS5-88-OB-1752C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-08-21 | PS5-12-01 | PS5 - Milestone I | 8 | Closed | 41 | 11 | AUGUST
T-405-0226 | PS5-88-IK-3250B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | On hold |  | 11 | NOVEMBER
T-673-0227 | PS5-64-OB-1952C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone D | 3 | In progress |  | 24 | AUGUST
T-655-0228 | PS5-10-OB-5489D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone D | 3 | On hold |  | 28 | AUGUST
T-420-0229 | PS5-28-UR-4475D | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-01-04 | PS5-10-04 | PS5 - Milestone E | 4 | Closed | 37 | 13 | JANUARY
T-661-0230 | PS5-64-IK-6134D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | To be completed |  | 37 | OCTOBER
T-502-0231 | PS5-36-IK-1237D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone E | 4 | To be completed |  | 17 | SEPTEMBER
T-312-0232 | PS5-26-OB-1394D | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-01-05 | PS5-06-01 | PS5 - Milestone I | 8 | Closed | 34 | 10 | JANUARY
T-449-0233 | PS5-46-IK-5214B | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone F | 5 | On hold |  | 12 | NOVEMBER
T-933-0234 | PS5-50-OB-8012A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone H | 7 | In progress |  | 19 | OCTOBER
T-215-0235 | PS5-33-UR-5088C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | In progress |  | 34 | AUGUST
T-620-0236 | PS5-78-OB-4621B | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-04-07 | PS5-99-03 | PS5 - Milestone C | 2 | Closed | 42 | 11 | APRIL
T-824-0237 | PS5-24-OB-2467B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone F | 5 | To be completed |  | 15 | NOVEMBER
T-900-0238 | PS5-28-OB-5375B | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone F | 5 | To be completed |  | 14 | OCTOBER
T-944-0239 | PS5-57-OB-9195A | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone E | 4 | To be completed |  | 36 | NOVEMBER
T-556-0240 | PS5-97-IK-4572A | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone H | 7 | In progress |  | 6 | AUGUST
T-381-0241 | PS5-71-OB-2975B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone D | 3 | In progress |  | 23 | NOVEMBER
T-365-0242 | PS5-84-OB-9656B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone D | 3 | To be completed |  | 8 | SEPTEMBER
T-840-0243 | PS5-66-IK-2773D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | In progress |  | 35 | NOVEMBER
T-045-0244 | PS5-82-UR-4586B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone F | 5 | In progress |  | 15 | OCTOBER
T-336-0245 | PS5-12-IK-6546B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-01-19 | PS5-09-03 | PS5 - Milestone I | 8 | Closed | 44 | 27 | JANUARY
T-961-0246 | PS5-55-IK-4506A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone C | 2 | In progress |  | 34 | OCTOBER
T-656-0247 | PS5-97-UR-6101D | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | To be completed |  | 42 | AUGUST
T-474-0248 | PS5-56-IK-4246C | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone F | 5 | To be completed |  | 33 | SEPTEMBER
T-313-0249 | PS5-52-OB-7424B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone H | 7 | In progress |  | 39 | AUGUST
T-930-0250 | PS5-94-OB-9673B | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-09-14 | PS5-62-01 | PS5 - Milestone A | 1 | Closed | 25 | 44 | SEPTEMBER
T-461-0251 | PS5-95-UR-8992A | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone H | 7 | In progress |  | 30 | SEPTEMBER
T-429-0252 | PS5-51-OB-1753B | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone A | 1 | In progress |  | 23 | OCTOBER
T-968-0253 | PS5-79-UR-5453D | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone I | 8 | On hold |  | 20 | SEPTEMBER
T-238-0254 | PS5-86-IK-5474A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-10-23 | PS5-08-02 | PS5 - Milestone F | 5 | Closed | 38 | 18 | OCTOBER
T-433-0255 | PS5-75-OB-3215C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-07-19 | PS5-03-01 | PS5 - Milestone I | 8 | Closed | 17 | 35 | JULY
T-101-0256 | PS5-65-IK-3955A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone I | 8 | To be completed |  | 19 | AUGUST
T-301-0257 | PS5-99-OB-3907A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone C | 2 | To be completed |  | 15 | NOVEMBER
T-640-0258 | PS5-45-OB-5012A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | On hold |  | 35 | AUGUST
T-892-0259 | PS5-44-UR-3853D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-11-19 | PS5-60-10 | PS5 - Milestone A | 1 | Closed | 37 | 19 | NOVEMBER
T-448-0260 | PS5-80-OB-2860B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone I | 8 | To be completed |  | 48 | OCTOBER
T-675-0261 | PS5-94-OB-9934D | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone C | 2 | To be completed |  | 44 | OCTOBER
T-274-0262 | PS5-90-OB-9951A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone D | 3 | To be completed |  | 26 | OCTOBER
T-450-0263 | PS5-60-IK-5753A | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone G | 6 | In progress |  | 17 | AUGUST
T-825-0264 | PS5-56-OB-9798B | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone H | 7 | To be completed |  | 42 | NOVEMBER
T-456-0265 | PS5-30-OB-3795A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | In progress |  | 23 | OCTOBER
T-082-0266 | PS5-78-IK-2216A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-05-22 | PS5-82-07 | PS5 - Milestone F | 5 | Closed | 32 | 24 | MAY
T-066-0267 | PS5-30-OB-9260B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-09-10 | PS5-01-01 | PS5 - Milestone I | 8 | Closed | 35 | 7 | SEPTEMBER
T-338-0268 | PS5-92-OB-2379B | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone A | 1 | In progress |  | 14 | OCTOBER
T-014-0269 | PS5-47-OB-2474D | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-02-28 | PS5-62-02 | PS5 - Milestone D | 3 | Closed | 16 | 20 | FEBRUARY
T-186-0270 | PS5-39-OB-7573B | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-10-20 | PS5-61-07 | PS5 - Milestone D | 3 | Closed | 34 | 44 | OCTOBER
T-449-0271 | PS5-66-OB-4198C | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | In progress |  | 20 | DECEMBER
T-938-0272 | PS5-16-OB-5495D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-04-18 | PS5-63-01 | PS5 - Milestone A | 1 | Closed | 30 | 35 | APRIL
T-101-0273 | PS5-62-OB-3511D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | On hold |  | 23 | SEPTEMBER
T-723-0274 | PS5-45-UR-6002B | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-03-05 | PS5-02-01 | PS5 - Milestone H | 7 | Closed | 32 | 33 | MARCH
T-372-0275 | PS5-91-OB-3861D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | To be completed |  | 43 | DECEMBER
T-592-0276 | PS5-65-OB-7941A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-03-23 | PS5-07-02 | PS5 - Milestone F | 5 | Closed | 37 | 23 | MARCH
T-743-0277 | PS5-98-OB-6682A | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone I | 8 | To be completed |  | 8 | DECEMBER
T-880-0278 | PS5-40-OB-7396C | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-08-08 | PS5-63-04 | PS5 - Milestone G | 6 | Closed | 10 | 30 | AUGUST
T-410-0279 | PS5-89-UR-5184D | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-05-23 | PS5-06-02 | PS5 - Milestone D | 3 | Closed | 15 | 30 | MAY
T-293-0280 | PS5-36-IK-6960B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-07 | PS5-60-10 | PS5 - Milestone C | 2 | Closed | 45 | 23 | APRIL
T-584-0281 | PS5-43-OB-5732A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone E | 4 | To be completed |  | 44 | OCTOBER
T-934-0282 | PS5-53-IK-9046C | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone E | 4 | To be completed |  | 20 | AUGUST
T-222-0283 | PS5-84-OB-7138D | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-03-09 | PS5-10-01 | PS5 - Milestone C | 2 | Closed | 11 | 27 | MARCH
T-880-0284 | PS5-36-OB-3906D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | In progress |  | 7 | OCTOBER
T-260-0285 | PS5-52-IK-4909C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone I | 8 | To be completed |  | 47 | AUGUST
T-433-0286 | PS5-95-OB-2871C | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-05-21 | PS5-05-02 | PS5 - Milestone E | 4 | Closed | 42 | 44 | MAY
T-349-0287 | PS5-02-OB-2270D | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-02-17 | PS5-08-02 | PS5 - Milestone H | 7 | Closed | 9 | 26 | FEBRUARY
T-934-0288 | PS5-33-OB-4067D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone B | 1.1 | In progress |  | 39 | AUGUST
T-383-0289 | PS5-05-OB-7472D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone C | 2 | On hold |  | 44 | AUGUST
T-142-0290 | PS5-33-OB-1226C | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | To be completed |  | 35 | OCTOBER
T-470-0291 | PS5-42-OB-8156A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone I | 8 | To be completed |  | 35 | SEPTEMBER
T-457-0292 | PS5-56-OB-8684B | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone A | 1 | In progress |  | 6 | DECEMBER
T-352-0293 | PS5-56-OB-3185C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone E | 4 | To be completed |  | 44 | SEPTEMBER
T-020-0294 | PS5-63-IK-2341D | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-12 | PS5-60-04 | PS5 - Milestone G | 6 | Closed | 9 | 36 | APRIL
T-026-0295 | PS5-17-IK-6656C | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-05-27 | PS5-04-01 | PS5 - Milestone G | 6 | Closed | 26 | 42 | MAY
T-041-0296 | PS5-58-OB-6939D | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone G | 6 | To be completed |  | 18 | SEPTEMBER
T-963-0297 | PS5-96-IK-7869B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-06-03 | PS5-09-01 | PS5 - Milestone I | 8 | Closed | 44 | 7 | JUNE
T-705-0298 | PS5-98-OB-6369D | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-10-25 | PS5-99-01 | PS5 - Milestone F | 5 | Closed | 43 | 29 | OCTOBER
T-063-0299 | PS5-72-IK-2469B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone A | 1 | To be completed |  | 12 | OCTOBER
T-727-0300 | PS5-26-OB-7145C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-06-08 | PS5-04-03 | PS5 - Milestone G | 6 | Closed | 43 | 22 | JUNE
T-025-0301 | PS5-51-UR-4350B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-01-09 | PS5-02-01 | PS5 - Milestone E | 4 | Closed | 8 | 37 | JANUARY
T-711-0302 | PS5-65-OB-5699A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone D | 3 | To be completed |  | 8 | OCTOBER
T-291-0303 | PS5-12-IK-5092B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone G | 6 | On hold |  | 31 | AUGUST
T-703-0304 | PS5-09-OB-4936D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone A | 1 | On hold |  | 30 | NOVEMBER
T-359-0305 | PS5-39-IK-1953A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone H | 7 | To be completed |  | 36 | NOVEMBER
T-212-0306 | PS5-74-IK-7086A | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone E | 4 | In progress |  | 38 | AUGUST
T-347-0307 | PS5-96-OB-8610A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-04-12 | PS5-06-02 | PS5 - Milestone D | 3 | Closed | 5 | 31 | APRIL
T-837-0308 | PS5-65-OB-8159A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | In progress |  | 30 | AUGUST
T-291-0309 | PS5-07-OB-6360D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone E | 4 | In progress |  | 26 | SEPTEMBER
T-789-0310 | PS5-15-UR-7131C | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-09-20 | PS5-01-05 | PS5 - Milestone C | 2 | Closed | 37 | 39 | SEPTEMBER
T-675-0311 | PS5-38-IK-8087B | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone F | 5 | In progress |  | 19 | DECEMBER
T-554-0312 | PS5-47-IK-5188B | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone E | 4 | On hold |  | 8 | SEPTEMBER
T-504-0313 | PS5-19-IK-1728C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | To be completed |  | 48 | NOVEMBER
T-692-0314 | PS5-32-OB-7776A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | In progress |  | 4 | SEPTEMBER
T-298-0315 | PS5-83-UR-9238C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-08-11 | PS5-04-01 | PS5 - Milestone B | 1.1 | Closed | 16 | 12 | AUGUST
T-370-0316 | PS5-96-OB-2799C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone I | 8 | On hold |  | 30 | NOVEMBER
T-400-0317 | PS5-33-OB-1231B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-01-19 | PS5-02-02 | PS5 - Milestone G | 6 | Closed | 24 | 11 | JANUARY
T-931-0318 | PS5-48-OB-9368A | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone B | 1.1 | To be completed |  | 29 | SEPTEMBER
T-500-0319 | PS5-71-IK-9611B | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-10-15 | PS5-04-01 | PS5 - Milestone B | 1.1 | Closed | 36 | 44 | OCTOBER
T-269-0320 | PS5-91-UR-7368C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone B | 1.1 | In progress |  | 15 | OCTOBER
T-418-0321 | PS5-76-OB-2812B | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone B | 1.1 | To be completed |  | 10 | AUGUST
T-433-0322 | PS5-20-UR-4156A | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone G | 6 | In progress |  | 30 | OCTOBER
T-004-0323 | PS5-39-OB-1578A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone F | 5 | In progress |  | 34 | SEPTEMBER
T-769-0324 | PS5-42-UR-4756D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone D | 3 | In progress |  | 9 | NOVEMBER
T-685-0325 | PS5-53-UR-2099C | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-11-27 | PS5-04-04 | PS5 - Milestone A | 1 | Closed | 45 | 46 | NOVEMBER
T-655-0326 | PS5-51-OB-7306B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-08-16 | PS5-03-02 | PS5 - Milestone B | 1.1 | Closed | 43 | 23 | AUGUST
T-013-0327 | PS5-25-UR-9050C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-07-28 | PS5-05-03 | PS5 - Milestone I | 8 | Closed | 46 | 46 | JULY
T-730-0328 | PS5-33-IK-3066D | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone D | 3 | In progress |  | 48 | AUGUST
T-415-0329 | PS5-65-OB-2009B | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-01-27 | PS5-61-02 | PS5 - Milestone H | 7 | Closed | 48 | 29 | JANUARY
T-982-0330 | PS5-65-UR-9317C | CQP05 - Insulation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone E | 4 | To be completed |  | 4 | DECEMBER
T-412-0331 | PS5-93-OB-7688D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-08-14 | PS5-10-06 | PS5 - Milestone B | 1.1 | Closed | 26 | 12 | AUGUST
T-579-0332 | PS5-40-IK-5857A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-11-09 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 20 | 24 | NOVEMBER
T-798-0333 | PS5-95-OB-2481C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone G | 6 | To be completed |  | 29 | OCTOBER
T-948-0334 | PS5-15-IK-2424A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-10-25 | PS5-06-02 | PS5 - Milestone C | 2 | Closed | 30 | 28 | OCTOBER
T-003-0335 | PS5-86-UR-1476D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | To be completed |  | 44 | DECEMBER
T-228-0336 | PS5-57-UR-1285A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone B | 1.1 | To be completed |  | 22 | NOVEMBER
T-647-0337 | PS5-90-OB-6693B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone D | 3 | In progress |  | 35 | NOVEMBER
T-618-0338 | PS5-32-OB-7430B | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone G | 6 | In progress |  | 41 | NOVEMBER
T-994-0339 | PS5-65-OB-9745A | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-12-08 | PS5-09-03 | PS5 - Milestone G | 6 | Closed | 25 | 17 | DECEMBER
T-919-0340 | PS5-07-OB-6370C | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-03-11 | PS5-04-02 | PS5 - Milestone C | 2 | Closed | 9 | 22 | MARCH
T-464-0341 | PS5-27-IK-5221B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-01-01 | PS5-03-23 | PS5 - Milestone F | 5 | Closed | 18 | 44 | JANUARY
T-218-0342 | PS5-14-IK-7192B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-10-21 | PS5-99-02 | PS5 - Milestone E | 4 | Closed | 13 | 10 | OCTOBER
T-091-0343 | PS5-75-OB-4216D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone F | 5 | To be completed |  | 4 | SEPTEMBER
T-781-0344 | PS5-99-UR-5045C | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-10-15 | PS5-05-02 | PS5 - Milestone E | 4 | Closed | 47 | 30 | OCTOBER
T-918-0345 | PS5-26-IK-1273C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone G | 6 | On hold |  | 34 | DECEMBER
T-247-0346 | PS5-21-UR-8335C | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-01-17 | PS5-82-01 | PS5 - Milestone E | 4 | Closed | 28 | 19 | JANUARY
T-231-0347 | PS5-14-OB-8698C | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone H | 7 | In progress |  | 32 | DECEMBER
T-946-0348 | PS5-20-OB-6236D | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | To be completed |  | 26 | AUGUST
T-611-0349 | PS5-83-UR-5362D | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone A | 1 | In progress |  | 15 | NOVEMBER
T-973-0350 | PS5-34-IK-2552C | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone F | 5 | To be completed |  | 18 | DECEMBER
T-145-0351 | PS5-93-OB-1795C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | In progress |  | 27 | DECEMBER
T-330-0352 | PS5-59-OB-5699C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-04-26 | PS5-03-02 | PS5 - Milestone B | 1.1 | Closed | 6 | 45 | APRIL
T-883-0353 | PS5-75-UR-5246B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone G | 6 | To be completed |  | 15 | DECEMBER
T-799-0354 | PS5-70-UR-5001B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone I | 8 | To be completed |  | 27 | NOVEMBER
T-415-0355 | PS5-25-OB-4318D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone F | 5 | To be completed |  | 47 | OCTOBER
T-984-0356 | PS5-95-IK-8887B | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone B | 1.1 | To be completed |  | 17 | SEPTEMBER
T-426-0357 | PS5-68-OB-4100D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone D | 3 | In progress |  | 13 | DECEMBER
T-192-0358 | PS5-45-UR-5107D | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone B | 1.1 | On hold |  | 36 | DECEMBER
T-270-0359 | PS5-99-OB-1838D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone F | 5 | To be completed |  | 18 | OCTOBER
T-318-0360 | PS5-58-OB-6902B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone C | 2 | To be completed |  | 36 | OCTOBER
T-931-0361 | PS5-69-IK-7323B | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | To be completed |  | 23 | DECEMBER
T-560-0362 | PS5-57-UR-9530C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-01 | PS5-60-04 | PS5 - Milestone A | 1 | Closed | 22 | 29 | APRIL
T-045-0363 | PS5-14-OB-3583C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone G | 6 | To be completed |  | 13 | AUGUST
T-446-0364 | PS5-31-IK-4646D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone D | 3 | In progress |  | 18 | NOVEMBER
T-283-0365 | PS5-47-IK-6013A | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone B | 1.1 | In progress |  | 38 | SEPTEMBER
T-526-0366 | PS5-40-OB-2307A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone G | 6 | To be completed |  | 30 | AUGUST
T-271-0367 | PS5-79-IK-4264C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-07-19 | PS5-01-08 | PS5 - Milestone C | 2 | Closed | 10 | 28 | JULY
T-484-0368 | PS5-29-UR-2247B | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone E | 4 | On hold |  | 15 | NOVEMBER
T-081-0369 | PS5-09-OB-8603D | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-05-24 | PS5-04-04 | PS5 - Milestone D | 3 | Closed | 27 | 5 | MAY
T-556-0370 | PS5-44-UR-4643C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-07-14 | PS5-08-02 | PS5 - Milestone A | 1 | Closed | 35 | 9 | JULY
T-774-0371 | PS5-98-UR-3565A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone F | 5 | To be completed |  | 36 | DECEMBER
T-006-0372 | PS5-16-UR-7833C | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-03-04 | PS5-12-01 | PS5 - Milestone C | 2 | Closed | 6 | 24 | MARCH
T-058-0373 | PS5-32-UR-6986A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone D | 3 | To be completed |  | 35 | SEPTEMBER
T-366-0374 | PS5-33-UR-5358A | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-05-02 | PS5-60-07 | PS5 - Milestone C | 2 | Closed | 26 | 37 | MAY
T-852-0375 | PS5-17-OB-9443B | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-02-10 | PS5-06-02 | PS5 - Milestone D | 3 | Closed | 7 | 21 | FEBRUARY
T-502-0376 | PS5-22-OB-1972C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | To be completed |  | 22 | DECEMBER
T-033-0377 | PS5-26-IK-6841B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone D | 3 | To be completed |  | 36 | AUGUST
T-389-0378 | PS5-01-OB-3213A | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-05-25 | PS5-60-07 | PS5 - Milestone F | 5 | Closed | 7 | 22 | MAY
T-367-0379 | PS5-17-IK-1077B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone B | 1.1 | To be completed |  | 27 | SEPTEMBER
T-431-0380 | PS5-72-IK-1840A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone A | 1 | In progress |  | 31 | NOVEMBER
T-349-0381 | PS5-32-OB-7315D | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | To be completed |  | 36 | OCTOBER
T-045-0382 | PS5-67-IK-4083A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone A | 1 | On hold |  | 33 | DECEMBER
T-747-0383 | PS5-63-UR-8365D | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | To be completed |  | 41 | OCTOBER
T-971-0384 | PS5-58-UR-7306A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone H | 7 | To be completed |  | 46 | NOVEMBER
T-832-0385 | PS5-15-OB-6140B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone A | 1 | In progress |  | 17 | AUGUST
T-399-0386 | PS5-41-OB-3966A | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-11-15 | PS5-82-02 | PS5 - Milestone C | 2 | Closed | 8 | 11 | NOVEMBER
T-338-0387 | PS5-62-UR-9998D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone I | 8 | In progress |  | 13 | NOVEMBER
T-903-0388 | PS5-52-OB-9680B | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-11-06 | PS5-05-02 | PS5 - Milestone H | 7 | Closed | 26 | 47 | NOVEMBER
T-923-0389 | PS5-54-UR-3031C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-12-26 | PS5-13-01 | PS5 - Milestone D | 3 | Closed | 29 | 35 | DECEMBER
T-005-0390 | PS5-01-OB-5452A | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-05-18 | PS5-99-02 | PS5 - Milestone B | 1.1 | Closed | 30 | 6 | MAY
T-601-0391 | PS5-53-UR-3891C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-01-15 | PS5-08-01 | PS5 - Milestone B | 1.1 | Closed | 25 | 23 | JANUARY
T-120-0392 | PS5-83-OB-4193D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone D | 3 | To be completed |  | 24 | DECEMBER
T-195-0393 | PS5-76-UR-6809C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone F | 5 | On hold |  | 31 | NOVEMBER
T-720-0394 | PS5-03-IK-2003D | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | In progress |  | 28 | AUGUST
T-363-0395 | PS5-19-OB-1009B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone E | 4 | To be completed |  | 32 | NOVEMBER
T-716-0396 | PS5-59-UR-1385C | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone H | 7 | To be completed |  | 39 | NOVEMBER
T-255-0397 | PS5-10-OB-4803C | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | In progress |  | 23 | AUGUST
T-672-0398 | PS5-06-UR-8140C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone H | 7 | In progress |  | 10 | NOVEMBER
T-098-0399 | PS5-18-UR-1908D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone A | 1 | In progress |  | 28 | OCTOBER
T-163-0400 | PS5-81-OB-7748D | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone G | 6 | To be completed |  | 25 | SEPTEMBER
T-993-0401 | PS5-67-OB-6454B | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone I | 8 | On hold |  | 18 | OCTOBER
T-325-0402 | PS5-16-OB-8216A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | In progress |  | 46 | OCTOBER
T-507-0403 | PS5-35-IK-2517A | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone A | 1 | On hold |  | 47 | AUGUST
T-038-0404 | PS5-50-UR-6484C | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | In progress |  | 9 | SEPTEMBER
T-071-0405 | PS5-23-OB-4242B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-08-17 | PS5-63-01 | PS5 - Milestone F | 5 | Closed | 25 | 37 | AUGUST
T-286-0406 | PS5-88-OB-2260B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-04-09 | PS5-01-09 | PS5 - Milestone H | 7 | Closed | 31 | 25 | APRIL
T-112-0407 | PS5-35-OB-3749C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-08-02 | PS5-04-04 | PS5 - Milestone C | 2 | Closed | 43 | 39 | AUGUST
T-918-0408 | PS5-52-OB-8987D | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-04-15 | PS5-01-06 | PS5 - Milestone I | 8 | Closed | 4 | 4 | APRIL
T-277-0409 | PS5-03-UR-4549B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-06-28 | PS5-10-06 | PS5 - Milestone I | 8 | Closed | 25 | 6 | JUNE
T-607-0410 | PS5-05-UR-2731D | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | On hold |  | 10 | DECEMBER
T-852-0411 | PS5-55-IK-3362C | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | To be completed |  | 47 | SEPTEMBER
T-079-0412 | PS5-23-OB-1073D | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone G | 6 | To be completed |  | 19 | DECEMBER
T-365-0413 | PS5-63-OB-4458A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone E | 4 | In progress |  | 43 | AUGUST
T-280-0414 | PS5-46-OB-9656B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | On hold |  | 40 | OCTOBER
T-263-0415 | PS5-13-UR-7770A | CQP04 - Hydrotest | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-08-05 | PS5-06-02 | PS5 - Milestone C | 2 | Closed | 40 | 27 | AUGUST
T-207-0416 | PS5-74-UR-6116D | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-09-24 | PS5-99-01 | PS5 - Milestone E | 4 | Closed | 18 | 27 | SEPTEMBER
T-179-0417 | PS5-02-OB-7276B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-10-18 | PS5-09-04 | PS5 - Milestone C | 2 | Closed | 15 | 27 | OCTOBER
T-828-0418 | PS5-23-OB-6578A | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-04-14 | PS5-04-03 | PS5 - Milestone H | 7 | Closed | 38 | 17 | APRIL
T-884-0419 | PS5-59-OB-2321C | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-03-26 | PS5-11-02 | PS5 - Milestone H | 7 | Closed | 12 | 40 | MARCH
T-287-0420 | PS5-13-IK-5042C | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-05-15 | PS5-12-02 | PS5 - Milestone A | 1 | Closed | 17 | 15 | MAY
T-435-0421 | PS5-82-OB-5210B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-08-28 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 12 | 7 | AUGUST
T-180-0422 | PS5-51-OB-2391C | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone A | 1 | To be completed |  | 34 | SEPTEMBER
T-273-0423 | PS5-17-IK-9069B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone D | 3 | To be completed |  | 33 | DECEMBER
T-098-0424 | PS5-13-IK-9623B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-03-04 | PS5-09-01 | PS5 - Milestone F | 5 | Closed | 18 | 28 | MARCH
T-476-0425 | PS5-43-UR-7037C | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone G | 6 | In progress |  | 23 | SEPTEMBER
T-136-0426 | PS5-83-OB-3461D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-11-19 | PS5-82-02 | PS5 - Milestone A | 1 | Closed | 23 | 30 | NOVEMBER
T-782-0427 | PS5-73-OB-4526C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone H | 7 | On hold |  | 9 | NOVEMBER
T-180-0428 | PS5-30-IK-1846A | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | On hold |  | 17 | AUGUST
T-586-0429 | PS5-11-OB-3518D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | In progress |  | 5 | OCTOBER
T-613-0430 | PS5-08-OB-3985B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone A | 1 | To be completed |  | 24 | DECEMBER
T-650-0431 | PS5-90-OB-9376A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-10-23 | PS5-03-02 | PS5 - Milestone E | 4 | Closed | 44 | 26 | OCTOBER
T-360-0432 | PS5-91-UR-5872D | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-11-21 | PS5-06-01 | PS5 - Milestone E | 4 | Closed | 6 | 26 | NOVEMBER
T-213-0433 | PS5-98-UR-6366A | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | In progress |  | 27 | SEPTEMBER
T-052-0434 | PS5-27-OB-1148B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone H | 7 | To be completed |  | 32 | OCTOBER
T-965-0435 | PS5-85-OB-8886D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone A | 1 | On hold |  | 29 | DECEMBER
T-789-0436 | PS5-30-IK-7390B | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone E | 4 | To be completed |  | 19 | AUGUST
T-547-0437 | PS5-58-OB-9021A | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-10-12 | PS5-07-02 | PS5 - Milestone C | 2 | Closed | 34 | 39 | OCTOBER
T-277-0438 | PS5-93-OB-2179A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-11-20 | PS5-01-08 | PS5 - Milestone H | 7 | Closed | 20 | 43 | NOVEMBER
T-717-0439 | PS5-39-IK-4653C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-03-28 | PS5-60-10 | PS5 - Milestone D | 3 | Closed | 41 | 24 | MARCH
T-731-0440 | PS5-16-OB-6876C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone G | 6 | To be completed |  | 7 | NOVEMBER
T-769-0441 | PS5-81-UR-7809B | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-02-07 | PS5-82-01 | PS5 - Milestone A | 1 | Closed | 44 | 14 | FEBRUARY
T-094-0442 | PS5-24-OB-2574B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone H | 7 | In progress |  | 15 | OCTOBER
T-403-0443 | PS5-66-UR-8716D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-12-27 | PS5-01-02 | PS5 - Milestone A | 1 | Closed | 14 | 8 | DECEMBER
T-541-0444 | PS5-35-UR-7134A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone I | 8 | To be completed |  | 30 | NOVEMBER
T-907-0445 | PS5-17-IK-9032C | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone G | 6 | In progress |  | 31 | SEPTEMBER
T-559-0446 | PS5-57-OB-2701B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-10-08 | PS5-01-01 | PS5 - Milestone C | 2 | Closed | 26 | 42 | OCTOBER
T-331-0447 | PS5-05-OB-3472D | CQS03 - Deluge System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | In progress |  | 4 | OCTOBER
T-768-0448 | PS5-87-IK-9895A | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-06-13 | PS5-12-01 | PS5 - Milestone A | 1 | Closed | 37 | 4 | JUNE
T-514-0449 | PS5-56-OB-4475B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-08-20 | PS5-01-01 | PS5 - Milestone I | 8 | Closed | 39 | 31 | AUGUST
T-456-0450 | PS5-36-OB-4749A | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone G | 6 | In progress |  | 13 | SEPTEMBER
T-300-0451 | PS5-27-OB-5012B | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | To be completed |  | 24 | AUGUST
T-642-0452 | PS5-62-OB-3684C | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | In progress |  | 41 | NOVEMBER
T-772-0453 | PS5-39-OB-4798B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone D | 3 | In progress |  | 43 | DECEMBER
T-253-0454 | PS5-15-IK-5299B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-11-28 | PS5-11-03 | PS5 - Milestone I | 8 | Closed | 42 | 28 | NOVEMBER
T-287-0455 | PS5-31-OB-3585A | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone D | 3 | In progress |  | 21 | OCTOBER
T-385-0456 | PS5-64-UR-3078C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone F | 5 | On hold |  | 6 | DECEMBER
T-332-0457 | PS5-71-IK-5659A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | To be completed |  | 8 | AUGUST
T-255-0458 | PS5-08-OB-6508A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone E | 4 | To be completed |  | 16 | AUGUST
T-611-0459 | PS5-52-OB-9607B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-10-13 | PS5-82-02 | PS5 - Milestone F | 5 | Closed | 44 | 24 | OCTOBER
T-605-0460 | PS5-61-OB-4596C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-04-15 | PS5-99-03 | PS5 - Milestone I | 8 | Closed | 19 | 31 | APRIL
T-014-0461 | PS5-97-OB-5789B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone A | 1 | In progress |  | 6 | DECEMBER
T-709-0462 | PS5-19-OB-6827A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | On hold |  | 26 | AUGUST
T-072-0463 | PS5-59-OB-6234A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone D | 3 | In progress |  | 32 | OCTOBER
T-509-0464 | PS5-43-IK-4284C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone F | 5 | To be completed |  | 27 | AUGUST
T-790-0465 | PS5-59-OB-6721A | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-17 | PS5-60-07 | PS5 - Milestone F | 5 | Closed | 6 | 30 | JULY
T-803-0466 | PS5-04-UR-8921D | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-06-13 | PS5-63-01 | PS5 - Milestone C | 2 | Closed | 25 | 18 | JUNE
T-108-0467 | PS5-62-UR-1041D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone B | 1.1 | On hold |  | 16 | OCTOBER
T-436-0468 | PS5-57-UR-4259C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone I | 8 | To be completed |  | 46 | DECEMBER
T-300-0469 | PS5-13-OB-6217D | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone G | 6 | In progress |  | 46 | NOVEMBER
T-646-0470 | PS5-70-IK-6330C | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone C | 2 | On hold |  | 25 | SEPTEMBER
T-966-0471 | PS5-15-OB-5690A | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-01-17 | PS5-99-03 | PS5 - Milestone E | 4 | Closed | 33 | 23 | JANUARY
T-647-0472 | PS5-49-OB-2463A | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | To be completed |  | 21 | AUGUST
T-136-0473 | PS5-81-OB-1378B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone A | 1 | To be completed |  | 43 | DECEMBER
T-810-0474 | PS5-84-OB-4459C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-14 | PS5-60-04 | PS5 - Milestone E | 4 | Closed | 35 | 12 | JUNE
T-360-0475 | PS5-09-IK-4014B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-08-02 | PS5-10-03 | PS5 - Milestone F | 5 | Closed | 43 | 44 | AUGUST
T-282-0476 | PS5-90-OB-9123C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone D | 3 | To be completed |  | 10 | OCTOBER
T-078-0477 | PS5-64-OB-9209D | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-10-19 | PS5-01-02 | PS5 - Milestone G | 6 | Closed | 30 | 38 | OCTOBER
T-101-0478 | PS5-47-OB-2657B | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-07-20 | PS5-07-03 | PS5 - Milestone A | 1 | Closed | 30 | 28 | JULY
T-415-0479 | PS5-76-OB-7466A | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone H | 7 | To be completed |  | 41 | NOVEMBER
T-480-0480 | PS5-30-UR-2467D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone E | 4 | To be completed |  | 10 | DECEMBER
T-343-0481 | PS5-05-IK-5300D | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone E | 4 | In progress |  | 31 | OCTOBER
T-266-0482 | PS5-12-OB-4591D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-10-26 | PS5-10-01 | PS5 - Milestone F | 5 | Closed | 39 | 6 | OCTOBER
T-255-0483 | PS5-77-OB-6329C | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone H | 7 | To be completed |  | 15 | DECEMBER
T-818-0484 | PS5-22-OB-3031A | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone A | 1 | To be completed |  | 13 | NOVEMBER
T-215-0485 | PS5-69-IK-3013D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone F | 5 | To be completed |  | 8 | NOVEMBER
T-379-0486 | PS5-52-OB-9364D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-03-28 | PS5-12-01 | PS5 - Milestone E | 4 | Closed | 37 | 15 | MARCH
T-675-0487 | PS5-80-UR-9007C | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | To be completed |  | 19 | SEPTEMBER
T-940-0488 | PS5-93-OB-8192B | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone H | 7 | In progress |  | 25 | NOVEMBER
T-299-0489 | PS5-35-UR-2194A | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | On hold |  | 44 | DECEMBER
T-922-0490 | PS5-57-UR-4059A | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-11-11 | PS5-05-01 | PS5 - Milestone G | 6 | Closed | 11 | 17 | NOVEMBER
T-207-0491 | PS5-14-IK-2570C | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone H | 7 | To be completed |  | 29 | AUGUST
T-544-0492 | PS5-89-IK-4177A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone C | 2 | In progress |  | 46 | AUGUST
T-025-0493 | PS5-87-OB-7984A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | In progress |  | 15 | AUGUST
T-321-0494 | PS5-64-UR-3369D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone F | 5 | To be completed |  | 10 | NOVEMBER
T-082-0495 | PS5-42-OB-9133D | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone B | 1.1 | In progress |  | 12 | AUGUST
T-222-0496 | PS5-54-OB-7411C | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone H | 7 | To be completed |  | 14 | NOVEMBER
T-948-0497 | PS5-36-UR-1293A | CQE01 - HV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | On hold |  | 13 | AUGUST
T-507-0498 | PS5-37-IK-8354C | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | To be completed |  | 37 | AUGUST
T-180-0499 | PS5-18-OB-3861D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone D | 3 | In progress |  | 6 | OCTOBER
T-659-0500 | PS5-11-OB-6100B | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-08-25 | PS5-10-02 | PS5 - Milestone D | 3 | Closed | 38 | 7 | AUGUST
T-865-0501 | PS5-45-IK-6988C | CQX04 - Painting & Coating | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-07-14 | PS5-82-02 | PS5 - Milestone C | 2 | Closed | 25 | 38 | JULY
T-121-0502 | PS5-57-UR-2556C | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone F | 5 | To be completed |  | 18 | AUGUST
T-433-0503 | PS5-34-OB-2892A | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | To be completed |  | 5 | OCTOBER
T-706-0504 | PS5-73-UR-2265D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone D | 3 | To be completed |  | 12 | SEPTEMBER
T-110-0505 | PS5-01-OB-8788A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone D | 3 | To be completed |  | 42 | AUGUST
T-920-0506 | PS5-91-OB-1093D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone H | 7 | To be completed |  | 25 | AUGUST
T-486-0507 | PS5-56-UR-6922A | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone D | 3 | To be completed |  | 45 | OCTOBER
T-337-0508 | PS5-96-OB-1355A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-08-04 | PS5-04-04 | PS5 - Milestone C | 2 | Closed | 16 | 27 | AUGUST
T-348-0509 | PS5-25-UR-3105C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone H | 7 | To be completed |  | 43 | OCTOBER
T-838-0510 | PS5-94-UR-2616B | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone C | 2 | On hold |  | 11 | DECEMBER
T-911-0511 | PS5-40-OB-8202A | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-03-10 | PS5-01-09 | PS5 - Milestone E | 4 | Closed | 17 | 32 | MARCH
T-929-0512 | PS5-41-OB-9892B | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-11-14 | PS5-82-02 | PS5 - Milestone E | 4 | Closed | 4 | 16 | NOVEMBER
T-214-0513 | PS5-84-OB-2857A | CQM01 - Pump Installation | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone B | 1.1 | On hold |  | 17 | NOVEMBER
T-980-0514 | PS5-55-IK-1200A | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone I | 8 | In progress |  | 46 | OCTOBER
T-128-0515 | PS5-54-IK-4371B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-09-27 | PS5-10-02 | PS5 - Milestone C | 2 | Closed | 23 | 46 | SEPTEMBER
T-152-0516 | PS5-17-UR-2023C | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone E | 4 | In progress |  | 22 | NOVEMBER
T-645-0517 | PS5-90-IK-3438A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | On hold |  | 31 | AUGUST
T-782-0518 | PS5-30-OB-8096D | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-05-14 | PS5-10-05 | PS5 - Milestone C | 2 | Closed | 24 | 4 | MAY
T-763-0519 | PS5-31-OB-1194D | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone F | 5 | To be completed |  | 47 | AUGUST
T-573-0520 | PS5-99-UR-1224B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-08-24 | PS5-82-07 | PS5 - Milestone I | 8 | Closed | 24 | 44 | AUGUST
T-483-0521 | PS5-32-OB-8828A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-04-09 | PS5-10-01 | PS5 - Milestone H | 7 | Closed | 36 | 27 | APRIL
T-488-0522 | PS5-03-OB-2893C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-06-02 | PS5-12-02 | PS5 - Milestone D | 3 | Closed | 39 | 40 | JUNE
T-616-0523 | PS5-45-OB-3509C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone A | 1 | In progress |  | 32 | OCTOBER
T-095-0524 | PS5-77-IK-5413A | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone G | 6 | To be completed |  | 44 | OCTOBER
T-094-0525 | PS5-98-OB-3459D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-09-18 | PS5-05-03 | PS5 - Milestone H | 7 | Closed | 33 | 41 | SEPTEMBER
T-402-0526 | PS5-63-OB-3244B | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-04-08 | PS5-04-02 | PS5 - Milestone I | 8 | Closed | 17 | 37 | APRIL
T-813-0527 | PS5-23-OB-9102A | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone B | 1.1 | To be completed |  | 45 | OCTOBER
T-038-0528 | PS5-57-UR-8883B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone H | 7 | To be completed |  | 36 | SEPTEMBER
T-370-0529 | PS5-89-OB-9099C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone E | 4 | In progress |  | 42 | OCTOBER
T-435-0530 | PS5-88-OB-3091C | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | In progress |  | 24 | NOVEMBER
T-384-0531 | PS5-98-OB-3918D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-02-01 | PS5-03-02 | PS5 - Milestone B | 1.1 | Closed | 40 | 21 | FEBRUARY
T-574-0532 | PS5-62-UR-9580D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone C | 2 | To be completed |  | 34 | SEPTEMBER
T-984-0533 | PS5-67-UR-8859C | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-04-16 | PS5-10-03 | PS5 - Milestone D | 3 | Closed | 11 | 31 | APRIL
T-079-0534 | PS5-58-IK-5422C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-08-03 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 19 | 38 | AUGUST
T-815-0535 | PS5-27-OB-2002C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone H | 7 | On hold |  | 29 | DECEMBER
T-943-0536 | PS5-46-IK-9318C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone F | 5 | In progress |  | 20 | AUGUST
T-828-0537 | PS5-18-IK-9063B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-10-21 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 14 | 25 | OCTOBER
T-224-0538 | PS5-96-OB-8311D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone D | 3 | To be completed |  | 30 | OCTOBER
T-716-0539 | PS5-12-OB-6445B | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-02-04 | PS5-01-08 | PS5 - Milestone G | 6 | Closed | 42 | 19 | FEBRUARY
T-011-0540 | PS5-28-OB-4460A | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone B | 1.1 | To be completed |  | 38 | NOVEMBER
T-403-0541 | PS5-24-IK-8352D | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone A | 1 | On hold |  | 23 | AUGUST
T-346-0542 | PS5-92-UR-7301D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone H | 7 | To be completed |  | 43 | NOVEMBER
T-324-0543 | PS5-90-IK-1183D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone A | 1 | On hold |  | 40 | NOVEMBER
T-037-0544 | PS5-41-IK-1909D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone E | 4 | In progress |  | 9 | NOVEMBER
T-749-0545 | PS5-51-OB-6176C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-01-19 | PS5-10-06 | PS5 - Milestone G | 6 | Closed | 19 | 6 | JANUARY
T-399-0546 | PS5-81-OB-1313C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-05-28 | PS5-02-01 | PS5 - Milestone D | 3 | Closed | 21 | 31 | MAY
T-302-0547 | PS5-92-OB-5175D | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | To be completed |  | 33 | AUGUST
T-919-0548 | PS5-71-UR-5620B | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-03-12 | PS5-07-02 | PS5 - Milestone E | 4 | Closed | 32 | 31 | MARCH
T-686-0549 | PS5-14-OB-6781A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone D | 3 | To be completed |  | 7 | AUGUST
T-797-0550 | PS5-64-IK-2165C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone F | 5 | To be completed |  | 34 | OCTOBER
T-414-0551 | PS5-61-OB-3656B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-03-23 | PS5-60-04 | PS5 - Milestone D | 3 | Closed | 10 | 30 | MARCH
T-702-0552 | PS5-40-OB-9884A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-06-25 | PS5-10-02 | PS5 - Milestone E | 4 | Closed | 8 | 9 | JUNE
T-769-0553 | PS5-92-IK-2512C | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | On hold |  | 23 | DECEMBER
T-243-0554 | PS5-75-UR-5738C | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-06-28 | PS5-01-03 | PS5 - Milestone A | 1 | Closed | 36 | 35 | JUNE
T-466-0555 | PS5-68-OB-6269A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone D | 3 | In progress |  | 26 | OCTOBER
T-445-0556 | PS5-55-OB-1939C | CQE04 - Transformer | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | To be completed |  | 11 | OCTOBER
T-462-0557 | PS5-56-OB-1253C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-06-19 | PS5-12-02 | PS5 - Milestone C | 2 | Closed | 32 | 24 | JUNE
T-680-0558 | PS5-39-IK-8296B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-12-19 | PS5-01-04 | PS5 - Milestone F | 5 | Closed | 11 | 21 | DECEMBER
T-371-0559 | PS5-48-IK-5195C | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone H | 7 | On hold |  | 43 | OCTOBER
T-347-0560 | PS5-94-IK-8756B | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone F | 5 | In progress |  | 47 | OCTOBER
T-977-0561 | PS5-28-OB-8361A | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-01-23 | PS5-07-01 | PS5 - Milestone D | 3 | Closed | 34 | 12 | JANUARY
T-756-0562 | PS5-83-OB-7604A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone G | 6 | In progress |  | 31 | AUGUST
T-711-0563 | PS5-47-OB-1927D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-05-18 | PS5-06-01 | PS5 - Milestone H | 7 | Closed | 29 | 10 | MAY
T-433-0564 | PS5-37-OB-2830B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone D | 3 | In progress |  | 31 | SEPTEMBER
T-078-0565 | PS5-45-OB-8805C | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | In progress |  | 36 | AUGUST
T-847-0566 | PS5-95-OB-3317A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-09-03 | PS5-07-01 | PS5 - Milestone A | 1 | Closed | 23 | 18 | SEPTEMBER
T-932-0567 | PS5-79-OB-2933C | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-09-01 | PS5-62-01 | PS5 - Milestone C | 2 | Closed | 23 | 30 | SEPTEMBER
T-448-0568 | PS5-46-IK-2571D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | On hold |  | 5 | DECEMBER
T-225-0569 | PS5-74-IK-4094C | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-07-22 | PS5-07-04 | PS5 - Milestone A | 1 | Closed | 34 | 26 | JULY
T-648-0570 | PS5-42-OB-4991A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone I | 8 | To be completed |  | 15 | NOVEMBER
T-050-0571 | PS5-43-IK-4241A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone C | 2 | On hold |  | 42 | AUGUST
T-606-0572 | PS5-31-IK-2298D | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone E | 4 | To be completed |  | 31 | NOVEMBER
T-021-0573 | PS5-57-OB-3709C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone I | 8 | In progress |  | 28 | DECEMBER
T-021-0574 | PS5-37-OB-5323A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-04-03 | PS5-06-01 | PS5 - Milestone E | 4 | Closed | 33 | 10 | APRIL
T-451-0575 | PS5-68-OB-5769C | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-08-02 | PS5-04-02 | PS5 - Milestone E | 4 | Closed | 26 | 24 | AUGUST
T-381-0576 | PS5-51-OB-4690D | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone D | 3 | To be completed |  | 18 | AUGUST
T-371-0577 | PS5-54-OB-9186D | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone A | 1 | On hold |  | 10 | DECEMBER
T-679-0578 | PS5-38-UR-7778A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | To be completed |  | 39 | AUGUST
T-279-0579 | PS5-89-OB-7600A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone E | 4 | On hold |  | 24 | SEPTEMBER
T-852-0580 | PS5-72-OB-1533D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-05-27 | PS5-09-03 | PS5 - Milestone D | 3 | Closed | 9 | 24 | MAY
T-418-0581 | PS5-77-UR-5489D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone B | 1.1 | On hold |  | 35 | AUGUST
T-327-0582 | PS5-61-IK-1134D | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-09-27 | PS5-62-01 | PS5 - Milestone G | 6 | Closed | 23 | 29 | SEPTEMBER
T-903-0583 | PS5-14-UR-9169D | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-02-25 | PS5-01-08 | PS5 - Milestone G | 6 | Closed | 11 | 23 | FEBRUARY
T-935-0584 | PS5-63-OB-3791B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone A | 1 | On hold |  | 28 | DECEMBER
T-769-0585 | PS5-52-OB-1307C | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-05-09 | PS5-01-06 | PS5 - Milestone E | 4 | Closed | 26 | 6 | MAY
T-973-0586 | PS5-57-OB-5805A | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone B | 1.1 | In progress |  | 40 | SEPTEMBER
T-442-0587 | PS5-69-OB-5336A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | In progress |  | 34 | NOVEMBER
T-805-0588 | PS5-11-IK-1618A | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone H | 7 | In progress |  | 4 | OCTOBER
T-522-0589 | PS5-37-IK-6940B | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-01-15 | PS5-63-04 | PS5 - Milestone F | 5 | Closed | 44 | 31 | JANUARY
T-569-0590 | PS5-98-UR-5905C | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | In progress |  | 17 | DECEMBER
T-435-0591 | PS5-60-IK-1891D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone B | 1.1 | To be completed |  | 10 | DECEMBER
T-095-0592 | PS5-23-UR-6607D | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-05-23 | PS5-01-06 | PS5 - Milestone F | 5 | Closed | 7 | 38 | MAY
T-873-0593 | PS5-52-UR-1774C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-03-12 | PS5-61-02 | PS5 - Milestone B | 1.1 | Closed | 19 | 33 | MARCH
T-774-0594 | PS5-10-OB-7772A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-06-04 | PS5-07-03 | PS5 - Milestone F | 5 | Closed | 26 | 38 | JUNE
T-951-0595 | PS5-19-OB-3427A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone G | 6 | To be completed |  | 27 | NOVEMBER
T-845-0596 | PS5-84-OB-2587D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone G | 6 | To be completed |  | 16 | DECEMBER
T-297-0597 | PS5-31-UR-1447D | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-07-11 | PS5-03-23 | PS5 - Milestone A | 1 | Closed | 7 | 18 | JULY
T-384-0598 | PS5-80-OB-5663B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-01-13 | PS5-61-02 | PS5 - Milestone A | 1 | Closed | 7 | 44 | JANUARY
T-872-0599 | PS5-59-OB-5307B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone A | 1 | In progress |  | 4 | DECEMBER
T-927-0600 | PS5-70-OB-9879B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-08-11 | PS5-10-06 | PS5 - Milestone A | 1 | Closed | 5 | 28 | AUGUST
T-016-0601 | PS5-48-UR-9785B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-03-12 | PS5-05-02 | PS5 - Milestone I | 8 | Closed | 27 | 7 | MARCH
T-016-0602 | PS5-93-IK-3000A | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | To be completed |  | 48 | NOVEMBER
T-507-0603 | PS5-34-OB-5503C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone B | 1.1 | To be completed |  | 25 | AUGUST
T-234-0604 | PS5-66-OB-4327A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone D | 3 | In progress |  | 47 | NOVEMBER
T-452-0605 | PS5-11-UR-5942D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone D | 3 | To be completed |  | 17 | NOVEMBER
T-595-0606 | PS5-37-UR-8056B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | To be completed |  | 26 | DECEMBER
T-035-0607 | PS5-97-IK-2783D | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-06-14 | PS5-02-02 | PS5 - Milestone E | 4 | Closed | 18 | 45 | JUNE
T-206-0608 | PS5-02-IK-3550D | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone I | 8 | In progress |  | 18 | SEPTEMBER
T-267-0609 | PS5-01-OB-6084A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-01-20 | PS5-03-02 | PS5 - Milestone G | 6 | Closed | 31 | 28 | JANUARY
T-491-0610 | PS5-94-OB-7989A | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-07-02 | PS5-10-03 | PS5 - Milestone H | 7 | Closed | 26 | 17 | JULY
T-098-0611 | PS5-78-UR-5826B | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-04-07 | PS5-06-02 | PS5 - Milestone I | 8 | Closed | 47 | 33 | APRIL
T-959-0612 | PS5-88-UR-9281C | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | To be completed |  | 31 | SEPTEMBER
T-501-0613 | PS5-76-OB-6104C | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-09-22 | PS5-01-02 | PS5 - Milestone A | 1 | Closed | 14 | 38 | SEPTEMBER
T-649-0614 | PS5-37-OB-8476D | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone F | 5 | On hold |  | 17 | NOVEMBER
T-266-0615 | PS5-68-OB-1729D | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-09-24 | PS5-01-06 | PS5 - Milestone I | 8 | Closed | 21 | 38 | SEPTEMBER
T-064-0616 | PS5-24-OB-4547A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone E | 4 | On hold |  | 48 | NOVEMBER
T-745-0617 | PS5-72-OB-4467B | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone G | 6 | To be completed |  | 45 | OCTOBER
T-808-0618 | PS5-41-OB-9855D | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone H | 7 | To be completed |  | 44 | AUGUST
T-279-0619 | PS5-62-IK-5129A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-08-22 | PS5-06-03 | PS5 - Milestone B | 1.1 | Closed | 35 | 38 | AUGUST
T-543-0620 | PS5-40-OB-8217C | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone D | 3 | In progress |  | 29 | NOVEMBER
T-632-0621 | PS5-90-OB-9372C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone B | 1.1 | In progress |  | 25 | NOVEMBER
T-589-0622 | PS5-78-OB-8589A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | To be completed |  | 30 | NOVEMBER
T-532-0623 | PS5-21-OB-4823C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-06-25 | PS5-09-03 | PS5 - Milestone A | 1 | Closed | 37 | 17 | JUNE
T-667-0624 | PS5-65-OB-4059C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-03-05 | PS5-04-02 | PS5 - Milestone D | 3 | Closed | 9 | 7 | MARCH
T-670-0625 | PS5-11-IK-3636B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone G | 6 | In progress |  | 44 | DECEMBER
T-654-0626 | PS5-05-OB-2236B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone G | 6 | To be completed |  | 40 | NOVEMBER
T-350-0627 | PS5-40-UR-1634A | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | To be completed |  | 37 | DECEMBER
T-351-0628 | PS5-86-OB-4235A | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-01-21 | PS5-60-10 | PS5 - Milestone C | 2 | Closed | 16 | 14 | JANUARY
T-645-0629 | PS5-69-OB-2076D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-10-04 | PS5-61-01 | PS5 - Milestone G | 6 | Closed | 9 | 17 | OCTOBER
T-433-0630 | PS5-33-UR-6080D | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone C | 2 | To be completed |  | 46 | OCTOBER
T-514-0631 | PS5-63-IK-2303A | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-01-28 | PS5-11-02 | PS5 - Milestone C | 2 | Closed | 14 | 36 | JANUARY
T-580-0632 | PS5-95-UR-1972B | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-06-12 | PS5-12-01 | PS5 - Milestone D | 3 | Closed | 26 | 24 | JUNE
T-645-0633 | PS5-18-OB-8503C | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-07-09 | PS5-05-02 | PS5 - Milestone D | 3 | Closed | 22 | 18 | JULY
T-880-0634 | PS5-61-OB-3121B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-08-23 | PS5-04-03 | PS5 - Milestone E | 4 | Closed | 29 | 21 | AUGUST
T-645-0635 | PS5-85-OB-1356A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-02-19 | PS5-04-04 | PS5 - Milestone I | 8 | Closed | 39 | 22 | FEBRUARY
T-134-0636 | PS5-65-UR-7941B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-02-13 | PS5-05-03 | PS5 - Milestone I | 8 | Closed | 42 | 34 | FEBRUARY
T-373-0637 | PS5-99-IK-4745B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-06-21 | PS5-06-01 | PS5 - Milestone E | 4 | Closed | 28 | 26 | JUNE
T-529-0638 | PS5-99-OB-7789D | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone D | 3 | To be completed |  | 19 | AUGUST
T-217-0639 | PS5-89-OB-3556C | CQP04 - Hydrotest | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone D | 3 | On hold |  | 10 | OCTOBER
T-271-0640 | PS5-99-OB-9277C | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-11-17 | PS5-06-01 | PS5 - Milestone G | 6 | Closed | 44 | 33 | NOVEMBER
T-958-0641 | PS5-17-OB-4560A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-01-20 | PS5-99-01 | PS5 - Milestone A | 1 | Closed | 20 | 46 | JANUARY
T-759-0642 | PS5-63-OB-8885C | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone G | 6 | In progress |  | 45 | DECEMBER
T-401-0643 | PS5-73-OB-9506B | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | In progress |  | 10 | SEPTEMBER
T-763-0644 | PS5-78-OB-2648B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | On hold |  | 10 | DECEMBER
T-200-0645 | PS5-27-OB-8306C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone C | 2 | On hold |  | 8 | AUGUST
T-391-0646 | PS5-47-OB-3334A | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-10-27 | PS5-10-03 | PS5 - Milestone H | 7 | Closed | 5 | 6 | OCTOBER
T-789-0647 | PS5-01-IK-2976C | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | In progress |  | 18 | DECEMBER
T-177-0648 | PS5-94-OB-3748C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-06-07 | PS5-61-02 | PS5 - Milestone D | 3 | Closed | 35 | 22 | JUNE
T-767-0649 | PS5-45-UR-5262D | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone C | 2 | On hold |  | 35 | OCTOBER
T-672-0650 | PS5-78-IK-2884C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone H | 7 | In progress |  | 46 | OCTOBER
T-460-0651 | PS5-86-OB-6812B | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-09-09 | PS5-10-05 | PS5 - Milestone G | 6 | Closed | 46 | 44 | SEPTEMBER
T-963-0652 | PS5-25-OB-9704B | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone A | 1 | To be completed |  | 5 | OCTOBER
T-748-0653 | PS5-59-OB-1156D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | To be completed |  | 7 | NOVEMBER
T-390-0654 | PS5-89-IK-8560B | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-03-13 | PS5-08-01 | PS5 - Milestone E | 4 | Closed | 29 | 27 | MARCH
T-446-0655 | PS5-67-IK-1344D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-05-03 | PS5-06-02 | PS5 - Milestone C | 2 | Closed | 13 | 19 | MAY
T-860-0656 | PS5-13-OB-6479A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-02-10 | PS5-01-07 | PS5 - Milestone E | 4 | Closed | 33 | 18 | FEBRUARY
T-155-0657 | PS5-75-UR-2022D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | To be completed |  | 28 | NOVEMBER
T-058-0658 | PS5-29-OB-8530A | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone A | 1 | To be completed |  | 21 | NOVEMBER
T-611-0659 | PS5-74-IK-7756B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-08-20 | PS5-03-23 | PS5 - Milestone H | 7 | Closed | 43 | 28 | AUGUST
T-528-0660 | PS5-86-OB-9864C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone E | 4 | In progress |  | 32 | SEPTEMBER
T-460-0661 | PS5-33-UR-4839A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone D | 3 | In progress |  | 6 | DECEMBER
T-396-0662 | PS5-58-UR-2439A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | In progress |  | 32 | AUGUST
T-963-0663 | PS5-78-OB-4931B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone A | 1 | To be completed |  | 24 | OCTOBER
T-818-0664 | PS5-29-OB-2027B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-10-14 | PS5-09-04 | PS5 - Milestone C | 2 | Closed | 8 | 19 | OCTOBER
T-615-0665 | PS5-34-OB-6687C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone A | 1 | On hold |  | 25 | OCTOBER
T-811-0666 | PS5-69-OB-1345C | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone E | 4 | In progress |  | 31 | AUGUST
T-894-0667 | PS5-93-OB-2573A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-05-28 | PS5-61-07 | PS5 - Milestone I | 8 | Closed | 47 | 13 | MAY
T-764-0668 | PS5-45-UR-5589D | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-01-18 | PS5-05-01 | PS5 - Milestone A | 1 | Closed | 43 | 45 | JANUARY
T-377-0669 | PS5-09-OB-2513B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | To be completed |  | 42 | SEPTEMBER
T-887-0670 | PS5-65-UR-3967D | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-07-09 | PS5-05-03 | PS5 - Milestone C | 2 | Closed | 40 | 6 | JULY
T-059-0671 | PS5-69-IK-6012D | CQE04 - Transformer | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone C | 2 | To be completed |  | 36 | SEPTEMBER
T-249-0672 | PS5-67-OB-2920A | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone F | 5 | To be completed |  | 25 | DECEMBER
T-828-0673 | PS5-32-UR-4355B | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-02-07 | PS5-60-10 | PS5 - Milestone E | 4 | Closed | 17 | 43 | FEBRUARY
T-288-0674 | PS5-31-IK-3371A | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone B | 1.1 | In progress |  | 26 | SEPTEMBER
T-015-0675 | PS5-54-IK-6336D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone F | 5 | To be completed |  | 6 | SEPTEMBER
T-755-0676 | PS5-45-OB-3944C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone E | 4 | In progress |  | 32 | DECEMBER
T-379-0677 | PS5-46-UR-3226B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-12-07 | PS5-61-07 | PS5 - Milestone C | 2 | Closed | 46 | 9 | DECEMBER
T-797-0678 | PS5-28-IK-2563D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone F | 5 | To be completed |  | 32 | SEPTEMBER
T-453-0679 | PS5-76-OB-1129C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-04-24 | PS5-11-02 | PS5 - Milestone G | 6 | Closed | 48 | 25 | APRIL
T-677-0680 | PS5-79-OB-6408B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone C | 2 | On hold |  | 16 | SEPTEMBER
T-015-0681 | PS5-70-UR-5597D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone E | 4 | In progress |  | 47 | NOVEMBER
T-940-0682 | PS5-94-OB-4316C | CQM01 - Pump Installation | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone G | 6 | To be completed |  | 8 | AUGUST
T-599-0683 | PS5-67-OB-1241B | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-10-05 | PS5-60-04 | PS5 - Milestone I | 8 | Closed | 36 | 27 | OCTOBER
T-937-0684 | PS5-23-IK-1566C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone A | 1 | In progress |  | 23 | OCTOBER
T-540-0685 | PS5-09-OB-1059B | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone D | 3 | To be completed |  | 15 | DECEMBER
T-270-0686 | PS5-99-IK-4431D | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-09-01 | PS5-60-10 | PS5 - Milestone A | 1 | Closed | 11 | 16 | SEPTEMBER
T-703-0687 | PS5-65-OB-5987A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-09-26 | PS5-62-01 | PS5 - Milestone H | 7 | Closed | 48 | 19 | SEPTEMBER
T-070-0688 | PS5-68-OB-5575B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | On hold |  | 48 | SEPTEMBER
T-061-0689 | PS5-17-UR-2751A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone B | 1.1 | On hold |  | 11 | OCTOBER
T-548-0690 | PS5-41-UR-1396B | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-08-28 | PS5-01-03 | PS5 - Milestone E | 4 | Closed | 20 | 11 | AUGUST
T-591-0691 | PS5-45-UR-2587D | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone C | 2 | To be completed |  | 8 | DECEMBER
T-223-0692 | PS5-85-OB-1524A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | To be completed |  | 45 | SEPTEMBER
T-838-0693 | PS5-52-OB-8625B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-07-20 | PS5-10-04 | PS5 - Milestone A | 1 | Closed | 14 | 6 | JULY
T-249-0694 | PS5-27-IK-1446A | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone A | 1 | On hold |  | 15 | SEPTEMBER
T-039-0695 | PS5-47-OB-6536A | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone F | 5 | To be completed |  | 12 | NOVEMBER
T-098-0696 | PS5-82-UR-6537C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone H | 7 | To be completed |  | 30 | OCTOBER
T-208-0697 | PS5-29-OB-6244D | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone D | 3 | To be completed |  | 4 | DECEMBER
T-443-0698 | PS5-67-UR-2987B | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | To be completed |  | 5 | OCTOBER
T-103-0699 | PS5-65-OB-1348A | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-07-28 | PS5-09-01 | PS5 - Milestone F | 5 | Closed | 10 | 28 | JULY
T-787-0700 | PS5-45-OB-8478D | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone I | 8 | On hold |  | 41 | AUGUST
T-680-0701 | PS5-19-IK-4215C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-13 | PS5-60-04 | PS5 - Milestone H | 7 | Closed | 26 | 31 | MAY
T-395-0702 | PS5-87-IK-4727B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-09-16 | PS5-05-02 | PS5 - Milestone A | 1 | Closed | 22 | 9 | SEPTEMBER
T-887-0703 | PS5-38-IK-7032B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | To be completed |  | 7 | OCTOBER
T-936-0704 | PS5-33-UR-8357C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-05-16 | PS5-04-03 | PS5 - Milestone A | 1 | Closed | 17 | 30 | MAY
T-729-0705 | PS5-56-IK-8240A | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-05-11 | PS5-01-05 | PS5 - Milestone A | 1 | Closed | 30 | 4 | MAY
T-346-0706 | PS5-42-UR-2315A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | To be completed |  | 32 | SEPTEMBER
T-275-0707 | PS5-87-OB-2576B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone C | 2 | To be completed |  | 32 | OCTOBER
T-776-0708 | PS5-79-OB-2692A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-08-07 | PS5-11-03 | PS5 - Milestone I | 8 | Closed | 38 | 14 | AUGUST
T-859-0709 | PS5-62-OB-5255B | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone G | 6 | To be completed |  | 28 | OCTOBER
T-816-0710 | PS5-74-UR-6835B | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone A | 1 | To be completed |  | 41 | AUGUST
T-333-0711 | PS5-88-IK-3309A | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone B | 1.1 | To be completed |  | 47 | AUGUST
T-193-0712 | PS5-68-UR-1699D | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-10-26 | PS5-11-02 | PS5 - Milestone B | 1.1 | Closed | 4 | 31 | OCTOBER
T-110-0713 | PS5-95-OB-8778B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone A | 1 | To be completed |  | 13 | DECEMBER
T-365-0714 | PS5-63-IK-6022B | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone A | 1 | To be completed |  | 5 | DECEMBER
T-122-0715 | PS5-99-IK-7105B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-08-07 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 24 | 42 | AUGUST
T-989-0716 | PS5-34-UR-9012D | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-03-23 | PS5-05-01 | PS5 - Milestone G | 6 | Closed | 44 | 43 | MARCH
T-198-0717 | PS5-03-OB-7507C | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone F | 5 | In progress |  | 13 | OCTOBER
T-814-0718 | PS5-01-UR-5391A | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-01-12 | PS5-60-04 | PS5 - Milestone I | 8 | Closed | 19 | 32 | JANUARY
T-297-0719 | PS5-10-UR-6643D | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-04-03 | PS5-07-02 | PS5 - Milestone H | 7 | Closed | 11 | 31 | APRIL
T-212-0720 | PS5-33-OB-9825B | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone B | 1.1 | To be completed |  | 18 | NOVEMBER
T-927-0721 | PS5-25-OB-2600D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-06-26 | PS5-10-04 | PS5 - Milestone B | 1.1 | Closed | 24 | 41 | JUNE
T-564-0722 | PS5-25-OB-3041B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | In progress |  | 34 | DECEMBER
T-291-0723 | PS5-37-OB-4024C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone F | 5 | To be completed |  | 31 | OCTOBER
T-083-0724 | PS5-34-UR-2534C | CQE02 - LV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-09-15 | PS5-82-01 | PS5 - Milestone D | 3 | Closed | 12 | 13 | SEPTEMBER
T-584-0725 | PS5-15-OB-7583B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone E | 4 | To be completed |  | 41 | DECEMBER
T-951-0726 | PS5-94-OB-3154D | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-09-26 | PS5-82-07 | PS5 - Milestone D | 3 | Closed | 35 | 48 | SEPTEMBER
T-957-0727 | PS5-23-OB-4278B | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-06-23 | PS5-02-01 | PS5 - Milestone F | 5 | Closed | 7 | 45 | JUNE
T-320-0728 | PS5-77-OB-8734A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone I | 8 | To be completed |  | 47 | NOVEMBER
T-079-0729 | PS5-23-UR-8278C | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-10-03 | PS5-02-01 | PS5 - Milestone A | 1 | Closed | 45 | 38 | OCTOBER
T-438-0730 | PS5-74-IK-5094C | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-08-21 | PS5-07-03 | PS5 - Milestone A | 1 | Closed | 30 | 41 | AUGUST
T-445-0731 | PS5-87-UR-4787D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone C | 2 | In progress |  | 28 | AUGUST
T-577-0732 | PS5-01-IK-5830B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone B | 1.1 | To be completed |  | 14 | AUGUST
T-222-0733 | PS5-58-OB-2150B | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone G | 6 | To be completed |  | 12 | DECEMBER
T-420-0734 | PS5-72-OB-7990B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-10-21 | PS5-63-04 | PS5 - Milestone G | 6 | Closed | 8 | 48 | OCTOBER
T-802-0735 | PS5-11-IK-6792A | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone D | 3 | In progress |  | 34 | NOVEMBER
T-301-0736 | PS5-40-UR-4114D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone C | 2 | To be completed |  | 28 | NOVEMBER
T-658-0737 | PS5-08-UR-2974D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone C | 2 | To be completed |  | 15 | OCTOBER
T-606-0738 | PS5-38-OB-4650D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-08-24 | PS5-02-01 | PS5 - Milestone G | 6 | Closed | 5 | 23 | AUGUST
T-329-0739 | PS5-41-OB-1248C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-10-27 | PS5-99-01 | PS5 - Milestone E | 4 | Closed | 10 | 43 | OCTOBER
T-173-0740 | PS5-87-OB-7015C | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone H | 7 | To be completed |  | 6 | SEPTEMBER
T-652-0741 | PS5-20-OB-1176C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone F | 5 | In progress |  | 46 | OCTOBER
T-055-0742 | PS5-74-OB-1108D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-06-16 | PS5-11-02 | PS5 - Milestone G | 6 | Closed | 28 | 11 | JUNE
T-301-0743 | PS5-89-IK-7170C | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | On hold |  | 9 | NOVEMBER
T-870-0744 | PS5-47-IK-7442D | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-10-15 | PS5-10-02 | PS5 - Milestone D | 3 | Closed | 16 | 21 | OCTOBER
T-389-0745 | PS5-93-OB-9957C | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone A | 1 | To be completed |  | 47 | OCTOBER
T-231-0746 | PS5-40-OB-5261B | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-02-10 | PS5-82-01 | PS5 - Milestone F | 5 | Closed | 28 | 11 | FEBRUARY
T-223-0747 | PS5-09-UR-2388D | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone A | 1 | To be completed |  | 24 | AUGUST
T-964-0748 | PS5-32-OB-7251C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone A | 1 | In progress |  | 26 | NOVEMBER
T-244-0749 | PS5-52-OB-8461B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-02-26 | PS5-06-03 | PS5 - Milestone H | 7 | Closed | 35 | 42 | FEBRUARY
T-606-0750 | PS5-54-OB-6138B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone C | 2 | To be completed |  | 11 | NOVEMBER
T-211-0751 | PS5-72-UR-7177D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone E | 4 | To be completed |  | 40 | DECEMBER
T-895-0752 | PS5-02-OB-9490B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | In progress |  | 9 | DECEMBER
T-269-0753 | PS5-60-IK-4051B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | In progress |  | 27 | DECEMBER
T-474-0754 | PS5-84-UR-8786B | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone F | 5 | In progress |  | 24 | AUGUST
T-966-0755 | PS5-04-UR-6146B | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone B | 1.1 | In progress |  | 42 | NOVEMBER
T-111-0756 | PS5-25-UR-3840D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-08-01 | PS5-01-03 | PS5 - Milestone I | 8 | Closed | 32 | 43 | AUGUST
T-419-0757 | PS5-53-OB-9642B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone G | 6 | To be completed |  | 18 | AUGUST
T-313-0758 | PS5-88-OB-5966A | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone D | 3 | To be completed |  | 29 | SEPTEMBER
T-839-0759 | PS5-33-IK-5706A | CQP02 - Valve Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone H | 7 | To be completed |  | 33 | NOVEMBER
T-942-0760 | PS5-65-UR-9726A | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-12-06 | PS5-05-02 | PS5 - Milestone A | 1 | Closed | 47 | 41 | DECEMBER
T-636-0761 | PS5-54-OB-1628D | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-01-10 | PS5-01-03 | PS5 - Milestone F | 5 | Closed | 17 | 16 | JANUARY
T-529-0762 | PS5-89-IK-3382B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone C | 2 | To be completed |  | 9 | OCTOBER
T-964-0763 | PS5-79-IK-3534A | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-04-08 | PS5-82-07 | PS5 - Milestone H | 7 | Closed | 20 | 24 | APRIL
T-069-0764 | PS5-02-UR-2274C | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone G | 6 | In progress |  | 45 | AUGUST
T-720-0765 | PS5-47-IK-8036C | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone C | 2 | In progress |  | 46 | OCTOBER
T-312-0766 | PS5-87-OB-2247D | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-08-22 | PS5-07-03 | PS5 - Milestone I | 8 | Closed | 36 | 43 | AUGUST
T-647-0767 | PS5-92-OB-3054D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-06-27 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 31 | 45 | JUNE
T-253-0768 | PS5-95-IK-1710B | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-09-10 | PS5-99-02 | PS5 - Milestone I | 8 | Closed | 9 | 36 | SEPTEMBER
T-790-0769 | PS5-35-OB-6756A | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-11-09 | PS5-01-03 | PS5 - Milestone F | 5 | Closed | 43 | 5 | NOVEMBER
T-339-0770 | PS5-31-OB-4801A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone B | 1.1 | On hold |  | 28 | SEPTEMBER
T-065-0771 | PS5-75-UR-4452A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-09-01 | PS5-07-04 | PS5 - Milestone E | 4 | Closed | 7 | 34 | SEPTEMBER
T-766-0772 | PS5-80-UR-7363A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-01-08 | PS5-08-02 | PS5 - Milestone A | 1 | Closed | 47 | 27 | JANUARY
T-753-0773 | PS5-57-UR-4759C | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-10-16 | PS5-11-03 | PS5 - Milestone G | 6 | Closed | 22 | 17 | OCTOBER
T-946-0774 | PS5-24-OB-6572B | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone F | 5 | On hold |  | 36 | NOVEMBER
T-777-0775 | PS5-82-OB-8387D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone I | 8 | To be completed |  | 30 | OCTOBER
T-535-0776 | PS5-58-IK-1875D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | To be completed |  | 6 | NOVEMBER
T-297-0777 | PS5-27-OB-7535D | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-01-09 | PS5-01-05 | PS5 - Milestone H | 7 | Closed | 20 | 34 | JANUARY
T-653-0778 | PS5-13-OB-2322D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | To be completed |  | 47 | AUGUST
T-636-0779 | PS5-81-IK-3053D | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone B | 1.1 | To be completed |  | 44 | NOVEMBER
T-456-0780 | PS5-44-OB-7007A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone G | 6 | In progress |  | 5 | DECEMBER
T-095-0781 | PS5-43-UR-1765A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-12-13 | PS5-03-02 | PS5 - Milestone D | 3 | Closed | 22 | 8 | DECEMBER
T-572-0782 | PS5-85-UR-2579B | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone E | 4 | On hold |  | 12 | AUGUST
T-443-0783 | PS5-59-UR-9051D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone E | 4 | In progress |  | 43 | AUGUST
T-485-0784 | PS5-80-OB-2715C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-01-15 | PS5-02-01 | PS5 - Milestone E | 4 | Closed | 26 | 29 | JANUARY
T-024-0785 | PS5-29-UR-7528C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-08-25 | PS5-82-01 | PS5 - Milestone G | 6 | Closed | 24 | 44 | AUGUST
T-736-0786 | PS5-52-IK-3658A | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-12-27 | PS5-99-01 | PS5 - Milestone B | 1.1 | Closed | 4 | 22 | DECEMBER
T-809-0787 | PS5-60-OB-1035A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-05-20 | PS5-07-02 | PS5 - Milestone D | 3 | Closed | 33 | 26 | MAY
T-218-0788 | PS5-68-UR-6595A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone H | 7 | To be completed |  | 13 | OCTOBER
T-704-0789 | PS5-32-OB-9914D | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-08-26 | PS5-01-07 | PS5 - Milestone D | 3 | Closed | 20 | 39 | AUGUST
T-410-0790 | PS5-41-OB-8925A | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone B | 1.1 | To be completed |  | 32 | OCTOBER
T-937-0791 | PS5-48-UR-2396B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone I | 8 | To be completed |  | 34 | NOVEMBER
T-432-0792 | PS5-95-IK-2652B | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone B | 1.1 | To be completed |  | 26 | DECEMBER
T-473-0793 | PS5-57-OB-9820C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone I | 8 | In progress |  | 48 | SEPTEMBER
T-675-0794 | PS5-62-OB-2635B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone D | 3 | In progress |  | 43 | AUGUST
T-669-0795 | PS5-40-OB-9049A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone H | 7 | In progress |  | 30 | SEPTEMBER
T-405-0796 | PS5-17-OB-8117A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone F | 5 | On hold |  | 36 | SEPTEMBER
T-967-0797 | PS5-11-UR-5309D | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone G | 6 | To be completed |  | 40 | DECEMBER
T-501-0798 | PS5-19-IK-5269A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone D | 3 | In progress |  | 28 | NOVEMBER
T-311-0799 | PS5-17-UR-3294B | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-01-20 | PS5-03-01 | PS5 - Milestone I | 8 | Closed | 23 | 37 | JANUARY
T-359-0800 | PS5-34-UR-7187A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-07-22 | PS5-01-04 | PS5 - Milestone C | 2 | Closed | 17 | 18 | JULY
T-010-0801 | PS5-33-OB-8247D | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | To be completed |  | 20 | NOVEMBER
T-965-0802 | PS5-98-OB-7753C | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-05-13 | PS5-61-07 | PS5 - Milestone F | 5 | Closed | 27 | 8 | MAY
T-660-0803 | PS5-59-OB-6359A | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-11-18 | PS5-03-02 | PS5 - Milestone D | 3 | Closed | 32 | 20 | NOVEMBER
T-561-0804 | PS5-86-UR-2948A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone H | 7 | In progress |  | 35 | DECEMBER
T-848-0805 | PS5-97-OB-7338D | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone F | 5 | To be completed |  | 27 | OCTOBER
T-108-0806 | PS5-83-OB-1534C | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone B | 1.1 | In progress |  | 33 | NOVEMBER
T-693-0807 | PS5-13-UR-8515B | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-06-17 | PS5-02-02 | PS5 - Milestone C | 2 | Closed | 32 | 35 | JUNE
T-280-0808 | PS5-63-IK-1229D | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone G | 6 | On hold |  | 16 | DECEMBER
T-572-0809 | PS5-96-IK-1539A | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-05-27 | PS5-05-01 | PS5 - Milestone C | 2 | Closed | 33 | 30 | MAY
T-566-0810 | PS5-50-IK-7877A | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-03-17 | PS5-10-06 | PS5 - Milestone C | 2 | Closed | 4 | 39 | MARCH
T-718-0811 | PS5-32-OB-1007B | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-09-25 | PS5-12-02 | PS5 - Milestone I | 8 | Closed | 38 | 13 | SEPTEMBER
T-924-0812 | PS5-98-OB-3786D | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone C | 2 | To be completed |  | 41 | NOVEMBER
T-459-0813 | PS5-01-UR-8443C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | To be completed |  | 14 | OCTOBER
T-208-0814 | PS5-72-OB-5412C | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone I | 8 | To be completed |  | 9 | OCTOBER
T-271-0815 | PS5-52-UR-9448D | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone D | 3 | In progress |  | 31 | NOVEMBER
T-604-0816 | PS5-53-OB-5454C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone F | 5 | On hold |  | 7 | OCTOBER
T-802-0817 | PS5-66-OB-5502B | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-11-02 | PS5-01-09 | PS5 - Milestone G | 6 | Closed | 38 | 9 | NOVEMBER
T-603-0818 | PS5-33-OB-1722C | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-09-10 | PS5-03-23 | PS5 - Milestone H | 7 | Closed | 15 | 39 | SEPTEMBER
T-367-0819 | PS5-59-OB-2316C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone I | 8 | On hold |  | 17 | AUGUST
T-028-0820 | PS5-90-IK-7952D | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-06-12 | PS5-63-01 | PS5 - Milestone F | 5 | Closed | 4 | 10 | JUNE
T-697-0821 | PS5-05-OB-3218D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone C | 2 | In progress |  | 40 | SEPTEMBER
T-708-0822 | PS5-63-UR-5706C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone H | 7 | In progress |  | 33 | AUGUST
T-882-0823 | PS5-87-OB-1605C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone A | 1 | To be completed |  | 19 | DECEMBER
T-018-0824 | PS5-41-OB-6640B | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-03-02 | PS5-63-04 | PS5 - Milestone E | 4 | Closed | 31 | 39 | MARCH
T-524-0825 | PS5-53-IK-7294D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone H | 7 | In progress |  | 31 | OCTOBER
T-232-0826 | PS5-06-OB-1880A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-05-28 | PS5-09-03 | PS5 - Milestone I | 8 | Closed | 29 | 45 | MAY
T-296-0827 | PS5-37-OB-1099B | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone D | 3 | To be completed |  | 48 | SEPTEMBER
T-440-0828 | PS5-78-IK-2735D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-04-25 | PS5-13-01 | PS5 - Milestone A | 1 | Closed | 41 | 29 | APRIL
T-289-0829 | PS5-21-UR-9593D | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-11-20 | PS5-06-03 | PS5 - Milestone I | 8 | Closed | 19 | 45 | NOVEMBER
T-884-0830 | PS5-14-OB-8233C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-08-24 | PS5-10-01 | PS5 - Milestone B | 1.1 | Closed | 16 | 28 | AUGUST
T-267-0831 | PS5-29-OB-5445B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone I | 8 | On hold |  | 17 | DECEMBER
T-650-0832 | PS5-95-OB-9625C | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-12-17 | PS5-82-07 | PS5 - Milestone G | 6 | Closed | 28 | 23 | DECEMBER
T-860-0833 | PS5-73-OB-1453D | CQP04 - Hydrotest | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone I | 8 | To be completed |  | 8 | OCTOBER
T-639-0834 | PS5-48-OB-7937C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone A | 1 | In progress |  | 10 | AUGUST
T-803-0835 | PS5-67-UR-6710C | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone I | 8 | To be completed |  | 14 | NOVEMBER
T-298-0836 | PS5-45-IK-9191A | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-03-26 | PS5-09-02 | PS5 - Milestone F | 5 | Closed | 28 | 15 | MARCH
T-140-0837 | PS5-64-OB-3520A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | To be completed |  | 44 | DECEMBER
T-283-0838 | PS5-27-UR-5584C | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone I | 8 | To be completed |  | 45 | NOVEMBER
T-834-0839 | PS5-22-IK-3469A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone D | 3 | In progress |  | 9 | SEPTEMBER
T-750-0840 | PS5-96-IK-9781B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone F | 5 | In progress |  | 44 | DECEMBER
T-825-0841 | PS5-31-OB-7645D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-03-09 | PS5-08-02 | PS5 - Milestone F | 5 | Closed | 18 | 43 | MARCH
T-055-0842 | PS5-65-OB-1585D | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-08-12 | PS5-01-01 | PS5 - Milestone E | 4 | Closed | 46 | 18 | AUGUST
T-572-0843 | PS5-34-UR-8188B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone F | 5 | In progress |  | 41 | DECEMBER
T-418-0844 | PS5-81-OB-1015C | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone F | 5 | In progress |  | 23 | DECEMBER
T-803-0845 | PS5-42-OB-7516B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone F | 5 | To be completed |  | 41 | OCTOBER
T-411-0846 | PS5-31-OB-2720D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | To be completed |  | 40 | OCTOBER
T-856-0847 | PS5-07-UR-9971B | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-10-03 | PS5-03-01 | PS5 - Milestone D | 3 | Closed | 13 | 17 | OCTOBER
T-270-0848 | PS5-95-UR-3798B | CQH02 - AHU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone B | 1.1 | To be completed |  | 18 | OCTOBER
T-274-0849 | PS5-85-UR-6454A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone A | 1 | To be completed |  | 35 | DECEMBER
T-605-0850 | PS5-36-IK-7683C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-07-04 | PS5-07-04 | PS5 - Milestone F | 5 | Closed | 22 | 7 | JULY
T-043-0851 | PS5-77-OB-7424A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone F | 5 | In progress |  | 28 | DECEMBER
T-073-0852 | PS5-63-UR-8034A | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone H | 7 | On hold |  | 24 | NOVEMBER
T-289-0853 | PS5-56-UR-3621A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-12-10 | PS5-63-01 | PS5 - Milestone H | 7 | Closed | 37 | 18 | DECEMBER
T-397-0854 | PS5-19-OB-1449D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone D | 3 | On hold |  | 22 | SEPTEMBER
T-833-0855 | PS5-48-OB-8254C | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone E | 4 | To be completed |  | 45 | SEPTEMBER
T-118-0856 | PS5-46-UR-6603C | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone F | 5 | To be completed |  | 18 | SEPTEMBER
T-783-0857 | PS5-05-IK-6575C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone I | 8 | In progress |  | 26 | DECEMBER
T-575-0858 | PS5-54-OB-8139C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | To be completed |  | 23 | AUGUST
T-563-0859 | PS5-32-IK-7239D | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-03-24 | PS5-63-04 | PS5 - Milestone E | 4 | Closed | 44 | 28 | MARCH
T-818-0860 | PS5-15-OB-7028B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-03-22 | PS5-04-02 | PS5 - Milestone H | 7 | Closed | 45 | 23 | MARCH
T-759-0861 | PS5-41-OB-5951B | CQE01 - HV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone G | 6 | In progress |  | 31 | DECEMBER
T-146-0862 | PS5-53-OB-5832D | CQM02 - Compressor | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-01-14 | PS5-05-02 | PS5 - Milestone E | 4 | Closed | 7 | 48 | JANUARY
T-695-0863 | PS5-53-UR-1494C | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone B | 1.1 | To be completed |  | 27 | AUGUST
T-451-0864 | PS5-71-OB-2011B | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone C | 2 | On hold |  | 46 | OCTOBER
T-755-0865 | PS5-06-OB-1600A | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-01-15 | PS5-10-02 | PS5 - Milestone E | 4 | Closed | 22 | 37 | JANUARY
T-736-0866 | PS5-76-OB-1418B | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-02-04 | PS5-13-01 | PS5 - Milestone G | 6 | Closed | 7 | 46 | FEBRUARY
T-019-0867 | PS5-92-OB-5737A | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-10-06 | PS5-62-02 | PS5 - Milestone C | 2 | Closed | 12 | 8 | OCTOBER
T-225-0868 | PS5-12-IK-9555C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-02-01 | PS5-63-04 | PS5 - Milestone A | 1 | Closed | 6 | 28 | FEBRUARY
T-356-0869 | PS5-10-IK-7605A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone G | 6 | On hold |  | 21 | OCTOBER
T-110-0870 | PS5-43-OB-2924A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-06-25 | PS5-63-04 | PS5 - Milestone H | 7 | Closed | 15 | 34 | JUNE
T-989-0871 | PS5-42-OB-5173D | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-02-02 | PS5-09-01 | PS5 - Milestone D | 3 | Closed | 15 | 24 | FEBRUARY
T-151-0872 | PS5-42-OB-9941C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone B | 1.1 | In progress |  | 15 | SEPTEMBER
T-835-0873 | PS5-31-OB-1638A | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone I | 8 | In progress |  | 41 | DECEMBER
T-857-0874 | PS5-93-OB-2812D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-10-20 | PS5-02-01 | PS5 - Milestone B | 1.1 | Closed | 46 | 48 | OCTOBER
T-654-0875 | PS5-25-IK-6419D | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone E | 4 | In progress |  | 31 | DECEMBER
T-564-0876 | PS5-09-OB-1614B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-11-20 | PS5-05-03 | PS5 - Milestone H | 7 | Closed | 14 | 40 | NOVEMBER
T-469-0877 | PS5-59-OB-1189B | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone C | 2 | To be completed |  | 12 | NOVEMBER
T-366-0878 | PS5-59-UR-1897C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-02-23 | PS5-01-07 | PS5 - Milestone I | 8 | Closed | 31 | 28 | FEBRUARY
T-662-0879 | PS5-52-OB-7856D | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone C | 2 | To be completed |  | 11 | AUGUST
T-922-0880 | PS5-62-UR-7750A | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone I | 8 | To be completed |  | 18 | DECEMBER
T-023-0881 | PS5-68-OB-1604B | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone F | 5 | In progress |  | 47 | NOVEMBER
T-989-0882 | PS5-48-OB-5833B | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-06-02 | PS5-07-02 | PS5 - Milestone A | 1 | Closed | 40 | 22 | JUNE
T-653-0883 | PS5-97-OB-8212B | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | In progress |  | 44 | OCTOBER
T-860-0884 | PS5-12-OB-8249B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | In progress |  | 48 | DECEMBER
T-350-0885 | PS5-83-UR-2723B | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone H | 7 | In progress |  | 45 | AUGUST
T-221-0886 | PS5-55-OB-5769C | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-09-13 | PS5-05-03 | PS5 - Milestone F | 5 | Closed | 27 | 29 | SEPTEMBER
T-209-0887 | PS5-77-UR-9134A | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone D | 3 | On hold |  | 7 | OCTOBER
T-824-0888 | PS5-01-UR-4921B | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone A | 1 | In progress |  | 29 | AUGUST
T-579-0889 | PS5-03-OB-7492B | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone H | 7 | In progress |  | 42 | AUGUST
T-709-0890 | PS5-22-OB-8273A | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone D | 3 | To be completed |  | 25 | NOVEMBER
T-148-0891 | PS5-12-IK-7276C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone C | 2 | To be completed |  | 20 | NOVEMBER
T-557-0892 | PS5-38-OB-7727A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone H | 7 | In progress |  | 23 | DECEMBER
T-340-0893 | PS5-57-IK-4649D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone D | 3 | On hold |  | 23 | DECEMBER
T-165-0894 | PS5-37-UR-8982C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-11-09 | PS5-60-07 | PS5 - Milestone D | 3 | Closed | 14 | 16 | NOVEMBER
T-843-0895 | PS5-67-OB-1724A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone B | 1.1 | To be completed |  | 31 | NOVEMBER
T-568-0896 | PS5-17-UR-6400B | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-03-24 | PS5-99-03 | PS5 - Milestone H | 7 | Closed | 6 | 44 | MARCH
T-974-0897 | PS5-50-OB-9571A | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-04-17 | PS5-10-02 | PS5 - Milestone F | 5 | Closed | 42 | 37 | APRIL
T-355-0898 | PS5-85-UR-1363B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-04-06 | PS5-01-06 | PS5 - Milestone C | 2 | Closed | 42 | 10 | APRIL
T-955-0899 | PS5-36-IK-2154A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-02-12 | PS5-10-02 | PS5 - Milestone I | 8 | Closed | 42 | 45 | FEBRUARY
T-669-0900 | PS5-63-IK-3370D | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-08-18 | PS5-11-03 | PS5 - Milestone E | 4 | Closed | 23 | 18 | AUGUST
T-460-0901 | PS5-43-IK-1009A | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | In progress |  | 24 | NOVEMBER
T-188-0902 | PS5-33-OB-5601A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone A | 1 | In progress |  | 9 | SEPTEMBER
T-671-0903 | PS5-31-OB-5943C | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone C | 2 | In progress |  | 37 | OCTOBER
T-084-0904 | PS5-64-IK-2408C | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone F | 5 | In progress |  | 7 | AUGUST
T-459-0905 | PS5-67-UR-8763B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-11-11 | PS5-04-04 | PS5 - Milestone F | 5 | Closed | 20 | 4 | NOVEMBER
T-677-0906 | PS5-01-UR-9711C | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-06-04 | PS5-07-03 | PS5 - Milestone E | 4 | Closed | 26 | 45 | JUNE
T-381-0907 | PS5-98-IK-6587C | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone C | 2 | To be completed |  | 18 | OCTOBER
T-705-0908 | PS5-07-IK-8176A | CQM02 - Compressor | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-04-13 | PS5-08-02 | PS5 - Milestone H | 7 | Closed | 20 | 35 | APRIL
T-857-0909 | PS5-58-OB-5465D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-02-18 | PS5-12-01 | PS5 - Milestone I | 8 | Closed | 25 | 13 | FEBRUARY
T-565-0910 | PS5-41-IK-5428D | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | To be completed |  | 21 | AUGUST
T-555-0911 | PS5-92-OB-7562A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-12-14 | PS5-04-04 | PS5 - Milestone E | 4 | Closed | 20 | 46 | DECEMBER
T-201-0912 | PS5-62-OB-6593D | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone C | 2 | In progress |  | 29 | AUGUST
T-067-0913 | PS5-38-OB-4530D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | In progress |  | 11 | SEPTEMBER
T-904-0914 | PS5-51-UR-2245C | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone G | 6 | In progress |  | 33 | DECEMBER
T-404-0915 | PS5-57-OB-5385C | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | In progress |  | 33 | NOVEMBER
T-806-0916 | PS5-80-UR-5789D | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone H | 7 | In progress |  | 32 | OCTOBER
T-533-0917 | PS5-24-UR-2084C | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone F | 5 | To be completed |  | 25 | AUGUST
T-686-0918 | PS5-78-UR-2916A | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone B | 1.1 | On hold |  | 29 | NOVEMBER
T-878-0919 | PS5-29-IK-5011A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone D | 3 | To be completed |  | 15 | SEPTEMBER
T-596-0920 | PS5-76-IK-8356B | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | In progress |  | 48 | NOVEMBER
T-071-0921 | PS5-35-UR-6402B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-06-18 | PS5-01-01 | PS5 - Milestone F | 5 | Closed | 16 | 29 | JUNE
T-034-0922 | PS5-85-OB-4178D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone G | 6 | In progress |  | 32 | OCTOBER
T-633-0923 | PS5-79-UR-2251A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-05-05 | PS5-04-02 | PS5 - Milestone A | 1 | Closed | 21 | 32 | MAY
T-494-0924 | PS5-18-OB-2546A | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone F | 5 | In progress |  | 36 | AUGUST
T-965-0925 | PS5-39-OB-7976A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-02-12 | PS5-99-03 | PS5 - Milestone D | 3 | Closed | 7 | 44 | FEBRUARY
T-536-0926 | PS5-03-OB-4286A | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone D | 3 | In progress |  | 21 | OCTOBER
T-125-0927 | PS5-45-IK-6445C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone G | 6 | On hold |  | 45 | SEPTEMBER
T-243-0928 | PS5-49-IK-2077B | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-10-13 | PS5-02-02 | PS5 - Milestone H | 7 | Closed | 48 | 40 | OCTOBER
T-433-0929 | PS5-67-OB-2759D | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone F | 5 | In progress |  | 46 | AUGUST
T-919-0930 | PS5-78-OB-4400A | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone A | 1 | In progress |  | 41 | OCTOBER
T-991-0931 | PS5-56-UR-6050C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | To be completed |  | 38 | OCTOBER
T-586-0932 | PS5-94-UR-3670C | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | To be completed |  | 25 | OCTOBER
T-243-0933 | PS5-66-OB-7495D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | On hold |  | 32 | OCTOBER
T-714-0934 | PS5-25-IK-3365C | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone C | 2 | On hold |  | 36 | DECEMBER
T-466-0935 | PS5-61-UR-2352A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone I | 8 | In progress |  | 39 | SEPTEMBER
T-826-0936 | PS5-25-IK-1367C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | To be completed |  | 45 | OCTOBER
T-509-0937 | PS5-05-OB-1609D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone A | 1 | To be completed |  | 26 | SEPTEMBER
T-172-0938 | PS5-41-IK-5079C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-01-28 | PS5-03-02 | PS5 - Milestone C | 2 | Closed | 24 | 27 | JANUARY
T-680-0939 | PS5-17-OB-6461A | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone E | 4 | To be completed |  | 35 | AUGUST
T-616-0940 | PS5-52-IK-3220D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-09-08 | PS5-03-03 | PS5 - Milestone B | 1.1 | Closed | 8 | 12 | SEPTEMBER
T-729-0941 | PS5-27-UR-1375A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone G | 6 | To be completed |  | 28 | AUGUST
T-520-0942 | PS5-40-OB-5807A | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone G | 6 | On hold |  | 14 | DECEMBER
T-750-0943 | PS5-79-IK-1121C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | To be completed |  | 21 | OCTOBER
T-029-0944 | PS5-90-OB-4031B | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone G | 6 | To be completed |  | 11 | NOVEMBER
T-610-0945 | PS5-46-IK-3743C | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-06-11 | PS5-13-01 | PS5 - Milestone B | 1.1 | Closed | 44 | 24 | JUNE
T-583-0946 | PS5-69-OB-3655A | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | To be completed |  | 8 | SEPTEMBER
T-643-0947 | PS5-43-OB-9449D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-12-09 | PS5-05-03 | PS5 - Milestone G | 6 | Closed | 19 | 10 | DECEMBER
T-873-0948 | PS5-09-UR-1256A | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-01-07 | PS5-12-02 | PS5 - Milestone G | 6 | Closed | 8 | 22 | JANUARY
T-346-0949 | PS5-85-UR-3181D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone E | 4 | To be completed |  | 5 | NOVEMBER
T-362-0950 | PS5-52-OB-6008A | CQH02 - AHU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-10-21 | PS5-61-07 | PS5 - Milestone A | 1 | Closed | 4 | 32 | OCTOBER
T-971-0951 | PS5-06-OB-2854D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | To be completed |  | 22 | SEPTEMBER
T-837-0952 | PS5-02-IK-3332A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-01-04 | PS5-10-05 | PS5 - Milestone A | 1 | Closed | 40 | 18 | JANUARY
T-444-0953 | PS5-52-OB-6036C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone D | 3 | To be completed |  | 30 | SEPTEMBER
T-381-0954 | PS5-64-OB-3103A | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone H | 7 | To be completed |  | 16 | AUGUST
T-136-0955 | PS5-27-OB-3912C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone F | 5 | On hold |  | 36 | AUGUST
T-534-0956 | PS5-86-OB-6848C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone D | 3 | To be completed |  | 8 | DECEMBER
T-795-0957 | PS5-66-IK-3785B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-01-02 | PS5-99-02 | PS5 - Milestone I | 8 | Closed | 32 | 42 | JANUARY
T-122-0958 | PS5-16-OB-7670A | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | On hold |  | 35 | DECEMBER
T-720-0959 | PS5-17-OB-4851C | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone E | 4 | In progress |  | 44 | NOVEMBER
T-645-0960 | PS5-99-IK-6628C | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | In progress |  | 44 | SEPTEMBER
T-030-0961 | PS5-03-OB-8945A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-05-21 | PS5-63-04 | PS5 - Milestone A | 1 | Closed | 20 | 10 | MAY
T-461-0962 | PS5-89-UR-5232A | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-11-06 | PS5-82-02 | PS5 - Milestone C | 2 | Closed | 45 | 44 | NOVEMBER
T-318-0963 | PS5-20-IK-4539B | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone B | 1.1 | In progress |  | 12 | NOVEMBER
T-471-0964 | PS5-21-OB-6578A | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone C | 2 | To be completed |  | 47 | NOVEMBER
T-385-0965 | PS5-05-OB-4909D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone I | 8 | In progress |  | 40 | NOVEMBER
T-400-0966 | PS5-81-OB-6501D | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone D | 3 | To be completed |  | 21 | OCTOBER
T-816-0967 | PS5-87-UR-1543C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | To be completed |  | 29 | AUGUST
T-130-0968 | PS5-78-OB-8745C | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone A | 1 | To be completed |  | 40 | OCTOBER
T-923-0969 | PS5-23-UR-1537B | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone F | 5 | In progress |  | 22 | OCTOBER
T-937-0970 | PS5-65-UR-7557B | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone A | 1 | In progress |  | 38 | DECEMBER
T-930-0971 | PS5-65-OB-2934A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-11-28 | PS5-01-05 | PS5 - Milestone B | 1.1 | Closed | 6 | 45 | NOVEMBER
T-346-0972 | PS5-06-IK-5694D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-03-05 | PS5-05-03 | PS5 - Milestone C | 2 | Closed | 29 | 45 | MARCH
T-867-0973 | PS5-15-UR-7850A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-09-09 | PS5-06-01 | PS5 - Milestone E | 4 | Closed | 27 | 24 | SEPTEMBER
T-689-0974 | PS5-49-OB-7316C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone H | 7 | To be completed |  | 6 | AUGUST
T-604-0975 | PS5-96-OB-5344A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone G | 6 | To be completed |  | 6 | OCTOBER
T-975-0976 | PS5-58-UR-5492B | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone H | 7 | In progress |  | 24 | NOVEMBER
T-330-0977 | PS5-97-OB-4855A | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-02-03 | PS5-01-02 | PS5 - Milestone E | 4 | Closed | 29 | 35 | FEBRUARY
T-185-0978 | PS5-75-OB-7642C | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-03-12 | PS5-03-03 | PS5 - Milestone B | 1.1 | Closed | 13 | 12 | MARCH
T-091-0979 | PS5-63-OB-7133C | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | To be completed |  | 46 | OCTOBER
T-576-0980 | PS5-28-UR-5630A | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | On hold |  | 16 | NOVEMBER
T-662-0981 | PS5-67-OB-9881D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone G | 6 | In progress |  | 27 | NOVEMBER
T-711-0982 | PS5-53-OB-5602B | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone D | 3 | To be completed |  | 13 | NOVEMBER
T-298-0983 | PS5-58-UR-9172D | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-03-22 | PS5-08-01 | PS5 - Milestone D | 3 | Closed | 15 | 44 | MARCH
T-762-0984 | PS5-17-UR-5039D | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone I | 8 | To be completed |  | 36 | OCTOBER
T-648-0985 | PS5-86-OB-2233C | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-09-03 | PS5-04-03 | PS5 - Milestone E | 4 | Closed | 36 | 5 | SEPTEMBER
T-340-0986 | PS5-17-UR-8928B | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone A | 1 | To be completed |  | 28 | NOVEMBER
T-330-0987 | PS5-07-OB-7428C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone C | 2 | To be completed |  | 15 | OCTOBER
T-180-0988 | PS5-38-IK-2740A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone F | 5 | To be completed |  | 31 | AUGUST
T-699-0989 | PS5-12-OB-4476D | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-07-24 | PS5-11-02 | PS5 - Milestone H | 7 | Closed | 4 | 33 | JULY
T-962-0990 | PS5-28-OB-9332B | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-07-11 | PS5-06-02 | PS5 - Milestone B | 1.1 | Closed | 8 | 28 | JULY
T-065-0991 | PS5-95-UR-3259A | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-10-13 | PS5-61-02 | PS5 - Milestone F | 5 | Closed | 23 | 40 | OCTOBER
T-306-0992 | PS5-78-OB-7850A | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone E | 4 | In progress |  | 35 | SEPTEMBER
T-993-0993 | PS5-83-OB-8857A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone E | 4 | To be completed |  | 46 | SEPTEMBER
T-556-0994 | PS5-31-IK-1241C | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone E | 4 | To be completed |  | 14 | AUGUST
T-691-0995 | PS5-91-IK-4689A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone A | 1 | In progress |  | 8 | SEPTEMBER
T-889-0996 | PS5-28-UR-9288D | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-08-21 | PS5-60-01 | PS5 - Milestone D | 3 | Closed | 23 | 10 | AUGUST
T-352-0997 | PS5-99-OB-3846D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone I | 8 | On hold |  | 26 | NOVEMBER
T-764-0998 | PS5-23-IK-5806C | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-10-22 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 23 | 24 | OCTOBER
T-480-0999 | PS5-89-IK-7324A | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone F | 5 | To be completed |  | 4 | AUGUST
T-133-1000 | PS5-64-IK-8927A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | In progress |  | 27 | SEPTEMBER
T-146-1001 | PS5-77-OB-8312D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone C | 2 | In progress |  | 21 | AUGUST
T-764-1002 | PS5-89-OB-5224B | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | To be completed |  | 11 | NOVEMBER
T-861-1003 | PS5-14-OB-2838B | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-06-11 | PS5-12-02 | PS5 - Milestone F | 5 | Closed | 21 | 7 | JUNE
T-094-1004 | PS5-34-UR-6829D | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone C | 2 | In progress |  | 43 | NOVEMBER
T-522-1005 | PS5-97-UR-4110A | CQP02 - Valve Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-17 | PS5-60-07 | PS5 - Milestone D | 3 | Closed | 43 | 43 | APRIL
T-895-1006 | PS5-78-OB-8637B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-04-12 | PS5-99-01 | PS5 - Milestone I | 8 | Closed | 36 | 29 | APRIL
T-102-1007 | PS5-10-OB-2898D | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone F | 5 | To be completed |  | 17 | NOVEMBER
T-800-1008 | PS5-85-UR-5319C | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-01-14 | PS5-11-01 | PS5 - Milestone F | 5 | Closed | 7 | 42 | JANUARY
T-937-1009 | PS5-29-OB-6115D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone I | 8 | In progress |  | 20 | NOVEMBER
T-321-1010 | PS5-19-IK-9103B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone F | 5 | In progress |  | 27 | NOVEMBER
T-990-1011 | PS5-58-OB-9003B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone H | 7 | To be completed |  | 4 | NOVEMBER
T-976-1012 | PS5-53-OB-6940C | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-01-16 | PS5-60-07 | PS5 - Milestone F | 5 | Closed | 8 | 35 | JANUARY
T-007-1013 | PS5-23-IK-1733A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone C | 2 | To be completed |  | 23 | AUGUST
T-249-1014 | PS5-62-UR-1457B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-12-12 | PS5-09-01 | PS5 - Milestone H | 7 | Closed | 35 | 26 | DECEMBER
T-203-1015 | PS5-27-UR-9913D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone F | 5 | On hold |  | 30 | SEPTEMBER
T-216-1016 | PS5-06-OB-7917D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-01-18 | PS5-01-09 | PS5 - Milestone A | 1 | Closed | 20 | 46 | JANUARY
T-211-1017 | PS5-37-UR-1695D | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-05-04 | PS5-01-06 | PS5 - Milestone D | 3 | Closed | 33 | 11 | MAY
T-987-1018 | PS5-29-OB-9652D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | To be completed |  | 44 | NOVEMBER
T-594-1019 | PS5-88-OB-1102D | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-03-28 | PS5-02-02 | PS5 - Milestone A | 1 | Closed | 46 | 26 | MARCH
T-301-1020 | PS5-58-UR-9574B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone D | 3 | In progress |  | 40 | AUGUST
T-233-1021 | PS5-10-OB-6652C | CQS01 - Fire Protection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-09-23 | PS5-05-01 | PS5 - Milestone E | 4 | Closed | 4 | 42 | SEPTEMBER
T-244-1022 | PS5-74-OB-1402B | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-03-17 | PS5-01-04 | PS5 - Milestone D | 3 | Closed | 18 | 18 | MARCH
T-711-1023 | PS5-39-OB-7409C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone H | 7 | On hold |  | 14 | OCTOBER
T-697-1024 | PS5-40-IK-6049C | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-01-03 | PS5-12-02 | PS5 - Milestone I | 8 | Closed | 42 | 13 | JANUARY
T-108-1025 | PS5-93-OB-8475B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone E | 4 | In progress |  | 12 | AUGUST
T-743-1026 | PS5-07-UR-8975A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-04-06 | PS5-09-01 | PS5 - Milestone I | 8 | Closed | 7 | 13 | APRIL
T-060-1027 | PS5-83-OB-9091D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | In progress |  | 45 | SEPTEMBER
T-123-1028 | PS5-22-OB-5680B | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone A | 1 | To be completed |  | 17 | NOVEMBER
T-962-1029 | PS5-45-OB-3615A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-09-06 | PS5-10-03 | PS5 - Milestone F | 5 | Closed | 42 | 24 | SEPTEMBER
T-776-1030 | PS5-58-UR-6715D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-06-07 | PS5-10-03 | PS5 - Milestone E | 4 | Closed | 36 | 26 | JUNE
T-123-1031 | PS5-72-OB-6985D | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone H | 7 | In progress |  | 33 | NOVEMBER
T-425-1032 | PS5-65-OB-1045B | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone F | 5 | To be completed |  | 20 | OCTOBER
T-712-1033 | PS5-81-OB-4610C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-05-23 | PS5-99-02 | PS5 - Milestone F | 5 | Closed | 15 | 36 | MAY
T-657-1034 | PS5-79-UR-3957B | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone E | 4 | In progress |  | 18 | AUGUST
T-982-1035 | PS5-93-OB-5811C | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-03-16 | PS5-05-03 | PS5 - Milestone E | 4 | Closed | 34 | 44 | MARCH
T-323-1036 | PS5-29-UR-6431C | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-05-12 | PS5-10-05 | PS5 - Milestone B | 1.1 | Closed | 40 | 42 | MAY
T-084-1037 | PS5-17-OB-1723A | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone F | 5 | On hold |  | 46 | SEPTEMBER
T-581-1038 | PS5-70-OB-1881B | CQM01 - Pump Installation | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone D | 3 | To be completed |  | 47 | SEPTEMBER
T-798-1039 | PS5-67-UR-5288D | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-01-01 | PS5-60-04 | PS5 - Milestone B | 1.1 | Closed | 26 | 42 | JANUARY
T-900-1040 | PS5-66-UR-9934C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-01-22 | PS5-05-02 | PS5 - Milestone B | 1.1 | Closed | 24 | 21 | JANUARY
T-911-1041 | PS5-16-OB-4359B | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone I | 8 | To be completed |  | 33 | OCTOBER
T-219-1042 | PS5-98-IK-2647A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone G | 6 | On hold |  | 39 | NOVEMBER
T-712-1043 | PS5-53-UR-3235B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-09-06 | PS5-60-01 | PS5 - Milestone F | 5 | Closed | 11 | 27 | SEPTEMBER
T-176-1044 | PS5-92-UR-6801D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-08-14 | PS5-09-01 | PS5 - Milestone A | 1 | Closed | 5 | 43 | AUGUST
T-578-1045 | PS5-45-OB-4283A | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone G | 6 | To be completed |  | 36 | OCTOBER
T-125-1046 | PS5-93-UR-4828D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-01-04 | PS5-02-02 | PS5 - Milestone D | 3 | Closed | 46 | 14 | JANUARY
T-151-1047 | PS5-63-OB-7819A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone B | 1.1 | To be completed |  | 35 | NOVEMBER
T-534-1048 | PS5-38-UR-6211A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone D | 3 | To be completed |  | 39 | SEPTEMBER
T-608-1049 | PS5-03-OB-4053C | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | In progress |  | 21 | OCTOBER
T-507-1050 | PS5-87-IK-4434B | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-11-26 | PS5-99-02 | PS5 - Milestone A | 1 | Closed | 7 | 25 | NOVEMBER
T-421-1051 | PS5-65-UR-3658A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone F | 5 | In progress |  | 25 | OCTOBER
T-978-1052 | PS5-58-OB-1877B | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | In progress |  | 12 | SEPTEMBER
T-401-1053 | PS5-20-UR-2904D | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | In progress |  | 25 | OCTOBER
T-607-1054 | PS5-17-OB-9628B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone B | 1.1 | To be completed |  | 41 | DECEMBER
T-865-1055 | PS5-19-OB-5732B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone E | 4 | To be completed |  | 23 | SEPTEMBER
T-336-1056 | PS5-13-IK-5932B | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone H | 7 | In progress |  | 27 | DECEMBER
T-391-1057 | PS5-41-OB-4757D | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-03-11 | PS5-10-04 | PS5 - Milestone I | 8 | Closed | 9 | 34 | MARCH
T-269-1058 | PS5-68-UR-4516B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone B | 1.1 | On hold |  | 12 | NOVEMBER
T-736-1059 | PS5-27-UR-5506D | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-05-04 | PS5-03-23 | PS5 - Milestone F | 5 | Closed | 34 | 12 | MAY
T-845-1060 | PS5-62-OB-1851D | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone H | 7 | To be completed |  | 19 | DECEMBER
T-993-1061 | PS5-82-OB-6991B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone D | 3 | On hold |  | 15 | AUGUST
T-543-1062 | PS5-16-OB-5428A | CQS01 - Fire Protection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-06-04 | PS5-07-03 | PS5 - Milestone C | 2 | Closed | 39 | 19 | JUNE
T-195-1063 | PS5-37-OB-2618D | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone A | 1 | To be completed |  | 44 | OCTOBER
T-850-1064 | PS5-81-OB-1400C | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-03-10 | PS5-09-03 | PS5 - Milestone A | 1 | Closed | 33 | 18 | MARCH
T-316-1065 | PS5-33-OB-9236A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone D | 3 | To be completed |  | 5 | DECEMBER
T-054-1066 | PS5-19-IK-2826C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone C | 2 | On hold |  | 46 | NOVEMBER
T-587-1067 | PS5-75-OB-6827A | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone C | 2 | To be completed |  | 17 | SEPTEMBER
T-956-1068 | PS5-14-OB-1862B | CQE01 - HV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-02-14 | PS5-02-03 | PS5 - Milestone H | 7 | Closed | 5 | 13 | FEBRUARY
T-866-1069 | PS5-61-IK-2509A | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone G | 6 | To be completed |  | 17 | AUGUST
T-564-1070 | PS5-35-OB-2492C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone I | 8 | In progress |  | 27 | DECEMBER
T-165-1071 | PS5-25-OB-4173D | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone D | 3 | On hold |  | 12 | DECEMBER
T-160-1072 | PS5-49-UR-4808B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-12-28 | PS5-03-03 | PS5 - Milestone B | 1.1 | Closed | 28 | 33 | DECEMBER
T-347-1073 | PS5-97-IK-9098B | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-10-06 | PS5-05-03 | PS5 - Milestone F | 5 | Closed | 31 | 42 | OCTOBER
T-768-1074 | PS5-37-UR-4342B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-04-13 | PS5-10-03 | PS5 - Milestone F | 5 | Closed | 20 | 31 | APRIL
T-605-1075 | PS5-02-IK-6827D | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone G | 6 | To be completed |  | 14 | AUGUST
T-548-1076 | PS5-07-OB-5453A | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | In progress |  | 45 | SEPTEMBER
T-128-1077 | PS5-45-OB-6623A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-04-03 | PS5-01-06 | PS5 - Milestone D | 3 | Closed | 42 | 27 | APRIL
T-695-1078 | PS5-95-IK-4500D | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone B | 1.1 | To be completed |  | 7 | AUGUST
T-270-1079 | PS5-42-IK-8345B | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone I | 8 | To be completed |  | 40 | OCTOBER
T-396-1080 | PS5-68-UR-8822B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-11-19 | PS5-09-02 | PS5 - Milestone C | 2 | Closed | 41 | 35 | NOVEMBER
T-780-1081 | PS5-66-OB-6464C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-08-06 | PS5-01-08 | PS5 - Milestone H | 7 | Closed | 29 | 32 | AUGUST
T-496-1082 | PS5-10-UR-8604B | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-11-28 | PS5-13-01 | PS5 - Milestone B | 1.1 | Closed | 10 | 5 | NOVEMBER
T-466-1083 | PS5-08-IK-4340D | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-06-03 | PS5-04-03 | PS5 - Milestone F | 5 | Closed | 19 | 28 | JUNE
T-730-1084 | PS5-73-IK-2162C | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone A | 1 | To be completed |  | 35 | AUGUST
T-075-1085 | PS5-12-OB-2271D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-03-23 | PS5-01-02 | PS5 - Milestone G | 6 | Closed | 19 | 35 | MARCH
T-490-1086 | PS5-28-OB-7818D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | To be completed |  | 32 | DECEMBER
T-936-1087 | PS5-84-OB-8711B | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone H | 7 | In progress |  | 48 | AUGUST
T-389-1088 | PS5-13-OB-9628D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone B | 1.1 | To be completed |  | 33 | NOVEMBER
T-176-1089 | PS5-90-OB-4574D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-01-05 | PS5-01-01 | PS5 - Milestone H | 7 | Closed | 6 | 24 | JANUARY
T-746-1090 | PS5-76-OB-1085D | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-12-13 | PS5-01-05 | PS5 - Milestone B | 1.1 | Closed | 31 | 43 | DECEMBER
T-859-1091 | PS5-23-UR-3487B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone A | 1 | To be completed |  | 20 | AUGUST
T-891-1092 | PS5-20-IK-5148D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone I | 8 | To be completed |  | 42 | AUGUST
T-856-1093 | PS5-34-OB-6428C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | On hold |  | 43 | AUGUST
T-186-1094 | PS5-30-OB-8584C | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone C | 2 | To be completed |  | 32 | NOVEMBER
T-017-1095 | PS5-31-OB-9585B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | To be completed |  | 33 | AUGUST
T-946-1096 | PS5-39-OB-4774A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | To be completed |  | 28 | NOVEMBER
T-867-1097 | PS5-79-OB-1680B | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone H | 7 | To be completed |  | 11 | SEPTEMBER
T-475-1098 | PS5-92-OB-5016C | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone F | 5 | On hold |  | 32 | OCTOBER
T-152-1099 | PS5-23-OB-7186B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | To be completed |  | 38 | SEPTEMBER
T-666-1100 | PS5-08-UR-1492C | CQM03 - Heat Exchanger | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-07-23 | PS5-04-01 | PS5 - Milestone H | 7 | Closed | 10 | 23 | JULY
T-142-1101 | PS5-32-IK-6454C | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-07 | PS5-60-04 | PS5 - Milestone G | 6 | Closed | 28 | 30 | JUNE
T-622-1102 | PS5-82-UR-1086D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone I | 8 | On hold |  | 48 | NOVEMBER
T-691-1103 | PS5-59-OB-1131A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-11-13 | PS5-03-03 | PS5 - Milestone D | 3 | Closed | 9 | 11 | NOVEMBER
T-282-1104 | PS5-21-OB-2853B | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-04-03 | PS5-12-01 | PS5 - Milestone I | 8 | Closed | 29 | 25 | APRIL
T-842-1105 | PS5-96-UR-2978D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-11-12 | PS5-01-09 | PS5 - Milestone G | 6 | Closed | 6 | 45 | NOVEMBER
T-502-1106 | PS5-29-UR-1231C | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-04-01 | PS5-01-08 | PS5 - Milestone A | 1 | Closed | 40 | 22 | APRIL
T-832-1107 | PS5-57-OB-4708C | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-07-28 | PS5-63-01 | PS5 - Milestone G | 6 | Closed | 23 | 19 | JULY
T-873-1108 | PS5-24-OB-5781A | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone H | 7 | To be completed |  | 28 | AUGUST
T-512-1109 | PS5-39-UR-9850C | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone B | 1.1 | On hold |  | 23 | DECEMBER
T-901-1110 | PS5-44-UR-9327D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-04-18 | PS5-12-01 | PS5 - Milestone I | 8 | Closed | 14 | 45 | APRIL
T-711-1111 | PS5-38-OB-5580A | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-03-26 | PS5-11-01 | PS5 - Milestone H | 7 | Closed | 11 | 23 | MARCH
T-453-1112 | PS5-91-OB-7296D | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone B | 1.1 | In progress |  | 31 | OCTOBER
T-758-1113 | PS5-45-UR-6483D | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone D | 3 | In progress |  | 44 | AUGUST
T-839-1114 | PS5-46-UR-6102B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-11-24 | PS5-60-10 | PS5 - Milestone D | 3 | Closed | 35 | 6 | NOVEMBER
T-573-1115 | PS5-26-OB-3327D | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone B | 1.1 | To be completed |  | 44 | NOVEMBER
T-074-1116 | PS5-59-OB-4784B | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone F | 5 | In progress |  | 42 | OCTOBER
T-446-1117 | PS5-21-OB-4488C | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone I | 8 | To be completed |  | 16 | OCTOBER
T-679-1118 | PS5-69-OB-5804A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-11-20 | PS5-03-23 | PS5 - Milestone G | 6 | Closed | 34 | 25 | NOVEMBER
T-039-1119 | PS5-50-OB-2701C | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-01-23 | PS5-10-05 | PS5 - Milestone D | 3 | Closed | 38 | 24 | JANUARY
T-330-1120 | PS5-49-IK-6114D | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone E | 4 | To be completed |  | 12 | SEPTEMBER
T-566-1121 | PS5-42-UR-3369C | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-04-06 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 26 | 29 | APRIL
T-526-1122 | PS5-38-IK-5439B | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-10-17 | PS5-06-03 | PS5 - Milestone A | 1 | Closed | 5 | 4 | OCTOBER
T-891-1123 | PS5-13-UR-2590B | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-05-04 | PS5-10-02 | PS5 - Milestone F | 5 | Closed | 15 | 27 | MAY
T-898-1124 | PS5-08-OB-1956A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone G | 6 | To be completed |  | 25 | NOVEMBER
T-439-1125 | PS5-11-OB-7895C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone G | 6 | In progress |  | 26 | AUGUST
T-693-1126 | PS5-97-IK-4202C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | In progress |  | 36 | AUGUST
T-399-1127 | PS5-81-UR-9702D | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | To be completed |  | 17 | AUGUST
T-899-1128 | PS5-78-UR-2578B | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone B | 1.1 | To be completed |  | 37 | DECEMBER
T-703-1129 | PS5-41-UR-3066B | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone F | 5 | In progress |  | 9 | DECEMBER
T-815-1130 | PS5-96-OB-8987D | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone I | 8 | To be completed |  | 17 | NOVEMBER
T-822-1131 | PS5-24-IK-6614C | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | To be completed |  | 31 | SEPTEMBER
T-395-1132 | PS5-28-OB-8467A | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-07-25 | PS5-01-09 | PS5 - Milestone B | 1.1 | Closed | 25 | 20 | JULY
T-195-1133 | PS5-26-IK-7590A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone C | 2 | To be completed |  | 41 | AUGUST
T-120-1134 | PS5-66-OB-4566C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone H | 7 | In progress |  | 15 | OCTOBER
T-226-1135 | PS5-99-OB-6577A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-08-09 | PS5-04-01 | PS5 - Milestone F | 5 | Closed | 46 | 28 | AUGUST
T-303-1136 | PS5-62-OB-2281A | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone I | 8 | In progress |  | 25 | SEPTEMBER
T-862-1137 | PS5-49-IK-7910D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone E | 4 | To be completed |  | 6 | SEPTEMBER
T-265-1138 | PS5-40-OB-1548D | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-04-13 | PS5-99-02 | PS5 - Milestone A | 1 | Closed | 47 | 39 | APRIL
T-690-1139 | PS5-36-OB-5022B | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-09-06 | PS5-06-03 | PS5 - Milestone H | 7 | Closed | 15 | 34 | SEPTEMBER
T-407-1140 | PS5-37-OB-6892A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-04-03 | PS5-99-01 | PS5 - Milestone D | 3 | Closed | 21 | 34 | APRIL
T-479-1141 | PS5-90-OB-2397A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-06-28 | PS5-82-01 | PS5 - Milestone I | 8 | Closed | 9 | 33 | JUNE
T-024-1142 | PS5-69-UR-3177D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone B | 1.1 | To be completed |  | 29 | SEPTEMBER
T-967-1143 | PS5-50-IK-1990C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-03-01 | PS5-61-07 | PS5 - Milestone I | 8 | Closed | 24 | 12 | MARCH
T-828-1144 | PS5-29-UR-6526A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-12-15 | PS5-03-01 | PS5 - Milestone B | 1.1 | Closed | 42 | 27 | DECEMBER
T-776-1145 | PS5-92-OB-1880B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-12-03 | PS5-62-01 | PS5 - Milestone A | 1 | Closed | 37 | 31 | DECEMBER
T-975-1146 | PS5-82-UR-6493B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-16 | PS5-60-07 | PS5 - Milestone B | 1.1 | Closed | 8 | 21 | JULY
T-955-1147 | PS5-09-UR-1827A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone F | 5 | On hold |  | 40 | OCTOBER
T-417-1148 | PS5-92-IK-4003D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-02-22 | PS5-10-04 | PS5 - Milestone A | 1 | Closed | 19 | 17 | FEBRUARY
T-169-1149 | PS5-10-OB-8684C | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | In progress |  | 22 | AUGUST
T-728-1150 | PS5-44-OB-8866D | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-03-16 | PS5-05-03 | PS5 - Milestone B | 1.1 | Closed | 35 | 47 | MARCH
T-718-1151 | PS5-83-IK-2508C | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone B | 1.1 | To be completed |  | 34 | DECEMBER
T-449-1152 | PS5-21-UR-8236C | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone F | 5 | To be completed |  | 32 | DECEMBER
T-391-1153 | PS5-93-OB-1017C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone H | 7 | To be completed |  | 35 | DECEMBER
T-190-1154 | PS5-57-IK-4210A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-03-24 | PS5-01-01 | PS5 - Milestone C | 2 | Closed | 18 | 42 | MARCH
T-677-1155 | PS5-98-OB-9893C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | On hold |  | 23 | OCTOBER
T-029-1156 | PS5-83-UR-8707B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | To be completed |  | 35 | SEPTEMBER
T-768-1157 | PS5-54-IK-4360A | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-06-07 | PS5-10-01 | PS5 - Milestone F | 5 | Closed | 18 | 12 | JUNE
T-316-1158 | PS5-97-UR-7118C | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | In progress |  | 21 | SEPTEMBER
T-830-1159 | PS5-85-IK-9049B | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone H | 7 | To be completed |  | 39 | NOVEMBER
T-282-1160 | PS5-15-OB-4920C | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | On hold |  | 43 | SEPTEMBER
T-570-1161 | PS5-66-UR-7529C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-09-07 | PS5-08-02 | PS5 - Milestone D | 3 | Closed | 13 | 26 | SEPTEMBER
T-763-1162 | PS5-19-UR-6449A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-09-04 | PS5-63-01 | PS5 - Milestone D | 3 | Closed | 44 | 42 | SEPTEMBER
T-967-1163 | PS5-67-IK-7617A | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | To be completed |  | 17 | AUGUST
T-192-1164 | PS5-69-OB-1926B | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-03-24 | PS5-05-03 | PS5 - Milestone F | 5 | Closed | 32 | 38 | MARCH
T-274-1165 | PS5-56-UR-4558A | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone D | 3 | In progress |  | 35 | DECEMBER
T-158-1166 | PS5-36-OB-9160A | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone G | 6 | On hold |  | 37 | AUGUST
T-412-1167 | PS5-31-IK-8742A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-04-05 | PS5-03-03 | PS5 - Milestone I | 8 | Closed | 17 | 42 | APRIL
T-954-1168 | PS5-87-IK-4712C | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-01-01 | PS5-82-02 | PS5 - Milestone C | 2 | Closed | 26 | 37 | JANUARY
T-955-1169 | PS5-42-OB-5379C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone I | 8 | In progress |  | 33 | OCTOBER
T-105-1170 | PS5-92-OB-8984B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone H | 7 | To be completed |  | 42 | SEPTEMBER
T-959-1171 | PS5-31-UR-1559A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone C | 2 | To be completed |  | 12 | NOVEMBER
T-921-1172 | PS5-41-OB-5131B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-12-14 | PS5-12-02 | PS5 - Milestone A | 1 | Closed | 28 | 45 | DECEMBER
T-896-1173 | PS5-01-OB-1414B | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-03-25 | PS5-03-03 | PS5 - Milestone G | 6 | Closed | 43 | 47 | MARCH
T-890-1174 | PS5-34-IK-6223B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-10-08 | PS5-11-03 | PS5 - Milestone F | 5 | Closed | 15 | 17 | OCTOBER
T-674-1175 | PS5-11-OB-7586C | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-05-25 | PS5-04-01 | PS5 - Milestone B | 1.1 | Closed | 7 | 19 | MAY
T-381-1176 | PS5-91-OB-1213D | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | In progress |  | 17 | AUGUST
T-467-1177 | PS5-25-OB-7156C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-05-02 | PS5-03-03 | PS5 - Milestone B | 1.1 | Closed | 37 | 13 | MAY
T-802-1178 | PS5-83-UR-5700A | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-03-17 | PS5-09-04 | PS5 - Milestone F | 5 | Closed | 36 | 26 | MARCH
T-671-1179 | PS5-53-OB-5303C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-12-04 | PS5-10-06 | PS5 - Milestone G | 6 | Closed | 37 | 40 | DECEMBER
T-364-1180 | PS5-40-OB-2136C | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | On hold |  | 35 | OCTOBER
T-159-1181 | PS5-29-OB-1774D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone E | 4 | In progress |  | 4 | AUGUST
T-407-1182 | PS5-81-IK-7162B | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone G | 6 | In progress |  | 27 | SEPTEMBER
T-553-1183 | PS5-74-UR-8803C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-12-15 | PS5-11-03 | PS5 - Milestone A | 1 | Closed | 41 | 10 | DECEMBER
T-713-1184 | PS5-99-OB-1299C | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone E | 4 | In progress |  | 33 | SEPTEMBER
T-085-1185 | PS5-13-OB-1805A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone H | 7 | On hold |  | 47 | OCTOBER
T-629-1186 | PS5-69-UR-2601D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone H | 7 | To be completed |  | 14 | SEPTEMBER
T-273-1187 | PS5-82-UR-6970B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone I | 8 | To be completed |  | 39 | SEPTEMBER
T-932-1188 | PS5-72-IK-4526C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-09-02 | PS5-61-01 | PS5 - Milestone I | 8 | Closed | 27 | 7 | SEPTEMBER
T-467-1189 | PS5-80-IK-2746D | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-08-18 | PS5-10-05 | PS5 - Milestone E | 4 | Closed | 37 | 11 | AUGUST
T-039-1190 | PS5-01-OB-6954B | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | In progress |  | 29 | OCTOBER
T-512-1191 | PS5-64-OB-8103B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone I | 8 | In progress |  | 26 | SEPTEMBER
T-191-1192 | PS5-49-OB-5413C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone D | 3 | To be completed |  | 45 | DECEMBER
T-966-1193 | PS5-08-IK-4385A | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | In progress |  | 9 | NOVEMBER
T-489-1194 | PS5-25-IK-6025B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | In progress |  | 16 | AUGUST
T-573-1195 | PS5-21-UR-6672C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-08-25 | PS5-05-02 | PS5 - Milestone C | 2 | Closed | 37 | 21 | AUGUST
T-460-1196 | PS5-36-OB-8399A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-05-01 | PS5-03-23 | PS5 - Milestone D | 3 | Closed | 40 | 44 | MAY
T-130-1197 | PS5-65-UR-5737B | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone H | 7 | In progress |  | 9 | DECEMBER
T-529-1198 | PS5-56-UR-6099C | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | In progress |  | 31 | OCTOBER
T-507-1199 | PS5-89-IK-3936A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone A | 1 | To be completed |  | 28 | OCTOBER
T-489-1200 | PS5-55-IK-1118C | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone G | 6 | In progress |  | 21 | OCTOBER
T-660-1201 | PS5-14-IK-6649A | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone I | 8 | To be completed |  | 10 | AUGUST
T-182-1202 | PS5-77-OB-7985C | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-04-13 | PS5-12-01 | PS5 - Milestone F | 5 | Closed | 37 | 7 | APRIL
T-733-1203 | PS5-22-UR-1380D | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-09-10 | PS5-08-01 | PS5 - Milestone I | 8 | Closed | 33 | 5 | SEPTEMBER
T-369-1204 | PS5-92-OB-1779C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone E | 4 | In progress |  | 34 | AUGUST
T-173-1205 | PS5-27-OB-4636D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone A | 1 | To be completed |  | 24 | SEPTEMBER
T-478-1206 | PS5-30-IK-4454B | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone D | 3 | On hold |  | 30 | OCTOBER
T-866-1207 | PS5-48-OB-4190C | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone D | 3 | On hold |  | 43 | DECEMBER
T-481-1208 | PS5-33-OB-6148A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | To be completed |  | 19 | AUGUST
T-320-1209 | PS5-92-OB-3562C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-12-07 | PS5-60-04 | PS5 - Milestone E | 4 | Closed | 15 | 31 | DECEMBER
T-371-1210 | PS5-60-UR-9810C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-03-07 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 40 | 23 | MARCH
T-280-1211 | PS5-80-OB-8510B | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone C | 2 | To be completed |  | 10 | NOVEMBER
T-062-1212 | PS5-27-OB-1053A | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-08-14 | PS5-11-01 | PS5 - Milestone G | 6 | Closed | 8 | 19 | AUGUST
T-847-1213 | PS5-43-IK-6432D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-03-03 | PS5-99-02 | PS5 - Milestone F | 5 | Closed | 40 | 36 | MARCH
T-039-1214 | PS5-80-UR-6596C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-06-05 | PS5-61-07 | PS5 - Milestone I | 8 | Closed | 25 | 15 | JUNE
T-978-1215 | PS5-69-UR-5190B | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | To be completed |  | 34 | NOVEMBER
T-186-1216 | PS5-14-UR-4434C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-01-26 | PS5-61-02 | PS5 - Milestone B | 1.1 | Closed | 10 | 15 | JANUARY
T-960-1217 | PS5-22-OB-4779C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone I | 8 | To be completed |  | 12 | OCTOBER
T-332-1218 | PS5-16-OB-9003C | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone E | 4 | To be completed |  | 39 | OCTOBER
T-203-1219 | PS5-23-OB-4115B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-04-06 | PS5-02-02 | PS5 - Milestone B | 1.1 | Closed | 30 | 43 | APRIL
T-584-1220 | PS5-59-UR-3883A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-02-02 | PS5-07-01 | PS5 - Milestone D | 3 | Closed | 26 | 22 | FEBRUARY
T-009-1221 | PS5-24-UR-6402B | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone C | 2 | On hold |  | 47 | NOVEMBER
T-715-1222 | PS5-72-OB-9117D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-10-24 | PS5-01-02 | PS5 - Milestone I | 8 | Closed | 40 | 40 | OCTOBER
T-989-1223 | PS5-85-OB-1143A | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone B | 1.1 | To be completed |  | 27 | NOVEMBER
T-210-1224 | PS5-22-OB-1561A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-04-15 | PS5-03-03 | PS5 - Milestone H | 7 | Closed | 41 | 42 | APRIL
T-074-1225 | PS5-12-OB-3647D | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone G | 6 | In progress |  | 46 | DECEMBER
T-703-1226 | PS5-38-UR-2280A | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-08-07 | PS5-12-01 | PS5 - Milestone B | 1.1 | Closed | 35 | 8 | AUGUST
T-627-1227 | PS5-58-UR-6435D | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone A | 1 | In progress |  | 20 | AUGUST
T-727-1228 | PS5-71-OB-1743B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-03-24 | PS5-06-02 | PS5 - Milestone B | 1.1 | Closed | 4 | 43 | MARCH
T-005-1229 | PS5-46-OB-6712A | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-06-04 | PS5-01-06 | PS5 - Milestone E | 4 | Closed | 19 | 47 | JUNE
T-178-1230 | PS5-53-IK-8409A | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone E | 4 | On hold |  | 48 | NOVEMBER
T-552-1231 | PS5-11-OB-5639C | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone E | 4 | To be completed |  | 27 | OCTOBER
T-585-1232 | PS5-13-OB-3710A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-08-26 | PS5-60-10 | PS5 - Milestone I | 8 | Closed | 28 | 28 | AUGUST
T-725-1233 | PS5-02-OB-5044B | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone C | 2 | To be completed |  | 47 | SEPTEMBER
T-689-1234 | PS5-45-UR-4919B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | In progress |  | 38 | AUGUST
T-206-1235 | PS5-60-OB-9066A | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | In progress |  | 24 | DECEMBER
T-458-1236 | PS5-98-IK-2100A | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone D | 3 | To be completed |  | 8 | NOVEMBER
T-147-1237 | PS5-53-OB-4235A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | In progress |  | 17 | DECEMBER
T-203-1238 | PS5-91-OB-8079B | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-04-03 | PS5-01-04 | PS5 - Milestone D | 3 | Closed | 23 | 30 | APRIL
T-853-1239 | PS5-40-IK-4063D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone B | 1.1 | In progress |  | 43 | SEPTEMBER
T-183-1240 | PS5-16-OB-1002D | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone G | 6 | On hold |  | 4 | DECEMBER
T-270-1241 | PS5-59-UR-1136D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone B | 1.1 | To be completed |  | 25 | OCTOBER
T-107-1242 | PS5-03-IK-3054B | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone G | 6 | To be completed |  | 29 | OCTOBER
T-703-1243 | PS5-41-IK-4321B | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone E | 4 | In progress |  | 45 | SEPTEMBER
T-007-1244 | PS5-12-UR-4377A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone H | 7 | In progress |  | 39 | DECEMBER
T-306-1245 | PS5-78-IK-2540D | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone H | 7 | To be completed |  | 23 | AUGUST
T-410-1246 | PS5-04-OB-9444D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone G | 6 | On hold |  | 36 | DECEMBER
T-691-1247 | PS5-48-UR-4112A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | In progress |  | 32 | DECEMBER
T-756-1248 | PS5-96-OB-2166A | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | In progress |  | 34 | AUGUST
T-609-1249 | PS5-81-UR-1576B | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-11-19 | PS5-01-04 | PS5 - Milestone C | 2 | Closed | 6 | 17 | NOVEMBER
T-644-1250 | PS5-98-OB-8693D | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone I | 8 | To be completed |  | 46 | AUGUST
T-403-1251 | PS5-01-IK-3987A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone H | 7 | On hold |  | 30 | DECEMBER
T-922-1252 | PS5-52-UR-1380B | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-06-15 | PS5-03-02 | PS5 - Milestone E | 4 | Closed | 47 | 47 | JUNE
T-533-1253 | PS5-35-UR-4579C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | To be completed |  | 9 | AUGUST
T-588-1254 | PS5-44-OB-5624B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone H | 7 | In progress |  | 14 | OCTOBER
T-783-1255 | PS5-15-OB-2416C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-03-23 | PS5-03-01 | PS5 - Milestone C | 2 | Closed | 47 | 30 | MARCH
T-249-1256 | PS5-65-OB-4208B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-02-21 | PS5-09-03 | PS5 - Milestone A | 1 | Closed | 24 | 34 | FEBRUARY
T-277-1257 | PS5-16-IK-3107B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone A | 1 | In progress |  | 38 | NOVEMBER
T-734-1258 | PS5-56-OB-9199B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone B | 1.1 | To be completed |  | 16 | AUGUST
T-567-1259 | PS5-48-OB-2978D | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-06-17 | PS5-01-08 | PS5 - Milestone B | 1.1 | Closed | 22 | 28 | JUNE
T-806-1260 | PS5-35-OB-9812A | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | To be completed |  | 19 | DECEMBER
T-409-1261 | PS5-72-UR-8588C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone D | 3 | In progress |  | 39 | AUGUST
T-513-1262 | PS5-86-OB-1748B | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone I | 8 | On hold |  | 45 | DECEMBER
T-223-1263 | PS5-15-OB-5883D | CQM01 - Pump Installation | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone D | 3 | On hold |  | 44 | SEPTEMBER
T-644-1264 | PS5-76-IK-3403D | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone D | 3 | To be completed |  | 18 | NOVEMBER
T-286-1265 | PS5-47-OB-2002B | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-09-24 | PS5-01-03 | PS5 - Milestone A | 1 | Closed | 9 | 46 | SEPTEMBER
T-722-1266 | PS5-14-OB-7585C | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone A | 1 | To be completed |  | 30 | AUGUST
T-111-1267 | PS5-69-OB-7442C | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-09-10 | PS5-04-02 | PS5 - Milestone A | 1 | Closed | 21 | 20 | SEPTEMBER
T-802-1268 | PS5-74-OB-4211C | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | In progress |  | 5 | NOVEMBER
T-918-1269 | PS5-80-OB-2024B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-02-16 | PS5-61-01 | PS5 - Milestone A | 1 | Closed | 28 | 31 | FEBRUARY
T-528-1270 | PS5-33-OB-5992B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | To be completed |  | 27 | DECEMBER
T-407-1271 | PS5-50-OB-8496A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone C | 2 | In progress |  | 11 | OCTOBER
T-644-1272 | PS5-68-UR-7016C | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone C | 2 | On hold |  | 41 | DECEMBER
T-360-1273 | PS5-04-UR-4072B | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-03-12 | PS5-61-01 | PS5 - Milestone C | 2 | Closed | 44 | 36 | MARCH
T-289-1274 | PS5-19-UR-9126C | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone I | 8 | To be completed |  | 11 | AUGUST
T-010-1275 | PS5-07-UR-9027D | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone D | 3 | On hold |  | 26 | AUGUST
T-857-1276 | PS5-46-OB-9982B | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone B | 1.1 | To be completed |  | 42 | OCTOBER
T-403-1277 | PS5-25-OB-2114D | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-12-20 | PS5-10-06 | PS5 - Milestone A | 1 | Closed | 11 | 37 | DECEMBER
T-425-1278 | PS5-90-UR-7370D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-07-05 | PS5-61-02 | PS5 - Milestone E | 4 | Closed | 34 | 8 | JULY
T-369-1279 | PS5-35-OB-9845C | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-11-26 | PS5-63-04 | PS5 - Milestone F | 5 | Closed | 44 | 20 | NOVEMBER
T-826-1280 | PS5-61-IK-6537A | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-08-02 | PS5-04-02 | PS5 - Milestone E | 4 | Closed | 20 | 22 | AUGUST
T-208-1281 | PS5-68-OB-2019B | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone H | 7 | On hold |  | 9 | AUGUST
T-682-1282 | PS5-98-OB-6089A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | To be completed |  | 23 | SEPTEMBER
T-241-1283 | PS5-07-OB-4963B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-04-14 | PS5-62-01 | PS5 - Milestone D | 3 | Closed | 23 | 29 | APRIL
T-431-1284 | PS5-14-OB-8544D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone C | 2 | On hold |  | 7 | OCTOBER
T-022-1285 | PS5-77-IK-2934A | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-07-15 | PS5-01-01 | PS5 - Milestone B | 1.1 | Closed | 26 | 29 | JULY
T-467-1286 | PS5-98-IK-7121A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone H | 7 | To be completed |  | 20 | SEPTEMBER
T-511-1287 | PS5-48-OB-3535D | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone B | 1.1 | In progress |  | 15 | AUGUST
T-201-1288 | PS5-59-OB-2925C | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | In progress |  | 29 | DECEMBER
T-235-1289 | PS5-83-OB-8890D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-03-24 | PS5-63-04 | PS5 - Milestone C | 2 | Closed | 34 | 43 | MARCH
T-292-1290 | PS5-20-OB-9327D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | In progress |  | 35 | AUGUST
T-844-1291 | PS5-39-IK-2437D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone H | 7 | In progress |  | 21 | NOVEMBER
T-190-1292 | PS5-86-OB-4404B | CQH02 - AHU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone D | 3 | In progress |  | 33 | AUGUST
T-454-1293 | PS5-39-OB-7677D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone D | 3 | On hold |  | 46 | OCTOBER
T-898-1294 | PS5-53-OB-8177C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-03-16 | PS5-01-03 | PS5 - Milestone D | 3 | Closed | 15 | 4 | MARCH
T-217-1295 | PS5-34-OB-6414A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-07-06 | PS5-01-04 | PS5 - Milestone F | 5 | Closed | 24 | 11 | JULY
T-051-1296 | PS5-69-OB-9339B | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone B | 1.1 | To be completed |  | 44 | DECEMBER
T-427-1297 | PS5-60-OB-2753D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-08-01 | PS5-62-01 | PS5 - Milestone G | 6 | Closed | 25 | 27 | AUGUST
T-707-1298 | PS5-85-IK-8967C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone G | 6 | To be completed |  | 16 | NOVEMBER
T-087-1299 | PS5-28-OB-9199A | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | To be completed |  | 21 | SEPTEMBER
T-300-1300 | PS5-88-UR-3452C | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone I | 8 | In progress |  | 42 | OCTOBER
T-532-1301 | PS5-32-IK-9404C | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-07-13 | PS5-06-02 | PS5 - Milestone C | 2 | Closed | 28 | 42 | JULY
T-148-1302 | PS5-61-OB-4105B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone C | 2 | On hold |  | 20 | DECEMBER
T-955-1303 | PS5-04-IK-8657C | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | In progress |  | 30 | DECEMBER
T-277-1304 | PS5-35-IK-7370D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-09-18 | PS5-61-07 | PS5 - Milestone E | 4 | Closed | 9 | 13 | SEPTEMBER
T-531-1305 | PS5-12-OB-3346A | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone A | 1 | On hold |  | 8 | DECEMBER
T-300-1306 | PS5-14-OB-6438A | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | In progress |  | 4 | DECEMBER
T-990-1307 | PS5-93-OB-1435B | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone H | 7 | In progress |  | 33 | AUGUST
T-798-1308 | PS5-08-UR-3299A | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone C | 2 | In progress |  | 46 | NOVEMBER
T-181-1309 | PS5-10-OB-5548D | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-04-02 | PS5-09-01 | PS5 - Milestone D | 3 | Closed | 43 | 30 | APRIL
T-756-1310 | PS5-79-UR-4375A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone E | 4 | To be completed |  | 21 | SEPTEMBER
T-723-1311 | PS5-87-UR-5917B | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone F | 5 | To be completed |  | 25 | AUGUST
T-830-1312 | PS5-97-OB-9624D | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone F | 5 | On hold |  | 47 | SEPTEMBER
T-588-1313 | PS5-36-OB-9656B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | In progress |  | 10 | DECEMBER
T-197-1314 | PS5-88-UR-8758B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-09-23 | PS5-01-02 | PS5 - Milestone D | 3 | Closed | 35 | 44 | SEPTEMBER
T-954-1315 | PS5-67-OB-9005A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone G | 6 | To be completed |  | 44 | SEPTEMBER
T-579-1316 | PS5-52-IK-4614C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-10-23 | PS5-99-02 | PS5 - Milestone A | 1 | Closed | 19 | 26 | OCTOBER
T-008-1317 | PS5-88-OB-1067A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone D | 3 | In progress |  | 15 | AUGUST
T-395-1318 | PS5-99-OB-9669C | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | To be completed |  | 31 | DECEMBER
T-831-1319 | PS5-60-IK-2632D | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-02-10 | PS5-02-01 | PS5 - Milestone H | 7 | Closed | 16 | 40 | FEBRUARY
T-190-1320 | PS5-60-UR-2984B | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone G | 6 | To be completed |  | 26 | NOVEMBER
T-161-1321 | PS5-36-OB-8003C | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone E | 4 | To be completed |  | 44 | NOVEMBER
T-880-1322 | PS5-16-IK-3716C | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-08-13 | PS5-62-01 | PS5 - Milestone E | 4 | Closed | 5 | 4 | AUGUST
T-779-1323 | PS5-61-UR-9317D | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | To be completed |  | 15 | NOVEMBER
T-278-1324 | PS5-43-OB-2894B | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone I | 8 | To be completed |  | 35 | SEPTEMBER
T-022-1325 | PS5-45-OB-3008C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone H | 7 | On hold |  | 45 | AUGUST
T-060-1326 | PS5-17-OB-7371D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone D | 3 | To be completed |  | 9 | DECEMBER
T-339-1327 | PS5-13-UR-2796C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone F | 5 | To be completed |  | 39 | OCTOBER
T-110-1328 | PS5-86-UR-9874A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-05-09 | PS5-06-02 | PS5 - Milestone H | 7 | Closed | 47 | 23 | MAY
T-484-1329 | PS5-58-UR-4744D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone C | 2 | To be completed |  | 6 | OCTOBER
T-191-1330 | PS5-61-UR-2294C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone G | 6 | To be completed |  | 28 | OCTOBER
T-121-1331 | PS5-65-OB-7360A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone H | 7 | In progress |  | 28 | NOVEMBER
T-323-1332 | PS5-65-OB-5984A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone B | 1.1 | To be completed |  | 19 | AUGUST
T-595-1333 | PS5-13-OB-2967C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone F | 5 | On hold |  | 29 | AUGUST
T-429-1334 | PS5-99-UR-6543D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-05-22 | PS5-07-02 | PS5 - Milestone E | 4 | Closed | 19 | 7 | MAY
T-765-1335 | PS5-38-OB-1642C | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone F | 5 | To be completed |  | 18 | OCTOBER
T-521-1336 | PS5-27-IK-1771B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-08-24 | PS5-08-01 | PS5 - Milestone B | 1.1 | Closed | 44 | 16 | AUGUST
T-009-1337 | PS5-29-IK-1712A | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone B | 1.1 | To be completed |  | 35 | NOVEMBER
T-657-1338 | PS5-68-OB-1294D | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone B | 1.1 | In progress |  | 4 | AUGUST
T-940-1339 | PS5-02-OB-2534C | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-12-04 | PS5-07-04 | PS5 - Milestone D | 3 | Closed | 45 | 40 | DECEMBER
T-275-1340 | PS5-37-UR-8344C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-10-05 | PS5-03-02 | PS5 - Milestone F | 5 | Closed | 24 | 28 | OCTOBER
T-936-1341 | PS5-51-IK-8260B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-06-23 | PS5-10-04 | PS5 - Milestone G | 6 | Closed | 44 | 41 | JUNE
T-810-1342 | PS5-29-UR-9555D | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-10-06 | PS5-10-02 | PS5 - Milestone I | 8 | Closed | 28 | 26 | OCTOBER
T-424-1343 | PS5-88-OB-7308C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-09-03 | PS5-03-23 | PS5 - Milestone H | 7 | Closed | 40 | 14 | SEPTEMBER
T-945-1344 | PS5-38-OB-7081D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-12-26 | PS5-63-01 | PS5 - Milestone A | 1 | Closed | 46 | 24 | DECEMBER
T-752-1345 | PS5-53-UR-4148C | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | To be completed |  | 34 | AUGUST
T-838-1346 | PS5-44-OB-1855B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone D | 3 | In progress |  | 38 | SEPTEMBER
T-071-1347 | PS5-32-UR-1049C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-03-03 | PS5-09-02 | PS5 - Milestone G | 6 | Closed | 32 | 47 | MARCH
T-059-1348 | PS5-66-UR-9161D | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-06-25 | PS5-01-02 | PS5 - Milestone C | 2 | Closed | 42 | 41 | JUNE
T-642-1349 | PS5-11-OB-6083D | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone G | 6 | To be completed |  | 44 | OCTOBER
T-389-1350 | PS5-31-IK-4310B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone H | 7 | To be completed |  | 7 | OCTOBER
T-624-1351 | PS5-49-UR-9068A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-08-06 | PS5-03-02 | PS5 - Milestone G | 6 | Closed | 19 | 13 | AUGUST
T-116-1352 | PS5-01-IK-6465C | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone G | 6 | In progress |  | 42 | DECEMBER
T-110-1353 | PS5-72-OB-1530B | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone H | 7 | On hold |  | 23 | SEPTEMBER
T-858-1354 | PS5-45-IK-5915B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone B | 1.1 | To be completed |  | 15 | OCTOBER
T-674-1355 | PS5-53-OB-4168A | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-05-24 | PS5-07-01 | PS5 - Milestone F | 5 | Closed | 16 | 18 | MAY
T-186-1356 | PS5-41-OB-2053D | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | In progress |  | 27 | OCTOBER
T-522-1357 | PS5-81-OB-4407B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | To be completed |  | 25 | DECEMBER
T-587-1358 | PS5-03-IK-4216D | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone E | 4 | On hold |  | 8 | OCTOBER
T-801-1359 | PS5-27-UR-8467A | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-11-24 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 43 | 45 | NOVEMBER
T-577-1360 | PS5-13-UR-1281B | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone G | 6 | On hold |  | 10 | NOVEMBER
T-599-1361 | PS5-29-UR-8020B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-11-08 | PS5-07-02 | PS5 - Milestone D | 3 | Closed | 11 | 11 | NOVEMBER
T-779-1362 | PS5-69-OB-9394A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-01-01 | PS5-10-02 | PS5 - Milestone B | 1.1 | Closed | 45 | 43 | JANUARY
T-701-1363 | PS5-92-OB-1128B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone F | 5 | In progress |  | 10 | NOVEMBER
T-214-1364 | PS5-11-IK-5050B | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone C | 2 | To be completed |  | 38 | SEPTEMBER
T-275-1365 | PS5-58-OB-2475D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-05-23 | PS5-04-02 | PS5 - Milestone E | 4 | Closed | 14 | 38 | MAY
T-136-1366 | PS5-77-OB-1064A | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | To be completed |  | 45 | AUGUST
T-879-1367 | PS5-56-UR-8421D | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone D | 3 | On hold |  | 17 | SEPTEMBER
T-491-1368 | PS5-45-OB-5546B | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone C | 2 | To be completed |  | 9 | SEPTEMBER
T-398-1369 | PS5-89-IK-3990D | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone E | 4 | To be completed |  | 41 | OCTOBER
T-329-1370 | PS5-01-OB-8910B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-05-24 | PS5-04-01 | PS5 - Milestone E | 4 | Closed | 35 | 12 | MAY
T-725-1371 | PS5-55-UR-4067A | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone H | 7 | On hold |  | 32 | OCTOBER
T-442-1372 | PS5-15-IK-3816D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-03-10 | PS5-03-23 | PS5 - Milestone E | 4 | Closed | 47 | 47 | MARCH
T-744-1373 | PS5-61-OB-9217C | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-09-28 | PS5-01-01 | PS5 - Milestone F | 5 | Closed | 6 | 41 | SEPTEMBER
T-505-1374 | PS5-73-OB-4466A | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | To be completed |  | 41 | SEPTEMBER
T-860-1375 | PS5-60-UR-6455D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone C | 2 | To be completed |  | 46 | SEPTEMBER
T-567-1376 | PS5-01-OB-8759C | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-03-27 | PS5-07-02 | PS5 - Milestone C | 2 | Closed | 34 | 38 | MARCH
T-521-1377 | PS5-66-IK-3648D | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone B | 1.1 | To be completed |  | 24 | SEPTEMBER
T-600-1378 | PS5-80-OB-5747C | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | To be completed |  | 10 | NOVEMBER
T-485-1379 | PS5-17-IK-1350D | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-07-10 | PS5-03-03 | PS5 - Milestone F | 5 | Closed | 42 | 40 | JULY
T-646-1380 | PS5-63-OB-6492B | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-04-23 | PS5-99-03 | PS5 - Milestone E | 4 | Closed | 46 | 15 | APRIL
T-481-1381 | PS5-12-OB-1771A | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-08-22 | PS5-10-06 | PS5 - Milestone H | 7 | Closed | 29 | 18 | AUGUST
T-331-1382 | PS5-69-OB-7888A | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone B | 1.1 | To be completed |  | 46 | OCTOBER
T-118-1383 | PS5-90-IK-5207C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone I | 8 | To be completed |  | 43 | OCTOBER
T-315-1384 | PS5-71-OB-5564A | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone F | 5 | In progress |  | 32 | SEPTEMBER
T-256-1385 | PS5-72-UR-3968B | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-02-27 | PS5-01-03 | PS5 - Milestone A | 1 | Closed | 14 | 28 | FEBRUARY
T-069-1386 | PS5-58-OB-6674B | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-11-19 | PS5-09-02 | PS5 - Milestone F | 5 | Closed | 41 | 39 | NOVEMBER
T-634-1387 | PS5-35-OB-9593A | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-09-20 | PS5-07-02 | PS5 - Milestone E | 4 | Closed | 6 | 4 | SEPTEMBER
T-606-1388 | PS5-98-UR-7379D | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-04-07 | PS5-10-06 | PS5 - Milestone G | 6 | Closed | 48 | 19 | APRIL
T-064-1389 | PS5-49-OB-2806A | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone F | 5 | In progress |  | 43 | NOVEMBER
T-223-1390 | PS5-93-OB-5739C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-10-06 | PS5-13-01 | PS5 - Milestone B | 1.1 | Closed | 26 | 38 | OCTOBER
T-943-1391 | PS5-60-OB-3421D | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone B | 1.1 | In progress |  | 39 | OCTOBER
T-646-1392 | PS5-28-OB-9036C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-03-02 | PS5-01-01 | PS5 - Milestone H | 7 | Closed | 33 | 31 | MARCH
T-758-1393 | PS5-57-OB-7858A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone C | 2 | In progress |  | 10 | AUGUST
T-263-1394 | PS5-85-UR-6655C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone I | 8 | In progress |  | 24 | NOVEMBER
T-612-1395 | PS5-51-OB-5165C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone C | 2 | To be completed |  | 5 | NOVEMBER
T-667-1396 | PS5-96-IK-3370D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone A | 1 | On hold |  | 19 | OCTOBER
T-662-1397 | PS5-39-UR-1231D | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone A | 1 | On hold |  | 24 | NOVEMBER
T-778-1398 | PS5-08-OB-8170C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone A | 1 | On hold |  | 24 | AUGUST
T-178-1399 | PS5-27-UR-6867A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-03-15 | PS5-61-02 | PS5 - Milestone I | 8 | Closed | 9 | 33 | MARCH
T-197-1400 | PS5-43-IK-3237D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone G | 6 | In progress |  | 4 | SEPTEMBER
T-335-1401 | PS5-88-UR-1705B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-11-21 | PS5-04-01 | PS5 - Milestone D | 3 | Closed | 29 | 34 | NOVEMBER
T-416-1402 | PS5-38-UR-6304D | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-04-08 | PS5-01-03 | PS5 - Milestone H | 7 | Closed | 39 | 33 | APRIL
T-355-1403 | PS5-20-OB-5151B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone B | 1.1 | To be completed |  | 8 | NOVEMBER
T-779-1404 | PS5-71-OB-8640A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone D | 3 | To be completed |  | 9 | SEPTEMBER
T-560-1405 | PS5-70-UR-4195B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | On hold |  | 8 | OCTOBER
T-157-1406 | PS5-45-UR-7733B | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone E | 4 | On hold |  | 35 | NOVEMBER
T-392-1407 | PS5-45-UR-4410D | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone A | 1 | In progress |  | 12 | OCTOBER
T-225-1408 | PS5-85-UR-6826D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | To be completed |  | 43 | NOVEMBER
T-745-1409 | PS5-08-OB-8719B | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | To be completed |  | 7 | NOVEMBER
T-981-1410 | PS5-88-IK-7428A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | To be completed |  | 15 | DECEMBER
T-564-1411 | PS5-77-IK-4449B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-12-12 | PS5-10-04 | PS5 - Milestone F | 5 | Closed | 12 | 33 | DECEMBER
T-794-1412 | PS5-53-OB-6847B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone A | 1 | In progress |  | 24 | OCTOBER
T-173-1413 | PS5-84-IK-6611C | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone F | 5 | On hold |  | 20 | OCTOBER
T-164-1414 | PS5-19-UR-4497C | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-11-26 | PS5-02-01 | PS5 - Milestone G | 6 | Closed | 21 | 44 | NOVEMBER
T-996-1415 | PS5-43-OB-5300A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-11-13 | PS5-09-04 | PS5 - Milestone H | 7 | Closed | 33 | 12 | NOVEMBER
T-242-1416 | PS5-69-UR-8220B | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-02-08 | PS5-09-01 | PS5 - Milestone C | 2 | Closed | 29 | 11 | FEBRUARY
T-455-1417 | PS5-23-OB-7770D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone F | 5 | To be completed |  | 46 | DECEMBER
T-055-1418 | PS5-92-OB-6630D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone H | 7 | To be completed |  | 40 | OCTOBER
T-016-1419 | PS5-57-UR-9197B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone D | 3 | On hold |  | 24 | DECEMBER
T-427-1420 | PS5-18-OB-9228B | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone F | 5 | In progress |  | 44 | AUGUST
T-238-1421 | PS5-65-OB-5997B | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | On hold |  | 26 | NOVEMBER
T-252-1422 | PS5-70-IK-6266B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone H | 7 | To be completed |  | 4 | OCTOBER
T-134-1423 | PS5-07-IK-5014A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone C | 2 | To be completed |  | 43 | DECEMBER
T-420-1424 | PS5-76-OB-1747D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone C | 2 | To be completed |  | 47 | OCTOBER
T-703-1425 | PS5-03-OB-8878B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-12-14 | PS5-06-03 | PS5 - Milestone I | 8 | Closed | 22 | 41 | DECEMBER
T-343-1426 | PS5-25-OB-2936A | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | In progress |  | 47 | SEPTEMBER
T-940-1427 | PS5-56-IK-5759A | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone E | 4 | In progress |  | 21 | AUGUST
T-914-1428 | PS5-45-IK-6247D | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-06-25 | PS5-06-01 | PS5 - Milestone B | 1.1 | Closed | 29 | 45 | JUNE
T-838-1429 | PS5-27-OB-1881B | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone F | 5 | To be completed |  | 39 | OCTOBER
T-034-1430 | PS5-52-IK-3949C | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-07-17 | PS5-06-03 | PS5 - Milestone C | 2 | Closed | 23 | 16 | JULY
T-671-1431 | PS5-57-OB-8544C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-02-09 | PS5-10-05 | PS5 - Milestone C | 2 | Closed | 20 | 12 | FEBRUARY
T-488-1432 | PS5-94-OB-1772D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone F | 5 | To be completed |  | 41 | AUGUST
T-318-1433 | PS5-14-IK-9182D | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-05-18 | PS5-11-03 | PS5 - Milestone A | 1 | Closed | 47 | 36 | MAY
T-470-1434 | PS5-81-OB-2033B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | In progress |  | 47 | SEPTEMBER
T-796-1435 | PS5-83-OB-5993A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-01-25 | PS5-10-04 | PS5 - Milestone H | 7 | Closed | 40 | 15 | JANUARY
T-800-1436 | PS5-57-IK-7686C | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone H | 7 | In progress |  | 32 | AUGUST
T-983-1437 | PS5-52-IK-7087D | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone D | 3 | To be completed |  | 8 | NOVEMBER
T-752-1438 | PS5-95-UR-3839B | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone G | 6 | In progress |  | 9 | OCTOBER
T-081-1439 | PS5-07-OB-2470C | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone I | 8 | To be completed |  | 9 | DECEMBER
T-605-1440 | PS5-36-UR-4093D | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-06-22 | PS5-10-04 | PS5 - Milestone H | 7 | Closed | 8 | 15 | JUNE
T-601-1441 | PS5-24-OB-9477C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone I | 8 | To be completed |  | 21 | DECEMBER
T-642-1442 | PS5-14-IK-5787B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone E | 4 | In progress |  | 44 | NOVEMBER
T-029-1443 | PS5-66-OB-4945A | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-03-26 | PS5-01-01 | PS5 - Milestone H | 7 | Closed | 21 | 26 | MARCH
T-720-1444 | PS5-77-OB-3267C | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-12-07 | PS5-62-02 | PS5 - Milestone F | 5 | Closed | 13 | 32 | DECEMBER
T-616-1445 | PS5-08-IK-5691B | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-10-10 | PS5-61-02 | PS5 - Milestone C | 2 | Closed | 19 | 35 | OCTOBER
T-983-1446 | PS5-88-OB-1225C | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone A | 1 | To be completed |  | 34 | SEPTEMBER
T-007-1447 | PS5-79-UR-3445A | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone H | 7 | To be completed |  | 12 | OCTOBER
T-236-1448 | PS5-22-OB-3353A | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-09-27 | PS5-60-10 | PS5 - Milestone A | 1 | Closed | 21 | 8 | SEPTEMBER
T-689-1449 | PS5-22-UR-4138A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-05-25 | PS5-01-08 | PS5 - Milestone I | 8 | Closed | 23 | 31 | MAY
T-661-1450 | PS5-30-OB-6210C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone H | 7 | To be completed |  | 15 | SEPTEMBER
T-734-1451 | PS5-07-IK-9452D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-08-05 | PS5-09-02 | PS5 - Milestone F | 5 | Closed | 44 | 43 | AUGUST
T-262-1452 | PS5-66-IK-1855C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone E | 4 | On hold |  | 32 | SEPTEMBER
T-657-1453 | PS5-59-OB-4984D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-07-22 | PS5-07-03 | PS5 - Milestone C | 2 | Closed | 28 | 34 | JULY
T-234-1454 | PS5-30-IK-4643C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-02-24 | PS5-99-03 | PS5 - Milestone F | 5 | Closed | 41 | 6 | FEBRUARY
T-391-1455 | PS5-98-OB-3765B | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone I | 8 | On hold |  | 37 | OCTOBER
T-819-1456 | PS5-79-IK-3593A | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-03-09 | PS5-04-04 | PS5 - Milestone A | 1 | Closed | 33 | 24 | MARCH
T-068-1457 | PS5-15-OB-6262C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-03-02 | PS5-03-03 | PS5 - Milestone H | 7 | Closed | 29 | 33 | MARCH
T-269-1458 | PS5-89-OB-9043D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone H | 7 | In progress |  | 35 | NOVEMBER
T-944-1459 | PS5-02-UR-4675B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-10-28 | PS5-01-07 | PS5 - Milestone D | 3 | Closed | 34 | 11 | OCTOBER
T-772-1460 | PS5-48-IK-4371A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-01-25 | PS5-10-05 | PS5 - Milestone A | 1 | Closed | 32 | 18 | JANUARY
T-557-1461 | PS5-64-IK-8577A | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-09-17 | PS5-04-04 | PS5 - Milestone F | 5 | Closed | 45 | 41 | SEPTEMBER
T-898-1462 | PS5-74-OB-1638B | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-09-08 | PS5-82-07 | PS5 - Milestone I | 8 | Closed | 31 | 33 | SEPTEMBER
T-494-1463 | PS5-06-OB-7223C | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-10-03 | PS5-06-03 | PS5 - Milestone A | 1 | Closed | 30 | 20 | OCTOBER
T-453-1464 | PS5-23-IK-6476D | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-01-04 | PS5-09-04 | PS5 - Milestone B | 1.1 | Closed | 10 | 36 | JANUARY
T-952-1465 | PS5-24-OB-7100A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-04-01 | PS5-99-02 | PS5 - Milestone C | 2 | Closed | 14 | 35 | APRIL
T-558-1466 | PS5-21-OB-8569B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-05-03 | PS5-08-01 | PS5 - Milestone B | 1.1 | Closed | 41 | 32 | MAY
T-722-1467 | PS5-39-OB-6429C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | To be completed |  | 7 | NOVEMBER
T-810-1468 | PS5-21-UR-2529D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone E | 4 | On hold |  | 16 | AUGUST
T-035-1469 | PS5-62-OB-9854A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-09-03 | PS5-01-03 | PS5 - Milestone F | 5 | Closed | 37 | 14 | SEPTEMBER
T-328-1470 | PS5-08-OB-4258A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone H | 7 | To be completed |  | 14 | AUGUST
T-534-1471 | PS5-64-UR-5754B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone E | 4 | To be completed |  | 47 | OCTOBER
T-891-1472 | PS5-01-OB-2976A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone H | 7 | To be completed |  | 38 | NOVEMBER
T-560-1473 | PS5-64-OB-1476C | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone H | 7 | To be completed |  | 8 | OCTOBER
T-037-1474 | PS5-23-OB-3807A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone C | 2 | To be completed |  | 10 | OCTOBER
T-819-1475 | PS5-70-UR-9192B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | To be completed |  | 10 | OCTOBER
T-515-1476 | PS5-98-OB-3514B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | To be completed |  | 29 | AUGUST
T-632-1477 | PS5-79-UR-8791B | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone H | 7 | To be completed |  | 30 | NOVEMBER
T-300-1478 | PS5-42-OB-3512A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-08-19 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 21 | 43 | AUGUST
T-774-1479 | PS5-88-IK-4507C | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | In progress |  | 10 | AUGUST
T-051-1480 | PS5-17-UR-6510C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-03-05 | PS5-82-01 | PS5 - Milestone F | 5 | Closed | 11 | 46 | MARCH
T-700-1481 | PS5-02-OB-6196C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone H | 7 | In progress |  | 31 | OCTOBER
T-985-1482 | PS5-57-IK-2318B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-11-16 | PS5-62-02 | PS5 - Milestone C | 2 | Closed | 29 | 31 | NOVEMBER
T-176-1483 | PS5-80-OB-9184B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | On hold |  | 17 | NOVEMBER
T-343-1484 | PS5-03-IK-9562B | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone E | 4 | In progress |  | 44 | DECEMBER
T-860-1485 | PS5-76-UR-6841D | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone C | 2 | To be completed |  | 35 | AUGUST
T-488-1486 | PS5-01-IK-4749B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-18 | PS5-60-10 | PS5 - Milestone D | 3 | Closed | 35 | 27 | JUNE
T-409-1487 | PS5-26-OB-5111B | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone H | 7 | In progress |  | 29 | DECEMBER
T-912-1488 | PS5-61-OB-9828D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone G | 6 | To be completed |  | 31 | OCTOBER
T-201-1489 | PS5-24-OB-8777C | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone G | 6 | To be completed |  | 24 | OCTOBER
T-568-1490 | PS5-93-UR-6112C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-01-13 | PS5-10-05 | PS5 - Milestone H | 7 | Closed | 30 | 22 | JANUARY
T-467-1491 | PS5-07-OB-6640D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone H | 7 | In progress |  | 14 | NOVEMBER
T-049-1492 | PS5-72-IK-5175B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-03-15 | PS5-60-10 | PS5 - Milestone I | 8 | Closed | 31 | 21 | MARCH
T-714-1493 | PS5-69-UR-9441C | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-03-08 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 18 | 18 | MARCH
T-823-1494 | PS5-81-UR-1130D | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone D | 3 | In progress |  | 31 | DECEMBER
T-158-1495 | PS5-69-OB-1001A | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | In progress |  | 14 | AUGUST
T-999-1496 | PS5-19-OB-8966D | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | In progress |  | 13 | OCTOBER
T-982-1497 | PS5-26-IK-4322B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-03-27 | PS5-05-01 | PS5 - Milestone F | 5 | Closed | 14 | 34 | MARCH
T-546-1498 | PS5-04-OB-1793D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone G | 6 | On hold |  | 47 | OCTOBER
T-575-1499 | PS5-49-IK-2918B | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-05-13 | PS5-03-03 | PS5 - Milestone H | 7 | Closed | 33 | 39 | MAY
T-180-1500 | PS5-14-OB-5697A | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | To be completed |  | 44 | OCTOBER
T-543-1501 | PS5-88-UR-4106C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone F | 5 | To be completed |  | 16 | DECEMBER
T-911-1502 | PS5-47-IK-6829C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | To be completed |  | 8 | DECEMBER
T-593-1503 | PS5-47-UR-1123A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone B | 1.1 | On hold |  | 27 | SEPTEMBER
T-323-1504 | PS5-19-OB-1074A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-05-12 | PS5-99-01 | PS5 - Milestone A | 1 | Closed | 17 | 36 | MAY
T-982-1505 | PS5-13-OB-1555B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone H | 7 | To be completed |  | 42 | OCTOBER
T-182-1506 | PS5-45-IK-8101D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | To be completed |  | 13 | DECEMBER
T-989-1507 | PS5-49-OB-4519C | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-02-15 | PS5-05-02 | PS5 - Milestone A | 1 | Closed | 17 | 48 | FEBRUARY
T-345-1508 | PS5-98-UR-6468A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-11-17 | PS5-01-05 | PS5 - Milestone H | 7 | Closed | 44 | 12 | NOVEMBER
T-135-1509 | PS5-60-UR-3786B | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | To be completed |  | 14 | AUGUST
T-895-1510 | PS5-27-IK-9675A | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone D | 3 | To be completed |  | 47 | SEPTEMBER
T-257-1511 | PS5-68-OB-6353C | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone A | 1 | To be completed |  | 9 | NOVEMBER
T-776-1512 | PS5-35-UR-4568A | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-01-27 | PS5-05-02 | PS5 - Milestone A | 1 | Closed | 41 | 38 | JANUARY
T-518-1513 | PS5-38-OB-7120B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-12-01 | PS5-08-01 | PS5 - Milestone E | 4 | Closed | 13 | 14 | DECEMBER
T-322-1514 | PS5-19-UR-9097B | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone H | 7 | In progress |  | 42 | OCTOBER
T-784-1515 | PS5-23-OB-7952B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-05-20 | PS5-04-03 | PS5 - Milestone F | 5 | Closed | 26 | 15 | MAY
T-683-1516 | PS5-41-OB-9171B | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-12-10 | PS5-03-02 | PS5 - Milestone E | 4 | Closed | 15 | 20 | DECEMBER
T-944-1517 | PS5-63-IK-6754A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone D | 3 | In progress |  | 16 | SEPTEMBER
T-906-1518 | PS5-56-IK-5915D | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone H | 7 | To be completed |  | 28 | DECEMBER
T-956-1519 | PS5-14-IK-6111C | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone I | 8 | In progress |  | 40 | NOVEMBER
T-408-1520 | PS5-11-OB-6687D | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone I | 8 | In progress |  | 10 | NOVEMBER
T-091-1521 | PS5-48-OB-2050B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-09-17 | PS5-99-02 | PS5 - Milestone E | 4 | Closed | 32 | 12 | SEPTEMBER
T-666-1522 | PS5-34-UR-1987B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-11-04 | PS5-01-02 | PS5 - Milestone B | 1.1 | Closed | 8 | 10 | NOVEMBER
T-900-1523 | PS5-71-UR-2100C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone G | 6 | To be completed |  | 32 | OCTOBER
T-351-1524 | PS5-58-IK-3295A | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone C | 2 | To be completed |  | 6 | NOVEMBER
T-456-1525 | PS5-18-OB-1940C | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-06-14 | PS5-10-03 | PS5 - Milestone I | 8 | Closed | 29 | 17 | JUNE
T-965-1526 | PS5-27-IK-1327C | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-01-21 | PS5-02-01 | PS5 - Milestone I | 8 | Closed | 22 | 27 | JANUARY
T-984-1527 | PS5-74-OB-4163B | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone I | 8 | To be completed |  | 26 | OCTOBER
T-648-1528 | PS5-76-IK-4143B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone E | 4 | In progress |  | 16 | NOVEMBER
T-802-1529 | PS5-03-OB-9715D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-09-21 | PS5-10-02 | PS5 - Milestone F | 5 | Closed | 26 | 46 | SEPTEMBER
T-705-1530 | PS5-01-UR-2569C | CQM04 - Vessel | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone I | 8 | To be completed |  | 31 | NOVEMBER
T-732-1531 | PS5-76-OB-7645B | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone F | 5 | In progress |  | 13 | OCTOBER
T-022-1532 | PS5-88-IK-3737B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone I | 8 | To be completed |  | 26 | OCTOBER
T-321-1533 | PS5-67-OB-9522C | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone D | 3 | On hold |  | 45 | OCTOBER
T-959-1534 | PS5-58-IK-7480C | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-06-01 | PS5-05-02 | PS5 - Milestone C | 2 | Closed | 18 | 37 | JUNE
T-146-1535 | PS5-21-UR-2351D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone B | 1.1 | On hold |  | 46 | DECEMBER
T-234-1536 | PS5-87-OB-4453C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone A | 1 | To be completed |  | 17 | OCTOBER
T-428-1537 | PS5-73-IK-4092B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone A | 1 | To be completed |  | 28 | DECEMBER
T-823-1538 | PS5-41-IK-5057C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-12-04 | PS5-02-01 | PS5 - Milestone H | 7 | Closed | 35 | 35 | DECEMBER
T-410-1539 | PS5-54-OB-4761A | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | In progress |  | 36 | AUGUST
T-470-1540 | PS5-01-IK-5245C | CQX04 - Painting & Coating | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone B | 1.1 | To be completed |  | 47 | DECEMBER
T-497-1541 | PS5-88-IK-1287B | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-07-12 | PS5-01-05 | PS5 - Milestone G | 6 | Closed | 26 | 10 | JULY
T-869-1542 | PS5-43-OB-6483C | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone E | 4 | In progress |  | 17 | SEPTEMBER
T-088-1543 | PS5-22-IK-9981C | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | To be completed |  | 23 | NOVEMBER
T-604-1544 | PS5-20-IK-3703D | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone E | 4 | In progress |  | 22 | DECEMBER
T-781-1545 | PS5-94-OB-7402C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-10-02 | PS5-82-02 | PS5 - Milestone D | 3 | Closed | 32 | 48 | OCTOBER
T-067-1546 | PS5-69-OB-2591B | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone H | 7 | On hold |  | 11 | SEPTEMBER
T-740-1547 | PS5-74-OB-5393D | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-11-02 | PS5-60-07 | PS5 - Milestone H | 7 | Closed | 21 | 8 | NOVEMBER
T-084-1548 | PS5-40-UR-3324D | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-02-16 | PS5-10-03 | PS5 - Milestone I | 8 | Closed | 22 | 26 | FEBRUARY
T-764-1549 | PS5-31-IK-8420C | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-11-15 | PS5-05-02 | PS5 - Milestone C | 2 | Closed | 9 | 39 | NOVEMBER
T-558-1550 | PS5-81-IK-5252C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-05-13 | PS5-01-05 | PS5 - Milestone A | 1 | Closed | 44 | 33 | MAY
T-455-1551 | PS5-07-IK-3118C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-09-03 | PS5-60-10 | PS5 - Milestone D | 3 | Closed | 47 | 32 | SEPTEMBER
T-875-1552 | PS5-47-IK-9729C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-05-05 | PS5-07-02 | PS5 - Milestone F | 5 | Closed | 43 | 46 | MAY
T-291-1553 | PS5-73-OB-1572B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-02-06 | PS5-61-02 | PS5 - Milestone E | 4 | Closed | 17 | 35 | FEBRUARY
T-094-1554 | PS5-15-UR-9491D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | To be completed |  | 7 | NOVEMBER
T-518-1555 | PS5-64-OB-1863C | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | To be completed |  | 11 | NOVEMBER
T-448-1556 | PS5-55-IK-7777B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone E | 4 | To be completed |  | 37 | NOVEMBER
T-659-1557 | PS5-51-OB-4416A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-04-20 | PS5-07-04 | PS5 - Milestone C | 2 | Closed | 19 | 38 | APRIL
T-463-1558 | PS5-95-OB-4581B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-03-28 | PS5-03-03 | PS5 - Milestone F | 5 | Closed | 39 | 31 | MARCH
T-312-1559 | PS5-42-OB-6202B | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | On hold |  | 28 | AUGUST
T-218-1560 | PS5-08-IK-3999A | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-20 | PS5-60-07 | PS5 - Milestone D | 3 | Closed | 42 | 40 | APRIL
T-240-1561 | PS5-26-IK-8329D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone E | 4 | In progress |  | 17 | AUGUST
T-912-1562 | PS5-04-OB-4839A | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone F | 5 | To be completed |  | 22 | DECEMBER
T-656-1563 | PS5-11-OB-4700C | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-01-24 | PS5-82-02 | PS5 - Milestone E | 4 | Closed | 16 | 30 | JANUARY
T-707-1564 | PS5-03-UR-5091C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-09-08 | PS5-10-04 | PS5 - Milestone D | 3 | Closed | 31 | 33 | SEPTEMBER
T-909-1565 | PS5-47-OB-2429D | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-05-16 | PS5-60-10 | PS5 - Milestone B | 1.1 | Closed | 38 | 10 | MAY
T-956-1566 | PS5-31-OB-9035C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-11-05 | PS5-02-01 | PS5 - Milestone A | 1 | Closed | 25 | 47 | NOVEMBER
T-154-1567 | PS5-94-UR-9154B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone A | 1 | On hold |  | 37 | AUGUST
T-782-1568 | PS5-35-IK-3481B | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-05-04 | PS5-01-05 | PS5 - Milestone B | 1.1 | Closed | 12 | 21 | MAY
T-600-1569 | PS5-17-UR-2336A | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | In progress |  | 32 | NOVEMBER
T-924-1570 | PS5-12-OB-3499D | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-10-23 | PS5-02-03 | PS5 - Milestone A | 1 | Closed | 26 | 6 | OCTOBER
T-920-1571 | PS5-09-OB-8668D | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone D | 3 | To be completed |  | 38 | NOVEMBER
T-744-1572 | PS5-03-IK-3787D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-12-06 | PS5-02-03 | PS5 - Milestone H | 7 | Closed | 38 | 44 | DECEMBER
T-051-1573 | PS5-50-IK-2584A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone B | 1.1 | To be completed |  | 14 | OCTOBER
T-846-1574 | PS5-47-IK-7863C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-01-10 | PS5-03-23 | PS5 - Milestone F | 5 | Closed | 6 | 36 | JANUARY
T-218-1575 | PS5-03-OB-9897D | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-05-05 | PS5-11-01 | PS5 - Milestone B | 1.1 | Closed | 12 | 28 | MAY
T-568-1576 | PS5-84-OB-3867C | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-02-08 | PS5-05-01 | PS5 - Milestone C | 2 | Closed | 17 | 34 | FEBRUARY
T-826-1577 | PS5-04-OB-3849B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone A | 1 | To be completed |  | 27 | DECEMBER
T-105-1578 | PS5-40-UR-6598D | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone I | 8 | To be completed |  | 23 | AUGUST
T-743-1579 | PS5-30-UR-4777A | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-08-24 | PS5-99-03 | PS5 - Milestone C | 2 | Closed | 17 | 6 | AUGUST
T-131-1580 | PS5-78-UR-6909D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone I | 8 | In progress |  | 6 | SEPTEMBER
T-895-1581 | PS5-27-OB-6781B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone E | 4 | In progress |  | 25 | SEPTEMBER
T-979-1582 | PS5-87-UR-8371C | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-06-07 | PS5-05-01 | PS5 - Milestone C | 2 | Closed | 15 | 21 | JUNE
T-048-1583 | PS5-15-IK-1665C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone B | 1.1 | To be completed |  | 36 | OCTOBER
T-756-1584 | PS5-04-UR-2798D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone A | 1 | In progress |  | 19 | NOVEMBER
T-209-1585 | PS5-14-OB-6363A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone D | 3 | To be completed |  | 38 | SEPTEMBER
T-508-1586 | PS5-91-IK-9842A | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | To be completed |  | 6 | AUGUST
T-663-1587 | PS5-63-IK-3234D | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone C | 2 | In progress |  | 44 | DECEMBER
T-399-1588 | PS5-93-UR-5561D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone G | 6 | To be completed |  | 45 | DECEMBER
T-380-1589 | PS5-11-IK-8623A | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-10-22 | PS5-99-01 | PS5 - Milestone G | 6 | Closed | 26 | 16 | OCTOBER
T-531-1590 | PS5-61-IK-5769A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone E | 4 | To be completed |  | 17 | OCTOBER
T-230-1591 | PS5-78-OB-2150A | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-01-02 | PS5-09-02 | PS5 - Milestone A | 1 | Closed | 35 | 26 | JANUARY
T-242-1592 | PS5-08-IK-4494B | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone I | 8 | To be completed |  | 44 | OCTOBER
T-085-1593 | PS5-30-OB-2396C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-04-18 | PS5-11-02 | PS5 - Milestone F | 5 | Closed | 36 | 38 | APRIL
T-304-1594 | PS5-19-IK-8123D | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone D | 3 | On hold |  | 17 | NOVEMBER
T-496-1595 | PS5-08-IK-5285A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone A | 1 | On hold |  | 34 | DECEMBER
T-576-1596 | PS5-07-UR-4860C | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone C | 2 | In progress |  | 5 | DECEMBER
T-678-1597 | PS5-67-UR-8761A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-06-24 | PS5-99-03 | PS5 - Milestone F | 5 | Closed | 21 | 41 | JUNE
T-780-1598 | PS5-05-OB-3454D | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone E | 4 | On hold |  | 30 | SEPTEMBER
T-332-1599 | PS5-45-OB-4129B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone D | 3 | To be completed |  | 20 | NOVEMBER
T-772-1600 | PS5-85-UR-8025B | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-12-15 | PS5-12-01 | PS5 - Milestone H | 7 | Closed | 44 | 27 | DECEMBER
T-385-1601 | PS5-53-IK-3460D | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone B | 1.1 | To be completed |  | 31 | OCTOBER
T-103-1602 | PS5-38-OB-4997A | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone H | 7 | In progress |  | 7 | SEPTEMBER
T-053-1603 | PS5-23-OB-6881C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone A | 1 | To be completed |  | 35 | SEPTEMBER
T-104-1604 | PS5-52-OB-9524A | CQM02 - Compressor | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-07-16 | PS5-82-07 | PS5 - Milestone E | 4 | Closed | 36 | 41 | JULY
T-489-1605 | PS5-77-UR-6961A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone A | 1 | To be completed |  | 25 | OCTOBER
T-955-1606 | PS5-53-OB-2007A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | To be completed |  | 41 | NOVEMBER
T-606-1607 | PS5-36-OB-5890B | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone G | 6 | To be completed |  | 15 | NOVEMBER
T-715-1608 | PS5-56-UR-8539B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-12-26 | PS5-09-04 | PS5 - Milestone F | 5 | Closed | 21 | 19 | DECEMBER
T-488-1609 | PS5-65-OB-4351C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone G | 6 | To be completed |  | 30 | SEPTEMBER
T-395-1610 | PS5-83-OB-8172A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-09-25 | PS5-06-01 | PS5 - Milestone B | 1.1 | Closed | 11 | 7 | SEPTEMBER
T-634-1611 | PS5-87-IK-8481D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone D | 3 | In progress |  | 41 | AUGUST
T-586-1612 | PS5-51-OB-4806C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone G | 6 | In progress |  | 35 | DECEMBER
T-014-1613 | PS5-03-OB-6918B | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone D | 3 | In progress |  | 45 | SEPTEMBER
T-941-1614 | PS5-20-UR-1073D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | To be completed |  | 34 | AUGUST
T-726-1615 | PS5-09-OB-7986B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-02-17 | PS5-99-02 | PS5 - Milestone H | 7 | Closed | 39 | 45 | FEBRUARY
T-088-1616 | PS5-90-OB-6337A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone I | 8 | To be completed |  | 27 | OCTOBER
T-560-1617 | PS5-68-UR-4229D | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-08-27 | PS5-60-07 | PS5 - Milestone G | 6 | Closed | 47 | 37 | AUGUST
T-458-1618 | PS5-38-UR-8278A | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-08-13 | PS5-01-04 | PS5 - Milestone B | 1.1 | Closed | 39 | 20 | AUGUST
T-871-1619 | PS5-50-IK-3321C | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | To be completed |  | 42 | DECEMBER
T-240-1620 | PS5-92-OB-1753A | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-12-14 | PS5-82-02 | PS5 - Milestone B | 1.1 | Closed | 32 | 40 | DECEMBER
T-666-1621 | PS5-32-OB-6045D | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone G | 6 | On hold |  | 14 | SEPTEMBER
T-673-1622 | PS5-91-OB-4046C | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone F | 5 | To be completed |  | 5 | AUGUST
T-270-1623 | PS5-45-UR-6395C | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-02-07 | PS5-12-02 | PS5 - Milestone E | 4 | Closed | 28 | 24 | FEBRUARY
T-154-1624 | PS5-66-OB-7074C | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-01-27 | PS5-07-03 | PS5 - Milestone G | 6 | Closed | 7 | 46 | JANUARY
T-966-1625 | PS5-68-IK-8418A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-02-10 | PS5-03-01 | PS5 - Milestone E | 4 | Closed | 5 | 30 | FEBRUARY
T-675-1626 | PS5-14-UR-7917B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | To be completed |  | 43 | DECEMBER
T-662-1627 | PS5-59-OB-1609B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | In progress |  | 38 | SEPTEMBER
T-659-1628 | PS5-07-UR-8578C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-04-24 | PS5-11-01 | PS5 - Milestone B | 1.1 | Closed | 16 | 18 | APRIL
T-129-1629 | PS5-02-IK-3184D | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone E | 4 | To be completed |  | 4 | NOVEMBER
T-633-1630 | PS5-30-IK-3739D | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone F | 5 | In progress |  | 22 | OCTOBER
T-728-1631 | PS5-81-IK-2785B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone G | 6 | In progress |  | 33 | SEPTEMBER
T-832-1632 | PS5-90-OB-2870B | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone C | 2 | To be completed |  | 24 | DECEMBER
T-504-1633 | PS5-27-IK-1913B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone A | 1 | On hold |  | 35 | AUGUST
T-826-1634 | PS5-41-OB-3159A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone B | 1.1 | On hold |  | 6 | SEPTEMBER
T-224-1635 | PS5-83-OB-1263B | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | To be completed |  | 16 | OCTOBER
T-632-1636 | PS5-57-UR-9797C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone C | 2 | In progress |  | 28 | AUGUST
T-995-1637 | PS5-94-IK-9762D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone B | 1.1 | On hold |  | 27 | NOVEMBER
T-907-1638 | PS5-16-OB-1583C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-10-27 | PS5-03-01 | PS5 - Milestone C | 2 | Closed | 25 | 17 | OCTOBER
T-457-1639 | PS5-97-OB-4456B | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | In progress |  | 12 | DECEMBER
T-330-1640 | PS5-89-IK-5751D | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone A | 1 | To be completed |  | 36 | SEPTEMBER
T-054-1641 | PS5-40-UR-9989B | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-10-17 | PS5-10-06 | PS5 - Milestone E | 4 | Closed | 42 | 41 | OCTOBER
T-653-1642 | PS5-47-IK-1794B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone E | 4 | In progress |  | 10 | DECEMBER
T-238-1643 | PS5-03-UR-4611A | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone A | 1 | In progress |  | 33 | DECEMBER
T-725-1644 | PS5-19-OB-2703D | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-06-08 | PS5-01-08 | PS5 - Milestone F | 5 | Closed | 18 | 19 | JUNE
T-435-1645 | PS5-23-OB-5509A | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-11-25 | PS5-12-01 | PS5 - Milestone I | 8 | Closed | 46 | 11 | NOVEMBER
T-717-1646 | PS5-10-OB-2155B | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | In progress |  | 4 | AUGUST
T-725-1647 | PS5-39-OB-1170B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone D | 3 | In progress |  | 15 | SEPTEMBER
T-165-1648 | PS5-10-OB-6610D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-01-10 | PS5-10-04 | PS5 - Milestone A | 1 | Closed | 44 | 17 | JANUARY
T-247-1649 | PS5-11-UR-9665D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone G | 6 | To be completed |  | 31 | AUGUST
T-038-1650 | PS5-73-IK-9567C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone H | 7 | In progress |  | 26 | NOVEMBER
T-906-1651 | PS5-08-UR-8804C | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone A | 1 | In progress |  | 43 | OCTOBER
T-344-1652 | PS5-99-OB-9325D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-02-10 | PS5-09-03 | PS5 - Milestone G | 6 | Closed | 19 | 13 | FEBRUARY
T-506-1653 | PS5-21-IK-3698C | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone G | 6 | In progress |  | 19 | NOVEMBER
T-023-1654 | PS5-46-OB-3449D | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone E | 4 | On hold |  | 27 | DECEMBER
T-207-1655 | PS5-36-UR-9557C | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone G | 6 | In progress |  | 25 | NOVEMBER
T-309-1656 | PS5-94-IK-1955B | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | To be completed |  | 22 | OCTOBER
T-255-1657 | PS5-04-OB-8187A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone F | 5 | To be completed |  | 29 | AUGUST
T-492-1658 | PS5-49-OB-4674B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone F | 5 | To be completed |  | 15 | DECEMBER
T-791-1659 | PS5-14-UR-9268A | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone E | 4 | In progress |  | 14 | SEPTEMBER
T-322-1660 | PS5-89-OB-7669C | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-11-27 | PS5-82-01 | PS5 - Milestone H | 7 | Closed | 33 | 26 | NOVEMBER
T-334-1661 | PS5-67-OB-9246D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone A | 1 | On hold |  | 5 | NOVEMBER
T-916-1662 | PS5-41-OB-3987A | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone E | 4 | To be completed |  | 26 | NOVEMBER
T-433-1663 | PS5-75-OB-3269D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-08-25 | PS5-99-03 | PS5 - Milestone A | 1 | Closed | 13 | 46 | AUGUST
T-216-1664 | PS5-61-IK-7342C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone G | 6 | In progress |  | 24 | OCTOBER
T-727-1665 | PS5-71-IK-6961A | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone F | 5 | To be completed |  | 7 | OCTOBER
T-785-1666 | PS5-53-OB-7117C | CQP04 - Hydrotest | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-12-26 | PS5-01-06 | PS5 - Milestone A | 1 | Closed | 24 | 40 | DECEMBER
T-161-1667 | PS5-48-OB-1918A | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-06-17 | PS5-09-02 | PS5 - Milestone D | 3 | Closed | 38 | 28 | JUNE
T-936-1668 | PS5-45-OB-2548D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-09-28 | PS5-01-06 | PS5 - Milestone C | 2 | Closed | 11 | 27 | SEPTEMBER
T-974-1669 | PS5-49-OB-6007B | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-06-08 | PS5-06-02 | PS5 - Milestone G | 6 | Closed | 33 | 48 | JUNE
T-823-1670 | PS5-51-OB-2057A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone A | 1 | To be completed |  | 26 | NOVEMBER
T-526-1671 | PS5-64-OB-7840A | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-05-22 | PS5-02-01 | PS5 - Milestone G | 6 | Closed | 8 | 34 | MAY
T-156-1672 | PS5-59-OB-3192D | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-01 | PS5-60-01 | PS5 - Milestone B | 1.1 | Closed | 16 | 4 | APRIL
T-324-1673 | PS5-72-IK-4200D | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-02-16 | PS5-61-07 | PS5 - Milestone E | 4 | Closed | 22 | 23 | FEBRUARY
T-973-1674 | PS5-95-OB-4227C | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone G | 6 | To be completed |  | 44 | NOVEMBER
T-811-1675 | PS5-81-UR-3640D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-07-03 | PS5-63-01 | PS5 - Milestone H | 7 | Closed | 29 | 17 | JULY
T-378-1676 | PS5-75-OB-5841D | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | In progress |  | 38 | NOVEMBER
T-119-1677 | PS5-12-OB-6178B | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | To be completed |  | 22 | AUGUST
T-632-1678 | PS5-54-OB-8871A | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone G | 6 | To be completed |  | 36 | NOVEMBER
T-314-1679 | PS5-25-OB-9194D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone C | 2 | In progress |  | 6 | SEPTEMBER
T-991-1680 | PS5-55-OB-5943C | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-03-14 | PS5-62-01 | PS5 - Milestone H | 7 | Closed | 4 | 8 | MARCH
T-362-1681 | PS5-06-OB-8070C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone E | 4 | To be completed |  | 26 | NOVEMBER
T-636-1682 | PS5-24-UR-3482D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone D | 3 | To be completed |  | 7 | NOVEMBER
T-656-1683 | PS5-08-OB-9316C | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone F | 5 | On hold |  | 22 | AUGUST
T-430-1684 | PS5-68-OB-1450D | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone G | 6 | In progress |  | 46 | NOVEMBER
T-274-1685 | PS5-50-IK-9313A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | To be completed |  | 27 | AUGUST
T-174-1686 | PS5-98-UR-1631C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone G | 6 | In progress |  | 47 | NOVEMBER
T-619-1687 | PS5-74-IK-8944C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-01-28 | PS5-04-02 | PS5 - Milestone B | 1.1 | Closed | 37 | 39 | JANUARY
T-761-1688 | PS5-60-IK-4401B | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-05-23 | PS5-09-03 | PS5 - Milestone G | 6 | Closed | 11 | 46 | MAY
T-177-1689 | PS5-31-UR-7119A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-10-13 | PS5-13-01 | PS5 - Milestone G | 6 | Closed | 41 | 34 | OCTOBER
T-156-1690 | PS5-49-OB-1555D | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone A | 1 | To be completed |  | 8 | OCTOBER
T-684-1691 | PS5-61-UR-2350C | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone I | 8 | To be completed |  | 21 | OCTOBER
T-083-1692 | PS5-98-OB-7448B | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | In progress |  | 15 | SEPTEMBER
T-058-1693 | PS5-13-IK-4059A | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-12-01 | PS5-09-04 | PS5 - Milestone B | 1.1 | Closed | 15 | 48 | DECEMBER
T-140-1694 | PS5-07-OB-7307C | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-07-03 | PS5-09-01 | PS5 - Milestone E | 4 | Closed | 38 | 28 | JULY
T-817-1695 | PS5-15-OB-3792B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone I | 8 | In progress |  | 7 | OCTOBER
T-005-1696 | PS5-68-OB-2818A | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | To be completed |  | 37 | AUGUST
T-444-1697 | PS5-47-IK-4060B | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone D | 3 | On hold |  | 15 | OCTOBER
T-668-1698 | PS5-30-OB-1838A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-02-24 | PS5-05-01 | PS5 - Milestone A | 1 | Closed | 8 | 28 | FEBRUARY
T-041-1699 | PS5-22-OB-3654A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone G | 6 | To be completed |  | 4 | SEPTEMBER
T-803-1700 | PS5-43-UR-2480C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone A | 1 | To be completed |  | 37 | DECEMBER
T-839-1701 | PS5-23-OB-8558A | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-04-19 | PS5-07-04 | PS5 - Milestone A | 1 | Closed | 6 | 23 | APRIL
T-835-1702 | PS5-87-OB-7994B | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-12-19 | PS5-07-04 | PS5 - Milestone I | 8 | Closed | 33 | 6 | DECEMBER
T-974-1703 | PS5-09-UR-3007D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | To be completed |  | 45 | SEPTEMBER
T-690-1704 | PS5-29-UR-5263B | CQM02 - Compressor | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-10-12 | PS5-09-01 | PS5 - Milestone I | 8 | Closed | 39 | 45 | OCTOBER
T-004-1705 | PS5-67-OB-5480C | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-11-27 | PS5-11-01 | PS5 - Milestone B | 1.1 | Closed | 25 | 42 | NOVEMBER
T-887-1706 | PS5-64-OB-6416A | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-11-05 | PS5-10-01 | PS5 - Milestone G | 6 | Closed | 39 | 11 | NOVEMBER
T-014-1707 | PS5-85-OB-7997A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone I | 8 | In progress |  | 37 | NOVEMBER
T-697-1708 | PS5-87-OB-7362B | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-02-14 | PS5-09-01 | PS5 - Milestone E | 4 | Closed | 43 | 5 | FEBRUARY
T-770-1709 | PS5-04-OB-7975A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | In progress |  | 43 | OCTOBER
T-866-1710 | PS5-60-OB-4571A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-03-11 | PS5-03-03 | PS5 - Milestone H | 7 | Closed | 45 | 22 | MARCH
T-746-1711 | PS5-35-UR-6397C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone A | 1 | In progress |  | 27 | DECEMBER
T-190-1712 | PS5-36-OB-4594B | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone D | 3 | To be completed |  | 43 | OCTOBER
T-517-1713 | PS5-66-IK-3321B | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone H | 7 | In progress |  | 28 | OCTOBER
T-021-1714 | PS5-27-IK-8978B | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | On hold |  | 23 | DECEMBER
T-530-1715 | PS5-25-OB-4804A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone E | 4 | In progress |  | 39 | SEPTEMBER
T-945-1716 | PS5-22-OB-1478D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | In progress |  | 44 | DECEMBER
T-844-1717 | PS5-55-OB-2770D | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-07-24 | PS5-63-01 | PS5 - Milestone C | 2 | Closed | 31 | 47 | JULY
T-841-1718 | PS5-40-OB-5854C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone G | 6 | In progress |  | 19 | OCTOBER
T-232-1719 | PS5-24-UR-9624B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-10-15 | PS5-01-05 | PS5 - Milestone D | 3 | Closed | 18 | 18 | OCTOBER
T-123-1720 | PS5-72-UR-9758C | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone A | 1 | To be completed |  | 48 | NOVEMBER
T-473-1721 | PS5-81-OB-1840C | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone A | 1 | In progress |  | 19 | OCTOBER
T-205-1722 | PS5-34-OB-5486B | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-07-17 | PS5-01-05 | PS5 - Milestone E | 4 | Closed | 24 | 20 | JULY
T-470-1723 | PS5-13-OB-7635D | CQS03 - Deluge System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone H | 7 | To be completed |  | 22 | SEPTEMBER
T-114-1724 | PS5-12-UR-6635A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone D | 3 | On hold |  | 36 | DECEMBER
T-048-1725 | PS5-64-OB-5271D | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone E | 4 | In progress |  | 46 | NOVEMBER
T-762-1726 | PS5-34-OB-3709A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone H | 7 | To be completed |  | 23 | SEPTEMBER
T-392-1727 | PS5-14-UR-7119C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | To be completed |  | 23 | DECEMBER
T-259-1728 | PS5-50-IK-5437C | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone E | 4 | To be completed |  | 24 | OCTOBER
T-086-1729 | PS5-97-IK-3187A | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | In progress |  | 22 | SEPTEMBER
T-766-1730 | PS5-14-OB-3239D | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone F | 5 | In progress |  | 23 | SEPTEMBER
T-469-1731 | PS5-94-OB-4457B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone C | 2 | To be completed |  | 19 | AUGUST
T-402-1732 | PS5-95-OB-9210B | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-04-11 | PS5-04-04 | PS5 - Milestone D | 3 | Closed | 35 | 36 | APRIL
T-325-1733 | PS5-35-OB-5776A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone F | 5 | In progress |  | 22 | OCTOBER
T-439-1734 | PS5-34-OB-5889B | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone C | 2 | To be completed |  | 48 | DECEMBER
T-337-1735 | PS5-46-OB-9670C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-12-16 | PS5-60-01 | PS5 - Milestone D | 3 | Closed | 16 | 40 | DECEMBER
T-497-1736 | PS5-06-IK-8767B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone F | 5 | In progress |  | 7 | DECEMBER
T-318-1737 | PS5-04-UR-8500B | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | On hold |  | 35 | AUGUST
T-392-1738 | PS5-70-UR-5901A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-01-08 | PS5-03-23 | PS5 - Milestone E | 4 | Closed | 11 | 5 | JANUARY
T-931-1739 | PS5-40-UR-1337C | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-07-01 | PS5-11-03 | PS5 - Milestone E | 4 | Closed | 31 | 16 | JULY
T-873-1740 | PS5-93-OB-5275B | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-12-11 | PS5-03-23 | PS5 - Milestone G | 6 | Closed | 16 | 30 | DECEMBER
T-571-1741 | PS5-16-OB-1666A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-02-23 | PS5-07-03 | PS5 - Milestone D | 3 | Closed | 16 | 39 | FEBRUARY
T-713-1742 | PS5-54-OB-8042C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-10-23 | PS5-01-05 | PS5 - Milestone H | 7 | Closed | 16 | 16 | OCTOBER
T-146-1743 | PS5-38-OB-2770D | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-04-18 | PS5-62-01 | PS5 - Milestone F | 5 | Closed | 27 | 23 | APRIL
T-257-1744 | PS5-76-IK-4517D | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone E | 4 | On hold |  | 27 | NOVEMBER
T-889-1745 | PS5-03-OB-4350A | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-09-10 | PS5-02-03 | PS5 - Milestone F | 5 | Closed | 14 | 4 | SEPTEMBER
T-366-1746 | PS5-42-IK-6955B | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | On hold |  | 44 | AUGUST
T-424-1747 | PS5-64-OB-1050D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone G | 6 | In progress |  | 48 | SEPTEMBER
T-952-1748 | PS5-42-OB-5237D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone A | 1 | To be completed |  | 41 | OCTOBER
T-775-1749 | PS5-75-OB-1109B | CQP04 - Hydrotest | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone E | 4 | In progress |  | 15 | SEPTEMBER
T-562-1750 | PS5-71-OB-1991A | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone F | 5 | To be completed |  | 5 | SEPTEMBER
T-401-1751 | PS5-51-UR-7115C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone E | 4 | To be completed |  | 34 | NOVEMBER
T-498-1752 | PS5-95-UR-8967B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone E | 4 | To be completed |  | 44 | DECEMBER
T-445-1753 | PS5-62-OB-8154A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-08-18 | PS5-02-01 | PS5 - Milestone E | 4 | Closed | 22 | 41 | AUGUST
T-361-1754 | PS5-83-IK-1052C | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-08-20 | PS5-04-04 | PS5 - Milestone G | 6 | Closed | 17 | 16 | AUGUST
T-511-1755 | PS5-08-IK-8304C | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-12-09 | PS5-82-07 | PS5 - Milestone A | 1 | Closed | 23 | 23 | DECEMBER
T-103-1756 | PS5-11-OB-2152D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | To be completed |  | 14 | OCTOBER
T-542-1757 | PS5-53-OB-1542C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone F | 5 | In progress |  | 15 | SEPTEMBER
T-592-1758 | PS5-88-IK-6924B | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone D | 3 | To be completed |  | 34 | SEPTEMBER
T-195-1759 | PS5-08-OB-5792A | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone A | 1 | On hold |  | 18 | OCTOBER
T-778-1760 | PS5-83-UR-1082A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-06-28 | PS5-12-01 | PS5 - Milestone H | 7 | Closed | 20 | 36 | JUNE
T-957-1761 | PS5-46-IK-2523D | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-12-19 | PS5-60-07 | PS5 - Milestone F | 5 | Closed | 39 | 28 | DECEMBER
T-904-1762 | PS5-23-UR-5653B | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone B | 1.1 | In progress |  | 40 | AUGUST
T-277-1763 | PS5-02-OB-9503B | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone B | 1.1 | To be completed |  | 4 | DECEMBER
T-477-1764 | PS5-76-OB-6392C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-12-04 | PS5-05-01 | PS5 - Milestone A | 1 | Closed | 18 | 10 | DECEMBER
T-870-1765 | PS5-63-OB-7940D | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone A | 1 | In progress |  | 7 | NOVEMBER
T-209-1766 | PS5-72-IK-3391C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-12-14 | PS5-62-01 | PS5 - Milestone H | 7 | Closed | 43 | 23 | DECEMBER
T-111-1767 | PS5-70-OB-2318B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | On hold |  | 35 | AUGUST
T-888-1768 | PS5-53-OB-7135B | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone E | 4 | On hold |  | 28 | AUGUST
T-204-1769 | PS5-79-OB-6637B | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | To be completed |  | 44 | SEPTEMBER
T-752-1770 | PS5-35-OB-3853A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone A | 1 | To be completed |  | 38 | OCTOBER
T-005-1771 | PS5-74-OB-4014C | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | To be completed |  | 40 | NOVEMBER
T-880-1772 | PS5-01-IK-4265A | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-04-15 | PS5-04-04 | PS5 - Milestone F | 5 | Closed | 32 | 12 | APRIL
T-989-1773 | PS5-03-UR-8484B | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone G | 6 | In progress |  | 20 | OCTOBER
T-948-1774 | PS5-07-IK-7877B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone I | 8 | To be completed |  | 12 | DECEMBER
T-278-1775 | PS5-97-OB-3394A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone B | 1.1 | On hold |  | 37 | DECEMBER
T-885-1776 | PS5-09-IK-3755D | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | On hold |  | 15 | DECEMBER
T-416-1777 | PS5-61-IK-1577A | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | To be completed |  | 25 | SEPTEMBER
T-065-1778 | PS5-31-IK-4081A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-02-23 | PS5-04-03 | PS5 - Milestone H | 7 | Closed | 23 | 38 | FEBRUARY
T-533-1779 | PS5-48-OB-9081B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone F | 5 | In progress |  | 48 | NOVEMBER
T-172-1780 | PS5-43-OB-5960B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-03-07 | PS5-61-02 | PS5 - Milestone H | 7 | Closed | 9 | 48 | MARCH
T-937-1781 | PS5-20-IK-6651A | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | In progress |  | 46 | AUGUST
T-470-1782 | PS5-51-UR-2658A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-09-04 | PS5-03-01 | PS5 - Milestone C | 2 | Closed | 29 | 43 | SEPTEMBER
T-051-1783 | PS5-49-UR-2137D | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone C | 2 | In progress |  | 6 | SEPTEMBER
T-882-1784 | PS5-68-OB-5675A | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone E | 4 | To be completed |  | 29 | AUGUST
T-540-1785 | PS5-72-OB-1607B | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-03-26 | PS5-99-01 | PS5 - Milestone C | 2 | Closed | 21 | 28 | MARCH
T-699-1786 | PS5-62-UR-5613C | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone D | 3 | To be completed |  | 8 | NOVEMBER
T-614-1787 | PS5-17-OB-9103A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | To be completed |  | 18 | SEPTEMBER
T-061-1788 | PS5-54-IK-3190A | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-12-09 | PS5-05-03 | PS5 - Milestone H | 7 | Closed | 48 | 32 | DECEMBER
T-272-1789 | PS5-16-IK-4638C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-09-23 | PS5-61-02 | PS5 - Milestone E | 4 | Closed | 48 | 27 | SEPTEMBER
T-752-1790 | PS5-06-OB-4397A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | To be completed |  | 35 | DECEMBER
T-678-1791 | PS5-55-OB-7178B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone E | 4 | In progress |  | 20 | OCTOBER
T-800-1792 | PS5-19-UR-2812B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone E | 4 | To be completed |  | 26 | AUGUST
T-019-1793 | PS5-37-UR-6167D | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-02-10 | PS5-04-02 | PS5 - Milestone E | 4 | Closed | 7 | 25 | FEBRUARY
T-685-1794 | PS5-11-UR-8885B | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone G | 6 | To be completed |  | 33 | DECEMBER
T-369-1795 | PS5-05-IK-1965C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone F | 5 | On hold |  | 24 | AUGUST
T-994-1796 | PS5-94-UR-1714C | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone B | 1.1 | On hold |  | 41 | SEPTEMBER
T-631-1797 | PS5-95-IK-3832D | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone D | 3 | To be completed |  | 48 | OCTOBER
T-664-1798 | PS5-61-OB-4352A | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | In progress |  | 19 | AUGUST
T-596-1799 | PS5-20-OB-7855B | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone D | 3 | To be completed |  | 38 | OCTOBER
T-124-1800 | PS5-64-UR-8835A | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-09-16 | PS5-01-09 | PS5 - Milestone B | 1.1 | Closed | 17 | 38 | SEPTEMBER
T-683-1801 | PS5-14-UR-2920A | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone A | 1 | In progress |  | 8 | NOVEMBER
T-986-1802 | PS5-26-OB-3921A | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-07-23 | PS5-10-04 | PS5 - Milestone D | 3 | Closed | 21 | 20 | JULY
T-354-1803 | PS5-92-IK-5610B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-24 | PS5-60-04 | PS5 - Milestone A | 1 | Closed | 18 | 43 | JULY
T-244-1804 | PS5-28-UR-8022D | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | In progress |  | 32 | SEPTEMBER
T-148-1805 | PS5-44-IK-5274C | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-11-12 | PS5-03-03 | PS5 - Milestone I | 8 | Closed | 31 | 39 | NOVEMBER
T-007-1806 | PS5-62-UR-1686C | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-09-16 | PS5-02-03 | PS5 - Milestone C | 2 | Closed | 34 | 12 | SEPTEMBER
T-761-1807 | PS5-52-UR-9504B | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | In progress |  | 40 | SEPTEMBER
T-625-1808 | PS5-96-UR-4724C | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone E | 4 | To be completed |  | 32 | AUGUST
T-303-1809 | PS5-07-UR-8612B | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone I | 8 | To be completed |  | 5 | OCTOBER
T-888-1810 | PS5-96-IK-3141A | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone I | 8 | To be completed |  | 6 | DECEMBER
T-204-1811 | PS5-70-UR-4770C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone D | 3 | To be completed |  | 41 | AUGUST
T-682-1812 | PS5-16-OB-9263D | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone I | 8 | To be completed |  | 41 | NOVEMBER
T-474-1813 | PS5-64-OB-6695C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone E | 4 | To be completed |  | 11 | OCTOBER
T-558-1814 | PS5-65-IK-6087A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | To be completed |  | 20 | SEPTEMBER
T-527-1815 | PS5-70-UR-9456B | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone I | 8 | On hold |  | 14 | AUGUST
T-168-1816 | PS5-14-OB-6010D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | To be completed |  | 23 | SEPTEMBER
T-046-1817 | PS5-91-UR-4159D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone G | 6 | In progress |  | 45 | NOVEMBER
T-880-1818 | PS5-48-OB-4936D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-02-24 | PS5-12-02 | PS5 - Milestone A | 1 | Closed | 44 | 46 | FEBRUARY
T-273-1819 | PS5-05-IK-6933C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-11-06 | PS5-11-01 | PS5 - Milestone B | 1.1 | Closed | 18 | 27 | NOVEMBER
T-376-1820 | PS5-81-IK-6818C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-10-15 | PS5-10-05 | PS5 - Milestone F | 5 | Closed | 24 | 22 | OCTOBER
T-617-1821 | PS5-65-OB-8338A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone A | 1 | To be completed |  | 47 | SEPTEMBER
T-090-1822 | PS5-78-IK-6833D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-04-02 | PS5-63-04 | PS5 - Milestone A | 1 | Closed | 31 | 16 | APRIL
T-818-1823 | PS5-72-OB-4361B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-02-12 | PS5-13-01 | PS5 - Milestone B | 1.1 | Closed | 7 | 19 | FEBRUARY
T-850-1824 | PS5-15-OB-6465D | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone G | 6 | To be completed |  | 5 | AUGUST
T-522-1825 | PS5-66-OB-7394C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-06-18 | PS5-07-03 | PS5 - Milestone B | 1.1 | Closed | 33 | 21 | JUNE
T-031-1826 | PS5-31-IK-2453B | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-01-25 | PS5-01-08 | PS5 - Milestone A | 1 | Closed | 21 | 46 | JANUARY
T-974-1827 | PS5-85-IK-1825D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-10-16 | PS5-09-02 | PS5 - Milestone F | 5 | Closed | 46 | 8 | OCTOBER
T-189-1828 | PS5-34-OB-3252D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | On hold |  | 47 | OCTOBER
T-198-1829 | PS5-15-OB-8104C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-04-01 | PS5-01-07 | PS5 - Milestone B | 1.1 | Closed | 47 | 11 | APRIL
T-928-1830 | PS5-95-UR-8999D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone C | 2 | To be completed |  | 28 | AUGUST
T-299-1831 | PS5-04-IK-2564A | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone I | 8 | In progress |  | 39 | AUGUST
T-937-1832 | PS5-67-UR-6263A | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-08-20 | PS5-01-03 | PS5 - Milestone B | 1.1 | Closed | 13 | 22 | AUGUST
T-303-1833 | PS5-71-OB-3266B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | To be completed |  | 12 | AUGUST
T-809-1834 | PS5-65-IK-7682A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone I | 8 | In progress |  | 43 | SEPTEMBER
T-637-1835 | PS5-48-OB-8027B | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-08-02 | PS5-10-06 | PS5 - Milestone G | 6 | Closed | 44 | 19 | AUGUST
T-613-1836 | PS5-84-OB-3762D | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone E | 4 | To be completed |  | 34 | OCTOBER
T-862-1837 | PS5-10-OB-9317A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-11-22 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 43 | 8 | NOVEMBER
T-048-1838 | PS5-37-OB-1053C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-08-17 | PS5-02-01 | PS5 - Milestone I | 8 | Closed | 21 | 48 | AUGUST
T-999-1839 | PS5-89-OB-6436A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-06-13 | PS5-09-01 | PS5 - Milestone F | 5 | Closed | 4 | 40 | JUNE
T-093-1840 | PS5-39-OB-3828C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone C | 2 | In progress |  | 4 | AUGUST
T-166-1841 | PS5-23-IK-6340D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-05-08 | PS5-82-02 | PS5 - Milestone G | 6 | Closed | 41 | 47 | MAY
T-149-1842 | PS5-60-OB-2181C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone E | 4 | To be completed |  | 6 | AUGUST
T-804-1843 | PS5-59-IK-4592A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone H | 7 | To be completed |  | 24 | SEPTEMBER
T-894-1844 | PS5-61-UR-4724C | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-11-01 | PS5-11-03 | PS5 - Milestone B | 1.1 | Closed | 37 | 38 | NOVEMBER
T-685-1845 | PS5-99-IK-6212C | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone I | 8 | To be completed |  | 47 | NOVEMBER
T-735-1846 | PS5-32-UR-7115D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone E | 4 | In progress |  | 28 | NOVEMBER
T-566-1847 | PS5-04-IK-8466A | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-04-25 | PS5-99-01 | PS5 - Milestone A | 1 | Closed | 29 | 31 | APRIL
T-672-1848 | PS5-34-UR-7504C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-08-08 | PS5-60-04 | PS5 - Milestone G | 6 | Closed | 22 | 22 | AUGUST
T-075-1849 | PS5-80-OB-4759A | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-09-20 | PS5-01-01 | PS5 - Milestone G | 6 | Closed | 21 | 23 | SEPTEMBER
T-260-1850 | PS5-45-OB-5640B | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone H | 7 | In progress |  | 5 | DECEMBER
T-501-1851 | PS5-08-OB-2022A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | On hold |  | 5 | NOVEMBER
T-029-1852 | PS5-89-IK-7861C | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone E | 4 | To be completed |  | 12 | NOVEMBER
T-976-1853 | PS5-08-OB-6398A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-08-26 | PS5-99-02 | PS5 - Milestone A | 1 | Closed | 39 | 48 | AUGUST
T-637-1854 | PS5-41-OB-2016A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone C | 2 | In progress |  | 6 | NOVEMBER
T-450-1855 | PS5-64-UR-2810A | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-12-10 | PS5-13-01 | PS5 - Milestone I | 8 | Closed | 42 | 24 | DECEMBER
T-881-1856 | PS5-90-OB-3298D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone B | 1.1 | To be completed |  | 31 | AUGUST
T-724-1857 | PS5-53-UR-5155C | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | To be completed |  | 5 | OCTOBER
T-254-1858 | PS5-96-UR-1125B | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-11-13 | PS5-10-03 | PS5 - Milestone D | 3 | Closed | 9 | 38 | NOVEMBER
T-448-1859 | PS5-88-OB-6694C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone C | 2 | To be completed |  | 28 | AUGUST
T-309-1860 | PS5-46-OB-2259C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-06-07 | PS5-06-03 | PS5 - Milestone C | 2 | Closed | 39 | 27 | JUNE
T-070-1861 | PS5-37-UR-7343D | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-07-21 | PS5-07-04 | PS5 - Milestone H | 7 | Closed | 37 | 42 | JULY
T-562-1862 | PS5-59-UR-1281A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | In progress |  | 19 | SEPTEMBER
T-449-1863 | PS5-95-IK-2685A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-08-08 | PS5-99-03 | PS5 - Milestone H | 7 | Closed | 23 | 27 | AUGUST
T-271-1864 | PS5-75-IK-2304A | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone H | 7 | On hold |  | 5 | AUGUST
T-176-1865 | PS5-66-IK-2164B | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-06-11 | PS5-10-05 | PS5 - Milestone F | 5 | Closed | 29 | 16 | JUNE
T-359-1866 | PS5-55-OB-4723A | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-04-07 | PS5-11-03 | PS5 - Milestone F | 5 | Closed | 45 | 48 | APRIL
T-763-1867 | PS5-16-UR-7069C | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-08-23 | PS5-99-02 | PS5 - Milestone C | 2 | Closed | 13 | 8 | AUGUST
T-586-1868 | PS5-28-UR-4385A | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-11-24 | PS5-02-01 | PS5 - Milestone B | 1.1 | Closed | 8 | 16 | NOVEMBER
T-654-1869 | PS5-16-OB-5357A | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | To be completed |  | 45 | DECEMBER
T-558-1870 | PS5-68-OB-8962C | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-09-23 | PS5-05-03 | PS5 - Milestone I | 8 | Closed | 31 | 36 | SEPTEMBER
T-282-1871 | PS5-21-UR-6642D | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone G | 6 | In progress |  | 44 | OCTOBER
T-829-1872 | PS5-63-IK-5188D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone I | 8 | To be completed |  | 13 | NOVEMBER
T-920-1873 | PS5-80-OB-6850D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | In progress |  | 47 | NOVEMBER
T-468-1874 | PS5-73-UR-3823D | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-06-09 | PS5-09-03 | PS5 - Milestone A | 1 | Closed | 20 | 26 | JUNE
T-978-1875 | PS5-91-IK-6011C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone I | 8 | To be completed |  | 37 | DECEMBER
T-396-1876 | PS5-15-OB-5207D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-08-04 | PS5-01-08 | PS5 - Milestone I | 8 | Closed | 14 | 46 | AUGUST
T-026-1877 | PS5-77-IK-5730A | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone G | 6 | In progress |  | 21 | OCTOBER
T-415-1878 | PS5-67-UR-8082C | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | To be completed |  | 42 | NOVEMBER
T-366-1879 | PS5-79-OB-8621B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-11-26 | PS5-01-05 | PS5 - Milestone I | 8 | Closed | 20 | 17 | NOVEMBER
T-115-1880 | PS5-89-UR-4384A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-01-11 | PS5-10-03 | PS5 - Milestone A | 1 | Closed | 22 | 18 | JANUARY
T-765-1881 | PS5-33-OB-3380B | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-12-08 | PS5-82-02 | PS5 - Milestone C | 2 | Closed | 47 | 7 | DECEMBER
T-050-1882 | PS5-57-IK-8695B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone I | 8 | On hold |  | 22 | SEPTEMBER
T-404-1883 | PS5-66-UR-8698A | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-01-24 | PS5-04-03 | PS5 - Milestone A | 1 | Closed | 23 | 6 | JANUARY
T-708-1884 | PS5-17-OB-2303C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone E | 4 | In progress |  | 10 | AUGUST
T-217-1885 | PS5-77-IK-8080A | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | To be completed |  | 10 | NOVEMBER
T-321-1886 | PS5-89-OB-4031B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone F | 5 | In progress |  | 33 | OCTOBER
T-703-1887 | PS5-19-OB-6432B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | In progress |  | 14 | SEPTEMBER
T-259-1888 | PS5-90-IK-9855C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-08-22 | PS5-62-02 | PS5 - Milestone D | 3 | Closed | 17 | 29 | AUGUST
T-331-1889 | PS5-97-IK-5260C | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | In progress |  | 6 | SEPTEMBER
T-420-1890 | PS5-91-OB-2131C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-10-23 | PS5-10-01 | PS5 - Milestone C | 2 | Closed | 30 | 46 | OCTOBER
T-891-1891 | PS5-91-OB-9504C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-08-18 | PS5-62-02 | PS5 - Milestone D | 3 | Closed | 40 | 35 | AUGUST
T-113-1892 | PS5-97-UR-7616D | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-12-08 | PS5-01-03 | PS5 - Milestone H | 7 | Closed | 36 | 16 | DECEMBER
T-424-1893 | PS5-89-UR-3917A | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone C | 2 | To be completed |  | 25 | OCTOBER
T-594-1894 | PS5-43-IK-8850B | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone E | 4 | In progress |  | 12 | DECEMBER
T-695-1895 | PS5-65-OB-3011A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-05-28 | PS5-07-03 | PS5 - Milestone E | 4 | Closed | 15 | 46 | MAY
T-791-1896 | PS5-54-IK-9055A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-12-26 | PS5-05-01 | PS5 - Milestone I | 8 | Closed | 25 | 18 | DECEMBER
T-340-1897 | PS5-50-OB-3905D | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone B | 1.1 | On hold |  | 35 | SEPTEMBER
T-553-1898 | PS5-40-OB-7700B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone C | 2 | To be completed |  | 40 | DECEMBER
T-708-1899 | PS5-91-UR-3096D | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone F | 5 | To be completed |  | 47 | SEPTEMBER
T-289-1900 | PS5-16-UR-7677B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-09-12 | PS5-07-03 | PS5 - Milestone A | 1 | Closed | 28 | 21 | SEPTEMBER
T-765-1901 | PS5-94-IK-2011A | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-03-10 | PS5-13-01 | PS5 - Milestone B | 1.1 | Closed | 15 | 16 | MARCH
T-194-1902 | PS5-64-UR-6192A | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-12-18 | PS5-03-23 | PS5 - Milestone D | 3 | Closed | 21 | 43 | DECEMBER
T-701-1903 | PS5-19-OB-1001B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-10-27 | PS5-60-07 | PS5 - Milestone B | 1.1 | Closed | 45 | 23 | OCTOBER
T-642-1904 | PS5-74-OB-9803D | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-12-21 | PS5-02-03 | PS5 - Milestone E | 4 | Closed | 19 | 5 | DECEMBER
T-083-1905 | PS5-86-IK-2797D | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone B | 1.1 | To be completed |  | 23 | NOVEMBER
T-650-1906 | PS5-23-OB-4120B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-03-21 | PS5-01-04 | PS5 - Milestone G | 6 | Closed | 45 | 48 | MARCH
T-707-1907 | PS5-94-OB-2549D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone C | 2 | On hold |  | 8 | OCTOBER
T-331-1908 | PS5-26-UR-3704B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-04-01 | PS5-82-01 | PS5 - Milestone E | 4 | Closed | 33 | 6 | APRIL
T-967-1909 | PS5-08-UR-3309C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-09-27 | PS5-06-03 | PS5 - Milestone A | 1 | Closed | 6 | 21 | SEPTEMBER
T-329-1910 | PS5-56-UR-3719B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone G | 6 | In progress |  | 37 | OCTOBER
T-924-1911 | PS5-61-OB-6595C | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone G | 6 | To be completed |  | 43 | NOVEMBER
T-846-1912 | PS5-32-UR-5433D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-07-19 | PS5-03-01 | PS5 - Milestone H | 7 | Closed | 16 | 38 | JULY
T-123-1913 | PS5-07-UR-1818C | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-10-15 | PS5-07-01 | PS5 - Milestone A | 1 | Closed | 6 | 45 | OCTOBER
T-553-1914 | PS5-46-OB-6840C | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-09 | PS5-60-10 | PS5 - Milestone E | 4 | Closed | 9 | 41 | APRIL
T-610-1915 | PS5-48-IK-6245B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-05-10 | PS5-09-01 | PS5 - Milestone D | 3 | Closed | 9 | 15 | MAY
T-862-1916 | PS5-66-UR-3304C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-10-10 | PS5-02-01 | PS5 - Milestone B | 1.1 | Closed | 46 | 36 | OCTOBER
T-846-1917 | PS5-83-IK-1380C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | On hold |  | 23 | SEPTEMBER
T-741-1918 | PS5-44-UR-6697A | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-09-18 | PS5-60-01 | PS5 - Milestone E | 4 | Closed | 36 | 41 | SEPTEMBER
T-231-1919 | PS5-81-OB-4646A | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone C | 2 | On hold |  | 22 | NOVEMBER
T-472-1920 | PS5-86-IK-6398C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-02-12 | PS5-06-03 | PS5 - Milestone F | 5 | Closed | 9 | 20 | FEBRUARY
T-380-1921 | PS5-97-OB-8491B | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-12-17 | PS5-62-02 | PS5 - Milestone D | 3 | Closed | 29 | 11 | DECEMBER
T-252-1922 | PS5-50-IK-6575C | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-07-10 | PS5-12-02 | PS5 - Milestone G | 6 | Closed | 11 | 9 | JULY
T-235-1923 | PS5-40-IK-4290B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-10-06 | PS5-61-07 | PS5 - Milestone G | 6 | Closed | 36 | 24 | OCTOBER
T-648-1924 | PS5-38-OB-9187C | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-08-20 | PS5-11-03 | PS5 - Milestone G | 6 | Closed | 19 | 30 | AUGUST
T-222-1925 | PS5-37-IK-1598A | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone A | 1 | On hold |  | 48 | NOVEMBER
T-869-1926 | PS5-40-OB-5940C | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-11-22 | PS5-61-07 | PS5 - Milestone F | 5 | Closed | 28 | 4 | NOVEMBER
T-136-1927 | PS5-69-OB-7631A | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone G | 6 | In progress |  | 43 | NOVEMBER
T-389-1928 | PS5-88-OB-9004D | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | In progress |  | 35 | NOVEMBER
T-364-1929 | PS5-89-OB-2936B | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-02-09 | PS5-06-02 | PS5 - Milestone G | 6 | Closed | 14 | 14 | FEBRUARY
T-276-1930 | PS5-89-IK-2431B | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone C | 2 | To be completed |  | 15 | OCTOBER
T-989-1931 | PS5-72-UR-4336C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-10-20 | PS5-03-01 | PS5 - Milestone E | 4 | Closed | 35 | 4 | OCTOBER
T-665-1932 | PS5-86-OB-9729D | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone B | 1.1 | In progress |  | 38 | AUGUST
T-762-1933 | PS5-74-OB-2040A | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-20 | PS5-60-04 | PS5 - Milestone A | 1 | Closed | 38 | 41 | MAY
T-103-1934 | PS5-50-OB-7488B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone I | 8 | To be completed |  | 47 | AUGUST
T-647-1935 | PS5-97-OB-5763D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone A | 1 | To be completed |  | 36 | SEPTEMBER
T-176-1936 | PS5-39-UR-9219B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone H | 7 | On hold |  | 38 | OCTOBER
T-883-1937 | PS5-95-OB-4313C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-11-09 | PS5-63-04 | PS5 - Milestone D | 3 | Closed | 41 | 42 | NOVEMBER
T-379-1938 | PS5-94-OB-7956A | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-11-15 | PS5-04-01 | PS5 - Milestone G | 6 | Closed | 26 | 11 | NOVEMBER
T-775-1939 | PS5-26-IK-7487C | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-04-03 | PS5-02-02 | PS5 - Milestone G | 6 | Closed | 40 | 44 | APRIL
T-125-1940 | PS5-55-UR-3903A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-11-02 | PS5-63-01 | PS5 - Milestone A | 1 | Closed | 15 | 11 | NOVEMBER
T-320-1941 | PS5-79-UR-2128A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone D | 3 | In progress |  | 4 | SEPTEMBER
T-148-1942 | PS5-33-IK-7576B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-11-22 | PS5-99-03 | PS5 - Milestone C | 2 | Closed | 18 | 11 | NOVEMBER
T-565-1943 | PS5-74-OB-8616B | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-01-01 | PS5-82-02 | PS5 - Milestone G | 6 | Closed | 24 | 41 | JANUARY
T-254-1944 | PS5-50-OB-7681C | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone F | 5 | On hold |  | 48 | OCTOBER
T-440-1945 | PS5-65-IK-8228A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone C | 2 | To be completed |  | 38 | SEPTEMBER
T-522-1946 | PS5-93-IK-9638C | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone A | 1 | In progress |  | 22 | SEPTEMBER
T-811-1947 | PS5-32-OB-9119C | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-10-06 | PS5-03-01 | PS5 - Milestone B | 1.1 | Closed | 18 | 16 | OCTOBER
T-760-1948 | PS5-63-UR-8730A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone G | 6 | In progress |  | 32 | DECEMBER
T-691-1949 | PS5-58-OB-5628B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | To be completed |  | 25 | DECEMBER
T-598-1950 | PS5-35-UR-9911A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone C | 2 | To be completed |  | 47 | OCTOBER
T-793-1951 | PS5-92-OB-7022D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-02-17 | PS5-09-02 | PS5 - Milestone I | 8 | Closed | 40 | 18 | FEBRUARY
T-607-1952 | PS5-66-UR-7737D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-12-09 | PS5-60-01 | PS5 - Milestone H | 7 | Closed | 37 | 44 | DECEMBER
T-260-1953 | PS5-57-OB-7344B | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-12-12 | PS5-06-03 | PS5 - Milestone D | 3 | Closed | 32 | 45 | DECEMBER
T-597-1954 | PS5-14-IK-9951A | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone E | 4 | In progress |  | 24 | OCTOBER
T-829-1955 | PS5-77-IK-7224A | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | To be completed |  | 9 | DECEMBER
T-337-1956 | PS5-52-OB-4178D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone H | 7 | To be completed |  | 15 | OCTOBER
T-870-1957 | PS5-30-IK-8873C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone D | 3 | To be completed |  | 33 | DECEMBER
T-087-1958 | PS5-46-IK-8905C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | On hold |  | 23 | SEPTEMBER
T-762-1959 | PS5-54-UR-9735C | CQM04 - Vessel | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | To be completed |  | 13 | DECEMBER
T-286-1960 | PS5-58-UR-3495D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone B | 1.1 | In progress |  | 15 | SEPTEMBER
T-590-1961 | PS5-50-OB-2059C | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | On hold |  | 21 | AUGUST
T-148-1962 | PS5-84-OB-9379D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone H | 7 | In progress |  | 11 | DECEMBER
T-659-1963 | PS5-92-OB-9402D | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | To be completed |  | 46 | AUGUST
T-870-1964 | PS5-01-IK-6937C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-09-26 | PS5-10-01 | PS5 - Milestone D | 3 | Closed | 15 | 36 | SEPTEMBER
T-322-1965 | PS5-44-UR-3131C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone H | 7 | In progress |  | 16 | DECEMBER
T-320-1966 | PS5-37-OB-3389A | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-11-10 | PS5-99-01 | PS5 - Milestone D | 3 | Closed | 33 | 18 | NOVEMBER
T-849-1967 | PS5-97-UR-8097A | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone C | 2 | In progress |  | 24 | OCTOBER
T-158-1968 | PS5-09-UR-3480B | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone A | 1 | To be completed |  | 22 | SEPTEMBER
T-269-1969 | PS5-47-OB-7890D | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-12-02 | PS5-82-01 | PS5 - Milestone G | 6 | Closed | 16 | 32 | DECEMBER
T-933-1970 | PS5-65-UR-6614D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-12-12 | PS5-62-02 | PS5 - Milestone A | 1 | Closed | 20 | 48 | DECEMBER
T-738-1971 | PS5-93-OB-9953A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | In progress |  | 25 | NOVEMBER
T-533-1972 | PS5-35-OB-9248C | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-03-08 | PS5-12-02 | PS5 - Milestone I | 8 | Closed | 27 | 34 | MARCH
T-726-1973 | PS5-09-IK-1730B | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-01-27 | PS5-11-03 | PS5 - Milestone G | 6 | Closed | 31 | 37 | JANUARY
T-606-1974 | PS5-11-OB-3322D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone A | 1 | On hold |  | 22 | AUGUST
T-007-1975 | PS5-12-UR-7451C | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | To be completed |  | 30 | SEPTEMBER
T-299-1976 | PS5-19-OB-5120C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-07-05 | PS5-04-01 | PS5 - Milestone G | 6 | Closed | 31 | 18 | JULY
T-125-1977 | PS5-76-OB-9531C | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone I | 8 | On hold |  | 41 | AUGUST
T-540-1978 | PS5-67-UR-5866B | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | To be completed |  | 11 | NOVEMBER
T-636-1979 | PS5-24-OB-6236B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-03-07 | PS5-03-03 | PS5 - Milestone D | 3 | Closed | 37 | 34 | MARCH
T-363-1980 | PS5-25-UR-5832D | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-06-23 | PS5-13-01 | PS5 - Milestone F | 5 | Closed | 30 | 43 | JUNE
T-015-1981 | PS5-89-OB-2606B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-10-20 | PS5-82-07 | PS5 - Milestone A | 1 | Closed | 36 | 40 | OCTOBER
T-513-1982 | PS5-78-IK-3288B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-01-09 | PS5-99-02 | PS5 - Milestone F | 5 | Closed | 33 | 17 | JANUARY
T-283-1983 | PS5-73-OB-2972A | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-04-15 | PS5-07-01 | PS5 - Milestone C | 2 | Closed | 41 | 24 | APRIL
T-738-1984 | PS5-66-IK-4862D | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-01-19 | PS5-10-02 | PS5 - Milestone D | 3 | Closed | 7 | 12 | JANUARY
T-081-1985 | PS5-27-OB-5415C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone I | 8 | In progress |  | 35 | AUGUST
T-740-1986 | PS5-74-UR-2829C | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone D | 3 | In progress |  | 46 | NOVEMBER
T-016-1987 | PS5-53-OB-4973D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone E | 4 | In progress |  | 14 | OCTOBER
T-828-1988 | PS5-14-IK-5008B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone G | 6 | To be completed |  | 10 | AUGUST
T-079-1989 | PS5-88-OB-6939C | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-08-19 | PS5-82-07 | PS5 - Milestone E | 4 | Closed | 8 | 30 | AUGUST
T-610-1990 | PS5-59-IK-2721D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-07-28 | PS5-07-02 | PS5 - Milestone D | 3 | Closed | 30 | 39 | JULY
T-706-1991 | PS5-57-IK-6685D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | On hold |  | 30 | SEPTEMBER
T-171-1992 | PS5-03-OB-5789B | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone F | 5 | To be completed |  | 45 | AUGUST
T-743-1993 | PS5-04-UR-9243C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone C | 2 | On hold |  | 15 | AUGUST
T-357-1994 | PS5-14-UR-3781C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone I | 8 | To be completed |  | 37 | DECEMBER
T-242-1995 | PS5-54-OB-3088A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-06-15 | PS5-62-02 | PS5 - Milestone H | 7 | Closed | 18 | 13 | JUNE
T-220-1996 | PS5-68-OB-2252C | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | To be completed |  | 12 | SEPTEMBER
T-343-1997 | PS5-23-OB-6701C | CQM03 - Heat Exchanger | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone G | 6 | On hold |  | 40 | AUGUST
T-026-1998 | PS5-86-IK-2757A | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | In progress |  | 25 | AUGUST
T-481-1999 | PS5-06-UR-1900C | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | On hold |  | 4 | AUGUST
T-381-2000 | PS5-15-IK-3003B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone E | 4 | On hold |  | 36 | DECEMBER
T-743-2001 | PS5-31-IK-2071D | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone F | 5 | To be completed |  | 18 | DECEMBER
T-490-2002 | PS5-44-OB-2147D | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-06-06 | PS5-06-01 | PS5 - Milestone E | 4 | Closed | 26 | 30 | JUNE
T-561-2003 | PS5-48-IK-8376B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone E | 4 | On hold |  | 5 | DECEMBER
T-108-2004 | PS5-05-IK-3826D | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone F | 5 | In progress |  | 5 | NOVEMBER
T-012-2005 | PS5-93-OB-7293D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-09-03 | PS5-07-01 | PS5 - Milestone F | 5 | Closed | 31 | 42 | SEPTEMBER
T-991-2006 | PS5-68-OB-5235B | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone I | 8 | To be completed |  | 41 | OCTOBER
T-918-2007 | PS5-45-OB-9557A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone G | 6 | To be completed |  | 38 | NOVEMBER
T-475-2008 | PS5-61-OB-2458A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-06-11 | PS5-06-02 | PS5 - Milestone E | 4 | Closed | 42 | 45 | JUNE
T-072-2009 | PS5-70-OB-8556C | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone G | 6 | To be completed |  | 41 | AUGUST
T-052-2010 | PS5-07-OB-7793D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone A | 1 | To be completed |  | 5 | SEPTEMBER
T-837-2011 | PS5-47-IK-3562D | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone G | 6 | To be completed |  | 42 | DECEMBER
T-277-2012 | PS5-16-OB-2706B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone H | 7 | To be completed |  | 16 | OCTOBER
T-694-2013 | PS5-76-UR-6401A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-06-08 | PS5-62-02 | PS5 - Milestone D | 3 | Closed | 31 | 22 | JUNE
T-801-2014 | PS5-58-IK-5435D | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone E | 4 | In progress |  | 26 | SEPTEMBER
T-265-2015 | PS5-72-UR-9366A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-06-24 | PS5-12-01 | PS5 - Milestone A | 1 | Closed | 7 | 9 | JUNE
T-704-2016 | PS5-61-IK-9067B | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone C | 2 | On hold |  | 36 | SEPTEMBER
T-353-2017 | PS5-66-OB-5275C | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone C | 2 | To be completed |  | 46 | DECEMBER
T-236-2018 | PS5-43-OB-2162D | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone F | 5 | To be completed |  | 48 | NOVEMBER
T-825-2019 | PS5-60-OB-1352B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone G | 6 | In progress |  | 32 | DECEMBER
T-122-2020 | PS5-86-OB-9775A | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-06-18 | PS5-04-01 | PS5 - Milestone F | 5 | Closed | 30 | 21 | JUNE
T-610-2021 | PS5-77-OB-1925C | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone E | 4 | In progress |  | 35 | SEPTEMBER
T-437-2022 | PS5-98-UR-3646A | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone G | 6 | In progress |  | 17 | SEPTEMBER
T-666-2023 | PS5-18-UR-5295C | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone E | 4 | In progress |  | 9 | SEPTEMBER
T-733-2024 | PS5-80-OB-3156B | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | In progress |  | 11 | AUGUST
T-711-2025 | PS5-02-OB-9685B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone B | 1.1 | On hold |  | 31 | SEPTEMBER
T-848-2026 | PS5-57-IK-8393A | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone F | 5 | To be completed |  | 30 | DECEMBER
T-079-2027 | PS5-42-IK-8769D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-10-18 | PS5-02-01 | PS5 - Milestone C | 2 | Closed | 46 | 12 | OCTOBER
T-809-2028 | PS5-65-UR-8392B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone B | 1.1 | To be completed |  | 15 | DECEMBER
T-534-2029 | PS5-97-IK-5718C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone B | 1.1 | To be completed |  | 17 | SEPTEMBER
T-976-2030 | PS5-74-IK-6989B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | To be completed |  | 31 | OCTOBER
T-514-2031 | PS5-15-OB-2477B | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-05-03 | PS5-82-02 | PS5 - Milestone C | 2 | Closed | 22 | 21 | MAY
T-320-2032 | PS5-22-IK-6279D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-03-09 | PS5-06-01 | PS5 - Milestone I | 8 | Closed | 21 | 34 | MARCH
T-813-2033 | PS5-72-UR-5423A | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | In progress |  | 42 | DECEMBER
T-567-2034 | PS5-62-IK-1839B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone G | 6 | On hold |  | 11 | DECEMBER
T-745-2035 | PS5-35-OB-8402A | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-02-28 | PS5-06-01 | PS5 - Milestone E | 4 | Closed | 10 | 31 | FEBRUARY
T-955-2036 | PS5-88-OB-3753A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-12-13 | PS5-09-02 | PS5 - Milestone H | 7 | Closed | 39 | 12 | DECEMBER
T-632-2037 | PS5-03-OB-8799B | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | To be completed |  | 23 | OCTOBER
T-463-2038 | PS5-71-OB-5727A | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone B | 1.1 | In progress |  | 35 | DECEMBER
T-611-2039 | PS5-16-UR-4945C | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone F | 5 | To be completed |  | 9 | DECEMBER
T-552-2040 | PS5-94-IK-4472A | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-04-25 | PS5-09-04 | PS5 - Milestone A | 1 | Closed | 35 | 28 | APRIL
T-179-2041 | PS5-18-UR-7943B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone F | 5 | In progress |  | 36 | OCTOBER
T-142-2042 | PS5-20-OB-6411B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-11-13 | PS5-08-02 | PS5 - Milestone D | 3 | Closed | 26 | 37 | NOVEMBER
T-738-2043 | PS5-96-UR-5734C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-01-20 | PS5-10-04 | PS5 - Milestone E | 4 | Closed | 13 | 21 | JANUARY
T-715-2044 | PS5-66-UR-3440A | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone G | 6 | In progress |  | 41 | OCTOBER
T-549-2045 | PS5-48-OB-5515D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-10-08 | PS5-09-02 | PS5 - Milestone I | 8 | Closed | 42 | 23 | OCTOBER
T-195-2046 | PS5-21-UR-4345D | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-04-16 | PS5-09-03 | PS5 - Milestone E | 4 | Closed | 17 | 16 | APRIL
T-995-2047 | PS5-77-UR-2250A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-08-18 | PS5-12-01 | PS5 - Milestone F | 5 | Closed | 28 | 25 | AUGUST
T-365-2048 | PS5-62-OB-8845A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone C | 2 | To be completed |  | 9 | NOVEMBER
T-346-2049 | PS5-98-IK-2855D | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone D | 3 | In progress |  | 19 | OCTOBER
T-968-2050 | PS5-59-UR-9848D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone B | 1.1 | In progress |  | 44 | SEPTEMBER
T-019-2051 | PS5-80-OB-5650C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone G | 6 | In progress |  | 18 | NOVEMBER
T-091-2052 | PS5-03-UR-9609B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | On hold |  | 37 | DECEMBER
T-871-2053 | PS5-65-OB-4131D | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone A | 1 | To be completed |  | 7 | SEPTEMBER
T-075-2054 | PS5-13-OB-7228B | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-04-06 | PS5-08-02 | PS5 - Milestone A | 1 | Closed | 11 | 8 | APRIL
T-639-2055 | PS5-54-IK-8739C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-07-26 | PS5-02-03 | PS5 - Milestone G | 6 | Closed | 5 | 7 | JULY
T-882-2056 | PS5-85-UR-2324A | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone E | 4 | To be completed |  | 43 | NOVEMBER
T-321-2057 | PS5-95-IK-3642C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone B | 1.1 | On hold |  | 13 | AUGUST
T-732-2058 | PS5-69-UR-2123A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone B | 1.1 | To be completed |  | 44 | DECEMBER
T-312-2059 | PS5-73-OB-1428B | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-07-02 | PS5-01-06 | PS5 - Milestone B | 1.1 | Closed | 13 | 48 | JULY
T-054-2060 | PS5-78-IK-6473A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-11-27 | PS5-62-02 | PS5 - Milestone H | 7 | Closed | 44 | 21 | NOVEMBER
T-797-2061 | PS5-89-UR-6670A | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone D | 3 | In progress |  | 13 | NOVEMBER
T-840-2062 | PS5-34-UR-2362B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone C | 2 | On hold |  | 46 | DECEMBER
T-231-2063 | PS5-95-OB-8944A | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-07-03 | PS5-07-02 | PS5 - Milestone G | 6 | Closed | 46 | 24 | JULY
T-107-2064 | PS5-28-OB-1096A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-04-20 | PS5-13-01 | PS5 - Milestone I | 8 | Closed | 32 | 39 | APRIL
T-887-2065 | PS5-19-UR-4730D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-09-14 | PS5-05-03 | PS5 - Milestone D | 3 | Closed | 12 | 13 | SEPTEMBER
T-845-2066 | PS5-50-IK-8175B | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | To be completed |  | 29 | SEPTEMBER
T-321-2067 | PS5-31-UR-1437A | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone F | 5 | In progress |  | 42 | SEPTEMBER
T-763-2068 | PS5-72-IK-2817C | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone G | 6 | On hold |  | 31 | NOVEMBER
T-312-2069 | PS5-55-UR-8094B | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone C | 2 | In progress |  | 44 | DECEMBER
T-343-2070 | PS5-92-IK-6135B | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone I | 8 | In progress |  | 22 | NOVEMBER
T-996-2071 | PS5-94-OB-4842B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | To be completed |  | 15 | DECEMBER
T-348-2072 | PS5-61-UR-7192D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone G | 6 | To be completed |  | 39 | AUGUST
T-052-2073 | PS5-63-OB-1290C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-04-02 | PS5-01-06 | PS5 - Milestone A | 1 | Closed | 12 | 9 | APRIL
T-349-2074 | PS5-02-OB-3643B | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-01-28 | PS5-06-02 | PS5 - Milestone C | 2 | Closed | 7 | 28 | JANUARY
T-280-2075 | PS5-91-OB-3296C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | To be completed |  | 6 | NOVEMBER
T-864-2076 | PS5-26-OB-1609B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone B | 1.1 | In progress |  | 8 | OCTOBER
T-009-2077 | PS5-73-IK-5441D | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone F | 5 | To be completed |  | 44 | DECEMBER
T-971-2078 | PS5-83-UR-4508B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | To be completed |  | 13 | SEPTEMBER
T-246-2079 | PS5-51-OB-9799A | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone H | 7 | To be completed |  | 42 | AUGUST
T-347-2080 | PS5-43-UR-2061C | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-05-13 | PS5-62-01 | PS5 - Milestone A | 1 | Closed | 16 | 21 | MAY
T-674-2081 | PS5-23-UR-6315B | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone G | 6 | In progress |  | 23 | DECEMBER
T-241-2082 | PS5-35-OB-2443C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-07-13 | PS5-09-02 | PS5 - Milestone F | 5 | Closed | 9 | 30 | JULY
T-278-2083 | PS5-86-UR-4094A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | To be completed |  | 20 | OCTOBER
T-653-2084 | PS5-65-OB-2857B | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone F | 5 | To be completed |  | 10 | NOVEMBER
T-100-2085 | PS5-57-OB-7940A | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-11-16 | PS5-61-01 | PS5 - Milestone H | 7 | Closed | 38 | 10 | NOVEMBER
T-322-2086 | PS5-61-OB-7713B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone H | 7 | In progress |  | 25 | SEPTEMBER
T-010-2087 | PS5-84-IK-7711C | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-10-15 | PS5-01-03 | PS5 - Milestone A | 1 | Closed | 25 | 29 | OCTOBER
T-869-2088 | PS5-48-OB-7913D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone E | 4 | In progress |  | 36 | DECEMBER
T-296-2089 | PS5-50-OB-9543B | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-03-05 | PS5-05-03 | PS5 - Milestone G | 6 | Closed | 31 | 37 | MARCH
T-987-2090 | PS5-05-OB-3196D | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-12-13 | PS5-09-04 | PS5 - Milestone I | 8 | Closed | 12 | 43 | DECEMBER
T-537-2091 | PS5-65-IK-2105C | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone B | 1.1 | To be completed |  | 29 | SEPTEMBER
T-527-2092 | PS5-09-UR-6531D | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-10-09 | PS5-60-01 | PS5 - Milestone D | 3 | Closed | 10 | 41 | OCTOBER
T-871-2093 | PS5-29-OB-2299B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone C | 2 | To be completed |  | 34 | AUGUST
T-679-2094 | PS5-05-IK-4768C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-02-26 | PS5-01-02 | PS5 - Milestone E | 4 | Closed | 23 | 19 | FEBRUARY
T-081-2095 | PS5-01-OB-5794C | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone F | 5 | On hold |  | 37 | DECEMBER
T-548-2096 | PS5-72-OB-1996D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | In progress |  | 42 | DECEMBER
T-797-2097 | PS5-54-OB-8607A | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone C | 2 | To be completed |  | 37 | SEPTEMBER
T-432-2098 | PS5-45-OB-6476B | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone F | 5 | In progress |  | 18 | DECEMBER
T-823-2099 | PS5-59-OB-6202A | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone A | 1 | In progress |  | 40 | NOVEMBER
T-532-2100 | PS5-15-IK-3820C | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-02-27 | PS5-09-02 | PS5 - Milestone D | 3 | Closed | 27 | 40 | FEBRUARY
T-819-2101 | PS5-71-OB-7570C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-10-05 | PS5-08-01 | PS5 - Milestone A | 1 | Closed | 30 | 11 | OCTOBER
T-955-2102 | PS5-61-UR-8259C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-01-28 | PS5-13-01 | PS5 - Milestone H | 7 | Closed | 29 | 24 | JANUARY
T-274-2103 | PS5-09-UR-9952B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | In progress |  | 33 | SEPTEMBER
T-968-2104 | PS5-25-IK-4588A | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone D | 3 | To be completed |  | 48 | OCTOBER
T-538-2105 | PS5-56-OB-4571C | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-03-20 | PS5-02-01 | PS5 - Milestone A | 1 | Closed | 16 | 24 | MARCH
T-864-2106 | PS5-87-UR-9378B | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone H | 7 | To be completed |  | 28 | SEPTEMBER
T-180-2107 | PS5-25-OB-1148A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone F | 5 | In progress |  | 29 | DECEMBER
T-509-2108 | PS5-70-UR-4509D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone F | 5 | On hold |  | 30 | OCTOBER
T-066-2109 | PS5-06-UR-7720D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone E | 4 | To be completed |  | 42 | NOVEMBER
T-384-2110 | PS5-45-UR-2600C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone C | 2 | In progress |  | 42 | DECEMBER
T-541-2111 | PS5-37-UR-8284D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone E | 4 | To be completed |  | 25 | DECEMBER
T-168-2112 | PS5-96-IK-4187C | CQH02 - AHU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | To be completed |  | 24 | AUGUST
T-691-2113 | PS5-89-OB-2011D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-10-10 | PS5-03-02 | PS5 - Milestone A | 1 | Closed | 11 | 32 | OCTOBER
T-117-2114 | PS5-01-OB-8396A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone B | 1.1 | To be completed |  | 22 | SEPTEMBER
T-427-2115 | PS5-19-OB-5471C | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-05-24 | PS5-02-01 | PS5 - Milestone G | 6 | Closed | 42 | 17 | MAY
T-621-2116 | PS5-04-OB-7625C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone C | 2 | On hold |  | 29 | AUGUST
T-528-2117 | PS5-94-OB-4160A | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone I | 8 | On hold |  | 17 | NOVEMBER
T-232-2118 | PS5-16-UR-3686D | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-05-11 | PS5-10-01 | PS5 - Milestone C | 2 | Closed | 27 | 28 | MAY
T-443-2119 | PS5-01-IK-7327C | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone G | 6 | To be completed |  | 23 | DECEMBER
T-107-2120 | PS5-63-OB-9859D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-12-04 | PS5-82-02 | PS5 - Milestone C | 2 | Closed | 24 | 48 | DECEMBER
T-652-2121 | PS5-94-UR-7973A | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone H | 7 | To be completed |  | 19 | OCTOBER
T-399-2122 | PS5-23-OB-8477C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-04-25 | PS5-01-05 | PS5 - Milestone E | 4 | Closed | 9 | 10 | APRIL
T-922-2123 | PS5-15-OB-8071D | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone A | 1 | To be completed |  | 37 | AUGUST
T-682-2124 | PS5-89-IK-9077A | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone C | 2 | In progress |  | 14 | AUGUST
T-822-2125 | PS5-57-OB-7604D | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-02-26 | PS5-04-02 | PS5 - Milestone H | 7 | Closed | 10 | 31 | FEBRUARY
T-847-2126 | PS5-58-IK-1153B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-03-14 | PS5-07-01 | PS5 - Milestone E | 4 | Closed | 45 | 11 | MARCH
T-279-2127 | PS5-35-OB-8930A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone G | 6 | To be completed |  | 27 | SEPTEMBER
T-738-2128 | PS5-73-OB-9052D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | On hold |  | 17 | DECEMBER
T-071-2129 | PS5-01-OB-3212C | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone G | 6 | To be completed |  | 35 | AUGUST
T-434-2130 | PS5-97-IK-3653B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-08-14 | PS5-60-01 | PS5 - Milestone F | 5 | Closed | 32 | 32 | AUGUST
T-292-2131 | PS5-05-OB-2186C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone B | 1.1 | On hold |  | 29 | SEPTEMBER
T-396-2132 | PS5-33-OB-4759A | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | To be completed |  | 29 | DECEMBER
T-210-2133 | PS5-94-IK-7728A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-03-20 | PS5-01-06 | PS5 - Milestone C | 2 | Closed | 8 | 46 | MARCH
T-987-2134 | PS5-27-OB-4562C | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone G | 6 | To be completed |  | 14 | DECEMBER
T-999-2135 | PS5-21-OB-5490D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone F | 5 | In progress |  | 15 | SEPTEMBER
T-540-2136 | PS5-62-OB-3363A | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone G | 6 | To be completed |  | 44 | DECEMBER
T-540-2137 | PS5-50-OB-6213C | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone F | 5 | In progress |  | 5 | NOVEMBER
T-267-2138 | PS5-40-OB-5057D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-01-15 | PS5-09-03 | PS5 - Milestone B | 1.1 | Closed | 10 | 23 | JANUARY
T-300-2139 | PS5-96-IK-2298C | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-05-25 | PS5-60-07 | PS5 - Milestone E | 4 | Closed | 31 | 7 | MAY
T-387-2140 | PS5-18-IK-4757D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone C | 2 | In progress |  | 10 | NOVEMBER
T-108-2141 | PS5-39-OB-3490C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-09-20 | PS5-01-09 | PS5 - Milestone E | 4 | Closed | 11 | 48 | SEPTEMBER
T-734-2142 | PS5-66-OB-8023B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone G | 6 | In progress |  | 21 | OCTOBER
T-040-2143 | PS5-70-OB-9314D | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | In progress |  | 37 | SEPTEMBER
T-612-2144 | PS5-11-UR-2046A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | To be completed |  | 41 | AUGUST
T-716-2145 | PS5-23-OB-7975C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-02-06 | PS5-07-04 | PS5 - Milestone F | 5 | Closed | 30 | 6 | FEBRUARY
T-654-2146 | PS5-17-OB-2472B | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone I | 8 | In progress |  | 28 | AUGUST
T-917-2147 | PS5-07-IK-6862A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-12-15 | PS5-11-01 | PS5 - Milestone F | 5 | Closed | 34 | 30 | DECEMBER
T-392-2148 | PS5-04-IK-2790D | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone I | 8 | To be completed |  | 27 | OCTOBER
T-133-2149 | PS5-22-UR-2272B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-03-27 | PS5-60-04 | PS5 - Milestone E | 4 | Closed | 29 | 18 | MARCH
T-340-2150 | PS5-24-OB-6679D | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone I | 8 | To be completed |  | 6 | OCTOBER
T-730-2151 | PS5-70-OB-2526B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-05-28 | PS5-11-03 | PS5 - Milestone G | 6 | Closed | 42 | 30 | MAY
T-927-2152 | PS5-99-OB-4335B | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone F | 5 | To be completed |  | 40 | OCTOBER
T-460-2153 | PS5-12-IK-6932D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-01-02 | PS5-03-23 | PS5 - Milestone C | 2 | Closed | 12 | 48 | JANUARY
T-525-2154 | PS5-48-OB-6509A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone H | 7 | In progress |  | 5 | OCTOBER
T-748-2155 | PS5-89-IK-2592A | CQP02 - Valve Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | To be completed |  | 19 | NOVEMBER
T-683-2156 | PS5-80-OB-8303C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone A | 1 | To be completed |  | 22 | NOVEMBER
T-631-2157 | PS5-94-OB-9117A | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone I | 8 | On hold |  | 37 | AUGUST
T-815-2158 | PS5-74-OB-8193D | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-01-07 | PS5-11-03 | PS5 - Milestone B | 1.1 | Closed | 7 | 7 | JANUARY
T-253-2159 | PS5-81-OB-5659B | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | In progress |  | 17 | SEPTEMBER
T-260-2160 | PS5-87-OB-2045D | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-09-13 | PS5-11-02 | PS5 - Milestone D | 3 | Closed | 30 | 21 | SEPTEMBER
T-305-2161 | PS5-08-OB-7975B | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone F | 5 | In progress |  | 13 | SEPTEMBER
T-288-2162 | PS5-10-OB-8768B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone H | 7 | In progress |  | 16 | AUGUST
T-138-2163 | PS5-14-UR-8100C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-03-26 | PS5-99-01 | PS5 - Milestone D | 3 | Closed | 30 | 4 | MARCH
T-819-2164 | PS5-31-OB-9867C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-06-04 | PS5-01-06 | PS5 - Milestone H | 7 | Closed | 16 | 25 | JUNE
T-323-2165 | PS5-32-OB-9019A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | To be completed |  | 13 | NOVEMBER
T-161-2166 | PS5-09-OB-5913B | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-02-14 | PS5-12-02 | PS5 - Milestone G | 6 | Closed | 38 | 9 | FEBRUARY
T-260-2167 | PS5-24-UR-6963B | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone E | 4 | To be completed |  | 12 | AUGUST
T-625-2168 | PS5-86-OB-9327D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone C | 2 | In progress |  | 44 | AUGUST
T-716-2169 | PS5-02-OB-4688C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | To be completed |  | 32 | NOVEMBER
T-988-2170 | PS5-97-IK-5243D | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | To be completed |  | 24 | DECEMBER
T-455-2171 | PS5-22-IK-6049D | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone B | 1.1 | To be completed |  | 26 | DECEMBER
T-730-2172 | PS5-25-UR-6228A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-08-14 | PS5-07-03 | PS5 - Milestone I | 8 | Closed | 45 | 22 | AUGUST
T-296-2173 | PS5-46-IK-7628A | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone G | 6 | To be completed |  | 25 | SEPTEMBER
T-228-2174 | PS5-35-OB-8523C | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | In progress |  | 43 | DECEMBER
T-827-2175 | PS5-69-UR-3373C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-02-25 | PS5-11-01 | PS5 - Milestone D | 3 | Closed | 15 | 10 | FEBRUARY
T-154-2176 | PS5-82-UR-4579D | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone H | 7 | To be completed |  | 24 | SEPTEMBER
T-924-2177 | PS5-02-IK-5190C | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone B | 1.1 | On hold |  | 19 | DECEMBER
T-977-2178 | PS5-49-UR-3392D | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone I | 8 | In progress |  | 19 | OCTOBER
T-715-2179 | PS5-73-UR-1247B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-10-22 | PS5-60-04 | PS5 - Milestone E | 4 | Closed | 37 | 27 | OCTOBER
T-924-2180 | PS5-62-UR-7803C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone D | 3 | In progress |  | 17 | NOVEMBER
T-141-2181 | PS5-99-OB-1204D | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone G | 6 | To be completed |  | 34 | AUGUST
T-509-2182 | PS5-66-IK-9274B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone C | 2 | In progress |  | 34 | DECEMBER
T-695-2183 | PS5-25-OB-4109B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone A | 1 | To be completed |  | 34 | NOVEMBER
T-093-2184 | PS5-24-UR-6513B | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | In progress |  | 15 | NOVEMBER
T-147-2185 | PS5-80-IK-4794B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone H | 7 | On hold |  | 21 | AUGUST
T-530-2186 | PS5-97-OB-9875C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone H | 7 | In progress |  | 37 | AUGUST
T-854-2187 | PS5-46-IK-3123D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | In progress |  | 18 | OCTOBER
T-560-2188 | PS5-74-OB-4283D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | To be completed |  | 30 | AUGUST
T-898-2189 | PS5-65-UR-7622A | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone H | 7 | In progress |  | 43 | SEPTEMBER
T-250-2190 | PS5-51-UR-9987C | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone I | 8 | In progress |  | 32 | NOVEMBER
T-692-2191 | PS5-80-IK-2179D | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-12-15 | PS5-01-01 | PS5 - Milestone G | 6 | Closed | 41 | 11 | DECEMBER
T-554-2192 | PS5-49-IK-7370D | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone G | 6 | On hold |  | 33 | OCTOBER
T-874-2193 | PS5-41-UR-4608D | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-10-04 | PS5-05-02 | PS5 - Milestone H | 7 | Closed | 13 | 34 | OCTOBER
T-245-2194 | PS5-27-UR-2800B | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | On hold |  | 7 | NOVEMBER
T-745-2195 | PS5-79-IK-2414A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone H | 7 | On hold |  | 24 | AUGUST
T-876-2196 | PS5-71-UR-3153D | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone A | 1 | To be completed |  | 19 | AUGUST
T-154-2197 | PS5-94-IK-7598A | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-11-16 | PS5-07-01 | PS5 - Milestone A | 1 | Closed | 26 | 45 | NOVEMBER
T-555-2198 | PS5-92-UR-7091B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone C | 2 | To be completed |  | 9 | AUGUST
T-059-2199 | PS5-21-OB-7762A | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-04-02 | PS5-10-02 | PS5 - Milestone A | 1 | Closed | 38 | 10 | APRIL
T-688-2200 | PS5-85-OB-8822C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone D | 3 | To be completed |  | 28 | SEPTEMBER
T-437-2201 | PS5-20-OB-5169D | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | In progress |  | 24 | OCTOBER
T-050-2202 | PS5-96-OB-5638B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | To be completed |  | 15 | AUGUST
T-613-2203 | PS5-40-OB-6449A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-05-12 | PS5-01-04 | PS5 - Milestone E | 4 | Closed | 43 | 13 | MAY
T-454-2204 | PS5-57-OB-7072A | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-11-08 | PS5-82-02 | PS5 - Milestone I | 8 | Closed | 13 | 26 | NOVEMBER
T-946-2205 | PS5-98-IK-3207B | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone A | 1 | To be completed |  | 19 | SEPTEMBER
T-791-2206 | PS5-97-OB-2697C | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone H | 7 | To be completed |  | 8 | AUGUST
T-745-2207 | PS5-74-OB-8727B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-23 | PS5-60-04 | PS5 - Milestone B | 1.1 | Closed | 42 | 34 | JULY
T-559-2208 | PS5-31-IK-6951B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-02-14 | PS5-01-04 | PS5 - Milestone D | 3 | Closed | 38 | 25 | FEBRUARY
T-261-2209 | PS5-31-UR-3474C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | In progress |  | 41 | OCTOBER
T-603-2210 | PS5-79-UR-3613B | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone B | 1.1 | On hold |  | 7 | DECEMBER
T-074-2211 | PS5-58-UR-9842A | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-05-01 | PS5-62-01 | PS5 - Milestone C | 2 | Closed | 37 | 43 | MAY
T-573-2212 | PS5-75-OB-8791D | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone D | 3 | To be completed |  | 7 | OCTOBER
T-041-2213 | PS5-59-UR-5736A | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone G | 6 | In progress |  | 47 | DECEMBER
T-098-2214 | PS5-43-IK-3488D | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone D | 3 | In progress |  | 46 | NOVEMBER
T-427-2215 | PS5-71-OB-8080B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone F | 5 | In progress |  | 19 | AUGUST
T-750-2216 | PS5-10-OB-7065A | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | In progress |  | 43 | AUGUST
T-664-2217 | PS5-99-UR-9137A | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-07-13 | PS5-04-04 | PS5 - Milestone H | 7 | Closed | 21 | 33 | JULY
T-918-2218 | PS5-46-UR-8127C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone H | 7 | In progress |  | 27 | NOVEMBER
T-894-2219 | PS5-46-OB-6253C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone F | 5 | In progress |  | 19 | AUGUST
T-164-2220 | PS5-85-OB-1158B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-04-21 | PS5-09-01 | PS5 - Milestone A | 1 | Closed | 42 | 17 | APRIL
T-707-2221 | PS5-20-OB-2588C | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | To be completed |  | 29 | OCTOBER
T-601-2222 | PS5-88-IK-5267A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-09-14 | PS5-99-01 | PS5 - Milestone I | 8 | Closed | 35 | 48 | SEPTEMBER
T-901-2223 | PS5-68-OB-1106B | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone I | 8 | To be completed |  | 9 | AUGUST
T-633-2224 | PS5-54-UR-4096D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone I | 8 | To be completed |  | 5 | OCTOBER
T-687-2225 | PS5-85-UR-6348C | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-04-07 | PS5-08-02 | PS5 - Milestone I | 8 | Closed | 39 | 14 | APRIL
T-361-2226 | PS5-44-OB-8997B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone B | 1.1 | On hold |  | 15 | OCTOBER
T-064-2227 | PS5-38-UR-9690D | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone A | 1 | In progress |  | 21 | NOVEMBER
T-022-2228 | PS5-33-OB-1667A | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone E | 4 | In progress |  | 16 | NOVEMBER
T-807-2229 | PS5-43-OB-8336A | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-12-16 | PS5-62-01 | PS5 - Milestone A | 1 | Closed | 7 | 15 | DECEMBER
T-580-2230 | PS5-02-UR-3435A | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone D | 3 | To be completed |  | 18 | OCTOBER
T-710-2231 | PS5-97-IK-9125A | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone I | 8 | In progress |  | 30 | AUGUST
T-998-2232 | PS5-45-UR-6064A | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-12-13 | PS5-99-03 | PS5 - Milestone E | 4 | Closed | 35 | 22 | DECEMBER
T-365-2233 | PS5-52-IK-2171D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone A | 1 | To be completed |  | 5 | DECEMBER
T-327-2234 | PS5-94-OB-8220D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-04-24 | PS5-05-02 | PS5 - Milestone G | 6 | Closed | 45 | 15 | APRIL
T-207-2235 | PS5-98-OB-2829D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-04-16 | PS5-03-01 | PS5 - Milestone F | 5 | Closed | 28 | 39 | APRIL
T-160-2236 | PS5-39-IK-1203A | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone I | 8 | In progress |  | 45 | DECEMBER
T-320-2237 | PS5-34-IK-1378A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone E | 4 | To be completed |  | 40 | OCTOBER
T-016-2238 | PS5-87-OB-5997B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-03-16 | PS5-10-03 | PS5 - Milestone D | 3 | Closed | 6 | 29 | MARCH
T-670-2239 | PS5-21-UR-3563A | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-01-14 | PS5-08-01 | PS5 - Milestone A | 1 | Closed | 5 | 45 | JANUARY
T-326-2240 | PS5-07-OB-4295B | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone C | 2 | In progress |  | 25 | SEPTEMBER
T-151-2241 | PS5-09-UR-3621B | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-12-23 | PS5-08-01 | PS5 - Milestone C | 2 | Closed | 46 | 28 | DECEMBER
T-671-2242 | PS5-44-UR-6880B | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone B | 1.1 | To be completed |  | 34 | AUGUST
T-259-2243 | PS5-72-UR-3855C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-08-19 | PS5-04-02 | PS5 - Milestone A | 1 | Closed | 35 | 20 | AUGUST
T-359-2244 | PS5-36-OB-6698A | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone I | 8 | To be completed |  | 30 | AUGUST
T-009-2245 | PS5-15-UR-1425A | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone H | 7 | In progress |  | 37 | DECEMBER
T-575-2246 | PS5-70-IK-1176A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | In progress |  | 8 | OCTOBER
T-020-2247 | PS5-92-IK-7879A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-09-21 | PS5-01-04 | PS5 - Milestone E | 4 | Closed | 39 | 35 | SEPTEMBER
T-622-2248 | PS5-92-OB-7892D | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone D | 3 | To be completed |  | 26 | SEPTEMBER
T-984-2249 | PS5-42-OB-6796B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone I | 8 | In progress |  | 37 | OCTOBER
T-658-2250 | PS5-36-IK-5069A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone A | 1 | On hold |  | 12 | SEPTEMBER
T-162-2251 | PS5-82-UR-9606C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone C | 2 | To be completed |  | 34 | NOVEMBER
T-775-2252 | PS5-68-IK-2789D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone G | 6 | To be completed |  | 28 | AUGUST
T-484-2253 | PS5-27-OB-5841A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | To be completed |  | 25 | DECEMBER
T-452-2254 | PS5-95-IK-4067C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-12-09 | PS5-05-01 | PS5 - Milestone C | 2 | Closed | 7 | 45 | DECEMBER
T-721-2255 | PS5-17-OB-6243C | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone B | 1.1 | To be completed |  | 4 | NOVEMBER
T-296-2256 | PS5-11-OB-7424D | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone B | 1.1 | To be completed |  | 34 | NOVEMBER
T-827-2257 | PS5-32-OB-6363B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone I | 8 | To be completed |  | 37 | NOVEMBER
T-281-2258 | PS5-02-IK-8944D | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-01-03 | PS5-04-03 | PS5 - Milestone D | 3 | Closed | 35 | 5 | JANUARY
T-630-2259 | PS5-24-UR-3335C | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone H | 7 | In progress |  | 34 | OCTOBER
T-173-2260 | PS5-50-OB-4973A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | To be completed |  | 27 | NOVEMBER
T-597-2261 | PS5-34-OB-5619A | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone B | 1.1 | In progress |  | 22 | DECEMBER
T-309-2262 | PS5-72-UR-1104B | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone E | 4 | In progress |  | 27 | NOVEMBER
T-401-2263 | PS5-64-IK-8110B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone I | 8 | In progress |  | 5 | NOVEMBER
T-528-2264 | PS5-03-OB-6761B | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-02-01 | PS5-06-02 | PS5 - Milestone E | 4 | Closed | 31 | 23 | FEBRUARY
T-940-2265 | PS5-58-OB-6870D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | To be completed |  | 29 | SEPTEMBER
T-963-2266 | PS5-57-OB-3758A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-04-25 | PS5-11-03 | PS5 - Milestone I | 8 | Closed | 40 | 28 | APRIL
T-640-2267 | PS5-64-OB-7718B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | On hold |  | 20 | SEPTEMBER
T-091-2268 | PS5-45-IK-8025B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone F | 5 | In progress |  | 15 | OCTOBER
T-446-2269 | PS5-62-OB-4584D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-03-09 | PS5-63-04 | PS5 - Milestone I | 8 | Closed | 41 | 25 | MARCH
T-938-2270 | PS5-12-UR-6192C | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone H | 7 | In progress |  | 48 | SEPTEMBER
T-397-2271 | PS5-64-OB-4770D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-01-27 | PS5-10-05 | PS5 - Milestone B | 1.1 | Closed | 15 | 47 | JANUARY
T-789-2272 | PS5-25-IK-1159A | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | In progress |  | 7 | OCTOBER
T-631-2273 | PS5-69-OB-7247B | CQP01 - Pipe Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | To be completed |  | 37 | NOVEMBER
T-091-2274 | PS5-06-OB-8267B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone D | 3 | To be completed |  | 19 | NOVEMBER
T-838-2275 | PS5-73-OB-3873B | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone E | 4 | To be completed |  | 43 | SEPTEMBER
T-513-2276 | PS5-92-OB-1171B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone C | 2 | To be completed |  | 39 | OCTOBER
T-105-2277 | PS5-16-OB-4213C | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-09-15 | PS5-01-06 | PS5 - Milestone B | 1.1 | Closed | 9 | 4 | SEPTEMBER
T-421-2278 | PS5-05-OB-4157D | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone B | 1.1 | To be completed |  | 22 | DECEMBER
T-638-2279 | PS5-04-IK-9119C | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone C | 2 | In progress |  | 46 | OCTOBER
T-338-2280 | PS5-49-UR-5380A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone F | 5 | In progress |  | 33 | SEPTEMBER
T-527-2281 | PS5-61-OB-8443C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-08-17 | PS5-08-01 | PS5 - Milestone B | 1.1 | Closed | 42 | 43 | AUGUST
T-360-2282 | PS5-19-OB-7240D | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-12-23 | PS5-60-04 | PS5 - Milestone I | 8 | Closed | 48 | 44 | DECEMBER
T-520-2283 | PS5-37-UR-7146D | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-02-02 | PS5-82-02 | PS5 - Milestone I | 8 | Closed | 4 | 14 | FEBRUARY
T-357-2284 | PS5-18-OB-3835C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | To be completed |  | 46 | NOVEMBER
T-955-2285 | PS5-80-OB-8723C | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone G | 6 | In progress |  | 29 | NOVEMBER
T-627-2286 | PS5-31-UR-5015A | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-07-23 | PS5-03-01 | PS5 - Milestone I | 8 | Closed | 35 | 48 | JULY
T-125-2287 | PS5-09-OB-3787A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-02-25 | PS5-60-10 | PS5 - Milestone F | 5 | Closed | 33 | 14 | FEBRUARY
T-679-2288 | PS5-58-UR-4668D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | On hold |  | 5 | AUGUST
T-802-2289 | PS5-55-UR-5223A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone D | 3 | To be completed |  | 31 | SEPTEMBER
T-154-2290 | PS5-68-OB-1152A | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone A | 1 | To be completed |  | 34 | SEPTEMBER
T-709-2291 | PS5-32-OB-2844A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-02-10 | PS5-61-01 | PS5 - Milestone A | 1 | Closed | 16 | 39 | FEBRUARY
T-249-2292 | PS5-99-IK-8198A | CQE02 - LV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-06-27 | PS5-09-01 | PS5 - Milestone F | 5 | Closed | 28 | 33 | JUNE
T-110-2293 | PS5-31-IK-7414B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-08-27 | PS5-07-03 | PS5 - Milestone C | 2 | Closed | 42 | 4 | AUGUST
T-372-2294 | PS5-06-OB-2935A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-09-08 | PS5-11-01 | PS5 - Milestone D | 3 | Closed | 36 | 23 | SEPTEMBER
T-479-2295 | PS5-74-OB-4324B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-28 | PS5-60-04 | PS5 - Milestone E | 4 | Closed | 6 | 28 | APRIL
T-499-2296 | PS5-24-UR-5976D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone F | 5 | To be completed |  | 38 | OCTOBER
T-565-2297 | PS5-77-OB-1906D | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-11-07 | PS5-99-02 | PS5 - Milestone C | 2 | Closed | 23 | 45 | NOVEMBER
T-740-2298 | PS5-64-IK-5004D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-02-13 | PS5-03-02 | PS5 - Milestone I | 8 | Closed | 47 | 44 | FEBRUARY
T-327-2299 | PS5-50-IK-3891C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-04-12 | PS5-11-01 | PS5 - Milestone G | 6 | Closed | 47 | 38 | APRIL
T-964-2300 | PS5-81-OB-6444A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-02-01 | PS5-13-01 | PS5 - Milestone D | 3 | Closed | 10 | 40 | FEBRUARY
T-463-2301 | PS5-14-OB-8464B | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-03-13 | PS5-01-01 | PS5 - Milestone A | 1 | Closed | 4 | 27 | MARCH
T-192-2302 | PS5-33-OB-5637A | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone E | 4 | In progress |  | 41 | SEPTEMBER
T-700-2303 | PS5-48-OB-4461D | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone H | 7 | In progress |  | 29 | DECEMBER
T-110-2304 | PS5-89-OB-3070B | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-11-18 | PS5-07-01 | PS5 - Milestone C | 2 | Closed | 26 | 12 | NOVEMBER
T-360-2305 | PS5-20-OB-1189C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | To be completed |  | 40 | OCTOBER
T-245-2306 | PS5-34-OB-9112C | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-09-16 | PS5-10-02 | PS5 - Milestone C | 2 | Closed | 32 | 46 | SEPTEMBER
T-549-2307 | PS5-85-OB-8119C | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone G | 6 | In progress |  | 29 | SEPTEMBER
T-412-2308 | PS5-09-OB-8544C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-09-26 | PS5-09-03 | PS5 - Milestone C | 2 | Closed | 24 | 23 | SEPTEMBER
T-375-2309 | PS5-25-OB-2992B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | In progress |  | 47 | DECEMBER
T-311-2310 | PS5-75-OB-6890B | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | To be completed |  | 7 | NOVEMBER
T-659-2311 | PS5-55-IK-1545D | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone G | 6 | In progress |  | 39 | AUGUST
T-270-2312 | PS5-21-OB-2804D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-09-06 | PS5-10-02 | PS5 - Milestone F | 5 | Closed | 31 | 22 | SEPTEMBER
T-310-2313 | PS5-90-IK-2778D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-06-26 | PS5-05-01 | PS5 - Milestone E | 4 | Closed | 17 | 35 | JUNE
T-503-2314 | PS5-15-OB-5141B | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone D | 3 | In progress |  | 26 | SEPTEMBER
T-340-2315 | PS5-61-OB-6840D | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-07-17 | PS5-04-02 | PS5 - Milestone C | 2 | Closed | 9 | 24 | JULY
T-446-2316 | PS5-19-IK-5515D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone D | 3 | In progress |  | 15 | AUGUST
T-071-2317 | PS5-14-IK-9659C | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone E | 4 | In progress |  | 16 | DECEMBER
T-119-2318 | PS5-47-OB-9121C | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-01-03 | PS5-60-07 | PS5 - Milestone D | 3 | Closed | 20 | 44 | JANUARY
T-840-2319 | PS5-40-OB-9327B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone F | 5 | In progress |  | 13 | DECEMBER
T-141-2320 | PS5-60-OB-8957A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-06-05 | PS5-09-01 | PS5 - Milestone A | 1 | Closed | 24 | 33 | JUNE
T-482-2321 | PS5-33-UR-5553B | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | To be completed |  | 32 | NOVEMBER
T-824-2322 | PS5-92-OB-3302D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-01-02 | PS5-01-02 | PS5 - Milestone F | 5 | Closed | 12 | 5 | JANUARY
T-773-2323 | PS5-70-UR-8262A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone D | 3 | On hold |  | 39 | DECEMBER
T-981-2324 | PS5-39-OB-8208B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone D | 3 | To be completed |  | 38 | DECEMBER
T-475-2325 | PS5-63-UR-2853D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone I | 8 | On hold |  | 22 | SEPTEMBER
T-279-2326 | PS5-18-OB-6723C | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | On hold |  | 5 | NOVEMBER
T-051-2327 | PS5-48-IK-8638B | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-04-04 | PS5-10-06 | PS5 - Milestone A | 1 | Closed | 6 | 34 | APRIL
T-092-2328 | PS5-05-UR-3343D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone I | 8 | In progress |  | 11 | SEPTEMBER
T-396-2329 | PS5-57-UR-6851C | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | To be completed |  | 25 | OCTOBER
T-709-2330 | PS5-89-OB-2623C | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone I | 8 | In progress |  | 35 | SEPTEMBER
T-533-2331 | PS5-67-UR-9358A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-04-12 | PS5-09-04 | PS5 - Milestone H | 7 | Closed | 29 | 47 | APRIL
T-464-2332 | PS5-57-OB-3292A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone H | 7 | To be completed |  | 47 | SEPTEMBER
T-387-2333 | PS5-10-UR-2191B | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone G | 6 | In progress |  | 9 | AUGUST
T-859-2334 | PS5-82-IK-3442C | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-02-22 | PS5-06-01 | PS5 - Milestone I | 8 | Closed | 47 | 24 | FEBRUARY
T-334-2335 | PS5-81-UR-2663C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-03-01 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 38 | 4 | MARCH
T-335-2336 | PS5-94-OB-4679A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | On hold |  | 7 | AUGUST
T-874-2337 | PS5-47-OB-4182A | CQS03 - Deluge System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone H | 7 | In progress |  | 26 | AUGUST
T-270-2338 | PS5-81-OB-9529D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone F | 5 | In progress |  | 14 | NOVEMBER
T-742-2339 | PS5-87-IK-7752B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-03-05 | PS5-63-01 | PS5 - Milestone H | 7 | Closed | 21 | 30 | MARCH
T-871-2340 | PS5-84-IK-1086D | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone D | 3 | In progress |  | 37 | NOVEMBER
T-457-2341 | PS5-12-UR-5483D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-04-12 | PS5-82-01 | PS5 - Milestone G | 6 | Closed | 7 | 39 | APRIL
T-705-2342 | PS5-39-OB-3047C | CQM02 - Compressor | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-11-12 | PS5-82-02 | PS5 - Milestone G | 6 | Closed | 44 | 37 | NOVEMBER
T-608-2343 | PS5-52-OB-1428C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone D | 3 | To be completed |  | 33 | DECEMBER
T-457-2344 | PS5-39-OB-9381C | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-09-01 | PS5-11-02 | PS5 - Milestone C | 2 | Closed | 44 | 8 | SEPTEMBER
T-086-2345 | PS5-71-OB-4900B | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone G | 6 | On hold |  | 31 | NOVEMBER
T-744-2346 | PS5-39-OB-7226A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone C | 2 | To be completed |  | 19 | DECEMBER
T-697-2347 | PS5-62-OB-7669D | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone G | 6 | To be completed |  | 37 | NOVEMBER
T-919-2348 | PS5-26-UR-3410C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone G | 6 | To be completed |  | 46 | SEPTEMBER
T-768-2349 | PS5-06-OB-9028D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-04-25 | PS5-63-01 | PS5 - Milestone I | 8 | Closed | 31 | 28 | APRIL
T-896-2350 | PS5-80-UR-8880B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone B | 1.1 | In progress |  | 9 | NOVEMBER
T-017-2351 | PS5-71-UR-4483D | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-11-11 | PS5-07-04 | PS5 - Milestone I | 8 | Closed | 6 | 10 | NOVEMBER
T-762-2352 | PS5-22-IK-9285C | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone H | 7 | In progress |  | 6 | NOVEMBER
T-883-2353 | PS5-39-OB-9783A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone H | 7 | In progress |  | 35 | NOVEMBER
T-621-2354 | PS5-24-UR-8606C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | On hold |  | 9 | OCTOBER
T-254-2355 | PS5-61-OB-2169C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone G | 6 | In progress |  | 33 | DECEMBER
T-407-2356 | PS5-09-UR-6360A | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | In progress |  | 10 | NOVEMBER
T-139-2357 | PS5-36-IK-8174B | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-06-11 | PS5-09-04 | PS5 - Milestone F | 5 | Closed | 43 | 44 | JUNE
T-628-2358 | PS5-24-IK-7244C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone A | 1 | To be completed |  | 24 | DECEMBER
T-099-2359 | PS5-11-IK-1477A | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | To be completed |  | 39 | OCTOBER
T-677-2360 | PS5-24-OB-4076D | CQE04 - Transformer | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone A | 1 | In progress |  | 38 | NOVEMBER
T-545-2361 | PS5-18-UR-7912C | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone I | 8 | On hold |  | 4 | DECEMBER
T-341-2362 | PS5-12-OB-9905A | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-04-22 | PS5-63-01 | PS5 - Milestone C | 2 | Closed | 34 | 15 | APRIL
T-463-2363 | PS5-11-OB-1960D | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | In progress |  | 46 | DECEMBER
T-671-2364 | PS5-42-UR-5317A | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-12-18 | PS5-10-06 | PS5 - Milestone F | 5 | Closed | 26 | 46 | DECEMBER
T-206-2365 | PS5-01-UR-6423C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-03-21 | PS5-06-03 | PS5 - Milestone D | 3 | Closed | 16 | 19 | MARCH
T-844-2366 | PS5-84-OB-5319B | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone G | 6 | To be completed |  | 18 | NOVEMBER
T-432-2367 | PS5-49-OB-9645B | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-11-24 | PS5-03-02 | PS5 - Milestone B | 1.1 | Closed | 16 | 22 | NOVEMBER
T-206-2368 | PS5-26-OB-2368A | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-08-02 | PS5-08-02 | PS5 - Milestone F | 5 | Closed | 24 | 5 | AUGUST
T-572-2369 | PS5-97-IK-6797C | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone F | 5 | To be completed |  | 19 | AUGUST
T-454-2370 | PS5-31-UR-3103B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone F | 5 | To be completed |  | 12 | NOVEMBER
T-086-2371 | PS5-09-OB-4054C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone I | 8 | To be completed |  | 48 | AUGUST
T-998-2372 | PS5-87-OB-8236A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone G | 6 | In progress |  | 6 | NOVEMBER
T-225-2373 | PS5-17-OB-4979D | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone C | 2 | To be completed |  | 6 | AUGUST
T-701-2374 | PS5-01-IK-9252B | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-01-07 | PS5-01-07 | PS5 - Milestone E | 4 | Closed | 14 | 5 | JANUARY
T-526-2375 | PS5-56-OB-8129C | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | To be completed |  | 44 | OCTOBER
T-361-2376 | PS5-30-IK-7877A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | In progress |  | 19 | NOVEMBER
T-928-2377 | PS5-50-OB-5239C | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-06-05 | PS5-01-05 | PS5 - Milestone H | 7 | Closed | 41 | 10 | JUNE
T-257-2378 | PS5-09-IK-1475A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone A | 1 | On hold |  | 39 | DECEMBER
T-551-2379 | PS5-37-OB-9795C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone C | 2 | In progress |  | 36 | AUGUST
T-053-2380 | PS5-37-OB-7621B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone D | 3 | To be completed |  | 48 | SEPTEMBER
T-893-2381 | PS5-18-OB-9482B | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-05-18 | PS5-02-03 | PS5 - Milestone F | 5 | Closed | 27 | 6 | MAY
T-556-2382 | PS5-89-OB-7972C | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-03-24 | PS5-05-02 | PS5 - Milestone D | 3 | Closed | 44 | 28 | MARCH
T-424-2383 | PS5-16-IK-9045C | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone C | 2 | To be completed |  | 18 | SEPTEMBER
T-046-2384 | PS5-46-IK-5558B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone B | 1.1 | To be completed |  | 24 | NOVEMBER
T-317-2385 | PS5-01-OB-3570B | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-05-16 | PS5-60-10 | PS5 - Milestone A | 1 | Closed | 36 | 33 | MAY
T-151-2386 | PS5-46-OB-9354D | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | To be completed |  | 38 | DECEMBER
T-719-2387 | PS5-09-UR-5543D | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-07-22 | PS5-10-01 | PS5 - Milestone I | 8 | Closed | 13 | 42 | JULY
T-845-2388 | PS5-19-OB-7747B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone G | 6 | To be completed |  | 13 | AUGUST
T-232-2389 | PS5-58-OB-9673B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone H | 7 | In progress |  | 32 | OCTOBER
T-953-2390 | PS5-56-UR-4566B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone I | 8 | On hold |  | 33 | DECEMBER
T-115-2391 | PS5-30-OB-2075B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-12-07 | PS5-62-02 | PS5 - Milestone C | 2 | Closed | 43 | 18 | DECEMBER
T-496-2392 | PS5-40-IK-7695A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-01-23 | PS5-10-04 | PS5 - Milestone A | 1 | Closed | 9 | 45 | JANUARY
T-679-2393 | PS5-88-OB-5416A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-12-05 | PS5-04-03 | PS5 - Milestone E | 4 | Closed | 37 | 13 | DECEMBER
T-060-2394 | PS5-68-OB-3079D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone F | 5 | To be completed |  | 7 | DECEMBER
T-158-2395 | PS5-67-UR-6776D | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-12-18 | PS5-09-01 | PS5 - Milestone B | 1.1 | Closed | 12 | 32 | DECEMBER
T-301-2396 | PS5-19-UR-7482D | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone A | 1 | In progress |  | 45 | DECEMBER
T-784-2397 | PS5-89-OB-2724B | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone C | 2 | To be completed |  | 14 | AUGUST
T-177-2398 | PS5-05-IK-1264A | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-03-25 | PS5-10-05 | PS5 - Milestone G | 6 | Closed | 45 | 40 | MARCH
T-356-2399 | PS5-84-OB-2482B | CQM02 - Compressor | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone B | 1.1 | To be completed |  | 39 | AUGUST
T-787-2400 | PS5-96-OB-3621C | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-06-13 | PS5-09-03 | PS5 - Milestone G | 6 | Closed | 44 | 46 | JUNE
T-940-2401 | PS5-91-OB-4824B | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-09-16 | PS5-10-04 | PS5 - Milestone C | 2 | Closed | 11 | 18 | SEPTEMBER
T-320-2402 | PS5-62-UR-1320B | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-12-02 | PS5-03-23 | PS5 - Milestone B | 1.1 | Closed | 42 | 9 | DECEMBER
T-167-2403 | PS5-79-OB-7533B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone A | 1 | To be completed |  | 20 | NOVEMBER
T-988-2404 | PS5-02-OB-3515B | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-08-15 | PS5-01-01 | PS5 - Milestone D | 3 | Closed | 22 | 13 | AUGUST
T-307-2405 | PS5-38-OB-4989D | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone F | 5 | To be completed |  | 38 | AUGUST
T-213-2406 | PS5-32-OB-7280D | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-06-05 | PS5-10-05 | PS5 - Milestone I | 8 | Closed | 43 | 42 | JUNE
T-325-2407 | PS5-77-IK-1457B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-01-13 | PS5-10-01 | PS5 - Milestone D | 3 | Closed | 20 | 4 | JANUARY
T-572-2408 | PS5-19-OB-1932C | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone I | 8 | To be completed |  | 43 | NOVEMBER
T-590-2409 | PS5-66-IK-8583C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-02-22 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 45 | 18 | FEBRUARY
T-229-2410 | PS5-30-UR-3418C | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone G | 6 | To be completed |  | 44 | AUGUST
T-344-2411 | PS5-79-UR-6193A | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone D | 3 | To be completed |  | 38 | NOVEMBER
T-562-2412 | PS5-65-OB-3012A | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-08-16 | PS5-04-04 | PS5 - Milestone A | 1 | Closed | 44 | 20 | AUGUST
T-523-2413 | PS5-73-OB-6796B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone C | 2 | On hold |  | 41 | SEPTEMBER
T-539-2414 | PS5-10-IK-1917B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | In progress |  | 38 | OCTOBER
T-689-2415 | PS5-25-IK-9877B | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone F | 5 | To be completed |  | 22 | OCTOBER
T-402-2416 | PS5-04-OB-9547C | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone F | 5 | To be completed |  | 26 | DECEMBER
T-777-2417 | PS5-88-OB-1847B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone G | 6 | In progress |  | 24 | SEPTEMBER
T-244-2418 | PS5-92-UR-5578D | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-10-26 | PS5-09-02 | PS5 - Milestone A | 1 | Closed | 27 | 35 | OCTOBER
T-344-2419 | PS5-19-UR-9212A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone E | 4 | In progress |  | 31 | SEPTEMBER
T-081-2420 | PS5-26-UR-6770D | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone I | 8 | To be completed |  | 45 | NOVEMBER
T-904-2421 | PS5-44-IK-9262C | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-05-25 | PS5-10-01 | PS5 - Milestone B | 1.1 | Closed | 24 | 32 | MAY
T-141-2422 | PS5-85-OB-3579D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone H | 7 | To be completed |  | 41 | DECEMBER
T-619-2423 | PS5-16-OB-3648D | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | To be completed |  | 19 | DECEMBER
T-101-2424 | PS5-45-UR-8728D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-08-07 | PS5-99-01 | PS5 - Milestone I | 8 | Closed | 33 | 22 | AUGUST
T-872-2425 | PS5-37-IK-1822C | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | To be completed |  | 14 | OCTOBER
T-186-2426 | PS5-21-OB-4793B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-08-07 | PS5-10-06 | PS5 - Milestone I | 8 | Closed | 44 | 26 | AUGUST
T-559-2427 | PS5-94-IK-1996D | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone F | 5 | To be completed |  | 6 | AUGUST
T-136-2428 | PS5-91-OB-5733B | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-06-17 | PS5-06-03 | PS5 - Milestone H | 7 | Closed | 10 | 40 | JUNE
T-084-2429 | PS5-77-OB-8170B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-02-12 | PS5-05-03 | PS5 - Milestone C | 2 | Closed | 32 | 40 | FEBRUARY
T-333-2430 | PS5-06-OB-8399D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-01-28 | PS5-01-03 | PS5 - Milestone E | 4 | Closed | 8 | 33 | JANUARY
T-021-2431 | PS5-60-OB-7872B | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-07-01 | PS5-01-05 | PS5 - Milestone C | 2 | Closed | 35 | 43 | JULY
T-752-2432 | PS5-42-UR-3281D | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone C | 2 | To be completed |  | 42 | AUGUST
T-625-2433 | PS5-53-OB-4525B | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone B | 1.1 | On hold |  | 5 | OCTOBER
T-250-2434 | PS5-73-UR-2897D | CQM03 - Heat Exchanger | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone I | 8 | To be completed |  | 28 | SEPTEMBER
T-690-2435 | PS5-41-UR-9104C | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone F | 5 | To be completed |  | 44 | NOVEMBER
T-154-2436 | PS5-07-OB-9960A | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone H | 7 | In progress |  | 24 | SEPTEMBER
T-954-2437 | PS5-41-UR-4660A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-05-19 | PS5-10-01 | PS5 - Milestone F | 5 | Closed | 6 | 17 | MAY
T-815-2438 | PS5-41-OB-4968A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone B | 1.1 | In progress |  | 44 | AUGUST
T-019-2439 | PS5-61-OB-4583B | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-05-21 | PS5-05-03 | PS5 - Milestone E | 4 | Closed | 8 | 26 | MAY
T-905-2440 | PS5-46-OB-6820D | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-02-13 | PS5-11-01 | PS5 - Milestone C | 2 | Closed | 23 | 11 | FEBRUARY
T-626-2441 | PS5-19-IK-1918C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-07-11 | PS5-09-01 | PS5 - Milestone F | 5 | Closed | 28 | 31 | JULY
T-630-2442 | PS5-99-OB-1219B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-01-28 | PS5-02-01 | PS5 - Milestone B | 1.1 | Closed | 13 | 6 | JANUARY
T-203-2443 | PS5-48-UR-5204C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone F | 5 | In progress |  | 26 | OCTOBER
T-640-2444 | PS5-69-OB-9046D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone G | 6 | In progress |  | 47 | OCTOBER
T-165-2445 | PS5-15-UR-1020D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone C | 2 | On hold |  | 34 | NOVEMBER
T-782-2446 | PS5-80-OB-5721A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone A | 1 | To be completed |  | 20 | SEPTEMBER
T-709-2447 | PS5-66-IK-7725B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone D | 3 | In progress |  | 19 | SEPTEMBER
T-202-2448 | PS5-49-OB-6828C | CQP05 - Insulation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | To be completed |  | 7 | SEPTEMBER
T-517-2449 | PS5-55-IK-9715A | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone B | 1.1 | In progress |  | 5 | NOVEMBER
T-410-2450 | PS5-28-IK-1125C | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone B | 1.1 | To be completed |  | 35 | DECEMBER
T-626-2451 | PS5-75-OB-9969D | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-10-17 | PS5-13-01 | PS5 - Milestone B | 1.1 | Closed | 44 | 4 | OCTOBER
T-477-2452 | PS5-83-OB-8480C | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-10-27 | PS5-02-02 | PS5 - Milestone H | 7 | Closed | 37 | 25 | OCTOBER
T-113-2453 | PS5-45-OB-6897B | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone G | 6 | To be completed |  | 34 | OCTOBER
T-633-2454 | PS5-88-IK-6763C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone E | 4 | To be completed |  | 24 | DECEMBER
T-205-2455 | PS5-14-OB-5336B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | In progress |  | 13 | AUGUST
T-651-2456 | PS5-23-OB-4896C | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone A | 1 | In progress |  | 24 | OCTOBER
T-463-2457 | PS5-05-OB-6714A | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone E | 4 | To be completed |  | 47 | NOVEMBER
T-358-2458 | PS5-90-OB-2426D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone C | 2 | In progress |  | 34 | OCTOBER
T-641-2459 | PS5-62-IK-9043A | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone C | 2 | To be completed |  | 5 | AUGUST
T-656-2460 | PS5-57-IK-9528D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | To be completed |  | 39 | OCTOBER
T-169-2461 | PS5-66-IK-7393C | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-03-19 | PS5-06-02 | PS5 - Milestone B | 1.1 | Closed | 13 | 29 | MARCH
T-676-2462 | PS5-79-OB-1869A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-10-05 | PS5-99-01 | PS5 - Milestone F | 5 | Closed | 29 | 11 | OCTOBER
T-299-2463 | PS5-92-OB-9915C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone I | 8 | To be completed |  | 34 | NOVEMBER
T-050-2464 | PS5-64-UR-8914D | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone E | 4 | To be completed |  | 9 | NOVEMBER
T-117-2465 | PS5-75-OB-9122B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone B | 1.1 | To be completed |  | 20 | AUGUST
T-275-2466 | PS5-86-UR-5700B | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | In progress |  | 43 | DECEMBER
T-908-2467 | PS5-23-OB-7808B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-06-04 | PS5-10-02 | PS5 - Milestone F | 5 | Closed | 19 | 10 | JUNE
T-093-2468 | PS5-11-UR-7223D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-12-15 | PS5-13-01 | PS5 - Milestone C | 2 | Closed | 39 | 30 | DECEMBER
T-067-2469 | PS5-01-IK-7017C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone G | 6 | To be completed |  | 39 | NOVEMBER
T-014-2470 | PS5-03-IK-3223B | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone D | 3 | To be completed |  | 29 | SEPTEMBER
T-645-2471 | PS5-33-OB-9988B | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-02-17 | PS5-82-02 | PS5 - Milestone C | 2 | Closed | 36 | 33 | FEBRUARY
T-789-2472 | PS5-94-OB-3056B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone G | 6 | In progress |  | 16 | AUGUST
T-631-2473 | PS5-89-OB-5647D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone A | 1 | In progress |  | 4 | NOVEMBER
T-824-2474 | PS5-72-UR-9455B | CQH02 - AHU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone D | 3 | To be completed |  | 22 | OCTOBER
T-816-2475 | PS5-86-IK-8740C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | In progress |  | 11 | AUGUST
T-207-2476 | PS5-32-IK-8812A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-09-09 | PS5-10-02 | PS5 - Milestone C | 2 | Closed | 39 | 27 | SEPTEMBER
T-998-2477 | PS5-19-OB-8419A | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-01-17 | PS5-99-03 | PS5 - Milestone E | 4 | Closed | 12 | 35 | JANUARY
T-980-2478 | PS5-61-UR-8078A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone E | 4 | On hold |  | 37 | OCTOBER
T-667-2479 | PS5-05-OB-2816C | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone F | 5 | To be completed |  | 14 | AUGUST
T-911-2480 | PS5-40-OB-5031A | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone I | 8 | To be completed |  | 34 | AUGUST
T-639-2481 | PS5-83-OB-6401D | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone H | 7 | On hold |  | 33 | NOVEMBER
T-420-2482 | PS5-33-OB-4012C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | To be completed |  | 40 | OCTOBER
T-130-2483 | PS5-24-IK-9799D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone E | 4 | To be completed |  | 4 | DECEMBER
T-927-2484 | PS5-36-OB-1784A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-12-01 | PS5-99-02 | PS5 - Milestone G | 6 | Closed | 33 | 20 | DECEMBER
T-816-2485 | PS5-44-UR-5044B | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone G | 6 | In progress |  | 28 | OCTOBER
T-284-2486 | PS5-50-IK-4299A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | To be completed |  | 46 | AUGUST
T-967-2487 | PS5-85-OB-3504C | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-05-05 | PS5-11-02 | PS5 - Milestone G | 6 | Closed | 19 | 44 | MAY
T-236-2488 | PS5-77-OB-7271C | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone D | 3 | In progress |  | 43 | DECEMBER
T-985-2489 | PS5-28-IK-9576A | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone I | 8 | To be completed |  | 13 | NOVEMBER
T-186-2490 | PS5-40-OB-1849C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-05-17 | PS5-11-02 | PS5 - Milestone B | 1.1 | Closed | 42 | 36 | MAY
T-821-2491 | PS5-81-OB-1871A | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone I | 8 | In progress |  | 40 | NOVEMBER
T-469-2492 | PS5-45-OB-2853A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone F | 5 | In progress |  | 31 | SEPTEMBER
T-006-2493 | PS5-13-OB-4643C | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone G | 6 | To be completed |  | 24 | AUGUST
T-298-2494 | PS5-01-IK-4999B | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone D | 3 | To be completed |  | 22 | OCTOBER
T-043-2495 | PS5-48-OB-4309A | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone F | 5 | In progress |  | 15 | AUGUST
T-841-2496 | PS5-16-OB-8966A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone D | 3 | In progress |  | 42 | DECEMBER
T-227-2497 | PS5-45-UR-2615B | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | In progress |  | 17 | OCTOBER
T-567-2498 | PS5-45-IK-2168A | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | On hold |  | 48 | DECEMBER
T-471-2499 | PS5-66-OB-8721C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone H | 7 | On hold |  | 43 | DECEMBER
T-055-2500 | PS5-27-IK-3677A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone D | 3 | In progress |  | 10 | NOVEMBER
T-078-2501 | PS5-28-OB-4258C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-09-28 | PS5-09-02 | PS5 - Milestone G | 6 | Closed | 22 | 40 | SEPTEMBER
T-104-2502 | PS5-60-OB-4054D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-08-24 | PS5-07-02 | PS5 - Milestone F | 5 | Closed | 25 | 48 | AUGUST
T-029-2503 | PS5-30-OB-7557A | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone D | 3 | On hold |  | 39 | OCTOBER
T-626-2504 | PS5-74-OB-3778A | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone A | 1 | To be completed |  | 20 | AUGUST
T-351-2505 | PS5-03-IK-9101C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-11-14 | PS5-01-09 | PS5 - Milestone I | 8 | Closed | 28 | 37 | NOVEMBER
T-268-2506 | PS5-75-UR-3198D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | To be completed |  | 13 | SEPTEMBER
T-173-2507 | PS5-94-IK-8285A | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-05-23 | PS5-07-01 | PS5 - Milestone F | 5 | Closed | 18 | 40 | MAY
T-694-2508 | PS5-33-OB-4829B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone F | 5 | In progress |  | 6 | AUGUST
T-506-2509 | PS5-19-OB-9179D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone F | 5 | To be completed |  | 18 | NOVEMBER
T-114-2510 | PS5-34-UR-1072A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-12-11 | PS5-03-03 | PS5 - Milestone C | 2 | Closed | 27 | 43 | DECEMBER
T-986-2511 | PS5-87-UR-6068A | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone I | 8 | To be completed |  | 23 | AUGUST
T-057-2512 | PS5-96-IK-5436A | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone G | 6 | To be completed |  | 30 | NOVEMBER
T-054-2513 | PS5-02-UR-9613C | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | To be completed |  | 21 | NOVEMBER
T-895-2514 | PS5-70-OB-4215C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone E | 4 | In progress |  | 47 | OCTOBER
T-614-2515 | PS5-07-UR-8081D | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone A | 1 | To be completed |  | 42 | NOVEMBER
T-714-2516 | PS5-65-OB-8973C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone E | 4 | On hold |  | 41 | NOVEMBER
T-745-2517 | PS5-11-IK-3075D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-06-16 | PS5-10-02 | PS5 - Milestone I | 8 | Closed | 6 | 27 | JUNE
T-317-2518 | PS5-40-OB-6894A | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone I | 8 | In progress |  | 27 | AUGUST
T-824-2519 | PS5-01-UR-3753D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-09-27 | PS5-08-01 | PS5 - Milestone H | 7 | Closed | 45 | 7 | SEPTEMBER
T-615-2520 | PS5-91-OB-7034C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-03-22 | PS5-60-04 | PS5 - Milestone B | 1.1 | Closed | 18 | 14 | MARCH
T-150-2521 | PS5-51-UR-3737A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-01-03 | PS5-04-03 | PS5 - Milestone C | 2 | Closed | 40 | 44 | JANUARY
T-083-2522 | PS5-91-IK-6436B | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone E | 4 | To be completed |  | 13 | DECEMBER
T-084-2523 | PS5-35-OB-8713A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone H | 7 | To be completed |  | 7 | DECEMBER
T-934-2524 | PS5-25-OB-8159C | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | To be completed |  | 34 | SEPTEMBER
T-088-2525 | PS5-48-OB-3330A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-06-28 | PS5-08-01 | PS5 - Milestone E | 4 | Closed | 20 | 25 | JUNE
T-568-2526 | PS5-84-OB-9989B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone E | 4 | In progress |  | 44 | SEPTEMBER
T-614-2527 | PS5-58-UR-1181D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | On hold |  | 48 | OCTOBER
T-871-2528 | PS5-47-OB-5043C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-03-01 | PS5-61-01 | PS5 - Milestone A | 1 | Closed | 7 | 32 | MARCH
T-219-2529 | PS5-86-UR-5092B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone G | 6 | On hold |  | 16 | AUGUST
T-724-2530 | PS5-40-OB-3821A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-07-02 | PS5-09-02 | PS5 - Milestone F | 5 | Closed | 36 | 14 | JULY
T-588-2531 | PS5-55-OB-7224C | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | To be completed |  | 41 | SEPTEMBER
T-425-2532 | PS5-97-IK-4277C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone A | 1 | On hold |  | 46 | NOVEMBER
T-236-2533 | PS5-84-IK-4892B | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-01-23 | PS5-01-09 | PS5 - Milestone F | 5 | Closed | 44 | 42 | JANUARY
T-859-2534 | PS5-68-OB-3001D | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone B | 1.1 | On hold |  | 46 | AUGUST
T-208-2535 | PS5-99-OB-9338A | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone C | 2 | In progress |  | 30 | OCTOBER
T-635-2536 | PS5-35-IK-3325C | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone A | 1 | In progress |  | 38 | OCTOBER
T-666-2537 | PS5-69-UR-8191A | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | In progress |  | 15 | NOVEMBER
T-414-2538 | PS5-30-OB-7724B | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-07-01 | PS5-08-01 | PS5 - Milestone G | 6 | Closed | 15 | 21 | JULY
T-208-2539 | PS5-64-OB-8869D | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | In progress |  | 28 | NOVEMBER
T-741-2540 | PS5-39-OB-9702B | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-03-02 | PS5-01-03 | PS5 - Milestone E | 4 | Closed | 41 | 47 | MARCH
T-252-2541 | PS5-85-IK-5119D | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-07-20 | PS5-08-02 | PS5 - Milestone A | 1 | Closed | 34 | 4 | JULY
T-889-2542 | PS5-29-UR-3962B | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone I | 8 | On hold |  | 37 | SEPTEMBER
T-870-2543 | PS5-97-UR-6248C | CQM02 - Compressor | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-05-03 | PS5-01-03 | PS5 - Milestone H | 7 | Closed | 35 | 21 | MAY
T-880-2544 | PS5-03-UR-3953D | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone C | 2 | To be completed |  | 30 | SEPTEMBER
T-631-2545 | PS5-75-OB-7611C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | To be completed |  | 37 | OCTOBER
T-963-2546 | PS5-49-UR-6177A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-10-15 | PS5-10-06 | PS5 - Milestone I | 8 | Closed | 10 | 39 | OCTOBER
T-586-2547 | PS5-41-UR-4166D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone H | 7 | In progress |  | 47 | DECEMBER
T-167-2548 | PS5-42-IK-9175C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone F | 5 | In progress |  | 15 | OCTOBER
T-530-2549 | PS5-77-UR-7525C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone G | 6 | To be completed |  | 24 | NOVEMBER
T-407-2550 | PS5-29-OB-1196D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-09-23 | PS5-04-03 | PS5 - Milestone H | 7 | Closed | 24 | 25 | SEPTEMBER
T-431-2551 | PS5-10-IK-6161A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone G | 6 | To be completed |  | 18 | OCTOBER
T-355-2552 | PS5-05-IK-6045C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone F | 5 | To be completed |  | 10 | AUGUST
T-651-2553 | PS5-94-OB-4710D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-11-24 | PS5-10-04 | PS5 - Milestone F | 5 | Closed | 41 | 35 | NOVEMBER
T-508-2554 | PS5-54-UR-6181D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-14 | PS5-60-10 | PS5 - Milestone D | 3 | Closed | 26 | 41 | JUNE
T-441-2555 | PS5-67-IK-8149B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | In progress |  | 31 | NOVEMBER
T-358-2556 | PS5-47-OB-5868C | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-07-08 | PS5-05-03 | PS5 - Milestone A | 1 | Closed | 47 | 42 | JULY
T-186-2557 | PS5-18-UR-7517A | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-06 | PS5-60-04 | PS5 - Milestone G | 6 | Closed | 45 | 9 | JULY
T-991-2558 | PS5-13-UR-2274D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-11-15 | PS5-06-03 | PS5 - Milestone H | 7 | Closed | 37 | 28 | NOVEMBER
T-309-2559 | PS5-82-OB-8274C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | On hold |  | 19 | NOVEMBER
T-665-2560 | PS5-70-IK-1802B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone B | 1.1 | To be completed |  | 48 | OCTOBER
T-490-2561 | PS5-41-OB-3032D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone G | 6 | In progress |  | 4 | OCTOBER
T-750-2562 | PS5-96-UR-8682C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone H | 7 | To be completed |  | 29 | AUGUST
T-323-2563 | PS5-37-OB-2337B | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-04-25 | PS5-62-01 | PS5 - Milestone E | 4 | Closed | 20 | 10 | APRIL
T-017-2564 | PS5-03-OB-5173B | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-02-23 | PS5-61-07 | PS5 - Milestone H | 7 | Closed | 38 | 18 | FEBRUARY
T-255-2565 | PS5-92-IK-7001A | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone A | 1 | In progress |  | 48 | NOVEMBER
T-553-2566 | PS5-16-UR-4290D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone E | 4 | In progress |  | 22 | SEPTEMBER
T-112-2567 | PS5-23-OB-1291A | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-12-12 | PS5-01-08 | PS5 - Milestone B | 1.1 | Closed | 31 | 44 | DECEMBER
T-157-2568 | PS5-38-OB-9225A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone F | 5 | In progress |  | 5 | SEPTEMBER
T-025-2569 | PS5-41-UR-9819B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-06-26 | PS5-04-03 | PS5 - Milestone F | 5 | Closed | 18 | 4 | JUNE
T-422-2570 | PS5-59-UR-4106C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | In progress |  | 22 | AUGUST
T-998-2571 | PS5-26-IK-2093B | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-02-27 | PS5-03-02 | PS5 - Milestone I | 8 | Closed | 22 | 33 | FEBRUARY
T-004-2572 | PS5-55-UR-5649D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-05-25 | PS5-13-01 | PS5 - Milestone I | 8 | Closed | 35 | 17 | MAY
T-208-2573 | PS5-18-OB-5970C | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-07-26 | PS5-01-03 | PS5 - Milestone C | 2 | Closed | 14 | 47 | JULY
T-629-2574 | PS5-12-OB-2787A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone F | 5 | To be completed |  | 41 | AUGUST
T-315-2575 | PS5-01-UR-1596B | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-12-08 | PS5-01-02 | PS5 - Milestone B | 1.1 | Closed | 46 | 34 | DECEMBER
T-971-2576 | PS5-98-UR-1710A | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone C | 2 | In progress |  | 29 | OCTOBER
T-319-2577 | PS5-83-UR-2708B | CQM01 - Pump Installation | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone H | 7 | To be completed |  | 14 | NOVEMBER
T-142-2578 | PS5-51-OB-3835A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone C | 2 | To be completed |  | 8 | DECEMBER
T-559-2579 | PS5-20-UR-6854B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone G | 6 | To be completed |  | 8 | SEPTEMBER
T-207-2580 | PS5-37-OB-2617D | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-09-17 | PS5-10-02 | PS5 - Milestone E | 4 | Closed | 45 | 37 | SEPTEMBER
T-043-2581 | PS5-51-IK-1439A | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone H | 7 | To be completed |  | 29 | DECEMBER
T-317-2582 | PS5-32-IK-2406A | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone E | 4 | In progress |  | 18 | SEPTEMBER
T-557-2583 | PS5-48-IK-2403C | CQM04 - Vessel | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-12-18 | PS5-99-01 | PS5 - Milestone C | 2 | Closed | 41 | 47 | DECEMBER
T-505-2584 | PS5-68-OB-3441B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone H | 7 | On hold |  | 9 | AUGUST
T-038-2585 | PS5-94-OB-9172C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone F | 5 | To be completed |  | 10 | OCTOBER
T-137-2586 | PS5-51-UR-8918D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | In progress |  | 22 | NOVEMBER
T-580-2587 | PS5-71-UR-9901C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone C | 2 | To be completed |  | 24 | NOVEMBER
T-607-2588 | PS5-76-UR-6923B | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-10-15 | PS5-01-02 | PS5 - Milestone B | 1.1 | Closed | 33 | 8 | OCTOBER
T-209-2589 | PS5-89-OB-2743D | CQM04 - Vessel | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | To be completed |  | 28 | OCTOBER
T-972-2590 | PS5-80-IK-7566C | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-07-03 | PS5-01-01 | PS5 - Milestone C | 2 | Closed | 18 | 41 | JULY
T-790-2591 | PS5-74-UR-2812C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone I | 8 | To be completed |  | 12 | OCTOBER
T-964-2592 | PS5-26-OB-8270C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone G | 6 | On hold |  | 42 | AUGUST
T-139-2593 | PS5-34-OB-9064D | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | To be completed |  | 15 | NOVEMBER
T-288-2594 | PS5-86-UR-2533D | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone D | 3 | To be completed |  | 14 | OCTOBER
T-904-2595 | PS5-60-OB-6244D | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-10-04 | PS5-06-01 | PS5 - Milestone I | 8 | Closed | 19 | 17 | OCTOBER
T-936-2596 | PS5-90-IK-5784C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-11-26 | PS5-02-03 | PS5 - Milestone C | 2 | Closed | 15 | 15 | NOVEMBER
T-765-2597 | PS5-70-OB-7640C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-12-01 | PS5-82-01 | PS5 - Milestone I | 8 | Closed | 19 | 17 | DECEMBER
T-327-2598 | PS5-28-IK-4479B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-08-07 | PS5-08-02 | PS5 - Milestone F | 5 | Closed | 41 | 22 | AUGUST
T-329-2599 | PS5-53-UR-9006C | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-07-04 | PS5-11-03 | PS5 - Milestone E | 4 | Closed | 37 | 35 | JULY
T-609-2600 | PS5-54-OB-3864D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-01-13 | PS5-10-06 | PS5 - Milestone B | 1.1 | Closed | 40 | 14 | JANUARY
T-419-2601 | PS5-37-UR-4301B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone D | 3 | To be completed |  | 24 | NOVEMBER
T-858-2602 | PS5-27-IK-1327A | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone A | 1 | In progress |  | 40 | SEPTEMBER
T-705-2603 | PS5-65-UR-3278A | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-10-08 | PS5-01-07 | PS5 - Milestone B | 1.1 | Closed | 9 | 27 | OCTOBER
T-400-2604 | PS5-53-IK-4711B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-12-20 | PS5-03-02 | PS5 - Milestone A | 1 | Closed | 21 | 7 | DECEMBER
T-498-2605 | PS5-95-IK-5294B | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone E | 4 | To be completed |  | 34 | AUGUST
T-914-2606 | PS5-30-OB-7198A | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone C | 2 | To be completed |  | 40 | DECEMBER
T-951-2607 | PS5-80-IK-1856D | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-01-24 | PS5-02-02 | PS5 - Milestone G | 6 | Closed | 25 | 23 | JANUARY
T-399-2608 | PS5-60-IK-9406D | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone H | 7 | On hold |  | 8 | AUGUST
T-893-2609 | PS5-15-UR-8613B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-04-11 | PS5-08-02 | PS5 - Milestone C | 2 | Closed | 45 | 10 | APRIL
T-344-2610 | PS5-89-UR-3396D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-01-11 | PS5-04-03 | PS5 - Milestone G | 6 | Closed | 40 | 33 | JANUARY
T-794-2611 | PS5-68-OB-7447A | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone F | 5 | To be completed |  | 32 | OCTOBER
T-036-2612 | PS5-23-UR-7874B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-01-05 | PS5-02-03 | PS5 - Milestone D | 3 | Closed | 6 | 46 | JANUARY
T-191-2613 | PS5-03-OB-6825A | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone A | 1 | In progress |  | 35 | OCTOBER
T-854-2614 | PS5-89-OB-1870C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone A | 1 | In progress |  | 32 | NOVEMBER
T-767-2615 | PS5-01-IK-3701D | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone I | 8 | In progress |  | 30 | DECEMBER
T-166-2616 | PS5-99-OB-8710A | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone H | 7 | In progress |  | 23 | OCTOBER
T-701-2617 | PS5-77-UR-6360D | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-05-06 | PS5-82-01 | PS5 - Milestone I | 8 | Closed | 32 | 48 | MAY
T-177-2618 | PS5-52-OB-8582D | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | In progress |  | 40 | NOVEMBER
T-444-2619 | PS5-47-UR-2067B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-06-28 | PS5-12-02 | PS5 - Milestone H | 7 | Closed | 42 | 42 | JUNE
T-337-2620 | PS5-86-OB-7038B | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-02-28 | PS5-07-04 | PS5 - Milestone C | 2 | Closed | 18 | 46 | FEBRUARY
T-641-2621 | PS5-60-IK-7739B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-05-06 | PS5-61-07 | PS5 - Milestone H | 7 | Closed | 34 | 10 | MAY
T-983-2622 | PS5-32-UR-5482D | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-10-15 | PS5-12-02 | PS5 - Milestone C | 2 | Closed | 46 | 41 | OCTOBER
T-201-2623 | PS5-02-OB-9508B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone A | 1 | In progress |  | 18 | AUGUST
T-844-2624 | PS5-04-IK-7447C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-09-17 | PS5-60-10 | PS5 - Milestone B | 1.1 | Closed | 38 | 20 | SEPTEMBER
T-786-2625 | PS5-12-IK-2085A | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone H | 7 | In progress |  | 28 | SEPTEMBER
T-856-2626 | PS5-83-OB-9188A | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-08-20 | PS5-62-01 | PS5 - Milestone A | 1 | Closed | 35 | 23 | AUGUST
T-965-2627 | PS5-01-OB-4032A | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-01-02 | PS5-01-01 | PS5 - Milestone F | 5 | Closed | 43 | 42 | JANUARY
T-254-2628 | PS5-20-OB-7777A | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | In progress |  | 29 | DECEMBER
T-870-2629 | PS5-77-UR-3060A | CQM03 - Heat Exchanger | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-10-22 | PS5-11-02 | PS5 - Milestone A | 1 | Closed | 18 | 43 | OCTOBER
T-224-2630 | PS5-20-IK-7883D | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-11-28 | PS5-04-01 | PS5 - Milestone A | 1 | Closed | 36 | 16 | NOVEMBER
T-158-2631 | PS5-15-IK-6334C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | In progress |  | 47 | OCTOBER
T-387-2632 | PS5-71-UR-7545C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-07-24 | PS5-82-07 | PS5 - Milestone B | 1.1 | Closed | 20 | 46 | JULY
T-693-2633 | PS5-03-OB-8948D | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone F | 5 | On hold |  | 33 | NOVEMBER
T-531-2634 | PS5-27-IK-6395B | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-12-03 | PS5-02-03 | PS5 - Milestone B | 1.1 | Closed | 5 | 10 | DECEMBER
T-245-2635 | PS5-58-OB-5925A | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone F | 5 | To be completed |  | 28 | SEPTEMBER
T-146-2636 | PS5-15-IK-6023D | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | To be completed |  | 45 | DECEMBER
T-557-2637 | PS5-65-UR-4168C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone A | 1 | To be completed |  | 25 | SEPTEMBER
T-609-2638 | PS5-29-IK-5826B | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | To be completed |  | 35 | DECEMBER
T-581-2639 | PS5-16-OB-1547D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone F | 5 | To be completed |  | 40 | SEPTEMBER
T-165-2640 | PS5-57-IK-9510D | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone E | 4 | On hold |  | 6 | NOVEMBER
T-211-2641 | PS5-81-OB-4551B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone A | 1 | To be completed |  | 14 | OCTOBER
T-843-2642 | PS5-82-IK-7101B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone D | 3 | To be completed |  | 33 | DECEMBER
T-344-2643 | PS5-23-IK-8578D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone I | 8 | To be completed |  | 32 | OCTOBER
T-335-2644 | PS5-13-OB-3830C | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-01-08 | PS5-01-03 | PS5 - Milestone A | 1 | Closed | 21 | 43 | JANUARY
T-663-2645 | PS5-46-UR-9258A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | In progress |  | 44 | SEPTEMBER
T-119-2646 | PS5-63-UR-9869A | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone C | 2 | To be completed |  | 42 | SEPTEMBER
T-092-2647 | PS5-58-UR-4239D | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-05-18 | PS5-61-07 | PS5 - Milestone I | 8 | Closed | 30 | 15 | MAY
T-587-2648 | PS5-28-UR-9235D | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-04-11 | PS5-01-04 | PS5 - Milestone H | 7 | Closed | 20 | 48 | APRIL
T-364-2649 | PS5-06-UR-5671B | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | On hold |  | 32 | SEPTEMBER
T-072-2650 | PS5-61-IK-2370B | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone A | 1 | To be completed |  | 37 | OCTOBER
T-620-2651 | PS5-75-UR-4413A | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone I | 8 | To be completed |  | 47 | SEPTEMBER
T-835-2652 | PS5-69-OB-8033A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone E | 4 | To be completed |  | 48 | NOVEMBER
T-963-2653 | PS5-83-IK-3555C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-01-16 | PS5-10-02 | PS5 - Milestone E | 4 | Closed | 9 | 15 | JANUARY
T-901-2654 | PS5-13-UR-7178D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-06-09 | PS5-03-03 | PS5 - Milestone B | 1.1 | Closed | 32 | 21 | JUNE
T-675-2655 | PS5-09-IK-4803B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone G | 6 | In progress |  | 36 | AUGUST
T-710-2656 | PS5-48-OB-5852B | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone A | 1 | In progress |  | 27 | OCTOBER
T-725-2657 | PS5-20-OB-1046A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone C | 2 | In progress |  | 48 | DECEMBER
T-169-2658 | PS5-05-OB-9514C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-11-27 | PS5-01-04 | PS5 - Milestone F | 5 | Closed | 9 | 9 | NOVEMBER
T-376-2659 | PS5-90-OB-6803D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone G | 6 | On hold |  | 43 | NOVEMBER
T-126-2660 | PS5-86-IK-2667A | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | To be completed |  | 41 | SEPTEMBER
T-179-2661 | PS5-94-OB-3102D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone G | 6 | In progress |  | 31 | OCTOBER
T-029-2662 | PS5-94-IK-9923B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | To be completed |  | 42 | SEPTEMBER
T-398-2663 | PS5-75-OB-5527C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-01-04 | PS5-07-03 | PS5 - Milestone I | 8 | Closed | 25 | 43 | JANUARY
T-283-2664 | PS5-25-OB-2143A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone B | 1.1 | In progress |  | 24 | AUGUST
T-128-2665 | PS5-62-OB-8236A | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-08-08 | PS5-06-02 | PS5 - Milestone B | 1.1 | Closed | 28 | 22 | AUGUST
T-629-2666 | PS5-97-OB-3281C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone G | 6 | In progress |  | 5 | OCTOBER
T-688-2667 | PS5-41-OB-2734B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-02-13 | PS5-99-02 | PS5 - Milestone C | 2 | Closed | 47 | 6 | FEBRUARY
T-072-2668 | PS5-95-OB-6899D | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone A | 1 | In progress |  | 15 | OCTOBER
T-329-2669 | PS5-23-OB-1179B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone F | 5 | On hold |  | 40 | NOVEMBER
T-924-2670 | PS5-52-IK-2324B | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone I | 8 | To be completed |  | 5 | NOVEMBER
T-273-2671 | PS5-17-IK-9280C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone D | 3 | To be completed |  | 42 | OCTOBER
T-267-2672 | PS5-15-OB-9316D | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-08-07 | PS5-10-06 | PS5 - Milestone E | 4 | Closed | 48 | 21 | AUGUST
T-399-2673 | PS5-03-OB-9064A | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-05-17 | PS5-09-03 | PS5 - Milestone B | 1.1 | Closed | 35 | 29 | MAY
T-692-2674 | PS5-74-UR-8680A | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone A | 1 | On hold |  | 13 | SEPTEMBER
T-364-2675 | PS5-63-OB-6897B | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-11-16 | PS5-10-05 | PS5 - Milestone H | 7 | Closed | 11 | 34 | NOVEMBER
T-122-2676 | PS5-68-IK-4928C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-11-20 | PS5-08-01 | PS5 - Milestone G | 6 | Closed | 14 | 14 | NOVEMBER
T-055-2677 | PS5-89-UR-1461C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone G | 6 | To be completed |  | 20 | AUGUST
T-467-2678 | PS5-41-UR-4144D | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone I | 8 | In progress |  | 38 | OCTOBER
T-942-2679 | PS5-13-OB-4027A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | In progress |  | 22 | SEPTEMBER
T-100-2680 | PS5-09-UR-5093B | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-01-28 | PS5-07-04 | PS5 - Milestone B | 1.1 | Closed | 39 | 47 | JANUARY
T-166-2681 | PS5-83-OB-4931D | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | In progress |  | 46 | NOVEMBER
T-447-2682 | PS5-50-UR-1337C | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-11-22 | PS5-61-02 | PS5 - Milestone I | 8 | Closed | 22 | 8 | NOVEMBER
T-702-2683 | PS5-69-UR-3135C | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone B | 1.1 | In progress |  | 21 | SEPTEMBER
T-986-2684 | PS5-66-UR-5559A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-10-22 | PS5-07-03 | PS5 - Milestone A | 1 | Closed | 17 | 45 | OCTOBER
T-729-2685 | PS5-62-UR-5533C | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone G | 6 | To be completed |  | 15 | DECEMBER
T-477-2686 | PS5-37-OB-3171A | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-10-01 | PS5-01-07 | PS5 - Milestone I | 8 | Closed | 38 | 30 | OCTOBER
T-257-2687 | PS5-46-UR-2011D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone G | 6 | To be completed |  | 40 | AUGUST
T-454-2688 | PS5-97-UR-4978C | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone G | 6 | In progress |  | 47 | AUGUST
T-249-2689 | PS5-46-OB-5362B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone G | 6 | In progress |  | 7 | NOVEMBER
T-255-2690 | PS5-05-OB-6926D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-06-02 | PS5-10-06 | PS5 - Milestone C | 2 | Closed | 30 | 42 | JUNE
T-711-2691 | PS5-63-OB-4860C | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-10-20 | PS5-61-02 | PS5 - Milestone D | 3 | Closed | 19 | 42 | OCTOBER
T-735-2692 | PS5-86-OB-2010B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | In progress |  | 34 | AUGUST
T-668-2693 | PS5-12-OB-6403D | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-07-13 | PS5-02-02 | PS5 - Milestone I | 8 | Closed | 35 | 47 | JULY
T-651-2694 | PS5-60-OB-8509D | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-01-21 | PS5-09-02 | PS5 - Milestone C | 2 | Closed | 32 | 25 | JANUARY
T-957-2695 | PS5-69-UR-7147A | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-05-27 | PS5-10-04 | PS5 - Milestone I | 8 | Closed | 42 | 4 | MAY
T-174-2696 | PS5-97-IK-5093A | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone A | 1 | In progress |  | 11 | DECEMBER
T-155-2697 | PS5-68-UR-8513A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone C | 2 | To be completed |  | 43 | AUGUST
T-159-2698 | PS5-27-UR-9893C | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone G | 6 | To be completed |  | 13 | SEPTEMBER
T-417-2699 | PS5-06-OB-7569B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-05-04 | PS5-01-02 | PS5 - Milestone A | 1 | Closed | 47 | 36 | MAY
T-602-2700 | PS5-91-OB-5395D | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-10-01 | PS5-09-01 | PS5 - Milestone H | 7 | Closed | 39 | 15 | OCTOBER
T-221-2701 | PS5-74-UR-9024B | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone G | 6 | To be completed |  | 21 | DECEMBER
T-149-2702 | PS5-83-OB-7739D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-09-12 | PS5-02-01 | PS5 - Milestone C | 2 | Closed | 43 | 18 | SEPTEMBER
T-648-2703 | PS5-41-IK-6523B | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone E | 4 | To be completed |  | 39 | NOVEMBER
T-190-2704 | PS5-48-UR-4659A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-04-14 | PS5-09-03 | PS5 - Milestone B | 1.1 | Closed | 47 | 39 | APRIL
T-367-2705 | PS5-19-IK-3385C | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone D | 3 | On hold |  | 14 | OCTOBER
T-126-2706 | PS5-81-OB-7287A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-11-15 | PS5-99-01 | PS5 - Milestone D | 3 | Closed | 43 | 25 | NOVEMBER
T-573-2707 | PS5-54-IK-2680A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-12-06 | PS5-01-06 | PS5 - Milestone A | 1 | Closed | 4 | 24 | DECEMBER
T-058-2708 | PS5-02-OB-4570C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone C | 2 | To be completed |  | 11 | DECEMBER
T-875-2709 | PS5-70-OB-9383A | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone A | 1 | On hold |  | 22 | AUGUST
T-183-2710 | PS5-95-IK-3285C | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-06-10 | PS5-82-01 | PS5 - Milestone I | 8 | Closed | 27 | 27 | JUNE
T-999-2711 | PS5-23-OB-6890C | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | In progress |  | 12 | OCTOBER
T-188-2712 | PS5-34-UR-5772D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | On hold |  | 7 | OCTOBER
T-112-2713 | PS5-96-IK-4666D | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone C | 2 | To be completed |  | 6 | SEPTEMBER
T-739-2714 | PS5-32-OB-3630B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone A | 1 | In progress |  | 43 | NOVEMBER
T-796-2715 | PS5-45-OB-5644A | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-06-09 | PS5-11-03 | PS5 - Milestone A | 1 | Closed | 39 | 11 | JUNE
T-583-2716 | PS5-95-OB-6338A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-06-03 | PS5-09-01 | PS5 - Milestone C | 2 | Closed | 45 | 44 | JUNE
T-777-2717 | PS5-14-OB-3087C | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone F | 5 | To be completed |  | 11 | DECEMBER
T-722-2718 | PS5-98-IK-4752A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | To be completed |  | 23 | DECEMBER
T-024-2719 | PS5-02-OB-3277B | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone F | 5 | To be completed |  | 10 | SEPTEMBER
T-536-2720 | PS5-53-OB-5775A | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone E | 4 | In progress |  | 43 | NOVEMBER
T-173-2721 | PS5-46-IK-1480D | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-10-21 | PS5-04-04 | PS5 - Milestone F | 5 | Closed | 24 | 18 | OCTOBER
T-349-2722 | PS5-10-OB-5382A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone B | 1.1 | To be completed |  | 8 | AUGUST
T-188-2723 | PS5-55-IK-5941A | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone C | 2 | On hold |  | 46 | AUGUST
T-003-2724 | PS5-69-OB-1301B | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-23 | PS5-60-07 | PS5 - Milestone A | 1 | Closed | 14 | 26 | JULY
T-884-2725 | PS5-82-OB-4189A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone B | 1.1 | To be completed |  | 26 | OCTOBER
T-213-2726 | PS5-97-OB-2447D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone B | 1.1 | On hold |  | 44 | AUGUST
T-158-2727 | PS5-72-OB-9582C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | To be completed |  | 41 | NOVEMBER
T-184-2728 | PS5-97-IK-3954B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone G | 6 | In progress |  | 7 | DECEMBER
T-393-2729 | PS5-22-UR-1244D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone G | 6 | In progress |  | 4 | OCTOBER
T-006-2730 | PS5-80-OB-9402C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-09-25 | PS5-10-04 | PS5 - Milestone F | 5 | Closed | 47 | 39 | SEPTEMBER
T-557-2731 | PS5-33-IK-5494A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-12-17 | PS5-01-09 | PS5 - Milestone B | 1.1 | Closed | 13 | 11 | DECEMBER
T-929-2732 | PS5-98-OB-1062A | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | To be completed |  | 17 | NOVEMBER
T-115-2733 | PS5-19-OB-1542B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | In progress |  | 4 | SEPTEMBER
T-504-2734 | PS5-31-UR-3763C | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-07-01 | PS5-06-01 | PS5 - Milestone E | 4 | Closed | 14 | 19 | JULY
T-736-2735 | PS5-66-OB-2729B | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-10-07 | PS5-01-07 | PS5 - Milestone F | 5 | Closed | 5 | 29 | OCTOBER
T-659-2736 | PS5-43-OB-8361B | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone G | 6 | To be completed |  | 21 | SEPTEMBER
T-095-2737 | PS5-40-UR-8950A | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | On hold |  | 26 | AUGUST
T-662-2738 | PS5-94-OB-2296A | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-10-28 | PS5-06-02 | PS5 - Milestone F | 5 | Closed | 24 | 30 | OCTOBER
T-094-2739 | PS5-25-OB-8813A | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-12-18 | PS5-60-07 | PS5 - Milestone C | 2 | Closed | 46 | 42 | DECEMBER
T-224-2740 | PS5-35-IK-7714C | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-11-17 | PS5-12-01 | PS5 - Milestone F | 5 | Closed | 32 | 22 | NOVEMBER
T-660-2741 | PS5-23-UR-7643D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-08-17 | PS5-01-07 | PS5 - Milestone H | 7 | Closed | 9 | 42 | AUGUST
T-842-2742 | PS5-26-OB-7913C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-03-01 | PS5-61-02 | PS5 - Milestone C | 2 | Closed | 10 | 13 | MARCH
T-204-2743 | PS5-56-OB-6054D | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone D | 3 | On hold |  | 20 | DECEMBER
T-330-2744 | PS5-59-OB-3935A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone E | 4 | In progress |  | 26 | NOVEMBER
T-060-2745 | PS5-46-UR-1749B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-08-28 | PS5-82-02 | PS5 - Milestone A | 1 | Closed | 9 | 45 | AUGUST
T-902-2746 | PS5-06-OB-5703A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone A | 1 | To be completed |  | 19 | DECEMBER
T-711-2747 | PS5-66-UR-9578C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-10-07 | PS5-07-02 | PS5 - Milestone F | 5 | Closed | 20 | 48 | OCTOBER
T-599-2748 | PS5-16-OB-8813A | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone G | 6 | On hold |  | 10 | DECEMBER
T-465-2749 | PS5-88-OB-8449D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-05-27 | PS5-03-23 | PS5 - Milestone E | 4 | Closed | 22 | 27 | MAY
T-959-2750 | PS5-90-OB-1944A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-09-01 | PS5-99-01 | PS5 - Milestone F | 5 | Closed | 16 | 39 | SEPTEMBER
T-123-2751 | PS5-63-OB-6331C | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | On hold |  | 28 | SEPTEMBER
T-613-2752 | PS5-35-OB-4703C | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-11-19 | PS5-03-02 | PS5 - Milestone E | 4 | Closed | 12 | 41 | NOVEMBER
T-906-2753 | PS5-14-IK-4946D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone A | 1 | In progress |  | 30 | SEPTEMBER
T-145-2754 | PS5-75-OB-8097C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-01-07 | PS5-11-03 | PS5 - Milestone B | 1.1 | Closed | 39 | 44 | JANUARY
T-490-2755 | PS5-17-OB-6437B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone C | 2 | To be completed |  | 15 | SEPTEMBER
T-963-2756 | PS5-62-OB-2453A | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone G | 6 | To be completed |  | 7 | NOVEMBER
T-585-2757 | PS5-80-IK-5556D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone B | 1.1 | In progress |  | 11 | NOVEMBER
T-060-2758 | PS5-65-OB-7025B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-12-21 | PS5-60-04 | PS5 - Milestone G | 6 | Closed | 5 | 14 | DECEMBER
T-279-2759 | PS5-16-OB-7370A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | To be completed |  | 48 | OCTOBER
T-194-2760 | PS5-06-IK-7164C | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-12-18 | PS5-60-07 | PS5 - Milestone H | 7 | Closed | 22 | 35 | DECEMBER
T-699-2761 | PS5-39-OB-1592A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone E | 4 | In progress |  | 15 | SEPTEMBER
T-346-2762 | PS5-47-OB-3718A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone D | 3 | To be completed |  | 12 | NOVEMBER
T-587-2763 | PS5-50-OB-1069C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | To be completed |  | 37 | NOVEMBER
T-704-2764 | PS5-57-UR-4231D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-09-05 | PS5-61-07 | PS5 - Milestone H | 7 | Closed | 15 | 39 | SEPTEMBER
T-027-2765 | PS5-23-UR-8719D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | In progress |  | 21 | DECEMBER
T-519-2766 | PS5-79-OB-2882A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone D | 3 | In progress |  | 20 | NOVEMBER
T-586-2767 | PS5-71-OB-2927A | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone B | 1.1 | To be completed |  | 34 | NOVEMBER
T-032-2768 | PS5-88-UR-4225D | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-02-26 | PS5-09-03 | PS5 - Milestone D | 3 | Closed | 31 | 41 | FEBRUARY
T-460-2769 | PS5-11-OB-9471B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone H | 7 | In progress |  | 7 | DECEMBER
T-382-2770 | PS5-32-OB-7085D | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone H | 7 | To be completed |  | 30 | DECEMBER
T-045-2771 | PS5-31-UR-6595A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-05-04 | PS5-60-07 | PS5 - Milestone A | 1 | Closed | 32 | 28 | MAY
T-799-2772 | PS5-11-OB-7876C | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-06-02 | PS5-01-06 | PS5 - Milestone A | 1 | Closed | 43 | 35 | JUNE
T-641-2773 | PS5-38-IK-8613B | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone H | 7 | In progress |  | 5 | AUGUST
T-120-2774 | PS5-11-OB-6555A | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | To be completed |  | 14 | NOVEMBER
T-928-2775 | PS5-50-OB-3658D | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone H | 7 | In progress |  | 26 | DECEMBER
T-342-2776 | PS5-58-OB-3761C | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone E | 4 | To be completed |  | 14 | DECEMBER
T-803-2777 | PS5-97-UR-6515D | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-01-05 | PS5-02-02 | PS5 - Milestone G | 6 | Closed | 32 | 48 | JANUARY
T-816-2778 | PS5-45-IK-2531A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone G | 6 | In progress |  | 15 | DECEMBER
T-950-2779 | PS5-83-OB-1989D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | To be completed |  | 8 | AUGUST
T-555-2780 | PS5-40-OB-3503A | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-03-05 | PS5-61-07 | PS5 - Milestone A | 1 | Closed | 23 | 36 | MARCH
T-579-2781 | PS5-14-UR-7120C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-12-05 | PS5-99-03 | PS5 - Milestone D | 3 | Closed | 46 | 39 | DECEMBER
T-584-2782 | PS5-78-IK-3168D | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | To be completed |  | 21 | AUGUST
T-852-2783 | PS5-38-OB-7758C | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-07-04 | PS5-01-01 | PS5 - Milestone F | 5 | Closed | 10 | 48 | JULY
T-106-2784 | PS5-78-IK-7075B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | To be completed |  | 20 | SEPTEMBER
T-006-2785 | PS5-45-IK-3408B | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone D | 3 | In progress |  | 37 | SEPTEMBER
T-422-2786 | PS5-52-UR-8383A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone F | 5 | To be completed |  | 22 | SEPTEMBER
T-534-2787 | PS5-96-IK-6501C | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-08-06 | PS5-12-01 | PS5 - Milestone E | 4 | Closed | 19 | 47 | AUGUST
T-589-2788 | PS5-65-UR-9388B | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone C | 2 | On hold |  | 6 | DECEMBER
T-738-2789 | PS5-98-OB-2735D | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-05-04 | PS5-04-01 | PS5 - Milestone A | 1 | Closed | 11 | 8 | MAY
T-429-2790 | PS5-68-OB-8906A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | To be completed |  | 36 | DECEMBER
T-200-2791 | PS5-90-OB-1531D | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone D | 3 | On hold |  | 7 | SEPTEMBER
T-143-2792 | PS5-83-OB-2246A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-05-24 | PS5-08-01 | PS5 - Milestone G | 6 | Closed | 43 | 43 | MAY
T-036-2793 | PS5-33-OB-6006B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone D | 3 | To be completed |  | 29 | OCTOBER
T-716-2794 | PS5-83-IK-9089D | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone C | 2 | In progress |  | 36 | OCTOBER
T-426-2795 | PS5-85-UR-2681B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone E | 4 | In progress |  | 5 | NOVEMBER
T-631-2796 | PS5-97-OB-4303C | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone A | 1 | On hold |  | 6 | DECEMBER
T-094-2797 | PS5-59-OB-5661B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-04-23 | PS5-08-01 | PS5 - Milestone H | 7 | Closed | 33 | 8 | APRIL
T-103-2798 | PS5-91-IK-4486B | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | To be completed |  | 30 | NOVEMBER
T-870-2799 | PS5-17-OB-2720B | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-08-01 | PS5-01-04 | PS5 - Milestone H | 7 | Closed | 14 | 29 | AUGUST
T-422-2800 | PS5-85-OB-4829A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | To be completed |  | 26 | DECEMBER
T-924-2801 | PS5-95-IK-3011D | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone F | 5 | In progress |  | 28 | DECEMBER
T-789-2802 | PS5-80-OB-8062C | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone F | 5 | To be completed |  | 30 | OCTOBER
T-784-2803 | PS5-32-OB-7947B | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-07-27 | PS5-01-02 | PS5 - Milestone A | 1 | Closed | 40 | 34 | JULY
T-367-2804 | PS5-63-OB-1888A | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone I | 8 | In progress |  | 47 | AUGUST
T-703-2805 | PS5-91-IK-4785D | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | On hold |  | 16 | OCTOBER
T-385-2806 | PS5-58-OB-4818D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-11-12 | PS5-04-04 | PS5 - Milestone C | 2 | Closed | 20 | 20 | NOVEMBER
T-845-2807 | PS5-48-OB-6276C | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone H | 7 | To be completed |  | 40 | OCTOBER
T-281-2808 | PS5-27-IK-7633C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone G | 6 | To be completed |  | 18 | OCTOBER
T-324-2809 | PS5-66-UR-3424B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | In progress |  | 44 | NOVEMBER
T-770-2810 | PS5-06-IK-3908B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone A | 1 | On hold |  | 18 | AUGUST
T-715-2811 | PS5-08-OB-6666A | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone G | 6 | To be completed |  | 17 | AUGUST
T-739-2812 | PS5-79-OB-1777B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone C | 2 | To be completed |  | 23 | OCTOBER
T-096-2813 | PS5-46-OB-5670D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-11-20 | PS5-10-05 | PS5 - Milestone C | 2 | Closed | 36 | 33 | NOVEMBER
T-369-2814 | PS5-91-OB-8001A | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-07-14 | PS5-04-02 | PS5 - Milestone B | 1.1 | Closed | 7 | 5 | JULY
T-459-2815 | PS5-51-OB-4927B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone G | 6 | To be completed |  | 15 | AUGUST
T-787-2816 | PS5-42-IK-2672B | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone G | 6 | To be completed |  | 44 | SEPTEMBER
T-246-2817 | PS5-12-OB-5307C | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone G | 6 | On hold |  | 5 | SEPTEMBER
T-462-2818 | PS5-48-IK-8873B | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | To be completed |  | 10 | OCTOBER
T-156-2819 | PS5-66-IK-8750D | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-07-27 | PS5-11-03 | PS5 - Milestone F | 5 | Closed | 11 | 43 | JULY
T-242-2820 | PS5-28-OB-7937B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone C | 2 | To be completed |  | 43 | DECEMBER
T-945-2821 | PS5-57-OB-2626C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | In progress |  | 46 | AUGUST
T-189-2822 | PS5-84-IK-9946C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-12-27 | PS5-01-05 | PS5 - Milestone B | 1.1 | Closed | 19 | 18 | DECEMBER
T-696-2823 | PS5-42-OB-5162A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone I | 8 | In progress |  | 5 | OCTOBER
T-825-2824 | PS5-74-OB-6473B | CQP01 - Pipe Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | On hold |  | 24 | AUGUST
T-253-2825 | PS5-66-OB-6239D | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone D | 3 | To be completed |  | 16 | SEPTEMBER
T-285-2826 | PS5-56-UR-1724B | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone I | 8 | To be completed |  | 23 | AUGUST
T-661-2827 | PS5-66-OB-9355D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone H | 7 | In progress |  | 45 | DECEMBER
T-241-2828 | PS5-18-OB-8042B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone I | 8 | In progress |  | 24 | NOVEMBER
T-813-2829 | PS5-57-OB-8941C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-07-03 | PS5-61-07 | PS5 - Milestone H | 7 | Closed | 45 | 42 | JULY
T-712-2830 | PS5-12-OB-3240B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone C | 2 | In progress |  | 27 | AUGUST
T-943-2831 | PS5-84-IK-7065C | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | In progress |  | 28 | AUGUST
T-168-2832 | PS5-71-UR-8297D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-05-10 | PS5-09-01 | PS5 - Milestone G | 6 | Closed | 16 | 4 | MAY
T-660-2833 | PS5-04-OB-5479B | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone D | 3 | To be completed |  | 21 | OCTOBER
T-498-2834 | PS5-23-IK-4970A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone C | 2 | On hold |  | 14 | DECEMBER
T-697-2835 | PS5-48-IK-5722C | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone I | 8 | To be completed |  | 35 | SEPTEMBER
T-991-2836 | PS5-31-OB-1050C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-25 | PS5-60-04 | PS5 - Milestone F | 5 | Closed | 32 | 9 | JULY
T-520-2837 | PS5-24-IK-5531D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone C | 2 | In progress |  | 47 | NOVEMBER
T-683-2838 | PS5-04-OB-7987C | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-07-23 | PS5-10-06 | PS5 - Milestone G | 6 | Closed | 24 | 9 | JULY
T-847-2839 | PS5-62-IK-5890A | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-08-24 | PS5-01-08 | PS5 - Milestone G | 6 | Closed | 48 | 23 | AUGUST
T-901-2840 | PS5-45-IK-5847A | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-04-15 | PS5-62-01 | PS5 - Milestone F | 5 | Closed | 23 | 21 | APRIL
T-614-2841 | PS5-57-OB-9436A | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone A | 1 | To be completed |  | 24 | AUGUST
T-580-2842 | PS5-16-IK-8621B | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone I | 8 | To be completed |  | 5 | DECEMBER
T-388-2843 | PS5-64-UR-3636B | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone I | 8 | On hold |  | 42 | DECEMBER
T-177-2844 | PS5-22-OB-7072B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone C | 2 | To be completed |  | 15 | DECEMBER
T-214-2845 | PS5-05-OB-7633A | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-12-23 | PS5-07-04 | PS5 - Milestone H | 7 | Closed | 30 | 18 | DECEMBER
T-471-2846 | PS5-53-OB-7078A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone H | 7 | On hold |  | 24 | NOVEMBER
T-044-2847 | PS5-45-IK-9204D | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-10-22 | PS5-12-02 | PS5 - Milestone H | 7 | Closed | 26 | 15 | OCTOBER
T-143-2848 | PS5-87-OB-6214B | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | To be completed |  | 5 | AUGUST
T-160-2849 | PS5-94-OB-5294A | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-08-23 | PS5-09-04 | PS5 - Milestone E | 4 | Closed | 30 | 39 | AUGUST
T-335-2850 | PS5-93-IK-1384B | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone A | 1 | To be completed |  | 5 | SEPTEMBER
T-006-2851 | PS5-15-OB-1839B | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-03-02 | PS5-99-02 | PS5 - Milestone B | 1.1 | Closed | 27 | 36 | MARCH
T-639-2852 | PS5-22-OB-3035A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-03-21 | PS5-01-06 | PS5 - Milestone E | 4 | Closed | 24 | 25 | MARCH
T-135-2853 | PS5-48-UR-8208C | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | To be completed |  | 4 | AUGUST
T-688-2854 | PS5-35-IK-3400B | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone C | 2 | To be completed |  | 4 | AUGUST
T-976-2855 | PS5-37-IK-8251C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-05-24 | PS5-12-02 | PS5 - Milestone B | 1.1 | Closed | 33 | 43 | MAY
T-689-2856 | PS5-81-UR-4018B | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone B | 1.1 | In progress |  | 9 | OCTOBER
T-091-2857 | PS5-51-OB-3985D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | In progress |  | 25 | OCTOBER
T-807-2858 | PS5-15-OB-9773A | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-03-10 | PS5-10-06 | PS5 - Milestone E | 4 | Closed | 20 | 15 | MARCH
T-343-2859 | PS5-39-IK-1139A | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-04-06 | PS5-10-04 | PS5 - Milestone H | 7 | Closed | 9 | 15 | APRIL
T-863-2860 | PS5-02-IK-3454B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone C | 2 | On hold |  | 47 | AUGUST
T-909-2861 | PS5-69-IK-3398C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-04-10 | PS5-03-01 | PS5 - Milestone D | 3 | Closed | 36 | 4 | APRIL
T-792-2862 | PS5-73-OB-6279C | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | To be completed |  | 9 | DECEMBER
T-826-2863 | PS5-32-OB-7188B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone I | 8 | To be completed |  | 28 | AUGUST
T-004-2864 | PS5-13-OB-8566B | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | In progress |  | 47 | NOVEMBER
T-887-2865 | PS5-66-IK-4227C | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-10-07 | PS5-04-01 | PS5 - Milestone B | 1.1 | Closed | 43 | 9 | OCTOBER
T-481-2866 | PS5-35-UR-4174A | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-02-22 | PS5-13-01 | PS5 - Milestone D | 3 | Closed | 26 | 31 | FEBRUARY
T-924-2867 | PS5-39-OB-8511C | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-06-19 | PS5-06-02 | PS5 - Milestone G | 6 | Closed | 39 | 25 | JUNE
T-275-2868 | PS5-04-UR-4439B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone G | 6 | To be completed |  | 7 | OCTOBER
T-494-2869 | PS5-73-OB-6494B | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone H | 7 | To be completed |  | 18 | AUGUST
T-578-2870 | PS5-84-OB-3525C | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone A | 1 | In progress |  | 13 | AUGUST
T-894-2871 | PS5-37-UR-8125B | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-02-24 | PS5-11-02 | PS5 - Milestone A | 1 | Closed | 43 | 28 | FEBRUARY
T-352-2872 | PS5-44-IK-4048A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone I | 8 | On hold |  | 41 | SEPTEMBER
T-673-2873 | PS5-62-OB-3048A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-01-12 | PS5-03-02 | PS5 - Milestone F | 5 | Closed | 7 | 39 | JANUARY
T-563-2874 | PS5-81-OB-2661C | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-01-02 | PS5-99-03 | PS5 - Milestone H | 7 | Closed | 6 | 18 | JANUARY
T-414-2875 | PS5-75-OB-8381A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone G | 6 | To be completed |  | 7 | DECEMBER
T-052-2876 | PS5-21-UR-2299C | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-10-13 | PS5-08-02 | PS5 - Milestone E | 4 | Closed | 41 | 44 | OCTOBER
T-341-2877 | PS5-80-UR-1984A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone E | 4 | To be completed |  | 46 | DECEMBER
T-948-2878 | PS5-36-UR-1059A | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-06-25 | PS5-10-04 | PS5 - Milestone H | 7 | Closed | 44 | 31 | JUNE
T-205-2879 | PS5-46-IK-3747C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone F | 5 | To be completed |  | 46 | NOVEMBER
T-814-2880 | PS5-40-UR-6002C | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-03-21 | PS5-82-07 | PS5 - Milestone F | 5 | Closed | 37 | 25 | MARCH
T-231-2881 | PS5-80-UR-1249A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone I | 8 | To be completed |  | 15 | DECEMBER
T-462-2882 | PS5-16-OB-9709C | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone E | 4 | In progress |  | 17 | AUGUST
T-971-2883 | PS5-41-OB-1928B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone H | 7 | To be completed |  | 6 | OCTOBER
T-133-2884 | PS5-36-IK-1131B | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone D | 3 | To be completed |  | 38 | NOVEMBER
T-132-2885 | PS5-77-OB-7657B | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | On hold |  | 30 | OCTOBER
T-284-2886 | PS5-11-IK-1222C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone D | 3 | To be completed |  | 31 | SEPTEMBER
T-592-2887 | PS5-54-OB-8549D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-02-22 | PS5-82-01 | PS5 - Milestone H | 7 | Closed | 39 | 32 | FEBRUARY
T-275-2888 | PS5-81-OB-5506C | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-01-16 | PS5-01-08 | PS5 - Milestone H | 7 | Closed | 46 | 33 | JANUARY
T-110-2889 | PS5-92-OB-8511B | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone D | 3 | To be completed |  | 13 | AUGUST
T-891-2890 | PS5-25-OB-8849D | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone H | 7 | In progress |  | 48 | SEPTEMBER
T-482-2891 | PS5-94-IK-5530D | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-12-13 | PS5-61-07 | PS5 - Milestone E | 4 | Closed | 43 | 31 | DECEMBER
T-638-2892 | PS5-57-OB-3049D | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone C | 2 | On hold |  | 24 | SEPTEMBER
T-171-2893 | PS5-42-OB-1847C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | To be completed |  | 19 | DECEMBER
T-757-2894 | PS5-66-OB-2631C | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone F | 5 | In progress |  | 43 | OCTOBER
T-840-2895 | PS5-65-IK-6237A | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | In progress |  | 28 | NOVEMBER
T-970-2896 | PS5-90-OB-7254C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone G | 6 | In progress |  | 24 | NOVEMBER
T-553-2897 | PS5-79-IK-7240C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-06-28 | PS5-09-01 | PS5 - Milestone G | 6 | Closed | 21 | 31 | JUNE
T-290-2898 | PS5-51-OB-7835A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-01-24 | PS5-07-02 | PS5 - Milestone I | 8 | Closed | 48 | 27 | JANUARY
T-341-2899 | PS5-21-OB-7469B | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-05-16 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 40 | 8 | MAY
T-888-2900 | PS5-21-OB-3004B | CQE01 - HV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone A | 1 | In progress |  | 41 | OCTOBER
T-708-2901 | PS5-75-OB-1031D | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | To be completed |  | 37 | DECEMBER
T-156-2902 | PS5-65-OB-6595D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | To be completed |  | 31 | SEPTEMBER
T-347-2903 | PS5-39-UR-2640D | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone C | 2 | To be completed |  | 42 | DECEMBER
T-945-2904 | PS5-40-IK-6129D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-10-18 | PS5-61-02 | PS5 - Milestone I | 8 | Closed | 6 | 24 | OCTOBER
T-730-2905 | PS5-33-OB-1169A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-05-20 | PS5-82-01 | PS5 - Milestone F | 5 | Closed | 38 | 33 | MAY
T-609-2906 | PS5-17-OB-7265B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-08-04 | PS5-60-01 | PS5 - Milestone A | 1 | Closed | 47 | 43 | AUGUST
T-772-2907 | PS5-81-IK-5583C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone H | 7 | To be completed |  | 35 | SEPTEMBER
T-974-2908 | PS5-20-OB-8953B | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-07-16 | PS5-03-01 | PS5 - Milestone E | 4 | Closed | 5 | 33 | JULY
T-374-2909 | PS5-50-OB-2717A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone I | 8 | To be completed |  | 14 | DECEMBER
T-907-2910 | PS5-05-OB-6093B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-12-25 | PS5-01-07 | PS5 - Milestone I | 8 | Closed | 38 | 37 | DECEMBER
T-832-2911 | PS5-20-OB-6943C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-11-01 | PS5-01-05 | PS5 - Milestone E | 4 | Closed | 20 | 16 | NOVEMBER
T-765-2912 | PS5-01-OB-6526B | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone F | 5 | To be completed |  | 26 | SEPTEMBER
T-798-2913 | PS5-39-OB-3193C | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone C | 2 | To be completed |  | 48 | NOVEMBER
T-764-2914 | PS5-58-OB-9331C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | To be completed |  | 38 | DECEMBER
T-382-2915 | PS5-40-OB-3275B | CQE02 - LV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-11-19 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 6 | 16 | NOVEMBER
T-658-2916 | PS5-96-OB-7733B | CQM02 - Compressor | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-04-02 | PS5-11-02 | PS5 - Milestone I | 8 | Closed | 47 | 6 | APRIL
T-372-2917 | PS5-62-OB-8722A | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-02-08 | PS5-10-04 | PS5 - Milestone H | 7 | Closed | 36 | 5 | FEBRUARY
T-199-2918 | PS5-48-OB-9162A | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | To be completed |  | 11 | OCTOBER
T-212-2919 | PS5-17-OB-1348A | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | On hold |  | 25 | SEPTEMBER
T-457-2920 | PS5-04-IK-8515D | CQM04 - Vessel | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone I | 8 | To be completed |  | 46 | SEPTEMBER
T-765-2921 | PS5-01-IK-9351D | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | On hold |  | 29 | DECEMBER
T-489-2922 | PS5-61-UR-2701A | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-10-17 | PS5-01-08 | PS5 - Milestone C | 2 | Closed | 45 | 8 | OCTOBER
T-267-2923 | PS5-65-OB-9822A | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-10-21 | PS5-02-02 | PS5 - Milestone H | 7 | Closed | 21 | 8 | OCTOBER
T-377-2924 | PS5-85-OB-7913D | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone F | 5 | On hold |  | 30 | SEPTEMBER
T-206-2925 | PS5-79-UR-2406C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-02-14 | PS5-01-01 | PS5 - Milestone E | 4 | Closed | 10 | 47 | FEBRUARY
T-057-2926 | PS5-60-OB-4846A | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-08-18 | PS5-10-01 | PS5 - Milestone G | 6 | Closed | 19 | 43 | AUGUST
T-203-2927 | PS5-35-IK-3000B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone C | 2 | To be completed |  | 10 | AUGUST
T-046-2928 | PS5-52-IK-2790C | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone C | 2 | In progress |  | 35 | NOVEMBER
T-855-2929 | PS5-27-OB-9673C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone A | 1 | In progress |  | 27 | OCTOBER
T-732-2930 | PS5-79-UR-4435A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-12-10 | PS5-61-01 | PS5 - Milestone H | 7 | Closed | 41 | 23 | DECEMBER
T-218-2931 | PS5-50-IK-8051C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone A | 1 | In progress |  | 8 | AUGUST
T-909-2932 | PS5-47-OB-4457A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-10-02 | PS5-99-01 | PS5 - Milestone D | 3 | Closed | 29 | 16 | OCTOBER
T-597-2933 | PS5-13-IK-6092A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-03-05 | PS5-12-01 | PS5 - Milestone G | 6 | Closed | 37 | 20 | MARCH
T-212-2934 | PS5-02-OB-8575A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone B | 1.1 | To be completed |  | 12 | AUGUST
T-848-2935 | PS5-39-IK-9385D | CQH02 - AHU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone H | 7 | To be completed |  | 24 | SEPTEMBER
T-779-2936 | PS5-04-OB-8166B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-10-16 | PS5-60-10 | PS5 - Milestone I | 8 | Closed | 38 | 48 | OCTOBER
T-210-2937 | PS5-36-IK-3756A | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone B | 1.1 | On hold |  | 27 | SEPTEMBER
T-612-2938 | PS5-92-OB-5607A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-12-03 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 19 | 21 | DECEMBER
T-360-2939 | PS5-53-IK-5540B | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone C | 2 | To be completed |  | 4 | NOVEMBER
T-068-2940 | PS5-62-OB-6551B | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone G | 6 | To be completed |  | 32 | DECEMBER
T-202-2941 | PS5-62-OB-3895A | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | To be completed |  | 37 | DECEMBER
T-569-2942 | PS5-18-UR-4360B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone B | 1.1 | On hold |  | 17 | NOVEMBER
T-602-2943 | PS5-06-OB-9899B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-04-28 | PS5-05-01 | PS5 - Milestone H | 7 | Closed | 30 | 19 | APRIL
T-185-2944 | PS5-14-OB-3486C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-01-18 | PS5-60-01 | PS5 - Milestone C | 2 | Closed | 8 | 29 | JANUARY
T-204-2945 | PS5-82-OB-8329D | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone H | 7 | On hold |  | 38 | OCTOBER
T-385-2946 | PS5-40-OB-7215A | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone H | 7 | To be completed |  | 34 | SEPTEMBER
T-529-2947 | PS5-27-IK-5601C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone D | 3 | To be completed |  | 28 | DECEMBER
T-872-2948 | PS5-44-UR-4104A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone C | 2 | In progress |  | 12 | OCTOBER
T-738-2949 | PS5-81-UR-3296D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone G | 6 | To be completed |  | 19 | NOVEMBER
T-367-2950 | PS5-12-IK-3587D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-12-02 | PS5-02-02 | PS5 - Milestone D | 3 | Closed | 39 | 28 | DECEMBER
T-099-2951 | PS5-15-OB-9766D | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone H | 7 | To be completed |  | 45 | SEPTEMBER
T-366-2952 | PS5-91-UR-1949C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-08-08 | PS5-10-03 | PS5 - Milestone A | 1 | Closed | 15 | 21 | AUGUST
T-215-2953 | PS5-45-IK-8440D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-04-27 | PS5-11-01 | PS5 - Milestone A | 1 | Closed | 8 | 12 | APRIL
T-882-2954 | PS5-12-OB-5473D | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | In progress |  | 32 | DECEMBER
T-359-2955 | PS5-90-OB-7251C | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | In progress |  | 17 | DECEMBER
T-094-2956 | PS5-99-OB-6088C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone D | 3 | To be completed |  | 38 | SEPTEMBER
T-443-2957 | PS5-98-OB-7089C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | To be completed |  | 14 | SEPTEMBER
T-618-2958 | PS5-78-OB-8429D | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-07-20 | PS5-09-03 | PS5 - Milestone G | 6 | Closed | 22 | 9 | JULY
T-044-2959 | PS5-96-IK-2841A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone A | 1 | To be completed |  | 20 | SEPTEMBER
T-918-2960 | PS5-47-IK-7296B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-02-11 | PS5-10-03 | PS5 - Milestone C | 2 | Closed | 32 | 16 | FEBRUARY
T-666-2961 | PS5-81-OB-5852C | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-10-03 | PS5-11-02 | PS5 - Milestone G | 6 | Closed | 34 | 12 | OCTOBER
T-271-2962 | PS5-45-IK-9789D | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone H | 7 | To be completed |  | 15 | SEPTEMBER
T-912-2963 | PS5-27-UR-8272A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone H | 7 | On hold |  | 31 | SEPTEMBER
T-845-2964 | PS5-79-OB-6372A | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone C | 2 | To be completed |  | 38 | NOVEMBER
T-105-2965 | PS5-63-UR-2433C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-01-06 | PS5-62-02 | PS5 - Milestone D | 3 | Closed | 42 | 37 | JANUARY
T-639-2966 | PS5-88-OB-8192A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone H | 7 | To be completed |  | 19 | SEPTEMBER
T-876-2967 | PS5-70-IK-5409D | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-08-05 | PS5-05-01 | PS5 - Milestone F | 5 | Closed | 25 | 10 | AUGUST
T-369-2968 | PS5-60-UR-6391D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-06-11 | PS5-63-01 | PS5 - Milestone E | 4 | Closed | 45 | 20 | JUNE
T-214-2969 | PS5-86-UR-9486D | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-04-07 | PS5-07-04 | PS5 - Milestone A | 1 | Closed | 17 | 19 | APRIL
T-398-2970 | PS5-07-OB-8499C | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone B | 1.1 | In progress |  | 9 | SEPTEMBER
T-271-2971 | PS5-80-UR-1150C | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone I | 8 | In progress |  | 48 | AUGUST
T-469-2972 | PS5-06-UR-9775B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone F | 5 | To be completed |  | 45 | OCTOBER
T-805-2973 | PS5-50-OB-1234A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone D | 3 | To be completed |  | 33 | NOVEMBER
T-986-2974 | PS5-23-UR-7683B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone I | 8 | To be completed |  | 10 | SEPTEMBER
T-617-2975 | PS5-13-OB-9872D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | In progress |  | 28 | OCTOBER
T-529-2976 | PS5-58-OB-9182D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-04-22 | PS5-10-06 | PS5 - Milestone D | 3 | Closed | 8 | 5 | APRIL
T-091-2977 | PS5-50-IK-8043D | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone D | 3 | To be completed |  | 24 | SEPTEMBER
T-244-2978 | PS5-55-OB-8661D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-01-20 | PS5-60-10 | PS5 - Milestone B | 1.1 | Closed | 6 | 44 | JANUARY
T-723-2979 | PS5-45-UR-7650B | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone D | 3 | In progress |  | 37 | DECEMBER
T-305-2980 | PS5-40-UR-4644C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-12-08 | PS5-60-10 | PS5 - Milestone I | 8 | Closed | 13 | 16 | DECEMBER
T-901-2981 | PS5-15-OB-4902B | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-02-19 | PS5-03-02 | PS5 - Milestone E | 4 | Closed | 22 | 36 | FEBRUARY
T-527-2982 | PS5-99-OB-9412A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone A | 1 | In progress |  | 41 | SEPTEMBER
T-100-2983 | PS5-73-UR-5212C | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone A | 1 | To be completed |  | 17 | DECEMBER
T-769-2984 | PS5-40-OB-4293A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone C | 2 | In progress |  | 8 | DECEMBER
T-061-2985 | PS5-97-IK-2498B | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-07-23 | PS5-04-04 | PS5 - Milestone I | 8 | Closed | 18 | 27 | JULY
T-890-2986 | PS5-99-UR-1820A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-10-05 | PS5-08-01 | PS5 - Milestone A | 1 | Closed | 13 | 14 | OCTOBER
T-730-2987 | PS5-74-IK-9997B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-03-12 | PS5-03-01 | PS5 - Milestone I | 8 | Closed | 22 | 27 | MARCH
T-655-2988 | PS5-44-OB-6029A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone A | 1 | On hold |  | 34 | OCTOBER
T-287-2989 | PS5-31-UR-1988C | CQP01 - Pipe Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | To be completed |  | 9 | SEPTEMBER
T-972-2990 | PS5-72-IK-4279A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone H | 7 | To be completed |  | 12 | DECEMBER
T-560-2991 | PS5-13-OB-2829C | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-09-06 | PS5-03-02 | PS5 - Milestone H | 7 | Closed | 7 | 45 | SEPTEMBER
T-377-2992 | PS5-16-OB-2453B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone D | 3 | In progress |  | 38 | NOVEMBER
T-858-2993 | PS5-28-OB-7273A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-05-22 | PS5-62-02 | PS5 - Milestone B | 1.1 | Closed | 33 | 43 | MAY
T-256-2994 | PS5-20-UR-8122A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-06-03 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 19 | 30 | JUNE
T-327-2995 | PS5-35-IK-2206D | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone I | 8 | To be completed |  | 35 | NOVEMBER
T-609-2996 | PS5-47-OB-6022B | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | To be completed |  | 42 | AUGUST
T-754-2997 | PS5-53-IK-5597C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | To be completed |  | 34 | OCTOBER
T-597-2998 | PS5-63-OB-6992B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-09-25 | PS5-99-03 | PS5 - Milestone H | 7 | Closed | 48 | 13 | SEPTEMBER
T-734-2999 | PS5-52-IK-8672D | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-12-22 | PS5-01-04 | PS5 - Milestone G | 6 | Closed | 39 | 7 | DECEMBER
T-235-3000 | PS5-89-OB-4865C | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone H | 7 | In progress |  | 5 | SEPTEMBER
T-820-3001 | PS5-04-OB-4735B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone F | 5 | To be completed |  | 23 | OCTOBER
T-329-3002 | PS5-83-OB-3335D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-01-12 | PS5-05-01 | PS5 - Milestone E | 4 | Closed | 5 | 29 | JANUARY
T-848-3003 | PS5-23-UR-7408A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone I | 8 | In progress |  | 38 | OCTOBER
T-046-3004 | PS5-36-OB-5899C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone F | 5 | In progress |  | 26 | AUGUST
T-776-3005 | PS5-84-UR-8655A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-06-17 | PS5-13-01 | PS5 - Milestone I | 8 | Closed | 36 | 11 | JUNE
T-197-3006 | PS5-14-UR-3844C | CQE04 - Transformer | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-01-25 | PS5-09-04 | PS5 - Milestone B | 1.1 | Closed | 27 | 12 | JANUARY
T-201-3007 | PS5-25-OB-3440C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone C | 2 | In progress |  | 37 | AUGUST
T-610-3008 | PS5-12-OB-8597B | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-08-06 | PS5-63-04 | PS5 - Milestone A | 1 | Closed | 28 | 18 | AUGUST
T-296-3009 | PS5-81-OB-9893D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-12-07 | PS5-99-02 | PS5 - Milestone H | 7 | Closed | 46 | 4 | DECEMBER
T-531-3010 | PS5-48-UR-6348B | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-08-01 | PS5-08-02 | PS5 - Milestone G | 6 | Closed | 8 | 29 | AUGUST
T-860-3011 | PS5-58-IK-9537B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-05-13 | PS5-05-03 | PS5 - Milestone B | 1.1 | Closed | 30 | 19 | MAY
T-523-3012 | PS5-31-OB-6473A | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone E | 4 | In progress |  | 8 | NOVEMBER
T-488-3013 | PS5-38-OB-6955A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | To be completed |  | 23 | SEPTEMBER
T-724-3014 | PS5-77-IK-7678C | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone B | 1.1 | In progress |  | 21 | OCTOBER
T-721-3015 | PS5-65-IK-3245D | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone D | 3 | On hold |  | 14 | OCTOBER
T-613-3016 | PS5-80-IK-6390A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone E | 4 | To be completed |  | 21 | DECEMBER
T-614-3017 | PS5-37-OB-2567C | CQX04 - Painting & Coating | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-01-25 | PS5-60-01 | PS5 - Milestone I | 8 | Closed | 13 | 6 | JANUARY
T-759-3018 | PS5-51-IK-2898D | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-09-06 | PS5-01-09 | PS5 - Milestone B | 1.1 | Closed | 45 | 4 | SEPTEMBER
T-017-3019 | PS5-43-OB-2089C | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | In progress |  | 46 | DECEMBER
T-639-3020 | PS5-76-IK-5459B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-11-02 | PS5-11-03 | PS5 - Milestone C | 2 | Closed | 10 | 12 | NOVEMBER
T-042-3021 | PS5-14-IK-4464A | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone A | 1 | On hold |  | 38 | AUGUST
T-977-3022 | PS5-50-OB-3533C | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone B | 1.1 | To be completed |  | 6 | AUGUST
T-439-3023 | PS5-06-UR-5107A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | On hold |  | 19 | NOVEMBER
T-061-3024 | PS5-52-UR-2097B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone I | 8 | In progress |  | 34 | SEPTEMBER
T-036-3025 | PS5-07-OB-8683A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-06-01 | PS5-06-02 | PS5 - Milestone C | 2 | Closed | 22 | 6 | JUNE
T-883-3026 | PS5-24-IK-5272A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone I | 8 | In progress |  | 23 | SEPTEMBER
T-497-3027 | PS5-06-OB-3282D | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-09-06 | PS5-61-02 | PS5 - Milestone I | 8 | Closed | 15 | 25 | SEPTEMBER
T-146-3028 | PS5-66-UR-4781B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone I | 8 | To be completed |  | 25 | OCTOBER
T-802-3029 | PS5-92-OB-3259C | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone D | 3 | To be completed |  | 39 | SEPTEMBER
T-143-3030 | PS5-31-OB-8123C | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-11-26 | PS5-06-01 | PS5 - Milestone D | 3 | Closed | 16 | 16 | NOVEMBER
T-110-3031 | PS5-95-IK-8459D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-07-18 | PS5-03-02 | PS5 - Milestone H | 7 | Closed | 18 | 46 | JULY
T-593-3032 | PS5-33-OB-8377A | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-03-09 | PS5-02-03 | PS5 - Milestone G | 6 | Closed | 8 | 18 | MARCH
T-509-3033 | PS5-10-OB-6576A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone G | 6 | To be completed |  | 34 | OCTOBER
T-599-3034 | PS5-07-OB-1551C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone D | 3 | To be completed |  | 8 | AUGUST
T-798-3035 | PS5-43-OB-1473A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone H | 7 | In progress |  | 19 | SEPTEMBER
T-383-3036 | PS5-75-OB-7738C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-12-28 | PS5-08-02 | PS5 - Milestone C | 2 | Closed | 22 | 41 | DECEMBER
T-506-3037 | PS5-15-IK-9054A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone A | 1 | In progress |  | 28 | NOVEMBER
T-120-3038 | PS5-17-OB-5171B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone G | 6 | On hold |  | 37 | AUGUST
T-591-3039 | PS5-18-OB-4350A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone B | 1.1 | To be completed |  | 6 | NOVEMBER
T-398-3040 | PS5-29-IK-9697A | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-09-08 | PS5-62-01 | PS5 - Milestone F | 5 | Closed | 41 | 26 | SEPTEMBER
T-570-3041 | PS5-77-UR-2032A | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-05-24 | PS5-61-07 | PS5 - Milestone B | 1.1 | Closed | 44 | 4 | MAY
T-654-3042 | PS5-48-OB-7275B | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-11-13 | PS5-63-04 | PS5 - Milestone D | 3 | Closed | 6 | 41 | NOVEMBER
T-991-3043 | PS5-42-OB-8371A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-01-21 | PS5-04-04 | PS5 - Milestone C | 2 | Closed | 13 | 46 | JANUARY
T-118-3044 | PS5-49-OB-1297B | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | On hold |  | 32 | DECEMBER
T-278-3045 | PS5-91-OB-1136C | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone I | 8 | To be completed |  | 24 | DECEMBER
T-284-3046 | PS5-65-OB-5718D | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone C | 2 | On hold |  | 16 | SEPTEMBER
T-755-3047 | PS5-83-IK-9076A | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-11-10 | PS5-01-01 | PS5 - Milestone B | 1.1 | Closed | 41 | 33 | NOVEMBER
T-368-3048 | PS5-14-OB-6095D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | In progress |  | 36 | OCTOBER
T-832-3049 | PS5-29-IK-9472B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-02-23 | PS5-09-01 | PS5 - Milestone C | 2 | Closed | 7 | 29 | FEBRUARY
T-440-3050 | PS5-71-OB-8363A | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone F | 5 | To be completed |  | 7 | SEPTEMBER
T-426-3051 | PS5-65-OB-7310A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | In progress |  | 12 | SEPTEMBER
T-876-3052 | PS5-56-OB-9383B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone B | 1.1 | To be completed |  | 35 | NOVEMBER
T-516-3053 | PS5-86-IK-4774B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-07-27 | PS5-06-03 | PS5 - Milestone F | 5 | Closed | 31 | 13 | JULY
T-367-3054 | PS5-20-OB-1848D | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone G | 6 | To be completed |  | 29 | DECEMBER
T-913-3055 | PS5-95-IK-3262B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-14 | PS5-60-07 | PS5 - Milestone G | 6 | Closed | 43 | 33 | JUNE
T-247-3056 | PS5-60-UR-7875D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone G | 6 | To be completed |  | 12 | SEPTEMBER
T-977-3057 | PS5-81-OB-3972D | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone I | 8 | In progress |  | 42 | OCTOBER
T-266-3058 | PS5-59-OB-5697D | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-10-26 | PS5-60-10 | PS5 - Milestone E | 4 | Closed | 6 | 26 | OCTOBER
T-625-3059 | PS5-95-OB-8034C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-04-13 | PS5-07-02 | PS5 - Milestone B | 1.1 | Closed | 33 | 9 | APRIL
T-572-3060 | PS5-26-UR-8596D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-08-20 | PS5-60-07 | PS5 - Milestone G | 6 | Closed | 34 | 37 | AUGUST
T-356-3061 | PS5-13-UR-8238D | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone H | 7 | In progress |  | 10 | SEPTEMBER
T-026-3062 | PS5-91-OB-4301D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | To be completed |  | 14 | AUGUST
T-318-3063 | PS5-98-OB-8608C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone F | 5 | To be completed |  | 21 | OCTOBER
T-420-3064 | PS5-17-IK-7581B | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-09-14 | PS5-11-03 | PS5 - Milestone G | 6 | Closed | 19 | 16 | SEPTEMBER
T-064-3065 | PS5-27-OB-9755B | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-08-16 | PS5-60-04 | PS5 - Milestone B | 1.1 | Closed | 11 | 38 | AUGUST
T-260-3066 | PS5-69-OB-9823B | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone E | 4 | To be completed |  | 14 | DECEMBER
T-170-3067 | PS5-63-OB-4497A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | To be completed |  | 12 | OCTOBER
T-714-3068 | PS5-16-OB-4470C | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-11-04 | PS5-12-01 | PS5 - Milestone A | 1 | Closed | 22 | 25 | NOVEMBER
T-639-3069 | PS5-13-OB-6346C | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-04-25 | PS5-05-01 | PS5 - Milestone I | 8 | Closed | 13 | 20 | APRIL
T-961-3070 | PS5-63-OB-3067A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-08-28 | PS5-10-02 | PS5 - Milestone D | 3 | Closed | 43 | 10 | AUGUST
T-131-3071 | PS5-40-UR-8113C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-03-26 | PS5-99-02 | PS5 - Milestone G | 6 | Closed | 12 | 16 | MARCH
T-975-3072 | PS5-10-UR-1149C | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone D | 3 | To be completed |  | 35 | SEPTEMBER
T-529-3073 | PS5-60-OB-7191C | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone D | 3 | On hold |  | 45 | NOVEMBER
T-128-3074 | PS5-92-UR-4096C | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-05-04 | PS5-09-02 | PS5 - Milestone I | 8 | Closed | 44 | 42 | MAY
T-948-3075 | PS5-08-OB-1779D | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone I | 8 | In progress |  | 45 | SEPTEMBER
T-180-3076 | PS5-63-OB-7760D | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone B | 1.1 | To be completed |  | 45 | OCTOBER
T-231-3077 | PS5-05-OB-7899B | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone I | 8 | To be completed |  | 17 | SEPTEMBER
T-857-3078 | PS5-86-IK-6101C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone I | 8 | To be completed |  | 32 | DECEMBER
T-857-3079 | PS5-90-OB-1446C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-07-13 | PS5-12-02 | PS5 - Milestone E | 4 | Closed | 14 | 43 | JULY
T-113-3080 | PS5-44-IK-7162A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone C | 2 | To be completed |  | 48 | DECEMBER
T-676-3081 | PS5-37-OB-3347D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-11-17 | PS5-04-03 | PS5 - Milestone F | 5 | Closed | 20 | 5 | NOVEMBER
T-985-3082 | PS5-54-OB-7300A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone I | 8 | To be completed |  | 36 | AUGUST
T-172-3083 | PS5-61-IK-4471D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone F | 5 | On hold |  | 37 | NOVEMBER
T-291-3084 | PS5-85-OB-2895C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone F | 5 | To be completed |  | 5 | AUGUST
T-953-3085 | PS5-49-OB-1019D | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | To be completed |  | 10 | NOVEMBER
T-370-3086 | PS5-24-OB-3123D | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-03-23 | PS5-06-03 | PS5 - Milestone C | 2 | Closed | 8 | 17 | MARCH
T-694-3087 | PS5-91-OB-7885B | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone I | 8 | To be completed |  | 16 | DECEMBER
T-289-3088 | PS5-86-OB-9455A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-01-02 | PS5-05-01 | PS5 - Milestone D | 3 | Closed | 23 | 10 | JANUARY
T-596-3089 | PS5-14-OB-6241A | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone H | 7 | In progress |  | 37 | OCTOBER
T-285-3090 | PS5-01-OB-3373D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone F | 5 | In progress |  | 31 | AUGUST
T-601-3091 | PS5-20-UR-5904B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | To be completed |  | 13 | NOVEMBER
T-603-3092 | PS5-95-UR-8829A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | In progress |  | 18 | NOVEMBER
T-970-3093 | PS5-77-UR-9236D | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-02-26 | PS5-60-07 | PS5 - Milestone B | 1.1 | Closed | 48 | 37 | FEBRUARY
T-307-3094 | PS5-98-IK-3013C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-12-17 | PS5-04-04 | PS5 - Milestone C | 2 | Closed | 5 | 21 | DECEMBER
T-085-3095 | PS5-46-UR-8791C | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone C | 2 | On hold |  | 44 | SEPTEMBER
T-727-3096 | PS5-28-UR-2491A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-04-10 | PS5-05-02 | PS5 - Milestone I | 8 | Closed | 20 | 34 | APRIL
T-930-3097 | PS5-88-OB-1690B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-10-13 | PS5-01-09 | PS5 - Milestone B | 1.1 | Closed | 19 | 35 | OCTOBER
T-960-3098 | PS5-29-OB-3511D | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone G | 6 | To be completed |  | 5 | AUGUST
T-952-3099 | PS5-20-OB-5868C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-19 | PS5-60-10 | PS5 - Milestone D | 3 | Closed | 11 | 12 | APRIL
T-228-3100 | PS5-09-OB-8736B | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone D | 3 | In progress |  | 22 | SEPTEMBER
T-954-3101 | PS5-80-IK-9168C | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone F | 5 | In progress |  | 28 | OCTOBER
T-217-3102 | PS5-69-OB-3857A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-01-16 | PS5-60-01 | PS5 - Milestone A | 1 | Closed | 21 | 8 | JANUARY
T-685-3103 | PS5-54-OB-4572B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone H | 7 | On hold |  | 16 | OCTOBER
T-200-3104 | PS5-20-IK-2917D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone F | 5 | In progress |  | 33 | NOVEMBER
T-943-3105 | PS5-06-IK-4010B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | On hold |  | 29 | NOVEMBER
T-803-3106 | PS5-71-UR-7308A | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-05-19 | PS5-10-03 | PS5 - Milestone B | 1.1 | Closed | 36 | 16 | MAY
T-110-3107 | PS5-72-OB-7982A | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-05-17 | PS5-04-02 | PS5 - Milestone B | 1.1 | Closed | 21 | 5 | MAY
T-794-3108 | PS5-03-OB-8311D | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone I | 8 | To be completed |  | 15 | SEPTEMBER
T-488-3109 | PS5-05-IK-7100C | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-04-06 | PS5-01-08 | PS5 - Milestone I | 8 | Closed | 17 | 33 | APRIL
T-010-3110 | PS5-44-UR-5382D | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone G | 6 | In progress |  | 26 | NOVEMBER
T-372-3111 | PS5-45-IK-6477D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone E | 4 | To be completed |  | 17 | DECEMBER
T-197-3112 | PS5-92-IK-8690A | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | To be completed |  | 4 | DECEMBER
T-701-3113 | PS5-37-OB-8693A | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone C | 2 | On hold |  | 13 | DECEMBER
T-224-3114 | PS5-07-OB-2096C | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | On hold |  | 30 | NOVEMBER
T-140-3115 | PS5-32-IK-3196C | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone G | 6 | On hold |  | 13 | NOVEMBER
T-726-3116 | PS5-53-UR-9640B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone F | 5 | In progress |  | 45 | NOVEMBER
T-361-3117 | PS5-65-OB-9220D | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | In progress |  | 47 | DECEMBER
T-566-3118 | PS5-70-OB-4122B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-04-18 | PS5-99-01 | PS5 - Milestone G | 6 | Closed | 13 | 15 | APRIL
T-846-3119 | PS5-51-IK-4570B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone D | 3 | In progress |  | 38 | AUGUST
T-883-3120 | PS5-21-IK-5699D | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-10-27 | PS5-10-02 | PS5 - Milestone A | 1 | Closed | 20 | 44 | OCTOBER
T-468-3121 | PS5-33-IK-5339B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-09-25 | PS5-02-03 | PS5 - Milestone C | 2 | Closed | 29 | 34 | SEPTEMBER
T-764-3122 | PS5-04-OB-2184A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone B | 1.1 | To be completed |  | 33 | AUGUST
T-025-3123 | PS5-63-IK-1469D | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | On hold |  | 21 | OCTOBER
T-212-3124 | PS5-79-OB-6019B | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone C | 2 | To be completed |  | 31 | AUGUST
T-218-3125 | PS5-80-OB-2841A | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | On hold |  | 44 | NOVEMBER
T-197-3126 | PS5-06-IK-6865A | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone D | 3 | In progress |  | 20 | NOVEMBER
T-128-3127 | PS5-85-UR-7845C | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-04-19 | PS5-04-02 | PS5 - Milestone E | 4 | Closed | 47 | 41 | APRIL
T-725-3128 | PS5-34-IK-8672D | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-06-09 | PS5-01-08 | PS5 - Milestone G | 6 | Closed | 45 | 42 | JUNE
T-673-3129 | PS5-92-IK-8449D | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone F | 5 | In progress |  | 47 | NOVEMBER
T-181-3130 | PS5-72-OB-4241D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | In progress |  | 6 | DECEMBER
T-649-3131 | PS5-81-OB-9382C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone B | 1.1 | In progress |  | 24 | OCTOBER
T-531-3132 | PS5-42-OB-9245C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-08-26 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 19 | 26 | AUGUST
T-629-3133 | PS5-68-OB-2214C | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-04-08 | PS5-01-02 | PS5 - Milestone F | 5 | Closed | 17 | 38 | APRIL
T-400-3134 | PS5-82-OB-7627C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone B | 1.1 | To be completed |  | 35 | OCTOBER
T-026-3135 | PS5-02-OB-7626D | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-04-17 | PS5-03-01 | PS5 - Milestone I | 8 | Closed | 12 | 12 | APRIL
T-644-3136 | PS5-75-IK-6784D | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-03-07 | PS5-03-03 | PS5 - Milestone G | 6 | Closed | 20 | 48 | MARCH
T-147-3137 | PS5-02-IK-9277B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone C | 2 | To be completed |  | 14 | NOVEMBER
T-814-3138 | PS5-22-OB-5896A | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone F | 5 | To be completed |  | 13 | NOVEMBER
T-668-3139 | PS5-55-OB-6190B | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | To be completed |  | 34 | OCTOBER
T-669-3140 | PS5-87-UR-4833B | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone H | 7 | In progress |  | 30 | SEPTEMBER
T-823-3141 | PS5-51-IK-6323A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone H | 7 | To be completed |  | 16 | DECEMBER
T-180-3142 | PS5-96-OB-9054A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | In progress |  | 34 | AUGUST
T-979-3143 | PS5-15-UR-8290A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone B | 1.1 | To be completed |  | 46 | AUGUST
T-648-3144 | PS5-06-UR-3879C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-08-14 | PS5-11-01 | PS5 - Milestone F | 5 | Closed | 39 | 22 | AUGUST
T-300-3145 | PS5-79-IK-3887A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone B | 1.1 | In progress |  | 32 | SEPTEMBER
T-440-3146 | PS5-71-UR-2328B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone C | 2 | To be completed |  | 48 | SEPTEMBER
T-868-3147 | PS5-40-IK-2866B | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-01-03 | PS5-61-01 | PS5 - Milestone H | 7 | Closed | 26 | 22 | JANUARY
T-324-3148 | PS5-20-UR-5153C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-08-23 | PS5-06-02 | PS5 - Milestone G | 6 | Closed | 16 | 47 | AUGUST
T-966-3149 | PS5-02-IK-9574B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-10-22 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 35 | 20 | OCTOBER
T-420-3150 | PS5-75-UR-1064D | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | To be completed |  | 33 | OCTOBER
T-653-3151 | PS5-69-UR-2952A | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-03-12 | PS5-01-04 | PS5 - Milestone A | 1 | Closed | 48 | 18 | MARCH
T-977-3152 | PS5-26-IK-4179B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone G | 6 | In progress |  | 25 | NOVEMBER
T-010-3153 | PS5-38-IK-3609B | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | To be completed |  | 46 | OCTOBER
T-441-3154 | PS5-59-UR-9978D | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | In progress |  | 23 | OCTOBER
T-905-3155 | PS5-46-OB-4202D | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone B | 1.1 | In progress |  | 22 | OCTOBER
T-975-3156 | PS5-41-UR-9225D | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-08-03 | PS5-04-01 | PS5 - Milestone E | 4 | Closed | 8 | 25 | AUGUST
T-453-3157 | PS5-86-IK-4287B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone I | 8 | In progress |  | 24 | OCTOBER
T-932-3158 | PS5-24-IK-1357A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-11-07 | PS5-12-01 | PS5 - Milestone G | 6 | Closed | 22 | 29 | NOVEMBER
T-491-3159 | PS5-11-OB-5845A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | In progress |  | 22 | SEPTEMBER
T-391-3160 | PS5-23-OB-2130B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone H | 7 | In progress |  | 47 | DECEMBER
T-868-3161 | PS5-99-OB-1987C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone E | 4 | To be completed |  | 23 | DECEMBER
T-650-3162 | PS5-76-OB-4636B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-03-08 | PS5-06-03 | PS5 - Milestone B | 1.1 | Closed | 42 | 11 | MARCH
T-158-3163 | PS5-12-OB-6061A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone A | 1 | To be completed |  | 13 | OCTOBER
T-528-3164 | PS5-10-OB-3606D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone G | 6 | To be completed |  | 26 | DECEMBER
T-429-3165 | PS5-81-OB-6808D | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-11-23 | PS5-06-01 | PS5 - Milestone F | 5 | Closed | 43 | 19 | NOVEMBER
T-912-3166 | PS5-75-IK-5840D | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-03-25 | PS5-60-07 | PS5 - Milestone F | 5 | Closed | 19 | 23 | MARCH
T-908-3167 | PS5-07-IK-6340A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone I | 8 | To be completed |  | 48 | NOVEMBER
T-221-3168 | PS5-36-OB-9612D | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-03-09 | PS5-61-02 | PS5 - Milestone B | 1.1 | Closed | 21 | 17 | MARCH
T-205-3169 | PS5-11-IK-3774D | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone E | 4 | To be completed |  | 19 | SEPTEMBER
T-567-3170 | PS5-48-IK-7250A | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone D | 3 | To be completed |  | 6 | SEPTEMBER
T-388-3171 | PS5-23-IK-9026B | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone D | 3 | To be completed |  | 35 | DECEMBER
T-178-3172 | PS5-36-UR-1636D | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-05-11 | PS5-09-04 | PS5 - Milestone I | 8 | Closed | 47 | 42 | MAY
T-545-3173 | PS5-41-UR-3420D | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone C | 2 | To be completed |  | 17 | NOVEMBER
T-630-3174 | PS5-94-OB-8576D | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | In progress |  | 46 | OCTOBER
T-109-3175 | PS5-03-OB-1525D | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone I | 8 | To be completed |  | 47 | AUGUST
T-303-3176 | PS5-35-OB-5144D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone C | 2 | In progress |  | 40 | SEPTEMBER
T-497-3177 | PS5-17-UR-8765B | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-03-02 | PS5-05-03 | PS5 - Milestone B | 1.1 | Closed | 40 | 8 | MARCH
T-783-3178 | PS5-58-OB-5174C | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-06-04 | PS5-82-02 | PS5 - Milestone C | 2 | Closed | 42 | 16 | JUNE
T-722-3179 | PS5-64-IK-5341D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone C | 2 | To be completed |  | 11 | AUGUST
T-461-3180 | PS5-96-OB-7655C | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone H | 7 | To be completed |  | 9 | DECEMBER
T-783-3181 | PS5-81-IK-8989A | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone H | 7 | On hold |  | 26 | DECEMBER
T-422-3182 | PS5-63-OB-7219B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone B | 1.1 | To be completed |  | 13 | NOVEMBER
T-119-3183 | PS5-66-OB-6023B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-01-15 | PS5-60-10 | PS5 - Milestone G | 6 | Closed | 8 | 5 | JANUARY
T-335-3184 | PS5-26-IK-9398D | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | In progress |  | 31 | SEPTEMBER
T-709-3185 | PS5-35-OB-1668A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-03-26 | PS5-07-01 | PS5 - Milestone I | 8 | Closed | 32 | 7 | MARCH
T-871-3186 | PS5-03-UR-3171D | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone D | 3 | On hold |  | 42 | DECEMBER
T-381-3187 | PS5-47-UR-6850A | CQS03 - Deluge System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-02-16 | PS5-12-02 | PS5 - Milestone I | 8 | Closed | 4 | 25 | FEBRUARY
T-250-3188 | PS5-39-UR-5217B | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone F | 5 | To be completed |  | 9 | SEPTEMBER
T-124-3189 | PS5-35-IK-4576C | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-11-09 | PS5-12-01 | PS5 - Milestone D | 3 | Closed | 47 | 7 | NOVEMBER
T-333-3190 | PS5-13-OB-1474C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-11-09 | PS5-82-07 | PS5 - Milestone A | 1 | Closed | 9 | 44 | NOVEMBER
T-722-3191 | PS5-48-OB-3328C | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone E | 4 | To be completed |  | 37 | AUGUST
T-563-3192 | PS5-23-IK-4594A | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone H | 7 | In progress |  | 11 | OCTOBER
T-888-3193 | PS5-96-OB-3449C | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone G | 6 | To be completed |  | 17 | DECEMBER
T-540-3194 | PS5-57-OB-8552C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone G | 6 | To be completed |  | 42 | DECEMBER
T-392-3195 | PS5-03-OB-1339B | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone E | 4 | To be completed |  | 34 | OCTOBER
T-020-3196 | PS5-64-IK-4081B | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone C | 2 | To be completed |  | 44 | AUGUST
T-942-3197 | PS5-59-OB-5173B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-08-24 | PS5-10-06 | PS5 - Milestone A | 1 | Closed | 35 | 28 | AUGUST
T-726-3198 | PS5-97-UR-9297A | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-05-18 | PS5-02-02 | PS5 - Milestone E | 4 | Closed | 21 | 28 | MAY
T-421-3199 | PS5-73-OB-3680B | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-05-19 | PS5-99-01 | PS5 - Milestone G | 6 | Closed | 38 | 9 | MAY
T-730-3200 | PS5-29-OB-4021D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone E | 4 | To be completed |  | 36 | DECEMBER
T-644-3201 | PS5-08-UR-2529A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-12-03 | PS5-06-03 | PS5 - Milestone C | 2 | Closed | 42 | 9 | DECEMBER
T-736-3202 | PS5-69-OB-4198D | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | On hold |  | 13 | OCTOBER
T-497-3203 | PS5-73-IK-2056A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-08-11 | PS5-02-01 | PS5 - Milestone H | 7 | Closed | 12 | 39 | AUGUST
T-478-3204 | PS5-77-OB-2800B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-03-14 | PS5-63-01 | PS5 - Milestone A | 1 | Closed | 28 | 48 | MARCH
T-692-3205 | PS5-11-OB-6864A | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-03-06 | PS5-03-01 | PS5 - Milestone E | 4 | Closed | 26 | 16 | MARCH
T-490-3206 | PS5-96-IK-6816D | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-10-28 | PS5-01-04 | PS5 - Milestone G | 6 | Closed | 12 | 24 | OCTOBER
T-444-3207 | PS5-69-OB-8974A | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-09-25 | PS5-05-01 | PS5 - Milestone H | 7 | Closed | 39 | 21 | SEPTEMBER
T-758-3208 | PS5-55-OB-2211B | CQM04 - Vessel | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone G | 6 | On hold |  | 7 | SEPTEMBER
T-688-3209 | PS5-68-OB-8294D | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone D | 3 | To be completed |  | 18 | SEPTEMBER
T-135-3210 | PS5-33-OB-2631C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone C | 2 | On hold |  | 17 | DECEMBER
T-009-3211 | PS5-44-OB-5357C | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-03-10 | PS5-04-04 | PS5 - Milestone E | 4 | Closed | 38 | 7 | MARCH
T-263-3212 | PS5-24-UR-7783D | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone D | 3 | On hold |  | 20 | OCTOBER
T-278-3213 | PS5-06-OB-9285A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone A | 1 | To be completed |  | 31 | AUGUST
T-700-3214 | PS5-31-IK-6620D | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone C | 2 | In progress |  | 38 | DECEMBER
T-681-3215 | PS5-34-UR-3537B | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-07-28 | PS5-62-01 | PS5 - Milestone D | 3 | Closed | 32 | 26 | JULY
T-938-3216 | PS5-63-UR-6494C | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone H | 7 | In progress |  | 32 | AUGUST
T-040-3217 | PS5-24-OB-5304B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-08-28 | PS5-04-04 | PS5 - Milestone E | 4 | Closed | 27 | 24 | AUGUST
T-128-3218 | PS5-69-IK-6460C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-04-26 | PS5-02-02 | PS5 - Milestone E | 4 | Closed | 22 | 16 | APRIL
T-700-3219 | PS5-51-OB-9518D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone A | 1 | In progress |  | 33 | NOVEMBER
T-362-3220 | PS5-35-UR-2038B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-21 | PS5-60-01 | PS5 - Milestone D | 3 | Closed | 32 | 48 | APRIL
T-883-3221 | PS5-85-OB-8124C | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-03-28 | PS5-09-03 | PS5 - Milestone A | 1 | Closed | 29 | 20 | MARCH
T-211-3222 | PS5-26-OB-4161D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone E | 4 | To be completed |  | 27 | NOVEMBER
T-212-3223 | PS5-87-OB-3366C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | In progress |  | 25 | OCTOBER
T-898-3224 | PS5-91-OB-4353C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-10-18 | PS5-61-07 | PS5 - Milestone E | 4 | Closed | 18 | 22 | OCTOBER
T-778-3225 | PS5-64-OB-8953B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | In progress |  | 39 | OCTOBER
T-578-3226 | PS5-31-IK-3185B | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone G | 6 | In progress |  | 5 | SEPTEMBER
T-402-3227 | PS5-45-UR-8415A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone B | 1.1 | To be completed |  | 7 | SEPTEMBER
T-010-3228 | PS5-16-UR-5905C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone D | 3 | To be completed |  | 39 | DECEMBER
T-720-3229 | PS5-16-IK-2531B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | To be completed |  | 36 | NOVEMBER
T-831-3230 | PS5-04-UR-2920D | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone I | 8 | On hold |  | 38 | AUGUST
T-150-3231 | PS5-75-OB-5598A | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone B | 1.1 | To be completed |  | 15 | OCTOBER
T-214-3232 | PS5-82-OB-4306A | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-07-27 | PS5-10-01 | PS5 - Milestone G | 6 | Closed | 41 | 6 | JULY
T-240-3233 | PS5-28-OB-5599B | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-02-01 | PS5-05-03 | PS5 - Milestone B | 1.1 | Closed | 16 | 5 | FEBRUARY
T-915-3234 | PS5-05-OB-8628B | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone G | 6 | On hold |  | 40 | OCTOBER
T-079-3235 | PS5-92-OB-6487B | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-02-20 | PS5-11-02 | PS5 - Milestone C | 2 | Closed | 20 | 11 | FEBRUARY
T-278-3236 | PS5-42-OB-3676D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-03-08 | PS5-62-01 | PS5 - Milestone D | 3 | Closed | 27 | 44 | MARCH
T-438-3237 | PS5-51-OB-1763D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone C | 2 | In progress |  | 40 | DECEMBER
T-592-3238 | PS5-44-OB-8421D | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-11-21 | PS5-10-05 | PS5 - Milestone E | 4 | Closed | 23 | 41 | NOVEMBER
T-640-3239 | PS5-33-UR-8759D | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-07-03 | PS5-06-01 | PS5 - Milestone H | 7 | Closed | 42 | 6 | JULY
T-844-3240 | PS5-01-UR-1773D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-03-17 | PS5-03-03 | PS5 - Milestone D | 3 | Closed | 46 | 29 | MARCH
T-423-3241 | PS5-05-OB-6676D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-17 | PS5-60-04 | PS5 - Milestone A | 1 | Closed | 20 | 19 | JULY
T-309-3242 | PS5-54-IK-4430C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone I | 8 | On hold |  | 15 | OCTOBER
T-595-3243 | PS5-79-IK-4695B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone I | 8 | On hold |  | 28 | NOVEMBER
T-566-3244 | PS5-40-OB-1667A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-12-12 | PS5-01-04 | PS5 - Milestone E | 4 | Closed | 23 | 12 | DECEMBER
T-485-3245 | PS5-66-IK-4722C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | In progress |  | 27 | OCTOBER
T-790-3246 | PS5-46-UR-9680D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | To be completed |  | 6 | OCTOBER
T-547-3247 | PS5-96-OB-5011A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-12-15 | PS5-63-01 | PS5 - Milestone D | 3 | Closed | 21 | 10 | DECEMBER
T-204-3248 | PS5-69-OB-7587B | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone D | 3 | In progress |  | 12 | SEPTEMBER
T-438-3249 | PS5-38-IK-4374A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone C | 2 | To be completed |  | 27 | DECEMBER
T-957-3250 | PS5-58-OB-9790C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-02-20 | PS5-10-03 | PS5 - Milestone H | 7 | Closed | 15 | 37 | FEBRUARY
T-278-3251 | PS5-82-OB-9870C | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone D | 3 | To be completed |  | 37 | AUGUST
T-327-3252 | PS5-99-OB-5057D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | On hold |  | 5 | NOVEMBER
T-664-3253 | PS5-12-OB-5865A | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone C | 2 | To be completed |  | 25 | DECEMBER
T-493-3254 | PS5-31-IK-6643C | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | To be completed |  | 45 | OCTOBER
T-579-3255 | PS5-71-OB-4850A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-04-10 | PS5-99-02 | PS5 - Milestone G | 6 | Closed | 9 | 40 | APRIL
T-280-3256 | PS5-86-OB-2608A | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone H | 7 | To be completed |  | 17 | SEPTEMBER
T-041-3257 | PS5-57-IK-1741B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-09-25 | PS5-04-04 | PS5 - Milestone G | 6 | Closed | 7 | 40 | SEPTEMBER
T-706-3258 | PS5-43-IK-5058A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-05-11 | PS5-10-04 | PS5 - Milestone B | 1.1 | Closed | 34 | 48 | MAY
T-957-3259 | PS5-26-OB-7206A | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone F | 5 | In progress |  | 5 | DECEMBER
T-242-3260 | PS5-74-IK-2778D | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone I | 8 | On hold |  | 35 | AUGUST
T-390-3261 | PS5-23-UR-3948B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-01-17 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 9 | 19 | JANUARY
T-082-3262 | PS5-17-IK-5402A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | To be completed |  | 25 | SEPTEMBER
T-107-3263 | PS5-58-UR-6806D | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-04-20 | PS5-03-03 | PS5 - Milestone G | 6 | Closed | 12 | 27 | APRIL
T-233-3264 | PS5-82-OB-8499C | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | To be completed |  | 27 | OCTOBER
T-020-3265 | PS5-77-UR-9282A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-07-01 | PS5-62-02 | PS5 - Milestone C | 2 | Closed | 27 | 24 | JULY
T-071-3266 | PS5-19-IK-5191D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone F | 5 | In progress |  | 23 | AUGUST
T-491-3267 | PS5-36-OB-4529C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone B | 1.1 | In progress |  | 48 | DECEMBER
T-413-3268 | PS5-20-OB-2592A | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone E | 4 | To be completed |  | 46 | OCTOBER
T-448-3269 | PS5-55-UR-3119C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | In progress |  | 21 | DECEMBER
T-449-3270 | PS5-09-OB-7242A | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone F | 5 | On hold |  | 25 | DECEMBER
T-154-3271 | PS5-40-OB-8916D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone G | 6 | On hold |  | 35 | DECEMBER
T-577-3272 | PS5-48-OB-7038C | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | On hold |  | 39 | DECEMBER
T-953-3273 | PS5-87-UR-1403A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-05-19 | PS5-07-01 | PS5 - Milestone C | 2 | Closed | 30 | 10 | MAY
T-462-3274 | PS5-62-UR-5786A | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-02-11 | PS5-09-04 | PS5 - Milestone D | 3 | Closed | 48 | 30 | FEBRUARY
T-175-3275 | PS5-53-OB-9787A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-09-06 | PS5-12-01 | PS5 - Milestone A | 1 | Closed | 16 | 48 | SEPTEMBER
T-994-3276 | PS5-50-UR-1629D | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | To be completed |  | 48 | NOVEMBER
T-054-3277 | PS5-33-OB-7767D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-09-19 | PS5-01-08 | PS5 - Milestone E | 4 | Closed | 27 | 32 | SEPTEMBER
T-560-3278 | PS5-09-OB-9292B | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-10-13 | PS5-61-01 | PS5 - Milestone B | 1.1 | Closed | 44 | 29 | OCTOBER
T-178-3279 | PS5-55-UR-5578B | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-09-18 | PS5-03-03 | PS5 - Milestone F | 5 | Closed | 21 | 46 | SEPTEMBER
T-101-3280 | PS5-67-UR-6890D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone D | 3 | To be completed |  | 39 | NOVEMBER
T-887-3281 | PS5-53-IK-1085B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-01-03 | PS5-03-23 | PS5 - Milestone H | 7 | Closed | 24 | 34 | JANUARY
T-896-3282 | PS5-46-OB-1243D | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone F | 5 | In progress |  | 8 | NOVEMBER
T-778-3283 | PS5-68-OB-5139C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone I | 8 | In progress |  | 41 | OCTOBER
T-994-3284 | PS5-64-IK-2458B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone D | 3 | To be completed |  | 29 | SEPTEMBER
T-208-3285 | PS5-89-OB-4032D | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-02-22 | PS5-03-01 | PS5 - Milestone H | 7 | Closed | 35 | 28 | FEBRUARY
T-716-3286 | PS5-82-IK-2084B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone D | 3 | On hold |  | 10 | NOVEMBER
T-153-3287 | PS5-06-OB-3922A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-09-19 | PS5-11-01 | PS5 - Milestone E | 4 | Closed | 40 | 21 | SEPTEMBER
T-723-3288 | PS5-99-IK-8377D | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone H | 7 | To be completed |  | 8 | DECEMBER
T-922-3289 | PS5-71-OB-8014A | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-03-01 | PS5-03-02 | PS5 - Milestone G | 6 | Closed | 21 | 4 | MARCH
T-051-3290 | PS5-40-UR-8409C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone H | 7 | In progress |  | 46 | AUGUST
T-755-3291 | PS5-47-OB-6872C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone E | 4 | On hold |  | 42 | NOVEMBER
T-546-3292 | PS5-62-UR-5466A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | To be completed |  | 33 | DECEMBER
T-068-3293 | PS5-48-UR-1169D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone I | 8 | In progress |  | 27 | NOVEMBER
T-751-3294 | PS5-84-UR-8289C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone I | 8 | In progress |  | 29 | DECEMBER
T-679-3295 | PS5-63-UR-2091D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone A | 1 | To be completed |  | 48 | OCTOBER
T-627-3296 | PS5-51-IK-3496C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-04-16 | PS5-01-03 | PS5 - Milestone I | 8 | Closed | 22 | 7 | APRIL
T-154-3297 | PS5-94-UR-9614B | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone H | 7 | In progress |  | 24 | DECEMBER
T-088-3298 | PS5-76-UR-3867D | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-10-26 | PS5-01-03 | PS5 - Milestone A | 1 | Closed | 39 | 40 | OCTOBER
T-732-3299 | PS5-34-UR-8347D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone F | 5 | In progress |  | 8 | NOVEMBER
T-893-3300 | PS5-51-UR-3028B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-12-02 | PS5-63-04 | PS5 - Milestone I | 8 | Closed | 14 | 42 | DECEMBER
T-989-3301 | PS5-50-UR-3305B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-12-23 | PS5-02-01 | PS5 - Milestone E | 4 | Closed | 28 | 7 | DECEMBER
T-762-3302 | PS5-05-OB-3546B | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone A | 1 | To be completed |  | 27 | DECEMBER
T-598-3303 | PS5-62-OB-9838B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-11-04 | PS5-08-02 | PS5 - Milestone E | 4 | Closed | 15 | 31 | NOVEMBER
T-919-3304 | PS5-02-IK-5834A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-06-23 | PS5-61-01 | PS5 - Milestone F | 5 | Closed | 13 | 21 | JUNE
T-805-3305 | PS5-94-UR-2678C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone F | 5 | To be completed |  | 27 | DECEMBER
T-548-3306 | PS5-86-UR-9820D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-11-06 | PS5-08-02 | PS5 - Milestone H | 7 | Closed | 25 | 15 | NOVEMBER
T-027-3307 | PS5-23-IK-5613A | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-08-28 | PS5-10-02 | PS5 - Milestone F | 5 | Closed | 10 | 22 | AUGUST
T-171-3308 | PS5-14-OB-9539D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-09-17 | PS5-05-03 | PS5 - Milestone A | 1 | Closed | 23 | 8 | SEPTEMBER
T-549-3309 | PS5-43-UR-9353B | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-09-13 | PS5-01-07 | PS5 - Milestone F | 5 | Closed | 25 | 22 | SEPTEMBER
T-481-3310 | PS5-21-OB-7008C | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-05-16 | PS5-05-01 | PS5 - Milestone I | 8 | Closed | 27 | 36 | MAY
T-693-3311 | PS5-14-UR-2780A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-04-15 | PS5-10-04 | PS5 - Milestone C | 2 | Closed | 11 | 10 | APRIL
T-048-3312 | PS5-23-OB-6440B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone D | 3 | To be completed |  | 12 | NOVEMBER
T-659-3313 | PS5-63-OB-7221C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone E | 4 | In progress |  | 5 | NOVEMBER
T-267-3314 | PS5-46-OB-5122A | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone H | 7 | To be completed |  | 31 | OCTOBER
T-603-3315 | PS5-47-OB-9828C | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-05-26 | PS5-82-07 | PS5 - Milestone B | 1.1 | Closed | 42 | 8 | MAY
T-904-3316 | PS5-10-OB-8406C | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone C | 2 | To be completed |  | 20 | SEPTEMBER
T-537-3317 | PS5-62-OB-9695A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-02-08 | PS5-60-07 | PS5 - Milestone A | 1 | Closed | 17 | 8 | FEBRUARY
T-801-3318 | PS5-81-OB-8882D | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone H | 7 | To be completed |  | 24 | SEPTEMBER
T-035-3319 | PS5-90-OB-1483C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone G | 6 | To be completed |  | 47 | OCTOBER
T-528-3320 | PS5-65-OB-7762D | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-01-14 | PS5-12-01 | PS5 - Milestone I | 8 | Closed | 20 | 40 | JANUARY
T-214-3321 | PS5-13-OB-7909A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-09-23 | PS5-08-01 | PS5 - Milestone G | 6 | Closed | 7 | 41 | SEPTEMBER
T-983-3322 | PS5-44-IK-4221C | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | In progress |  | 9 | NOVEMBER
T-917-3323 | PS5-32-OB-8939D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-07-11 | PS5-01-05 | PS5 - Milestone E | 4 | Closed | 20 | 26 | JULY
T-282-3324 | PS5-99-OB-7924A | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | On hold |  | 48 | OCTOBER
T-466-3325 | PS5-50-UR-1136A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-01-11 | PS5-10-05 | PS5 - Milestone F | 5 | Closed | 6 | 36 | JANUARY
T-240-3326 | PS5-12-OB-2877C | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | On hold |  | 42 | NOVEMBER
T-343-3327 | PS5-87-OB-6468D | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-10-12 | PS5-06-02 | PS5 - Milestone F | 5 | Closed | 23 | 46 | OCTOBER
T-371-3328 | PS5-70-IK-2014D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone C | 2 | In progress |  | 10 | OCTOBER
T-697-3329 | PS5-51-UR-6238C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone B | 1.1 | On hold |  | 6 | DECEMBER
T-183-3330 | PS5-69-OB-3963D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-03-13 | PS5-01-03 | PS5 - Milestone D | 3 | Closed | 27 | 29 | MARCH
T-225-3331 | PS5-98-OB-6507C | CQP04 - Hydrotest | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | To be completed |  | 45 | SEPTEMBER
T-446-3332 | PS5-85-UR-4301A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-02-14 | PS5-02-03 | PS5 - Milestone G | 6 | Closed | 18 | 7 | FEBRUARY
T-181-3333 | PS5-75-OB-4897A | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone H | 7 | In progress |  | 27 | SEPTEMBER
T-407-3334 | PS5-47-OB-7118D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone F | 5 | In progress |  | 22 | OCTOBER
T-180-3335 | PS5-36-OB-4573A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone F | 5 | To be completed |  | 15 | SEPTEMBER
T-111-3336 | PS5-57-UR-8213D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-04-21 | PS5-06-01 | PS5 - Milestone I | 8 | Closed | 23 | 27 | APRIL
T-807-3337 | PS5-15-OB-5582B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-08-09 | PS5-11-02 | PS5 - Milestone I | 8 | Closed | 8 | 7 | AUGUST
T-558-3338 | PS5-75-OB-1088B | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-05-23 | PS5-06-02 | PS5 - Milestone G | 6 | Closed | 19 | 18 | MAY
T-620-3339 | PS5-32-UR-7190C | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-05-13 | PS5-12-02 | PS5 - Milestone I | 8 | Closed | 48 | 18 | MAY
T-682-3340 | PS5-93-UR-6629C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-05-03 | PS5-03-03 | PS5 - Milestone B | 1.1 | Closed | 35 | 47 | MAY
T-716-3341 | PS5-53-OB-9322C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-10-06 | PS5-08-01 | PS5 - Milestone B | 1.1 | Closed | 19 | 26 | OCTOBER
T-466-3342 | PS5-75-IK-1720A | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone I | 8 | To be completed |  | 36 | NOVEMBER
T-781-3343 | PS5-70-OB-7431C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone D | 3 | To be completed |  | 23 | OCTOBER
T-795-3344 | PS5-05-UR-5408A | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone A | 1 | In progress |  | 45 | SEPTEMBER
T-792-3345 | PS5-88-OB-5166D | CQE04 - Transformer | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-09-23 | PS5-82-07 | PS5 - Milestone I | 8 | Closed | 31 | 41 | SEPTEMBER
T-692-3346 | PS5-20-IK-4025B | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-02-01 | PS5-01-02 | PS5 - Milestone B | 1.1 | Closed | 8 | 35 | FEBRUARY
T-291-3347 | PS5-51-UR-1842C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | To be completed |  | 44 | DECEMBER
T-136-3348 | PS5-04-UR-3739C | CQE04 - Transformer | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-05-23 | PS5-62-02 | PS5 - Milestone H | 7 | Closed | 38 | 27 | MAY
T-546-3349 | PS5-46-IK-1832C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-02-05 | PS5-04-04 | PS5 - Milestone I | 8 | Closed | 39 | 7 | FEBRUARY
T-931-3350 | PS5-23-OB-8470B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-03-23 | PS5-63-04 | PS5 - Milestone F | 5 | Closed | 42 | 32 | MARCH
T-654-3351 | PS5-59-OB-9789C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-01-27 | PS5-02-02 | PS5 - Milestone H | 7 | Closed | 23 | 20 | JANUARY
T-836-3352 | PS5-77-OB-2750B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | To be completed |  | 17 | DECEMBER
T-281-3353 | PS5-99-UR-6360A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | To be completed |  | 22 | OCTOBER
T-117-3354 | PS5-79-UR-8540B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone A | 1 | To be completed |  | 44 | NOVEMBER
T-280-3355 | PS5-94-OB-6008B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-11-20 | PS5-05-03 | PS5 - Milestone I | 8 | Closed | 41 | 40 | NOVEMBER
T-738-3356 | PS5-70-OB-9281D | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-11-01 | PS5-09-01 | PS5 - Milestone D | 3 | Closed | 40 | 25 | NOVEMBER
T-833-3357 | PS5-52-OB-1337B | CQE01 - HV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone F | 5 | To be completed |  | 26 | OCTOBER
T-641-3358 | PS5-94-UR-7041B | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone I | 8 | On hold |  | 32 | SEPTEMBER
T-491-3359 | PS5-28-OB-8336A | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-01-17 | PS5-09-02 | PS5 - Milestone B | 1.1 | Closed | 14 | 24 | JANUARY
T-818-3360 | PS5-58-UR-1148B | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-22 | PS5-60-04 | PS5 - Milestone F | 5 | Closed | 28 | 27 | APRIL
T-068-3361 | PS5-18-IK-1776A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-03-25 | PS5-09-03 | PS5 - Milestone G | 6 | Closed | 15 | 29 | MARCH
T-969-3362 | PS5-57-IK-3958A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | On hold |  | 45 | DECEMBER
T-656-3363 | PS5-99-IK-5981A | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone A | 1 | In progress |  | 48 | AUGUST
T-282-3364 | PS5-84-UR-4502B | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | In progress |  | 36 | NOVEMBER
T-078-3365 | PS5-10-UR-6895C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone B | 1.1 | To be completed |  | 44 | SEPTEMBER
T-687-3366 | PS5-79-OB-2009A | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-01-06 | PS5-12-01 | PS5 - Milestone H | 7 | Closed | 10 | 40 | JANUARY
T-014-3367 | PS5-57-OB-1657C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-12-28 | PS5-01-04 | PS5 - Milestone F | 5 | Closed | 35 | 41 | DECEMBER
T-065-3368 | PS5-05-UR-1616B | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone E | 4 | In progress |  | 28 | SEPTEMBER
T-569-3369 | PS5-86-UR-8671B | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | To be completed |  | 7 | SEPTEMBER
T-086-3370 | PS5-27-UR-1781C | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-06-23 | PS5-01-04 | PS5 - Milestone B | 1.1 | Closed | 16 | 17 | JUNE
T-843-3371 | PS5-62-IK-3772B | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | In progress |  | 48 | OCTOBER
T-439-3372 | PS5-21-OB-6677D | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone D | 3 | To be completed |  | 12 | NOVEMBER
T-149-3373 | PS5-57-IK-9114C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-08-25 | PS5-10-04 | PS5 - Milestone A | 1 | Closed | 30 | 38 | AUGUST
T-982-3374 | PS5-40-UR-9351D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | On hold |  | 28 | OCTOBER
T-466-3375 | PS5-17-OB-6821D | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone G | 6 | On hold |  | 10 | AUGUST
T-838-3376 | PS5-63-IK-7620D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-09-13 | PS5-03-02 | PS5 - Milestone D | 3 | Closed | 12 | 14 | SEPTEMBER
T-424-3377 | PS5-73-OB-8902B | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone F | 5 | In progress |  | 16 | SEPTEMBER
T-709-3378 | PS5-76-IK-9755C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone C | 2 | On hold |  | 32 | OCTOBER
T-258-3379 | PS5-94-OB-9303C | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-09-12 | PS5-60-10 | PS5 - Milestone H | 7 | Closed | 39 | 9 | SEPTEMBER
T-440-3380 | PS5-99-IK-1779C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-04-07 | PS5-10-05 | PS5 - Milestone A | 1 | Closed | 40 | 25 | APRIL
T-756-3381 | PS5-42-OB-1749B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone E | 4 | In progress |  | 9 | DECEMBER
T-127-3382 | PS5-39-OB-3554B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-10-16 | PS5-63-04 | PS5 - Milestone H | 7 | Closed | 41 | 27 | OCTOBER
T-921-3383 | PS5-18-OB-3944B | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-07-11 | PS5-01-06 | PS5 - Milestone F | 5 | Closed | 43 | 5 | JULY
T-618-3384 | PS5-06-IK-4463B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone G | 6 | In progress |  | 47 | SEPTEMBER
T-053-3385 | PS5-61-UR-2718D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone E | 4 | On hold |  | 30 | AUGUST
T-495-3386 | PS5-84-OB-3859C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone G | 6 | In progress |  | 14 | OCTOBER
T-900-3387 | PS5-75-OB-1373B | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | To be completed |  | 8 | OCTOBER
T-907-3388 | PS5-25-OB-1359C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone D | 3 | In progress |  | 47 | DECEMBER
T-154-3389 | PS5-10-IK-7899B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | To be completed |  | 13 | OCTOBER
T-963-3390 | PS5-05-OB-4446B | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-04-24 | PS5-82-07 | PS5 - Milestone D | 3 | Closed | 30 | 34 | APRIL
T-356-3391 | PS5-58-UR-9059D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-05-19 | PS5-10-04 | PS5 - Milestone A | 1 | Closed | 27 | 27 | MAY
T-555-3392 | PS5-38-OB-8140C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-01-10 | PS5-02-01 | PS5 - Milestone G | 6 | Closed | 11 | 44 | JANUARY
T-161-3393 | PS5-74-OB-4471C | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone H | 7 | In progress |  | 12 | SEPTEMBER
T-546-3394 | PS5-29-OB-6186D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone F | 5 | In progress |  | 12 | SEPTEMBER
T-851-3395 | PS5-08-IK-5329C | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | In progress |  | 22 | AUGUST
T-219-3396 | PS5-60-OB-1300C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-06-13 | PS5-62-01 | PS5 - Milestone I | 8 | Closed | 36 | 41 | JUNE
T-128-3397 | PS5-64-UR-1899B | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone E | 4 | In progress |  | 35 | SEPTEMBER
T-862-3398 | PS5-20-IK-7391A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone H | 7 | To be completed |  | 36 | NOVEMBER
T-750-3399 | PS5-24-OB-8846A | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone C | 2 | In progress |  | 15 | SEPTEMBER
T-064-3400 | PS5-58-UR-9417C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone I | 8 | To be completed |  | 26 | NOVEMBER
T-932-3401 | PS5-29-UR-7622C | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | To be completed |  | 8 | SEPTEMBER
T-796-3402 | PS5-12-IK-8107C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-10-19 | PS5-05-01 | PS5 - Milestone F | 5 | Closed | 43 | 29 | OCTOBER
T-825-3403 | PS5-70-UR-5291D | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone H | 7 | In progress |  | 17 | OCTOBER
T-547-3404 | PS5-93-OB-1104C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-05-10 | PS5-04-01 | PS5 - Milestone I | 8 | Closed | 29 | 37 | MAY
T-840-3405 | PS5-27-UR-7059B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-09-28 | PS5-04-03 | PS5 - Milestone B | 1.1 | Closed | 28 | 26 | SEPTEMBER
T-932-3406 | PS5-05-OB-4901C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-01-28 | PS5-11-03 | PS5 - Milestone C | 2 | Closed | 5 | 32 | JANUARY
T-231-3407 | PS5-10-UR-9624A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-01-27 | PS5-03-03 | PS5 - Milestone C | 2 | Closed | 13 | 42 | JANUARY
T-039-3408 | PS5-64-OB-4971D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone H | 7 | In progress |  | 44 | NOVEMBER
T-428-3409 | PS5-05-OB-9195A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone D | 3 | In progress |  | 32 | OCTOBER
T-732-3410 | PS5-55-UR-2336D | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-10-01 | PS5-05-02 | PS5 - Milestone I | 8 | Closed | 36 | 34 | OCTOBER
T-218-3411 | PS5-47-UR-6307A | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-12-08 | PS5-02-02 | PS5 - Milestone E | 4 | Closed | 6 | 39 | DECEMBER
T-758-3412 | PS5-99-OB-2522A | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-10-03 | PS5-06-01 | PS5 - Milestone H | 7 | Closed | 7 | 10 | OCTOBER
T-785-3413 | PS5-51-OB-9716D | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone D | 3 | On hold |  | 29 | NOVEMBER
T-594-3414 | PS5-89-OB-9986C | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | To be completed |  | 4 | DECEMBER
T-769-3415 | PS5-35-UR-5250D | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone F | 5 | To be completed |  | 36 | NOVEMBER
T-423-3416 | PS5-83-IK-3621A | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-05-12 | PS5-02-03 | PS5 - Milestone H | 7 | Closed | 30 | 23 | MAY
T-714-3417 | PS5-07-OB-5745A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-11-19 | PS5-11-02 | PS5 - Milestone F | 5 | Closed | 38 | 22 | NOVEMBER
T-162-3418 | PS5-36-IK-2790D | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-09-02 | PS5-05-03 | PS5 - Milestone B | 1.1 | Closed | 29 | 18 | SEPTEMBER
T-337-3419 | PS5-02-OB-8987B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-06-26 | PS5-06-01 | PS5 - Milestone H | 7 | Closed | 13 | 26 | JUNE
T-776-3420 | PS5-90-OB-7971B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone E | 4 | To be completed |  | 11 | NOVEMBER
T-892-3421 | PS5-47-OB-1721D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-01-03 | PS5-10-02 | PS5 - Milestone E | 4 | Closed | 11 | 32 | JANUARY
T-390-3422 | PS5-49-UR-7450C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-11-05 | PS5-11-01 | PS5 - Milestone H | 7 | Closed | 9 | 9 | NOVEMBER
T-040-3423 | PS5-58-OB-2965C | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone C | 2 | In progress |  | 46 | SEPTEMBER
T-104-3424 | PS5-55-IK-6510C | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | On hold |  | 40 | SEPTEMBER
T-899-3425 | PS5-54-OB-2840A | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-04-02 | PS5-99-02 | PS5 - Milestone A | 1 | Closed | 36 | 34 | APRIL
T-937-3426 | PS5-28-OB-2021B | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-04-19 | PS5-09-03 | PS5 - Milestone E | 4 | Closed | 40 | 28 | APRIL
T-245-3427 | PS5-94-UR-7584D | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | On hold |  | 15 | NOVEMBER
T-995-3428 | PS5-48-UR-9951B | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-12-09 | PS5-07-03 | PS5 - Milestone I | 8 | Closed | 15 | 23 | DECEMBER
T-759-3429 | PS5-28-OB-2628A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | On hold |  | 4 | NOVEMBER
T-181-3430 | PS5-05-IK-4288A | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone H | 7 | To be completed |  | 4 | SEPTEMBER
T-504-3431 | PS5-26-IK-6659B | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone D | 3 | On hold |  | 16 | NOVEMBER
T-744-3432 | PS5-95-OB-3045B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-12-21 | PS5-61-07 | PS5 - Milestone F | 5 | Closed | 33 | 31 | DECEMBER
T-463-3433 | PS5-37-IK-2922D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone G | 6 | In progress |  | 43 | NOVEMBER
T-655-3434 | PS5-10-IK-2441D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-05-17 | PS5-60-07 | PS5 - Milestone A | 1 | Closed | 41 | 31 | MAY
T-295-3435 | PS5-80-UR-2514C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-06-13 | PS5-06-02 | PS5 - Milestone G | 6 | Closed | 27 | 24 | JUNE
T-635-3436 | PS5-61-UR-7538D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-10-12 | PS5-07-01 | PS5 - Milestone B | 1.1 | Closed | 40 | 46 | OCTOBER
T-933-3437 | PS5-43-UR-5433D | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone G | 6 | To be completed |  | 20 | SEPTEMBER
T-603-3438 | PS5-49-OB-8409D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-02-28 | PS5-10-02 | PS5 - Milestone A | 1 | Closed | 26 | 30 | FEBRUARY
T-941-3439 | PS5-28-UR-6464C | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | To be completed |  | 27 | AUGUST
T-451-3440 | PS5-54-IK-2849D | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-12-28 | PS5-82-02 | PS5 - Milestone I | 8 | Closed | 42 | 14 | DECEMBER
T-527-3441 | PS5-09-UR-7766B | CQM01 - Pump Installation | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-10-02 | PS5-03-02 | PS5 - Milestone A | 1 | Closed | 30 | 28 | OCTOBER
T-119-3442 | PS5-87-UR-5322B | CQS03 - Deluge System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-02-23 | PS5-02-03 | PS5 - Milestone A | 1 | Closed | 7 | 10 | FEBRUARY
T-047-3443 | PS5-50-OB-3877D | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone G | 6 | To be completed |  | 26 | DECEMBER
T-046-3444 | PS5-78-OB-2985B | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | On hold |  | 7 | SEPTEMBER
T-124-3445 | PS5-34-UR-6792A | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-05-11 | PS5-61-02 | PS5 - Milestone E | 4 | Closed | 21 | 26 | MAY
T-992-3446 | PS5-65-IK-9985D | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-04-27 | PS5-10-05 | PS5 - Milestone I | 8 | Closed | 34 | 44 | APRIL
T-889-3447 | PS5-56-OB-9491B | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone D | 3 | To be completed |  | 27 | AUGUST
T-316-3448 | PS5-09-UR-3768A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone E | 4 | To be completed |  | 6 | NOVEMBER
T-754-3449 | PS5-71-IK-8247B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-04-20 | PS5-82-02 | PS5 - Milestone I | 8 | Closed | 25 | 23 | APRIL
T-535-3450 | PS5-17-UR-7997A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-03 | PS5-60-01 | PS5 - Milestone H | 7 | Closed | 45 | 39 | APRIL
T-808-3451 | PS5-57-IK-8883D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-06-21 | PS5-04-03 | PS5 - Milestone D | 3 | Closed | 14 | 13 | JUNE
T-675-3452 | PS5-32-IK-1087D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-03-01 | PS5-62-01 | PS5 - Milestone B | 1.1 | Closed | 34 | 44 | MARCH
T-442-3453 | PS5-59-IK-6415D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone C | 2 | In progress |  | 7 | SEPTEMBER
T-787-3454 | PS5-13-OB-1419D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | In progress |  | 12 | NOVEMBER
T-116-3455 | PS5-45-OB-6869C | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone D | 3 | To be completed |  | 39 | DECEMBER
T-632-3456 | PS5-78-UR-9392C | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-01-22 | PS5-12-01 | PS5 - Milestone F | 5 | Closed | 27 | 15 | JANUARY
T-522-3457 | PS5-45-OB-4832D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-09-24 | PS5-02-03 | PS5 - Milestone D | 3 | Closed | 4 | 21 | SEPTEMBER
T-052-3458 | PS5-40-UR-2707C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone A | 1 | To be completed |  | 44 | SEPTEMBER
T-982-3459 | PS5-34-UR-1705B | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone A | 1 | To be completed |  | 6 | OCTOBER
T-676-3460 | PS5-16-IK-3071A | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-11-05 | PS5-09-03 | PS5 - Milestone I | 8 | Closed | 38 | 45 | NOVEMBER
T-257-3461 | PS5-97-UR-5363A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone F | 5 | In progress |  | 21 | OCTOBER
T-537-3462 | PS5-59-IK-3733C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone F | 5 | In progress |  | 15 | DECEMBER
T-156-3463 | PS5-38-UR-2320B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone A | 1 | On hold |  | 7 | OCTOBER
T-616-3464 | PS5-37-OB-7810D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-03-06 | PS5-10-03 | PS5 - Milestone G | 6 | Closed | 20 | 12 | MARCH
T-570-3465 | PS5-33-OB-8133A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone F | 5 | In progress |  | 36 | OCTOBER
T-673-3466 | PS5-58-IK-4908C | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-09-17 | PS5-03-23 | PS5 - Milestone F | 5 | Closed | 17 | 28 | SEPTEMBER
T-781-3467 | PS5-16-IK-9209C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone H | 7 | In progress |  | 48 | SEPTEMBER
T-127-3468 | PS5-02-OB-8676C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone I | 8 | To be completed |  | 44 | SEPTEMBER
T-159-3469 | PS5-69-IK-7514B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone A | 1 | In progress |  | 7 | AUGUST
T-158-3470 | PS5-38-OB-4385A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | To be completed |  | 48 | NOVEMBER
T-782-3471 | PS5-67-UR-8722D | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-11-09 | PS5-01-06 | PS5 - Milestone I | 8 | Closed | 19 | 36 | NOVEMBER
T-302-3472 | PS5-63-OB-5105B | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-11-23 | PS5-61-02 | PS5 - Milestone A | 1 | Closed | 46 | 9 | NOVEMBER
T-363-3473 | PS5-14-IK-7466A | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-02-14 | PS5-09-03 | PS5 - Milestone D | 3 | Closed | 12 | 24 | FEBRUARY
T-249-3474 | PS5-83-IK-6017D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-12-21 | PS5-01-03 | PS5 - Milestone A | 1 | Closed | 8 | 40 | DECEMBER
T-973-3475 | PS5-41-IK-5167C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone A | 1 | On hold |  | 24 | DECEMBER
T-894-3476 | PS5-85-OB-5518A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-04-11 | PS5-01-07 | PS5 - Milestone F | 5 | Closed | 16 | 39 | APRIL
T-699-3477 | PS5-52-OB-5519A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone F | 5 | On hold |  | 16 | DECEMBER
T-784-3478 | PS5-13-IK-9353A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone A | 1 | In progress |  | 20 | SEPTEMBER
T-498-3479 | PS5-31-IK-9074B | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone I | 8 | On hold |  | 8 | AUGUST
T-160-3480 | PS5-82-OB-3559C | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | In progress |  | 42 | AUGUST
T-872-3481 | PS5-66-OB-3847C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone A | 1 | On hold |  | 39 | DECEMBER
T-992-3482 | PS5-10-UR-3792D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-08-17 | PS5-05-01 | PS5 - Milestone I | 8 | Closed | 10 | 41 | AUGUST
T-347-3483 | PS5-28-IK-4000C | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone A | 1 | To be completed |  | 27 | NOVEMBER
T-210-3484 | PS5-33-IK-2145C | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | To be completed |  | 7 | OCTOBER
T-784-3485 | PS5-81-IK-6214C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone I | 8 | In progress |  | 20 | OCTOBER
T-834-3486 | PS5-86-UR-5466A | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone G | 6 | In progress |  | 31 | SEPTEMBER
T-569-3487 | PS5-99-OB-9608A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone E | 4 | To be completed |  | 29 | SEPTEMBER
T-012-3488 | PS5-17-OB-8301C | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone D | 3 | To be completed |  | 22 | DECEMBER
T-753-3489 | PS5-12-OB-1681D | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone F | 5 | To be completed |  | 19 | NOVEMBER
T-357-3490 | PS5-66-IK-4138B | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | In progress |  | 34 | DECEMBER
T-693-3491 | PS5-16-UR-8628A | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone A | 1 | In progress |  | 7 | DECEMBER
T-365-3492 | PS5-18-UR-5586A | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-11-27 | PS5-09-02 | PS5 - Milestone G | 6 | Closed | 28 | 18 | NOVEMBER
T-295-3493 | PS5-93-OB-7023B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone C | 2 | In progress |  | 40 | AUGUST
T-593-3494 | PS5-22-OB-2118B | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | On hold |  | 35 | SEPTEMBER
T-645-3495 | PS5-54-UR-2550B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone G | 6 | To be completed |  | 9 | DECEMBER
T-685-3496 | PS5-43-OB-8747C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone A | 1 | In progress |  | 39 | AUGUST
T-319-3497 | PS5-99-OB-5432A | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-08-20 | PS5-99-03 | PS5 - Milestone G | 6 | Closed | 9 | 30 | AUGUST
T-228-3498 | PS5-99-OB-4176B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone E | 4 | To be completed |  | 40 | SEPTEMBER
T-542-3499 | PS5-44-UR-2978D | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-06-18 | PS5-09-02 | PS5 - Milestone I | 8 | Closed | 8 | 35 | JUNE
T-749-3500 | PS5-03-OB-2886D | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone G | 6 | On hold |  | 41 | AUGUST
T-890-3501 | PS5-50-UR-2107B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone D | 3 | To be completed |  | 30 | SEPTEMBER
T-393-3502 | PS5-33-UR-1269D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone H | 7 | On hold |  | 28 | OCTOBER
T-299-3503 | PS5-84-OB-1515A | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-08-21 | PS5-13-01 | PS5 - Milestone C | 2 | Closed | 32 | 40 | AUGUST
T-409-3504 | PS5-73-OB-5453B | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-05-22 | PS5-01-07 | PS5 - Milestone C | 2 | Closed | 31 | 22 | MAY
T-664-3505 | PS5-13-IK-8227B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-10-14 | PS5-01-08 | PS5 - Milestone E | 4 | Closed | 46 | 4 | OCTOBER
T-018-3506 | PS5-79-UR-6977C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone C | 2 | To be completed |  | 17 | SEPTEMBER
T-129-3507 | PS5-83-OB-4015C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone G | 6 | On hold |  | 40 | NOVEMBER
T-277-3508 | PS5-74-IK-6521A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-02-09 | PS5-61-07 | PS5 - Milestone H | 7 | Closed | 44 | 14 | FEBRUARY
T-881-3509 | PS5-60-UR-6945B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-08-17 | PS5-01-07 | PS5 - Milestone I | 8 | Closed | 34 | 32 | AUGUST
T-254-3510 | PS5-75-IK-1592B | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone H | 7 | In progress |  | 15 | NOVEMBER
T-488-3511 | PS5-86-UR-8974B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone D | 3 | On hold |  | 7 | SEPTEMBER
T-977-3512 | PS5-66-OB-9076A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | To be completed |  | 7 | DECEMBER
T-383-3513 | PS5-21-UR-4181A | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-07-04 | PS5-01-07 | PS5 - Milestone E | 4 | Closed | 24 | 35 | JULY
T-178-3514 | PS5-29-OB-8399A | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone E | 4 | In progress |  | 19 | OCTOBER
T-950-3515 | PS5-69-OB-9581D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone F | 5 | To be completed |  | 19 | AUGUST
T-947-3516 | PS5-67-OB-5032A | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone D | 3 | On hold |  | 42 | SEPTEMBER
T-460-3517 | PS5-69-IK-4453B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone H | 7 | On hold |  | 26 | OCTOBER
T-518-3518 | PS5-88-IK-7473C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone I | 8 | To be completed |  | 29 | SEPTEMBER
T-429-3519 | PS5-83-OB-8198A | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone D | 3 | To be completed |  | 44 | AUGUST
T-630-3520 | PS5-83-UR-2977D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone G | 6 | In progress |  | 15 | SEPTEMBER
T-830-3521 | PS5-30-OB-5511B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone A | 1 | On hold |  | 33 | OCTOBER
T-304-3522 | PS5-26-IK-8126A | CQM01 - Pump Installation | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-07-06 | PS5-01-09 | PS5 - Milestone G | 6 | Closed | 8 | 21 | JULY
T-817-3523 | PS5-79-UR-1129B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-05-04 | PS5-06-01 | PS5 - Milestone F | 5 | Closed | 17 | 21 | MAY
T-329-3524 | PS5-59-IK-4481A | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone E | 4 | In progress |  | 8 | OCTOBER
T-265-3525 | PS5-56-IK-4241C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | To be completed |  | 13 | DECEMBER
T-648-3526 | PS5-44-IK-6999C | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone F | 5 | To be completed |  | 11 | SEPTEMBER
T-794-3527 | PS5-91-OB-3089A | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-07-19 | PS5-04-01 | PS5 - Milestone I | 8 | Closed | 44 | 16 | JULY
T-666-3528 | PS5-13-IK-9901C | CQP02 - Valve Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone I | 8 | In progress |  | 10 | NOVEMBER
T-386-3529 | PS5-19-OB-4478B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone G | 6 | In progress |  | 18 | NOVEMBER
T-090-3530 | PS5-16-UR-7009C | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone A | 1 | In progress |  | 44 | OCTOBER
T-981-3531 | PS5-37-IK-1498B | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-02-20 | PS5-82-07 | PS5 - Milestone A | 1 | Closed | 38 | 29 | FEBRUARY
T-254-3532 | PS5-37-OB-3324A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-02-21 | PS5-09-02 | PS5 - Milestone I | 8 | Closed | 7 | 14 | FEBRUARY
T-274-3533 | PS5-12-IK-3666A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-03-08 | PS5-61-02 | PS5 - Milestone D | 3 | Closed | 30 | 34 | MARCH
T-253-3534 | PS5-72-IK-6463D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone H | 7 | To be completed |  | 27 | DECEMBER
T-713-3535 | PS5-06-IK-5675C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone G | 6 | On hold |  | 37 | SEPTEMBER
T-397-3536 | PS5-04-OB-9626B | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-08-08 | PS5-03-03 | PS5 - Milestone C | 2 | Closed | 35 | 37 | AUGUST
T-800-3537 | PS5-86-OB-8173B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | To be completed |  | 46 | AUGUST
T-159-3538 | PS5-36-OB-2964D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-11-02 | PS5-82-02 | PS5 - Milestone B | 1.1 | Closed | 15 | 34 | NOVEMBER
T-418-3539 | PS5-42-OB-1862A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone F | 5 | To be completed |  | 20 | DECEMBER
T-910-3540 | PS5-48-IK-9799A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone C | 2 | On hold |  | 4 | OCTOBER
T-264-3541 | PS5-16-OB-8424D | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-06-05 | PS5-11-02 | PS5 - Milestone B | 1.1 | Closed | 13 | 7 | JUNE
T-205-3542 | PS5-84-IK-5845C | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | To be completed |  | 14 | OCTOBER
T-113-3543 | PS5-65-OB-4849C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | To be completed |  | 22 | SEPTEMBER
T-587-3544 | PS5-38-IK-2541A | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone H | 7 | In progress |  | 20 | OCTOBER
T-592-3545 | PS5-49-IK-5252B | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-11-02 | PS5-09-01 | PS5 - Milestone E | 4 | Closed | 5 | 45 | NOVEMBER
T-599-3546 | PS5-88-OB-6001C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone D | 3 | To be completed |  | 18 | SEPTEMBER
T-846-3547 | PS5-87-OB-4664D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | To be completed |  | 34 | DECEMBER
T-857-3548 | PS5-27-IK-7957D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-09-18 | PS5-03-03 | PS5 - Milestone B | 1.1 | Closed | 35 | 8 | SEPTEMBER
T-056-3549 | PS5-69-IK-1428A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-12-24 | PS5-11-02 | PS5 - Milestone F | 5 | Closed | 24 | 17 | DECEMBER
T-791-3550 | PS5-70-UR-8224B | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | To be completed |  | 40 | NOVEMBER
T-820-3551 | PS5-19-IK-7022C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-10-07 | PS5-82-02 | PS5 - Milestone E | 4 | Closed | 48 | 36 | OCTOBER
T-976-3552 | PS5-72-OB-5174D | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-05-03 | PS5-01-06 | PS5 - Milestone C | 2 | Closed | 20 | 40 | MAY
T-492-3553 | PS5-69-IK-2273D | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone B | 1.1 | In progress |  | 27 | NOVEMBER
T-602-3554 | PS5-18-OB-6795C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone I | 8 | In progress |  | 15 | AUGUST
T-088-3555 | PS5-38-IK-1734D | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-08-27 | PS5-09-01 | PS5 - Milestone E | 4 | Closed | 42 | 20 | AUGUST
T-203-3556 | PS5-19-OB-7328D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-01-23 | PS5-61-01 | PS5 - Milestone E | 4 | Closed | 15 | 39 | JANUARY
T-245-3557 | PS5-43-OB-9471B | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-05-06 | PS5-02-03 | PS5 - Milestone G | 6 | Closed | 16 | 37 | MAY
T-027-3558 | PS5-27-OB-3198A | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-12-05 | PS5-10-05 | PS5 - Milestone B | 1.1 | Closed | 30 | 14 | DECEMBER
T-854-3559 | PS5-18-OB-1775B | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone F | 5 | On hold |  | 21 | OCTOBER
T-721-3560 | PS5-79-IK-3189A | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone G | 6 | In progress |  | 15 | NOVEMBER
T-911-3561 | PS5-58-IK-8867C | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | On hold |  | 39 | NOVEMBER
T-337-3562 | PS5-50-OB-5311C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone G | 6 | On hold |  | 45 | AUGUST
T-947-3563 | PS5-60-UR-2153A | CQM04 - Vessel | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone D | 3 | To be completed |  | 10 | NOVEMBER
T-587-3564 | PS5-61-UR-3534D | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-10-24 | PS5-82-07 | PS5 - Milestone A | 1 | Closed | 29 | 39 | OCTOBER
T-147-3565 | PS5-05-OB-2249C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | In progress |  | 42 | OCTOBER
T-368-3566 | PS5-45-OB-6177D | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-12-05 | PS5-07-01 | PS5 - Milestone H | 7 | Closed | 13 | 35 | DECEMBER
T-392-3567 | PS5-19-IK-9720A | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone B | 1.1 | In progress |  | 8 | DECEMBER
T-602-3568 | PS5-46-IK-3795B | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | On hold |  | 19 | DECEMBER
T-581-3569 | PS5-05-OB-5200D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-05-16 | PS5-10-02 | PS5 - Milestone C | 2 | Closed | 33 | 41 | MAY
T-286-3570 | PS5-44-UR-4784B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-07-13 | PS5-06-03 | PS5 - Milestone E | 4 | Closed | 40 | 12 | JULY
T-574-3571 | PS5-99-IK-8015C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-01-06 | PS5-05-01 | PS5 - Milestone C | 2 | Closed | 16 | 5 | JANUARY
T-122-3572 | PS5-78-OB-5542C | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-10-17 | PS5-07-04 | PS5 - Milestone H | 7 | Closed | 31 | 21 | OCTOBER
T-734-3573 | PS5-13-UR-3001C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-03-08 | PS5-62-01 | PS5 - Milestone F | 5 | Closed | 46 | 35 | MARCH
T-614-3574 | PS5-30-UR-7079D | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone B | 1.1 | To be completed |  | 42 | NOVEMBER
T-337-3575 | PS5-26-OB-2930D | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone H | 7 | On hold |  | 41 | AUGUST
T-162-3576 | PS5-68-IK-8321C | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-11-16 | PS5-01-03 | PS5 - Milestone F | 5 | Closed | 18 | 9 | NOVEMBER
T-692-3577 | PS5-33-UR-2236B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | In progress |  | 18 | OCTOBER
T-960-3578 | PS5-37-UR-7504D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | In progress |  | 39 | OCTOBER
T-709-3579 | PS5-45-UR-6499D | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone G | 6 | To be completed |  | 14 | AUGUST
T-181-3580 | PS5-11-IK-8618B | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone A | 1 | On hold |  | 24 | OCTOBER
T-541-3581 | PS5-62-OB-1341C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-09-16 | PS5-10-04 | PS5 - Milestone B | 1.1 | Closed | 43 | 41 | SEPTEMBER
T-946-3582 | PS5-82-OB-1587B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone E | 4 | In progress |  | 19 | DECEMBER
T-878-3583 | PS5-75-OB-6392D | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone G | 6 | To be completed |  | 23 | AUGUST
T-255-3584 | PS5-43-OB-9465D | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone F | 5 | In progress |  | 36 | OCTOBER
T-151-3585 | PS5-72-OB-1180B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone E | 4 | To be completed |  | 23 | SEPTEMBER
T-782-3586 | PS5-19-IK-3731C | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone F | 5 | To be completed |  | 15 | SEPTEMBER
T-263-3587 | PS5-41-UR-5826C | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone G | 6 | To be completed |  | 24 | AUGUST
T-350-3588 | PS5-30-IK-6522C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone D | 3 | To be completed |  | 12 | SEPTEMBER
T-588-3589 | PS5-31-UR-7588B | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone B | 1.1 | On hold |  | 4 | NOVEMBER
T-592-3590 | PS5-91-OB-4375D | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | To be completed |  | 27 | OCTOBER
T-977-3591 | PS5-31-OB-5501D | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | To be completed |  | 36 | OCTOBER
T-205-3592 | PS5-46-OB-3335D | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone C | 2 | To be completed |  | 21 | AUGUST
T-638-3593 | PS5-75-OB-5623D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-03-21 | PS5-03-01 | PS5 - Milestone C | 2 | Closed | 13 | 9 | MARCH
T-913-3594 | PS5-20-IK-9913C | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | To be completed |  | 15 | OCTOBER
T-738-3595 | PS5-24-OB-9403A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-04-22 | PS5-10-04 | PS5 - Milestone I | 8 | Closed | 7 | 5 | APRIL
T-092-3596 | PS5-11-IK-1653D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone E | 4 | In progress |  | 29 | AUGUST
T-084-3597 | PS5-07-OB-7481D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-02-07 | PS5-62-02 | PS5 - Milestone F | 5 | Closed | 20 | 33 | FEBRUARY
T-752-3598 | PS5-92-IK-5449B | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | In progress |  | 7 | AUGUST
T-502-3599 | PS5-96-UR-7653D | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone I | 8 | In progress |  | 31 | SEPTEMBER
T-972-3600 | PS5-70-UR-5770C | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-07-17 | PS5-07-04 | PS5 - Milestone D | 3 | Closed | 45 | 17 | JULY
T-229-3601 | PS5-15-UR-7082B | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | To be completed |  | 6 | SEPTEMBER
T-013-3602 | PS5-97-OB-8303A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | On hold |  | 14 | SEPTEMBER
T-194-3603 | PS5-58-OB-4441B | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone E | 4 | To be completed |  | 32 | AUGUST
T-589-3604 | PS5-92-OB-9646D | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-06-06 | PS5-63-04 | PS5 - Milestone H | 7 | Closed | 21 | 46 | JUNE
T-916-3605 | PS5-30-OB-9289D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-01-12 | PS5-10-05 | PS5 - Milestone E | 4 | Closed | 18 | 15 | JANUARY
T-979-3606 | PS5-05-IK-2488C | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone F | 5 | To be completed |  | 40 | DECEMBER
T-151-3607 | PS5-10-OB-6426D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone I | 8 | To be completed |  | 34 | OCTOBER
T-365-3608 | PS5-45-OB-7427B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-07-17 | PS5-01-02 | PS5 - Milestone B | 1.1 | Closed | 39 | 8 | JULY
T-341-3609 | PS5-32-IK-5983D | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-02-09 | PS5-03-03 | PS5 - Milestone H | 7 | Closed | 34 | 6 | FEBRUARY
T-054-3610 | PS5-79-UR-6649B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-01-27 | PS5-61-07 | PS5 - Milestone I | 8 | Closed | 22 | 8 | JANUARY
T-730-3611 | PS5-39-OB-7113D | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-11-21 | PS5-10-01 | PS5 - Milestone G | 6 | Closed | 20 | 30 | NOVEMBER
T-846-3612 | PS5-43-OB-1773A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone C | 2 | To be completed |  | 11 | DECEMBER
T-385-3613 | PS5-92-IK-4990A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone I | 8 | To be completed |  | 4 | AUGUST
T-577-3614 | PS5-18-IK-5513D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone E | 4 | In progress |  | 21 | NOVEMBER
T-063-3615 | PS5-27-IK-3333B | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | In progress |  | 14 | OCTOBER
T-868-3616 | PS5-30-OB-6246A | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-04-16 | PS5-10-01 | PS5 - Milestone A | 1 | Closed | 7 | 20 | APRIL
T-316-3617 | PS5-47-OB-4915A | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-04-03 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 9 | 19 | APRIL
T-065-3618 | PS5-14-UR-8048B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone I | 8 | To be completed |  | 5 | DECEMBER
T-318-3619 | PS5-36-OB-9724A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-05-18 | PS5-09-03 | PS5 - Milestone B | 1.1 | Closed | 47 | 7 | MAY
T-655-3620 | PS5-53-IK-7133A | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone B | 1.1 | To be completed |  | 34 | DECEMBER
T-233-3621 | PS5-17-OB-1476B | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone G | 6 | To be completed |  | 18 | AUGUST
T-811-3622 | PS5-30-IK-9643B | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-03-21 | PS5-10-01 | PS5 - Milestone H | 7 | Closed | 40 | 36 | MARCH
T-451-3623 | PS5-28-IK-4331C | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone F | 5 | To be completed |  | 48 | AUGUST
T-763-3624 | PS5-74-OB-2424A | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | In progress |  | 20 | SEPTEMBER
T-343-3625 | PS5-54-IK-9698D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone B | 1.1 | In progress |  | 24 | AUGUST
T-413-3626 | PS5-36-IK-1876B | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | On hold |  | 7 | SEPTEMBER
T-681-3627 | PS5-92-OB-7212C | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-03-09 | PS5-09-04 | PS5 - Milestone F | 5 | Closed | 8 | 8 | MARCH
T-939-3628 | PS5-22-OB-9408B | CQM01 - Pump Installation | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-09-15 | PS5-63-04 | PS5 - Milestone C | 2 | Closed | 48 | 48 | SEPTEMBER
T-380-3629 | PS5-11-OB-2115A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | To be completed |  | 21 | NOVEMBER
T-131-3630 | PS5-39-OB-2120C | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone D | 3 | To be completed |  | 25 | DECEMBER
T-909-3631 | PS5-92-IK-3864D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | To be completed |  | 16 | DECEMBER
T-427-3632 | PS5-03-OB-2116C | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | In progress |  | 21 | DECEMBER
T-520-3633 | PS5-89-OB-5243A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | In progress |  | 21 | AUGUST
T-794-3634 | PS5-38-UR-1692D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone E | 4 | In progress |  | 11 | DECEMBER
T-473-3635 | PS5-22-UR-8112D | CQM03 - Heat Exchanger | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone H | 7 | In progress |  | 8 | NOVEMBER
T-263-3636 | PS5-76-OB-2172A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone B | 1.1 | In progress |  | 21 | DECEMBER
T-867-3637 | PS5-05-OB-2496C | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone E | 4 | In progress |  | 41 | AUGUST
T-075-3638 | PS5-86-UR-4383B | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-08-06 | PS5-12-01 | PS5 - Milestone E | 4 | Closed | 14 | 9 | AUGUST
T-320-3639 | PS5-05-OB-3450A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-01-05 | PS5-82-02 | PS5 - Milestone E | 4 | Closed | 28 | 44 | JANUARY
T-617-3640 | PS5-56-OB-1637C | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | In progress |  | 40 | AUGUST
T-198-3641 | PS5-38-OB-3918B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-02-26 | PS5-63-01 | PS5 - Milestone I | 8 | Closed | 9 | 7 | FEBRUARY
T-581-3642 | PS5-85-IK-7122A | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-01-11 | PS5-07-02 | PS5 - Milestone A | 1 | Closed | 17 | 42 | JANUARY
T-396-3643 | PS5-29-OB-7033D | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-10-09 | PS5-10-02 | PS5 - Milestone H | 7 | Closed | 25 | 35 | OCTOBER
T-915-3644 | PS5-24-OB-3091D | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone C | 2 | To be completed |  | 8 | DECEMBER
T-649-3645 | PS5-04-OB-6972A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-01-24 | PS5-10-03 | PS5 - Milestone A | 1 | Closed | 29 | 33 | JANUARY
T-037-3646 | PS5-91-OB-3150C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-05-22 | PS5-08-01 | PS5 - Milestone B | 1.1 | Closed | 35 | 44 | MAY
T-315-3647 | PS5-33-OB-6355D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone B | 1.1 | On hold |  | 12 | AUGUST
T-687-3648 | PS5-10-OB-2411A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-06-20 | PS5-10-02 | PS5 - Milestone D | 3 | Closed | 36 | 43 | JUNE
T-795-3649 | PS5-94-UR-9077D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone F | 5 | On hold |  | 39 | SEPTEMBER
T-458-3650 | PS5-98-IK-6049A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone H | 7 | In progress |  | 16 | DECEMBER
T-412-3651 | PS5-54-IK-6819A | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-10-01 | PS5-61-07 | PS5 - Milestone E | 4 | Closed | 33 | 8 | OCTOBER
T-492-3652 | PS5-83-OB-7592A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone B | 1.1 | To be completed |  | 40 | OCTOBER
T-585-3653 | PS5-07-OB-6792C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-02-27 | PS5-11-01 | PS5 - Milestone B | 1.1 | Closed | 16 | 13 | FEBRUARY
T-612-3654 | PS5-37-IK-9115D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone B | 1.1 | To be completed |  | 36 | SEPTEMBER
T-141-3655 | PS5-71-IK-2063C | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone G | 6 | In progress |  | 12 | AUGUST
T-247-3656 | PS5-42-IK-9078C | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone B | 1.1 | In progress |  | 34 | DECEMBER
T-081-3657 | PS5-51-OB-7208B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone D | 3 | In progress |  | 34 | DECEMBER
T-972-3658 | PS5-69-UR-1577C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | In progress |  | 33 | SEPTEMBER
T-510-3659 | PS5-11-IK-6869C | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone G | 6 | To be completed |  | 44 | SEPTEMBER
T-624-3660 | PS5-86-OB-8443C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-12-14 | PS5-01-05 | PS5 - Milestone B | 1.1 | Closed | 48 | 32 | DECEMBER
T-424-3661 | PS5-42-IK-1547B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone E | 4 | In progress |  | 47 | SEPTEMBER
T-666-3662 | PS5-65-UR-7704A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone B | 1.1 | To be completed |  | 46 | SEPTEMBER
T-286-3663 | PS5-18-OB-9723C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone I | 8 | To be completed |  | 6 | DECEMBER
T-174-3664 | PS5-21-OB-7566C | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone A | 1 | In progress |  | 19 | NOVEMBER
T-498-3665 | PS5-33-UR-7250D | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone G | 6 | To be completed |  | 33 | NOVEMBER
T-041-3666 | PS5-66-OB-7089B | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone A | 1 | To be completed |  | 18 | SEPTEMBER
T-611-3667 | PS5-33-IK-3899A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-02-17 | PS5-01-05 | PS5 - Milestone F | 5 | Closed | 11 | 8 | FEBRUARY
T-774-3668 | PS5-54-UR-3875B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone H | 7 | To be completed |  | 5 | DECEMBER
T-926-3669 | PS5-51-IK-5113B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone G | 6 | On hold |  | 12 | SEPTEMBER
T-370-3670 | PS5-55-OB-8057C | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone A | 1 | To be completed |  | 5 | DECEMBER
T-906-3671 | PS5-71-OB-9394D | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-04-03 | PS5-09-01 | PS5 - Milestone H | 7 | Closed | 39 | 36 | APRIL
T-854-3672 | PS5-38-IK-4095B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | To be completed |  | 24 | NOVEMBER
T-776-3673 | PS5-66-OB-7720D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-06-02 | PS5-10-05 | PS5 - Milestone G | 6 | Closed | 30 | 21 | JUNE
T-906-3674 | PS5-99-OB-1483C | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone A | 1 | On hold |  | 31 | AUGUST
T-661-3675 | PS5-32-UR-8760C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone E | 4 | To be completed |  | 21 | AUGUST
T-339-3676 | PS5-51-IK-9811C | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-08-21 | PS5-09-03 | PS5 - Milestone C | 2 | Closed | 41 | 48 | AUGUST
T-171-3677 | PS5-33-IK-8379D | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone G | 6 | On hold |  | 9 | NOVEMBER
T-361-3678 | PS5-45-UR-3280C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-11-16 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 44 | 46 | NOVEMBER
T-145-3679 | PS5-13-UR-7445B | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone E | 4 | In progress |  | 24 | DECEMBER
T-420-3680 | PS5-81-UR-5902A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone H | 7 | In progress |  | 16 | DECEMBER
T-585-3681 | PS5-11-UR-1084D | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone I | 8 | In progress |  | 22 | SEPTEMBER
T-794-3682 | PS5-11-UR-5647C | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone A | 1 | In progress |  | 27 | SEPTEMBER
T-932-3683 | PS5-44-OB-2640B | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone C | 2 | On hold |  | 18 | OCTOBER
T-341-3684 | PS5-04-OB-8601B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone A | 1 | In progress |  | 17 | DECEMBER
T-393-3685 | PS5-45-IK-3521D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-02-08 | PS5-05-02 | PS5 - Milestone H | 7 | Closed | 19 | 39 | FEBRUARY
T-877-3686 | PS5-92-OB-2454D | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | To be completed |  | 15 | AUGUST
T-744-3687 | PS5-58-IK-5905A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone B | 1.1 | In progress |  | 43 | OCTOBER
T-946-3688 | PS5-14-UR-5395C | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | In progress |  | 23 | AUGUST
T-266-3689 | PS5-90-UR-9597C | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-01-26 | PS5-09-02 | PS5 - Milestone C | 2 | Closed | 48 | 23 | JANUARY
T-460-3690 | PS5-63-OB-4308A | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-03-19 | PS5-01-09 | PS5 - Milestone B | 1.1 | Closed | 4 | 18 | MARCH
T-454-3691 | PS5-68-OB-4710A | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone E | 4 | To be completed |  | 5 | AUGUST
T-489-3692 | PS5-38-OB-4303A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-07-08 | PS5-10-02 | PS5 - Milestone B | 1.1 | Closed | 7 | 19 | JULY
T-012-3693 | PS5-82-OB-8684A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-03-26 | PS5-09-03 | PS5 - Milestone G | 6 | Closed | 16 | 38 | MARCH
T-276-3694 | PS5-93-OB-7325B | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone D | 3 | In progress |  | 43 | OCTOBER
T-225-3695 | PS5-09-OB-2381D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone B | 1.1 | To be completed |  | 36 | SEPTEMBER
T-123-3696 | PS5-74-OB-3689A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-11-14 | PS5-61-01 | PS5 - Milestone C | 2 | Closed | 26 | 27 | NOVEMBER
T-309-3697 | PS5-51-UR-2600C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone I | 8 | In progress |  | 12 | NOVEMBER
T-213-3698 | PS5-87-OB-5008D | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-09-14 | PS5-09-01 | PS5 - Milestone H | 7 | Closed | 27 | 20 | SEPTEMBER
T-771-3699 | PS5-66-IK-7184A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-03-04 | PS5-04-04 | PS5 - Milestone I | 8 | Closed | 36 | 5 | MARCH
T-773-3700 | PS5-11-OB-5167A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-03-19 | PS5-03-01 | PS5 - Milestone I | 8 | Closed | 12 | 40 | MARCH
T-256-3701 | PS5-64-OB-5087D | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone B | 1.1 | To be completed |  | 45 | AUGUST
T-784-3702 | PS5-95-UR-3871D | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-02-19 | PS5-03-01 | PS5 - Milestone E | 4 | Closed | 27 | 23 | FEBRUARY
T-858-3703 | PS5-13-IK-2026D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone I | 8 | To be completed |  | 30 | NOVEMBER
T-728-3704 | PS5-37-OB-4699C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | To be completed |  | 22 | SEPTEMBER
T-520-3705 | PS5-76-IK-5827A | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone B | 1.1 | In progress |  | 46 | DECEMBER
T-535-3706 | PS5-82-IK-7772C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-09-27 | PS5-82-07 | PS5 - Milestone D | 3 | Closed | 46 | 21 | SEPTEMBER
T-153-3707 | PS5-67-OB-2332B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-05-27 | PS5-03-23 | PS5 - Milestone D | 3 | Closed | 4 | 24 | MAY
T-834-3708 | PS5-36-UR-3700B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone F | 5 | To be completed |  | 28 | AUGUST
T-034-3709 | PS5-80-IK-6585C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone A | 1 | To be completed |  | 32 | AUGUST
T-061-3710 | PS5-37-OB-6022B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-08-03 | PS5-09-02 | PS5 - Milestone D | 3 | Closed | 34 | 20 | AUGUST
T-613-3711 | PS5-08-IK-8565B | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | In progress |  | 15 | OCTOBER
T-098-3712 | PS5-25-UR-1182C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-04-09 | PS5-61-02 | PS5 - Milestone D | 3 | Closed | 34 | 28 | APRIL
T-750-3713 | PS5-52-OB-3632A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone F | 5 | In progress |  | 15 | NOVEMBER
T-333-3714 | PS5-09-OB-1626D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | To be completed |  | 30 | OCTOBER
T-450-3715 | PS5-77-IK-9562A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | In progress |  | 8 | OCTOBER
T-193-3716 | PS5-79-UR-4422B | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-01-20 | PS5-99-02 | PS5 - Milestone I | 8 | Closed | 17 | 26 | JANUARY
T-014-3717 | PS5-67-OB-4992A | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-05-10 | PS5-10-01 | PS5 - Milestone C | 2 | Closed | 31 | 39 | MAY
T-949-3718 | PS5-06-UR-2106C | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone I | 8 | On hold |  | 7 | AUGUST
T-824-3719 | PS5-63-IK-5669C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-12-23 | PS5-60-04 | PS5 - Milestone A | 1 | Closed | 42 | 39 | DECEMBER
T-739-3720 | PS5-03-IK-2259A | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone I | 8 | To be completed |  | 27 | SEPTEMBER
T-441-3721 | PS5-73-OB-1010B | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone H | 7 | To be completed |  | 24 | DECEMBER
T-327-3722 | PS5-74-UR-7242C | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-03-11 | PS5-12-01 | PS5 - Milestone G | 6 | Closed | 7 | 24 | MARCH
T-175-3723 | PS5-53-IK-3039D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone F | 5 | In progress |  | 18 | SEPTEMBER
T-059-3724 | PS5-03-OB-5172B | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-04-26 | PS5-07-01 | PS5 - Milestone H | 7 | Closed | 43 | 45 | APRIL
T-645-3725 | PS5-42-UR-4530D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-04-02 | PS5-10-05 | PS5 - Milestone C | 2 | Closed | 11 | 20 | APRIL
T-869-3726 | PS5-75-OB-9144B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone G | 6 | In progress |  | 9 | OCTOBER
T-644-3727 | PS5-99-OB-8013D | CQS01 - Fire Protection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-11-27 | PS5-09-03 | PS5 - Milestone I | 8 | Closed | 39 | 15 | NOVEMBER
T-662-3728 | PS5-35-OB-5951B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone I | 8 | To be completed |  | 15 | DECEMBER
T-919-3729 | PS5-66-OB-5215A | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | In progress |  | 13 | NOVEMBER
T-225-3730 | PS5-83-IK-8815D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone D | 3 | On hold |  | 17 | NOVEMBER
T-328-3731 | PS5-61-OB-7698C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-11-02 | PS5-04-03 | PS5 - Milestone C | 2 | Closed | 22 | 19 | NOVEMBER
T-281-3732 | PS5-79-OB-8392B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-08-11 | PS5-60-07 | PS5 - Milestone F | 5 | Closed | 45 | 18 | AUGUST
T-144-3733 | PS5-62-OB-3335D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | On hold |  | 8 | SEPTEMBER
T-499-3734 | PS5-29-OB-6472A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-12-24 | PS5-10-06 | PS5 - Milestone G | 6 | Closed | 19 | 11 | DECEMBER
T-449-3735 | PS5-19-OB-3896C | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-01-14 | PS5-01-04 | PS5 - Milestone H | 7 | Closed | 14 | 18 | JANUARY
T-777-3736 | PS5-43-OB-4880A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone I | 8 | To be completed |  | 16 | DECEMBER
T-506-3737 | PS5-18-UR-8071B | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-11-09 | PS5-12-02 | PS5 - Milestone D | 3 | Closed | 5 | 28 | NOVEMBER
T-328-3738 | PS5-84-IK-1243B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-10-23 | PS5-10-06 | PS5 - Milestone A | 1 | Closed | 44 | 31 | OCTOBER
T-611-3739 | PS5-07-IK-4289D | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone F | 5 | In progress |  | 5 | SEPTEMBER
T-880-3740 | PS5-53-OB-2738C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-02-08 | PS5-11-03 | PS5 - Milestone H | 7 | Closed | 35 | 16 | FEBRUARY
T-026-3741 | PS5-92-IK-7138B | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | To be completed |  | 8 | AUGUST
T-101-3742 | PS5-91-UR-7631D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-09-02 | PS5-12-01 | PS5 - Milestone I | 8 | Closed | 17 | 25 | SEPTEMBER
T-196-3743 | PS5-17-OB-5468B | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | In progress |  | 41 | DECEMBER
T-915-3744 | PS5-13-UR-7044B | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-09-25 | PS5-82-07 | PS5 - Milestone A | 1 | Closed | 42 | 42 | SEPTEMBER
T-764-3745 | PS5-11-OB-5121D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | In progress |  | 35 | AUGUST
T-469-3746 | PS5-65-OB-9582A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-09-28 | PS5-10-01 | PS5 - Milestone B | 1.1 | Closed | 41 | 33 | SEPTEMBER
T-357-3747 | PS5-94-OB-2313B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone I | 8 | In progress |  | 13 | DECEMBER
T-953-3748 | PS5-04-UR-3668B | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone F | 5 | In progress |  | 27 | DECEMBER
T-569-3749 | PS5-78-IK-6558B | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-05-25 | PS5-08-01 | PS5 - Milestone I | 8 | Closed | 47 | 7 | MAY
T-749-3750 | PS5-74-IK-4554D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-11-04 | PS5-06-02 | PS5 - Milestone D | 3 | Closed | 21 | 30 | NOVEMBER
T-521-3751 | PS5-75-OB-6621B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-02-26 | PS5-01-02 | PS5 - Milestone F | 5 | Closed | 30 | 36 | FEBRUARY
T-606-3752 | PS5-56-OB-4976C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-01-18 | PS5-99-01 | PS5 - Milestone C | 2 | Closed | 13 | 44 | JANUARY
T-032-3753 | PS5-83-OB-1658C | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | To be completed |  | 33 | AUGUST
T-595-3754 | PS5-72-IK-4962A | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-02-01 | PS5-62-02 | PS5 - Milestone F | 5 | Closed | 9 | 43 | FEBRUARY
T-720-3755 | PS5-90-OB-3278C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-09-08 | PS5-02-02 | PS5 - Milestone A | 1 | Closed | 46 | 35 | SEPTEMBER
T-305-3756 | PS5-30-OB-1834A | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-02-09 | PS5-99-01 | PS5 - Milestone A | 1 | Closed | 5 | 19 | FEBRUARY
T-840-3757 | PS5-59-UR-3301A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone C | 2 | To be completed |  | 32 | OCTOBER
T-181-3758 | PS5-14-OB-3502B | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone G | 6 | In progress |  | 6 | SEPTEMBER
T-201-3759 | PS5-53-UR-8058A | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone I | 8 | To be completed |  | 9 | AUGUST
T-662-3760 | PS5-51-OB-3474C | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-10-13 | PS5-10-06 | PS5 - Milestone D | 3 | Closed | 4 | 24 | OCTOBER
T-054-3761 | PS5-92-OB-5255C | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone D | 3 | On hold |  | 11 | AUGUST
T-412-3762 | PS5-38-UR-6351C | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone D | 3 | To be completed |  | 34 | DECEMBER
T-010-3763 | PS5-78-OB-8082B | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone C | 2 | In progress |  | 44 | DECEMBER
T-984-3764 | PS5-17-OB-5082D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | In progress |  | 13 | AUGUST
T-005-3765 | PS5-58-IK-5613A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone D | 3 | In progress |  | 14 | SEPTEMBER
T-150-3766 | PS5-71-IK-8098A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-02-11 | PS5-10-03 | PS5 - Milestone D | 3 | Closed | 38 | 38 | FEBRUARY
T-587-3767 | PS5-27-OB-5658B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-02-01 | PS5-01-03 | PS5 - Milestone B | 1.1 | Closed | 9 | 44 | FEBRUARY
T-174-3768 | PS5-73-OB-8392C | CQP01 - Pipe Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-09-12 | PS5-99-03 | PS5 - Milestone C | 2 | Closed | 44 | 27 | SEPTEMBER
T-336-3769 | PS5-83-OB-4970C | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-11-23 | PS5-01-04 | PS5 - Milestone F | 5 | Closed | 30 | 9 | NOVEMBER
T-871-3770 | PS5-18-OB-6388B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone H | 7 | To be completed |  | 10 | OCTOBER
T-168-3771 | PS5-49-OB-5718A | CQM04 - Vessel | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone A | 1 | In progress |  | 41 | NOVEMBER
T-752-3772 | PS5-44-UR-2577A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | In progress |  | 10 | NOVEMBER
T-691-3773 | PS5-15-OB-6333C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-04-13 | PS5-06-02 | PS5 - Milestone E | 4 | Closed | 33 | 31 | APRIL
T-027-3774 | PS5-94-UR-6686B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone H | 7 | To be completed |  | 15 | AUGUST
T-386-3775 | PS5-69-OB-7622A | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | On hold |  | 44 | SEPTEMBER
T-617-3776 | PS5-47-UR-4283B | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone D | 3 | To be completed |  | 9 | AUGUST
T-719-3777 | PS5-25-IK-8765A | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone I | 8 | On hold |  | 32 | OCTOBER
T-434-3778 | PS5-44-UR-8124D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-04-08 | PS5-07-03 | PS5 - Milestone E | 4 | Closed | 40 | 19 | APRIL
T-017-3779 | PS5-12-OB-4088D | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone A | 1 | To be completed |  | 18 | NOVEMBER
T-721-3780 | PS5-97-IK-7938C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-05-16 | PS5-02-02 | PS5 - Milestone B | 1.1 | Closed | 22 | 35 | MAY
T-519-3781 | PS5-31-IK-8029C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-01-14 | PS5-08-02 | PS5 - Milestone A | 1 | Closed | 44 | 46 | JANUARY
T-972-3782 | PS5-41-OB-9639D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone E | 4 | To be completed |  | 9 | AUGUST
T-698-3783 | PS5-54-OB-5711C | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone F | 5 | In progress |  | 39 | SEPTEMBER
T-171-3784 | PS5-72-OB-4254A | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone B | 1.1 | In progress |  | 32 | SEPTEMBER
T-014-3785 | PS5-20-UR-1244B | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone F | 5 | In progress |  | 45 | OCTOBER
T-949-3786 | PS5-09-OB-7754A | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone C | 2 | To be completed |  | 44 | OCTOBER
T-230-3787 | PS5-45-OB-2724D | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone A | 1 | To be completed |  | 16 | DECEMBER
T-185-3788 | PS5-05-OB-1130D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-12-25 | PS5-03-01 | PS5 - Milestone G | 6 | Closed | 37 | 28 | DECEMBER
T-757-3789 | PS5-98-OB-8257B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone B | 1.1 | To be completed |  | 21 | OCTOBER
T-200-3790 | PS5-76-OB-3935B | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone A | 1 | To be completed |  | 21 | AUGUST
T-149-3791 | PS5-61-OB-5408C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-09-26 | PS5-01-08 | PS5 - Milestone E | 4 | Closed | 40 | 28 | SEPTEMBER
T-838-3792 | PS5-31-OB-2393B | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone B | 1.1 | In progress |  | 24 | DECEMBER
T-042-3793 | PS5-20-IK-7684D | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-02-26 | PS5-03-01 | PS5 - Milestone A | 1 | Closed | 48 | 38 | FEBRUARY
T-061-3794 | PS5-43-IK-2123A | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone G | 6 | On hold |  | 24 | SEPTEMBER
T-497-3795 | PS5-11-UR-3483A | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone C | 2 | In progress |  | 23 | SEPTEMBER
T-592-3796 | PS5-61-OB-8719C | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-28 | PS5-60-04 | PS5 - Milestone B | 1.1 | Closed | 12 | 30 | FEBRUARY
T-039-3797 | PS5-22-OB-3007D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone B | 1.1 | In progress |  | 30 | OCTOBER
T-881-3798 | PS5-58-OB-8613D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone B | 1.1 | In progress |  | 41 | NOVEMBER
T-493-3799 | PS5-78-OB-4195C | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-07-12 | PS5-82-07 | PS5 - Milestone D | 3 | Closed | 42 | 15 | JULY
T-219-3800 | PS5-69-OB-9456D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone I | 8 | To be completed |  | 33 | DECEMBER
T-660-3801 | PS5-38-IK-5007D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-04-16 | PS5-04-01 | PS5 - Milestone B | 1.1 | Closed | 31 | 23 | APRIL
T-852-3802 | PS5-44-OB-7387B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | To be completed |  | 32 | NOVEMBER
T-790-3803 | PS5-22-UR-4639A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | To be completed |  | 44 | OCTOBER
T-989-3804 | PS5-79-UR-6392D | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone E | 4 | To be completed |  | 26 | SEPTEMBER
T-009-3805 | PS5-26-OB-2254A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone E | 4 | To be completed |  | 29 | NOVEMBER
T-004-3806 | PS5-72-IK-5424D | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone I | 8 | On hold |  | 13 | DECEMBER
T-035-3807 | PS5-94-OB-8998B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-01-18 | PS5-04-01 | PS5 - Milestone C | 2 | Closed | 22 | 11 | JANUARY
T-551-3808 | PS5-63-UR-3509D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone A | 1 | To be completed |  | 25 | AUGUST
T-945-3809 | PS5-26-IK-5141B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone G | 6 | To be completed |  | 22 | OCTOBER
T-053-3810 | PS5-49-OB-3720A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone H | 7 | To be completed |  | 44 | OCTOBER
T-749-3811 | PS5-39-UR-2079C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | To be completed |  | 10 | NOVEMBER
T-762-3812 | PS5-37-OB-7739D | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone D | 3 | To be completed |  | 19 | OCTOBER
T-466-3813 | PS5-69-IK-1458B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-07-16 | PS5-01-06 | PS5 - Milestone C | 2 | Closed | 20 | 22 | JULY
T-735-3814 | PS5-95-OB-1373D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | To be completed |  | 36 | SEPTEMBER
T-568-3815 | PS5-90-OB-4088D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone D | 3 | To be completed |  | 14 | AUGUST
T-339-3816 | PS5-07-OB-9571A | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone I | 8 | To be completed |  | 48 | OCTOBER
T-817-3817 | PS5-30-UR-4118B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone F | 5 | To be completed |  | 8 | OCTOBER
T-814-3818 | PS5-19-UR-5295C | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-05-18 | PS5-99-03 | PS5 - Milestone C | 2 | Closed | 48 | 13 | MAY
T-197-3819 | PS5-89-IK-7392D | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone E | 4 | In progress |  | 19 | OCTOBER
T-571-3820 | PS5-69-OB-7135C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-02-21 | PS5-09-03 | PS5 - Milestone B | 1.1 | Closed | 23 | 8 | FEBRUARY
T-452-3821 | PS5-41-IK-7850B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone C | 2 | To be completed |  | 45 | AUGUST
T-533-3822 | PS5-48-UR-1444D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-02-19 | PS5-05-02 | PS5 - Milestone G | 6 | Closed | 20 | 33 | FEBRUARY
T-219-3823 | PS5-07-OB-6522C | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-05-23 | PS5-11-02 | PS5 - Milestone E | 4 | Closed | 16 | 24 | MAY
T-940-3824 | PS5-77-OB-9972B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | To be completed |  | 11 | DECEMBER
T-847-3825 | PS5-36-OB-9110B | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone A | 1 | To be completed |  | 29 | SEPTEMBER
T-170-3826 | PS5-89-IK-5567A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone A | 1 | On hold |  | 47 | AUGUST
T-446-3827 | PS5-87-OB-7664B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | To be completed |  | 29 | AUGUST
T-341-3828 | PS5-81-IK-5453B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-11-16 | PS5-99-03 | PS5 - Milestone F | 5 | Closed | 35 | 44 | NOVEMBER
T-585-3829 | PS5-15-UR-2969A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | In progress |  | 26 | NOVEMBER
T-055-3830 | PS5-75-OB-6335B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone E | 4 | To be completed |  | 16 | OCTOBER
T-338-3831 | PS5-90-UR-5841B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-01-24 | PS5-09-03 | PS5 - Milestone F | 5 | Closed | 42 | 18 | JANUARY
T-163-3832 | PS5-51-UR-5839D | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | To be completed |  | 31 | DECEMBER
T-515-3833 | PS5-66-OB-2510B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone E | 4 | In progress |  | 38 | AUGUST
T-308-3834 | PS5-26-UR-1200B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-07-15 | PS5-10-01 | PS5 - Milestone F | 5 | Closed | 23 | 44 | JULY
T-228-3835 | PS5-61-OB-8212C | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone D | 3 | To be completed |  | 17 | OCTOBER
T-406-3836 | PS5-31-UR-5554A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-10-23 | PS5-05-01 | PS5 - Milestone C | 2 | Closed | 36 | 9 | OCTOBER
T-564-3837 | PS5-20-OB-4243A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | On hold |  | 17 | SEPTEMBER
T-552-3838 | PS5-33-OB-3402C | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone B | 1.1 | In progress |  | 14 | OCTOBER
T-858-3839 | PS5-95-OB-5382C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone F | 5 | To be completed |  | 17 | NOVEMBER
T-137-3840 | PS5-60-OB-7127B | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone B | 1.1 | To be completed |  | 12 | AUGUST
T-566-3841 | PS5-67-IK-1309B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-06-27 | PS5-07-02 | PS5 - Milestone H | 7 | Closed | 37 | 4 | JUNE
T-168-3842 | PS5-96-OB-3791D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-01-22 | PS5-01-07 | PS5 - Milestone B | 1.1 | Closed | 8 | 14 | JANUARY
T-602-3843 | PS5-82-OB-1918C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone C | 2 | To be completed |  | 28 | SEPTEMBER
T-739-3844 | PS5-19-UR-4208D | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone D | 3 | To be completed |  | 15 | OCTOBER
T-903-3845 | PS5-34-UR-3996B | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone A | 1 | In progress |  | 22 | SEPTEMBER
T-127-3846 | PS5-37-UR-7517B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone A | 1 | In progress |  | 16 | NOVEMBER
T-898-3847 | PS5-47-OB-6592C | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | To be completed |  | 44 | AUGUST
T-726-3848 | PS5-16-OB-8773D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone H | 7 | To be completed |  | 40 | OCTOBER
T-833-3849 | PS5-45-UR-1492A | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-01-03 | PS5-04-04 | PS5 - Milestone G | 6 | Closed | 31 | 26 | JANUARY
T-525-3850 | PS5-22-OB-2208D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone H | 7 | To be completed |  | 28 | OCTOBER
T-594-3851 | PS5-72-UR-5680A | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-07-14 | PS5-01-09 | PS5 - Milestone D | 3 | Closed | 34 | 7 | JULY
T-909-3852 | PS5-61-IK-6216B | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-05-07 | PS5-99-02 | PS5 - Milestone H | 7 | Closed | 41 | 27 | MAY
T-267-3853 | PS5-58-IK-4889C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-01-23 | PS5-82-02 | PS5 - Milestone G | 6 | Closed | 39 | 36 | JANUARY
T-793-3854 | PS5-41-OB-1463D | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone H | 7 | In progress |  | 7 | OCTOBER
T-200-3855 | PS5-12-UR-1118B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-05-23 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 7 | 23 | MAY
T-889-3856 | PS5-34-OB-5378D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | On hold |  | 35 | AUGUST
T-703-3857 | PS5-38-OB-2916C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone I | 8 | In progress |  | 21 | OCTOBER
T-331-3858 | PS5-26-UR-7690A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone H | 7 | On hold |  | 35 | DECEMBER
T-272-3859 | PS5-74-OB-5207D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone A | 1 | To be completed |  | 38 | SEPTEMBER
T-456-3860 | PS5-40-UR-5199C | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | To be completed |  | 45 | SEPTEMBER
T-893-3861 | PS5-96-OB-4441B | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone H | 7 | In progress |  | 42 | NOVEMBER
T-355-3862 | PS5-73-IK-5213B | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone D | 3 | To be completed |  | 5 | DECEMBER
T-594-3863 | PS5-78-IK-2077D | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-03-02 | PS5-63-01 | PS5 - Milestone H | 7 | Closed | 42 | 40 | MARCH
T-161-3864 | PS5-37-OB-4581A | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone E | 4 | To be completed |  | 45 | AUGUST
T-323-3865 | PS5-11-UR-3412C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-05-21 | PS5-61-07 | PS5 - Milestone F | 5 | Closed | 31 | 16 | MAY
T-786-3866 | PS5-90-IK-2803B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-10-18 | PS5-63-04 | PS5 - Milestone D | 3 | Closed | 33 | 30 | OCTOBER
T-571-3867 | PS5-35-UR-3022D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone I | 8 | To be completed |  | 22 | NOVEMBER
T-152-3868 | PS5-20-UR-1319B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-26 | PS5-60-04 | PS5 - Milestone C | 2 | Closed | 33 | 37 | MAY
T-598-3869 | PS5-89-OB-3881A | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | In progress |  | 44 | DECEMBER
T-882-3870 | PS5-85-UR-9718B | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | To be completed |  | 12 | NOVEMBER
T-918-3871 | PS5-93-IK-9034C | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone E | 4 | To be completed |  | 39 | AUGUST
T-692-3872 | PS5-79-OB-5599A | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone C | 2 | In progress |  | 39 | OCTOBER
T-376-3873 | PS5-24-IK-3442B | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-05-01 | PS5-01-08 | PS5 - Milestone F | 5 | Closed | 7 | 29 | MAY
T-738-3874 | PS5-79-OB-4937A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-04-10 | PS5-05-03 | PS5 - Milestone G | 6 | Closed | 29 | 34 | APRIL
T-241-3875 | PS5-79-OB-1121B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone A | 1 | In progress |  | 37 | NOVEMBER
T-515-3876 | PS5-89-OB-9102B | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-07-21 | PS5-03-02 | PS5 - Milestone B | 1.1 | Closed | 10 | 31 | JULY
T-087-3877 | PS5-41-OB-1164B | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone E | 4 | In progress |  | 45 | NOVEMBER
T-839-3878 | PS5-91-OB-3898A | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone A | 1 | On hold |  | 22 | DECEMBER
T-494-3879 | PS5-31-OB-8198D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-07-02 | PS5-02-03 | PS5 - Milestone E | 4 | Closed | 11 | 36 | JULY
T-011-3880 | PS5-52-OB-5133C | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-03-12 | PS5-09-01 | PS5 - Milestone C | 2 | Closed | 18 | 34 | MARCH
T-718-3881 | PS5-08-UR-9213A | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-01-06 | PS5-10-01 | PS5 - Milestone E | 4 | Closed | 36 | 30 | JANUARY
T-891-3882 | PS5-23-IK-5736A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-12-11 | PS5-13-01 | PS5 - Milestone F | 5 | Closed | 24 | 15 | DECEMBER
T-281-3883 | PS5-01-OB-1702D | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-12-07 | PS5-02-02 | PS5 - Milestone B | 1.1 | Closed | 36 | 29 | DECEMBER
T-043-3884 | PS5-06-OB-6905C | CQP05 - Insulation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone G | 6 | To be completed |  | 37 | AUGUST
T-408-3885 | PS5-31-UR-1739C | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-06-14 | PS5-08-02 | PS5 - Milestone G | 6 | Closed | 14 | 25 | JUNE
T-130-3886 | PS5-95-IK-7514B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | To be completed |  | 48 | NOVEMBER
T-769-3887 | PS5-37-IK-5987B | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | To be completed |  | 15 | DECEMBER
T-215-3888 | PS5-98-OB-6955C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-04-21 | PS5-10-02 | PS5 - Milestone I | 8 | Closed | 14 | 29 | APRIL
T-922-3889 | PS5-16-OB-8047B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-07-09 | PS5-11-02 | PS5 - Milestone F | 5 | Closed | 37 | 29 | JULY
T-180-3890 | PS5-97-OB-1825D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-04-08 | PS5-03-03 | PS5 - Milestone C | 2 | Closed | 20 | 8 | APRIL
T-370-3891 | PS5-53-OB-1676B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-08-22 | PS5-10-04 | PS5 - Milestone A | 1 | Closed | 38 | 16 | AUGUST
T-099-3892 | PS5-34-OB-4865C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-02-14 | PS5-01-02 | PS5 - Milestone A | 1 | Closed | 45 | 41 | FEBRUARY
T-650-3893 | PS5-55-UR-5034A | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone B | 1.1 | In progress |  | 30 | AUGUST
T-104-3894 | PS5-26-OB-2942D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-11-15 | PS5-05-02 | PS5 - Milestone G | 6 | Closed | 32 | 5 | NOVEMBER
T-963-3895 | PS5-81-OB-9727D | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-09-15 | PS5-63-04 | PS5 - Milestone B | 1.1 | Closed | 26 | 45 | SEPTEMBER
T-447-3896 | PS5-90-IK-1085D | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-06-05 | PS5-02-02 | PS5 - Milestone D | 3 | Closed | 33 | 21 | JUNE
T-985-3897 | PS5-90-OB-6595B | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-11-09 | PS5-03-01 | PS5 - Milestone E | 4 | Closed | 32 | 43 | NOVEMBER
T-802-3898 | PS5-15-UR-7675A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone B | 1.1 | To be completed |  | 42 | DECEMBER
T-014-3899 | PS5-53-IK-7393A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-05-18 | PS5-11-02 | PS5 - Milestone C | 2 | Closed | 8 | 23 | MAY
T-451-3900 | PS5-62-OB-3001C | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-10-26 | PS5-11-03 | PS5 - Milestone I | 8 | Closed | 28 | 11 | OCTOBER
T-887-3901 | PS5-87-OB-1757B | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-03-07 | PS5-02-03 | PS5 - Milestone C | 2 | Closed | 35 | 46 | MARCH
T-406-3902 | PS5-65-IK-1097D | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone F | 5 | To be completed |  | 11 | DECEMBER
T-080-3903 | PS5-14-UR-4034D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone H | 7 | To be completed |  | 46 | DECEMBER
T-153-3904 | PS5-37-OB-9201C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone B | 1.1 | On hold |  | 47 | AUGUST
T-316-3905 | PS5-76-IK-9252A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-05-20 | PS5-01-04 | PS5 - Milestone C | 2 | Closed | 27 | 17 | MAY
T-034-3906 | PS5-28-OB-9099D | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone A | 1 | To be completed |  | 23 | AUGUST
T-655-3907 | PS5-27-OB-7471A | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone H | 7 | To be completed |  | 7 | OCTOBER
T-097-3908 | PS5-19-OB-2569A | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | To be completed |  | 23 | OCTOBER
T-808-3909 | PS5-60-OB-2542D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-06-15 | PS5-08-02 | PS5 - Milestone C | 2 | Closed | 40 | 9 | JUNE
T-751-3910 | PS5-27-OB-5646C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone B | 1.1 | In progress |  | 31 | AUGUST
T-996-3911 | PS5-02-OB-8694D | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone A | 1 | In progress |  | 29 | SEPTEMBER
T-191-3912 | PS5-66-OB-6573C | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone D | 3 | In progress |  | 25 | NOVEMBER
T-416-3913 | PS5-58-IK-5413D | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | To be completed |  | 31 | AUGUST
T-837-3914 | PS5-35-UR-8401C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone G | 6 | In progress |  | 11 | AUGUST
T-613-3915 | PS5-73-OB-2886C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone H | 7 | To be completed |  | 24 | AUGUST
T-518-3916 | PS5-09-UR-5033C | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone F | 5 | To be completed |  | 13 | AUGUST
T-403-3917 | PS5-68-OB-1942C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone G | 6 | On hold |  | 33 | OCTOBER
T-377-3918 | PS5-06-UR-8737A | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone E | 4 | In progress |  | 10 | NOVEMBER
T-574-3919 | PS5-39-OB-7476A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | To be completed |  | 15 | OCTOBER
T-019-3920 | PS5-60-OB-5884C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone H | 7 | On hold |  | 9 | DECEMBER
T-813-3921 | PS5-86-OB-6104D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | In progress |  | 4 | DECEMBER
T-892-3922 | PS5-55-OB-8348A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | To be completed |  | 47 | AUGUST
T-356-3923 | PS5-56-OB-6626C | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone F | 5 | To be completed |  | 28 | NOVEMBER
T-495-3924 | PS5-11-IK-8167A | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone E | 4 | To be completed |  | 11 | DECEMBER
T-901-3925 | PS5-57-OB-2839D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-06-18 | PS5-05-02 | PS5 - Milestone C | 2 | Closed | 8 | 26 | JUNE
T-228-3926 | PS5-46-UR-3904B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-04-25 | PS5-63-01 | PS5 - Milestone G | 6 | Closed | 18 | 26 | APRIL
T-676-3927 | PS5-39-IK-5046C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-09-15 | PS5-10-01 | PS5 - Milestone A | 1 | Closed | 39 | 24 | SEPTEMBER
T-434-3928 | PS5-60-IK-4574A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-11-15 | PS5-07-02 | PS5 - Milestone I | 8 | Closed | 40 | 25 | NOVEMBER
T-477-3929 | PS5-23-UR-6932C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | To be completed |  | 41 | DECEMBER
T-587-3930 | PS5-44-OB-2479B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone H | 7 | To be completed |  | 36 | SEPTEMBER
T-207-3931 | PS5-52-OB-7594D | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-03-05 | PS5-01-05 | PS5 - Milestone B | 1.1 | Closed | 34 | 25 | MARCH
T-812-3932 | PS5-32-OB-9976C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone E | 4 | In progress |  | 31 | DECEMBER
T-516-3933 | PS5-26-OB-6749A | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | To be completed |  | 12 | OCTOBER
T-888-3934 | PS5-77-UR-2279C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone G | 6 | On hold |  | 34 | NOVEMBER
T-481-3935 | PS5-33-OB-9205B | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-07-28 | PS5-11-01 | PS5 - Milestone C | 2 | Closed | 31 | 22 | JULY
T-464-3936 | PS5-13-OB-5220B | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone F | 5 | In progress |  | 47 | DECEMBER
T-711-3937 | PS5-07-OB-7321B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-04-04 | PS5-04-03 | PS5 - Milestone A | 1 | Closed | 22 | 40 | APRIL
T-476-3938 | PS5-75-OB-9242B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-08-09 | PS5-60-07 | PS5 - Milestone F | 5 | Closed | 36 | 20 | AUGUST
T-690-3939 | PS5-20-OB-7271C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone H | 7 | In progress |  | 24 | OCTOBER
T-024-3940 | PS5-71-OB-5272A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | In progress |  | 37 | SEPTEMBER
T-440-3941 | PS5-04-IK-4376C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-03-05 | PS5-03-03 | PS5 - Milestone I | 8 | Closed | 48 | 40 | MARCH
T-533-3942 | PS5-57-OB-3505B | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-05-26 | PS5-05-01 | PS5 - Milestone E | 4 | Closed | 22 | 14 | MAY
T-970-3943 | PS5-52-UR-2516D | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone C | 2 | To be completed |  | 14 | AUGUST
T-146-3944 | PS5-89-IK-1960A | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | To be completed |  | 47 | OCTOBER
T-353-3945 | PS5-70-OB-5699D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-08-28 | PS5-60-07 | PS5 - Milestone E | 4 | Closed | 48 | 28 | AUGUST
T-719-3946 | PS5-10-OB-5999C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone G | 6 | To be completed |  | 46 | OCTOBER
T-222-3947 | PS5-80-UR-2055A | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone F | 5 | To be completed |  | 24 | DECEMBER
T-143-3948 | PS5-32-UR-8271D | CQP02 - Valve Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-04-14 | PS5-62-02 | PS5 - Milestone B | 1.1 | Closed | 42 | 11 | APRIL
T-376-3949 | PS5-19-UR-7594B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-12-22 | PS5-06-01 | PS5 - Milestone F | 5 | Closed | 19 | 46 | DECEMBER
T-647-3950 | PS5-37-OB-4076A | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone C | 2 | To be completed |  | 7 | DECEMBER
T-799-3951 | PS5-65-OB-6784C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-06-13 | PS5-02-01 | PS5 - Milestone A | 1 | Closed | 8 | 41 | JUNE
T-707-3952 | PS5-98-OB-5282A | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone C | 2 | On hold |  | 9 | OCTOBER
T-569-3953 | PS5-66-IK-6744A | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-09-08 | PS5-03-01 | PS5 - Milestone A | 1 | Closed | 47 | 47 | SEPTEMBER
T-213-3954 | PS5-70-OB-8696D | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone E | 4 | On hold |  | 21 | AUGUST
T-843-3955 | PS5-88-OB-7055B | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone D | 3 | To be completed |  | 29 | NOVEMBER
T-193-3956 | PS5-46-OB-5832B | CQH02 - AHU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-07-04 | PS5-06-03 | PS5 - Milestone B | 1.1 | Closed | 23 | 9 | JULY
T-942-3957 | PS5-69-IK-9415B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone G | 6 | In progress |  | 35 | DECEMBER
T-932-3958 | PS5-41-OB-2305D | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone H | 7 | To be completed |  | 34 | SEPTEMBER
T-360-3959 | PS5-18-OB-5004D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-05-01 | PS5-63-01 | PS5 - Milestone D | 3 | Closed | 9 | 38 | MAY
T-371-3960 | PS5-22-OB-2527D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone G | 6 | In progress |  | 15 | NOVEMBER
T-736-3961 | PS5-05-OB-1315B | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-04-02 | PS5-62-02 | PS5 - Milestone I | 8 | Closed | 15 | 4 | APRIL
T-605-3962 | PS5-39-OB-3736A | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-01-16 | PS5-61-07 | PS5 - Milestone D | 3 | Closed | 18 | 11 | JANUARY
T-209-3963 | PS5-07-UR-3636A | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | To be completed |  | 48 | OCTOBER
T-742-3964 | PS5-76-UR-4717C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-10-22 | PS5-61-01 | PS5 - Milestone E | 4 | Closed | 11 | 35 | OCTOBER
T-638-3965 | PS5-51-IK-1972B | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-02-19 | PS5-07-03 | PS5 - Milestone F | 5 | Closed | 24 | 47 | FEBRUARY
T-116-3966 | PS5-27-UR-8935A | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-09-14 | PS5-01-03 | PS5 - Milestone E | 4 | Closed | 42 | 10 | SEPTEMBER
T-549-3967 | PS5-72-OB-3963C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone A | 1 | To be completed |  | 28 | AUGUST
T-924-3968 | PS5-55-UR-8913C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-10-07 | PS5-60-04 | PS5 - Milestone D | 3 | Closed | 31 | 41 | OCTOBER
T-971-3969 | PS5-32-OB-7507D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-10-15 | PS5-10-01 | PS5 - Milestone H | 7 | Closed | 5 | 9 | OCTOBER
T-550-3970 | PS5-75-OB-8328C | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone D | 3 | On hold |  | 17 | NOVEMBER
T-897-3971 | PS5-95-UR-7052B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-06-03 | PS5-04-03 | PS5 - Milestone C | 2 | Closed | 16 | 8 | JUNE
T-909-3972 | PS5-51-UR-9984B | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone G | 6 | To be completed |  | 48 | DECEMBER
T-948-3973 | PS5-11-IK-3687B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-03-04 | PS5-60-07 | PS5 - Milestone C | 2 | Closed | 45 | 36 | MARCH
T-090-3974 | PS5-77-UR-4298A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone F | 5 | On hold |  | 46 | NOVEMBER
T-679-3975 | PS5-15-IK-6741C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-08-08 | PS5-60-01 | PS5 - Milestone G | 6 | Closed | 26 | 45 | AUGUST
T-329-3976 | PS5-33-IK-9692C | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone B | 1.1 | In progress |  | 6 | AUGUST
T-094-3977 | PS5-20-OB-5547D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone C | 2 | In progress |  | 30 | SEPTEMBER
T-021-3978 | PS5-86-OB-5266B | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone E | 4 | In progress |  | 21 | AUGUST
T-566-3979 | PS5-34-OB-4446C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | To be completed |  | 8 | SEPTEMBER
T-943-3980 | PS5-80-OB-6891D | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone B | 1.1 | In progress |  | 26 | AUGUST
T-711-3981 | PS5-52-OB-7624B | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | To be completed |  | 36 | AUGUST
T-666-3982 | PS5-65-UR-8769B | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone I | 8 | In progress |  | 26 | SEPTEMBER
T-460-3983 | PS5-54-IK-9857A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-10-20 | PS5-99-03 | PS5 - Milestone F | 5 | Closed | 45 | 33 | OCTOBER
T-863-3984 | PS5-67-OB-2737B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-05-05 | PS5-99-02 | PS5 - Milestone D | 3 | Closed | 16 | 4 | MAY
T-023-3985 | PS5-20-OB-4088C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-09-08 | PS5-08-01 | PS5 - Milestone H | 7 | Closed | 18 | 33 | SEPTEMBER
T-347-3986 | PS5-77-IK-5540D | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone I | 8 | To be completed |  | 41 | OCTOBER
T-752-3987 | PS5-89-IK-1844B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone I | 8 | To be completed |  | 29 | AUGUST
T-997-3988 | PS5-13-UR-3398A | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone H | 7 | To be completed |  | 12 | DECEMBER
T-140-3989 | PS5-55-OB-1665B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone D | 3 | In progress |  | 6 | OCTOBER
T-992-3990 | PS5-40-OB-3036D | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-12-28 | PS5-01-06 | PS5 - Milestone H | 7 | Closed | 41 | 14 | DECEMBER
T-213-3991 | PS5-36-OB-2645D | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone A | 1 | To be completed |  | 24 | OCTOBER
T-158-3992 | PS5-01-UR-8119C | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | To be completed |  | 17 | NOVEMBER
T-859-3993 | PS5-64-OB-2813A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-01-13 | PS5-02-03 | PS5 - Milestone F | 5 | Closed | 33 | 18 | JANUARY
T-742-3994 | PS5-26-OB-1919C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone H | 7 | In progress |  | 31 | NOVEMBER
T-381-3995 | PS5-69-UR-4796A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone B | 1.1 | In progress |  | 38 | AUGUST
T-489-3996 | PS5-35-UR-7738C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-01-03 | PS5-09-03 | PS5 - Milestone H | 7 | Closed | 48 | 28 | JANUARY
T-198-3997 | PS5-85-OB-4966D | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone E | 4 | To be completed |  | 27 | OCTOBER
T-865-3998 | PS5-52-OB-4707C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | In progress |  | 44 | DECEMBER
T-707-3999 | PS5-42-UR-9721D | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone D | 3 | On hold |  | 46 | AUGUST
T-217-4000 | PS5-42-OB-7405B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone F | 5 | On hold |  | 16 | OCTOBER
T-111-4001 | PS5-78-OB-2724C | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-12-23 | PS5-60-07 | PS5 - Milestone H | 7 | Closed | 42 | 45 | DECEMBER
T-154-4002 | PS5-29-UR-4513D | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone C | 2 | In progress |  | 44 | SEPTEMBER
T-291-4003 | PS5-34-OB-7310C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-10-12 | PS5-82-01 | PS5 - Milestone F | 5 | Closed | 43 | 6 | OCTOBER
T-882-4004 | PS5-46-OB-1068B | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone C | 2 | To be completed |  | 35 | AUGUST
T-760-4005 | PS5-23-OB-2513B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone G | 6 | In progress |  | 17 | SEPTEMBER
T-895-4006 | PS5-48-IK-2928B | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone C | 2 | In progress |  | 15 | NOVEMBER
T-867-4007 | PS5-54-IK-1266D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone I | 8 | To be completed |  | 28 | NOVEMBER
T-993-4008 | PS5-37-IK-3796A | CQP01 - Pipe Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-08-12 | PS5-60-07 | PS5 - Milestone H | 7 | Closed | 21 | 46 | AUGUST
T-269-4009 | PS5-14-OB-8567B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-05-02 | PS5-01-08 | PS5 - Milestone A | 1 | Closed | 25 | 7 | MAY
T-910-4010 | PS5-94-UR-8963C | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-09-14 | PS5-82-02 | PS5 - Milestone A | 1 | Closed | 16 | 38 | SEPTEMBER
T-279-4011 | PS5-31-IK-3541C | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone G | 6 | In progress |  | 31 | DECEMBER
T-517-4012 | PS5-26-OB-5020D | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-01-11 | PS5-03-23 | PS5 - Milestone G | 6 | Closed | 37 | 45 | JANUARY
T-356-4013 | PS5-87-UR-9528D | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-10 | PS5-60-10 | PS5 - Milestone B | 1.1 | Closed | 47 | 19 | JUNE
T-570-4014 | PS5-30-IK-2591B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-06-18 | PS5-99-02 | PS5 - Milestone G | 6 | Closed | 39 | 17 | JUNE
T-926-4015 | PS5-42-IK-1270D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone G | 6 | In progress |  | 31 | NOVEMBER
T-860-4016 | PS5-68-IK-9458D | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone I | 8 | To be completed |  | 20 | DECEMBER
T-616-4017 | PS5-81-OB-3886A | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-03-13 | PS5-11-01 | PS5 - Milestone C | 2 | Closed | 4 | 25 | MARCH
T-647-4018 | PS5-85-OB-9262A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone D | 3 | To be completed |  | 8 | DECEMBER
T-555-4019 | PS5-45-UR-2437D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone F | 5 | To be completed |  | 19 | SEPTEMBER
T-186-4020 | PS5-26-OB-2144D | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-10-05 | PS5-12-01 | PS5 - Milestone G | 6 | Closed | 9 | 21 | OCTOBER
T-933-4021 | PS5-86-IK-1432A | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone C | 2 | To be completed |  | 4 | DECEMBER
T-712-4022 | PS5-99-IK-6309B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-10-18 | PS5-01-06 | PS5 - Milestone D | 3 | Closed | 24 | 15 | OCTOBER
T-631-4023 | PS5-25-IK-5206A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | In progress |  | 32 | SEPTEMBER
T-370-4024 | PS5-29-OB-3905D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | To be completed |  | 16 | NOVEMBER
T-720-4025 | PS5-68-IK-5589A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | In progress |  | 43 | DECEMBER
T-769-4026 | PS5-52-OB-9613C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-03-06 | PS5-03-01 | PS5 - Milestone A | 1 | Closed | 34 | 12 | MARCH
T-524-4027 | PS5-87-OB-7353B | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-04-14 | PS5-07-02 | PS5 - Milestone F | 5 | Closed | 28 | 45 | APRIL
T-340-4028 | PS5-42-OB-5773B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-12-05 | PS5-03-03 | PS5 - Milestone I | 8 | Closed | 30 | 41 | DECEMBER
T-569-4029 | PS5-71-OB-7932D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone I | 8 | In progress |  | 11 | SEPTEMBER
T-959-4030 | PS5-72-OB-9701C | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-05-10 | PS5-08-01 | PS5 - Milestone A | 1 | Closed | 18 | 33 | MAY
T-939-4031 | PS5-80-UR-1027A | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | To be completed |  | 47 | NOVEMBER
T-805-4032 | PS5-94-IK-7380C | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | To be completed |  | 23 | SEPTEMBER
T-705-4033 | PS5-03-OB-6185B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone F | 5 | In progress |  | 13 | DECEMBER
T-772-4034 | PS5-61-OB-2783D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone I | 8 | To be completed |  | 6 | SEPTEMBER
T-370-4035 | PS5-07-UR-5060B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone F | 5 | On hold |  | 34 | AUGUST
T-799-4036 | PS5-17-OB-7151B | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone E | 4 | In progress |  | 44 | AUGUST
T-866-4037 | PS5-16-OB-7908D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-05-23 | PS5-82-01 | PS5 - Milestone B | 1.1 | Closed | 6 | 35 | MAY
T-846-4038 | PS5-68-UR-3336B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-08-12 | PS5-12-01 | PS5 - Milestone F | 5 | Closed | 42 | 16 | AUGUST
T-023-4039 | PS5-13-OB-4366C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-07-05 | PS5-09-01 | PS5 - Milestone D | 3 | Closed | 30 | 47 | JULY
T-655-4040 | PS5-29-IK-4707B | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone H | 7 | On hold |  | 20 | AUGUST
T-774-4041 | PS5-07-OB-3856A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone F | 5 | To be completed |  | 4 | AUGUST
T-911-4042 | PS5-40-OB-4032A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone H | 7 | In progress |  | 47 | OCTOBER
T-652-4043 | PS5-03-UR-9549D | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-09-02 | PS5-60-10 | PS5 - Milestone F | 5 | Closed | 18 | 15 | SEPTEMBER
T-589-4044 | PS5-83-UR-2023D | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-07-05 | PS5-09-04 | PS5 - Milestone A | 1 | Closed | 47 | 26 | JULY
T-337-4045 | PS5-66-IK-1335C | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-02-26 | PS5-12-01 | PS5 - Milestone A | 1 | Closed | 32 | 31 | FEBRUARY
T-898-4046 | PS5-19-IK-5730B | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone A | 1 | To be completed |  | 37 | DECEMBER
T-638-4047 | PS5-73-UR-6503B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | In progress |  | 40 | OCTOBER
T-904-4048 | PS5-90-UR-5978A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-07-24 | PS5-05-03 | PS5 - Milestone I | 8 | Closed | 39 | 33 | JULY
T-139-4049 | PS5-35-OB-7298C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone D | 3 | On hold |  | 35 | DECEMBER
T-264-4050 | PS5-08-UR-6270B | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | To be completed |  | 36 | DECEMBER
T-086-4051 | PS5-87-UR-1538D | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone C | 2 | On hold |  | 13 | AUGUST
T-670-4052 | PS5-35-OB-9626B | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone F | 5 | To be completed |  | 20 | SEPTEMBER
T-562-4053 | PS5-02-OB-5381A | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-05-21 | PS5-09-04 | PS5 - Milestone I | 8 | Closed | 41 | 27 | MAY
T-097-4054 | PS5-35-OB-3059C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-03-27 | PS5-12-01 | PS5 - Milestone I | 8 | Closed | 34 | 13 | MARCH
T-407-4055 | PS5-56-OB-2413A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-06-12 | PS5-01-07 | PS5 - Milestone H | 7 | Closed | 28 | 21 | JUNE
T-159-4056 | PS5-10-UR-6387C | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-04-28 | PS5-07-03 | PS5 - Milestone C | 2 | Closed | 4 | 18 | APRIL
T-629-4057 | PS5-24-UR-2338B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone C | 2 | In progress |  | 44 | NOVEMBER
T-201-4058 | PS5-43-OB-3934A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-09-15 | PS5-02-02 | PS5 - Milestone B | 1.1 | Closed | 6 | 4 | SEPTEMBER
T-759-4059 | PS5-15-OB-1726D | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone A | 1 | To be completed |  | 4 | SEPTEMBER
T-738-4060 | PS5-78-UR-9925C | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-11-22 | PS5-07-01 | PS5 - Milestone H | 7 | Closed | 45 | 41 | NOVEMBER
T-077-4061 | PS5-80-OB-2058B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone E | 4 | To be completed |  | 29 | NOVEMBER
T-407-4062 | PS5-31-OB-4274D | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-06-13 | PS5-07-02 | PS5 - Milestone H | 7 | Closed | 25 | 20 | JUNE
T-980-4063 | PS5-72-IK-7811C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone E | 4 | To be completed |  | 38 | OCTOBER
T-695-4064 | PS5-94-UR-1976B | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone F | 5 | In progress |  | 42 | AUGUST
T-204-4065 | PS5-39-IK-7467D | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone C | 2 | In progress |  | 12 | NOVEMBER
T-065-4066 | PS5-75-OB-4400B | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-01-12 | PS5-82-02 | PS5 - Milestone G | 6 | Closed | 23 | 13 | JANUARY
T-761-4067 | PS5-85-OB-5333D | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | To be completed |  | 4 | AUGUST
T-465-4068 | PS5-68-OB-1348A | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-10-15 | PS5-01-01 | PS5 - Milestone I | 8 | Closed | 27 | 19 | OCTOBER
T-878-4069 | PS5-52-IK-8948C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone I | 8 | In progress |  | 4 | SEPTEMBER
T-646-4070 | PS5-80-UR-2023A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone C | 2 | To be completed |  | 41 | SEPTEMBER
T-016-4071 | PS5-75-OB-3555A | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone E | 4 | In progress |  | 45 | AUGUST
T-589-4072 | PS5-98-UR-9228C | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone F | 5 | In progress |  | 29 | DECEMBER
T-964-4073 | PS5-90-UR-9867A | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-03-20 | PS5-09-01 | PS5 - Milestone I | 8 | Closed | 18 | 26 | MARCH
T-177-4074 | PS5-89-UR-9574B | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | In progress |  | 25 | AUGUST
T-977-4075 | PS5-59-UR-8164D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone G | 6 | To be completed |  | 45 | NOVEMBER
T-494-4076 | PS5-69-OB-7327B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-07-05 | PS5-01-09 | PS5 - Milestone G | 6 | Closed | 27 | 36 | JULY
T-087-4077 | PS5-76-UR-4120C | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-12-27 | PS5-04-03 | PS5 - Milestone I | 8 | Closed | 30 | 29 | DECEMBER
T-355-4078 | PS5-88-UR-5317A | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone F | 5 | To be completed |  | 23 | AUGUST
T-347-4079 | PS5-65-IK-4772B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-01-13 | PS5-11-01 | PS5 - Milestone G | 6 | Closed | 47 | 11 | JANUARY
T-038-4080 | PS5-06-OB-7755A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-04-14 | PS5-01-09 | PS5 - Milestone I | 8 | Closed | 9 | 48 | APRIL
T-059-4081 | PS5-44-OB-1515D | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone A | 1 | On hold |  | 32 | SEPTEMBER
T-461-4082 | PS5-28-IK-2388C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone E | 4 | To be completed |  | 46 | SEPTEMBER
T-257-4083 | PS5-47-UR-3799C | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone H | 7 | To be completed |  | 7 | NOVEMBER
T-533-4084 | PS5-58-IK-5781C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-03-22 | PS5-05-01 | PS5 - Milestone E | 4 | Closed | 15 | 5 | MARCH
T-784-4085 | PS5-31-UR-2853C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone F | 5 | To be completed |  | 5 | DECEMBER
T-660-4086 | PS5-13-UR-5899D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | To be completed |  | 42 | SEPTEMBER
T-924-4087 | PS5-38-IK-4876A | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | To be completed |  | 34 | OCTOBER
T-192-4088 | PS5-52-OB-5713B | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-05-07 | PS5-82-02 | PS5 - Milestone I | 8 | Closed | 14 | 24 | MAY
T-331-4089 | PS5-70-OB-1762C | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone I | 8 | In progress |  | 17 | SEPTEMBER
T-922-4090 | PS5-44-OB-3548D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone H | 7 | To be completed |  | 17 | SEPTEMBER
T-540-4091 | PS5-52-UR-9938D | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-05-15 | PS5-11-01 | PS5 - Milestone H | 7 | Closed | 21 | 34 | MAY
T-540-4092 | PS5-73-OB-5604B | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone B | 1.1 | To be completed |  | 39 | SEPTEMBER
T-096-4093 | PS5-63-OB-6934A | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-06-06 | PS5-03-23 | PS5 - Milestone H | 7 | Closed | 44 | 4 | JUNE
T-751-4094 | PS5-49-IK-9552C | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-12-28 | PS5-03-02 | PS5 - Milestone H | 7 | Closed | 23 | 42 | DECEMBER
T-592-4095 | PS5-99-UR-7495B | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone E | 4 | In progress |  | 29 | AUGUST
T-150-4096 | PS5-75-IK-5628A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone F | 5 | In progress |  | 27 | OCTOBER
T-521-4097 | PS5-31-IK-7777C | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | In progress |  | 7 | AUGUST
T-566-4098 | PS5-04-OB-1199A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone E | 4 | In progress |  | 7 | OCTOBER
T-024-4099 | PS5-89-OB-3154C | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-01-10 | PS5-12-01 | PS5 - Milestone I | 8 | Closed | 44 | 48 | JANUARY
T-612-4100 | PS5-85-UR-9131A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone D | 3 | In progress |  | 14 | NOVEMBER
T-427-4101 | PS5-96-UR-2537D | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-03-15 | PS5-07-03 | PS5 - Milestone F | 5 | Closed | 4 | 21 | MARCH
T-796-4102 | PS5-01-OB-6582C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | To be completed |  | 37 | AUGUST
T-560-4103 | PS5-46-OB-4298C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone C | 2 | In progress |  | 18 | DECEMBER
T-184-4104 | PS5-84-OB-5844C | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | In progress |  | 37 | NOVEMBER
T-083-4105 | PS5-99-UR-8584B | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-01-08 | PS5-09-02 | PS5 - Milestone H | 7 | Closed | 24 | 22 | JANUARY
T-862-4106 | PS5-94-IK-8822C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone G | 6 | To be completed |  | 29 | OCTOBER
T-784-4107 | PS5-99-IK-6289A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone H | 7 | To be completed |  | 9 | SEPTEMBER
T-279-4108 | PS5-14-OB-1693C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-04-18 | PS5-08-01 | PS5 - Milestone I | 8 | Closed | 37 | 14 | APRIL
T-713-4109 | PS5-18-OB-6517B | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | In progress |  | 41 | OCTOBER
T-040-4110 | PS5-50-IK-3529C | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | To be completed |  | 19 | AUGUST
T-201-4111 | PS5-81-OB-9887D | CQP01 - Pipe Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone G | 6 | To be completed |  | 44 | DECEMBER
T-367-4112 | PS5-52-OB-2710A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | To be completed |  | 20 | AUGUST
T-672-4113 | PS5-41-UR-1503B | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-08-13 | PS5-60-10 | PS5 - Milestone F | 5 | Closed | 4 | 30 | AUGUST
T-805-4114 | PS5-62-OB-2520D | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-11-24 | PS5-03-02 | PS5 - Milestone D | 3 | Closed | 5 | 12 | NOVEMBER
T-200-4115 | PS5-67-OB-4548C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-08-24 | PS5-10-04 | PS5 - Milestone H | 7 | Closed | 32 | 12 | AUGUST
T-966-4116 | PS5-34-OB-4505D | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | To be completed |  | 40 | AUGUST
T-410-4117 | PS5-23-OB-8790A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-09-10 | PS5-05-03 | PS5 - Milestone H | 7 | Closed | 14 | 26 | SEPTEMBER
T-446-4118 | PS5-73-OB-7313A | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone D | 3 | To be completed |  | 29 | SEPTEMBER
T-764-4119 | PS5-73-UR-1139A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | On hold |  | 4 | AUGUST
T-567-4120 | PS5-68-OB-3016C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone G | 6 | On hold |  | 48 | OCTOBER
T-770-4121 | PS5-11-OB-5686D | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone C | 2 | To be completed |  | 35 | SEPTEMBER
T-342-4122 | PS5-30-OB-6170D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-01-26 | PS5-07-03 | PS5 - Milestone H | 7 | Closed | 4 | 15 | JANUARY
T-238-4123 | PS5-37-OB-9484B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone F | 5 | To be completed |  | 39 | NOVEMBER
T-648-4124 | PS5-02-IK-7695C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-11-26 | PS5-13-01 | PS5 - Milestone D | 3 | Closed | 39 | 38 | NOVEMBER
T-242-4125 | PS5-97-IK-5899A | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | To be completed |  | 46 | DECEMBER
T-367-4126 | PS5-24-OB-3597D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone H | 7 | To be completed |  | 44 | NOVEMBER
T-333-4127 | PS5-44-UR-1853A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-01-05 | PS5-07-02 | PS5 - Milestone I | 8 | Closed | 10 | 48 | JANUARY
T-993-4128 | PS5-01-OB-7475D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | To be completed |  | 41 | DECEMBER
T-685-4129 | PS5-04-OB-5013D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-10-06 | PS5-03-03 | PS5 - Milestone C | 2 | Closed | 16 | 8 | OCTOBER
T-808-4130 | PS5-97-IK-2201A | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone A | 1 | In progress |  | 46 | AUGUST
T-769-4131 | PS5-04-UR-5625A | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone D | 3 | To be completed |  | 23 | DECEMBER
T-305-4132 | PS5-82-IK-3018A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone A | 1 | In progress |  | 31 | DECEMBER
T-597-4133 | PS5-20-IK-5556B | CQM01 - Pump Installation | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | In progress |  | 32 | NOVEMBER
T-106-4134 | PS5-79-UR-2313A | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone I | 8 | To be completed |  | 35 | AUGUST
T-918-4135 | PS5-74-UR-2698C | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone H | 7 | To be completed |  | 19 | DECEMBER
T-380-4136 | PS5-19-UR-1522A | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone H | 7 | In progress |  | 46 | OCTOBER
T-679-4137 | PS5-45-OB-4204D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone A | 1 | On hold |  | 30 | DECEMBER
T-258-4138 | PS5-28-UR-5573A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone C | 2 | In progress |  | 42 | AUGUST
T-284-4139 | PS5-12-OB-7294D | CQM04 - Vessel | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-04-07 | PS5-04-03 | PS5 - Milestone D | 3 | Closed | 42 | 14 | APRIL
T-576-4140 | PS5-60-UR-3945B | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-09-20 | PS5-01-06 | PS5 - Milestone H | 7 | Closed | 40 | 41 | SEPTEMBER
T-671-4141 | PS5-24-IK-2923A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-08-08 | PS5-60-01 | PS5 - Milestone D | 3 | Closed | 36 | 47 | AUGUST
T-829-4142 | PS5-73-OB-1727B | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-04-02 | PS5-08-01 | PS5 - Milestone B | 1.1 | Closed | 48 | 34 | APRIL
T-761-4143 | PS5-79-UR-8355A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-05-28 | PS5-11-02 | PS5 - Milestone I | 8 | Closed | 26 | 41 | MAY
T-606-4144 | PS5-76-IK-8621D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | On hold |  | 43 | SEPTEMBER
T-651-4145 | PS5-97-UR-4677D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | In progress |  | 10 | SEPTEMBER
T-705-4146 | PS5-58-IK-9810B | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | To be completed |  | 28 | NOVEMBER
T-805-4147 | PS5-17-OB-9575A | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-05-10 | PS5-05-01 | PS5 - Milestone G | 6 | Closed | 47 | 13 | MAY
T-682-4148 | PS5-02-UR-6216A | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-11-23 | PS5-99-02 | PS5 - Milestone I | 8 | Closed | 39 | 22 | NOVEMBER
T-286-4149 | PS5-99-UR-4279C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone B | 1.1 | In progress |  | 10 | NOVEMBER
T-079-4150 | PS5-12-OB-9665B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone H | 7 | To be completed |  | 43 | SEPTEMBER
T-728-4151 | PS5-21-OB-8398A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone F | 5 | In progress |  | 31 | AUGUST
T-734-4152 | PS5-74-IK-2743B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone F | 5 | On hold |  | 21 | NOVEMBER
T-820-4153 | PS5-71-IK-6133A | CQM01 - Pump Installation | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-03-10 | PS5-06-02 | PS5 - Milestone D | 3 | Closed | 16 | 34 | MARCH
T-833-4154 | PS5-69-IK-4885D | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-02-01 | PS5-04-01 | PS5 - Milestone F | 5 | Closed | 12 | 23 | FEBRUARY
T-225-4155 | PS5-18-OB-9749D | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone A | 1 | In progress |  | 12 | SEPTEMBER
T-440-4156 | PS5-73-OB-3934A | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | To be completed |  | 25 | NOVEMBER
T-610-4157 | PS5-84-IK-3791B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | On hold |  | 37 | NOVEMBER
T-460-4158 | PS5-92-OB-6530D | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone I | 8 | To be completed |  | 17 | NOVEMBER
T-650-4159 | PS5-27-OB-1037B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-03-08 | PS5-03-03 | PS5 - Milestone H | 7 | Closed | 8 | 23 | MARCH
T-265-4160 | PS5-52-OB-4129C | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | To be completed |  | 28 | SEPTEMBER
T-089-4161 | PS5-27-UR-3616B | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-08-07 | PS5-07-01 | PS5 - Milestone I | 8 | Closed | 42 | 34 | AUGUST
T-454-4162 | PS5-79-OB-2097B | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | On hold |  | 35 | DECEMBER
T-815-4163 | PS5-86-OB-1425D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone H | 7 | To be completed |  | 14 | SEPTEMBER
T-559-4164 | PS5-46-OB-2495C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-01-02 | PS5-04-03 | PS5 - Milestone I | 8 | Closed | 47 | 27 | JANUARY
T-017-4165 | PS5-87-OB-7223A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone C | 2 | To be completed |  | 5 | AUGUST
T-297-4166 | PS5-29-OB-8079B | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-07-05 | PS5-05-01 | PS5 - Milestone H | 7 | Closed | 7 | 20 | JULY
T-739-4167 | PS5-79-IK-1720A | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-04-08 | PS5-01-01 | PS5 - Milestone C | 2 | Closed | 14 | 19 | APRIL
T-181-4168 | PS5-89-UR-3231D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-12-03 | PS5-13-01 | PS5 - Milestone B | 1.1 | Closed | 36 | 11 | DECEMBER
T-198-4169 | PS5-77-OB-8707C | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | In progress |  | 25 | SEPTEMBER
T-342-4170 | PS5-24-IK-1371C | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-06-14 | PS5-01-08 | PS5 - Milestone A | 1 | Closed | 38 | 19 | JUNE
T-854-4171 | PS5-59-OB-9014A | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone H | 7 | In progress |  | 4 | AUGUST
T-075-4172 | PS5-77-UR-6837D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone C | 2 | On hold |  | 26 | DECEMBER
T-769-4173 | PS5-76-OB-4066D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | To be completed |  | 45 | AUGUST
T-673-4174 | PS5-50-UR-4397B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-08-15 | PS5-61-07 | PS5 - Milestone F | 5 | Closed | 46 | 13 | AUGUST
T-212-4175 | PS5-72-UR-5719A | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | To be completed |  | 48 | SEPTEMBER
T-699-4176 | PS5-06-OB-4328A | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-11-11 | PS5-60-01 | PS5 - Milestone F | 5 | Closed | 45 | 33 | NOVEMBER
T-738-4177 | PS5-20-OB-7570A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-06-26 | PS5-01-04 | PS5 - Milestone E | 4 | Closed | 17 | 5 | JUNE
T-241-4178 | PS5-94-OB-5284B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-02-09 | PS5-07-04 | PS5 - Milestone F | 5 | Closed | 22 | 48 | FEBRUARY
T-822-4179 | PS5-66-IK-8444D | CQP04 - Hydrotest | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-12-24 | PS5-09-01 | PS5 - Milestone F | 5 | Closed | 48 | 21 | DECEMBER
T-236-4180 | PS5-05-IK-6855C | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-02-28 | PS5-12-02 | PS5 - Milestone H | 7 | Closed | 48 | 24 | FEBRUARY
T-177-4181 | PS5-51-IK-9814B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-07-26 | PS5-61-02 | PS5 - Milestone F | 5 | Closed | 13 | 46 | JULY
T-315-4182 | PS5-46-UR-5504A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone A | 1 | To be completed |  | 8 | NOVEMBER
T-259-4183 | PS5-91-IK-9718C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone E | 4 | To be completed |  | 33 | NOVEMBER
T-303-4184 | PS5-56-IK-5828C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone E | 4 | In progress |  | 42 | DECEMBER
T-829-4185 | PS5-36-UR-4802D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-01-14 | PS5-09-02 | PS5 - Milestone I | 8 | Closed | 10 | 46 | JANUARY
T-312-4186 | PS5-14-OB-5621B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-01-26 | PS5-02-02 | PS5 - Milestone A | 1 | Closed | 15 | 15 | JANUARY
T-928-4187 | PS5-01-IK-2403D | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-11-07 | PS5-60-04 | PS5 - Milestone G | 6 | Closed | 35 | 4 | NOVEMBER
T-805-4188 | PS5-15-IK-9485D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | On hold |  | 14 | SEPTEMBER
T-134-4189 | PS5-28-IK-8437C | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone H | 7 | To be completed |  | 17 | DECEMBER
T-635-4190 | PS5-29-OB-1057A | CQE01 - HV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone B | 1.1 | To be completed |  | 8 | NOVEMBER
T-422-4191 | PS5-95-UR-9412B | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone A | 1 | In progress |  | 4 | SEPTEMBER
T-043-4192 | PS5-06-IK-2955A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-07-16 | PS5-82-07 | PS5 - Milestone E | 4 | Closed | 14 | 35 | JULY
T-569-4193 | PS5-56-IK-6907C | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-03-19 | PS5-62-01 | PS5 - Milestone B | 1.1 | Closed | 12 | 36 | MARCH
T-455-4194 | PS5-67-OB-4638C | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-04-12 | PS5-10-06 | PS5 - Milestone F | 5 | Closed | 5 | 44 | APRIL
T-842-4195 | PS5-15-UR-4131C | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-05-25 | PS5-06-03 | PS5 - Milestone E | 4 | Closed | 7 | 36 | MAY
T-069-4196 | PS5-55-OB-9709A | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-09-04 | PS5-99-03 | PS5 - Milestone C | 2 | Closed | 17 | 14 | SEPTEMBER
T-778-4197 | PS5-98-OB-6371C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-08-18 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 27 | 6 | AUGUST
T-407-4198 | PS5-78-UR-3240C | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone B | 1.1 | To be completed |  | 31 | DECEMBER
T-565-4199 | PS5-85-UR-4488D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone C | 2 | To be completed |  | 7 | NOVEMBER
T-202-4200 | PS5-59-IK-8914D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-05-03 | PS5-04-03 | PS5 - Milestone C | 2 | Closed | 31 | 30 | MAY
T-072-4201 | PS5-13-OB-2196B | CQE04 - Transformer | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-09-24 | PS5-10-03 | PS5 - Milestone A | 1 | Closed | 27 | 48 | SEPTEMBER
T-701-4202 | PS5-75-OB-2789B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone A | 1 | On hold |  | 21 | SEPTEMBER
T-171-4203 | PS5-53-OB-9834C | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone E | 4 | To be completed |  | 28 | OCTOBER
T-745-4204 | PS5-06-OB-2888D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone C | 2 | To be completed |  | 43 | AUGUST
T-751-4205 | PS5-84-OB-7527A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | In progress |  | 38 | DECEMBER
T-759-4206 | PS5-72-OB-1226D | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-12-07 | PS5-05-02 | PS5 - Milestone I | 8 | Closed | 24 | 34 | DECEMBER
T-955-4207 | PS5-01-OB-3998C | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone C | 2 | To be completed |  | 45 | AUGUST
T-760-4208 | PS5-07-OB-4365A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-02-13 | PS5-02-01 | PS5 - Milestone D | 3 | Closed | 47 | 42 | FEBRUARY
T-841-4209 | PS5-05-OB-9252C | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-07-19 | PS5-60-10 | PS5 - Milestone E | 4 | Closed | 46 | 10 | JULY
T-196-4210 | PS5-44-IK-1086D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone C | 2 | To be completed |  | 13 | NOVEMBER
T-790-4211 | PS5-90-IK-9642C | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone B | 1.1 | In progress |  | 25 | SEPTEMBER
T-871-4212 | PS5-96-OB-2837B | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone D | 3 | To be completed |  | 45 | OCTOBER
T-171-4213 | PS5-26-UR-2935A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-01-27 | PS5-03-23 | PS5 - Milestone G | 6 | Closed | 6 | 40 | JANUARY
T-662-4214 | PS5-06-OB-6323B | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone E | 4 | In progress |  | 7 | SEPTEMBER
T-452-4215 | PS5-63-UR-1404C | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-01-24 | PS5-06-03 | PS5 - Milestone H | 7 | Closed | 28 | 21 | JANUARY
T-052-4216 | PS5-73-IK-4427C | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone B | 1.1 | In progress |  | 15 | DECEMBER
T-496-4217 | PS5-10-IK-7462D | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-08-07 | PS5-01-01 | PS5 - Milestone G | 6 | Closed | 18 | 19 | AUGUST
T-392-4218 | PS5-36-UR-7022C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-12-16 | PS5-61-02 | PS5 - Milestone C | 2 | Closed | 15 | 48 | DECEMBER
T-806-4219 | PS5-31-IK-2403B | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone E | 4 | In progress |  | 44 | SEPTEMBER
T-884-4220 | PS5-16-OB-9870A | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone I | 8 | To be completed |  | 44 | SEPTEMBER
T-702-4221 | PS5-82-UR-3840A | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-03-16 | PS5-60-07 | PS5 - Milestone F | 5 | Closed | 8 | 18 | MARCH
T-864-4222 | PS5-40-UR-2937B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone A | 1 | To be completed |  | 11 | NOVEMBER
T-080-4223 | PS5-71-IK-3524C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-03-12 | PS5-07-02 | PS5 - Milestone D | 3 | Closed | 28 | 47 | MARCH
T-103-4224 | PS5-30-UR-7811C | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone C | 2 | To be completed |  | 10 | NOVEMBER
T-953-4225 | PS5-25-OB-8733A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-07-15 | PS5-09-04 | PS5 - Milestone A | 1 | Closed | 30 | 44 | JULY
T-989-4226 | PS5-08-OB-3372C | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-02-24 | PS5-01-03 | PS5 - Milestone F | 5 | Closed | 25 | 47 | FEBRUARY
T-820-4227 | PS5-80-OB-2860A | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-02-11 | PS5-10-04 | PS5 - Milestone G | 6 | Closed | 15 | 25 | FEBRUARY
T-197-4228 | PS5-36-IK-8155A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-03-23 | PS5-07-01 | PS5 - Milestone H | 7 | Closed | 6 | 17 | MARCH
T-634-4229 | PS5-19-IK-3158C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone I | 8 | On hold |  | 48 | OCTOBER
T-186-4230 | PS5-04-OB-3255C | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-11-18 | PS5-99-03 | PS5 - Milestone F | 5 | Closed | 27 | 12 | NOVEMBER
T-183-4231 | PS5-98-OB-9161C | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-11-11 | PS5-06-03 | PS5 - Milestone A | 1 | Closed | 21 | 20 | NOVEMBER
T-201-4232 | PS5-28-OB-8576C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone A | 1 | In progress |  | 6 | DECEMBER
T-233-4233 | PS5-79-OB-7504A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | To be completed |  | 45 | NOVEMBER
T-204-4234 | PS5-61-OB-8822D | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone A | 1 | On hold |  | 15 | NOVEMBER
T-304-4235 | PS5-11-OB-1725C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone A | 1 | In progress |  | 27 | OCTOBER
T-593-4236 | PS5-70-OB-1346C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-08-18 | PS5-08-02 | PS5 - Milestone I | 8 | Closed | 36 | 46 | AUGUST
T-582-4237 | PS5-06-UR-4797A | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-02-28 | PS5-08-01 | PS5 - Milestone D | 3 | Closed | 47 | 17 | FEBRUARY
T-971-4238 | PS5-26-OB-9992B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | To be completed |  | 5 | OCTOBER
T-940-4239 | PS5-14-UR-9063A | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone C | 2 | In progress |  | 44 | NOVEMBER
T-465-4240 | PS5-91-OB-8414D | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone H | 7 | On hold |  | 45 | OCTOBER
T-876-4241 | PS5-48-IK-2319C | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | To be completed |  | 22 | NOVEMBER
T-075-4242 | PS5-08-OB-4172A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone D | 3 | To be completed |  | 25 | DECEMBER
T-174-4243 | PS5-12-UR-8476D | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-08-04 | PS5-10-03 | PS5 - Milestone B | 1.1 | Closed | 20 | 26 | AUGUST
T-505-4244 | PS5-87-UR-3135A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-04-09 | PS5-04-01 | PS5 - Milestone H | 7 | Closed | 43 | 7 | APRIL
T-142-4245 | PS5-69-OB-4472B | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone H | 7 | On hold |  | 21 | DECEMBER
T-430-4246 | PS5-65-OB-4057C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | In progress |  | 27 | OCTOBER
T-092-4247 | PS5-02-IK-4462B | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | In progress |  | 31 | NOVEMBER
T-580-4248 | PS5-72-OB-2485A | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone G | 6 | In progress |  | 33 | SEPTEMBER
T-968-4249 | PS5-53-UR-3796D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone E | 4 | To be completed |  | 23 | NOVEMBER
T-761-4250 | PS5-55-IK-8851B | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone D | 3 | In progress |  | 48 | DECEMBER
T-296-4251 | PS5-24-OB-2992B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-11-08 | PS5-99-01 | PS5 - Milestone H | 7 | Closed | 45 | 34 | NOVEMBER
T-556-4252 | PS5-47-OB-9437A | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-05-07 | PS5-06-02 | PS5 - Milestone C | 2 | Closed | 21 | 38 | MAY
T-153-4253 | PS5-24-IK-1056B | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-02-10 | PS5-99-02 | PS5 - Milestone G | 6 | Closed | 48 | 42 | FEBRUARY
T-680-4254 | PS5-20-IK-6362B | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-02-14 | PS5-61-01 | PS5 - Milestone F | 5 | Closed | 22 | 8 | FEBRUARY
T-568-4255 | PS5-21-OB-3342B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone F | 5 | On hold |  | 17 | AUGUST
T-679-4256 | PS5-17-UR-9142C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-04-18 | PS5-01-03 | PS5 - Milestone D | 3 | Closed | 13 | 42 | APRIL
T-668-4257 | PS5-47-IK-3049A | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone A | 1 | To be completed |  | 31 | AUGUST
T-661-4258 | PS5-33-UR-7154D | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone E | 4 | To be completed |  | 7 | SEPTEMBER
T-377-4259 | PS5-23-IK-7145C | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-08-10 | PS5-99-03 | PS5 - Milestone I | 8 | Closed | 29 | 16 | AUGUST
T-170-4260 | PS5-22-OB-7800A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone B | 1.1 | In progress |  | 34 | AUGUST
T-286-4261 | PS5-24-OB-5492D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | To be completed |  | 40 | NOVEMBER
T-499-4262 | PS5-27-OB-2957A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone B | 1.1 | To be completed |  | 4 | SEPTEMBER
T-429-4263 | PS5-88-UR-9826D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-04-12 | PS5-09-02 | PS5 - Milestone A | 1 | Closed | 27 | 10 | APRIL
T-448-4264 | PS5-89-OB-6630D | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone G | 6 | To be completed |  | 26 | DECEMBER
T-986-4265 | PS5-70-OB-6261C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone F | 5 | In progress |  | 6 | NOVEMBER
T-263-4266 | PS5-72-UR-9547C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone G | 6 | In progress |  | 21 | DECEMBER
T-077-4267 | PS5-90-UR-8999D | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone D | 3 | To be completed |  | 15 | OCTOBER
T-884-4268 | PS5-69-UR-3874C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-09-22 | PS5-04-01 | PS5 - Milestone I | 8 | Closed | 16 | 13 | SEPTEMBER
T-576-4269 | PS5-80-OB-3420C | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone B | 1.1 | On hold |  | 34 | NOVEMBER
T-718-4270 | PS5-81-UR-7893C | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-10-09 | PS5-11-02 | PS5 - Milestone I | 8 | Closed | 14 | 10 | OCTOBER
T-473-4271 | PS5-65-IK-7687B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-12-25 | PS5-10-05 | PS5 - Milestone B | 1.1 | Closed | 25 | 28 | DECEMBER
T-902-4272 | PS5-91-OB-5485A | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone B | 1.1 | On hold |  | 46 | NOVEMBER
T-315-4273 | PS5-74-OB-5652C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone B | 1.1 | On hold |  | 22 | NOVEMBER
T-063-4274 | PS5-56-UR-2436C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | To be completed |  | 21 | SEPTEMBER
T-367-4275 | PS5-08-OB-7340A | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone G | 6 | In progress |  | 46 | OCTOBER
T-567-4276 | PS5-14-IK-6863A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-09-25 | PS5-82-02 | PS5 - Milestone D | 3 | Closed | 12 | 46 | SEPTEMBER
T-167-4277 | PS5-45-OB-6603C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-07-26 | PS5-63-01 | PS5 - Milestone I | 8 | Closed | 40 | 17 | JULY
T-843-4278 | PS5-56-OB-1841C | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-12-20 | PS5-62-02 | PS5 - Milestone D | 3 | Closed | 9 | 27 | DECEMBER
T-091-4279 | PS5-72-OB-4983A | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | To be completed |  | 21 | NOVEMBER
T-523-4280 | PS5-12-UR-9987C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone H | 7 | In progress |  | 8 | SEPTEMBER
T-607-4281 | PS5-72-IK-8542D | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-05-12 | PS5-01-01 | PS5 - Milestone C | 2 | Closed | 36 | 7 | MAY
T-807-4282 | PS5-57-IK-7015D | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone E | 4 | To be completed |  | 28 | DECEMBER
T-663-4283 | PS5-38-IK-6006D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone E | 4 | To be completed |  | 7 | DECEMBER
T-554-4284 | PS5-98-UR-4743D | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-10-16 | PS5-62-01 | PS5 - Milestone F | 5 | Closed | 46 | 5 | OCTOBER
T-801-4285 | PS5-07-UR-3050B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-12-05 | PS5-99-01 | PS5 - Milestone I | 8 | Closed | 37 | 45 | DECEMBER
T-394-4286 | PS5-86-UR-2732C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone A | 1 | In progress |  | 39 | OCTOBER
T-884-4287 | PS5-54-IK-6129C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone A | 1 | In progress |  | 24 | SEPTEMBER
T-837-4288 | PS5-97-UR-5939C | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone H | 7 | On hold |  | 48 | NOVEMBER
T-965-4289 | PS5-99-IK-1062D | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone B | 1.1 | In progress |  | 11 | SEPTEMBER
T-356-4290 | PS5-73-OB-5979C | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | To be completed |  | 23 | OCTOBER
T-064-4291 | PS5-67-OB-7675A | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | To be completed |  | 46 | OCTOBER
T-083-4292 | PS5-24-IK-5306D | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-07-25 | PS5-08-01 | PS5 - Milestone I | 8 | Closed | 39 | 20 | JULY
T-220-4293 | PS5-08-OB-3607D | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-07-03 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 17 | 6 | JULY
T-355-4294 | PS5-69-IK-4539A | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-09-04 | PS5-60-04 | PS5 - Milestone I | 8 | Closed | 37 | 15 | SEPTEMBER
T-738-4295 | PS5-40-OB-5773D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | To be completed |  | 19 | DECEMBER
T-088-4296 | PS5-39-OB-2587A | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | In progress |  | 22 | NOVEMBER
T-886-4297 | PS5-43-UR-7311D | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone F | 5 | To be completed |  | 26 | AUGUST
T-723-4298 | PS5-91-OB-8217D | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone E | 4 | To be completed |  | 29 | DECEMBER
T-423-4299 | PS5-69-OB-8276C | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | To be completed |  | 39 | NOVEMBER
T-402-4300 | PS5-38-OB-4483D | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone D | 3 | On hold |  | 23 | NOVEMBER
T-148-4301 | PS5-38-IK-3312C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-03-09 | PS5-61-07 | PS5 - Milestone I | 8 | Closed | 14 | 37 | MARCH
T-354-4302 | PS5-77-IK-4440A | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone I | 8 | In progress |  | 42 | OCTOBER
T-711-4303 | PS5-81-UR-4231A | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-02-17 | PS5-62-02 | PS5 - Milestone B | 1.1 | Closed | 24 | 6 | FEBRUARY
T-341-4304 | PS5-06-OB-4691C | CQE02 - LV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone D | 3 | On hold |  | 37 | AUGUST
T-053-4305 | PS5-89-OB-1108A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-12-14 | PS5-62-01 | PS5 - Milestone F | 5 | Closed | 14 | 14 | DECEMBER
T-559-4306 | PS5-44-OB-7059A | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-06-25 | PS5-10-04 | PS5 - Milestone H | 7 | Closed | 14 | 27 | JUNE
T-970-4307 | PS5-11-IK-2584D | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone G | 6 | On hold |  | 37 | DECEMBER
T-817-4308 | PS5-51-IK-7268A | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone F | 5 | To be completed |  | 41 | OCTOBER
T-025-4309 | PS5-53-IK-3590C | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone A | 1 | In progress |  | 45 | AUGUST
T-429-4310 | PS5-74-OB-9227B | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-12-24 | PS5-10-04 | PS5 - Milestone F | 5 | Closed | 20 | 4 | DECEMBER
T-868-4311 | PS5-68-UR-8845D | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone I | 8 | In progress |  | 29 | DECEMBER
T-874-4312 | PS5-10-UR-2120B | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone H | 7 | In progress |  | 29 | OCTOBER
T-742-4313 | PS5-22-OB-9745D | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-01-24 | PS5-62-01 | PS5 - Milestone F | 5 | Closed | 8 | 4 | JANUARY
T-372-4314 | PS5-17-OB-8111A | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-04-21 | PS5-99-01 | PS5 - Milestone A | 1 | Closed | 25 | 5 | APRIL
T-727-4315 | PS5-85-IK-8831C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-09-17 | PS5-04-02 | PS5 - Milestone I | 8 | Closed | 42 | 48 | SEPTEMBER
T-840-4316 | PS5-05-UR-3665D | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone D | 3 | To be completed |  | 30 | DECEMBER
T-673-4317 | PS5-10-UR-5148D | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone G | 6 | To be completed |  | 26 | NOVEMBER
T-341-4318 | PS5-56-IK-7985A | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-08-11 | PS5-03-01 | PS5 - Milestone H | 7 | Closed | 14 | 47 | AUGUST
T-184-4319 | PS5-96-UR-5955B | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone H | 7 | To be completed |  | 11 | SEPTEMBER
T-027-4320 | PS5-62-IK-4762C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-02-23 | PS5-03-02 | PS5 - Milestone A | 1 | Closed | 5 | 12 | FEBRUARY
T-440-4321 | PS5-64-IK-4815C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | In progress |  | 12 | OCTOBER
T-576-4322 | PS5-34-IK-8502A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone F | 5 | To be completed |  | 28 | SEPTEMBER
T-936-4323 | PS5-82-IK-3494A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-05-28 | PS5-82-02 | PS5 - Milestone A | 1 | Closed | 40 | 4 | MAY
T-394-4324 | PS5-98-UR-8344B | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone B | 1.1 | In progress |  | 4 | DECEMBER
T-067-4325 | PS5-61-OB-4377C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-09-03 | PS5-06-03 | PS5 - Milestone A | 1 | Closed | 20 | 27 | SEPTEMBER
T-761-4326 | PS5-30-UR-6813D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-11-20 | PS5-99-03 | PS5 - Milestone B | 1.1 | Closed | 14 | 43 | NOVEMBER
T-896-4327 | PS5-41-UR-3002C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone D | 3 | To be completed |  | 12 | AUGUST
T-092-4328 | PS5-21-IK-1495B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone H | 7 | On hold |  | 28 | NOVEMBER
T-939-4329 | PS5-96-OB-1220D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone H | 7 | To be completed |  | 34 | OCTOBER
T-964-4330 | PS5-20-IK-1056A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone F | 5 | To be completed |  | 11 | NOVEMBER
T-350-4331 | PS5-28-UR-5953A | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone C | 2 | On hold |  | 22 | SEPTEMBER
T-460-4332 | PS5-54-OB-1579B | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-10-13 | PS5-01-02 | PS5 - Milestone H | 7 | Closed | 44 | 10 | OCTOBER
T-515-4333 | PS5-75-IK-5235B | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone E | 4 | In progress |  | 37 | DECEMBER
T-461-4334 | PS5-72-OB-5355C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-05-03 | PS5-04-04 | PS5 - Milestone F | 5 | Closed | 32 | 12 | MAY
T-057-4335 | PS5-49-UR-6327D | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | To be completed |  | 36 | AUGUST
T-646-4336 | PS5-45-IK-6517D | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-09-28 | PS5-61-02 | PS5 - Milestone I | 8 | Closed | 45 | 24 | SEPTEMBER
T-446-4337 | PS5-71-UR-6013A | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-08-14 | PS5-06-03 | PS5 - Milestone D | 3 | Closed | 47 | 39 | AUGUST
T-702-4338 | PS5-12-UR-1269D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone G | 6 | To be completed |  | 43 | SEPTEMBER
T-629-4339 | PS5-36-OB-2286C | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone B | 1.1 | In progress |  | 16 | SEPTEMBER
T-904-4340 | PS5-88-UR-5026B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-01-28 | PS5-07-01 | PS5 - Milestone E | 4 | Closed | 19 | 17 | JANUARY
T-126-4341 | PS5-29-UR-7333D | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-11-03 | PS5-01-02 | PS5 - Milestone C | 2 | Closed | 30 | 40 | NOVEMBER
T-160-4342 | PS5-53-IK-6465D | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone F | 5 | To be completed |  | 21 | SEPTEMBER
T-475-4343 | PS5-04-OB-6519A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-08-07 | PS5-01-04 | PS5 - Milestone F | 5 | Closed | 47 | 33 | AUGUST
T-651-4344 | PS5-61-OB-6902B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone D | 3 | To be completed |  | 11 | OCTOBER
T-950-4345 | PS5-66-UR-6713A | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-06-03 | PS5-99-02 | PS5 - Milestone I | 8 | Closed | 18 | 43 | JUNE
T-853-4346 | PS5-34-UR-9092B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone B | 1.1 | In progress |  | 15 | NOVEMBER
T-685-4347 | PS5-82-OB-7397D | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-09-16 | PS5-09-01 | PS5 - Milestone E | 4 | Closed | 23 | 33 | SEPTEMBER
T-147-4348 | PS5-36-OB-2661C | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-05-19 | PS5-04-03 | PS5 - Milestone D | 3 | Closed | 4 | 22 | MAY
T-022-4349 | PS5-54-OB-3577B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-06-03 | PS5-63-01 | PS5 - Milestone G | 6 | Closed | 5 | 36 | JUNE
T-097-4350 | PS5-55-OB-6585B | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone B | 1.1 | To be completed |  | 29 | SEPTEMBER
T-163-4351 | PS5-59-OB-7073B | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone F | 5 | To be completed |  | 23 | NOVEMBER
T-416-4352 | PS5-54-UR-6454D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-06-05 | PS5-01-05 | PS5 - Milestone H | 7 | Closed | 25 | 37 | JUNE
T-501-4353 | PS5-36-UR-8590C | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone E | 4 | To be completed |  | 14 | DECEMBER
T-918-4354 | PS5-70-OB-5736B | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-09-14 | PS5-03-02 | PS5 - Milestone I | 8 | Closed | 33 | 19 | SEPTEMBER
T-812-4355 | PS5-02-OB-1901A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-02-07 | PS5-09-01 | PS5 - Milestone E | 4 | Closed | 30 | 18 | FEBRUARY
T-737-4356 | PS5-30-UR-3174D | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone B | 1.1 | To be completed |  | 39 | NOVEMBER
T-148-4357 | PS5-03-IK-3369B | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone D | 3 | In progress |  | 40 | SEPTEMBER
T-363-4358 | PS5-74-OB-7305C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-03-17 | PS5-11-01 | PS5 - Milestone B | 1.1 | Closed | 47 | 12 | MARCH
T-933-4359 | PS5-98-OB-5389A | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-07-05 | PS5-13-01 | PS5 - Milestone A | 1 | Closed | 10 | 23 | JULY
T-292-4360 | PS5-73-IK-3056B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-06-08 | PS5-09-02 | PS5 - Milestone G | 6 | Closed | 45 | 25 | JUNE
T-216-4361 | PS5-27-OB-7204A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone I | 8 | To be completed |  | 8 | AUGUST
T-586-4362 | PS5-41-IK-6449D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | On hold |  | 5 | DECEMBER
T-379-4363 | PS5-45-OB-7689A | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | In progress |  | 33 | AUGUST
T-265-4364 | PS5-62-OB-8942B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone I | 8 | To be completed |  | 32 | AUGUST
T-785-4365 | PS5-86-IK-4288A | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-02-02 | PS5-02-01 | PS5 - Milestone H | 7 | Closed | 28 | 8 | FEBRUARY
T-725-4366 | PS5-29-OB-8254D | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-08-10 | PS5-63-01 | PS5 - Milestone C | 2 | Closed | 47 | 35 | AUGUST
T-995-4367 | PS5-67-OB-2964C | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | In progress |  | 11 | OCTOBER
T-912-4368 | PS5-87-OB-3587A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-05-11 | PS5-07-04 | PS5 - Milestone H | 7 | Closed | 19 | 23 | MAY
T-195-4369 | PS5-50-UR-7898D | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-02-18 | PS5-82-02 | PS5 - Milestone E | 4 | Closed | 17 | 35 | FEBRUARY
T-392-4370 | PS5-73-UR-5201B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone B | 1.1 | In progress |  | 47 | OCTOBER
T-719-4371 | PS5-26-OB-7476A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone A | 1 | To be completed |  | 24 | AUGUST
T-122-4372 | PS5-05-UR-4868D | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-12-06 | PS5-06-02 | PS5 - Milestone D | 3 | Closed | 40 | 23 | DECEMBER
T-150-4373 | PS5-20-OB-1205C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone H | 7 | In progress |  | 9 | DECEMBER
T-654-4374 | PS5-43-OB-4520B | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | On hold |  | 25 | NOVEMBER
T-707-4375 | PS5-52-OB-3816A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone D | 3 | To be completed |  | 21 | DECEMBER
T-175-4376 | PS5-87-OB-7921B | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone B | 1.1 | In progress |  | 22 | DECEMBER
T-448-4377 | PS5-26-IK-4566B | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone F | 5 | On hold |  | 43 | AUGUST
T-007-4378 | PS5-30-UR-6530B | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone D | 3 | In progress |  | 33 | AUGUST
T-646-4379 | PS5-54-OB-6807C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone G | 6 | To be completed |  | 6 | SEPTEMBER
T-028-4380 | PS5-19-OB-5127A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone F | 5 | On hold |  | 34 | DECEMBER
T-946-4381 | PS5-01-UR-6902A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone F | 5 | To be completed |  | 16 | AUGUST
T-410-4382 | PS5-28-OB-8554D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-12-17 | PS5-62-01 | PS5 - Milestone E | 4 | Closed | 19 | 38 | DECEMBER
T-119-4383 | PS5-70-OB-3060D | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | On hold |  | 32 | OCTOBER
T-405-4384 | PS5-67-UR-2086A | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-08-14 | PS5-07-03 | PS5 - Milestone C | 2 | Closed | 25 | 8 | AUGUST
T-555-4385 | PS5-08-IK-1397B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-02-13 | PS5-01-01 | PS5 - Milestone B | 1.1 | Closed | 45 | 5 | FEBRUARY
T-942-4386 | PS5-13-OB-3756A | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | To be completed |  | 9 | DECEMBER
T-281-4387 | PS5-24-OB-3604A | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-09-09 | PS5-05-01 | PS5 - Milestone D | 3 | Closed | 42 | 36 | SEPTEMBER
T-840-4388 | PS5-78-UR-8716A | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone A | 1 | In progress |  | 46 | AUGUST
T-166-4389 | PS5-91-OB-6617D | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone F | 5 | To be completed |  | 6 | SEPTEMBER
T-557-4390 | PS5-75-UR-1785B | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-08-01 | PS5-01-06 | PS5 - Milestone E | 4 | Closed | 32 | 27 | AUGUST
T-845-4391 | PS5-22-IK-5771A | CQP01 - Pipe Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | To be completed |  | 9 | DECEMBER
T-676-4392 | PS5-90-OB-4371A | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | On hold |  | 36 | NOVEMBER
T-515-4393 | PS5-37-OB-9844D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone C | 2 | To be completed |  | 25 | NOVEMBER
T-355-4394 | PS5-49-IK-3991A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-01-28 | PS5-60-04 | PS5 - Milestone I | 8 | Closed | 27 | 20 | JANUARY
T-194-4395 | PS5-57-UR-7562A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone B | 1.1 | To be completed |  | 13 | OCTOBER
T-070-4396 | PS5-16-IK-8092B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-02-02 | PS5-06-03 | PS5 - Milestone F | 5 | Closed | 24 | 34 | FEBRUARY
T-704-4397 | PS5-02-IK-4666D | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-12-16 | PS5-99-02 | PS5 - Milestone C | 2 | Closed | 31 | 28 | DECEMBER
T-258-4398 | PS5-35-OB-3072C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | In progress |  | 42 | NOVEMBER
T-960-4399 | PS5-71-OB-1063A | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone B | 1.1 | To be completed |  | 9 | NOVEMBER
T-314-4400 | PS5-35-OB-8009C | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-02-02 | PS5-03-23 | PS5 - Milestone H | 7 | Closed | 16 | 46 | FEBRUARY
T-473-4401 | PS5-40-UR-9607D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone A | 1 | To be completed |  | 31 | AUGUST
T-764-4402 | PS5-88-OB-5644D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone I | 8 | To be completed |  | 34 | DECEMBER
T-270-4403 | PS5-08-OB-7099A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone F | 5 | To be completed |  | 42 | NOVEMBER
T-331-4404 | PS5-53-UR-9031D | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-02-25 | PS5-06-02 | PS5 - Milestone D | 3 | Closed | 22 | 27 | FEBRUARY
T-580-4405 | PS5-70-IK-2637B | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-04-28 | PS5-11-03 | PS5 - Milestone I | 8 | Closed | 10 | 14 | APRIL
T-875-4406 | PS5-82-UR-1994C | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone G | 6 | On hold |  | 5 | NOVEMBER
T-647-4407 | PS5-61-OB-6796D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | To be completed |  | 45 | SEPTEMBER
T-342-4408 | PS5-74-IK-7161B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone D | 3 | To be completed |  | 47 | OCTOBER
T-518-4409 | PS5-49-IK-5325C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone I | 8 | In progress |  | 20 | DECEMBER
T-316-4410 | PS5-83-UR-7299C | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone E | 4 | In progress |  | 23 | DECEMBER
T-023-4411 | PS5-02-UR-1405C | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone D | 3 | In progress |  | 7 | OCTOBER
T-786-4412 | PS5-39-IK-6319A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-03-11 | PS5-01-07 | PS5 - Milestone I | 8 | Closed | 27 | 26 | MARCH
T-028-4413 | PS5-04-OB-3078B | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone I | 8 | To be completed |  | 40 | OCTOBER
T-287-4414 | PS5-84-OB-8798B | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone G | 6 | In progress |  | 13 | AUGUST
T-676-4415 | PS5-92-OB-6443A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-01-25 | PS5-62-02 | PS5 - Milestone C | 2 | Closed | 42 | 22 | JANUARY
T-760-4416 | PS5-82-OB-2058A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone I | 8 | In progress |  | 11 | NOVEMBER
T-494-4417 | PS5-75-IK-7614A | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-07-25 | PS5-62-01 | PS5 - Milestone F | 5 | Closed | 42 | 4 | JULY
T-945-4418 | PS5-62-IK-9772A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-09-15 | PS5-01-05 | PS5 - Milestone C | 2 | Closed | 33 | 28 | SEPTEMBER
T-414-4419 | PS5-42-OB-1545D | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-08-03 | PS5-01-05 | PS5 - Milestone D | 3 | Closed | 39 | 15 | AUGUST
T-811-4420 | PS5-30-IK-9167B | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone F | 5 | In progress |  | 9 | OCTOBER
T-193-4421 | PS5-68-OB-9743B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone H | 7 | To be completed |  | 11 | DECEMBER
T-160-4422 | PS5-33-UR-3415C | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone H | 7 | In progress |  | 42 | DECEMBER
T-412-4423 | PS5-73-IK-6162C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-05-17 | PS5-02-03 | PS5 - Milestone A | 1 | Closed | 46 | 16 | MAY
T-362-4424 | PS5-68-OB-8363C | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone F | 5 | To be completed |  | 37 | AUGUST
T-280-4425 | PS5-91-UR-5235D | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | To be completed |  | 19 | SEPTEMBER
T-060-4426 | PS5-58-IK-5820A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone I | 8 | In progress |  | 10 | SEPTEMBER
T-222-4427 | PS5-13-OB-3821C | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-02-19 | PS5-04-04 | PS5 - Milestone F | 5 | Closed | 4 | 28 | FEBRUARY
T-149-4428 | PS5-91-OB-3606B | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-04-17 | PS5-11-03 | PS5 - Milestone B | 1.1 | Closed | 39 | 29 | APRIL
T-876-4429 | PS5-92-IK-7085A | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-02-24 | PS5-04-03 | PS5 - Milestone F | 5 | Closed | 35 | 48 | FEBRUARY
T-678-4430 | PS5-39-UR-4392A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone D | 3 | In progress |  | 42 | OCTOBER
T-919-4431 | PS5-08-OB-1714C | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-11-01 | PS5-12-02 | PS5 - Milestone A | 1 | Closed | 48 | 23 | NOVEMBER
T-704-4432 | PS5-10-OB-7613C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-06-19 | PS5-61-01 | PS5 - Milestone E | 4 | Closed | 11 | 11 | JUNE
T-418-4433 | PS5-23-IK-8471B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-09-26 | PS5-11-01 | PS5 - Milestone D | 3 | Closed | 17 | 5 | SEPTEMBER
T-125-4434 | PS5-31-OB-1295B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-11-17 | PS5-12-01 | PS5 - Milestone F | 5 | Closed | 15 | 27 | NOVEMBER
T-222-4435 | PS5-42-OB-5737C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone I | 8 | To be completed |  | 44 | DECEMBER
T-354-4436 | PS5-92-OB-1480A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-01-10 | PS5-11-03 | PS5 - Milestone B | 1.1 | Closed | 41 | 48 | JANUARY
T-302-4437 | PS5-51-IK-1187A | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-07-28 | PS5-01-07 | PS5 - Milestone E | 4 | Closed | 19 | 33 | JULY
T-187-4438 | PS5-88-OB-7813D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone G | 6 | To be completed |  | 32 | DECEMBER
T-804-4439 | PS5-80-OB-3867A | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-08-07 | PS5-10-02 | PS5 - Milestone A | 1 | Closed | 13 | 9 | AUGUST
T-753-4440 | PS5-92-UR-3443A | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone E | 4 | To be completed |  | 45 | OCTOBER
T-909-4441 | PS5-54-OB-3646D | CQM04 - Vessel | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-05-12 | PS5-09-02 | PS5 - Milestone B | 1.1 | Closed | 24 | 27 | MAY
T-746-4442 | PS5-58-IK-7675B | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-05-22 | PS5-82-07 | PS5 - Milestone C | 2 | Closed | 21 | 35 | MAY
T-647-4443 | PS5-61-OB-1836C | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone I | 8 | To be completed |  | 8 | SEPTEMBER
T-292-4444 | PS5-71-UR-9120B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone H | 7 | To be completed |  | 32 | OCTOBER
T-427-4445 | PS5-36-OB-9012C | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | On hold |  | 41 | DECEMBER
T-917-4446 | PS5-19-OB-5570D | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-11-10 | PS5-60-07 | PS5 - Milestone G | 6 | Closed | 38 | 32 | NOVEMBER
T-975-4447 | PS5-77-UR-1474B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone I | 8 | In progress |  | 23 | DECEMBER
T-823-4448 | PS5-69-OB-8108C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-11-24 | PS5-06-02 | PS5 - Milestone C | 2 | Closed | 47 | 37 | NOVEMBER
T-958-4449 | PS5-58-OB-9365D | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-03-07 | PS5-01-02 | PS5 - Milestone D | 3 | Closed | 47 | 35 | MARCH
T-776-4450 | PS5-77-UR-5757A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-01-06 | PS5-01-02 | PS5 - Milestone E | 4 | Closed | 17 | 6 | JANUARY
T-818-4451 | PS5-31-OB-9206D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | To be completed |  | 42 | SEPTEMBER
T-943-4452 | PS5-89-UR-3654A | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-04-24 | PS5-06-03 | PS5 - Milestone G | 6 | Closed | 35 | 43 | APRIL
T-657-4453 | PS5-31-OB-3260B | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone A | 1 | In progress |  | 36 | SEPTEMBER
T-886-4454 | PS5-51-OB-8142B | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone G | 6 | On hold |  | 26 | OCTOBER
T-091-4455 | PS5-75-OB-9378A | CQM01 - Pump Installation | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone A | 1 | To be completed |  | 17 | AUGUST
T-796-4456 | PS5-21-UR-2821D | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone D | 3 | In progress |  | 14 | AUGUST
T-386-4457 | PS5-79-OB-5591D | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone E | 4 | In progress |  | 24 | OCTOBER
T-885-4458 | PS5-09-IK-5486A | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-07-05 | PS5-99-01 | PS5 - Milestone B | 1.1 | Closed | 31 | 17 | JULY
T-526-4459 | PS5-36-OB-1827B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone E | 4 | To be completed |  | 12 | NOVEMBER
T-530-4460 | PS5-21-IK-3454A | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-10-03 | PS5-02-01 | PS5 - Milestone E | 4 | Closed | 35 | 6 | OCTOBER
T-337-4461 | PS5-81-IK-6169D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-07-07 | PS5-08-01 | PS5 - Milestone G | 6 | Closed | 12 | 22 | JULY
T-193-4462 | PS5-48-OB-1478B | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone E | 4 | To be completed |  | 33 | OCTOBER
T-904-4463 | PS5-66-OB-2940A | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-03-06 | PS5-10-04 | PS5 - Milestone B | 1.1 | Closed | 11 | 27 | MARCH
T-730-4464 | PS5-66-IK-5298D | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-12-19 | PS5-01-05 | PS5 - Milestone A | 1 | Closed | 16 | 23 | DECEMBER
T-481-4465 | PS5-24-OB-2066C | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone I | 8 | On hold |  | 32 | NOVEMBER
T-873-4466 | PS5-20-UR-1713B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-02-13 | PS5-06-03 | PS5 - Milestone H | 7 | Closed | 17 | 34 | FEBRUARY
T-683-4467 | PS5-54-IK-9217D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-10-19 | PS5-09-02 | PS5 - Milestone F | 5 | Closed | 29 | 33 | OCTOBER
T-143-4468 | PS5-11-OB-4808D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone D | 3 | To be completed |  | 47 | OCTOBER
T-159-4469 | PS5-57-IK-1093C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-12-26 | PS5-01-08 | PS5 - Milestone F | 5 | Closed | 4 | 38 | DECEMBER
T-059-4470 | PS5-56-OB-1751D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone A | 1 | In progress |  | 22 | DECEMBER
T-835-4471 | PS5-57-IK-6405B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | In progress |  | 48 | NOVEMBER
T-072-4472 | PS5-48-OB-3473C | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | On hold |  | 30 | SEPTEMBER
T-269-4473 | PS5-19-IK-9019D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone I | 8 | In progress |  | 43 | NOVEMBER
T-220-4474 | PS5-98-IK-6022A | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone H | 7 | In progress |  | 43 | AUGUST
T-257-4475 | PS5-29-OB-2815A | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-07-19 | PS5-11-03 | PS5 - Milestone C | 2 | Closed | 30 | 42 | JULY
T-304-4476 | PS5-59-OB-9062D | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-07-12 | PS5-08-02 | PS5 - Milestone F | 5 | Closed | 37 | 27 | JULY
T-630-4477 | PS5-09-UR-7482A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-05-07 | PS5-12-01 | PS5 - Milestone E | 4 | Closed | 20 | 8 | MAY
T-656-4478 | PS5-51-OB-2421D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone H | 7 | To be completed |  | 38 | DECEMBER
T-799-4479 | PS5-74-UR-7688A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-01-22 | PS5-02-03 | PS5 - Milestone B | 1.1 | Closed | 13 | 30 | JANUARY
T-037-4480 | PS5-03-IK-3864D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | To be completed |  | 40 | NOVEMBER
T-176-4481 | PS5-86-IK-2669A | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-09-06 | PS5-06-03 | PS5 - Milestone F | 5 | Closed | 18 | 14 | SEPTEMBER
T-058-4482 | PS5-98-OB-2562B | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-03-26 | PS5-12-01 | PS5 - Milestone F | 5 | Closed | 44 | 37 | MARCH
T-919-4483 | PS5-88-OB-2696D | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone D | 3 | In progress |  | 26 | DECEMBER
T-166-4484 | PS5-16-IK-1132C | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-10-16 | PS5-10-06 | PS5 - Milestone B | 1.1 | Closed | 43 | 26 | OCTOBER
T-766-4485 | PS5-43-IK-3631A | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-02-19 | PS5-61-02 | PS5 - Milestone A | 1 | Closed | 45 | 14 | FEBRUARY
T-077-4486 | PS5-28-IK-2527A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone B | 1.1 | In progress |  | 17 | AUGUST
T-274-4487 | PS5-89-OB-2081B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone D | 3 | To be completed |  | 28 | SEPTEMBER
T-166-4488 | PS5-69-OB-7969A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone A | 1 | In progress |  | 34 | OCTOBER
T-970-4489 | PS5-08-UR-7349D | CQM04 - Vessel | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone B | 1.1 | In progress |  | 6 | AUGUST
T-095-4490 | PS5-20-OB-3361D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | To be completed |  | 21 | NOVEMBER
T-803-4491 | PS5-15-UR-2927A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone B | 1.1 | In progress |  | 29 | SEPTEMBER
T-713-4492 | PS5-43-OB-7798B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-08-03 | PS5-82-02 | PS5 - Milestone E | 4 | Closed | 25 | 22 | AUGUST
T-475-4493 | PS5-47-OB-7084B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-05-25 | PS5-04-01 | PS5 - Milestone C | 2 | Closed | 43 | 42 | MAY
T-715-4494 | PS5-51-IK-4043A | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | On hold |  | 26 | AUGUST
T-617-4495 | PS5-63-UR-1772B | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone F | 5 | In progress |  | 21 | AUGUST
T-325-4496 | PS5-11-UR-9940A | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone G | 6 | To be completed |  | 25 | SEPTEMBER
T-793-4497 | PS5-37-UR-3987D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | In progress |  | 48 | OCTOBER
T-880-4498 | PS5-44-OB-8379D | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-07-11 | PS5-09-04 | PS5 - Milestone C | 2 | Closed | 27 | 4 | JULY
T-769-4499 | PS5-65-UR-5036C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-05-06 | PS5-05-03 | PS5 - Milestone D | 3 | Closed | 48 | 22 | MAY
T-358-4500 | PS5-29-OB-4777C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone H | 7 | To be completed |  | 42 | SEPTEMBER
T-323-4501 | PS5-68-UR-6762A | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-05-12 | PS5-60-10 | PS5 - Milestone A | 1 | Closed | 5 | 7 | MAY
T-761-4502 | PS5-28-UR-5860C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone G | 6 | In progress |  | 19 | DECEMBER
T-083-4503 | PS5-88-IK-6541D | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-05-14 | PS5-12-01 | PS5 - Milestone A | 1 | Closed | 36 | 44 | MAY
T-430-4504 | PS5-92-UR-7490C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone C | 2 | In progress |  | 14 | OCTOBER
T-483-4505 | PS5-98-OB-7273A | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-11-26 | PS5-10-06 | PS5 - Milestone D | 3 | Closed | 20 | 15 | NOVEMBER
T-422-4506 | PS5-78-OB-3231B | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone I | 8 | On hold |  | 8 | NOVEMBER
T-845-4507 | PS5-19-OB-2644C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone E | 4 | In progress |  | 12 | SEPTEMBER
T-026-4508 | PS5-19-UR-3000B | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone E | 4 | In progress |  | 27 | DECEMBER
T-247-4509 | PS5-11-OB-3579C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | On hold |  | 43 | NOVEMBER
T-073-4510 | PS5-76-OB-8788D | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone C | 2 | In progress |  | 24 | SEPTEMBER
T-658-4511 | PS5-38-OB-8123B | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-04-12 | PS5-99-03 | PS5 - Milestone F | 5 | Closed | 45 | 36 | APRIL
T-462-4512 | PS5-37-UR-4274B | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone E | 4 | On hold |  | 48 | NOVEMBER
T-327-4513 | PS5-60-OB-1217D | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone F | 5 | To be completed |  | 4 | DECEMBER
T-984-4514 | PS5-19-OB-7219D | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-07-21 | PS5-04-04 | PS5 - Milestone I | 8 | Closed | 19 | 34 | JULY
T-694-4515 | PS5-11-OB-7757A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | In progress |  | 23 | OCTOBER
T-063-4516 | PS5-51-IK-5138C | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone I | 8 | To be completed |  | 39 | OCTOBER
T-449-4517 | PS5-11-IK-9060D | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-05-13 | PS5-01-06 | PS5 - Milestone H | 7 | Closed | 9 | 46 | MAY
T-796-4518 | PS5-47-UR-3515A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone A | 1 | To be completed |  | 34 | SEPTEMBER
T-398-4519 | PS5-46-OB-2704B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone I | 8 | To be completed |  | 30 | NOVEMBER
T-773-4520 | PS5-70-OB-7874B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-07-15 | PS5-62-02 | PS5 - Milestone I | 8 | Closed | 13 | 42 | JULY
T-369-4521 | PS5-86-IK-8957C | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone B | 1.1 | To be completed |  | 17 | SEPTEMBER
T-975-4522 | PS5-23-IK-9512C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone B | 1.1 | To be completed |  | 18 | AUGUST
T-015-4523 | PS5-35-IK-1525C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-11-24 | PS5-07-01 | PS5 - Milestone B | 1.1 | Closed | 17 | 23 | NOVEMBER
T-804-4524 | PS5-19-OB-9063A | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-09-08 | PS5-99-01 | PS5 - Milestone E | 4 | Closed | 20 | 36 | SEPTEMBER
T-607-4525 | PS5-26-OB-8931A | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | To be completed |  | 30 | SEPTEMBER
T-811-4526 | PS5-53-IK-5230D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone C | 2 | To be completed |  | 8 | NOVEMBER
T-252-4527 | PS5-23-OB-1405A | CQM04 - Vessel | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-11-02 | PS5-61-02 | PS5 - Milestone I | 8 | Closed | 26 | 13 | NOVEMBER
T-698-4528 | PS5-05-UR-3665C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-09-03 | PS5-03-01 | PS5 - Milestone E | 4 | Closed | 32 | 14 | SEPTEMBER
T-070-4529 | PS5-50-OB-1836B | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone C | 2 | To be completed |  | 7 | DECEMBER
T-603-4530 | PS5-75-UR-1074A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone F | 5 | To be completed |  | 25 | SEPTEMBER
T-716-4531 | PS5-57-UR-5333A | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone I | 8 | To be completed |  | 7 | SEPTEMBER
T-686-4532 | PS5-53-OB-8522B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone H | 7 | To be completed |  | 33 | AUGUST
T-458-4533 | PS5-32-OB-3878C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | On hold |  | 31 | NOVEMBER
T-516-4534 | PS5-16-IK-6091D | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-28 | PS5-60-04 | PS5 - Milestone A | 1 | Closed | 46 | 21 | APRIL
T-576-4535 | PS5-76-OB-2941A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone C | 2 | In progress |  | 29 | NOVEMBER
T-014-4536 | PS5-16-UR-3698C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone F | 5 | In progress |  | 4 | AUGUST
T-103-4537 | PS5-59-OB-1355C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone A | 1 | To be completed |  | 30 | OCTOBER
T-279-4538 | PS5-68-UR-2428D | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-03-13 | PS5-05-03 | PS5 - Milestone E | 4 | Closed | 20 | 34 | MARCH
T-745-4539 | PS5-58-IK-8600B | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone H | 7 | On hold |  | 31 | DECEMBER
T-746-4540 | PS5-66-UR-6027A | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-02-27 | PS5-03-03 | PS5 - Milestone D | 3 | Closed | 6 | 27 | FEBRUARY
T-854-4541 | PS5-53-IK-1429C | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-11-12 | PS5-82-02 | PS5 - Milestone C | 2 | Closed | 8 | 47 | NOVEMBER
T-987-4542 | PS5-46-OB-5649B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-05-10 | PS5-62-01 | PS5 - Milestone G | 6 | Closed | 12 | 7 | MAY
T-748-4543 | PS5-15-UR-8358C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone E | 4 | To be completed |  | 40 | NOVEMBER
T-491-4544 | PS5-28-OB-8143A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone I | 8 | To be completed |  | 19 | SEPTEMBER
T-591-4545 | PS5-62-OB-5145A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-09-04 | PS5-04-04 | PS5 - Milestone A | 1 | Closed | 6 | 45 | SEPTEMBER
T-262-4546 | PS5-37-OB-9992D | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | In progress |  | 9 | OCTOBER
T-909-4547 | PS5-31-OB-4336C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | To be completed |  | 17 | AUGUST
T-589-4548 | PS5-27-OB-5365D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone G | 6 | To be completed |  | 38 | NOVEMBER
T-473-4549 | PS5-77-OB-8888A | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-06-10 | PS5-04-01 | PS5 - Milestone A | 1 | Closed | 37 | 5 | JUNE
T-929-4550 | PS5-44-OB-8760D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone C | 2 | To be completed |  | 9 | OCTOBER
T-323-4551 | PS5-62-OB-4924A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone G | 6 | In progress |  | 36 | AUGUST
T-135-4552 | PS5-48-IK-4286B | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone E | 4 | To be completed |  | 40 | DECEMBER
T-399-4553 | PS5-72-IK-3529A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone B | 1.1 | In progress |  | 15 | NOVEMBER
T-053-4554 | PS5-17-UR-9114C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone G | 6 | In progress |  | 16 | DECEMBER
T-384-4555 | PS5-59-UR-3593B | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-08-14 | PS5-07-02 | PS5 - Milestone C | 2 | Closed | 36 | 30 | AUGUST
T-006-4556 | PS5-11-OB-8775B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | To be completed |  | 27 | DECEMBER
T-555-4557 | PS5-70-OB-6137A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-05-14 | PS5-04-04 | PS5 - Milestone C | 2 | Closed | 38 | 42 | MAY
T-382-4558 | PS5-68-OB-2687C | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone G | 6 | To be completed |  | 42 | AUGUST
T-153-4559 | PS5-95-OB-2659B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-11-14 | PS5-63-04 | PS5 - Milestone G | 6 | Closed | 17 | 40 | NOVEMBER
T-442-4560 | PS5-86-OB-8636D | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-05-11 | PS5-82-01 | PS5 - Milestone D | 3 | Closed | 45 | 43 | MAY
T-472-4561 | PS5-04-IK-6529D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-05-20 | PS5-07-03 | PS5 - Milestone H | 7 | Closed | 39 | 15 | MAY
T-205-4562 | PS5-65-IK-7879D | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-12-12 | PS5-08-01 | PS5 - Milestone F | 5 | Closed | 44 | 48 | DECEMBER
T-660-4563 | PS5-97-UR-9785B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-02-23 | PS5-10-06 | PS5 - Milestone F | 5 | Closed | 11 | 8 | FEBRUARY
T-359-4564 | PS5-08-UR-3566D | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-11-25 | PS5-04-01 | PS5 - Milestone F | 5 | Closed | 13 | 18 | NOVEMBER
T-773-4565 | PS5-33-UR-3274A | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-01-15 | PS5-02-02 | PS5 - Milestone G | 6 | Closed | 11 | 8 | JANUARY
T-547-4566 | PS5-63-OB-6440B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone I | 8 | In progress |  | 36 | DECEMBER
T-281-4567 | PS5-75-OB-3568B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone C | 2 | In progress |  | 27 | SEPTEMBER
T-953-4568 | PS5-69-IK-8135A | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone H | 7 | In progress |  | 26 | NOVEMBER
T-209-4569 | PS5-26-IK-1673B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | To be completed |  | 48 | DECEMBER
T-303-4570 | PS5-02-OB-4673B | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | To be completed |  | 44 | SEPTEMBER
T-305-4571 | PS5-36-OB-4094D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone B | 1.1 | To be completed |  | 30 | AUGUST
T-926-4572 | PS5-92-UR-3101B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-08-28 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 26 | 30 | AUGUST
T-970-4573 | PS5-99-UR-9291D | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone G | 6 | In progress |  | 16 | AUGUST
T-410-4574 | PS5-05-UR-7493D | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-04-15 | PS5-62-01 | PS5 - Milestone I | 8 | Closed | 40 | 12 | APRIL
T-539-4575 | PS5-81-UR-1168C | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone E | 4 | In progress |  | 33 | NOVEMBER
T-943-4576 | PS5-09-OB-6852C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone F | 5 | To be completed |  | 20 | AUGUST
T-018-4577 | PS5-68-UR-2688C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone E | 4 | To be completed |  | 22 | OCTOBER
T-793-4578 | PS5-94-OB-7679A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | On hold |  | 12 | NOVEMBER
T-748-4579 | PS5-71-OB-6644C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-04-05 | PS5-62-02 | PS5 - Milestone F | 5 | Closed | 17 | 19 | APRIL
T-656-4580 | PS5-67-OB-2934C | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone G | 6 | In progress |  | 35 | DECEMBER
T-472-4581 | PS5-03-OB-8897C | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone E | 4 | In progress |  | 11 | SEPTEMBER
T-592-4582 | PS5-32-OB-3967D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-07-11 | PS5-11-01 | PS5 - Milestone C | 2 | Closed | 46 | 5 | JULY
T-848-4583 | PS5-14-UR-7502D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-11-10 | PS5-06-01 | PS5 - Milestone A | 1 | Closed | 19 | 39 | NOVEMBER
T-454-4584 | PS5-57-IK-9495B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone I | 8 | To be completed |  | 6 | NOVEMBER
T-883-4585 | PS5-49-OB-4999B | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone F | 5 | On hold |  | 7 | DECEMBER
T-456-4586 | PS5-16-OB-3371A | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone B | 1.1 | To be completed |  | 22 | DECEMBER
T-802-4587 | PS5-01-IK-2086A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone I | 8 | On hold |  | 30 | NOVEMBER
T-353-4588 | PS5-89-UR-1071B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-08-26 | PS5-82-02 | PS5 - Milestone C | 2 | Closed | 17 | 33 | AUGUST
T-003-4589 | PS5-82-IK-5325A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-07-09 | PS5-60-10 | PS5 - Milestone A | 1 | Closed | 19 | 16 | JULY
T-690-4590 | PS5-13-OB-3284A | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-07-02 | PS5-04-03 | PS5 - Milestone B | 1.1 | Closed | 28 | 38 | JULY
T-271-4591 | PS5-68-OB-7017B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone I | 8 | In progress |  | 19 | AUGUST
T-690-4592 | PS5-42-OB-1739C | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | In progress |  | 12 | SEPTEMBER
T-023-4593 | PS5-88-UR-1910D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | To be completed |  | 38 | SEPTEMBER
T-884-4594 | PS5-79-IK-8911D | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-09-14 | PS5-07-04 | PS5 - Milestone C | 2 | Closed | 46 | 45 | SEPTEMBER
T-057-4595 | PS5-74-OB-6727A | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone E | 4 | In progress |  | 8 | DECEMBER
T-868-4596 | PS5-80-IK-3778D | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone C | 2 | In progress |  | 25 | AUGUST
T-966-4597 | PS5-68-OB-1402C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone E | 4 | To be completed |  | 22 | NOVEMBER
T-591-4598 | PS5-47-UR-7529C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-08-06 | PS5-01-06 | PS5 - Milestone I | 8 | Closed | 15 | 14 | AUGUST
T-368-4599 | PS5-83-OB-4485D | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | On hold |  | 39 | SEPTEMBER
T-365-4600 | PS5-28-IK-8871A | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone H | 7 | In progress |  | 34 | DECEMBER
T-956-4601 | PS5-43-UR-8415A | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone E | 4 | In progress |  | 14 | AUGUST
T-239-4602 | PS5-91-OB-4772A | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-04-13 | PS5-61-01 | PS5 - Milestone I | 8 | Closed | 30 | 42 | APRIL
T-342-4603 | PS5-86-UR-7706C | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | In progress |  | 6 | NOVEMBER
T-114-4604 | PS5-76-IK-9030B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone I | 8 | On hold |  | 18 | OCTOBER
T-468-4605 | PS5-14-OB-9137A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone D | 3 | To be completed |  | 27 | DECEMBER
T-476-4606 | PS5-79-OB-3289B | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone C | 2 | On hold |  | 21 | AUGUST
T-711-4607 | PS5-49-UR-1546D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone H | 7 | In progress |  | 32 | OCTOBER
T-145-4608 | PS5-31-OB-2343B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone I | 8 | To be completed |  | 42 | SEPTEMBER
T-583-4609 | PS5-10-OB-5300D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-10-13 | PS5-01-08 | PS5 - Milestone C | 2 | Closed | 22 | 38 | OCTOBER
T-499-4610 | PS5-39-UR-6725D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone B | 1.1 | In progress |  | 43 | DECEMBER
T-391-4611 | PS5-88-OB-7326A | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-06-20 | PS5-61-01 | PS5 - Milestone C | 2 | Closed | 29 | 30 | JUNE
T-173-4612 | PS5-83-UR-3831A | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | To be completed |  | 32 | NOVEMBER
T-794-4613 | PS5-43-IK-6522A | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone H | 7 | In progress |  | 29 | AUGUST
T-254-4614 | PS5-84-OB-3898B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-11-09 | PS5-02-01 | PS5 - Milestone G | 6 | Closed | 17 | 33 | NOVEMBER
T-727-4615 | PS5-86-OB-3643B | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-03-16 | PS5-61-07 | PS5 - Milestone B | 1.1 | Closed | 15 | 6 | MARCH
T-357-4616 | PS5-39-IK-7498B | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone A | 1 | In progress |  | 23 | NOVEMBER
T-689-4617 | PS5-32-OB-6991A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | To be completed |  | 10 | SEPTEMBER
T-774-4618 | PS5-90-IK-8715B | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-04-08 | PS5-08-01 | PS5 - Milestone C | 2 | Closed | 17 | 35 | APRIL
T-923-4619 | PS5-37-OB-8436D | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | In progress |  | 9 | DECEMBER
T-018-4620 | PS5-10-OB-9420B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-05-05 | PS5-06-03 | PS5 - Milestone C | 2 | Closed | 34 | 18 | MAY
T-672-4621 | PS5-45-IK-8597B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone G | 6 | In progress |  | 23 | OCTOBER
T-444-4622 | PS5-27-OB-1973D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | To be completed |  | 39 | SEPTEMBER
T-559-4623 | PS5-93-UR-3459D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone H | 7 | To be completed |  | 4 | NOVEMBER
T-991-4624 | PS5-28-IK-7916A | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone I | 8 | To be completed |  | 19 | DECEMBER
T-309-4625 | PS5-10-OB-2481D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-02-12 | PS5-07-01 | PS5 - Milestone F | 5 | Closed | 45 | 45 | FEBRUARY
T-074-4626 | PS5-09-UR-1540C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone C | 2 | To be completed |  | 11 | OCTOBER
T-673-4627 | PS5-45-OB-4561C | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | To be completed |  | 15 | OCTOBER
T-170-4628 | PS5-99-OB-7677D | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-05-26 | PS5-10-01 | PS5 - Milestone E | 4 | Closed | 34 | 24 | MAY
T-052-4629 | PS5-20-OB-6280D | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-10-10 | PS5-01-02 | PS5 - Milestone B | 1.1 | Closed | 22 | 12 | OCTOBER
T-230-4630 | PS5-16-OB-1262C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone B | 1.1 | In progress |  | 24 | SEPTEMBER
T-318-4631 | PS5-93-OB-5566C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | To be completed |  | 35 | AUGUST
T-953-4632 | PS5-97-OB-7443D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-12-26 | PS5-06-03 | PS5 - Milestone D | 3 | Closed | 14 | 5 | DECEMBER
T-754-4633 | PS5-85-OB-8054D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone F | 5 | On hold |  | 29 | NOVEMBER
T-439-4634 | PS5-65-IK-2963C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-03-23 | PS5-03-03 | PS5 - Milestone H | 7 | Closed | 13 | 33 | MARCH
T-219-4635 | PS5-46-OB-1934C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone E | 4 | To be completed |  | 29 | OCTOBER
T-531-4636 | PS5-36-UR-6620B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone E | 4 | To be completed |  | 21 | SEPTEMBER
T-901-4637 | PS5-93-UR-2144A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone E | 4 | In progress |  | 10 | AUGUST
T-918-4638 | PS5-09-OB-1374B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-11-02 | PS5-02-01 | PS5 - Milestone I | 8 | Closed | 42 | 24 | NOVEMBER
T-968-4639 | PS5-15-OB-5481A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone D | 3 | In progress |  | 33 | AUGUST
T-881-4640 | PS5-52-OB-5934D | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone I | 8 | On hold |  | 19 | SEPTEMBER
T-709-4641 | PS5-97-OB-5155B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | In progress |  | 31 | DECEMBER
T-125-4642 | PS5-05-IK-9570D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone G | 6 | To be completed |  | 7 | DECEMBER
T-717-4643 | PS5-42-UR-9356D | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone A | 1 | On hold |  | 44 | OCTOBER
T-859-4644 | PS5-36-OB-8259A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-12-16 | PS5-10-03 | PS5 - Milestone I | 8 | Closed | 25 | 38 | DECEMBER
T-618-4645 | PS5-96-IK-2972C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone A | 1 | On hold |  | 17 | SEPTEMBER
T-616-4646 | PS5-92-OB-4285A | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-04-16 | PS5-05-03 | PS5 - Milestone H | 7 | Closed | 36 | 24 | APRIL
T-953-4647 | PS5-76-OB-1713C | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-03-25 | PS5-02-01 | PS5 - Milestone G | 6 | Closed | 47 | 9 | MARCH
T-079-4648 | PS5-38-OB-1801B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone G | 6 | On hold |  | 36 | AUGUST
T-532-4649 | PS5-95-UR-3433B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-08-24 | PS5-11-02 | PS5 - Milestone H | 7 | Closed | 31 | 43 | AUGUST
T-182-4650 | PS5-45-OB-4161A | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone G | 6 | To be completed |  | 5 | OCTOBER
T-814-4651 | PS5-51-OB-9146A | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-08-13 | PS5-01-06 | PS5 - Milestone E | 4 | Closed | 42 | 29 | AUGUST
T-138-4652 | PS5-90-IK-2827C | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone G | 6 | On hold |  | 34 | OCTOBER
T-193-4653 | PS5-99-OB-6910D | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | To be completed |  | 6 | SEPTEMBER
T-824-4654 | PS5-46-UR-9613B | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-10-22 | PS5-10-06 | PS5 - Milestone F | 5 | Closed | 22 | 33 | OCTOBER
T-922-4655 | PS5-27-OB-8027B | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone A | 1 | To be completed |  | 36 | DECEMBER
T-043-4656 | PS5-15-OB-8756A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone C | 2 | In progress |  | 42 | NOVEMBER
T-039-4657 | PS5-69-OB-3911C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone F | 5 | To be completed |  | 18 | SEPTEMBER
T-942-4658 | PS5-85-IK-9839B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone D | 3 | In progress |  | 45 | AUGUST
T-871-4659 | PS5-24-IK-6333C | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone C | 2 | In progress |  | 29 | DECEMBER
T-530-4660 | PS5-97-UR-3894A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone G | 6 | To be completed |  | 21 | OCTOBER
T-688-4661 | PS5-02-IK-1209D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone I | 8 | To be completed |  | 33 | NOVEMBER
T-505-4662 | PS5-95-UR-6281A | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-11-14 | PS5-61-07 | PS5 - Milestone G | 6 | Closed | 16 | 28 | NOVEMBER
T-268-4663 | PS5-25-OB-3770D | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone B | 1.1 | To be completed |  | 12 | NOVEMBER
T-241-4664 | PS5-43-UR-4668C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | In progress |  | 45 | OCTOBER
T-886-4665 | PS5-80-OB-5192C | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | In progress |  | 48 | NOVEMBER
T-580-4666 | PS5-79-IK-7068C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-09-19 | PS5-04-04 | PS5 - Milestone D | 3 | Closed | 17 | 13 | SEPTEMBER
T-656-4667 | PS5-31-UR-8962A | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-02-13 | PS5-07-04 | PS5 - Milestone D | 3 | Closed | 38 | 22 | FEBRUARY
T-100-4668 | PS5-32-OB-4486C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone G | 6 | To be completed |  | 42 | DECEMBER
T-942-4669 | PS5-23-OB-5030D | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-08-20 | PS5-11-01 | PS5 - Milestone F | 5 | Closed | 6 | 6 | AUGUST
T-661-4670 | PS5-72-OB-9921C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-07-25 | PS5-82-07 | PS5 - Milestone H | 7 | Closed | 36 | 46 | JULY
T-671-4671 | PS5-93-IK-7624B | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-10-02 | PS5-01-08 | PS5 - Milestone D | 3 | Closed | 40 | 31 | OCTOBER
T-607-4672 | PS5-64-OB-6173C | CQM01 - Pump Installation | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-06-14 | PS5-09-01 | PS5 - Milestone H | 7 | Closed | 45 | 19 | JUNE
T-496-4673 | PS5-27-OB-9875B | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-11-09 | PS5-12-01 | PS5 - Milestone A | 1 | Closed | 39 | 28 | NOVEMBER
T-075-4674 | PS5-15-IK-4717A | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-05-18 | PS5-01-03 | PS5 - Milestone A | 1 | Closed | 31 | 40 | MAY
T-832-4675 | PS5-88-UR-8802C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-04-20 | PS5-61-07 | PS5 - Milestone H | 7 | Closed | 45 | 8 | APRIL
T-886-4676 | PS5-47-UR-4336B | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone A | 1 | To be completed |  | 21 | OCTOBER
T-278-4677 | PS5-58-OB-1386D | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-01-16 | PS5-03-01 | PS5 - Milestone B | 1.1 | Closed | 46 | 40 | JANUARY
T-487-4678 | PS5-92-OB-2833B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | In progress |  | 25 | OCTOBER
T-548-4679 | PS5-50-IK-3170B | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | In progress |  | 16 | SEPTEMBER
T-832-4680 | PS5-89-OB-4232C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | To be completed |  | 23 | OCTOBER
T-112-4681 | PS5-25-OB-3819D | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone A | 1 | In progress |  | 10 | OCTOBER
T-306-4682 | PS5-54-OB-7032C | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone B | 1.1 | To be completed |  | 44 | NOVEMBER
T-082-4683 | PS5-19-UR-3814A | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone E | 4 | On hold |  | 42 | AUGUST
T-803-4684 | PS5-54-OB-4452A | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone F | 5 | To be completed |  | 15 | DECEMBER
T-941-4685 | PS5-23-IK-1328B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-03-25 | PS5-10-04 | PS5 - Milestone H | 7 | Closed | 20 | 13 | MARCH
T-596-4686 | PS5-15-UR-4763D | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone H | 7 | On hold |  | 29 | SEPTEMBER
T-516-4687 | PS5-79-UR-6779B | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-05-16 | PS5-10-01 | PS5 - Milestone F | 5 | Closed | 31 | 22 | MAY
T-234-4688 | PS5-56-OB-1800A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | In progress |  | 20 | OCTOBER
T-559-4689 | PS5-66-OB-2736C | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone F | 5 | To be completed |  | 20 | DECEMBER
T-342-4690 | PS5-06-OB-4018D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-01-14 | PS5-03-01 | PS5 - Milestone A | 1 | Closed | 42 | 30 | JANUARY
T-160-4691 | PS5-61-OB-6996B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone B | 1.1 | On hold |  | 6 | DECEMBER
T-882-4692 | PS5-62-OB-3888A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone I | 8 | To be completed |  | 8 | AUGUST
T-836-4693 | PS5-97-UR-4180C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone B | 1.1 | On hold |  | 45 | SEPTEMBER
T-709-4694 | PS5-52-IK-3464D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-06-16 | PS5-01-01 | PS5 - Milestone D | 3 | Closed | 47 | 35 | JUNE
T-956-4695 | PS5-34-OB-8308B | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone F | 5 | On hold |  | 33 | AUGUST
T-962-4696 | PS5-54-OB-3349A | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | In progress |  | 33 | SEPTEMBER
T-983-4697 | PS5-87-UR-8367D | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone E | 4 | On hold |  | 4 | AUGUST
T-676-4698 | PS5-86-OB-5100B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-09-28 | PS5-62-01 | PS5 - Milestone H | 7 | Closed | 39 | 6 | SEPTEMBER
T-475-4699 | PS5-82-UR-9841C | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-12-10 | PS5-10-05 | PS5 - Milestone E | 4 | Closed | 11 | 18 | DECEMBER
T-739-4700 | PS5-42-IK-1787A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone B | 1.1 | To be completed |  | 46 | NOVEMBER
T-086-4701 | PS5-16-IK-8447D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-10-16 | PS5-13-01 | PS5 - Milestone D | 3 | Closed | 35 | 41 | OCTOBER
T-666-4702 | PS5-99-OB-5931C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | On hold |  | 40 | SEPTEMBER
T-128-4703 | PS5-54-OB-1512A | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone E | 4 | To be completed |  | 29 | OCTOBER
T-853-4704 | PS5-54-UR-7995A | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone A | 1 | To be completed |  | 20 | OCTOBER
T-106-4705 | PS5-32-UR-1814A | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone G | 6 | To be completed |  | 27 | DECEMBER
T-619-4706 | PS5-14-OB-2861B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-11-08 | PS5-01-04 | PS5 - Milestone H | 7 | Closed | 33 | 28 | NOVEMBER
T-534-4707 | PS5-89-OB-6384D | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-12-11 | PS5-10-03 | PS5 - Milestone H | 7 | Closed | 7 | 45 | DECEMBER
T-296-4708 | PS5-03-OB-6373B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-12-15 | PS5-07-01 | PS5 - Milestone B | 1.1 | Closed | 17 | 23 | DECEMBER
T-752-4709 | PS5-69-IK-8204A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone A | 1 | To be completed |  | 37 | DECEMBER
T-079-4710 | PS5-86-OB-7108D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-09-06 | PS5-10-06 | PS5 - Milestone D | 3 | Closed | 29 | 18 | SEPTEMBER
T-314-4711 | PS5-94-OB-7407B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone C | 2 | To be completed |  | 40 | AUGUST
T-530-4712 | PS5-94-OB-7845D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-02-09 | PS5-10-05 | PS5 - Milestone G | 6 | Closed | 48 | 11 | FEBRUARY
T-725-4713 | PS5-54-OB-6482A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | To be completed |  | 42 | OCTOBER
T-070-4714 | PS5-40-OB-2790B | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone A | 1 | To be completed |  | 40 | DECEMBER
T-060-4715 | PS5-95-UR-8631B | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-11-25 | PS5-04-01 | PS5 - Milestone B | 1.1 | Closed | 39 | 32 | NOVEMBER
T-691-4716 | PS5-64-IK-7983C | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-11-08 | PS5-02-02 | PS5 - Milestone E | 4 | Closed | 31 | 12 | NOVEMBER
T-247-4717 | PS5-49-IK-4648A | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-03-02 | PS5-99-02 | PS5 - Milestone F | 5 | Closed | 19 | 42 | MARCH
T-632-4718 | PS5-13-OB-3877A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-12-15 | PS5-07-02 | PS5 - Milestone A | 1 | Closed | 39 | 22 | DECEMBER
T-280-4719 | PS5-38-IK-1526C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-05-09 | PS5-99-01 | PS5 - Milestone A | 1 | Closed | 9 | 7 | MAY
T-780-4720 | PS5-47-UR-5307D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-09-05 | PS5-99-02 | PS5 - Milestone F | 5 | Closed | 37 | 9 | SEPTEMBER
T-124-4721 | PS5-04-OB-5962D | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-10-06 | PS5-60-04 | PS5 - Milestone G | 6 | Closed | 43 | 25 | OCTOBER
T-037-4722 | PS5-95-OB-6011B | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | In progress |  | 33 | NOVEMBER
T-211-4723 | PS5-45-OB-8537B | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone I | 8 | On hold |  | 29 | AUGUST
T-813-4724 | PS5-22-UR-6817D | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-11-20 | PS5-01-09 | PS5 - Milestone I | 8 | Closed | 24 | 25 | NOVEMBER
T-783-4725 | PS5-72-IK-4454B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-05-15 | PS5-62-02 | PS5 - Milestone F | 5 | Closed | 35 | 13 | MAY
T-497-4726 | PS5-75-UR-5215D | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone H | 7 | To be completed |  | 26 | SEPTEMBER
T-149-4727 | PS5-29-IK-6597D | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-07-07 | PS5-99-01 | PS5 - Milestone H | 7 | Closed | 35 | 12 | JULY
T-333-4728 | PS5-99-OB-2633C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-03-20 | PS5-02-02 | PS5 - Milestone F | 5 | Closed | 11 | 19 | MARCH
T-781-4729 | PS5-03-IK-4703A | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-02-14 | PS5-99-01 | PS5 - Milestone D | 3 | Closed | 47 | 32 | FEBRUARY
T-247-4730 | PS5-15-OB-9636A | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone D | 3 | To be completed |  | 27 | AUGUST
T-330-4731 | PS5-83-UR-8256B | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone F | 5 | On hold |  | 18 | OCTOBER
T-624-4732 | PS5-45-OB-7417C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone B | 1.1 | In progress |  | 25 | SEPTEMBER
T-813-4733 | PS5-59-OB-5493D | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone D | 3 | To be completed |  | 6 | SEPTEMBER
T-546-4734 | PS5-35-IK-6580A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone E | 4 | To be completed |  | 19 | SEPTEMBER
T-269-4735 | PS5-37-UR-4661C | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | To be completed |  | 25 | AUGUST
T-705-4736 | PS5-53-OB-2476C | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-08-03 | PS5-12-02 | PS5 - Milestone I | 8 | Closed | 11 | 33 | AUGUST
T-411-4737 | PS5-37-IK-3017A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | In progress |  | 44 | OCTOBER
T-129-4738 | PS5-09-UR-6075C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone F | 5 | To be completed |  | 14 | OCTOBER
T-293-4739 | PS5-04-IK-8199C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-09-24 | PS5-09-01 | PS5 - Milestone F | 5 | Closed | 16 | 41 | SEPTEMBER
T-510-4740 | PS5-41-OB-8425B | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone D | 3 | To be completed |  | 41 | DECEMBER
T-660-4741 | PS5-31-OB-9328C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-08-28 | PS5-99-03 | PS5 - Milestone B | 1.1 | Closed | 6 | 10 | AUGUST
T-248-4742 | PS5-36-UR-9106A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-12-24 | PS5-02-03 | PS5 - Milestone E | 4 | Closed | 44 | 40 | DECEMBER
T-037-4743 | PS5-37-OB-1167C | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-05-28 | PS5-09-02 | PS5 - Milestone G | 6 | Closed | 26 | 31 | MAY
T-375-4744 | PS5-83-IK-4665B | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone G | 6 | In progress |  | 35 | NOVEMBER
T-234-4745 | PS5-35-IK-7827B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone H | 7 | To be completed |  | 8 | AUGUST
T-412-4746 | PS5-61-IK-2806C | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone I | 8 | On hold |  | 11 | SEPTEMBER
T-230-4747 | PS5-99-OB-1924D | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-09 | PS5-60-01 | PS5 - Milestone B | 1.1 | Closed | 48 | 20 | APRIL
T-245-4748 | PS5-76-UR-2598A | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-09-03 | PS5-09-03 | PS5 - Milestone B | 1.1 | Closed | 17 | 18 | SEPTEMBER
T-817-4749 | PS5-78-OB-8786C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone A | 1 | In progress |  | 11 | NOVEMBER
T-939-4750 | PS5-39-OB-8248B | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone I | 8 | To be completed |  | 24 | NOVEMBER
T-364-4751 | PS5-66-OB-7888C | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-08-13 | PS5-61-01 | PS5 - Milestone I | 8 | Closed | 6 | 20 | AUGUST
T-222-4752 | PS5-94-OB-7286D | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-26 | PS5-60-04 | PS5 - Milestone B | 1.1 | Closed | 36 | 25 | APRIL
T-959-4753 | PS5-71-OB-7888B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-09-07 | PS5-09-02 | PS5 - Milestone B | 1.1 | Closed | 9 | 18 | SEPTEMBER
T-904-4754 | PS5-61-OB-2290C | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone D | 3 | On hold |  | 25 | NOVEMBER
T-548-4755 | PS5-02-OB-7027D | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-05-06 | PS5-05-01 | PS5 - Milestone B | 1.1 | Closed | 42 | 48 | MAY
T-114-4756 | PS5-82-OB-1309A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-02-28 | PS5-02-03 | PS5 - Milestone H | 7 | Closed | 42 | 40 | FEBRUARY
T-076-4757 | PS5-26-OB-2007D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone H | 7 | To be completed |  | 5 | SEPTEMBER
T-976-4758 | PS5-42-OB-1693B | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-03-19 | PS5-99-02 | PS5 - Milestone E | 4 | Closed | 12 | 26 | MARCH
T-026-4759 | PS5-14-IK-1867C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-02-11 | PS5-10-03 | PS5 - Milestone A | 1 | Closed | 8 | 12 | FEBRUARY
T-061-4760 | PS5-14-IK-7055C | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone D | 3 | In progress |  | 9 | OCTOBER
T-416-4761 | PS5-29-OB-8856D | CQM03 - Heat Exchanger | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone D | 3 | In progress |  | 35 | NOVEMBER
T-996-4762 | PS5-44-UR-2872A | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone B | 1.1 | In progress |  | 45 | OCTOBER
T-921-4763 | PS5-42-OB-6191A | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-07-21 | PS5-08-01 | PS5 - Milestone B | 1.1 | Closed | 31 | 16 | JULY
T-901-4764 | PS5-81-UR-9262C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-10-07 | PS5-82-02 | PS5 - Milestone H | 7 | Closed | 5 | 17 | OCTOBER
T-983-4765 | PS5-42-OB-8559D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone E | 4 | In progress |  | 44 | NOVEMBER
T-006-4766 | PS5-08-IK-9898D | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone E | 4 | To be completed |  | 9 | AUGUST
T-564-4767 | PS5-35-OB-9701D | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-07-21 | PS5-10-06 | PS5 - Milestone D | 3 | Closed | 4 | 20 | JULY
T-458-4768 | PS5-94-UR-1852A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone E | 4 | In progress |  | 8 | NOVEMBER
T-271-4769 | PS5-23-IK-6171A | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-08-25 | PS5-09-04 | PS5 - Milestone G | 6 | Closed | 29 | 9 | AUGUST
T-365-4770 | PS5-61-UR-5683D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-12-17 | PS5-60-10 | PS5 - Milestone I | 8 | Closed | 37 | 41 | DECEMBER
T-208-4771 | PS5-78-IK-3237D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | In progress |  | 6 | SEPTEMBER
T-493-4772 | PS5-46-UR-9024D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone D | 3 | In progress |  | 23 | DECEMBER
T-168-4773 | PS5-29-UR-4959B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone E | 4 | To be completed |  | 32 | NOVEMBER
T-342-4774 | PS5-26-OB-1414C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-05-14 | PS5-02-03 | PS5 - Milestone E | 4 | Closed | 12 | 11 | MAY
T-511-4775 | PS5-32-OB-7535D | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | To be completed |  | 42 | NOVEMBER
T-059-4776 | PS5-54-OB-8125D | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-11-17 | PS5-05-01 | PS5 - Milestone B | 1.1 | Closed | 6 | 30 | NOVEMBER
T-049-4777 | PS5-09-IK-6240C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-07-25 | PS5-02-01 | PS5 - Milestone I | 8 | Closed | 47 | 4 | JULY
T-279-4778 | PS5-11-IK-6781C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-03-23 | PS5-02-03 | PS5 - Milestone E | 4 | Closed | 11 | 26 | MARCH
T-889-4779 | PS5-53-IK-2237B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone H | 7 | On hold |  | 22 | DECEMBER
T-105-4780 | PS5-23-OB-8861C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | In progress |  | 10 | SEPTEMBER
T-940-4781 | PS5-84-OB-1957A | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-02-05 | PS5-05-02 | PS5 - Milestone G | 6 | Closed | 26 | 25 | FEBRUARY
T-904-4782 | PS5-31-UR-8785A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-07-02 | PS5-08-02 | PS5 - Milestone C | 2 | Closed | 28 | 31 | JULY
T-981-4783 | PS5-15-IK-6858B | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone B | 1.1 | To be completed |  | 38 | AUGUST
T-591-4784 | PS5-68-UR-4235B | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone D | 3 | To be completed |  | 42 | SEPTEMBER
T-157-4785 | PS5-53-OB-7136B | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone H | 7 | In progress |  | 39 | NOVEMBER
T-546-4786 | PS5-86-IK-3508B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-02-19 | PS5-07-03 | PS5 - Milestone E | 4 | Closed | 34 | 30 | FEBRUARY
T-513-4787 | PS5-78-IK-3043C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-01-08 | PS5-63-01 | PS5 - Milestone B | 1.1 | Closed | 5 | 13 | JANUARY
T-429-4788 | PS5-74-OB-5298C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone B | 1.1 | On hold |  | 14 | SEPTEMBER
T-697-4789 | PS5-74-OB-7322B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone H | 7 | To be completed |  | 17 | DECEMBER
T-452-4790 | PS5-24-IK-7875C | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-10-21 | PS5-60-10 | PS5 - Milestone D | 3 | Closed | 46 | 28 | OCTOBER
T-141-4791 | PS5-91-OB-5086D | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | To be completed |  | 15 | OCTOBER
T-875-4792 | PS5-01-IK-9142B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone B | 1.1 | In progress |  | 25 | SEPTEMBER
T-324-4793 | PS5-99-IK-1378B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-10-03 | PS5-01-03 | PS5 - Milestone A | 1 | Closed | 34 | 46 | OCTOBER
T-926-4794 | PS5-05-IK-8993B | CQX04 - Painting & Coating | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-02-11 | PS5-10-06 | PS5 - Milestone F | 5 | Closed | 16 | 27 | FEBRUARY
T-767-4795 | PS5-34-OB-4968C | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | To be completed |  | 28 | NOVEMBER
T-667-4796 | PS5-41-OB-2074C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-03-20 | PS5-10-02 | PS5 - Milestone E | 4 | Closed | 10 | 26 | MARCH
T-724-4797 | PS5-52-IK-1437B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone C | 2 | On hold |  | 30 | DECEMBER
T-661-4798 | PS5-02-OB-1252A | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone I | 8 | To be completed |  | 22 | DECEMBER
T-365-4799 | PS5-14-IK-3298C | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | To be completed |  | 19 | OCTOBER
T-768-4800 | PS5-91-OB-6147D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone H | 7 | To be completed |  | 47 | AUGUST
T-816-4801 | PS5-46-OB-2655C | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-06-18 | PS5-10-05 | PS5 - Milestone H | 7 | Closed | 8 | 10 | JUNE
T-846-4802 | PS5-85-IK-9708A | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone I | 8 | To be completed |  | 48 | OCTOBER
T-414-4803 | PS5-86-UR-7145C | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | To be completed |  | 22 | NOVEMBER
T-992-4804 | PS5-07-OB-9031C | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-03-04 | PS5-05-03 | PS5 - Milestone B | 1.1 | Closed | 15 | 4 | MARCH
T-847-4805 | PS5-76-OB-2372D | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone G | 6 | On hold |  | 11 | AUGUST
T-959-4806 | PS5-12-IK-2992C | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | To be completed |  | 35 | NOVEMBER
T-061-4807 | PS5-40-UR-9410C | CQM01 - Pump Installation | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | In progress |  | 14 | OCTOBER
T-319-4808 | PS5-65-UR-9516D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-12-05 | PS5-82-01 | PS5 - Milestone E | 4 | Closed | 10 | 48 | DECEMBER
T-860-4809 | PS5-15-UR-1366C | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | On hold |  | 33 | OCTOBER
T-509-4810 | PS5-53-IK-3689C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-04-26 | PS5-10-03 | PS5 - Milestone F | 5 | Closed | 39 | 39 | APRIL
T-314-4811 | PS5-29-IK-6438D | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone B | 1.1 | To be completed |  | 48 | NOVEMBER
T-808-4812 | PS5-85-UR-4873C | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-03-03 | PS5-82-02 | PS5 - Milestone I | 8 | Closed | 17 | 40 | MARCH
T-792-4813 | PS5-38-IK-9286A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-06-08 | PS5-09-02 | PS5 - Milestone D | 3 | Closed | 42 | 41 | JUNE
T-108-4814 | PS5-07-UR-7962C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone E | 4 | To be completed |  | 42 | AUGUST
T-839-4815 | PS5-42-UR-5387B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone A | 1 | In progress |  | 28 | OCTOBER
T-347-4816 | PS5-51-OB-5930B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-03-05 | PS5-09-01 | PS5 - Milestone I | 8 | Closed | 36 | 28 | MARCH
T-017-4817 | PS5-93-OB-4502D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone I | 8 | In progress |  | 21 | OCTOBER
T-482-4818 | PS5-81-IK-1617A | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone H | 7 | To be completed |  | 27 | SEPTEMBER
T-806-4819 | PS5-86-OB-1872B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-05-27 | PS5-03-01 | PS5 - Milestone G | 6 | Closed | 30 | 6 | MAY
T-117-4820 | PS5-02-IK-7540A | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone C | 2 | To be completed |  | 37 | SEPTEMBER
T-284-4821 | PS5-69-OB-4185D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-04-03 | PS5-01-04 | PS5 - Milestone G | 6 | Closed | 19 | 23 | APRIL
T-994-4822 | PS5-73-OB-2621A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone E | 4 | On hold |  | 31 | DECEMBER
T-128-4823 | PS5-98-UR-4475B | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-04-04 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 20 | 30 | APRIL
T-738-4824 | PS5-82-UR-9568C | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-10-11 | PS5-99-02 | PS5 - Milestone C | 2 | Closed | 25 | 29 | OCTOBER
T-377-4825 | PS5-13-UR-8692B | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | To be completed |  | 18 | SEPTEMBER
T-152-4826 | PS5-12-UR-3861C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-06-12 | PS5-07-01 | PS5 - Milestone H | 7 | Closed | 9 | 20 | JUNE
T-443-4827 | PS5-44-OB-6648C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | To be completed |  | 21 | NOVEMBER
T-235-4828 | PS5-87-OB-6157A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-09-04 | PS5-08-02 | PS5 - Milestone C | 2 | Closed | 37 | 20 | SEPTEMBER
T-715-4829 | PS5-22-OB-5020D | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone E | 4 | To be completed |  | 48 | NOVEMBER
T-147-4830 | PS5-96-IK-5995C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-07-22 | PS5-08-02 | PS5 - Milestone H | 7 | Closed | 41 | 29 | JULY
T-678-4831 | PS5-48-UR-2681D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-02-12 | PS5-63-01 | PS5 - Milestone G | 6 | Closed | 20 | 27 | FEBRUARY
T-476-4832 | PS5-66-OB-8245A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone B | 1.1 | In progress |  | 41 | OCTOBER
T-810-4833 | PS5-03-UR-9698D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-16 | PS5-60-04 | PS5 - Milestone A | 1 | Closed | 4 | 37 | MAY
T-356-4834 | PS5-04-UR-9753D | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-12-14 | PS5-01-04 | PS5 - Milestone C | 2 | Closed | 4 | 15 | DECEMBER
T-667-4835 | PS5-13-UR-3884B | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-12-05 | PS5-10-02 | PS5 - Milestone D | 3 | Closed | 18 | 29 | DECEMBER
T-826-4836 | PS5-34-UR-6712B | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone E | 4 | In progress |  | 5 | NOVEMBER
T-308-4837 | PS5-33-IK-5914A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone B | 1.1 | In progress |  | 34 | AUGUST
T-622-4838 | PS5-33-UR-8671D | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-02-22 | PS5-06-02 | PS5 - Milestone H | 7 | Closed | 18 | 39 | FEBRUARY
T-407-4839 | PS5-27-OB-3011A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-01-09 | PS5-13-01 | PS5 - Milestone C | 2 | Closed | 37 | 20 | JANUARY
T-093-4840 | PS5-74-OB-2767C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone I | 8 | To be completed |  | 7 | SEPTEMBER
T-751-4841 | PS5-06-IK-2938A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-07-01 | PS5-03-03 | PS5 - Milestone D | 3 | Closed | 4 | 33 | JULY
T-265-4842 | PS5-14-UR-8833B | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone B | 1.1 | In progress |  | 33 | DECEMBER
T-777-4843 | PS5-90-OB-7578D | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-12-02 | PS5-09-03 | PS5 - Milestone I | 8 | Closed | 19 | 43 | DECEMBER
T-055-4844 | PS5-54-OB-6656A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone H | 7 | To be completed |  | 35 | NOVEMBER
T-969-4845 | PS5-48-OB-7239B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone F | 5 | On hold |  | 21 | AUGUST
T-163-4846 | PS5-13-OB-2724A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone I | 8 | To be completed |  | 5 | NOVEMBER
T-268-4847 | PS5-06-IK-5320A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-02-26 | PS5-13-01 | PS5 - Milestone A | 1 | Closed | 4 | 28 | FEBRUARY
T-050-4848 | PS5-53-UR-8296B | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone E | 4 | To be completed |  | 13 | AUGUST
T-348-4849 | PS5-84-OB-3119C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-06-21 | PS5-04-03 | PS5 - Milestone A | 1 | Closed | 17 | 29 | JUNE
T-037-4850 | PS5-18-OB-3196B | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-03-10 | PS5-09-01 | PS5 - Milestone E | 4 | Closed | 42 | 33 | MARCH
T-175-4851 | PS5-02-OB-6258C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone B | 1.1 | To be completed |  | 10 | NOVEMBER
T-157-4852 | PS5-08-OB-1614B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-10-25 | PS5-63-04 | PS5 - Milestone D | 3 | Closed | 42 | 7 | OCTOBER
T-386-4853 | PS5-55-OB-7392B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone G | 6 | To be completed |  | 6 | OCTOBER
T-399-4854 | PS5-20-IK-5225A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-04-14 | PS5-03-01 | PS5 - Milestone I | 8 | Closed | 5 | 30 | APRIL
T-352-4855 | PS5-28-IK-3230C | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone E | 4 | To be completed |  | 46 | SEPTEMBER
T-039-4856 | PS5-85-OB-6832C | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-11-05 | PS5-01-05 | PS5 - Milestone D | 3 | Closed | 15 | 41 | NOVEMBER
T-607-4857 | PS5-81-OB-1022B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone D | 3 | On hold |  | 19 | OCTOBER
T-158-4858 | PS5-40-OB-9728A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | In progress |  | 16 | OCTOBER
T-533-4859 | PS5-16-OB-1652D | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone B | 1.1 | To be completed |  | 41 | NOVEMBER
T-218-4860 | PS5-34-UR-2469B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | To be completed |  | 43 | NOVEMBER
T-012-4861 | PS5-63-OB-3043A | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone B | 1.1 | On hold |  | 20 | NOVEMBER
T-835-4862 | PS5-58-UR-6417C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone G | 6 | On hold |  | 46 | NOVEMBER
T-035-4863 | PS5-01-OB-7756B | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-02-11 | PS5-61-07 | PS5 - Milestone H | 7 | Closed | 6 | 5 | FEBRUARY
T-656-4864 | PS5-11-UR-5615B | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | To be completed |  | 46 | AUGUST
T-348-4865 | PS5-01-UR-8654A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | To be completed |  | 32 | SEPTEMBER
T-025-4866 | PS5-08-IK-3975A | CQS01 - Fire Protection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-05-16 | PS5-11-03 | PS5 - Milestone G | 6 | Closed | 25 | 36 | MAY
T-910-4867 | PS5-49-IK-4856C | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-05-07 | PS5-08-01 | PS5 - Milestone G | 6 | Closed | 22 | 13 | MAY
T-123-4868 | PS5-98-OB-2158A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-05-25 | PS5-07-03 | PS5 - Milestone E | 4 | Closed | 23 | 16 | MAY
T-204-4869 | PS5-98-IK-3472B | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-05-07 | PS5-08-02 | PS5 - Milestone B | 1.1 | Closed | 27 | 32 | MAY
T-814-4870 | PS5-83-OB-2091A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-11-19 | PS5-09-03 | PS5 - Milestone A | 1 | Closed | 4 | 34 | NOVEMBER
T-840-4871 | PS5-27-OB-8863C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone D | 3 | In progress |  | 5 | NOVEMBER
T-448-4872 | PS5-62-IK-9423C | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-03-11 | PS5-02-01 | PS5 - Milestone A | 1 | Closed | 13 | 8 | MARCH
T-369-4873 | PS5-63-OB-7293C | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | In progress |  | 7 | SEPTEMBER
T-015-4874 | PS5-93-UR-6217A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | In progress |  | 10 | AUGUST
T-644-4875 | PS5-59-OB-5755B | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone D | 3 | To be completed |  | 36 | SEPTEMBER
T-475-4876 | PS5-32-UR-3828A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone C | 2 | To be completed |  | 27 | AUGUST
T-801-4877 | PS5-91-IK-9849B | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone H | 7 | To be completed |  | 8 | NOVEMBER
T-685-4878 | PS5-32-OB-4735D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-06-06 | PS5-09-02 | PS5 - Milestone H | 7 | Closed | 8 | 19 | JUNE
T-274-4879 | PS5-64-OB-8630C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-12-26 | PS5-03-03 | PS5 - Milestone I | 8 | Closed | 44 | 22 | DECEMBER
T-381-4880 | PS5-84-IK-7021A | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-05-24 | PS5-01-07 | PS5 - Milestone F | 5 | Closed | 15 | 32 | MAY
T-053-4881 | PS5-53-OB-7563C | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-03-21 | PS5-04-01 | PS5 - Milestone F | 5 | Closed | 7 | 37 | MARCH
T-168-4882 | PS5-87-IK-2244C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-09-28 | PS5-01-06 | PS5 - Milestone A | 1 | Closed | 20 | 12 | SEPTEMBER
T-407-4883 | PS5-35-IK-1768D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone I | 8 | In progress |  | 37 | NOVEMBER
T-707-4884 | PS5-66-IK-7927B | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone F | 5 | To be completed |  | 48 | OCTOBER
T-733-4885 | PS5-28-IK-9755A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | To be completed |  | 9 | SEPTEMBER
T-625-4886 | PS5-59-OB-8229B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | In progress |  | 35 | DECEMBER
T-636-4887 | PS5-72-UR-7218A | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone C | 2 | In progress |  | 5 | OCTOBER
T-217-4888 | PS5-78-IK-5674D | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-07-26 | PS5-08-02 | PS5 - Milestone G | 6 | Closed | 45 | 12 | JULY
T-143-4889 | PS5-40-OB-7380C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | To be completed |  | 7 | AUGUST
T-828-4890 | PS5-71-IK-1368C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-10-17 | PS5-04-01 | PS5 - Milestone E | 4 | Closed | 10 | 47 | OCTOBER
T-960-4891 | PS5-11-OB-5746D | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone C | 2 | In progress |  | 31 | SEPTEMBER
T-174-4892 | PS5-15-UR-1579A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-05-02 | PS5-99-02 | PS5 - Milestone G | 6 | Closed | 17 | 17 | MAY
T-782-4893 | PS5-80-OB-9471C | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-06-10 | PS5-06-03 | PS5 - Milestone C | 2 | Closed | 28 | 30 | JUNE
T-469-4894 | PS5-69-IK-1345C | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-12-01 | PS5-05-03 | PS5 - Milestone E | 4 | Closed | 38 | 36 | DECEMBER
T-338-4895 | PS5-77-IK-7651D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-10-21 | PS5-07-04 | PS5 - Milestone F | 5 | Closed | 13 | 13 | OCTOBER
T-925-4896 | PS5-61-IK-8342B | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone A | 1 | On hold |  | 40 | AUGUST
T-302-4897 | PS5-19-UR-6330B | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-03-06 | PS5-03-01 | PS5 - Milestone B | 1.1 | Closed | 38 | 15 | MARCH
T-259-4898 | PS5-04-OB-4718C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-05-02 | PS5-61-02 | PS5 - Milestone H | 7 | Closed | 45 | 25 | MAY
T-451-4899 | PS5-88-OB-6121C | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone F | 5 | On hold |  | 30 | AUGUST
T-654-4900 | PS5-41-OB-7318D | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-09-14 | PS5-10-06 | PS5 - Milestone G | 6 | Closed | 28 | 48 | SEPTEMBER
T-153-4901 | PS5-28-OB-5279A | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone F | 5 | In progress |  | 23 | OCTOBER
T-226-4902 | PS5-67-OB-6187C | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone E | 4 | In progress |  | 21 | OCTOBER
T-010-4903 | PS5-75-UR-7998D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | To be completed |  | 23 | OCTOBER
T-935-4904 | PS5-40-UR-7965A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-07-11 | PS5-01-03 | PS5 - Milestone B | 1.1 | Closed | 35 | 4 | JULY
T-079-4905 | PS5-95-UR-2631D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-05-10 | PS5-10-04 | PS5 - Milestone G | 6 | Closed | 29 | 40 | MAY
T-882-4906 | PS5-44-UR-5982A | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-04-22 | PS5-03-23 | PS5 - Milestone E | 4 | Closed | 40 | 41 | APRIL
T-627-4907 | PS5-32-OB-1725A | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-07-18 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 38 | 18 | JULY
T-842-4908 | PS5-95-UR-5479B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-09-03 | PS5-01-04 | PS5 - Milestone G | 6 | Closed | 21 | 23 | SEPTEMBER
T-655-4909 | PS5-42-OB-3664D | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-04-28 | PS5-10-01 | PS5 - Milestone B | 1.1 | Closed | 8 | 15 | APRIL
T-311-4910 | PS5-36-OB-8462A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-08-18 | PS5-08-02 | PS5 - Milestone G | 6 | Closed | 33 | 47 | AUGUST
T-951-4911 | PS5-02-OB-4573D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone C | 2 | In progress |  | 38 | NOVEMBER
T-431-4912 | PS5-99-OB-2268A | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone C | 2 | In progress |  | 19 | SEPTEMBER
T-796-4913 | PS5-78-OB-3861D | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | To be completed |  | 18 | OCTOBER
T-398-4914 | PS5-70-OB-3271C | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-10-21 | PS5-63-01 | PS5 - Milestone G | 6 | Closed | 34 | 9 | OCTOBER
T-683-4915 | PS5-32-OB-3834A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | To be completed |  | 8 | OCTOBER
T-058-4916 | PS5-50-OB-1078D | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-06-16 | PS5-12-01 | PS5 - Milestone D | 3 | Closed | 28 | 39 | JUNE
T-081-4917 | PS5-31-OB-9023D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone H | 7 | In progress |  | 34 | DECEMBER
T-610-4918 | PS5-35-IK-4613B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone A | 1 | To be completed |  | 21 | AUGUST
T-331-4919 | PS5-56-OB-7318C | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-02-23 | PS5-10-01 | PS5 - Milestone D | 3 | Closed | 46 | 21 | FEBRUARY
T-915-4920 | PS5-73-IK-2892A | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone I | 8 | To be completed |  | 40 | SEPTEMBER
T-506-4921 | PS5-70-UR-1713A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-03-16 | PS5-02-03 | PS5 - Milestone I | 8 | Closed | 16 | 18 | MARCH
T-058-4922 | PS5-74-OB-3011A | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone H | 7 | To be completed |  | 4 | DECEMBER
T-743-4923 | PS5-58-IK-4826C | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone F | 5 | To be completed |  | 44 | OCTOBER
T-209-4924 | PS5-46-OB-1409B | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-12-21 | PS5-99-02 | PS5 - Milestone G | 6 | Closed | 11 | 44 | DECEMBER
T-050-4925 | PS5-97-OB-4979B | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-10-05 | PS5-07-04 | PS5 - Milestone G | 6 | Closed | 35 | 8 | OCTOBER
T-729-4926 | PS5-57-UR-1933B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone G | 6 | To be completed |  | 24 | OCTOBER
T-321-4927 | PS5-16-UR-4091B | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-07-15 | PS5-82-01 | PS5 - Milestone I | 8 | Closed | 25 | 16 | JULY
T-490-4928 | PS5-47-UR-8280D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone A | 1 | In progress |  | 24 | SEPTEMBER
T-807-4929 | PS5-85-UR-4603B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-12-23 | PS5-01-01 | PS5 - Milestone G | 6 | Closed | 24 | 44 | DECEMBER
T-559-4930 | PS5-20-OB-9206A | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone G | 6 | In progress |  | 12 | SEPTEMBER
T-461-4931 | PS5-96-OB-2294A | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-11-22 | PS5-62-01 | PS5 - Milestone F | 5 | Closed | 9 | 47 | NOVEMBER
T-987-4932 | PS5-33-OB-2322C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone H | 7 | To be completed |  | 6 | OCTOBER
T-470-4933 | PS5-85-IK-9278D | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone E | 4 | To be completed |  | 19 | OCTOBER
T-937-4934 | PS5-81-IK-4409C | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone H | 7 | On hold |  | 23 | AUGUST
T-915-4935 | PS5-37-IK-3136A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone H | 7 | To be completed |  | 48 | OCTOBER
T-139-4936 | PS5-74-OB-2211A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone I | 8 | To be completed |  | 6 | NOVEMBER
T-496-4937 | PS5-47-IK-8603A | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | In progress |  | 43 | DECEMBER
T-443-4938 | PS5-75-OB-5808C | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone A | 1 | On hold |  | 38 | OCTOBER
T-142-4939 | PS5-60-OB-4077A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone D | 3 | To be completed |  | 48 | SEPTEMBER
T-982-4940 | PS5-31-OB-8974B | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-06-17 | PS5-03-23 | PS5 - Milestone G | 6 | Closed | 6 | 20 | JUNE
T-488-4941 | PS5-94-IK-8561A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-01-23 | PS5-03-02 | PS5 - Milestone I | 8 | Closed | 16 | 26 | JANUARY
T-677-4942 | PS5-64-OB-3094D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone B | 1.1 | In progress |  | 38 | SEPTEMBER
T-473-4943 | PS5-22-IK-3432D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone A | 1 | To be completed |  | 20 | AUGUST
T-356-4944 | PS5-30-UR-6100D | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone E | 4 | In progress |  | 23 | AUGUST
T-696-4945 | PS5-67-OB-8717D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone I | 8 | To be completed |  | 22 | AUGUST
T-562-4946 | PS5-12-IK-8866A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone F | 5 | On hold |  | 44 | AUGUST
T-850-4947 | PS5-54-UR-9070C | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone H | 7 | To be completed |  | 7 | SEPTEMBER
T-466-4948 | PS5-25-OB-4389A | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone E | 4 | In progress |  | 37 | OCTOBER
T-322-4949 | PS5-64-IK-9332C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-12-14 | PS5-02-02 | PS5 - Milestone C | 2 | Closed | 5 | 46 | DECEMBER
T-667-4950 | PS5-13-UR-8821B | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | In progress |  | 7 | AUGUST
T-462-4951 | PS5-87-OB-2718C | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | In progress |  | 4 | AUGUST
T-445-4952 | PS5-91-IK-1813D | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone B | 1.1 | To be completed |  | 34 | SEPTEMBER
T-470-4953 | PS5-06-OB-6379D | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone H | 7 | In progress |  | 46 | OCTOBER
T-785-4954 | PS5-66-UR-1536D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | On hold |  | 18 | OCTOBER
T-990-4955 | PS5-86-UR-6967B | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-09-11 | PS5-11-03 | PS5 - Milestone B | 1.1 | Closed | 46 | 17 | SEPTEMBER
T-918-4956 | PS5-80-OB-8716A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-04-01 | PS5-62-01 | PS5 - Milestone F | 5 | Closed | 32 | 18 | APRIL
T-211-4957 | PS5-39-IK-5328D | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone C | 2 | To be completed |  | 5 | NOVEMBER
T-313-4958 | PS5-72-OB-4901B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone H | 7 | To be completed |  | 24 | SEPTEMBER
T-408-4959 | PS5-60-UR-1789C | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-09-05 | PS5-06-01 | PS5 - Milestone G | 6 | Closed | 39 | 10 | SEPTEMBER
T-970-4960 | PS5-74-IK-3601A | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-09-07 | PS5-03-23 | PS5 - Milestone B | 1.1 | Closed | 10 | 26 | SEPTEMBER
T-960-4961 | PS5-58-OB-4626A | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone E | 4 | In progress |  | 39 | NOVEMBER
T-399-4962 | PS5-34-OB-4986D | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone C | 2 | To be completed |  | 21 | AUGUST
T-514-4963 | PS5-56-UR-5776B | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone G | 6 | To be completed |  | 7 | DECEMBER
T-663-4964 | PS5-27-OB-7062C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone E | 4 | On hold |  | 48 | NOVEMBER
T-474-4965 | PS5-22-UR-3872B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-14 | PS5-60-04 | PS5 - Milestone C | 2 | Closed | 43 | 37 | APRIL
T-075-4966 | PS5-11-OB-4217C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone A | 1 | In progress |  | 16 | NOVEMBER
T-531-4967 | PS5-57-OB-5655B | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-03-24 | PS5-09-01 | PS5 - Milestone I | 8 | Closed | 27 | 27 | MARCH
T-034-4968 | PS5-28-OB-7040C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-05-14 | PS5-60-07 | PS5 - Milestone D | 3 | Closed | 12 | 25 | MAY
T-613-4969 | PS5-96-UR-5563B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-09-08 | PS5-01-09 | PS5 - Milestone E | 4 | Closed | 9 | 24 | SEPTEMBER
T-028-4970 | PS5-78-OB-9081D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone C | 2 | In progress |  | 34 | DECEMBER
T-947-4971 | PS5-99-OB-8715B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-07-15 | PS5-07-04 | PS5 - Milestone A | 1 | Closed | 38 | 38 | JULY
T-691-4972 | PS5-86-IK-9271B | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone H | 7 | On hold |  | 42 | NOVEMBER
T-226-4973 | PS5-77-UR-6136C | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-07-27 | PS5-03-01 | PS5 - Milestone F | 5 | Closed | 41 | 6 | JULY
T-814-4974 | PS5-31-OB-4104A | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | In progress |  | 40 | DECEMBER
T-718-4975 | PS5-65-UR-1122C | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone A | 1 | To be completed |  | 30 | SEPTEMBER
T-184-4976 | PS5-08-IK-3643D | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | In progress |  | 43 | NOVEMBER
T-257-4977 | PS5-10-OB-8498D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-02-05 | PS5-05-03 | PS5 - Milestone D | 3 | Closed | 11 | 37 | FEBRUARY
T-080-4978 | PS5-48-IK-6921B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone I | 8 | In progress |  | 43 | DECEMBER
T-399-4979 | PS5-98-OB-4598D | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone A | 1 | On hold |  | 35 | NOVEMBER
T-084-4980 | PS5-94-IK-1104B | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-07-10 | PS5-63-04 | PS5 - Milestone I | 8 | Closed | 30 | 20 | JULY
T-629-4981 | PS5-35-OB-9017B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | In progress |  | 26 | AUGUST
T-497-4982 | PS5-36-OB-4097A | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-11-27 | PS5-04-03 | PS5 - Milestone I | 8 | Closed | 16 | 26 | NOVEMBER
T-128-4983 | PS5-86-OB-4007B | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-08-22 | PS5-10-03 | PS5 - Milestone H | 7 | Closed | 48 | 18 | AUGUST
T-492-4984 | PS5-69-OB-1042A | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-11-10 | PS5-09-01 | PS5 - Milestone H | 7 | Closed | 9 | 27 | NOVEMBER
T-457-4985 | PS5-79-OB-8312D | CQE01 - HV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-12-26 | PS5-01-04 | PS5 - Milestone G | 6 | Closed | 15 | 41 | DECEMBER
T-648-4986 | PS5-65-IK-4041A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-03-10 | PS5-99-01 | PS5 - Milestone F | 5 | Closed | 8 | 12 | MARCH
T-748-4987 | PS5-60-UR-4973D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone D | 3 | On hold |  | 19 | OCTOBER
T-643-4988 | PS5-39-OB-9980D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone A | 1 | To be completed |  | 4 | AUGUST
T-186-4989 | PS5-96-OB-2546D | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone C | 2 | To be completed |  | 17 | SEPTEMBER
T-108-4990 | PS5-44-UR-5536A | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | On hold |  | 7 | DECEMBER
T-675-4991 | PS5-17-OB-7704D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-01-15 | PS5-62-02 | PS5 - Milestone E | 4 | Closed | 28 | 7 | JANUARY
T-253-4992 | PS5-50-OB-9849C | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | In progress |  | 34 | AUGUST
T-949-4993 | PS5-47-OB-2572C | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-09-16 | PS5-60-04 | PS5 - Milestone E | 4 | Closed | 39 | 17 | SEPTEMBER
T-641-4994 | PS5-16-OB-3854A | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone G | 6 | In progress |  | 45 | DECEMBER
T-055-4995 | PS5-30-UR-5701A | CQM04 - Vessel | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone H | 7 | To be completed |  | 47 | NOVEMBER
T-142-4996 | PS5-54-IK-2359D | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-05-16 | PS5-99-02 | PS5 - Milestone G | 6 | Closed | 8 | 15 | MAY
T-608-4997 | PS5-80-OB-3464B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-06-18 | PS5-62-01 | PS5 - Milestone H | 7 | Closed | 7 | 21 | JUNE
T-638-4998 | PS5-59-UR-7609A | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-01-15 | PS5-99-01 | PS5 - Milestone I | 8 | Closed | 21 | 44 | JANUARY
T-676-4999 | PS5-07-IK-6406A | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone D | 3 | To be completed |  | 9 | OCTOBER
T-026-5000 | PS5-50-OB-3219B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone D | 3 | In progress |  | 33 | SEPTEMBER
T-612-5001 | PS5-13-UR-2739D | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone A | 1 | On hold |  | 37 | OCTOBER
T-442-5002 | PS5-77-IK-8606B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone I | 8 | In progress |  | 24 | OCTOBER
T-211-5003 | PS5-62-OB-4506B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-02-18 | PS5-11-01 | PS5 - Milestone G | 6 | Closed | 36 | 33 | FEBRUARY
T-556-5004 | PS5-28-OB-3775D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-10-23 | PS5-12-01 | PS5 - Milestone C | 2 | Closed | 22 | 16 | OCTOBER
T-871-5005 | PS5-69-UR-4954C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone D | 3 | In progress |  | 14 | NOVEMBER
T-463-5006 | PS5-06-OB-4606D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-09-04 | PS5-02-03 | PS5 - Milestone E | 4 | Closed | 29 | 10 | SEPTEMBER
T-114-5007 | PS5-60-UR-9154A | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-03-15 | PS5-01-02 | PS5 - Milestone A | 1 | Closed | 48 | 47 | MARCH
T-639-5008 | PS5-81-OB-6393C | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-09-02 | PS5-07-03 | PS5 - Milestone I | 8 | Closed | 26 | 17 | SEPTEMBER
T-881-5009 | PS5-20-IK-8432A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | In progress |  | 7 | SEPTEMBER
T-751-5010 | PS5-53-UR-1776D | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone C | 2 | To be completed |  | 40 | OCTOBER
T-831-5011 | PS5-42-OB-4323C | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-10-10 | PS5-09-01 | PS5 - Milestone C | 2 | Closed | 22 | 6 | OCTOBER
T-309-5012 | PS5-56-UR-9351C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | To be completed |  | 37 | OCTOBER
T-124-5013 | PS5-13-UR-8216C | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone D | 3 | To be completed |  | 29 | OCTOBER
T-334-5014 | PS5-73-IK-6079A | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-01-14 | PS5-01-08 | PS5 - Milestone C | 2 | Closed | 24 | 12 | JANUARY
T-824-5015 | PS5-33-UR-2544A | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone B | 1.1 | To be completed |  | 30 | DECEMBER
T-825-5016 | PS5-67-IK-3423B | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone C | 2 | To be completed |  | 14 | SEPTEMBER
T-642-5017 | PS5-20-OB-8138A | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-02-28 | PS5-01-01 | PS5 - Milestone B | 1.1 | Closed | 32 | 34 | FEBRUARY
T-459-5018 | PS5-45-OB-8290A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone I | 8 | In progress |  | 17 | AUGUST
T-729-5019 | PS5-40-OB-8589C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone E | 4 | To be completed |  | 27 | DECEMBER
T-871-5020 | PS5-33-UR-1809D | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone B | 1.1 | In progress |  | 45 | SEPTEMBER
T-235-5021 | PS5-82-OB-2931B | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone A | 1 | To be completed |  | 14 | OCTOBER
T-402-5022 | PS5-18-IK-4848A | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-12-14 | PS5-02-02 | PS5 - Milestone I | 8 | Closed | 32 | 14 | DECEMBER
T-018-5023 | PS5-10-UR-4417C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone H | 7 | To be completed |  | 15 | DECEMBER
T-956-5024 | PS5-60-OB-1971D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-06-10 | PS5-61-01 | PS5 - Milestone H | 7 | Closed | 28 | 38 | JUNE
T-259-5025 | PS5-43-OB-3804D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone B | 1.1 | In progress |  | 38 | OCTOBER
T-610-5026 | PS5-68-OB-3185A | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-10-08 | PS5-13-01 | PS5 - Milestone G | 6 | Closed | 42 | 12 | OCTOBER
T-176-5027 | PS5-87-IK-8577A | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-02-19 | PS5-09-04 | PS5 - Milestone C | 2 | Closed | 5 | 22 | FEBRUARY
T-759-5028 | PS5-40-IK-3587B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | To be completed |  | 39 | SEPTEMBER
T-066-5029 | PS5-35-OB-8978C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone D | 3 | To be completed |  | 9 | SEPTEMBER
T-617-5030 | PS5-73-UR-7250D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-04-22 | PS5-12-02 | PS5 - Milestone C | 2 | Closed | 23 | 26 | APRIL
T-207-5031 | PS5-61-UR-4336C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone H | 7 | To be completed |  | 6 | AUGUST
T-412-5032 | PS5-64-UR-5231A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | In progress |  | 44 | SEPTEMBER
T-871-5033 | PS5-21-OB-9288C | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-02-25 | PS5-01-06 | PS5 - Milestone E | 4 | Closed | 9 | 46 | FEBRUARY
T-850-5034 | PS5-44-OB-1377B | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone C | 2 | On hold |  | 15 | DECEMBER
T-680-5035 | PS5-54-IK-5259A | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-04-07 | PS5-10-04 | PS5 - Milestone I | 8 | Closed | 36 | 10 | APRIL
T-504-5036 | PS5-97-UR-7827C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone G | 6 | In progress |  | 40 | AUGUST
T-632-5037 | PS5-52-OB-3161B | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-01-21 | PS5-07-03 | PS5 - Milestone H | 7 | Closed | 9 | 41 | JANUARY
T-276-5038 | PS5-45-IK-1328C | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone F | 5 | To be completed |  | 16 | NOVEMBER
T-897-5039 | PS5-95-OB-1562D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone D | 3 | On hold |  | 26 | OCTOBER
T-193-5040 | PS5-71-IK-9761B | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone C | 2 | To be completed |  | 23 | DECEMBER
T-392-5041 | PS5-60-IK-2765A | CQM03 - Heat Exchanger | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone D | 3 | To be completed |  | 47 | OCTOBER
T-750-5042 | PS5-94-IK-4945C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-11-07 | PS5-60-04 | PS5 - Milestone I | 8 | Closed | 12 | 43 | NOVEMBER
T-279-5043 | PS5-11-OB-1340B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | In progress |  | 20 | SEPTEMBER
T-070-5044 | PS5-03-UR-9950A | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-01-28 | PS5-04-03 | PS5 - Milestone D | 3 | Closed | 32 | 34 | JANUARY
T-027-5045 | PS5-97-OB-4817B | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-12-16 | PS5-10-06 | PS5 - Milestone G | 6 | Closed | 30 | 6 | DECEMBER
T-635-5046 | PS5-03-OB-2765B | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone A | 1 | To be completed |  | 8 | NOVEMBER
T-248-5047 | PS5-12-UR-9136A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | In progress |  | 11 | DECEMBER
T-170-5048 | PS5-38-OB-1549A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone F | 5 | On hold |  | 37 | SEPTEMBER
T-418-5049 | PS5-45-UR-4827B | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone D | 3 | In progress |  | 25 | AUGUST
T-217-5050 | PS5-06-IK-4593D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-04-17 | PS5-99-03 | PS5 - Milestone F | 5 | Closed | 18 | 39 | APRIL
T-689-5051 | PS5-80-OB-1871B | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone B | 1.1 | To be completed |  | 46 | SEPTEMBER
T-824-5052 | PS5-89-OB-8468D | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone B | 1.1 | To be completed |  | 30 | SEPTEMBER
T-897-5053 | PS5-94-OB-6328D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone F | 5 | To be completed |  | 11 | SEPTEMBER
T-574-5054 | PS5-88-OB-2611A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-03-20 | PS5-06-02 | PS5 - Milestone A | 1 | Closed | 42 | 13 | MARCH
T-253-5055 | PS5-45-UR-8605A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone B | 1.1 | To be completed |  | 17 | DECEMBER
T-516-5056 | PS5-01-IK-7753B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone A | 1 | In progress |  | 31 | OCTOBER
T-436-5057 | PS5-81-OB-6024A | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone B | 1.1 | To be completed |  | 47 | AUGUST
T-367-5058 | PS5-10-OB-4823C | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-03-22 | PS5-07-01 | PS5 - Milestone G | 6 | Closed | 40 | 5 | MARCH
T-663-5059 | PS5-66-UR-8620A | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone E | 4 | To be completed |  | 7 | NOVEMBER
T-015-5060 | PS5-04-OB-7284D | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone H | 7 | On hold |  | 31 | AUGUST
T-056-5061 | PS5-46-OB-3347C | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-02-23 | PS5-99-02 | PS5 - Milestone A | 1 | Closed | 21 | 6 | FEBRUARY
T-388-5062 | PS5-41-OB-7719A | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-10-09 | PS5-11-02 | PS5 - Milestone B | 1.1 | Closed | 41 | 26 | OCTOBER
T-678-5063 | PS5-48-IK-4823B | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone C | 2 | In progress |  | 22 | AUGUST
T-802-5064 | PS5-18-UR-4522B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone E | 4 | To be completed |  | 9 | SEPTEMBER
T-371-5065 | PS5-26-IK-5989C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone I | 8 | To be completed |  | 32 | SEPTEMBER
T-361-5066 | PS5-97-IK-6925D | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone A | 1 | To be completed |  | 7 | DECEMBER
T-655-5067 | PS5-35-IK-8598B | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone A | 1 | To be completed |  | 25 | NOVEMBER
T-632-5068 | PS5-59-UR-5303C | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone H | 7 | In progress |  | 48 | OCTOBER
T-098-5069 | PS5-68-OB-4863B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-03-18 | PS5-10-01 | PS5 - Milestone D | 3 | Closed | 32 | 32 | MARCH
T-913-5070 | PS5-39-OB-3831B | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-08-01 | PS5-11-03 | PS5 - Milestone E | 4 | Closed | 37 | 7 | AUGUST
T-255-5071 | PS5-01-OB-6532A | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-07-19 | PS5-11-01 | PS5 - Milestone H | 7 | Closed | 36 | 12 | JULY
T-944-5072 | PS5-20-UR-2673B | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-01-10 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 22 | 6 | JANUARY
T-234-5073 | PS5-22-OB-5593D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone F | 5 | To be completed |  | 44 | DECEMBER
T-418-5074 | PS5-25-UR-6258A | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-02-22 | PS5-11-02 | PS5 - Milestone B | 1.1 | Closed | 24 | 5 | FEBRUARY
T-633-5075 | PS5-69-UR-9702C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-07-21 | PS5-05-03 | PS5 - Milestone H | 7 | Closed | 14 | 25 | JULY
T-831-5076 | PS5-41-OB-9152B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | To be completed |  | 13 | SEPTEMBER
T-766-5077 | PS5-93-OB-9860A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone B | 1.1 | In progress |  | 14 | SEPTEMBER
T-230-5078 | PS5-99-OB-5981B | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone E | 4 | To be completed |  | 19 | SEPTEMBER
T-235-5079 | PS5-56-IK-2338C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-06-19 | PS5-11-01 | PS5 - Milestone H | 7 | Closed | 33 | 4 | JUNE
T-099-5080 | PS5-49-OB-9540C | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone F | 5 | To be completed |  | 30 | AUGUST
T-097-5081 | PS5-47-OB-9479D | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-08-05 | PS5-82-01 | PS5 - Milestone C | 2 | Closed | 16 | 12 | AUGUST
T-801-5082 | PS5-47-UR-3055C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-05-11 | PS5-04-01 | PS5 - Milestone I | 8 | Closed | 33 | 48 | MAY
T-156-5083 | PS5-08-IK-2210D | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone H | 7 | To be completed |  | 36 | AUGUST
T-423-5084 | PS5-70-UR-7030B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone I | 8 | To be completed |  | 17 | SEPTEMBER
T-910-5085 | PS5-12-OB-5164A | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-11-14 | PS5-11-02 | PS5 - Milestone I | 8 | Closed | 43 | 43 | NOVEMBER
T-987-5086 | PS5-67-OB-9923B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-05-19 | PS5-07-04 | PS5 - Milestone H | 7 | Closed | 21 | 17 | MAY
T-499-5087 | PS5-48-IK-1479B | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone B | 1.1 | On hold |  | 9 | DECEMBER
T-582-5088 | PS5-22-IK-6780D | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-03-15 | PS5-09-03 | PS5 - Milestone F | 5 | Closed | 25 | 18 | MARCH
T-379-5089 | PS5-99-IK-6744B | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone C | 2 | To be completed |  | 19 | OCTOBER
T-305-5090 | PS5-94-IK-3320D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-06-07 | PS5-10-06 | PS5 - Milestone F | 5 | Closed | 30 | 14 | JUNE
T-602-5091 | PS5-72-OB-7162B | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | In progress |  | 43 | AUGUST
T-364-5092 | PS5-65-IK-3164C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-03-17 | PS5-61-02 | PS5 - Milestone G | 6 | Closed | 16 | 20 | MARCH
T-029-5093 | PS5-09-IK-9173A | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone E | 4 | To be completed |  | 12 | NOVEMBER
T-786-5094 | PS5-96-IK-8795C | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone D | 3 | In progress |  | 21 | DECEMBER
T-641-5095 | PS5-72-IK-8558C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | In progress |  | 14 | DECEMBER
T-228-5096 | PS5-88-OB-7479B | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone G | 6 | To be completed |  | 14 | AUGUST
T-779-5097 | PS5-38-OB-2598B | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-06-04 | PS5-82-07 | PS5 - Milestone H | 7 | Closed | 45 | 4 | JUNE
T-944-5098 | PS5-54-OB-7520B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone B | 1.1 | To be completed |  | 26 | DECEMBER
T-229-5099 | PS5-30-OB-9721D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone I | 8 | To be completed |  | 25 | DECEMBER
T-310-5100 | PS5-58-OB-7973B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone C | 2 | In progress |  | 11 | OCTOBER
T-004-5101 | PS5-63-OB-5236A | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-01-04 | PS5-11-02 | PS5 - Milestone G | 6 | Closed | 31 | 32 | JANUARY
T-311-5102 | PS5-94-OB-3061C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | On hold |  | 4 | SEPTEMBER
T-363-5103 | PS5-13-UR-3278C | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-02-25 | PS5-03-02 | PS5 - Milestone E | 4 | Closed | 31 | 8 | FEBRUARY
T-110-5104 | PS5-60-OB-5833D | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone G | 6 | In progress |  | 16 | SEPTEMBER
T-638-5105 | PS5-86-UR-2650C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | To be completed |  | 23 | DECEMBER
T-377-5106 | PS5-90-UR-1741B | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone F | 5 | To be completed |  | 5 | DECEMBER
T-334-5107 | PS5-20-OB-8352B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-07-20 | PS5-09-03 | PS5 - Milestone B | 1.1 | Closed | 28 | 7 | JULY
T-494-5108 | PS5-53-OB-2923D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone B | 1.1 | In progress |  | 21 | AUGUST
T-420-5109 | PS5-69-UR-6453C | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone C | 2 | In progress |  | 11 | NOVEMBER
T-028-5110 | PS5-17-OB-8833B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone G | 6 | In progress |  | 28 | OCTOBER
T-961-5111 | PS5-83-UR-5538B | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone H | 7 | In progress |  | 8 | AUGUST
T-196-5112 | PS5-25-IK-3443C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-06-11 | PS5-11-02 | PS5 - Milestone E | 4 | Closed | 23 | 31 | JUNE
T-302-5113 | PS5-51-UR-9739C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone E | 4 | On hold |  | 12 | OCTOBER
T-077-5114 | PS5-32-OB-5869D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone G | 6 | On hold |  | 39 | DECEMBER
T-597-5115 | PS5-56-OB-5529A | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-02-19 | PS5-01-07 | PS5 - Milestone B | 1.1 | Closed | 19 | 28 | FEBRUARY
T-461-5116 | PS5-38-OB-8489A | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone F | 5 | In progress |  | 23 | DECEMBER
T-223-5117 | PS5-13-OB-2103D | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone B | 1.1 | On hold |  | 37 | AUGUST
T-195-5118 | PS5-28-IK-4242B | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-02-07 | PS5-05-02 | PS5 - Milestone E | 4 | Closed | 46 | 34 | FEBRUARY
T-139-5119 | PS5-07-OB-6853A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-09-09 | PS5-03-03 | PS5 - Milestone B | 1.1 | Closed | 12 | 5 | SEPTEMBER
T-304-5120 | PS5-66-IK-5347C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone H | 7 | To be completed |  | 5 | SEPTEMBER
T-070-5121 | PS5-39-IK-6912B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone H | 7 | In progress |  | 41 | AUGUST
T-702-5122 | PS5-73-IK-1660A | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-10-26 | PS5-11-01 | PS5 - Milestone B | 1.1 | Closed | 21 | 26 | OCTOBER
T-206-5123 | PS5-22-OB-9976C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone D | 3 | To be completed |  | 9 | AUGUST
T-877-5124 | PS5-02-OB-5412B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-05-12 | PS5-99-03 | PS5 - Milestone B | 1.1 | Closed | 22 | 23 | MAY
T-062-5125 | PS5-50-OB-8166B | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone B | 1.1 | In progress |  | 14 | AUGUST
T-682-5126 | PS5-21-OB-6496A | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-10-25 | PS5-60-07 | PS5 - Milestone G | 6 | Closed | 19 | 24 | OCTOBER
T-740-5127 | PS5-02-OB-2515B | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-11-20 | PS5-01-01 | PS5 - Milestone G | 6 | Closed | 4 | 28 | NOVEMBER
T-688-5128 | PS5-71-UR-1380B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-06-23 | PS5-01-01 | PS5 - Milestone H | 7 | Closed | 42 | 30 | JUNE
T-606-5129 | PS5-07-UR-5719B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-03-11 | PS5-02-02 | PS5 - Milestone F | 5 | Closed | 28 | 47 | MARCH
T-090-5130 | PS5-93-OB-6542A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone E | 4 | To be completed |  | 45 | NOVEMBER
T-635-5131 | PS5-33-UR-5024A | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone A | 1 | To be completed |  | 25 | AUGUST
T-804-5132 | PS5-40-IK-6091B | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-10-24 | PS5-63-04 | PS5 - Milestone A | 1 | Closed | 46 | 29 | OCTOBER
T-914-5133 | PS5-84-UR-6734A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-01-07 | PS5-10-01 | PS5 - Milestone I | 8 | Closed | 35 | 24 | JANUARY
T-927-5134 | PS5-68-UR-5608D | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-10-09 | PS5-09-02 | PS5 - Milestone D | 3 | Closed | 38 | 18 | OCTOBER
T-617-5135 | PS5-21-IK-9805C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone C | 2 | In progress |  | 47 | SEPTEMBER
T-806-5136 | PS5-10-UR-2960B | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-09-23 | PS5-03-23 | PS5 - Milestone E | 4 | Closed | 48 | 40 | SEPTEMBER
T-984-5137 | PS5-39-OB-2617B | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-01-01 | PS5-10-04 | PS5 - Milestone I | 8 | Closed | 28 | 43 | JANUARY
T-253-5138 | PS5-24-IK-7889C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-07-21 | PS5-60-10 | PS5 - Milestone G | 6 | Closed | 22 | 34 | JULY
T-991-5139 | PS5-89-OB-8021A | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone I | 8 | In progress |  | 38 | AUGUST
T-532-5140 | PS5-46-IK-5961D | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone H | 7 | In progress |  | 42 | DECEMBER
T-851-5141 | PS5-50-UR-8299D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone G | 6 | To be completed |  | 24 | AUGUST
T-871-5142 | PS5-82-OB-5000D | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone D | 3 | To be completed |  | 38 | SEPTEMBER
T-463-5143 | PS5-35-IK-5810B | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone G | 6 | To be completed |  | 14 | SEPTEMBER
T-480-5144 | PS5-16-OB-9611D | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-12-03 | PS5-01-05 | PS5 - Milestone E | 4 | Closed | 28 | 18 | DECEMBER
T-550-5145 | PS5-19-UR-2740D | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-07-02 | PS5-09-01 | PS5 - Milestone C | 2 | Closed | 44 | 9 | JULY
T-992-5146 | PS5-73-UR-6626C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | To be completed |  | 29 | NOVEMBER
T-778-5147 | PS5-57-OB-5756C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-10-23 | PS5-62-02 | PS5 - Milestone D | 3 | Closed | 29 | 46 | OCTOBER
T-789-5148 | PS5-57-OB-8072D | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-07-15 | PS5-82-07 | PS5 - Milestone G | 6 | Closed | 23 | 48 | JULY
T-556-5149 | PS5-73-UR-1390C | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone H | 7 | On hold |  | 22 | SEPTEMBER
T-456-5150 | PS5-41-IK-2623D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone I | 8 | To be completed |  | 38 | AUGUST
T-532-5151 | PS5-50-IK-2718B | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone A | 1 | In progress |  | 11 | NOVEMBER
T-951-5152 | PS5-31-OB-1988C | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-03-01 | PS5-11-01 | PS5 - Milestone B | 1.1 | Closed | 19 | 10 | MARCH
T-123-5153 | PS5-17-OB-3229C | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-10-21 | PS5-01-02 | PS5 - Milestone E | 4 | Closed | 5 | 11 | OCTOBER
T-773-5154 | PS5-19-OB-7522B | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-10-15 | PS5-01-01 | PS5 - Milestone F | 5 | Closed | 26 | 9 | OCTOBER
T-647-5155 | PS5-99-IK-1862B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone G | 6 | To be completed |  | 22 | OCTOBER
T-257-5156 | PS5-48-IK-4258C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone C | 2 | On hold |  | 41 | OCTOBER
T-814-5157 | PS5-35-OB-1627D | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone C | 2 | To be completed |  | 24 | AUGUST
T-933-5158 | PS5-25-OB-8224A | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-11-19 | PS5-09-01 | PS5 - Milestone G | 6 | Closed | 38 | 37 | NOVEMBER
T-102-5159 | PS5-45-OB-8262A | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-02-13 | PS5-01-04 | PS5 - Milestone H | 7 | Closed | 43 | 35 | FEBRUARY
T-096-5160 | PS5-12-OB-4763D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-09-09 | PS5-10-02 | PS5 - Milestone A | 1 | Closed | 10 | 39 | SEPTEMBER
T-704-5161 | PS5-68-OB-3704D | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-01-22 | PS5-12-01 | PS5 - Milestone B | 1.1 | Closed | 28 | 46 | JANUARY
T-153-5162 | PS5-36-OB-2311B | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone F | 5 | In progress |  | 37 | OCTOBER
T-476-5163 | PS5-20-UR-8843B | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | To be completed |  | 37 | NOVEMBER
T-009-5164 | PS5-93-OB-4204C | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | To be completed |  | 22 | AUGUST
T-734-5165 | PS5-71-OB-2076D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-04-02 | PS5-12-02 | PS5 - Milestone B | 1.1 | Closed | 27 | 46 | APRIL
T-937-5166 | PS5-71-UR-1734C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone F | 5 | To be completed |  | 7 | AUGUST
T-199-5167 | PS5-52-OB-2831A | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone D | 3 | In progress |  | 26 | OCTOBER
T-138-5168 | PS5-58-IK-6982C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | On hold |  | 32 | SEPTEMBER
T-741-5169 | PS5-93-IK-4211A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-07-04 | PS5-62-02 | PS5 - Milestone H | 7 | Closed | 26 | 40 | JULY
T-041-5170 | PS5-12-OB-5324B | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone H | 7 | In progress |  | 27 | DECEMBER
T-296-5171 | PS5-67-IK-7219B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-04-17 | PS5-99-02 | PS5 - Milestone B | 1.1 | Closed | 44 | 48 | APRIL
T-772-5172 | PS5-68-IK-7060B | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone A | 1 | In progress |  | 27 | DECEMBER
T-412-5173 | PS5-89-UR-1454D | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone G | 6 | In progress |  | 14 | NOVEMBER
T-367-5174 | PS5-03-OB-4632B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-03-06 | PS5-10-05 | PS5 - Milestone H | 7 | Closed | 30 | 48 | MARCH
T-251-5175 | PS5-98-OB-8269C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone C | 2 | In progress |  | 19 | AUGUST
T-879-5176 | PS5-48-IK-1898A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone B | 1.1 | In progress |  | 41 | DECEMBER
T-991-5177 | PS5-44-OB-1354A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-03-02 | PS5-08-01 | PS5 - Milestone I | 8 | Closed | 20 | 38 | MARCH
T-132-5178 | PS5-69-OB-7673C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-02-13 | PS5-13-01 | PS5 - Milestone C | 2 | Closed | 18 | 9 | FEBRUARY
T-825-5179 | PS5-09-UR-1508D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-03-23 | PS5-01-04 | PS5 - Milestone I | 8 | Closed | 34 | 15 | MARCH
T-439-5180 | PS5-21-IK-6752A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone D | 3 | To be completed |  | 10 | AUGUST
T-686-5181 | PS5-76-OB-5359A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-06-24 | PS5-04-01 | PS5 - Milestone H | 7 | Closed | 40 | 37 | JUNE
T-254-5182 | PS5-08-UR-4532B | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | In progress |  | 31 | SEPTEMBER
T-141-5183 | PS5-14-IK-4795D | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | In progress |  | 24 | OCTOBER
T-177-5184 | PS5-84-IK-5335C | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | To be completed |  | 8 | AUGUST
T-387-5185 | PS5-42-IK-4450B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-06-06 | PS5-61-01 | PS5 - Milestone H | 7 | Closed | 32 | 23 | JUNE
T-432-5186 | PS5-09-OB-3168A | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone D | 3 | To be completed |  | 33 | SEPTEMBER
T-215-5187 | PS5-42-UR-4773C | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-08-19 | PS5-01-04 | PS5 - Milestone B | 1.1 | Closed | 38 | 29 | AUGUST
T-005-5188 | PS5-54-UR-8024A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | On hold |  | 37 | OCTOBER
T-965-5189 | PS5-52-OB-8734D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-03-14 | PS5-05-02 | PS5 - Milestone A | 1 | Closed | 31 | 20 | MARCH
T-579-5190 | PS5-75-IK-3509C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-12-08 | PS5-06-03 | PS5 - Milestone D | 3 | Closed | 14 | 48 | DECEMBER
T-070-5191 | PS5-38-OB-5165B | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone G | 6 | In progress |  | 37 | NOVEMBER
T-849-5192 | PS5-89-IK-4638A | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone E | 4 | In progress |  | 23 | AUGUST
T-820-5193 | PS5-61-OB-8959A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | On hold |  | 32 | NOVEMBER
T-441-5194 | PS5-92-OB-3556C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-01-08 | PS5-01-05 | PS5 - Milestone G | 6 | Closed | 44 | 35 | JANUARY
T-571-5195 | PS5-50-OB-4337D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-11-04 | PS5-11-03 | PS5 - Milestone H | 7 | Closed | 17 | 19 | NOVEMBER
T-875-5196 | PS5-21-IK-8997C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | In progress |  | 22 | SEPTEMBER
T-496-5197 | PS5-08-OB-9039D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | On hold |  | 37 | AUGUST
T-053-5198 | PS5-72-OB-8869B | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone A | 1 | To be completed |  | 11 | AUGUST
T-270-5199 | PS5-11-UR-4308C | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-02-09 | PS5-82-01 | PS5 - Milestone E | 4 | Closed | 15 | 32 | FEBRUARY
T-437-5200 | PS5-14-OB-4563B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-11-09 | PS5-01-07 | PS5 - Milestone F | 5 | Closed | 24 | 11 | NOVEMBER
T-720-5201 | PS5-65-UR-8544D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone G | 6 | To be completed |  | 36 | OCTOBER
T-080-5202 | PS5-76-IK-5579A | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | To be completed |  | 21 | NOVEMBER
T-597-5203 | PS5-81-UR-9585C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone F | 5 | To be completed |  | 30 | AUGUST
T-990-5204 | PS5-20-OB-8951D | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone G | 6 | To be completed |  | 31 | SEPTEMBER
T-295-5205 | PS5-45-UR-4410D | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone A | 1 | To be completed |  | 19 | DECEMBER
T-056-5206 | PS5-19-OB-8684C | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone F | 5 | To be completed |  | 5 | DECEMBER
T-064-5207 | PS5-88-OB-7500B | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | To be completed |  | 19 | OCTOBER
T-258-5208 | PS5-87-OB-1224C | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-11-21 | PS5-08-01 | PS5 - Milestone C | 2 | Closed | 19 | 8 | NOVEMBER
T-959-5209 | PS5-20-OB-2075B | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-07-18 | PS5-01-06 | PS5 - Milestone H | 7 | Closed | 22 | 20 | JULY
T-881-5210 | PS5-33-OB-7601D | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-02-16 | PS5-10-06 | PS5 - Milestone F | 5 | Closed | 36 | 28 | FEBRUARY
T-101-5211 | PS5-32-OB-8109B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-12-07 | PS5-01-05 | PS5 - Milestone A | 1 | Closed | 39 | 47 | DECEMBER
T-435-5212 | PS5-94-OB-2365D | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | To be completed |  | 34 | OCTOBER
T-916-5213 | PS5-25-UR-3897B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-08-26 | PS5-01-07 | PS5 - Milestone I | 8 | Closed | 24 | 17 | AUGUST
T-556-5214 | PS5-44-UR-6794D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone D | 3 | To be completed |  | 8 | DECEMBER
T-408-5215 | PS5-65-IK-2818C | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone H | 7 | To be completed |  | 22 | SEPTEMBER
T-513-5216 | PS5-49-UR-9616B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone B | 1.1 | To be completed |  | 24 | AUGUST
T-129-5217 | PS5-59-OB-4325C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone D | 3 | To be completed |  | 46 | OCTOBER
T-270-5218 | PS5-95-OB-5650A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | To be completed |  | 27 | NOVEMBER
T-262-5219 | PS5-29-IK-1518B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-01-03 | PS5-03-01 | PS5 - Milestone C | 2 | Closed | 43 | 47 | JANUARY
T-299-5220 | PS5-96-UR-1666C | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-11-03 | PS5-10-05 | PS5 - Milestone E | 4 | Closed | 9 | 39 | NOVEMBER
T-403-5221 | PS5-29-UR-9814B | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | On hold |  | 20 | SEPTEMBER
T-534-5222 | PS5-39-UR-4027D | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-04-25 | PS5-82-02 | PS5 - Milestone F | 5 | Closed | 17 | 21 | APRIL
T-169-5223 | PS5-80-OB-7510A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone I | 8 | To be completed |  | 27 | DECEMBER
T-423-5224 | PS5-41-UR-6792D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone I | 8 | In progress |  | 31 | NOVEMBER
T-249-5225 | PS5-49-IK-2674C | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-01-20 | PS5-01-06 | PS5 - Milestone D | 3 | Closed | 16 | 38 | JANUARY
T-706-5226 | PS5-29-OB-9150B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-06-26 | PS5-61-07 | PS5 - Milestone D | 3 | Closed | 25 | 38 | JUNE
T-194-5227 | PS5-83-OB-3279C | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone D | 3 | In progress |  | 21 | SEPTEMBER
T-180-5228 | PS5-26-UR-3830A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone D | 3 | In progress |  | 34 | AUGUST
T-622-5229 | PS5-81-OB-9690C | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone A | 1 | To be completed |  | 26 | SEPTEMBER
T-964-5230 | PS5-58-OB-1324C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone C | 2 | To be completed |  | 36 | SEPTEMBER
T-931-5231 | PS5-56-IK-8881B | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone E | 4 | On hold |  | 5 | AUGUST
T-576-5232 | PS5-16-OB-9936D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-05-08 | PS5-63-01 | PS5 - Milestone D | 3 | Closed | 37 | 26 | MAY
T-765-5233 | PS5-76-UR-7234C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone D | 3 | To be completed |  | 17 | DECEMBER
T-822-5234 | PS5-90-UR-4578D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-08-14 | PS5-61-07 | PS5 - Milestone C | 2 | Closed | 7 | 14 | AUGUST
T-272-5235 | PS5-79-OB-2664B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone E | 4 | On hold |  | 35 | OCTOBER
T-581-5236 | PS5-17-UR-8424D | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone A | 1 | To be completed |  | 13 | OCTOBER
T-868-5237 | PS5-09-OB-6699C | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | On hold |  | 44 | AUGUST
T-892-5238 | PS5-50-IK-1749B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-02-22 | PS5-01-03 | PS5 - Milestone A | 1 | Closed | 33 | 21 | FEBRUARY
T-214-5239 | PS5-90-OB-3023A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-02-25 | PS5-05-01 | PS5 - Milestone E | 4 | Closed | 21 | 45 | FEBRUARY
T-425-5240 | PS5-26-OB-9086A | CQE02 - LV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-12-07 | PS5-04-03 | PS5 - Milestone I | 8 | Closed | 16 | 25 | DECEMBER
T-020-5241 | PS5-51-IK-6055B | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone E | 4 | In progress |  | 25 | OCTOBER
T-008-5242 | PS5-51-OB-1864C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-10-21 | PS5-01-09 | PS5 - Milestone B | 1.1 | Closed | 12 | 27 | OCTOBER
T-011-5243 | PS5-41-OB-5696C | CQP04 - Hydrotest | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-05 | PS5-60-04 | PS5 - Milestone G | 6 | Closed | 48 | 28 | APRIL
T-324-5244 | PS5-17-OB-8545B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-11-08 | PS5-04-04 | PS5 - Milestone E | 4 | Closed | 24 | 10 | NOVEMBER
T-710-5245 | PS5-80-IK-5242A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone C | 2 | In progress |  | 34 | DECEMBER
T-023-5246 | PS5-56-UR-7456D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-11-07 | PS5-61-02 | PS5 - Milestone I | 8 | Closed | 26 | 42 | NOVEMBER
T-398-5247 | PS5-81-OB-2104C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone C | 2 | In progress |  | 48 | OCTOBER
T-011-5248 | PS5-84-OB-7549A | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone G | 6 | To be completed |  | 27 | DECEMBER
T-443-5249 | PS5-12-OB-3422B | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-05-24 | PS5-12-02 | PS5 - Milestone A | 1 | Closed | 46 | 37 | MAY
T-400-5250 | PS5-90-OB-7139D | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-02-18 | PS5-82-01 | PS5 - Milestone F | 5 | Closed | 11 | 48 | FEBRUARY
T-135-5251 | PS5-26-OB-3245D | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-06-08 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 11 | 33 | JUNE
T-998-5252 | PS5-08-IK-3054A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-07-26 | PS5-03-03 | PS5 - Milestone D | 3 | Closed | 9 | 45 | JULY
T-333-5253 | PS5-48-IK-9057A | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-09-16 | PS5-99-03 | PS5 - Milestone E | 4 | Closed | 11 | 18 | SEPTEMBER
T-013-5254 | PS5-27-UR-8034A | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | In progress |  | 42 | AUGUST
T-615-5255 | PS5-89-UR-9621A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-19 | PS5-60-07 | PS5 - Milestone H | 7 | Closed | 14 | 13 | JULY
T-954-5256 | PS5-32-OB-1835B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-05-02 | PS5-05-01 | PS5 - Milestone E | 4 | Closed | 36 | 25 | MAY
T-273-5257 | PS5-09-OB-4178D | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-09-15 | PS5-61-01 | PS5 - Milestone H | 7 | Closed | 43 | 32 | SEPTEMBER
T-467-5258 | PS5-29-OB-9978A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-06-15 | PS5-62-01 | PS5 - Milestone B | 1.1 | Closed | 22 | 6 | JUNE
T-782-5259 | PS5-57-OB-7122A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone G | 6 | To be completed |  | 24 | SEPTEMBER
T-650-5260 | PS5-74-UR-2928A | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-04-26 | PS5-99-03 | PS5 - Milestone G | 6 | Closed | 40 | 33 | APRIL
T-704-5261 | PS5-80-UR-7535D | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-09-21 | PS5-82-01 | PS5 - Milestone B | 1.1 | Closed | 39 | 4 | SEPTEMBER
T-993-5262 | PS5-19-IK-4954D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone F | 5 | To be completed |  | 28 | DECEMBER
T-974-5263 | PS5-26-UR-4221A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-11-23 | PS5-99-03 | PS5 - Milestone H | 7 | Closed | 34 | 38 | NOVEMBER
T-278-5264 | PS5-41-IK-2554B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-03-26 | PS5-82-01 | PS5 - Milestone G | 6 | Closed | 27 | 11 | MARCH
T-670-5265 | PS5-11-OB-6965C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-10-01 | PS5-10-02 | PS5 - Milestone G | 6 | Closed | 15 | 28 | OCTOBER
T-531-5266 | PS5-99-IK-8607C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone F | 5 | In progress |  | 44 | AUGUST
T-983-5267 | PS5-81-OB-6375A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone B | 1.1 | To be completed |  | 16 | SEPTEMBER
T-279-5268 | PS5-66-IK-1588B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-09-12 | PS5-01-05 | PS5 - Milestone E | 4 | Closed | 44 | 42 | SEPTEMBER
T-550-5269 | PS5-84-OB-1019A | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-08-06 | PS5-06-03 | PS5 - Milestone E | 4 | Closed | 10 | 22 | AUGUST
T-691-5270 | PS5-69-OB-3325D | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone H | 7 | In progress |  | 9 | DECEMBER
T-812-5271 | PS5-51-OB-1882A | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-06-05 | PS5-08-02 | PS5 - Milestone H | 7 | Closed | 12 | 42 | JUNE
T-758-5272 | PS5-25-IK-6955A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | To be completed |  | 30 | AUGUST
T-395-5273 | PS5-65-OB-4335A | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone F | 5 | To be completed |  | 14 | NOVEMBER
T-912-5274 | PS5-75-OB-9487D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-06-12 | PS5-04-03 | PS5 - Milestone C | 2 | Closed | 24 | 26 | JUNE
T-086-5275 | PS5-27-UR-4173C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-10-13 | PS5-60-07 | PS5 - Milestone D | 3 | Closed | 37 | 5 | OCTOBER
T-021-5276 | PS5-46-UR-6298A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-10-26 | PS5-05-01 | PS5 - Milestone A | 1 | Closed | 20 | 14 | OCTOBER
T-965-5277 | PS5-65-UR-5398D | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone B | 1.1 | To be completed |  | 21 | NOVEMBER
T-286-5278 | PS5-08-UR-4057B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone F | 5 | In progress |  | 30 | SEPTEMBER
T-558-5279 | PS5-49-IK-6636B | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone G | 6 | To be completed |  | 19 | NOVEMBER
T-244-5280 | PS5-10-UR-4764B | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone A | 1 | To be completed |  | 12 | NOVEMBER
T-559-5281 | PS5-10-IK-6237D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone F | 5 | To be completed |  | 40 | AUGUST
T-179-5282 | PS5-61-IK-2117A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | To be completed |  | 24 | DECEMBER
T-373-5283 | PS5-02-OB-7486C | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-03-25 | PS5-10-02 | PS5 - Milestone A | 1 | Closed | 15 | 38 | MARCH
T-441-5284 | PS5-73-UR-4867D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | To be completed |  | 6 | AUGUST
T-957-5285 | PS5-01-UR-7520C | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-05-13 | PS5-07-03 | PS5 - Milestone B | 1.1 | Closed | 14 | 48 | MAY
T-036-5286 | PS5-37-UR-2226C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-12-26 | PS5-06-03 | PS5 - Milestone H | 7 | Closed | 12 | 14 | DECEMBER
T-336-5287 | PS5-95-UR-8712B | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | In progress |  | 38 | NOVEMBER
T-731-5288 | PS5-91-OB-1087D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone G | 6 | To be completed |  | 9 | OCTOBER
T-044-5289 | PS5-62-IK-2044C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone I | 8 | In progress |  | 7 | NOVEMBER
T-150-5290 | PS5-26-OB-3766A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone G | 6 | In progress |  | 41 | SEPTEMBER
T-614-5291 | PS5-19-OB-3297A | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-08-24 | PS5-61-01 | PS5 - Milestone H | 7 | Closed | 8 | 20 | AUGUST
T-868-5292 | PS5-32-IK-9222A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone E | 4 | In progress |  | 28 | OCTOBER
T-708-5293 | PS5-86-OB-4057A | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-11-22 | PS5-02-01 | PS5 - Milestone C | 2 | Closed | 16 | 17 | NOVEMBER
T-235-5294 | PS5-15-IK-1713C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone A | 1 | To be completed |  | 7 | OCTOBER
T-501-5295 | PS5-81-IK-4582C | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-12-11 | PS5-99-03 | PS5 - Milestone B | 1.1 | Closed | 10 | 31 | DECEMBER
T-107-5296 | PS5-05-IK-7138C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone B | 1.1 | On hold |  | 36 | SEPTEMBER
T-378-5297 | PS5-91-OB-6859A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-09-26 | PS5-08-01 | PS5 - Milestone D | 3 | Closed | 47 | 48 | SEPTEMBER
T-483-5298 | PS5-71-OB-1401A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone I | 8 | To be completed |  | 35 | OCTOBER
T-386-5299 | PS5-44-IK-1546C | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-05-22 | PS5-06-03 | PS5 - Milestone A | 1 | Closed | 28 | 30 | MAY
T-276-5300 | PS5-28-IK-5993C | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone I | 8 | On hold |  | 39 | SEPTEMBER
T-168-5301 | PS5-44-IK-4470B | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone E | 4 | To be completed |  | 48 | NOVEMBER
T-746-5302 | PS5-82-OB-1804B | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-20 | PS5-60-04 | PS5 - Milestone I | 8 | Closed | 12 | 32 | JUNE
T-641-5303 | PS5-14-UR-2267B | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-01-16 | PS5-06-01 | PS5 - Milestone E | 4 | Closed | 9 | 25 | JANUARY
T-571-5304 | PS5-36-UR-6727A | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone C | 2 | To be completed |  | 42 | SEPTEMBER
T-472-5305 | PS5-76-UR-3926C | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-01-18 | PS5-05-03 | PS5 - Milestone G | 6 | Closed | 16 | 28 | JANUARY
T-699-5306 | PS5-93-OB-3520A | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone G | 6 | To be completed |  | 36 | NOVEMBER
T-263-5307 | PS5-46-OB-8192A | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone I | 8 | In progress |  | 43 | NOVEMBER
T-128-5308 | PS5-81-OB-6580A | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-03-10 | PS5-10-03 | PS5 - Milestone H | 7 | Closed | 4 | 15 | MARCH
T-808-5309 | PS5-26-OB-3435B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | In progress |  | 41 | NOVEMBER
T-774-5310 | PS5-20-UR-5722A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone D | 3 | To be completed |  | 27 | DECEMBER
T-722-5311 | PS5-79-OB-7120D | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone B | 1.1 | To be completed |  | 48 | OCTOBER
T-651-5312 | PS5-33-IK-9360D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone B | 1.1 | To be completed |  | 44 | OCTOBER
T-027-5313 | PS5-05-IK-2226C | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | To be completed |  | 9 | AUGUST
T-471-5314 | PS5-04-IK-2891C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-01-09 | PS5-10-03 | PS5 - Milestone I | 8 | Closed | 29 | 7 | JANUARY
T-947-5315 | PS5-86-UR-5857B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone A | 1 | To be completed |  | 15 | AUGUST
T-429-5316 | PS5-45-OB-8194B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | To be completed |  | 30 | NOVEMBER
T-541-5317 | PS5-07-IK-7918B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone F | 5 | In progress |  | 22 | AUGUST
T-742-5318 | PS5-24-UR-1072B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone B | 1.1 | In progress |  | 44 | AUGUST
T-503-5319 | PS5-82-UR-2512A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-11-04 | PS5-09-04 | PS5 - Milestone H | 7 | Closed | 6 | 39 | NOVEMBER
T-644-5320 | PS5-63-IK-5214A | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-02-15 | PS5-10-04 | PS5 - Milestone I | 8 | Closed | 26 | 12 | FEBRUARY
T-390-5321 | PS5-74-UR-2313C | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone C | 2 | In progress |  | 9 | DECEMBER
T-812-5322 | PS5-84-OB-3622D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone G | 6 | To be completed |  | 46 | OCTOBER
T-639-5323 | PS5-19-UR-1821B | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-03-09 | PS5-10-01 | PS5 - Milestone E | 4 | Closed | 15 | 42 | MARCH
T-618-5324 | PS5-23-UR-2795C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | In progress |  | 45 | OCTOBER
T-995-5325 | PS5-93-OB-7572C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone A | 1 | To be completed |  | 12 | DECEMBER
T-944-5326 | PS5-56-UR-7520C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone H | 7 | To be completed |  | 45 | AUGUST
T-483-5327 | PS5-13-OB-2146D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone A | 1 | To be completed |  | 4 | DECEMBER
T-796-5328 | PS5-83-OB-1971A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone I | 8 | In progress |  | 13 | NOVEMBER
T-511-5329 | PS5-66-OB-3167C | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone E | 4 | To be completed |  | 20 | AUGUST
T-805-5330 | PS5-52-UR-7749D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone E | 4 | To be completed |  | 17 | DECEMBER
T-410-5331 | PS5-47-UR-5517B | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone E | 4 | To be completed |  | 6 | DECEMBER
T-720-5332 | PS5-44-OB-4738C | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone C | 2 | To be completed |  | 22 | OCTOBER
T-392-5333 | PS5-20-OB-6370B | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone H | 7 | In progress |  | 27 | SEPTEMBER
T-495-5334 | PS5-21-OB-4807B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-09-17 | PS5-09-01 | PS5 - Milestone H | 7 | Closed | 40 | 21 | SEPTEMBER
T-556-5335 | PS5-45-UR-4404D | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone E | 4 | In progress |  | 32 | SEPTEMBER
T-601-5336 | PS5-47-UR-2192A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-02-01 | PS5-10-03 | PS5 - Milestone A | 1 | Closed | 38 | 42 | FEBRUARY
T-253-5337 | PS5-56-UR-7556C | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone I | 8 | On hold |  | 47 | NOVEMBER
T-226-5338 | PS5-21-UR-1280B | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-09 | PS5-60-04 | PS5 - Milestone G | 6 | Closed | 38 | 20 | JULY
T-584-5339 | PS5-32-IK-4432D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-10-01 | PS5-01-03 | PS5 - Milestone H | 7 | Closed | 44 | 32 | OCTOBER
T-880-5340 | PS5-62-OB-5741B | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone G | 6 | To be completed |  | 5 | SEPTEMBER
T-262-5341 | PS5-90-UR-3560C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-02-10 | PS5-08-02 | PS5 - Milestone G | 6 | Closed | 14 | 8 | FEBRUARY
T-720-5342 | PS5-94-IK-4187D | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone I | 8 | To be completed |  | 37 | AUGUST
T-872-5343 | PS5-19-UR-2322A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | To be completed |  | 38 | AUGUST
T-460-5344 | PS5-80-IK-8046D | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone D | 3 | In progress |  | 30 | DECEMBER
T-733-5345 | PS5-15-OB-8520B | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone D | 3 | In progress |  | 5 | SEPTEMBER
T-349-5346 | PS5-64-UR-5795B | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | In progress |  | 12 | DECEMBER
T-686-5347 | PS5-61-OB-4075C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | To be completed |  | 25 | AUGUST
T-797-5348 | PS5-19-OB-1840D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | To be completed |  | 32 | OCTOBER
T-948-5349 | PS5-57-OB-9166A | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-01-08 | PS5-05-01 | PS5 - Milestone I | 8 | Closed | 27 | 6 | JANUARY
T-875-5350 | PS5-09-UR-9951B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone I | 8 | In progress |  | 9 | SEPTEMBER
T-019-5351 | PS5-18-UR-9003D | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone H | 7 | To be completed |  | 7 | AUGUST
T-612-5352 | PS5-09-OB-6589C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-02-17 | PS5-01-04 | PS5 - Milestone D | 3 | Closed | 31 | 21 | FEBRUARY
T-933-5353 | PS5-70-IK-5793A | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone E | 4 | To be completed |  | 19 | OCTOBER
T-129-5354 | PS5-35-OB-5274B | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | On hold |  | 48 | NOVEMBER
T-988-5355 | PS5-20-UR-5156A | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-04-17 | PS5-04-01 | PS5 - Milestone G | 6 | Closed | 36 | 10 | APRIL
T-257-5356 | PS5-79-OB-8760D | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-10-25 | PS5-10-06 | PS5 - Milestone C | 2 | Closed | 20 | 29 | OCTOBER
T-865-5357 | PS5-61-OB-4858B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone E | 4 | In progress |  | 11 | OCTOBER
T-808-5358 | PS5-49-UR-4668D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone G | 6 | On hold |  | 22 | AUGUST
T-528-5359 | PS5-42-OB-7897C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone F | 5 | In progress |  | 21 | NOVEMBER
T-325-5360 | PS5-79-OB-7410C | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone D | 3 | On hold |  | 9 | DECEMBER
T-356-5361 | PS5-37-OB-7443D | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-08-14 | PS5-62-02 | PS5 - Milestone C | 2 | Closed | 5 | 45 | AUGUST
T-704-5362 | PS5-31-IK-4859A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-11-07 | PS5-01-09 | PS5 - Milestone G | 6 | Closed | 4 | 5 | NOVEMBER
T-161-5363 | PS5-32-OB-9651B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-10-04 | PS5-99-03 | PS5 - Milestone B | 1.1 | Closed | 20 | 23 | OCTOBER
T-657-5364 | PS5-20-OB-8960D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone F | 5 | In progress |  | 42 | AUGUST
T-296-5365 | PS5-54-IK-2825C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone A | 1 | On hold |  | 35 | OCTOBER
T-918-5366 | PS5-39-UR-3379B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-02-27 | PS5-06-01 | PS5 - Milestone A | 1 | Closed | 38 | 8 | FEBRUARY
T-914-5367 | PS5-75-OB-8392D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone C | 2 | To be completed |  | 18 | SEPTEMBER
T-193-5368 | PS5-29-OB-2348B | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone H | 7 | In progress |  | 18 | SEPTEMBER
T-286-5369 | PS5-93-OB-7958D | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-07-17 | PS5-01-03 | PS5 - Milestone D | 3 | Closed | 36 | 36 | JULY
T-146-5370 | PS5-57-OB-4635D | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-11-15 | PS5-01-03 | PS5 - Milestone A | 1 | Closed | 39 | 30 | NOVEMBER
T-744-5371 | PS5-19-OB-2727D | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone D | 3 | In progress |  | 46 | OCTOBER
T-343-5372 | PS5-66-OB-9968B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-12-10 | PS5-01-02 | PS5 - Milestone D | 3 | Closed | 8 | 31 | DECEMBER
T-452-5373 | PS5-52-OB-3813D | CQE02 - LV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone E | 4 | In progress |  | 21 | AUGUST
T-946-5374 | PS5-76-IK-6526A | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-11-07 | PS5-11-03 | PS5 - Milestone G | 6 | Closed | 16 | 8 | NOVEMBER
T-404-5375 | PS5-82-UR-6966C | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-02-24 | PS5-04-01 | PS5 - Milestone B | 1.1 | Closed | 22 | 47 | FEBRUARY
T-787-5376 | PS5-39-IK-4292B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone D | 3 | To be completed |  | 32 | SEPTEMBER
T-543-5377 | PS5-61-IK-8022C | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone C | 2 | To be completed |  | 11 | OCTOBER
T-653-5378 | PS5-82-UR-7013B | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone A | 1 | In progress |  | 17 | DECEMBER
T-657-5379 | PS5-83-IK-7901A | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-03-25 | PS5-04-03 | PS5 - Milestone H | 7 | Closed | 34 | 24 | MARCH
T-192-5380 | PS5-14-OB-1940B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone G | 6 | To be completed |  | 43 | NOVEMBER
T-522-5381 | PS5-11-OB-6078B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-02-17 | PS5-82-02 | PS5 - Milestone E | 4 | Closed | 28 | 10 | FEBRUARY
T-242-5382 | PS5-78-IK-2204B | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-09-10 | PS5-12-01 | PS5 - Milestone C | 2 | Closed | 40 | 11 | SEPTEMBER
T-626-5383 | PS5-42-OB-7664A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone D | 3 | To be completed |  | 43 | DECEMBER
T-017-5384 | PS5-56-OB-6253A | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone G | 6 | To be completed |  | 7 | OCTOBER
T-789-5385 | PS5-58-OB-6800D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone B | 1.1 | On hold |  | 10 | DECEMBER
T-835-5386 | PS5-79-OB-2154A | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone B | 1.1 | To be completed |  | 35 | DECEMBER
T-067-5387 | PS5-79-UR-1673A | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-04-23 | PS5-02-03 | PS5 - Milestone G | 6 | Closed | 19 | 40 | APRIL
T-364-5388 | PS5-19-OB-8378D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone A | 1 | To be completed |  | 6 | NOVEMBER
T-118-5389 | PS5-62-IK-6273B | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-07-23 | PS5-63-01 | PS5 - Milestone D | 3 | Closed | 37 | 37 | JULY
T-235-5390 | PS5-78-UR-2240C | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | To be completed |  | 22 | DECEMBER
T-800-5391 | PS5-93-OB-7436B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone G | 6 | In progress |  | 39 | NOVEMBER
T-828-5392 | PS5-81-IK-6591C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | In progress |  | 34 | AUGUST
T-793-5393 | PS5-23-OB-3589A | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-02-28 | PS5-06-01 | PS5 - Milestone F | 5 | Closed | 35 | 41 | FEBRUARY
T-214-5394 | PS5-01-UR-4515D | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | In progress |  | 19 | SEPTEMBER
T-380-5395 | PS5-15-UR-8605C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-12-05 | PS5-04-02 | PS5 - Milestone I | 8 | Closed | 29 | 10 | DECEMBER
T-416-5396 | PS5-85-OB-1686A | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-07-09 | PS5-61-07 | PS5 - Milestone B | 1.1 | Closed | 27 | 20 | JULY
T-112-5397 | PS5-57-OB-9845D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone E | 4 | In progress |  | 35 | NOVEMBER
T-010-5398 | PS5-70-IK-5878C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone A | 1 | In progress |  | 34 | NOVEMBER
T-411-5399 | PS5-88-UR-4226B | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone I | 8 | On hold |  | 46 | NOVEMBER
T-282-5400 | PS5-64-IK-8454C | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-03-07 | PS5-07-03 | PS5 - Milestone F | 5 | Closed | 36 | 22 | MARCH
T-554-5401 | PS5-76-UR-6319B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone H | 7 | On hold |  | 26 | DECEMBER
T-313-5402 | PS5-58-UR-1883B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone D | 3 | To be completed |  | 34 | NOVEMBER
T-006-5403 | PS5-28-OB-9578B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-07-18 | PS5-82-02 | PS5 - Milestone H | 7 | Closed | 28 | 16 | JULY
T-781-5404 | PS5-37-IK-5014A | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | To be completed |  | 47 | AUGUST
T-934-5405 | PS5-97-OB-8412B | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone A | 1 | To be completed |  | 32 | NOVEMBER
T-216-5406 | PS5-17-IK-8326A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone H | 7 | In progress |  | 34 | DECEMBER
T-146-5407 | PS5-34-OB-5781A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone F | 5 | In progress |  | 11 | DECEMBER
T-568-5408 | PS5-83-OB-4512C | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone E | 4 | To be completed |  | 24 | OCTOBER
T-999-5409 | PS5-15-UR-1317C | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone E | 4 | In progress |  | 33 | SEPTEMBER
T-711-5410 | PS5-79-UR-7541B | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | To be completed |  | 21 | SEPTEMBER
T-322-5411 | PS5-26-UR-3217A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | In progress |  | 12 | DECEMBER
T-758-5412 | PS5-08-UR-5682A | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-11-28 | PS5-03-02 | PS5 - Milestone A | 1 | Closed | 13 | 45 | NOVEMBER
T-120-5413 | PS5-05-IK-3347C | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-05-06 | PS5-06-03 | PS5 - Milestone A | 1 | Closed | 33 | 43 | MAY
T-629-5414 | PS5-73-OB-9875A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone G | 6 | To be completed |  | 36 | OCTOBER
T-094-5415 | PS5-92-IK-5347A | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-04-10 | PS5-12-02 | PS5 - Milestone G | 6 | Closed | 37 | 22 | APRIL
T-639-5416 | PS5-14-UR-2290C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-04-04 | PS5-10-03 | PS5 - Milestone A | 1 | Closed | 25 | 9 | APRIL
T-692-5417 | PS5-66-UR-2105D | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-02-19 | PS5-01-05 | PS5 - Milestone D | 3 | Closed | 35 | 42 | FEBRUARY
T-752-5418 | PS5-09-IK-5884C | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | On hold |  | 33 | OCTOBER
T-289-5419 | PS5-28-IK-3246B | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone G | 6 | On hold |  | 38 | NOVEMBER
T-532-5420 | PS5-12-IK-8858D | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone A | 1 | In progress |  | 16 | OCTOBER
T-796-5421 | PS5-73-IK-1070C | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone G | 6 | In progress |  | 45 | AUGUST
T-622-5422 | PS5-93-UR-5054C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | On hold |  | 16 | AUGUST
T-245-5423 | PS5-18-OB-9558D | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone F | 5 | To be completed |  | 24 | DECEMBER
T-460-5424 | PS5-56-OB-5020C | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone H | 7 | In progress |  | 20 | DECEMBER
T-942-5425 | PS5-48-OB-3503D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-11-25 | PS5-99-01 | PS5 - Milestone C | 2 | Closed | 40 | 28 | NOVEMBER
T-565-5426 | PS5-42-IK-7281D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-10-20 | PS5-08-01 | PS5 - Milestone F | 5 | Closed | 22 | 14 | OCTOBER
T-821-5427 | PS5-77-UR-6316A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | To be completed |  | 25 | DECEMBER
T-731-5428 | PS5-78-IK-8023C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-04-01 | PS5-01-02 | PS5 - Milestone A | 1 | Closed | 32 | 8 | APRIL
T-232-5429 | PS5-14-IK-4550D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | To be completed |  | 26 | AUGUST
T-985-5430 | PS5-55-UR-3985D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-04-28 | PS5-03-23 | PS5 - Milestone F | 5 | Closed | 10 | 6 | APRIL
T-447-5431 | PS5-20-OB-5409C | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-11-27 | PS5-06-03 | PS5 - Milestone B | 1.1 | Closed | 33 | 31 | NOVEMBER
T-844-5432 | PS5-35-UR-5067D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone H | 7 | In progress |  | 20 | DECEMBER
T-074-5433 | PS5-91-OB-8539C | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone H | 7 | To be completed |  | 31 | DECEMBER
T-983-5434 | PS5-37-OB-5520D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone B | 1.1 | In progress |  | 4 | NOVEMBER
T-065-5435 | PS5-28-OB-8188B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone F | 5 | To be completed |  | 12 | OCTOBER
T-510-5436 | PS5-09-UR-5907A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone F | 5 | To be completed |  | 16 | DECEMBER
T-770-5437 | PS5-40-IK-9804D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | To be completed |  | 45 | SEPTEMBER
T-797-5438 | PS5-09-OB-7803C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone F | 5 | To be completed |  | 21 | DECEMBER
T-284-5439 | PS5-30-OB-4327D | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone F | 5 | To be completed |  | 7 | OCTOBER
T-934-5440 | PS5-61-UR-5926A | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | To be completed |  | 4 | DECEMBER
T-442-5441 | PS5-12-IK-1062C | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone H | 7 | To be completed |  | 43 | DECEMBER
T-345-5442 | PS5-47-OB-3073B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-10-10 | PS5-01-06 | PS5 - Milestone F | 5 | Closed | 15 | 41 | OCTOBER
T-631-5443 | PS5-56-UR-1818B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-07-25 | PS5-61-02 | PS5 - Milestone C | 2 | Closed | 12 | 34 | JULY
T-554-5444 | PS5-10-IK-6449D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone C | 2 | On hold |  | 19 | NOVEMBER
T-106-5445 | PS5-88-UR-1167C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | To be completed |  | 44 | DECEMBER
T-923-5446 | PS5-60-OB-6930C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-09-13 | PS5-01-01 | PS5 - Milestone H | 7 | Closed | 43 | 12 | SEPTEMBER
T-653-5447 | PS5-70-IK-8623C | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone A | 1 | To be completed |  | 14 | SEPTEMBER
T-623-5448 | PS5-70-IK-9762B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone C | 2 | On hold |  | 17 | SEPTEMBER
T-142-5449 | PS5-81-OB-2494A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-12-13 | PS5-05-01 | PS5 - Milestone D | 3 | Closed | 35 | 23 | DECEMBER
T-413-5450 | PS5-42-OB-2317D | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-12-03 | PS5-01-06 | PS5 - Milestone F | 5 | Closed | 29 | 28 | DECEMBER
T-292-5451 | PS5-57-OB-3802B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone E | 4 | To be completed |  | 30 | AUGUST
T-448-5452 | PS5-45-OB-8669D | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-10-09 | PS5-01-01 | PS5 - Milestone D | 3 | Closed | 21 | 12 | OCTOBER
T-601-5453 | PS5-21-OB-9022C | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone I | 8 | In progress |  | 4 | AUGUST
T-220-5454 | PS5-19-OB-4288A | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone I | 8 | On hold |  | 48 | AUGUST
T-266-5455 | PS5-64-IK-9588B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone D | 3 | To be completed |  | 28 | OCTOBER
T-529-5456 | PS5-92-UR-5807C | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-08-17 | PS5-09-01 | PS5 - Milestone A | 1 | Closed | 48 | 19 | AUGUST
T-306-5457 | PS5-15-OB-3477C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone B | 1.1 | In progress |  | 25 | NOVEMBER
T-924-5458 | PS5-37-IK-3652A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone E | 4 | To be completed |  | 17 | OCTOBER
T-015-5459 | PS5-58-IK-9376B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | To be completed |  | 12 | NOVEMBER
T-902-5460 | PS5-74-OB-4337A | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-04-09 | PS5-13-01 | PS5 - Milestone D | 3 | Closed | 28 | 45 | APRIL
T-966-5461 | PS5-13-IK-1752B | CQE04 - Transformer | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-03-20 | PS5-01-04 | PS5 - Milestone D | 3 | Closed | 20 | 22 | MARCH
T-778-5462 | PS5-18-UR-6840B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | To be completed |  | 21 | NOVEMBER
T-804-5463 | PS5-86-OB-1450B | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-07-21 | PS5-01-08 | PS5 - Milestone G | 6 | Closed | 9 | 34 | JULY
T-666-5464 | PS5-78-UR-6677A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone E | 4 | In progress |  | 31 | OCTOBER
T-437-5465 | PS5-84-OB-4623C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-04-16 | PS5-11-02 | PS5 - Milestone F | 5 | Closed | 5 | 20 | APRIL
T-170-5466 | PS5-69-IK-4767C | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone G | 6 | To be completed |  | 10 | DECEMBER
T-841-5467 | PS5-36-IK-2122A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-10-13 | PS5-02-03 | PS5 - Milestone D | 3 | Closed | 11 | 48 | OCTOBER
T-978-5468 | PS5-79-OB-7130C | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone G | 6 | On hold |  | 48 | OCTOBER
T-771-5469 | PS5-53-OB-1507B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | To be completed |  | 21 | DECEMBER
T-230-5470 | PS5-99-OB-2644D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone G | 6 | In progress |  | 31 | NOVEMBER
T-668-5471 | PS5-27-UR-4423C | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone H | 7 | In progress |  | 47 | SEPTEMBER
T-325-5472 | PS5-76-UR-4991D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone C | 2 | To be completed |  | 29 | AUGUST
T-048-5473 | PS5-62-UR-6772A | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-12-20 | PS5-08-01 | PS5 - Milestone F | 5 | Closed | 17 | 21 | DECEMBER
T-757-5474 | PS5-02-OB-9871C | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-01-28 | PS5-82-02 | PS5 - Milestone D | 3 | Closed | 40 | 33 | JANUARY
T-807-5475 | PS5-38-OB-8102B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-06-04 | PS5-13-01 | PS5 - Milestone H | 7 | Closed | 5 | 9 | JUNE
T-092-5476 | PS5-92-OB-1385C | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone G | 6 | On hold |  | 45 | NOVEMBER
T-328-5477 | PS5-13-UR-4494A | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-10-12 | PS5-10-04 | PS5 - Milestone I | 8 | Closed | 14 | 24 | OCTOBER
T-163-5478 | PS5-39-IK-9557B | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-01-08 | PS5-02-02 | PS5 - Milestone E | 4 | Closed | 4 | 8 | JANUARY
T-860-5479 | PS5-11-OB-4564A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-02-11 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 19 | 7 | FEBRUARY
T-203-5480 | PS5-24-IK-7870D | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | To be completed |  | 43 | SEPTEMBER
T-416-5481 | PS5-89-OB-2009A | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | To be completed |  | 7 | AUGUST
T-553-5482 | PS5-61-IK-2023B | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone A | 1 | To be completed |  | 23 | DECEMBER
T-040-5483 | PS5-80-OB-6727A | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone H | 7 | In progress |  | 32 | AUGUST
T-577-5484 | PS5-59-IK-8721B | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone C | 2 | On hold |  | 28 | DECEMBER
T-222-5485 | PS5-86-IK-2570A | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone E | 4 | On hold |  | 27 | AUGUST
T-901-5486 | PS5-47-UR-2583D | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | In progress |  | 34 | OCTOBER
T-092-5487 | PS5-90-UR-6338D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone C | 2 | To be completed |  | 31 | AUGUST
T-567-5488 | PS5-44-IK-3747C | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone D | 3 | To be completed |  | 23 | SEPTEMBER
T-576-5489 | PS5-41-OB-1646D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-08-26 | PS5-13-01 | PS5 - Milestone A | 1 | Closed | 42 | 37 | AUGUST
T-092-5490 | PS5-60-OB-3337B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone D | 3 | To be completed |  | 43 | OCTOBER
T-414-5491 | PS5-59-OB-5005C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-04-24 | PS5-11-01 | PS5 - Milestone H | 7 | Closed | 31 | 17 | APRIL
T-449-5492 | PS5-97-OB-7974D | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-03-19 | PS5-62-02 | PS5 - Milestone D | 3 | Closed | 37 | 39 | MARCH
T-012-5493 | PS5-05-OB-7526C | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone I | 8 | In progress |  | 17 | OCTOBER
T-049-5494 | PS5-73-OB-7778C | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-05-22 | PS5-03-03 | PS5 - Milestone D | 3 | Closed | 9 | 37 | MAY
T-188-5495 | PS5-39-UR-9793D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | In progress |  | 22 | DECEMBER
T-645-5496 | PS5-23-UR-2215C | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone I | 8 | In progress |  | 14 | SEPTEMBER
T-794-5497 | PS5-67-OB-7217A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone H | 7 | On hold |  | 13 | DECEMBER
T-100-5498 | PS5-56-OB-7779D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-05-03 | PS5-07-03 | PS5 - Milestone F | 5 | Closed | 28 | 48 | MAY
T-590-5499 | PS5-89-IK-8402C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-10-10 | PS5-08-02 | PS5 - Milestone H | 7 | Closed | 43 | 25 | OCTOBER
T-714-5500 | PS5-43-UR-7478C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-01-09 | PS5-08-02 | PS5 - Milestone C | 2 | Closed | 37 | 4 | JANUARY
T-171-5501 | PS5-61-UR-9777A | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-06-02 | PS5-09-04 | PS5 - Milestone D | 3 | Closed | 26 | 9 | JUNE
T-948-5502 | PS5-38-OB-2675B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone I | 8 | On hold |  | 31 | NOVEMBER
T-221-5503 | PS5-70-OB-6219B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-10-16 | PS5-99-02 | PS5 - Milestone B | 1.1 | Closed | 13 | 30 | OCTOBER
T-891-5504 | PS5-07-IK-9612B | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone F | 5 | To be completed |  | 34 | SEPTEMBER
T-599-5505 | PS5-57-UR-6073B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-02-25 | PS5-10-06 | PS5 - Milestone C | 2 | Closed | 37 | 23 | FEBRUARY
T-048-5506 | PS5-14-UR-8236A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone H | 7 | In progress |  | 42 | DECEMBER
T-036-5507 | PS5-37-UR-3108C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone I | 8 | In progress |  | 35 | NOVEMBER
T-251-5508 | PS5-73-IK-7640A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone B | 1.1 | In progress |  | 33 | DECEMBER
T-501-5509 | PS5-07-OB-2771D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone G | 6 | To be completed |  | 23 | AUGUST
T-871-5510 | PS5-88-IK-1916B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone C | 2 | On hold |  | 28 | DECEMBER
T-322-5511 | PS5-16-OB-3559D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-07-06 | PS5-07-02 | PS5 - Milestone E | 4 | Closed | 47 | 28 | JULY
T-861-5512 | PS5-18-UR-4567D | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone I | 8 | To be completed |  | 32 | AUGUST
T-047-5513 | PS5-63-OB-4318A | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | In progress |  | 15 | NOVEMBER
T-397-5514 | PS5-30-IK-5492D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-12-05 | PS5-02-01 | PS5 - Milestone G | 6 | Closed | 4 | 20 | DECEMBER
T-600-5515 | PS5-34-UR-1113A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-05-22 | PS5-06-02 | PS5 - Milestone C | 2 | Closed | 48 | 29 | MAY
T-266-5516 | PS5-83-UR-2387B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone E | 4 | To be completed |  | 6 | SEPTEMBER
T-970-5517 | PS5-82-OB-4072C | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone G | 6 | On hold |  | 12 | DECEMBER
T-939-5518 | PS5-14-IK-1656D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone G | 6 | In progress |  | 10 | DECEMBER
T-111-5519 | PS5-92-OB-1979D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | To be completed |  | 33 | OCTOBER
T-999-5520 | PS5-57-OB-1452C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone B | 1.1 | In progress |  | 14 | OCTOBER
T-574-5521 | PS5-77-IK-8954C | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone A | 1 | To be completed |  | 38 | OCTOBER
T-003-5522 | PS5-09-OB-5355D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | To be completed |  | 17 | AUGUST
T-092-5523 | PS5-03-UR-4192B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone G | 6 | To be completed |  | 38 | NOVEMBER
T-175-5524 | PS5-04-UR-8343B | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-05-16 | PS5-02-03 | PS5 - Milestone E | 4 | Closed | 35 | 37 | MAY
T-079-5525 | PS5-17-OB-7062C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone B | 1.1 | In progress |  | 16 | OCTOBER
T-015-5526 | PS5-90-IK-7905B | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-09-02 | PS5-01-06 | PS5 - Milestone A | 1 | Closed | 33 | 18 | SEPTEMBER
T-916-5527 | PS5-42-IK-4543D | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone H | 7 | On hold |  | 23 | NOVEMBER
T-837-5528 | PS5-24-OB-3072B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-11-14 | PS5-07-02 | PS5 - Milestone I | 8 | Closed | 41 | 43 | NOVEMBER
T-873-5529 | PS5-55-UR-5607B | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone C | 2 | On hold |  | 20 | AUGUST
T-929-5530 | PS5-22-OB-9147C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | In progress |  | 42 | AUGUST
T-689-5531 | PS5-35-OB-7927A | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone E | 4 | On hold |  | 31 | OCTOBER
T-127-5532 | PS5-28-OB-1605A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone B | 1.1 | In progress |  | 45 | DECEMBER
T-732-5533 | PS5-23-UR-7638B | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | In progress |  | 37 | DECEMBER
T-053-5534 | PS5-34-IK-5351B | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone I | 8 | In progress |  | 35 | SEPTEMBER
T-131-5535 | PS5-21-OB-2270B | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone A | 1 | On hold |  | 19 | DECEMBER
T-085-5536 | PS5-75-OB-9855A | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone C | 2 | On hold |  | 14 | NOVEMBER
T-118-5537 | PS5-35-OB-1783D | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-11-14 | PS5-11-03 | PS5 - Milestone E | 4 | Closed | 20 | 19 | NOVEMBER
T-837-5538 | PS5-60-OB-6793B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone I | 8 | On hold |  | 40 | DECEMBER
T-122-5539 | PS5-47-UR-3531B | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-11-03 | PS5-10-05 | PS5 - Milestone G | 6 | Closed | 44 | 22 | NOVEMBER
T-094-5540 | PS5-01-IK-1362B | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-07-20 | PS5-04-01 | PS5 - Milestone F | 5 | Closed | 6 | 41 | JULY
T-199-5541 | PS5-51-OB-6567C | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone E | 4 | In progress |  | 47 | SEPTEMBER
T-811-5542 | PS5-95-OB-8520C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone I | 8 | To be completed |  | 9 | NOVEMBER
T-536-5543 | PS5-28-OB-9237C | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone F | 5 | To be completed |  | 47 | NOVEMBER
T-278-5544 | PS5-78-UR-2935B | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-11-04 | PS5-06-03 | PS5 - Milestone C | 2 | Closed | 40 | 47 | NOVEMBER
T-421-5545 | PS5-22-OB-8054A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-07-25 | PS5-04-01 | PS5 - Milestone A | 1 | Closed | 26 | 28 | JULY
T-006-5546 | PS5-75-OB-6918D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-08-20 | PS5-62-01 | PS5 - Milestone B | 1.1 | Closed | 31 | 23 | AUGUST
T-537-5547 | PS5-51-OB-3047C | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone C | 2 | On hold |  | 21 | NOVEMBER
T-947-5548 | PS5-30-UR-2175C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | To be completed |  | 45 | OCTOBER
T-287-5549 | PS5-09-IK-2067D | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | To be completed |  | 46 | SEPTEMBER
T-820-5550 | PS5-27-OB-2152C | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone A | 1 | To be completed |  | 18 | DECEMBER
T-896-5551 | PS5-13-OB-3265D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-01-28 | PS5-62-01 | PS5 - Milestone B | 1.1 | Closed | 21 | 28 | JANUARY
T-426-5552 | PS5-47-IK-1066B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone F | 5 | To be completed |  | 25 | NOVEMBER
T-452-5553 | PS5-48-OB-8826B | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-10-06 | PS5-09-01 | PS5 - Milestone D | 3 | Closed | 6 | 33 | OCTOBER
T-439-5554 | PS5-45-OB-2802D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone I | 8 | In progress |  | 13 | OCTOBER
T-447-5555 | PS5-21-IK-9668A | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone E | 4 | On hold |  | 25 | OCTOBER
T-555-5556 | PS5-83-OB-3393A | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | In progress |  | 25 | SEPTEMBER
T-936-5557 | PS5-26-IK-8337C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-11-13 | PS5-01-08 | PS5 - Milestone E | 4 | Closed | 8 | 46 | NOVEMBER
T-470-5558 | PS5-56-OB-9366B | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-02-23 | PS5-05-03 | PS5 - Milestone D | 3 | Closed | 43 | 22 | FEBRUARY
T-848-5559 | PS5-09-OB-5851D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-10-26 | PS5-61-01 | PS5 - Milestone E | 4 | Closed | 11 | 20 | OCTOBER
T-788-5560 | PS5-65-UR-2535B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone G | 6 | On hold |  | 14 | NOVEMBER
T-117-5561 | PS5-90-OB-7841B | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-05-20 | PS5-99-01 | PS5 - Milestone G | 6 | Closed | 45 | 16 | MAY
T-244-5562 | PS5-85-UR-1660A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | On hold |  | 27 | NOVEMBER
T-635-5563 | PS5-94-UR-7264C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone F | 5 | In progress |  | 21 | AUGUST
T-075-5564 | PS5-09-OB-1704C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-05-28 | PS5-03-02 | PS5 - Milestone C | 2 | Closed | 35 | 11 | MAY
T-284-5565 | PS5-82-UR-6390A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone A | 1 | To be completed |  | 5 | DECEMBER
T-055-5566 | PS5-23-IK-1395B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-10-01 | PS5-03-01 | PS5 - Milestone C | 2 | Closed | 26 | 46 | OCTOBER
T-818-5567 | PS5-64-OB-7632C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone I | 8 | To be completed |  | 23 | DECEMBER
T-566-5568 | PS5-45-UR-2071D | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | To be completed |  | 36 | SEPTEMBER
T-507-5569 | PS5-61-OB-4877B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-04-27 | PS5-06-03 | PS5 - Milestone D | 3 | Closed | 22 | 42 | APRIL
T-427-5570 | PS5-01-OB-3100B | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone G | 6 | In progress |  | 7 | SEPTEMBER
T-484-5571 | PS5-03-OB-8593D | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-05-07 | PS5-07-02 | PS5 - Milestone A | 1 | Closed | 25 | 20 | MAY
T-793-5572 | PS5-81-OB-3896C | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone I | 8 | To be completed |  | 21 | DECEMBER
T-401-5573 | PS5-19-IK-4725C | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone F | 5 | To be completed |  | 21 | DECEMBER
T-586-5574 | PS5-43-OB-8829B | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-02-28 | PS5-08-01 | PS5 - Milestone E | 4 | Closed | 24 | 40 | FEBRUARY
T-453-5575 | PS5-34-OB-5666D | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone C | 2 | To be completed |  | 15 | AUGUST
T-200-5576 | PS5-89-UR-2330B | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone F | 5 | In progress |  | 48 | SEPTEMBER
T-019-5577 | PS5-80-UR-8718B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-03-09 | PS5-10-05 | PS5 - Milestone A | 1 | Closed | 34 | 10 | MARCH
T-213-5578 | PS5-12-OB-2337D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone I | 8 | In progress |  | 15 | OCTOBER
T-119-5579 | PS5-80-OB-9258D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone E | 4 | To be completed |  | 24 | SEPTEMBER
T-404-5580 | PS5-16-IK-5052D | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone H | 7 | To be completed |  | 29 | NOVEMBER
T-691-5581 | PS5-96-UR-4685C | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone I | 8 | In progress |  | 32 | NOVEMBER
T-359-5582 | PS5-28-OB-2676B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone C | 2 | In progress |  | 35 | NOVEMBER
T-300-5583 | PS5-63-OB-6701D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-06-04 | PS5-04-03 | PS5 - Milestone H | 7 | Closed | 41 | 25 | JUNE
T-686-5584 | PS5-39-OB-5496C | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-02-13 | PS5-61-01 | PS5 - Milestone E | 4 | Closed | 23 | 30 | FEBRUARY
T-956-5585 | PS5-12-OB-3041D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone B | 1.1 | To be completed |  | 42 | NOVEMBER
T-472-5586 | PS5-33-UR-2318C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-09-19 | PS5-07-02 | PS5 - Milestone D | 3 | Closed | 18 | 7 | SEPTEMBER
T-398-5587 | PS5-72-OB-2357A | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-01-14 | PS5-07-03 | PS5 - Milestone B | 1.1 | Closed | 33 | 19 | JANUARY
T-261-5588 | PS5-58-OB-6390C | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone D | 3 | In progress |  | 21 | AUGUST
T-554-5589 | PS5-96-OB-7627C | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | In progress |  | 7 | SEPTEMBER
T-847-5590 | PS5-54-OB-9034A | CQS01 - Fire Protection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone E | 4 | To be completed |  | 17 | OCTOBER
T-195-5591 | PS5-27-IK-2673C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-09-11 | PS5-09-01 | PS5 - Milestone A | 1 | Closed | 27 | 5 | SEPTEMBER
T-901-5592 | PS5-04-OB-4497A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone F | 5 | On hold |  | 10 | AUGUST
T-651-5593 | PS5-61-IK-2815D | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-05-23 | PS5-62-01 | PS5 - Milestone C | 2 | Closed | 21 | 39 | MAY
T-229-5594 | PS5-21-OB-5770B | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone A | 1 | To be completed |  | 26 | OCTOBER
T-043-5595 | PS5-45-OB-9837C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone D | 3 | In progress |  | 44 | AUGUST
T-594-5596 | PS5-49-IK-6937B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-07-25 | PS5-04-01 | PS5 - Milestone E | 4 | Closed | 8 | 12 | JULY
T-942-5597 | PS5-25-IK-5803C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-01-26 | PS5-05-01 | PS5 - Milestone D | 3 | Closed | 34 | 8 | JANUARY
T-621-5598 | PS5-28-UR-7592A | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone F | 5 | To be completed |  | 23 | NOVEMBER
T-541-5599 | PS5-11-OB-9167A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone F | 5 | In progress |  | 10 | AUGUST
T-715-5600 | PS5-82-UR-2350A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone C | 2 | To be completed |  | 28 | OCTOBER
T-578-5601 | PS5-94-OB-8124A | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone D | 3 | On hold |  | 4 | DECEMBER
T-712-5602 | PS5-86-OB-1431B | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone H | 7 | On hold |  | 46 | SEPTEMBER
T-195-5603 | PS5-42-UR-2469D | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone A | 1 | To be completed |  | 21 | NOVEMBER
T-564-5604 | PS5-66-IK-8474D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone D | 3 | In progress |  | 39 | OCTOBER
T-381-5605 | PS5-20-OB-8657A | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone D | 3 | On hold |  | 43 | NOVEMBER
T-041-5606 | PS5-28-IK-5335B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-06-24 | PS5-01-06 | PS5 - Milestone B | 1.1 | Closed | 44 | 23 | JUNE
T-860-5607 | PS5-41-IK-1453D | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone E | 4 | To be completed |  | 31 | SEPTEMBER
T-877-5608 | PS5-70-IK-9907A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | To be completed |  | 15 | NOVEMBER
T-105-5609 | PS5-78-OB-7580C | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone A | 1 | To be completed |  | 35 | DECEMBER
T-985-5610 | PS5-74-OB-5240A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone H | 7 | To be completed |  | 12 | DECEMBER
T-813-5611 | PS5-66-UR-6692C | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-01-03 | PS5-10-05 | PS5 - Milestone B | 1.1 | Closed | 4 | 9 | JANUARY
T-907-5612 | PS5-45-OB-8712B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone H | 7 | To be completed |  | 35 | DECEMBER
T-937-5613 | PS5-20-UR-5948B | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-08-08 | PS5-10-04 | PS5 - Milestone C | 2 | Closed | 47 | 4 | AUGUST
T-453-5614 | PS5-66-OB-1271D | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-01-18 | PS5-60-04 | PS5 - Milestone B | 1.1 | Closed | 17 | 24 | JANUARY
T-329-5615 | PS5-77-OB-5946B | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone C | 2 | To be completed |  | 18 | DECEMBER
T-125-5616 | PS5-24-IK-1847B | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-11-28 | PS5-01-01 | PS5 - Milestone I | 8 | Closed | 42 | 35 | NOVEMBER
T-806-5617 | PS5-79-IK-4768D | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone A | 1 | On hold |  | 24 | AUGUST
T-031-5618 | PS5-66-UR-6550C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone I | 8 | To be completed |  | 37 | NOVEMBER
T-138-5619 | PS5-40-OB-4292B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone A | 1 | To be completed |  | 48 | DECEMBER
T-132-5620 | PS5-71-OB-5464C | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone A | 1 | In progress |  | 38 | SEPTEMBER
T-056-5621 | PS5-84-OB-7305B | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone H | 7 | To be completed |  | 14 | NOVEMBER
T-155-5622 | PS5-19-IK-2660B | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone I | 8 | To be completed |  | 48 | AUGUST
T-674-5623 | PS5-31-OB-8485B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone E | 4 | To be completed |  | 48 | OCTOBER
T-908-5624 | PS5-06-IK-3703B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone H | 7 | In progress |  | 5 | AUGUST
T-182-5625 | PS5-10-OB-8126D | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone E | 4 | In progress |  | 32 | NOVEMBER
T-195-5626 | PS5-50-IK-7118C | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-10-24 | PS5-04-03 | PS5 - Milestone E | 4 | Closed | 39 | 48 | OCTOBER
T-510-5627 | PS5-08-UR-2014C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | In progress |  | 27 | AUGUST
T-397-5628 | PS5-33-OB-6547A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | On hold |  | 40 | AUGUST
T-261-5629 | PS5-36-UR-9487B | CQP01 - Pipe Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | To be completed |  | 4 | AUGUST
T-940-5630 | PS5-62-UR-2624B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone A | 1 | To be completed |  | 4 | SEPTEMBER
T-264-5631 | PS5-41-OB-7490A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-09-16 | PS5-07-04 | PS5 - Milestone G | 6 | Closed | 5 | 4 | SEPTEMBER
T-823-5632 | PS5-20-OB-3293C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone I | 8 | On hold |  | 26 | DECEMBER
T-865-5633 | PS5-77-OB-3483D | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-08-27 | PS5-60-07 | PS5 - Milestone C | 2 | Closed | 7 | 15 | AUGUST
T-704-5634 | PS5-40-UR-9943C | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-03-26 | PS5-60-10 | PS5 - Milestone B | 1.1 | Closed | 11 | 20 | MARCH
T-077-5635 | PS5-47-OB-5790C | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone D | 3 | To be completed |  | 22 | SEPTEMBER
T-455-5636 | PS5-57-UR-3190A | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone G | 6 | To be completed |  | 12 | AUGUST
T-439-5637 | PS5-80-OB-5126D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone C | 2 | To be completed |  | 8 | NOVEMBER
T-167-5638 | PS5-46-IK-2641C | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-15 | PS5-60-04 | PS5 - Milestone F | 5 | Closed | 32 | 13 | APRIL
T-943-5639 | PS5-26-IK-5379B | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone E | 4 | To be completed |  | 10 | DECEMBER
T-846-5640 | PS5-08-UR-7620B | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-08-10 | PS5-01-04 | PS5 - Milestone G | 6 | Closed | 24 | 28 | AUGUST
T-049-5641 | PS5-58-IK-1403C | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone H | 7 | To be completed |  | 27 | NOVEMBER
T-743-5642 | PS5-65-UR-9983A | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone D | 3 | On hold |  | 34 | DECEMBER
T-966-5643 | PS5-62-OB-8521C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone G | 6 | On hold |  | 5 | NOVEMBER
T-107-5644 | PS5-07-OB-1319B | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | In progress |  | 24 | DECEMBER
T-554-5645 | PS5-81-IK-1808C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-02-27 | PS5-62-02 | PS5 - Milestone H | 7 | Closed | 43 | 33 | FEBRUARY
T-279-5646 | PS5-95-OB-8199B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone H | 7 | To be completed |  | 34 | SEPTEMBER
T-474-5647 | PS5-51-UR-3981C | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone B | 1.1 | To be completed |  | 20 | NOVEMBER
T-876-5648 | PS5-11-OB-3326B | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-01-26 | PS5-61-01 | PS5 - Milestone I | 8 | Closed | 36 | 5 | JANUARY
T-397-5649 | PS5-74-IK-4295C | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-05-27 | PS5-99-01 | PS5 - Milestone I | 8 | Closed | 8 | 24 | MAY
T-196-5650 | PS5-63-IK-1567A | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | On hold |  | 9 | NOVEMBER
T-562-5651 | PS5-06-UR-9674C | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | In progress |  | 33 | OCTOBER
T-472-5652 | PS5-13-UR-7485B | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone A | 1 | In progress |  | 44 | DECEMBER
T-880-5653 | PS5-31-OB-1664A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | In progress |  | 37 | SEPTEMBER
T-068-5654 | PS5-49-OB-6154C | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone C | 2 | To be completed |  | 28 | SEPTEMBER
T-367-5655 | PS5-75-IK-4431C | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-10-16 | PS5-10-05 | PS5 - Milestone G | 6 | Closed | 38 | 28 | OCTOBER
T-310-5656 | PS5-42-OB-3846A | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-08-19 | PS5-10-02 | PS5 - Milestone E | 4 | Closed | 21 | 34 | AUGUST
T-519-5657 | PS5-19-OB-3431C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone F | 5 | In progress |  | 19 | SEPTEMBER
T-122-5658 | PS5-92-OB-4164B | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-07-19 | PS5-82-02 | PS5 - Milestone C | 2 | Closed | 25 | 11 | JULY
T-209-5659 | PS5-28-UR-9824D | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone A | 1 | In progress |  | 16 | DECEMBER
T-610-5660 | PS5-31-OB-4066B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | To be completed |  | 36 | SEPTEMBER
T-933-5661 | PS5-89-IK-2413B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone A | 1 | In progress |  | 32 | AUGUST
T-717-5662 | PS5-69-OB-3369D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-10-18 | PS5-99-02 | PS5 - Milestone D | 3 | Closed | 24 | 44 | OCTOBER
T-094-5663 | PS5-05-OB-1191A | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone G | 6 | To be completed |  | 47 | DECEMBER
T-152-5664 | PS5-43-IK-6842B | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone I | 8 | To be completed |  | 14 | OCTOBER
T-685-5665 | PS5-29-OB-1804A | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone A | 1 | In progress |  | 15 | OCTOBER
T-685-5666 | PS5-04-IK-7248A | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-01-24 | PS5-06-01 | PS5 - Milestone B | 1.1 | Closed | 23 | 9 | JANUARY
T-400-5667 | PS5-41-UR-5934B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone B | 1.1 | To be completed |  | 16 | DECEMBER
T-543-5668 | PS5-77-OB-9213C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-04-15 | PS5-08-01 | PS5 - Milestone B | 1.1 | Closed | 8 | 29 | APRIL
T-309-5669 | PS5-66-OB-8271C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-02-10 | PS5-62-02 | PS5 - Milestone C | 2 | Closed | 32 | 19 | FEBRUARY
T-717-5670 | PS5-13-OB-7213A | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-02-07 | PS5-60-07 | PS5 - Milestone B | 1.1 | Closed | 47 | 48 | FEBRUARY
T-412-5671 | PS5-14-UR-7224B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone A | 1 | On hold |  | 45 | DECEMBER
T-352-5672 | PS5-46-OB-5278C | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone D | 3 | To be completed |  | 32 | DECEMBER
T-666-5673 | PS5-20-UR-9034A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-03-23 | PS5-08-02 | PS5 - Milestone I | 8 | Closed | 39 | 44 | MARCH
T-407-5674 | PS5-24-UR-4782C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-02-25 | PS5-10-06 | PS5 - Milestone I | 8 | Closed | 26 | 7 | FEBRUARY
T-998-5675 | PS5-77-UR-9425B | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone F | 5 | In progress |  | 22 | OCTOBER
T-249-5676 | PS5-27-OB-1590B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | On hold |  | 28 | OCTOBER
T-651-5677 | PS5-87-IK-5744B | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-12-18 | PS5-82-07 | PS5 - Milestone D | 3 | Closed | 20 | 13 | DECEMBER
T-268-5678 | PS5-09-UR-5550D | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone C | 2 | In progress |  | 25 | DECEMBER
T-872-5679 | PS5-75-UR-6159D | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone E | 4 | To be completed |  | 11 | AUGUST
T-558-5680 | PS5-54-UR-4018D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-05-17 | PS5-07-01 | PS5 - Milestone H | 7 | Closed | 48 | 19 | MAY
T-818-5681 | PS5-12-OB-8358D | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone E | 4 | On hold |  | 42 | SEPTEMBER
T-650-5682 | PS5-61-UR-8389D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-06-25 | PS5-05-02 | PS5 - Milestone F | 5 | Closed | 41 | 34 | JUNE
T-436-5683 | PS5-16-IK-3080D | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-07-05 | PS5-03-02 | PS5 - Milestone A | 1 | Closed | 14 | 26 | JULY
T-509-5684 | PS5-06-OB-2905C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | In progress |  | 12 | OCTOBER
T-581-5685 | PS5-79-OB-4174B | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone E | 4 | To be completed |  | 31 | DECEMBER
T-388-5686 | PS5-07-OB-2074A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone C | 2 | On hold |  | 12 | AUGUST
T-707-5687 | PS5-90-OB-7630C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone D | 3 | To be completed |  | 34 | NOVEMBER
T-667-5688 | PS5-98-OB-7725D | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-12-07 | PS5-09-02 | PS5 - Milestone I | 8 | Closed | 46 | 18 | DECEMBER
T-761-5689 | PS5-23-OB-6300D | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-04-02 | PS5-61-07 | PS5 - Milestone D | 3 | Closed | 28 | 21 | APRIL
T-015-5690 | PS5-38-OB-9987D | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone I | 8 | To be completed |  | 8 | DECEMBER
T-486-5691 | PS5-54-IK-6568D | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-10-08 | PS5-06-02 | PS5 - Milestone D | 3 | Closed | 11 | 31 | OCTOBER
T-813-5692 | PS5-91-UR-9750B | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-01-14 | PS5-60-10 | PS5 - Milestone G | 6 | Closed | 23 | 34 | JANUARY
T-525-5693 | PS5-94-OB-1555A | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone E | 4 | To be completed |  | 34 | NOVEMBER
T-424-5694 | PS5-99-UR-7215D | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-06-21 | PS5-08-01 | PS5 - Milestone D | 3 | Closed | 30 | 45 | JUNE
T-890-5695 | PS5-73-UR-3271B | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone E | 4 | To be completed |  | 21 | OCTOBER
T-408-5696 | PS5-69-IK-8960C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-05-08 | PS5-82-07 | PS5 - Milestone H | 7 | Closed | 24 | 41 | MAY
T-844-5697 | PS5-65-IK-5438B | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-12-07 | PS5-11-01 | PS5 - Milestone C | 2 | Closed | 13 | 13 | DECEMBER
T-073-5698 | PS5-62-IK-6921C | CQM04 - Vessel | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-11-02 | PS5-03-23 | PS5 - Milestone E | 4 | Closed | 12 | 17 | NOVEMBER
T-034-5699 | PS5-13-OB-9442A | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-07-09 | PS5-09-01 | PS5 - Milestone B | 1.1 | Closed | 43 | 8 | JULY
T-563-5700 | PS5-84-OB-3231B | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-03-06 | PS5-04-04 | PS5 - Milestone D | 3 | Closed | 11 | 21 | MARCH
T-944-5701 | PS5-26-OB-9712C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone G | 6 | In progress |  | 36 | DECEMBER
T-927-5702 | PS5-67-OB-9446A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone A | 1 | In progress |  | 41 | SEPTEMBER
T-164-5703 | PS5-22-OB-7011A | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-10-08 | PS5-99-03 | PS5 - Milestone D | 3 | Closed | 21 | 31 | OCTOBER
T-689-5704 | PS5-24-IK-4721A | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone H | 7 | To be completed |  | 43 | OCTOBER
T-015-5705 | PS5-80-IK-5079B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | In progress |  | 46 | DECEMBER
T-716-5706 | PS5-28-OB-6106A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone G | 6 | To be completed |  | 34 | NOVEMBER
T-856-5707 | PS5-22-IK-1585D | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-02-14 | PS5-12-02 | PS5 - Milestone D | 3 | Closed | 34 | 20 | FEBRUARY
T-445-5708 | PS5-86-OB-3296D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-01-18 | PS5-03-03 | PS5 - Milestone A | 1 | Closed | 27 | 10 | JANUARY
T-018-5709 | PS5-76-UR-8625D | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone D | 3 | In progress |  | 45 | DECEMBER
T-943-5710 | PS5-86-OB-7743A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | In progress |  | 42 | AUGUST
T-578-5711 | PS5-57-IK-7636A | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone F | 5 | To be completed |  | 31 | NOVEMBER
T-109-5712 | PS5-98-OB-6061D | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | On hold |  | 30 | OCTOBER
T-538-5713 | PS5-08-OB-2029D | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | To be completed |  | 19 | AUGUST
T-382-5714 | PS5-28-IK-2791D | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | To be completed |  | 26 | AUGUST
T-911-5715 | PS5-31-OB-7694D | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-08-22 | PS5-61-07 | PS5 - Milestone H | 7 | Closed | 41 | 35 | AUGUST
T-285-5716 | PS5-90-UR-9553A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-01-11 | PS5-05-02 | PS5 - Milestone H | 7 | Closed | 47 | 10 | JANUARY
T-227-5717 | PS5-29-OB-8149B | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-02-05 | PS5-09-01 | PS5 - Milestone D | 3 | Closed | 26 | 43 | FEBRUARY
T-010-5718 | PS5-73-OB-9352C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-12-10 | PS5-82-02 | PS5 - Milestone C | 2 | Closed | 47 | 36 | DECEMBER
T-869-5719 | PS5-49-OB-3395D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-03-16 | PS5-05-01 | PS5 - Milestone C | 2 | Closed | 16 | 21 | MARCH
T-036-5720 | PS5-40-IK-4021B | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone A | 1 | To be completed |  | 37 | NOVEMBER
T-405-5721 | PS5-92-UR-7567A | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone I | 8 | To be completed |  | 42 | SEPTEMBER
T-505-5722 | PS5-20-OB-2090B | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-05-16 | PS5-99-02 | PS5 - Milestone A | 1 | Closed | 39 | 34 | MAY
T-507-5723 | PS5-08-UR-3346C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone D | 3 | To be completed |  | 25 | DECEMBER
T-671-5724 | PS5-12-IK-9740C | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone B | 1.1 | In progress |  | 34 | AUGUST
T-310-5725 | PS5-26-OB-5294C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-08-23 | PS5-06-02 | PS5 - Milestone E | 4 | Closed | 16 | 18 | AUGUST
T-598-5726 | PS5-65-IK-1051D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone F | 5 | In progress |  | 4 | NOVEMBER
T-785-5727 | PS5-93-UR-5600C | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | In progress |  | 21 | SEPTEMBER
T-531-5728 | PS5-30-OB-1911A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | On hold |  | 22 | AUGUST
T-233-5729 | PS5-07-OB-6103B | CQE01 - HV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | On hold |  | 6 | DECEMBER
T-643-5730 | PS5-29-OB-5846D | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone A | 1 | To be completed |  | 16 | OCTOBER
T-604-5731 | PS5-93-IK-9654D | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone D | 3 | On hold |  | 15 | NOVEMBER
T-157-5732 | PS5-43-OB-5599D | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-03-22 | PS5-61-07 | PS5 - Milestone C | 2 | Closed | 46 | 10 | MARCH
T-018-5733 | PS5-93-IK-1931B | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone D | 3 | On hold |  | 25 | DECEMBER
T-306-5734 | PS5-57-IK-5980C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-09-26 | PS5-07-04 | PS5 - Milestone G | 6 | Closed | 48 | 30 | SEPTEMBER
T-563-5735 | PS5-39-IK-1176B | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone C | 2 | In progress |  | 7 | SEPTEMBER
T-502-5736 | PS5-79-UR-6894A | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone E | 4 | To be completed |  | 16 | NOVEMBER
T-163-5737 | PS5-75-OB-5550D | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone B | 1.1 | To be completed |  | 29 | AUGUST
T-623-5738 | PS5-69-OB-7881A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone D | 3 | In progress |  | 10 | NOVEMBER
T-598-5739 | PS5-79-UR-6798D | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone C | 2 | To be completed |  | 44 | OCTOBER
T-878-5740 | PS5-64-UR-7111A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | To be completed |  | 22 | DECEMBER
T-533-5741 | PS5-33-UR-6767C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-04-14 | PS5-02-03 | PS5 - Milestone E | 4 | Closed | 25 | 41 | APRIL
T-786-5742 | PS5-31-IK-4072A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | To be completed |  | 6 | DECEMBER
T-755-5743 | PS5-90-UR-9349A | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-05-19 | PS5-01-03 | PS5 - Milestone I | 8 | Closed | 18 | 30 | MAY
T-809-5744 | PS5-97-OB-9860B | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | To be completed |  | 40 | OCTOBER
T-534-5745 | PS5-30-UR-2979B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone H | 7 | To be completed |  | 48 | DECEMBER
T-381-5746 | PS5-43-IK-9432A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-08-24 | PS5-62-02 | PS5 - Milestone F | 5 | Closed | 42 | 36 | AUGUST
T-557-5747 | PS5-67-OB-2384A | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | To be completed |  | 30 | SEPTEMBER
T-494-5748 | PS5-40-OB-5999A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | In progress |  | 45 | AUGUST
T-129-5749 | PS5-04-OB-1391D | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone D | 3 | In progress |  | 35 | AUGUST
T-384-5750 | PS5-15-OB-5782B | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone A | 1 | On hold |  | 22 | AUGUST
T-149-5751 | PS5-93-OB-4986B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone B | 1.1 | In progress |  | 16 | OCTOBER
T-253-5752 | PS5-25-UR-5555B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone A | 1 | On hold |  | 5 | OCTOBER
T-006-5753 | PS5-99-OB-8093D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-12 | PS5-60-04 | PS5 - Milestone C | 2 | Closed | 8 | 26 | JULY
T-643-5754 | PS5-42-UR-8100B | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone B | 1.1 | To be completed |  | 26 | DECEMBER
T-336-5755 | PS5-88-OB-3319C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone A | 1 | On hold |  | 47 | OCTOBER
T-225-5756 | PS5-61-IK-9784A | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | On hold |  | 19 | AUGUST
T-014-5757 | PS5-41-OB-3532C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone A | 1 | To be completed |  | 8 | DECEMBER
T-238-5758 | PS5-39-IK-4461B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone E | 4 | To be completed |  | 38 | DECEMBER
T-164-5759 | PS5-38-OB-6946A | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone H | 7 | To be completed |  | 41 | AUGUST
T-313-5760 | PS5-02-OB-6373B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-16 | PS5-60-01 | PS5 - Milestone E | 4 | Closed | 11 | 32 | APRIL
T-628-5761 | PS5-36-OB-2920D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-08-19 | PS5-61-01 | PS5 - Milestone I | 8 | Closed | 45 | 12 | AUGUST
T-854-5762 | PS5-09-IK-4665C | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | To be completed |  | 14 | AUGUST
T-685-5763 | PS5-47-OB-2925B | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone I | 8 | To be completed |  | 28 | NOVEMBER
T-511-5764 | PS5-25-OB-2676D | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-06-27 | PS5-99-01 | PS5 - Milestone B | 1.1 | Closed | 32 | 29 | JUNE
T-975-5765 | PS5-42-UR-7091D | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-06-25 | PS5-82-07 | PS5 - Milestone A | 1 | Closed | 33 | 9 | JUNE
T-007-5766 | PS5-63-IK-5077A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-12-15 | PS5-13-01 | PS5 - Milestone A | 1 | Closed | 17 | 6 | DECEMBER
T-579-5767 | PS5-63-IK-9517D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-06-20 | PS5-61-02 | PS5 - Milestone B | 1.1 | Closed | 26 | 40 | JUNE
T-120-5768 | PS5-95-IK-3182C | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone E | 4 | To be completed |  | 10 | OCTOBER
T-017-5769 | PS5-58-IK-8024B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | To be completed |  | 36 | AUGUST
T-491-5770 | PS5-46-OB-7457C | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-12-01 | PS5-04-02 | PS5 - Milestone H | 7 | Closed | 37 | 26 | DECEMBER
T-742-5771 | PS5-07-OB-1080A | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | To be completed |  | 8 | OCTOBER
T-737-5772 | PS5-18-OB-7987A | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-04-12 | PS5-07-02 | PS5 - Milestone G | 6 | Closed | 45 | 45 | APRIL
T-684-5773 | PS5-22-OB-9140C | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-11-14 | PS5-61-01 | PS5 - Milestone C | 2 | Closed | 12 | 44 | NOVEMBER
T-851-5774 | PS5-87-OB-6788C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone F | 5 | In progress |  | 7 | OCTOBER
T-806-5775 | PS5-69-OB-6213C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone E | 4 | In progress |  | 14 | OCTOBER
T-701-5776 | PS5-83-IK-1329B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone G | 6 | On hold |  | 33 | SEPTEMBER
T-518-5777 | PS5-78-OB-1226B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone F | 5 | On hold |  | 36 | OCTOBER
T-495-5778 | PS5-02-UR-5405B | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone H | 7 | To be completed |  | 35 | AUGUST
T-400-5779 | PS5-23-OB-7799C | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-08-26 | PS5-61-02 | PS5 - Milestone H | 7 | Closed | 30 | 4 | AUGUST
T-064-5780 | PS5-44-OB-4919A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | In progress |  | 7 | OCTOBER
T-358-5781 | PS5-03-OB-4828A | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone H | 7 | To be completed |  | 45 | NOVEMBER
T-957-5782 | PS5-53-OB-9623B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone E | 4 | In progress |  | 35 | DECEMBER
T-255-5783 | PS5-36-IK-8452A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | To be completed |  | 14 | NOVEMBER
T-765-5784 | PS5-44-IK-7288B | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone A | 1 | To be completed |  | 38 | OCTOBER
T-994-5785 | PS5-35-IK-1396A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-10-17 | PS5-01-01 | PS5 - Milestone G | 6 | Closed | 30 | 17 | OCTOBER
T-976-5786 | PS5-81-IK-3702B | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-11-14 | PS5-62-01 | PS5 - Milestone A | 1 | Closed | 32 | 10 | NOVEMBER
T-695-5787 | PS5-74-OB-2955D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-03-16 | PS5-07-01 | PS5 - Milestone G | 6 | Closed | 42 | 15 | MARCH
T-231-5788 | PS5-92-UR-9534C | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | To be completed |  | 42 | DECEMBER
T-070-5789 | PS5-80-IK-1193B | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone H | 7 | To be completed |  | 6 | AUGUST
T-422-5790 | PS5-51-OB-7941A | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone F | 5 | In progress |  | 5 | OCTOBER
T-469-5791 | PS5-96-IK-5597D | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone G | 6 | In progress |  | 30 | SEPTEMBER
T-569-5792 | PS5-83-IK-8582A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | In progress |  | 20 | SEPTEMBER
T-333-5793 | PS5-73-UR-1896A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | In progress |  | 29 | SEPTEMBER
T-136-5794 | PS5-56-OB-5468C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone C | 2 | To be completed |  | 41 | NOVEMBER
T-477-5795 | PS5-36-UR-5960B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone G | 6 | In progress |  | 25 | NOVEMBER
T-056-5796 | PS5-71-IK-4082C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-03-28 | PS5-63-01 | PS5 - Milestone B | 1.1 | Closed | 30 | 28 | MARCH
T-825-5797 | PS5-05-OB-9412A | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | To be completed |  | 41 | SEPTEMBER
T-132-5798 | PS5-53-UR-8448A | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone B | 1.1 | To be completed |  | 38 | OCTOBER
T-318-5799 | PS5-08-OB-2842C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone I | 8 | In progress |  | 9 | NOVEMBER
T-197-5800 | PS5-72-IK-3935C | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone E | 4 | To be completed |  | 28 | NOVEMBER
T-235-5801 | PS5-55-IK-6331D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone G | 6 | To be completed |  | 14 | SEPTEMBER
T-445-5802 | PS5-21-UR-2938D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone A | 1 | In progress |  | 45 | NOVEMBER
T-706-5803 | PS5-74-UR-6288D | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone C | 2 | In progress |  | 13 | DECEMBER
T-781-5804 | PS5-40-UR-6718C | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-10-18 | PS5-08-02 | PS5 - Milestone B | 1.1 | Closed | 41 | 10 | OCTOBER
T-044-5805 | PS5-65-UR-3087C | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone H | 7 | In progress |  | 8 | DECEMBER
T-150-5806 | PS5-18-UR-5854A | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-08-11 | PS5-06-02 | PS5 - Milestone G | 6 | Closed | 9 | 45 | AUGUST
T-039-5807 | PS5-90-UR-7779A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone I | 8 | To be completed |  | 42 | OCTOBER
T-357-5808 | PS5-27-OB-5787B | CQE01 - HV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | To be completed |  | 7 | DECEMBER
T-436-5809 | PS5-16-UR-9241C | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone F | 5 | To be completed |  | 6 | OCTOBER
T-899-5810 | PS5-80-OB-9146B | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone I | 8 | On hold |  | 41 | AUGUST
T-153-5811 | PS5-54-IK-3238A | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone G | 6 | In progress |  | 43 | OCTOBER
T-987-5812 | PS5-14-UR-8108A | CQH02 - AHU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-02-16 | PS5-13-01 | PS5 - Milestone E | 4 | Closed | 32 | 28 | FEBRUARY
T-377-5813 | PS5-94-IK-9770D | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | To be completed |  | 37 | DECEMBER
T-770-5814 | PS5-98-OB-8804D | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | In progress |  | 36 | NOVEMBER
T-591-5815 | PS5-85-IK-1713A | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | To be completed |  | 47 | DECEMBER
T-828-5816 | PS5-53-OB-2033D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone H | 7 | To be completed |  | 12 | OCTOBER
T-687-5817 | PS5-08-OB-2971C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-04-06 | PS5-63-04 | PS5 - Milestone I | 8 | Closed | 7 | 10 | APRIL
T-834-5818 | PS5-31-UR-1459B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-14 | PS5-60-07 | PS5 - Milestone I | 8 | Closed | 30 | 36 | APRIL
T-312-5819 | PS5-74-OB-6481B | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-01-25 | PS5-06-01 | PS5 - Milestone G | 6 | Closed | 32 | 26 | JANUARY
T-534-5820 | PS5-85-OB-8551D | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-03-01 | PS5-12-02 | PS5 - Milestone C | 2 | Closed | 30 | 7 | MARCH
T-766-5821 | PS5-20-IK-4329C | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone H | 7 | In progress |  | 15 | DECEMBER
T-721-5822 | PS5-66-IK-5151B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-07-12 | PS5-06-01 | PS5 - Milestone F | 5 | Closed | 48 | 24 | JULY
T-059-5823 | PS5-73-IK-2125A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone F | 5 | On hold |  | 14 | AUGUST
T-991-5824 | PS5-47-OB-8767B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-09-02 | PS5-06-01 | PS5 - Milestone A | 1 | Closed | 25 | 12 | SEPTEMBER
T-821-5825 | PS5-22-IK-7049C | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone E | 4 | To be completed |  | 16 | NOVEMBER
T-917-5826 | PS5-89-OB-1276D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-02-23 | PS5-08-02 | PS5 - Milestone B | 1.1 | Closed | 11 | 9 | FEBRUARY
T-372-5827 | PS5-39-OB-1214C | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone A | 1 | To be completed |  | 38 | DECEMBER
T-228-5828 | PS5-64-IK-4428C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | In progress |  | 33 | SEPTEMBER
T-467-5829 | PS5-84-OB-3566C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone F | 5 | To be completed |  | 47 | OCTOBER
T-484-5830 | PS5-90-IK-2978D | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-04-11 | PS5-61-07 | PS5 - Milestone D | 3 | Closed | 40 | 33 | APRIL
T-417-5831 | PS5-63-UR-7668C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone I | 8 | In progress |  | 33 | NOVEMBER
T-166-5832 | PS5-75-IK-5574B | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-08-18 | PS5-11-01 | PS5 - Milestone H | 7 | Closed | 36 | 43 | AUGUST
T-673-5833 | PS5-33-UR-5008C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-09-04 | PS5-60-04 | PS5 - Milestone F | 5 | Closed | 22 | 27 | SEPTEMBER
T-173-5834 | PS5-70-UR-6827D | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone E | 4 | On hold |  | 41 | DECEMBER
T-411-5835 | PS5-45-UR-5853A | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-12-28 | PS5-03-01 | PS5 - Milestone A | 1 | Closed | 46 | 23 | DECEMBER
T-890-5836 | PS5-65-UR-9376A | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-03-11 | PS5-01-09 | PS5 - Milestone H | 7 | Closed | 28 | 39 | MARCH
T-492-5837 | PS5-53-OB-8311C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-04-13 | PS5-99-01 | PS5 - Milestone F | 5 | Closed | 36 | 45 | APRIL
T-130-5838 | PS5-36-OB-1572C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone D | 3 | In progress |  | 28 | SEPTEMBER
T-466-5839 | PS5-35-UR-4729C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-11-17 | PS5-02-01 | PS5 - Milestone H | 7 | Closed | 16 | 47 | NOVEMBER
T-464-5840 | PS5-60-UR-3007B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-03-27 | PS5-82-01 | PS5 - Milestone A | 1 | Closed | 19 | 48 | MARCH
T-974-5841 | PS5-73-OB-4355B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone C | 2 | In progress |  | 35 | OCTOBER
T-555-5842 | PS5-10-IK-3576B | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone B | 1.1 | To be completed |  | 14 | SEPTEMBER
T-011-5843 | PS5-48-UR-1321B | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-06-19 | PS5-82-02 | PS5 - Milestone I | 8 | Closed | 30 | 44 | JUNE
T-628-5844 | PS5-58-OB-9194A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone F | 5 | In progress |  | 19 | SEPTEMBER
T-734-5845 | PS5-53-IK-5905B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone A | 1 | In progress |  | 40 | OCTOBER
T-956-5846 | PS5-08-UR-4821A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone E | 4 | In progress |  | 39 | NOVEMBER
T-840-5847 | PS5-14-OB-2207C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-11-20 | PS5-04-01 | PS5 - Milestone H | 7 | Closed | 11 | 30 | NOVEMBER
T-498-5848 | PS5-87-OB-4555D | CQP02 - Valve Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone A | 1 | To be completed |  | 28 | DECEMBER
T-449-5849 | PS5-52-IK-6022B | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | To be completed |  | 11 | SEPTEMBER
T-443-5850 | PS5-83-OB-2080A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-08-01 | PS5-10-02 | PS5 - Milestone I | 8 | Closed | 28 | 38 | AUGUST
T-551-5851 | PS5-11-IK-2415A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-08-20 | PS5-03-23 | PS5 - Milestone B | 1.1 | Closed | 35 | 15 | AUGUST
T-154-5852 | PS5-34-OB-7772C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-10-25 | PS5-99-01 | PS5 - Milestone C | 2 | Closed | 16 | 37 | OCTOBER
T-986-5853 | PS5-50-OB-1740C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone A | 1 | In progress |  | 40 | AUGUST
T-503-5854 | PS5-84-OB-7837A | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone A | 1 | To be completed |  | 45 | NOVEMBER
T-946-5855 | PS5-06-UR-4528C | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | To be completed |  | 17 | NOVEMBER
T-276-5856 | PS5-43-OB-1487B | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | In progress |  | 36 | SEPTEMBER
T-731-5857 | PS5-18-OB-1438D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-10-25 | PS5-60-01 | PS5 - Milestone E | 4 | Closed | 5 | 36 | OCTOBER
T-392-5858 | PS5-78-IK-7211A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-12-08 | PS5-04-03 | PS5 - Milestone A | 1 | Closed | 21 | 10 | DECEMBER
T-020-5859 | PS5-23-UR-6567C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | To be completed |  | 20 | OCTOBER
T-248-5860 | PS5-01-OB-9227B | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | To be completed |  | 20 | AUGUST
T-783-5861 | PS5-57-IK-9655B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | In progress |  | 8 | DECEMBER
T-215-5862 | PS5-70-IK-5909D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone H | 7 | To be completed |  | 36 | AUGUST
T-495-5863 | PS5-53-IK-8299A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-05-19 | PS5-60-07 | PS5 - Milestone F | 5 | Closed | 20 | 41 | MAY
T-822-5864 | PS5-95-OB-8635D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-02-10 | PS5-11-03 | PS5 - Milestone G | 6 | Closed | 11 | 15 | FEBRUARY
T-229-5865 | PS5-93-OB-5356B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | To be completed |  | 25 | AUGUST
T-835-5866 | PS5-64-IK-9219D | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-09-12 | PS5-10-01 | PS5 - Milestone D | 3 | Closed | 36 | 15 | SEPTEMBER
T-719-5867 | PS5-77-OB-2908D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone I | 8 | To be completed |  | 38 | SEPTEMBER
T-630-5868 | PS5-36-OB-6370B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-07-13 | PS5-03-02 | PS5 - Milestone F | 5 | Closed | 34 | 36 | JULY
T-919-5869 | PS5-73-OB-8681A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | To be completed |  | 7 | AUGUST
T-360-5870 | PS5-04-OB-1720A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | To be completed |  | 24 | SEPTEMBER
T-652-5871 | PS5-72-UR-4211A | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | To be completed |  | 29 | AUGUST
T-682-5872 | PS5-87-OB-4366C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone F | 5 | To be completed |  | 28 | OCTOBER
T-221-5873 | PS5-02-IK-1466B | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-07-16 | PS5-03-02 | PS5 - Milestone G | 6 | Closed | 6 | 26 | JULY
T-725-5874 | PS5-86-OB-2121B | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | In progress |  | 19 | DECEMBER
T-527-5875 | PS5-07-UR-1436A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone H | 7 | In progress |  | 12 | SEPTEMBER
T-730-5876 | PS5-32-IK-3998C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-01-09 | PS5-12-01 | PS5 - Milestone H | 7 | Closed | 42 | 32 | JANUARY
T-549-5877 | PS5-21-IK-6211C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone F | 5 | To be completed |  | 43 | SEPTEMBER
T-765-5878 | PS5-53-OB-2986A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone H | 7 | On hold |  | 21 | DECEMBER
T-907-5879 | PS5-09-IK-6408D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-04-25 | PS5-01-03 | PS5 - Milestone G | 6 | Closed | 9 | 19 | APRIL
T-564-5880 | PS5-11-UR-7379D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone E | 4 | To be completed |  | 40 | AUGUST
T-166-5881 | PS5-61-OB-8519C | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone G | 6 | To be completed |  | 40 | OCTOBER
T-915-5882 | PS5-78-IK-3712A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone D | 3 | On hold |  | 41 | DECEMBER
T-933-5883 | PS5-75-OB-1015C | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-03-07 | PS5-82-01 | PS5 - Milestone C | 2 | Closed | 4 | 46 | MARCH
T-975-5884 | PS5-03-OB-5535C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-10-09 | PS5-05-03 | PS5 - Milestone A | 1 | Closed | 4 | 40 | OCTOBER
T-742-5885 | PS5-66-OB-2961B | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-04-06 | PS5-10-04 | PS5 - Milestone E | 4 | Closed | 9 | 17 | APRIL
T-296-5886 | PS5-23-IK-2501D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-02-02 | PS5-03-02 | PS5 - Milestone F | 5 | Closed | 9 | 15 | FEBRUARY
T-836-5887 | PS5-57-IK-4157B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-07-19 | PS5-82-02 | PS5 - Milestone D | 3 | Closed | 39 | 11 | JULY
T-345-5888 | PS5-22-OB-8865C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-04-03 | PS5-09-01 | PS5 - Milestone I | 8 | Closed | 42 | 16 | APRIL
T-377-5889 | PS5-03-IK-9181B | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone C | 2 | On hold |  | 43 | SEPTEMBER
T-703-5890 | PS5-78-IK-8206B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone F | 5 | On hold |  | 29 | NOVEMBER
T-706-5891 | PS5-06-IK-6098B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone G | 6 | On hold |  | 13 | OCTOBER
T-777-5892 | PS5-83-OB-9321D | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-04-26 | PS5-07-03 | PS5 - Milestone G | 6 | Closed | 29 | 9 | APRIL
T-688-5893 | PS5-41-IK-4869A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-07-07 | PS5-63-01 | PS5 - Milestone B | 1.1 | Closed | 28 | 39 | JULY
T-058-5894 | PS5-97-OB-8785C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-03-09 | PS5-01-08 | PS5 - Milestone E | 4 | Closed | 26 | 24 | MARCH
T-420-5895 | PS5-41-IK-7547A | CQX04 - Painting & Coating | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | In progress |  | 26 | OCTOBER
T-754-5896 | PS5-34-OB-5370A | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone H | 7 | In progress |  | 22 | OCTOBER
T-059-5897 | PS5-97-IK-6589D | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-11-16 | PS5-10-05 | PS5 - Milestone B | 1.1 | Closed | 34 | 44 | NOVEMBER
T-187-5898 | PS5-64-OB-4225A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | To be completed |  | 18 | AUGUST
T-384-5899 | PS5-08-OB-6515B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone B | 1.1 | To be completed |  | 4 | AUGUST
T-316-5900 | PS5-24-OB-3550C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone B | 1.1 | To be completed |  | 42 | AUGUST
T-209-5901 | PS5-37-OB-4161C | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-04-27 | PS5-01-02 | PS5 - Milestone G | 6 | Closed | 37 | 27 | APRIL
T-365-5902 | PS5-64-OB-1885D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone H | 7 | To be completed |  | 20 | SEPTEMBER
T-159-5903 | PS5-63-UR-4006B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone C | 2 | In progress |  | 12 | NOVEMBER
T-174-5904 | PS5-54-UR-3472B | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone H | 7 | On hold |  | 45 | OCTOBER
T-050-5905 | PS5-57-OB-4733B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-05-18 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 39 | 6 | MAY
T-574-5906 | PS5-03-OB-7907A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-02-02 | PS5-09-01 | PS5 - Milestone I | 8 | Closed | 35 | 29 | FEBRUARY
T-654-5907 | PS5-79-OB-1211C | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-06-14 | PS5-11-01 | PS5 - Milestone H | 7 | Closed | 11 | 6 | JUNE
T-843-5908 | PS5-17-OB-5554A | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-12-23 | PS5-11-02 | PS5 - Milestone A | 1 | Closed | 27 | 34 | DECEMBER
T-024-5909 | PS5-07-OB-4982D | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-12-01 | PS5-06-01 | PS5 - Milestone H | 7 | Closed | 45 | 14 | DECEMBER
T-888-5910 | PS5-46-UR-5016B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-04-26 | PS5-10-04 | PS5 - Milestone I | 8 | Closed | 11 | 35 | APRIL
T-206-5911 | PS5-36-IK-6211C | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | To be completed |  | 25 | OCTOBER
T-903-5912 | PS5-01-OB-7734A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone G | 6 | On hold |  | 21 | AUGUST
T-715-5913 | PS5-97-UR-7815C | CQP04 - Hydrotest | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-05-01 | PS5-02-02 | PS5 - Milestone G | 6 | Closed | 21 | 13 | MAY
T-173-5914 | PS5-44-OB-7771B | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone B | 1.1 | To be completed |  | 7 | SEPTEMBER
T-142-5915 | PS5-51-OB-9580D | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-09-04 | PS5-08-01 | PS5 - Milestone E | 4 | Closed | 48 | 4 | SEPTEMBER
T-237-5916 | PS5-64-IK-5305A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone G | 6 | To be completed |  | 39 | OCTOBER
T-299-5917 | PS5-83-OB-9077A | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone F | 5 | To be completed |  | 22 | OCTOBER
T-276-5918 | PS5-19-IK-5144B | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-05-03 | PS5-11-02 | PS5 - Milestone A | 1 | Closed | 11 | 4 | MAY
T-422-5919 | PS5-49-UR-9612D | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone I | 8 | In progress |  | 28 | AUGUST
T-121-5920 | PS5-15-UR-1786A | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-02-16 | PS5-03-03 | PS5 - Milestone H | 7 | Closed | 12 | 31 | FEBRUARY
T-363-5921 | PS5-54-IK-9164B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | To be completed |  | 16 | SEPTEMBER
T-347-5922 | PS5-45-UR-7849A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-09-01 | PS5-61-07 | PS5 - Milestone B | 1.1 | Closed | 11 | 18 | SEPTEMBER
T-487-5923 | PS5-20-OB-1280C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone B | 1.1 | In progress |  | 40 | NOVEMBER
T-081-5924 | PS5-88-OB-8248D | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-06-20 | PS5-01-08 | PS5 - Milestone I | 8 | Closed | 36 | 9 | JUNE
T-804-5925 | PS5-59-IK-5295B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-02-16 | PS5-10-03 | PS5 - Milestone D | 3 | Closed | 13 | 6 | FEBRUARY
T-881-5926 | PS5-36-OB-6559A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-11-20 | PS5-01-08 | PS5 - Milestone H | 7 | Closed | 17 | 32 | NOVEMBER
T-484-5927 | PS5-16-OB-4950B | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone B | 1.1 | To be completed |  | 45 | OCTOBER
T-267-5928 | PS5-80-OB-2615A | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone B | 1.1 | To be completed |  | 36 | NOVEMBER
T-083-5929 | PS5-92-OB-5518B | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-09-23 | PS5-63-01 | PS5 - Milestone F | 5 | Closed | 13 | 25 | SEPTEMBER
T-715-5930 | PS5-04-OB-7553B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-03-04 | PS5-61-02 | PS5 - Milestone I | 8 | Closed | 28 | 48 | MARCH
T-349-5931 | PS5-82-OB-6720C | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone E | 4 | To be completed |  | 19 | NOVEMBER
T-423-5932 | PS5-38-IK-2786B | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone H | 7 | To be completed |  | 20 | SEPTEMBER
T-747-5933 | PS5-91-UR-3647C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | To be completed |  | 25 | OCTOBER
T-223-5934 | PS5-23-OB-3056B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone I | 8 | To be completed |  | 40 | OCTOBER
T-275-5935 | PS5-65-OB-6207C | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone C | 2 | To be completed |  | 21 | SEPTEMBER
T-923-5936 | PS5-46-IK-2057A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-03-11 | PS5-05-01 | PS5 - Milestone G | 6 | Closed | 48 | 21 | MARCH
T-481-5937 | PS5-85-IK-9430B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-07-04 | PS5-99-03 | PS5 - Milestone C | 2 | Closed | 28 | 18 | JULY
T-371-5938 | PS5-85-OB-4860A | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | In progress |  | 16 | DECEMBER
T-705-5939 | PS5-40-UR-2053D | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | On hold |  | 27 | DECEMBER
T-380-5940 | PS5-64-OB-9498A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone D | 3 | To be completed |  | 39 | DECEMBER
T-580-5941 | PS5-42-UR-8570B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | In progress |  | 5 | NOVEMBER
T-345-5942 | PS5-40-OB-3668C | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-11-16 | PS5-62-01 | PS5 - Milestone B | 1.1 | Closed | 30 | 32 | NOVEMBER
T-647-5943 | PS5-05-OB-7284C | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone C | 2 | On hold |  | 21 | OCTOBER
T-444-5944 | PS5-79-UR-4850B | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone G | 6 | On hold |  | 34 | SEPTEMBER
T-776-5945 | PS5-62-UR-6626D | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone H | 7 | In progress |  | 10 | OCTOBER
T-720-5946 | PS5-31-OB-7697C | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | To be completed |  | 46 | SEPTEMBER
T-401-5947 | PS5-70-OB-1010B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-04-10 | PS5-61-01 | PS5 - Milestone A | 1 | Closed | 20 | 32 | APRIL
T-816-5948 | PS5-98-IK-2583A | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-08-03 | PS5-03-23 | PS5 - Milestone H | 7 | Closed | 5 | 37 | AUGUST
T-356-5949 | PS5-14-UR-8925B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone C | 2 | In progress |  | 10 | DECEMBER
T-114-5950 | PS5-79-UR-9027B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone I | 8 | In progress |  | 48 | SEPTEMBER
T-592-5951 | PS5-23-OB-9475B | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone D | 3 | In progress |  | 7 | OCTOBER
T-922-5952 | PS5-91-UR-9362C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone I | 8 | To be completed |  | 7 | DECEMBER
T-584-5953 | PS5-18-IK-5104B | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone F | 5 | In progress |  | 10 | NOVEMBER
T-875-5954 | PS5-53-OB-7849A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-04-19 | PS5-04-01 | PS5 - Milestone I | 8 | Closed | 14 | 33 | APRIL
T-214-5955 | PS5-78-IK-8465A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone F | 5 | In progress |  | 20 | DECEMBER
T-347-5956 | PS5-08-UR-6464A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-04-03 | PS5-01-02 | PS5 - Milestone E | 4 | Closed | 22 | 35 | APRIL
T-275-5957 | PS5-42-OB-1578C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone B | 1.1 | In progress |  | 20 | DECEMBER
T-879-5958 | PS5-23-OB-7597B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone G | 6 | To be completed |  | 41 | DECEMBER
T-341-5959 | PS5-49-OB-2754C | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone I | 8 | To be completed |  | 42 | AUGUST
T-917-5960 | PS5-90-OB-7620B | CQM04 - Vessel | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-10-21 | PS5-10-02 | PS5 - Milestone E | 4 | Closed | 37 | 25 | OCTOBER
T-278-5961 | PS5-51-OB-9039A | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone F | 5 | In progress |  | 39 | AUGUST
T-651-5962 | PS5-11-UR-5901D | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | To be completed |  | 19 | OCTOBER
T-270-5963 | PS5-25-IK-9756A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-08-24 | PS5-07-01 | PS5 - Milestone B | 1.1 | Closed | 38 | 21 | AUGUST
T-749-5964 | PS5-96-OB-2820D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-10-19 | PS5-10-06 | PS5 - Milestone D | 3 | Closed | 9 | 26 | OCTOBER
T-642-5965 | PS5-07-OB-9478B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone C | 2 | On hold |  | 27 | SEPTEMBER
T-070-5966 | PS5-36-OB-9049C | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-04-25 | PS5-10-03 | PS5 - Milestone H | 7 | Closed | 47 | 14 | APRIL
T-672-5967 | PS5-11-OB-5725D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | In progress |  | 7 | AUGUST
T-934-5968 | PS5-43-IK-4679C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone G | 6 | In progress |  | 4 | AUGUST
T-937-5969 | PS5-77-IK-4770D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone A | 1 | In progress |  | 17 | SEPTEMBER
T-146-5970 | PS5-38-OB-4013B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-03-23 | PS5-01-04 | PS5 - Milestone F | 5 | Closed | 21 | 42 | MARCH
T-795-5971 | PS5-14-OB-1776C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone A | 1 | To be completed |  | 38 | NOVEMBER
T-667-5972 | PS5-52-OB-4469D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-10-15 | PS5-11-01 | PS5 - Milestone E | 4 | Closed | 20 | 39 | OCTOBER
T-486-5973 | PS5-57-IK-7865A | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone G | 6 | To be completed |  | 8 | AUGUST
T-526-5974 | PS5-90-UR-1127C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-08-17 | PS5-60-01 | PS5 - Milestone G | 6 | Closed | 45 | 16 | AUGUST
T-136-5975 | PS5-05-OB-2902B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | To be completed |  | 39 | NOVEMBER
T-648-5976 | PS5-16-OB-1729D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone D | 3 | In progress |  | 20 | AUGUST
T-802-5977 | PS5-38-UR-2945C | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-11-20 | PS5-08-02 | PS5 - Milestone B | 1.1 | Closed | 6 | 30 | NOVEMBER
T-326-5978 | PS5-47-UR-1059B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | To be completed |  | 31 | SEPTEMBER
T-817-5979 | PS5-20-IK-5820A | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-04-20 | PS5-07-04 | PS5 - Milestone D | 3 | Closed | 39 | 22 | APRIL
T-969-5980 | PS5-75-OB-6326B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-10-24 | PS5-01-01 | PS5 - Milestone E | 4 | Closed | 37 | 24 | OCTOBER
T-204-5981 | PS5-66-IK-3884D | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone E | 4 | In progress |  | 18 | NOVEMBER
T-736-5982 | PS5-14-OB-7976D | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone A | 1 | In progress |  | 15 | SEPTEMBER
T-009-5983 | PS5-76-OB-2577D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone D | 3 | To be completed |  | 25 | AUGUST
T-402-5984 | PS5-03-IK-3867B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-08-15 | PS5-06-03 | PS5 - Milestone F | 5 | Closed | 33 | 29 | AUGUST
T-797-5985 | PS5-39-UR-6143C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | To be completed |  | 12 | AUGUST
T-375-5986 | PS5-62-OB-2355B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone E | 4 | On hold |  | 45 | NOVEMBER
T-308-5987 | PS5-24-UR-5460B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-03-15 | PS5-10-05 | PS5 - Milestone D | 3 | Closed | 31 | 9 | MARCH
T-939-5988 | PS5-61-IK-6910A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone A | 1 | On hold |  | 44 | NOVEMBER
T-345-5989 | PS5-14-OB-8422A | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone B | 1.1 | In progress |  | 32 | NOVEMBER
T-427-5990 | PS5-74-UR-1486C | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone G | 6 | To be completed |  | 45 | NOVEMBER
T-978-5991 | PS5-24-OB-6702A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-06-21 | PS5-12-01 | PS5 - Milestone I | 8 | Closed | 24 | 13 | JUNE
T-572-5992 | PS5-16-UR-8934B | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-09-08 | PS5-13-01 | PS5 - Milestone B | 1.1 | Closed | 16 | 9 | SEPTEMBER
T-419-5993 | PS5-45-OB-1068A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | In progress |  | 10 | OCTOBER
T-482-5994 | PS5-85-UR-8378A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone C | 2 | To be completed |  | 12 | OCTOBER
T-994-5995 | PS5-60-OB-8455C | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone A | 1 | To be completed |  | 7 | NOVEMBER
T-612-5996 | PS5-35-OB-5666A | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone C | 2 | To be completed |  | 25 | DECEMBER
T-178-5997 | PS5-61-IK-4343B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone H | 7 | To be completed |  | 35 | DECEMBER
T-993-5998 | PS5-55-OB-1212A | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone G | 6 | To be completed |  | 42 | DECEMBER
T-578-5999 | PS5-20-OB-3942A | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-10-14 | PS5-07-01 | PS5 - Milestone H | 7 | Closed | 23 | 31 | OCTOBER
T-726-6000 | PS5-78-IK-1305B | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone C | 2 | To be completed |  | 46 | OCTOBER
T-838-6001 | PS5-71-OB-4355A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-01-20 | PS5-11-02 | PS5 - Milestone C | 2 | Closed | 31 | 30 | JANUARY
T-682-6002 | PS5-32-UR-3111A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-07-02 | PS5-05-03 | PS5 - Milestone I | 8 | Closed | 17 | 19 | JULY
T-331-6003 | PS5-94-IK-7567C | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-06-09 | PS5-03-03 | PS5 - Milestone H | 7 | Closed | 19 | 10 | JUNE
T-774-6004 | PS5-47-OB-6572B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-07-16 | PS5-01-04 | PS5 - Milestone A | 1 | Closed | 16 | 10 | JULY
T-425-6005 | PS5-76-OB-8549A | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone G | 6 | On hold |  | 35 | SEPTEMBER
T-404-6006 | PS5-46-OB-7976C | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | On hold |  | 35 | SEPTEMBER
T-133-6007 | PS5-82-IK-9023A | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-01-07 | PS5-11-03 | PS5 - Milestone G | 6 | Closed | 15 | 47 | JANUARY
T-120-6008 | PS5-09-UR-1586D | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-04-24 | PS5-07-04 | PS5 - Milestone D | 3 | Closed | 12 | 24 | APRIL
T-086-6009 | PS5-56-IK-7897B | CQE02 - LV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-12-24 | PS5-12-02 | PS5 - Milestone F | 5 | Closed | 6 | 35 | DECEMBER
T-177-6010 | PS5-71-UR-3412A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone A | 1 | In progress |  | 30 | SEPTEMBER
T-021-6011 | PS5-20-IK-6742B | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-05-21 | PS5-05-02 | PS5 - Milestone E | 4 | Closed | 16 | 45 | MAY
T-016-6012 | PS5-82-OB-8914C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-06-18 | PS5-61-01 | PS5 - Milestone C | 2 | Closed | 43 | 10 | JUNE
T-051-6013 | PS5-07-OB-2428A | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone C | 2 | To be completed |  | 10 | OCTOBER
T-787-6014 | PS5-06-OB-1938A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-07-10 | PS5-01-08 | PS5 - Milestone E | 4 | Closed | 6 | 14 | JULY
T-165-6015 | PS5-35-OB-7431A | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone C | 2 | To be completed |  | 8 | NOVEMBER
T-581-6016 | PS5-14-IK-1415B | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone I | 8 | To be completed |  | 29 | OCTOBER
T-564-6017 | PS5-98-IK-8091D | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-08-13 | PS5-01-09 | PS5 - Milestone F | 5 | Closed | 38 | 5 | AUGUST
T-499-6018 | PS5-02-OB-6780B | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-01-15 | PS5-03-03 | PS5 - Milestone H | 7 | Closed | 15 | 16 | JANUARY
T-923-6019 | PS5-42-OB-3490A | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-07-07 | PS5-06-02 | PS5 - Milestone E | 4 | Closed | 16 | 6 | JULY
T-709-6020 | PS5-20-OB-2075C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | To be completed |  | 29 | NOVEMBER
T-617-6021 | PS5-90-UR-8856D | CQM03 - Heat Exchanger | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-11 | PS5-60-10 | PS5 - Milestone B | 1.1 | Closed | 42 | 44 | JUNE
T-126-6022 | PS5-90-UR-1886B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-01-20 | PS5-60-04 | PS5 - Milestone E | 4 | Closed | 28 | 47 | JANUARY
T-934-6023 | PS5-73-IK-5979A | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-05-08 | PS5-10-05 | PS5 - Milestone C | 2 | Closed | 16 | 20 | MAY
T-095-6024 | PS5-81-UR-6934C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-03-16 | PS5-08-02 | PS5 - Milestone D | 3 | Closed | 46 | 26 | MARCH
T-205-6025 | PS5-05-IK-3814C | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone F | 5 | In progress |  | 24 | OCTOBER
T-636-6026 | PS5-11-IK-9836D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | In progress |  | 17 | SEPTEMBER
T-463-6027 | PS5-20-IK-2853B | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-05-09 | PS5-12-01 | PS5 - Milestone A | 1 | Closed | 14 | 34 | MAY
T-024-6028 | PS5-07-OB-8444B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | On hold |  | 11 | DECEMBER
T-830-6029 | PS5-31-IK-3886C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-06-04 | PS5-01-06 | PS5 - Milestone F | 5 | Closed | 12 | 27 | JUNE
T-842-6030 | PS5-55-OB-3967D | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone I | 8 | To be completed |  | 35 | NOVEMBER
T-489-6031 | PS5-65-OB-7071D | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone D | 3 | In progress |  | 35 | DECEMBER
T-569-6032 | PS5-73-UR-3731B | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-02-14 | PS5-06-03 | PS5 - Milestone C | 2 | Closed | 17 | 41 | FEBRUARY
T-475-6033 | PS5-85-IK-9588B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-10-01 | PS5-05-01 | PS5 - Milestone G | 6 | Closed | 17 | 18 | OCTOBER
T-625-6034 | PS5-06-OB-6401B | CQP01 - Pipe Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone C | 2 | On hold |  | 18 | AUGUST
T-475-6035 | PS5-71-UR-6236D | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone D | 3 | In progress |  | 20 | DECEMBER
T-106-6036 | PS5-56-OB-7859B | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone A | 1 | To be completed |  | 43 | DECEMBER
T-060-6037 | PS5-30-OB-3772D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-12-04 | PS5-05-01 | PS5 - Milestone F | 5 | Closed | 47 | 26 | DECEMBER
T-576-6038 | PS5-40-OB-1173B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone E | 4 | In progress |  | 8 | SEPTEMBER
T-953-6039 | PS5-42-UR-6053D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-11-16 | PS5-82-07 | PS5 - Milestone F | 5 | Closed | 15 | 19 | NOVEMBER
T-589-6040 | PS5-16-OB-7870A | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone D | 3 | To be completed |  | 38 | DECEMBER
T-899-6041 | PS5-80-OB-6085A | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-02-27 | PS5-04-02 | PS5 - Milestone D | 3 | Closed | 8 | 20 | FEBRUARY
T-933-6042 | PS5-31-UR-8930B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone A | 1 | On hold |  | 23 | AUGUST
T-995-6043 | PS5-21-OB-2727B | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | To be completed |  | 17 | NOVEMBER
T-451-6044 | PS5-46-OB-1544C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone I | 8 | To be completed |  | 24 | AUGUST
T-388-6045 | PS5-43-UR-6702C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone B | 1.1 | To be completed |  | 8 | SEPTEMBER
T-898-6046 | PS5-80-IK-9243A | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone B | 1.1 | In progress |  | 16 | SEPTEMBER
T-701-6047 | PS5-60-IK-2293D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone E | 4 | In progress |  | 7 | AUGUST
T-623-6048 | PS5-67-OB-2391A | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone C | 2 | In progress |  | 16 | NOVEMBER
T-748-6049 | PS5-88-UR-7462C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | On hold |  | 19 | AUGUST
T-671-6050 | PS5-94-IK-3619A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | On hold |  | 10 | OCTOBER
T-946-6051 | PS5-16-UR-8639A | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | To be completed |  | 38 | DECEMBER
T-651-6052 | PS5-16-IK-6059B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone H | 7 | In progress |  | 9 | OCTOBER
T-354-6053 | PS5-61-OB-7370D | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-11-28 | PS5-82-01 | PS5 - Milestone D | 3 | Closed | 14 | 7 | NOVEMBER
T-627-6054 | PS5-93-OB-2897C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone D | 3 | On hold |  | 18 | DECEMBER
T-644-6055 | PS5-71-IK-4999C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-12-25 | PS5-01-02 | PS5 - Milestone G | 6 | Closed | 14 | 21 | DECEMBER
T-925-6056 | PS5-51-OB-7723A | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone B | 1.1 | To be completed |  | 29 | DECEMBER
T-637-6057 | PS5-94-UR-7008B | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-02-09 | PS5-63-01 | PS5 - Milestone G | 6 | Closed | 9 | 29 | FEBRUARY
T-345-6058 | PS5-66-OB-8458C | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | To be completed |  | 17 | DECEMBER
T-623-6059 | PS5-82-OB-6476B | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-05 | PS5-60-04 | PS5 - Milestone D | 3 | Closed | 8 | 26 | JUNE
T-755-6060 | PS5-45-IK-4518C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone A | 1 | To be completed |  | 43 | NOVEMBER
T-220-6061 | PS5-19-OB-2635B | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone G | 6 | In progress |  | 23 | NOVEMBER
T-816-6062 | PS5-17-OB-2450D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone D | 3 | To be completed |  | 19 | AUGUST
T-107-6063 | PS5-80-UR-6120B | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-11-02 | PS5-03-01 | PS5 - Milestone G | 6 | Closed | 34 | 6 | NOVEMBER
T-058-6064 | PS5-45-OB-2166A | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone F | 5 | In progress |  | 5 | OCTOBER
T-043-6065 | PS5-28-UR-9398A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-12-18 | PS5-11-01 | PS5 - Milestone D | 3 | Closed | 14 | 42 | DECEMBER
T-747-6066 | PS5-24-IK-4020C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone D | 3 | On hold |  | 18 | NOVEMBER
T-926-6067 | PS5-27-UR-4813A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-07-10 | PS5-07-02 | PS5 - Milestone C | 2 | Closed | 39 | 42 | JULY
T-932-6068 | PS5-44-OB-1091B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-11-11 | PS5-07-02 | PS5 - Milestone D | 3 | Closed | 32 | 28 | NOVEMBER
T-580-6069 | PS5-10-OB-1598D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone C | 2 | To be completed |  | 44 | OCTOBER
T-857-6070 | PS5-51-UR-6022C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-12-26 | PS5-07-02 | PS5 - Milestone I | 8 | Closed | 24 | 4 | DECEMBER
T-568-6071 | PS5-60-IK-3608D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone H | 7 | In progress |  | 45 | AUGUST
T-458-6072 | PS5-87-UR-3215A | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone C | 2 | To be completed |  | 23 | SEPTEMBER
T-287-6073 | PS5-40-OB-7035B | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-12-02 | PS5-63-01 | PS5 - Milestone I | 8 | Closed | 5 | 32 | DECEMBER
T-688-6074 | PS5-09-OB-7100C | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-09-28 | PS5-05-02 | PS5 - Milestone H | 7 | Closed | 12 | 44 | SEPTEMBER
T-255-6075 | PS5-98-IK-8989A | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone E | 4 | To be completed |  | 34 | AUGUST
T-703-6076 | PS5-44-IK-9612A | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone B | 1.1 | To be completed |  | 14 | DECEMBER
T-454-6077 | PS5-52-UR-2448B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-08-14 | PS5-01-05 | PS5 - Milestone A | 1 | Closed | 23 | 39 | AUGUST
T-672-6078 | PS5-44-OB-6599B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-10-19 | PS5-06-01 | PS5 - Milestone D | 3 | Closed | 20 | 44 | OCTOBER
T-447-6079 | PS5-54-OB-1617D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone C | 2 | To be completed |  | 43 | SEPTEMBER
T-957-6080 | PS5-10-OB-7844B | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-05-25 | PS5-01-07 | PS5 - Milestone G | 6 | Closed | 40 | 44 | MAY
T-360-6081 | PS5-50-OB-4900A | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-12-18 | PS5-02-01 | PS5 - Milestone D | 3 | Closed | 18 | 30 | DECEMBER
T-688-6082 | PS5-53-OB-6131B | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-08-06 | PS5-06-03 | PS5 - Milestone E | 4 | Closed | 35 | 30 | AUGUST
T-469-6083 | PS5-23-IK-6924A | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone E | 4 | To be completed |  | 33 | DECEMBER
T-299-6084 | PS5-60-IK-1565A | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | To be completed |  | 7 | NOVEMBER
T-847-6085 | PS5-78-OB-4975B | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone H | 7 | To be completed |  | 30 | DECEMBER
T-899-6086 | PS5-65-OB-6187B | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-08-08 | PS5-04-01 | PS5 - Milestone C | 2 | Closed | 26 | 6 | AUGUST
T-319-6087 | PS5-90-UR-9866A | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone B | 1.1 | On hold |  | 40 | OCTOBER
T-923-6088 | PS5-34-IK-1539A | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone A | 1 | To be completed |  | 12 | SEPTEMBER
T-843-6089 | PS5-79-UR-8684D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | To be completed |  | 22 | AUGUST
T-694-6090 | PS5-08-IK-9905C | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone C | 2 | To be completed |  | 42 | DECEMBER
T-818-6091 | PS5-68-IK-3439A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone C | 2 | To be completed |  | 39 | NOVEMBER
T-319-6092 | PS5-94-IK-5196D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-01-07 | PS5-05-03 | PS5 - Milestone E | 4 | Closed | 29 | 25 | JANUARY
T-163-6093 | PS5-49-OB-5187C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-03-02 | PS5-01-03 | PS5 - Milestone C | 2 | Closed | 33 | 30 | MARCH
T-769-6094 | PS5-31-OB-9508C | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone A | 1 | To be completed |  | 22 | NOVEMBER
T-784-6095 | PS5-64-IK-3853A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone I | 8 | To be completed |  | 25 | DECEMBER
T-278-6096 | PS5-05-IK-2229B | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-10-01 | PS5-09-02 | PS5 - Milestone H | 7 | Closed | 12 | 25 | OCTOBER
T-822-6097 | PS5-30-OB-9299B | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-05-15 | PS5-02-01 | PS5 - Milestone D | 3 | Closed | 21 | 8 | MAY
T-919-6098 | PS5-50-OB-9047A | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone H | 7 | In progress |  | 25 | DECEMBER
T-710-6099 | PS5-95-OB-7465A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-03-27 | PS5-01-03 | PS5 - Milestone E | 4 | Closed | 24 | 46 | MARCH
T-267-6100 | PS5-22-OB-9710B | CQP04 - Hydrotest | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone I | 8 | In progress |  | 12 | SEPTEMBER
T-339-6101 | PS5-53-IK-9492D | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-10-11 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 39 | 22 | OCTOBER
T-731-6102 | PS5-46-OB-3637D | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone F | 5 | In progress |  | 12 | NOVEMBER
T-640-6103 | PS5-63-OB-6299B | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone G | 6 | To be completed |  | 21 | NOVEMBER
T-674-6104 | PS5-05-OB-1318A | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone I | 8 | In progress |  | 12 | NOVEMBER
T-313-6105 | PS5-55-IK-7871B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-10-17 | PS5-62-01 | PS5 - Milestone G | 6 | Closed | 7 | 4 | OCTOBER
T-018-6106 | PS5-56-OB-7224C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | To be completed |  | 32 | AUGUST
T-558-6107 | PS5-70-UR-9208D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | To be completed |  | 10 | NOVEMBER
T-225-6108 | PS5-97-OB-8458A | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-09-18 | PS5-03-23 | PS5 - Milestone G | 6 | Closed | 24 | 17 | SEPTEMBER
T-055-6109 | PS5-11-UR-2368A | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone C | 2 | On hold |  | 20 | AUGUST
T-327-6110 | PS5-21-UR-4733D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone I | 8 | In progress |  | 31 | SEPTEMBER
T-615-6111 | PS5-74-UR-1071B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | In progress |  | 36 | DECEMBER
T-007-6112 | PS5-09-OB-8628C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone G | 6 | To be completed |  | 13 | OCTOBER
T-906-6113 | PS5-42-OB-4056D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone H | 7 | In progress |  | 29 | SEPTEMBER
T-737-6114 | PS5-51-OB-3030D | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone E | 4 | In progress |  | 36 | OCTOBER
T-803-6115 | PS5-13-IK-9091D | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-11-19 | PS5-60-01 | PS5 - Milestone G | 6 | Closed | 38 | 36 | NOVEMBER
T-819-6116 | PS5-27-IK-9416A | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | To be completed |  | 29 | OCTOBER
T-194-6117 | PS5-47-IK-4444D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-05-04 | PS5-99-02 | PS5 - Milestone C | 2 | Closed | 24 | 36 | MAY
T-538-6118 | PS5-89-OB-5592B | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone I | 8 | To be completed |  | 35 | DECEMBER
T-360-6119 | PS5-26-UR-9585D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-10-09 | PS5-08-02 | PS5 - Milestone F | 5 | Closed | 39 | 35 | OCTOBER
T-066-6120 | PS5-95-OB-1386D | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone H | 7 | To be completed |  | 42 | OCTOBER
T-079-6121 | PS5-74-IK-7831C | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone C | 2 | To be completed |  | 40 | NOVEMBER
T-360-6122 | PS5-94-IK-3101C | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-03-22 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 28 | 5 | MARCH
T-726-6123 | PS5-82-OB-7934C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone A | 1 | In progress |  | 33 | DECEMBER
T-670-6124 | PS5-63-OB-8212C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-12 | PS5-60-07 | PS5 - Milestone A | 1 | Closed | 11 | 20 | JULY
T-677-6125 | PS5-70-UR-6698A | CQS03 - Deluge System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-05-05 | PS5-04-04 | PS5 - Milestone D | 3 | Closed | 43 | 41 | MAY
T-371-6126 | PS5-66-IK-1672A | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone E | 4 | In progress |  | 8 | OCTOBER
T-369-6127 | PS5-85-OB-9994C | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-02-18 | PS5-09-01 | PS5 - Milestone A | 1 | Closed | 32 | 27 | FEBRUARY
T-331-6128 | PS5-81-OB-5493A | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-08-10 | PS5-01-08 | PS5 - Milestone G | 6 | Closed | 12 | 31 | AUGUST
T-671-6129 | PS5-07-OB-8911B | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-04-28 | PS5-04-01 | PS5 - Milestone D | 3 | Closed | 26 | 44 | APRIL
T-411-6130 | PS5-56-OB-7092B | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone C | 2 | To be completed |  | 40 | DECEMBER
T-961-6131 | PS5-37-UR-5020A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone A | 1 | In progress |  | 27 | NOVEMBER
T-594-6132 | PS5-53-UR-6246A | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | To be completed |  | 46 | OCTOBER
T-223-6133 | PS5-94-OB-5441C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone B | 1.1 | To be completed |  | 6 | NOVEMBER
T-900-6134 | PS5-96-OB-7669C | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone H | 7 | In progress |  | 46 | DECEMBER
T-037-6135 | PS5-18-UR-9848D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-11-12 | PS5-05-01 | PS5 - Milestone G | 6 | Closed | 26 | 19 | NOVEMBER
T-582-6136 | PS5-37-IK-5810D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-06-25 | PS5-04-01 | PS5 - Milestone C | 2 | Closed | 47 | 28 | JUNE
T-375-6137 | PS5-92-OB-8113C | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | In progress |  | 48 | OCTOBER
T-383-6138 | PS5-32-IK-1635A | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-04-06 | PS5-11-01 | PS5 - Milestone B | 1.1 | Closed | 21 | 42 | APRIL
T-724-6139 | PS5-51-UR-1740A | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone E | 4 | In progress |  | 26 | DECEMBER
T-156-6140 | PS5-91-UR-9769C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone B | 1.1 | To be completed |  | 37 | OCTOBER
T-638-6141 | PS5-31-OB-6314D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | In progress |  | 7 | SEPTEMBER
T-038-6142 | PS5-04-OB-6490C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone H | 7 | In progress |  | 36 | DECEMBER
T-021-6143 | PS5-50-IK-9637B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-03-28 | PS5-10-03 | PS5 - Milestone H | 7 | Closed | 29 | 8 | MARCH
T-836-6144 | PS5-86-IK-8767D | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone E | 4 | To be completed |  | 35 | SEPTEMBER
T-778-6145 | PS5-50-UR-9250B | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-07-17 | PS5-62-02 | PS5 - Milestone E | 4 | Closed | 7 | 24 | JULY
T-572-6146 | PS5-38-OB-7887A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone H | 7 | To be completed |  | 17 | AUGUST
T-746-6147 | PS5-83-IK-3551B | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone G | 6 | On hold |  | 4 | SEPTEMBER
T-894-6148 | PS5-90-OB-5755A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-03-01 | PS5-01-03 | PS5 - Milestone H | 7 | Closed | 46 | 40 | MARCH
T-235-6149 | PS5-35-OB-8480C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-09-25 | PS5-01-05 | PS5 - Milestone H | 7 | Closed | 23 | 32 | SEPTEMBER
T-022-6150 | PS5-39-OB-7311B | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone G | 6 | On hold |  | 38 | AUGUST
T-948-6151 | PS5-97-IK-8408B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone D | 3 | In progress |  | 15 | NOVEMBER
T-051-6152 | PS5-23-OB-4510A | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone D | 3 | To be completed |  | 22 | NOVEMBER
T-009-6153 | PS5-11-UR-7125D | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone E | 4 | On hold |  | 18 | NOVEMBER
T-943-6154 | PS5-19-IK-2249A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone A | 1 | On hold |  | 25 | AUGUST
T-395-6155 | PS5-19-OB-4624C | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone B | 1.1 | To be completed |  | 29 | AUGUST
T-371-6156 | PS5-42-UR-5949A | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-06-24 | PS5-82-01 | PS5 - Milestone D | 3 | Closed | 25 | 44 | JUNE
T-254-6157 | PS5-82-OB-5937C | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | To be completed |  | 10 | NOVEMBER
T-738-6158 | PS5-49-OB-4183B | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-04-19 | PS5-08-01 | PS5 - Milestone A | 1 | Closed | 14 | 27 | APRIL
T-770-6159 | PS5-60-OB-2833D | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-10-20 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 46 | 33 | OCTOBER
T-746-6160 | PS5-84-IK-9297D | CQP02 - Valve Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | To be completed |  | 14 | AUGUST
T-023-6161 | PS5-38-OB-8139C | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | To be completed |  | 36 | SEPTEMBER
T-204-6162 | PS5-89-UR-2935A | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone D | 3 | To be completed |  | 15 | SEPTEMBER
T-183-6163 | PS5-25-UR-7305A | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | In progress |  | 25 | OCTOBER
T-603-6164 | PS5-92-IK-8682C | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-07-16 | PS5-05-01 | PS5 - Milestone D | 3 | Closed | 15 | 44 | JULY
T-084-6165 | PS5-01-UR-2666C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-09-03 | PS5-05-03 | PS5 - Milestone G | 6 | Closed | 42 | 44 | SEPTEMBER
T-553-6166 | PS5-12-OB-4995A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone I | 8 | On hold |  | 5 | NOVEMBER
T-014-6167 | PS5-90-OB-9688D | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone A | 1 | In progress |  | 22 | NOVEMBER
T-463-6168 | PS5-38-UR-3117C | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone B | 1.1 | To be completed |  | 39 | NOVEMBER
T-254-6169 | PS5-14-OB-8196D | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone C | 2 | To be completed |  | 30 | SEPTEMBER
T-070-6170 | PS5-18-IK-4256A | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-04-08 | PS5-63-01 | PS5 - Milestone I | 8 | Closed | 11 | 43 | APRIL
T-212-6171 | PS5-72-OB-6122A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone H | 7 | In progress |  | 36 | DECEMBER
T-081-6172 | PS5-56-OB-1057D | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | To be completed |  | 47 | NOVEMBER
T-744-6173 | PS5-96-OB-4771B | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | To be completed |  | 11 | NOVEMBER
T-387-6174 | PS5-63-OB-5724C | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-05-01 | PS5-02-01 | PS5 - Milestone E | 4 | Closed | 45 | 10 | MAY
T-219-6175 | PS5-09-IK-5323B | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-02-21 | PS5-04-03 | PS5 - Milestone C | 2 | Closed | 4 | 41 | FEBRUARY
T-415-6176 | PS5-90-IK-4847D | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-02-21 | PS5-10-05 | PS5 - Milestone C | 2 | Closed | 37 | 8 | FEBRUARY
T-107-6177 | PS5-21-OB-2481B | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-02-22 | PS5-07-02 | PS5 - Milestone D | 3 | Closed | 43 | 34 | FEBRUARY
T-357-6178 | PS5-22-OB-9550D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone D | 3 | In progress |  | 41 | SEPTEMBER
T-241-6179 | PS5-87-UR-8554B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-10-08 | PS5-08-02 | PS5 - Milestone D | 3 | Closed | 4 | 18 | OCTOBER
T-264-6180 | PS5-28-OB-8656C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-03-17 | PS5-60-01 | PS5 - Milestone A | 1 | Closed | 6 | 40 | MARCH
T-733-6181 | PS5-62-UR-8313A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-07-02 | PS5-09-04 | PS5 - Milestone I | 8 | Closed | 44 | 25 | JULY
T-827-6182 | PS5-52-IK-1073C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | In progress |  | 5 | DECEMBER
T-357-6183 | PS5-50-IK-3020C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | To be completed |  | 8 | OCTOBER
T-897-6184 | PS5-08-OB-2990D | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone H | 7 | On hold |  | 33 | NOVEMBER
T-227-6185 | PS5-82-IK-9370D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | On hold |  | 31 | DECEMBER
T-219-6186 | PS5-10-IK-7706B | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone A | 1 | To be completed |  | 42 | NOVEMBER
T-407-6187 | PS5-98-OB-3982A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone I | 8 | In progress |  | 8 | DECEMBER
T-119-6188 | PS5-03-OB-6238D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone D | 3 | On hold |  | 28 | AUGUST
T-601-6189 | PS5-71-OB-9790D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-12-26 | PS5-09-01 | PS5 - Milestone F | 5 | Closed | 8 | 12 | DECEMBER
T-727-6190 | PS5-42-OB-6820A | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-04-02 | PS5-07-04 | PS5 - Milestone E | 4 | Closed | 7 | 25 | APRIL
T-471-6191 | PS5-66-OB-9072B | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone F | 5 | In progress |  | 21 | DECEMBER
T-574-6192 | PS5-95-UR-2149A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-11-03 | PS5-60-07 | PS5 - Milestone G | 6 | Closed | 26 | 29 | NOVEMBER
T-698-6193 | PS5-45-IK-5472C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-11-28 | PS5-10-05 | PS5 - Milestone E | 4 | Closed | 46 | 19 | NOVEMBER
T-265-6194 | PS5-59-UR-1450B | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone D | 3 | In progress |  | 35 | OCTOBER
T-816-6195 | PS5-46-IK-7139B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-19 | PS5-60-07 | PS5 - Milestone G | 6 | Closed | 22 | 37 | JULY
T-827-6196 | PS5-51-IK-3057C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone C | 2 | On hold |  | 42 | DECEMBER
T-829-6197 | PS5-13-OB-4366C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone C | 2 | On hold |  | 9 | DECEMBER
T-170-6198 | PS5-55-OB-4477B | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | To be completed |  | 8 | NOVEMBER
T-117-6199 | PS5-53-OB-3273B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone D | 3 | In progress |  | 12 | OCTOBER
T-688-6200 | PS5-94-UR-4242C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone B | 1.1 | To be completed |  | 8 | NOVEMBER
T-531-6201 | PS5-87-OB-7864C | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone F | 5 | On hold |  | 16 | AUGUST
T-239-6202 | PS5-33-UR-9992A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone H | 7 | To be completed |  | 13 | DECEMBER
T-714-6203 | PS5-80-UR-4085D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone G | 6 | To be completed |  | 43 | SEPTEMBER
T-136-6204 | PS5-89-OB-1990B | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone I | 8 | In progress |  | 15 | AUGUST
T-833-6205 | PS5-82-OB-7616C | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone H | 7 | To be completed |  | 30 | AUGUST
T-979-6206 | PS5-05-OB-4368D | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | In progress |  | 30 | SEPTEMBER
T-137-6207 | PS5-78-OB-1610C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone I | 8 | In progress |  | 5 | SEPTEMBER
T-042-6208 | PS5-12-OB-9188D | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone E | 4 | To be completed |  | 9 | OCTOBER
T-307-6209 | PS5-64-OB-2157B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone B | 1.1 | On hold |  | 45 | OCTOBER
T-485-6210 | PS5-11-UR-8043D | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-01-13 | PS5-05-03 | PS5 - Milestone G | 6 | Closed | 38 | 8 | JANUARY
T-751-6211 | PS5-57-UR-5080C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone F | 5 | On hold |  | 12 | DECEMBER
T-974-6212 | PS5-16-OB-4007D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone H | 7 | On hold |  | 13 | NOVEMBER
T-153-6213 | PS5-14-OB-4153C | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone B | 1.1 | In progress |  | 17 | SEPTEMBER
T-129-6214 | PS5-76-OB-2629B | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-12-17 | PS5-04-03 | PS5 - Milestone E | 4 | Closed | 40 | 21 | DECEMBER
T-956-6215 | PS5-56-OB-1476C | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-11-10 | PS5-11-03 | PS5 - Milestone G | 6 | Closed | 20 | 10 | NOVEMBER
T-347-6216 | PS5-20-IK-2915A | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | To be completed |  | 18 | DECEMBER
T-655-6217 | PS5-15-OB-2301C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-07-17 | PS5-61-07 | PS5 - Milestone I | 8 | Closed | 20 | 29 | JULY
T-899-6218 | PS5-15-OB-7176D | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-03-24 | PS5-07-03 | PS5 - Milestone E | 4 | Closed | 39 | 7 | MARCH
T-186-6219 | PS5-99-UR-4804A | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-04-16 | PS5-61-07 | PS5 - Milestone F | 5 | Closed | 10 | 16 | APRIL
T-311-6220 | PS5-94-OB-2053A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-02-22 | PS5-07-01 | PS5 - Milestone A | 1 | Closed | 22 | 27 | FEBRUARY
T-348-6221 | PS5-31-OB-5071A | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone A | 1 | To be completed |  | 13 | NOVEMBER
T-501-6222 | PS5-71-OB-1964A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-10-23 | PS5-01-08 | PS5 - Milestone B | 1.1 | Closed | 36 | 43 | OCTOBER
T-979-6223 | PS5-97-IK-1438B | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone E | 4 | To be completed |  | 5 | OCTOBER
T-676-6224 | PS5-94-OB-6894D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone E | 4 | To be completed |  | 16 | DECEMBER
T-125-6225 | PS5-74-OB-5191C | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone I | 8 | To be completed |  | 5 | OCTOBER
T-574-6226 | PS5-10-OB-6971B | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone I | 8 | On hold |  | 6 | OCTOBER
T-548-6227 | PS5-90-OB-6742C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | To be completed |  | 18 | SEPTEMBER
T-946-6228 | PS5-04-UR-5108D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone C | 2 | To be completed |  | 46 | SEPTEMBER
T-180-6229 | PS5-13-UR-9038B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone G | 6 | To be completed |  | 21 | SEPTEMBER
T-552-6230 | PS5-85-IK-4106D | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-03-23 | PS5-06-02 | PS5 - Milestone A | 1 | Closed | 24 | 17 | MARCH
T-626-6231 | PS5-50-UR-8880A | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-12-09 | PS5-11-02 | PS5 - Milestone G | 6 | Closed | 15 | 10 | DECEMBER
T-719-6232 | PS5-23-OB-6804D | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone D | 3 | To be completed |  | 26 | OCTOBER
T-226-6233 | PS5-71-IK-7504A | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | To be completed |  | 5 | OCTOBER
T-468-6234 | PS5-63-IK-5130A | CQP04 - Hydrotest | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-02-12 | PS5-82-02 | PS5 - Milestone D | 3 | Closed | 27 | 41 | FEBRUARY
T-796-6235 | PS5-22-OB-1514A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-12-04 | PS5-11-02 | PS5 - Milestone H | 7 | Closed | 33 | 6 | DECEMBER
T-102-6236 | PS5-07-IK-3270D | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-11-10 | PS5-99-03 | PS5 - Milestone D | 3 | Closed | 24 | 47 | NOVEMBER
T-148-6237 | PS5-86-OB-8617D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-10-20 | PS5-06-01 | PS5 - Milestone I | 8 | Closed | 28 | 27 | OCTOBER
T-539-6238 | PS5-60-OB-2862D | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone H | 7 | In progress |  | 36 | SEPTEMBER
T-326-6239 | PS5-14-OB-4923D | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone D | 3 | To be completed |  | 34 | SEPTEMBER
T-295-6240 | PS5-85-OB-4197A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-08-04 | PS5-01-05 | PS5 - Milestone C | 2 | Closed | 13 | 44 | AUGUST
T-254-6241 | PS5-41-OB-2782C | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | On hold |  | 42 | NOVEMBER
T-724-6242 | PS5-21-UR-6316D | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-11-23 | PS5-60-04 | PS5 - Milestone H | 7 | Closed | 18 | 27 | NOVEMBER
T-378-6243 | PS5-06-IK-3804C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone G | 6 | In progress |  | 37 | DECEMBER
T-544-6244 | PS5-36-OB-7890D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone F | 5 | On hold |  | 15 | OCTOBER
T-174-6245 | PS5-57-OB-6281B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-11-05 | PS5-04-01 | PS5 - Milestone H | 7 | Closed | 16 | 46 | NOVEMBER
T-435-6246 | PS5-69-UR-7046B | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-12-08 | PS5-03-01 | PS5 - Milestone G | 6 | Closed | 22 | 22 | DECEMBER
T-946-6247 | PS5-72-OB-2070D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-02-07 | PS5-07-03 | PS5 - Milestone E | 4 | Closed | 32 | 19 | FEBRUARY
T-929-6248 | PS5-72-OB-8740C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-09-05 | PS5-01-04 | PS5 - Milestone I | 8 | Closed | 4 | 48 | SEPTEMBER
T-945-6249 | PS5-03-OB-8655D | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | In progress |  | 41 | SEPTEMBER
T-474-6250 | PS5-09-OB-7481B | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone C | 2 | In progress |  | 6 | OCTOBER
T-794-6251 | PS5-70-OB-9728D | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone H | 7 | To be completed |  | 15 | AUGUST
T-954-6252 | PS5-86-IK-6569B | CQP04 - Hydrotest | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone F | 5 | On hold |  | 45 | NOVEMBER
T-708-6253 | PS5-64-OB-4367C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | In progress |  | 32 | SEPTEMBER
T-252-6254 | PS5-86-IK-8144D | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone A | 1 | To be completed |  | 26 | OCTOBER
T-268-6255 | PS5-34-UR-8950A | CQP05 - Insulation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-05-04 | PS5-01-02 | PS5 - Milestone D | 3 | Closed | 12 | 10 | MAY
T-576-6256 | PS5-39-OB-7933B | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone B | 1.1 | In progress |  | 26 | DECEMBER
T-210-6257 | PS5-60-OB-8474C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone I | 8 | To be completed |  | 41 | AUGUST
T-247-6258 | PS5-18-IK-4498B | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone F | 5 | To be completed |  | 13 | AUGUST
T-557-6259 | PS5-76-OB-7779A | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-01-12 | PS5-62-02 | PS5 - Milestone C | 2 | Closed | 31 | 21 | JANUARY
T-240-6260 | PS5-02-UR-7695B | CQP05 - Insulation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-01-26 | PS5-01-04 | PS5 - Milestone D | 3 | Closed | 29 | 7 | JANUARY
T-409-6261 | PS5-90-OB-9759C | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone F | 5 | In progress |  | 11 | AUGUST
T-780-6262 | PS5-35-OB-1736B | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | On hold |  | 22 | SEPTEMBER
T-417-6263 | PS5-80-UR-8112B | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone A | 1 | To be completed |  | 8 | SEPTEMBER
T-958-6264 | PS5-16-UR-5282D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone D | 3 | In progress |  | 29 | DECEMBER
T-427-6265 | PS5-25-UR-4007B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone A | 1 | In progress |  | 42 | AUGUST
T-347-6266 | PS5-23-OB-9821C | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone A | 1 | In progress |  | 33 | SEPTEMBER
T-930-6267 | PS5-50-OB-5187C | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone G | 6 | In progress |  | 42 | DECEMBER
T-881-6268 | PS5-58-UR-3475D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone C | 2 | In progress |  | 11 | NOVEMBER
T-841-6269 | PS5-02-IK-7279B | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-10-16 | PS5-99-01 | PS5 - Milestone C | 2 | Closed | 43 | 40 | OCTOBER
T-060-6270 | PS5-04-UR-4412A | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-01-19 | PS5-11-01 | PS5 - Milestone B | 1.1 | Closed | 33 | 14 | JANUARY
T-653-6271 | PS5-29-UR-2182B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-12-26 | PS5-06-03 | PS5 - Milestone H | 7 | Closed | 46 | 48 | DECEMBER
T-145-6272 | PS5-42-IK-1343B | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-12-24 | PS5-05-01 | PS5 - Milestone I | 8 | Closed | 29 | 35 | DECEMBER
T-713-6273 | PS5-42-OB-6653B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | In progress |  | 26 | AUGUST
T-263-6274 | PS5-31-OB-3987D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-05-21 | PS5-82-07 | PS5 - Milestone H | 7 | Closed | 11 | 22 | MAY
T-615-6275 | PS5-03-OB-7423B | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-07-24 | PS5-08-01 | PS5 - Milestone C | 2 | Closed | 19 | 28 | JULY
T-178-6276 | PS5-81-OB-8594B | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | In progress |  | 34 | AUGUST
T-846-6277 | PS5-03-OB-9424A | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone E | 4 | In progress |  | 29 | SEPTEMBER
T-249-6278 | PS5-34-OB-4334B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone H | 7 | To be completed |  | 37 | DECEMBER
T-989-6279 | PS5-16-UR-3291B | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | In progress |  | 27 | SEPTEMBER
T-110-6280 | PS5-87-OB-2818A | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone D | 3 | To be completed |  | 29 | SEPTEMBER
T-245-6281 | PS5-36-UR-2491D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-02-07 | PS5-06-02 | PS5 - Milestone C | 2 | Closed | 12 | 9 | FEBRUARY
T-071-6282 | PS5-86-IK-1688A | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-11-21 | PS5-10-03 | PS5 - Milestone A | 1 | Closed | 11 | 40 | NOVEMBER
T-551-6283 | PS5-34-OB-1004C | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-01-06 | PS5-82-07 | PS5 - Milestone B | 1.1 | Closed | 41 | 14 | JANUARY
T-834-6284 | PS5-65-OB-5828A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-01-01 | PS5-07-04 | PS5 - Milestone F | 5 | Closed | 35 | 35 | JANUARY
T-869-6285 | PS5-65-IK-4213A | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-09-03 | PS5-10-02 | PS5 - Milestone I | 8 | Closed | 36 | 14 | SEPTEMBER
T-142-6286 | PS5-24-UR-3963C | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-04-13 | PS5-63-01 | PS5 - Milestone C | 2 | Closed | 7 | 35 | APRIL
T-571-6287 | PS5-17-UR-3912A | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-10-06 | PS5-01-02 | PS5 - Milestone B | 1.1 | Closed | 22 | 40 | OCTOBER
T-477-6288 | PS5-53-OB-6802A | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone D | 3 | On hold |  | 32 | DECEMBER
T-501-6289 | PS5-47-IK-2726A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-05-17 | PS5-10-04 | PS5 - Milestone G | 6 | Closed | 32 | 29 | MAY
T-927-6290 | PS5-04-UR-1745B | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone H | 7 | To be completed |  | 8 | AUGUST
T-036-6291 | PS5-65-OB-8848D | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone G | 6 | To be completed |  | 8 | NOVEMBER
T-905-6292 | PS5-55-IK-7300C | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-07-26 | PS5-10-01 | PS5 - Milestone C | 2 | Closed | 15 | 29 | JULY
T-648-6293 | PS5-27-UR-7735A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone A | 1 | On hold |  | 45 | DECEMBER
T-728-6294 | PS5-88-OB-8127A | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone I | 8 | To be completed |  | 24 | NOVEMBER
T-604-6295 | PS5-73-OB-7275B | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-09-19 | PS5-82-02 | PS5 - Milestone B | 1.1 | Closed | 26 | 21 | SEPTEMBER
T-505-6296 | PS5-01-OB-9824C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone F | 5 | To be completed |  | 40 | OCTOBER
T-556-6297 | PS5-59-IK-7168B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone F | 5 | In progress |  | 19 | AUGUST
T-260-6298 | PS5-26-UR-1043D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-07-23 | PS5-12-01 | PS5 - Milestone A | 1 | Closed | 35 | 44 | JULY
T-064-6299 | PS5-16-OB-5859D | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-11-03 | PS5-04-04 | PS5 - Milestone E | 4 | Closed | 29 | 34 | NOVEMBER
T-935-6300 | PS5-08-OB-2744A | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-03-24 | PS5-02-02 | PS5 - Milestone G | 6 | Closed | 20 | 15 | MARCH
T-829-6301 | PS5-49-IK-1884C | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone I | 8 | In progress |  | 45 | NOVEMBER
T-723-6302 | PS5-63-OB-8721B | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone I | 8 | To be completed |  | 26 | NOVEMBER
T-554-6303 | PS5-53-OB-5798B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-08-03 | PS5-10-02 | PS5 - Milestone B | 1.1 | Closed | 41 | 33 | AUGUST
T-370-6304 | PS5-88-OB-3551B | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-04-24 | PS5-01-07 | PS5 - Milestone H | 7 | Closed | 47 | 19 | APRIL
T-466-6305 | PS5-61-IK-7279C | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-03-27 | PS5-07-03 | PS5 - Milestone H | 7 | Closed | 22 | 26 | MARCH
T-879-6306 | PS5-65-OB-7718A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone H | 7 | To be completed |  | 5 | DECEMBER
T-282-6307 | PS5-20-IK-4565A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | To be completed |  | 39 | OCTOBER
T-938-6308 | PS5-04-IK-1747D | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone A | 1 | To be completed |  | 45 | NOVEMBER
T-004-6309 | PS5-97-OB-5190B | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone E | 4 | In progress |  | 9 | DECEMBER
T-180-6310 | PS5-09-IK-9141A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-07-27 | PS5-05-03 | PS5 - Milestone H | 7 | Closed | 42 | 33 | JULY
T-178-6311 | PS5-99-OB-9347C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-01-07 | PS5-03-23 | PS5 - Milestone F | 5 | Closed | 41 | 10 | JANUARY
T-035-6312 | PS5-13-IK-4143B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone D | 3 | In progress |  | 44 | NOVEMBER
T-508-6313 | PS5-47-OB-2605A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-07-26 | PS5-09-01 | PS5 - Milestone G | 6 | Closed | 41 | 32 | JULY
T-026-6314 | PS5-25-OB-5508D | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone B | 1.1 | In progress |  | 16 | AUGUST
T-118-6315 | PS5-63-OB-3269A | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-11-06 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 13 | 29 | NOVEMBER
T-829-6316 | PS5-92-UR-6430B | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | To be completed |  | 45 | SEPTEMBER
T-539-6317 | PS5-55-UR-4810B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | To be completed |  | 23 | OCTOBER
T-627-6318 | PS5-17-IK-5225D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone H | 7 | On hold |  | 27 | OCTOBER
T-971-6319 | PS5-38-IK-4963A | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone A | 1 | To be completed |  | 25 | NOVEMBER
T-554-6320 | PS5-14-OB-3322D | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-10-05 | PS5-09-01 | PS5 - Milestone F | 5 | Closed | 7 | 31 | OCTOBER
T-785-6321 | PS5-24-OB-6875C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-04-14 | PS5-10-06 | PS5 - Milestone H | 7 | Closed | 34 | 16 | APRIL
T-598-6322 | PS5-16-UR-2183A | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-06-16 | PS5-63-04 | PS5 - Milestone F | 5 | Closed | 45 | 14 | JUNE
T-330-6323 | PS5-86-UR-9031D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-12-19 | PS5-82-07 | PS5 - Milestone H | 7 | Closed | 13 | 14 | DECEMBER
T-710-6324 | PS5-54-UR-3270A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-01-04 | PS5-61-02 | PS5 - Milestone D | 3 | Closed | 12 | 30 | JANUARY
T-352-6325 | PS5-77-IK-4795A | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-04-03 | PS5-01-04 | PS5 - Milestone D | 3 | Closed | 18 | 11 | APRIL
T-518-6326 | PS5-20-OB-1412B | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-05-09 | PS5-04-02 | PS5 - Milestone F | 5 | Closed | 14 | 32 | MAY
T-513-6327 | PS5-14-UR-6761D | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone F | 5 | To be completed |  | 14 | NOVEMBER
T-378-6328 | PS5-12-IK-9025D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone F | 5 | To be completed |  | 25 | DECEMBER
T-638-6329 | PS5-06-IK-3610A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-12-17 | PS5-07-02 | PS5 - Milestone G | 6 | Closed | 35 | 23 | DECEMBER
T-068-6330 | PS5-24-UR-8062D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone B | 1.1 | On hold |  | 44 | SEPTEMBER
T-943-6331 | PS5-17-OB-6592C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | On hold |  | 22 | NOVEMBER
T-789-6332 | PS5-61-OB-3715D | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone H | 7 | To be completed |  | 9 | OCTOBER
T-412-6333 | PS5-59-UR-1031C | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-09-25 | PS5-10-04 | PS5 - Milestone H | 7 | Closed | 43 | 31 | SEPTEMBER
T-607-6334 | PS5-86-OB-9207A | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | To be completed |  | 22 | DECEMBER
T-600-6335 | PS5-79-UR-1137A | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone D | 3 | To be completed |  | 5 | OCTOBER
T-038-6336 | PS5-30-OB-6840B | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone H | 7 | On hold |  | 21 | SEPTEMBER
T-008-6337 | PS5-82-OB-8610A | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-12-11 | PS5-09-04 | PS5 - Milestone D | 3 | Closed | 42 | 38 | DECEMBER
T-961-6338 | PS5-25-OB-9192C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone E | 4 | In progress |  | 48 | SEPTEMBER
T-053-6339 | PS5-26-UR-6339D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-09-07 | PS5-01-04 | PS5 - Milestone B | 1.1 | Closed | 19 | 47 | SEPTEMBER
T-509-6340 | PS5-85-UR-3893B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone E | 4 | To be completed |  | 43 | OCTOBER
T-764-6341 | PS5-49-OB-7753A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone C | 2 | On hold |  | 6 | DECEMBER
T-511-6342 | PS5-71-OB-1822B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-10-17 | PS5-63-04 | PS5 - Milestone D | 3 | Closed | 22 | 12 | OCTOBER
T-589-6343 | PS5-17-OB-3291C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-05-06 | PS5-01-08 | PS5 - Milestone F | 5 | Closed | 16 | 5 | MAY
T-279-6344 | PS5-99-OB-2140C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone E | 4 | To be completed |  | 45 | DECEMBER
T-545-6345 | PS5-45-OB-3229D | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone D | 3 | To be completed |  | 18 | AUGUST
T-599-6346 | PS5-70-UR-4898A | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone E | 4 | To be completed |  | 12 | DECEMBER
T-721-6347 | PS5-19-OB-4500C | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | In progress |  | 16 | SEPTEMBER
T-360-6348 | PS5-78-OB-3001D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone E | 4 | In progress |  | 46 | NOVEMBER
T-607-6349 | PS5-54-UR-9821A | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone F | 5 | In progress |  | 34 | OCTOBER
T-557-6350 | PS5-23-OB-9209D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-08-24 | PS5-08-01 | PS5 - Milestone E | 4 | Closed | 45 | 41 | AUGUST
T-770-6351 | PS5-29-OB-5460D | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-08-23 | PS5-02-03 | PS5 - Milestone D | 3 | Closed | 26 | 33 | AUGUST
T-440-6352 | PS5-40-IK-3712D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone A | 1 | On hold |  | 18 | AUGUST
T-866-6353 | PS5-11-IK-8283D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone H | 7 | In progress |  | 24 | SEPTEMBER
T-407-6354 | PS5-10-IK-5992C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone C | 2 | To be completed |  | 31 | NOVEMBER
T-758-6355 | PS5-10-IK-9171A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-09-25 | PS5-04-02 | PS5 - Milestone I | 8 | Closed | 24 | 22 | SEPTEMBER
T-683-6356 | PS5-40-OB-3781D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone B | 1.1 | On hold |  | 23 | SEPTEMBER
T-105-6357 | PS5-97-OB-9362C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-01-25 | PS5-63-04 | PS5 - Milestone A | 1 | Closed | 37 | 17 | JANUARY
T-664-6358 | PS5-22-UR-4816B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | To be completed |  | 32 | SEPTEMBER
T-201-6359 | PS5-75-UR-6390A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone C | 2 | To be completed |  | 29 | SEPTEMBER
T-714-6360 | PS5-28-UR-8202D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone F | 5 | In progress |  | 32 | AUGUST
T-069-6361 | PS5-60-UR-3900A | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone D | 3 | To be completed |  | 9 | OCTOBER
T-684-6362 | PS5-43-OB-1368C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-06-13 | PS5-12-02 | PS5 - Milestone G | 6 | Closed | 40 | 46 | JUNE
T-843-6363 | PS5-95-OB-3918C | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-03-05 | PS5-01-04 | PS5 - Milestone A | 1 | Closed | 12 | 22 | MARCH
T-976-6364 | PS5-41-OB-6537A | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-08-12 | PS5-01-01 | PS5 - Milestone A | 1 | Closed | 8 | 41 | AUGUST
T-139-6365 | PS5-70-OB-9315C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone E | 4 | To be completed |  | 25 | NOVEMBER
T-049-6366 | PS5-62-UR-5045B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone B | 1.1 | To be completed |  | 36 | AUGUST
T-543-6367 | PS5-38-IK-1613C | CQE01 - HV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-08-18 | PS5-11-02 | PS5 - Milestone A | 1 | Closed | 27 | 28 | AUGUST
T-467-6368 | PS5-84-IK-7574A | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | To be completed |  | 7 | DECEMBER
T-455-6369 | PS5-31-OB-8758D | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone H | 7 | In progress |  | 10 | AUGUST
T-557-6370 | PS5-61-IK-5938C | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | On hold |  | 17 | DECEMBER
T-528-6371 | PS5-63-IK-4893B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone D | 3 | On hold |  | 42 | SEPTEMBER
T-580-6372 | PS5-72-UR-1865D | CQP04 - Hydrotest | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone F | 5 | To be completed |  | 24 | AUGUST
T-830-6373 | PS5-33-OB-8336B | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-09-28 | PS5-09-04 | PS5 - Milestone A | 1 | Closed | 35 | 28 | SEPTEMBER
T-934-6374 | PS5-66-IK-7464C | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-02-06 | PS5-11-01 | PS5 - Milestone D | 3 | Closed | 27 | 14 | FEBRUARY
T-858-6375 | PS5-82-OB-6820C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-12-24 | PS5-02-01 | PS5 - Milestone D | 3 | Closed | 8 | 29 | DECEMBER
T-902-6376 | PS5-23-IK-9301A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-07-03 | PS5-01-03 | PS5 - Milestone I | 8 | Closed | 46 | 29 | JULY
T-939-6377 | PS5-33-OB-4661D | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-01-25 | PS5-62-01 | PS5 - Milestone D | 3 | Closed | 37 | 47 | JANUARY
T-211-6378 | PS5-24-OB-2390C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone F | 5 | To be completed |  | 39 | AUGUST
T-675-6379 | PS5-22-IK-1689C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | To be completed |  | 17 | OCTOBER
T-925-6380 | PS5-18-UR-4653C | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone A | 1 | To be completed |  | 38 | DECEMBER
T-857-6381 | PS5-46-UR-3167B | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone G | 6 | In progress |  | 16 | AUGUST
T-783-6382 | PS5-35-OB-2862D | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-01-20 | PS5-08-01 | PS5 - Milestone I | 8 | Closed | 18 | 31 | JANUARY
T-569-6383 | PS5-82-OB-9923B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-05-13 | PS5-07-03 | PS5 - Milestone F | 5 | Closed | 28 | 40 | MAY
T-519-6384 | PS5-72-OB-8264B | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone I | 8 | To be completed |  | 23 | DECEMBER
T-896-6385 | PS5-72-UR-6847D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone E | 4 | On hold |  | 23 | AUGUST
T-297-6386 | PS5-73-IK-5778A | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-08-07 | PS5-12-01 | PS5 - Milestone F | 5 | Closed | 13 | 11 | AUGUST
T-086-6387 | PS5-22-OB-5321B | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | To be completed |  | 20 | NOVEMBER
T-972-6388 | PS5-87-IK-5100C | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-09-02 | PS5-07-03 | PS5 - Milestone B | 1.1 | Closed | 35 | 29 | SEPTEMBER
T-531-6389 | PS5-85-IK-7885D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-01-25 | PS5-06-01 | PS5 - Milestone F | 5 | Closed | 46 | 12 | JANUARY
T-992-6390 | PS5-35-OB-6691C | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | On hold |  | 14 | DECEMBER
T-218-6391 | PS5-46-UR-4338D | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-02-14 | PS5-01-05 | PS5 - Milestone H | 7 | Closed | 32 | 31 | FEBRUARY
T-114-6392 | PS5-47-IK-2427A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-09-16 | PS5-10-02 | PS5 - Milestone I | 8 | Closed | 33 | 30 | SEPTEMBER
T-486-6393 | PS5-61-OB-5259B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone B | 1.1 | To be completed |  | 23 | SEPTEMBER
T-408-6394 | PS5-97-OB-2777C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone C | 2 | In progress |  | 9 | SEPTEMBER
T-699-6395 | PS5-05-UR-3773C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-04-04 | PS5-09-03 | PS5 - Milestone D | 3 | Closed | 44 | 40 | APRIL
T-556-6396 | PS5-68-OB-4354B | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-09-12 | PS5-10-05 | PS5 - Milestone C | 2 | Closed | 25 | 16 | SEPTEMBER
T-267-6397 | PS5-88-IK-1521D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone D | 3 | In progress |  | 8 | NOVEMBER
T-946-6398 | PS5-03-IK-5411C | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | To be completed |  | 14 | DECEMBER
T-224-6399 | PS5-98-UR-9529C | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-12-17 | PS5-63-01 | PS5 - Milestone H | 7 | Closed | 40 | 43 | DECEMBER
T-006-6400 | PS5-57-OB-2231D | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | To be completed |  | 37 | AUGUST
T-264-6401 | PS5-89-UR-6727A | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-04-22 | PS5-06-02 | PS5 - Milestone D | 3 | Closed | 5 | 15 | APRIL
T-040-6402 | PS5-66-OB-2855D | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone G | 6 | In progress |  | 33 | OCTOBER
T-302-6403 | PS5-33-OB-9789B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone C | 2 | To be completed |  | 33 | AUGUST
T-174-6404 | PS5-17-UR-6639D | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-05-02 | PS5-61-01 | PS5 - Milestone D | 3 | Closed | 48 | 17 | MAY
T-834-6405 | PS5-33-OB-3791D | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone F | 5 | To be completed |  | 5 | NOVEMBER
T-162-6406 | PS5-23-UR-9059D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-12-15 | PS5-10-02 | PS5 - Milestone A | 1 | Closed | 10 | 14 | DECEMBER
T-829-6407 | PS5-12-OB-6941A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-03-24 | PS5-11-03 | PS5 - Milestone H | 7 | Closed | 29 | 19 | MARCH
T-583-6408 | PS5-93-IK-8411A | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone A | 1 | To be completed |  | 9 | NOVEMBER
T-201-6409 | PS5-43-OB-2055A | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-04-21 | PS5-10-02 | PS5 - Milestone C | 2 | Closed | 32 | 46 | APRIL
T-642-6410 | PS5-85-OB-5899D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | To be completed |  | 25 | DECEMBER
T-854-6411 | PS5-57-IK-1973D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone G | 6 | To be completed |  | 14 | NOVEMBER
T-853-6412 | PS5-27-OB-3329C | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-10-11 | PS5-09-02 | PS5 - Milestone C | 2 | Closed | 28 | 39 | OCTOBER
T-516-6413 | PS5-99-OB-6933C | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone D | 3 | In progress |  | 26 | OCTOBER
T-864-6414 | PS5-41-OB-5923C | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-10-24 | PS5-06-02 | PS5 - Milestone B | 1.1 | Closed | 18 | 5 | OCTOBER
T-242-6415 | PS5-11-OB-3021A | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-08-25 | PS5-01-01 | PS5 - Milestone E | 4 | Closed | 16 | 33 | AUGUST
T-141-6416 | PS5-98-IK-1516D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone A | 1 | To be completed |  | 42 | DECEMBER
T-153-6417 | PS5-11-OB-6476B | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | On hold |  | 33 | SEPTEMBER
T-598-6418 | PS5-27-OB-9293C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-02-14 | PS5-04-01 | PS5 - Milestone G | 6 | Closed | 42 | 36 | FEBRUARY
T-730-6419 | PS5-53-UR-5596C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-07-12 | PS5-01-03 | PS5 - Milestone F | 5 | Closed | 24 | 12 | JULY
T-521-6420 | PS5-13-IK-4577B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone D | 3 | On hold |  | 10 | NOVEMBER
T-769-6421 | PS5-57-UR-5730C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone C | 2 | In progress |  | 38 | SEPTEMBER
T-904-6422 | PS5-45-UR-4563C | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-09-04 | PS5-13-01 | PS5 - Milestone C | 2 | Closed | 31 | 48 | SEPTEMBER
T-294-6423 | PS5-07-UR-8777B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-03-09 | PS5-03-03 | PS5 - Milestone F | 5 | Closed | 15 | 38 | MARCH
T-807-6424 | PS5-80-OB-4374D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-04-26 | PS5-82-02 | PS5 - Milestone G | 6 | Closed | 27 | 34 | APRIL
T-494-6425 | PS5-15-UR-5404C | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone D | 3 | In progress |  | 4 | OCTOBER
T-057-6426 | PS5-32-IK-6200D | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-10-14 | PS5-10-06 | PS5 - Milestone A | 1 | Closed | 15 | 26 | OCTOBER
T-577-6427 | PS5-57-OB-5895C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone I | 8 | To be completed |  | 16 | AUGUST
T-844-6428 | PS5-44-UR-2509C | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone A | 1 | To be completed |  | 42 | OCTOBER
T-261-6429 | PS5-94-UR-6089D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-10-17 | PS5-60-04 | PS5 - Milestone F | 5 | Closed | 17 | 36 | OCTOBER
T-136-6430 | PS5-46-UR-4806A | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone F | 5 | To be completed |  | 12 | NOVEMBER
T-020-6431 | PS5-15-UR-8174D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone C | 2 | On hold |  | 24 | DECEMBER
T-425-6432 | PS5-47-OB-3725D | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone F | 5 | On hold |  | 21 | SEPTEMBER
T-326-6433 | PS5-51-IK-7067D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone G | 6 | In progress |  | 31 | NOVEMBER
T-274-6434 | PS5-03-UR-6122A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone F | 5 | On hold |  | 27 | DECEMBER
T-617-6435 | PS5-40-IK-6423A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-09-15 | PS5-11-02 | PS5 - Milestone G | 6 | Closed | 14 | 14 | SEPTEMBER
T-339-6436 | PS5-41-OB-6386B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone G | 6 | On hold |  | 11 | SEPTEMBER
T-460-6437 | PS5-85-UR-7957C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone H | 7 | To be completed |  | 21 | SEPTEMBER
T-156-6438 | PS5-64-UR-1396A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-11-21 | PS5-12-02 | PS5 - Milestone E | 4 | Closed | 46 | 13 | NOVEMBER
T-761-6439 | PS5-26-OB-1433B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone H | 7 | In progress |  | 45 | DECEMBER
T-492-6440 | PS5-94-OB-8995A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone G | 6 | To be completed |  | 24 | DECEMBER
T-780-6441 | PS5-87-IK-5947C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone B | 1.1 | To be completed |  | 45 | NOVEMBER
T-546-6442 | PS5-01-OB-8423A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone H | 7 | In progress |  | 20 | SEPTEMBER
T-902-6443 | PS5-91-OB-5296D | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-09-08 | PS5-02-01 | PS5 - Milestone F | 5 | Closed | 31 | 8 | SEPTEMBER
T-594-6444 | PS5-01-IK-1752A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-08-04 | PS5-61-02 | PS5 - Milestone I | 8 | Closed | 12 | 18 | AUGUST
T-779-6445 | PS5-34-UR-2786B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-08-27 | PS5-03-02 | PS5 - Milestone G | 6 | Closed | 4 | 18 | AUGUST
T-619-6446 | PS5-43-OB-1405B | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-11-04 | PS5-61-02 | PS5 - Milestone D | 3 | Closed | 40 | 32 | NOVEMBER
T-052-6447 | PS5-84-IK-2468A | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone C | 2 | To be completed |  | 25 | OCTOBER
T-098-6448 | PS5-91-OB-7764A | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | To be completed |  | 39 | SEPTEMBER
T-841-6449 | PS5-12-OB-6070C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone D | 3 | To be completed |  | 47 | AUGUST
T-857-6450 | PS5-86-OB-7349C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone G | 6 | To be completed |  | 24 | OCTOBER
T-230-6451 | PS5-39-OB-2652A | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone H | 7 | To be completed |  | 41 | DECEMBER
T-099-6452 | PS5-82-UR-8767D | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-01-03 | PS5-07-04 | PS5 - Milestone H | 7 | Closed | 28 | 18 | JANUARY
T-658-6453 | PS5-50-OB-9064D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-02-16 | PS5-99-01 | PS5 - Milestone A | 1 | Closed | 33 | 5 | FEBRUARY
T-398-6454 | PS5-08-OB-1584B | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-08-22 | PS5-63-01 | PS5 - Milestone A | 1 | Closed | 34 | 16 | AUGUST
T-912-6455 | PS5-17-OB-7209A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-08-11 | PS5-60-01 | PS5 - Milestone F | 5 | Closed | 23 | 45 | AUGUST
T-706-6456 | PS5-10-OB-6396A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-01-17 | PS5-08-02 | PS5 - Milestone B | 1.1 | Closed | 13 | 7 | JANUARY
T-550-6457 | PS5-38-OB-6847C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone D | 3 | In progress |  | 48 | DECEMBER
T-728-6458 | PS5-97-OB-7750D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-05-05 | PS5-06-02 | PS5 - Milestone E | 4 | Closed | 4 | 38 | MAY
T-479-6459 | PS5-61-IK-3167D | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone E | 4 | In progress |  | 40 | AUGUST
T-950-6460 | PS5-79-OB-3395B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-04-08 | PS5-01-01 | PS5 - Milestone D | 3 | Closed | 29 | 37 | APRIL
T-341-6461 | PS5-15-UR-8405C | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone A | 1 | To be completed |  | 16 | AUGUST
T-190-6462 | PS5-85-OB-7474B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-07-13 | PS5-61-07 | PS5 - Milestone F | 5 | Closed | 31 | 10 | JULY
T-833-6463 | PS5-34-UR-8167D | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-05-17 | PS5-07-01 | PS5 - Milestone F | 5 | Closed | 36 | 11 | MAY
T-712-6464 | PS5-84-OB-7813B | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone D | 3 | On hold |  | 40 | AUGUST
T-424-6465 | PS5-41-OB-1491C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | On hold |  | 37 | AUGUST
T-657-6466 | PS5-47-OB-7941B | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-09-22 | PS5-01-05 | PS5 - Milestone I | 8 | Closed | 40 | 21 | SEPTEMBER
T-373-6467 | PS5-44-OB-9539C | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone A | 1 | To be completed |  | 12 | AUGUST
T-176-6468 | PS5-03-IK-7287B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone C | 2 | In progress |  | 42 | NOVEMBER
T-883-6469 | PS5-42-OB-4727D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone D | 3 | In progress |  | 26 | SEPTEMBER
T-884-6470 | PS5-69-OB-8406D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | To be completed |  | 16 | NOVEMBER
T-277-6471 | PS5-20-UR-7629A | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-08-07 | PS5-04-01 | PS5 - Milestone F | 5 | Closed | 33 | 29 | AUGUST
T-336-6472 | PS5-22-UR-5041B | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-08-05 | PS5-63-01 | PS5 - Milestone E | 4 | Closed | 22 | 46 | AUGUST
T-904-6473 | PS5-38-IK-9665C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-02-14 | PS5-12-02 | PS5 - Milestone E | 4 | Closed | 48 | 20 | FEBRUARY
T-494-6474 | PS5-28-UR-3564B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-08-17 | PS5-03-03 | PS5 - Milestone C | 2 | Closed | 34 | 10 | AUGUST
T-096-6475 | PS5-83-OB-8782A | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone B | 1.1 | To be completed |  | 26 | SEPTEMBER
T-199-6476 | PS5-32-UR-9663A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | To be completed |  | 23 | NOVEMBER
T-185-6477 | PS5-37-UR-5069B | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-10-02 | PS5-62-02 | PS5 - Milestone C | 2 | Closed | 20 | 43 | OCTOBER
T-925-6478 | PS5-56-UR-5896D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone I | 8 | To be completed |  | 34 | NOVEMBER
T-593-6479 | PS5-69-IK-5196A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone H | 7 | To be completed |  | 16 | SEPTEMBER
T-498-6480 | PS5-08-OB-6532A | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-09-01 | PS5-10-05 | PS5 - Milestone D | 3 | Closed | 31 | 41 | SEPTEMBER
T-113-6481 | PS5-82-OB-2055D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | To be completed |  | 30 | OCTOBER
T-728-6482 | PS5-95-OB-7899D | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone D | 3 | On hold |  | 8 | OCTOBER
T-829-6483 | PS5-43-IK-5313D | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-12-06 | PS5-05-02 | PS5 - Milestone F | 5 | Closed | 30 | 37 | DECEMBER
T-524-6484 | PS5-36-OB-3719C | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-11-24 | PS5-60-07 | PS5 - Milestone H | 7 | Closed | 38 | 4 | NOVEMBER
T-236-6485 | PS5-70-UR-9360D | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone E | 4 | In progress |  | 6 | OCTOBER
T-515-6486 | PS5-71-OB-7265D | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | In progress |  | 4 | AUGUST
T-865-6487 | PS5-89-UR-2303B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone A | 1 | In progress |  | 7 | SEPTEMBER
T-402-6488 | PS5-93-OB-5904B | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone H | 7 | To be completed |  | 38 | DECEMBER
T-648-6489 | PS5-24-OB-6947C | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone B | 1.1 | To be completed |  | 46 | DECEMBER
T-004-6490 | PS5-55-UR-7816B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-08-02 | PS5-01-09 | PS5 - Milestone D | 3 | Closed | 17 | 25 | AUGUST
T-101-6491 | PS5-88-OB-5246C | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-02-23 | PS5-63-04 | PS5 - Milestone C | 2 | Closed | 39 | 30 | FEBRUARY
T-501-6492 | PS5-72-UR-6911B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-03-19 | PS5-82-01 | PS5 - Milestone C | 2 | Closed | 22 | 18 | MARCH
T-123-6493 | PS5-43-UR-5471B | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | To be completed |  | 11 | AUGUST
T-726-6494 | PS5-38-OB-5044D | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone D | 3 | On hold |  | 17 | OCTOBER
T-071-6495 | PS5-80-UR-7009A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-05-06 | PS5-60-01 | PS5 - Milestone A | 1 | Closed | 40 | 39 | MAY
T-705-6496 | PS5-07-IK-9048A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone A | 1 | To be completed |  | 4 | SEPTEMBER
T-544-6497 | PS5-16-IK-5418A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone D | 3 | In progress |  | 30 | OCTOBER
T-654-6498 | PS5-68-IK-3894A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone F | 5 | In progress |  | 8 | AUGUST
T-758-6499 | PS5-84-UR-8884B | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-06-27 | PS5-08-02 | PS5 - Milestone A | 1 | Closed | 28 | 45 | JUNE
T-262-6500 | PS5-72-OB-4000C | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-11-09 | PS5-62-01 | PS5 - Milestone F | 5 | Closed | 10 | 23 | NOVEMBER
T-207-6501 | PS5-98-UR-8609D | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone A | 1 | To be completed |  | 27 | NOVEMBER
T-365-6502 | PS5-22-UR-1277A | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone I | 8 | In progress |  | 45 | NOVEMBER
T-742-6503 | PS5-85-OB-6410A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-12-27 | PS5-60-01 | PS5 - Milestone B | 1.1 | Closed | 35 | 33 | DECEMBER
T-295-6504 | PS5-98-UR-3371A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone H | 7 | In progress |  | 18 | NOVEMBER
T-394-6505 | PS5-27-IK-9617A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone I | 8 | To be completed |  | 7 | NOVEMBER
T-239-6506 | PS5-65-UR-9523C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-09-25 | PS5-99-02 | PS5 - Milestone D | 3 | Closed | 47 | 26 | SEPTEMBER
T-904-6507 | PS5-95-OB-4817B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-01-25 | PS5-12-01 | PS5 - Milestone F | 5 | Closed | 44 | 16 | JANUARY
T-274-6508 | PS5-92-UR-9520D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone F | 5 | On hold |  | 21 | NOVEMBER
T-177-6509 | PS5-41-OB-5521B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-03-19 | PS5-03-01 | PS5 - Milestone H | 7 | Closed | 16 | 31 | MARCH
T-887-6510 | PS5-30-OB-8852C | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone H | 7 | On hold |  | 36 | OCTOBER
T-986-6511 | PS5-35-OB-1449D | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone G | 6 | In progress |  | 27 | AUGUST
T-612-6512 | PS5-06-OB-9724C | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone I | 8 | In progress |  | 18 | DECEMBER
T-525-6513 | PS5-98-OB-8861A | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone C | 2 | To be completed |  | 25 | NOVEMBER
T-363-6514 | PS5-08-UR-8447A | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-01-15 | PS5-06-03 | PS5 - Milestone I | 8 | Closed | 13 | 35 | JANUARY
T-698-6515 | PS5-15-UR-6004B | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-06-03 | PS5-01-04 | PS5 - Milestone E | 4 | Closed | 9 | 32 | JUNE
T-244-6516 | PS5-17-UR-4563D | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-12-03 | PS5-61-07 | PS5 - Milestone H | 7 | Closed | 45 | 17 | DECEMBER
T-284-6517 | PS5-08-OB-4838D | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | In progress |  | 24 | AUGUST
T-694-6518 | PS5-91-OB-4027B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-02-23 | PS5-05-02 | PS5 - Milestone F | 5 | Closed | 8 | 22 | FEBRUARY
T-032-6519 | PS5-02-OB-4677D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone C | 2 | To be completed |  | 42 | NOVEMBER
T-151-6520 | PS5-82-OB-8299D | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-10-04 | PS5-09-03 | PS5 - Milestone I | 8 | Closed | 28 | 43 | OCTOBER
T-747-6521 | PS5-18-IK-7921D | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-04-06 | PS5-82-01 | PS5 - Milestone B | 1.1 | Closed | 11 | 17 | APRIL
T-202-6522 | PS5-77-OB-1178B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone H | 7 | To be completed |  | 26 | DECEMBER
T-426-6523 | PS5-59-OB-6396A | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-10-04 | PS5-09-04 | PS5 - Milestone D | 3 | Closed | 9 | 31 | OCTOBER
T-815-6524 | PS5-46-UR-6474B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone A | 1 | In progress |  | 23 | OCTOBER
T-505-6525 | PS5-79-UR-4372C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone H | 7 | In progress |  | 45 | SEPTEMBER
T-578-6526 | PS5-54-OB-1531D | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone D | 3 | In progress |  | 36 | AUGUST
T-039-6527 | PS5-07-UR-3797D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-03-13 | PS5-01-09 | PS5 - Milestone H | 7 | Closed | 6 | 38 | MARCH
T-760-6528 | PS5-50-OB-9930C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone E | 4 | In progress |  | 23 | SEPTEMBER
T-319-6529 | PS5-31-IK-7109D | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone H | 7 | To be completed |  | 46 | OCTOBER
T-988-6530 | PS5-70-UR-7137C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-09-24 | PS5-60-10 | PS5 - Milestone I | 8 | Closed | 48 | 34 | SEPTEMBER
T-337-6531 | PS5-07-OB-3394C | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | In progress |  | 7 | AUGUST
T-518-6532 | PS5-83-OB-1434C | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone C | 2 | In progress |  | 44 | SEPTEMBER
T-317-6533 | PS5-65-IK-6884D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone E | 4 | In progress |  | 24 | NOVEMBER
T-704-6534 | PS5-32-IK-6491A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-01-14 | PS5-10-04 | PS5 - Milestone C | 2 | Closed | 41 | 9 | JANUARY
T-187-6535 | PS5-54-OB-8468D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-04-20 | PS5-09-01 | PS5 - Milestone I | 8 | Closed | 31 | 39 | APRIL
T-669-6536 | PS5-36-UR-4599C | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone D | 3 | To be completed |  | 33 | SEPTEMBER
T-728-6537 | PS5-73-OB-6232D | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone G | 6 | To be completed |  | 14 | NOVEMBER
T-317-6538 | PS5-55-IK-5211C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-09-11 | PS5-10-04 | PS5 - Milestone C | 2 | Closed | 48 | 13 | SEPTEMBER
T-390-6539 | PS5-34-UR-5898A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone D | 3 | To be completed |  | 24 | SEPTEMBER
T-876-6540 | PS5-17-UR-1963D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone C | 2 | In progress |  | 21 | DECEMBER
T-815-6541 | PS5-78-IK-6074C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-04-22 | PS5-01-06 | PS5 - Milestone A | 1 | Closed | 35 | 18 | APRIL
T-908-6542 | PS5-15-UR-6556A | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-10-04 | PS5-08-02 | PS5 - Milestone A | 1 | Closed | 44 | 31 | OCTOBER
T-047-6543 | PS5-11-OB-4529D | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-10-02 | PS5-03-03 | PS5 - Milestone C | 2 | Closed | 26 | 12 | OCTOBER
T-130-6544 | PS5-28-IK-6370C | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone E | 4 | On hold |  | 44 | DECEMBER
T-254-6545 | PS5-01-UR-2379C | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone E | 4 | To be completed |  | 16 | OCTOBER
T-278-6546 | PS5-04-OB-6752A | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone E | 4 | On hold |  | 34 | OCTOBER
T-635-6547 | PS5-62-OB-4390A | CQM04 - Vessel | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone D | 3 | To be completed |  | 38 | SEPTEMBER
T-314-6548 | PS5-72-UR-5917B | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone B | 1.1 | In progress |  | 44 | DECEMBER
T-437-6549 | PS5-11-OB-4100C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone B | 1.1 | To be completed |  | 41 | AUGUST
T-798-6550 | PS5-33-IK-8130B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-06-09 | PS5-12-02 | PS5 - Milestone D | 3 | Closed | 39 | 48 | JUNE
T-467-6551 | PS5-24-UR-4351B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone H | 7 | To be completed |  | 35 | NOVEMBER
T-469-6552 | PS5-02-OB-1342A | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | On hold |  | 27 | NOVEMBER
T-784-6553 | PS5-04-OB-3813B | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone D | 3 | To be completed |  | 19 | SEPTEMBER
T-724-6554 | PS5-62-UR-8810B | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone B | 1.1 | In progress |  | 19 | OCTOBER
T-638-6555 | PS5-98-OB-4677B | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-06-10 | PS5-01-05 | PS5 - Milestone E | 4 | Closed | 7 | 28 | JUNE
T-350-6556 | PS5-26-UR-2396C | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-10-03 | PS5-12-01 | PS5 - Milestone B | 1.1 | Closed | 44 | 33 | OCTOBER
T-163-6557 | PS5-93-IK-7283B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone E | 4 | On hold |  | 28 | SEPTEMBER
T-121-6558 | PS5-08-UR-1146A | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone I | 8 | To be completed |  | 48 | AUGUST
T-071-6559 | PS5-86-OB-6637A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-01-07 | PS5-13-01 | PS5 - Milestone D | 3 | Closed | 47 | 36 | JANUARY
T-453-6560 | PS5-25-OB-4158B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | To be completed |  | 5 | SEPTEMBER
T-631-6561 | PS5-96-OB-2196B | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone F | 5 | On hold |  | 25 | SEPTEMBER
T-545-6562 | PS5-84-UR-1787A | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-10-06 | PS5-01-08 | PS5 - Milestone F | 5 | Closed | 13 | 28 | OCTOBER
T-400-6563 | PS5-62-OB-9801A | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | On hold |  | 36 | NOVEMBER
T-500-6564 | PS5-57-UR-9822B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone G | 6 | In progress |  | 21 | DECEMBER
T-306-6565 | PS5-77-OB-5528D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | In progress |  | 48 | SEPTEMBER
T-451-6566 | PS5-74-OB-1517C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-17 | PS5-60-04 | PS5 - Milestone E | 4 | Closed | 13 | 47 | MAY
T-319-6567 | PS5-70-OB-1772C | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-04-05 | PS5-01-03 | PS5 - Milestone B | 1.1 | Closed | 17 | 23 | APRIL
T-702-6568 | PS5-42-OB-2930D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone A | 1 | In progress |  | 26 | DECEMBER
T-091-6569 | PS5-20-UR-8478D | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone F | 5 | In progress |  | 38 | DECEMBER
T-378-6570 | PS5-76-IK-8735A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-01-07 | PS5-02-01 | PS5 - Milestone D | 3 | Closed | 24 | 21 | JANUARY
T-222-6571 | PS5-55-OB-7303D | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone G | 6 | To be completed |  | 19 | NOVEMBER
T-906-6572 | PS5-08-OB-1867A | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone F | 5 | To be completed |  | 37 | NOVEMBER
T-516-6573 | PS5-86-UR-4253C | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone G | 6 | In progress |  | 17 | AUGUST
T-303-6574 | PS5-86-UR-7954A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone I | 8 | To be completed |  | 39 | NOVEMBER
T-870-6575 | PS5-06-OB-7368B | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone B | 1.1 | To be completed |  | 43 | AUGUST
T-098-6576 | PS5-52-IK-9983C | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-03-14 | PS5-09-01 | PS5 - Milestone B | 1.1 | Closed | 47 | 22 | MARCH
T-756-6577 | PS5-40-IK-9818B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-06-10 | PS5-04-04 | PS5 - Milestone F | 5 | Closed | 24 | 4 | JUNE
T-021-6578 | PS5-34-IK-6141D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone F | 5 | To be completed |  | 30 | NOVEMBER
T-088-6579 | PS5-69-IK-2870B | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone E | 4 | To be completed |  | 42 | AUGUST
T-817-6580 | PS5-99-IK-3575D | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | On hold |  | 39 | DECEMBER
T-629-6581 | PS5-88-UR-9142C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone E | 4 | On hold |  | 21 | SEPTEMBER
T-641-6582 | PS5-33-IK-7764D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-08-06 | PS5-01-09 | PS5 - Milestone D | 3 | Closed | 10 | 20 | AUGUST
T-232-6583 | PS5-80-UR-5895C | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-01-24 | PS5-08-01 | PS5 - Milestone D | 3 | Closed | 27 | 15 | JANUARY
T-021-6584 | PS5-98-UR-1618A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone B | 1.1 | On hold |  | 48 | AUGUST
T-384-6585 | PS5-10-OB-9538B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone E | 4 | In progress |  | 48 | OCTOBER
T-673-6586 | PS5-93-OB-3297A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone A | 1 | To be completed |  | 17 | AUGUST
T-944-6587 | PS5-50-UR-2168C | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | To be completed |  | 6 | AUGUST
T-888-6588 | PS5-27-OB-8099C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-01-28 | PS5-09-03 | PS5 - Milestone I | 8 | Closed | 6 | 20 | JANUARY
T-371-6589 | PS5-14-OB-1386B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-10-25 | PS5-05-01 | PS5 - Milestone A | 1 | Closed | 48 | 20 | OCTOBER
T-524-6590 | PS5-68-OB-3871D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone F | 5 | To be completed |  | 27 | DECEMBER
T-460-6591 | PS5-36-OB-7470C | CQX04 - Painting & Coating | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone E | 4 | On hold |  | 30 | NOVEMBER
T-617-6592 | PS5-37-OB-6025C | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-08-10 | PS5-08-02 | PS5 - Milestone I | 8 | Closed | 45 | 26 | AUGUST
T-839-6593 | PS5-67-UR-2430D | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone H | 7 | On hold |  | 16 | OCTOBER
T-135-6594 | PS5-64-OB-3086A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone F | 5 | In progress |  | 33 | SEPTEMBER
T-633-6595 | PS5-34-OB-9319B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-11-09 | PS5-60-07 | PS5 - Milestone H | 7 | Closed | 7 | 39 | NOVEMBER
T-486-6596 | PS5-17-OB-4152C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone D | 3 | To be completed |  | 38 | SEPTEMBER
T-945-6597 | PS5-09-IK-5033B | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone H | 7 | In progress |  | 26 | NOVEMBER
T-288-6598 | PS5-52-OB-4122C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone E | 4 | In progress |  | 48 | NOVEMBER
T-390-6599 | PS5-53-OB-8808C | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone F | 5 | To be completed |  | 7 | SEPTEMBER
T-738-6600 | PS5-78-OB-5464D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone B | 1.1 | To be completed |  | 37 | NOVEMBER
T-940-6601 | PS5-74-IK-1596A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone H | 7 | To be completed |  | 13 | DECEMBER
T-577-6602 | PS5-53-IK-9299B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | To be completed |  | 39 | AUGUST
T-517-6603 | PS5-35-IK-6058B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone I | 8 | To be completed |  | 48 | NOVEMBER
T-953-6604 | PS5-14-IK-1725B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-01-17 | PS5-10-01 | PS5 - Milestone H | 7 | Closed | 24 | 4 | JANUARY
T-905-6605 | PS5-30-OB-8906A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | In progress |  | 9 | DECEMBER
T-129-6606 | PS5-83-OB-6269B | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | To be completed |  | 20 | OCTOBER
T-652-6607 | PS5-07-OB-1806C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone H | 7 | To be completed |  | 19 | NOVEMBER
T-035-6608 | PS5-23-IK-5986D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-04-14 | PS5-05-02 | PS5 - Milestone F | 5 | Closed | 31 | 5 | APRIL
T-755-6609 | PS5-78-OB-4714B | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone A | 1 | To be completed |  | 12 | NOVEMBER
T-800-6610 | PS5-02-OB-8698A | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-11-28 | PS5-62-02 | PS5 - Milestone C | 2 | Closed | 11 | 8 | NOVEMBER
T-782-6611 | PS5-53-UR-8060C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone A | 1 | In progress |  | 46 | NOVEMBER
T-159-6612 | PS5-10-IK-5911C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone G | 6 | To be completed |  | 37 | SEPTEMBER
T-395-6613 | PS5-65-OB-5719C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-01-10 | PS5-82-01 | PS5 - Milestone A | 1 | Closed | 40 | 36 | JANUARY
T-093-6614 | PS5-09-IK-6036B | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone B | 1.1 | In progress |  | 27 | SEPTEMBER
T-758-6615 | PS5-14-UR-7958B | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-10-13 | PS5-02-03 | PS5 - Milestone H | 7 | Closed | 33 | 33 | OCTOBER
T-628-6616 | PS5-84-OB-4848B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | To be completed |  | 28 | SEPTEMBER
T-579-6617 | PS5-94-IK-5779C | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone B | 1.1 | On hold |  | 11 | SEPTEMBER
T-437-6618 | PS5-16-IK-1699A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-08-03 | PS5-05-03 | PS5 - Milestone E | 4 | Closed | 33 | 42 | AUGUST
T-553-6619 | PS5-99-IK-2151B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-03-21 | PS5-03-03 | PS5 - Milestone F | 5 | Closed | 32 | 29 | MARCH
T-311-6620 | PS5-58-IK-3827B | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-08-21 | PS5-01-06 | PS5 - Milestone C | 2 | Closed | 37 | 6 | AUGUST
T-874-6621 | PS5-24-IK-8762C | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone G | 6 | In progress |  | 25 | OCTOBER
T-058-6622 | PS5-36-OB-9385C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-03-10 | PS5-62-02 | PS5 - Milestone C | 2 | Closed | 17 | 43 | MARCH
T-746-6623 | PS5-26-IK-3337D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | In progress |  | 48 | OCTOBER
T-047-6624 | PS5-11-IK-4805C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone C | 2 | In progress |  | 42 | SEPTEMBER
T-790-6625 | PS5-97-IK-8065A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone E | 4 | To be completed |  | 11 | DECEMBER
T-366-6626 | PS5-29-OB-8655B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-11-04 | PS5-99-02 | PS5 - Milestone E | 4 | Closed | 43 | 47 | NOVEMBER
T-506-6627 | PS5-80-UR-7529C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-03-20 | PS5-11-02 | PS5 - Milestone F | 5 | Closed | 46 | 26 | MARCH
T-079-6628 | PS5-72-IK-2454C | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | On hold |  | 37 | OCTOBER
T-891-6629 | PS5-42-OB-6074C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-06-24 | PS5-05-03 | PS5 - Milestone G | 6 | Closed | 10 | 29 | JUNE
T-130-6630 | PS5-63-OB-5558A | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | To be completed |  | 25 | SEPTEMBER
T-740-6631 | PS5-46-OB-9607B | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone G | 6 | In progress |  | 35 | DECEMBER
T-770-6632 | PS5-89-IK-6282D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-10-19 | PS5-07-04 | PS5 - Milestone G | 6 | Closed | 4 | 35 | OCTOBER
T-237-6633 | PS5-98-IK-1509A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | In progress |  | 14 | SEPTEMBER
T-647-6634 | PS5-13-IK-1796B | CQX04 - Painting & Coating | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone G | 6 | In progress |  | 32 | OCTOBER
T-882-6635 | PS5-09-OB-2736C | CQM01 - Pump Installation | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | In progress |  | 10 | SEPTEMBER
T-704-6636 | PS5-33-IK-8101C | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | To be completed |  | 30 | NOVEMBER
T-412-6637 | PS5-10-OB-7851B | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone A | 1 | To be completed |  | 26 | AUGUST
T-211-6638 | PS5-87-OB-5754D | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-08-08 | PS5-62-02 | PS5 - Milestone G | 6 | Closed | 41 | 27 | AUGUST
T-177-6639 | PS5-25-IK-5620B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone I | 8 | In progress |  | 22 | AUGUST
T-099-6640 | PS5-72-IK-1452D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone B | 1.1 | On hold |  | 20 | DECEMBER
T-318-6641 | PS5-72-IK-4111B | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-06-19 | PS5-10-04 | PS5 - Milestone F | 5 | Closed | 33 | 11 | JUNE
T-766-6642 | PS5-95-UR-6012D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone A | 1 | To be completed |  | 48 | AUGUST
T-293-6643 | PS5-20-IK-5925B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-06-01 | PS5-06-02 | PS5 - Milestone F | 5 | Closed | 39 | 40 | JUNE
T-512-6644 | PS5-12-OB-4765A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone F | 5 | On hold |  | 31 | NOVEMBER
T-472-6645 | PS5-62-IK-7005A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone H | 7 | To be completed |  | 31 | SEPTEMBER
T-075-6646 | PS5-32-IK-9921D | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-02-19 | PS5-10-04 | PS5 - Milestone I | 8 | Closed | 25 | 32 | FEBRUARY
T-058-6647 | PS5-59-OB-7031C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone G | 6 | In progress |  | 43 | OCTOBER
T-738-6648 | PS5-58-UR-2089D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone I | 8 | To be completed |  | 25 | AUGUST
T-909-6649 | PS5-66-IK-3553C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-11-17 | PS5-01-01 | PS5 - Milestone I | 8 | Closed | 43 | 29 | NOVEMBER
T-384-6650 | PS5-94-IK-5090B | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone E | 4 | To be completed |  | 38 | NOVEMBER
T-047-6651 | PS5-53-IK-4186B | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-12-15 | PS5-99-02 | PS5 - Milestone B | 1.1 | Closed | 41 | 10 | DECEMBER
T-197-6652 | PS5-83-OB-4135B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-06-11 | PS5-99-01 | PS5 - Milestone D | 3 | Closed | 11 | 9 | JUNE
T-033-6653 | PS5-32-OB-7400D | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-09-28 | PS5-61-02 | PS5 - Milestone G | 6 | Closed | 5 | 21 | SEPTEMBER
T-616-6654 | PS5-43-OB-1725C | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-08-13 | PS5-02-02 | PS5 - Milestone I | 8 | Closed | 46 | 30 | AUGUST
T-761-6655 | PS5-62-IK-7707C | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | In progress |  | 28 | DECEMBER
T-869-6656 | PS5-42-OB-7227A | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone E | 4 | To be completed |  | 4 | DECEMBER
T-770-6657 | PS5-90-IK-2740D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-07-05 | PS5-06-02 | PS5 - Milestone B | 1.1 | Closed | 44 | 42 | JULY
T-615-6658 | PS5-58-IK-8461B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone G | 6 | On hold |  | 39 | OCTOBER
T-569-6659 | PS5-68-OB-1618A | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-02-03 | PS5-10-06 | PS5 - Milestone D | 3 | Closed | 15 | 12 | FEBRUARY
T-191-6660 | PS5-97-OB-4504B | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone G | 6 | To be completed |  | 28 | OCTOBER
T-291-6661 | PS5-60-IK-3553C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-08-17 | PS5-01-06 | PS5 - Milestone E | 4 | Closed | 12 | 46 | AUGUST
T-383-6662 | PS5-39-OB-6533B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone I | 8 | To be completed |  | 26 | AUGUST
T-935-6663 | PS5-49-IK-3940A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone G | 6 | To be completed |  | 44 | NOVEMBER
T-044-6664 | PS5-31-OB-2375B | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-02-08 | PS5-10-05 | PS5 - Milestone F | 5 | Closed | 45 | 40 | FEBRUARY
T-857-6665 | PS5-72-OB-8193C | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-10-16 | PS5-07-02 | PS5 - Milestone D | 3 | Closed | 29 | 34 | OCTOBER
T-529-6666 | PS5-88-IK-9852B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-11-10 | PS5-01-04 | PS5 - Milestone A | 1 | Closed | 27 | 18 | NOVEMBER
T-599-6667 | PS5-28-OB-6415D | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-07-14 | PS5-01-05 | PS5 - Milestone C | 2 | Closed | 26 | 43 | JULY
T-326-6668 | PS5-75-OB-1739D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone B | 1.1 | To be completed |  | 20 | AUGUST
T-652-6669 | PS5-43-OB-2311B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-10-04 | PS5-06-02 | PS5 - Milestone A | 1 | Closed | 32 | 29 | OCTOBER
T-322-6670 | PS5-07-OB-3253C | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-09-13 | PS5-08-01 | PS5 - Milestone C | 2 | Closed | 21 | 24 | SEPTEMBER
T-174-6671 | PS5-32-IK-8251B | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-01-17 | PS5-60-04 | PS5 - Milestone F | 5 | Closed | 42 | 6 | JANUARY
T-080-6672 | PS5-87-IK-8437A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-02-21 | PS5-03-23 | PS5 - Milestone B | 1.1 | Closed | 31 | 35 | FEBRUARY
T-674-6673 | PS5-57-OB-2427C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone E | 4 | To be completed |  | 39 | DECEMBER
T-060-6674 | PS5-94-IK-3694B | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone A | 1 | To be completed |  | 35 | DECEMBER
T-742-6675 | PS5-67-IK-3612C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-07-20 | PS5-07-01 | PS5 - Milestone D | 3 | Closed | 29 | 15 | JULY
T-873-6676 | PS5-31-IK-5744C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone B | 1.1 | In progress |  | 28 | OCTOBER
T-966-6677 | PS5-61-OB-4512B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone E | 4 | In progress |  | 7 | SEPTEMBER
T-168-6678 | PS5-19-IK-6821A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-10-09 | PS5-10-02 | PS5 - Milestone C | 2 | Closed | 38 | 46 | OCTOBER
T-620-6679 | PS5-96-OB-3441D | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-10-16 | PS5-62-01 | PS5 - Milestone B | 1.1 | Closed | 34 | 24 | OCTOBER
T-656-6680 | PS5-57-UR-4238C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone E | 4 | To be completed |  | 46 | AUGUST
T-467-6681 | PS5-30-OB-9689C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-05-18 | PS5-99-01 | PS5 - Milestone D | 3 | Closed | 29 | 21 | MAY
T-418-6682 | PS5-02-UR-3492C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-11-17 | PS5-03-01 | PS5 - Milestone G | 6 | Closed | 40 | 39 | NOVEMBER
T-739-6683 | PS5-02-UR-8461C | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-09-14 | PS5-05-02 | PS5 - Milestone H | 7 | Closed | 21 | 38 | SEPTEMBER
T-518-6684 | PS5-92-IK-4386C | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | To be completed |  | 42 | SEPTEMBER
T-028-6685 | PS5-65-OB-3923C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone H | 7 | To be completed |  | 23 | NOVEMBER
T-195-6686 | PS5-26-OB-8989D | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone H | 7 | In progress |  | 9 | SEPTEMBER
T-568-6687 | PS5-95-UR-6768C | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone G | 6 | To be completed |  | 9 | OCTOBER
T-700-6688 | PS5-41-OB-3706A | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone H | 7 | To be completed |  | 32 | OCTOBER
T-194-6689 | PS5-17-OB-2338A | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-06-04 | PS5-82-02 | PS5 - Milestone I | 8 | Closed | 37 | 31 | JUNE
T-114-6690 | PS5-87-IK-7842B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone G | 6 | In progress |  | 20 | OCTOBER
T-260-6691 | PS5-86-OB-2196A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | To be completed |  | 25 | SEPTEMBER
T-384-6692 | PS5-78-OB-6707B | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-08-27 | PS5-01-07 | PS5 - Milestone C | 2 | Closed | 35 | 21 | AUGUST
T-322-6693 | PS5-06-IK-8300B | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone C | 2 | On hold |  | 23 | NOVEMBER
T-420-6694 | PS5-52-UR-2570B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-12-04 | PS5-10-01 | PS5 - Milestone I | 8 | Closed | 27 | 32 | DECEMBER
T-823-6695 | PS5-99-OB-7125C | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone B | 1.1 | In progress |  | 39 | NOVEMBER
T-183-6696 | PS5-47-OB-8067D | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | To be completed |  | 26 | AUGUST
T-862-6697 | PS5-89-IK-2794D | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone B | 1.1 | On hold |  | 4 | SEPTEMBER
T-452-6698 | PS5-15-UR-7752C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone A | 1 | On hold |  | 40 | AUGUST
T-514-6699 | PS5-36-OB-9948B | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone D | 3 | To be completed |  | 5 | NOVEMBER
T-132-6700 | PS5-28-UR-6114B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-10-15 | PS5-03-03 | PS5 - Milestone C | 2 | Closed | 24 | 26 | OCTOBER
T-904-6701 | PS5-54-UR-7117C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone G | 6 | To be completed |  | 21 | AUGUST
T-082-6702 | PS5-58-OB-9477C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-09-19 | PS5-82-07 | PS5 - Milestone C | 2 | Closed | 6 | 38 | SEPTEMBER
T-598-6703 | PS5-16-OB-9964A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | To be completed |  | 47 | AUGUST
T-099-6704 | PS5-69-OB-1601C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone C | 2 | To be completed |  | 27 | AUGUST
T-756-6705 | PS5-70-OB-8454D | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone D | 3 | On hold |  | 37 | NOVEMBER
T-445-6706 | PS5-25-IK-4157C | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone G | 6 | To be completed |  | 48 | NOVEMBER
T-166-6707 | PS5-58-OB-4000C | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone E | 4 | In progress |  | 34 | OCTOBER
T-483-6708 | PS5-28-OB-1229D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-02-07 | PS5-12-02 | PS5 - Milestone D | 3 | Closed | 26 | 36 | FEBRUARY
T-694-6709 | PS5-06-OB-2803B | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone F | 5 | In progress |  | 22 | AUGUST
T-034-6710 | PS5-45-OB-2698A | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-04-25 | PS5-61-07 | PS5 - Milestone D | 3 | Closed | 19 | 22 | APRIL
T-302-6711 | PS5-24-OB-4111D | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-05-24 | PS5-99-02 | PS5 - Milestone A | 1 | Closed | 43 | 32 | MAY
T-346-6712 | PS5-77-OB-4165A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone C | 2 | On hold |  | 27 | OCTOBER
T-355-6713 | PS5-95-OB-5856A | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone H | 7 | On hold |  | 18 | DECEMBER
T-110-6714 | PS5-51-UR-1492A | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone I | 8 | On hold |  | 16 | DECEMBER
T-712-6715 | PS5-90-OB-3589B | CQM02 - Compressor | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-01-01 | PS5-01-02 | PS5 - Milestone C | 2 | Closed | 10 | 13 | JANUARY
T-759-6716 | PS5-84-IK-9593D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-04-27 | PS5-06-02 | PS5 - Milestone C | 2 | Closed | 12 | 18 | APRIL
T-673-6717 | PS5-02-IK-4164B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone I | 8 | In progress |  | 33 | SEPTEMBER
T-693-6718 | PS5-36-OB-9608A | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-02-09 | PS5-10-03 | PS5 - Milestone H | 7 | Closed | 12 | 21 | FEBRUARY
T-367-6719 | PS5-43-OB-3387D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone F | 5 | To be completed |  | 32 | NOVEMBER
T-224-6720 | PS5-45-OB-6464D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone I | 8 | On hold |  | 15 | AUGUST
T-315-6721 | PS5-37-OB-6732B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-11-22 | PS5-63-01 | PS5 - Milestone E | 4 | Closed | 6 | 9 | NOVEMBER
T-804-6722 | PS5-41-IK-2401A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-01-23 | PS5-10-01 | PS5 - Milestone H | 7 | Closed | 39 | 21 | JANUARY
T-753-6723 | PS5-33-UR-1214A | CQX04 - Painting & Coating | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone E | 4 | To be completed |  | 16 | SEPTEMBER
T-177-6724 | PS5-09-IK-1566C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone D | 3 | On hold |  | 30 | OCTOBER
T-060-6725 | PS5-59-UR-8210A | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone F | 5 | To be completed |  | 15 | AUGUST
T-527-6726 | PS5-58-UR-3929A | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-07-15 | PS5-09-01 | PS5 - Milestone I | 8 | Closed | 34 | 38 | JULY
T-221-6727 | PS5-86-OB-4109C | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone G | 6 | On hold |  | 22 | AUGUST
T-983-6728 | PS5-95-IK-7625D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone C | 2 | To be completed |  | 7 | OCTOBER
T-378-6729 | PS5-29-OB-6865C | CQM04 - Vessel | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone D | 3 | In progress |  | 25 | SEPTEMBER
T-144-6730 | PS5-94-OB-1105A | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-24 | PS5-60-07 | PS5 - Milestone D | 3 | Closed | 34 | 46 | APRIL
T-326-6731 | PS5-11-OB-6452D | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | To be completed |  | 45 | DECEMBER
T-777-6732 | PS5-24-UR-4980C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-01-17 | PS5-82-07 | PS5 - Milestone H | 7 | Closed | 7 | 30 | JANUARY
T-010-6733 | PS5-33-OB-2086D | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone D | 3 | In progress |  | 19 | NOVEMBER
T-417-6734 | PS5-88-UR-2870A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone C | 2 | In progress |  | 35 | DECEMBER
T-813-6735 | PS5-23-OB-6126D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-07-04 | PS5-82-02 | PS5 - Milestone E | 4 | Closed | 41 | 48 | JULY
T-900-6736 | PS5-67-UR-8223D | CQE04 - Transformer | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-08-24 | PS5-04-02 | PS5 - Milestone D | 3 | Closed | 38 | 29 | AUGUST
T-694-6737 | PS5-39-OB-1089B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | To be completed |  | 25 | AUGUST
T-465-6738 | PS5-71-UR-1604B | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone B | 1.1 | To be completed |  | 34 | NOVEMBER
T-254-6739 | PS5-24-OB-6328A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-10-17 | PS5-10-02 | PS5 - Milestone E | 4 | Closed | 41 | 13 | OCTOBER
T-323-6740 | PS5-93-OB-3407A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone A | 1 | To be completed |  | 46 | SEPTEMBER
T-936-6741 | PS5-60-UR-2530C | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-07-15 | PS5-12-02 | PS5 - Milestone C | 2 | Closed | 22 | 47 | JULY
T-165-6742 | PS5-13-UR-2973A | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone H | 7 | To be completed |  | 17 | AUGUST
T-274-6743 | PS5-72-OB-1469C | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone E | 4 | To be completed |  | 45 | AUGUST
T-726-6744 | PS5-34-OB-3427A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-02-23 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 29 | 40 | FEBRUARY
T-767-6745 | PS5-67-OB-3034D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-09-19 | PS5-04-01 | PS5 - Milestone C | 2 | Closed | 25 | 9 | SEPTEMBER
T-576-6746 | PS5-88-UR-9527C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone D | 3 | On hold |  | 30 | NOVEMBER
T-483-6747 | PS5-64-OB-9197D | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-03-13 | PS5-08-01 | PS5 - Milestone I | 8 | Closed | 37 | 6 | MARCH
T-421-6748 | PS5-04-IK-7847A | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone C | 2 | To be completed |  | 35 | OCTOBER
T-552-6749 | PS5-42-IK-1832D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-01-06 | PS5-01-03 | PS5 - Milestone B | 1.1 | Closed | 19 | 12 | JANUARY
T-170-6750 | PS5-94-OB-5901D | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-11-02 | PS5-09-01 | PS5 - Milestone G | 6 | Closed | 30 | 26 | NOVEMBER
T-256-6751 | PS5-77-OB-4852A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-02-25 | PS5-07-04 | PS5 - Milestone F | 5 | Closed | 6 | 26 | FEBRUARY
T-055-6752 | PS5-81-UR-8470D | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | In progress |  | 19 | DECEMBER
T-253-6753 | PS5-93-OB-7013B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone A | 1 | On hold |  | 18 | SEPTEMBER
T-976-6754 | PS5-02-OB-4536B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone B | 1.1 | In progress |  | 6 | OCTOBER
T-644-6755 | PS5-66-IK-4103D | CQM02 - Compressor | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone B | 1.1 | To be completed |  | 11 | DECEMBER
T-957-6756 | PS5-54-OB-8673D | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone B | 1.1 | In progress |  | 35 | DECEMBER
T-928-6757 | PS5-78-UR-6933C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-05-05 | PS5-10-06 | PS5 - Milestone D | 3 | Closed | 6 | 46 | MAY
T-010-6758 | PS5-67-IK-5438B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-02-10 | PS5-61-07 | PS5 - Milestone D | 3 | Closed | 15 | 4 | FEBRUARY
T-861-6759 | PS5-30-OB-4532D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-09-06 | PS5-03-01 | PS5 - Milestone A | 1 | Closed | 18 | 14 | SEPTEMBER
T-627-6760 | PS5-16-OB-9675D | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-11-04 | PS5-08-01 | PS5 - Milestone D | 3 | Closed | 26 | 26 | NOVEMBER
T-794-6761 | PS5-88-OB-7057C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone E | 4 | To be completed |  | 25 | OCTOBER
T-647-6762 | PS5-09-OB-4907A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone D | 3 | To be completed |  | 23 | NOVEMBER
T-159-6763 | PS5-55-OB-4177A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone E | 4 | In progress |  | 20 | NOVEMBER
T-433-6764 | PS5-03-OB-1284B | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | In progress |  | 22 | OCTOBER
T-558-6765 | PS5-77-OB-7084C | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone G | 6 | In progress |  | 12 | AUGUST
T-531-6766 | PS5-01-UR-8101C | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-01-23 | PS5-09-03 | PS5 - Milestone F | 5 | Closed | 42 | 5 | JANUARY
T-585-6767 | PS5-65-OB-1471A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone E | 4 | In progress |  | 17 | NOVEMBER
T-099-6768 | PS5-55-IK-9920D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone H | 7 | To be completed |  | 17 | NOVEMBER
T-580-6769 | PS5-74-IK-9778D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-04-05 | PS5-04-01 | PS5 - Milestone C | 2 | Closed | 41 | 21 | APRIL
T-231-6770 | PS5-83-OB-1260C | CQP04 - Hydrotest | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone D | 3 | On hold |  | 39 | DECEMBER
T-802-6771 | PS5-44-OB-6298C | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone B | 1.1 | In progress |  | 14 | AUGUST
T-484-6772 | PS5-08-OB-4083C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-07-13 | PS5-02-01 | PS5 - Milestone B | 1.1 | Closed | 48 | 25 | JULY
T-864-6773 | PS5-15-OB-3369D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-03-25 | PS5-02-01 | PS5 - Milestone B | 1.1 | Closed | 25 | 38 | MARCH
T-398-6774 | PS5-72-OB-5632C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-03-25 | PS5-99-03 | PS5 - Milestone I | 8 | Closed | 45 | 46 | MARCH
T-275-6775 | PS5-61-IK-6803C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-08-15 | PS5-06-01 | PS5 - Milestone G | 6 | Closed | 7 | 22 | AUGUST
T-313-6776 | PS5-38-OB-2128C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone H | 7 | To be completed |  | 44 | DECEMBER
T-919-6777 | PS5-66-UR-4781B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone F | 5 | On hold |  | 44 | DECEMBER
T-474-6778 | PS5-19-OB-2144D | CQM04 - Vessel | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-12 | PS5-60-07 | PS5 - Milestone C | 2 | Closed | 42 | 42 | JUNE
T-734-6779 | PS5-45-OB-9731C | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | In progress |  | 21 | SEPTEMBER
T-411-6780 | PS5-93-UR-7333A | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-07-12 | PS5-01-03 | PS5 - Milestone H | 7 | Closed | 8 | 21 | JULY
T-926-6781 | PS5-30-OB-3443A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone F | 5 | On hold |  | 42 | DECEMBER
T-515-6782 | PS5-64-UR-6388A | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-03-08 | PS5-06-02 | PS5 - Milestone D | 3 | Closed | 48 | 29 | MARCH
T-324-6783 | PS5-66-UR-3919A | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-12-09 | PS5-09-04 | PS5 - Milestone F | 5 | Closed | 45 | 35 | DECEMBER
T-693-6784 | PS5-95-IK-1885C | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-06-09 | PS5-13-01 | PS5 - Milestone B | 1.1 | Closed | 47 | 32 | JUNE
T-676-6785 | PS5-05-OB-4115A | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | On hold |  | 43 | OCTOBER
T-884-6786 | PS5-15-IK-8899D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone G | 6 | To be completed |  | 36 | SEPTEMBER
T-738-6787 | PS5-17-OB-7613C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone I | 8 | In progress |  | 10 | OCTOBER
T-194-6788 | PS5-82-UR-1978D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-05-13 | PS5-01-04 | PS5 - Milestone D | 3 | Closed | 4 | 46 | MAY
T-560-6789 | PS5-53-OB-5597D | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | To be completed |  | 18 | OCTOBER
T-086-6790 | PS5-36-UR-2402D | CQS03 - Deluge System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-08-05 | PS5-02-03 | PS5 - Milestone C | 2 | Closed | 16 | 45 | AUGUST
T-138-6791 | PS5-88-OB-3583B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-08-24 | PS5-05-02 | PS5 - Milestone H | 7 | Closed | 17 | 34 | AUGUST
T-285-6792 | PS5-41-IK-7980A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | In progress |  | 44 | NOVEMBER
T-121-6793 | PS5-75-UR-7478C | CQP02 - Valve Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-01-14 | PS5-01-01 | PS5 - Milestone G | 6 | Closed | 18 | 28 | JANUARY
T-718-6794 | PS5-35-OB-5504C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone G | 6 | On hold |  | 21 | DECEMBER
T-168-6795 | PS5-42-OB-7240A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-01-18 | PS5-07-01 | PS5 - Milestone G | 6 | Closed | 48 | 30 | JANUARY
T-202-6796 | PS5-64-OB-9771B | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone H | 7 | In progress |  | 21 | SEPTEMBER
T-484-6797 | PS5-93-IK-8952A | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone E | 4 | To be completed |  | 40 | OCTOBER
T-099-6798 | PS5-26-OB-5369B | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-10-04 | PS5-62-01 | PS5 - Milestone I | 8 | Closed | 47 | 4 | OCTOBER
T-758-6799 | PS5-68-UR-3345B | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | To be completed |  | 47 | DECEMBER
T-843-6800 | PS5-49-IK-9700A | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-03-18 | PS5-08-01 | PS5 - Milestone D | 3 | Closed | 14 | 20 | MARCH
T-602-6801 | PS5-36-UR-7933A | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone I | 8 | To be completed |  | 46 | DECEMBER
T-892-6802 | PS5-63-IK-1323C | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone C | 2 | In progress |  | 20 | DECEMBER
T-373-6803 | PS5-17-OB-9095C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-04-17 | PS5-07-04 | PS5 - Milestone A | 1 | Closed | 6 | 25 | APRIL
T-583-6804 | PS5-99-IK-4194D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-07-05 | PS5-03-03 | PS5 - Milestone A | 1 | Closed | 27 | 4 | JULY
T-323-6805 | PS5-29-OB-5357C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-06-06 | PS5-04-04 | PS5 - Milestone E | 4 | Closed | 9 | 26 | JUNE
T-206-6806 | PS5-69-OB-6703C | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | On hold |  | 35 | OCTOBER
T-136-6807 | PS5-53-UR-9443B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | In progress |  | 5 | DECEMBER
T-028-6808 | PS5-53-UR-2208D | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-09-13 | PS5-10-04 | PS5 - Milestone A | 1 | Closed | 14 | 6 | SEPTEMBER
T-281-6809 | PS5-68-UR-5812A | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-08-03 | PS5-12-02 | PS5 - Milestone B | 1.1 | Closed | 22 | 42 | AUGUST
T-881-6810 | PS5-64-UR-4073A | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-10-26 | PS5-10-01 | PS5 - Milestone F | 5 | Closed | 20 | 34 | OCTOBER
T-194-6811 | PS5-93-IK-9338D | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-01-22 | PS5-06-03 | PS5 - Milestone G | 6 | Closed | 26 | 7 | JANUARY
T-186-6812 | PS5-92-OB-4692B | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-04-20 | PS5-09-03 | PS5 - Milestone H | 7 | Closed | 25 | 35 | APRIL
T-507-6813 | PS5-03-IK-1257B | CQE02 - LV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone D | 3 | In progress |  | 17 | NOVEMBER
T-374-6814 | PS5-83-IK-8153C | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone G | 6 | On hold |  | 8 | OCTOBER
T-052-6815 | PS5-67-IK-4902A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone E | 4 | To be completed |  | 5 | AUGUST
T-607-6816 | PS5-63-IK-4201C | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-07-06 | PS5-61-01 | PS5 - Milestone I | 8 | Closed | 30 | 14 | JULY
T-815-6817 | PS5-87-IK-8698B | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone E | 4 | To be completed |  | 45 | AUGUST
T-319-6818 | PS5-93-UR-4102C | CQM01 - Pump Installation | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-01-03 | PS5-61-07 | PS5 - Milestone C | 2 | Closed | 37 | 17 | JANUARY
T-767-6819 | PS5-93-UR-6498D | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | On hold |  | 38 | NOVEMBER
T-251-6820 | PS5-79-OB-1210B | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone C | 2 | To be completed |  | 27 | OCTOBER
T-919-6821 | PS5-19-IK-2852C | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-09-25 | PS5-01-02 | PS5 - Milestone G | 6 | Closed | 38 | 22 | SEPTEMBER
T-046-6822 | PS5-06-IK-7503D | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | In progress |  | 48 | OCTOBER
T-080-6823 | PS5-25-IK-9033C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone E | 4 | On hold |  | 16 | SEPTEMBER
T-673-6824 | PS5-34-OB-1769A | CQS03 - Deluge System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-06-24 | PS5-08-01 | PS5 - Milestone H | 7 | Closed | 23 | 23 | JUNE
T-803-6825 | PS5-02-OB-4055D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | To be completed |  | 13 | NOVEMBER
T-568-6826 | PS5-56-OB-2206B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone F | 5 | In progress |  | 23 | DECEMBER
T-223-6827 | PS5-35-OB-3653C | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-12-27 | PS5-10-01 | PS5 - Milestone A | 1 | Closed | 24 | 10 | DECEMBER
T-231-6828 | PS5-13-IK-3828C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone I | 8 | On hold |  | 47 | NOVEMBER
T-359-6829 | PS5-09-OB-9020B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone B | 1.1 | On hold |  | 43 | NOVEMBER
T-430-6830 | PS5-36-IK-7582C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-10-13 | PS5-01-08 | PS5 - Milestone I | 8 | Closed | 38 | 44 | OCTOBER
T-033-6831 | PS5-52-OB-4659C | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-08-10 | PS5-10-04 | PS5 - Milestone H | 7 | Closed | 7 | 13 | AUGUST
T-592-6832 | PS5-16-OB-7623D | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-09-15 | PS5-08-01 | PS5 - Milestone B | 1.1 | Closed | 36 | 15 | SEPTEMBER
T-820-6833 | PS5-66-IK-6857D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | To be completed |  | 25 | DECEMBER
T-096-6834 | PS5-24-OB-9087D | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone H | 7 | In progress |  | 40 | SEPTEMBER
T-853-6835 | PS5-96-UR-5810B | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone A | 1 | In progress |  | 33 | AUGUST
T-876-6836 | PS5-20-OB-4543D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone A | 1 | To be completed |  | 28 | OCTOBER
T-574-6837 | PS5-41-OB-4444D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | To be completed |  | 4 | AUGUST
T-721-6838 | PS5-57-IK-2146C | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-06-18 | PS5-12-01 | PS5 - Milestone C | 2 | Closed | 11 | 43 | JUNE
T-832-6839 | PS5-17-IK-2576A | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone B | 1.1 | To be completed |  | 22 | SEPTEMBER
T-679-6840 | PS5-14-IK-8476B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-05-03 | PS5-82-07 | PS5 - Milestone G | 6 | Closed | 30 | 15 | MAY
T-992-6841 | PS5-71-OB-9004C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-08-14 | PS5-82-02 | PS5 - Milestone F | 5 | Closed | 19 | 13 | AUGUST
T-408-6842 | PS5-70-OB-1233D | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-08-22 | PS5-60-01 | PS5 - Milestone D | 3 | Closed | 36 | 6 | AUGUST
T-837-6843 | PS5-80-OB-5425A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-10-22 | PS5-62-02 | PS5 - Milestone E | 4 | Closed | 44 | 39 | OCTOBER
T-612-6844 | PS5-71-OB-2956D | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-02-05 | PS5-62-01 | PS5 - Milestone H | 7 | Closed | 28 | 25 | FEBRUARY
T-664-6845 | PS5-44-OB-5993A | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-02-05 | PS5-12-01 | PS5 - Milestone G | 6 | Closed | 18 | 13 | FEBRUARY
T-090-6846 | PS5-29-UR-2396C | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone A | 1 | To be completed |  | 10 | AUGUST
T-920-6847 | PS5-20-OB-7954C | CQM02 - Compressor | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone D | 3 | On hold |  | 37 | AUGUST
T-551-6848 | PS5-91-OB-9486A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-11-25 | PS5-60-01 | PS5 - Milestone D | 3 | Closed | 45 | 48 | NOVEMBER
T-620-6849 | PS5-11-IK-2983B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone A | 1 | To be completed |  | 39 | SEPTEMBER
T-680-6850 | PS5-79-IK-4422C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | In progress |  | 39 | OCTOBER
T-672-6851 | PS5-09-OB-8443A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone G | 6 | To be completed |  | 7 | NOVEMBER
T-618-6852 | PS5-64-OB-8001C | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone G | 6 | To be completed |  | 24 | NOVEMBER
T-242-6853 | PS5-85-UR-5339B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | To be completed |  | 18 | NOVEMBER
T-623-6854 | PS5-65-OB-9159B | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-10 | PS5-60-10 | PS5 - Milestone B | 1.1 | Closed | 27 | 21 | APRIL
T-508-6855 | PS5-72-OB-9681A | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-06-04 | PS5-04-02 | PS5 - Milestone D | 3 | Closed | 4 | 10 | JUNE
T-842-6856 | PS5-73-IK-6661B | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-03-24 | PS5-01-02 | PS5 - Milestone G | 6 | Closed | 36 | 45 | MARCH
T-370-6857 | PS5-61-OB-1089D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone E | 4 | To be completed |  | 42 | DECEMBER
T-455-6858 | PS5-02-UR-3713D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-06-15 | PS5-10-04 | PS5 - Milestone H | 7 | Closed | 28 | 29 | JUNE
T-270-6859 | PS5-98-IK-3945A | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-10-17 | PS5-61-01 | PS5 - Milestone E | 4 | Closed | 28 | 10 | OCTOBER
T-476-6860 | PS5-98-OB-8616C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | To be completed |  | 39 | DECEMBER
T-374-6861 | PS5-94-OB-4845A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone E | 4 | In progress |  | 37 | SEPTEMBER
T-082-6862 | PS5-68-OB-2057A | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-04-15 | PS5-01-08 | PS5 - Milestone B | 1.1 | Closed | 47 | 18 | APRIL
T-382-6863 | PS5-19-IK-8262C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone C | 2 | To be completed |  | 16 | OCTOBER
T-635-6864 | PS5-11-OB-1300C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone G | 6 | In progress |  | 41 | SEPTEMBER
T-979-6865 | PS5-51-OB-1782A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-07-25 | PS5-99-02 | PS5 - Milestone D | 3 | Closed | 20 | 36 | JULY
T-705-6866 | PS5-25-OB-1196C | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone I | 8 | On hold |  | 36 | AUGUST
T-060-6867 | PS5-13-IK-6950D | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone G | 6 | To be completed |  | 20 | OCTOBER
T-741-6868 | PS5-43-UR-9800D | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-09-02 | PS5-04-04 | PS5 - Milestone I | 8 | Closed | 39 | 4 | SEPTEMBER
T-180-6869 | PS5-08-OB-4375A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | To be completed |  | 38 | DECEMBER
T-162-6870 | PS5-40-OB-2560C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-06-22 | PS5-10-05 | PS5 - Milestone D | 3 | Closed | 39 | 36 | JUNE
T-666-6871 | PS5-28-OB-5431C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-05-07 | PS5-08-02 | PS5 - Milestone B | 1.1 | Closed | 46 | 37 | MAY
T-832-6872 | PS5-72-OB-3791A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone H | 7 | In progress |  | 26 | AUGUST
T-618-6873 | PS5-70-OB-7713D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-08-07 | PS5-10-06 | PS5 - Milestone D | 3 | Closed | 30 | 25 | AUGUST
T-660-6874 | PS5-52-OB-9278A | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | To be completed |  | 44 | SEPTEMBER
T-032-6875 | PS5-64-IK-9539D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-07-14 | PS5-03-02 | PS5 - Milestone G | 6 | Closed | 17 | 45 | JULY
T-949-6876 | PS5-01-OB-5019B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-12-21 | PS5-82-01 | PS5 - Milestone D | 3 | Closed | 20 | 45 | DECEMBER
T-270-6877 | PS5-95-IK-2524A | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone I | 8 | On hold |  | 41 | NOVEMBER
T-844-6878 | PS5-87-IK-3207A | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone G | 6 | On hold |  | 13 | DECEMBER
T-017-6879 | PS5-65-IK-9897A | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-07-03 | PS5-10-02 | PS5 - Milestone H | 7 | Closed | 9 | 26 | JULY
T-835-6880 | PS5-07-OB-1316A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-05-04 | PS5-10-05 | PS5 - Milestone H | 7 | Closed | 45 | 18 | MAY
T-768-6881 | PS5-82-OB-4408D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-06-28 | PS5-07-04 | PS5 - Milestone F | 5 | Closed | 30 | 29 | JUNE
T-775-6882 | PS5-12-OB-4623B | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone F | 5 | To be completed |  | 10 | OCTOBER
T-751-6883 | PS5-50-OB-9481B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | In progress |  | 41 | NOVEMBER
T-534-6884 | PS5-82-UR-6828C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-05-18 | PS5-05-01 | PS5 - Milestone C | 2 | Closed | 10 | 11 | MAY
T-707-6885 | PS5-34-UR-7663C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone C | 2 | To be completed |  | 21 | NOVEMBER
T-880-6886 | PS5-58-OB-9938A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-02-26 | PS5-01-08 | PS5 - Milestone I | 8 | Closed | 6 | 24 | FEBRUARY
T-360-6887 | PS5-40-IK-2285A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone F | 5 | To be completed |  | 40 | NOVEMBER
T-871-6888 | PS5-48-OB-7374A | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-08-16 | PS5-06-02 | PS5 - Milestone F | 5 | Closed | 30 | 13 | AUGUST
T-669-6889 | PS5-21-UR-1330B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone C | 2 | To be completed |  | 19 | OCTOBER
T-318-6890 | PS5-20-OB-1363D | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone A | 1 | In progress |  | 11 | OCTOBER
T-078-6891 | PS5-93-UR-6043B | CQM04 - Vessel | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone G | 6 | On hold |  | 29 | AUGUST
T-388-6892 | PS5-68-OB-1603D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone B | 1.1 | To be completed |  | 28 | NOVEMBER
T-344-6893 | PS5-29-OB-4100B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-07-15 | PS5-61-07 | PS5 - Milestone C | 2 | Closed | 21 | 11 | JULY
T-897-6894 | PS5-44-IK-5026C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-07-12 | PS5-05-02 | PS5 - Milestone C | 2 | Closed | 7 | 46 | JULY
T-387-6895 | PS5-71-IK-5039B | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-12-23 | PS5-11-01 | PS5 - Milestone F | 5 | Closed | 37 | 35 | DECEMBER
T-307-6896 | PS5-16-IK-9751A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone D | 3 | To be completed |  | 5 | DECEMBER
T-192-6897 | PS5-91-OB-3257B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone H | 7 | To be completed |  | 15 | SEPTEMBER
T-042-6898 | PS5-54-UR-6085C | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-01-27 | PS5-11-01 | PS5 - Milestone E | 4 | Closed | 10 | 21 | JANUARY
T-617-6899 | PS5-93-OB-5198C | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-12-14 | PS5-99-01 | PS5 - Milestone D | 3 | Closed | 27 | 30 | DECEMBER
T-417-6900 | PS5-83-UR-8471B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone A | 1 | To be completed |  | 37 | OCTOBER
T-821-6901 | PS5-30-OB-4382D | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-02-08 | PS5-01-02 | PS5 - Milestone C | 2 | Closed | 7 | 36 | FEBRUARY
T-889-6902 | PS5-60-OB-3578C | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone A | 1 | To be completed |  | 38 | SEPTEMBER
T-723-6903 | PS5-79-IK-8515A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-05-21 | PS5-82-07 | PS5 - Milestone H | 7 | Closed | 17 | 36 | MAY
T-566-6904 | PS5-78-OB-9643A | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone A | 1 | In progress |  | 31 | NOVEMBER
T-100-6905 | PS5-13-OB-6896B | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-12-08 | PS5-05-02 | PS5 - Milestone E | 4 | Closed | 6 | 25 | DECEMBER
T-797-6906 | PS5-10-UR-9165B | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-02-06 | PS5-01-02 | PS5 - Milestone E | 4 | Closed | 30 | 12 | FEBRUARY
T-745-6907 | PS5-36-OB-6241A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone G | 6 | In progress |  | 46 | OCTOBER
T-562-6908 | PS5-06-OB-7816C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-03-04 | PS5-01-07 | PS5 - Milestone C | 2 | Closed | 36 | 38 | MARCH
T-416-6909 | PS5-73-UR-8911A | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone G | 6 | On hold |  | 32 | DECEMBER
T-886-6910 | PS5-29-UR-9964D | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-03-20 | PS5-02-02 | PS5 - Milestone G | 6 | Closed | 12 | 11 | MARCH
T-677-6911 | PS5-26-OB-8262B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-02-13 | PS5-05-02 | PS5 - Milestone H | 7 | Closed | 6 | 11 | FEBRUARY
T-531-6912 | PS5-91-UR-9733D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone B | 1.1 | To be completed |  | 22 | DECEMBER
T-264-6913 | PS5-51-IK-6765B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone C | 2 | To be completed |  | 48 | NOVEMBER
T-722-6914 | PS5-53-IK-7398B | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone F | 5 | In progress |  | 22 | SEPTEMBER
T-096-6915 | PS5-64-UR-2142D | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone D | 3 | In progress |  | 42 | SEPTEMBER
T-546-6916 | PS5-88-IK-1661A | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-07-18 | PS5-01-02 | PS5 - Milestone I | 8 | Closed | 17 | 44 | JULY
T-976-6917 | PS5-17-OB-1785C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-07-09 | PS5-01-04 | PS5 - Milestone F | 5 | Closed | 14 | 6 | JULY
T-166-6918 | PS5-74-OB-3695B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-11-05 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 13 | 40 | NOVEMBER
T-013-6919 | PS5-78-IK-3540D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone F | 5 | In progress |  | 10 | DECEMBER
T-384-6920 | PS5-62-UR-9912B | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-02-14 | PS5-09-01 | PS5 - Milestone E | 4 | Closed | 46 | 30 | FEBRUARY
T-342-6921 | PS5-02-OB-5382C | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-08-09 | PS5-01-09 | PS5 - Milestone H | 7 | Closed | 38 | 29 | AUGUST
T-829-6922 | PS5-08-IK-4347B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone I | 8 | To be completed |  | 48 | SEPTEMBER
T-655-6923 | PS5-55-OB-3653D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | In progress |  | 13 | AUGUST
T-882-6924 | PS5-10-IK-7455D | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone F | 5 | In progress |  | 30 | NOVEMBER
T-083-6925 | PS5-45-OB-7931B | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | On hold |  | 36 | NOVEMBER
T-198-6926 | PS5-56-UR-6269D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | To be completed |  | 15 | AUGUST
T-839-6927 | PS5-98-OB-9634C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-14 | PS5-60-04 | PS5 - Milestone F | 5 | Closed | 18 | 35 | MAY
T-934-6928 | PS5-85-UR-5551B | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone E | 4 | On hold |  | 28 | OCTOBER
T-078-6929 | PS5-23-OB-7599A | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone A | 1 | To be completed |  | 7 | NOVEMBER
T-289-6930 | PS5-94-UR-3493A | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-12-19 | PS5-82-01 | PS5 - Milestone F | 5 | Closed | 4 | 11 | DECEMBER
T-936-6931 | PS5-97-OB-3580B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone H | 7 | To be completed |  | 23 | AUGUST
T-218-6932 | PS5-59-OB-6977D | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone D | 3 | To be completed |  | 43 | NOVEMBER
T-685-6933 | PS5-63-UR-5224C | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone F | 5 | To be completed |  | 45 | NOVEMBER
T-791-6934 | PS5-78-IK-4617A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-10-04 | PS5-10-05 | PS5 - Milestone D | 3 | Closed | 5 | 47 | OCTOBER
T-111-6935 | PS5-48-OB-6302A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-04-03 | PS5-10-06 | PS5 - Milestone G | 6 | Closed | 20 | 44 | APRIL
T-004-6936 | PS5-59-IK-7502C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-11-24 | PS5-01-04 | PS5 - Milestone A | 1 | Closed | 5 | 48 | NOVEMBER
T-011-6937 | PS5-80-UR-9617A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone I | 8 | To be completed |  | 34 | DECEMBER
T-307-6938 | PS5-73-UR-1313C | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-05-21 | PS5-13-01 | PS5 - Milestone I | 8 | Closed | 43 | 21 | MAY
T-929-6939 | PS5-67-IK-6614D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone D | 3 | To be completed |  | 25 | NOVEMBER
T-529-6940 | PS5-69-OB-1587A | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-05-06 | PS5-61-01 | PS5 - Milestone D | 3 | Closed | 39 | 16 | MAY
T-215-6941 | PS5-50-UR-8863B | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-01-10 | PS5-03-01 | PS5 - Milestone D | 3 | Closed | 44 | 42 | JANUARY
T-488-6942 | PS5-84-OB-7208A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone H | 7 | To be completed |  | 4 | OCTOBER
T-695-6943 | PS5-03-UR-6097D | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-07-12 | PS5-62-02 | PS5 - Milestone I | 8 | Closed | 12 | 12 | JULY
T-142-6944 | PS5-98-OB-3957A | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | To be completed |  | 46 | DECEMBER
T-477-6945 | PS5-28-OB-8177B | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone D | 3 | To be completed |  | 20 | SEPTEMBER
T-449-6946 | PS5-71-OB-2168D | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | To be completed |  | 15 | OCTOBER
T-081-6947 | PS5-37-IK-2384C | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-05-15 | PS5-99-02 | PS5 - Milestone D | 3 | Closed | 43 | 20 | MAY
T-275-6948 | PS5-41-OB-1808C | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone B | 1.1 | In progress |  | 28 | NOVEMBER
T-693-6949 | PS5-43-OB-6989A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone A | 1 | To be completed |  | 31 | NOVEMBER
T-475-6950 | PS5-20-IK-7998D | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone D | 3 | In progress |  | 39 | AUGUST
T-321-6951 | PS5-31-UR-6914B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone F | 5 | To be completed |  | 36 | SEPTEMBER
T-264-6952 | PS5-83-OB-6416B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | To be completed |  | 41 | DECEMBER
T-581-6953 | PS5-87-UR-7769A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone F | 5 | On hold |  | 48 | AUGUST
T-417-6954 | PS5-73-UR-8550B | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-09-08 | PS5-99-03 | PS5 - Milestone A | 1 | Closed | 42 | 29 | SEPTEMBER
T-224-6955 | PS5-33-OB-5173D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-07-19 | PS5-07-04 | PS5 - Milestone H | 7 | Closed | 35 | 13 | JULY
T-600-6956 | PS5-43-OB-3568C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone B | 1.1 | To be completed |  | 32 | AUGUST
T-969-6957 | PS5-68-IK-4078A | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone E | 4 | To be completed |  | 32 | OCTOBER
T-224-6958 | PS5-63-UR-6605C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone C | 2 | To be completed |  | 18 | OCTOBER
T-844-6959 | PS5-99-OB-7972C | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone E | 4 | In progress |  | 26 | OCTOBER
T-841-6960 | PS5-46-UR-6295B | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone E | 4 | In progress |  | 5 | DECEMBER
T-479-6961 | PS5-59-UR-3053D | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone E | 4 | On hold |  | 18 | AUGUST
T-584-6962 | PS5-27-OB-7225A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-12-12 | PS5-11-02 | PS5 - Milestone I | 8 | Closed | 6 | 34 | DECEMBER
T-192-6963 | PS5-79-OB-9266A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-09-10 | PS5-62-01 | PS5 - Milestone B | 1.1 | Closed | 18 | 27 | SEPTEMBER
T-582-6964 | PS5-15-OB-7281D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone H | 7 | To be completed |  | 43 | SEPTEMBER
T-965-6965 | PS5-06-UR-1044C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone C | 2 | To be completed |  | 15 | OCTOBER
T-906-6966 | PS5-89-OB-9387A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-08-27 | PS5-02-02 | PS5 - Milestone B | 1.1 | Closed | 43 | 22 | AUGUST
T-853-6967 | PS5-89-OB-7032A | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-02-15 | PS5-03-02 | PS5 - Milestone G | 6 | Closed | 39 | 33 | FEBRUARY
T-559-6968 | PS5-75-UR-4304A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone I | 8 | In progress |  | 37 | SEPTEMBER
T-589-6969 | PS5-94-UR-1369B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone H | 7 | On hold |  | 24 | SEPTEMBER
T-750-6970 | PS5-98-OB-9206B | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone C | 2 | To be completed |  | 18 | OCTOBER
T-734-6971 | PS5-58-OB-8400D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | To be completed |  | 45 | OCTOBER
T-364-6972 | PS5-90-IK-8651C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-12-09 | PS5-02-03 | PS5 - Milestone A | 1 | Closed | 10 | 46 | DECEMBER
T-192-6973 | PS5-56-IK-6582A | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone F | 5 | To be completed |  | 40 | OCTOBER
T-702-6974 | PS5-46-OB-2262D | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone E | 4 | In progress |  | 7 | DECEMBER
T-078-6975 | PS5-57-OB-7103D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-05-15 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 42 | 9 | MAY
T-596-6976 | PS5-14-OB-6981D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-03-11 | PS5-61-07 | PS5 - Milestone G | 6 | Closed | 14 | 37 | MARCH
T-232-6977 | PS5-18-OB-4720D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone C | 2 | In progress |  | 13 | DECEMBER
T-836-6978 | PS5-52-OB-7140B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone B | 1.1 | To be completed |  | 10 | AUGUST
T-207-6979 | PS5-41-OB-7986C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone F | 5 | To be completed |  | 42 | AUGUST
T-246-6980 | PS5-82-OB-6748C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-05-10 | PS5-10-06 | PS5 - Milestone C | 2 | Closed | 17 | 44 | MAY
T-767-6981 | PS5-84-UR-9577C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | On hold |  | 47 | OCTOBER
T-838-6982 | PS5-34-UR-8312D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-04-06 | PS5-99-02 | PS5 - Milestone C | 2 | Closed | 11 | 34 | APRIL
T-925-6983 | PS5-90-OB-1000C | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone A | 1 | On hold |  | 30 | SEPTEMBER
T-875-6984 | PS5-03-IK-4856D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone D | 3 | In progress |  | 38 | OCTOBER
T-734-6985 | PS5-41-UR-7110D | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-04-08 | PS5-99-03 | PS5 - Milestone E | 4 | Closed | 30 | 30 | APRIL
T-531-6986 | PS5-50-IK-8612C | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | To be completed |  | 22 | DECEMBER
T-827-6987 | PS5-19-UR-9849C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone I | 8 | In progress |  | 40 | AUGUST
T-591-6988 | PS5-90-UR-9415A | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-20 | PS5-60-07 | PS5 - Milestone I | 8 | Closed | 15 | 4 | JULY
T-791-6989 | PS5-23-IK-1488C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone A | 1 | On hold |  | 31 | SEPTEMBER
T-289-6990 | PS5-15-IK-8611C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone B | 1.1 | In progress |  | 42 | NOVEMBER
T-767-6991 | PS5-96-OB-8578A | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-02-16 | PS5-02-02 | PS5 - Milestone E | 4 | Closed | 40 | 12 | FEBRUARY
T-347-6992 | PS5-99-UR-7171D | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-01-09 | PS5-01-08 | PS5 - Milestone B | 1.1 | Closed | 9 | 31 | JANUARY
T-618-6993 | PS5-77-OB-3949B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone D | 3 | To be completed |  | 48 | DECEMBER
T-099-6994 | PS5-13-OB-4845D | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-12-05 | PS5-03-02 | PS5 - Milestone B | 1.1 | Closed | 18 | 39 | DECEMBER
T-425-6995 | PS5-50-IK-4711A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | On hold |  | 22 | NOVEMBER
T-844-6996 | PS5-32-OB-6422B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone B | 1.1 | In progress |  | 17 | OCTOBER
T-383-6997 | PS5-29-OB-4201B | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-03-22 | PS5-01-05 | PS5 - Milestone A | 1 | Closed | 44 | 21 | MARCH
T-423-6998 | PS5-01-UR-8140A | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-12-06 | PS5-09-01 | PS5 - Milestone B | 1.1 | Closed | 15 | 10 | DECEMBER
T-141-6999 | PS5-96-OB-7081C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-09-01 | PS5-01-05 | PS5 - Milestone A | 1 | Closed | 11 | 41 | SEPTEMBER
T-538-7000 | PS5-50-OB-9870B | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-01-03 | PS5-04-02 | PS5 - Milestone A | 1 | Closed | 27 | 22 | JANUARY
T-159-7001 | PS5-09-IK-4157B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone C | 2 | To be completed |  | 47 | DECEMBER
T-424-7002 | PS5-23-IK-8338C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone I | 8 | In progress |  | 34 | DECEMBER
T-254-7003 | PS5-39-OB-9906A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone A | 1 | To be completed |  | 8 | DECEMBER
T-231-7004 | PS5-91-UR-4636A | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | To be completed |  | 19 | SEPTEMBER
T-011-7005 | PS5-72-IK-8504A | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | To be completed |  | 13 | SEPTEMBER
T-872-7006 | PS5-56-UR-4147C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-06-08 | PS5-08-01 | PS5 - Milestone D | 3 | Closed | 13 | 17 | JUNE
T-866-7007 | PS5-61-OB-2460C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-04-23 | PS5-61-02 | PS5 - Milestone G | 6 | Closed | 20 | 5 | APRIL
T-994-7008 | PS5-65-IK-1930D | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone B | 1.1 | On hold |  | 11 | OCTOBER
T-669-7009 | PS5-68-UR-6809D | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-01-12 | PS5-82-07 | PS5 - Milestone C | 2 | Closed | 37 | 27 | JANUARY
T-237-7010 | PS5-52-IK-4436C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-04-18 | PS5-08-02 | PS5 - Milestone G | 6 | Closed | 8 | 42 | APRIL
T-205-7011 | PS5-44-IK-1208C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-05-27 | PS5-10-04 | PS5 - Milestone G | 6 | Closed | 24 | 33 | MAY
T-883-7012 | PS5-10-OB-5519D | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | To be completed |  | 12 | AUGUST
T-738-7013 | PS5-04-UR-5946D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone A | 1 | In progress |  | 8 | NOVEMBER
T-813-7014 | PS5-72-OB-2542A | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone F | 5 | On hold |  | 15 | OCTOBER
T-325-7015 | PS5-53-IK-4803A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone A | 1 | To be completed |  | 8 | NOVEMBER
T-918-7016 | PS5-79-IK-2450C | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone H | 7 | In progress |  | 23 | SEPTEMBER
T-580-7017 | PS5-45-IK-6385B | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone D | 3 | To be completed |  | 10 | DECEMBER
T-364-7018 | PS5-67-UR-5339B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-06-24 | PS5-01-03 | PS5 - Milestone I | 8 | Closed | 29 | 31 | JUNE
T-041-7019 | PS5-91-UR-3896B | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone I | 8 | In progress |  | 7 | AUGUST
T-057-7020 | PS5-35-IK-9433A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone C | 2 | In progress |  | 45 | AUGUST
T-718-7021 | PS5-37-UR-1242D | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-08-27 | PS5-01-09 | PS5 - Milestone D | 3 | Closed | 15 | 5 | AUGUST
T-418-7022 | PS5-37-OB-3718C | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-11-10 | PS5-04-01 | PS5 - Milestone A | 1 | Closed | 7 | 29 | NOVEMBER
T-498-7023 | PS5-07-IK-6997A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-05-05 | PS5-03-03 | PS5 - Milestone G | 6 | Closed | 41 | 40 | MAY
T-940-7024 | PS5-50-OB-7319D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-10-07 | PS5-10-01 | PS5 - Milestone E | 4 | Closed | 13 | 31 | OCTOBER
T-528-7025 | PS5-14-UR-6620B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-01-04 | PS5-05-02 | PS5 - Milestone C | 2 | Closed | 21 | 40 | JANUARY
T-202-7026 | PS5-32-OB-7819C | CQS01 - Fire Protection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-02-12 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 42 | 21 | FEBRUARY
T-580-7027 | PS5-61-UR-4071B | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-09-26 | PS5-12-02 | PS5 - Milestone A | 1 | Closed | 16 | 43 | SEPTEMBER
T-530-7028 | PS5-69-OB-9818D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone C | 2 | To be completed |  | 10 | AUGUST
T-692-7029 | PS5-78-OB-3293D | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone I | 8 | To be completed |  | 17 | OCTOBER
T-441-7030 | PS5-13-OB-6399C | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone D | 3 | To be completed |  | 8 | DECEMBER
T-549-7031 | PS5-87-OB-2925A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | To be completed |  | 11 | OCTOBER
T-907-7032 | PS5-38-IK-1800A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone C | 2 | To be completed |  | 17 | OCTOBER
T-181-7033 | PS5-84-OB-4242D | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone H | 7 | To be completed |  | 6 | AUGUST
T-822-7034 | PS5-50-IK-6363C | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-08-07 | PS5-82-01 | PS5 - Milestone D | 3 | Closed | 13 | 20 | AUGUST
T-180-7035 | PS5-53-OB-8295B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-07-19 | PS5-10-05 | PS5 - Milestone C | 2 | Closed | 13 | 7 | JULY
T-125-7036 | PS5-70-OB-6186C | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-05-04 | PS5-05-02 | PS5 - Milestone G | 6 | Closed | 14 | 32 | MAY
T-866-7037 | PS5-34-UR-1682D | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-11-18 | PS5-07-01 | PS5 - Milestone E | 4 | Closed | 47 | 41 | NOVEMBER
T-536-7038 | PS5-08-OB-3357C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | On hold |  | 12 | NOVEMBER
T-272-7039 | PS5-51-OB-3342D | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone F | 5 | To be completed |  | 30 | OCTOBER
T-014-7040 | PS5-42-IK-2593B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-06-06 | PS5-05-03 | PS5 - Milestone G | 6 | Closed | 5 | 7 | JUNE
T-421-7041 | PS5-47-UR-2930A | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-04-18 | PS5-99-01 | PS5 - Milestone D | 3 | Closed | 18 | 37 | APRIL
T-306-7042 | PS5-83-UR-5471B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone D | 3 | To be completed |  | 41 | AUGUST
T-026-7043 | PS5-70-OB-3297C | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone E | 4 | On hold |  | 40 | DECEMBER
T-298-7044 | PS5-80-IK-1587B | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-08-18 | PS5-62-02 | PS5 - Milestone A | 1 | Closed | 9 | 15 | AUGUST
T-087-7045 | PS5-37-IK-9127A | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-08-19 | PS5-12-01 | PS5 - Milestone D | 3 | Closed | 7 | 15 | AUGUST
T-613-7046 | PS5-02-IK-6471B | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-06-14 | PS5-63-01 | PS5 - Milestone I | 8 | Closed | 25 | 5 | JUNE
T-485-7047 | PS5-47-UR-2967D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone A | 1 | To be completed |  | 32 | OCTOBER
T-662-7048 | PS5-24-OB-3216B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone B | 1.1 | In progress |  | 40 | OCTOBER
T-939-7049 | PS5-09-OB-9499A | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-01-17 | PS5-04-04 | PS5 - Milestone C | 2 | Closed | 22 | 10 | JANUARY
T-959-7050 | PS5-80-UR-5137A | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-03-18 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 39 | 36 | MARCH
T-426-7051 | PS5-45-UR-2172D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-10-11 | PS5-04-01 | PS5 - Milestone A | 1 | Closed | 22 | 43 | OCTOBER
T-514-7052 | PS5-87-OB-2761C | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-03-09 | PS5-02-03 | PS5 - Milestone A | 1 | Closed | 23 | 29 | MARCH
T-411-7053 | PS5-44-UR-6388D | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | To be completed |  | 8 | OCTOBER
T-144-7054 | PS5-05-OB-8195A | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | In progress |  | 30 | DECEMBER
T-284-7055 | PS5-25-UR-9394A | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-05-17 | PS5-12-01 | PS5 - Milestone E | 4 | Closed | 41 | 31 | MAY
T-591-7056 | PS5-16-OB-3186B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone C | 2 | To be completed |  | 33 | SEPTEMBER
T-989-7057 | PS5-21-OB-3879D | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone E | 4 | To be completed |  | 42 | NOVEMBER
T-904-7058 | PS5-48-IK-5909A | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone C | 2 | On hold |  | 11 | SEPTEMBER
T-299-7059 | PS5-12-IK-5015D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone E | 4 | On hold |  | 25 | OCTOBER
T-828-7060 | PS5-82-IK-3559B | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone G | 6 | On hold |  | 41 | NOVEMBER
T-612-7061 | PS5-81-OB-2593B | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-08-28 | PS5-04-02 | PS5 - Milestone A | 1 | Closed | 36 | 25 | AUGUST
T-300-7062 | PS5-18-IK-2780A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-12-06 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 5 | 45 | DECEMBER
T-925-7063 | PS5-38-OB-6433C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-07-01 | PS5-03-23 | PS5 - Milestone C | 2 | Closed | 8 | 6 | JULY
T-714-7064 | PS5-37-OB-1007B | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-01-05 | PS5-06-02 | PS5 - Milestone A | 1 | Closed | 24 | 38 | JANUARY
T-371-7065 | PS5-01-IK-2576C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-09-22 | PS5-01-08 | PS5 - Milestone H | 7 | Closed | 4 | 20 | SEPTEMBER
T-313-7066 | PS5-80-OB-6021C | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-03-27 | PS5-03-23 | PS5 - Milestone D | 3 | Closed | 35 | 12 | MARCH
T-471-7067 | PS5-28-UR-8244C | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | To be completed |  | 13 | AUGUST
T-534-7068 | PS5-94-OB-9030C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-02-13 | PS5-61-02 | PS5 - Milestone G | 6 | Closed | 28 | 17 | FEBRUARY
T-992-7069 | PS5-59-IK-6416D | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone I | 8 | To be completed |  | 40 | AUGUST
T-369-7070 | PS5-13-IK-3429C | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-03-27 | PS5-04-03 | PS5 - Milestone A | 1 | Closed | 44 | 46 | MARCH
T-710-7071 | PS5-12-OB-4960C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone A | 1 | To be completed |  | 24 | AUGUST
T-530-7072 | PS5-32-OB-9619D | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-12-02 | PS5-63-04 | PS5 - Milestone A | 1 | Closed | 42 | 40 | DECEMBER
T-588-7073 | PS5-76-IK-7992B | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-03-14 | PS5-04-04 | PS5 - Milestone G | 6 | Closed | 21 | 38 | MARCH
T-050-7074 | PS5-17-OB-6547C | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone E | 4 | To be completed |  | 22 | AUGUST
T-326-7075 | PS5-16-IK-1029C | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-10-09 | PS5-11-02 | PS5 - Milestone H | 7 | Closed | 21 | 37 | OCTOBER
T-588-7076 | PS5-63-UR-9826C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-02-12 | PS5-12-01 | PS5 - Milestone C | 2 | Closed | 43 | 18 | FEBRUARY
T-900-7077 | PS5-24-UR-4445A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-07-15 | PS5-07-03 | PS5 - Milestone D | 3 | Closed | 35 | 9 | JULY
T-170-7078 | PS5-03-OB-8681C | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | In progress |  | 42 | AUGUST
T-292-7079 | PS5-05-IK-2110D | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-03-12 | PS5-82-02 | PS5 - Milestone H | 7 | Closed | 7 | 20 | MARCH
T-981-7080 | PS5-76-UR-1832B | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone I | 8 | On hold |  | 5 | DECEMBER
T-531-7081 | PS5-01-UR-6635A | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-06-26 | PS5-10-06 | PS5 - Milestone F | 5 | Closed | 30 | 7 | JUNE
T-853-7082 | PS5-62-IK-9468B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone C | 2 | In progress |  | 7 | NOVEMBER
T-112-7083 | PS5-44-OB-7661B | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone D | 3 | To be completed |  | 37 | OCTOBER
T-841-7084 | PS5-15-UR-5761C | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone B | 1.1 | On hold |  | 24 | AUGUST
T-566-7085 | PS5-73-UR-4060C | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | In progress |  | 4 | SEPTEMBER
T-591-7086 | PS5-48-OB-9186D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone C | 2 | To be completed |  | 27 | SEPTEMBER
T-003-7087 | PS5-51-OB-3776C | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone H | 7 | To be completed |  | 14 | DECEMBER
T-183-7088 | PS5-72-UR-6569A | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | To be completed |  | 41 | NOVEMBER
T-982-7089 | PS5-24-OB-8158C | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | In progress |  | 21 | OCTOBER
T-377-7090 | PS5-79-OB-5006D | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-07-26 | PS5-11-02 | PS5 - Milestone C | 2 | Closed | 39 | 37 | JULY
T-417-7091 | PS5-28-UR-4336B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone D | 3 | To be completed |  | 40 | NOVEMBER
T-976-7092 | PS5-07-UR-9406A | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-11-23 | PS5-62-02 | PS5 - Milestone A | 1 | Closed | 22 | 4 | NOVEMBER
T-784-7093 | PS5-87-IK-8932C | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone G | 6 | In progress |  | 29 | SEPTEMBER
T-111-7094 | PS5-12-IK-8350C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone G | 6 | To be completed |  | 41 | DECEMBER
T-021-7095 | PS5-34-IK-1647A | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone A | 1 | In progress |  | 18 | DECEMBER
T-444-7096 | PS5-61-OB-6699A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | On hold |  | 48 | NOVEMBER
T-631-7097 | PS5-20-UR-6380B | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone F | 5 | To be completed |  | 31 | NOVEMBER
T-663-7098 | PS5-27-OB-9078D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone A | 1 | To be completed |  | 33 | SEPTEMBER
T-626-7099 | PS5-76-OB-7485A | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone C | 2 | To be completed |  | 15 | NOVEMBER
T-852-7100 | PS5-58-IK-9375A | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone A | 1 | To be completed |  | 13 | AUGUST
T-240-7101 | PS5-65-UR-1875A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone I | 8 | On hold |  | 37 | SEPTEMBER
T-609-7102 | PS5-98-OB-5209D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone A | 1 | To be completed |  | 38 | DECEMBER
T-583-7103 | PS5-25-OB-3106B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone H | 7 | To be completed |  | 33 | SEPTEMBER
T-703-7104 | PS5-76-IK-5366D | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | To be completed |  | 30 | AUGUST
T-135-7105 | PS5-27-OB-7340D | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone D | 3 | On hold |  | 48 | DECEMBER
T-428-7106 | PS5-25-OB-4975B | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-01-05 | PS5-61-01 | PS5 - Milestone I | 8 | Closed | 41 | 34 | JANUARY
T-868-7107 | PS5-83-IK-8011A | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-09-13 | PS5-10-04 | PS5 - Milestone I | 8 | Closed | 48 | 18 | SEPTEMBER
T-077-7108 | PS5-37-OB-4891B | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone G | 6 | To be completed |  | 20 | OCTOBER
T-270-7109 | PS5-35-UR-6100A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | To be completed |  | 48 | NOVEMBER
T-935-7110 | PS5-69-IK-1708B | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone C | 2 | To be completed |  | 12 | SEPTEMBER
T-951-7111 | PS5-75-UR-5773D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-07-14 | PS5-06-02 | PS5 - Milestone D | 3 | Closed | 47 | 36 | JULY
T-955-7112 | PS5-76-IK-2701B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone E | 4 | To be completed |  | 32 | SEPTEMBER
T-395-7113 | PS5-56-OB-7724A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone A | 1 | To be completed |  | 23 | SEPTEMBER
T-172-7114 | PS5-37-OB-6676B | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-09-18 | PS5-62-02 | PS5 - Milestone F | 5 | Closed | 25 | 34 | SEPTEMBER
T-987-7115 | PS5-47-OB-3804B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | On hold |  | 16 | SEPTEMBER
T-723-7116 | PS5-09-UR-3153C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-12-23 | PS5-10-05 | PS5 - Milestone B | 1.1 | Closed | 41 | 20 | DECEMBER
T-569-7117 | PS5-15-IK-4489C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone D | 3 | In progress |  | 4 | OCTOBER
T-297-7118 | PS5-59-IK-7727D | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-04-26 | PS5-01-06 | PS5 - Milestone B | 1.1 | Closed | 43 | 38 | APRIL
T-399-7119 | PS5-14-IK-7871A | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-01-21 | PS5-62-02 | PS5 - Milestone B | 1.1 | Closed | 17 | 12 | JANUARY
T-066-7120 | PS5-09-UR-9653A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | To be completed |  | 27 | NOVEMBER
T-507-7121 | PS5-78-OB-3475B | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone G | 6 | On hold |  | 15 | DECEMBER
T-272-7122 | PS5-30-UR-9263C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | On hold |  | 35 | DECEMBER
T-105-7123 | PS5-61-OB-1541A | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | To be completed |  | 41 | OCTOBER
T-126-7124 | PS5-12-OB-6026A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone E | 4 | In progress |  | 41 | DECEMBER
T-381-7125 | PS5-18-UR-7187C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | To be completed |  | 6 | DECEMBER
T-311-7126 | PS5-58-OB-5031C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone D | 3 | To be completed |  | 36 | DECEMBER
T-506-7127 | PS5-36-OB-8956C | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone G | 6 | On hold |  | 39 | OCTOBER
T-671-7128 | PS5-21-OB-6375D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-08-11 | PS5-60-07 | PS5 - Milestone F | 5 | Closed | 48 | 38 | AUGUST
T-375-7129 | PS5-14-OB-4539D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone B | 1.1 | To be completed |  | 29 | DECEMBER
T-037-7130 | PS5-68-OB-2782B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-11-13 | PS5-07-01 | PS5 - Milestone H | 7 | Closed | 36 | 24 | NOVEMBER
T-514-7131 | PS5-12-OB-6195A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-06-20 | PS5-01-01 | PS5 - Milestone G | 6 | Closed | 21 | 40 | JUNE
T-138-7132 | PS5-78-IK-1595B | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone G | 6 | To be completed |  | 47 | AUGUST
T-923-7133 | PS5-23-OB-6969A | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-11-06 | PS5-06-01 | PS5 - Milestone A | 1 | Closed | 25 | 21 | NOVEMBER
T-711-7134 | PS5-88-OB-4331B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone B | 1.1 | To be completed |  | 42 | DECEMBER
T-899-7135 | PS5-93-OB-8739A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | In progress |  | 23 | NOVEMBER
T-394-7136 | PS5-38-IK-8620A | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-06-11 | PS5-01-05 | PS5 - Milestone I | 8 | Closed | 36 | 14 | JUNE
T-248-7137 | PS5-87-OB-8708B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-03-25 | PS5-04-04 | PS5 - Milestone C | 2 | Closed | 43 | 40 | MARCH
T-549-7138 | PS5-34-UR-1897D | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-09-06 | PS5-02-01 | PS5 - Milestone D | 3 | Closed | 13 | 24 | SEPTEMBER
T-559-7139 | PS5-50-OB-8832A | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-03-26 | PS5-01-04 | PS5 - Milestone A | 1 | Closed | 35 | 30 | MARCH
T-145-7140 | PS5-51-UR-5781C | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-03-28 | PS5-10-06 | PS5 - Milestone C | 2 | Closed | 34 | 30 | MARCH
T-166-7141 | PS5-62-IK-5447C | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone D | 3 | To be completed |  | 39 | NOVEMBER
T-795-7142 | PS5-95-OB-5591B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-07-04 | PS5-61-02 | PS5 - Milestone D | 3 | Closed | 13 | 36 | JULY
T-746-7143 | PS5-47-OB-5563A | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-11-28 | PS5-09-04 | PS5 - Milestone D | 3 | Closed | 7 | 42 | NOVEMBER
T-823-7144 | PS5-16-OB-5054C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | To be completed |  | 22 | DECEMBER
T-617-7145 | PS5-67-OB-1685B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone I | 8 | On hold |  | 34 | OCTOBER
T-600-7146 | PS5-65-UR-2837D | CQP05 - Insulation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-08-23 | PS5-01-02 | PS5 - Milestone H | 7 | Closed | 41 | 9 | AUGUST
T-918-7147 | PS5-88-IK-6603A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-11-20 | PS5-02-01 | PS5 - Milestone F | 5 | Closed | 25 | 4 | NOVEMBER
T-293-7148 | PS5-82-OB-9187C | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-10-01 | PS5-11-01 | PS5 - Milestone C | 2 | Closed | 25 | 38 | OCTOBER
T-601-7149 | PS5-82-OB-2643C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-07-22 | PS5-02-02 | PS5 - Milestone I | 8 | Closed | 10 | 15 | JULY
T-919-7150 | PS5-75-OB-4489B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone A | 1 | On hold |  | 47 | NOVEMBER
T-814-7151 | PS5-19-UR-1900A | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-06-09 | PS5-10-06 | PS5 - Milestone A | 1 | Closed | 7 | 10 | JUNE
T-221-7152 | PS5-60-UR-7235D | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | In progress |  | 5 | OCTOBER
T-015-7153 | PS5-94-OB-5474C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | To be completed |  | 35 | AUGUST
T-683-7154 | PS5-03-OB-1896B | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone F | 5 | To be completed |  | 45 | SEPTEMBER
T-030-7155 | PS5-27-OB-2632B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-04-06 | PS5-62-01 | PS5 - Milestone F | 5 | Closed | 14 | 36 | APRIL
T-050-7156 | PS5-21-OB-4426D | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-03-10 | PS5-04-04 | PS5 - Milestone C | 2 | Closed | 13 | 23 | MARCH
T-327-7157 | PS5-58-IK-9462A | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone F | 5 | To be completed |  | 38 | NOVEMBER
T-078-7158 | PS5-15-OB-5540D | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone D | 3 | On hold |  | 31 | AUGUST
T-159-7159 | PS5-76-IK-8803B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-04-24 | PS5-10-06 | PS5 - Milestone A | 1 | Closed | 37 | 16 | APRIL
T-415-7160 | PS5-56-UR-7390C | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone F | 5 | In progress |  | 13 | AUGUST
T-746-7161 | PS5-81-OB-6444A | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-02-02 | PS5-09-04 | PS5 - Milestone F | 5 | Closed | 18 | 25 | FEBRUARY
T-846-7162 | PS5-53-OB-7983D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone C | 2 | In progress |  | 11 | AUGUST
T-170-7163 | PS5-88-OB-4953A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone G | 6 | In progress |  | 10 | DECEMBER
T-992-7164 | PS5-95-OB-9151C | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-03-28 | PS5-60-10 | PS5 - Milestone A | 1 | Closed | 21 | 31 | MARCH
T-090-7165 | PS5-29-IK-1158C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone B | 1.1 | In progress |  | 12 | DECEMBER
T-479-7166 | PS5-03-UR-9440D | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-08-17 | PS5-11-01 | PS5 - Milestone H | 7 | Closed | 30 | 45 | AUGUST
T-099-7167 | PS5-08-OB-1981D | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-08-04 | PS5-04-04 | PS5 - Milestone C | 2 | Closed | 25 | 39 | AUGUST
T-132-7168 | PS5-92-IK-9854B | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-08-03 | PS5-01-02 | PS5 - Milestone B | 1.1 | Closed | 48 | 13 | AUGUST
T-329-7169 | PS5-91-IK-3305C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | In progress |  | 4 | SEPTEMBER
T-859-7170 | PS5-66-OB-5391D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone H | 7 | On hold |  | 32 | OCTOBER
T-255-7171 | PS5-87-OB-1673A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-10-18 | PS5-10-03 | PS5 - Milestone H | 7 | Closed | 25 | 26 | OCTOBER
T-132-7172 | PS5-87-OB-7710D | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone G | 6 | In progress |  | 23 | DECEMBER
T-830-7173 | PS5-82-OB-2124C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-05-05 | PS5-82-02 | PS5 - Milestone B | 1.1 | Closed | 24 | 22 | MAY
T-949-7174 | PS5-64-OB-8833D | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-02-16 | PS5-07-01 | PS5 - Milestone A | 1 | Closed | 4 | 48 | FEBRUARY
T-595-7175 | PS5-49-OB-8326A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone C | 2 | To be completed |  | 5 | NOVEMBER
T-662-7176 | PS5-83-OB-7719A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-05-09 | PS5-12-02 | PS5 - Milestone F | 5 | Closed | 17 | 25 | MAY
T-524-7177 | PS5-91-OB-2907B | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone I | 8 | To be completed |  | 6 | NOVEMBER
T-494-7178 | PS5-53-OB-7944D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | In progress |  | 37 | DECEMBER
T-409-7179 | PS5-91-OB-8127C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-08-24 | PS5-63-04 | PS5 - Milestone A | 1 | Closed | 41 | 37 | AUGUST
T-443-7180 | PS5-91-IK-5489C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone I | 8 | On hold |  | 37 | DECEMBER
T-111-7181 | PS5-77-UR-4994C | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-09-03 | PS5-02-01 | PS5 - Milestone G | 6 | Closed | 41 | 34 | SEPTEMBER
T-047-7182 | PS5-89-UR-8326C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone G | 6 | On hold |  | 24 | DECEMBER
T-625-7183 | PS5-48-UR-2997C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-06-11 | PS5-03-03 | PS5 - Milestone C | 2 | Closed | 44 | 9 | JUNE
T-593-7184 | PS5-75-IK-9531B | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone F | 5 | On hold |  | 12 | DECEMBER
T-118-7185 | PS5-23-OB-4940A | CQM01 - Pump Installation | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone H | 7 | To be completed |  | 34 | OCTOBER
T-328-7186 | PS5-70-UR-9546A | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone E | 4 | In progress |  | 29 | DECEMBER
T-267-7187 | PS5-49-UR-9833B | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | To be completed |  | 46 | AUGUST
T-857-7188 | PS5-01-OB-7945B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone E | 4 | To be completed |  | 43 | SEPTEMBER
T-843-7189 | PS5-10-IK-2939C | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone A | 1 | In progress |  | 18 | OCTOBER
T-719-7190 | PS5-91-OB-7901A | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone A | 1 | To be completed |  | 4 | OCTOBER
T-800-7191 | PS5-12-OB-1667A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-07-24 | PS5-01-06 | PS5 - Milestone H | 7 | Closed | 35 | 19 | JULY
T-292-7192 | PS5-44-IK-3342D | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone I | 8 | To be completed |  | 22 | AUGUST
T-534-7193 | PS5-65-IK-1876B | CQP05 - Insulation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-01-13 | PS5-03-23 | PS5 - Milestone F | 5 | Closed | 46 | 33 | JANUARY
T-893-7194 | PS5-31-UR-9481D | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone A | 1 | On hold |  | 9 | SEPTEMBER
T-977-7195 | PS5-75-UR-2343C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone B | 1.1 | To be completed |  | 19 | SEPTEMBER
T-119-7196 | PS5-06-OB-7204C | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-01-03 | PS5-99-01 | PS5 - Milestone F | 5 | Closed | 33 | 40 | JANUARY
T-375-7197 | PS5-07-IK-8682A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone H | 7 | To be completed |  | 30 | SEPTEMBER
T-973-7198 | PS5-17-OB-6529C | CQE02 - LV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone D | 3 | In progress |  | 8 | SEPTEMBER
T-895-7199 | PS5-67-OB-4056D | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone A | 1 | To be completed |  | 46 | SEPTEMBER
T-431-7200 | PS5-16-UR-7271A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone B | 1.1 | To be completed |  | 6 | AUGUST
T-900-7201 | PS5-10-UR-1998A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-20 | PS5-60-01 | PS5 - Milestone H | 7 | Closed | 35 | 48 | JUNE
T-616-7202 | PS5-52-OB-9178C | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | On hold |  | 8 | OCTOBER
T-132-7203 | PS5-71-OB-6698C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone D | 3 | To be completed |  | 10 | DECEMBER
T-732-7204 | PS5-84-IK-1180B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | In progress |  | 34 | NOVEMBER
T-044-7205 | PS5-69-OB-6422A | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | To be completed |  | 19 | AUGUST
T-217-7206 | PS5-17-OB-5677A | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-08-28 | PS5-11-02 | PS5 - Milestone G | 6 | Closed | 25 | 43 | AUGUST
T-086-7207 | PS5-26-OB-6760C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-09-15 | PS5-01-07 | PS5 - Milestone A | 1 | Closed | 47 | 18 | SEPTEMBER
T-005-7208 | PS5-71-OB-1703D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone I | 8 | To be completed |  | 6 | DECEMBER
T-259-7209 | PS5-20-OB-1947D | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone C | 2 | In progress |  | 44 | OCTOBER
T-712-7210 | PS5-30-UR-6435B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-08-16 | PS5-61-01 | PS5 - Milestone F | 5 | Closed | 12 | 17 | AUGUST
T-788-7211 | PS5-83-OB-6667B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | In progress |  | 43 | DECEMBER
T-555-7212 | PS5-14-OB-7929A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | To be completed |  | 31 | DECEMBER
T-561-7213 | PS5-84-IK-8694B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone D | 3 | To be completed |  | 4 | DECEMBER
T-262-7214 | PS5-90-OB-8779B | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-12-23 | PS5-04-02 | PS5 - Milestone F | 5 | Closed | 19 | 40 | DECEMBER
T-086-7215 | PS5-69-OB-4810A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone C | 2 | To be completed |  | 28 | DECEMBER
T-968-7216 | PS5-42-IK-4914C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone F | 5 | To be completed |  | 48 | NOVEMBER
T-337-7217 | PS5-83-OB-8486B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-03-20 | PS5-61-02 | PS5 - Milestone H | 7 | Closed | 34 | 5 | MARCH
T-637-7218 | PS5-92-IK-9125D | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone A | 1 | In progress |  | 48 | AUGUST
T-104-7219 | PS5-23-OB-1021D | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone C | 2 | On hold |  | 14 | AUGUST
T-621-7220 | PS5-18-IK-6727C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone H | 7 | To be completed |  | 27 | SEPTEMBER
T-557-7221 | PS5-49-OB-6030C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone F | 5 | To be completed |  | 36 | OCTOBER
T-606-7222 | PS5-75-UR-3670C | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | In progress |  | 31 | OCTOBER
T-335-7223 | PS5-08-UR-3261B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | To be completed |  | 14 | OCTOBER
T-392-7224 | PS5-33-OB-2811A | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-11-10 | PS5-99-03 | PS5 - Milestone B | 1.1 | Closed | 21 | 19 | NOVEMBER
T-742-7225 | PS5-77-OB-2150B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone A | 1 | On hold |  | 41 | SEPTEMBER
T-635-7226 | PS5-51-OB-9458A | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone B | 1.1 | In progress |  | 23 | OCTOBER
T-024-7227 | PS5-21-OB-5930B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-05-18 | PS5-01-04 | PS5 - Milestone B | 1.1 | Closed | 6 | 34 | MAY
T-755-7228 | PS5-58-OB-9227C | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-04-20 | PS5-01-01 | PS5 - Milestone G | 6 | Closed | 16 | 33 | APRIL
T-809-7229 | PS5-24-UR-3515C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | In progress |  | 40 | NOVEMBER
T-743-7230 | PS5-35-IK-4222C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-12-06 | PS5-99-01 | PS5 - Milestone D | 3 | Closed | 17 | 38 | DECEMBER
T-795-7231 | PS5-87-OB-6569C | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone C | 2 | To be completed |  | 18 | DECEMBER
T-600-7232 | PS5-03-IK-3236C | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-07-10 | PS5-99-03 | PS5 - Milestone E | 4 | Closed | 26 | 17 | JULY
T-336-7233 | PS5-89-OB-8903D | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-09-01 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 15 | 46 | SEPTEMBER
T-671-7234 | PS5-35-OB-1326B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-10-14 | PS5-01-07 | PS5 - Milestone D | 3 | Closed | 41 | 48 | OCTOBER
T-220-7235 | PS5-20-OB-4137B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone E | 4 | In progress |  | 36 | SEPTEMBER
T-865-7236 | PS5-38-OB-9787D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone I | 8 | To be completed |  | 47 | DECEMBER
T-405-7237 | PS5-11-OB-1066C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone B | 1.1 | In progress |  | 30 | OCTOBER
T-770-7238 | PS5-83-IK-6899B | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | To be completed |  | 24 | SEPTEMBER
T-838-7239 | PS5-18-IK-2374C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone D | 3 | To be completed |  | 38 | OCTOBER
T-374-7240 | PS5-78-UR-1193D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone C | 2 | In progress |  | 31 | NOVEMBER
T-045-7241 | PS5-16-OB-7088D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | To be completed |  | 29 | NOVEMBER
T-076-7242 | PS5-64-OB-2325C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | To be completed |  | 4 | AUGUST
T-902-7243 | PS5-76-OB-7395B | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone D | 3 | On hold |  | 10 | OCTOBER
T-173-7244 | PS5-32-OB-9822A | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-12-13 | PS5-60-04 | PS5 - Milestone D | 3 | Closed | 11 | 25 | DECEMBER
T-147-7245 | PS5-71-IK-6475A | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-02-25 | PS5-07-04 | PS5 - Milestone D | 3 | Closed | 35 | 15 | FEBRUARY
T-294-7246 | PS5-42-UR-4469B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone A | 1 | To be completed |  | 4 | NOVEMBER
T-869-7247 | PS5-60-OB-7057B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone F | 5 | On hold |  | 11 | OCTOBER
T-445-7248 | PS5-70-UR-1840C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-11-20 | PS5-05-02 | PS5 - Milestone C | 2 | Closed | 31 | 6 | NOVEMBER
T-649-7249 | PS5-34-OB-4542A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-07-05 | PS5-06-03 | PS5 - Milestone H | 7 | Closed | 19 | 36 | JULY
T-543-7250 | PS5-13-OB-8180A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone B | 1.1 | In progress |  | 6 | AUGUST
T-573-7251 | PS5-62-OB-9657B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-06-05 | PS5-04-01 | PS5 - Milestone B | 1.1 | Closed | 16 | 23 | JUNE
T-812-7252 | PS5-44-UR-3583A | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-10-06 | PS5-02-02 | PS5 - Milestone I | 8 | Closed | 38 | 24 | OCTOBER
T-801-7253 | PS5-77-OB-2774A | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-02-28 | PS5-06-03 | PS5 - Milestone H | 7 | Closed | 36 | 48 | FEBRUARY
T-547-7254 | PS5-68-OB-9376B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone C | 2 | In progress |  | 35 | OCTOBER
T-192-7255 | PS5-37-OB-6022D | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone D | 3 | On hold |  | 19 | OCTOBER
T-319-7256 | PS5-35-IK-2482D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-03-04 | PS5-05-03 | PS5 - Milestone G | 6 | Closed | 40 | 9 | MARCH
T-149-7257 | PS5-94-IK-5186C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | To be completed |  | 24 | OCTOBER
T-422-7258 | PS5-12-IK-7549A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone E | 4 | To be completed |  | 37 | AUGUST
T-229-7259 | PS5-04-OB-5099B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone B | 1.1 | In progress |  | 37 | NOVEMBER
T-805-7260 | PS5-47-OB-6700A | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-05-08 | PS5-01-04 | PS5 - Milestone D | 3 | Closed | 36 | 27 | MAY
T-578-7261 | PS5-37-OB-5774D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | To be completed |  | 7 | AUGUST
T-141-7262 | PS5-30-OB-5400B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone G | 6 | On hold |  | 21 | AUGUST
T-988-7263 | PS5-77-IK-3726B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone I | 8 | To be completed |  | 12 | SEPTEMBER
T-287-7264 | PS5-10-OB-9660C | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone F | 5 | To be completed |  | 4 | OCTOBER
T-135-7265 | PS5-18-IK-6970D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone H | 7 | On hold |  | 10 | SEPTEMBER
T-373-7266 | PS5-11-OB-6447C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-05-10 | PS5-61-02 | PS5 - Milestone C | 2 | Closed | 40 | 26 | MAY
T-416-7267 | PS5-04-OB-3545C | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone G | 6 | In progress |  | 25 | OCTOBER
T-589-7268 | PS5-19-OB-6870C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-07-21 | PS5-02-02 | PS5 - Milestone H | 7 | Closed | 46 | 9 | JULY
T-952-7269 | PS5-05-OB-6906C | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone C | 2 | In progress |  | 37 | NOVEMBER
T-635-7270 | PS5-46-UR-4459B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-01-20 | PS5-10-05 | PS5 - Milestone A | 1 | Closed | 25 | 29 | JANUARY
T-300-7271 | PS5-09-OB-5241C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | To be completed |  | 45 | AUGUST
T-631-7272 | PS5-82-OB-1130D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone G | 6 | In progress |  | 34 | SEPTEMBER
T-699-7273 | PS5-85-UR-1890B | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | To be completed |  | 5 | NOVEMBER
T-996-7274 | PS5-81-IK-3606C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-03-17 | PS5-10-02 | PS5 - Milestone E | 4 | Closed | 44 | 13 | MARCH
T-790-7275 | PS5-91-OB-6794C | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone G | 6 | In progress |  | 48 | OCTOBER
T-055-7276 | PS5-33-IK-6357D | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-08-12 | PS5-82-01 | PS5 - Milestone A | 1 | Closed | 11 | 6 | AUGUST
T-509-7277 | PS5-83-OB-3685D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | In progress |  | 30 | DECEMBER
T-678-7278 | PS5-57-UR-6557C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-05-25 | PS5-61-07 | PS5 - Milestone H | 7 | Closed | 13 | 7 | MAY
T-499-7279 | PS5-97-IK-5614A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone F | 5 | To be completed |  | 30 | SEPTEMBER
T-309-7280 | PS5-73-UR-2910D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-08-20 | PS5-06-01 | PS5 - Milestone I | 8 | Closed | 41 | 5 | AUGUST
T-712-7281 | PS5-29-UR-2147B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone E | 4 | In progress |  | 41 | AUGUST
T-656-7282 | PS5-68-UR-4113A | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-05-09 | PS5-01-05 | PS5 - Milestone E | 4 | Closed | 37 | 39 | MAY
T-675-7283 | PS5-30-IK-3894A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | To be completed |  | 25 | OCTOBER
T-552-7284 | PS5-09-UR-7511D | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-01-13 | PS5-02-03 | PS5 - Milestone B | 1.1 | Closed | 26 | 38 | JANUARY
T-285-7285 | PS5-38-OB-4535D | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-09-03 | PS5-03-02 | PS5 - Milestone C | 2 | Closed | 33 | 9 | SEPTEMBER
T-634-7286 | PS5-96-OB-7510A | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone A | 1 | To be completed |  | 19 | OCTOBER
T-219-7287 | PS5-25-IK-9588D | CQP05 - Insulation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone A | 1 | To be completed |  | 19 | AUGUST
T-908-7288 | PS5-78-OB-8696C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-10-15 | PS5-82-07 | PS5 - Milestone F | 5 | Closed | 13 | 9 | OCTOBER
T-955-7289 | PS5-62-UR-1956C | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone B | 1.1 | To be completed |  | 34 | AUGUST
T-790-7290 | PS5-74-OB-6173D | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone E | 4 | To be completed |  | 21 | DECEMBER
T-836-7291 | PS5-77-OB-1505C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone A | 1 | To be completed |  | 7 | SEPTEMBER
T-305-7292 | PS5-80-IK-7225C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-04-04 | PS5-04-03 | PS5 - Milestone H | 7 | Closed | 32 | 15 | APRIL
T-764-7293 | PS5-34-UR-3931A | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-11-15 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 22 | 22 | NOVEMBER
T-954-7294 | PS5-67-UR-7892A | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | To be completed |  | 40 | NOVEMBER
T-983-7295 | PS5-33-IK-2319A | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-04-06 | PS5-07-02 | PS5 - Milestone H | 7 | Closed | 16 | 44 | APRIL
T-295-7296 | PS5-06-UR-6557D | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone F | 5 | In progress |  | 45 | OCTOBER
T-325-7297 | PS5-41-OB-2253B | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-03-21 | PS5-09-01 | PS5 - Milestone I | 8 | Closed | 12 | 9 | MARCH
T-619-7298 | PS5-40-IK-4017D | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone D | 3 | In progress |  | 35 | SEPTEMBER
T-027-7299 | PS5-20-OB-9623C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-09-20 | PS5-61-07 | PS5 - Milestone G | 6 | Closed | 34 | 28 | SEPTEMBER
T-473-7300 | PS5-16-UR-9603A | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-10-12 | PS5-01-02 | PS5 - Milestone B | 1.1 | Closed | 9 | 18 | OCTOBER
T-780-7301 | PS5-76-IK-4404D | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | To be completed |  | 34 | NOVEMBER
T-789-7302 | PS5-98-OB-3856C | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-04-03 | PS5-99-01 | PS5 - Milestone H | 7 | Closed | 4 | 12 | APRIL
T-272-7303 | PS5-44-IK-7374B | CQP04 - Hydrotest | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-07-10 | PS5-06-03 | PS5 - Milestone F | 5 | Closed | 9 | 7 | JULY
T-217-7304 | PS5-82-OB-2684A | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-03-20 | PS5-61-02 | PS5 - Milestone B | 1.1 | Closed | 37 | 37 | MARCH
T-177-7305 | PS5-13-OB-3398C | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-07-06 | PS5-07-01 | PS5 - Milestone G | 6 | Closed | 24 | 15 | JULY
T-689-7306 | PS5-16-UR-6309A | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone E | 4 | To be completed |  | 46 | OCTOBER
T-558-7307 | PS5-80-IK-7550D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone H | 7 | To be completed |  | 10 | SEPTEMBER
T-829-7308 | PS5-08-UR-4369C | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone A | 1 | In progress |  | 42 | SEPTEMBER
T-456-7309 | PS5-46-OB-4639C | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone G | 6 | In progress |  | 22 | SEPTEMBER
T-388-7310 | PS5-55-OB-7249D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-11-10 | PS5-82-07 | PS5 - Milestone A | 1 | Closed | 47 | 29 | NOVEMBER
T-209-7311 | PS5-78-IK-2079D | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone H | 7 | To be completed |  | 35 | NOVEMBER
T-135-7312 | PS5-82-OB-5252B | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-04-02 | PS5-03-23 | PS5 - Milestone D | 3 | Closed | 37 | 18 | APRIL
T-478-7313 | PS5-30-OB-8039C | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone A | 1 | In progress |  | 14 | OCTOBER
T-763-7314 | PS5-92-UR-1022C | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone A | 1 | In progress |  | 34 | OCTOBER
T-057-7315 | PS5-09-IK-9228C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-06-24 | PS5-11-02 | PS5 - Milestone B | 1.1 | Closed | 8 | 28 | JUNE
T-591-7316 | PS5-63-OB-4730A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | In progress |  | 5 | SEPTEMBER
T-065-7317 | PS5-60-UR-1672B | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone C | 2 | In progress |  | 17 | OCTOBER
T-578-7318 | PS5-65-IK-4956B | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-12-24 | PS5-02-02 | PS5 - Milestone H | 7 | Closed | 14 | 39 | DECEMBER
T-132-7319 | PS5-77-OB-6882D | CQM01 - Pump Installation | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone H | 7 | To be completed |  | 23 | OCTOBER
T-110-7320 | PS5-13-UR-7378B | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | To be completed |  | 4 | NOVEMBER
T-893-7321 | PS5-40-UR-6850D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-10-05 | PS5-01-06 | PS5 - Milestone D | 3 | Closed | 14 | 8 | OCTOBER
T-265-7322 | PS5-33-OB-2995B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone G | 6 | To be completed |  | 36 | SEPTEMBER
T-992-7323 | PS5-69-UR-6172B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-02-15 | PS5-02-02 | PS5 - Milestone C | 2 | Closed | 40 | 30 | FEBRUARY
T-332-7324 | PS5-72-OB-2723B | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone I | 8 | On hold |  | 12 | NOVEMBER
T-466-7325 | PS5-80-UR-2979A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-05-21 | PS5-11-03 | PS5 - Milestone C | 2 | Closed | 30 | 7 | MAY
T-473-7326 | PS5-58-UR-5682D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone G | 6 | To be completed |  | 21 | NOVEMBER
T-623-7327 | PS5-53-UR-9119C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone F | 5 | To be completed |  | 25 | NOVEMBER
T-587-7328 | PS5-14-OB-1860A | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone F | 5 | To be completed |  | 40 | NOVEMBER
T-085-7329 | PS5-72-OB-4081A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone E | 4 | On hold |  | 5 | NOVEMBER
T-566-7330 | PS5-13-OB-2577C | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-10-24 | PS5-06-01 | PS5 - Milestone F | 5 | Closed | 41 | 13 | OCTOBER
T-157-7331 | PS5-20-UR-3704C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone H | 7 | To be completed |  | 24 | DECEMBER
T-897-7332 | PS5-56-OB-4023A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-11-15 | PS5-05-01 | PS5 - Milestone D | 3 | Closed | 28 | 46 | NOVEMBER
T-881-7333 | PS5-91-OB-3007A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone A | 1 | In progress |  | 37 | DECEMBER
T-567-7334 | PS5-31-IK-7479A | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-10-08 | PS5-01-02 | PS5 - Milestone C | 2 | Closed | 48 | 29 | OCTOBER
T-412-7335 | PS5-94-IK-2098C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-07-08 | PS5-05-03 | PS5 - Milestone C | 2 | Closed | 44 | 37 | JULY
T-794-7336 | PS5-35-IK-3056B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-10-06 | PS5-82-07 | PS5 - Milestone F | 5 | Closed | 32 | 5 | OCTOBER
T-884-7337 | PS5-06-OB-4038C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-06-27 | PS5-04-03 | PS5 - Milestone C | 2 | Closed | 35 | 12 | JUNE
T-294-7338 | PS5-98-IK-3823D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-02-02 | PS5-04-04 | PS5 - Milestone I | 8 | Closed | 21 | 26 | FEBRUARY
T-056-7339 | PS5-05-OB-3077D | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | On hold |  | 26 | SEPTEMBER
T-509-7340 | PS5-51-IK-4773C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone G | 6 | On hold |  | 10 | SEPTEMBER
T-771-7341 | PS5-88-UR-1288D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-01-02 | PS5-60-01 | PS5 - Milestone G | 6 | Closed | 15 | 25 | JANUARY
T-770-7342 | PS5-68-IK-7163A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone C | 2 | To be completed |  | 18 | DECEMBER
T-299-7343 | PS5-35-OB-8272A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | On hold |  | 13 | AUGUST
T-893-7344 | PS5-51-OB-4120D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | In progress |  | 42 | NOVEMBER
T-055-7345 | PS5-61-OB-4761A | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-04-16 | PS5-82-02 | PS5 - Milestone I | 8 | Closed | 26 | 48 | APRIL
T-916-7346 | PS5-77-IK-6548C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-12-19 | PS5-03-03 | PS5 - Milestone H | 7 | Closed | 15 | 42 | DECEMBER
T-097-7347 | PS5-94-OB-5054A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | On hold |  | 37 | NOVEMBER
T-870-7348 | PS5-31-OB-3220D | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-10-23 | PS5-12-02 | PS5 - Milestone B | 1.1 | Closed | 30 | 16 | OCTOBER
T-492-7349 | PS5-81-OB-2340C | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone A | 1 | In progress |  | 7 | OCTOBER
T-206-7350 | PS5-06-IK-6367C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-05-21 | PS5-04-04 | PS5 - Milestone C | 2 | Closed | 48 | 5 | MAY
T-395-7351 | PS5-13-UR-1958D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-20 | PS5-60-07 | PS5 - Milestone E | 4 | Closed | 38 | 35 | APRIL
T-925-7352 | PS5-70-OB-7405D | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone E | 4 | In progress |  | 46 | NOVEMBER
T-420-7353 | PS5-08-UR-2990C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone C | 2 | To be completed |  | 10 | OCTOBER
T-796-7354 | PS5-40-IK-3403B | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone A | 1 | To be completed |  | 28 | AUGUST
T-894-7355 | PS5-15-OB-7842D | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone H | 7 | On hold |  | 38 | OCTOBER
T-771-7356 | PS5-13-UR-1018D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone F | 5 | In progress |  | 41 | SEPTEMBER
T-008-7357 | PS5-79-OB-4232A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone D | 3 | On hold |  | 34 | SEPTEMBER
T-964-7358 | PS5-81-OB-3540C | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-11-07 | PS5-01-05 | PS5 - Milestone H | 7 | Closed | 34 | 30 | NOVEMBER
T-245-7359 | PS5-27-UR-8299B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-10-10 | PS5-05-02 | PS5 - Milestone F | 5 | Closed | 31 | 46 | OCTOBER
T-324-7360 | PS5-63-UR-4286A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | In progress |  | 10 | NOVEMBER
T-267-7361 | PS5-57-IK-8415A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone I | 8 | On hold |  | 34 | DECEMBER
T-416-7362 | PS5-92-UR-2730A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-04-08 | PS5-12-02 | PS5 - Milestone C | 2 | Closed | 16 | 37 | APRIL
T-788-7363 | PS5-99-OB-6832B | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone B | 1.1 | To be completed |  | 40 | NOVEMBER
T-416-7364 | PS5-90-IK-7111C | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | On hold |  | 39 | DECEMBER
T-440-7365 | PS5-63-OB-8678A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone H | 7 | To be completed |  | 35 | OCTOBER
T-602-7366 | PS5-07-OB-2587D | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone B | 1.1 | To be completed |  | 32 | AUGUST
T-173-7367 | PS5-03-IK-8042C | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone C | 2 | To be completed |  | 35 | AUGUST
T-162-7368 | PS5-84-OB-2233C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-05-05 | PS5-63-04 | PS5 - Milestone D | 3 | Closed | 13 | 18 | MAY
T-473-7369 | PS5-68-IK-9579A | CQM04 - Vessel | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone H | 7 | In progress |  | 9 | DECEMBER
T-390-7370 | PS5-50-UR-1923C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone G | 6 | In progress |  | 4 | DECEMBER
T-782-7371 | PS5-52-OB-4008C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone A | 1 | In progress |  | 45 | AUGUST
T-823-7372 | PS5-58-OB-9038B | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-04-08 | PS5-03-02 | PS5 - Milestone F | 5 | Closed | 17 | 45 | APRIL
T-878-7373 | PS5-34-UR-5590B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone H | 7 | On hold |  | 8 | OCTOBER
T-109-7374 | PS5-20-OB-8649D | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone B | 1.1 | On hold |  | 40 | AUGUST
T-619-7375 | PS5-97-OB-6599D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone B | 1.1 | To be completed |  | 35 | DECEMBER
T-782-7376 | PS5-34-UR-7921D | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-12-12 | PS5-08-02 | PS5 - Milestone A | 1 | Closed | 14 | 32 | DECEMBER
T-095-7377 | PS5-44-IK-1517C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-07-13 | PS5-09-02 | PS5 - Milestone G | 6 | Closed | 48 | 42 | JULY
T-721-7378 | PS5-88-OB-6250D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-09-26 | PS5-06-03 | PS5 - Milestone B | 1.1 | Closed | 21 | 7 | SEPTEMBER
T-811-7379 | PS5-98-OB-9234D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone A | 1 | To be completed |  | 22 | OCTOBER
T-075-7380 | PS5-79-UR-9650A | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | On hold |  | 5 | AUGUST
T-559-7381 | PS5-65-IK-6716D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-02-09 | PS5-01-09 | PS5 - Milestone F | 5 | Closed | 33 | 5 | FEBRUARY
T-267-7382 | PS5-46-UR-9946D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-06-24 | PS5-61-07 | PS5 - Milestone I | 8 | Closed | 42 | 6 | JUNE
T-972-7383 | PS5-60-IK-9269C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-10-22 | PS5-99-02 | PS5 - Milestone D | 3 | Closed | 43 | 32 | OCTOBER
T-191-7384 | PS5-35-OB-8755D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-05-02 | PS5-09-02 | PS5 - Milestone I | 8 | Closed | 18 | 36 | MAY
T-892-7385 | PS5-35-OB-5630B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-01-16 | PS5-13-01 | PS5 - Milestone H | 7 | Closed | 31 | 40 | JANUARY
T-158-7386 | PS5-03-IK-6909B | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone F | 5 | In progress |  | 26 | DECEMBER
T-458-7387 | PS5-28-OB-5326B | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | To be completed |  | 9 | DECEMBER
T-865-7388 | PS5-14-IK-5421B | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-12-02 | PS5-04-04 | PS5 - Milestone C | 2 | Closed | 11 | 36 | DECEMBER
T-392-7389 | PS5-07-OB-4477C | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-01-20 | PS5-01-09 | PS5 - Milestone F | 5 | Closed | 30 | 17 | JANUARY
T-924-7390 | PS5-31-OB-7563C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone B | 1.1 | On hold |  | 13 | NOVEMBER
T-972-7391 | PS5-99-IK-5594C | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-05-06 | PS5-61-07 | PS5 - Milestone D | 3 | Closed | 33 | 43 | MAY
T-774-7392 | PS5-62-UR-8536A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone G | 6 | On hold |  | 39 | OCTOBER
T-362-7393 | PS5-27-OB-5704C | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-03-19 | PS5-03-02 | PS5 - Milestone A | 1 | Closed | 31 | 43 | MARCH
T-219-7394 | PS5-74-OB-7551D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-11-08 | PS5-03-02 | PS5 - Milestone C | 2 | Closed | 5 | 39 | NOVEMBER
T-098-7395 | PS5-93-OB-9325D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone B | 1.1 | To be completed |  | 46 | AUGUST
T-559-7396 | PS5-61-OB-3954A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone F | 5 | In progress |  | 48 | NOVEMBER
T-114-7397 | PS5-94-UR-7786C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone H | 7 | To be completed |  | 27 | AUGUST
T-451-7398 | PS5-88-OB-9708A | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone F | 5 | On hold |  | 47 | AUGUST
T-792-7399 | PS5-17-OB-2516B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-08-22 | PS5-63-01 | PS5 - Milestone F | 5 | Closed | 7 | 33 | AUGUST
T-421-7400 | PS5-37-UR-1835C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone D | 3 | In progress |  | 5 | OCTOBER
T-291-7401 | PS5-99-UR-4171B | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone A | 1 | In progress |  | 5 | OCTOBER
T-635-7402 | PS5-81-OB-5456C | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | In progress |  | 19 | DECEMBER
T-607-7403 | PS5-46-OB-9534B | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-09-11 | PS5-63-04 | PS5 - Milestone F | 5 | Closed | 31 | 24 | SEPTEMBER
T-972-7404 | PS5-19-IK-3249B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | In progress |  | 19 | SEPTEMBER
T-844-7405 | PS5-48-UR-2126C | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone I | 8 | To be completed |  | 23 | AUGUST
T-710-7406 | PS5-27-OB-7015B | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone G | 6 | To be completed |  | 26 | OCTOBER
T-156-7407 | PS5-77-OB-7748A | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone H | 7 | To be completed |  | 20 | OCTOBER
T-237-7408 | PS5-50-OB-5836C | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-01-26 | PS5-04-01 | PS5 - Milestone G | 6 | Closed | 36 | 15 | JANUARY
T-895-7409 | PS5-06-OB-8705D | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-05-24 | PS5-09-01 | PS5 - Milestone A | 1 | Closed | 42 | 16 | MAY
T-168-7410 | PS5-31-IK-2732C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-02-15 | PS5-05-02 | PS5 - Milestone C | 2 | Closed | 35 | 32 | FEBRUARY
T-876-7411 | PS5-39-OB-8843A | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone G | 6 | In progress |  | 46 | OCTOBER
T-467-7412 | PS5-41-UR-5773A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | In progress |  | 32 | AUGUST
T-166-7413 | PS5-02-OB-1219D | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone E | 4 | On hold |  | 8 | OCTOBER
T-961-7414 | PS5-10-OB-7289C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone E | 4 | In progress |  | 39 | SEPTEMBER
T-317-7415 | PS5-84-UR-7776D | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone F | 5 | To be completed |  | 33 | DECEMBER
T-363-7416 | PS5-49-UR-1565D | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone C | 2 | To be completed |  | 31 | SEPTEMBER
T-877-7417 | PS5-68-UR-7389D | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | To be completed |  | 45 | DECEMBER
T-354-7418 | PS5-17-OB-4016C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-10-24 | PS5-10-03 | PS5 - Milestone C | 2 | Closed | 40 | 7 | OCTOBER
T-246-7419 | PS5-27-OB-1180B | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-10-14 | PS5-07-04 | PS5 - Milestone H | 7 | Closed | 9 | 33 | OCTOBER
T-671-7420 | PS5-56-IK-9944C | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-03-14 | PS5-02-02 | PS5 - Milestone I | 8 | Closed | 7 | 24 | MARCH
T-813-7421 | PS5-62-OB-8131D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-02-25 | PS5-10-06 | PS5 - Milestone I | 8 | Closed | 17 | 7 | FEBRUARY
T-304-7422 | PS5-54-OB-2765C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | To be completed |  | 40 | OCTOBER
T-900-7423 | PS5-94-OB-1229A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone C | 2 | In progress |  | 21 | NOVEMBER
T-140-7424 | PS5-76-IK-9595D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone B | 1.1 | On hold |  | 10 | DECEMBER
T-664-7425 | PS5-40-OB-6722A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-11-01 | PS5-09-03 | PS5 - Milestone H | 7 | Closed | 43 | 7 | NOVEMBER
T-323-7426 | PS5-44-IK-1086D | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone F | 5 | In progress |  | 29 | AUGUST
T-213-7427 | PS5-95-OB-1420A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-08-24 | PS5-03-23 | PS5 - Milestone A | 1 | Closed | 42 | 48 | AUGUST
T-265-7428 | PS5-02-OB-9218D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-11-06 | PS5-01-06 | PS5 - Milestone F | 5 | Closed | 45 | 16 | NOVEMBER
T-083-7429 | PS5-07-OB-4334D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-08-28 | PS5-01-04 | PS5 - Milestone B | 1.1 | Closed | 14 | 13 | AUGUST
T-907-7430 | PS5-20-IK-4167C | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone A | 1 | To be completed |  | 42 | OCTOBER
T-226-7431 | PS5-01-OB-6791C | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-01-07 | PS5-01-06 | PS5 - Milestone B | 1.1 | Closed | 20 | 29 | JANUARY
T-311-7432 | PS5-22-UR-5463C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone E | 4 | In progress |  | 48 | DECEMBER
T-471-7433 | PS5-55-UR-4056B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone F | 5 | On hold |  | 39 | NOVEMBER
T-570-7434 | PS5-10-IK-5356C | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone D | 3 | On hold |  | 36 | OCTOBER
T-538-7435 | PS5-35-OB-7682D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone B | 1.1 | To be completed |  | 41 | AUGUST
T-764-7436 | PS5-83-OB-9711D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-10-28 | PS5-12-01 | PS5 - Milestone B | 1.1 | Closed | 11 | 8 | OCTOBER
T-852-7437 | PS5-73-OB-1091B | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-10-20 | PS5-01-04 | PS5 - Milestone E | 4 | Closed | 12 | 16 | OCTOBER
T-132-7438 | PS5-57-OB-4449A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone G | 6 | To be completed |  | 43 | NOVEMBER
T-155-7439 | PS5-22-IK-2673C | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | In progress |  | 33 | DECEMBER
T-362-7440 | PS5-24-IK-8512A | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone F | 5 | In progress |  | 46 | OCTOBER
T-719-7441 | PS5-52-OB-4562C | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone D | 3 | In progress |  | 42 | DECEMBER
T-684-7442 | PS5-31-OB-1416C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-04-03 | PS5-10-02 | PS5 - Milestone F | 5 | Closed | 38 | 46 | APRIL
T-290-7443 | PS5-15-OB-6700C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-08-26 | PS5-04-03 | PS5 - Milestone B | 1.1 | Closed | 26 | 5 | AUGUST
T-748-7444 | PS5-03-OB-4901A | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone F | 5 | On hold |  | 40 | DECEMBER
T-719-7445 | PS5-21-UR-7122D | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-05-15 | PS5-04-01 | PS5 - Milestone G | 6 | Closed | 24 | 21 | MAY
T-684-7446 | PS5-33-UR-3656D | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-06-27 | PS5-03-23 | PS5 - Milestone E | 4 | Closed | 37 | 35 | JUNE
T-837-7447 | PS5-52-UR-1304C | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-01-11 | PS5-99-02 | PS5 - Milestone E | 4 | Closed | 16 | 46 | JANUARY
T-803-7448 | PS5-50-UR-2116B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone E | 4 | To be completed |  | 34 | OCTOBER
T-212-7449 | PS5-22-UR-2812C | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-07-09 | PS5-05-02 | PS5 - Milestone C | 2 | Closed | 13 | 48 | JULY
T-318-7450 | PS5-20-UR-1139B | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone F | 5 | On hold |  | 8 | NOVEMBER
T-471-7451 | PS5-21-OB-3316A | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-08-22 | PS5-08-02 | PS5 - Milestone H | 7 | Closed | 41 | 10 | AUGUST
T-717-7452 | PS5-20-UR-4875B | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | On hold |  | 16 | OCTOBER
T-097-7453 | PS5-44-OB-6692D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone F | 5 | In progress |  | 16 | AUGUST
T-786-7454 | PS5-70-UR-3786A | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | In progress |  | 21 | NOVEMBER
T-473-7455 | PS5-36-OB-8390B | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone C | 2 | To be completed |  | 23 | SEPTEMBER
T-923-7456 | PS5-90-OB-4110C | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-11-06 | PS5-08-02 | PS5 - Milestone F | 5 | Closed | 48 | 13 | NOVEMBER
T-916-7457 | PS5-11-UR-3618D | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-06-21 | PS5-09-03 | PS5 - Milestone F | 5 | Closed | 38 | 46 | JUNE
T-786-7458 | PS5-46-UR-7309D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone B | 1.1 | In progress |  | 43 | NOVEMBER
T-354-7459 | PS5-45-UR-8249D | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone H | 7 | In progress |  | 9 | OCTOBER
T-975-7460 | PS5-98-OB-2561C | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone I | 8 | In progress |  | 26 | AUGUST
T-437-7461 | PS5-23-UR-8736D | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-11 | PS5-60-01 | PS5 - Milestone E | 4 | Closed | 6 | 6 | APRIL
T-706-7462 | PS5-33-OB-4983A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone D | 3 | To be completed |  | 9 | NOVEMBER
T-559-7463 | PS5-24-UR-3655D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone C | 2 | To be completed |  | 25 | DECEMBER
T-822-7464 | PS5-70-UR-6171D | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone F | 5 | To be completed |  | 32 | SEPTEMBER
T-331-7465 | PS5-89-OB-5125C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-07-08 | PS5-07-04 | PS5 - Milestone I | 8 | Closed | 35 | 10 | JULY
T-971-7466 | PS5-04-OB-6477B | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone H | 7 | In progress |  | 29 | DECEMBER
T-624-7467 | PS5-41-OB-5854A | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-10-18 | PS5-62-01 | PS5 - Milestone C | 2 | Closed | 14 | 19 | OCTOBER
T-963-7468 | PS5-58-UR-8647D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-10-03 | PS5-07-02 | PS5 - Milestone G | 6 | Closed | 12 | 39 | OCTOBER
T-192-7469 | PS5-95-IK-6971C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-07-06 | PS5-01-05 | PS5 - Milestone A | 1 | Closed | 35 | 48 | JULY
T-248-7470 | PS5-97-OB-7359B | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone F | 5 | On hold |  | 17 | DECEMBER
T-703-7471 | PS5-35-IK-7695B | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone C | 2 | To be completed |  | 48 | OCTOBER
T-711-7472 | PS5-59-OB-2608D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone G | 6 | On hold |  | 33 | DECEMBER
T-606-7473 | PS5-34-OB-4654B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-04-27 | PS5-01-04 | PS5 - Milestone F | 5 | Closed | 17 | 37 | APRIL
T-111-7474 | PS5-60-IK-9917B | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone C | 2 | To be completed |  | 6 | DECEMBER
T-743-7475 | PS5-67-OB-5306D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone D | 3 | In progress |  | 34 | NOVEMBER
T-468-7476 | PS5-44-IK-4659D | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-10-15 | PS5-99-02 | PS5 - Milestone I | 8 | Closed | 35 | 42 | OCTOBER
T-195-7477 | PS5-96-UR-5633A | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | To be completed |  | 21 | AUGUST
T-296-7478 | PS5-55-UR-2209A | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone F | 5 | To be completed |  | 13 | NOVEMBER
T-793-7479 | PS5-45-UR-9220A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone I | 8 | To be completed |  | 25 | SEPTEMBER
T-048-7480 | PS5-74-IK-4038B | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone F | 5 | To be completed |  | 6 | NOVEMBER
T-152-7481 | PS5-66-UR-9731D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | In progress |  | 25 | DECEMBER
T-016-7482 | PS5-39-UR-7475A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone E | 4 | To be completed |  | 6 | SEPTEMBER
T-479-7483 | PS5-43-UR-4037B | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone I | 8 | In progress |  | 11 | AUGUST
T-297-7484 | PS5-53-OB-3197B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-10-16 | PS5-05-02 | PS5 - Milestone I | 8 | Closed | 9 | 24 | OCTOBER
T-365-7485 | PS5-72-OB-4309C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone D | 3 | In progress |  | 18 | SEPTEMBER
T-957-7486 | PS5-91-OB-5755D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-10-10 | PS5-60-01 | PS5 - Milestone B | 1.1 | Closed | 6 | 22 | OCTOBER
T-221-7487 | PS5-04-UR-8887B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | To be completed |  | 15 | OCTOBER
T-080-7488 | PS5-56-IK-8926A | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-12-15 | PS5-09-02 | PS5 - Milestone A | 1 | Closed | 39 | 41 | DECEMBER
T-739-7489 | PS5-10-OB-5402D | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-05-01 | PS5-01-03 | PS5 - Milestone I | 8 | Closed | 42 | 31 | MAY
T-407-7490 | PS5-64-OB-6301D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone I | 8 | To be completed |  | 23 | DECEMBER
T-547-7491 | PS5-35-OB-7135A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | To be completed |  | 8 | DECEMBER
T-188-7492 | PS5-94-IK-5691A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone H | 7 | In progress |  | 25 | DECEMBER
T-608-7493 | PS5-88-UR-2664B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone H | 7 | On hold |  | 28 | NOVEMBER
T-913-7494 | PS5-83-UR-2538D | CQM04 - Vessel | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone H | 7 | To be completed |  | 11 | OCTOBER
T-216-7495 | PS5-13-OB-6399D | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone A | 1 | To be completed |  | 37 | AUGUST
T-107-7496 | PS5-02-OB-8198D | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-04-12 | PS5-05-03 | PS5 - Milestone D | 3 | Closed | 20 | 40 | APRIL
T-832-7497 | PS5-04-IK-4732B | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone F | 5 | In progress |  | 30 | NOVEMBER
T-548-7498 | PS5-81-IK-4828B | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone G | 6 | On hold |  | 8 | DECEMBER
T-088-7499 | PS5-09-IK-4555A | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone H | 7 | To be completed |  | 17 | OCTOBER
T-973-7500 | PS5-18-IK-1065C | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone B | 1.1 | To be completed |  | 8 | NOVEMBER
T-411-7501 | PS5-66-OB-7585A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone D | 3 | To be completed |  | 31 | SEPTEMBER
T-986-7502 | PS5-21-IK-7555D | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone D | 3 | To be completed |  | 7 | AUGUST
T-374-7503 | PS5-64-UR-7181C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | To be completed |  | 42 | NOVEMBER
T-504-7504 | PS5-48-OB-2617D | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone F | 5 | To be completed |  | 47 | NOVEMBER
T-452-7505 | PS5-04-OB-9479A | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone B | 1.1 | To be completed |  | 12 | OCTOBER
T-268-7506 | PS5-93-OB-1351D | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone E | 4 | To be completed |  | 37 | SEPTEMBER
T-311-7507 | PS5-40-OB-5498C | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone C | 2 | On hold |  | 9 | NOVEMBER
T-505-7508 | PS5-51-UR-1109B | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone E | 4 | In progress |  | 13 | SEPTEMBER
T-112-7509 | PS5-30-UR-1192D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | To be completed |  | 34 | AUGUST
T-195-7510 | PS5-99-OB-8075C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | In progress |  | 7 | NOVEMBER
T-458-7511 | PS5-10-UR-9631B | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone H | 7 | To be completed |  | 43 | DECEMBER
T-711-7512 | PS5-13-IK-4064A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | In progress |  | 19 | DECEMBER
T-355-7513 | PS5-81-OB-5785C | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | To be completed |  | 14 | DECEMBER
T-060-7514 | PS5-67-UR-2769D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-09-10 | PS5-01-01 | PS5 - Milestone E | 4 | Closed | 44 | 17 | SEPTEMBER
T-509-7515 | PS5-53-OB-2516B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-01-04 | PS5-10-06 | PS5 - Milestone I | 8 | Closed | 9 | 20 | JANUARY
T-518-7516 | PS5-67-UR-3321B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-11-18 | PS5-09-03 | PS5 - Milestone C | 2 | Closed | 34 | 43 | NOVEMBER
T-155-7517 | PS5-20-UR-3560D | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone D | 3 | In progress |  | 4 | OCTOBER
T-753-7518 | PS5-78-UR-4804A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-06-11 | PS5-01-09 | PS5 - Milestone H | 7 | Closed | 31 | 19 | JUNE
T-370-7519 | PS5-49-OB-3329A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-12-07 | PS5-60-10 | PS5 - Milestone B | 1.1 | Closed | 40 | 34 | DECEMBER
T-908-7520 | PS5-77-IK-2803A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-11-08 | PS5-99-02 | PS5 - Milestone I | 8 | Closed | 22 | 34 | NOVEMBER
T-299-7521 | PS5-39-IK-6594B | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-08-19 | PS5-01-09 | PS5 - Milestone I | 8 | Closed | 23 | 33 | AUGUST
T-716-7522 | PS5-70-OB-1094A | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone C | 2 | In progress |  | 21 | DECEMBER
T-298-7523 | PS5-51-IK-9895B | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-01-09 | PS5-06-03 | PS5 - Milestone C | 2 | Closed | 33 | 14 | JANUARY
T-767-7524 | PS5-64-IK-5995A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone H | 7 | To be completed |  | 8 | NOVEMBER
T-352-7525 | PS5-96-OB-9281A | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-03-24 | PS5-04-02 | PS5 - Milestone E | 4 | Closed | 17 | 10 | MARCH
T-561-7526 | PS5-80-UR-2652A | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-03-17 | PS5-60-04 | PS5 - Milestone G | 6 | Closed | 6 | 4 | MARCH
T-615-7527 | PS5-81-IK-3212C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone H | 7 | In progress |  | 44 | NOVEMBER
T-411-7528 | PS5-10-OB-2871C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-12-12 | PS5-06-03 | PS5 - Milestone A | 1 | Closed | 21 | 44 | DECEMBER
T-170-7529 | PS5-09-IK-8724D | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-06-16 | PS5-01-04 | PS5 - Milestone I | 8 | Closed | 47 | 40 | JUNE
T-978-7530 | PS5-61-OB-7022C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | In progress |  | 12 | DECEMBER
T-396-7531 | PS5-73-UR-2393B | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-12-25 | PS5-04-04 | PS5 - Milestone G | 6 | Closed | 36 | 39 | DECEMBER
T-331-7532 | PS5-03-IK-7302B | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone F | 5 | To be completed |  | 48 | DECEMBER
T-743-7533 | PS5-58-OB-8920A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-04-17 | PS5-10-03 | PS5 - Milestone I | 8 | Closed | 9 | 46 | APRIL
T-559-7534 | PS5-86-UR-9027B | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone H | 7 | In progress |  | 29 | SEPTEMBER
T-321-7535 | PS5-35-IK-2693C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone B | 1.1 | To be completed |  | 42 | OCTOBER
T-013-7536 | PS5-68-UR-3024D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone F | 5 | To be completed |  | 48 | SEPTEMBER
T-023-7537 | PS5-28-UR-8199D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone A | 1 | To be completed |  | 19 | DECEMBER
T-023-7538 | PS5-98-UR-5080D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone D | 3 | In progress |  | 7 | DECEMBER
T-619-7539 | PS5-59-UR-6719B | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone E | 4 | To be completed |  | 12 | OCTOBER
T-178-7540 | PS5-60-IK-8078A | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-12-11 | PS5-10-01 | PS5 - Milestone H | 7 | Closed | 6 | 22 | DECEMBER
T-521-7541 | PS5-17-OB-8495C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone D | 3 | In progress |  | 32 | OCTOBER
T-155-7542 | PS5-92-OB-2527C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-05-24 | PS5-12-02 | PS5 - Milestone A | 1 | Closed | 5 | 22 | MAY
T-153-7543 | PS5-46-UR-1652C | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone G | 6 | To be completed |  | 30 | SEPTEMBER
T-823-7544 | PS5-12-OB-2065D | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone F | 5 | On hold |  | 19 | NOVEMBER
T-166-7545 | PS5-99-IK-6578D | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone D | 3 | To be completed |  | 47 | NOVEMBER
T-673-7546 | PS5-61-OB-2461C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-08-07 | PS5-09-03 | PS5 - Milestone I | 8 | Closed | 47 | 9 | AUGUST
T-579-7547 | PS5-58-UR-4645B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | In progress |  | 7 | OCTOBER
T-339-7548 | PS5-01-IK-5108C | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone D | 3 | To be completed |  | 48 | OCTOBER
T-187-7549 | PS5-52-OB-5641A | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-03-11 | PS5-09-03 | PS5 - Milestone A | 1 | Closed | 26 | 41 | MARCH
T-977-7550 | PS5-73-IK-6381C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone G | 6 | To be completed |  | 30 | NOVEMBER
T-979-7551 | PS5-83-OB-5618C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-07-10 | PS5-63-04 | PS5 - Milestone G | 6 | Closed | 11 | 25 | JULY
T-256-7552 | PS5-35-OB-1622D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-02-27 | PS5-09-03 | PS5 - Milestone H | 7 | Closed | 29 | 27 | FEBRUARY
T-705-7553 | PS5-23-IK-6692C | CQS03 - Deluge System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-08-26 | PS5-04-04 | PS5 - Milestone H | 7 | Closed | 4 | 5 | AUGUST
T-162-7554 | PS5-81-OB-6881C | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-05-13 | PS5-63-01 | PS5 - Milestone G | 6 | Closed | 21 | 22 | MAY
T-569-7555 | PS5-99-UR-7211D | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone C | 2 | To be completed |  | 41 | OCTOBER
T-651-7556 | PS5-22-OB-2300D | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone E | 4 | In progress |  | 43 | NOVEMBER
T-665-7557 | PS5-02-IK-2627A | CQP05 - Insulation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone I | 8 | In progress |  | 37 | AUGUST
T-982-7558 | PS5-97-UR-3028A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone A | 1 | To be completed |  | 22 | OCTOBER
T-050-7559 | PS5-40-IK-7115C | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone F | 5 | In progress |  | 21 | OCTOBER
T-747-7560 | PS5-76-UR-2202B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-06-09 | PS5-10-01 | PS5 - Milestone B | 1.1 | Closed | 46 | 24 | JUNE
T-365-7561 | PS5-06-UR-3852D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | To be completed |  | 38 | OCTOBER
T-687-7562 | PS5-77-UR-3422D | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-02-26 | PS5-01-03 | PS5 - Milestone I | 8 | Closed | 48 | 21 | FEBRUARY
T-140-7563 | PS5-86-IK-6932A | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-11-04 | PS5-07-01 | PS5 - Milestone E | 4 | Closed | 48 | 4 | NOVEMBER
T-749-7564 | PS5-08-OB-4089B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone D | 3 | To be completed |  | 26 | SEPTEMBER
T-703-7565 | PS5-75-IK-7290A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | To be completed |  | 18 | OCTOBER
T-395-7566 | PS5-37-IK-1125C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-05-26 | PS5-08-02 | PS5 - Milestone A | 1 | Closed | 20 | 41 | MAY
T-349-7567 | PS5-74-IK-6905B | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone C | 2 | In progress |  | 40 | AUGUST
T-338-7568 | PS5-35-OB-5794C | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-05-15 | PS5-10-05 | PS5 - Milestone H | 7 | Closed | 47 | 28 | MAY
T-300-7569 | PS5-27-UR-8544C | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone F | 5 | To be completed |  | 20 | DECEMBER
T-496-7570 | PS5-39-OB-7211B | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | To be completed |  | 13 | AUGUST
T-257-7571 | PS5-48-IK-1147C | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone C | 2 | In progress |  | 6 | OCTOBER
T-671-7572 | PS5-39-UR-8156D | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone G | 6 | In progress |  | 6 | AUGUST
T-157-7573 | PS5-77-OB-2357C | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone B | 1.1 | In progress |  | 5 | OCTOBER
T-317-7574 | PS5-74-UR-8752B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-12 | PS5-60-10 | PS5 - Milestone A | 1 | Closed | 32 | 29 | APRIL
T-571-7575 | PS5-44-UR-8195A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone C | 2 | In progress |  | 10 | NOVEMBER
T-170-7576 | PS5-87-IK-1086D | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-10-26 | PS5-02-03 | PS5 - Milestone H | 7 | Closed | 46 | 6 | OCTOBER
T-052-7577 | PS5-62-IK-7087D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-03-23 | PS5-10-05 | PS5 - Milestone B | 1.1 | Closed | 29 | 20 | MARCH
T-210-7578 | PS5-66-IK-5916B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-12-12 | PS5-10-02 | PS5 - Milestone C | 2 | Closed | 8 | 23 | DECEMBER
T-418-7579 | PS5-57-OB-3278B | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-11-24 | PS5-03-03 | PS5 - Milestone C | 2 | Closed | 12 | 13 | NOVEMBER
T-428-7580 | PS5-36-UR-3204B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone A | 1 | To be completed |  | 17 | DECEMBER
T-546-7581 | PS5-53-OB-5051A | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-01-16 | PS5-01-07 | PS5 - Milestone D | 3 | Closed | 27 | 37 | JANUARY
T-686-7582 | PS5-04-OB-4653D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-05 | PS5-60-04 | PS5 - Milestone D | 3 | Closed | 27 | 6 | MAY
T-805-7583 | PS5-78-UR-5371A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | To be completed |  | 37 | AUGUST
T-157-7584 | PS5-95-IK-3628A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone D | 3 | In progress |  | 27 | DECEMBER
T-979-7585 | PS5-96-OB-1748D | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone B | 1.1 | To be completed |  | 35 | SEPTEMBER
T-574-7586 | PS5-85-OB-4220A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-12-16 | PS5-02-02 | PS5 - Milestone A | 1 | Closed | 39 | 9 | DECEMBER
T-670-7587 | PS5-78-OB-9127D | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone B | 1.1 | To be completed |  | 20 | OCTOBER
T-410-7588 | PS5-66-OB-1460B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-03-09 | PS5-03-02 | PS5 - Milestone B | 1.1 | Closed | 22 | 23 | MARCH
T-924-7589 | PS5-64-UR-6848A | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-03-11 | PS5-01-07 | PS5 - Milestone B | 1.1 | Closed | 9 | 15 | MARCH
T-293-7590 | PS5-68-OB-4988C | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-02-07 | PS5-09-04 | PS5 - Milestone C | 2 | Closed | 32 | 33 | FEBRUARY
T-538-7591 | PS5-78-OB-3980C | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-10-02 | PS5-12-01 | PS5 - Milestone B | 1.1 | Closed | 13 | 6 | OCTOBER
T-607-7592 | PS5-52-IK-8609B | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone H | 7 | In progress |  | 38 | DECEMBER
T-527-7593 | PS5-09-OB-4538B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone F | 5 | On hold |  | 32 | DECEMBER
T-706-7594 | PS5-15-IK-8733A | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-12-24 | PS5-01-05 | PS5 - Milestone F | 5 | Closed | 37 | 19 | DECEMBER
T-433-7595 | PS5-78-OB-2459A | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-02-06 | PS5-09-03 | PS5 - Milestone D | 3 | Closed | 16 | 35 | FEBRUARY
T-535-7596 | PS5-82-OB-1596A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone G | 6 | In progress |  | 4 | NOVEMBER
T-928-7597 | PS5-76-UR-2120D | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-08-12 | PS5-60-10 | PS5 - Milestone G | 6 | Closed | 47 | 4 | AUGUST
T-634-7598 | PS5-78-OB-4939D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone C | 2 | To be completed |  | 17 | DECEMBER
T-332-7599 | PS5-16-UR-5368B | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | In progress |  | 46 | AUGUST
T-185-7600 | PS5-64-OB-1345C | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-04-12 | PS5-04-01 | PS5 - Milestone H | 7 | Closed | 44 | 38 | APRIL
T-625-7601 | PS5-02-OB-2596A | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone I | 8 | In progress |  | 19 | DECEMBER
T-058-7602 | PS5-37-OB-1224C | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-01-26 | PS5-12-01 | PS5 - Milestone D | 3 | Closed | 12 | 22 | JANUARY
T-441-7603 | PS5-64-OB-4727C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-08-10 | PS5-62-02 | PS5 - Milestone I | 8 | Closed | 35 | 19 | AUGUST
T-365-7604 | PS5-32-IK-3260C | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | To be completed |  | 4 | SEPTEMBER
T-272-7605 | PS5-97-IK-6309B | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-10-21 | PS5-60-01 | PS5 - Milestone H | 7 | Closed | 10 | 17 | OCTOBER
T-566-7606 | PS5-94-OB-7935B | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone F | 5 | To be completed |  | 42 | SEPTEMBER
T-577-7607 | PS5-56-OB-8928C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | On hold |  | 41 | DECEMBER
T-444-7608 | PS5-68-OB-7759C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | In progress |  | 18 | NOVEMBER
T-845-7609 | PS5-88-IK-5582A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone C | 2 | In progress |  | 16 | AUGUST
T-251-7610 | PS5-32-OB-9653B | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-02-06 | PS5-08-01 | PS5 - Milestone C | 2 | Closed | 5 | 24 | FEBRUARY
T-273-7611 | PS5-37-OB-3989C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone A | 1 | In progress |  | 28 | OCTOBER
T-958-7612 | PS5-43-UR-5265A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | To be completed |  | 27 | NOVEMBER
T-895-7613 | PS5-45-UR-3579C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-08-05 | PS5-07-01 | PS5 - Milestone D | 3 | Closed | 36 | 36 | AUGUST
T-824-7614 | PS5-76-OB-9685D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone A | 1 | To be completed |  | 32 | SEPTEMBER
T-053-7615 | PS5-60-IK-6805B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone D | 3 | On hold |  | 24 | AUGUST
T-058-7616 | PS5-02-OB-6241D | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-02-09 | PS5-13-01 | PS5 - Milestone H | 7 | Closed | 36 | 30 | FEBRUARY
T-388-7617 | PS5-06-IK-2048A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone B | 1.1 | On hold |  | 20 | OCTOBER
T-317-7618 | PS5-88-IK-1676C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone A | 1 | To be completed |  | 17 | OCTOBER
T-885-7619 | PS5-22-OB-8940D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-12-14 | PS5-62-01 | PS5 - Milestone A | 1 | Closed | 25 | 5 | DECEMBER
T-371-7620 | PS5-05-IK-7924C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone D | 3 | On hold |  | 21 | SEPTEMBER
T-887-7621 | PS5-25-UR-6863B | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-02-28 | PS5-11-02 | PS5 - Milestone B | 1.1 | Closed | 38 | 6 | FEBRUARY
T-947-7622 | PS5-81-OB-6028B | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone B | 1.1 | On hold |  | 26 | OCTOBER
T-541-7623 | PS5-61-OB-1575D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-08-15 | PS5-63-01 | PS5 - Milestone C | 2 | Closed | 7 | 29 | AUGUST
T-678-7624 | PS5-11-IK-6550B | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone G | 6 | To be completed |  | 28 | AUGUST
T-870-7625 | PS5-27-IK-9206D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | To be completed |  | 20 | NOVEMBER
T-124-7626 | PS5-26-OB-6705B | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | To be completed |  | 25 | SEPTEMBER
T-691-7627 | PS5-97-OB-9094A | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | On hold |  | 33 | DECEMBER
T-379-7628 | PS5-23-OB-9226C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone G | 6 | In progress |  | 16 | NOVEMBER
T-890-7629 | PS5-53-IK-4117D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-18 | PS5-60-01 | PS5 - Milestone B | 1.1 | Closed | 18 | 29 | JUNE
T-772-7630 | PS5-86-OB-5765B | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-04-10 | PS5-07-01 | PS5 - Milestone C | 2 | Closed | 20 | 4 | APRIL
T-003-7631 | PS5-32-OB-8402B | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-03-14 | PS5-09-03 | PS5 - Milestone A | 1 | Closed | 23 | 39 | MARCH
T-442-7632 | PS5-78-OB-5662D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone E | 4 | To be completed |  | 10 | NOVEMBER
T-629-7633 | PS5-38-IK-9726A | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-03-11 | PS5-06-01 | PS5 - Milestone B | 1.1 | Closed | 16 | 28 | MARCH
T-866-7634 | PS5-10-OB-7043B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone D | 3 | In progress |  | 16 | SEPTEMBER
T-699-7635 | PS5-20-IK-6302D | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone H | 7 | To be completed |  | 40 | AUGUST
T-252-7636 | PS5-48-OB-5559B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | To be completed |  | 21 | NOVEMBER
T-654-7637 | PS5-76-UR-6607A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-06-04 | PS5-07-02 | PS5 - Milestone I | 8 | Closed | 43 | 14 | JUNE
T-928-7638 | PS5-32-OB-9249B | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone I | 8 | To be completed |  | 18 | OCTOBER
T-879-7639 | PS5-93-OB-5573D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone A | 1 | To be completed |  | 17 | OCTOBER
T-556-7640 | PS5-95-OB-7086A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone B | 1.1 | To be completed |  | 39 | DECEMBER
T-777-7641 | PS5-97-UR-4656B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | In progress |  | 11 | AUGUST
T-506-7642 | PS5-04-OB-1637C | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | On hold |  | 13 | DECEMBER
T-720-7643 | PS5-10-IK-7087B | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-07-28 | PS5-61-02 | PS5 - Milestone E | 4 | Closed | 30 | 5 | JULY
T-292-7644 | PS5-04-OB-7422C | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-11-06 | PS5-11-03 | PS5 - Milestone H | 7 | Closed | 28 | 9 | NOVEMBER
T-783-7645 | PS5-89-IK-3621D | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-10-07 | PS5-99-03 | PS5 - Milestone G | 6 | Closed | 37 | 18 | OCTOBER
T-871-7646 | PS5-91-OB-1631C | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-12-24 | PS5-02-02 | PS5 - Milestone D | 3 | Closed | 17 | 13 | DECEMBER
T-867-7647 | PS5-59-OB-3697D | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone I | 8 | On hold |  | 47 | SEPTEMBER
T-034-7648 | PS5-55-IK-6133B | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-05-17 | PS5-63-01 | PS5 - Milestone G | 6 | Closed | 45 | 17 | MAY
T-062-7649 | PS5-63-UR-8756A | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | In progress |  | 26 | NOVEMBER
T-155-7650 | PS5-37-OB-8329D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | In progress |  | 25 | SEPTEMBER
T-489-7651 | PS5-38-OB-8779B | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone E | 4 | In progress |  | 13 | AUGUST
T-799-7652 | PS5-74-IK-8432C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-01-09 | PS5-13-01 | PS5 - Milestone C | 2 | Closed | 47 | 43 | JANUARY
T-958-7653 | PS5-43-IK-7463A | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone C | 2 | To be completed |  | 14 | AUGUST
T-205-7654 | PS5-01-IK-9747C | CQM04 - Vessel | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-12-07 | PS5-01-02 | PS5 - Milestone D | 3 | Closed | 19 | 21 | DECEMBER
T-874-7655 | PS5-04-IK-1663C | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone C | 2 | To be completed |  | 45 | NOVEMBER
T-331-7656 | PS5-99-UR-3071C | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone D | 3 | On hold |  | 16 | SEPTEMBER
T-557-7657 | PS5-23-IK-5291D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone I | 8 | To be completed |  | 42 | OCTOBER
T-026-7658 | PS5-74-IK-1574D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-07-13 | PS5-01-06 | PS5 - Milestone A | 1 | Closed | 33 | 21 | JULY
T-581-7659 | PS5-52-IK-7062C | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | In progress |  | 30 | NOVEMBER
T-210-7660 | PS5-89-OB-2762A | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone B | 1.1 | In progress |  | 24 | OCTOBER
T-218-7661 | PS5-27-IK-1699B | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone G | 6 | To be completed |  | 46 | OCTOBER
T-161-7662 | PS5-76-IK-7219C | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone D | 3 | On hold |  | 9 | NOVEMBER
T-765-7663 | PS5-99-UR-2231D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-03-19 | PS5-12-02 | PS5 - Milestone C | 2 | Closed | 18 | 29 | MARCH
T-817-7664 | PS5-27-IK-9095B | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-11-17 | PS5-82-01 | PS5 - Milestone E | 4 | Closed | 24 | 25 | NOVEMBER
T-513-7665 | PS5-45-IK-3522B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-02-07 | PS5-10-03 | PS5 - Milestone F | 5 | Closed | 4 | 16 | FEBRUARY
T-072-7666 | PS5-85-OB-2923D | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone C | 2 | In progress |  | 24 | AUGUST
T-380-7667 | PS5-24-IK-4144C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-03-27 | PS5-07-04 | PS5 - Milestone F | 5 | Closed | 26 | 44 | MARCH
T-933-7668 | PS5-20-OB-9676B | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | To be completed |  | 11 | DECEMBER
T-661-7669 | PS5-09-IK-6366C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone G | 6 | In progress |  | 20 | SEPTEMBER
T-546-7670 | PS5-16-OB-7065B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-04-08 | PS5-06-03 | PS5 - Milestone C | 2 | Closed | 12 | 41 | APRIL
T-265-7671 | PS5-08-IK-6871A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-10-23 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 4 | 17 | OCTOBER
T-894-7672 | PS5-31-OB-8615D | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone C | 2 | On hold |  | 16 | DECEMBER
T-404-7673 | PS5-21-OB-4124D | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone A | 1 | To be completed |  | 19 | SEPTEMBER
T-716-7674 | PS5-44-UR-4513B | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-08-02 | PS5-01-09 | PS5 - Milestone E | 4 | Closed | 15 | 19 | AUGUST
T-752-7675 | PS5-33-IK-3954C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone A | 1 | To be completed |  | 43 | NOVEMBER
T-345-7676 | PS5-38-UR-1019A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | On hold |  | 44 | AUGUST
T-900-7677 | PS5-54-OB-6272A | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone C | 2 | On hold |  | 33 | SEPTEMBER
T-957-7678 | PS5-70-OB-9507C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone G | 6 | In progress |  | 40 | OCTOBER
T-547-7679 | PS5-12-OB-5767C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone D | 3 | On hold |  | 29 | DECEMBER
T-562-7680 | PS5-38-OB-5160C | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone H | 7 | In progress |  | 25 | OCTOBER
T-053-7681 | PS5-79-OB-2879D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone F | 5 | To be completed |  | 35 | SEPTEMBER
T-659-7682 | PS5-71-OB-9255C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-04-09 | PS5-12-01 | PS5 - Milestone H | 7 | Closed | 30 | 5 | APRIL
T-797-7683 | PS5-52-OB-2467B | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | On hold |  | 11 | SEPTEMBER
T-924-7684 | PS5-28-OB-8132D | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-01-27 | PS5-03-03 | PS5 - Milestone F | 5 | Closed | 27 | 43 | JANUARY
T-404-7685 | PS5-66-IK-5206A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone D | 3 | In progress |  | 21 | AUGUST
T-368-7686 | PS5-57-OB-6498B | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-02-23 | PS5-99-03 | PS5 - Milestone C | 2 | Closed | 7 | 48 | FEBRUARY
T-333-7687 | PS5-10-OB-1006C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone F | 5 | In progress |  | 31 | DECEMBER
T-357-7688 | PS5-08-IK-7441D | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-09-28 | PS5-01-07 | PS5 - Milestone G | 6 | Closed | 29 | 46 | SEPTEMBER
T-584-7689 | PS5-40-OB-1282A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone H | 7 | On hold |  | 5 | OCTOBER
T-078-7690 | PS5-59-UR-1881D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-08-07 | PS5-12-01 | PS5 - Milestone G | 6 | Closed | 21 | 4 | AUGUST
T-605-7691 | PS5-70-UR-5246A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone D | 3 | In progress |  | 35 | SEPTEMBER
T-118-7692 | PS5-87-OB-3292D | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone G | 6 | In progress |  | 16 | DECEMBER
T-833-7693 | PS5-01-UR-9976C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone H | 7 | To be completed |  | 16 | SEPTEMBER
T-879-7694 | PS5-82-OB-8829C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | On hold |  | 30 | SEPTEMBER
T-261-7695 | PS5-80-OB-6943B | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-12-11 | PS5-62-01 | PS5 - Milestone H | 7 | Closed | 28 | 4 | DECEMBER
T-094-7696 | PS5-88-OB-1505D | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-01-04 | PS5-01-02 | PS5 - Milestone G | 6 | Closed | 29 | 18 | JANUARY
T-813-7697 | PS5-40-UR-5711B | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone A | 1 | On hold |  | 20 | NOVEMBER
T-123-7698 | PS5-39-UR-5900B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone G | 6 | To be completed |  | 9 | AUGUST
T-531-7699 | PS5-93-IK-4077B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-10-28 | PS5-02-01 | PS5 - Milestone C | 2 | Closed | 39 | 10 | OCTOBER
T-258-7700 | PS5-98-UR-2778C | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone E | 4 | In progress |  | 32 | AUGUST
T-335-7701 | PS5-60-OB-7095D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-05-21 | PS5-07-04 | PS5 - Milestone F | 5 | Closed | 44 | 13 | MAY
T-049-7702 | PS5-65-OB-3974D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-07-22 | PS5-04-03 | PS5 - Milestone D | 3 | Closed | 15 | 32 | JULY
T-720-7703 | PS5-79-UR-5912D | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-04-19 | PS5-82-02 | PS5 - Milestone A | 1 | Closed | 10 | 43 | APRIL
T-511-7704 | PS5-91-OB-6121B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-03-24 | PS5-10-02 | PS5 - Milestone C | 2 | Closed | 22 | 40 | MARCH
T-886-7705 | PS5-21-OB-2680A | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-05-27 | PS5-08-02 | PS5 - Milestone I | 8 | Closed | 44 | 11 | MAY
T-144-7706 | PS5-80-OB-6907B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone I | 8 | To be completed |  | 7 | AUGUST
T-814-7707 | PS5-15-UR-2714B | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone G | 6 | On hold |  | 8 | SEPTEMBER
T-379-7708 | PS5-40-OB-9627B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone D | 3 | In progress |  | 22 | SEPTEMBER
T-409-7709 | PS5-19-IK-8737D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-09-09 | PS5-12-01 | PS5 - Milestone A | 1 | Closed | 17 | 35 | SEPTEMBER
T-963-7710 | PS5-31-UR-6279B | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone B | 1.1 | To be completed |  | 9 | NOVEMBER
T-979-7711 | PS5-71-UR-6848D | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-08-24 | PS5-01-01 | PS5 - Milestone C | 2 | Closed | 7 | 27 | AUGUST
T-276-7712 | PS5-58-UR-1970B | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone A | 1 | To be completed |  | 25 | AUGUST
T-794-7713 | PS5-62-UR-6207D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone C | 2 | To be completed |  | 33 | SEPTEMBER
T-841-7714 | PS5-58-UR-6586D | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone H | 7 | To be completed |  | 14 | SEPTEMBER
T-140-7715 | PS5-41-OB-6694C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-03-11 | PS5-09-03 | PS5 - Milestone B | 1.1 | Closed | 6 | 42 | MARCH
T-362-7716 | PS5-38-UR-2849B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-04-07 | PS5-62-02 | PS5 - Milestone H | 7 | Closed | 40 | 24 | APRIL
T-543-7717 | PS5-01-IK-5868C | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone H | 7 | To be completed |  | 17 | DECEMBER
T-908-7718 | PS5-89-OB-4196C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | In progress |  | 20 | AUGUST
T-768-7719 | PS5-82-OB-1894D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone C | 2 | In progress |  | 26 | NOVEMBER
T-380-7720 | PS5-95-OB-1369B | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-04-24 | PS5-04-03 | PS5 - Milestone B | 1.1 | Closed | 4 | 36 | APRIL
T-441-7721 | PS5-19-OB-5301C | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | In progress |  | 11 | DECEMBER
T-449-7722 | PS5-26-OB-6122C | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-10-21 | PS5-10-04 | PS5 - Milestone G | 6 | Closed | 44 | 40 | OCTOBER
T-045-7723 | PS5-53-UR-7341B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | In progress |  | 11 | OCTOBER
T-898-7724 | PS5-36-OB-4438B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | To be completed |  | 18 | NOVEMBER
T-919-7725 | PS5-14-OB-4828A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone G | 6 | In progress |  | 38 | NOVEMBER
T-396-7726 | PS5-91-OB-7109B | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-06-25 | PS5-04-04 | PS5 - Milestone A | 1 | Closed | 32 | 47 | JUNE
T-110-7727 | PS5-43-IK-6233C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-03-18 | PS5-12-01 | PS5 - Milestone A | 1 | Closed | 5 | 42 | MARCH
T-374-7728 | PS5-82-IK-9137D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-12-13 | PS5-62-02 | PS5 - Milestone H | 7 | Closed | 5 | 14 | DECEMBER
T-840-7729 | PS5-51-OB-1986A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone F | 5 | In progress |  | 18 | DECEMBER
T-777-7730 | PS5-76-IK-5818B | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone H | 7 | In progress |  | 34 | OCTOBER
T-142-7731 | PS5-82-IK-8963A | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone G | 6 | On hold |  | 39 | SEPTEMBER
T-496-7732 | PS5-49-OB-6612B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-03-16 | PS5-11-03 | PS5 - Milestone H | 7 | Closed | 5 | 46 | MARCH
T-220-7733 | PS5-16-OB-8179A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-08-08 | PS5-05-01 | PS5 - Milestone F | 5 | Closed | 10 | 9 | AUGUST
T-330-7734 | PS5-57-OB-2214C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-02-03 | PS5-09-03 | PS5 - Milestone E | 4 | Closed | 25 | 20 | FEBRUARY
T-909-7735 | PS5-26-UR-1526A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone G | 6 | In progress |  | 21 | SEPTEMBER
T-737-7736 | PS5-42-OB-2414B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-08-27 | PS5-01-03 | PS5 - Milestone I | 8 | Closed | 27 | 22 | AUGUST
T-619-7737 | PS5-87-OB-3921C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | On hold |  | 38 | NOVEMBER
T-382-7738 | PS5-38-IK-8426B | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone A | 1 | To be completed |  | 6 | AUGUST
T-095-7739 | PS5-23-UR-2213C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-08-01 | PS5-01-08 | PS5 - Milestone D | 3 | Closed | 13 | 21 | AUGUST
T-270-7740 | PS5-15-OB-2677B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | To be completed |  | 18 | OCTOBER
T-432-7741 | PS5-17-UR-1547D | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-02-10 | PS5-13-01 | PS5 - Milestone I | 8 | Closed | 16 | 32 | FEBRUARY
T-279-7742 | PS5-28-IK-3164D | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone D | 3 | In progress |  | 11 | OCTOBER
T-596-7743 | PS5-70-IK-8142B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone E | 4 | To be completed |  | 25 | NOVEMBER
T-435-7744 | PS5-18-UR-3121D | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-05-11 | PS5-61-07 | PS5 - Milestone F | 5 | Closed | 43 | 33 | MAY
T-886-7745 | PS5-03-OB-5798A | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-02-07 | PS5-08-01 | PS5 - Milestone G | 6 | Closed | 39 | 27 | FEBRUARY
T-167-7746 | PS5-39-IK-2460B | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-03-01 | PS5-60-07 | PS5 - Milestone E | 4 | Closed | 24 | 22 | MARCH
T-178-7747 | PS5-68-OB-5763A | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone B | 1.1 | In progress |  | 7 | DECEMBER
T-420-7748 | PS5-62-IK-3845A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-05-05 | PS5-07-02 | PS5 - Milestone C | 2 | Closed | 9 | 4 | MAY
T-862-7749 | PS5-72-OB-8684A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone A | 1 | To be completed |  | 7 | OCTOBER
T-908-7750 | PS5-99-UR-9467A | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-12-11 | PS5-82-02 | PS5 - Milestone A | 1 | Closed | 41 | 13 | DECEMBER
T-765-7751 | PS5-73-OB-1510A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone H | 7 | To be completed |  | 38 | OCTOBER
T-218-7752 | PS5-06-OB-5322A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-07-04 | PS5-99-03 | PS5 - Milestone C | 2 | Closed | 16 | 12 | JULY
T-504-7753 | PS5-49-OB-5769D | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone G | 6 | To be completed |  | 22 | OCTOBER
T-890-7754 | PS5-35-UR-6607D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-04-03 | PS5-99-03 | PS5 - Milestone D | 3 | Closed | 44 | 18 | APRIL
T-757-7755 | PS5-93-IK-7312D | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone I | 8 | In progress |  | 7 | AUGUST
T-219-7756 | PS5-94-UR-6552D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | To be completed |  | 14 | OCTOBER
T-463-7757 | PS5-47-OB-9620A | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone E | 4 | On hold |  | 30 | SEPTEMBER
T-750-7758 | PS5-05-OB-7833D | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-09-08 | PS5-10-06 | PS5 - Milestone B | 1.1 | Closed | 8 | 36 | SEPTEMBER
T-320-7759 | PS5-39-OB-6000D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone F | 5 | On hold |  | 8 | DECEMBER
T-450-7760 | PS5-72-IK-5713D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-03-11 | PS5-63-04 | PS5 - Milestone B | 1.1 | Closed | 37 | 47 | MARCH
T-469-7761 | PS5-85-UR-7829D | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-05-22 | PS5-11-01 | PS5 - Milestone I | 8 | Closed | 26 | 14 | MAY
T-725-7762 | PS5-40-IK-5954D | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone B | 1.1 | In progress |  | 14 | OCTOBER
T-148-7763 | PS5-58-OB-2138A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | To be completed |  | 44 | DECEMBER
T-832-7764 | PS5-62-UR-2532B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | On hold |  | 40 | AUGUST
T-535-7765 | PS5-19-OB-2454D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone D | 3 | To be completed |  | 7 | SEPTEMBER
T-012-7766 | PS5-62-OB-4811D | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone E | 4 | To be completed |  | 17 | OCTOBER
T-470-7767 | PS5-08-UR-7202B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone F | 5 | To be completed |  | 5 | DECEMBER
T-335-7768 | PS5-64-UR-9917D | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | To be completed |  | 46 | AUGUST
T-744-7769 | PS5-25-OB-9260A | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone H | 7 | To be completed |  | 22 | NOVEMBER
T-463-7770 | PS5-26-IK-3090A | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone B | 1.1 | On hold |  | 24 | SEPTEMBER
T-176-7771 | PS5-79-OB-6228A | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone C | 2 | On hold |  | 4 | AUGUST
T-256-7772 | PS5-52-UR-6299D | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | To be completed |  | 26 | OCTOBER
T-209-7773 | PS5-83-OB-8767D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone A | 1 | To be completed |  | 26 | SEPTEMBER
T-278-7774 | PS5-19-IK-3835B | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | In progress |  | 32 | OCTOBER
T-948-7775 | PS5-34-OB-1812C | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-12-07 | PS5-09-04 | PS5 - Milestone C | 2 | Closed | 11 | 38 | DECEMBER
T-619-7776 | PS5-15-OB-9133C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone I | 8 | To be completed |  | 6 | NOVEMBER
T-115-7777 | PS5-31-UR-5089A | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-02-01 | PS5-82-02 | PS5 - Milestone H | 7 | Closed | 22 | 6 | FEBRUARY
T-198-7778 | PS5-17-OB-2179B | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-07-14 | PS5-01-01 | PS5 - Milestone H | 7 | Closed | 22 | 28 | JULY
T-699-7779 | PS5-58-IK-2492B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone E | 4 | On hold |  | 48 | SEPTEMBER
T-996-7780 | PS5-79-UR-3508C | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-10-13 | PS5-61-02 | PS5 - Milestone E | 4 | Closed | 44 | 32 | OCTOBER
T-825-7781 | PS5-50-OB-1724D | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone H | 7 | On hold |  | 45 | SEPTEMBER
T-816-7782 | PS5-42-UR-4907C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone G | 6 | To be completed |  | 9 | SEPTEMBER
T-833-7783 | PS5-57-OB-7728B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone D | 3 | On hold |  | 33 | NOVEMBER
T-845-7784 | PS5-97-IK-9543D | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone H | 7 | To be completed |  | 43 | AUGUST
T-624-7785 | PS5-06-UR-9164C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone D | 3 | To be completed |  | 33 | NOVEMBER
T-236-7786 | PS5-89-IK-8544A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone E | 4 | In progress |  | 39 | OCTOBER
T-377-7787 | PS5-72-UR-9337C | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone C | 2 | In progress |  | 16 | OCTOBER
T-160-7788 | PS5-52-OB-3513B | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | To be completed |  | 30 | DECEMBER
T-227-7789 | PS5-58-OB-4676D | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-06-24 | PS5-02-01 | PS5 - Milestone B | 1.1 | Closed | 30 | 46 | JUNE
T-336-7790 | PS5-10-OB-4217C | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-08 | PS5-60-04 | PS5 - Milestone A | 1 | Closed | 41 | 40 | JULY
T-487-7791 | PS5-26-OB-2514A | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | To be completed |  | 8 | OCTOBER
T-951-7792 | PS5-89-OB-2129B | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-10-23 | PS5-01-02 | PS5 - Milestone D | 3 | Closed | 40 | 27 | OCTOBER
T-519-7793 | PS5-48-UR-5211C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-04-22 | PS5-12-02 | PS5 - Milestone B | 1.1 | Closed | 22 | 47 | APRIL
T-955-7794 | PS5-57-OB-7430B | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone E | 4 | In progress |  | 13 | AUGUST
T-173-7795 | PS5-82-IK-3378A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-01-07 | PS5-10-02 | PS5 - Milestone B | 1.1 | Closed | 39 | 5 | JANUARY
T-297-7796 | PS5-09-UR-4196D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone A | 1 | To be completed |  | 27 | SEPTEMBER
T-552-7797 | PS5-65-OB-5514D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | In progress |  | 34 | DECEMBER
T-900-7798 | PS5-15-OB-3649C | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | In progress |  | 30 | NOVEMBER
T-659-7799 | PS5-41-OB-9983B | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | To be completed |  | 35 | NOVEMBER
T-398-7800 | PS5-22-OB-7273B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-05-21 | PS5-01-09 | PS5 - Milestone B | 1.1 | Closed | 21 | 24 | MAY
T-906-7801 | PS5-83-IK-4588D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone A | 1 | On hold |  | 32 | SEPTEMBER
T-205-7802 | PS5-75-OB-3756A | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone F | 5 | On hold |  | 26 | AUGUST
T-665-7803 | PS5-84-OB-1587D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-03-12 | PS5-05-01 | PS5 - Milestone H | 7 | Closed | 10 | 35 | MARCH
T-673-7804 | PS5-79-OB-3204D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone E | 4 | To be completed |  | 5 | SEPTEMBER
T-221-7805 | PS5-85-UR-9577A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-11-19 | PS5-11-02 | PS5 - Milestone C | 2 | Closed | 24 | 28 | NOVEMBER
T-356-7806 | PS5-17-OB-2074D | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-04-26 | PS5-13-01 | PS5 - Milestone A | 1 | Closed | 8 | 35 | APRIL
T-703-7807 | PS5-71-UR-4562C | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone G | 6 | In progress |  | 37 | SEPTEMBER
T-150-7808 | PS5-36-OB-7466B | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-03-10 | PS5-02-01 | PS5 - Milestone B | 1.1 | Closed | 37 | 20 | MARCH
T-081-7809 | PS5-91-IK-6043D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone I | 8 | To be completed |  | 19 | NOVEMBER
T-148-7810 | PS5-47-IK-3134D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone H | 7 | To be completed |  | 46 | NOVEMBER
T-458-7811 | PS5-47-IK-5981B | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-10-06 | PS5-10-01 | PS5 - Milestone E | 4 | Closed | 40 | 21 | OCTOBER
T-522-7812 | PS5-03-OB-7664A | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone A | 1 | In progress |  | 24 | SEPTEMBER
T-254-7813 | PS5-13-OB-5196B | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-06-15 | PS5-09-02 | PS5 - Milestone A | 1 | Closed | 20 | 27 | JUNE
T-462-7814 | PS5-44-UR-3005A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-06-05 | PS5-01-03 | PS5 - Milestone I | 8 | Closed | 12 | 38 | JUNE
T-069-7815 | PS5-78-OB-7604A | CQH02 - AHU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone A | 1 | In progress |  | 9 | AUGUST
T-707-7816 | PS5-92-UR-2539C | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone E | 4 | To be completed |  | 28 | AUGUST
T-556-7817 | PS5-95-OB-9003A | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | To be completed |  | 14 | NOVEMBER
T-373-7818 | PS5-43-OB-4985D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | To be completed |  | 47 | OCTOBER
T-542-7819 | PS5-21-OB-2646C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone F | 5 | On hold |  | 9 | NOVEMBER
T-637-7820 | PS5-91-OB-3127A | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone I | 8 | On hold |  | 15 | AUGUST
T-890-7821 | PS5-27-IK-3558B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone A | 1 | On hold |  | 29 | OCTOBER
T-626-7822 | PS5-74-UR-3354B | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone F | 5 | To be completed |  | 31 | NOVEMBER
T-947-7823 | PS5-87-IK-1082C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-01-10 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 43 | 18 | JANUARY
T-035-7824 | PS5-81-UR-3658D | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone G | 6 | To be completed |  | 44 | SEPTEMBER
T-954-7825 | PS5-22-OB-5978C | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone I | 8 | In progress |  | 45 | OCTOBER
T-679-7826 | PS5-74-UR-7389D | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone F | 5 | To be completed |  | 21 | DECEMBER
T-884-7827 | PS5-94-UR-2760C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone B | 1.1 | To be completed |  | 17 | AUGUST
T-575-7828 | PS5-64-IK-2802A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone A | 1 | In progress |  | 30 | OCTOBER
T-354-7829 | PS5-66-OB-9623A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone G | 6 | To be completed |  | 43 | SEPTEMBER
T-516-7830 | PS5-58-IK-6133A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | To be completed |  | 12 | AUGUST
T-456-7831 | PS5-68-UR-1745D | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-12-20 | PS5-01-05 | PS5 - Milestone I | 8 | Closed | 20 | 18 | DECEMBER
T-469-7832 | PS5-34-OB-5614B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone E | 4 | To be completed |  | 17 | DECEMBER
T-484-7833 | PS5-02-UR-3035D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone I | 8 | To be completed |  | 10 | SEPTEMBER
T-211-7834 | PS5-24-IK-6557A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone B | 1.1 | In progress |  | 19 | SEPTEMBER
T-448-7835 | PS5-74-OB-1710B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-09-03 | PS5-62-01 | PS5 - Milestone H | 7 | Closed | 47 | 12 | SEPTEMBER
T-605-7836 | PS5-48-OB-4985C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone F | 5 | To be completed |  | 19 | DECEMBER
T-164-7837 | PS5-80-OB-5646A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-06-23 | PS5-07-04 | PS5 - Milestone H | 7 | Closed | 7 | 30 | JUNE
T-889-7838 | PS5-73-UR-1387B | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone A | 1 | To be completed |  | 23 | NOVEMBER
T-717-7839 | PS5-92-IK-3906C | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone G | 6 | In progress |  | 30 | AUGUST
T-891-7840 | PS5-16-UR-3250A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | To be completed |  | 23 | OCTOBER
T-288-7841 | PS5-57-OB-5921D | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone G | 6 | To be completed |  | 23 | NOVEMBER
T-193-7842 | PS5-48-IK-4679C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | To be completed |  | 29 | SEPTEMBER
T-606-7843 | PS5-83-OB-9731B | CQM04 - Vessel | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone D | 3 | On hold |  | 29 | SEPTEMBER
T-934-7844 | PS5-58-UR-1866A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-11-25 | PS5-04-03 | PS5 - Milestone A | 1 | Closed | 7 | 22 | NOVEMBER
T-809-7845 | PS5-28-OB-7576B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-11-07 | PS5-07-04 | PS5 - Milestone E | 4 | Closed | 28 | 24 | NOVEMBER
T-100-7846 | PS5-18-UR-4847D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | To be completed |  | 8 | AUGUST
T-585-7847 | PS5-19-UR-5224B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-01-21 | PS5-06-01 | PS5 - Milestone A | 1 | Closed | 33 | 43 | JANUARY
T-978-7848 | PS5-24-UR-5529C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone E | 4 | To be completed |  | 48 | OCTOBER
T-885-7849 | PS5-68-IK-6888D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-10-24 | PS5-03-02 | PS5 - Milestone H | 7 | Closed | 14 | 42 | OCTOBER
T-695-7850 | PS5-69-OB-7980B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone B | 1.1 | In progress |  | 28 | OCTOBER
T-694-7851 | PS5-15-UR-4948A | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-03-12 | PS5-61-07 | PS5 - Milestone G | 6 | Closed | 6 | 22 | MARCH
T-915-7852 | PS5-73-OB-1886D | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-11-13 | PS5-04-04 | PS5 - Milestone E | 4 | Closed | 10 | 28 | NOVEMBER
T-305-7853 | PS5-49-IK-5721B | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone A | 1 | To be completed |  | 36 | NOVEMBER
T-657-7854 | PS5-63-OB-3688B | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone E | 4 | To be completed |  | 18 | SEPTEMBER
T-519-7855 | PS5-35-OB-9760B | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-12-26 | PS5-60-07 | PS5 - Milestone D | 3 | Closed | 24 | 33 | DECEMBER
T-799-7856 | PS5-76-UR-6312C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone H | 7 | To be completed |  | 45 | AUGUST
T-396-7857 | PS5-13-OB-5624A | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-04-18 | PS5-82-01 | PS5 - Milestone A | 1 | Closed | 14 | 34 | APRIL
T-159-7858 | PS5-73-OB-2981D | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-01-20 | PS5-01-05 | PS5 - Milestone D | 3 | Closed | 43 | 17 | JANUARY
T-895-7859 | PS5-43-IK-9737B | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-03-20 | PS5-09-04 | PS5 - Milestone C | 2 | Closed | 46 | 21 | MARCH
T-934-7860 | PS5-30-UR-6971A | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone E | 4 | In progress |  | 33 | NOVEMBER
T-234-7861 | PS5-70-UR-9806A | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone I | 8 | To be completed |  | 13 | SEPTEMBER
T-162-7862 | PS5-71-IK-2231D | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone C | 2 | To be completed |  | 10 | OCTOBER
T-933-7863 | PS5-87-IK-9827C | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | To be completed |  | 24 | NOVEMBER
T-076-7864 | PS5-92-IK-9040C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-04-01 | PS5-03-02 | PS5 - Milestone C | 2 | Closed | 20 | 14 | APRIL
T-414-7865 | PS5-59-IK-4148C | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-04-07 | PS5-11-01 | PS5 - Milestone A | 1 | Closed | 41 | 12 | APRIL
T-109-7866 | PS5-59-IK-8391A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone F | 5 | To be completed |  | 14 | AUGUST
T-897-7867 | PS5-22-UR-9109B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-09-25 | PS5-61-02 | PS5 - Milestone D | 3 | Closed | 36 | 29 | SEPTEMBER
T-143-7868 | PS5-65-OB-6436A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone E | 4 | In progress |  | 36 | OCTOBER
T-405-7869 | PS5-77-UR-9831C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-10-09 | PS5-05-02 | PS5 - Milestone D | 3 | Closed | 23 | 18 | OCTOBER
T-873-7870 | PS5-56-OB-9688A | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone F | 5 | On hold |  | 37 | NOVEMBER
T-899-7871 | PS5-61-OB-9230B | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-07-04 | PS5-02-02 | PS5 - Milestone E | 4 | Closed | 9 | 34 | JULY
T-962-7872 | PS5-72-OB-5115A | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone C | 2 | In progress |  | 38 | SEPTEMBER
T-382-7873 | PS5-49-IK-7720D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-01-27 | PS5-06-01 | PS5 - Milestone D | 3 | Closed | 36 | 48 | JANUARY
T-303-7874 | PS5-76-OB-5379B | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | On hold |  | 5 | SEPTEMBER
T-376-7875 | PS5-55-OB-9924D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone C | 2 | To be completed |  | 21 | OCTOBER
T-323-7876 | PS5-52-UR-6958C | CQM01 - Pump Installation | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-04-05 | PS5-02-03 | PS5 - Milestone I | 8 | Closed | 38 | 19 | APRIL
T-951-7877 | PS5-69-OB-3729C | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-12-27 | PS5-09-02 | PS5 - Milestone H | 7 | Closed | 4 | 48 | DECEMBER
T-153-7878 | PS5-68-UR-3906B | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-06-19 | PS5-13-01 | PS5 - Milestone I | 8 | Closed | 5 | 43 | JUNE
T-150-7879 | PS5-70-UR-8524B | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone F | 5 | To be completed |  | 26 | AUGUST
T-234-7880 | PS5-94-IK-2073B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone D | 3 | On hold |  | 28 | SEPTEMBER
T-981-7881 | PS5-71-OB-7025D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone G | 6 | To be completed |  | 24 | DECEMBER
T-117-7882 | PS5-72-IK-2579D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone A | 1 | To be completed |  | 13 | AUGUST
T-443-7883 | PS5-30-UR-4724A | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone B | 1.1 | To be completed |  | 34 | AUGUST
T-052-7884 | PS5-90-OB-8210B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone I | 8 | To be completed |  | 28 | OCTOBER
T-807-7885 | PS5-28-OB-4009B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone C | 2 | To be completed |  | 14 | AUGUST
T-763-7886 | PS5-12-OB-3995C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | To be completed |  | 40 | AUGUST
T-439-7887 | PS5-07-OB-5476D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-08-15 | PS5-02-01 | PS5 - Milestone D | 3 | Closed | 41 | 28 | AUGUST
T-160-7888 | PS5-92-IK-6013D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | To be completed |  | 13 | SEPTEMBER
T-937-7889 | PS5-57-OB-2946D | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone B | 1.1 | To be completed |  | 40 | SEPTEMBER
T-044-7890 | PS5-78-OB-8802D | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | To be completed |  | 7 | SEPTEMBER
T-506-7891 | PS5-22-OB-4093A | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone A | 1 | On hold |  | 9 | AUGUST
T-985-7892 | PS5-41-OB-2178C | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-04-05 | PS5-07-03 | PS5 - Milestone C | 2 | Closed | 23 | 19 | APRIL
T-909-7893 | PS5-85-OB-1463A | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | In progress |  | 11 | DECEMBER
T-650-7894 | PS5-24-OB-2683D | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone D | 3 | On hold |  | 27 | DECEMBER
T-978-7895 | PS5-87-OB-8735B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone F | 5 | To be completed |  | 8 | OCTOBER
T-130-7896 | PS5-40-UR-3635A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone A | 1 | To be completed |  | 34 | AUGUST
T-898-7897 | PS5-64-UR-5624A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-02-20 | PS5-09-01 | PS5 - Milestone A | 1 | Closed | 43 | 20 | FEBRUARY
T-193-7898 | PS5-98-OB-6571A | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone C | 2 | To be completed |  | 26 | DECEMBER
T-585-7899 | PS5-36-OB-4032C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | In progress |  | 21 | NOVEMBER
T-942-7900 | PS5-98-OB-8473B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-06-25 | PS5-63-04 | PS5 - Milestone A | 1 | Closed | 48 | 4 | JUNE
T-186-7901 | PS5-34-IK-7850A | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone G | 6 | On hold |  | 14 | AUGUST
T-088-7902 | PS5-93-UR-2091A | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-11 | PS5-60-01 | PS5 - Milestone G | 6 | Closed | 21 | 4 | JUNE
T-341-7903 | PS5-46-IK-4253A | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-07-04 | PS5-01-08 | PS5 - Milestone F | 5 | Closed | 44 | 43 | JULY
T-571-7904 | PS5-63-OB-5954D | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-04-06 | PS5-99-01 | PS5 - Milestone E | 4 | Closed | 24 | 6 | APRIL
T-231-7905 | PS5-36-IK-1032B | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-11 | PS5-60-04 | PS5 - Milestone D | 3 | Closed | 20 | 37 | FEBRUARY
T-332-7906 | PS5-64-OB-4301C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone D | 3 | In progress |  | 24 | AUGUST
T-967-7907 | PS5-46-OB-6241D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-04-04 | PS5-03-23 | PS5 - Milestone H | 7 | Closed | 7 | 29 | APRIL
T-728-7908 | PS5-06-OB-1100D | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | On hold |  | 26 | SEPTEMBER
T-064-7909 | PS5-66-IK-3175B | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone F | 5 | In progress |  | 20 | NOVEMBER
T-839-7910 | PS5-01-OB-9415A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-09-24 | PS5-06-03 | PS5 - Milestone E | 4 | Closed | 35 | 6 | SEPTEMBER
T-901-7911 | PS5-18-UR-3263D | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone D | 3 | On hold |  | 19 | AUGUST
T-407-7912 | PS5-21-OB-4910B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | To be completed |  | 5 | AUGUST
T-753-7913 | PS5-25-OB-5127D | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-04-19 | PS5-04-04 | PS5 - Milestone C | 2 | Closed | 25 | 8 | APRIL
T-389-7914 | PS5-70-OB-7945C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-09-19 | PS5-09-02 | PS5 - Milestone B | 1.1 | Closed | 5 | 31 | SEPTEMBER
T-400-7915 | PS5-08-OB-4282B | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-02-06 | PS5-99-03 | PS5 - Milestone D | 3 | Closed | 34 | 24 | FEBRUARY
T-918-7916 | PS5-14-OB-8802D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-01-08 | PS5-01-08 | PS5 - Milestone A | 1 | Closed | 10 | 20 | JANUARY
T-014-7917 | PS5-28-IK-3731D | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone G | 6 | To be completed |  | 37 | NOVEMBER
T-150-7918 | PS5-21-IK-8618A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-08-20 | PS5-11-02 | PS5 - Milestone E | 4 | Closed | 13 | 30 | AUGUST
T-020-7919 | PS5-54-OB-9008B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-12 | PS5-60-04 | PS5 - Milestone H | 7 | Closed | 8 | 16 | JUNE
T-305-7920 | PS5-73-OB-2249A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | On hold |  | 29 | DECEMBER
T-996-7921 | PS5-20-OB-5665B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone C | 2 | In progress |  | 4 | DECEMBER
T-470-7922 | PS5-11-UR-1784C | CQM04 - Vessel | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | To be completed |  | 18 | AUGUST
T-337-7923 | PS5-76-IK-4567A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone F | 5 | On hold |  | 34 | AUGUST
T-088-7924 | PS5-77-OB-8276C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-12-04 | PS5-10-01 | PS5 - Milestone F | 5 | Closed | 43 | 24 | DECEMBER
T-708-7925 | PS5-94-OB-2893D | CQP04 - Hydrotest | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | To be completed |  | 42 | AUGUST
T-440-7926 | PS5-84-OB-3142B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-03-17 | PS5-11-01 | PS5 - Milestone F | 5 | Closed | 31 | 9 | MARCH
T-119-7927 | PS5-13-UR-7454D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone A | 1 | To be completed |  | 17 | NOVEMBER
T-373-7928 | PS5-75-IK-2615A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-02-15 | PS5-62-01 | PS5 - Milestone A | 1 | Closed | 24 | 41 | FEBRUARY
T-796-7929 | PS5-94-IK-8890C | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | To be completed |  | 17 | NOVEMBER
T-169-7930 | PS5-11-IK-6132B | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-11-25 | PS5-10-05 | PS5 - Milestone A | 1 | Closed | 37 | 28 | NOVEMBER
T-360-7931 | PS5-38-OB-5245C | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-01-22 | PS5-10-02 | PS5 - Milestone D | 3 | Closed | 16 | 37 | JANUARY
T-556-7932 | PS5-15-OB-5032D | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-06-24 | PS5-99-02 | PS5 - Milestone D | 3 | Closed | 40 | 13 | JUNE
T-587-7933 | PS5-87-OB-8332D | CQP01 - Pipe Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone E | 4 | To be completed |  | 5 | NOVEMBER
T-457-7934 | PS5-33-UR-9859B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone F | 5 | To be completed |  | 44 | AUGUST
T-910-7935 | PS5-68-OB-8693A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-07-17 | PS5-09-04 | PS5 - Milestone E | 4 | Closed | 6 | 18 | JULY
T-945-7936 | PS5-46-OB-1490A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone G | 6 | In progress |  | 28 | SEPTEMBER
T-731-7937 | PS5-31-OB-9547A | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | On hold |  | 31 | NOVEMBER
T-589-7938 | PS5-83-OB-9300D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone A | 1 | In progress |  | 29 | DECEMBER
T-542-7939 | PS5-13-OB-1867C | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone C | 2 | To be completed |  | 33 | SEPTEMBER
T-626-7940 | PS5-61-IK-3226B | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-05-26 | PS5-03-02 | PS5 - Milestone C | 2 | Closed | 11 | 42 | MAY
T-930-7941 | PS5-16-OB-3952D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | To be completed |  | 5 | OCTOBER
T-501-7942 | PS5-42-IK-9253C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-06-13 | PS5-09-03 | PS5 - Milestone F | 5 | Closed | 43 | 22 | JUNE
T-913-7943 | PS5-59-IK-5220B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-10-07 | PS5-01-01 | PS5 - Milestone F | 5 | Closed | 40 | 12 | OCTOBER
T-164-7944 | PS5-68-OB-5779A | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone A | 1 | In progress |  | 16 | OCTOBER
T-820-7945 | PS5-81-UR-8274B | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone A | 1 | To be completed |  | 29 | NOVEMBER
T-402-7946 | PS5-66-OB-3380D | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone D | 3 | To be completed |  | 16 | SEPTEMBER
T-084-7947 | PS5-02-OB-1263B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-07-26 | PS5-07-03 | PS5 - Milestone I | 8 | Closed | 36 | 22 | JULY
T-584-7948 | PS5-01-OB-6901B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone B | 1.1 | In progress |  | 5 | OCTOBER
T-026-7949 | PS5-01-UR-9613C | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-02 | PS5-60-04 | PS5 - Milestone E | 4 | Closed | 26 | 6 | JULY
T-081-7950 | PS5-84-OB-1364C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone C | 2 | On hold |  | 23 | OCTOBER
T-486-7951 | PS5-45-IK-6448B | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-06-02 | PS5-09-03 | PS5 - Milestone B | 1.1 | Closed | 7 | 48 | JUNE
T-579-7952 | PS5-45-OB-5364B | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-11-13 | PS5-10-01 | PS5 - Milestone C | 2 | Closed | 18 | 4 | NOVEMBER
T-060-7953 | PS5-71-OB-9344D | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | To be completed |  | 28 | DECEMBER
T-038-7954 | PS5-33-UR-9056B | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-12-23 | PS5-12-01 | PS5 - Milestone G | 6 | Closed | 9 | 44 | DECEMBER
T-895-7955 | PS5-88-OB-6026D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-08-27 | PS5-60-01 | PS5 - Milestone A | 1 | Closed | 7 | 30 | AUGUST
T-196-7956 | PS5-21-UR-9583B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | To be completed |  | 16 | OCTOBER
T-078-7957 | PS5-96-OB-5257C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone D | 3 | On hold |  | 15 | OCTOBER
T-426-7958 | PS5-24-OB-7344D | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-12-16 | PS5-06-03 | PS5 - Milestone G | 6 | Closed | 33 | 15 | DECEMBER
T-298-7959 | PS5-84-IK-3424A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-01-07 | PS5-10-01 | PS5 - Milestone E | 4 | Closed | 20 | 37 | JANUARY
T-706-7960 | PS5-86-UR-2688D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | To be completed |  | 30 | DECEMBER
T-746-7961 | PS5-36-UR-1180A | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-12-05 | PS5-09-03 | PS5 - Milestone H | 7 | Closed | 5 | 48 | DECEMBER
T-512-7962 | PS5-81-OB-7277C | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | In progress |  | 8 | SEPTEMBER
T-215-7963 | PS5-82-OB-1267B | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone F | 5 | To be completed |  | 6 | AUGUST
T-621-7964 | PS5-45-OB-3130D | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone G | 6 | In progress |  | 38 | AUGUST
T-910-7965 | PS5-85-OB-8083B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone D | 3 | To be completed |  | 11 | SEPTEMBER
T-088-7966 | PS5-79-UR-9140C | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone G | 6 | To be completed |  | 46 | SEPTEMBER
T-953-7967 | PS5-15-UR-5830C | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | On hold |  | 32 | SEPTEMBER
T-172-7968 | PS5-70-UR-4423B | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone C | 2 | To be completed |  | 41 | DECEMBER
T-734-7969 | PS5-19-UR-3709A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | To be completed |  | 19 | DECEMBER
T-683-7970 | PS5-32-UR-3534A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone F | 5 | To be completed |  | 19 | AUGUST
T-628-7971 | PS5-11-IK-7406C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-07-24 | PS5-05-01 | PS5 - Milestone E | 4 | Closed | 14 | 27 | JULY
T-422-7972 | PS5-32-OB-9019A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-07-26 | PS5-01-09 | PS5 - Milestone H | 7 | Closed | 15 | 15 | JULY
T-003-7973 | PS5-19-OB-3626C | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-01-23 | PS5-01-01 | PS5 - Milestone F | 5 | Closed | 26 | 11 | JANUARY
T-599-7974 | PS5-18-IK-9411A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-10-15 | PS5-07-02 | PS5 - Milestone E | 4 | Closed | 5 | 37 | OCTOBER
T-161-7975 | PS5-93-OB-4598B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone D | 3 | In progress |  | 48 | AUGUST
T-846-7976 | PS5-96-OB-3399D | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-09-09 | PS5-10-01 | PS5 - Milestone G | 6 | Closed | 26 | 28 | SEPTEMBER
T-645-7977 | PS5-15-OB-6304C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone E | 4 | On hold |  | 25 | SEPTEMBER
T-080-7978 | PS5-57-IK-7470D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | To be completed |  | 17 | DECEMBER
T-324-7979 | PS5-52-OB-7698A | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone H | 7 | In progress |  | 22 | NOVEMBER
T-168-7980 | PS5-68-IK-7702D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-11-24 | PS5-09-03 | PS5 - Milestone C | 2 | Closed | 21 | 42 | NOVEMBER
T-218-7981 | PS5-75-OB-7661B | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-08-20 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 36 | 20 | AUGUST
T-560-7982 | PS5-59-OB-9070D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | To be completed |  | 38 | SEPTEMBER
T-248-7983 | PS5-70-OB-5403D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-06-11 | PS5-03-03 | PS5 - Milestone G | 6 | Closed | 15 | 37 | JUNE
T-334-7984 | PS5-49-OB-5437D | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone G | 6 | To be completed |  | 43 | NOVEMBER
T-582-7985 | PS5-87-OB-2598C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | To be completed |  | 10 | AUGUST
T-801-7986 | PS5-56-UR-9664D | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone F | 5 | To be completed |  | 37 | OCTOBER
T-336-7987 | PS5-20-OB-1928A | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-02-17 | PS5-01-08 | PS5 - Milestone H | 7 | Closed | 25 | 21 | FEBRUARY
T-731-7988 | PS5-99-OB-4067C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-03-21 | PS5-03-02 | PS5 - Milestone C | 2 | Closed | 15 | 9 | MARCH
T-208-7989 | PS5-07-UR-9614A | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone A | 1 | To be completed |  | 42 | DECEMBER
T-146-7990 | PS5-86-OB-9901C | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-03-13 | PS5-62-01 | PS5 - Milestone H | 7 | Closed | 33 | 19 | MARCH
T-231-7991 | PS5-31-OB-5732C | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone D | 3 | In progress |  | 4 | NOVEMBER
T-076-7992 | PS5-41-IK-3862C | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone E | 4 | To be completed |  | 40 | SEPTEMBER
T-889-7993 | PS5-32-UR-6071B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone G | 6 | In progress |  | 24 | NOVEMBER
T-332-7994 | PS5-05-OB-6142B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | In progress |  | 31 | SEPTEMBER
T-949-7995 | PS5-84-OB-9546A | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-06-11 | PS5-06-03 | PS5 - Milestone D | 3 | Closed | 42 | 41 | JUNE
T-567-7996 | PS5-54-OB-5255A | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-10-13 | PS5-05-03 | PS5 - Milestone E | 4 | Closed | 27 | 35 | OCTOBER
T-667-7997 | PS5-97-IK-3637C | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-11-09 | PS5-01-02 | PS5 - Milestone E | 4 | Closed | 30 | 33 | NOVEMBER
T-803-7998 | PS5-97-OB-3695C | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone A | 1 | To be completed |  | 11 | OCTOBER
T-784-7999 | PS5-08-IK-8504A | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-09-12 | PS5-61-01 | PS5 - Milestone D | 3 | Closed | 18 | 14 | SEPTEMBER
T-636-8000 | PS5-37-UR-6042C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-21 | PS5-60-07 | PS5 - Milestone I | 8 | Closed | 5 | 36 | JULY
T-522-8001 | PS5-44-OB-4366D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | In progress |  | 41 | AUGUST
T-369-8002 | PS5-27-OB-5323D | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone E | 4 | To be completed |  | 22 | AUGUST
T-822-8003 | PS5-79-UR-5210C | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-01-06 | PS5-06-01 | PS5 - Milestone A | 1 | Closed | 47 | 29 | JANUARY
T-120-8004 | PS5-41-IK-2758B | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-05-28 | PS5-05-03 | PS5 - Milestone D | 3 | Closed | 14 | 26 | MAY
T-860-8005 | PS5-19-OB-7488A | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-01-12 | PS5-07-01 | PS5 - Milestone F | 5 | Closed | 34 | 31 | JANUARY
T-068-8006 | PS5-71-IK-8017D | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone C | 2 | On hold |  | 40 | OCTOBER
T-427-8007 | PS5-77-OB-1505C | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-05-25 | PS5-05-03 | PS5 - Milestone E | 4 | Closed | 25 | 42 | MAY
T-387-8008 | PS5-96-OB-9676B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone H | 7 | In progress |  | 40 | OCTOBER
T-166-8009 | PS5-29-OB-9851A | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone D | 3 | To be completed |  | 16 | AUGUST
T-706-8010 | PS5-43-UR-5452B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone F | 5 | To be completed |  | 37 | SEPTEMBER
T-270-8011 | PS5-58-OB-7569A | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone D | 3 | In progress |  | 14 | OCTOBER
T-152-8012 | PS5-26-UR-9434B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-01-02 | PS5-82-02 | PS5 - Milestone F | 5 | Closed | 11 | 22 | JANUARY
T-481-8013 | PS5-31-OB-9083B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone C | 2 | In progress |  | 34 | SEPTEMBER
T-145-8014 | PS5-86-IK-7709C | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-01-08 | PS5-60-01 | PS5 - Milestone B | 1.1 | Closed | 5 | 17 | JANUARY
T-895-8015 | PS5-39-OB-5565D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | To be completed |  | 7 | AUGUST
T-274-8016 | PS5-41-IK-7349B | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | In progress |  | 28 | DECEMBER
T-892-8017 | PS5-52-OB-2614D | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone I | 8 | In progress |  | 39 | NOVEMBER
T-762-8018 | PS5-39-OB-3339C | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone I | 8 | In progress |  | 45 | AUGUST
T-994-8019 | PS5-79-OB-4915C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone F | 5 | On hold |  | 8 | SEPTEMBER
T-891-8020 | PS5-24-OB-9855D | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone E | 4 | To be completed |  | 35 | AUGUST
T-999-8021 | PS5-53-IK-8089C | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-01-26 | PS5-04-04 | PS5 - Milestone G | 6 | Closed | 23 | 19 | JANUARY
T-759-8022 | PS5-12-OB-6537C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone E | 4 | To be completed |  | 27 | DECEMBER
T-279-8023 | PS5-77-UR-2936A | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone B | 1.1 | To be completed |  | 13 | AUGUST
T-064-8024 | PS5-32-OB-1274B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-05-14 | PS5-12-02 | PS5 - Milestone E | 4 | Closed | 12 | 35 | MAY
T-777-8025 | PS5-05-UR-6352C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-10-06 | PS5-02-03 | PS5 - Milestone F | 5 | Closed | 16 | 25 | OCTOBER
T-102-8026 | PS5-29-OB-1083B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone C | 2 | On hold |  | 19 | AUGUST
T-164-8027 | PS5-90-OB-8055C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone G | 6 | On hold |  | 31 | OCTOBER
T-937-8028 | PS5-98-UR-7466C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone F | 5 | In progress |  | 38 | SEPTEMBER
T-427-8029 | PS5-51-UR-8512D | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | On hold |  | 25 | NOVEMBER
T-631-8030 | PS5-92-IK-4177B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-05-27 | PS5-02-02 | PS5 - Milestone E | 4 | Closed | 34 | 13 | MAY
T-888-8031 | PS5-90-OB-4148C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-04-18 | PS5-12-02 | PS5 - Milestone B | 1.1 | Closed | 46 | 23 | APRIL
T-755-8032 | PS5-97-OB-1258A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-04-07 | PS5-82-01 | PS5 - Milestone F | 5 | Closed | 45 | 39 | APRIL
T-524-8033 | PS5-53-OB-9372B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-10-03 | PS5-02-03 | PS5 - Milestone A | 1 | Closed | 9 | 40 | OCTOBER
T-383-8034 | PS5-48-IK-7779D | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone I | 8 | To be completed |  | 19 | SEPTEMBER
T-873-8035 | PS5-01-IK-9266D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-12-15 | PS5-04-04 | PS5 - Milestone H | 7 | Closed | 21 | 23 | DECEMBER
T-044-8036 | PS5-38-UR-1284A | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | To be completed |  | 8 | SEPTEMBER
T-742-8037 | PS5-50-OB-4888C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-03-01 | PS5-06-01 | PS5 - Milestone E | 4 | Closed | 18 | 12 | MARCH
T-200-8038 | PS5-64-OB-4786A | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone H | 7 | To be completed |  | 44 | NOVEMBER
T-303-8039 | PS5-31-UR-1531B | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone G | 6 | In progress |  | 26 | NOVEMBER
T-173-8040 | PS5-86-OB-2965C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-03-04 | PS5-82-02 | PS5 - Milestone A | 1 | Closed | 8 | 24 | MARCH
T-879-8041 | PS5-85-IK-1652A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-09-25 | PS5-63-04 | PS5 - Milestone D | 3 | Closed | 18 | 44 | SEPTEMBER
T-561-8042 | PS5-47-IK-7619A | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone B | 1.1 | To be completed |  | 28 | AUGUST
T-035-8043 | PS5-34-UR-4659A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone G | 6 | To be completed |  | 17 | AUGUST
T-743-8044 | PS5-76-UR-8040D | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-01-01 | PS5-06-03 | PS5 - Milestone B | 1.1 | Closed | 4 | 16 | JANUARY
T-207-8045 | PS5-49-OB-1335D | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | To be completed |  | 30 | NOVEMBER
T-920-8046 | PS5-26-OB-9748B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-09-21 | PS5-07-01 | PS5 - Milestone I | 8 | Closed | 30 | 16 | SEPTEMBER
T-672-8047 | PS5-26-OB-9207A | CQP04 - Hydrotest | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone H | 7 | To be completed |  | 10 | OCTOBER
T-259-8048 | PS5-92-OB-7095B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-04-04 | PS5-02-01 | PS5 - Milestone H | 7 | Closed | 17 | 14 | APRIL
T-650-8049 | PS5-90-OB-7596C | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone B | 1.1 | To be completed |  | 40 | DECEMBER
T-439-8050 | PS5-90-IK-3939C | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-08-19 | PS5-63-04 | PS5 - Milestone A | 1 | Closed | 39 | 34 | AUGUST
T-946-8051 | PS5-75-OB-5512B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone E | 4 | In progress |  | 6 | OCTOBER
T-478-8052 | PS5-56-OB-1594C | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-04-11 | PS5-09-02 | PS5 - Milestone C | 2 | Closed | 39 | 29 | APRIL
T-137-8053 | PS5-73-UR-3237C | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | In progress |  | 34 | OCTOBER
T-122-8054 | PS5-81-IK-2977A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone E | 4 | In progress |  | 40 | DECEMBER
T-143-8055 | PS5-64-IK-1566B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone G | 6 | In progress |  | 36 | AUGUST
T-960-8056 | PS5-08-IK-1424D | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-04-11 | PS5-10-06 | PS5 - Milestone C | 2 | Closed | 41 | 32 | APRIL
T-603-8057 | PS5-80-UR-3605A | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone C | 2 | To be completed |  | 34 | OCTOBER
T-037-8058 | PS5-77-OB-6918C | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-11-06 | PS5-63-04 | PS5 - Milestone B | 1.1 | Closed | 35 | 31 | NOVEMBER
T-169-8059 | PS5-16-OB-6802A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone I | 8 | In progress |  | 46 | SEPTEMBER
T-203-8060 | PS5-76-OB-4082C | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | In progress |  | 34 | NOVEMBER
T-857-8061 | PS5-74-IK-5856A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-12-12 | PS5-04-02 | PS5 - Milestone B | 1.1 | Closed | 24 | 11 | DECEMBER
T-929-8062 | PS5-40-OB-4934A | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-02-26 | PS5-01-08 | PS5 - Milestone C | 2 | Closed | 46 | 12 | FEBRUARY
T-232-8063 | PS5-03-UR-2904A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | To be completed |  | 25 | AUGUST
T-921-8064 | PS5-25-IK-2060D | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone E | 4 | To be completed |  | 17 | DECEMBER
T-643-8065 | PS5-04-UR-5278A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-05-28 | PS5-09-03 | PS5 - Milestone F | 5 | Closed | 32 | 6 | MAY
T-686-8066 | PS5-80-UR-1632D | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone I | 8 | To be completed |  | 34 | SEPTEMBER
T-661-8067 | PS5-97-IK-4304D | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone H | 7 | To be completed |  | 44 | OCTOBER
T-329-8068 | PS5-86-UR-3291C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone B | 1.1 | In progress |  | 36 | OCTOBER
T-665-8069 | PS5-99-UR-7792D | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-09-03 | PS5-02-03 | PS5 - Milestone D | 3 | Closed | 6 | 29 | SEPTEMBER
T-912-8070 | PS5-12-OB-7794C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-07-03 | PS5-12-01 | PS5 - Milestone A | 1 | Closed | 26 | 21 | JULY
T-791-8071 | PS5-78-UR-2758A | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone H | 7 | To be completed |  | 5 | OCTOBER
T-246-8072 | PS5-05-OB-8737A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone A | 1 | To be completed |  | 39 | AUGUST
T-744-8073 | PS5-55-OB-4931C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone A | 1 | On hold |  | 35 | SEPTEMBER
T-006-8074 | PS5-71-OB-8514D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-08-07 | PS5-60-01 | PS5 - Milestone A | 1 | Closed | 38 | 44 | AUGUST
T-690-8075 | PS5-67-UR-8120A | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-06-06 | PS5-07-02 | PS5 - Milestone E | 4 | Closed | 16 | 22 | JUNE
T-170-8076 | PS5-55-OB-5068C | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-03-20 | PS5-61-02 | PS5 - Milestone B | 1.1 | Closed | 30 | 9 | MARCH
T-313-8077 | PS5-23-UR-6715D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-03-09 | PS5-04-01 | PS5 - Milestone C | 2 | Closed | 40 | 48 | MARCH
T-862-8078 | PS5-56-OB-8586A | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone B | 1.1 | To be completed |  | 14 | AUGUST
T-563-8079 | PS5-14-OB-1465C | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-10-28 | PS5-01-05 | PS5 - Milestone H | 7 | Closed | 10 | 48 | OCTOBER
T-257-8080 | PS5-83-UR-5678D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone E | 4 | On hold |  | 26 | OCTOBER
T-514-8081 | PS5-14-OB-3851D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-07-18 | PS5-11-02 | PS5 - Milestone I | 8 | Closed | 46 | 9 | JULY
T-104-8082 | PS5-02-OB-2165C | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | To be completed |  | 37 | AUGUST
T-701-8083 | PS5-52-IK-1912C | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | In progress |  | 15 | OCTOBER
T-458-8084 | PS5-04-UR-7993A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone E | 4 | In progress |  | 19 | DECEMBER
T-989-8085 | PS5-20-OB-6406A | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-10-25 | PS5-05-02 | PS5 - Milestone B | 1.1 | Closed | 44 | 46 | OCTOBER
T-005-8086 | PS5-35-OB-4388C | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-03-15 | PS5-02-01 | PS5 - Milestone E | 4 | Closed | 38 | 17 | MARCH
T-310-8087 | PS5-28-OB-3355B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone A | 1 | In progress |  | 30 | SEPTEMBER
T-126-8088 | PS5-79-UR-4179D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone D | 3 | In progress |  | 19 | AUGUST
T-248-8089 | PS5-48-OB-5138D | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone B | 1.1 | In progress |  | 23 | NOVEMBER
T-067-8090 | PS5-81-OB-5658B | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-01-09 | PS5-02-03 | PS5 - Milestone C | 2 | Closed | 27 | 36 | JANUARY
T-403-8091 | PS5-21-UR-4672A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-02-05 | PS5-11-01 | PS5 - Milestone B | 1.1 | Closed | 10 | 13 | FEBRUARY
T-030-8092 | PS5-44-OB-1992D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-03-18 | PS5-08-02 | PS5 - Milestone E | 4 | Closed | 19 | 44 | MARCH
T-414-8093 | PS5-65-UR-3455D | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone G | 6 | To be completed |  | 41 | NOVEMBER
T-507-8094 | PS5-44-OB-9812A | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-12-26 | PS5-01-05 | PS5 - Milestone B | 1.1 | Closed | 44 | 41 | DECEMBER
T-857-8095 | PS5-23-IK-7356D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-03-06 | PS5-02-03 | PS5 - Milestone D | 3 | Closed | 21 | 17 | MARCH
T-412-8096 | PS5-51-UR-9541D | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone A | 1 | To be completed |  | 47 | AUGUST
T-353-8097 | PS5-39-IK-6336B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone A | 1 | In progress |  | 32 | DECEMBER
T-128-8098 | PS5-39-IK-9614C | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone H | 7 | To be completed |  | 7 | AUGUST
T-420-8099 | PS5-82-UR-2059C | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | On hold |  | 41 | DECEMBER
T-723-8100 | PS5-02-OB-7692B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-11-08 | PS5-06-01 | PS5 - Milestone E | 4 | Closed | 27 | 26 | NOVEMBER
T-825-8101 | PS5-02-OB-4871A | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-09-04 | PS5-10-06 | PS5 - Milestone E | 4 | Closed | 28 | 26 | SEPTEMBER
T-349-8102 | PS5-19-OB-2285B | CQM03 - Heat Exchanger | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone A | 1 | On hold |  | 13 | SEPTEMBER
T-985-8103 | PS5-38-OB-5620A | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone F | 5 | To be completed |  | 18 | DECEMBER
T-276-8104 | PS5-92-OB-8902D | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone D | 3 | In progress |  | 15 | NOVEMBER
T-951-8105 | PS5-76-UR-4253B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone I | 8 | On hold |  | 43 | SEPTEMBER
T-729-8106 | PS5-40-IK-6396C | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | To be completed |  | 8 | DECEMBER
T-356-8107 | PS5-71-OB-9028C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-06-23 | PS5-61-07 | PS5 - Milestone B | 1.1 | Closed | 41 | 42 | JUNE
T-894-8108 | PS5-01-IK-6156B | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-03-20 | PS5-05-02 | PS5 - Milestone A | 1 | Closed | 9 | 48 | MARCH
T-835-8109 | PS5-92-IK-9886A | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone C | 2 | To be completed |  | 26 | DECEMBER
T-856-8110 | PS5-57-OB-5757B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone D | 3 | To be completed |  | 44 | AUGUST
T-388-8111 | PS5-24-UR-9980C | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-11-19 | PS5-04-02 | PS5 - Milestone I | 8 | Closed | 26 | 40 | NOVEMBER
T-363-8112 | PS5-29-UR-2604A | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-25 | PS5-60-07 | PS5 - Milestone C | 2 | Closed | 31 | 48 | APRIL
T-493-8113 | PS5-22-OB-3059A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone G | 6 | In progress |  | 45 | SEPTEMBER
T-242-8114 | PS5-78-IK-6981D | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone I | 8 | To be completed |  | 35 | OCTOBER
T-906-8115 | PS5-79-OB-7548A | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone D | 3 | To be completed |  | 24 | SEPTEMBER
T-894-8116 | PS5-79-UR-9970B | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone G | 6 | To be completed |  | 18 | SEPTEMBER
T-496-8117 | PS5-04-OB-3393A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone D | 3 | On hold |  | 38 | SEPTEMBER
T-307-8118 | PS5-64-UR-7790A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | In progress |  | 37 | SEPTEMBER
T-450-8119 | PS5-13-OB-8791B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-04-03 | PS5-01-06 | PS5 - Milestone A | 1 | Closed | 23 | 11 | APRIL
T-689-8120 | PS5-79-UR-6171D | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | On hold |  | 45 | NOVEMBER
T-271-8121 | PS5-32-UR-4655A | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone D | 3 | In progress |  | 30 | DECEMBER
T-009-8122 | PS5-62-OB-2389C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone C | 2 | In progress |  | 32 | DECEMBER
T-350-8123 | PS5-75-IK-2872A | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone C | 2 | To be completed |  | 16 | DECEMBER
T-833-8124 | PS5-68-UR-6229D | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone B | 1.1 | To be completed |  | 11 | SEPTEMBER
T-405-8125 | PS5-63-UR-4225C | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone E | 4 | To be completed |  | 41 | DECEMBER
T-131-8126 | PS5-99-IK-1940C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-10-26 | PS5-03-02 | PS5 - Milestone C | 2 | Closed | 5 | 25 | OCTOBER
T-161-8127 | PS5-47-OB-9466C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone B | 1.1 | In progress |  | 20 | OCTOBER
T-496-8128 | PS5-55-OB-9407D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-12-25 | PS5-06-02 | PS5 - Milestone I | 8 | Closed | 20 | 15 | DECEMBER
T-773-8129 | PS5-84-UR-4454C | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | To be completed |  | 4 | SEPTEMBER
T-733-8130 | PS5-85-OB-2473B | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | To be completed |  | 11 | OCTOBER
T-667-8131 | PS5-61-OB-7178D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone E | 4 | On hold |  | 8 | AUGUST
T-509-8132 | PS5-78-OB-6827B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone G | 6 | In progress |  | 35 | AUGUST
T-275-8133 | PS5-79-UR-3040B | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-07-07 | PS5-10-02 | PS5 - Milestone F | 5 | Closed | 28 | 15 | JULY
T-009-8134 | PS5-28-OB-2343B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone G | 6 | In progress |  | 36 | NOVEMBER
T-453-8135 | PS5-10-IK-3414B | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-09-11 | PS5-10-03 | PS5 - Milestone E | 4 | Closed | 46 | 22 | SEPTEMBER
T-976-8136 | PS5-35-OB-6890C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone I | 8 | In progress |  | 25 | OCTOBER
T-604-8137 | PS5-10-UR-6385D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone F | 5 | In progress |  | 22 | AUGUST
T-414-8138 | PS5-25-UR-7440A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-06-27 | PS5-04-04 | PS5 - Milestone B | 1.1 | Closed | 6 | 6 | JUNE
T-129-8139 | PS5-87-OB-1380A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone B | 1.1 | To be completed |  | 12 | OCTOBER
T-559-8140 | PS5-47-OB-5767D | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | To be completed |  | 12 | OCTOBER
T-169-8141 | PS5-10-OB-4592D | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone H | 7 | On hold |  | 26 | DECEMBER
T-539-8142 | PS5-49-UR-4423D | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-05-26 | PS5-09-01 | PS5 - Milestone G | 6 | Closed | 34 | 31 | MAY
T-152-8143 | PS5-99-OB-4398D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone E | 4 | In progress |  | 40 | DECEMBER
T-869-8144 | PS5-34-IK-9400B | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone F | 5 | To be completed |  | 41 | OCTOBER
T-193-8145 | PS5-80-UR-2145B | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone H | 7 | To be completed |  | 16 | DECEMBER
T-429-8146 | PS5-19-UR-3306A | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-11-18 | PS5-60-10 | PS5 - Milestone C | 2 | Closed | 13 | 13 | NOVEMBER
T-428-8147 | PS5-60-OB-2477D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-09-21 | PS5-04-01 | PS5 - Milestone C | 2 | Closed | 12 | 8 | SEPTEMBER
T-622-8148 | PS5-45-UR-4322B | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone A | 1 | In progress |  | 17 | AUGUST
T-821-8149 | PS5-18-OB-8971D | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-09-25 | PS5-82-07 | PS5 - Milestone C | 2 | Closed | 32 | 10 | SEPTEMBER
T-362-8150 | PS5-58-UR-5201B | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone A | 1 | In progress |  | 7 | OCTOBER
T-832-8151 | PS5-08-UR-9651A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone E | 4 | To be completed |  | 25 | SEPTEMBER
T-300-8152 | PS5-65-OB-3151B | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone A | 1 | On hold |  | 34 | AUGUST
T-217-8153 | PS5-64-IK-6490D | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone B | 1.1 | On hold |  | 19 | AUGUST
T-468-8154 | PS5-01-OB-7986B | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone B | 1.1 | In progress |  | 5 | AUGUST
T-891-8155 | PS5-81-IK-4146C | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone D | 3 | To be completed |  | 16 | SEPTEMBER
T-317-8156 | PS5-73-UR-4798A | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-03-01 | PS5-09-02 | PS5 - Milestone B | 1.1 | Closed | 27 | 10 | MARCH
T-466-8157 | PS5-81-IK-9892C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-06-14 | PS5-61-07 | PS5 - Milestone D | 3 | Closed | 23 | 4 | JUNE
T-650-8158 | PS5-69-UR-8985B | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | To be completed |  | 13 | SEPTEMBER
T-086-8159 | PS5-13-UR-6967D | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | On hold |  | 6 | AUGUST
T-787-8160 | PS5-02-OB-7552A | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | In progress |  | 21 | DECEMBER
T-705-8161 | PS5-78-IK-7452C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-09-16 | PS5-03-03 | PS5 - Milestone I | 8 | Closed | 11 | 31 | SEPTEMBER
T-622-8162 | PS5-71-OB-2176B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-11-01 | PS5-10-03 | PS5 - Milestone I | 8 | Closed | 30 | 37 | NOVEMBER
T-794-8163 | PS5-64-UR-2722A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-04-27 | PS5-61-02 | PS5 - Milestone G | 6 | Closed | 37 | 5 | APRIL
T-387-8164 | PS5-42-OB-5680D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | In progress |  | 20 | AUGUST
T-690-8165 | PS5-56-OB-7672A | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-12-16 | PS5-03-01 | PS5 - Milestone G | 6 | Closed | 40 | 12 | DECEMBER
T-314-8166 | PS5-97-UR-4995D | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | To be completed |  | 26 | DECEMBER
T-985-8167 | PS5-67-OB-7744C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-12-02 | PS5-02-03 | PS5 - Milestone B | 1.1 | Closed | 10 | 4 | DECEMBER
T-519-8168 | PS5-98-OB-6614B | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | On hold |  | 45 | DECEMBER
T-941-8169 | PS5-76-UR-1447D | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-03-24 | PS5-01-02 | PS5 - Milestone C | 2 | Closed | 7 | 28 | MARCH
T-748-8170 | PS5-75-IK-3754D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone A | 1 | To be completed |  | 48 | AUGUST
T-161-8171 | PS5-81-OB-4694D | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-06-14 | PS5-04-03 | PS5 - Milestone E | 4 | Closed | 34 | 47 | JUNE
T-372-8172 | PS5-77-OB-2940D | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone F | 5 | To be completed |  | 6 | AUGUST
T-488-8173 | PS5-34-OB-1504D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone A | 1 | On hold |  | 18 | AUGUST
T-509-8174 | PS5-45-UR-1510A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone C | 2 | In progress |  | 32 | NOVEMBER
T-479-8175 | PS5-63-IK-9960A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone G | 6 | In progress |  | 17 | AUGUST
T-098-8176 | PS5-49-IK-5277A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone H | 7 | To be completed |  | 33 | AUGUST
T-709-8177 | PS5-31-IK-7634D | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone F | 5 | To be completed |  | 12 | NOVEMBER
T-578-8178 | PS5-62-OB-3444C | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone I | 8 | In progress |  | 10 | OCTOBER
T-215-8179 | PS5-76-UR-8792B | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-06-14 | PS5-11-01 | PS5 - Milestone C | 2 | Closed | 34 | 9 | JUNE
T-132-8180 | PS5-15-OB-4911C | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone G | 6 | To be completed |  | 18 | SEPTEMBER
T-530-8181 | PS5-17-OB-3899C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-15 | PS5-60-04 | PS5 - Milestone C | 2 | Closed | 8 | 4 | FEBRUARY
T-079-8182 | PS5-70-OB-2262A | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone I | 8 | On hold |  | 45 | OCTOBER
T-475-8183 | PS5-70-OB-3574A | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | To be completed |  | 43 | OCTOBER
T-006-8184 | PS5-09-OB-6987A | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone G | 6 | To be completed |  | 30 | OCTOBER
T-918-8185 | PS5-09-IK-5465D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone B | 1.1 | To be completed |  | 17 | NOVEMBER
T-488-8186 | PS5-62-OB-6497C | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone E | 4 | To be completed |  | 12 | SEPTEMBER
T-363-8187 | PS5-28-OB-7008C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone I | 8 | In progress |  | 34 | SEPTEMBER
T-443-8188 | PS5-30-IK-4936C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone B | 1.1 | To be completed |  | 14 | SEPTEMBER
T-483-8189 | PS5-97-OB-8919D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone H | 7 | To be completed |  | 12 | DECEMBER
T-593-8190 | PS5-51-UR-2084A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-05-01 | PS5-03-03 | PS5 - Milestone A | 1 | Closed | 42 | 44 | MAY
T-398-8191 | PS5-50-IK-4515B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone D | 3 | To be completed |  | 19 | NOVEMBER
T-728-8192 | PS5-51-OB-7395A | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-06-19 | PS5-01-02 | PS5 - Milestone A | 1 | Closed | 6 | 28 | JUNE
T-661-8193 | PS5-02-IK-1808A | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone E | 4 | In progress |  | 29 | DECEMBER
T-607-8194 | PS5-44-OB-5038C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-09-06 | PS5-01-09 | PS5 - Milestone D | 3 | Closed | 29 | 30 | SEPTEMBER
T-144-8195 | PS5-06-IK-5830A | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone C | 2 | To be completed |  | 38 | AUGUST
T-741-8196 | PS5-67-IK-7560D | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | On hold |  | 37 | OCTOBER
T-554-8197 | PS5-37-OB-1206A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone I | 8 | On hold |  | 38 | DECEMBER
T-890-8198 | PS5-83-IK-1216B | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-02-01 | PS5-99-02 | PS5 - Milestone G | 6 | Closed | 48 | 40 | FEBRUARY
T-851-8199 | PS5-41-UR-5841D | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-07-09 | PS5-63-04 | PS5 - Milestone C | 2 | Closed | 42 | 6 | JULY
T-006-8200 | PS5-35-IK-4552D | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | In progress |  | 21 | OCTOBER
T-729-8201 | PS5-18-OB-9632D | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-03-18 | PS5-09-02 | PS5 - Milestone C | 2 | Closed | 15 | 19 | MARCH
T-155-8202 | PS5-17-IK-5358C | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone C | 2 | On hold |  | 9 | NOVEMBER
T-396-8203 | PS5-03-OB-3444A | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone H | 7 | In progress |  | 11 | NOVEMBER
T-242-8204 | PS5-43-OB-1216C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone F | 5 | In progress |  | 27 | SEPTEMBER
T-622-8205 | PS5-72-UR-9003A | CQH02 - AHU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone C | 2 | On hold |  | 5 | AUGUST
T-708-8206 | PS5-98-OB-2898B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone A | 1 | To be completed |  | 44 | AUGUST
T-179-8207 | PS5-13-OB-1396B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone H | 7 | In progress |  | 5 | AUGUST
T-366-8208 | PS5-83-UR-9693C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone E | 4 | On hold |  | 26 | OCTOBER
T-552-8209 | PS5-28-OB-3186A | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-04-10 | PS5-01-02 | PS5 - Milestone C | 2 | Closed | 22 | 30 | APRIL
T-328-8210 | PS5-45-OB-2487B | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone C | 2 | On hold |  | 42 | AUGUST
T-579-8211 | PS5-59-OB-7063C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | In progress |  | 48 | NOVEMBER
T-047-8212 | PS5-85-OB-5694C | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone E | 4 | To be completed |  | 32 | AUGUST
T-356-8213 | PS5-46-IK-3251D | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | In progress |  | 47 | DECEMBER
T-458-8214 | PS5-88-IK-1187C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-02-18 | PS5-99-03 | PS5 - Milestone I | 8 | Closed | 6 | 25 | FEBRUARY
T-254-8215 | PS5-56-OB-6164D | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone I | 8 | To be completed |  | 30 | SEPTEMBER
T-015-8216 | PS5-01-OB-9708D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-12-25 | PS5-07-01 | PS5 - Milestone E | 4 | Closed | 25 | 39 | DECEMBER
T-643-8217 | PS5-14-OB-5894B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-10-08 | PS5-03-03 | PS5 - Milestone F | 5 | Closed | 5 | 12 | OCTOBER
T-452-8218 | PS5-65-UR-8721C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone I | 8 | To be completed |  | 11 | AUGUST
T-004-8219 | PS5-24-UR-9493D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-07-19 | PS5-01-09 | PS5 - Milestone B | 1.1 | Closed | 45 | 42 | JULY
T-357-8220 | PS5-67-OB-7044A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-04-15 | PS5-07-04 | PS5 - Milestone E | 4 | Closed | 37 | 9 | APRIL
T-644-8221 | PS5-81-IK-8298C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-24 | PS5-60-04 | PS5 - Milestone A | 1 | Closed | 46 | 25 | JULY
T-188-8222 | PS5-10-IK-9852C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-06-23 | PS5-04-04 | PS5 - Milestone E | 4 | Closed | 33 | 7 | JUNE
T-113-8223 | PS5-17-IK-8907A | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone C | 2 | To be completed |  | 18 | SEPTEMBER
T-046-8224 | PS5-91-IK-1158A | CQM03 - Heat Exchanger | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone H | 7 | In progress |  | 31 | AUGUST
T-057-8225 | PS5-61-OB-9989C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | In progress |  | 19 | SEPTEMBER
T-117-8226 | PS5-58-IK-5528B | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone E | 4 | To be completed |  | 43 | NOVEMBER
T-974-8227 | PS5-47-OB-8827B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-11-08 | PS5-62-02 | PS5 - Milestone G | 6 | Closed | 6 | 31 | NOVEMBER
T-123-8228 | PS5-88-IK-6100B | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone H | 7 | To be completed |  | 19 | DECEMBER
T-201-8229 | PS5-54-UR-1539C | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone I | 8 | To be completed |  | 30 | NOVEMBER
T-639-8230 | PS5-66-OB-2538B | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | In progress |  | 43 | DECEMBER
T-678-8231 | PS5-73-OB-1836D | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-02-04 | PS5-61-07 | PS5 - Milestone H | 7 | Closed | 48 | 26 | FEBRUARY
T-243-8232 | PS5-07-IK-5467A | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-12-01 | PS5-01-04 | PS5 - Milestone D | 3 | Closed | 34 | 12 | DECEMBER
T-056-8233 | PS5-44-UR-8433B | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone C | 2 | To be completed |  | 17 | DECEMBER
T-830-8234 | PS5-77-OB-2022C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone G | 6 | To be completed |  | 30 | DECEMBER
T-533-8235 | PS5-43-OB-4033B | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | In progress |  | 38 | AUGUST
T-166-8236 | PS5-77-UR-9910A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-02-08 | PS5-63-04 | PS5 - Milestone I | 8 | Closed | 36 | 8 | FEBRUARY
T-999-8237 | PS5-95-OB-1780C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | On hold |  | 41 | NOVEMBER
T-779-8238 | PS5-95-OB-4075A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-07-27 | PS5-01-06 | PS5 - Milestone E | 4 | Closed | 31 | 5 | JULY
T-684-8239 | PS5-46-IK-7593C | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone H | 7 | To be completed |  | 22 | DECEMBER
T-120-8240 | PS5-47-IK-6765D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone D | 3 | In progress |  | 41 | AUGUST
T-529-8241 | PS5-88-UR-8216C | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone A | 1 | To be completed |  | 9 | NOVEMBER
T-119-8242 | PS5-08-OB-5320A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-06-02 | PS5-11-03 | PS5 - Milestone B | 1.1 | Closed | 5 | 13 | JUNE
T-018-8243 | PS5-24-OB-6413B | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-03-26 | PS5-07-04 | PS5 - Milestone A | 1 | Closed | 23 | 22 | MARCH
T-247-8244 | PS5-39-OB-3103A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | In progress |  | 36 | SEPTEMBER
T-205-8245 | PS5-21-IK-5910B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone A | 1 | On hold |  | 30 | SEPTEMBER
T-539-8246 | PS5-56-IK-5085D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | On hold |  | 43 | AUGUST
T-304-8247 | PS5-52-IK-4767B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone A | 1 | In progress |  | 30 | OCTOBER
T-625-8248 | PS5-70-IK-3238A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-03-19 | PS5-61-01 | PS5 - Milestone G | 6 | Closed | 27 | 9 | MARCH
T-999-8249 | PS5-14-OB-9337A | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | On hold |  | 12 | DECEMBER
T-903-8250 | PS5-74-OB-4743D | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-04-20 | PS5-61-07 | PS5 - Milestone B | 1.1 | Closed | 15 | 29 | APRIL
T-952-8251 | PS5-55-OB-4620C | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-02-15 | PS5-61-01 | PS5 - Milestone B | 1.1 | Closed | 5 | 28 | FEBRUARY
T-099-8252 | PS5-94-UR-4879A | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-01-16 | PS5-09-01 | PS5 - Milestone B | 1.1 | Closed | 27 | 22 | JANUARY
T-793-8253 | PS5-66-IK-5654D | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-08-12 | PS5-10-03 | PS5 - Milestone I | 8 | Closed | 44 | 45 | AUGUST
T-321-8254 | PS5-54-OB-3987B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone E | 4 | To be completed |  | 47 | OCTOBER
T-130-8255 | PS5-75-UR-7973C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone G | 6 | To be completed |  | 29 | DECEMBER
T-491-8256 | PS5-90-UR-7612A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone E | 4 | In progress |  | 17 | AUGUST
T-586-8257 | PS5-20-OB-2691D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone B | 1.1 | To be completed |  | 4 | OCTOBER
T-008-8258 | PS5-20-IK-9750B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone G | 6 | To be completed |  | 10 | DECEMBER
T-078-8259 | PS5-29-OB-5392D | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | To be completed |  | 16 | AUGUST
T-659-8260 | PS5-22-IK-2137A | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone D | 3 | In progress |  | 6 | NOVEMBER
T-124-8261 | PS5-80-IK-9748C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-10-01 | PS5-82-07 | PS5 - Milestone B | 1.1 | Closed | 35 | 46 | OCTOBER
T-154-8262 | PS5-54-IK-9792D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone A | 1 | To be completed |  | 5 | OCTOBER
T-190-8263 | PS5-04-OB-9126B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | On hold |  | 33 | DECEMBER
T-126-8264 | PS5-58-OB-9286B | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-08-22 | PS5-60-07 | PS5 - Milestone I | 8 | Closed | 33 | 30 | AUGUST
T-553-8265 | PS5-36-UR-2524D | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone I | 8 | On hold |  | 5 | NOVEMBER
T-988-8266 | PS5-27-OB-9926C | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-02-20 | PS5-62-01 | PS5 - Milestone F | 5 | Closed | 41 | 6 | FEBRUARY
T-298-8267 | PS5-89-UR-9961A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone A | 1 | On hold |  | 48 | NOVEMBER
T-945-8268 | PS5-46-IK-8942D | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-12-14 | PS5-02-02 | PS5 - Milestone E | 4 | Closed | 18 | 11 | DECEMBER
T-281-8269 | PS5-49-UR-9924A | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-06-24 | PS5-10-03 | PS5 - Milestone C | 2 | Closed | 41 | 17 | JUNE
T-909-8270 | PS5-86-OB-1369A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone H | 7 | To be completed |  | 21 | DECEMBER
T-540-8271 | PS5-08-OB-2694A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | In progress |  | 45 | AUGUST
T-677-8272 | PS5-39-UR-6830A | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone D | 3 | To be completed |  | 46 | DECEMBER
T-880-8273 | PS5-65-OB-4156B | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | On hold |  | 12 | SEPTEMBER
T-417-8274 | PS5-14-OB-7953A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-03-04 | PS5-61-01 | PS5 - Milestone G | 6 | Closed | 33 | 16 | MARCH
T-483-8275 | PS5-46-OB-4814B | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-05-27 | PS5-82-02 | PS5 - Milestone F | 5 | Closed | 18 | 48 | MAY
T-885-8276 | PS5-71-OB-3773C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-04-16 | PS5-99-02 | PS5 - Milestone C | 2 | Closed | 39 | 6 | APRIL
T-988-8277 | PS5-89-UR-1865D | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-05-11 | PS5-62-01 | PS5 - Milestone G | 6 | Closed | 42 | 30 | MAY
T-067-8278 | PS5-42-UR-6873D | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | On hold |  | 28 | NOVEMBER
T-514-8279 | PS5-41-IK-9519C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-09-14 | PS5-11-01 | PS5 - Milestone I | 8 | Closed | 9 | 22 | SEPTEMBER
T-716-8280 | PS5-27-IK-5153D | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-02-10 | PS5-08-02 | PS5 - Milestone E | 4 | Closed | 6 | 30 | FEBRUARY
T-704-8281 | PS5-80-OB-7798C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | On hold |  | 30 | SEPTEMBER
T-236-8282 | PS5-09-OB-9070C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone I | 8 | To be completed |  | 20 | NOVEMBER
T-216-8283 | PS5-30-OB-9611B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-10-22 | PS5-82-07 | PS5 - Milestone A | 1 | Closed | 41 | 4 | OCTOBER
T-650-8284 | PS5-02-OB-8097A | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone C | 2 | In progress |  | 25 | AUGUST
T-123-8285 | PS5-23-UR-5018A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone B | 1.1 | To be completed |  | 10 | NOVEMBER
T-366-8286 | PS5-53-IK-6776B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone H | 7 | To be completed |  | 23 | SEPTEMBER
T-600-8287 | PS5-09-UR-9587A | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone D | 3 | To be completed |  | 45 | DECEMBER
T-778-8288 | PS5-40-OB-4593A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-04-03 | PS5-04-03 | PS5 - Milestone C | 2 | Closed | 41 | 35 | APRIL
T-517-8289 | PS5-79-OB-3834C | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone A | 1 | In progress |  | 48 | OCTOBER
T-664-8290 | PS5-52-OB-9658A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-04-01 | PS5-09-04 | PS5 - Milestone B | 1.1 | Closed | 45 | 20 | APRIL
T-262-8291 | PS5-33-OB-3950C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-20 | PS5-60-01 | PS5 - Milestone D | 3 | Closed | 8 | 25 | FEBRUARY
T-963-8292 | PS5-33-OB-1707A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-08-06 | PS5-02-01 | PS5 - Milestone I | 8 | Closed | 19 | 16 | AUGUST
T-143-8293 | PS5-56-OB-2015B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone E | 4 | To be completed |  | 40 | SEPTEMBER
T-574-8294 | PS5-84-UR-6097A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-06-13 | PS5-10-02 | PS5 - Milestone E | 4 | Closed | 25 | 6 | JUNE
T-181-8295 | PS5-65-IK-9540B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone H | 7 | To be completed |  | 10 | AUGUST
T-559-8296 | PS5-01-OB-7991D | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone I | 8 | To be completed |  | 14 | DECEMBER
T-226-8297 | PS5-79-IK-3805A | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | In progress |  | 45 | AUGUST
T-044-8298 | PS5-74-OB-1362A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone G | 6 | In progress |  | 46 | AUGUST
T-102-8299 | PS5-50-UR-3981A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone H | 7 | On hold |  | 48 | AUGUST
T-146-8300 | PS5-12-IK-1254C | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-06-05 | PS5-04-02 | PS5 - Milestone B | 1.1 | Closed | 35 | 21 | JUNE
T-483-8301 | PS5-97-OB-6091B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-12-25 | PS5-04-04 | PS5 - Milestone C | 2 | Closed | 26 | 29 | DECEMBER
T-385-8302 | PS5-90-OB-6119D | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone E | 4 | In progress |  | 31 | SEPTEMBER
T-668-8303 | PS5-18-UR-2879B | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone A | 1 | In progress |  | 37 | OCTOBER
T-021-8304 | PS5-52-OB-9834D | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-09-02 | PS5-01-02 | PS5 - Milestone A | 1 | Closed | 4 | 44 | SEPTEMBER
T-068-8305 | PS5-69-UR-3419A | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone A | 1 | In progress |  | 6 | DECEMBER
T-887-8306 | PS5-92-IK-3064D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone I | 8 | To be completed |  | 8 | DECEMBER
T-180-8307 | PS5-78-OB-1357B | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-09-14 | PS5-61-02 | PS5 - Milestone F | 5 | Closed | 39 | 27 | SEPTEMBER
T-284-8308 | PS5-22-IK-7553C | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone E | 4 | To be completed |  | 19 | OCTOBER
T-912-8309 | PS5-49-OB-8435A | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-03-18 | PS5-07-03 | PS5 - Milestone G | 6 | Closed | 10 | 33 | MARCH
T-014-8310 | PS5-02-UR-3952B | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-11-03 | PS5-07-02 | PS5 - Milestone D | 3 | Closed | 48 | 23 | NOVEMBER
T-300-8311 | PS5-99-UR-2609A | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-01-08 | PS5-09-03 | PS5 - Milestone A | 1 | Closed | 35 | 15 | JANUARY
T-742-8312 | PS5-88-UR-5676B | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone E | 4 | On hold |  | 46 | NOVEMBER
T-708-8313 | PS5-79-IK-7574C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone A | 1 | To be completed |  | 43 | AUGUST
T-141-8314 | PS5-83-IK-4754B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-10-11 | PS5-03-01 | PS5 - Milestone H | 7 | Closed | 35 | 16 | OCTOBER
T-188-8315 | PS5-65-UR-5052C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone B | 1.1 | To be completed |  | 32 | OCTOBER
T-701-8316 | PS5-86-OB-1550D | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-03-07 | PS5-01-06 | PS5 - Milestone I | 8 | Closed | 43 | 33 | MARCH
T-867-8317 | PS5-97-OB-8743D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-03-03 | PS5-04-02 | PS5 - Milestone F | 5 | Closed | 5 | 20 | MARCH
T-404-8318 | PS5-42-IK-1173D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone D | 3 | In progress |  | 22 | AUGUST
T-076-8319 | PS5-07-OB-7101D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone I | 8 | To be completed |  | 32 | NOVEMBER
T-092-8320 | PS5-04-OB-3318C | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone I | 8 | To be completed |  | 9 | SEPTEMBER
T-261-8321 | PS5-27-UR-9243B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-06-12 | PS5-01-03 | PS5 - Milestone D | 3 | Closed | 18 | 24 | JUNE
T-073-8322 | PS5-08-OB-9638D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone A | 1 | To be completed |  | 34 | OCTOBER
T-134-8323 | PS5-33-OB-8893A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-03-20 | PS5-82-02 | PS5 - Milestone B | 1.1 | Closed | 7 | 17 | MARCH
T-308-8324 | PS5-95-OB-5125D | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | To be completed |  | 17 | OCTOBER
T-315-8325 | PS5-94-OB-3436B | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | In progress |  | 23 | SEPTEMBER
T-614-8326 | PS5-78-IK-7550C | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone A | 1 | To be completed |  | 7 | OCTOBER
T-073-8327 | PS5-25-IK-4303D | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone H | 7 | To be completed |  | 22 | OCTOBER
T-594-8328 | PS5-93-OB-8458A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-11-06 | PS5-06-01 | PS5 - Milestone I | 8 | Closed | 30 | 23 | NOVEMBER
T-824-8329 | PS5-61-OB-3096C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-05-05 | PS5-05-03 | PS5 - Milestone E | 4 | Closed | 22 | 33 | MAY
T-308-8330 | PS5-14-OB-3911D | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-11-08 | PS5-05-02 | PS5 - Milestone I | 8 | Closed | 23 | 26 | NOVEMBER
T-315-8331 | PS5-15-OB-4470D | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-05-26 | PS5-01-06 | PS5 - Milestone F | 5 | Closed | 48 | 43 | MAY
T-807-8332 | PS5-48-OB-7263D | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone F | 5 | To be completed |  | 27 | NOVEMBER
T-409-8333 | PS5-65-UR-5498B | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone G | 6 | To be completed |  | 7 | DECEMBER
T-684-8334 | PS5-41-OB-9777B | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-03-09 | PS5-01-03 | PS5 - Milestone F | 5 | Closed | 37 | 17 | MARCH
T-516-8335 | PS5-16-OB-3276C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-07-25 | PS5-02-03 | PS5 - Milestone G | 6 | Closed | 27 | 12 | JULY
T-954-8336 | PS5-58-IK-2475C | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone F | 5 | In progress |  | 5 | SEPTEMBER
T-382-8337 | PS5-84-IK-3784C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | To be completed |  | 47 | SEPTEMBER
T-960-8338 | PS5-59-IK-9472D | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone A | 1 | In progress |  | 33 | SEPTEMBER
T-724-8339 | PS5-48-IK-5996A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone G | 6 | In progress |  | 21 | DECEMBER
T-874-8340 | PS5-45-OB-2019D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | On hold |  | 26 | DECEMBER
T-148-8341 | PS5-55-OB-1786D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | To be completed |  | 22 | DECEMBER
T-890-8342 | PS5-79-OB-7495C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | In progress |  | 32 | AUGUST
T-252-8343 | PS5-83-IK-8455D | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-03-17 | PS5-06-03 | PS5 - Milestone B | 1.1 | Closed | 28 | 36 | MARCH
T-374-8344 | PS5-39-UR-6927C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone F | 5 | On hold |  | 43 | AUGUST
T-809-8345 | PS5-82-IK-1123C | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone G | 6 | To be completed |  | 10 | SEPTEMBER
T-373-8346 | PS5-68-OB-8147C | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone A | 1 | In progress |  | 42 | NOVEMBER
T-893-8347 | PS5-97-UR-1021A | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone B | 1.1 | In progress |  | 32 | DECEMBER
T-166-8348 | PS5-85-OB-2302B | CQM04 - Vessel | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone A | 1 | To be completed |  | 36 | AUGUST
T-810-8349 | PS5-54-OB-3070B | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | To be completed |  | 43 | SEPTEMBER
T-279-8350 | PS5-03-OB-1425B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone H | 7 | On hold |  | 13 | NOVEMBER
T-923-8351 | PS5-21-UR-7535A | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | On hold |  | 12 | OCTOBER
T-400-8352 | PS5-77-OB-9714C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone G | 6 | To be completed |  | 48 | SEPTEMBER
T-623-8353 | PS5-65-OB-4258A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone D | 3 | On hold |  | 21 | SEPTEMBER
T-244-8354 | PS5-24-OB-5766C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-06-15 | PS5-03-01 | PS5 - Milestone D | 3 | Closed | 24 | 12 | JUNE
T-475-8355 | PS5-01-UR-8062B | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone C | 2 | On hold |  | 8 | OCTOBER
T-940-8356 | PS5-55-OB-9288B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone C | 2 | To be completed |  | 28 | SEPTEMBER
T-896-8357 | PS5-40-OB-6740C | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone A | 1 | On hold |  | 24 | OCTOBER
T-436-8358 | PS5-49-OB-2233C | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-12-15 | PS5-99-03 | PS5 - Milestone D | 3 | Closed | 17 | 22 | DECEMBER
T-996-8359 | PS5-68-IK-4310C | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone G | 6 | To be completed |  | 39 | AUGUST
T-106-8360 | PS5-01-IK-9037D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-06-22 | PS5-12-01 | PS5 - Milestone B | 1.1 | Closed | 43 | 46 | JUNE
T-179-8361 | PS5-95-IK-9390A | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone G | 6 | In progress |  | 29 | SEPTEMBER
T-961-8362 | PS5-36-OB-4660B | CQE02 - LV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone E | 4 | To be completed |  | 25 | DECEMBER
T-607-8363 | PS5-30-IK-9192D | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | To be completed |  | 35 | DECEMBER
T-429-8364 | PS5-95-OB-1304C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-12-27 | PS5-10-05 | PS5 - Milestone I | 8 | Closed | 31 | 35 | DECEMBER
T-601-8365 | PS5-90-UR-4044D | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-06-19 | PS5-11-03 | PS5 - Milestone C | 2 | Closed | 21 | 24 | JUNE
T-461-8366 | PS5-15-UR-6764D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-01-16 | PS5-61-02 | PS5 - Milestone F | 5 | Closed | 24 | 29 | JANUARY
T-964-8367 | PS5-97-IK-6800A | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-09-08 | PS5-10-06 | PS5 - Milestone D | 3 | Closed | 31 | 21 | SEPTEMBER
T-125-8368 | PS5-60-IK-2592A | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone B | 1.1 | On hold |  | 25 | OCTOBER
T-598-8369 | PS5-28-OB-5693D | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone I | 8 | To be completed |  | 14 | SEPTEMBER
T-094-8370 | PS5-95-UR-3953A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | In progress |  | 38 | SEPTEMBER
T-490-8371 | PS5-81-IK-3332D | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone E | 4 | On hold |  | 35 | NOVEMBER
T-286-8372 | PS5-84-IK-9928D | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-04-12 | PS5-03-02 | PS5 - Milestone D | 3 | Closed | 7 | 18 | APRIL
T-641-8373 | PS5-06-OB-9449C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone G | 6 | In progress |  | 25 | NOVEMBER
T-998-8374 | PS5-80-UR-5889B | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-11-12 | PS5-61-01 | PS5 - Milestone I | 8 | Closed | 28 | 27 | NOVEMBER
T-867-8375 | PS5-03-OB-3054C | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-06-11 | PS5-09-01 | PS5 - Milestone F | 5 | Closed | 43 | 33 | JUNE
T-155-8376 | PS5-33-OB-9569A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone E | 4 | In progress |  | 39 | DECEMBER
T-582-8377 | PS5-16-UR-2122A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone D | 3 | To be completed |  | 43 | OCTOBER
T-894-8378 | PS5-10-UR-4706A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone D | 3 | To be completed |  | 35 | DECEMBER
T-246-8379 | PS5-84-OB-6338A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-10-10 | PS5-05-02 | PS5 - Milestone G | 6 | Closed | 33 | 28 | OCTOBER
T-941-8380 | PS5-28-OB-5815D | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone C | 2 | To be completed |  | 31 | NOVEMBER
T-768-8381 | PS5-26-IK-5840C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | To be completed |  | 45 | NOVEMBER
T-427-8382 | PS5-21-IK-2184B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone D | 3 | On hold |  | 28 | OCTOBER
T-609-8383 | PS5-94-OB-1494B | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-07-06 | PS5-11-01 | PS5 - Milestone B | 1.1 | Closed | 16 | 16 | JULY
T-375-8384 | PS5-16-IK-8050B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | To be completed |  | 36 | OCTOBER
T-311-8385 | PS5-02-OB-4577A | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | In progress |  | 10 | AUGUST
T-970-8386 | PS5-47-IK-4521D | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone F | 5 | To be completed |  | 11 | AUGUST
T-514-8387 | PS5-96-OB-9333C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone C | 2 | To be completed |  | 6 | SEPTEMBER
T-394-8388 | PS5-06-OB-4048D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone D | 3 | On hold |  | 41 | AUGUST
T-289-8389 | PS5-54-UR-2542B | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-06-21 | PS5-01-01 | PS5 - Milestone G | 6 | Closed | 14 | 22 | JUNE
T-703-8390 | PS5-39-OB-6727C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone E | 4 | To be completed |  | 37 | DECEMBER
T-073-8391 | PS5-63-OB-4258D | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-01-12 | PS5-02-03 | PS5 - Milestone E | 4 | Closed | 33 | 15 | JANUARY
T-764-8392 | PS5-21-OB-5702B | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone I | 8 | To be completed |  | 20 | SEPTEMBER
T-878-8393 | PS5-99-OB-5447B | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-07-03 | PS5-01-09 | PS5 - Milestone A | 1 | Closed | 6 | 22 | JULY
T-702-8394 | PS5-73-UR-3251C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone A | 1 | In progress |  | 23 | OCTOBER
T-016-8395 | PS5-50-OB-6681A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | On hold |  | 17 | AUGUST
T-322-8396 | PS5-51-OB-4584D | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone E | 4 | To be completed |  | 37 | AUGUST
T-649-8397 | PS5-23-OB-8660B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone C | 2 | On hold |  | 8 | SEPTEMBER
T-182-8398 | PS5-03-OB-4658A | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone F | 5 | In progress |  | 35 | SEPTEMBER
T-715-8399 | PS5-25-OB-9350B | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | In progress |  | 6 | NOVEMBER
T-522-8400 | PS5-75-UR-2009D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-12-17 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 20 | 9 | DECEMBER
T-755-8401 | PS5-05-OB-3246C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-05-12 | PS5-11-03 | PS5 - Milestone C | 2 | Closed | 46 | 40 | MAY
T-527-8402 | PS5-90-UR-5185D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone C | 2 | On hold |  | 35 | SEPTEMBER
T-422-8403 | PS5-37-OB-9566A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-11-02 | PS5-61-07 | PS5 - Milestone B | 1.1 | Closed | 7 | 31 | NOVEMBER
T-205-8404 | PS5-44-OB-3240B | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-07-17 | PS5-02-03 | PS5 - Milestone H | 7 | Closed | 30 | 48 | JULY
T-965-8405 | PS5-80-UR-9191A | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-11-12 | PS5-12-01 | PS5 - Milestone I | 8 | Closed | 33 | 15 | NOVEMBER
T-121-8406 | PS5-33-UR-7186A | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone H | 7 | On hold |  | 13 | OCTOBER
T-671-8407 | PS5-57-IK-3550C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone B | 1.1 | In progress |  | 47 | SEPTEMBER
T-727-8408 | PS5-38-OB-6204C | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-12-09 | PS5-04-04 | PS5 - Milestone I | 8 | Closed | 11 | 37 | DECEMBER
T-929-8409 | PS5-88-UR-5195B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone C | 2 | To be completed |  | 18 | SEPTEMBER
T-271-8410 | PS5-31-OB-2555D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-03-15 | PS5-11-03 | PS5 - Milestone C | 2 | Closed | 34 | 28 | MARCH
T-637-8411 | PS5-20-OB-7029B | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone I | 8 | In progress |  | 36 | SEPTEMBER
T-526-8412 | PS5-64-IK-7043B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone I | 8 | In progress |  | 38 | OCTOBER
T-341-8413 | PS5-21-OB-2075C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone D | 3 | To be completed |  | 26 | SEPTEMBER
T-436-8414 | PS5-13-OB-5535B | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone E | 4 | To be completed |  | 29 | DECEMBER
T-912-8415 | PS5-89-IK-7111A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone D | 3 | To be completed |  | 44 | DECEMBER
T-895-8416 | PS5-83-IK-4545A | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone G | 6 | To be completed |  | 23 | OCTOBER
T-769-8417 | PS5-45-IK-5797C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-11-26 | PS5-07-01 | PS5 - Milestone F | 5 | Closed | 9 | 38 | NOVEMBER
T-834-8418 | PS5-05-UR-7386B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone E | 4 | To be completed |  | 30 | OCTOBER
T-469-8419 | PS5-90-UR-8950D | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | To be completed |  | 48 | DECEMBER
T-915-8420 | PS5-14-OB-2839B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-07-07 | PS5-01-07 | PS5 - Milestone A | 1 | Closed | 7 | 16 | JULY
T-756-8421 | PS5-68-OB-2829B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-08-23 | PS5-10-04 | PS5 - Milestone D | 3 | Closed | 40 | 41 | AUGUST
T-907-8422 | PS5-52-OB-3701D | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone F | 5 | To be completed |  | 20 | NOVEMBER
T-986-8423 | PS5-64-IK-4055D | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone C | 2 | In progress |  | 46 | DECEMBER
T-934-8424 | PS5-43-OB-2529C | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-10-24 | PS5-10-04 | PS5 - Milestone E | 4 | Closed | 26 | 7 | OCTOBER
T-541-8425 | PS5-63-IK-5115B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | To be completed |  | 35 | OCTOBER
T-665-8426 | PS5-95-UR-2149A | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-05-16 | PS5-03-03 | PS5 - Milestone C | 2 | Closed | 42 | 4 | MAY
T-306-8427 | PS5-55-OB-8690B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone D | 3 | On hold |  | 13 | NOVEMBER
T-333-8428 | PS5-52-UR-7541B | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | To be completed |  | 8 | AUGUST
T-732-8429 | PS5-76-OB-4549D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone B | 1.1 | To be completed |  | 47 | NOVEMBER
T-405-8430 | PS5-06-UR-3859C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | In progress |  | 34 | AUGUST
T-608-8431 | PS5-76-UR-6552D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone A | 1 | To be completed |  | 6 | OCTOBER
T-944-8432 | PS5-36-IK-4855D | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-05-27 | PS5-10-01 | PS5 - Milestone A | 1 | Closed | 14 | 45 | MAY
T-905-8433 | PS5-04-OB-7669D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone H | 7 | To be completed |  | 47 | OCTOBER
T-881-8434 | PS5-68-OB-1824A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone B | 1.1 | To be completed |  | 42 | SEPTEMBER
T-374-8435 | PS5-37-OB-7171C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | To be completed |  | 42 | NOVEMBER
T-623-8436 | PS5-49-OB-9040A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-11-17 | PS5-10-02 | PS5 - Milestone E | 4 | Closed | 10 | 8 | NOVEMBER
T-455-8437 | PS5-48-OB-4277B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-12-17 | PS5-12-01 | PS5 - Milestone G | 6 | Closed | 46 | 35 | DECEMBER
T-110-8438 | PS5-05-UR-5356C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-08-06 | PS5-01-07 | PS5 - Milestone A | 1 | Closed | 14 | 5 | AUGUST
T-153-8439 | PS5-40-UR-4752C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | In progress |  | 20 | OCTOBER
T-747-8440 | PS5-62-UR-4394C | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-03-24 | PS5-07-02 | PS5 - Milestone F | 5 | Closed | 34 | 29 | MARCH
T-858-8441 | PS5-14-OB-8523D | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-10-02 | PS5-60-07 | PS5 - Milestone H | 7 | Closed | 14 | 32 | OCTOBER
T-604-8442 | PS5-06-OB-8280C | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone C | 2 | To be completed |  | 12 | NOVEMBER
T-960-8443 | PS5-65-UR-2005A | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-12-14 | PS5-05-02 | PS5 - Milestone B | 1.1 | Closed | 34 | 6 | DECEMBER
T-328-8444 | PS5-14-OB-7484C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | To be completed |  | 20 | NOVEMBER
T-990-8445 | PS5-25-IK-9706C | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-10-26 | PS5-10-05 | PS5 - Milestone F | 5 | Closed | 29 | 24 | OCTOBER
T-588-8446 | PS5-01-IK-8055B | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone I | 8 | In progress |  | 14 | OCTOBER
T-888-8447 | PS5-10-OB-2961D | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-04-27 | PS5-03-03 | PS5 - Milestone A | 1 | Closed | 14 | 32 | APRIL
T-385-8448 | PS5-90-OB-4920D | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-02-02 | PS5-12-01 | PS5 - Milestone D | 3 | Closed | 48 | 20 | FEBRUARY
T-774-8449 | PS5-91-IK-3524D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | To be completed |  | 23 | NOVEMBER
T-133-8450 | PS5-45-UR-8370B | CQM04 - Vessel | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | In progress |  | 38 | DECEMBER
T-799-8451 | PS5-58-IK-7275A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone F | 5 | On hold |  | 8 | SEPTEMBER
T-685-8452 | PS5-59-UR-5970D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone C | 2 | To be completed |  | 37 | DECEMBER
T-724-8453 | PS5-70-OB-7753A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | To be completed |  | 5 | SEPTEMBER
T-305-8454 | PS5-63-UR-7303A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-09-17 | PS5-10-04 | PS5 - Milestone D | 3 | Closed | 29 | 34 | SEPTEMBER
T-322-8455 | PS5-36-OB-3525D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone B | 1.1 | On hold |  | 32 | AUGUST
T-847-8456 | PS5-05-IK-2431A | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone B | 1.1 | To be completed |  | 14 | AUGUST
T-565-8457 | PS5-66-UR-5147C | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone F | 5 | To be completed |  | 9 | NOVEMBER
T-289-8458 | PS5-58-IK-8691A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone A | 1 | To be completed |  | 35 | NOVEMBER
T-057-8459 | PS5-56-UR-5004D | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone D | 3 | In progress |  | 48 | SEPTEMBER
T-493-8460 | PS5-39-OB-6183D | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | In progress |  | 27 | AUGUST
T-026-8461 | PS5-75-OB-5792C | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-01-10 | PS5-12-02 | PS5 - Milestone B | 1.1 | Closed | 25 | 36 | JANUARY
T-032-8462 | PS5-99-OB-2902C | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | To be completed |  | 37 | OCTOBER
T-992-8463 | PS5-34-OB-4479B | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-09-28 | PS5-60-04 | PS5 - Milestone D | 3 | Closed | 41 | 38 | SEPTEMBER
T-993-8464 | PS5-68-IK-2431D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-09-22 | PS5-02-01 | PS5 - Milestone A | 1 | Closed | 18 | 33 | SEPTEMBER
T-923-8465 | PS5-20-OB-4040A | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-01-24 | PS5-05-01 | PS5 - Milestone G | 6 | Closed | 42 | 12 | JANUARY
T-550-8466 | PS5-99-OB-5848C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | To be completed |  | 19 | DECEMBER
T-858-8467 | PS5-13-IK-3935D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone H | 7 | To be completed |  | 23 | NOVEMBER
T-273-8468 | PS5-13-OB-5020B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone G | 6 | In progress |  | 36 | OCTOBER
T-468-8469 | PS5-16-OB-8119A | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone C | 2 | In progress |  | 19 | SEPTEMBER
T-057-8470 | PS5-34-IK-9344D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-03-19 | PS5-60-04 | PS5 - Milestone I | 8 | Closed | 13 | 26 | MARCH
T-105-8471 | PS5-57-IK-1275B | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | In progress |  | 36 | DECEMBER
T-955-8472 | PS5-16-IK-8638A | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone B | 1.1 | To be completed |  | 12 | AUGUST
T-083-8473 | PS5-43-OB-8571C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone A | 1 | To be completed |  | 30 | DECEMBER
T-307-8474 | PS5-29-OB-7841B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-02-02 | PS5-01-04 | PS5 - Milestone E | 4 | Closed | 4 | 28 | FEBRUARY
T-111-8475 | PS5-83-IK-1459C | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone A | 1 | To be completed |  | 25 | DECEMBER
T-269-8476 | PS5-29-IK-5701C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | In progress |  | 16 | NOVEMBER
T-359-8477 | PS5-34-UR-3278C | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-06-25 | PS5-09-03 | PS5 - Milestone B | 1.1 | Closed | 15 | 35 | JUNE
T-219-8478 | PS5-36-OB-7151B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone H | 7 | To be completed |  | 9 | DECEMBER
T-158-8479 | PS5-97-IK-3794D | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone G | 6 | In progress |  | 47 | DECEMBER
T-387-8480 | PS5-46-OB-6019D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone F | 5 | In progress |  | 22 | AUGUST
T-899-8481 | PS5-62-UR-5558A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone G | 6 | On hold |  | 17 | DECEMBER
T-475-8482 | PS5-27-OB-3573A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone D | 3 | To be completed |  | 12 | OCTOBER
T-589-8483 | PS5-98-OB-5215C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | To be completed |  | 37 | NOVEMBER
T-850-8484 | PS5-09-OB-7476C | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone C | 2 | In progress |  | 32 | DECEMBER
T-269-8485 | PS5-23-IK-2275B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-11-24 | PS5-07-01 | PS5 - Milestone E | 4 | Closed | 21 | 15 | NOVEMBER
T-028-8486 | PS5-34-OB-3194D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-12-25 | PS5-61-02 | PS5 - Milestone G | 6 | Closed | 45 | 40 | DECEMBER
T-706-8487 | PS5-71-UR-2708D | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-12-19 | PS5-10-02 | PS5 - Milestone I | 8 | Closed | 12 | 35 | DECEMBER
T-079-8488 | PS5-46-OB-7832D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone D | 3 | In progress |  | 44 | OCTOBER
T-571-8489 | PS5-02-IK-7044C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone H | 7 | To be completed |  | 10 | AUGUST
T-420-8490 | PS5-48-OB-2938A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone C | 2 | To be completed |  | 39 | OCTOBER
T-454-8491 | PS5-25-OB-1874C | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | In progress |  | 31 | DECEMBER
T-546-8492 | PS5-08-OB-2690D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone F | 5 | To be completed |  | 6 | DECEMBER
T-120-8493 | PS5-12-OB-2468D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone E | 4 | In progress |  | 40 | NOVEMBER
T-299-8494 | PS5-95-IK-8807B | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-12-05 | PS5-62-02 | PS5 - Milestone I | 8 | Closed | 17 | 6 | DECEMBER
T-754-8495 | PS5-46-OB-2461A | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone F | 5 | In progress |  | 46 | AUGUST
T-912-8496 | PS5-96-IK-6631D | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone E | 4 | On hold |  | 21 | OCTOBER
T-773-8497 | PS5-65-UR-9855D | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone A | 1 | To be completed |  | 7 | AUGUST
T-458-8498 | PS5-80-OB-9387A | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-02-11 | PS5-09-03 | PS5 - Milestone A | 1 | Closed | 25 | 15 | FEBRUARY
T-278-8499 | PS5-42-UR-3962D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-12-23 | PS5-03-01 | PS5 - Milestone F | 5 | Closed | 32 | 34 | DECEMBER
T-936-8500 | PS5-09-OB-6406C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone H | 7 | On hold |  | 33 | SEPTEMBER
T-765-8501 | PS5-93-OB-5024C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone I | 8 | In progress |  | 36 | OCTOBER
T-336-8502 | PS5-29-IK-6023B | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone I | 8 | In progress |  | 5 | OCTOBER
T-472-8503 | PS5-52-IK-7263B | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone H | 7 | On hold |  | 12 | AUGUST
T-471-8504 | PS5-62-UR-6821D | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone A | 1 | On hold |  | 46 | DECEMBER
T-723-8505 | PS5-77-UR-6458C | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-08-24 | PS5-01-01 | PS5 - Milestone F | 5 | Closed | 5 | 16 | AUGUST
T-983-8506 | PS5-88-IK-3334D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-01-14 | PS5-60-10 | PS5 - Milestone E | 4 | Closed | 8 | 43 | JANUARY
T-891-8507 | PS5-14-OB-8958A | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-05-22 | PS5-61-07 | PS5 - Milestone C | 2 | Closed | 37 | 30 | MAY
T-135-8508 | PS5-71-IK-7807C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone G | 6 | On hold |  | 22 | OCTOBER
T-794-8509 | PS5-46-IK-9302C | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone F | 5 | To be completed |  | 38 | AUGUST
T-103-8510 | PS5-66-OB-2607C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-07-05 | PS5-01-05 | PS5 - Milestone B | 1.1 | Closed | 44 | 35 | JULY
T-278-8511 | PS5-76-UR-4495D | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-11-23 | PS5-03-01 | PS5 - Milestone E | 4 | Closed | 22 | 6 | NOVEMBER
T-175-8512 | PS5-89-OB-3852C | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-01-12 | PS5-12-01 | PS5 - Milestone H | 7 | Closed | 29 | 44 | JANUARY
T-034-8513 | PS5-12-IK-9807C | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-06-07 | PS5-08-01 | PS5 - Milestone C | 2 | Closed | 30 | 33 | JUNE
T-457-8514 | PS5-68-OB-5137D | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-03-07 | PS5-01-01 | PS5 - Milestone H | 7 | Closed | 5 | 31 | MARCH
T-105-8515 | PS5-56-IK-7654B | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone G | 6 | To be completed |  | 47 | OCTOBER
T-046-8516 | PS5-50-OB-4491A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-09-24 | PS5-01-02 | PS5 - Milestone E | 4 | Closed | 32 | 14 | SEPTEMBER
T-768-8517 | PS5-45-UR-3270C | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone A | 1 | To be completed |  | 45 | AUGUST
T-637-8518 | PS5-24-IK-1370D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-11-16 | PS5-10-01 | PS5 - Milestone C | 2 | Closed | 36 | 48 | NOVEMBER
T-511-8519 | PS5-06-OB-4086A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone D | 3 | In progress |  | 10 | SEPTEMBER
T-206-8520 | PS5-36-OB-7002C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone I | 8 | In progress |  | 45 | AUGUST
T-056-8521 | PS5-25-IK-2101C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-08-06 | PS5-06-03 | PS5 - Milestone B | 1.1 | Closed | 26 | 48 | AUGUST
T-686-8522 | PS5-86-OB-2935C | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-08-06 | PS5-01-03 | PS5 - Milestone F | 5 | Closed | 24 | 23 | AUGUST
T-196-8523 | PS5-18-UR-7798D | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-03-04 | PS5-03-02 | PS5 - Milestone C | 2 | Closed | 22 | 45 | MARCH
T-039-8524 | PS5-71-UR-2022C | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone A | 1 | To be completed |  | 10 | NOVEMBER
T-797-8525 | PS5-71-UR-9191C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | To be completed |  | 20 | NOVEMBER
T-336-8526 | PS5-23-IK-2889B | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-11-07 | PS5-08-02 | PS5 - Milestone H | 7 | Closed | 24 | 5 | NOVEMBER
T-568-8527 | PS5-70-OB-9553C | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-02-09 | PS5-01-02 | PS5 - Milestone I | 8 | Closed | 4 | 29 | FEBRUARY
T-984-8528 | PS5-19-OB-8792D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone E | 4 | To be completed |  | 5 | DECEMBER
T-022-8529 | PS5-24-OB-7349B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone H | 7 | On hold |  | 34 | AUGUST
T-564-8530 | PS5-02-UR-2103D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone I | 8 | In progress |  | 9 | SEPTEMBER
T-204-8531 | PS5-90-IK-8965B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone H | 7 | To be completed |  | 31 | AUGUST
T-235-8532 | PS5-12-OB-5133C | CQM04 - Vessel | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone I | 8 | On hold |  | 6 | SEPTEMBER
T-906-8533 | PS5-05-UR-3135C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone I | 8 | In progress |  | 18 | SEPTEMBER
T-010-8534 | PS5-86-OB-8354D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone H | 7 | To be completed |  | 25 | OCTOBER
T-478-8535 | PS5-17-OB-1365C | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | In progress |  | 31 | DECEMBER
T-816-8536 | PS5-20-UR-2972D | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone G | 6 | In progress |  | 15 | DECEMBER
T-375-8537 | PS5-79-OB-7217D | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-04-07 | PS5-07-03 | PS5 - Milestone I | 8 | Closed | 40 | 34 | APRIL
T-648-8538 | PS5-95-UR-8253B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone B | 1.1 | To be completed |  | 32 | SEPTEMBER
T-023-8539 | PS5-11-UR-5984A | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-03-11 | PS5-99-02 | PS5 - Milestone E | 4 | Closed | 37 | 18 | MARCH
T-015-8540 | PS5-74-IK-6288C | CQM04 - Vessel | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone G | 6 | To be completed |  | 4 | OCTOBER
T-882-8541 | PS5-75-UR-8098C | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone F | 5 | To be completed |  | 34 | NOVEMBER
T-027-8542 | PS5-40-IK-3525D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone A | 1 | In progress |  | 26 | AUGUST
T-725-8543 | PS5-61-OB-8185D | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone F | 5 | To be completed |  | 10 | SEPTEMBER
T-737-8544 | PS5-94-OB-7083C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone I | 8 | On hold |  | 5 | NOVEMBER
T-088-8545 | PS5-14-OB-3559D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-10-22 | PS5-05-02 | PS5 - Milestone F | 5 | Closed | 37 | 38 | OCTOBER
T-638-8546 | PS5-93-IK-8600B | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone F | 5 | To be completed |  | 6 | NOVEMBER
T-325-8547 | PS5-22-IK-5933A | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-12-17 | PS5-60-10 | PS5 - Milestone I | 8 | Closed | 15 | 6 | DECEMBER
T-226-8548 | PS5-23-UR-2134A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone G | 6 | In progress |  | 4 | OCTOBER
T-850-8549 | PS5-18-UR-6865C | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone E | 4 | To be completed |  | 4 | OCTOBER
T-952-8550 | PS5-75-UR-4534C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-03-20 | PS5-61-01 | PS5 - Milestone F | 5 | Closed | 18 | 28 | MARCH
T-993-8551 | PS5-08-UR-4606A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-07-08 | PS5-07-03 | PS5 - Milestone C | 2 | Closed | 38 | 5 | JULY
T-296-8552 | PS5-44-IK-7259A | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-04-28 | PS5-62-02 | PS5 - Milestone E | 4 | Closed | 8 | 36 | APRIL
T-432-8553 | PS5-07-OB-3136C | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-02-13 | PS5-01-03 | PS5 - Milestone C | 2 | Closed | 7 | 45 | FEBRUARY
T-303-8554 | PS5-48-OB-9315B | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | To be completed |  | 9 | NOVEMBER
T-340-8555 | PS5-79-UR-6675C | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone D | 3 | In progress |  | 36 | NOVEMBER
T-895-8556 | PS5-35-OB-7579B | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone B | 1.1 | In progress |  | 32 | SEPTEMBER
T-681-8557 | PS5-15-IK-2059A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone F | 5 | To be completed |  | 36 | AUGUST
T-354-8558 | PS5-49-IK-5738B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone C | 2 | In progress |  | 12 | AUGUST
T-649-8559 | PS5-08-OB-2067B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone B | 1.1 | To be completed |  | 24 | NOVEMBER
T-513-8560 | PS5-82-OB-1647C | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | On hold |  | 15 | NOVEMBER
T-411-8561 | PS5-06-OB-4113B | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-02-19 | PS5-99-01 | PS5 - Milestone H | 7 | Closed | 23 | 42 | FEBRUARY
T-299-8562 | PS5-75-UR-1170C | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-05-26 | PS5-02-02 | PS5 - Milestone E | 4 | Closed | 21 | 27 | MAY
T-497-8563 | PS5-05-IK-9659A | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-07-07 | PS5-99-03 | PS5 - Milestone H | 7 | Closed | 4 | 11 | JULY
T-841-8564 | PS5-03-OB-9642C | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-05-28 | PS5-61-02 | PS5 - Milestone E | 4 | Closed | 40 | 35 | MAY
T-969-8565 | PS5-04-UR-6661D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone D | 3 | In progress |  | 41 | DECEMBER
T-871-8566 | PS5-80-OB-6076A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-02-06 | PS5-01-02 | PS5 - Milestone C | 2 | Closed | 44 | 43 | FEBRUARY
T-444-8567 | PS5-68-UR-6026A | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone G | 6 | To be completed |  | 24 | DECEMBER
T-953-8568 | PS5-75-IK-6006A | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-04-16 | PS5-06-02 | PS5 - Milestone H | 7 | Closed | 13 | 13 | APRIL
T-651-8569 | PS5-95-OB-7758B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone F | 5 | To be completed |  | 11 | OCTOBER
T-332-8570 | PS5-35-OB-1554D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone B | 1.1 | To be completed |  | 14 | AUGUST
T-039-8571 | PS5-72-UR-4900C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | To be completed |  | 42 | SEPTEMBER
T-696-8572 | PS5-86-OB-7567D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone H | 7 | In progress |  | 22 | DECEMBER
T-714-8573 | PS5-97-UR-4234B | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | To be completed |  | 4 | AUGUST
T-100-8574 | PS5-30-IK-3219C | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-07-26 | PS5-62-01 | PS5 - Milestone E | 4 | Closed | 39 | 21 | JULY
T-181-8575 | PS5-81-UR-3915D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | On hold |  | 15 | AUGUST
T-854-8576 | PS5-77-IK-4905B | CQP04 - Hydrotest | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-02-07 | PS5-04-01 | PS5 - Milestone I | 8 | Closed | 20 | 43 | FEBRUARY
T-517-8577 | PS5-43-OB-1655D | CQM04 - Vessel | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-09-09 | PS5-06-03 | PS5 - Milestone D | 3 | Closed | 47 | 23 | SEPTEMBER
T-432-8578 | PS5-74-UR-1095C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone I | 8 | In progress |  | 6 | OCTOBER
T-602-8579 | PS5-68-UR-9088C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone F | 5 | In progress |  | 32 | SEPTEMBER
T-401-8580 | PS5-37-IK-5087B | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-05-02 | PS5-99-03 | PS5 - Milestone F | 5 | Closed | 46 | 39 | MAY
T-399-8581 | PS5-17-OB-9551A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone A | 1 | To be completed |  | 31 | NOVEMBER
T-186-8582 | PS5-04-OB-1070B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone A | 1 | To be completed |  | 37 | SEPTEMBER
T-784-8583 | PS5-62-IK-9141C | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-06-20 | PS5-11-01 | PS5 - Milestone E | 4 | Closed | 24 | 4 | JUNE
T-241-8584 | PS5-89-IK-6813C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | In progress |  | 27 | OCTOBER
T-030-8585 | PS5-23-UR-4131B | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone E | 4 | On hold |  | 48 | SEPTEMBER
T-316-8586 | PS5-19-OB-5572D | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-10-02 | PS5-11-01 | PS5 - Milestone F | 5 | Closed | 10 | 19 | OCTOBER
T-363-8587 | PS5-56-UR-7038A | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone G | 6 | On hold |  | 11 | OCTOBER
T-369-8588 | PS5-27-OB-3319D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | To be completed |  | 22 | NOVEMBER
T-724-8589 | PS5-44-UR-3577C | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-04-18 | PS5-10-01 | PS5 - Milestone A | 1 | Closed | 38 | 23 | APRIL
T-222-8590 | PS5-14-OB-1764A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-12-24 | PS5-11-02 | PS5 - Milestone D | 3 | Closed | 46 | 32 | DECEMBER
T-179-8591 | PS5-78-IK-7145A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | To be completed |  | 25 | DECEMBER
T-919-8592 | PS5-92-OB-3898C | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-08-20 | PS5-11-02 | PS5 - Milestone C | 2 | Closed | 47 | 12 | AUGUST
T-324-8593 | PS5-61-OB-4417B | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-11-03 | PS5-01-09 | PS5 - Milestone F | 5 | Closed | 15 | 9 | NOVEMBER
T-479-8594 | PS5-38-OB-4714B | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-02-11 | PS5-61-02 | PS5 - Milestone I | 8 | Closed | 40 | 45 | FEBRUARY
T-746-8595 | PS5-55-OB-8209A | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-07-14 | PS5-05-01 | PS5 - Milestone I | 8 | Closed | 47 | 16 | JULY
T-017-8596 | PS5-09-UR-1997C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-01-26 | PS5-60-07 | PS5 - Milestone H | 7 | Closed | 47 | 5 | JANUARY
T-613-8597 | PS5-05-IK-7516B | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone I | 8 | In progress |  | 14 | NOVEMBER
T-202-8598 | PS5-51-OB-6675A | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | In progress |  | 6 | AUGUST
T-019-8599 | PS5-30-IK-3956A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone C | 2 | To be completed |  | 44 | SEPTEMBER
T-814-8600 | PS5-88-UR-5523D | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone C | 2 | In progress |  | 10 | OCTOBER
T-039-8601 | PS5-72-OB-4929C | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone A | 1 | To be completed |  | 7 | OCTOBER
T-729-8602 | PS5-89-UR-6808B | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone A | 1 | In progress |  | 21 | NOVEMBER
T-282-8603 | PS5-80-OB-8207B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-04-13 | PS5-01-02 | PS5 - Milestone C | 2 | Closed | 47 | 4 | APRIL
T-800-8604 | PS5-66-OB-6950B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone D | 3 | In progress |  | 29 | NOVEMBER
T-388-8605 | PS5-58-UR-3266D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-12-20 | PS5-82-02 | PS5 - Milestone A | 1 | Closed | 12 | 23 | DECEMBER
T-203-8606 | PS5-95-IK-6618B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone I | 8 | To be completed |  | 31 | SEPTEMBER
T-469-8607 | PS5-58-OB-6209C | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone C | 2 | In progress |  | 26 | NOVEMBER
T-175-8608 | PS5-39-OB-3693A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone I | 8 | In progress |  | 46 | NOVEMBER
T-324-8609 | PS5-24-UR-6960B | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone E | 4 | On hold |  | 22 | AUGUST
T-567-8610 | PS5-35-UR-9629B | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-12-23 | PS5-04-01 | PS5 - Milestone D | 3 | Closed | 27 | 38 | DECEMBER
T-674-8611 | PS5-07-UR-9527D | CQP05 - Insulation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-10-14 | PS5-82-01 | PS5 - Milestone H | 7 | Closed | 7 | 32 | OCTOBER
T-692-8612 | PS5-47-UR-1045B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone B | 1.1 | To be completed |  | 11 | NOVEMBER
T-757-8613 | PS5-33-UR-6509B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone I | 8 | In progress |  | 39 | SEPTEMBER
T-378-8614 | PS5-41-OB-4217C | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-12-11 | PS5-01-01 | PS5 - Milestone A | 1 | Closed | 46 | 42 | DECEMBER
T-203-8615 | PS5-71-IK-3092D | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-09-16 | PS5-63-04 | PS5 - Milestone D | 3 | Closed | 42 | 39 | SEPTEMBER
T-588-8616 | PS5-56-IK-6975B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-04-15 | PS5-12-01 | PS5 - Milestone H | 7 | Closed | 43 | 46 | APRIL
T-431-8617 | PS5-55-UR-8285D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone C | 2 | On hold |  | 18 | SEPTEMBER
T-835-8618 | PS5-38-OB-6488D | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-12-13 | PS5-10-06 | PS5 - Milestone I | 8 | Closed | 20 | 27 | DECEMBER
T-659-8619 | PS5-96-IK-9691C | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-06-05 | PS5-82-02 | PS5 - Milestone C | 2 | Closed | 22 | 31 | JUNE
T-580-8620 | PS5-59-OB-9584D | CQM02 - Compressor | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone F | 5 | In progress |  | 42 | DECEMBER
T-481-8621 | PS5-41-OB-9852A | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-02-24 | PS5-60-10 | PS5 - Milestone I | 8 | Closed | 10 | 39 | FEBRUARY
T-031-8622 | PS5-94-OB-3071C | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone A | 1 | In progress |  | 26 | OCTOBER
T-099-8623 | PS5-84-OB-5622D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-07-18 | PS5-04-03 | PS5 - Milestone E | 4 | Closed | 30 | 32 | JULY
T-812-8624 | PS5-22-OB-4346D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone C | 2 | To be completed |  | 10 | OCTOBER
T-264-8625 | PS5-61-UR-6623A | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-08-06 | PS5-01-06 | PS5 - Milestone B | 1.1 | Closed | 35 | 32 | AUGUST
T-054-8626 | PS5-82-OB-5894C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-01-13 | PS5-82-02 | PS5 - Milestone F | 5 | Closed | 44 | 24 | JANUARY
T-838-8627 | PS5-36-OB-5302D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-03-24 | PS5-04-02 | PS5 - Milestone E | 4 | Closed | 14 | 30 | MARCH
T-356-8628 | PS5-23-OB-9313B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone E | 4 | On hold |  | 24 | OCTOBER
T-509-8629 | PS5-55-UR-4259B | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-09-09 | PS5-62-02 | PS5 - Milestone E | 4 | Closed | 21 | 22 | SEPTEMBER
T-839-8630 | PS5-34-IK-5050D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-06-27 | PS5-01-09 | PS5 - Milestone C | 2 | Closed | 22 | 34 | JUNE
T-265-8631 | PS5-41-OB-7954C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone A | 1 | In progress |  | 15 | OCTOBER
T-576-8632 | PS5-33-UR-4045B | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone B | 1.1 | In progress |  | 27 | SEPTEMBER
T-098-8633 | PS5-74-OB-8516C | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone B | 1.1 | In progress |  | 11 | AUGUST
T-312-8634 | PS5-87-UR-7226D | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-06-11 | PS5-10-06 | PS5 - Milestone F | 5 | Closed | 16 | 30 | JUNE
T-829-8635 | PS5-60-OB-9340C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone B | 1.1 | In progress |  | 20 | OCTOBER
T-853-8636 | PS5-42-OB-9603B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone D | 3 | In progress |  | 27 | DECEMBER
T-425-8637 | PS5-65-OB-6990A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-01-01 | PS5-01-06 | PS5 - Milestone E | 4 | Closed | 15 | 27 | JANUARY
T-817-8638 | PS5-62-OB-4514A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-03-10 | PS5-11-03 | PS5 - Milestone A | 1 | Closed | 41 | 48 | MARCH
T-134-8639 | PS5-83-OB-9765D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-06-12 | PS5-09-03 | PS5 - Milestone B | 1.1 | Closed | 5 | 43 | JUNE
T-266-8640 | PS5-43-UR-4148C | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-06-02 | PS5-13-01 | PS5 - Milestone D | 3 | Closed | 40 | 41 | JUNE
T-015-8641 | PS5-96-OB-1196A | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-12-03 | PS5-09-03 | PS5 - Milestone C | 2 | Closed | 40 | 29 | DECEMBER
T-706-8642 | PS5-81-UR-7493C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-08-05 | PS5-01-07 | PS5 - Milestone F | 5 | Closed | 46 | 24 | AUGUST
T-920-8643 | PS5-10-IK-8445C | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-11-26 | PS5-01-05 | PS5 - Milestone E | 4 | Closed | 23 | 31 | NOVEMBER
T-450-8644 | PS5-33-OB-4186A | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | To be completed |  | 5 | DECEMBER
T-090-8645 | PS5-29-IK-3098A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-07-09 | PS5-09-01 | PS5 - Milestone H | 7 | Closed | 44 | 11 | JULY
T-772-8646 | PS5-91-UR-8543C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-03-21 | PS5-01-01 | PS5 - Milestone A | 1 | Closed | 40 | 27 | MARCH
T-692-8647 | PS5-32-OB-2660C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-01-19 | PS5-01-09 | PS5 - Milestone G | 6 | Closed | 43 | 43 | JANUARY
T-032-8648 | PS5-63-OB-8899D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | In progress |  | 43 | SEPTEMBER
T-846-8649 | PS5-11-OB-5202A | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-04-16 | PS5-01-06 | PS5 - Milestone C | 2 | Closed | 16 | 21 | APRIL
T-187-8650 | PS5-55-UR-2950A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone I | 8 | To be completed |  | 47 | SEPTEMBER
T-666-8651 | PS5-95-IK-8576C | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone A | 1 | To be completed |  | 44 | AUGUST
T-570-8652 | PS5-10-OB-9823C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone C | 2 | To be completed |  | 42 | OCTOBER
T-763-8653 | PS5-34-UR-6414A | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | To be completed |  | 30 | SEPTEMBER
T-538-8654 | PS5-97-IK-5838C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone H | 7 | On hold |  | 9 | NOVEMBER
T-865-8655 | PS5-97-OB-3776B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-03-14 | PS5-01-09 | PS5 - Milestone E | 4 | Closed | 41 | 35 | MARCH
T-839-8656 | PS5-74-OB-6685D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | In progress |  | 14 | AUGUST
T-519-8657 | PS5-12-OB-5686C | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-05-25 | PS5-08-02 | PS5 - Milestone F | 5 | Closed | 14 | 39 | MAY
T-194-8658 | PS5-23-UR-4892B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone H | 7 | To be completed |  | 45 | AUGUST
T-827-8659 | PS5-06-OB-3949B | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-02-11 | PS5-04-03 | PS5 - Milestone F | 5 | Closed | 27 | 12 | FEBRUARY
T-698-8660 | PS5-77-IK-7975A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | On hold |  | 40 | DECEMBER
T-186-8661 | PS5-37-IK-1193B | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-09-14 | PS5-04-03 | PS5 - Milestone A | 1 | Closed | 24 | 20 | SEPTEMBER
T-750-8662 | PS5-14-OB-6053B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-11-25 | PS5-02-01 | PS5 - Milestone G | 6 | Closed | 34 | 7 | NOVEMBER
T-221-8663 | PS5-04-OB-7418D | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-02-25 | PS5-10-05 | PS5 - Milestone A | 1 | Closed | 34 | 43 | FEBRUARY
T-630-8664 | PS5-01-IK-2456B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone D | 3 | To be completed |  | 5 | DECEMBER
T-964-8665 | PS5-87-UR-8132B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-02-12 | PS5-12-01 | PS5 - Milestone F | 5 | Closed | 12 | 25 | FEBRUARY
T-270-8666 | PS5-40-OB-2946A | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-05-07 | PS5-61-02 | PS5 - Milestone G | 6 | Closed | 44 | 39 | MAY
T-960-8667 | PS5-87-IK-8726C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-11-26 | PS5-60-10 | PS5 - Milestone D | 3 | Closed | 32 | 9 | NOVEMBER
T-275-8668 | PS5-30-IK-1579D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-10-06 | PS5-01-02 | PS5 - Milestone A | 1 | Closed | 4 | 18 | OCTOBER
T-498-8669 | PS5-28-IK-6772A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone D | 3 | To be completed |  | 12 | AUGUST
T-732-8670 | PS5-73-IK-9760B | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone F | 5 | In progress |  | 30 | NOVEMBER
T-741-8671 | PS5-62-IK-7085C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-11-28 | PS5-07-01 | PS5 - Milestone D | 3 | Closed | 25 | 28 | NOVEMBER
T-189-8672 | PS5-74-OB-5732C | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-07-28 | PS5-02-02 | PS5 - Milestone B | 1.1 | Closed | 33 | 37 | JULY
T-625-8673 | PS5-86-OB-2227C | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-02-17 | PS5-07-02 | PS5 - Milestone H | 7 | Closed | 9 | 24 | FEBRUARY
T-098-8674 | PS5-57-UR-5085A | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone E | 4 | In progress |  | 46 | NOVEMBER
T-936-8675 | PS5-04-UR-2417D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone D | 3 | To be completed |  | 48 | DECEMBER
T-570-8676 | PS5-42-OB-8242A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone B | 1.1 | To be completed |  | 5 | AUGUST
T-507-8677 | PS5-69-OB-2704C | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-10-04 | PS5-09-01 | PS5 - Milestone C | 2 | Closed | 17 | 14 | OCTOBER
T-375-8678 | PS5-01-UR-9244C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone H | 7 | To be completed |  | 14 | SEPTEMBER
T-866-8679 | PS5-15-OB-7482D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone E | 4 | To be completed |  | 6 | NOVEMBER
T-762-8680 | PS5-81-UR-1000B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone G | 6 | In progress |  | 22 | AUGUST
T-128-8681 | PS5-87-OB-5839A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone I | 8 | To be completed |  | 41 | OCTOBER
T-358-8682 | PS5-54-UR-4118C | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | In progress |  | 17 | AUGUST
T-708-8683 | PS5-16-IK-1937B | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-09-27 | PS5-05-02 | PS5 - Milestone G | 6 | Closed | 16 | 25 | SEPTEMBER
T-490-8684 | PS5-16-IK-5311C | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone A | 1 | To be completed |  | 19 | SEPTEMBER
T-872-8685 | PS5-43-OB-1465B | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-03-18 | PS5-02-02 | PS5 - Milestone G | 6 | Closed | 33 | 11 | MARCH
T-110-8686 | PS5-62-UR-1464B | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-07-28 | PS5-05-01 | PS5 - Milestone H | 7 | Closed | 6 | 5 | JULY
T-792-8687 | PS5-72-OB-6161B | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone H | 7 | To be completed |  | 37 | DECEMBER
T-095-8688 | PS5-19-IK-1470A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-12-04 | PS5-05-03 | PS5 - Milestone C | 2 | Closed | 25 | 15 | DECEMBER
T-526-8689 | PS5-89-OB-5956A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-12-09 | PS5-09-02 | PS5 - Milestone I | 8 | Closed | 11 | 41 | DECEMBER
T-064-8690 | PS5-84-UR-9827A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-09-18 | PS5-09-03 | PS5 - Milestone G | 6 | Closed | 17 | 46 | SEPTEMBER
T-436-8691 | PS5-87-OB-1633D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-12-08 | PS5-06-01 | PS5 - Milestone F | 5 | Closed | 21 | 29 | DECEMBER
T-531-8692 | PS5-76-OB-7130B | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone B | 1.1 | To be completed |  | 43 | NOVEMBER
T-375-8693 | PS5-85-UR-2087B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-06-27 | PS5-08-01 | PS5 - Milestone E | 4 | Closed | 4 | 38 | JUNE
T-958-8694 | PS5-39-IK-1718B | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-01-13 | PS5-01-08 | PS5 - Milestone E | 4 | Closed | 6 | 19 | JANUARY
T-869-8695 | PS5-18-UR-2264A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone I | 8 | On hold |  | 46 | OCTOBER
T-049-8696 | PS5-22-OB-3554B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-03-14 | PS5-10-04 | PS5 - Milestone F | 5 | Closed | 25 | 24 | MARCH
T-106-8697 | PS5-70-OB-7107D | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-12-06 | PS5-12-02 | PS5 - Milestone I | 8 | Closed | 11 | 16 | DECEMBER
T-359-8698 | PS5-08-IK-1650D | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-26 | PS5-60-07 | PS5 - Milestone B | 1.1 | Closed | 43 | 20 | JUNE
T-785-8699 | PS5-02-IK-8200D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone G | 6 | To be completed |  | 40 | OCTOBER
T-936-8700 | PS5-26-OB-5586D | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-28 | PS5-60-04 | PS5 - Milestone H | 7 | Closed | 37 | 14 | FEBRUARY
T-753-8701 | PS5-90-UR-8900C | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone G | 6 | To be completed |  | 19 | NOVEMBER
T-463-8702 | PS5-17-OB-2125B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-03-22 | PS5-62-01 | PS5 - Milestone B | 1.1 | Closed | 33 | 21 | MARCH
T-751-8703 | PS5-12-OB-6465B | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone F | 5 | To be completed |  | 47 | NOVEMBER
T-739-8704 | PS5-13-OB-6065A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-07-06 | PS5-10-03 | PS5 - Milestone C | 2 | Closed | 35 | 37 | JULY
T-967-8705 | PS5-05-IK-6429B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-07-08 | PS5-10-06 | PS5 - Milestone D | 3 | Closed | 45 | 6 | JULY
T-359-8706 | PS5-21-IK-7990A | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone H | 7 | To be completed |  | 46 | OCTOBER
T-816-8707 | PS5-06-OB-1373C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-02-05 | PS5-61-02 | PS5 - Milestone F | 5 | Closed | 25 | 10 | FEBRUARY
T-411-8708 | PS5-10-IK-8447D | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-09-14 | PS5-61-01 | PS5 - Milestone H | 7 | Closed | 48 | 20 | SEPTEMBER
T-688-8709 | PS5-42-OB-2097D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone I | 8 | To be completed |  | 43 | DECEMBER
T-092-8710 | PS5-11-OB-5853B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone H | 7 | In progress |  | 11 | OCTOBER
T-525-8711 | PS5-02-OB-7763A | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone G | 6 | To be completed |  | 24 | NOVEMBER
T-933-8712 | PS5-37-OB-9929A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone D | 3 | In progress |  | 5 | OCTOBER
T-260-8713 | PS5-48-OB-3359C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | To be completed |  | 23 | SEPTEMBER
T-569-8714 | PS5-80-UR-4689D | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-08-06 | PS5-01-07 | PS5 - Milestone F | 5 | Closed | 41 | 6 | AUGUST
T-940-8715 | PS5-52-IK-3099A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-02-24 | PS5-05-03 | PS5 - Milestone I | 8 | Closed | 23 | 40 | FEBRUARY
T-427-8716 | PS5-06-OB-1839D | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone C | 2 | To be completed |  | 22 | AUGUST
T-155-8717 | PS5-37-OB-3310C | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-03-16 | PS5-63-04 | PS5 - Milestone F | 5 | Closed | 4 | 22 | MARCH
T-618-8718 | PS5-39-IK-1653C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone E | 4 | To be completed |  | 21 | AUGUST
T-546-8719 | PS5-55-IK-7744D | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-04-15 | PS5-04-02 | PS5 - Milestone D | 3 | Closed | 25 | 24 | APRIL
T-437-8720 | PS5-06-UR-5960D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone I | 8 | On hold |  | 43 | SEPTEMBER
T-727-8721 | PS5-86-OB-8860D | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone H | 7 | In progress |  | 34 | AUGUST
T-869-8722 | PS5-60-OB-3648D | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-09-25 | PS5-09-04 | PS5 - Milestone C | 2 | Closed | 30 | 32 | SEPTEMBER
T-025-8723 | PS5-38-IK-8373B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-04-19 | PS5-07-01 | PS5 - Milestone E | 4 | Closed | 19 | 25 | APRIL
T-997-8724 | PS5-73-OB-3042C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-07-10 | PS5-06-03 | PS5 - Milestone A | 1 | Closed | 33 | 9 | JULY
T-577-8725 | PS5-35-UR-5487C | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-09-14 | PS5-01-03 | PS5 - Milestone D | 3 | Closed | 23 | 13 | SEPTEMBER
T-550-8726 | PS5-52-OB-1026D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone D | 3 | To be completed |  | 21 | SEPTEMBER
T-344-8727 | PS5-63-UR-6931D | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone D | 3 | To be completed |  | 30 | AUGUST
T-657-8728 | PS5-70-IK-1213D | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone I | 8 | On hold |  | 45 | NOVEMBER
T-195-8729 | PS5-72-OB-8477B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | On hold |  | 35 | OCTOBER
T-422-8730 | PS5-63-UR-9359C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone G | 6 | In progress |  | 41 | DECEMBER
T-728-8731 | PS5-61-IK-1024D | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone B | 1.1 | On hold |  | 4 | DECEMBER
T-886-8732 | PS5-25-IK-8786D | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone E | 4 | In progress |  | 48 | NOVEMBER
T-749-8733 | PS5-01-OB-9320D | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-03-26 | PS5-63-04 | PS5 - Milestone D | 3 | Closed | 7 | 26 | MARCH
T-526-8734 | PS5-39-UR-3225A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-09-02 | PS5-62-02 | PS5 - Milestone G | 6 | Closed | 19 | 36 | SEPTEMBER
T-270-8735 | PS5-02-UR-1813B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-02-07 | PS5-99-03 | PS5 - Milestone H | 7 | Closed | 47 | 10 | FEBRUARY
T-815-8736 | PS5-47-OB-8949C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone I | 8 | To be completed |  | 33 | AUGUST
T-959-8737 | PS5-99-UR-4849D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone G | 6 | To be completed |  | 48 | NOVEMBER
T-330-8738 | PS5-14-OB-1107D | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-05-19 | PS5-10-03 | PS5 - Milestone E | 4 | Closed | 40 | 44 | MAY
T-200-8739 | PS5-74-UR-5397D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-11-11 | PS5-11-02 | PS5 - Milestone G | 6 | Closed | 21 | 25 | NOVEMBER
T-852-8740 | PS5-82-UR-7208C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone C | 2 | To be completed |  | 22 | AUGUST
T-667-8741 | PS5-71-IK-2040C | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-01-24 | PS5-11-02 | PS5 - Milestone H | 7 | Closed | 47 | 14 | JANUARY
T-822-8742 | PS5-35-UR-7943D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-04-07 | PS5-11-01 | PS5 - Milestone F | 5 | Closed | 22 | 34 | APRIL
T-977-8743 | PS5-31-IK-8545A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone B | 1.1 | To be completed |  | 10 | NOVEMBER
T-948-8744 | PS5-71-UR-7761C | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-04-14 | PS5-02-01 | PS5 - Milestone I | 8 | Closed | 16 | 31 | APRIL
T-785-8745 | PS5-63-OB-7095D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone E | 4 | In progress |  | 14 | DECEMBER
T-005-8746 | PS5-18-OB-2994C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-09-09 | PS5-09-02 | PS5 - Milestone H | 7 | Closed | 19 | 44 | SEPTEMBER
T-102-8747 | PS5-02-OB-1900A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-11-07 | PS5-04-03 | PS5 - Milestone C | 2 | Closed | 26 | 21 | NOVEMBER
T-855-8748 | PS5-56-OB-1381A | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone D | 3 | To be completed |  | 33 | AUGUST
T-053-8749 | PS5-89-UR-2240A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-03-23 | PS5-09-03 | PS5 - Milestone G | 6 | Closed | 29 | 33 | MARCH
T-949-8750 | PS5-88-OB-6760B | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone D | 3 | To be completed |  | 23 | OCTOBER
T-236-8751 | PS5-65-UR-1392A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone H | 7 | To be completed |  | 26 | SEPTEMBER
T-015-8752 | PS5-75-OB-9680A | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-05-04 | PS5-62-01 | PS5 - Milestone E | 4 | Closed | 15 | 33 | MAY
T-199-8753 | PS5-75-IK-3008C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-12-17 | PS5-04-04 | PS5 - Milestone D | 3 | Closed | 6 | 15 | DECEMBER
T-441-8754 | PS5-86-UR-5036A | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone A | 1 | To be completed |  | 21 | AUGUST
T-639-8755 | PS5-77-OB-9035C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-11-16 | PS5-12-02 | PS5 - Milestone I | 8 | Closed | 10 | 19 | NOVEMBER
T-774-8756 | PS5-98-OB-4818D | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone A | 1 | To be completed |  | 32 | NOVEMBER
T-266-8757 | PS5-96-OB-8176C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-10-06 | PS5-01-03 | PS5 - Milestone D | 3 | Closed | 12 | 46 | OCTOBER
T-731-8758 | PS5-19-IK-3819D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-10-28 | PS5-08-01 | PS5 - Milestone F | 5 | Closed | 37 | 19 | OCTOBER
T-022-8759 | PS5-05-UR-2921C | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-07-18 | PS5-05-03 | PS5 - Milestone D | 3 | Closed | 38 | 43 | JULY
T-870-8760 | PS5-33-OB-3056D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone B | 1.1 | On hold |  | 39 | NOVEMBER
T-749-8761 | PS5-77-OB-3792A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone C | 2 | In progress |  | 14 | AUGUST
T-257-8762 | PS5-70-OB-4548B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone D | 3 | To be completed |  | 12 | OCTOBER
T-385-8763 | PS5-99-OB-2415C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-05-10 | PS5-02-03 | PS5 - Milestone E | 4 | Closed | 28 | 12 | MAY
T-719-8764 | PS5-26-UR-3555B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone A | 1 | To be completed |  | 27 | SEPTEMBER
T-437-8765 | PS5-99-OB-5669B | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-12-28 | PS5-60-10 | PS5 - Milestone C | 2 | Closed | 19 | 34 | DECEMBER
T-766-8766 | PS5-90-IK-8758C | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone C | 2 | On hold |  | 9 | OCTOBER
T-996-8767 | PS5-39-IK-9763A | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone D | 3 | On hold |  | 9 | OCTOBER
T-364-8768 | PS5-83-OB-2168D | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone H | 7 | On hold |  | 9 | OCTOBER
T-536-8769 | PS5-49-OB-3013B | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-09-16 | PS5-01-05 | PS5 - Milestone F | 5 | Closed | 7 | 18 | SEPTEMBER
T-613-8770 | PS5-18-OB-2032B | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone F | 5 | In progress |  | 41 | DECEMBER
T-171-8771 | PS5-30-UR-8623B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-06-12 | PS5-06-01 | PS5 - Milestone B | 1.1 | Closed | 9 | 35 | JUNE
T-684-8772 | PS5-19-UR-5770D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone F | 5 | To be completed |  | 10 | SEPTEMBER
T-436-8773 | PS5-61-IK-6397A | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone G | 6 | To be completed |  | 8 | DECEMBER
T-998-8774 | PS5-58-OB-5676B | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone F | 5 | On hold |  | 30 | DECEMBER
T-650-8775 | PS5-95-IK-7842B | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-05-25 | PS5-99-02 | PS5 - Milestone G | 6 | Closed | 42 | 22 | MAY
T-937-8776 | PS5-20-UR-7209A | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone D | 3 | To be completed |  | 43 | OCTOBER
T-355-8777 | PS5-65-UR-4806B | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone B | 1.1 | To be completed |  | 36 | OCTOBER
T-560-8778 | PS5-01-OB-7040C | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone E | 4 | To be completed |  | 30 | SEPTEMBER
T-159-8779 | PS5-93-OB-4748B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone A | 1 | On hold |  | 36 | NOVEMBER
T-837-8780 | PS5-88-UR-5988A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone B | 1.1 | In progress |  | 12 | DECEMBER
T-268-8781 | PS5-09-OB-4950A | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-02-09 | PS5-02-01 | PS5 - Milestone D | 3 | Closed | 33 | 7 | FEBRUARY
T-223-8782 | PS5-13-UR-8755A | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | On hold |  | 46 | DECEMBER
T-058-8783 | PS5-69-OB-6422D | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone H | 7 | In progress |  | 15 | SEPTEMBER
T-013-8784 | PS5-55-OB-4186A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone H | 7 | In progress |  | 45 | DECEMBER
T-974-8785 | PS5-18-OB-1105B | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-11-22 | PS5-08-01 | PS5 - Milestone B | 1.1 | Closed | 48 | 40 | NOVEMBER
T-047-8786 | PS5-48-UR-4260B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | To be completed |  | 7 | NOVEMBER
T-105-8787 | PS5-64-UR-6707C | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone E | 4 | In progress |  | 35 | DECEMBER
T-048-8788 | PS5-18-IK-3147C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-09-25 | PS5-82-01 | PS5 - Milestone D | 3 | Closed | 29 | 14 | SEPTEMBER
T-467-8789 | PS5-75-UR-5947B | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-09-23 | PS5-63-04 | PS5 - Milestone C | 2 | Closed | 6 | 40 | SEPTEMBER
T-309-8790 | PS5-52-IK-5548C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone F | 5 | To be completed |  | 17 | OCTOBER
T-615-8791 | PS5-85-OB-3827C | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone G | 6 | To be completed |  | 25 | NOVEMBER
T-714-8792 | PS5-28-OB-5497A | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone C | 2 | In progress |  | 32 | AUGUST
T-297-8793 | PS5-89-IK-6775A | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-08-16 | PS5-02-02 | PS5 - Milestone D | 3 | Closed | 25 | 16 | AUGUST
T-246-8794 | PS5-67-OB-9212D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-04-21 | PS5-10-03 | PS5 - Milestone D | 3 | Closed | 16 | 27 | APRIL
T-077-8795 | PS5-41-IK-3729D | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-08-12 | PS5-01-07 | PS5 - Milestone H | 7 | Closed | 39 | 12 | AUGUST
T-700-8796 | PS5-72-IK-6153C | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone H | 7 | To be completed |  | 9 | OCTOBER
T-822-8797 | PS5-23-OB-4112D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone I | 8 | To be completed |  | 18 | OCTOBER
T-729-8798 | PS5-77-OB-3137D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone D | 3 | In progress |  | 14 | NOVEMBER
T-420-8799 | PS5-75-IK-5472C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | On hold |  | 24 | AUGUST
T-056-8800 | PS5-43-OB-8945A | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone E | 4 | To be completed |  | 24 | SEPTEMBER
T-296-8801 | PS5-38-OB-5029D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-06-03 | PS5-61-07 | PS5 - Milestone H | 7 | Closed | 26 | 44 | JUNE
T-929-8802 | PS5-42-OB-7258B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-08-12 | PS5-01-07 | PS5 - Milestone B | 1.1 | Closed | 42 | 8 | AUGUST
T-370-8803 | PS5-64-OB-2581A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone H | 7 | To be completed |  | 27 | OCTOBER
T-304-8804 | PS5-08-OB-9501C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-01-20 | PS5-11-03 | PS5 - Milestone D | 3 | Closed | 26 | 19 | JANUARY
T-137-8805 | PS5-04-OB-1430B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | To be completed |  | 23 | AUGUST
T-605-8806 | PS5-52-OB-4784B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-10-07 | PS5-09-02 | PS5 - Milestone G | 6 | Closed | 20 | 9 | OCTOBER
T-372-8807 | PS5-88-OB-4569A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-02-27 | PS5-61-07 | PS5 - Milestone D | 3 | Closed | 33 | 47 | FEBRUARY
T-081-8808 | PS5-10-OB-8569D | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-10-19 | PS5-09-03 | PS5 - Milestone H | 7 | Closed | 11 | 5 | OCTOBER
T-336-8809 | PS5-51-UR-3359C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | In progress |  | 14 | OCTOBER
T-550-8810 | PS5-03-OB-8050D | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-07-26 | PS5-05-03 | PS5 - Milestone A | 1 | Closed | 35 | 6 | JULY
T-098-8811 | PS5-17-OB-1428A | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone F | 5 | To be completed |  | 18 | DECEMBER
T-433-8812 | PS5-89-UR-8977C | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone I | 8 | In progress |  | 15 | AUGUST
T-921-8813 | PS5-31-OB-8155B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-02-26 | PS5-09-03 | PS5 - Milestone E | 4 | Closed | 19 | 30 | FEBRUARY
T-687-8814 | PS5-77-IK-6122C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-06-11 | PS5-07-01 | PS5 - Milestone G | 6 | Closed | 6 | 31 | JUNE
T-850-8815 | PS5-82-UR-6424B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-01-02 | PS5-11-01 | PS5 - Milestone B | 1.1 | Closed | 47 | 12 | JANUARY
T-289-8816 | PS5-35-OB-6271D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | To be completed |  | 9 | DECEMBER
T-498-8817 | PS5-50-IK-6722B | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone E | 4 | To be completed |  | 13 | OCTOBER
T-891-8818 | PS5-57-OB-6804B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | In progress |  | 39 | AUGUST
T-317-8819 | PS5-16-IK-7293B | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-08-12 | PS5-10-03 | PS5 - Milestone E | 4 | Closed | 21 | 47 | AUGUST
T-665-8820 | PS5-43-IK-8028A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone H | 7 | To be completed |  | 8 | DECEMBER
T-215-8821 | PS5-36-OB-3587B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone F | 5 | In progress |  | 34 | DECEMBER
T-084-8822 | PS5-23-OB-2231A | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone E | 4 | To be completed |  | 23 | NOVEMBER
T-816-8823 | PS5-33-OB-4300C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-12-15 | PS5-01-06 | PS5 - Milestone A | 1 | Closed | 35 | 27 | DECEMBER
T-454-8824 | PS5-65-OB-3545C | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | To be completed |  | 48 | OCTOBER
T-956-8825 | PS5-94-UR-8048B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-06-04 | PS5-10-02 | PS5 - Milestone E | 4 | Closed | 26 | 26 | JUNE
T-879-8826 | PS5-53-IK-7941C | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone A | 1 | To be completed |  | 14 | DECEMBER
T-204-8827 | PS5-10-UR-8542A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone H | 7 | To be completed |  | 29 | AUGUST
T-725-8828 | PS5-13-IK-7907C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-03-03 | PS5-99-02 | PS5 - Milestone C | 2 | Closed | 28 | 30 | MARCH
T-188-8829 | PS5-77-OB-3634B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-07-13 | PS5-11-03 | PS5 - Milestone I | 8 | Closed | 10 | 17 | JULY
T-170-8830 | PS5-59-OB-2178B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-03-10 | PS5-04-03 | PS5 - Milestone B | 1.1 | Closed | 44 | 18 | MARCH
T-003-8831 | PS5-39-OB-5158C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-03-08 | PS5-04-04 | PS5 - Milestone F | 5 | Closed | 35 | 4 | MARCH
T-502-8832 | PS5-13-IK-2930C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-07-14 | PS5-05-01 | PS5 - Milestone A | 1 | Closed | 26 | 35 | JULY
T-981-8833 | PS5-08-IK-8116A | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | In progress |  | 38 | SEPTEMBER
T-049-8834 | PS5-47-UR-5439C | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | To be completed |  | 43 | SEPTEMBER
T-203-8835 | PS5-30-UR-1903A | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone D | 3 | To be completed |  | 18 | DECEMBER
T-601-8836 | PS5-94-OB-9115B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-01-26 | PS5-60-01 | PS5 - Milestone I | 8 | Closed | 26 | 36 | JANUARY
T-066-8837 | PS5-72-OB-8393D | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone I | 8 | To be completed |  | 26 | NOVEMBER
T-354-8838 | PS5-63-IK-1552D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone F | 5 | To be completed |  | 23 | OCTOBER
T-082-8839 | PS5-40-OB-3882B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone F | 5 | In progress |  | 4 | NOVEMBER
T-211-8840 | PS5-07-OB-4541B | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone A | 1 | To be completed |  | 6 | OCTOBER
T-526-8841 | PS5-91-UR-3508B | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone D | 3 | In progress |  | 47 | SEPTEMBER
T-141-8842 | PS5-25-OB-4914B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | To be completed |  | 40 | OCTOBER
T-553-8843 | PS5-20-OB-9348C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone D | 3 | On hold |  | 38 | DECEMBER
T-369-8844 | PS5-33-UR-1923C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-01-20 | PS5-10-02 | PS5 - Milestone H | 7 | Closed | 22 | 34 | JANUARY
T-332-8845 | PS5-93-UR-2479B | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-05-06 | PS5-07-02 | PS5 - Milestone H | 7 | Closed | 18 | 43 | MAY
T-971-8846 | PS5-33-OB-4004A | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-09-20 | PS5-09-01 | PS5 - Milestone A | 1 | Closed | 31 | 7 | SEPTEMBER
T-592-8847 | PS5-74-IK-7637C | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-09-20 | PS5-07-02 | PS5 - Milestone H | 7 | Closed | 19 | 18 | SEPTEMBER
T-409-8848 | PS5-85-IK-7770A | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone A | 1 | To be completed |  | 16 | AUGUST
T-835-8849 | PS5-21-OB-8606D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-10-23 | PS5-82-01 | PS5 - Milestone G | 6 | Closed | 46 | 28 | OCTOBER
T-930-8850 | PS5-72-OB-7705C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone C | 2 | To be completed |  | 16 | NOVEMBER
T-562-8851 | PS5-67-IK-8293A | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone C | 2 | In progress |  | 16 | DECEMBER
T-770-8852 | PS5-58-IK-3931B | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-04-16 | PS5-07-02 | PS5 - Milestone B | 1.1 | Closed | 34 | 20 | APRIL
T-963-8853 | PS5-13-IK-2230C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-09-21 | PS5-63-01 | PS5 - Milestone F | 5 | Closed | 23 | 24 | SEPTEMBER
T-475-8854 | PS5-10-IK-3063A | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-08-21 | PS5-03-23 | PS5 - Milestone A | 1 | Closed | 39 | 36 | AUGUST
T-408-8855 | PS5-06-OB-3825D | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone B | 1.1 | To be completed |  | 33 | AUGUST
T-654-8856 | PS5-11-OB-4305B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | To be completed |  | 25 | SEPTEMBER
T-311-8857 | PS5-35-UR-3485C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-08-10 | PS5-01-08 | PS5 - Milestone F | 5 | Closed | 25 | 43 | AUGUST
T-072-8858 | PS5-71-UR-9407C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-11-08 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 37 | 45 | NOVEMBER
T-111-8859 | PS5-31-UR-8610C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-12-22 | PS5-02-03 | PS5 - Milestone B | 1.1 | Closed | 46 | 7 | DECEMBER
T-350-8860 | PS5-77-IK-9796D | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone C | 2 | To be completed |  | 11 | OCTOBER
T-790-8861 | PS5-43-IK-4893C | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | To be completed |  | 33 | DECEMBER
T-302-8862 | PS5-24-OB-2481D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | To be completed |  | 43 | OCTOBER
T-203-8863 | PS5-70-UR-6109D | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | In progress |  | 48 | NOVEMBER
T-398-8864 | PS5-75-OB-6279A | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone C | 2 | In progress |  | 26 | SEPTEMBER
T-069-8865 | PS5-60-OB-4791A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone F | 5 | In progress |  | 24 | NOVEMBER
T-335-8866 | PS5-45-UR-5310A | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-10-01 | PS5-08-01 | PS5 - Milestone D | 3 | Closed | 34 | 33 | OCTOBER
T-249-8867 | PS5-89-IK-1888A | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone B | 1.1 | In progress |  | 43 | NOVEMBER
T-652-8868 | PS5-08-OB-3143A | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone A | 1 | In progress |  | 44 | SEPTEMBER
T-889-8869 | PS5-90-UR-4824A | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone H | 7 | To be completed |  | 27 | DECEMBER
T-493-8870 | PS5-86-IK-8634D | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone B | 1.1 | To be completed |  | 47 | OCTOBER
T-258-8871 | PS5-20-OB-9526A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | To be completed |  | 13 | AUGUST
T-847-8872 | PS5-55-OB-6843A | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone F | 5 | To be completed |  | 45 | NOVEMBER
T-447-8873 | PS5-01-UR-9402C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone F | 5 | To be completed |  | 16 | OCTOBER
T-246-8874 | PS5-21-OB-2779A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-10-03 | PS5-61-02 | PS5 - Milestone G | 6 | Closed | 36 | 15 | OCTOBER
T-010-8875 | PS5-01-UR-2929A | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | On hold |  | 21 | OCTOBER
T-050-8876 | PS5-23-IK-1193C | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone I | 8 | In progress |  | 13 | DECEMBER
T-998-8877 | PS5-35-OB-3425A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone G | 6 | To be completed |  | 34 | OCTOBER
T-521-8878 | PS5-08-OB-2087C | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | In progress |  | 46 | NOVEMBER
T-250-8879 | PS5-76-IK-2316C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | To be completed |  | 17 | OCTOBER
T-477-8880 | PS5-20-OB-7578B | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone B | 1.1 | To be completed |  | 17 | DECEMBER
T-897-8881 | PS5-51-OB-8247C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | In progress |  | 29 | SEPTEMBER
T-693-8882 | PS5-45-UR-8663B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-06-01 | PS5-01-09 | PS5 - Milestone A | 1 | Closed | 17 | 37 | JUNE
T-226-8883 | PS5-41-UR-4417A | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | In progress |  | 45 | AUGUST
T-665-8884 | PS5-22-IK-8290B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-17 | PS5-60-04 | PS5 - Milestone E | 4 | Closed | 37 | 34 | MAY
T-776-8885 | PS5-47-IK-1565C | CQS01 - Fire Protection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone F | 5 | To be completed |  | 48 | SEPTEMBER
T-282-8886 | PS5-71-UR-6732A | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-08-25 | PS5-04-03 | PS5 - Milestone C | 2 | Closed | 16 | 41 | AUGUST
T-802-8887 | PS5-14-OB-1050C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-02-24 | PS5-99-02 | PS5 - Milestone C | 2 | Closed | 17 | 10 | FEBRUARY
T-775-8888 | PS5-08-UR-1787A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone H | 7 | To be completed |  | 11 | NOVEMBER
T-692-8889 | PS5-49-UR-8741C | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-07-26 | PS5-60-10 | PS5 - Milestone F | 5 | Closed | 35 | 36 | JULY
T-163-8890 | PS5-33-IK-7320A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-06-18 | PS5-04-02 | PS5 - Milestone A | 1 | Closed | 45 | 17 | JUNE
T-388-8891 | PS5-91-UR-5631D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-10-03 | PS5-10-05 | PS5 - Milestone H | 7 | Closed | 33 | 21 | OCTOBER
T-417-8892 | PS5-76-IK-9090A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone C | 2 | In progress |  | 25 | DECEMBER
T-706-8893 | PS5-88-OB-4683C | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-05-19 | PS5-13-01 | PS5 - Milestone F | 5 | Closed | 36 | 37 | MAY
T-670-8894 | PS5-87-OB-2016B | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | To be completed |  | 44 | AUGUST
T-832-8895 | PS5-36-UR-6458B | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | In progress |  | 14 | DECEMBER
T-659-8896 | PS5-26-IK-9140D | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | In progress |  | 18 | DECEMBER
T-062-8897 | PS5-17-OB-7985A | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone A | 1 | To be completed |  | 40 | AUGUST
T-831-8898 | PS5-18-OB-1589C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-12-25 | PS5-63-01 | PS5 - Milestone G | 6 | Closed | 8 | 18 | DECEMBER
T-219-8899 | PS5-20-OB-2123C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-06-05 | PS5-07-03 | PS5 - Milestone G | 6 | Closed | 15 | 31 | JUNE
T-111-8900 | PS5-67-OB-7725D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | To be completed |  | 28 | OCTOBER
T-868-8901 | PS5-67-OB-2582B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-01-24 | PS5-10-01 | PS5 - Milestone D | 3 | Closed | 27 | 17 | JANUARY
T-235-8902 | PS5-58-OB-3422B | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-04-08 | PS5-10-03 | PS5 - Milestone B | 1.1 | Closed | 42 | 46 | APRIL
T-213-8903 | PS5-94-OB-4120D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-05-24 | PS5-06-02 | PS5 - Milestone E | 4 | Closed | 21 | 13 | MAY
T-627-8904 | PS5-75-OB-2653D | CQS01 - Fire Protection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-06-28 | PS5-03-01 | PS5 - Milestone G | 6 | Closed | 25 | 44 | JUNE
T-246-8905 | PS5-48-IK-7110B | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone D | 3 | In progress |  | 30 | AUGUST
T-047-8906 | PS5-23-IK-2489D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone C | 2 | In progress |  | 43 | OCTOBER
T-648-8907 | PS5-13-IK-3805B | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone H | 7 | To be completed |  | 25 | OCTOBER
T-873-8908 | PS5-38-OB-3568B | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone B | 1.1 | In progress |  | 9 | NOVEMBER
T-643-8909 | PS5-79-OB-9788A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone A | 1 | To be completed |  | 27 | NOVEMBER
T-322-8910 | PS5-15-OB-6913B | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone B | 1.1 | On hold |  | 32 | OCTOBER
T-860-8911 | PS5-59-OB-4755C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone A | 1 | To be completed |  | 16 | NOVEMBER
T-148-8912 | PS5-37-UR-8878D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-05-11 | PS5-01-01 | PS5 - Milestone A | 1 | Closed | 22 | 4 | MAY
T-270-8913 | PS5-53-OB-6949C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone B | 1.1 | In progress |  | 39 | AUGUST
T-134-8914 | PS5-62-OB-6267D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone B | 1.1 | On hold |  | 14 | SEPTEMBER
T-070-8915 | PS5-64-IK-2159C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-01-04 | PS5-63-01 | PS5 - Milestone H | 7 | Closed | 35 | 31 | JANUARY
T-137-8916 | PS5-34-IK-4047C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | To be completed |  | 27 | SEPTEMBER
T-663-8917 | PS5-95-OB-5366B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone B | 1.1 | In progress |  | 35 | DECEMBER
T-593-8918 | PS5-58-IK-5103B | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone I | 8 | On hold |  | 9 | DECEMBER
T-851-8919 | PS5-71-OB-5126B | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone H | 7 | To be completed |  | 22 | OCTOBER
T-990-8920 | PS5-52-IK-5609B | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone C | 2 | In progress |  | 43 | NOVEMBER
T-910-8921 | PS5-96-IK-2119A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-02-28 | PS5-06-02 | PS5 - Milestone G | 6 | Closed | 20 | 4 | FEBRUARY
T-143-8922 | PS5-01-UR-3961B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-10-26 | PS5-11-01 | PS5 - Milestone H | 7 | Closed | 41 | 6 | OCTOBER
T-193-8923 | PS5-44-OB-6308B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | To be completed |  | 23 | OCTOBER
T-122-8924 | PS5-10-OB-1344B | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-06-22 | PS5-63-01 | PS5 - Milestone E | 4 | Closed | 46 | 21 | JUNE
T-408-8925 | PS5-29-IK-8819C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone D | 3 | To be completed |  | 34 | OCTOBER
T-078-8926 | PS5-72-OB-1280A | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | To be completed |  | 19 | SEPTEMBER
T-817-8927 | PS5-88-UR-1695C | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-07-03 | PS5-02-02 | PS5 - Milestone H | 7 | Closed | 12 | 16 | JULY
T-660-8928 | PS5-49-IK-7446C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-04-02 | PS5-03-01 | PS5 - Milestone H | 7 | Closed | 33 | 6 | APRIL
T-505-8929 | PS5-12-OB-8114A | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone A | 1 | To be completed |  | 31 | DECEMBER
T-201-8930 | PS5-86-OB-4448C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-03-15 | PS5-11-02 | PS5 - Milestone G | 6 | Closed | 38 | 29 | MARCH
T-570-8931 | PS5-33-IK-1119C | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone E | 4 | On hold |  | 18 | NOVEMBER
T-542-8932 | PS5-08-IK-8515A | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone A | 1 | To be completed |  | 10 | NOVEMBER
T-183-8933 | PS5-56-OB-4246A | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone D | 3 | To be completed |  | 41 | OCTOBER
T-007-8934 | PS5-23-UR-3804A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-10-17 | PS5-10-03 | PS5 - Milestone C | 2 | Closed | 14 | 32 | OCTOBER
T-901-8935 | PS5-98-OB-4641B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone C | 2 | To be completed |  | 35 | NOVEMBER
T-036-8936 | PS5-24-IK-3309D | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone C | 2 | In progress |  | 39 | AUGUST
T-898-8937 | PS5-40-OB-9852A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone G | 6 | To be completed |  | 9 | SEPTEMBER
T-956-8938 | PS5-17-OB-6918B | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone F | 5 | In progress |  | 27 | AUGUST
T-197-8939 | PS5-86-OB-6432B | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-04-21 | PS5-10-02 | PS5 - Milestone C | 2 | Closed | 24 | 27 | APRIL
T-858-8940 | PS5-49-IK-3177B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone I | 8 | To be completed |  | 19 | SEPTEMBER
T-475-8941 | PS5-26-OB-1042A | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone G | 6 | In progress |  | 9 | DECEMBER
T-052-8942 | PS5-35-UR-2417B | CQS03 - Deluge System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | In progress |  | 29 | OCTOBER
T-308-8943 | PS5-90-UR-9776C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone D | 3 | To be completed |  | 4 | NOVEMBER
T-810-8944 | PS5-85-UR-3254D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone F | 5 | To be completed |  | 43 | SEPTEMBER
T-848-8945 | PS5-58-UR-6663B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-05-16 | PS5-61-02 | PS5 - Milestone G | 6 | Closed | 22 | 4 | MAY
T-781-8946 | PS5-45-OB-3558C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-05-11 | PS5-12-02 | PS5 - Milestone C | 2 | Closed | 19 | 7 | MAY
T-798-8947 | PS5-83-IK-7646A | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone I | 8 | On hold |  | 17 | OCTOBER
T-839-8948 | PS5-84-UR-8092C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-07-12 | PS5-02-03 | PS5 - Milestone A | 1 | Closed | 48 | 12 | JULY
T-434-8949 | PS5-54-UR-4719C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone D | 3 | To be completed |  | 22 | NOVEMBER
T-376-8950 | PS5-80-OB-8940B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-09-16 | PS5-01-06 | PS5 - Milestone D | 3 | Closed | 12 | 27 | SEPTEMBER
T-313-8951 | PS5-15-UR-2706D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-05-20 | PS5-10-04 | PS5 - Milestone F | 5 | Closed | 12 | 45 | MAY
T-427-8952 | PS5-11-IK-4406D | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-07-09 | PS5-99-02 | PS5 - Milestone B | 1.1 | Closed | 24 | 20 | JULY
T-690-8953 | PS5-49-OB-5062B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-09-17 | PS5-12-02 | PS5 - Milestone B | 1.1 | Closed | 10 | 16 | SEPTEMBER
T-142-8954 | PS5-48-IK-3309D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone D | 3 | To be completed |  | 43 | DECEMBER
T-042-8955 | PS5-49-OB-9027D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | To be completed |  | 10 | DECEMBER
T-466-8956 | PS5-60-IK-5206A | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-07-02 | PS5-08-01 | PS5 - Milestone F | 5 | Closed | 6 | 7 | JULY
T-875-8957 | PS5-77-OB-6628B | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-09-27 | PS5-61-02 | PS5 - Milestone F | 5 | Closed | 32 | 26 | SEPTEMBER
T-236-8958 | PS5-16-UR-8824D | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | To be completed |  | 18 | OCTOBER
T-069-8959 | PS5-41-UR-8681D | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-11-16 | PS5-99-03 | PS5 - Milestone E | 4 | Closed | 33 | 9 | NOVEMBER
T-315-8960 | PS5-86-OB-6395B | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | In progress |  | 31 | SEPTEMBER
T-774-8961 | PS5-87-OB-3585A | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-08-10 | PS5-05-03 | PS5 - Milestone F | 5 | Closed | 33 | 32 | AUGUST
T-472-8962 | PS5-06-UR-4296B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone E | 4 | In progress |  | 18 | OCTOBER
T-705-8963 | PS5-92-OB-6851D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-05-10 | PS5-05-03 | PS5 - Milestone B | 1.1 | Closed | 5 | 28 | MAY
T-441-8964 | PS5-95-OB-9321D | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone F | 5 | To be completed |  | 7 | DECEMBER
T-351-8965 | PS5-93-OB-7331B | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-03-25 | PS5-03-03 | PS5 - Milestone B | 1.1 | Closed | 23 | 25 | MARCH
T-320-8966 | PS5-33-UR-9044A | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone I | 8 | In progress |  | 30 | DECEMBER
T-529-8967 | PS5-20-OB-3538C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone A | 1 | On hold |  | 28 | NOVEMBER
T-565-8968 | PS5-20-UR-5878B | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone B | 1.1 | In progress |  | 42 | DECEMBER
T-715-8969 | PS5-87-IK-7541A | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-09-19 | PS5-12-02 | PS5 - Milestone B | 1.1 | Closed | 7 | 41 | SEPTEMBER
T-941-8970 | PS5-77-OB-1379A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-07-21 | PS5-03-02 | PS5 - Milestone F | 5 | Closed | 32 | 13 | JULY
T-378-8971 | PS5-32-IK-5276D | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | In progress |  | 43 | NOVEMBER
T-891-8972 | PS5-58-UR-4715D | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | To be completed |  | 12 | NOVEMBER
T-952-8973 | PS5-41-OB-9121D | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone E | 4 | In progress |  | 25 | AUGUST
T-989-8974 | PS5-94-OB-2501A | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-02-05 | PS5-04-04 | PS5 - Milestone E | 4 | Closed | 8 | 6 | FEBRUARY
T-428-8975 | PS5-12-IK-7507A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone A | 1 | To be completed |  | 18 | NOVEMBER
T-126-8976 | PS5-16-OB-6958C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone G | 6 | To be completed |  | 34 | OCTOBER
T-666-8977 | PS5-12-OB-6065A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone A | 1 | In progress |  | 25 | NOVEMBER
T-242-8978 | PS5-24-OB-6323A | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-05-12 | PS5-02-01 | PS5 - Milestone E | 4 | Closed | 21 | 35 | MAY
T-444-8979 | PS5-21-UR-3738B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone B | 1.1 | To be completed |  | 43 | AUGUST
T-836-8980 | PS5-37-OB-6771B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-08-01 | PS5-08-02 | PS5 - Milestone A | 1 | Closed | 15 | 27 | AUGUST
T-907-8981 | PS5-18-UR-1767B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone D | 3 | In progress |  | 33 | DECEMBER
T-659-8982 | PS5-26-IK-5771C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone A | 1 | To be completed |  | 24 | AUGUST
T-304-8983 | PS5-72-UR-6102A | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone I | 8 | In progress |  | 38 | AUGUST
T-993-8984 | PS5-11-OB-3571A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-03-28 | PS5-09-01 | PS5 - Milestone E | 4 | Closed | 5 | 10 | MARCH
T-946-8985 | PS5-54-UR-7615A | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone G | 6 | On hold |  | 25 | SEPTEMBER
T-571-8986 | PS5-83-OB-6829A | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-09-16 | PS5-11-01 | PS5 - Milestone E | 4 | Closed | 30 | 16 | SEPTEMBER
T-016-8987 | PS5-96-IK-3544D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone A | 1 | In progress |  | 25 | NOVEMBER
T-790-8988 | PS5-32-OB-1728C | CQM03 - Heat Exchanger | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | In progress |  | 46 | OCTOBER
T-385-8989 | PS5-07-OB-4429A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone H | 7 | To be completed |  | 6 | SEPTEMBER
T-843-8990 | PS5-38-OB-6064D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone C | 2 | To be completed |  | 45 | DECEMBER
T-722-8991 | PS5-71-OB-5738A | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone C | 2 | To be completed |  | 28 | SEPTEMBER
T-902-8992 | PS5-79-OB-8371A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-03-17 | PS5-99-01 | PS5 - Milestone C | 2 | Closed | 27 | 9 | MARCH
T-922-8993 | PS5-23-IK-2310C | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone C | 2 | To be completed |  | 34 | SEPTEMBER
T-134-8994 | PS5-77-OB-8223A | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone G | 6 | To be completed |  | 38 | NOVEMBER
T-914-8995 | PS5-78-OB-8981C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-08-11 | PS5-01-01 | PS5 - Milestone D | 3 | Closed | 22 | 31 | AUGUST
T-911-8996 | PS5-31-OB-2352D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-09-14 | PS5-02-01 | PS5 - Milestone D | 3 | Closed | 14 | 21 | SEPTEMBER
T-695-8997 | PS5-28-OB-8934D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone E | 4 | To be completed |  | 29 | AUGUST
T-308-8998 | PS5-68-UR-3683B | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone G | 6 | To be completed |  | 36 | AUGUST
T-314-8999 | PS5-12-OB-3916D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | In progress |  | 29 | DECEMBER
T-810-9000 | PS5-20-UR-6583A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | To be completed |  | 5 | NOVEMBER
T-377-9001 | PS5-44-OB-3372A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone G | 6 | To be completed |  | 8 | AUGUST
T-109-9002 | PS5-02-OB-1858D | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-10-02 | PS5-04-02 | PS5 - Milestone F | 5 | Closed | 35 | 42 | OCTOBER
T-533-9003 | PS5-09-OB-3989C | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone C | 2 | To be completed |  | 20 | OCTOBER
T-784-9004 | PS5-22-UR-7296C | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-09-15 | PS5-01-04 | PS5 - Milestone C | 2 | Closed | 48 | 6 | SEPTEMBER
T-327-9005 | PS5-58-OB-2877A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone C | 2 | To be completed |  | 10 | SEPTEMBER
T-835-9006 | PS5-58-OB-9383D | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-12-07 | PS5-06-02 | PS5 - Milestone I | 8 | Closed | 27 | 35 | DECEMBER
T-119-9007 | PS5-61-OB-6847B | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-05-27 | PS5-08-01 | PS5 - Milestone G | 6 | Closed | 45 | 26 | MAY
T-033-9008 | PS5-40-OB-4048B | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | In progress |  | 47 | SEPTEMBER
T-464-9009 | PS5-82-OB-5321C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone H | 7 | To be completed |  | 43 | DECEMBER
T-509-9010 | PS5-11-IK-2450D | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone F | 5 | In progress |  | 4 | SEPTEMBER
T-250-9011 | PS5-24-IK-2079C | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone B | 1.1 | In progress |  | 32 | DECEMBER
T-993-9012 | PS5-01-UR-7477B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone D | 3 | To be completed |  | 44 | SEPTEMBER
T-932-9013 | PS5-71-OB-2530C | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone D | 3 | In progress |  | 13 | SEPTEMBER
T-048-9014 | PS5-21-UR-2026D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone C | 2 | To be completed |  | 31 | AUGUST
T-817-9015 | PS5-28-UR-2995D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-11-16 | PS5-10-02 | PS5 - Milestone E | 4 | Closed | 13 | 29 | NOVEMBER
T-753-9016 | PS5-36-OB-1529B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-07-28 | PS5-01-07 | PS5 - Milestone B | 1.1 | Closed | 33 | 14 | JULY
T-820-9017 | PS5-78-IK-1635D | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone H | 7 | To be completed |  | 37 | DECEMBER
T-070-9018 | PS5-43-IK-8734C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone G | 6 | To be completed |  | 10 | SEPTEMBER
T-600-9019 | PS5-35-UR-3018C | CQE02 - LV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone C | 2 | To be completed |  | 24 | OCTOBER
T-935-9020 | PS5-89-OB-9398D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone B | 1.1 | In progress |  | 9 | DECEMBER
T-344-9021 | PS5-56-IK-1107A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone I | 8 | In progress |  | 28 | OCTOBER
T-357-9022 | PS5-83-OB-8839D | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | To be completed |  | 10 | AUGUST
T-515-9023 | PS5-30-IK-9683D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone F | 5 | In progress |  | 45 | AUGUST
T-609-9024 | PS5-06-OB-2525D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-03-05 | PS5-62-02 | PS5 - Milestone G | 6 | Closed | 5 | 5 | MARCH
T-507-9025 | PS5-45-UR-4506D | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-02-21 | PS5-07-04 | PS5 - Milestone E | 4 | Closed | 46 | 31 | FEBRUARY
T-264-9026 | PS5-61-OB-5246B | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-12-05 | PS5-05-03 | PS5 - Milestone B | 1.1 | Closed | 23 | 17 | DECEMBER
T-979-9027 | PS5-52-IK-8328C | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone C | 2 | In progress |  | 12 | DECEMBER
T-820-9028 | PS5-71-OB-6697A | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-01-20 | PS5-07-01 | PS5 - Milestone H | 7 | Closed | 10 | 33 | JANUARY
T-506-9029 | PS5-60-OB-6263A | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-03-13 | PS5-07-02 | PS5 - Milestone C | 2 | Closed | 7 | 43 | MARCH
T-027-9030 | PS5-22-OB-6767A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-06-27 | PS5-02-03 | PS5 - Milestone G | 6 | Closed | 14 | 47 | JUNE
T-345-9031 | PS5-60-IK-7205A | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone A | 1 | In progress |  | 41 | SEPTEMBER
T-815-9032 | PS5-08-IK-8000B | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone I | 8 | To be completed |  | 13 | SEPTEMBER
T-499-9033 | PS5-62-IK-3588D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-08-04 | PS5-01-05 | PS5 - Milestone D | 3 | Closed | 16 | 45 | AUGUST
T-385-9034 | PS5-56-OB-3730A | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-06-12 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 18 | 6 | JUNE
T-906-9035 | PS5-18-UR-7324B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-06-17 | PS5-07-04 | PS5 - Milestone G | 6 | Closed | 48 | 34 | JUNE
T-308-9036 | PS5-52-OB-4382D | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone G | 6 | On hold |  | 4 | AUGUST
T-487-9037 | PS5-52-UR-7124D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-06-14 | PS5-08-02 | PS5 - Milestone D | 3 | Closed | 7 | 24 | JUNE
T-541-9038 | PS5-74-OB-6697C | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | To be completed |  | 32 | SEPTEMBER
T-899-9039 | PS5-04-OB-7448C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone G | 6 | In progress |  | 27 | NOVEMBER
T-690-9040 | PS5-14-IK-6947B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone G | 6 | In progress |  | 7 | AUGUST
T-008-9041 | PS5-69-IK-4349B | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone I | 8 | To be completed |  | 11 | DECEMBER
T-389-9042 | PS5-75-OB-3068D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-11-05 | PS5-01-02 | PS5 - Milestone D | 3 | Closed | 38 | 6 | NOVEMBER
T-458-9043 | PS5-50-OB-3633B | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone E | 4 | In progress |  | 45 | DECEMBER
T-706-9044 | PS5-97-IK-8638A | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-10-09 | PS5-09-01 | PS5 - Milestone C | 2 | Closed | 21 | 8 | OCTOBER
T-322-9045 | PS5-82-OB-6491D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-04-01 | PS5-10-03 | PS5 - Milestone B | 1.1 | Closed | 20 | 31 | APRIL
T-178-9046 | PS5-63-IK-9802C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | To be completed |  | 13 | AUGUST
T-093-9047 | PS5-57-OB-9722A | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone I | 8 | To be completed |  | 44 | OCTOBER
T-394-9048 | PS5-54-OB-6377D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | On hold |  | 39 | DECEMBER
T-160-9049 | PS5-44-IK-8074C | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone F | 5 | To be completed |  | 40 | SEPTEMBER
T-078-9050 | PS5-23-IK-6896C | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-01-21 | PS5-10-05 | PS5 - Milestone H | 7 | Closed | 29 | 39 | JANUARY
T-515-9051 | PS5-90-OB-1039C | CQM01 - Pump Installation | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-06-05 | PS5-99-03 | PS5 - Milestone B | 1.1 | Closed | 20 | 24 | JUNE
T-124-9052 | PS5-08-IK-3469C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone A | 1 | To be completed |  | 14 | NOVEMBER
T-625-9053 | PS5-18-OB-4530B | CQM03 - Heat Exchanger | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone E | 4 | To be completed |  | 37 | NOVEMBER
T-181-9054 | PS5-72-OB-5933B | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | To be completed |  | 36 | DECEMBER
T-041-9055 | PS5-31-OB-4431B | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone G | 6 | To be completed |  | 27 | SEPTEMBER
T-601-9056 | PS5-49-OB-8732A | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone B | 1.1 | To be completed |  | 35 | SEPTEMBER
T-163-9057 | PS5-66-OB-1306D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone F | 5 | In progress |  | 27 | OCTOBER
T-977-9058 | PS5-13-OB-6157D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-11-15 | PS5-01-09 | PS5 - Milestone C | 2 | Closed | 15 | 17 | NOVEMBER
T-058-9059 | PS5-93-IK-2328A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | In progress |  | 31 | OCTOBER
T-623-9060 | PS5-46-IK-9700B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-08-26 | PS5-63-04 | PS5 - Milestone F | 5 | Closed | 42 | 12 | AUGUST
T-021-9061 | PS5-62-OB-2608C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-09-07 | PS5-05-01 | PS5 - Milestone C | 2 | Closed | 25 | 23 | SEPTEMBER
T-797-9062 | PS5-66-UR-5166D | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone B | 1.1 | To be completed |  | 14 | OCTOBER
T-091-9063 | PS5-53-OB-1080C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-06-25 | PS5-02-02 | PS5 - Milestone A | 1 | Closed | 34 | 45 | JUNE
T-101-9064 | PS5-15-OB-2267C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | On hold |  | 22 | NOVEMBER
T-053-9065 | PS5-44-OB-4132C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-08-09 | PS5-08-01 | PS5 - Milestone A | 1 | Closed | 41 | 17 | AUGUST
T-702-9066 | PS5-01-OB-8841B | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | To be completed |  | 22 | SEPTEMBER
T-142-9067 | PS5-28-OB-2008D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | To be completed |  | 48 | OCTOBER
T-028-9068 | PS5-13-IK-3653D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone A | 1 | To be completed |  | 13 | AUGUST
T-727-9069 | PS5-68-OB-6609A | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone G | 6 | To be completed |  | 19 | DECEMBER
T-867-9070 | PS5-54-IK-6036D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone I | 8 | To be completed |  | 30 | NOVEMBER
T-158-9071 | PS5-92-UR-4969A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone H | 7 | In progress |  | 23 | SEPTEMBER
T-723-9072 | PS5-08-UR-8031D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone D | 3 | To be completed |  | 29 | OCTOBER
T-732-9073 | PS5-30-IK-5940D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone B | 1.1 | To be completed |  | 18 | DECEMBER
T-426-9074 | PS5-74-UR-8295B | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone G | 6 | To be completed |  | 13 | DECEMBER
T-065-9075 | PS5-53-OB-5534B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-07-24 | PS5-08-01 | PS5 - Milestone B | 1.1 | Closed | 4 | 28 | JULY
T-926-9076 | PS5-47-OB-2623D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone I | 8 | In progress |  | 40 | NOVEMBER
T-555-9077 | PS5-12-IK-1110A | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone I | 8 | To be completed |  | 13 | OCTOBER
T-294-9078 | PS5-26-IK-4757A | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-03-08 | PS5-61-07 | PS5 - Milestone A | 1 | Closed | 48 | 12 | MARCH
T-007-9079 | PS5-94-OB-3813C | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-11-16 | PS5-04-02 | PS5 - Milestone E | 4 | Closed | 8 | 12 | NOVEMBER
T-779-9080 | PS5-12-OB-2746B | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-02-12 | PS5-01-03 | PS5 - Milestone A | 1 | Closed | 31 | 4 | FEBRUARY
T-126-9081 | PS5-14-UR-2097A | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone B | 1.1 | In progress |  | 47 | OCTOBER
T-249-9082 | PS5-28-UR-9200C | CQM04 - Vessel | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone H | 7 | To be completed |  | 8 | OCTOBER
T-546-9083 | PS5-43-IK-7563D | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone I | 8 | To be completed |  | 20 | AUGUST
T-628-9084 | PS5-93-OB-1115A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | On hold |  | 32 | NOVEMBER
T-961-9085 | PS5-25-UR-6371C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-01-28 | PS5-99-02 | PS5 - Milestone D | 3 | Closed | 14 | 22 | JANUARY
T-508-9086 | PS5-34-OB-1956C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | On hold |  | 45 | DECEMBER
T-281-9087 | PS5-65-IK-5755A | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-07-08 | PS5-06-01 | PS5 - Milestone D | 3 | Closed | 44 | 15 | JULY
T-823-9088 | PS5-16-OB-1506D | CQE02 - LV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone A | 1 | To be completed |  | 15 | NOVEMBER
T-289-9089 | PS5-83-IK-5674D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone H | 7 | To be completed |  | 24 | OCTOBER
T-307-9090 | PS5-33-UR-8278B | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-10-18 | PS5-10-06 | PS5 - Milestone A | 1 | Closed | 21 | 7 | OCTOBER
T-559-9091 | PS5-80-IK-5768C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone H | 7 | In progress |  | 32 | DECEMBER
T-503-9092 | PS5-28-OB-3882C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-10-09 | PS5-02-02 | PS5 - Milestone H | 7 | Closed | 28 | 39 | OCTOBER
T-600-9093 | PS5-55-IK-7465B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone B | 1.1 | To be completed |  | 45 | AUGUST
T-789-9094 | PS5-82-UR-5256B | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone I | 8 | To be completed |  | 16 | SEPTEMBER
T-753-9095 | PS5-01-UR-1482A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone I | 8 | On hold |  | 40 | AUGUST
T-356-9096 | PS5-67-OB-4071B | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone C | 2 | On hold |  | 29 | OCTOBER
T-861-9097 | PS5-14-UR-9583B | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone I | 8 | To be completed |  | 48 | OCTOBER
T-119-9098 | PS5-27-UR-3233C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-08-03 | PS5-82-07 | PS5 - Milestone E | 4 | Closed | 14 | 4 | AUGUST
T-168-9099 | PS5-60-IK-5232A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone H | 7 | In progress |  | 21 | DECEMBER
T-064-9100 | PS5-35-UR-8265A | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | In progress |  | 18 | OCTOBER
T-280-9101 | PS5-55-OB-2853D | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-09-22 | PS5-60-10 | PS5 - Milestone I | 8 | Closed | 9 | 42 | SEPTEMBER
T-761-9102 | PS5-33-IK-9547C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | In progress |  | 35 | NOVEMBER
T-896-9103 | PS5-89-OB-6230B | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone F | 5 | To be completed |  | 42 | NOVEMBER
T-170-9104 | PS5-50-OB-2799A | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-05-05 | PS5-03-01 | PS5 - Milestone I | 8 | Closed | 45 | 31 | MAY
T-090-9105 | PS5-50-UR-9233D | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone I | 8 | To be completed |  | 13 | OCTOBER
T-593-9106 | PS5-22-OB-5894C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | To be completed |  | 26 | OCTOBER
T-235-9107 | PS5-87-IK-5788D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone H | 7 | In progress |  | 32 | NOVEMBER
T-821-9108 | PS5-60-UR-5950A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-08-24 | PS5-01-05 | PS5 - Milestone A | 1 | Closed | 7 | 36 | AUGUST
T-322-9109 | PS5-10-OB-8985A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone D | 3 | On hold |  | 18 | OCTOBER
T-577-9110 | PS5-69-IK-7084D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | To be completed |  | 39 | NOVEMBER
T-006-9111 | PS5-82-OB-6055A | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone C | 2 | In progress |  | 37 | AUGUST
T-759-9112 | PS5-45-IK-2756D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone F | 5 | To be completed |  | 45 | NOVEMBER
T-560-9113 | PS5-45-OB-7789D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone E | 4 | To be completed |  | 34 | AUGUST
T-689-9114 | PS5-35-UR-8222A | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-06-10 | PS5-09-03 | PS5 - Milestone D | 3 | Closed | 22 | 34 | JUNE
T-601-9115 | PS5-93-OB-2924D | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-01-24 | PS5-07-01 | PS5 - Milestone C | 2 | Closed | 5 | 4 | JANUARY
T-338-9116 | PS5-88-UR-4815D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-07-16 | PS5-62-01 | PS5 - Milestone B | 1.1 | Closed | 12 | 17 | JULY
T-016-9117 | PS5-40-IK-6704B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone B | 1.1 | In progress |  | 30 | NOVEMBER
T-434-9118 | PS5-65-UR-1892C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-04-02 | PS5-10-01 | PS5 - Milestone C | 2 | Closed | 28 | 46 | APRIL
T-197-9119 | PS5-94-UR-9794B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone B | 1.1 | In progress |  | 25 | OCTOBER
T-192-9120 | PS5-34-UR-9945D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-04-20 | PS5-61-02 | PS5 - Milestone G | 6 | Closed | 5 | 12 | APRIL
T-440-9121 | PS5-85-OB-3480D | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone D | 3 | In progress |  | 33 | SEPTEMBER
T-583-9122 | PS5-79-IK-3289B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-02-22 | PS5-82-01 | PS5 - Milestone C | 2 | Closed | 4 | 19 | FEBRUARY
T-281-9123 | PS5-87-IK-7074A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-04-15 | PS5-12-02 | PS5 - Milestone B | 1.1 | Closed | 40 | 36 | APRIL
T-860-9124 | PS5-84-UR-2366A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-02-14 | PS5-01-04 | PS5 - Milestone H | 7 | Closed | 26 | 6 | FEBRUARY
T-138-9125 | PS5-70-OB-3040D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-05-17 | PS5-62-02 | PS5 - Milestone I | 8 | Closed | 12 | 16 | MAY
T-254-9126 | PS5-59-OB-6965B | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | In progress |  | 15 | OCTOBER
T-640-9127 | PS5-83-UR-3056A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone D | 3 | On hold |  | 15 | AUGUST
T-716-9128 | PS5-34-OB-8908C | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone B | 1.1 | To be completed |  | 29 | AUGUST
T-486-9129 | PS5-24-OB-3330C | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-11-07 | PS5-06-03 | PS5 - Milestone E | 4 | Closed | 30 | 26 | NOVEMBER
T-346-9130 | PS5-16-OB-7772C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-03-16 | PS5-03-01 | PS5 - Milestone A | 1 | Closed | 20 | 29 | MARCH
T-543-9131 | PS5-89-IK-4388C | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone I | 8 | To be completed |  | 9 | NOVEMBER
T-918-9132 | PS5-29-OB-4413B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-08-22 | PS5-10-06 | PS5 - Milestone H | 7 | Closed | 14 | 41 | AUGUST
T-409-9133 | PS5-43-OB-5316D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone A | 1 | To be completed |  | 10 | NOVEMBER
T-985-9134 | PS5-02-IK-5456A | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | To be completed |  | 16 | NOVEMBER
T-235-9135 | PS5-62-OB-4451B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone A | 1 | In progress |  | 38 | DECEMBER
T-088-9136 | PS5-95-OB-4220D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone B | 1.1 | In progress |  | 43 | AUGUST
T-061-9137 | PS5-44-UR-8941C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | To be completed |  | 36 | DECEMBER
T-541-9138 | PS5-72-IK-5365C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-02-21 | PS5-01-08 | PS5 - Milestone F | 5 | Closed | 6 | 21 | FEBRUARY
T-611-9139 | PS5-92-IK-9416C | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-05-16 | PS5-10-03 | PS5 - Milestone I | 8 | Closed | 47 | 37 | MAY
T-852-9140 | PS5-38-UR-8990C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone G | 6 | To be completed |  | 34 | OCTOBER
T-222-9141 | PS5-82-UR-7251B | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | On hold |  | 42 | SEPTEMBER
T-474-9142 | PS5-62-UR-8927B | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | On hold |  | 11 | NOVEMBER
T-293-9143 | PS5-79-OB-3727C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-06-05 | PS5-99-03 | PS5 - Milestone G | 6 | Closed | 23 | 5 | JUNE
T-316-9144 | PS5-31-OB-2628B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone I | 8 | To be completed |  | 15 | AUGUST
T-082-9145 | PS5-71-UR-5073A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-08-15 | PS5-61-01 | PS5 - Milestone D | 3 | Closed | 30 | 6 | AUGUST
T-041-9146 | PS5-58-OB-8125A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone H | 7 | On hold |  | 9 | OCTOBER
T-209-9147 | PS5-56-OB-4012D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | On hold |  | 9 | OCTOBER
T-562-9148 | PS5-37-IK-1359B | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone F | 5 | In progress |  | 28 | OCTOBER
T-447-9149 | PS5-07-OB-9404D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-12-24 | PS5-04-02 | PS5 - Milestone B | 1.1 | Closed | 5 | 48 | DECEMBER
T-396-9150 | PS5-30-OB-8148D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-09-04 | PS5-10-01 | PS5 - Milestone G | 6 | Closed | 17 | 46 | SEPTEMBER
T-325-9151 | PS5-89-OB-1579A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-11-17 | PS5-01-09 | PS5 - Milestone F | 5 | Closed | 47 | 44 | NOVEMBER
T-665-9152 | PS5-34-OB-9310A | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone I | 8 | To be completed |  | 44 | NOVEMBER
T-730-9153 | PS5-44-IK-2840B | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | To be completed |  | 38 | NOVEMBER
T-635-9154 | PS5-58-UR-6911B | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-01-13 | PS5-01-02 | PS5 - Milestone H | 7 | Closed | 9 | 11 | JANUARY
T-506-9155 | PS5-45-IK-8120C | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone D | 3 | To be completed |  | 29 | NOVEMBER
T-577-9156 | PS5-09-OB-7512B | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-11-21 | PS5-01-08 | PS5 - Milestone A | 1 | Closed | 43 | 24 | NOVEMBER
T-490-9157 | PS5-26-UR-9729D | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-06-07 | PS5-10-02 | PS5 - Milestone D | 3 | Closed | 31 | 12 | JUNE
T-085-9158 | PS5-57-OB-8261D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-07-01 | PS5-61-02 | PS5 - Milestone A | 1 | Closed | 20 | 39 | JULY
T-377-9159 | PS5-85-IK-3726B | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone D | 3 | On hold |  | 36 | SEPTEMBER
T-795-9160 | PS5-84-UR-2554B | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone C | 2 | To be completed |  | 38 | DECEMBER
T-366-9161 | PS5-35-OB-9831D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone B | 1.1 | In progress |  | 9 | AUGUST
T-441-9162 | PS5-78-IK-9910A | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone A | 1 | In progress |  | 8 | NOVEMBER
T-189-9163 | PS5-63-IK-1085C | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-08-21 | PS5-03-01 | PS5 - Milestone B | 1.1 | Closed | 14 | 19 | AUGUST
T-213-9164 | PS5-26-UR-8671B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone H | 7 | In progress |  | 45 | DECEMBER
T-681-9165 | PS5-53-UR-7987C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone I | 8 | In progress |  | 15 | AUGUST
T-322-9166 | PS5-53-OB-3606B | CQP05 - Insulation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone C | 2 | In progress |  | 43 | SEPTEMBER
T-927-9167 | PS5-64-IK-4188A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone H | 7 | To be completed |  | 9 | DECEMBER
T-251-9168 | PS5-23-OB-1253D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone D | 3 | To be completed |  | 28 | AUGUST
T-970-9169 | PS5-14-OB-4232D | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone H | 7 | In progress |  | 44 | NOVEMBER
T-467-9170 | PS5-70-UR-5362C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-02-23 | PS5-10-05 | PS5 - Milestone C | 2 | Closed | 35 | 10 | FEBRUARY
T-198-9171 | PS5-17-OB-6760A | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone H | 7 | On hold |  | 19 | NOVEMBER
T-651-9172 | PS5-07-OB-2116B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-10-08 | PS5-82-02 | PS5 - Milestone I | 8 | Closed | 31 | 42 | OCTOBER
T-875-9173 | PS5-36-UR-8534A | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-06-26 | PS5-11-01 | PS5 - Milestone E | 4 | Closed | 40 | 30 | JUNE
T-507-9174 | PS5-77-IK-2543A | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-12-18 | PS5-07-04 | PS5 - Milestone D | 3 | Closed | 43 | 32 | DECEMBER
T-019-9175 | PS5-73-IK-3078B | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-10-28 | PS5-02-02 | PS5 - Milestone B | 1.1 | Closed | 22 | 19 | OCTOBER
T-400-9176 | PS5-19-OB-7381A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-15 | PS5-60-01 | PS5 - Milestone F | 5 | Closed | 27 | 45 | FEBRUARY
T-282-9177 | PS5-27-OB-5628A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-10-24 | PS5-13-01 | PS5 - Milestone B | 1.1 | Closed | 14 | 24 | OCTOBER
T-447-9178 | PS5-99-OB-3104B | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone I | 8 | To be completed |  | 6 | DECEMBER
T-237-9179 | PS5-40-OB-9352B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-12-21 | PS5-06-02 | PS5 - Milestone E | 4 | Closed | 48 | 4 | DECEMBER
T-004-9180 | PS5-35-IK-1650C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-07-20 | PS5-61-01 | PS5 - Milestone B | 1.1 | Closed | 20 | 29 | JULY
T-448-9181 | PS5-59-IK-5098C | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone F | 5 | In progress |  | 11 | AUGUST
T-044-9182 | PS5-08-OB-8070B | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | In progress |  | 4 | NOVEMBER
T-605-9183 | PS5-32-UR-7122A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone B | 1.1 | To be completed |  | 26 | OCTOBER
T-200-9184 | PS5-40-UR-9289A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone G | 6 | In progress |  | 7 | NOVEMBER
T-513-9185 | PS5-57-UR-7300A | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-03-08 | PS5-10-02 | PS5 - Milestone D | 3 | Closed | 8 | 12 | MARCH
T-589-9186 | PS5-13-IK-5001C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | To be completed |  | 47 | NOVEMBER
T-678-9187 | PS5-71-OB-7440D | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-01-18 | PS5-01-07 | PS5 - Milestone G | 6 | Closed | 42 | 47 | JANUARY
T-952-9188 | PS5-90-IK-2286D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone C | 2 | To be completed |  | 22 | NOVEMBER
T-657-9189 | PS5-54-IK-3873D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone C | 2 | To be completed |  | 14 | NOVEMBER
T-893-9190 | PS5-75-OB-3325C | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | To be completed |  | 32 | AUGUST
T-152-9191 | PS5-82-IK-7153A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-09-27 | PS5-13-01 | PS5 - Milestone I | 8 | Closed | 34 | 7 | SEPTEMBER
T-091-9192 | PS5-77-OB-2566A | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-04-05 | PS5-82-02 | PS5 - Milestone H | 7 | Closed | 22 | 48 | APRIL
T-993-9193 | PS5-85-OB-8503C | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | To be completed |  | 19 | OCTOBER
T-427-9194 | PS5-78-OB-5282C | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone D | 3 | In progress |  | 48 | DECEMBER
T-251-9195 | PS5-47-OB-1743D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-02-16 | PS5-09-01 | PS5 - Milestone A | 1 | Closed | 4 | 35 | FEBRUARY
T-239-9196 | PS5-96-IK-7079A | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone G | 6 | To be completed |  | 47 | NOVEMBER
T-297-9197 | PS5-39-OB-4710D | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone E | 4 | To be completed |  | 5 | SEPTEMBER
T-117-9198 | PS5-97-OB-8977C | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | On hold |  | 30 | NOVEMBER
T-554-9199 | PS5-04-OB-2922A | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | In progress |  | 22 | OCTOBER
T-673-9200 | PS5-03-OB-7153A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-10-15 | PS5-02-03 | PS5 - Milestone G | 6 | Closed | 38 | 4 | OCTOBER
T-836-9201 | PS5-16-OB-6609D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-11-10 | PS5-04-01 | PS5 - Milestone I | 8 | Closed | 35 | 14 | NOVEMBER
T-849-9202 | PS5-11-IK-2054C | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-05-05 | PS5-07-03 | PS5 - Milestone A | 1 | Closed | 42 | 36 | MAY
T-803-9203 | PS5-47-IK-5781D | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | On hold |  | 12 | OCTOBER
T-457-9204 | PS5-14-UR-3701D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone D | 3 | To be completed |  | 38 | DECEMBER
T-599-9205 | PS5-86-UR-6157B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone B | 1.1 | In progress |  | 35 | SEPTEMBER
T-849-9206 | PS5-76-OB-1093B | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-01-20 | PS5-05-01 | PS5 - Milestone E | 4 | Closed | 28 | 4 | JANUARY
T-629-9207 | PS5-74-OB-4566D | CQS03 - Deluge System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-03-25 | PS5-99-02 | PS5 - Milestone G | 6 | Closed | 39 | 41 | MARCH
T-850-9208 | PS5-42-OB-9158C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-11-08 | PS5-99-03 | PS5 - Milestone F | 5 | Closed | 32 | 29 | NOVEMBER
T-744-9209 | PS5-95-OB-8108D | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone C | 2 | On hold |  | 10 | OCTOBER
T-899-9210 | PS5-62-OB-6737C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone G | 6 | To be completed |  | 7 | AUGUST
T-676-9211 | PS5-58-IK-2060A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-10-20 | PS5-12-02 | PS5 - Milestone G | 6 | Closed | 36 | 23 | OCTOBER
T-721-9212 | PS5-45-OB-4376A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | To be completed |  | 43 | SEPTEMBER
T-768-9213 | PS5-09-IK-9068D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone G | 6 | On hold |  | 21 | DECEMBER
T-661-9214 | PS5-22-UR-8508D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone G | 6 | On hold |  | 46 | DECEMBER
T-009-9215 | PS5-68-UR-5667D | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-05-14 | PS5-06-01 | PS5 - Milestone H | 7 | Closed | 34 | 17 | MAY
T-250-9216 | PS5-93-OB-4110D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone A | 1 | In progress |  | 17 | OCTOBER
T-771-9217 | PS5-66-IK-5205C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone G | 6 | On hold |  | 25 | NOVEMBER
T-273-9218 | PS5-18-UR-8732D | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-08-19 | PS5-06-03 | PS5 - Milestone F | 5 | Closed | 28 | 22 | AUGUST
T-107-9219 | PS5-31-OB-3747C | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone D | 3 | On hold |  | 6 | NOVEMBER
T-813-9220 | PS5-99-UR-2145C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-11-20 | PS5-11-01 | PS5 - Milestone G | 6 | Closed | 12 | 34 | NOVEMBER
T-675-9221 | PS5-85-IK-1082A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-01-12 | PS5-07-01 | PS5 - Milestone F | 5 | Closed | 36 | 31 | JANUARY
T-427-9222 | PS5-61-OB-9154B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-08-28 | PS5-05-01 | PS5 - Milestone A | 1 | Closed | 35 | 4 | AUGUST
T-343-9223 | PS5-21-UR-9699D | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone I | 8 | In progress |  | 27 | NOVEMBER
T-402-9224 | PS5-84-OB-4252D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone E | 4 | In progress |  | 48 | DECEMBER
T-470-9225 | PS5-67-OB-5167B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-10-12 | PS5-09-04 | PS5 - Milestone F | 5 | Closed | 24 | 41 | OCTOBER
T-934-9226 | PS5-85-IK-1961C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone E | 4 | To be completed |  | 47 | DECEMBER
T-519-9227 | PS5-13-OB-5240C | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone H | 7 | To be completed |  | 11 | OCTOBER
T-677-9228 | PS5-99-OB-2662C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-08-14 | PS5-01-02 | PS5 - Milestone B | 1.1 | Closed | 28 | 16 | AUGUST
T-698-9229 | PS5-77-OB-5027C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | To be completed |  | 43 | OCTOBER
T-523-9230 | PS5-41-OB-1039A | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | To be completed |  | 27 | SEPTEMBER
T-799-9231 | PS5-34-OB-3984B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone C | 2 | To be completed |  | 18 | NOVEMBER
T-679-9232 | PS5-88-OB-4702D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-03 | PS5-60-04 | PS5 - Milestone I | 8 | Closed | 26 | 30 | MAY
T-965-9233 | PS5-41-IK-5702B | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone F | 5 | To be completed |  | 28 | DECEMBER
T-796-9234 | PS5-08-UR-5565A | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone D | 3 | To be completed |  | 14 | AUGUST
T-790-9235 | PS5-42-OB-8398C | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-02-06 | PS5-13-01 | PS5 - Milestone I | 8 | Closed | 7 | 9 | FEBRUARY
T-971-9236 | PS5-84-UR-8808D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-05-20 | PS5-02-03 | PS5 - Milestone H | 7 | Closed | 19 | 32 | MAY
T-082-9237 | PS5-73-IK-4069D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-03-17 | PS5-07-03 | PS5 - Milestone B | 1.1 | Closed | 45 | 44 | MARCH
T-073-9238 | PS5-51-OB-9514A | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone C | 2 | To be completed |  | 11 | NOVEMBER
T-045-9239 | PS5-93-OB-7550B | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | To be completed |  | 10 | NOVEMBER
T-860-9240 | PS5-69-IK-1334C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-02-22 | PS5-06-01 | PS5 - Milestone I | 8 | Closed | 21 | 35 | FEBRUARY
T-566-9241 | PS5-18-UR-1934A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone E | 4 | In progress |  | 39 | OCTOBER
T-323-9242 | PS5-26-OB-1349B | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone A | 1 | In progress |  | 28 | OCTOBER
T-926-9243 | PS5-23-UR-8518B | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone G | 6 | To be completed |  | 42 | NOVEMBER
T-515-9244 | PS5-70-OB-3792C | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | To be completed |  | 19 | AUGUST
T-236-9245 | PS5-87-UR-5774D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | In progress |  | 17 | SEPTEMBER
T-791-9246 | PS5-93-OB-7174D | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone A | 1 | On hold |  | 21 | DECEMBER
T-364-9247 | PS5-23-IK-7431A | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone E | 4 | In progress |  | 25 | NOVEMBER
T-376-9248 | PS5-38-OB-6957B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone G | 6 | In progress |  | 35 | SEPTEMBER
T-239-9249 | PS5-90-IK-6379D | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | To be completed |  | 29 | SEPTEMBER
T-319-9250 | PS5-32-OB-6547D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-05-24 | PS5-06-01 | PS5 - Milestone D | 3 | Closed | 34 | 17 | MAY
T-031-9251 | PS5-79-UR-6962B | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-11-18 | PS5-13-01 | PS5 - Milestone D | 3 | Closed | 48 | 48 | NOVEMBER
T-313-9252 | PS5-86-OB-9262C | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone H | 7 | To be completed |  | 38 | DECEMBER
T-974-9253 | PS5-98-OB-6284D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-12-05 | PS5-10-05 | PS5 - Milestone D | 3 | Closed | 9 | 29 | DECEMBER
T-865-9254 | PS5-01-OB-8456B | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | To be completed |  | 32 | NOVEMBER
T-454-9255 | PS5-36-UR-6819D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone B | 1.1 | To be completed |  | 37 | SEPTEMBER
T-974-9256 | PS5-95-OB-3919C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | To be completed |  | 10 | NOVEMBER
T-501-9257 | PS5-84-OB-1568B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-06-05 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 39 | 11 | JUNE
T-144-9258 | PS5-44-OB-7766D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone B | 1.1 | To be completed |  | 9 | DECEMBER
T-058-9259 | PS5-19-OB-4647A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone I | 8 | To be completed |  | 36 | OCTOBER
T-395-9260 | PS5-09-IK-1852C | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone I | 8 | To be completed |  | 28 | DECEMBER
T-298-9261 | PS5-10-IK-8616B | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone F | 5 | On hold |  | 48 | AUGUST
T-402-9262 | PS5-15-OB-9779C | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone A | 1 | To be completed |  | 19 | OCTOBER
T-961-9263 | PS5-36-UR-7629D | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-03-20 | PS5-01-08 | PS5 - Milestone E | 4 | Closed | 29 | 42 | MARCH
T-700-9264 | PS5-06-IK-9472B | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | In progress |  | 27 | AUGUST
T-999-9265 | PS5-16-OB-9309B | CQH02 - AHU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-07-25 | PS5-02-03 | PS5 - Milestone B | 1.1 | Closed | 28 | 5 | JULY
T-499-9266 | PS5-21-IK-7213B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone F | 5 | In progress |  | 23 | SEPTEMBER
T-724-9267 | PS5-90-IK-8510D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone G | 6 | In progress |  | 44 | OCTOBER
T-258-9268 | PS5-90-OB-3162A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | On hold |  | 33 | SEPTEMBER
T-735-9269 | PS5-18-UR-6619A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-08-09 | PS5-01-05 | PS5 - Milestone F | 5 | Closed | 28 | 10 | AUGUST
T-180-9270 | PS5-31-IK-1303C | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-02-25 | PS5-82-07 | PS5 - Milestone H | 7 | Closed | 47 | 25 | FEBRUARY
T-445-9271 | PS5-12-OB-9039A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-03-20 | PS5-07-03 | PS5 - Milestone B | 1.1 | Closed | 25 | 28 | MARCH
T-074-9272 | PS5-22-OB-1185A | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-02-25 | PS5-99-02 | PS5 - Milestone I | 8 | Closed | 13 | 38 | FEBRUARY
T-476-9273 | PS5-09-IK-2526A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone D | 3 | To be completed |  | 13 | OCTOBER
T-442-9274 | PS5-80-UR-3916D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-09-14 | PS5-07-03 | PS5 - Milestone C | 2 | Closed | 38 | 42 | SEPTEMBER
T-720-9275 | PS5-03-OB-9219C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-08-24 | PS5-01-06 | PS5 - Milestone I | 8 | Closed | 42 | 25 | AUGUST
T-099-9276 | PS5-90-IK-5863C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-03-27 | PS5-10-02 | PS5 - Milestone A | 1 | Closed | 41 | 15 | MARCH
T-932-9277 | PS5-43-OB-1537D | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-07-10 | PS5-01-03 | PS5 - Milestone A | 1 | Closed | 22 | 4 | JULY
T-073-9278 | PS5-71-UR-1765D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-09-21 | PS5-61-01 | PS5 - Milestone G | 6 | Closed | 6 | 42 | SEPTEMBER
T-602-9279 | PS5-42-UR-7424B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-09-10 | PS5-01-03 | PS5 - Milestone D | 3 | Closed | 31 | 47 | SEPTEMBER
T-840-9280 | PS5-33-UR-2086D | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | To be completed |  | 6 | DECEMBER
T-887-9281 | PS5-47-IK-1631A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-03-28 | PS5-61-01 | PS5 - Milestone B | 1.1 | Closed | 7 | 28 | MARCH
T-733-9282 | PS5-81-OB-7400A | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-08-08 | PS5-01-04 | PS5 - Milestone C | 2 | Closed | 45 | 19 | AUGUST
T-373-9283 | PS5-13-UR-3477D | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-07-24 | PS5-01-03 | PS5 - Milestone G | 6 | Closed | 46 | 39 | JULY
T-968-9284 | PS5-88-OB-9838B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-11-18 | PS5-08-02 | PS5 - Milestone C | 2 | Closed | 26 | 31 | NOVEMBER
T-603-9285 | PS5-98-UR-8338A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-02-25 | PS5-06-02 | PS5 - Milestone D | 3 | Closed | 29 | 8 | FEBRUARY
T-503-9286 | PS5-76-OB-7183C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-08-15 | PS5-09-02 | PS5 - Milestone H | 7 | Closed | 42 | 18 | AUGUST
T-399-9287 | PS5-97-IK-6012B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone H | 7 | To be completed |  | 7 | NOVEMBER
T-031-9288 | PS5-88-OB-4339B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone I | 8 | To be completed |  | 43 | AUGUST
T-707-9289 | PS5-61-IK-1794C | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-07-10 | PS5-03-03 | PS5 - Milestone G | 6 | Closed | 37 | 39 | JULY
T-263-9290 | PS5-70-IK-2951D | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone D | 3 | To be completed |  | 26 | AUGUST
T-754-9291 | PS5-72-OB-3396B | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-03-27 | PS5-10-03 | PS5 - Milestone H | 7 | Closed | 7 | 6 | MARCH
T-153-9292 | PS5-79-IK-1293D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone G | 6 | To be completed |  | 7 | NOVEMBER
T-970-9293 | PS5-41-OB-7266C | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone I | 8 | To be completed |  | 10 | OCTOBER
T-464-9294 | PS5-45-IK-5482B | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | To be completed |  | 24 | NOVEMBER
T-781-9295 | PS5-30-OB-8321D | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone F | 5 | To be completed |  | 47 | OCTOBER
T-926-9296 | PS5-38-IK-6067A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-08-18 | PS5-10-01 | PS5 - Milestone I | 8 | Closed | 13 | 27 | AUGUST
T-626-9297 | PS5-61-IK-3607C | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | On hold |  | 23 | SEPTEMBER
T-295-9298 | PS5-79-OB-5581B | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone F | 5 | On hold |  | 45 | AUGUST
T-735-9299 | PS5-85-IK-9695A | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-08-17 | PS5-07-04 | PS5 - Milestone C | 2 | Closed | 32 | 27 | AUGUST
T-730-9300 | PS5-35-IK-9751D | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-10-06 | PS5-09-03 | PS5 - Milestone C | 2 | Closed | 30 | 19 | OCTOBER
T-801-9301 | PS5-63-IK-3011B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | In progress |  | 24 | AUGUST
T-272-9302 | PS5-77-IK-3373D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone D | 3 | To be completed |  | 39 | SEPTEMBER
T-567-9303 | PS5-17-UR-5239D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone E | 4 | To be completed |  | 8 | SEPTEMBER
T-256-9304 | PS5-20-IK-1280C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone B | 1.1 | To be completed |  | 45 | DECEMBER
T-339-9305 | PS5-47-IK-3406B | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone E | 4 | To be completed |  | 25 | DECEMBER
T-814-9306 | PS5-20-UR-2351C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone A | 1 | On hold |  | 16 | OCTOBER
T-699-9307 | PS5-49-OB-6571C | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone G | 6 | In progress |  | 26 | SEPTEMBER
T-944-9308 | PS5-33-UR-6081D | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-01-10 | PS5-10-04 | PS5 - Milestone G | 6 | Closed | 27 | 15 | JANUARY
T-568-9309 | PS5-08-IK-5530D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-04-18 | PS5-05-02 | PS5 - Milestone B | 1.1 | Closed | 47 | 37 | APRIL
T-718-9310 | PS5-29-IK-5376A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | In progress |  | 34 | AUGUST
T-153-9311 | PS5-45-UR-8623C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone D | 3 | To be completed |  | 32 | SEPTEMBER
T-422-9312 | PS5-53-OB-8530B | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone E | 4 | To be completed |  | 37 | DECEMBER
T-156-9313 | PS5-41-IK-3582B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-07-02 | PS5-05-03 | PS5 - Milestone G | 6 | Closed | 5 | 14 | JULY
T-822-9314 | PS5-35-UR-8688B | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | In progress |  | 17 | DECEMBER
T-900-9315 | PS5-99-UR-9008D | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-05-21 | PS5-07-03 | PS5 - Milestone A | 1 | Closed | 29 | 21 | MAY
T-115-9316 | PS5-26-OB-3515B | CQP01 - Pipe Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone D | 3 | To be completed |  | 21 | AUGUST
T-038-9317 | PS5-35-IK-5230A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | On hold |  | 19 | OCTOBER
T-826-9318 | PS5-87-OB-1233C | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-11-05 | PS5-60-04 | PS5 - Milestone A | 1 | Closed | 34 | 27 | NOVEMBER
T-351-9319 | PS5-94-UR-4572C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-10-16 | PS5-01-04 | PS5 - Milestone F | 5 | Closed | 5 | 23 | OCTOBER
T-469-9320 | PS5-23-UR-5354C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone H | 7 | In progress |  | 32 | SEPTEMBER
T-817-9321 | PS5-55-IK-6686C | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone I | 8 | In progress |  | 29 | SEPTEMBER
T-110-9322 | PS5-16-OB-5777B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-08-13 | PS5-62-01 | PS5 - Milestone F | 5 | Closed | 10 | 5 | AUGUST
T-964-9323 | PS5-38-UR-5933D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone I | 8 | To be completed |  | 12 | AUGUST
T-490-9324 | PS5-78-OB-8504D | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | On hold |  | 35 | NOVEMBER
T-606-9325 | PS5-33-IK-9985B | CQS01 - Fire Protection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone G | 6 | To be completed |  | 44 | OCTOBER
T-689-9326 | PS5-41-IK-8658D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone C | 2 | On hold |  | 48 | SEPTEMBER
T-687-9327 | PS5-66-UR-1151B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | In progress |  | 9 | NOVEMBER
T-670-9328 | PS5-74-UR-2625B | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone E | 4 | To be completed |  | 12 | DECEMBER
T-426-9329 | PS5-52-OB-1229B | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone C | 2 | To be completed |  | 16 | NOVEMBER
T-304-9330 | PS5-90-IK-7608B | CQE02 - LV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone C | 2 | To be completed |  | 32 | AUGUST
T-662-9331 | PS5-95-OB-3685D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-04-09 | PS5-03-02 | PS5 - Milestone E | 4 | Closed | 43 | 35 | APRIL
T-761-9332 | PS5-05-IK-8924B | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-04-02 | PS5-07-03 | PS5 - Milestone B | 1.1 | Closed | 18 | 28 | APRIL
T-212-9333 | PS5-36-OB-8492B | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone C | 2 | To be completed |  | 44 | NOVEMBER
T-495-9334 | PS5-06-OB-5836D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-09-07 | PS5-04-02 | PS5 - Milestone F | 5 | Closed | 17 | 43 | SEPTEMBER
T-108-9335 | PS5-46-UR-5536B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-09-24 | PS5-60-07 | PS5 - Milestone B | 1.1 | Closed | 38 | 17 | SEPTEMBER
T-970-9336 | PS5-95-IK-2609C | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone F | 5 | In progress |  | 5 | DECEMBER
T-939-9337 | PS5-62-OB-2990B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-09-22 | PS5-60-10 | PS5 - Milestone A | 1 | Closed | 21 | 28 | SEPTEMBER
T-969-9338 | PS5-50-OB-2027D | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone C | 2 | To be completed |  | 32 | SEPTEMBER
T-104-9339 | PS5-72-OB-1027C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | In progress |  | 29 | SEPTEMBER
T-557-9340 | PS5-31-OB-4990D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone G | 6 | To be completed |  | 23 | DECEMBER
T-104-9341 | PS5-66-OB-8886B | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-04-24 | PS5-01-04 | PS5 - Milestone A | 1 | Closed | 15 | 22 | APRIL
T-880-9342 | PS5-09-OB-8713A | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | To be completed |  | 18 | OCTOBER
T-856-9343 | PS5-23-IK-4929D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | In progress |  | 8 | SEPTEMBER
T-433-9344 | PS5-11-IK-3329B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone E | 4 | To be completed |  | 4 | OCTOBER
T-129-9345 | PS5-48-OB-5599C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone A | 1 | On hold |  | 39 | AUGUST
T-955-9346 | PS5-05-IK-2545C | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone A | 1 | To be completed |  | 25 | OCTOBER
T-849-9347 | PS5-90-IK-7161C | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-09-23 | PS5-05-02 | PS5 - Milestone C | 2 | Closed | 26 | 33 | SEPTEMBER
T-025-9348 | PS5-21-IK-3747D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone C | 2 | To be completed |  | 27 | OCTOBER
T-308-9349 | PS5-73-OB-1166A | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone B | 1.1 | On hold |  | 31 | NOVEMBER
T-752-9350 | PS5-94-OB-4841D | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone I | 8 | In progress |  | 6 | AUGUST
T-701-9351 | PS5-97-UR-1422A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone B | 1.1 | To be completed |  | 46 | OCTOBER
T-482-9352 | PS5-67-UR-5045A | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-02-25 | PS5-06-03 | PS5 - Milestone A | 1 | Closed | 39 | 46 | FEBRUARY
T-860-9353 | PS5-95-UR-5503D | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-05-26 | PS5-06-01 | PS5 - Milestone E | 4 | Closed | 25 | 23 | MAY
T-403-9354 | PS5-69-UR-1648B | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-06-18 | PS5-01-08 | PS5 - Milestone E | 4 | Closed | 42 | 13 | JUNE
T-784-9355 | PS5-88-UR-5269A | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone D | 3 | In progress |  | 8 | DECEMBER
T-186-9356 | PS5-62-OB-6224A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone C | 2 | In progress |  | 16 | DECEMBER
T-588-9357 | PS5-95-UR-2738B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-11-05 | PS5-60-10 | PS5 - Milestone H | 7 | Closed | 24 | 35 | NOVEMBER
T-466-9358 | PS5-12-OB-4554A | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-11-11 | PS5-63-01 | PS5 - Milestone G | 6 | Closed | 14 | 42 | NOVEMBER
T-882-9359 | PS5-76-IK-5875B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | On hold |  | 26 | NOVEMBER
T-022-9360 | PS5-44-UR-5259D | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone H | 7 | On hold |  | 23 | NOVEMBER
T-159-9361 | PS5-52-OB-7750B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone A | 1 | To be completed |  | 30 | AUGUST
T-890-9362 | PS5-05-OB-1163D | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-10-27 | PS5-10-01 | PS5 - Milestone I | 8 | Closed | 36 | 36 | OCTOBER
T-743-9363 | PS5-85-IK-2547C | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone D | 3 | To be completed |  | 20 | NOVEMBER
T-796-9364 | PS5-53-OB-3572B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-07-02 | PS5-04-02 | PS5 - Milestone C | 2 | Closed | 27 | 48 | JULY
T-818-9365 | PS5-24-UR-7425C | CQS01 - Fire Protection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-11-14 | PS5-03-01 | PS5 - Milestone G | 6 | Closed | 23 | 15 | NOVEMBER
T-087-9366 | PS5-51-IK-5010B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone G | 6 | To be completed |  | 4 | NOVEMBER
T-400-9367 | PS5-31-UR-7377A | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone E | 4 | In progress |  | 4 | DECEMBER
T-934-9368 | PS5-61-IK-9545A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-02-26 | PS5-06-02 | PS5 - Milestone I | 8 | Closed | 47 | 48 | FEBRUARY
T-585-9369 | PS5-67-IK-2569D | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-10-02 | PS5-09-04 | PS5 - Milestone I | 8 | Closed | 20 | 35 | OCTOBER
T-203-9370 | PS5-70-OB-7670B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone F | 5 | To be completed |  | 9 | DECEMBER
T-903-9371 | PS5-30-OB-7118D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone E | 4 | In progress |  | 34 | SEPTEMBER
T-113-9372 | PS5-90-OB-1172B | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | On hold |  | 14 | AUGUST
T-506-9373 | PS5-09-OB-1235C | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone G | 6 | To be completed |  | 40 | OCTOBER
T-554-9374 | PS5-17-OB-5690C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone H | 7 | In progress |  | 17 | DECEMBER
T-193-9375 | PS5-52-IK-9889B | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone I | 8 | On hold |  | 10 | DECEMBER
T-146-9376 | PS5-50-UR-3288C | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone F | 5 | To be completed |  | 13 | NOVEMBER
T-667-9377 | PS5-04-UR-4919D | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone A | 1 | In progress |  | 4 | NOVEMBER
T-168-9378 | PS5-26-IK-2948C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-12-09 | PS5-02-02 | PS5 - Milestone B | 1.1 | Closed | 15 | 27 | DECEMBER
T-511-9379 | PS5-73-IK-2243A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-10-06 | PS5-61-01 | PS5 - Milestone B | 1.1 | Closed | 33 | 12 | OCTOBER
T-358-9380 | PS5-15-OB-6566D | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-04-05 | PS5-04-02 | PS5 - Milestone C | 2 | Closed | 7 | 22 | APRIL
T-153-9381 | PS5-81-OB-4072B | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-09-25 | PS5-08-01 | PS5 - Milestone D | 3 | Closed | 45 | 48 | SEPTEMBER
T-264-9382 | PS5-86-OB-7494C | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone E | 4 | To be completed |  | 26 | NOVEMBER
T-888-9383 | PS5-98-OB-6506C | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone F | 5 | In progress |  | 35 | SEPTEMBER
T-507-9384 | PS5-82-UR-7355B | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-08-23 | PS5-05-02 | PS5 - Milestone D | 3 | Closed | 35 | 10 | AUGUST
T-800-9385 | PS5-88-OB-2157A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-07-10 | PS5-61-07 | PS5 - Milestone I | 8 | Closed | 38 | 29 | JULY
T-417-9386 | PS5-79-OB-9219D | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone B | 1.1 | To be completed |  | 28 | NOVEMBER
T-700-9387 | PS5-01-OB-1615C | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | To be completed |  | 33 | NOVEMBER
T-610-9388 | PS5-06-IK-5675D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-05-24 | PS5-60-07 | PS5 - Milestone H | 7 | Closed | 38 | 31 | MAY
T-562-9389 | PS5-13-OB-2126A | CQM04 - Vessel | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-08-28 | PS5-02-01 | PS5 - Milestone I | 8 | Closed | 45 | 38 | AUGUST
T-760-9390 | PS5-82-IK-8058C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-07-28 | PS5-03-02 | PS5 - Milestone E | 4 | Closed | 45 | 40 | JULY
T-286-9391 | PS5-19-UR-3392C | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone D | 3 | To be completed |  | 16 | AUGUST
T-102-9392 | PS5-76-OB-5434B | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-04-16 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 33 | 36 | APRIL
T-187-9393 | PS5-30-IK-4870B | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-01-20 | PS5-05-03 | PS5 - Milestone G | 6 | Closed | 37 | 31 | JANUARY
T-913-9394 | PS5-33-OB-4939C | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone A | 1 | In progress |  | 23 | AUGUST
T-768-9395 | PS5-62-UR-2091C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone D | 3 | In progress |  | 20 | SEPTEMBER
T-268-9396 | PS5-36-OB-3782C | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-09-10 | PS5-12-02 | PS5 - Milestone E | 4 | Closed | 22 | 23 | SEPTEMBER
T-386-9397 | PS5-66-IK-8111A | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone F | 5 | On hold |  | 43 | NOVEMBER
T-427-9398 | PS5-16-OB-6038B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-05-15 | PS5-01-05 | PS5 - Milestone B | 1.1 | Closed | 35 | 43 | MAY
T-598-9399 | PS5-52-UR-1685B | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-08-04 | PS5-13-01 | PS5 - Milestone D | 3 | Closed | 29 | 25 | AUGUST
T-625-9400 | PS5-21-OB-5653D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-06-07 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 47 | 36 | JUNE
T-583-9401 | PS5-14-UR-4850A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-04-23 | PS5-09-04 | PS5 - Milestone F | 5 | Closed | 32 | 41 | APRIL
T-244-9402 | PS5-61-OB-5535D | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-12-02 | PS5-12-02 | PS5 - Milestone F | 5 | Closed | 26 | 46 | DECEMBER
T-115-9403 | PS5-93-OB-5188A | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-07-05 | PS5-82-07 | PS5 - Milestone G | 6 | Closed | 4 | 23 | JULY
T-892-9404 | PS5-22-OB-5895A | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | To be completed |  | 4 | SEPTEMBER
T-561-9405 | PS5-38-UR-5457C | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-06-02 | PS5-05-03 | PS5 - Milestone G | 6 | Closed | 26 | 5 | JUNE
T-878-9406 | PS5-98-IK-2515D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-01-21 | PS5-01-06 | PS5 - Milestone D | 3 | Closed | 31 | 29 | JANUARY
T-029-9407 | PS5-18-OB-1739B | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-06-21 | PS5-61-02 | PS5 - Milestone A | 1 | Closed | 4 | 29 | JUNE
T-875-9408 | PS5-73-OB-1455C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone D | 3 | On hold |  | 40 | DECEMBER
T-975-9409 | PS5-95-UR-7502B | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-08-28 | PS5-06-02 | PS5 - Milestone D | 3 | Closed | 43 | 22 | AUGUST
T-568-9410 | PS5-16-IK-3338D | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-12-10 | PS5-60-10 | PS5 - Milestone E | 4 | Closed | 6 | 4 | DECEMBER
T-276-9411 | PS5-81-UR-2948A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-03-26 | PS5-03-03 | PS5 - Milestone B | 1.1 | Closed | 48 | 26 | MARCH
T-725-9412 | PS5-12-OB-2122D | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-12-25 | PS5-07-03 | PS5 - Milestone B | 1.1 | Closed | 39 | 48 | DECEMBER
T-606-9413 | PS5-18-OB-7111D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone B | 1.1 | To be completed |  | 21 | AUGUST
T-255-9414 | PS5-11-IK-6382D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone C | 2 | On hold |  | 27 | OCTOBER
T-022-9415 | PS5-64-OB-8501B | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone B | 1.1 | In progress |  | 42 | OCTOBER
T-011-9416 | PS5-80-IK-3447C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone B | 1.1 | To be completed |  | 4 | SEPTEMBER
T-354-9417 | PS5-88-IK-1933C | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-11-04 | PS5-07-03 | PS5 - Milestone F | 5 | Closed | 45 | 24 | NOVEMBER
T-604-9418 | PS5-26-OB-5637A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone C | 2 | To be completed |  | 20 | NOVEMBER
T-961-9419 | PS5-66-UR-9540A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-04-15 | PS5-99-03 | PS5 - Milestone F | 5 | Closed | 22 | 43 | APRIL
T-267-9420 | PS5-92-IK-3511B | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone A | 1 | To be completed |  | 6 | NOVEMBER
T-550-9421 | PS5-54-OB-5054D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-06-01 | PS5-99-02 | PS5 - Milestone E | 4 | Closed | 27 | 20 | JUNE
T-463-9422 | PS5-61-IK-8266D | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone D | 3 | To be completed |  | 19 | AUGUST
T-903-9423 | PS5-48-IK-9896C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone C | 2 | On hold |  | 48 | OCTOBER
T-095-9424 | PS5-52-UR-7057D | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | In progress |  | 27 | AUGUST
T-571-9425 | PS5-54-IK-9664C | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-07-15 | PS5-01-06 | PS5 - Milestone F | 5 | Closed | 47 | 4 | JULY
T-339-9426 | PS5-55-UR-1107B | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-08-21 | PS5-04-01 | PS5 - Milestone C | 2 | Closed | 15 | 19 | AUGUST
T-676-9427 | PS5-36-UR-3251C | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-05-12 | PS5-03-02 | PS5 - Milestone F | 5 | Closed | 31 | 24 | MAY
T-691-9428 | PS5-40-OB-8145C | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | On hold |  | 15 | SEPTEMBER
T-817-9429 | PS5-23-OB-9013B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-08-26 | PS5-07-03 | PS5 - Milestone B | 1.1 | Closed | 44 | 16 | AUGUST
T-924-9430 | PS5-94-IK-1384D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-06-03 | PS5-10-01 | PS5 - Milestone F | 5 | Closed | 46 | 42 | JUNE
T-780-9431 | PS5-54-OB-9278B | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone H | 7 | To be completed |  | 13 | DECEMBER
T-356-9432 | PS5-18-IK-8295C | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone E | 4 | To be completed |  | 9 | OCTOBER
T-284-9433 | PS5-53-OB-5693D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone B | 1.1 | On hold |  | 45 | NOVEMBER
T-018-9434 | PS5-47-UR-4747A | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-09-24 | PS5-07-04 | PS5 - Milestone D | 3 | Closed | 24 | 37 | SEPTEMBER
T-499-9435 | PS5-11-IK-9638A | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | In progress |  | 30 | AUGUST
T-408-9436 | PS5-91-OB-5622C | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone B | 1.1 | In progress |  | 35 | DECEMBER
T-818-9437 | PS5-68-OB-5841B | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone D | 3 | To be completed |  | 18 | SEPTEMBER
T-091-9438 | PS5-64-OB-3522D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-05-27 | PS5-01-05 | PS5 - Milestone I | 8 | Closed | 4 | 33 | MAY
T-184-9439 | PS5-31-OB-6060D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-08-22 | PS5-60-10 | PS5 - Milestone H | 7 | Closed | 34 | 8 | AUGUST
T-443-9440 | PS5-75-OB-3084D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-02-26 | PS5-01-02 | PS5 - Milestone C | 2 | Closed | 38 | 46 | FEBRUARY
T-058-9441 | PS5-63-UR-3087A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone G | 6 | In progress |  | 25 | AUGUST
T-483-9442 | PS5-93-OB-1553A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-11-10 | PS5-12-01 | PS5 - Milestone A | 1 | Closed | 45 | 18 | NOVEMBER
T-308-9443 | PS5-52-UR-8530C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-05-28 | PS5-02-03 | PS5 - Milestone B | 1.1 | Closed | 12 | 21 | MAY
T-661-9444 | PS5-79-UR-6440C | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-11-04 | PS5-62-01 | PS5 - Milestone B | 1.1 | Closed | 41 | 10 | NOVEMBER
T-692-9445 | PS5-52-UR-1367D | CQH02 - AHU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-03-18 | PS5-61-02 | PS5 - Milestone C | 2 | Closed | 9 | 41 | MARCH
T-433-9446 | PS5-93-OB-2347A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone H | 7 | On hold |  | 8 | AUGUST
T-232-9447 | PS5-43-OB-9107D | CQM04 - Vessel | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-01-07 | PS5-05-01 | PS5 - Milestone G | 6 | Closed | 28 | 4 | JANUARY
T-349-9448 | PS5-88-OB-9461A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-11-01 | PS5-09-02 | PS5 - Milestone H | 7 | Closed | 10 | 32 | NOVEMBER
T-241-9449 | PS5-73-OB-2106D | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-08-25 | PS5-06-02 | PS5 - Milestone B | 1.1 | Closed | 7 | 17 | AUGUST
T-825-9450 | PS5-50-OB-2638A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone A | 1 | To be completed |  | 30 | AUGUST
T-866-9451 | PS5-71-OB-8602C | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone F | 5 | In progress |  | 6 | AUGUST
T-420-9452 | PS5-74-IK-9500B | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone C | 2 | In progress |  | 21 | OCTOBER
T-875-9453 | PS5-50-OB-1734C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-08-08 | PS5-01-07 | PS5 - Milestone H | 7 | Closed | 22 | 41 | AUGUST
T-121-9454 | PS5-02-UR-6038B | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | To be completed |  | 37 | DECEMBER
T-810-9455 | PS5-38-OB-2453A | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-05-07 | PS5-07-01 | PS5 - Milestone I | 8 | Closed | 24 | 9 | MAY
T-540-9456 | PS5-83-IK-8534D | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-07-25 | PS5-61-01 | PS5 - Milestone E | 4 | Closed | 30 | 29 | JULY
T-553-9457 | PS5-91-OB-2510D | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-12-24 | PS5-11-01 | PS5 - Milestone C | 2 | Closed | 40 | 48 | DECEMBER
T-075-9458 | PS5-25-OB-4566C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone A | 1 | To be completed |  | 26 | OCTOBER
T-024-9459 | PS5-46-UR-7771A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-05-27 | PS5-63-04 | PS5 - Milestone A | 1 | Closed | 28 | 29 | MAY
T-311-9460 | PS5-53-UR-8002D | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone I | 8 | On hold |  | 48 | AUGUST
T-279-9461 | PS5-83-OB-1656A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone D | 3 | To be completed |  | 10 | NOVEMBER
T-292-9462 | PS5-03-IK-3371A | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone H | 7 | To be completed |  | 10 | NOVEMBER
T-814-9463 | PS5-99-OB-5127C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone F | 5 | To be completed |  | 9 | SEPTEMBER
T-750-9464 | PS5-19-OB-6952D | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone H | 7 | In progress |  | 35 | DECEMBER
T-812-9465 | PS5-22-OB-5388D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone I | 8 | To be completed |  | 10 | DECEMBER
T-462-9466 | PS5-95-OB-9621D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone A | 1 | In progress |  | 12 | DECEMBER
T-737-9467 | PS5-14-UR-2527B | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone A | 1 | To be completed |  | 39 | SEPTEMBER
T-084-9468 | PS5-78-IK-9242A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-04-05 | PS5-01-05 | PS5 - Milestone G | 6 | Closed | 31 | 44 | APRIL
T-242-9469 | PS5-96-UR-8074A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone E | 4 | In progress |  | 31 | AUGUST
T-480-9470 | PS5-39-OB-9883B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone B | 1.1 | To be completed |  | 17 | DECEMBER
T-163-9471 | PS5-06-IK-5130A | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone A | 1 | In progress |  | 46 | AUGUST
T-842-9472 | PS5-69-OB-4619A | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone H | 7 | On hold |  | 16 | SEPTEMBER
T-773-9473 | PS5-11-OB-7809B | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone A | 1 | On hold |  | 4 | OCTOBER
T-966-9474 | PS5-56-IK-6210C | CQH02 - AHU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-11-25 | PS5-03-23 | PS5 - Milestone D | 3 | Closed | 38 | 22 | NOVEMBER
T-411-9475 | PS5-17-IK-6626B | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | On hold |  | 10 | NOVEMBER
T-878-9476 | PS5-79-OB-6106B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-11-20 | PS5-63-01 | PS5 - Milestone G | 6 | Closed | 28 | 44 | NOVEMBER
T-927-9477 | PS5-07-OB-3769A | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | To be completed |  | 11 | SEPTEMBER
T-245-9478 | PS5-48-OB-4601A | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone B | 1.1 | To be completed |  | 35 | NOVEMBER
T-742-9479 | PS5-47-OB-6483D | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-06-13 | PS5-04-01 | PS5 - Milestone F | 5 | Closed | 46 | 43 | JUNE
T-933-9480 | PS5-09-OB-9043D | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone I | 8 | On hold |  | 43 | DECEMBER
T-216-9481 | PS5-07-UR-7093D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone A | 1 | In progress |  | 26 | SEPTEMBER
T-682-9482 | PS5-86-OB-4410C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone E | 4 | To be completed |  | 19 | NOVEMBER
T-192-9483 | PS5-94-OB-6084D | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-07-28 | PS5-06-01 | PS5 - Milestone D | 3 | Closed | 31 | 48 | JULY
T-149-9484 | PS5-17-OB-1575D | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-07-18 | PS5-05-01 | PS5 - Milestone A | 1 | Closed | 30 | 4 | JULY
T-339-9485 | PS5-28-IK-1741D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone E | 4 | In progress |  | 18 | SEPTEMBER
T-420-9486 | PS5-26-UR-3752B | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | To be completed |  | 27 | SEPTEMBER
T-950-9487 | PS5-53-OB-2548A | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-10-11 | PS5-99-01 | PS5 - Milestone D | 3 | Closed | 47 | 48 | OCTOBER
T-756-9488 | PS5-51-OB-6580B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone H | 7 | To be completed |  | 29 | NOVEMBER
T-401-9489 | PS5-85-IK-7045B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone I | 8 | In progress |  | 37 | SEPTEMBER
T-630-9490 | PS5-88-IK-2212C | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | In progress |  | 20 | OCTOBER
T-815-9491 | PS5-02-OB-2104C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-01-26 | PS5-10-02 | PS5 - Milestone F | 5 | Closed | 45 | 13 | JANUARY
T-379-9492 | PS5-40-UR-6007B | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone G | 6 | In progress |  | 13 | AUGUST
T-223-9493 | PS5-36-UR-9699B | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-06-09 | PS5-02-01 | PS5 - Milestone G | 6 | Closed | 4 | 10 | JUNE
T-248-9494 | PS5-70-OB-9382A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone G | 6 | To be completed |  | 24 | NOVEMBER
T-577-9495 | PS5-61-OB-8162D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-11-25 | PS5-02-02 | PS5 - Milestone B | 1.1 | Closed | 16 | 30 | NOVEMBER
T-916-9496 | PS5-94-OB-3251B | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-02-15 | PS5-60-07 | PS5 - Milestone F | 5 | Closed | 18 | 13 | FEBRUARY
T-977-9497 | PS5-40-OB-2039D | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | To be completed |  | 28 | AUGUST
T-564-9498 | PS5-01-OB-9023A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone I | 8 | In progress |  | 22 | OCTOBER
T-431-9499 | PS5-31-OB-9494B | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone D | 3 | To be completed |  | 25 | AUGUST
T-710-9500 | PS5-37-UR-1140B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone F | 5 | In progress |  | 35 | SEPTEMBER
T-324-9501 | PS5-93-UR-2147D | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-03-01 | PS5-11-02 | PS5 - Milestone B | 1.1 | Closed | 16 | 5 | MARCH
T-686-9502 | PS5-26-IK-4977A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-05-11 | PS5-60-07 | PS5 - Milestone C | 2 | Closed | 37 | 41 | MAY
T-443-9503 | PS5-72-OB-5263D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | To be completed |  | 14 | DECEMBER
T-679-9504 | PS5-22-IK-8612A | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-03-15 | PS5-02-02 | PS5 - Milestone C | 2 | Closed | 37 | 13 | MARCH
T-129-9505 | PS5-95-OB-8967A | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-12-13 | PS5-10-03 | PS5 - Milestone F | 5 | Closed | 48 | 35 | DECEMBER
T-627-9506 | PS5-03-OB-8860A | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-03-01 | PS5-60-04 | PS5 - Milestone C | 2 | Closed | 24 | 5 | MARCH
T-147-9507 | PS5-86-OB-3365B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone H | 7 | To be completed |  | 47 | DECEMBER
T-496-9508 | PS5-11-OB-7035C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone A | 1 | In progress |  | 25 | NOVEMBER
T-558-9509 | PS5-58-OB-8014B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-11-11 | PS5-01-08 | PS5 - Milestone D | 3 | Closed | 31 | 24 | NOVEMBER
T-634-9510 | PS5-19-UR-7643B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-10-14 | PS5-10-06 | PS5 - Milestone I | 8 | Closed | 32 | 23 | OCTOBER
T-849-9511 | PS5-78-OB-3121C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-10-17 | PS5-08-01 | PS5 - Milestone A | 1 | Closed | 15 | 45 | OCTOBER
T-449-9512 | PS5-07-IK-3875A | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-08-17 | PS5-04-03 | PS5 - Milestone F | 5 | Closed | 46 | 21 | AUGUST
T-468-9513 | PS5-15-OB-7051B | CQE01 - HV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-03-03 | PS5-10-04 | PS5 - Milestone I | 8 | Closed | 24 | 18 | MARCH
T-305-9514 | PS5-40-OB-7582B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-09 | PS5-60-07 | PS5 - Milestone C | 2 | Closed | 19 | 28 | JULY
T-244-9515 | PS5-53-OB-4915C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-05-21 | PS5-61-01 | PS5 - Milestone G | 6 | Closed | 21 | 31 | MAY
T-531-9516 | PS5-87-OB-7491B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | On hold |  | 30 | AUGUST
T-975-9517 | PS5-36-IK-8686B | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-05-20 | PS5-05-01 | PS5 - Milestone G | 6 | Closed | 19 | 44 | MAY
T-819-9518 | PS5-01-OB-2575C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone A | 1 | To be completed |  | 12 | NOVEMBER
T-069-9519 | PS5-69-IK-7102C | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-05-08 | PS5-60-10 | PS5 - Milestone B | 1.1 | Closed | 27 | 13 | MAY
T-826-9520 | PS5-84-IK-1370B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone I | 8 | To be completed |  | 27 | DECEMBER
T-472-9521 | PS5-28-OB-8884A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-03-20 | PS5-03-02 | PS5 - Milestone F | 5 | Closed | 18 | 5 | MARCH
T-609-9522 | PS5-03-IK-8289B | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-06-05 | PS5-01-07 | PS5 - Milestone A | 1 | Closed | 39 | 34 | JUNE
T-990-9523 | PS5-61-UR-9606A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-03-04 | PS5-04-02 | PS5 - Milestone H | 7 | Closed | 30 | 6 | MARCH
T-348-9524 | PS5-76-IK-3308B | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | In progress |  | 37 | AUGUST
T-013-9525 | PS5-48-IK-7774C | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone A | 1 | To be completed |  | 44 | DECEMBER
T-433-9526 | PS5-70-OB-6211C | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone B | 1.1 | In progress |  | 40 | SEPTEMBER
T-744-9527 | PS5-70-IK-7691C | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-03-19 | PS5-04-03 | PS5 - Milestone E | 4 | Closed | 43 | 37 | MARCH
T-369-9528 | PS5-04-UR-2430A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone I | 8 | To be completed |  | 11 | NOVEMBER
T-513-9529 | PS5-03-OB-8382A | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-10-20 | PS5-01-08 | PS5 - Milestone I | 8 | Closed | 37 | 32 | OCTOBER
T-942-9530 | PS5-67-OB-2308A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-12-03 | PS5-05-02 | PS5 - Milestone D | 3 | Closed | 4 | 30 | DECEMBER
T-841-9531 | PS5-77-OB-9085D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-06-10 | PS5-09-02 | PS5 - Milestone D | 3 | Closed | 20 | 18 | JUNE
T-064-9532 | PS5-96-OB-4862D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone B | 1.1 | In progress |  | 18 | DECEMBER
T-286-9533 | PS5-39-IK-2040D | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-04-07 | PS5-13-01 | PS5 - Milestone C | 2 | Closed | 35 | 18 | APRIL
T-895-9534 | PS5-04-OB-9287C | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-20 | PS5-60-01 | PS5 - Milestone B | 1.1 | Closed | 45 | 39 | JUNE
T-153-9535 | PS5-45-UR-5049C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-03-02 | PS5-01-02 | PS5 - Milestone A | 1 | Closed | 25 | 39 | MARCH
T-104-9536 | PS5-55-IK-7112B | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone I | 8 | In progress |  | 28 | NOVEMBER
T-805-9537 | PS5-59-OB-7771A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone D | 3 | To be completed |  | 41 | DECEMBER
T-965-9538 | PS5-75-UR-4524D | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone C | 2 | To be completed |  | 41 | NOVEMBER
T-641-9539 | PS5-29-OB-1924C | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone F | 5 | In progress |  | 15 | NOVEMBER
T-629-9540 | PS5-95-OB-7240C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone C | 2 | To be completed |  | 48 | NOVEMBER
T-661-9541 | PS5-33-OB-9155A | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone F | 5 | In progress |  | 22 | NOVEMBER
T-851-9542 | PS5-14-OB-9549A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone G | 6 | In progress |  | 46 | OCTOBER
T-101-9543 | PS5-38-OB-3314C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-08-28 | PS5-01-05 | PS5 - Milestone D | 3 | Closed | 41 | 38 | AUGUST
T-097-9544 | PS5-96-IK-8015D | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone C | 2 | In progress |  | 36 | OCTOBER
T-246-9545 | PS5-49-OB-6770C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone I | 8 | On hold |  | 47 | NOVEMBER
T-861-9546 | PS5-28-IK-7524A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone F | 5 | To be completed |  | 34 | SEPTEMBER
T-742-9547 | PS5-76-OB-6703B | CQP04 - Hydrotest | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone D | 3 | In progress |  | 5 | SEPTEMBER
T-810-9548 | PS5-97-OB-6101A | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone F | 5 | To be completed |  | 5 | SEPTEMBER
T-616-9549 | PS5-32-IK-6055A | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | In progress |  | 29 | DECEMBER
T-230-9550 | PS5-80-OB-5528B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone F | 5 | In progress |  | 33 | DECEMBER
T-901-9551 | PS5-10-OB-6331B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-12-15 | PS5-01-09 | PS5 - Milestone G | 6 | Closed | 36 | 8 | DECEMBER
T-735-9552 | PS5-63-OB-5755D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | To be completed |  | 30 | DECEMBER
T-104-9553 | PS5-22-IK-8971B | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone H | 7 | To be completed |  | 6 | DECEMBER
T-140-9554 | PS5-52-UR-9201C | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-12-05 | PS5-01-08 | PS5 - Milestone B | 1.1 | Closed | 6 | 39 | DECEMBER
T-072-9555 | PS5-66-OB-7108D | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | To be completed |  | 19 | SEPTEMBER
T-917-9556 | PS5-99-IK-6047B | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone H | 7 | To be completed |  | 8 | AUGUST
T-346-9557 | PS5-01-UR-9726C | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-02-18 | PS5-04-01 | PS5 - Milestone C | 2 | Closed | 24 | 10 | FEBRUARY
T-684-9558 | PS5-84-IK-8477A | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-05-19 | PS5-04-04 | PS5 - Milestone G | 6 | Closed | 44 | 8 | MAY
T-556-9559 | PS5-42-OB-4537C | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone I | 8 | In progress |  | 8 | OCTOBER
T-940-9560 | PS5-69-IK-8178D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone D | 3 | To be completed |  | 47 | AUGUST
T-631-9561 | PS5-42-OB-4674D | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone D | 3 | To be completed |  | 36 | OCTOBER
T-405-9562 | PS5-68-OB-4149A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | To be completed |  | 24 | NOVEMBER
T-204-9563 | PS5-96-IK-5266A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone E | 4 | To be completed |  | 36 | DECEMBER
T-318-9564 | PS5-26-UR-1968B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone H | 7 | On hold |  | 10 | SEPTEMBER
T-021-9565 | PS5-23-UR-5609B | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone I | 8 | To be completed |  | 6 | AUGUST
T-287-9566 | PS5-90-UR-1954C | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone C | 2 | To be completed |  | 48 | OCTOBER
T-140-9567 | PS5-53-OB-9916B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone C | 2 | In progress |  | 38 | AUGUST
T-015-9568 | PS5-24-OB-7159C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-05-06 | PS5-02-02 | PS5 - Milestone I | 8 | Closed | 6 | 25 | MAY
T-048-9569 | PS5-53-OB-5967C | CQS03 - Deluge System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | To be completed |  | 27 | SEPTEMBER
T-040-9570 | PS5-98-UR-6569B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-09-21 | PS5-08-02 | PS5 - Milestone B | 1.1 | Closed | 26 | 31 | SEPTEMBER
T-389-9571 | PS5-87-UR-6216A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | To be completed |  | 30 | DECEMBER
T-880-9572 | PS5-30-IK-7100D | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-12-16 | PS5-61-07 | PS5 - Milestone F | 5 | Closed | 47 | 33 | DECEMBER
T-997-9573 | PS5-50-IK-4067B | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone E | 4 | In progress |  | 5 | DECEMBER
T-567-9574 | PS5-61-OB-3402D | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone B | 1.1 | In progress |  | 16 | SEPTEMBER
T-904-9575 | PS5-45-UR-4961B | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone B | 1.1 | To be completed |  | 6 | NOVEMBER
T-653-9576 | PS5-20-OB-2974A | CQM01 - Pump Installation | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-05-28 | PS5-09-02 | PS5 - Milestone H | 7 | Closed | 18 | 37 | MAY
T-944-9577 | PS5-31-IK-5564B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-09-22 | PS5-82-02 | PS5 - Milestone A | 1 | Closed | 32 | 28 | SEPTEMBER
T-487-9578 | PS5-77-OB-4144D | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | To be completed |  | 15 | OCTOBER
T-932-9579 | PS5-42-OB-9798A | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone A | 1 | On hold |  | 47 | OCTOBER
T-806-9580 | PS5-95-UR-6166C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone H | 7 | To be completed |  | 37 | SEPTEMBER
T-061-9581 | PS5-97-UR-3075D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-06-26 | PS5-82-02 | PS5 - Milestone C | 2 | Closed | 13 | 27 | JUNE
T-634-9582 | PS5-12-UR-8593C | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone A | 1 | To be completed |  | 35 | DECEMBER
T-275-9583 | PS5-88-IK-3358C | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone F | 5 | In progress |  | 7 | SEPTEMBER
T-452-9584 | PS5-47-OB-2332C | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | To be completed |  | 9 | NOVEMBER
T-844-9585 | PS5-20-OB-6046A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-07-24 | PS5-02-03 | PS5 - Milestone H | 7 | Closed | 11 | 8 | JULY
T-426-9586 | PS5-95-OB-8754D | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | To be completed |  | 30 | OCTOBER
T-108-9587 | PS5-82-OB-6216C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone A | 1 | To be completed |  | 9 | DECEMBER
T-736-9588 | PS5-67-IK-2591A | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone G | 6 | To be completed |  | 34 | OCTOBER
T-251-9589 | PS5-33-OB-2189B | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-12-16 | PS5-01-03 | PS5 - Milestone E | 4 | Closed | 26 | 45 | DECEMBER
T-431-9590 | PS5-18-IK-2031B | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone B | 1.1 | In progress |  | 14 | SEPTEMBER
T-475-9591 | PS5-63-UR-8055D | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone A | 1 | On hold |  | 45 | SEPTEMBER
T-843-9592 | PS5-07-OB-8666A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-10-16 | PS5-01-07 | PS5 - Milestone C | 2 | Closed | 44 | 37 | OCTOBER
T-262-9593 | PS5-73-IK-8583B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-05-23 | PS5-60-01 | PS5 - Milestone H | 7 | Closed | 9 | 25 | MAY
T-572-9594 | PS5-05-OB-3065C | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-04-16 | PS5-99-03 | PS5 - Milestone F | 5 | Closed | 18 | 27 | APRIL
T-573-9595 | PS5-77-IK-9074D | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-09-09 | PS5-12-02 | PS5 - Milestone I | 8 | Closed | 11 | 8 | SEPTEMBER
T-339-9596 | PS5-60-IK-8335D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-12-01 | PS5-01-04 | PS5 - Milestone E | 4 | Closed | 8 | 36 | DECEMBER
T-775-9597 | PS5-17-OB-6858A | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone A | 1 | In progress |  | 39 | OCTOBER
T-812-9598 | PS5-86-OB-4005A | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone F | 5 | In progress |  | 24 | OCTOBER
T-839-9599 | PS5-46-UR-6468C | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone G | 6 | To be completed |  | 40 | DECEMBER
T-631-9600 | PS5-52-IK-9469B | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone I | 8 | In progress |  | 38 | NOVEMBER
T-775-9601 | PS5-22-IK-5507B | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-03-18 | PS5-12-02 | PS5 - Milestone G | 6 | Closed | 33 | 26 | MARCH
T-885-9602 | PS5-64-IK-5890B | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone I | 8 | In progress |  | 43 | OCTOBER
T-982-9603 | PS5-79-OB-5137C | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-09-04 | PS5-63-01 | PS5 - Milestone I | 8 | Closed | 30 | 30 | SEPTEMBER
T-905-9604 | PS5-38-IK-2270B | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-05-18 | PS5-09-03 | PS5 - Milestone F | 5 | Closed | 35 | 25 | MAY
T-778-9605 | PS5-12-IK-2655B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone H | 7 | In progress |  | 22 | AUGUST
T-499-9606 | PS5-64-IK-1665A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone C | 2 | In progress |  | 16 | DECEMBER
T-930-9607 | PS5-21-OB-5220A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | To be completed |  | 42 | OCTOBER
T-191-9608 | PS5-14-UR-9552C | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | To be completed |  | 6 | SEPTEMBER
T-903-9609 | PS5-16-IK-4247A | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone E | 4 | In progress |  | 8 | DECEMBER
T-970-9610 | PS5-88-OB-1329D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone F | 5 | On hold |  | 10 | NOVEMBER
T-140-9611 | PS5-66-OB-9279A | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone I | 8 | To be completed |  | 41 | AUGUST
T-267-9612 | PS5-91-UR-9855C | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone G | 6 | To be completed |  | 5 | NOVEMBER
T-225-9613 | PS5-47-OB-5157D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-05-08 | PS5-04-04 | PS5 - Milestone A | 1 | Closed | 26 | 43 | MAY
T-455-9614 | PS5-66-IK-7023D | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone A | 1 | To be completed |  | 33 | NOVEMBER
T-309-9615 | PS5-59-UR-3917C | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-08-03 | PS5-01-06 | PS5 - Milestone C | 2 | Closed | 36 | 16 | AUGUST
T-931-9616 | PS5-81-UR-7360D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-04-15 | PS5-07-04 | PS5 - Milestone A | 1 | Closed | 8 | 10 | APRIL
T-723-9617 | PS5-31-IK-5351B | CQM04 - Vessel | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone I | 8 | In progress |  | 8 | AUGUST
T-272-9618 | PS5-63-OB-6613B | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone B | 1.1 | In progress |  | 42 | OCTOBER
T-752-9619 | PS5-21-OB-3093B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-02-16 | PS5-01-06 | PS5 - Milestone A | 1 | Closed | 21 | 38 | FEBRUARY
T-119-9620 | PS5-13-OB-8782B | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone D | 3 | To be completed |  | 15 | SEPTEMBER
T-591-9621 | PS5-69-UR-9612D | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-11-04 | PS5-06-01 | PS5 - Milestone D | 3 | Closed | 18 | 27 | NOVEMBER
T-930-9622 | PS5-77-OB-9647C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-12-05 | PS5-06-02 | PS5 - Milestone C | 2 | Closed | 44 | 6 | DECEMBER
T-388-9623 | PS5-72-IK-8569D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone F | 5 | To be completed |  | 36 | NOVEMBER
T-587-9624 | PS5-66-IK-7051C | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-06-23 | PS5-09-03 | PS5 - Milestone A | 1 | Closed | 43 | 33 | JUNE
T-700-9625 | PS5-52-OB-1859C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-03-02 | PS5-10-04 | PS5 - Milestone C | 2 | Closed | 5 | 18 | MARCH
T-860-9626 | PS5-30-UR-9937B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-09-20 | PS5-99-01 | PS5 - Milestone C | 2 | Closed | 9 | 24 | SEPTEMBER
T-350-9627 | PS5-40-IK-2532D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone E | 4 | To be completed |  | 11 | DECEMBER
T-811-9628 | PS5-50-IK-6611D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-07-05 | PS5-07-02 | PS5 - Milestone C | 2 | Closed | 34 | 18 | JULY
T-623-9629 | PS5-46-OB-3342B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-12-05 | PS5-07-04 | PS5 - Milestone A | 1 | Closed | 42 | 5 | DECEMBER
T-164-9630 | PS5-75-OB-9410A | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-08-19 | PS5-10-05 | PS5 - Milestone E | 4 | Closed | 29 | 11 | AUGUST
T-056-9631 | PS5-20-OB-3766C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone I | 8 | To be completed |  | 24 | NOVEMBER
T-008-9632 | PS5-24-IK-5240C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | On hold |  | 16 | SEPTEMBER
T-119-9633 | PS5-75-OB-4830D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone D | 3 | In progress |  | 31 | SEPTEMBER
T-740-9634 | PS5-91-OB-2495A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-06-19 | PS5-08-01 | PS5 - Milestone C | 2 | Closed | 36 | 12 | JUNE
T-088-9635 | PS5-26-OB-3895B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-05-15 | PS5-02-03 | PS5 - Milestone F | 5 | Closed | 7 | 34 | MAY
T-581-9636 | PS5-31-UR-6135B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone I | 8 | In progress |  | 42 | AUGUST
T-451-9637 | PS5-22-OB-1456D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-06-19 | PS5-82-01 | PS5 - Milestone G | 6 | Closed | 28 | 37 | JUNE
T-860-9638 | PS5-15-OB-5532B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-05-27 | PS5-04-01 | PS5 - Milestone H | 7 | Closed | 29 | 22 | MAY
T-275-9639 | PS5-71-OB-9781B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-02-01 | PS5-07-02 | PS5 - Milestone F | 5 | Closed | 8 | 19 | FEBRUARY
T-508-9640 | PS5-66-OB-5611B | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | To be completed |  | 48 | NOVEMBER
T-073-9641 | PS5-63-IK-1838A | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone D | 3 | On hold |  | 33 | DECEMBER
T-235-9642 | PS5-87-OB-4951D | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-10-02 | PS5-07-03 | PS5 - Milestone G | 6 | Closed | 38 | 43 | OCTOBER
T-095-9643 | PS5-42-OB-1210D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone H | 7 | To be completed |  | 12 | NOVEMBER
T-927-9644 | PS5-58-OB-3054A | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone C | 2 | To be completed |  | 26 | NOVEMBER
T-926-9645 | PS5-49-OB-3581C | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-06-23 | PS5-07-04 | PS5 - Milestone B | 1.1 | Closed | 16 | 43 | JUNE
T-111-9646 | PS5-53-UR-6991D | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-06-19 | PS5-01-09 | PS5 - Milestone G | 6 | Closed | 6 | 22 | JUNE
T-978-9647 | PS5-85-OB-8701B | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | To be completed |  | 4 | SEPTEMBER
T-365-9648 | PS5-38-UR-5033C | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone B | 1.1 | To be completed |  | 32 | OCTOBER
T-698-9649 | PS5-18-OB-4570C | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-10-24 | PS5-99-02 | PS5 - Milestone F | 5 | Closed | 8 | 45 | OCTOBER
T-326-9650 | PS5-49-OB-7174B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-11-01 | PS5-82-07 | PS5 - Milestone A | 1 | Closed | 6 | 47 | NOVEMBER
T-434-9651 | PS5-58-UR-2952C | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone I | 8 | To be completed |  | 40 | OCTOBER
T-638-9652 | PS5-34-IK-1397C | CQM01 - Pump Installation | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone C | 2 | In progress |  | 7 | DECEMBER
T-718-9653 | PS5-53-IK-4404D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-07-18 | PS5-62-01 | PS5 - Milestone G | 6 | Closed | 44 | 17 | JULY
T-324-9654 | PS5-83-OB-8982B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | To be completed |  | 19 | AUGUST
T-858-9655 | PS5-33-OB-4404A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone D | 3 | To be completed |  | 45 | AUGUST
T-533-9656 | PS5-36-OB-4381D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | In progress |  | 45 | OCTOBER
T-812-9657 | PS5-78-OB-4346D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone F | 5 | In progress |  | 43 | AUGUST
T-785-9658 | PS5-78-OB-5958A | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone C | 2 | To be completed |  | 18 | SEPTEMBER
T-462-9659 | PS5-92-UR-4938B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone D | 3 | To be completed |  | 30 | SEPTEMBER
T-243-9660 | PS5-22-UR-9493A | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-02-13 | PS5-03-02 | PS5 - Milestone D | 3 | Closed | 24 | 36 | FEBRUARY
T-108-9661 | PS5-67-OB-4711B | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-01-19 | PS5-03-01 | PS5 - Milestone H | 7 | Closed | 12 | 5 | JANUARY
T-866-9662 | PS5-64-OB-1412A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone H | 7 | To be completed |  | 26 | NOVEMBER
T-007-9663 | PS5-23-UR-7857A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-04-18 | PS5-10-05 | PS5 - Milestone B | 1.1 | Closed | 42 | 6 | APRIL
T-156-9664 | PS5-77-UR-2921B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-02-09 | PS5-02-01 | PS5 - Milestone C | 2 | Closed | 32 | 44 | FEBRUARY
T-891-9665 | PS5-45-OB-1293C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone D | 3 | On hold |  | 22 | NOVEMBER
T-968-9666 | PS5-99-OB-1500C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone E | 4 | In progress |  | 11 | DECEMBER
T-243-9667 | PS5-84-OB-4784B | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-03-13 | PS5-03-23 | PS5 - Milestone B | 1.1 | Closed | 5 | 7 | MARCH
T-513-9668 | PS5-03-OB-8980D | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-12-03 | PS5-03-02 | PS5 - Milestone G | 6 | Closed | 39 | 31 | DECEMBER
T-390-9669 | PS5-15-UR-3404D | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-07-04 | PS5-82-02 | PS5 - Milestone B | 1.1 | Closed | 45 | 13 | JULY
T-275-9670 | PS5-76-OB-4428D | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-07-22 | PS5-02-01 | PS5 - Milestone E | 4 | Closed | 9 | 14 | JULY
T-705-9671 | PS5-40-IK-7362A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-12-05 | PS5-99-03 | PS5 - Milestone G | 6 | Closed | 23 | 25 | DECEMBER
T-537-9672 | PS5-22-OB-1249B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-12-22 | PS5-63-04 | PS5 - Milestone A | 1 | Closed | 6 | 16 | DECEMBER
T-503-9673 | PS5-92-OB-4283D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone D | 3 | In progress |  | 20 | AUGUST
T-816-9674 | PS5-16-IK-4224C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | To be completed |  | 42 | OCTOBER
T-389-9675 | PS5-30-OB-9415C | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone G | 6 | To be completed |  | 47 | OCTOBER
T-098-9676 | PS5-92-UR-6769B | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-04-15 | PS5-99-03 | PS5 - Milestone G | 6 | Closed | 8 | 21 | APRIL
T-182-9677 | PS5-68-UR-4244A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-10-13 | PS5-10-02 | PS5 - Milestone G | 6 | Closed | 24 | 5 | OCTOBER
T-911-9678 | PS5-51-OB-1987D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | In progress |  | 41 | OCTOBER
T-976-9679 | PS5-01-IK-2948D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone G | 6 | In progress |  | 28 | AUGUST
T-419-9680 | PS5-42-OB-2282A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | On hold |  | 46 | AUGUST
T-046-9681 | PS5-21-OB-6458B | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-01-15 | PS5-03-01 | PS5 - Milestone B | 1.1 | Closed | 23 | 16 | JANUARY
T-838-9682 | PS5-09-IK-8912C | CQM03 - Heat Exchanger | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-06-28 | PS5-10-05 | PS5 - Milestone H | 7 | Closed | 32 | 41 | JUNE
T-853-9683 | PS5-88-IK-1718B | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone A | 1 | On hold |  | 36 | DECEMBER
T-468-9684 | PS5-68-IK-4837D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone H | 7 | To be completed |  | 9 | AUGUST
T-875-9685 | PS5-96-OB-4940A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-05-28 | PS5-06-01 | PS5 - Milestone A | 1 | Closed | 40 | 20 | MAY
T-322-9686 | PS5-13-OB-6386A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-09-26 | PS5-11-02 | PS5 - Milestone B | 1.1 | Closed | 27 | 40 | SEPTEMBER
T-976-9687 | PS5-13-OB-6775B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | To be completed |  | 47 | SEPTEMBER
T-508-9688 | PS5-90-OB-8988A | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-10-19 | PS5-07-03 | PS5 - Milestone E | 4 | Closed | 21 | 7 | OCTOBER
T-351-9689 | PS5-20-IK-5568C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-11-24 | PS5-05-01 | PS5 - Milestone C | 2 | Closed | 19 | 13 | NOVEMBER
T-852-9690 | PS5-56-UR-9889C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-09-26 | PS5-60-01 | PS5 - Milestone B | 1.1 | Closed | 48 | 10 | SEPTEMBER
T-993-9691 | PS5-50-UR-3447D | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-17 | PS5-60-04 | PS5 - Milestone G | 6 | Closed | 12 | 19 | MAY
T-091-9692 | PS5-64-OB-7421D | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone G | 6 | On hold |  | 45 | AUGUST
T-558-9693 | PS5-88-OB-1088B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone C | 2 | To be completed |  | 28 | AUGUST
T-127-9694 | PS5-20-UR-7847A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-09-26 | PS5-60-04 | PS5 - Milestone C | 2 | Closed | 40 | 6 | SEPTEMBER
T-043-9695 | PS5-04-UR-2433D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone F | 5 | In progress |  | 43 | AUGUST
T-157-9696 | PS5-66-OB-7757B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-04-14 | PS5-13-01 | PS5 - Milestone D | 3 | Closed | 38 | 14 | APRIL
T-661-9697 | PS5-18-OB-5200A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone I | 8 | In progress |  | 29 | OCTOBER
T-842-9698 | PS5-97-OB-6511B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone F | 5 | To be completed |  | 29 | NOVEMBER
T-657-9699 | PS5-62-OB-9004D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-08-04 | PS5-61-02 | PS5 - Milestone C | 2 | Closed | 30 | 29 | AUGUST
T-855-9700 | PS5-15-OB-5258C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | In progress |  | 26 | OCTOBER
T-019-9701 | PS5-56-OB-9492C | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone A | 1 | On hold |  | 22 | SEPTEMBER
T-875-9702 | PS5-50-UR-3576C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-11-16 | PS5-08-02 | PS5 - Milestone A | 1 | Closed | 22 | 35 | NOVEMBER
T-486-9703 | PS5-06-IK-8710A | CQM03 - Heat Exchanger | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone G | 6 | To be completed |  | 23 | AUGUST
T-266-9704 | PS5-82-OB-4211D | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone B | 1.1 | To be completed |  | 35 | OCTOBER
T-469-9705 | PS5-51-OB-3421D | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | To be completed |  | 20 | SEPTEMBER
T-643-9706 | PS5-89-IK-1247B | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone A | 1 | To be completed |  | 36 | OCTOBER
T-751-9707 | PS5-33-UR-5766C | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-06-15 | PS5-01-02 | PS5 - Milestone C | 2 | Closed | 40 | 21 | JUNE
T-304-9708 | PS5-86-IK-6159C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-09-22 | PS5-07-01 | PS5 - Milestone H | 7 | Closed | 14 | 43 | SEPTEMBER
T-907-9709 | PS5-13-OB-5341C | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone D | 3 | To be completed |  | 22 | AUGUST
T-163-9710 | PS5-76-OB-9725B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-04-14 | PS5-02-01 | PS5 - Milestone F | 5 | Closed | 14 | 44 | APRIL
T-728-9711 | PS5-37-OB-9589B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone H | 7 | To be completed |  | 21 | OCTOBER
T-354-9712 | PS5-89-UR-7035B | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | In progress |  | 25 | NOVEMBER
T-250-9713 | PS5-41-OB-6143D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-11-19 | PS5-01-05 | PS5 - Milestone H | 7 | Closed | 31 | 29 | NOVEMBER
T-967-9714 | PS5-34-UR-2416C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-12-25 | PS5-02-03 | PS5 - Milestone H | 7 | Closed | 34 | 15 | DECEMBER
T-837-9715 | PS5-93-IK-6115C | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone H | 7 | In progress |  | 28 | NOVEMBER
T-837-9716 | PS5-99-OB-7362B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-04-13 | PS5-01-04 | PS5 - Milestone E | 4 | Closed | 23 | 28 | APRIL
T-283-9717 | PS5-48-IK-5957C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone D | 3 | To be completed |  | 22 | DECEMBER
T-426-9718 | PS5-42-UR-2795C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone G | 6 | On hold |  | 38 | NOVEMBER
T-573-9719 | PS5-48-IK-5631A | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | To be completed |  | 7 | OCTOBER
T-237-9720 | PS5-99-OB-3460C | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone G | 6 | On hold |  | 7 | NOVEMBER
T-434-9721 | PS5-61-OB-9629B | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone I | 8 | To be completed |  | 21 | AUGUST
T-587-9722 | PS5-79-UR-5620A | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | In progress |  | 33 | DECEMBER
T-333-9723 | PS5-42-OB-9919C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-04-21 | PS5-06-02 | PS5 - Milestone A | 1 | Closed | 32 | 24 | APRIL
T-707-9724 | PS5-79-IK-1381D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-08-07 | PS5-06-03 | PS5 - Milestone E | 4 | Closed | 43 | 36 | AUGUST
T-730-9725 | PS5-92-UR-3000A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone F | 5 | To be completed |  | 44 | OCTOBER
T-857-9726 | PS5-06-UR-5324D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone C | 2 | On hold |  | 7 | OCTOBER
T-244-9727 | PS5-30-OB-5473A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone D | 3 | To be completed |  | 20 | NOVEMBER
T-752-9728 | PS5-18-OB-8753A | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone G | 6 | To be completed |  | 10 | DECEMBER
T-126-9729 | PS5-29-UR-5775B | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-07-14 | PS5-99-01 | PS5 - Milestone D | 3 | Closed | 31 | 4 | JULY
T-223-9730 | PS5-56-IK-4209B | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-08-12 | PS5-12-01 | PS5 - Milestone I | 8 | Closed | 8 | 43 | AUGUST
T-098-9731 | PS5-16-IK-8693D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone H | 7 | To be completed |  | 45 | SEPTEMBER
T-959-9732 | PS5-67-OB-4516C | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone A | 1 | To be completed |  | 28 | SEPTEMBER
T-136-9733 | PS5-79-OB-9053B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone A | 1 | To be completed |  | 30 | OCTOBER
T-339-9734 | PS5-28-OB-6646B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-10-02 | PS5-63-04 | PS5 - Milestone E | 4 | Closed | 17 | 20 | OCTOBER
T-521-9735 | PS5-77-OB-3330C | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-12-24 | PS5-10-05 | PS5 - Milestone G | 6 | Closed | 9 | 29 | DECEMBER
T-899-9736 | PS5-04-IK-1181B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone A | 1 | On hold |  | 20 | AUGUST
T-004-9737 | PS5-21-OB-5280D | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-01-14 | PS5-07-01 | PS5 - Milestone G | 6 | Closed | 41 | 14 | JANUARY
T-433-9738 | PS5-22-OB-7203B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-03-12 | PS5-01-01 | PS5 - Milestone G | 6 | Closed | 29 | 36 | MARCH
T-458-9739 | PS5-71-UR-4285A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-07-15 | PS5-61-01 | PS5 - Milestone F | 5 | Closed | 19 | 27 | JULY
T-489-9740 | PS5-82-IK-6814D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-02-22 | PS5-99-02 | PS5 - Milestone E | 4 | Closed | 42 | 43 | FEBRUARY
T-590-9741 | PS5-23-IK-6661B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-05-11 | PS5-06-03 | PS5 - Milestone B | 1.1 | Closed | 46 | 38 | MAY
T-686-9742 | PS5-77-OB-3727A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone I | 8 | To be completed |  | 36 | SEPTEMBER
T-150-9743 | PS5-29-OB-9735D | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone H | 7 | In progress |  | 13 | NOVEMBER
T-873-9744 | PS5-23-OB-3016A | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-06-28 | PS5-99-03 | PS5 - Milestone D | 3 | Closed | 23 | 34 | JUNE
T-521-9745 | PS5-67-IK-5357B | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone G | 6 | To be completed |  | 5 | SEPTEMBER
T-099-9746 | PS5-84-OB-9895D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-03-26 | PS5-01-07 | PS5 - Milestone D | 3 | Closed | 43 | 18 | MARCH
T-143-9747 | PS5-20-UR-3803A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-07-06 | PS5-61-02 | PS5 - Milestone G | 6 | Closed | 5 | 11 | JULY
T-414-9748 | PS5-61-OB-7758D | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone G | 6 | To be completed |  | 48 | OCTOBER
T-753-9749 | PS5-64-OB-3335B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-01-14 | PS5-61-07 | PS5 - Milestone I | 8 | Closed | 27 | 6 | JANUARY
T-515-9750 | PS5-54-OB-4907C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | To be completed |  | 43 | NOVEMBER
T-626-9751 | PS5-37-OB-2670B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone A | 1 | On hold |  | 24 | AUGUST
T-564-9752 | PS5-95-UR-1268C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | On hold |  | 45 | NOVEMBER
T-324-9753 | PS5-33-IK-7998D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-02-05 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 25 | 48 | FEBRUARY
T-074-9754 | PS5-59-OB-8982B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone E | 4 | To be completed |  | 5 | SEPTEMBER
T-597-9755 | PS5-74-OB-1362A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone H | 7 | To be completed |  | 46 | NOVEMBER
T-055-9756 | PS5-28-UR-6750C | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-11-02 | PS5-01-01 | PS5 - Milestone D | 3 | Closed | 28 | 27 | NOVEMBER
T-490-9757 | PS5-01-OB-9606A | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone I | 8 | To be completed |  | 45 | OCTOBER
T-883-9758 | PS5-33-OB-8953C | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone A | 1 | To be completed |  | 9 | DECEMBER
T-718-9759 | PS5-33-IK-1584C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone I | 8 | On hold |  | 32 | OCTOBER
T-404-9760 | PS5-51-OB-7119A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone I | 8 | To be completed |  | 36 | OCTOBER
T-233-9761 | PS5-23-OB-3381D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone A | 1 | On hold |  | 10 | SEPTEMBER
T-035-9762 | PS5-89-IK-8292A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-11-10 | PS5-04-01 | PS5 - Milestone I | 8 | Closed | 23 | 17 | NOVEMBER
T-489-9763 | PS5-12-IK-6411C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone C | 2 | In progress |  | 40 | SEPTEMBER
T-038-9764 | PS5-51-OB-7738B | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-08-08 | PS5-10-06 | PS5 - Milestone A | 1 | Closed | 43 | 31 | AUGUST
T-224-9765 | PS5-29-OB-6641D | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone C | 2 | To be completed |  | 8 | DECEMBER
T-151-9766 | PS5-58-OB-4597B | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone C | 2 | In progress |  | 19 | OCTOBER
T-575-9767 | PS5-37-UR-1785A | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-03-18 | PS5-01-01 | PS5 - Milestone H | 7 | Closed | 33 | 29 | MARCH
T-643-9768 | PS5-62-IK-7519B | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone D | 3 | On hold |  | 45 | DECEMBER
T-357-9769 | PS5-63-OB-5379C | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-08-23 | PS5-08-01 | PS5 - Milestone H | 7 | Closed | 17 | 20 | AUGUST
T-169-9770 | PS5-20-IK-7824C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-10-16 | PS5-08-01 | PS5 - Milestone A | 1 | Closed | 25 | 37 | OCTOBER
T-286-9771 | PS5-64-OB-4901A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone I | 8 | To be completed |  | 13 | DECEMBER
T-156-9772 | PS5-20-IK-7046C | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-01-10 | PS5-05-02 | PS5 - Milestone A | 1 | Closed | 34 | 29 | JANUARY
T-115-9773 | PS5-17-OB-8330C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-09-12 | PS5-07-02 | PS5 - Milestone B | 1.1 | Closed | 14 | 26 | SEPTEMBER
T-121-9774 | PS5-93-UR-9870B | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | On hold |  | 16 | SEPTEMBER
T-265-9775 | PS5-69-OB-7108A | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-08-13 | PS5-63-01 | PS5 - Milestone G | 6 | Closed | 18 | 16 | AUGUST
T-914-9776 | PS5-31-UR-4063D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone C | 2 | To be completed |  | 21 | SEPTEMBER
T-136-9777 | PS5-08-UR-6733B | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone I | 8 | In progress |  | 20 | SEPTEMBER
T-172-9778 | PS5-85-OB-4628D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | To be completed |  | 6 | DECEMBER
T-798-9779 | PS5-86-IK-3560D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-11-27 | PS5-10-04 | PS5 - Milestone F | 5 | Closed | 42 | 11 | NOVEMBER
T-111-9780 | PS5-94-OB-5327A | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone B | 1.1 | To be completed |  | 20 | DECEMBER
T-066-9781 | PS5-41-OB-4060B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-11-17 | PS5-63-04 | PS5 - Milestone B | 1.1 | Closed | 19 | 44 | NOVEMBER
T-796-9782 | PS5-56-UR-8914A | CQX04 - Painting & Coating | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-03-14 | PS5-82-01 | PS5 - Milestone C | 2 | Closed | 31 | 25 | MARCH
T-410-9783 | PS5-23-OB-3496D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-01-27 | PS5-11-01 | PS5 - Milestone H | 7 | Closed | 44 | 6 | JANUARY
T-187-9784 | PS5-76-OB-6296B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-06-14 | PS5-10-01 | PS5 - Milestone C | 2 | Closed | 12 | 22 | JUNE
T-856-9785 | PS5-39-UR-8863C | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-12-16 | PS5-10-01 | PS5 - Milestone A | 1 | Closed | 26 | 10 | DECEMBER
T-416-9786 | PS5-10-OB-2194B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone I | 8 | To be completed |  | 4 | NOVEMBER
T-223-9787 | PS5-02-OB-3407C | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone H | 7 | In progress |  | 33 | DECEMBER
T-905-9788 | PS5-63-IK-8263C | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-02-24 | PS5-82-07 | PS5 - Milestone D | 3 | Closed | 22 | 45 | FEBRUARY
T-887-9789 | PS5-66-IK-2965A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-08-15 | PS5-61-01 | PS5 - Milestone F | 5 | Closed | 31 | 13 | AUGUST
T-305-9790 | PS5-73-OB-8959D | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone B | 1.1 | To be completed |  | 30 | SEPTEMBER
T-042-9791 | PS5-58-IK-7272A | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-08-17 | PS5-10-05 | PS5 - Milestone C | 2 | Closed | 20 | 23 | AUGUST
T-739-9792 | PS5-17-OB-4925B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-26 | PS5-60-04 | PS5 - Milestone H | 7 | Closed | 10 | 33 | APRIL
T-450-9793 | PS5-98-OB-7716C | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-10-17 | PS5-99-02 | PS5 - Milestone A | 1 | Closed | 25 | 30 | OCTOBER
T-315-9794 | PS5-27-OB-5474A | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | To be completed |  | 31 | SEPTEMBER
T-494-9795 | PS5-59-OB-3863D | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-11-05 | PS5-82-02 | PS5 - Milestone E | 4 | Closed | 16 | 40 | NOVEMBER
T-751-9796 | PS5-78-IK-1391C | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone D | 3 | To be completed |  | 29 | OCTOBER
T-450-9797 | PS5-69-IK-6857A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone H | 7 | To be completed |  | 14 | OCTOBER
T-470-9798 | PS5-96-OB-6022D | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone H | 7 | In progress |  | 6 | NOVEMBER
T-398-9799 | PS5-16-UR-4693B | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-06-10 | PS5-10-04 | PS5 - Milestone A | 1 | Closed | 14 | 36 | JUNE
T-432-9800 | PS5-90-OB-9163C | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone H | 7 | To be completed |  | 12 | OCTOBER
T-623-9801 | PS5-37-IK-5660A | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone I | 8 | On hold |  | 9 | DECEMBER
T-768-9802 | PS5-89-UR-2694B | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | To be completed |  | 42 | NOVEMBER
T-214-9803 | PS5-25-OB-4839D | CQM01 - Pump Installation | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone I | 8 | To be completed |  | 43 | OCTOBER
T-536-9804 | PS5-47-IK-7098A | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone E | 4 | To be completed |  | 28 | OCTOBER
T-116-9805 | PS5-79-UR-3451C | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone E | 4 | On hold |  | 14 | SEPTEMBER
T-125-9806 | PS5-05-OB-3193D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone C | 2 | To be completed |  | 35 | AUGUST
T-898-9807 | PS5-72-UR-7002C | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone F | 5 | In progress |  | 13 | AUGUST
T-723-9808 | PS5-06-UR-2932B | CQE01 - HV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | In progress |  | 18 | DECEMBER
T-230-9809 | PS5-68-OB-7540B | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone H | 7 | To be completed |  | 42 | SEPTEMBER
T-004-9810 | PS5-38-UR-2843C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | To be completed |  | 26 | DECEMBER
T-213-9811 | PS5-06-UR-8359B | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-11-26 | PS5-07-01 | PS5 - Milestone H | 7 | Closed | 27 | 44 | NOVEMBER
T-042-9812 | PS5-24-IK-2493A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone C | 2 | To be completed |  | 10 | DECEMBER
T-518-9813 | PS5-45-IK-4547B | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone C | 2 | On hold |  | 31 | OCTOBER
T-580-9814 | PS5-70-OB-6468D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone F | 5 | To be completed |  | 33 | SEPTEMBER
T-134-9815 | PS5-10-IK-3863D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone G | 6 | In progress |  | 46 | AUGUST
T-333-9816 | PS5-45-IK-8918A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-01-21 | PS5-01-01 | PS5 - Milestone E | 4 | Closed | 9 | 4 | JANUARY
T-092-9817 | PS5-82-OB-1626B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone H | 7 | To be completed |  | 19 | NOVEMBER
T-301-9818 | PS5-44-OB-3688B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone B | 1.1 | In progress |  | 36 | AUGUST
T-038-9819 | PS5-22-OB-6858C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-11-28 | PS5-06-01 | PS5 - Milestone I | 8 | Closed | 22 | 37 | NOVEMBER
T-557-9820 | PS5-07-OB-1203D | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-10-14 | PS5-61-01 | PS5 - Milestone H | 7 | Closed | 6 | 10 | OCTOBER
T-814-9821 | PS5-97-IK-5568D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-11-25 | PS5-04-02 | PS5 - Milestone E | 4 | Closed | 41 | 25 | NOVEMBER
T-696-9822 | PS5-35-UR-9107A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone I | 8 | On hold |  | 21 | SEPTEMBER
T-028-9823 | PS5-48-UR-5067A | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone C | 2 | In progress |  | 5 | DECEMBER
T-507-9824 | PS5-59-OB-7528D | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-06-10 | PS5-05-02 | PS5 - Milestone G | 6 | Closed | 40 | 24 | JUNE
T-961-9825 | PS5-23-OB-1047C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | To be completed |  | 10 | NOVEMBER
T-677-9826 | PS5-42-OB-3770A | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-17 | PS5-60-01 | PS5 - Milestone I | 8 | Closed | 40 | 42 | FEBRUARY
T-155-9827 | PS5-74-IK-8797B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone G | 6 | To be completed |  | 44 | NOVEMBER
T-967-9828 | PS5-83-UR-3206A | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone G | 6 | In progress |  | 45 | SEPTEMBER
T-487-9829 | PS5-75-OB-1548D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-05-16 | PS5-01-07 | PS5 - Milestone F | 5 | Closed | 7 | 12 | MAY
T-072-9830 | PS5-51-IK-9348A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone C | 2 | To be completed |  | 11 | SEPTEMBER
T-004-9831 | PS5-22-UR-8349C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone E | 4 | To be completed |  | 47 | SEPTEMBER
T-123-9832 | PS5-34-OB-1952A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | In progress |  | 38 | AUGUST
T-052-9833 | PS5-27-UR-3672B | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-12 | PS5-60-10 | PS5 - Milestone B | 1.1 | Closed | 29 | 21 | JUNE
T-844-9834 | PS5-68-IK-9529C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-05-18 | PS5-01-07 | PS5 - Milestone E | 4 | Closed | 10 | 48 | MAY
T-977-9835 | PS5-13-IK-6117C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-11-03 | PS5-11-03 | PS5 - Milestone F | 5 | Closed | 19 | 8 | NOVEMBER
T-691-9836 | PS5-71-IK-9090A | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | On hold |  | 4 | OCTOBER
T-886-9837 | PS5-84-OB-9973A | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone A | 1 | In progress |  | 37 | AUGUST
T-902-9838 | PS5-56-OB-9550B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone I | 8 | To be completed |  | 20 | NOVEMBER
T-842-9839 | PS5-40-OB-7631D | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone I | 8 | On hold |  | 35 | AUGUST
T-241-9840 | PS5-12-OB-6262A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone A | 1 | To be completed |  | 47 | AUGUST
T-063-9841 | PS5-65-OB-7709D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone C | 2 | On hold |  | 27 | AUGUST
T-972-9842 | PS5-88-UR-6080A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-12-25 | PS5-09-03 | PS5 - Milestone D | 3 | Closed | 26 | 39 | DECEMBER
T-618-9843 | PS5-08-OB-3063D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone I | 8 | To be completed |  | 10 | SEPTEMBER
T-266-9844 | PS5-23-OB-8700A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-12-13 | PS5-01-05 | PS5 - Milestone F | 5 | Closed | 26 | 6 | DECEMBER
T-939-9845 | PS5-80-UR-3123A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-04-12 | PS5-61-02 | PS5 - Milestone C | 2 | Closed | 25 | 45 | APRIL
T-934-9846 | PS5-80-UR-4372B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-01-14 | PS5-04-03 | PS5 - Milestone A | 1 | Closed | 20 | 43 | JANUARY
T-224-9847 | PS5-52-IK-8559A | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-04-03 | PS5-82-07 | PS5 - Milestone G | 6 | Closed | 4 | 30 | APRIL
T-883-9848 | PS5-71-IK-5496C | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | To be completed |  | 8 | DECEMBER
T-256-9849 | PS5-40-IK-6517A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | In progress |  | 17 | SEPTEMBER
T-090-9850 | PS5-49-OB-8644D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone G | 6 | In progress |  | 26 | OCTOBER
T-294-9851 | PS5-10-OB-8227B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone E | 4 | On hold |  | 12 | NOVEMBER
T-820-9852 | PS5-62-OB-9742C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone B | 1.1 | To be completed |  | 26 | AUGUST
T-569-9853 | PS5-50-OB-5911A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone D | 3 | To be completed |  | 39 | SEPTEMBER
T-951-9854 | PS5-02-IK-5848A | CQX04 - Painting & Coating | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-04-25 | PS5-02-01 | PS5 - Milestone E | 4 | Closed | 41 | 33 | APRIL
T-448-9855 | PS5-37-IK-6541A | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone H | 7 | On hold |  | 31 | SEPTEMBER
T-308-9856 | PS5-33-UR-1963D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-01-12 | PS5-63-01 | PS5 - Milestone E | 4 | Closed | 42 | 46 | JANUARY
T-243-9857 | PS5-81-UR-6239A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | In progress |  | 13 | DECEMBER
T-594-9858 | PS5-90-UR-6116D | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-06-14 | PS5-05-03 | PS5 - Milestone H | 7 | Closed | 40 | 40 | JUNE
T-055-9859 | PS5-44-OB-5833D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone B | 1.1 | In progress |  | 41 | OCTOBER
T-574-9860 | PS5-59-OB-3565A | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone F | 5 | In progress |  | 7 | AUGUST
T-890-9861 | PS5-15-UR-9893D | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone F | 5 | In progress |  | 12 | OCTOBER
T-276-9862 | PS5-38-IK-8543C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone I | 8 | To be completed |  | 38 | NOVEMBER
T-659-9863 | PS5-92-UR-2012A | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-07-02 | PS5-03-03 | PS5 - Milestone B | 1.1 | Closed | 28 | 45 | JULY
T-989-9864 | PS5-33-IK-7076B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone B | 1.1 | To be completed |  | 4 | SEPTEMBER
T-087-9865 | PS5-70-IK-2702A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-08 | PS5-60-04 | PS5 - Milestone D | 3 | Closed | 34 | 13 | APRIL
T-379-9866 | PS5-41-IK-2045D | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | In progress |  | 44 | DECEMBER
T-195-9867 | PS5-63-OB-7294B | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone E | 4 | On hold |  | 22 | SEPTEMBER
T-783-9868 | PS5-86-OB-3941C | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone D | 3 | In progress |  | 19 | AUGUST
T-461-9869 | PS5-48-OB-5722D | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-02-11 | PS5-61-01 | PS5 - Milestone G | 6 | Closed | 44 | 31 | FEBRUARY
T-779-9870 | PS5-58-OB-2373B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-03-01 | PS5-01-03 | PS5 - Milestone H | 7 | Closed | 39 | 44 | MARCH
T-175-9871 | PS5-35-OB-6644A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone F | 5 | To be completed |  | 29 | AUGUST
T-696-9872 | PS5-22-UR-1561D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone B | 1.1 | To be completed |  | 18 | NOVEMBER
T-103-9873 | PS5-08-OB-6464C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | To be completed |  | 39 | DECEMBER
T-677-9874 | PS5-37-OB-6339A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | To be completed |  | 24 | AUGUST
T-071-9875 | PS5-91-OB-1339A | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-08-03 | PS5-61-07 | PS5 - Milestone I | 8 | Closed | 31 | 10 | AUGUST
T-670-9876 | PS5-47-IK-2780D | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-02-22 | PS5-11-03 | PS5 - Milestone G | 6 | Closed | 35 | 38 | FEBRUARY
T-024-9877 | PS5-48-UR-1178C | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone C | 2 | In progress |  | 43 | DECEMBER
T-824-9878 | PS5-47-OB-5815B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-09-24 | PS5-01-02 | PS5 - Milestone F | 5 | Closed | 20 | 38 | SEPTEMBER
T-592-9879 | PS5-31-IK-7561A | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone H | 7 | In progress |  | 48 | OCTOBER
T-383-9880 | PS5-15-IK-6188D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-09-21 | PS5-12-01 | PS5 - Milestone D | 3 | Closed | 15 | 30 | SEPTEMBER
T-364-9881 | PS5-22-OB-5104D | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone B | 1.1 | In progress |  | 13 | DECEMBER
T-421-9882 | PS5-20-UR-7132D | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone G | 6 | To be completed |  | 37 | AUGUST
T-093-9883 | PS5-28-OB-7654A | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-11-08 | PS5-09-03 | PS5 - Milestone F | 5 | Closed | 24 | 16 | NOVEMBER
T-414-9884 | PS5-60-OB-9395A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone A | 1 | To be completed |  | 16 | SEPTEMBER
T-522-9885 | PS5-43-OB-5120B | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-03-19 | PS5-03-01 | PS5 - Milestone C | 2 | Closed | 35 | 12 | MARCH
T-693-9886 | PS5-37-OB-5639D | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-04-22 | PS5-02-02 | PS5 - Milestone E | 4 | Closed | 21 | 16 | APRIL
T-817-9887 | PS5-77-UR-3505C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-11-09 | PS5-82-07 | PS5 - Milestone G | 6 | Closed | 11 | 36 | NOVEMBER
T-128-9888 | PS5-79-IK-6196B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone C | 2 | To be completed |  | 28 | OCTOBER
T-154-9889 | PS5-09-IK-3441A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone E | 4 | In progress |  | 8 | AUGUST
T-779-9890 | PS5-14-UR-5073A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-04-18 | PS5-09-02 | PS5 - Milestone E | 4 | Closed | 31 | 42 | APRIL
T-812-9891 | PS5-26-OB-9538B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-02-18 | PS5-82-02 | PS5 - Milestone F | 5 | Closed | 8 | 19 | FEBRUARY
T-662-9892 | PS5-29-OB-2161C | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-07-25 | PS5-04-03 | PS5 - Milestone I | 8 | Closed | 36 | 19 | JULY
T-492-9893 | PS5-54-UR-9673C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-01-10 | PS5-01-06 | PS5 - Milestone C | 2 | Closed | 43 | 20 | JANUARY
T-589-9894 | PS5-51-OB-5666A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone H | 7 | To be completed |  | 30 | AUGUST
T-908-9895 | PS5-02-OB-9308D | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone A | 1 | To be completed |  | 35 | NOVEMBER
T-467-9896 | PS5-69-OB-8380C | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone G | 6 | To be completed |  | 48 | AUGUST
T-277-9897 | PS5-94-IK-6148A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone G | 6 | To be completed |  | 21 | DECEMBER
T-797-9898 | PS5-09-OB-6154D | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | To be completed |  | 47 | AUGUST
T-557-9899 | PS5-59-IK-3986B | CQS03 - Deluge System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | To be completed |  | 18 | AUGUST
T-165-9900 | PS5-46-IK-2885C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | In progress |  | 34 | NOVEMBER
T-292-9901 | PS5-51-OB-5991C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-03-17 | PS5-13-01 | PS5 - Milestone E | 4 | Closed | 16 | 28 | MARCH
T-147-9902 | PS5-87-UR-1605D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-05-25 | PS5-01-03 | PS5 - Milestone D | 3 | Closed | 33 | 26 | MAY
T-950-9903 | PS5-01-IK-6018D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone B | 1.1 | On hold |  | 37 | SEPTEMBER
T-512-9904 | PS5-17-UR-9781B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone C | 2 | On hold |  | 10 | SEPTEMBER
T-918-9905 | PS5-60-IK-7336D | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-12-22 | PS5-13-01 | PS5 - Milestone C | 2 | Closed | 8 | 34 | DECEMBER
T-028-9906 | PS5-83-OB-9107D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone B | 1.1 | To be completed |  | 19 | NOVEMBER
T-195-9907 | PS5-42-IK-4129B | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone G | 6 | To be completed |  | 44 | NOVEMBER
T-337-9908 | PS5-52-UR-4954D | CQS01 - Fire Protection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone I | 8 | To be completed |  | 20 | OCTOBER
T-454-9909 | PS5-01-UR-1461C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | In progress |  | 32 | AUGUST
T-278-9910 | PS5-59-UR-6963B | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone A | 1 | On hold |  | 36 | AUGUST
T-511-9911 | PS5-60-OB-2318D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone D | 3 | To be completed |  | 30 | AUGUST
T-096-9912 | PS5-97-IK-5976B | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-07-24 | PS5-01-03 | PS5 - Milestone E | 4 | Closed | 41 | 24 | JULY
T-658-9913 | PS5-09-OB-3663A | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-07-21 | PS5-04-03 | PS5 - Milestone C | 2 | Closed | 33 | 41 | JULY
T-599-9914 | PS5-29-UR-2584C | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-05-14 | PS5-01-05 | PS5 - Milestone I | 8 | Closed | 29 | 43 | MAY
T-447-9915 | PS5-75-OB-9877B | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | In progress |  | 28 | SEPTEMBER
T-277-9916 | PS5-17-UR-9704D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone H | 7 | To be completed |  | 21 | SEPTEMBER
T-966-9917 | PS5-46-OB-2506A | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone F | 5 | To be completed |  | 12 | AUGUST
T-875-9918 | PS5-27-IK-7859B | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-02-02 | PS5-01-04 | PS5 - Milestone C | 2 | Closed | 21 | 16 | FEBRUARY
T-157-9919 | PS5-38-UR-6739D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone D | 3 | In progress |  | 13 | DECEMBER
T-842-9920 | PS5-09-IK-9031C | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-06-01 | PS5-10-02 | PS5 - Milestone C | 2 | Closed | 16 | 8 | JUNE
T-674-9921 | PS5-55-IK-2737C | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-06-17 | PS5-63-01 | PS5 - Milestone A | 1 | Closed | 21 | 29 | JUNE
T-389-9922 | PS5-58-IK-1506A | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone B | 1.1 | On hold |  | 4 | OCTOBER
T-257-9923 | PS5-40-UR-6513A | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-04-09 | PS5-10-05 | PS5 - Milestone E | 4 | Closed | 34 | 9 | APRIL
T-012-9924 | PS5-07-OB-1963C | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone H | 7 | On hold |  | 47 | NOVEMBER
T-088-9925 | PS5-86-IK-4660C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | To be completed |  | 23 | DECEMBER
T-811-9926 | PS5-96-OB-3657C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone A | 1 | In progress |  | 20 | DECEMBER
T-531-9927 | PS5-79-OB-1981B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | In progress |  | 22 | NOVEMBER
T-746-9928 | PS5-93-OB-4665A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | On hold |  | 22 | OCTOBER
T-208-9929 | PS5-60-IK-9774A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone C | 2 | On hold |  | 32 | SEPTEMBER
T-888-9930 | PS5-33-UR-7175D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone C | 2 | In progress |  | 19 | DECEMBER
T-840-9931 | PS5-22-OB-6961A | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | In progress |  | 7 | DECEMBER
T-681-9932 | PS5-87-OB-2744A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone E | 4 | To be completed |  | 32 | DECEMBER
T-768-9933 | PS5-96-UR-3793A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone F | 5 | To be completed |  | 38 | DECEMBER
T-990-9934 | PS5-99-IK-8719C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-07-17 | PS5-09-03 | PS5 - Milestone D | 3 | Closed | 15 | 11 | JULY
T-379-9935 | PS5-02-UR-8469A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | To be completed |  | 36 | SEPTEMBER
T-900-9936 | PS5-93-IK-1862D | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-24 | PS5-60-07 | PS5 - Milestone H | 7 | Closed | 45 | 26 | APRIL
T-094-9937 | PS5-55-UR-4596D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone I | 8 | In progress |  | 40 | OCTOBER
T-794-9938 | PS5-35-IK-4758A | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | In progress |  | 46 | SEPTEMBER
T-933-9939 | PS5-08-IK-4809A | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | To be completed |  | 25 | OCTOBER
T-503-9940 | PS5-66-OB-7974B | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone G | 6 | To be completed |  | 29 | AUGUST
T-728-9941 | PS5-87-UR-3277C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | To be completed |  | 16 | NOVEMBER
T-043-9942 | PS5-92-OB-4475C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone E | 4 | In progress |  | 39 | DECEMBER
T-261-9943 | PS5-46-IK-4172A | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-02-23 | PS5-11-03 | PS5 - Milestone F | 5 | Closed | 12 | 31 | FEBRUARY
T-296-9944 | PS5-66-IK-6027A | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | In progress |  | 33 | OCTOBER
T-057-9945 | PS5-72-IK-3994C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone I | 8 | On hold |  | 38 | AUGUST
T-838-9946 | PS5-09-UR-6417D | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | On hold |  | 23 | OCTOBER
T-622-9947 | PS5-11-OB-4146A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-10-10 | PS5-12-01 | PS5 - Milestone G | 6 | Closed | 10 | 25 | OCTOBER
T-427-9948 | PS5-96-OB-2489D | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | To be completed |  | 27 | DECEMBER
T-431-9949 | PS5-30-UR-2590A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | On hold |  | 41 | AUGUST
T-699-9950 | PS5-84-UR-9598C | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone B | 1.1 | To be completed |  | 37 | SEPTEMBER
T-063-9951 | PS5-30-OB-3865C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone H | 7 | In progress |  | 13 | AUGUST
T-828-9952 | PS5-04-OB-7819A | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-10-01 | PS5-06-03 | PS5 - Milestone G | 6 | Closed | 42 | 22 | OCTOBER
T-848-9953 | PS5-51-OB-1894D | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-11-22 | PS5-06-02 | PS5 - Milestone C | 2 | Closed | 42 | 20 | NOVEMBER
T-294-9954 | PS5-72-IK-8192A | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone I | 8 | To be completed |  | 32 | NOVEMBER
T-689-9955 | PS5-95-OB-7304C | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-08-10 | PS5-61-02 | PS5 - Milestone H | 7 | Closed | 42 | 7 | AUGUST
T-102-9956 | PS5-10-UR-9252D | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | To be completed |  | 20 | DECEMBER
T-840-9957 | PS5-78-OB-3770C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone B | 1.1 | To be completed |  | 34 | NOVEMBER
T-572-9958 | PS5-61-OB-9740C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone C | 2 | To be completed |  | 41 | OCTOBER
T-412-9959 | PS5-88-IK-1500B | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone H | 7 | To be completed |  | 37 | AUGUST
T-120-9960 | PS5-95-OB-9307B | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-10-25 | PS5-12-02 | PS5 - Milestone A | 1 | Closed | 27 | 25 | OCTOBER
T-181-9961 | PS5-61-UR-7408D | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone E | 4 | To be completed |  | 40 | DECEMBER
T-347-9962 | PS5-57-OB-6009B | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone F | 5 | To be completed |  | 41 | OCTOBER
T-224-9963 | PS5-58-IK-2679C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-03-17 | PS5-01-07 | PS5 - Milestone D | 3 | Closed | 28 | 19 | MARCH
T-576-9964 | PS5-84-OB-9141A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone F | 5 | In progress |  | 21 | OCTOBER
T-355-9965 | PS5-35-IK-2848B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-07-20 | PS5-05-03 | PS5 - Milestone D | 3 | Closed | 4 | 35 | JULY
T-260-9966 | PS5-14-IK-7285B | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-12-13 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 32 | 47 | DECEMBER
T-520-9967 | PS5-68-IK-7979C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone C | 2 | To be completed |  | 38 | DECEMBER
T-349-9968 | PS5-85-IK-5670A | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-10-20 | PS5-63-01 | PS5 - Milestone D | 3 | Closed | 25 | 35 | OCTOBER
T-867-9969 | PS5-89-OB-9883D | CQS01 - Fire Protection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-11-16 | PS5-04-02 | PS5 - Milestone H | 7 | Closed | 26 | 30 | NOVEMBER
T-174-9970 | PS5-22-OB-4809A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone C | 2 | In progress |  | 31 | NOVEMBER
T-466-9971 | PS5-12-IK-5424A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-09-16 | PS5-07-02 | PS5 - Milestone I | 8 | Closed | 41 | 33 | SEPTEMBER
T-533-9972 | PS5-53-OB-1061D | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone I | 8 | To be completed |  | 45 | OCTOBER
T-279-9973 | PS5-33-UR-6697A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-07-06 | PS5-01-02 | PS5 - Milestone G | 6 | Closed | 6 | 33 | JULY
T-048-9974 | PS5-66-UR-6497C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone A | 1 | To be completed |  | 42 | SEPTEMBER
T-464-9975 | PS5-32-IK-2044C | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-07-09 | PS5-82-02 | PS5 - Milestone E | 4 | Closed | 42 | 30 | JULY
T-269-9976 | PS5-78-OB-2845A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone F | 5 | To be completed |  | 34 | OCTOBER
T-988-9977 | PS5-79-OB-2101C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-03-13 | PS5-07-03 | PS5 - Milestone D | 3 | Closed | 33 | 11 | MARCH
T-009-9978 | PS5-02-IK-4370A | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-10-19 | PS5-99-02 | PS5 - Milestone B | 1.1 | Closed | 42 | 47 | OCTOBER
T-064-9979 | PS5-35-IK-5002A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-08-17 | PS5-06-01 | PS5 - Milestone E | 4 | Closed | 43 | 4 | AUGUST
T-794-9980 | PS5-99-OB-7075A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-09-10 | PS5-06-01 | PS5 - Milestone G | 6 | Closed | 22 | 17 | SEPTEMBER
T-788-9981 | PS5-95-IK-6702A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-10-17 | PS5-02-01 | PS5 - Milestone D | 3 | Closed | 47 | 16 | OCTOBER
T-167-9982 | PS5-53-UR-6292D | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-12-27 | PS5-10-04 | PS5 - Milestone A | 1 | Closed | 47 | 17 | DECEMBER
T-887-9983 | PS5-14-OB-6929C | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-12-15 | PS5-10-01 | PS5 - Milestone G | 6 | Closed | 40 | 17 | DECEMBER
T-734-9984 | PS5-37-IK-2283D | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-04-28 | PS5-01-02 | PS5 - Milestone G | 6 | Closed | 4 | 48 | APRIL
T-996-9985 | PS5-98-OB-1521C | CQS03 - Deluge System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-02-10 | PS5-01-01 | PS5 - Milestone B | 1.1 | Closed | 35 | 47 | FEBRUARY
T-821-9986 | PS5-20-UR-4449C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone C | 2 | To be completed |  | 24 | OCTOBER
T-609-9987 | PS5-41-OB-1693D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | In progress |  | 7 | OCTOBER
T-030-9988 | PS5-76-UR-4617B | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone B | 1.1 | On hold |  | 22 | SEPTEMBER
T-490-9989 | PS5-14-OB-3652B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | On hold |  | 45 | AUGUST
T-072-9990 | PS5-54-UR-2429D | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-03-19 | PS5-09-03 | PS5 - Milestone C | 2 | Closed | 17 | 18 | MARCH
T-926-9991 | PS5-17-IK-6344D | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | In progress |  | 18 | OCTOBER
T-594-9992 | PS5-46-OB-8888D | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-01-17 | PS5-07-01 | PS5 - Milestone B | 1.1 | Closed | 27 | 13 | JANUARY
T-728-9993 | PS5-47-IK-6330A | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone I | 8 | To be completed |  | 24 | NOVEMBER
T-765-9994 | PS5-72-OB-1344D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-09-16 | PS5-06-02 | PS5 - Milestone B | 1.1 | Closed | 41 | 20 | SEPTEMBER
T-852-9995 | PS5-55-OB-4834D | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone I | 8 | On hold |  | 24 | SEPTEMBER
T-394-9996 | PS5-77-OB-3061A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | To be completed |  | 15 | SEPTEMBER
T-731-9997 | PS5-09-OB-3071A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-02-20 | PS5-82-01 | PS5 - Milestone F | 5 | Closed | 24 | 8 | FEBRUARY
T-886-9998 | PS5-34-OB-9324C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-05-04 | PS5-12-02 | PS5 - Milestone A | 1 | Closed | 47 | 16 | MAY
T-204-9999 | PS5-71-OB-3174B | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone C | 2 | In progress |  | 29 | AUGUST
T-757-10000 | PS5-20-OB-5155C | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone A | 1 | To be completed |  | 29 | NOVEMBER
T-178-10001 | PS5-62-UR-1055A | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-03 | PS5-60-04 | PS5 - Milestone B | 1.1 | Closed | 28 | 25 | APRIL
T-165-10002 | PS5-09-UR-5086D | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-09-10 | PS5-07-03 | PS5 - Milestone F | 5 | Closed | 34 | 19 | SEPTEMBER
T-020-10003 | PS5-78-OB-7495A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-10-16 | PS5-05-03 | PS5 - Milestone I | 8 | Closed | 7 | 46 | OCTOBER
T-592-10004 | PS5-79-IK-5295B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-10-28 | PS5-01-06 | PS5 - Milestone I | 8 | Closed | 11 | 29 | OCTOBER
T-823-10005 | PS5-86-OB-7874B | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone C | 2 | To be completed |  | 44 | NOVEMBER
T-804-10006 | PS5-24-OB-1373C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone B | 1.1 | To be completed |  | 36 | NOVEMBER
T-246-10007 | PS5-05-IK-7162B | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-02-03 | PS5-03-23 | PS5 - Milestone F | 5 | Closed | 5 | 37 | FEBRUARY
T-300-10008 | PS5-17-OB-9495A | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-06-09 | PS5-11-03 | PS5 - Milestone A | 1 | Closed | 18 | 7 | JUNE
T-346-10009 | PS5-02-UR-3958B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-04-06 | PS5-03-02 | PS5 - Milestone E | 4 | Closed | 45 | 43 | APRIL
T-296-10010 | PS5-53-OB-6161B | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone C | 2 | To be completed |  | 11 | SEPTEMBER
T-764-10011 | PS5-51-UR-5059A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | In progress |  | 9 | SEPTEMBER
T-595-10012 | PS5-72-OB-5522C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone F | 5 | To be completed |  | 45 | NOVEMBER
T-744-10013 | PS5-18-UR-8117D | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone F | 5 | To be completed |  | 34 | DECEMBER
T-867-10014 | PS5-19-OB-2057C | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-10-22 | PS5-60-10 | PS5 - Milestone H | 7 | Closed | 33 | 46 | OCTOBER
T-464-10015 | PS5-46-IK-8132B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-02-19 | PS5-08-02 | PS5 - Milestone G | 6 | Closed | 8 | 5 | FEBRUARY
T-865-10016 | PS5-97-UR-2251B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-01-21 | PS5-60-04 | PS5 - Milestone B | 1.1 | Closed | 32 | 28 | JANUARY
T-057-10017 | PS5-49-OB-4595D | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone C | 2 | In progress |  | 27 | SEPTEMBER
T-684-10018 | PS5-42-OB-8842C | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone E | 4 | To be completed |  | 5 | SEPTEMBER
T-769-10019 | PS5-73-IK-9878B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-01-04 | PS5-99-02 | PS5 - Milestone A | 1 | Closed | 11 | 4 | JANUARY
T-946-10020 | PS5-28-IK-8446B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone G | 6 | In progress |  | 29 | NOVEMBER
T-096-10021 | PS5-40-OB-2862B | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | On hold |  | 6 | SEPTEMBER
T-921-10022 | PS5-70-IK-6543C | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone G | 6 | In progress |  | 9 | AUGUST
T-712-10023 | PS5-99-OB-6495A | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone E | 4 | To be completed |  | 40 | AUGUST
T-003-10024 | PS5-90-OB-1193D | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-12-02 | PS5-61-01 | PS5 - Milestone E | 4 | Closed | 8 | 46 | DECEMBER
T-229-10025 | PS5-68-IK-5639B | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-12-19 | PS5-60-01 | PS5 - Milestone F | 5 | Closed | 42 | 33 | DECEMBER
T-497-10026 | PS5-81-UR-9966B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone B | 1.1 | To be completed |  | 24 | NOVEMBER
T-008-10027 | PS5-27-OB-1766D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone E | 4 | In progress |  | 39 | SEPTEMBER
T-752-10028 | PS5-97-UR-4610A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone C | 2 | To be completed |  | 30 | OCTOBER
T-981-10029 | PS5-17-IK-8068B | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone I | 8 | In progress |  | 39 | OCTOBER
T-626-10030 | PS5-41-OB-1864D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-08-17 | PS5-01-05 | PS5 - Milestone B | 1.1 | Closed | 37 | 17 | AUGUST
T-659-10031 | PS5-73-IK-6166D | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone I | 8 | To be completed |  | 41 | DECEMBER
T-865-10032 | PS5-85-OB-3838A | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | In progress |  | 32 | DECEMBER
T-749-10033 | PS5-52-UR-9752B | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-11-13 | PS5-06-03 | PS5 - Milestone B | 1.1 | Closed | 25 | 18 | NOVEMBER
T-974-10034 | PS5-57-OB-6296C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | In progress |  | 47 | NOVEMBER
T-795-10035 | PS5-27-OB-7720D | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone C | 2 | To be completed |  | 36 | OCTOBER
T-639-10036 | PS5-64-OB-1578B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-09-24 | PS5-12-02 | PS5 - Milestone G | 6 | Closed | 18 | 9 | SEPTEMBER
T-312-10037 | PS5-35-OB-7906B | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-12-07 | PS5-02-01 | PS5 - Milestone B | 1.1 | Closed | 23 | 19 | DECEMBER
T-528-10038 | PS5-21-OB-6462D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone F | 5 | To be completed |  | 32 | NOVEMBER
T-151-10039 | PS5-78-UR-2701A | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone C | 2 | On hold |  | 18 | SEPTEMBER
T-396-10040 | PS5-66-IK-4848C | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone E | 4 | To be completed |  | 18 | DECEMBER
T-642-10041 | PS5-10-OB-8885A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-04-28 | PS5-07-03 | PS5 - Milestone G | 6 | Closed | 35 | 48 | APRIL
T-062-10042 | PS5-33-OB-5121D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone G | 6 | To be completed |  | 13 | SEPTEMBER
T-884-10043 | PS5-95-OB-1989A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-08-08 | PS5-62-02 | PS5 - Milestone C | 2 | Closed | 41 | 13 | AUGUST
T-602-10044 | PS5-55-UR-4945B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-10-22 | PS5-09-04 | PS5 - Milestone F | 5 | Closed | 30 | 30 | OCTOBER
T-766-10045 | PS5-81-IK-2778D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | To be completed |  | 35 | OCTOBER
T-529-10046 | PS5-62-OB-4028D | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-01-24 | PS5-04-04 | PS5 - Milestone D | 3 | Closed | 19 | 47 | JANUARY
T-577-10047 | PS5-44-OB-3894D | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-09-10 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 23 | 18 | SEPTEMBER
T-191-10048 | PS5-95-OB-9545A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | To be completed |  | 45 | OCTOBER
T-601-10049 | PS5-88-IK-6397B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-03-19 | PS5-01-01 | PS5 - Milestone D | 3 | Closed | 9 | 25 | MARCH
T-193-10050 | PS5-32-IK-3072C | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone G | 6 | To be completed |  | 47 | OCTOBER
T-821-10051 | PS5-02-UR-3771D | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-05-18 | PS5-01-08 | PS5 - Milestone F | 5 | Closed | 33 | 34 | MAY
T-071-10052 | PS5-70-UR-3991A | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-02-28 | PS5-03-03 | PS5 - Milestone I | 8 | Closed | 21 | 18 | FEBRUARY
T-241-10053 | PS5-56-IK-6817D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-11-25 | PS5-05-01 | PS5 - Milestone F | 5 | Closed | 5 | 43 | NOVEMBER
T-528-10054 | PS5-05-IK-1675A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone I | 8 | To be completed |  | 39 | DECEMBER
T-674-10055 | PS5-45-UR-4570B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-12-01 | PS5-06-01 | PS5 - Milestone B | 1.1 | Closed | 21 | 7 | DECEMBER
T-737-10056 | PS5-50-IK-1960D | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone F | 5 | To be completed |  | 24 | OCTOBER
T-282-10057 | PS5-81-IK-9861C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone F | 5 | On hold |  | 18 | SEPTEMBER
T-438-10058 | PS5-42-UR-2824B | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-05-22 | PS5-11-01 | PS5 - Milestone D | 3 | Closed | 20 | 28 | MAY
T-238-10059 | PS5-37-OB-1093A | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone F | 5 | In progress |  | 32 | NOVEMBER
T-075-10060 | PS5-17-IK-9299B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-09-20 | PS5-01-09 | PS5 - Milestone D | 3 | Closed | 45 | 23 | SEPTEMBER
T-978-10061 | PS5-27-IK-1301A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone E | 4 | To be completed |  | 32 | NOVEMBER
T-347-10062 | PS5-81-OB-5871C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | To be completed |  | 12 | SEPTEMBER
T-846-10063 | PS5-58-OB-1007D | CQP04 - Hydrotest | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-03-03 | PS5-61-01 | PS5 - Milestone C | 2 | Closed | 19 | 37 | MARCH
T-627-10064 | PS5-55-IK-9381D | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-03-18 | PS5-11-03 | PS5 - Milestone B | 1.1 | Closed | 17 | 6 | MARCH
T-455-10065 | PS5-61-IK-2751D | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone E | 4 | To be completed |  | 42 | OCTOBER
T-556-10066 | PS5-76-OB-5450A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone I | 8 | In progress |  | 24 | AUGUST
T-592-10067 | PS5-31-IK-5049A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone E | 4 | On hold |  | 22 | DECEMBER
T-318-10068 | PS5-22-OB-7293A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-01-15 | PS5-04-02 | PS5 - Milestone I | 8 | Closed | 40 | 25 | JANUARY
T-107-10069 | PS5-34-IK-2770D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone H | 7 | To be completed |  | 20 | OCTOBER
T-848-10070 | PS5-31-OB-3239B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone G | 6 | To be completed |  | 24 | OCTOBER
T-418-10071 | PS5-04-OB-6923C | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone D | 3 | To be completed |  | 42 | AUGUST
T-219-10072 | PS5-21-IK-3433D | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone G | 6 | To be completed |  | 44 | NOVEMBER
T-735-10073 | PS5-81-IK-3218A | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-04-27 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 20 | 47 | APRIL
T-923-10074 | PS5-33-OB-1168C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-15 | PS5-60-07 | PS5 - Milestone E | 4 | Closed | 7 | 38 | JULY
T-965-10075 | PS5-56-IK-3149D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-13 | PS5-60-04 | PS5 - Milestone B | 1.1 | Closed | 19 | 27 | JUNE
T-151-10076 | PS5-70-OB-7666D | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone G | 6 | To be completed |  | 23 | SEPTEMBER
T-542-10077 | PS5-71-IK-6543D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-08-20 | PS5-13-01 | PS5 - Milestone G | 6 | Closed | 39 | 23 | AUGUST
T-842-10078 | PS5-83-UR-5406A | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-02-21 | PS5-02-03 | PS5 - Milestone I | 8 | Closed | 37 | 16 | FEBRUARY
T-101-10079 | PS5-78-OB-8989C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-04-12 | PS5-07-01 | PS5 - Milestone E | 4 | Closed | 24 | 37 | APRIL
T-222-10080 | PS5-57-IK-8360B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone E | 4 | To be completed |  | 7 | SEPTEMBER
T-203-10081 | PS5-87-OB-3528C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone E | 4 | To be completed |  | 38 | AUGUST
T-633-10082 | PS5-97-IK-1027D | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-02-18 | PS5-99-01 | PS5 - Milestone B | 1.1 | Closed | 28 | 29 | FEBRUARY
T-078-10083 | PS5-54-UR-6314C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone C | 2 | In progress |  | 45 | SEPTEMBER
T-384-10084 | PS5-22-OB-3755A | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone F | 5 | To be completed |  | 29 | OCTOBER
T-641-10085 | PS5-02-UR-2709B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-03-04 | PS5-04-01 | PS5 - Milestone E | 4 | Closed | 19 | 28 | MARCH
T-601-10086 | PS5-62-IK-9512D | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone E | 4 | In progress |  | 15 | OCTOBER
T-797-10087 | PS5-38-OB-9876C | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-11-03 | PS5-12-01 | PS5 - Milestone F | 5 | Closed | 6 | 48 | NOVEMBER
T-317-10088 | PS5-73-IK-2657C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone G | 6 | To be completed |  | 38 | SEPTEMBER
T-555-10089 | PS5-15-UR-3113D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone A | 1 | In progress |  | 29 | OCTOBER
T-446-10090 | PS5-73-IK-7755B | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone B | 1.1 | To be completed |  | 39 | AUGUST
T-090-10091 | PS5-97-IK-5056A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone D | 3 | To be completed |  | 15 | DECEMBER
T-885-10092 | PS5-05-IK-6171A | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-03-04 | PS5-82-02 | PS5 - Milestone B | 1.1 | Closed | 30 | 22 | MARCH
T-852-10093 | PS5-58-OB-3534C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-01-25 | PS5-01-03 | PS5 - Milestone E | 4 | Closed | 32 | 7 | JANUARY
T-817-10094 | PS5-10-IK-2667D | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone I | 8 | To be completed |  | 22 | AUGUST
T-586-10095 | PS5-92-UR-4286B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone I | 8 | To be completed |  | 28 | SEPTEMBER
T-536-10096 | PS5-19-OB-8668B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone A | 1 | To be completed |  | 36 | NOVEMBER
T-137-10097 | PS5-80-UR-3404B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-01-03 | PS5-60-10 | PS5 - Milestone F | 5 | Closed | 10 | 41 | JANUARY
T-180-10098 | PS5-67-OB-3847C | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone B | 1.1 | To be completed |  | 35 | AUGUST
T-680-10099 | PS5-23-UR-4194C | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone H | 7 | In progress |  | 20 | SEPTEMBER
T-276-10100 | PS5-83-IK-6854D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | To be completed |  | 19 | AUGUST
T-365-10101 | PS5-26-IK-2014A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone B | 1.1 | In progress |  | 7 | AUGUST
T-687-10102 | PS5-59-OB-5110C | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-01-26 | PS5-02-01 | PS5 - Milestone G | 6 | Closed | 9 | 25 | JANUARY
T-675-10103 | PS5-33-IK-6972D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | On hold |  | 41 | SEPTEMBER
T-979-10104 | PS5-83-OB-4736D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone C | 2 | On hold |  | 11 | SEPTEMBER
T-263-10105 | PS5-05-OB-4408B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-02-25 | PS5-07-03 | PS5 - Milestone I | 8 | Closed | 4 | 10 | FEBRUARY
T-502-10106 | PS5-11-OB-5174B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone A | 1 | In progress |  | 9 | SEPTEMBER
T-122-10107 | PS5-83-OB-6606A | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone A | 1 | To be completed |  | 22 | OCTOBER
T-068-10108 | PS5-66-UR-5429D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-10-22 | PS5-03-01 | PS5 - Milestone F | 5 | Closed | 12 | 31 | OCTOBER
T-059-10109 | PS5-41-UR-9008D | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-09-07 | PS5-12-01 | PS5 - Milestone C | 2 | Closed | 13 | 32 | SEPTEMBER
T-787-10110 | PS5-10-UR-6603A | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone C | 2 | In progress |  | 23 | NOVEMBER
T-195-10111 | PS5-46-OB-5012B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone B | 1.1 | To be completed |  | 48 | NOVEMBER
T-119-10112 | PS5-51-IK-6982D | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone E | 4 | To be completed |  | 13 | OCTOBER
T-951-10113 | PS5-51-OB-1381D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone D | 3 | To be completed |  | 23 | AUGUST
T-902-10114 | PS5-59-UR-6029C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | On hold |  | 9 | OCTOBER
T-443-10115 | PS5-88-OB-4479D | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone B | 1.1 | In progress |  | 17 | AUGUST
T-767-10116 | PS5-03-OB-9610A | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone F | 5 | To be completed |  | 41 | OCTOBER
T-273-10117 | PS5-84-IK-1032C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-12-22 | PS5-99-02 | PS5 - Milestone D | 3 | Closed | 38 | 25 | DECEMBER
T-293-10118 | PS5-77-IK-8833C | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-04-17 | PS5-03-01 | PS5 - Milestone C | 2 | Closed | 48 | 18 | APRIL
T-454-10119 | PS5-54-OB-1557D | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone E | 4 | In progress |  | 5 | OCTOBER
T-875-10120 | PS5-71-OB-7070D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone F | 5 | To be completed |  | 17 | NOVEMBER
T-178-10121 | PS5-99-UR-7162A | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-07-19 | PS5-82-01 | PS5 - Milestone H | 7 | Closed | 26 | 15 | JULY
T-070-10122 | PS5-97-IK-2187A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone B | 1.1 | To be completed |  | 11 | OCTOBER
T-831-10123 | PS5-60-IK-5513D | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-08-09 | PS5-03-01 | PS5 - Milestone G | 6 | Closed | 43 | 25 | AUGUST
T-176-10124 | PS5-44-UR-8828C | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-11-15 | PS5-99-02 | PS5 - Milestone H | 7 | Closed | 17 | 37 | NOVEMBER
T-157-10125 | PS5-23-UR-5973B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone B | 1.1 | In progress |  | 36 | OCTOBER
T-335-10126 | PS5-13-OB-3348B | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone C | 2 | To be completed |  | 10 | AUGUST
T-047-10127 | PS5-97-IK-2474B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-10-08 | PS5-02-02 | PS5 - Milestone G | 6 | Closed | 4 | 12 | OCTOBER
T-927-10128 | PS5-62-IK-7431B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone I | 8 | In progress |  | 6 | DECEMBER
T-185-10129 | PS5-35-OB-2478C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone A | 1 | In progress |  | 13 | SEPTEMBER
T-706-10130 | PS5-42-OB-6531A | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-12-28 | PS5-03-03 | PS5 - Milestone A | 1 | Closed | 17 | 25 | DECEMBER
T-565-10131 | PS5-50-IK-5895B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone D | 3 | To be completed |  | 8 | NOVEMBER
T-278-10132 | PS5-08-IK-4251D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-04-06 | PS5-07-01 | PS5 - Milestone F | 5 | Closed | 21 | 26 | APRIL
T-092-10133 | PS5-99-OB-3123B | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-05-25 | PS5-08-01 | PS5 - Milestone F | 5 | Closed | 28 | 11 | MAY
T-726-10134 | PS5-57-OB-2737D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone H | 7 | In progress |  | 17 | NOVEMBER
T-958-10135 | PS5-63-OB-6006D | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone C | 2 | To be completed |  | 45 | NOVEMBER
T-781-10136 | PS5-17-IK-4795D | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone H | 7 | In progress |  | 40 | SEPTEMBER
T-317-10137 | PS5-51-OB-5350C | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-05-07 | PS5-12-01 | PS5 - Milestone A | 1 | Closed | 27 | 16 | MAY
T-021-10138 | PS5-53-UR-5963A | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | To be completed |  | 27 | DECEMBER
T-397-10139 | PS5-89-OB-4248C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-05-15 | PS5-12-01 | PS5 - Milestone G | 6 | Closed | 14 | 11 | MAY
T-334-10140 | PS5-20-UR-1406B | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone H | 7 | In progress |  | 28 | OCTOBER
T-727-10141 | PS5-22-OB-7952D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-04-28 | PS5-03-02 | PS5 - Milestone H | 7 | Closed | 48 | 22 | APRIL
T-669-10142 | PS5-76-OB-3141C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone H | 7 | On hold |  | 41 | DECEMBER
T-207-10143 | PS5-41-UR-8731A | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-03-24 | PS5-01-08 | PS5 - Milestone G | 6 | Closed | 27 | 27 | MARCH
T-294-10144 | PS5-90-OB-8169A | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone I | 8 | To be completed |  | 43 | OCTOBER
T-637-10145 | PS5-99-UR-3593A | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone C | 2 | In progress |  | 23 | NOVEMBER
T-137-10146 | PS5-79-OB-3550C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone B | 1.1 | On hold |  | 12 | DECEMBER
T-199-10147 | PS5-91-OB-6743A | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone D | 3 | To be completed |  | 46 | NOVEMBER
T-768-10148 | PS5-02-OB-5036D | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone A | 1 | To be completed |  | 30 | DECEMBER
T-055-10149 | PS5-84-UR-1793A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone E | 4 | To be completed |  | 9 | AUGUST
T-481-10150 | PS5-80-OB-5878D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone B | 1.1 | To be completed |  | 26 | NOVEMBER
T-491-10151 | PS5-13-OB-1892B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | In progress |  | 27 | SEPTEMBER
T-665-10152 | PS5-80-IK-9651D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone I | 8 | On hold |  | 29 | NOVEMBER
T-346-10153 | PS5-97-UR-3603A | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone H | 7 | On hold |  | 40 | NOVEMBER
T-712-10154 | PS5-05-UR-8883B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone E | 4 | On hold |  | 29 | OCTOBER
T-071-10155 | PS5-65-OB-8239C | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | In progress |  | 19 | DECEMBER
T-447-10156 | PS5-20-UR-2699D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-01-21 | PS5-60-10 | PS5 - Milestone C | 2 | Closed | 10 | 48 | JANUARY
T-460-10157 | PS5-76-UR-3795C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-05-22 | PS5-82-01 | PS5 - Milestone I | 8 | Closed | 19 | 4 | MAY
T-388-10158 | PS5-65-OB-5799B | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone C | 2 | In progress |  | 11 | OCTOBER
T-792-10159 | PS5-02-IK-1109C | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-12-08 | PS5-05-01 | PS5 - Milestone H | 7 | Closed | 41 | 22 | DECEMBER
T-467-10160 | PS5-83-OB-1274D | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-07-17 | PS5-03-01 | PS5 - Milestone I | 8 | Closed | 47 | 9 | JULY
T-525-10161 | PS5-76-OB-4741B | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-03-07 | PS5-08-01 | PS5 - Milestone E | 4 | Closed | 24 | 40 | MARCH
T-646-10162 | PS5-27-IK-6692A | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-04-18 | PS5-61-02 | PS5 - Milestone D | 3 | Closed | 5 | 34 | APRIL
T-625-10163 | PS5-25-OB-2852B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | To be completed |  | 27 | OCTOBER
T-980-10164 | PS5-23-UR-3617B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone F | 5 | In progress |  | 11 | AUGUST
T-689-10165 | PS5-90-IK-4767D | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | On hold |  | 17 | SEPTEMBER
T-386-10166 | PS5-70-UR-4513C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone E | 4 | To be completed |  | 41 | OCTOBER
T-219-10167 | PS5-97-IK-2337C | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-03-09 | PS5-60-07 | PS5 - Milestone H | 7 | Closed | 23 | 16 | MARCH
T-956-10168 | PS5-61-IK-6681C | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | To be completed |  | 4 | OCTOBER
T-296-10169 | PS5-65-OB-7647A | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-20 | PS5-60-07 | PS5 - Milestone C | 2 | Closed | 11 | 16 | JUNE
T-831-10170 | PS5-57-UR-8656C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone C | 2 | To be completed |  | 42 | AUGUST
T-949-10171 | PS5-17-OB-5898A | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-05-21 | PS5-82-02 | PS5 - Milestone F | 5 | Closed | 31 | 13 | MAY
T-706-10172 | PS5-66-UR-4968D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-05-22 | PS5-10-05 | PS5 - Milestone D | 3 | Closed | 35 | 23 | MAY
T-467-10173 | PS5-54-UR-6114A | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone G | 6 | To be completed |  | 8 | DECEMBER
T-460-10174 | PS5-43-OB-5602A | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone H | 7 | In progress |  | 12 | DECEMBER
T-042-10175 | PS5-88-IK-4545B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone I | 8 | In progress |  | 16 | NOVEMBER
T-279-10176 | PS5-49-UR-4860D | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone F | 5 | To be completed |  | 21 | AUGUST
T-304-10177 | PS5-49-OB-3507D | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-12-23 | PS5-60-01 | PS5 - Milestone I | 8 | Closed | 10 | 33 | DECEMBER
T-276-10178 | PS5-34-OB-5803C | CQM01 - Pump Installation | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone B | 1.1 | To be completed |  | 37 | NOVEMBER
T-756-10179 | PS5-06-UR-8533D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | On hold |  | 14 | AUGUST
T-710-10180 | PS5-93-UR-2346D | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-09-25 | PS5-60-01 | PS5 - Milestone I | 8 | Closed | 6 | 29 | SEPTEMBER
T-079-10181 | PS5-34-IK-8838B | CQM04 - Vessel | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone D | 3 | To be completed |  | 28 | OCTOBER
T-474-10182 | PS5-16-OB-5498B | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone A | 1 | To be completed |  | 35 | NOVEMBER
T-629-10183 | PS5-49-UR-7516A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-12-07 | PS5-12-02 | PS5 - Milestone I | 8 | Closed | 8 | 31 | DECEMBER
T-094-10184 | PS5-69-IK-3351C | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | To be completed |  | 48 | AUGUST
T-644-10185 | PS5-95-UR-6460B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone B | 1.1 | In progress |  | 48 | AUGUST
T-709-10186 | PS5-92-UR-5637C | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-03-26 | PS5-09-01 | PS5 - Milestone G | 6 | Closed | 31 | 44 | MARCH
T-793-10187 | PS5-10-IK-9680D | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | In progress |  | 26 | DECEMBER
T-189-10188 | PS5-71-OB-3465A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | In progress |  | 22 | DECEMBER
T-488-10189 | PS5-97-OB-5177D | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-10-06 | PS5-11-03 | PS5 - Milestone E | 4 | Closed | 7 | 47 | OCTOBER
T-665-10190 | PS5-81-OB-6581A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-02-09 | PS5-07-02 | PS5 - Milestone B | 1.1 | Closed | 24 | 10 | FEBRUARY
T-026-10191 | PS5-20-UR-8981C | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-01-15 | PS5-60-07 | PS5 - Milestone D | 3 | Closed | 31 | 5 | JANUARY
T-167-10192 | PS5-37-OB-1615C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone A | 1 | In progress |  | 14 | DECEMBER
T-673-10193 | PS5-98-OB-8695A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone F | 5 | To be completed |  | 48 | OCTOBER
T-931-10194 | PS5-86-IK-7417D | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone G | 6 | On hold |  | 19 | AUGUST
T-088-10195 | PS5-80-OB-9787C | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-05-11 | PS5-06-02 | PS5 - Milestone F | 5 | Closed | 14 | 13 | MAY
T-214-10196 | PS5-07-UR-1168A | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-03-28 | PS5-01-06 | PS5 - Milestone I | 8 | Closed | 22 | 21 | MARCH
T-218-10197 | PS5-98-UR-9635A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | To be completed |  | 7 | OCTOBER
T-740-10198 | PS5-62-OB-6737B | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | In progress |  | 20 | OCTOBER
T-529-10199 | PS5-83-OB-1973A | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-01-16 | PS5-03-03 | PS5 - Milestone F | 5 | Closed | 39 | 4 | JANUARY
T-752-10200 | PS5-07-OB-4456C | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone D | 3 | To be completed |  | 25 | OCTOBER
T-842-10201 | PS5-15-IK-9692B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone I | 8 | On hold |  | 29 | SEPTEMBER
T-124-10202 | PS5-14-IK-3440C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone C | 2 | In progress |  | 17 | SEPTEMBER
T-508-10203 | PS5-12-OB-2345B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone G | 6 | To be completed |  | 7 | OCTOBER
T-250-10204 | PS5-37-UR-6840A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone A | 1 | To be completed |  | 40 | AUGUST
T-850-10205 | PS5-96-OB-6454C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone E | 4 | In progress |  | 40 | NOVEMBER
T-026-10206 | PS5-16-UR-2046D | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone E | 4 | On hold |  | 35 | OCTOBER
T-603-10207 | PS5-87-UR-4104B | CQP04 - Hydrotest | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone B | 1.1 | To be completed |  | 37 | NOVEMBER
T-959-10208 | PS5-32-IK-3327A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-06-15 | PS5-05-01 | PS5 - Milestone F | 5 | Closed | 10 | 44 | JUNE
T-526-10209 | PS5-96-UR-1152A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone D | 3 | To be completed |  | 40 | SEPTEMBER
T-994-10210 | PS5-45-OB-3843A | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone F | 5 | In progress |  | 42 | AUGUST
T-330-10211 | PS5-54-UR-6781D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone G | 6 | On hold |  | 33 | DECEMBER
T-711-10212 | PS5-15-UR-3779D | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | To be completed |  | 43 | NOVEMBER
T-303-10213 | PS5-08-OB-3223B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-12-12 | PS5-11-01 | PS5 - Milestone A | 1 | Closed | 43 | 33 | DECEMBER
T-657-10214 | PS5-12-IK-7402B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone F | 5 | To be completed |  | 13 | SEPTEMBER
T-034-10215 | PS5-12-UR-4545A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone B | 1.1 | To be completed |  | 15 | AUGUST
T-352-10216 | PS5-41-OB-4750C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-11-20 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 42 | 24 | NOVEMBER
T-928-10217 | PS5-73-OB-9522B | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-10-13 | PS5-01-01 | PS5 - Milestone B | 1.1 | Closed | 5 | 40 | OCTOBER
T-765-10218 | PS5-35-OB-7858A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-10-04 | PS5-61-07 | PS5 - Milestone C | 2 | Closed | 9 | 45 | OCTOBER
T-936-10219 | PS5-07-UR-8377D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone B | 1.1 | To be completed |  | 16 | NOVEMBER
T-248-10220 | PS5-37-IK-3796B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone H | 7 | To be completed |  | 19 | NOVEMBER
T-668-10221 | PS5-76-OB-5590C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-10-08 | PS5-11-02 | PS5 - Milestone A | 1 | Closed | 31 | 41 | OCTOBER
T-596-10222 | PS5-94-UR-9106A | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-10-09 | PS5-99-01 | PS5 - Milestone G | 6 | Closed | 33 | 5 | OCTOBER
T-973-10223 | PS5-03-OB-1748C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone F | 5 | To be completed |  | 32 | SEPTEMBER
T-433-10224 | PS5-33-UR-1278A | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-01-06 | PS5-61-07 | PS5 - Milestone B | 1.1 | Closed | 33 | 18 | JANUARY
T-732-10225 | PS5-56-OB-5477A | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone E | 4 | On hold |  | 6 | NOVEMBER
T-262-10226 | PS5-67-OB-7993A | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | To be completed |  | 4 | SEPTEMBER
T-716-10227 | PS5-64-OB-1184A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | To be completed |  | 30 | AUGUST
T-194-10228 | PS5-49-UR-2143C | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone B | 1.1 | In progress |  | 24 | DECEMBER
T-493-10229 | PS5-88-OB-1509A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone G | 6 | To be completed |  | 39 | AUGUST
T-540-10230 | PS5-94-UR-8952C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | To be completed |  | 28 | SEPTEMBER
T-957-10231 | PS5-20-OB-9025D | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone D | 3 | To be completed |  | 46 | SEPTEMBER
T-508-10232 | PS5-32-IK-2330A | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone C | 2 | To be completed |  | 24 | AUGUST
T-883-10233 | PS5-59-UR-3108B | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-06-17 | PS5-03-02 | PS5 - Milestone B | 1.1 | Closed | 44 | 19 | JUNE
T-782-10234 | PS5-76-IK-5269C | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone D | 3 | On hold |  | 33 | OCTOBER
T-290-10235 | PS5-97-UR-9886B | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone C | 2 | To be completed |  | 27 | OCTOBER
T-824-10236 | PS5-12-UR-3198D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-08-17 | PS5-01-07 | PS5 - Milestone B | 1.1 | Closed | 7 | 36 | AUGUST
T-350-10237 | PS5-57-IK-2263A | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone I | 8 | To be completed |  | 42 | NOVEMBER
T-312-10238 | PS5-25-OB-7590A | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-12-10 | PS5-61-01 | PS5 - Milestone G | 6 | Closed | 20 | 32 | DECEMBER
T-600-10239 | PS5-46-OB-9839C | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-10-05 | PS5-60-04 | PS5 - Milestone C | 2 | Closed | 37 | 36 | OCTOBER
T-836-10240 | PS5-76-OB-5885B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone A | 1 | In progress |  | 17 | AUGUST
T-672-10241 | PS5-83-IK-4248A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone D | 3 | On hold |  | 10 | SEPTEMBER
T-152-10242 | PS5-88-UR-5942C | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-07-07 | PS5-11-03 | PS5 - Milestone A | 1 | Closed | 14 | 44 | JULY
T-103-10243 | PS5-19-IK-8724D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone G | 6 | To be completed |  | 16 | SEPTEMBER
T-744-10244 | PS5-98-IK-6503B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone F | 5 | To be completed |  | 26 | SEPTEMBER
T-943-10245 | PS5-97-UR-2286A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-09-17 | PS5-02-03 | PS5 - Milestone A | 1 | Closed | 42 | 7 | SEPTEMBER
T-545-10246 | PS5-49-IK-5153A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-11-25 | PS5-09-04 | PS5 - Milestone F | 5 | Closed | 48 | 4 | NOVEMBER
T-014-10247 | PS5-83-IK-5346C | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | To be completed |  | 34 | OCTOBER
T-711-10248 | PS5-77-OB-6433D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone E | 4 | To be completed |  | 27 | OCTOBER
T-719-10249 | PS5-82-OB-9451B | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-23 | PS5-60-01 | PS5 - Milestone A | 1 | Closed | 10 | 5 | FEBRUARY
T-151-10250 | PS5-03-IK-6719C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone F | 5 | To be completed |  | 11 | NOVEMBER
T-167-10251 | PS5-87-OB-1537B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-04-15 | PS5-01-09 | PS5 - Milestone I | 8 | Closed | 33 | 15 | APRIL
T-445-10252 | PS5-81-UR-7972D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-10-04 | PS5-01-04 | PS5 - Milestone A | 1 | Closed | 17 | 45 | OCTOBER
T-694-10253 | PS5-99-OB-7580D | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone H | 7 | To be completed |  | 24 | AUGUST
T-705-10254 | PS5-21-IK-9036D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-10-21 | PS5-01-02 | PS5 - Milestone G | 6 | Closed | 22 | 48 | OCTOBER
T-773-10255 | PS5-88-OB-1242B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-08-25 | PS5-09-01 | PS5 - Milestone C | 2 | Closed | 14 | 10 | AUGUST
T-094-10256 | PS5-85-UR-4072C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-01-24 | PS5-12-02 | PS5 - Milestone I | 8 | Closed | 29 | 15 | JANUARY
T-243-10257 | PS5-68-UR-6069B | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-08-28 | PS5-60-04 | PS5 - Milestone A | 1 | Closed | 42 | 42 | AUGUST
T-675-10258 | PS5-16-IK-6838A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-05-09 | PS5-06-02 | PS5 - Milestone I | 8 | Closed | 40 | 25 | MAY
T-722-10259 | PS5-43-OB-9793D | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone G | 6 | In progress |  | 19 | SEPTEMBER
T-680-10260 | PS5-30-IK-6685B | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone G | 6 | To be completed |  | 28 | DECEMBER
T-477-10261 | PS5-20-OB-7275A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-04-08 | PS5-06-02 | PS5 - Milestone A | 1 | Closed | 7 | 45 | APRIL
T-433-10262 | PS5-14-OB-5890D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-08-21 | PS5-99-01 | PS5 - Milestone I | 8 | Closed | 15 | 45 | AUGUST
T-914-10263 | PS5-04-OB-9533C | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | To be completed |  | 8 | AUGUST
T-107-10264 | PS5-83-OB-9379B | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-11-12 | PS5-11-02 | PS5 - Milestone A | 1 | Closed | 26 | 12 | NOVEMBER
T-882-10265 | PS5-44-OB-5077C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-01-04 | PS5-02-01 | PS5 - Milestone E | 4 | Closed | 16 | 5 | JANUARY
T-110-10266 | PS5-51-IK-5701B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | To be completed |  | 22 | AUGUST
T-683-10267 | PS5-77-OB-2760C | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone H | 7 | To be completed |  | 8 | OCTOBER
T-665-10268 | PS5-66-UR-6689D | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | In progress |  | 6 | DECEMBER
T-608-10269 | PS5-62-OB-7506B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone F | 5 | To be completed |  | 8 | AUGUST
T-827-10270 | PS5-26-UR-4971B | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone H | 7 | In progress |  | 27 | AUGUST
T-871-10271 | PS5-20-UR-3713A | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone F | 5 | In progress |  | 27 | NOVEMBER
T-310-10272 | PS5-24-OB-4715C | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone H | 7 | In progress |  | 33 | NOVEMBER
T-200-10273 | PS5-95-IK-7896A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone F | 5 | To be completed |  | 46 | AUGUST
T-564-10274 | PS5-39-OB-6047C | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-11-20 | PS5-04-01 | PS5 - Milestone G | 6 | Closed | 36 | 34 | NOVEMBER
T-333-10275 | PS5-15-OB-5422C | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-03-01 | PS5-07-02 | PS5 - Milestone A | 1 | Closed | 44 | 45 | MARCH
T-494-10276 | PS5-85-UR-3885C | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-11-13 | PS5-62-02 | PS5 - Milestone A | 1 | Closed | 5 | 36 | NOVEMBER
T-984-10277 | PS5-84-IK-4120A | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | On hold |  | 40 | DECEMBER
T-791-10278 | PS5-14-IK-9587A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-10-18 | PS5-05-02 | PS5 - Milestone B | 1.1 | Closed | 39 | 10 | OCTOBER
T-823-10279 | PS5-38-OB-5055C | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | On hold |  | 30 | NOVEMBER
T-754-10280 | PS5-63-OB-9769D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone I | 8 | To be completed |  | 23 | NOVEMBER
T-178-10281 | PS5-53-IK-2812B | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-01-13 | PS5-61-02 | PS5 - Milestone A | 1 | Closed | 32 | 47 | JANUARY
T-223-10282 | PS5-33-OB-3575D | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-11-20 | PS5-01-08 | PS5 - Milestone E | 4 | Closed | 12 | 29 | NOVEMBER
T-441-10283 | PS5-69-OB-3567C | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone I | 8 | To be completed |  | 28 | OCTOBER
T-051-10284 | PS5-65-IK-8512D | CQS03 - Deluge System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | To be completed |  | 37 | NOVEMBER
T-884-10285 | PS5-34-OB-7359C | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone B | 1.1 | To be completed |  | 9 | SEPTEMBER
T-361-10286 | PS5-22-IK-4945C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone A | 1 | To be completed |  | 29 | AUGUST
T-032-10287 | PS5-37-UR-9419C | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone F | 5 | To be completed |  | 11 | SEPTEMBER
T-247-10288 | PS5-26-IK-6472A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | On hold |  | 11 | SEPTEMBER
T-639-10289 | PS5-34-UR-6667C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | In progress |  | 46 | SEPTEMBER
T-026-10290 | PS5-55-OB-9480C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone B | 1.1 | To be completed |  | 22 | AUGUST
T-310-10291 | PS5-51-OB-2439D | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone G | 6 | In progress |  | 37 | DECEMBER
T-395-10292 | PS5-52-UR-3328A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-01-20 | PS5-13-01 | PS5 - Milestone D | 3 | Closed | 19 | 34 | JANUARY
T-411-10293 | PS5-17-OB-9042B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone F | 5 | In progress |  | 4 | DECEMBER
T-195-10294 | PS5-76-OB-2255B | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone I | 8 | In progress |  | 30 | NOVEMBER
T-717-10295 | PS5-94-IK-7701B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone A | 1 | In progress |  | 40 | DECEMBER
T-979-10296 | PS5-85-IK-3964A | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-05-22 | PS5-07-04 | PS5 - Milestone A | 1 | Closed | 9 | 27 | MAY
T-518-10297 | PS5-99-UR-9730B | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone F | 5 | To be completed |  | 29 | SEPTEMBER
T-330-10298 | PS5-41-OB-3915D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-05-10 | PS5-08-02 | PS5 - Milestone I | 8 | Closed | 13 | 10 | MAY
T-054-10299 | PS5-95-OB-4762A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone B | 1.1 | In progress |  | 43 | SEPTEMBER
T-730-10300 | PS5-72-IK-9352B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-04-28 | PS5-04-04 | PS5 - Milestone I | 8 | Closed | 34 | 23 | APRIL
T-157-10301 | PS5-70-OB-8690B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-05-07 | PS5-99-01 | PS5 - Milestone B | 1.1 | Closed | 40 | 4 | MAY
T-788-10302 | PS5-34-IK-9733A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-01-20 | PS5-62-01 | PS5 - Milestone A | 1 | Closed | 13 | 34 | JANUARY
T-553-10303 | PS5-80-OB-6093C | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone F | 5 | To be completed |  | 26 | AUGUST
T-754-10304 | PS5-62-OB-3876C | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone D | 3 | To be completed |  | 44 | DECEMBER
T-927-10305 | PS5-91-IK-8861A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-11-06 | PS5-01-01 | PS5 - Milestone A | 1 | Closed | 23 | 16 | NOVEMBER
T-029-10306 | PS5-55-UR-6824A | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone H | 7 | To be completed |  | 40 | SEPTEMBER
T-030-10307 | PS5-43-UR-2262D | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone D | 3 | In progress |  | 17 | SEPTEMBER
T-237-10308 | PS5-04-OB-4115B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone I | 8 | To be completed |  | 46 | OCTOBER
T-337-10309 | PS5-01-OB-2635D | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone D | 3 | To be completed |  | 25 | AUGUST
T-281-10310 | PS5-25-OB-7396B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone D | 3 | In progress |  | 12 | AUGUST
T-744-10311 | PS5-56-UR-4589D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-09-18 | PS5-03-02 | PS5 - Milestone D | 3 | Closed | 22 | 36 | SEPTEMBER
T-129-10312 | PS5-02-OB-3111A | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone E | 4 | To be completed |  | 26 | NOVEMBER
T-906-10313 | PS5-90-UR-5002D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone G | 6 | To be completed |  | 20 | AUGUST
T-201-10314 | PS5-90-IK-3105A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-02 | PS5-60-01 | PS5 - Milestone E | 4 | Closed | 5 | 17 | FEBRUARY
T-352-10315 | PS5-47-OB-4710C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-08-03 | PS5-06-03 | PS5 - Milestone H | 7 | Closed | 33 | 43 | AUGUST
T-285-10316 | PS5-91-IK-9263C | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone D | 3 | In progress |  | 18 | OCTOBER
T-404-10317 | PS5-06-OB-9123A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-11-12 | PS5-01-08 | PS5 - Milestone A | 1 | Closed | 32 | 26 | NOVEMBER
T-116-10318 | PS5-55-OB-3777A | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | On hold |  | 36 | DECEMBER
T-964-10319 | PS5-02-UR-1705D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone E | 4 | To be completed |  | 43 | OCTOBER
T-706-10320 | PS5-65-UR-1929B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-10-04 | PS5-09-02 | PS5 - Milestone C | 2 | Closed | 11 | 27 | OCTOBER
T-882-10321 | PS5-70-UR-4970A | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-01-27 | PS5-11-02 | PS5 - Milestone A | 1 | Closed | 35 | 32 | JANUARY
T-348-10322 | PS5-09-OB-3065A | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone D | 3 | To be completed |  | 48 | DECEMBER
T-375-10323 | PS5-56-OB-1090C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | On hold |  | 27 | DECEMBER
T-921-10324 | PS5-02-UR-8798B | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-03-21 | PS5-07-01 | PS5 - Milestone G | 6 | Closed | 14 | 7 | MARCH
T-978-10325 | PS5-11-OB-9051A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone F | 5 | To be completed |  | 29 | DECEMBER
T-525-10326 | PS5-39-OB-6130C | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-12-15 | PS5-61-07 | PS5 - Milestone B | 1.1 | Closed | 39 | 6 | DECEMBER
T-636-10327 | PS5-96-UR-5273B | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-01-12 | PS5-99-02 | PS5 - Milestone F | 5 | Closed | 31 | 28 | JANUARY
T-097-10328 | PS5-38-UR-5097B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone B | 1.1 | To be completed |  | 35 | NOVEMBER
T-586-10329 | PS5-67-IK-5351A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone I | 8 | To be completed |  | 29 | OCTOBER
T-110-10330 | PS5-43-IK-7793A | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone B | 1.1 | In progress |  | 20 | OCTOBER
T-389-10331 | PS5-78-OB-2972C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone D | 3 | On hold |  | 26 | NOVEMBER
T-420-10332 | PS5-54-OB-3125B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-07-13 | PS5-08-01 | PS5 - Milestone E | 4 | Closed | 48 | 31 | JULY
T-290-10333 | PS5-71-OB-4404D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | On hold |  | 24 | OCTOBER
T-857-10334 | PS5-48-OB-8112B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | In progress |  | 17 | SEPTEMBER
T-793-10335 | PS5-33-OB-6781C | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-01-26 | PS5-06-03 | PS5 - Milestone F | 5 | Closed | 15 | 46 | JANUARY
T-614-10336 | PS5-56-OB-3192D | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone G | 6 | On hold |  | 47 | DECEMBER
T-008-10337 | PS5-27-UR-6465C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | On hold |  | 39 | AUGUST
T-579-10338 | PS5-60-UR-7767B | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone G | 6 | On hold |  | 33 | NOVEMBER
T-682-10339 | PS5-42-OB-1102D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone E | 4 | In progress |  | 42 | AUGUST
T-180-10340 | PS5-16-UR-1072C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone G | 6 | On hold |  | 12 | NOVEMBER
T-429-10341 | PS5-89-IK-4031B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone F | 5 | On hold |  | 22 | OCTOBER
T-397-10342 | PS5-71-UR-3894A | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-09-09 | PS5-62-01 | PS5 - Milestone I | 8 | Closed | 38 | 6 | SEPTEMBER
T-760-10343 | PS5-93-OB-1215D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-04-08 | PS5-10-06 | PS5 - Milestone H | 7 | Closed | 31 | 44 | APRIL
T-005-10344 | PS5-30-OB-3073C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone B | 1.1 | To be completed |  | 20 | AUGUST
T-265-10345 | PS5-97-OB-7045A | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone C | 2 | On hold |  | 19 | AUGUST
T-187-10346 | PS5-30-UR-9933C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-01-08 | PS5-02-02 | PS5 - Milestone A | 1 | Closed | 35 | 41 | JANUARY
T-570-10347 | PS5-33-UR-4286D | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-02-18 | PS5-01-08 | PS5 - Milestone F | 5 | Closed | 32 | 21 | FEBRUARY
T-508-10348 | PS5-20-OB-9947D | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-10-26 | PS5-01-07 | PS5 - Milestone C | 2 | Closed | 42 | 48 | OCTOBER
T-119-10349 | PS5-05-OB-9095B | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone C | 2 | To be completed |  | 37 | NOVEMBER
T-320-10350 | PS5-15-OB-5140C | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-10-09 | PS5-82-02 | PS5 - Milestone B | 1.1 | Closed | 6 | 28 | OCTOBER
T-625-10351 | PS5-92-IK-5131D | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-01-27 | PS5-63-01 | PS5 - Milestone H | 7 | Closed | 42 | 9 | JANUARY
T-308-10352 | PS5-24-IK-1772B | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-10-14 | PS5-07-04 | PS5 - Milestone H | 7 | Closed | 43 | 32 | OCTOBER
T-067-10353 | PS5-94-UR-5511B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-01-01 | PS5-60-10 | PS5 - Milestone B | 1.1 | Closed | 5 | 32 | JANUARY
T-968-10354 | PS5-17-OB-4625C | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-09-08 | PS5-02-01 | PS5 - Milestone E | 4 | Closed | 43 | 8 | SEPTEMBER
T-783-10355 | PS5-94-OB-6798D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-09-07 | PS5-08-02 | PS5 - Milestone A | 1 | Closed | 9 | 33 | SEPTEMBER
T-021-10356 | PS5-55-OB-1682C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-03-04 | PS5-07-04 | PS5 - Milestone E | 4 | Closed | 20 | 37 | MARCH
T-288-10357 | PS5-39-UR-4371B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone I | 8 | To be completed |  | 25 | AUGUST
T-380-10358 | PS5-83-UR-6595C | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone I | 8 | To be completed |  | 39 | DECEMBER
T-238-10359 | PS5-14-UR-4712B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone G | 6 | On hold |  | 41 | AUGUST
T-915-10360 | PS5-22-IK-7827D | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-08-22 | PS5-61-02 | PS5 - Milestone H | 7 | Closed | 38 | 15 | AUGUST
T-377-10361 | PS5-25-IK-8615A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone G | 6 | In progress |  | 28 | AUGUST
T-955-10362 | PS5-04-OB-6673D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone D | 3 | In progress |  | 11 | AUGUST
T-185-10363 | PS5-02-UR-8018D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-08-06 | PS5-13-01 | PS5 - Milestone F | 5 | Closed | 21 | 17 | AUGUST
T-325-10364 | PS5-70-UR-2729D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-04-13 | PS5-12-01 | PS5 - Milestone G | 6 | Closed | 37 | 41 | APRIL
T-214-10365 | PS5-94-OB-2686B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone B | 1.1 | On hold |  | 47 | DECEMBER
T-482-10366 | PS5-47-OB-8858C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | In progress |  | 10 | OCTOBER
T-569-10367 | PS5-75-OB-7252C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone C | 2 | To be completed |  | 41 | DECEMBER
T-131-10368 | PS5-87-OB-1642C | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone B | 1.1 | In progress |  | 48 | OCTOBER
T-162-10369 | PS5-41-OB-7708B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone A | 1 | In progress |  | 28 | DECEMBER
T-720-10370 | PS5-72-UR-1304B | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-05-02 | PS5-60-01 | PS5 - Milestone B | 1.1 | Closed | 42 | 15 | MAY
T-003-10371 | PS5-39-OB-3913D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | In progress |  | 19 | AUGUST
T-890-10372 | PS5-50-UR-9318D | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone H | 7 | On hold |  | 32 | NOVEMBER
T-042-10373 | PS5-61-UR-8441D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | On hold |  | 22 | SEPTEMBER
T-710-10374 | PS5-65-OB-1173A | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-01-15 | PS5-01-08 | PS5 - Milestone I | 8 | Closed | 44 | 17 | JANUARY
T-654-10375 | PS5-40-IK-6041D | CQH02 - AHU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | To be completed |  | 25 | NOVEMBER
T-335-10376 | PS5-96-IK-8879A | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-07-15 | PS5-04-01 | PS5 - Milestone F | 5 | Closed | 10 | 21 | JULY
T-869-10377 | PS5-02-OB-2385A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone B | 1.1 | In progress |  | 42 | OCTOBER
T-597-10378 | PS5-95-OB-4917A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-07-18 | PS5-02-02 | PS5 - Milestone I | 8 | Closed | 23 | 30 | JULY
T-706-10379 | PS5-95-IK-3334C | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone C | 2 | On hold |  | 20 | NOVEMBER
T-861-10380 | PS5-07-IK-8037D | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-05-09 | PS5-02-02 | PS5 - Milestone F | 5 | Closed | 38 | 21 | MAY
T-884-10381 | PS5-14-IK-3110C | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-04-20 | PS5-99-02 | PS5 - Milestone F | 5 | Closed | 35 | 12 | APRIL
T-248-10382 | PS5-11-OB-5751A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-05-16 | PS5-63-04 | PS5 - Milestone G | 6 | Closed | 11 | 18 | MAY
T-725-10383 | PS5-87-OB-3026C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone G | 6 | To be completed |  | 16 | DECEMBER
T-640-10384 | PS5-78-OB-1651B | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-03-19 | PS5-07-03 | PS5 - Milestone E | 4 | Closed | 4 | 27 | MARCH
T-882-10385 | PS5-33-IK-9756D | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | On hold |  | 8 | DECEMBER
T-205-10386 | PS5-49-OB-4064C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone F | 5 | In progress |  | 40 | DECEMBER
T-544-10387 | PS5-72-OB-6872C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-12-07 | PS5-01-09 | PS5 - Milestone B | 1.1 | Closed | 38 | 30 | DECEMBER
T-844-10388 | PS5-72-UR-4395C | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-09-04 | PS5-01-09 | PS5 - Milestone D | 3 | Closed | 40 | 27 | SEPTEMBER
T-742-10389 | PS5-31-OB-8491A | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone C | 2 | To be completed |  | 10 | NOVEMBER
T-194-10390 | PS5-80-OB-9404D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-07-07 | PS5-12-02 | PS5 - Milestone H | 7 | Closed | 22 | 18 | JULY
T-990-10391 | PS5-35-OB-7762B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone A | 1 | To be completed |  | 39 | SEPTEMBER
T-382-10392 | PS5-40-OB-5330C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-07-13 | PS5-07-04 | PS5 - Milestone E | 4 | Closed | 44 | 35 | JULY
T-617-10393 | PS5-19-OB-5199B | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone D | 3 | In progress |  | 9 | OCTOBER
T-841-10394 | PS5-65-UR-8507A | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-08-08 | PS5-07-01 | PS5 - Milestone I | 8 | Closed | 36 | 18 | AUGUST
T-226-10395 | PS5-02-OB-7953C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone F | 5 | To be completed |  | 31 | AUGUST
T-874-10396 | PS5-03-OB-3917B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-07-19 | PS5-10-05 | PS5 - Milestone C | 2 | Closed | 26 | 38 | JULY
T-667-10397 | PS5-01-UR-8823A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | To be completed |  | 38 | OCTOBER
T-482-10398 | PS5-21-IK-4396C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | To be completed |  | 48 | OCTOBER
T-678-10399 | PS5-24-OB-2673D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-06-20 | PS5-11-02 | PS5 - Milestone F | 5 | Closed | 37 | 42 | JUNE
T-392-10400 | PS5-44-UR-1308C | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-09-23 | PS5-08-02 | PS5 - Milestone B | 1.1 | Closed | 17 | 18 | SEPTEMBER
T-730-10401 | PS5-05-IK-3762C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone H | 7 | In progress |  | 11 | NOVEMBER
T-317-10402 | PS5-91-UR-8344B | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone I | 8 | To be completed |  | 32 | AUGUST
T-354-10403 | PS5-24-OB-6302D | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone E | 4 | To be completed |  | 48 | DECEMBER
T-825-10404 | PS5-55-IK-6727A | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-02-25 | PS5-61-01 | PS5 - Milestone E | 4 | Closed | 5 | 21 | FEBRUARY
T-404-10405 | PS5-22-UR-8445A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone F | 5 | On hold |  | 41 | SEPTEMBER
T-631-10406 | PS5-72-IK-6195A | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone F | 5 | To be completed |  | 14 | OCTOBER
T-375-10407 | PS5-13-UR-1366C | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone C | 2 | On hold |  | 4 | AUGUST
T-641-10408 | PS5-24-OB-4821C | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-04-02 | PS5-01-06 | PS5 - Milestone B | 1.1 | Closed | 28 | 46 | APRIL
T-064-10409 | PS5-12-OB-6727A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone H | 7 | In progress |  | 44 | SEPTEMBER
T-434-10410 | PS5-31-OB-3599C | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-11-27 | PS5-07-01 | PS5 - Milestone E | 4 | Closed | 10 | 42 | NOVEMBER
T-840-10411 | PS5-51-UR-1009C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-11-16 | PS5-61-07 | PS5 - Milestone G | 6 | Closed | 47 | 46 | NOVEMBER
T-668-10412 | PS5-36-OB-9260B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone A | 1 | In progress |  | 6 | NOVEMBER
T-164-10413 | PS5-64-UR-2687A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-01-08 | PS5-04-04 | PS5 - Milestone H | 7 | Closed | 15 | 33 | JANUARY
T-199-10414 | PS5-60-OB-3485A | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone F | 5 | In progress |  | 8 | DECEMBER
T-349-10415 | PS5-36-OB-9926A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-05-04 | PS5-03-01 | PS5 - Milestone F | 5 | Closed | 26 | 22 | MAY
T-772-10416 | PS5-85-OB-1963D | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone I | 8 | In progress |  | 32 | DECEMBER
T-452-10417 | PS5-79-OB-6489B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | In progress |  | 40 | OCTOBER
T-460-10418 | PS5-07-OB-9272B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone I | 8 | In progress |  | 21 | AUGUST
T-286-10419 | PS5-64-IK-7961A | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone A | 1 | In progress |  | 27 | AUGUST
T-442-10420 | PS5-02-UR-4764C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone I | 8 | In progress |  | 39 | SEPTEMBER
T-492-10421 | PS5-25-IK-4840A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone B | 1.1 | To be completed |  | 6 | SEPTEMBER
T-187-10422 | PS5-95-OB-2334B | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-04-26 | PS5-99-01 | PS5 - Milestone F | 5 | Closed | 31 | 21 | APRIL
T-597-10423 | PS5-89-IK-4398D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-01-23 | PS5-82-01 | PS5 - Milestone C | 2 | Closed | 8 | 40 | JANUARY
T-440-10424 | PS5-59-UR-8957A | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone A | 1 | To be completed |  | 21 | DECEMBER
T-979-10425 | PS5-48-OB-3306C | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-12-10 | PS5-63-01 | PS5 - Milestone B | 1.1 | Closed | 17 | 22 | DECEMBER
T-642-10426 | PS5-94-OB-1363B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-02-23 | PS5-04-01 | PS5 - Milestone I | 8 | Closed | 6 | 17 | FEBRUARY
T-593-10427 | PS5-24-UR-9954B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone H | 7 | In progress |  | 32 | OCTOBER
T-364-10428 | PS5-19-OB-5669D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone E | 4 | To be completed |  | 7 | SEPTEMBER
T-993-10429 | PS5-86-OB-3592A | CQM04 - Vessel | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone B | 1.1 | To be completed |  | 13 | OCTOBER
T-606-10430 | PS5-88-OB-6153C | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone F | 5 | In progress |  | 41 | SEPTEMBER
T-592-10431 | PS5-84-UR-8537C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone D | 3 | On hold |  | 47 | NOVEMBER
T-749-10432 | PS5-34-OB-6187C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone H | 7 | In progress |  | 12 | NOVEMBER
T-815-10433 | PS5-68-OB-1386B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone F | 5 | On hold |  | 17 | DECEMBER
T-878-10434 | PS5-99-OB-1005D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone F | 5 | In progress |  | 45 | NOVEMBER
T-440-10435 | PS5-18-IK-8923B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-10-07 | PS5-10-06 | PS5 - Milestone G | 6 | Closed | 44 | 14 | OCTOBER
T-405-10436 | PS5-18-UR-8766D | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-04-09 | PS5-10-06 | PS5 - Milestone E | 4 | Closed | 5 | 8 | APRIL
T-100-10437 | PS5-71-IK-7890D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone E | 4 | To be completed |  | 28 | DECEMBER
T-590-10438 | PS5-03-IK-2208C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-02-26 | PS5-10-01 | PS5 - Milestone A | 1 | Closed | 33 | 15 | FEBRUARY
T-775-10439 | PS5-53-IK-2721B | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | In progress |  | 10 | SEPTEMBER
T-601-10440 | PS5-44-OB-7565A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone F | 5 | To be completed |  | 32 | SEPTEMBER
T-331-10441 | PS5-08-UR-1499B | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-03-24 | PS5-11-03 | PS5 - Milestone G | 6 | Closed | 18 | 39 | MARCH
T-017-10442 | PS5-40-IK-5304A | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone D | 3 | On hold |  | 44 | OCTOBER
T-511-10443 | PS5-19-UR-7115C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone C | 2 | To be completed |  | 43 | SEPTEMBER
T-647-10444 | PS5-30-OB-7587D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone F | 5 | In progress |  | 14 | DECEMBER
T-850-10445 | PS5-07-OB-1422B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone I | 8 | To be completed |  | 6 | DECEMBER
T-073-10446 | PS5-52-UR-9085B | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone F | 5 | In progress |  | 39 | AUGUST
T-581-10447 | PS5-69-IK-5437C | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-10-05 | PS5-01-03 | PS5 - Milestone B | 1.1 | Closed | 43 | 13 | OCTOBER
T-187-10448 | PS5-83-OB-6905A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-03-25 | PS5-01-09 | PS5 - Milestone G | 6 | Closed | 47 | 47 | MARCH
T-414-10449 | PS5-58-UR-4043B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone A | 1 | To be completed |  | 36 | DECEMBER
T-793-10450 | PS5-02-IK-1407D | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | To be completed |  | 6 | NOVEMBER
T-196-10451 | PS5-38-UR-6046D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone H | 7 | In progress |  | 29 | SEPTEMBER
T-801-10452 | PS5-26-OB-6000B | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-03-18 | PS5-06-03 | PS5 - Milestone D | 3 | Closed | 47 | 7 | MARCH
T-794-10453 | PS5-01-IK-3839D | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone C | 2 | In progress |  | 45 | AUGUST
T-273-10454 | PS5-66-IK-5373D | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone G | 6 | On hold |  | 34 | OCTOBER
T-495-10455 | PS5-59-UR-3017D | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone G | 6 | To be completed |  | 42 | OCTOBER
T-846-10456 | PS5-10-UR-3285D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-03-13 | PS5-01-07 | PS5 - Milestone B | 1.1 | Closed | 44 | 38 | MARCH
T-746-10457 | PS5-27-OB-2660C | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-07-17 | PS5-06-01 | PS5 - Milestone H | 7 | Closed | 18 | 7 | JULY
T-177-10458 | PS5-92-IK-9451D | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-06-08 | PS5-07-02 | PS5 - Milestone H | 7 | Closed | 44 | 17 | JUNE
T-049-10459 | PS5-04-OB-1330D | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone I | 8 | On hold |  | 44 | DECEMBER
T-828-10460 | PS5-42-IK-2573A | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-05-17 | PS5-62-02 | PS5 - Milestone B | 1.1 | Closed | 7 | 7 | MAY
T-857-10461 | PS5-17-OB-7983D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone A | 1 | To be completed |  | 30 | OCTOBER
T-803-10462 | PS5-87-IK-4886D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | On hold |  | 22 | AUGUST
T-179-10463 | PS5-88-OB-2271B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone B | 1.1 | To be completed |  | 44 | SEPTEMBER
T-518-10464 | PS5-04-IK-3898D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-10-10 | PS5-02-03 | PS5 - Milestone E | 4 | Closed | 33 | 7 | OCTOBER
T-064-10465 | PS5-91-UR-8680D | CQX04 - Painting & Coating | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone H | 7 | To be completed |  | 48 | DECEMBER
T-652-10466 | PS5-62-OB-5314D | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-07-25 | PS5-04-02 | PS5 - Milestone I | 8 | Closed | 27 | 23 | JULY
T-375-10467 | PS5-56-OB-1610D | CQM01 - Pump Installation | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone B | 1.1 | In progress |  | 40 | SEPTEMBER
T-613-10468 | PS5-82-UR-2412D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone A | 1 | In progress |  | 12 | DECEMBER
T-863-10469 | PS5-61-OB-9732A | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone H | 7 | To be completed |  | 27 | DECEMBER
T-254-10470 | PS5-65-OB-4682B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-02-10 | PS5-01-01 | PS5 - Milestone A | 1 | Closed | 22 | 31 | FEBRUARY
T-449-10471 | PS5-58-UR-4241D | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone C | 2 | To be completed |  | 21 | NOVEMBER
T-631-10472 | PS5-78-IK-2402D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone E | 4 | To be completed |  | 24 | AUGUST
T-283-10473 | PS5-52-OB-6614B | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-02-02 | PS5-09-01 | PS5 - Milestone C | 2 | Closed | 38 | 20 | FEBRUARY
T-794-10474 | PS5-43-UR-4276D | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone G | 6 | To be completed |  | 23 | DECEMBER
T-136-10475 | PS5-40-OB-5516B | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone B | 1.1 | On hold |  | 48 | OCTOBER
T-533-10476 | PS5-54-OB-7605A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone G | 6 | In progress |  | 17 | SEPTEMBER
T-297-10477 | PS5-41-UR-4959C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone I | 8 | On hold |  | 12 | DECEMBER
T-961-10478 | PS5-91-OB-4548D | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone E | 4 | On hold |  | 48 | AUGUST
T-508-10479 | PS5-22-UR-7114D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-04-22 | PS5-82-01 | PS5 - Milestone D | 3 | Closed | 14 | 40 | APRIL
T-503-10480 | PS5-81-OB-3569B | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-10-28 | PS5-08-02 | PS5 - Milestone D | 3 | Closed | 48 | 10 | OCTOBER
T-883-10481 | PS5-23-IK-6467B | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone C | 2 | To be completed |  | 11 | AUGUST
T-732-10482 | PS5-34-OB-4137A | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone A | 1 | On hold |  | 10 | AUGUST
T-294-10483 | PS5-28-IK-7914A | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-13 | PS5-60-10 | PS5 - Milestone G | 6 | Closed | 20 | 7 | JUNE
T-968-10484 | PS5-78-UR-6112B | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone A | 1 | To be completed |  | 10 | AUGUST
T-665-10485 | PS5-48-OB-3113A | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-01-27 | PS5-61-02 | PS5 - Milestone E | 4 | Closed | 21 | 15 | JANUARY
T-253-10486 | PS5-72-UR-7149B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone A | 1 | On hold |  | 45 | NOVEMBER
T-945-10487 | PS5-24-IK-6238B | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone H | 7 | In progress |  | 33 | SEPTEMBER
T-188-10488 | PS5-78-OB-9092A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-05-08 | PS5-01-05 | PS5 - Milestone G | 6 | Closed | 31 | 25 | MAY
T-577-10489 | PS5-74-UR-5946A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone B | 1.1 | In progress |  | 31 | SEPTEMBER
T-038-10490 | PS5-50-OB-9804C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone D | 3 | In progress |  | 4 | NOVEMBER
T-097-10491 | PS5-28-OB-5579A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone I | 8 | On hold |  | 20 | SEPTEMBER
T-811-10492 | PS5-19-IK-5673C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone A | 1 | To be completed |  | 34 | OCTOBER
T-687-10493 | PS5-44-OB-7341D | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | To be completed |  | 41 | NOVEMBER
T-371-10494 | PS5-59-OB-4942D | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-09-25 | PS5-10-04 | PS5 - Milestone A | 1 | Closed | 30 | 8 | SEPTEMBER
T-519-10495 | PS5-47-OB-5397B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | In progress |  | 10 | OCTOBER
T-427-10496 | PS5-51-UR-8785D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-07-15 | PS5-01-02 | PS5 - Milestone B | 1.1 | Closed | 28 | 32 | JULY
T-276-10497 | PS5-82-OB-5869C | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone H | 7 | To be completed |  | 47 | DECEMBER
T-955-10498 | PS5-95-OB-2531A | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-04-11 | PS5-11-03 | PS5 - Milestone G | 6 | Closed | 48 | 17 | APRIL
T-671-10499 | PS5-58-UR-9101C | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone H | 7 | To be completed |  | 27 | AUGUST
T-457-10500 | PS5-11-OB-8464D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone D | 3 | On hold |  | 23 | OCTOBER
T-536-10501 | PS5-38-OB-8916A | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | In progress |  | 7 | SEPTEMBER
T-137-10502 | PS5-39-IK-2162B | CQP05 - Insulation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone I | 8 | On hold |  | 9 | AUGUST
T-846-10503 | PS5-31-UR-2781A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-10-28 | PS5-07-01 | PS5 - Milestone E | 4 | Closed | 32 | 40 | OCTOBER
T-461-10504 | PS5-84-IK-8537B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | On hold |  | 35 | OCTOBER
T-938-10505 | PS5-33-UR-8278A | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-11-03 | PS5-01-01 | PS5 - Milestone D | 3 | Closed | 13 | 35 | NOVEMBER
T-026-10506 | PS5-03-OB-8109A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone D | 3 | On hold |  | 32 | DECEMBER
T-812-10507 | PS5-87-IK-1600D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone B | 1.1 | To be completed |  | 43 | AUGUST
T-250-10508 | PS5-68-IK-2322B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-08-12 | PS5-08-01 | PS5 - Milestone C | 2 | Closed | 11 | 23 | AUGUST
T-078-10509 | PS5-94-OB-4819B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | To be completed |  | 17 | OCTOBER
T-735-10510 | PS5-48-UR-2203C | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | To be completed |  | 31 | OCTOBER
T-044-10511 | PS5-41-IK-2031B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone H | 7 | To be completed |  | 48 | OCTOBER
T-682-10512 | PS5-33-OB-6853C | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone C | 2 | To be completed |  | 7 | SEPTEMBER
T-456-10513 | PS5-74-OB-4555B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | To be completed |  | 43 | DECEMBER
T-445-10514 | PS5-90-UR-7969D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-04-22 | PS5-09-04 | PS5 - Milestone I | 8 | Closed | 8 | 29 | APRIL
T-661-10515 | PS5-38-OB-1765B | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone C | 2 | To be completed |  | 9 | SEPTEMBER
T-870-10516 | PS5-77-OB-3174A | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | To be completed |  | 6 | SEPTEMBER
T-340-10517 | PS5-44-OB-1859B | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone A | 1 | To be completed |  | 4 | NOVEMBER
T-048-10518 | PS5-23-OB-9521A | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone A | 1 | In progress |  | 40 | AUGUST
T-941-10519 | PS5-01-OB-9599C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone D | 3 | In progress |  | 17 | NOVEMBER
T-123-10520 | PS5-55-OB-9139D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-10-22 | PS5-10-02 | PS5 - Milestone A | 1 | Closed | 15 | 42 | OCTOBER
T-661-10521 | PS5-19-OB-1889C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | To be completed |  | 33 | SEPTEMBER
T-856-10522 | PS5-61-OB-3896C | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone I | 8 | In progress |  | 36 | SEPTEMBER
T-221-10523 | PS5-60-UR-6050C | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-09-26 | PS5-07-01 | PS5 - Milestone G | 6 | Closed | 11 | 48 | SEPTEMBER
T-143-10524 | PS5-92-OB-8839B | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone B | 1.1 | To be completed |  | 33 | DECEMBER
T-406-10525 | PS5-93-OB-5019C | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-05-03 | PS5-82-07 | PS5 - Milestone G | 6 | Closed | 33 | 24 | MAY
T-827-10526 | PS5-14-OB-1049B | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-08-26 | PS5-63-01 | PS5 - Milestone B | 1.1 | Closed | 30 | 42 | AUGUST
T-256-10527 | PS5-42-OB-3994D | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-05-01 | PS5-07-02 | PS5 - Milestone D | 3 | Closed | 22 | 5 | MAY
T-138-10528 | PS5-23-OB-8143D | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone H | 7 | To be completed |  | 17 | OCTOBER
T-306-10529 | PS5-29-OB-6995D | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-08-17 | PS5-06-03 | PS5 - Milestone A | 1 | Closed | 37 | 16 | AUGUST
T-192-10530 | PS5-73-OB-7697D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-10-12 | PS5-05-03 | PS5 - Milestone C | 2 | Closed | 46 | 35 | OCTOBER
T-870-10531 | PS5-64-OB-7078A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-08-01 | PS5-63-01 | PS5 - Milestone B | 1.1 | Closed | 21 | 40 | AUGUST
T-031-10532 | PS5-43-IK-6003D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-12-05 | PS5-10-05 | PS5 - Milestone C | 2 | Closed | 35 | 29 | DECEMBER
T-105-10533 | PS5-32-OB-8966C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone E | 4 | To be completed |  | 5 | SEPTEMBER
T-319-10534 | PS5-71-IK-5391A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-08-08 | PS5-01-08 | PS5 - Milestone H | 7 | Closed | 16 | 33 | AUGUST
T-492-10535 | PS5-67-UR-3749D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone B | 1.1 | To be completed |  | 32 | AUGUST
T-030-10536 | PS5-56-OB-6575B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | To be completed |  | 35 | NOVEMBER
T-224-10537 | PS5-91-OB-1954D | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone C | 2 | To be completed |  | 40 | SEPTEMBER
T-421-10538 | PS5-94-OB-2691B | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-02-04 | PS5-12-02 | PS5 - Milestone H | 7 | Closed | 13 | 26 | FEBRUARY
T-219-10539 | PS5-07-UR-7800B | CQP04 - Hydrotest | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-05-15 | PS5-02-02 | PS5 - Milestone D | 3 | Closed | 29 | 34 | MAY
T-334-10540 | PS5-95-UR-2595C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | In progress |  | 40 | DECEMBER
T-311-10541 | PS5-60-IK-3156D | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone C | 2 | To be completed |  | 27 | AUGUST
T-663-10542 | PS5-38-UR-2746B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-07-17 | PS5-62-01 | PS5 - Milestone E | 4 | Closed | 18 | 22 | JULY
T-878-10543 | PS5-65-IK-9348D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone A | 1 | In progress |  | 4 | DECEMBER
T-411-10544 | PS5-29-IK-7744A | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone C | 2 | In progress |  | 48 | AUGUST
T-465-10545 | PS5-94-IK-3688B | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone A | 1 | To be completed |  | 43 | SEPTEMBER
T-793-10546 | PS5-67-UR-2041B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-11-17 | PS5-06-02 | PS5 - Milestone G | 6 | Closed | 38 | 23 | NOVEMBER
T-238-10547 | PS5-32-IK-1554C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-10-11 | PS5-08-02 | PS5 - Milestone A | 1 | Closed | 21 | 32 | OCTOBER
T-361-10548 | PS5-34-IK-2657C | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | To be completed |  | 35 | SEPTEMBER
T-606-10549 | PS5-57-IK-4257B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone F | 5 | To be completed |  | 43 | AUGUST
T-641-10550 | PS5-32-IK-3768B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-05-15 | PS5-01-03 | PS5 - Milestone D | 3 | Closed | 13 | 28 | MAY
T-601-10551 | PS5-15-OB-6906B | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone C | 2 | To be completed |  | 43 | NOVEMBER
T-654-10552 | PS5-88-OB-5977B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-07-04 | PS5-07-04 | PS5 - Milestone I | 8 | Closed | 48 | 20 | JULY
T-731-10553 | PS5-76-OB-3353C | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone G | 6 | To be completed |  | 27 | NOVEMBER
T-300-10554 | PS5-39-UR-5858C | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone G | 6 | To be completed |  | 45 | SEPTEMBER
T-978-10555 | PS5-72-OB-8077D | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone F | 5 | In progress |  | 26 | OCTOBER
T-391-10556 | PS5-72-UR-8315C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-07-20 | PS5-61-01 | PS5 - Milestone G | 6 | Closed | 21 | 11 | JULY
T-647-10557 | PS5-82-OB-1409C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-04-13 | PS5-61-02 | PS5 - Milestone B | 1.1 | Closed | 32 | 46 | APRIL
T-894-10558 | PS5-46-OB-5561C | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone A | 1 | To be completed |  | 29 | SEPTEMBER
T-377-10559 | PS5-25-OB-7910C | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone I | 8 | In progress |  | 41 | DECEMBER
T-302-10560 | PS5-18-IK-3264C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone E | 4 | In progress |  | 17 | DECEMBER
T-844-10561 | PS5-34-OB-8175B | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-03-18 | PS5-60-07 | PS5 - Milestone A | 1 | Closed | 19 | 46 | MARCH
T-216-10562 | PS5-91-IK-3120D | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone E | 4 | To be completed |  | 13 | SEPTEMBER
T-655-10563 | PS5-82-UR-6302D | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone H | 7 | In progress |  | 32 | SEPTEMBER
T-378-10564 | PS5-48-UR-3246D | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone B | 1.1 | On hold |  | 8 | NOVEMBER
T-480-10565 | PS5-40-IK-7341B | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-02-20 | PS5-06-02 | PS5 - Milestone A | 1 | Closed | 21 | 48 | FEBRUARY
T-417-10566 | PS5-87-OB-3340D | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | In progress |  | 30 | AUGUST
T-804-10567 | PS5-66-OB-1227D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone A | 1 | In progress |  | 46 | SEPTEMBER
T-453-10568 | PS5-84-OB-2924D | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-08-23 | PS5-09-04 | PS5 - Milestone A | 1 | Closed | 17 | 13 | AUGUST
T-966-10569 | PS5-11-UR-2326C | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone B | 1.1 | In progress |  | 13 | OCTOBER
T-418-10570 | PS5-51-OB-9188C | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-05-09 | PS5-10-04 | PS5 - Milestone A | 1 | Closed | 23 | 20 | MAY
T-793-10571 | PS5-97-OB-7898B | CQS03 - Deluge System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-09-20 | PS5-01-08 | PS5 - Milestone D | 3 | Closed | 36 | 22 | SEPTEMBER
T-908-10572 | PS5-61-UR-8511A | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | To be completed |  | 29 | OCTOBER
T-513-10573 | PS5-78-IK-9524B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-01-09 | PS5-02-03 | PS5 - Milestone C | 2 | Closed | 23 | 33 | JANUARY
T-702-10574 | PS5-97-OB-4519B | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone D | 3 | In progress |  | 15 | OCTOBER
T-525-10575 | PS5-58-OB-2233C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-08-01 | PS5-07-03 | PS5 - Milestone E | 4 | Closed | 5 | 19 | AUGUST
T-440-10576 | PS5-71-IK-3638A | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | On hold |  | 36 | AUGUST
T-024-10577 | PS5-12-OB-4902A | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone C | 2 | To be completed |  | 25 | AUGUST
T-440-10578 | PS5-80-UR-7777A | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone B | 1.1 | To be completed |  | 22 | DECEMBER
T-691-10579 | PS5-03-UR-7844A | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | To be completed |  | 23 | NOVEMBER
T-358-10580 | PS5-87-IK-7909D | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-05-16 | PS5-01-07 | PS5 - Milestone B | 1.1 | Closed | 10 | 15 | MAY
T-268-10581 | PS5-33-UR-8760D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone A | 1 | To be completed |  | 9 | AUGUST
T-828-10582 | PS5-01-UR-1070B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone G | 6 | In progress |  | 22 | OCTOBER
T-634-10583 | PS5-01-OB-2088C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-06-10 | PS5-11-03 | PS5 - Milestone D | 3 | Closed | 4 | 15 | JUNE
T-594-10584 | PS5-73-OB-8432D | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone E | 4 | To be completed |  | 39 | AUGUST
T-749-10585 | PS5-75-UR-4424D | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone E | 4 | In progress |  | 27 | NOVEMBER
T-807-10586 | PS5-83-OB-8260C | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-08-28 | PS5-99-02 | PS5 - Milestone H | 7 | Closed | 6 | 14 | AUGUST
T-282-10587 | PS5-85-IK-8906D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-12-16 | PS5-07-02 | PS5 - Milestone C | 2 | Closed | 14 | 45 | DECEMBER
T-313-10588 | PS5-99-IK-1018B | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-12-21 | PS5-10-02 | PS5 - Milestone H | 7 | Closed | 26 | 22 | DECEMBER
T-622-10589 | PS5-86-IK-4414A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone H | 7 | To be completed |  | 45 | SEPTEMBER
T-879-10590 | PS5-58-OB-6413D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone D | 3 | On hold |  | 36 | SEPTEMBER
T-707-10591 | PS5-41-UR-9391B | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone F | 5 | To be completed |  | 48 | SEPTEMBER
T-385-10592 | PS5-11-OB-4037D | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-08-07 | PS5-12-02 | PS5 - Milestone A | 1 | Closed | 41 | 35 | AUGUST
T-260-10593 | PS5-03-OB-5030C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | To be completed |  | 25 | DECEMBER
T-039-10594 | PS5-70-IK-5851A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone A | 1 | To be completed |  | 20 | OCTOBER
T-054-10595 | PS5-63-OB-5800B | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | In progress |  | 38 | SEPTEMBER
T-657-10596 | PS5-35-UR-1999A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-04-16 | PS5-01-08 | PS5 - Milestone G | 6 | Closed | 48 | 32 | APRIL
T-791-10597 | PS5-55-OB-4316D | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-10-28 | PS5-01-01 | PS5 - Milestone H | 7 | Closed | 8 | 44 | OCTOBER
T-796-10598 | PS5-46-OB-7027A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-05-07 | PS5-62-01 | PS5 - Milestone I | 8 | Closed | 43 | 25 | MAY
T-580-10599 | PS5-20-OB-7863C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone H | 7 | To be completed |  | 14 | SEPTEMBER
T-581-10600 | PS5-79-OB-3368D | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-04-26 | PS5-61-07 | PS5 - Milestone E | 4 | Closed | 34 | 37 | APRIL
T-122-10601 | PS5-53-IK-3403D | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-03-14 | PS5-06-01 | PS5 - Milestone H | 7 | Closed | 27 | 16 | MARCH
T-390-10602 | PS5-90-OB-6427D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone C | 2 | To be completed |  | 38 | OCTOBER
T-498-10603 | PS5-86-OB-1087D | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone B | 1.1 | In progress |  | 12 | AUGUST
T-085-10604 | PS5-59-IK-6566B | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-09-11 | PS5-07-01 | PS5 - Milestone A | 1 | Closed | 18 | 32 | SEPTEMBER
T-890-10605 | PS5-04-OB-6281C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone G | 6 | In progress |  | 7 | OCTOBER
T-783-10606 | PS5-57-IK-9522D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-12-13 | PS5-63-01 | PS5 - Milestone A | 1 | Closed | 23 | 25 | DECEMBER
T-059-10607 | PS5-31-UR-7440C | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone B | 1.1 | To be completed |  | 5 | OCTOBER
T-718-10608 | PS5-71-IK-5993A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | On hold |  | 29 | AUGUST
T-117-10609 | PS5-64-UR-9434B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-06-13 | PS5-82-01 | PS5 - Milestone F | 5 | Closed | 12 | 20 | JUNE
T-965-10610 | PS5-18-OB-5687A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-01-28 | PS5-11-03 | PS5 - Milestone H | 7 | Closed | 42 | 16 | JANUARY
T-103-10611 | PS5-02-OB-4107D | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-07-12 | PS5-02-03 | PS5 - Milestone D | 3 | Closed | 12 | 25 | JULY
T-560-10612 | PS5-03-OB-5297D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone A | 1 | On hold |  | 16 | DECEMBER
T-881-10613 | PS5-78-OB-1585A | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-11-23 | PS5-05-03 | PS5 - Milestone H | 7 | Closed | 28 | 44 | NOVEMBER
T-099-10614 | PS5-90-UR-8775A | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | In progress |  | 47 | DECEMBER
T-557-10615 | PS5-05-OB-1245A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-06-06 | PS5-09-04 | PS5 - Milestone C | 2 | Closed | 6 | 30 | JUNE
T-870-10616 | PS5-16-OB-9537C | CQP05 - Insulation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-02-15 | PS5-12-01 | PS5 - Milestone I | 8 | Closed | 4 | 29 | FEBRUARY
T-917-10617 | PS5-89-OB-2197B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone F | 5 | In progress |  | 4 | AUGUST
T-391-10618 | PS5-02-UR-9168B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | On hold |  | 7 | AUGUST
T-715-10619 | PS5-17-OB-5491A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-06-05 | PS5-62-02 | PS5 - Milestone D | 3 | Closed | 29 | 5 | JUNE
T-184-10620 | PS5-73-OB-1670B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone A | 1 | In progress |  | 21 | DECEMBER
T-679-10621 | PS5-19-OB-7907D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | In progress |  | 22 | NOVEMBER
T-346-10622 | PS5-69-OB-8226A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-12-17 | PS5-07-03 | PS5 - Milestone D | 3 | Closed | 13 | 41 | DECEMBER
T-379-10623 | PS5-86-IK-6946D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-12-14 | PS5-06-03 | PS5 - Milestone A | 1 | Closed | 28 | 5 | DECEMBER
T-547-10624 | PS5-16-OB-7009C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-03-16 | PS5-05-01 | PS5 - Milestone D | 3 | Closed | 22 | 6 | MARCH
T-209-10625 | PS5-38-UR-3334A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone I | 8 | In progress |  | 25 | AUGUST
T-226-10626 | PS5-03-OB-7109A | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-08-06 | PS5-05-02 | PS5 - Milestone G | 6 | Closed | 28 | 31 | AUGUST
T-931-10627 | PS5-78-IK-7656D | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone I | 8 | In progress |  | 5 | AUGUST
T-783-10628 | PS5-11-UR-9759B | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | In progress |  | 10 | AUGUST
T-244-10629 | PS5-83-IK-3531D | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-05-17 | PS5-05-03 | PS5 - Milestone H | 7 | Closed | 31 | 44 | MAY
T-340-10630 | PS5-45-OB-7467B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone B | 1.1 | In progress |  | 21 | NOVEMBER
T-389-10631 | PS5-93-OB-2031A | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone C | 2 | To be completed |  | 27 | SEPTEMBER
T-255-10632 | PS5-01-IK-1793B | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone B | 1.1 | To be completed |  | 21 | NOVEMBER
T-168-10633 | PS5-60-OB-4863B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone D | 3 | To be completed |  | 24 | DECEMBER
T-299-10634 | PS5-02-OB-6822B | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone D | 3 | To be completed |  | 10 | OCTOBER
T-060-10635 | PS5-66-IK-7666D | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone E | 4 | To be completed |  | 36 | NOVEMBER
T-978-10636 | PS5-76-UR-6041B | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone D | 3 | To be completed |  | 7 | NOVEMBER
T-687-10637 | PS5-37-IK-8721D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone E | 4 | To be completed |  | 33 | NOVEMBER
T-262-10638 | PS5-47-OB-6672D | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone A | 1 | To be completed |  | 22 | DECEMBER
T-254-10639 | PS5-32-UR-5072D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | To be completed |  | 24 | SEPTEMBER
T-083-10640 | PS5-18-OB-8275C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone C | 2 | On hold |  | 48 | OCTOBER
T-113-10641 | PS5-11-UR-2672A | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone I | 8 | To be completed |  | 9 | NOVEMBER
T-181-10642 | PS5-97-OB-9300A | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone D | 3 | In progress |  | 6 | OCTOBER
T-955-10643 | PS5-55-UR-6078D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-01-07 | PS5-05-03 | PS5 - Milestone F | 5 | Closed | 33 | 37 | JANUARY
T-418-10644 | PS5-71-UR-2474A | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-07-11 | PS5-11-01 | PS5 - Milestone G | 6 | Closed | 34 | 11 | JULY
T-054-10645 | PS5-83-IK-9446D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | On hold |  | 10 | OCTOBER
T-656-10646 | PS5-12-UR-6397A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone G | 6 | To be completed |  | 34 | NOVEMBER
T-358-10647 | PS5-06-OB-7641A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone C | 2 | In progress |  | 40 | SEPTEMBER
T-387-10648 | PS5-92-UR-2698C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-08-27 | PS5-04-01 | PS5 - Milestone I | 8 | Closed | 44 | 46 | AUGUST
T-224-10649 | PS5-07-UR-3971A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-07-16 | PS5-60-10 | PS5 - Milestone D | 3 | Closed | 27 | 11 | JULY
T-174-10650 | PS5-53-UR-1936D | CQP01 - Pipe Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-07-17 | PS5-12-02 | PS5 - Milestone E | 4 | Closed | 17 | 45 | JULY
T-246-10651 | PS5-05-OB-5837A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone A | 1 | To be completed |  | 22 | SEPTEMBER
T-971-10652 | PS5-73-IK-3545B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-12-23 | PS5-03-02 | PS5 - Milestone C | 2 | Closed | 25 | 44 | DECEMBER
T-816-10653 | PS5-19-IK-9591D | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone H | 7 | To be completed |  | 16 | AUGUST
T-127-10654 | PS5-48-IK-6979C | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone C | 2 | In progress |  | 6 | SEPTEMBER
T-034-10655 | PS5-59-IK-3174A | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-02-12 | PS5-01-01 | PS5 - Milestone I | 8 | Closed | 12 | 36 | FEBRUARY
T-356-10656 | PS5-92-IK-4077D | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone E | 4 | To be completed |  | 21 | AUGUST
T-159-10657 | PS5-11-OB-3361C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone C | 2 | To be completed |  | 22 | SEPTEMBER
T-408-10658 | PS5-94-UR-3391D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | To be completed |  | 43 | DECEMBER
T-863-10659 | PS5-44-OB-3978C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | To be completed |  | 42 | DECEMBER
T-043-10660 | PS5-22-UR-6268D | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone G | 6 | To be completed |  | 11 | AUGUST
T-783-10661 | PS5-01-OB-6865A | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone G | 6 | To be completed |  | 41 | SEPTEMBER
T-090-10662 | PS5-61-IK-2859D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone C | 2 | To be completed |  | 39 | NOVEMBER
T-631-10663 | PS5-71-IK-5981B | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-07-09 | PS5-63-04 | PS5 - Milestone A | 1 | Closed | 14 | 42 | JULY
T-244-10664 | PS5-07-UR-9903B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | To be completed |  | 5 | DECEMBER
T-660-10665 | PS5-39-IK-7000A | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-09-04 | PS5-10-01 | PS5 - Milestone I | 8 | Closed | 28 | 28 | SEPTEMBER
T-988-10666 | PS5-46-OB-2627A | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-02-24 | PS5-61-02 | PS5 - Milestone G | 6 | Closed | 24 | 35 | FEBRUARY
T-699-10667 | PS5-43-UR-4985C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-11-07 | PS5-01-09 | PS5 - Milestone A | 1 | Closed | 45 | 30 | NOVEMBER
T-788-10668 | PS5-87-OB-1090A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | To be completed |  | 5 | DECEMBER
T-169-10669 | PS5-65-IK-3113C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-08-06 | PS5-07-01 | PS5 - Milestone H | 7 | Closed | 34 | 11 | AUGUST
T-736-10670 | PS5-86-OB-8429D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone I | 8 | To be completed |  | 6 | NOVEMBER
T-266-10671 | PS5-06-UR-4003A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone I | 8 | In progress |  | 8 | DECEMBER
T-364-10672 | PS5-37-OB-9576D | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone C | 2 | To be completed |  | 11 | OCTOBER
T-341-10673 | PS5-18-OB-1471A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone A | 1 | In progress |  | 34 | AUGUST
T-653-10674 | PS5-57-IK-4395D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone D | 3 | In progress |  | 26 | NOVEMBER
T-545-10675 | PS5-54-OB-4852D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-08-13 | PS5-10-05 | PS5 - Milestone D | 3 | Closed | 34 | 45 | AUGUST
T-597-10676 | PS5-65-UR-3204A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone C | 2 | On hold |  | 18 | DECEMBER
T-901-10677 | PS5-50-UR-4067A | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone E | 4 | To be completed |  | 43 | NOVEMBER
T-633-10678 | PS5-06-OB-9400C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-03-08 | PS5-82-02 | PS5 - Milestone D | 3 | Closed | 26 | 29 | MARCH
T-819-10679 | PS5-21-IK-3618A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone F | 5 | In progress |  | 33 | SEPTEMBER
T-572-10680 | PS5-33-UR-4753C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-06-22 | PS5-12-02 | PS5 - Milestone C | 2 | Closed | 39 | 48 | JUNE
T-387-10681 | PS5-83-IK-5798D | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone E | 4 | To be completed |  | 38 | AUGUST
T-246-10682 | PS5-92-OB-8513B | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-01-01 | PS5-11-01 | PS5 - Milestone H | 7 | Closed | 4 | 9 | JANUARY
T-761-10683 | PS5-95-OB-4620D | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-11-17 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 40 | 47 | NOVEMBER
T-067-10684 | PS5-59-OB-3008B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone I | 8 | To be completed |  | 23 | NOVEMBER
T-305-10685 | PS5-25-OB-8233D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone G | 6 | On hold |  | 7 | SEPTEMBER
T-811-10686 | PS5-85-OB-8069B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone A | 1 | In progress |  | 8 | SEPTEMBER
T-368-10687 | PS5-23-OB-5299D | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone I | 8 | On hold |  | 11 | SEPTEMBER
T-110-10688 | PS5-77-IK-2623B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone I | 8 | To be completed |  | 21 | SEPTEMBER
T-514-10689 | PS5-67-OB-4142C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone D | 3 | In progress |  | 32 | OCTOBER
T-195-10690 | PS5-08-IK-6916C | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | In progress |  | 23 | NOVEMBER
T-219-10691 | PS5-60-UR-7506B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-04-16 | PS5-01-04 | PS5 - Milestone G | 6 | Closed | 28 | 16 | APRIL
T-976-10692 | PS5-78-OB-6724D | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone B | 1.1 | In progress |  | 12 | DECEMBER
T-477-10693 | PS5-08-UR-7722B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone E | 4 | To be completed |  | 4 | NOVEMBER
T-679-10694 | PS5-34-OB-7037C | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone D | 3 | To be completed |  | 14 | OCTOBER
T-368-10695 | PS5-97-OB-8629C | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-08-15 | PS5-07-01 | PS5 - Milestone B | 1.1 | Closed | 4 | 30 | AUGUST
T-588-10696 | PS5-49-IK-7171C | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone E | 4 | On hold |  | 25 | OCTOBER
T-856-10697 | PS5-18-OB-5075D | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-05-24 | PS5-08-02 | PS5 - Milestone C | 2 | Closed | 22 | 32 | MAY
T-974-10698 | PS5-60-OB-3344D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-06-16 | PS5-11-01 | PS5 - Milestone B | 1.1 | Closed | 33 | 26 | JUNE
T-053-10699 | PS5-55-OB-5252B | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone A | 1 | To be completed |  | 26 | AUGUST
T-880-10700 | PS5-29-OB-6390D | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-01-06 | PS5-07-02 | PS5 - Milestone C | 2 | Closed | 32 | 35 | JANUARY
T-180-10701 | PS5-26-IK-3402A | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone I | 8 | On hold |  | 7 | OCTOBER
T-889-10702 | PS5-22-UR-8520A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-01-21 | PS5-04-03 | PS5 - Milestone E | 4 | Closed | 10 | 21 | JANUARY
T-727-10703 | PS5-26-OB-1608C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone H | 7 | To be completed |  | 31 | DECEMBER
T-645-10704 | PS5-56-UR-1160C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-03-15 | PS5-10-01 | PS5 - Milestone B | 1.1 | Closed | 10 | 45 | MARCH
T-696-10705 | PS5-61-IK-2869C | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-04-08 | PS5-99-01 | PS5 - Milestone B | 1.1 | Closed | 17 | 44 | APRIL
T-185-10706 | PS5-20-OB-3638C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone I | 8 | To be completed |  | 23 | SEPTEMBER
T-862-10707 | PS5-99-OB-6530D | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone B | 1.1 | To be completed |  | 42 | NOVEMBER
T-549-10708 | PS5-15-IK-2114D | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-02-20 | PS5-63-04 | PS5 - Milestone F | 5 | Closed | 44 | 32 | FEBRUARY
T-908-10709 | PS5-60-IK-1041A | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone G | 6 | In progress |  | 18 | AUGUST
T-341-10710 | PS5-79-IK-8650B | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone A | 1 | To be completed |  | 8 | AUGUST
T-985-10711 | PS5-61-OB-1471D | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone G | 6 | To be completed |  | 39 | AUGUST
T-004-10712 | PS5-56-OB-1414D | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | To be completed |  | 20 | SEPTEMBER
T-961-10713 | PS5-45-IK-9229C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-12-08 | PS5-08-02 | PS5 - Milestone G | 6 | Closed | 8 | 42 | DECEMBER
T-919-10714 | PS5-60-OB-4631C | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-03-27 | PS5-09-01 | PS5 - Milestone B | 1.1 | Closed | 25 | 46 | MARCH
T-915-10715 | PS5-98-OB-3792B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | In progress |  | 4 | NOVEMBER
T-318-10716 | PS5-57-OB-4574D | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-05-27 | PS5-07-01 | PS5 - Milestone F | 5 | Closed | 16 | 42 | MAY
T-228-10717 | PS5-27-OB-1938C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone B | 1.1 | To be completed |  | 46 | SEPTEMBER
T-580-10718 | PS5-13-OB-7701C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-07-26 | PS5-04-04 | PS5 - Milestone D | 3 | Closed | 14 | 48 | JULY
T-146-10719 | PS5-25-OB-2884C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | In progress |  | 19 | SEPTEMBER
T-124-10720 | PS5-02-IK-8522D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | On hold |  | 43 | SEPTEMBER
T-684-10721 | PS5-49-UR-9518C | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-03-08 | PS5-62-01 | PS5 - Milestone A | 1 | Closed | 14 | 28 | MARCH
T-523-10722 | PS5-11-OB-5571A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-06-10 | PS5-01-04 | PS5 - Milestone I | 8 | Closed | 30 | 43 | JUNE
T-798-10723 | PS5-03-OB-5037A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone C | 2 | On hold |  | 42 | SEPTEMBER
T-064-10724 | PS5-40-UR-9964D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-08-18 | PS5-99-03 | PS5 - Milestone C | 2 | Closed | 44 | 11 | AUGUST
T-834-10725 | PS5-38-OB-9113A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-10-04 | PS5-11-01 | PS5 - Milestone I | 8 | Closed | 16 | 44 | OCTOBER
T-740-10726 | PS5-40-OB-3840C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone G | 6 | To be completed |  | 29 | NOVEMBER
T-696-10727 | PS5-47-OB-8117B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | To be completed |  | 48 | OCTOBER
T-505-10728 | PS5-11-OB-1904A | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | To be completed |  | 34 | DECEMBER
T-072-10729 | PS5-41-OB-3129D | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone E | 4 | On hold |  | 6 | AUGUST
T-263-10730 | PS5-55-UR-6246C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone E | 4 | In progress |  | 41 | DECEMBER
T-915-10731 | PS5-88-OB-7602A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone F | 5 | In progress |  | 33 | DECEMBER
T-216-10732 | PS5-38-OB-2566A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone D | 3 | To be completed |  | 35 | SEPTEMBER
T-458-10733 | PS5-31-OB-4509A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone B | 1.1 | To be completed |  | 45 | SEPTEMBER
T-913-10734 | PS5-66-UR-6504C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone H | 7 | In progress |  | 14 | DECEMBER
T-274-10735 | PS5-80-UR-7847C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | On hold |  | 6 | DECEMBER
T-640-10736 | PS5-96-IK-7495B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone I | 8 | To be completed |  | 17 | OCTOBER
T-133-10737 | PS5-82-UR-9986A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-04-26 | PS5-99-03 | PS5 - Milestone B | 1.1 | Closed | 10 | 27 | APRIL
T-967-10738 | PS5-24-UR-8035A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone D | 3 | On hold |  | 25 | OCTOBER
T-401-10739 | PS5-09-OB-1276B | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone I | 8 | To be completed |  | 41 | SEPTEMBER
T-464-10740 | PS5-94-OB-5473C | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-05-02 | PS5-04-03 | PS5 - Milestone D | 3 | Closed | 26 | 13 | MAY
T-266-10741 | PS5-95-OB-8990C | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-07-25 | PS5-99-01 | PS5 - Milestone F | 5 | Closed | 13 | 26 | JULY
T-776-10742 | PS5-24-IK-6628A | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone A | 1 | To be completed |  | 25 | AUGUST
T-635-10743 | PS5-08-IK-9699B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | To be completed |  | 27 | DECEMBER
T-515-10744 | PS5-64-IK-6059D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-12-28 | PS5-10-03 | PS5 - Milestone B | 1.1 | Closed | 37 | 23 | DECEMBER
T-635-10745 | PS5-21-IK-7020D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone H | 7 | On hold |  | 4 | AUGUST
T-584-10746 | PS5-47-OB-5411A | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-10-27 | PS5-06-03 | PS5 - Milestone B | 1.1 | Closed | 46 | 29 | OCTOBER
T-563-10747 | PS5-59-UR-7761C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | In progress |  | 46 | DECEMBER
T-987-10748 | PS5-34-OB-2949A | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-09-24 | PS5-06-03 | PS5 - Milestone E | 4 | Closed | 20 | 20 | SEPTEMBER
T-490-10749 | PS5-98-UR-1714C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-08-27 | PS5-05-03 | PS5 - Milestone D | 3 | Closed | 44 | 42 | AUGUST
T-539-10750 | PS5-39-IK-3412A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-06-16 | PS5-05-01 | PS5 - Milestone A | 1 | Closed | 29 | 6 | JUNE
T-616-10751 | PS5-23-UR-8714B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-07-05 | PS5-01-02 | PS5 - Milestone G | 6 | Closed | 35 | 9 | JULY
T-687-10752 | PS5-96-UR-6356D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-12-23 | PS5-10-03 | PS5 - Milestone B | 1.1 | Closed | 23 | 33 | DECEMBER
T-566-10753 | PS5-69-OB-4625A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | To be completed |  | 20 | AUGUST
T-197-10754 | PS5-06-OB-7007A | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-11-18 | PS5-09-04 | PS5 - Milestone H | 7 | Closed | 13 | 21 | NOVEMBER
T-848-10755 | PS5-78-UR-5613D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-09-07 | PS5-12-01 | PS5 - Milestone E | 4 | Closed | 43 | 13 | SEPTEMBER
T-130-10756 | PS5-31-IK-4867C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-05-05 | PS5-61-02 | PS5 - Milestone C | 2 | Closed | 46 | 11 | MAY
T-209-10757 | PS5-63-UR-6992C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-03-22 | PS5-05-01 | PS5 - Milestone E | 4 | Closed | 17 | 5 | MARCH
T-500-10758 | PS5-80-OB-8640C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone B | 1.1 | In progress |  | 28 | DECEMBER
T-165-10759 | PS5-14-IK-8626A | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone E | 4 | To be completed |  | 28 | DECEMBER
T-848-10760 | PS5-79-UR-9989D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone D | 3 | On hold |  | 13 | SEPTEMBER
T-922-10761 | PS5-33-OB-7090B | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone C | 2 | To be completed |  | 44 | DECEMBER
T-492-10762 | PS5-52-OB-7339A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | In progress |  | 8 | DECEMBER
T-181-10763 | PS5-65-OB-4754D | CQS03 - Deluge System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-05-14 | PS5-13-01 | PS5 - Milestone C | 2 | Closed | 6 | 15 | MAY
T-294-10764 | PS5-22-OB-4994B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-01-28 | PS5-01-09 | PS5 - Milestone G | 6 | Closed | 29 | 9 | JANUARY
T-117-10765 | PS5-82-UR-6984D | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone G | 6 | In progress |  | 31 | DECEMBER
T-449-10766 | PS5-15-UR-8669D | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone D | 3 | To be completed |  | 11 | NOVEMBER
T-048-10767 | PS5-35-OB-2216B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone G | 6 | In progress |  | 47 | NOVEMBER
T-118-10768 | PS5-37-IK-1762C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | On hold |  | 41 | OCTOBER
T-875-10769 | PS5-13-UR-9809D | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone D | 3 | To be completed |  | 48 | OCTOBER
T-176-10770 | PS5-09-UR-6836D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | To be completed |  | 11 | DECEMBER
T-531-10771 | PS5-26-IK-2543B | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone I | 8 | To be completed |  | 28 | NOVEMBER
T-164-10772 | PS5-17-IK-4735A | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone G | 6 | On hold |  | 7 | OCTOBER
T-499-10773 | PS5-22-OB-2214D | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-09-24 | PS5-99-01 | PS5 - Milestone I | 8 | Closed | 13 | 46 | SEPTEMBER
T-993-10774 | PS5-83-IK-1265D | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-09-20 | PS5-01-01 | PS5 - Milestone D | 3 | Closed | 16 | 33 | SEPTEMBER
T-096-10775 | PS5-86-OB-8938D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-01-06 | PS5-03-23 | PS5 - Milestone G | 6 | Closed | 36 | 26 | JANUARY
T-555-10776 | PS5-44-OB-4849B | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone E | 4 | In progress |  | 22 | SEPTEMBER
T-033-10777 | PS5-71-UR-3022B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-06-02 | PS5-09-01 | PS5 - Milestone H | 7 | Closed | 13 | 40 | JUNE
T-571-10778 | PS5-56-OB-7063C | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone C | 2 | To be completed |  | 41 | DECEMBER
T-408-10779 | PS5-72-OB-3925D | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-01-17 | PS5-10-03 | PS5 - Milestone H | 7 | Closed | 17 | 28 | JANUARY
T-827-10780 | PS5-90-UR-6235B | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone I | 8 | To be completed |  | 36 | OCTOBER
T-861-10781 | PS5-56-OB-6518D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone I | 8 | To be completed |  | 18 | SEPTEMBER
T-141-10782 | PS5-94-OB-5574B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-08-10 | PS5-01-03 | PS5 - Milestone B | 1.1 | Closed | 30 | 5 | AUGUST
T-726-10783 | PS5-31-IK-8860A | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-04-05 | PS5-04-03 | PS5 - Milestone F | 5 | Closed | 11 | 42 | APRIL
T-206-10784 | PS5-67-UR-5988A | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone D | 3 | To be completed |  | 42 | SEPTEMBER
T-601-10785 | PS5-18-IK-7425B | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone I | 8 | In progress |  | 27 | NOVEMBER
T-389-10786 | PS5-41-UR-8813B | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-03-22 | PS5-03-01 | PS5 - Milestone C | 2 | Closed | 36 | 20 | MARCH
T-084-10787 | PS5-49-OB-8180A | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone G | 6 | To be completed |  | 39 | DECEMBER
T-623-10788 | PS5-57-IK-1757A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone G | 6 | In progress |  | 26 | OCTOBER
T-615-10789 | PS5-95-IK-1714A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone B | 1.1 | In progress |  | 5 | DECEMBER
T-228-10790 | PS5-70-OB-9961B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone H | 7 | On hold |  | 39 | NOVEMBER
T-119-10791 | PS5-23-OB-4999B | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone A | 1 | To be completed |  | 25 | OCTOBER
T-534-10792 | PS5-80-OB-2564D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone I | 8 | On hold |  | 6 | DECEMBER
T-180-10793 | PS5-87-UR-1345B | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-08-13 | PS5-10-02 | PS5 - Milestone G | 6 | Closed | 45 | 22 | AUGUST
T-451-10794 | PS5-52-UR-9767D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone A | 1 | To be completed |  | 44 | AUGUST
T-655-10795 | PS5-25-OB-3967D | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone G | 6 | To be completed |  | 8 | SEPTEMBER
T-330-10796 | PS5-23-IK-7221C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone F | 5 | On hold |  | 30 | SEPTEMBER
T-615-10797 | PS5-96-OB-8111B | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone C | 2 | In progress |  | 21 | DECEMBER
T-724-10798 | PS5-09-UR-7643D | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-05-07 | PS5-01-05 | PS5 - Milestone F | 5 | Closed | 14 | 37 | MAY
T-025-10799 | PS5-12-IK-8995C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-09-11 | PS5-02-02 | PS5 - Milestone B | 1.1 | Closed | 40 | 41 | SEPTEMBER
T-004-10800 | PS5-91-IK-1624A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | To be completed |  | 41 | AUGUST
T-168-10801 | PS5-14-OB-9817B | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone D | 3 | To be completed |  | 42 | AUGUST
T-946-10802 | PS5-42-OB-7927D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | To be completed |  | 9 | OCTOBER
T-030-10803 | PS5-47-IK-2413B | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone B | 1.1 | In progress |  | 17 | OCTOBER
T-990-10804 | PS5-01-OB-2699A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-10-21 | PS5-60-01 | PS5 - Milestone D | 3 | Closed | 31 | 33 | OCTOBER
T-219-10805 | PS5-33-OB-8805A | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone A | 1 | In progress |  | 12 | DECEMBER
T-555-10806 | PS5-32-OB-9007B | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone H | 7 | To be completed |  | 36 | DECEMBER
T-123-10807 | PS5-89-OB-4939A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-11-24 | PS5-01-07 | PS5 - Milestone E | 4 | Closed | 5 | 34 | NOVEMBER
T-969-10808 | PS5-66-OB-2942B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-07-04 | PS5-63-01 | PS5 - Milestone H | 7 | Closed | 24 | 48 | JULY
T-793-10809 | PS5-42-IK-3270A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone I | 8 | In progress |  | 12 | NOVEMBER
T-967-10810 | PS5-85-IK-3834C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | To be completed |  | 42 | NOVEMBER
T-885-10811 | PS5-08-OB-2574B | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone B | 1.1 | To be completed |  | 9 | AUGUST
T-954-10812 | PS5-11-OB-2134D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-08-06 | PS5-03-03 | PS5 - Milestone D | 3 | Closed | 20 | 12 | AUGUST
T-355-10813 | PS5-28-UR-4792A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone F | 5 | To be completed |  | 9 | AUGUST
T-460-10814 | PS5-95-OB-9445A | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-11-17 | PS5-60-04 | PS5 - Milestone F | 5 | Closed | 30 | 21 | NOVEMBER
T-587-10815 | PS5-55-IK-6348D | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone G | 6 | On hold |  | 18 | DECEMBER
T-400-10816 | PS5-28-OB-6346D | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-10-06 | PS5-05-02 | PS5 - Milestone I | 8 | Closed | 23 | 43 | OCTOBER
T-855-10817 | PS5-83-IK-9274A | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-04-27 | PS5-09-04 | PS5 - Milestone A | 1 | Closed | 11 | 31 | APRIL
T-727-10818 | PS5-27-IK-3242A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-04-08 | PS5-62-02 | PS5 - Milestone I | 8 | Closed | 14 | 23 | APRIL
T-379-10819 | PS5-97-UR-4348D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-11-06 | PS5-13-01 | PS5 - Milestone D | 3 | Closed | 41 | 10 | NOVEMBER
T-599-10820 | PS5-32-OB-7980A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-04-12 | PS5-01-09 | PS5 - Milestone E | 4 | Closed | 47 | 31 | APRIL
T-970-10821 | PS5-18-UR-2322B | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | On hold |  | 40 | DECEMBER
T-803-10822 | PS5-30-IK-7084A | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-12-02 | PS5-07-01 | PS5 - Milestone I | 8 | Closed | 19 | 7 | DECEMBER
T-529-10823 | PS5-78-IK-5271A | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone G | 6 | In progress |  | 36 | AUGUST
T-320-10824 | PS5-54-OB-3698C | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone F | 5 | In progress |  | 35 | AUGUST
T-993-10825 | PS5-43-UR-7086B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | In progress |  | 25 | AUGUST
T-058-10826 | PS5-29-OB-1362A | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-02-03 | PS5-09-03 | PS5 - Milestone F | 5 | Closed | 45 | 18 | FEBRUARY
T-843-10827 | PS5-15-UR-4322D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-02-06 | PS5-82-02 | PS5 - Milestone A | 1 | Closed | 21 | 11 | FEBRUARY
T-148-10828 | PS5-50-IK-1476C | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone B | 1.1 | To be completed |  | 17 | NOVEMBER
T-811-10829 | PS5-17-OB-7760B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-09-22 | PS5-07-03 | PS5 - Milestone F | 5 | Closed | 7 | 48 | SEPTEMBER
T-245-10830 | PS5-53-IK-5905A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-07-27 | PS5-11-03 | PS5 - Milestone H | 7 | Closed | 10 | 30 | JULY
T-979-10831 | PS5-78-OB-7859B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-03-01 | PS5-01-03 | PS5 - Milestone F | 5 | Closed | 33 | 34 | MARCH
T-919-10832 | PS5-78-IK-2989C | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | In progress |  | 46 | DECEMBER
T-132-10833 | PS5-01-IK-8148D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone F | 5 | On hold |  | 42 | SEPTEMBER
T-810-10834 | PS5-89-OB-4465D | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone D | 3 | To be completed |  | 7 | DECEMBER
T-910-10835 | PS5-99-OB-2150A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-12-04 | PS5-10-01 | PS5 - Milestone D | 3 | Closed | 23 | 45 | DECEMBER
T-634-10836 | PS5-56-IK-2761D | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | In progress |  | 27 | OCTOBER
T-683-10837 | PS5-68-OB-1644A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | To be completed |  | 23 | AUGUST
T-402-10838 | PS5-44-OB-7972D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-03-19 | PS5-10-06 | PS5 - Milestone G | 6 | Closed | 30 | 10 | MARCH
T-848-10839 | PS5-46-UR-4458B | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-12-01 | PS5-09-03 | PS5 - Milestone H | 7 | Closed | 11 | 14 | DECEMBER
T-649-10840 | PS5-46-OB-6693D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-11-06 | PS5-82-07 | PS5 - Milestone A | 1 | Closed | 37 | 39 | NOVEMBER
T-275-10841 | PS5-40-OB-4828C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-08-15 | PS5-07-02 | PS5 - Milestone E | 4 | Closed | 46 | 27 | AUGUST
T-755-10842 | PS5-47-OB-4832C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone I | 8 | To be completed |  | 32 | NOVEMBER
T-797-10843 | PS5-06-UR-1210C | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone I | 8 | To be completed |  | 9 | SEPTEMBER
T-096-10844 | PS5-95-IK-5517C | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-06-19 | PS5-82-07 | PS5 - Milestone D | 3 | Closed | 46 | 38 | JUNE
T-142-10845 | PS5-53-OB-1379B | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | To be completed |  | 33 | SEPTEMBER
T-018-10846 | PS5-49-IK-5215C | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | To be completed |  | 8 | NOVEMBER
T-415-10847 | PS5-51-OB-1842D | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | To be completed |  | 25 | OCTOBER
T-111-10848 | PS5-63-OB-1342C | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone C | 2 | To be completed |  | 37 | NOVEMBER
T-959-10849 | PS5-02-OB-3124B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-05-10 | PS5-04-01 | PS5 - Milestone E | 4 | Closed | 22 | 17 | MAY
T-504-10850 | PS5-52-UR-5242D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-05-10 | PS5-10-04 | PS5 - Milestone G | 6 | Closed | 26 | 11 | MAY
T-897-10851 | PS5-61-UR-2029B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-12-03 | PS5-01-07 | PS5 - Milestone A | 1 | Closed | 15 | 4 | DECEMBER
T-267-10852 | PS5-25-OB-1113A | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone H | 7 | On hold |  | 15 | NOVEMBER
T-860-10853 | PS5-24-UR-3846C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone B | 1.1 | On hold |  | 11 | OCTOBER
T-153-10854 | PS5-25-OB-2094A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-07-23 | PS5-01-04 | PS5 - Milestone B | 1.1 | Closed | 37 | 40 | JULY
T-736-10855 | PS5-30-UR-4037C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | To be completed |  | 47 | OCTOBER
T-715-10856 | PS5-04-UR-4054A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone A | 1 | In progress |  | 10 | DECEMBER
T-590-10857 | PS5-66-OB-4010C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-12-20 | PS5-63-01 | PS5 - Milestone D | 3 | Closed | 46 | 47 | DECEMBER
T-554-10858 | PS5-44-OB-4971C | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone A | 1 | To be completed |  | 8 | NOVEMBER
T-449-10859 | PS5-83-OB-9210D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone B | 1.1 | To be completed |  | 27 | SEPTEMBER
T-523-10860 | PS5-76-OB-8800D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone D | 3 | To be completed |  | 8 | NOVEMBER
T-668-10861 | PS5-13-UR-3156C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-06-14 | PS5-01-09 | PS5 - Milestone E | 4 | Closed | 33 | 22 | JUNE
T-380-10862 | PS5-71-IK-3051B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone A | 1 | To be completed |  | 8 | NOVEMBER
T-739-10863 | PS5-75-IK-2726C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-02-26 | PS5-02-03 | PS5 - Milestone G | 6 | Closed | 17 | 4 | FEBRUARY
T-711-10864 | PS5-14-OB-7734A | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | To be completed |  | 28 | SEPTEMBER
T-876-10865 | PS5-32-UR-1505D | CQM01 - Pump Installation | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-08-19 | PS5-04-03 | PS5 - Milestone A | 1 | Closed | 34 | 13 | AUGUST
T-368-10866 | PS5-17-IK-4464B | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-06-14 | PS5-05-02 | PS5 - Milestone D | 3 | Closed | 13 | 12 | JUNE
T-035-10867 | PS5-08-UR-4232B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | To be completed |  | 32 | OCTOBER
T-083-10868 | PS5-36-UR-2053C | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | In progress |  | 12 | NOVEMBER
T-582-10869 | PS5-81-IK-6827A | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-11-06 | PS5-10-01 | PS5 - Milestone H | 7 | Closed | 23 | 4 | NOVEMBER
T-860-10870 | PS5-07-UR-4251D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone G | 6 | To be completed |  | 30 | NOVEMBER
T-313-10871 | PS5-12-OB-6498A | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-07-25 | PS5-99-02 | PS5 - Milestone H | 7 | Closed | 32 | 4 | JULY
T-123-10872 | PS5-95-OB-3653A | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | On hold |  | 40 | OCTOBER
T-249-10873 | PS5-80-UR-8811B | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone A | 1 | To be completed |  | 19 | DECEMBER
T-137-10874 | PS5-96-UR-8837B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone A | 1 | To be completed |  | 19 | DECEMBER
T-675-10875 | PS5-08-UR-2665D | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-12-11 | PS5-60-07 | PS5 - Milestone D | 3 | Closed | 47 | 31 | DECEMBER
T-189-10876 | PS5-90-OB-3674D | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone A | 1 | In progress |  | 20 | SEPTEMBER
T-105-10877 | PS5-91-IK-8928A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-12-14 | PS5-05-03 | PS5 - Milestone D | 3 | Closed | 33 | 6 | DECEMBER
T-159-10878 | PS5-23-UR-4554C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-06-19 | PS5-63-04 | PS5 - Milestone I | 8 | Closed | 35 | 35 | JUNE
T-884-10879 | PS5-65-OB-2142A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | In progress |  | 24 | SEPTEMBER
T-021-10880 | PS5-58-IK-5245C | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-03-23 | PS5-99-03 | PS5 - Milestone D | 3 | Closed | 14 | 30 | MARCH
T-697-10881 | PS5-53-OB-9022C | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone F | 5 | To be completed |  | 33 | AUGUST
T-586-10882 | PS5-69-OB-6071B | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-12-02 | PS5-82-02 | PS5 - Milestone D | 3 | Closed | 34 | 14 | DECEMBER
T-962-10883 | PS5-37-IK-7287D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone A | 1 | To be completed |  | 11 | NOVEMBER
T-243-10884 | PS5-37-IK-3519A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone B | 1.1 | To be completed |  | 8 | NOVEMBER
T-270-10885 | PS5-29-OB-4220A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-01-07 | PS5-02-03 | PS5 - Milestone C | 2 | Closed | 9 | 38 | JANUARY
T-871-10886 | PS5-59-IK-3591D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone F | 5 | On hold |  | 31 | SEPTEMBER
T-693-10887 | PS5-94-OB-1894B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | On hold |  | 16 | AUGUST
T-971-10888 | PS5-39-OB-9249D | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone D | 3 | To be completed |  | 24 | AUGUST
T-104-10889 | PS5-95-IK-7139C | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone A | 1 | To be completed |  | 12 | AUGUST
T-422-10890 | PS5-79-UR-9847C | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-11-16 | PS5-06-01 | PS5 - Milestone G | 6 | Closed | 38 | 30 | NOVEMBER
T-884-10891 | PS5-48-OB-3134C | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone D | 3 | On hold |  | 24 | OCTOBER
T-878-10892 | PS5-97-OB-1156A | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-06-25 | PS5-07-01 | PS5 - Milestone C | 2 | Closed | 15 | 4 | JUNE
T-359-10893 | PS5-95-IK-3794A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone C | 2 | To be completed |  | 42 | SEPTEMBER
T-278-10894 | PS5-18-UR-5250C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone I | 8 | To be completed |  | 33 | OCTOBER
T-579-10895 | PS5-48-OB-3212D | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone H | 7 | In progress |  | 10 | AUGUST
T-419-10896 | PS5-58-IK-7814D | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone A | 1 | In progress |  | 42 | DECEMBER
T-780-10897 | PS5-10-OB-4786D | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone G | 6 | On hold |  | 42 | NOVEMBER
T-499-10898 | PS5-45-OB-8171C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone I | 8 | To be completed |  | 13 | OCTOBER
T-400-10899 | PS5-27-OB-9804B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone C | 2 | On hold |  | 41 | SEPTEMBER
T-913-10900 | PS5-13-IK-3548C | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone E | 4 | On hold |  | 10 | AUGUST
T-415-10901 | PS5-80-UR-8687D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone I | 8 | To be completed |  | 29 | SEPTEMBER
T-316-10902 | PS5-87-OB-7375A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone A | 1 | To be completed |  | 32 | NOVEMBER
T-933-10903 | PS5-11-OB-7041C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | To be completed |  | 31 | DECEMBER
T-204-10904 | PS5-41-UR-4447B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone E | 4 | To be completed |  | 33 | AUGUST
T-746-10905 | PS5-08-OB-5543C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | In progress |  | 14 | DECEMBER
T-379-10906 | PS5-98-IK-6151D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-04-11 | PS5-03-03 | PS5 - Milestone C | 2 | Closed | 29 | 36 | APRIL
T-910-10907 | PS5-75-UR-6174B | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone H | 7 | In progress |  | 20 | DECEMBER
T-056-10908 | PS5-12-UR-4978C | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone F | 5 | On hold |  | 26 | DECEMBER
T-860-10909 | PS5-42-IK-1553B | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-11-20 | PS5-01-01 | PS5 - Milestone A | 1 | Closed | 46 | 44 | NOVEMBER
T-119-10910 | PS5-66-OB-9312B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-01-24 | PS5-09-03 | PS5 - Milestone I | 8 | Closed | 14 | 45 | JANUARY
T-984-10911 | PS5-07-OB-7402A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone D | 3 | In progress |  | 12 | SEPTEMBER
T-466-10912 | PS5-85-OB-4686C | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-11-05 | PS5-07-01 | PS5 - Milestone E | 4 | Closed | 39 | 45 | NOVEMBER
T-251-10913 | PS5-07-IK-5245B | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-12-14 | PS5-03-02 | PS5 - Milestone I | 8 | Closed | 24 | 10 | DECEMBER
T-942-10914 | PS5-03-IK-1637B | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone A | 1 | To be completed |  | 15 | NOVEMBER
T-791-10915 | PS5-79-UR-8342D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone A | 1 | To be completed |  | 40 | OCTOBER
T-343-10916 | PS5-40-OB-2102C | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone F | 5 | In progress |  | 18 | OCTOBER
T-951-10917 | PS5-55-UR-4040B | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-11-27 | PS5-04-03 | PS5 - Milestone G | 6 | Closed | 4 | 29 | NOVEMBER
T-073-10918 | PS5-34-UR-8831B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | On hold |  | 36 | DECEMBER
T-013-10919 | PS5-26-OB-1861A | CQP02 - Valve Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone D | 3 | On hold |  | 16 | OCTOBER
T-946-10920 | PS5-65-OB-9135C | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone G | 6 | To be completed |  | 24 | OCTOBER
T-160-10921 | PS5-47-IK-3381C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-04-20 | PS5-12-02 | PS5 - Milestone B | 1.1 | Closed | 14 | 12 | APRIL
T-601-10922 | PS5-87-OB-6240C | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-12-17 | PS5-61-01 | PS5 - Milestone A | 1 | Closed | 36 | 9 | DECEMBER
T-544-10923 | PS5-30-OB-3781A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone C | 2 | To be completed |  | 23 | NOVEMBER
T-530-10924 | PS5-11-OB-5840C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone A | 1 | To be completed |  | 29 | NOVEMBER
T-314-10925 | PS5-41-OB-6925D | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-12-22 | PS5-10-03 | PS5 - Milestone G | 6 | Closed | 43 | 47 | DECEMBER
T-388-10926 | PS5-56-UR-4894B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-04-21 | PS5-11-01 | PS5 - Milestone D | 3 | Closed | 16 | 4 | APRIL
T-739-10927 | PS5-97-IK-9748B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-12-13 | PS5-07-02 | PS5 - Milestone F | 5 | Closed | 42 | 48 | DECEMBER
T-848-10928 | PS5-95-UR-7961C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-11-16 | PS5-06-01 | PS5 - Milestone D | 3 | Closed | 37 | 31 | NOVEMBER
T-401-10929 | PS5-31-OB-2936B | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-05-09 | PS5-13-01 | PS5 - Milestone A | 1 | Closed | 20 | 14 | MAY
T-888-10930 | PS5-97-IK-1448C | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-03-04 | PS5-09-02 | PS5 - Milestone A | 1 | Closed | 37 | 15 | MARCH
T-031-10931 | PS5-46-OB-5303A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone H | 7 | To be completed |  | 34 | NOVEMBER
T-708-10932 | PS5-03-OB-6510A | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone F | 5 | In progress |  | 32 | NOVEMBER
T-129-10933 | PS5-33-IK-4488D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-04-15 | PS5-01-03 | PS5 - Milestone C | 2 | Closed | 28 | 41 | APRIL
T-491-10934 | PS5-56-OB-8273D | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone G | 6 | In progress |  | 46 | DECEMBER
T-981-10935 | PS5-08-OB-7908C | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone A | 1 | To be completed |  | 35 | NOVEMBER
T-662-10936 | PS5-67-OB-3792A | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone F | 5 | To be completed |  | 39 | OCTOBER
T-018-10937 | PS5-84-UR-3625C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-05-03 | PS5-01-09 | PS5 - Milestone E | 4 | Closed | 8 | 39 | MAY
T-461-10938 | PS5-28-OB-8638A | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone F | 5 | To be completed |  | 33 | AUGUST
T-036-10939 | PS5-82-OB-7923B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | To be completed |  | 43 | DECEMBER
T-904-10940 | PS5-53-OB-8693B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-03-06 | PS5-10-03 | PS5 - Milestone A | 1 | Closed | 15 | 34 | MARCH
T-310-10941 | PS5-63-OB-2661D | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone C | 2 | To be completed |  | 30 | OCTOBER
T-712-10942 | PS5-56-OB-9303A | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone A | 1 | In progress |  | 6 | OCTOBER
T-439-10943 | PS5-98-UR-6199D | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone I | 8 | On hold |  | 36 | OCTOBER
T-411-10944 | PS5-28-OB-5560A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | In progress |  | 6 | DECEMBER
T-972-10945 | PS5-82-UR-7264A | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-02-18 | PS5-63-04 | PS5 - Milestone D | 3 | Closed | 9 | 12 | FEBRUARY
T-171-10946 | PS5-28-OB-8572C | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-10-18 | PS5-05-03 | PS5 - Milestone I | 8 | Closed | 5 | 25 | OCTOBER
T-552-10947 | PS5-91-OB-7315C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone B | 1.1 | In progress |  | 38 | OCTOBER
T-339-10948 | PS5-95-UR-8859D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-01-23 | PS5-01-02 | PS5 - Milestone A | 1 | Closed | 8 | 10 | JANUARY
T-358-10949 | PS5-14-IK-9457B | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-08-12 | PS5-01-08 | PS5 - Milestone D | 3 | Closed | 22 | 13 | AUGUST
T-222-10950 | PS5-23-OB-6858D | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone E | 4 | On hold |  | 13 | NOVEMBER
T-076-10951 | PS5-98-UR-6165B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-08-13 | PS5-05-01 | PS5 - Milestone A | 1 | Closed | 26 | 11 | AUGUST
T-836-10952 | PS5-08-OB-1723B | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone G | 6 | To be completed |  | 46 | OCTOBER
T-477-10953 | PS5-09-UR-1311B | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-07-19 | PS5-01-05 | PS5 - Milestone E | 4 | Closed | 33 | 19 | JULY
T-236-10954 | PS5-94-IK-1711A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone C | 2 | On hold |  | 14 | OCTOBER
T-296-10955 | PS5-65-OB-4300B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone D | 3 | On hold |  | 8 | SEPTEMBER
T-757-10956 | PS5-55-OB-1183D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-04-27 | PS5-11-02 | PS5 - Milestone F | 5 | Closed | 43 | 14 | APRIL
T-416-10957 | PS5-84-OB-5371C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone G | 6 | In progress |  | 28 | DECEMBER
T-992-10958 | PS5-45-OB-7093A | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone A | 1 | In progress |  | 33 | NOVEMBER
T-686-10959 | PS5-09-IK-3452D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone H | 7 | In progress |  | 4 | NOVEMBER
T-769-10960 | PS5-61-OB-5354C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-02-05 | PS5-99-01 | PS5 - Milestone B | 1.1 | Closed | 8 | 20 | FEBRUARY
T-256-10961 | PS5-73-OB-4532C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone H | 7 | To be completed |  | 28 | NOVEMBER
T-370-10962 | PS5-65-IK-5189C | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone H | 7 | To be completed |  | 10 | AUGUST
T-379-10963 | PS5-64-OB-7384A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone I | 8 | To be completed |  | 13 | NOVEMBER
T-468-10964 | PS5-61-IK-7051D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone E | 4 | On hold |  | 33 | NOVEMBER
T-879-10965 | PS5-18-IK-3423D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone A | 1 | On hold |  | 11 | AUGUST
T-259-10966 | PS5-59-OB-3459C | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-05-06 | PS5-10-05 | PS5 - Milestone F | 5 | Closed | 24 | 42 | MAY
T-897-10967 | PS5-33-IK-2157C | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone H | 7 | In progress |  | 4 | OCTOBER
T-221-10968 | PS5-13-OB-3446A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-11-22 | PS5-10-03 | PS5 - Milestone B | 1.1 | Closed | 12 | 8 | NOVEMBER
T-648-10969 | PS5-64-IK-1718A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-01-22 | PS5-05-01 | PS5 - Milestone A | 1 | Closed | 43 | 41 | JANUARY
T-696-10970 | PS5-32-IK-5107B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone A | 1 | To be completed |  | 42 | OCTOBER
T-128-10971 | PS5-73-OB-1739B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-10-19 | PS5-01-01 | PS5 - Milestone D | 3 | Closed | 10 | 38 | OCTOBER
T-316-10972 | PS5-40-OB-1199A | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-06-23 | PS5-10-01 | PS5 - Milestone A | 1 | Closed | 42 | 29 | JUNE
T-252-10973 | PS5-43-OB-3057C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-08-02 | PS5-62-02 | PS5 - Milestone C | 2 | Closed | 46 | 13 | AUGUST
T-564-10974 | PS5-35-OB-1067D | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone D | 3 | On hold |  | 30 | SEPTEMBER
T-489-10975 | PS5-14-UR-5982C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone E | 4 | In progress |  | 22 | DECEMBER
T-984-10976 | PS5-39-OB-9291D | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-03-10 | PS5-10-04 | PS5 - Milestone C | 2 | Closed | 48 | 39 | MARCH
T-353-10977 | PS5-16-OB-3973B | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone E | 4 | To be completed |  | 46 | NOVEMBER
T-671-10978 | PS5-42-OB-2189C | CQM02 - Compressor | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone F | 5 | To be completed |  | 9 | DECEMBER
T-529-10979 | PS5-38-UR-1505A | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone I | 8 | On hold |  | 47 | SEPTEMBER
T-937-10980 | PS5-85-OB-2998C | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone D | 3 | In progress |  | 32 | NOVEMBER
T-008-10981 | PS5-17-OB-8960A | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone I | 8 | To be completed |  | 9 | NOVEMBER
T-554-10982 | PS5-39-UR-3776A | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | In progress |  | 43 | NOVEMBER
T-748-10983 | PS5-34-OB-1562A | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-06-05 | PS5-63-04 | PS5 - Milestone I | 8 | Closed | 26 | 18 | JUNE
T-182-10984 | PS5-22-OB-3200B | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone E | 4 | To be completed |  | 5 | NOVEMBER
T-862-10985 | PS5-78-OB-8589A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-07-06 | PS5-01-01 | PS5 - Milestone E | 4 | Closed | 34 | 30 | JULY
T-382-10986 | PS5-05-IK-2248B | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone F | 5 | To be completed |  | 34 | DECEMBER
T-846-10987 | PS5-15-UR-6325D | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone H | 7 | On hold |  | 45 | DECEMBER
T-457-10988 | PS5-81-OB-6681D | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-01-17 | PS5-09-03 | PS5 - Milestone C | 2 | Closed | 37 | 47 | JANUARY
T-732-10989 | PS5-58-IK-8141A | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone C | 2 | On hold |  | 42 | NOVEMBER
T-380-10990 | PS5-48-OB-4686D | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone C | 2 | To be completed |  | 47 | AUGUST
T-410-10991 | PS5-48-OB-9751C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone G | 6 | In progress |  | 14 | AUGUST
T-541-10992 | PS5-38-OB-6455B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone G | 6 | To be completed |  | 34 | OCTOBER
T-028-10993 | PS5-56-OB-8963B | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone C | 2 | On hold |  | 26 | SEPTEMBER
T-271-10994 | PS5-42-UR-8178D | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-03-23 | PS5-01-03 | PS5 - Milestone C | 2 | Closed | 24 | 34 | MARCH
T-717-10995 | PS5-69-OB-6989D | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | To be completed |  | 19 | OCTOBER
T-155-10996 | PS5-52-IK-4683D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone E | 4 | On hold |  | 21 | SEPTEMBER
T-794-10997 | PS5-18-OB-2028A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-08-09 | PS5-06-01 | PS5 - Milestone E | 4 | Closed | 39 | 32 | AUGUST
T-873-10998 | PS5-45-UR-1977D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | In progress |  | 27 | SEPTEMBER
T-270-10999 | PS5-29-IK-4297D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone H | 7 | In progress |  | 12 | OCTOBER
T-867-11000 | PS5-79-OB-6470D | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-07-02 | PS5-03-01 | PS5 - Milestone D | 3 | Closed | 23 | 33 | JULY
T-775-11001 | PS5-21-IK-9356D | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | To be completed |  | 16 | SEPTEMBER
T-313-11002 | PS5-05-IK-6776D | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | On hold |  | 33 | NOVEMBER
T-941-11003 | PS5-72-OB-2788C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone H | 7 | To be completed |  | 41 | SEPTEMBER
T-717-11004 | PS5-80-OB-2167C | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-08-23 | PS5-04-02 | PS5 - Milestone B | 1.1 | Closed | 43 | 22 | AUGUST
T-940-11005 | PS5-96-IK-1456D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone I | 8 | To be completed |  | 12 | AUGUST
T-961-11006 | PS5-32-IK-7385D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-06-03 | PS5-06-01 | PS5 - Milestone F | 5 | Closed | 43 | 17 | JUNE
T-305-11007 | PS5-10-UR-5846C | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | In progress |  | 45 | NOVEMBER
T-013-11008 | PS5-72-IK-7599A | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-01-10 | PS5-08-02 | PS5 - Milestone B | 1.1 | Closed | 39 | 31 | JANUARY
T-485-11009 | PS5-54-OB-5787A | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone B | 1.1 | To be completed |  | 20 | SEPTEMBER
T-687-11010 | PS5-19-OB-2862D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-05-14 | PS5-82-07 | PS5 - Milestone F | 5 | Closed | 47 | 48 | MAY
T-907-11011 | PS5-19-OB-8116D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-02-12 | PS5-11-02 | PS5 - Milestone C | 2 | Closed | 43 | 13 | FEBRUARY
T-770-11012 | PS5-78-OB-5101C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-06-03 | PS5-03-23 | PS5 - Milestone H | 7 | Closed | 42 | 20 | JUNE
T-564-11013 | PS5-68-IK-4930A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-05-24 | PS5-01-02 | PS5 - Milestone B | 1.1 | Closed | 32 | 5 | MAY
T-595-11014 | PS5-37-OB-6457B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone D | 3 | In progress |  | 6 | NOVEMBER
T-498-11015 | PS5-19-IK-2317B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone F | 5 | On hold |  | 5 | AUGUST
T-754-11016 | PS5-21-UR-4609B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-02-20 | PS5-12-02 | PS5 - Milestone G | 6 | Closed | 39 | 42 | FEBRUARY
T-752-11017 | PS5-87-IK-5723B | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-07-27 | PS5-11-02 | PS5 - Milestone B | 1.1 | Closed | 35 | 37 | JULY
T-401-11018 | PS5-06-UR-8855C | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone F | 5 | To be completed |  | 48 | OCTOBER
T-087-11019 | PS5-36-OB-8723D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone H | 7 | On hold |  | 20 | AUGUST
T-466-11020 | PS5-90-OB-3523C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone A | 1 | In progress |  | 44 | DECEMBER
T-512-11021 | PS5-34-IK-9857C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone G | 6 | On hold |  | 40 | AUGUST
T-218-11022 | PS5-15-OB-2888D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-08-08 | PS5-11-03 | PS5 - Milestone H | 7 | Closed | 30 | 44 | AUGUST
T-635-11023 | PS5-13-OB-2684B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-03-15 | PS5-06-03 | PS5 - Milestone B | 1.1 | Closed | 10 | 48 | MARCH
T-620-11024 | PS5-37-OB-6679A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-08-03 | PS5-01-09 | PS5 - Milestone I | 8 | Closed | 44 | 18 | AUGUST
T-117-11025 | PS5-57-OB-4168C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone G | 6 | On hold |  | 11 | AUGUST
T-436-11026 | PS5-17-OB-6861B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone E | 4 | In progress |  | 9 | SEPTEMBER
T-575-11027 | PS5-81-UR-4229D | CQM01 - Pump Installation | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone E | 4 | In progress |  | 14 | DECEMBER
T-493-11028 | PS5-65-UR-5924D | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone G | 6 | In progress |  | 12 | DECEMBER
T-105-11029 | PS5-69-OB-2354B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-01-28 | PS5-09-02 | PS5 - Milestone F | 5 | Closed | 15 | 10 | JANUARY
T-509-11030 | PS5-68-OB-5464B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-10-28 | PS5-10-03 | PS5 - Milestone B | 1.1 | Closed | 28 | 18 | OCTOBER
T-548-11031 | PS5-47-OB-8938A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone F | 5 | On hold |  | 16 | DECEMBER
T-423-11032 | PS5-85-OB-6970A | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone I | 8 | To be completed |  | 10 | AUGUST
T-648-11033 | PS5-25-IK-8776A | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone C | 2 | To be completed |  | 20 | DECEMBER
T-436-11034 | PS5-59-IK-7539D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-08-02 | PS5-11-03 | PS5 - Milestone F | 5 | Closed | 7 | 18 | AUGUST
T-946-11035 | PS5-56-IK-6494B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone E | 4 | To be completed |  | 10 | OCTOBER
T-316-11036 | PS5-62-IK-9943A | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone H | 7 | In progress |  | 34 | DECEMBER
T-243-11037 | PS5-35-OB-8362B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone A | 1 | To be completed |  | 16 | DECEMBER
T-596-11038 | PS5-91-UR-8481B | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | In progress |  | 42 | OCTOBER
T-132-11039 | PS5-85-OB-9312D | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone E | 4 | To be completed |  | 44 | SEPTEMBER
T-691-11040 | PS5-42-OB-5940C | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-02-18 | PS5-07-02 | PS5 - Milestone A | 1 | Closed | 36 | 17 | FEBRUARY
T-380-11041 | PS5-64-IK-4636C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-12-04 | PS5-62-02 | PS5 - Milestone I | 8 | Closed | 16 | 35 | DECEMBER
T-200-11042 | PS5-13-OB-6062A | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone G | 6 | To be completed |  | 40 | OCTOBER
T-965-11043 | PS5-52-OB-2199B | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-12-16 | PS5-01-01 | PS5 - Milestone C | 2 | Closed | 30 | 5 | DECEMBER
T-857-11044 | PS5-60-UR-4905D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone C | 2 | In progress |  | 39 | OCTOBER
T-197-11045 | PS5-86-OB-7460B | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone B | 1.1 | In progress |  | 43 | SEPTEMBER
T-465-11046 | PS5-90-UR-1095D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone A | 1 | In progress |  | 13 | OCTOBER
T-648-11047 | PS5-09-OB-6374B | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | To be completed |  | 36 | OCTOBER
T-717-11048 | PS5-54-UR-4924C | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone D | 3 | On hold |  | 18 | NOVEMBER
T-660-11049 | PS5-28-OB-2865C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-08-14 | PS5-04-04 | PS5 - Milestone A | 1 | Closed | 13 | 29 | AUGUST
T-631-11050 | PS5-86-IK-8303D | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-11-11 | PS5-04-01 | PS5 - Milestone B | 1.1 | Closed | 8 | 39 | NOVEMBER
T-125-11051 | PS5-86-OB-5444B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | To be completed |  | 25 | OCTOBER
T-823-11052 | PS5-96-IK-2836A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone B | 1.1 | In progress |  | 23 | AUGUST
T-656-11053 | PS5-65-OB-6734A | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone A | 1 | To be completed |  | 48 | DECEMBER
T-483-11054 | PS5-70-OB-2860A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-10-21 | PS5-61-01 | PS5 - Milestone H | 7 | Closed | 18 | 25 | OCTOBER
T-109-11055 | PS5-20-UR-6045A | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-08-23 | PS5-01-06 | PS5 - Milestone A | 1 | Closed | 25 | 23 | AUGUST
T-600-11056 | PS5-74-OB-4208B | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone G | 6 | In progress |  | 31 | AUGUST
T-327-11057 | PS5-41-IK-5636D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-03-12 | PS5-99-02 | PS5 - Milestone B | 1.1 | Closed | 25 | 33 | MARCH
T-948-11058 | PS5-46-OB-7678C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-05-13 | PS5-01-06 | PS5 - Milestone A | 1 | Closed | 45 | 5 | MAY
T-260-11059 | PS5-70-IK-9671A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-10-20 | PS5-01-03 | PS5 - Milestone E | 4 | Closed | 4 | 4 | OCTOBER
T-249-11060 | PS5-34-IK-1999A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | In progress |  | 42 | NOVEMBER
T-576-11061 | PS5-29-UR-6442B | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone G | 6 | In progress |  | 26 | SEPTEMBER
T-905-11062 | PS5-17-OB-1069C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-08-08 | PS5-02-01 | PS5 - Milestone F | 5 | Closed | 5 | 20 | AUGUST
T-355-11063 | PS5-10-OB-1057B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone A | 1 | In progress |  | 37 | OCTOBER
T-875-11064 | PS5-89-OB-7367A | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone D | 3 | To be completed |  | 25 | OCTOBER
T-572-11065 | PS5-95-IK-3250B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-06-09 | PS5-82-07 | PS5 - Milestone E | 4 | Closed | 14 | 31 | JUNE
T-459-11066 | PS5-31-OB-3206A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-07-28 | PS5-03-03 | PS5 - Milestone C | 2 | Closed | 9 | 25 | JULY
T-003-11067 | PS5-44-UR-9772A | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-04-03 | PS5-08-01 | PS5 - Milestone A | 1 | Closed | 46 | 6 | APRIL
T-597-11068 | PS5-03-UR-5930C | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | On hold |  | 34 | NOVEMBER
T-975-11069 | PS5-31-OB-1660B | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone H | 7 | In progress |  | 38 | NOVEMBER
T-153-11070 | PS5-24-IK-2090B | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone D | 3 | To be completed |  | 28 | DECEMBER
T-718-11071 | PS5-82-IK-4468D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | In progress |  | 42 | NOVEMBER
T-405-11072 | PS5-16-OB-4372D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-03-16 | PS5-82-01 | PS5 - Milestone B | 1.1 | Closed | 15 | 48 | MARCH
T-671-11073 | PS5-61-OB-5777D | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | To be completed |  | 28 | OCTOBER
T-967-11074 | PS5-43-OB-8628D | CQE01 - HV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone H | 7 | In progress |  | 19 | NOVEMBER
T-997-11075 | PS5-69-OB-9931D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone F | 5 | On hold |  | 30 | SEPTEMBER
T-923-11076 | PS5-21-IK-3119C | CQS03 - Deluge System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone I | 8 | To be completed |  | 30 | NOVEMBER
T-517-11077 | PS5-40-OB-6297D | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-11-24 | PS5-63-01 | PS5 - Milestone G | 6 | Closed | 33 | 6 | NOVEMBER
T-488-11078 | PS5-48-OB-5941D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone E | 4 | In progress |  | 40 | AUGUST
T-839-11079 | PS5-32-UR-4587B | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone F | 5 | In progress |  | 27 | OCTOBER
T-147-11080 | PS5-10-UR-4227D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone G | 6 | To be completed |  | 37 | DECEMBER
T-365-11081 | PS5-05-OB-2876D | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | To be completed |  | 5 | AUGUST
T-937-11082 | PS5-33-OB-6218B | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-09-27 | PS5-82-02 | PS5 - Milestone I | 8 | Closed | 42 | 13 | SEPTEMBER
T-478-11083 | PS5-99-OB-5804C | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone A | 1 | To be completed |  | 41 | NOVEMBER
T-701-11084 | PS5-02-OB-6716A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | To be completed |  | 25 | SEPTEMBER
T-610-11085 | PS5-69-UR-3055D | CQM03 - Heat Exchanger | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone F | 5 | In progress |  | 44 | OCTOBER
T-737-11086 | PS5-66-OB-1909C | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-02-01 | PS5-03-01 | PS5 - Milestone A | 1 | Closed | 36 | 19 | FEBRUARY
T-890-11087 | PS5-57-UR-5604D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone D | 3 | To be completed |  | 31 | SEPTEMBER
T-073-11088 | PS5-65-OB-9078C | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-10-10 | PS5-06-03 | PS5 - Milestone G | 6 | Closed | 20 | 38 | OCTOBER
T-738-11089 | PS5-70-OB-9028B | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone E | 4 | To be completed |  | 32 | SEPTEMBER
T-328-11090 | PS5-10-IK-8797D | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-03-19 | PS5-04-04 | PS5 - Milestone E | 4 | Closed | 23 | 11 | MARCH
T-676-11091 | PS5-87-OB-5759D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone I | 8 | On hold |  | 38 | NOVEMBER
T-167-11092 | PS5-29-OB-3431A | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-11-23 | PS5-12-01 | PS5 - Milestone I | 8 | Closed | 31 | 10 | NOVEMBER
T-533-11093 | PS5-27-UR-5594C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone I | 8 | To be completed |  | 27 | SEPTEMBER
T-677-11094 | PS5-96-UR-9371A | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone C | 2 | In progress |  | 40 | DECEMBER
T-169-11095 | PS5-15-UR-4669C | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone B | 1.1 | To be completed |  | 6 | NOVEMBER
T-686-11096 | PS5-94-IK-1507D | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone G | 6 | In progress |  | 21 | AUGUST
T-405-11097 | PS5-54-IK-3724B | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-05-24 | PS5-10-01 | PS5 - Milestone I | 8 | Closed | 13 | 27 | MAY
T-686-11098 | PS5-64-IK-4843C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone G | 6 | To be completed |  | 40 | DECEMBER
T-739-11099 | PS5-11-OB-9276B | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone C | 2 | On hold |  | 47 | SEPTEMBER
T-165-11100 | PS5-41-OB-8312A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-07-18 | PS5-03-03 | PS5 - Milestone I | 8 | Closed | 43 | 42 | JULY
T-201-11101 | PS5-06-OB-1817A | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone E | 4 | To be completed |  | 12 | AUGUST
T-766-11102 | PS5-76-OB-4676C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-11-21 | PS5-02-03 | PS5 - Milestone G | 6 | Closed | 37 | 32 | NOVEMBER
T-147-11103 | PS5-69-IK-9212D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone A | 1 | In progress |  | 25 | NOVEMBER
T-499-11104 | PS5-85-IK-8645A | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone G | 6 | To be completed |  | 7 | OCTOBER
T-932-11105 | PS5-51-OB-5063D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone E | 4 | On hold |  | 38 | OCTOBER
T-887-11106 | PS5-98-IK-4037D | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone G | 6 | In progress |  | 39 | OCTOBER
T-166-11107 | PS5-67-OB-8655C | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-02-19 | PS5-08-01 | PS5 - Milestone F | 5 | Closed | 42 | 43 | FEBRUARY
T-509-11108 | PS5-16-OB-5686A | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone D | 3 | In progress |  | 46 | DECEMBER
T-802-11109 | PS5-91-IK-7261A | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-11-19 | PS5-61-01 | PS5 - Milestone F | 5 | Closed | 36 | 20 | NOVEMBER
T-179-11110 | PS5-40-OB-6326C | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-03-21 | PS5-06-03 | PS5 - Milestone I | 8 | Closed | 10 | 10 | MARCH
T-301-11111 | PS5-08-IK-4336D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-09-11 | PS5-82-07 | PS5 - Milestone C | 2 | Closed | 14 | 12 | SEPTEMBER
T-641-11112 | PS5-57-OB-2993B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone G | 6 | To be completed |  | 19 | AUGUST
T-486-11113 | PS5-81-UR-4709B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-03-10 | PS5-63-04 | PS5 - Milestone F | 5 | Closed | 31 | 33 | MARCH
T-764-11114 | PS5-87-OB-8728A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | To be completed |  | 16 | SEPTEMBER
T-306-11115 | PS5-85-UR-5067D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone I | 8 | To be completed |  | 10 | NOVEMBER
T-842-11116 | PS5-62-IK-6211A | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone D | 3 | To be completed |  | 38 | SEPTEMBER
T-917-11117 | PS5-66-UR-7904A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | To be completed |  | 39 | AUGUST
T-607-11118 | PS5-20-UR-5797A | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | To be completed |  | 41 | OCTOBER
T-939-11119 | PS5-66-UR-3490B | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone G | 6 | To be completed |  | 14 | AUGUST
T-684-11120 | PS5-02-UR-7489D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone D | 3 | To be completed |  | 25 | SEPTEMBER
T-460-11121 | PS5-68-UR-9813B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | In progress |  | 10 | OCTOBER
T-700-11122 | PS5-87-OB-2396B | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-01-16 | PS5-61-07 | PS5 - Milestone A | 1 | Closed | 33 | 5 | JANUARY
T-346-11123 | PS5-29-OB-2595C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone G | 6 | In progress |  | 23 | DECEMBER
T-224-11124 | PS5-62-OB-6119B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | In progress |  | 39 | OCTOBER
T-351-11125 | PS5-09-IK-5550A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | To be completed |  | 26 | NOVEMBER
T-803-11126 | PS5-33-OB-2796B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone H | 7 | In progress |  | 16 | AUGUST
T-454-11127 | PS5-96-IK-6635C | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-11-16 | PS5-07-02 | PS5 - Milestone B | 1.1 | Closed | 11 | 25 | NOVEMBER
T-971-11128 | PS5-39-OB-2233A | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | To be completed |  | 22 | DECEMBER
T-720-11129 | PS5-63-OB-1302C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone C | 2 | On hold |  | 28 | OCTOBER
T-267-11130 | PS5-52-UR-1111C | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-12-18 | PS5-06-01 | PS5 - Milestone F | 5 | Closed | 17 | 10 | DECEMBER
T-022-11131 | PS5-79-OB-8958D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-07-20 | PS5-09-02 | PS5 - Milestone D | 3 | Closed | 13 | 39 | JULY
T-109-11132 | PS5-06-IK-3660B | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-07-15 | PS5-07-04 | PS5 - Milestone D | 3 | Closed | 21 | 29 | JULY
T-887-11133 | PS5-24-OB-5432D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone H | 7 | To be completed |  | 22 | SEPTEMBER
T-646-11134 | PS5-21-IK-9508C | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone H | 7 | In progress |  | 31 | DECEMBER
T-759-11135 | PS5-43-UR-9564A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone I | 8 | In progress |  | 47 | DECEMBER
T-866-11136 | PS5-86-UR-9070A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-02-16 | PS5-11-01 | PS5 - Milestone B | 1.1 | Closed | 5 | 20 | FEBRUARY
T-928-11137 | PS5-95-OB-7730B | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone E | 4 | In progress |  | 40 | AUGUST
T-053-11138 | PS5-08-IK-8125B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone D | 3 | To be completed |  | 35 | SEPTEMBER
T-813-11139 | PS5-77-OB-1542D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-12-01 | PS5-11-02 | PS5 - Milestone A | 1 | Closed | 4 | 16 | DECEMBER
T-119-11140 | PS5-31-IK-2035A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone B | 1.1 | To be completed |  | 9 | SEPTEMBER
T-334-11141 | PS5-20-OB-5516C | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | To be completed |  | 35 | NOVEMBER
T-578-11142 | PS5-33-OB-4974C | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone G | 6 | In progress |  | 27 | OCTOBER
T-993-11143 | PS5-32-OB-2896B | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-04-09 | PS5-12-01 | PS5 - Milestone E | 4 | Closed | 6 | 6 | APRIL
T-135-11144 | PS5-75-UR-3917C | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone H | 7 | To be completed |  | 31 | SEPTEMBER
T-461-11145 | PS5-64-IK-4902C | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-10-25 | PS5-99-01 | PS5 - Milestone H | 7 | Closed | 24 | 25 | OCTOBER
T-680-11146 | PS5-32-OB-7826B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone B | 1.1 | In progress |  | 19 | SEPTEMBER
T-194-11147 | PS5-64-UR-5552C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-05-02 | PS5-07-01 | PS5 - Milestone E | 4 | Closed | 23 | 27 | MAY
T-279-11148 | PS5-41-OB-4841C | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-03-16 | PS5-06-01 | PS5 - Milestone E | 4 | Closed | 40 | 6 | MARCH
T-462-11149 | PS5-77-OB-9798B | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone D | 3 | To be completed |  | 32 | OCTOBER
T-821-11150 | PS5-35-UR-9751D | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone H | 7 | On hold |  | 37 | NOVEMBER
T-642-11151 | PS5-77-IK-8667A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-04-15 | PS5-82-01 | PS5 - Milestone D | 3 | Closed | 28 | 36 | APRIL
T-413-11152 | PS5-79-OB-6145C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone D | 3 | In progress |  | 32 | NOVEMBER
T-338-11153 | PS5-61-OB-5782B | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone B | 1.1 | In progress |  | 48 | OCTOBER
T-712-11154 | PS5-89-OB-4877D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-02-24 | PS5-62-02 | PS5 - Milestone B | 1.1 | Closed | 33 | 12 | FEBRUARY
T-849-11155 | PS5-07-OB-8204A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-08-13 | PS5-10-05 | PS5 - Milestone F | 5 | Closed | 38 | 24 | AUGUST
T-829-11156 | PS5-81-UR-3892B | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-01-13 | PS5-01-01 | PS5 - Milestone G | 6 | Closed | 47 | 27 | JANUARY
T-380-11157 | PS5-12-UR-2728A | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-02-02 | PS5-99-01 | PS5 - Milestone B | 1.1 | Closed | 47 | 18 | FEBRUARY
T-217-11158 | PS5-65-OB-1332D | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-01-10 | PS5-01-01 | PS5 - Milestone B | 1.1 | Closed | 29 | 23 | JANUARY
T-751-11159 | PS5-66-UR-5431D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone B | 1.1 | In progress |  | 26 | SEPTEMBER
T-494-11160 | PS5-91-UR-5977B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone I | 8 | To be completed |  | 9 | DECEMBER
T-934-11161 | PS5-46-IK-2614D | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone I | 8 | To be completed |  | 32 | DECEMBER
T-154-11162 | PS5-78-OB-2558C | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | To be completed |  | 48 | AUGUST
T-551-11163 | PS5-88-IK-6246C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone A | 1 | In progress |  | 20 | OCTOBER
T-334-11164 | PS5-53-UR-7436B | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone G | 6 | To be completed |  | 31 | NOVEMBER
T-519-11165 | PS5-43-IK-2059C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | To be completed |  | 22 | NOVEMBER
T-031-11166 | PS5-12-UR-3361B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone C | 2 | To be completed |  | 32 | DECEMBER
T-770-11167 | PS5-31-OB-1594A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone E | 4 | On hold |  | 44 | OCTOBER
T-288-11168 | PS5-08-OB-8277B | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone D | 3 | On hold |  | 29 | SEPTEMBER
T-640-11169 | PS5-90-OB-8813D | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-04-15 | PS5-82-02 | PS5 - Milestone F | 5 | Closed | 17 | 9 | APRIL
T-500-11170 | PS5-59-OB-8786A | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-08-08 | PS5-02-01 | PS5 - Milestone I | 8 | Closed | 41 | 24 | AUGUST
T-578-11171 | PS5-14-OB-1888A | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone F | 5 | On hold |  | 17 | SEPTEMBER
T-459-11172 | PS5-20-UR-3585A | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone B | 1.1 | To be completed |  | 45 | SEPTEMBER
T-296-11173 | PS5-15-IK-8239C | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-10-22 | PS5-07-03 | PS5 - Milestone E | 4 | Closed | 23 | 47 | OCTOBER
T-220-11174 | PS5-16-OB-1448A | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-09-12 | PS5-03-23 | PS5 - Milestone E | 4 | Closed | 28 | 22 | SEPTEMBER
T-262-11175 | PS5-60-OB-2813C | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone G | 6 | In progress |  | 35 | SEPTEMBER
T-356-11176 | PS5-08-IK-5309C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-08-24 | PS5-02-01 | PS5 - Milestone B | 1.1 | Closed | 40 | 32 | AUGUST
T-308-11177 | PS5-97-OB-8481C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | On hold |  | 8 | NOVEMBER
T-259-11178 | PS5-45-OB-8424A | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | In progress |  | 39 | NOVEMBER
T-329-11179 | PS5-91-OB-8275D | CQS01 - Fire Protection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-05-16 | PS5-60-10 | PS5 - Milestone F | 5 | Closed | 45 | 39 | MAY
T-514-11180 | PS5-80-OB-8165C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | In progress |  | 15 | DECEMBER
T-197-11181 | PS5-31-IK-1564D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | In progress |  | 9 | AUGUST
T-438-11182 | PS5-66-UR-4764D | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone E | 4 | In progress |  | 33 | OCTOBER
T-902-11183 | PS5-54-OB-1685D | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone I | 8 | To be completed |  | 16 | AUGUST
T-119-11184 | PS5-57-OB-7236B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone H | 7 | To be completed |  | 13 | OCTOBER
T-624-11185 | PS5-95-UR-5904C | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-08-25 | PS5-06-02 | PS5 - Milestone B | 1.1 | Closed | 43 | 29 | AUGUST
T-371-11186 | PS5-10-OB-1202A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-04-08 | PS5-10-02 | PS5 - Milestone E | 4 | Closed | 18 | 40 | APRIL
T-359-11187 | PS5-53-UR-3484D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-02-17 | PS5-04-02 | PS5 - Milestone C | 2 | Closed | 39 | 31 | FEBRUARY
T-564-11188 | PS5-37-OB-9742A | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone F | 5 | To be completed |  | 33 | AUGUST
T-979-11189 | PS5-02-OB-8338D | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone H | 7 | On hold |  | 23 | SEPTEMBER
T-184-11190 | PS5-05-IK-2429B | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone F | 5 | On hold |  | 42 | SEPTEMBER
T-944-11191 | PS5-80-UR-8289D | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone B | 1.1 | To be completed |  | 20 | SEPTEMBER
T-575-11192 | PS5-14-IK-7046B | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone G | 6 | To be completed |  | 47 | NOVEMBER
T-860-11193 | PS5-84-OB-6014D | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-04-20 | PS5-10-02 | PS5 - Milestone H | 7 | Closed | 13 | 47 | APRIL
T-239-11194 | PS5-39-OB-1871B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone H | 7 | In progress |  | 14 | AUGUST
T-032-11195 | PS5-61-UR-1480D | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-12-24 | PS5-07-01 | PS5 - Milestone F | 5 | Closed | 16 | 39 | DECEMBER
T-090-11196 | PS5-51-UR-3381A | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-07-15 | PS5-10-01 | PS5 - Milestone F | 5 | Closed | 30 | 13 | JULY
T-438-11197 | PS5-28-IK-7694C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-07-28 | PS5-60-01 | PS5 - Milestone E | 4 | Closed | 5 | 31 | JULY
T-657-11198 | PS5-39-OB-7305B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone G | 6 | To be completed |  | 47 | DECEMBER
T-494-11199 | PS5-30-OB-1919D | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone A | 1 | To be completed |  | 4 | SEPTEMBER
T-343-11200 | PS5-66-UR-3786C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | In progress |  | 11 | SEPTEMBER
T-118-11201 | PS5-24-IK-1913A | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-06-06 | PS5-10-01 | PS5 - Milestone C | 2 | Closed | 31 | 27 | JUNE
T-432-11202 | PS5-98-OB-7366C | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-01-21 | PS5-99-01 | PS5 - Milestone G | 6 | Closed | 16 | 32 | JANUARY
T-489-11203 | PS5-81-OB-5805C | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | To be completed |  | 6 | DECEMBER
T-884-11204 | PS5-18-UR-7126C | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | To be completed |  | 42 | SEPTEMBER
T-671-11205 | PS5-67-OB-5585C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-07-25 | PS5-01-02 | PS5 - Milestone F | 5 | Closed | 12 | 14 | JULY
T-307-11206 | PS5-94-OB-5413A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone C | 2 | On hold |  | 30 | SEPTEMBER
T-545-11207 | PS5-96-IK-2875A | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone E | 4 | In progress |  | 45 | OCTOBER
T-233-11208 | PS5-26-OB-1104C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone E | 4 | In progress |  | 28 | OCTOBER
T-237-11209 | PS5-70-OB-4621C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-07-12 | PS5-62-02 | PS5 - Milestone B | 1.1 | Closed | 6 | 5 | JULY
T-572-11210 | PS5-67-OB-3838A | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone D | 3 | To be completed |  | 14 | NOVEMBER
T-227-11211 | PS5-82-OB-8545C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-09-03 | PS5-03-03 | PS5 - Milestone D | 3 | Closed | 31 | 35 | SEPTEMBER
T-525-11212 | PS5-41-IK-2812D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-12-05 | PS5-82-07 | PS5 - Milestone H | 7 | Closed | 14 | 9 | DECEMBER
T-509-11213 | PS5-71-UR-2461A | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone C | 2 | To be completed |  | 35 | SEPTEMBER
T-519-11214 | PS5-89-OB-9623A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone E | 4 | In progress |  | 25 | OCTOBER
T-532-11215 | PS5-69-OB-2931A | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone D | 3 | To be completed |  | 44 | OCTOBER
T-705-11216 | PS5-19-OB-4481A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone I | 8 | In progress |  | 40 | OCTOBER
T-059-11217 | PS5-93-UR-7719C | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-04-14 | PS5-03-03 | PS5 - Milestone D | 3 | Closed | 11 | 44 | APRIL
T-269-11218 | PS5-30-OB-9469D | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone E | 4 | In progress |  | 33 | DECEMBER
T-920-11219 | PS5-06-OB-9138A | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone F | 5 | In progress |  | 27 | NOVEMBER
T-445-11220 | PS5-90-IK-7747C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | In progress |  | 10 | AUGUST
T-500-11221 | PS5-74-OB-8114C | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | To be completed |  | 8 | DECEMBER
T-961-11222 | PS5-80-OB-2974C | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone B | 1.1 | To be completed |  | 32 | SEPTEMBER
T-394-11223 | PS5-44-UR-8390D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone I | 8 | To be completed |  | 6 | OCTOBER
T-607-11224 | PS5-09-OB-9915B | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-05-07 | PS5-03-02 | PS5 - Milestone C | 2 | Closed | 41 | 31 | MAY
T-643-11225 | PS5-91-OB-7172B | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone G | 6 | On hold |  | 17 | AUGUST
T-460-11226 | PS5-22-IK-6726A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-09-01 | PS5-11-01 | PS5 - Milestone F | 5 | Closed | 34 | 47 | SEPTEMBER
T-723-11227 | PS5-50-OB-7783A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | To be completed |  | 25 | AUGUST
T-990-11228 | PS5-49-IK-8151A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | In progress |  | 37 | AUGUST
T-220-11229 | PS5-79-OB-6198D | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone A | 1 | In progress |  | 4 | AUGUST
T-337-11230 | PS5-20-UR-7584D | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone E | 4 | To be completed |  | 38 | OCTOBER
T-312-11231 | PS5-61-OB-7157B | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone E | 4 | To be completed |  | 21 | AUGUST
T-633-11232 | PS5-70-OB-4536C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-09-07 | PS5-01-04 | PS5 - Milestone D | 3 | Closed | 26 | 46 | SEPTEMBER
T-852-11233 | PS5-43-OB-4500C | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone B | 1.1 | To be completed |  | 31 | NOVEMBER
T-105-11234 | PS5-78-OB-2379D | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-04-13 | PS5-63-01 | PS5 - Milestone C | 2 | Closed | 21 | 26 | APRIL
T-377-11235 | PS5-64-IK-6297D | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-12-20 | PS5-06-03 | PS5 - Milestone C | 2 | Closed | 14 | 17 | DECEMBER
T-192-11236 | PS5-62-IK-5076C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone I | 8 | To be completed |  | 31 | DECEMBER
T-286-11237 | PS5-78-OB-4232C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone G | 6 | In progress |  | 5 | SEPTEMBER
T-177-11238 | PS5-61-IK-3889B | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone A | 1 | In progress |  | 19 | OCTOBER
T-945-11239 | PS5-29-UR-1088C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | To be completed |  | 46 | AUGUST
T-343-11240 | PS5-65-IK-9573A | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-06-25 | PS5-11-02 | PS5 - Milestone D | 3 | Closed | 37 | 17 | JUNE
T-050-11241 | PS5-81-UR-8261C | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone E | 4 | In progress |  | 15 | AUGUST
T-278-11242 | PS5-54-UR-7020D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-10-04 | PS5-12-02 | PS5 - Milestone A | 1 | Closed | 22 | 38 | OCTOBER
T-718-11243 | PS5-74-UR-9753D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone D | 3 | To be completed |  | 17 | NOVEMBER
T-319-11244 | PS5-90-UR-2303B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-01-23 | PS5-62-02 | PS5 - Milestone F | 5 | Closed | 13 | 11 | JANUARY
T-054-11245 | PS5-33-UR-5597B | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone G | 6 | To be completed |  | 17 | OCTOBER
T-005-11246 | PS5-16-OB-8193A | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-04-22 | PS5-01-03 | PS5 - Milestone F | 5 | Closed | 45 | 47 | APRIL
T-708-11247 | PS5-13-OB-8856B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-12-24 | PS5-02-03 | PS5 - Milestone E | 4 | Closed | 16 | 9 | DECEMBER
T-794-11248 | PS5-44-OB-3647B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-03-23 | PS5-10-05 | PS5 - Milestone I | 8 | Closed | 18 | 35 | MARCH
T-047-11249 | PS5-58-OB-5751C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-07-12 | PS5-10-06 | PS5 - Milestone D | 3 | Closed | 22 | 33 | JULY
T-011-11250 | PS5-58-OB-3748D | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-04-16 | PS5-10-03 | PS5 - Milestone A | 1 | Closed | 13 | 40 | APRIL
T-570-11251 | PS5-69-OB-4758C | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-11-19 | PS5-60-10 | PS5 - Milestone E | 4 | Closed | 34 | 5 | NOVEMBER
T-392-11252 | PS5-81-OB-7736D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone E | 4 | In progress |  | 18 | DECEMBER
T-759-11253 | PS5-48-OB-9024B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone C | 2 | To be completed |  | 33 | OCTOBER
T-781-11254 | PS5-69-OB-9806D | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone G | 6 | To be completed |  | 39 | OCTOBER
T-927-11255 | PS5-33-OB-4379B | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | In progress |  | 44 | DECEMBER
T-104-11256 | PS5-97-OB-9181A | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone H | 7 | To be completed |  | 48 | DECEMBER
T-872-11257 | PS5-20-OB-5443C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone E | 4 | To be completed |  | 26 | OCTOBER
T-207-11258 | PS5-17-UR-6923B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone A | 1 | To be completed |  | 31 | OCTOBER
T-735-11259 | PS5-28-UR-2180B | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone C | 2 | In progress |  | 34 | AUGUST
T-484-11260 | PS5-43-IK-6456B | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-01-23 | PS5-11-03 | PS5 - Milestone I | 8 | Closed | 34 | 43 | JANUARY
T-149-11261 | PS5-46-IK-8420B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-02-16 | PS5-82-07 | PS5 - Milestone A | 1 | Closed | 44 | 7 | FEBRUARY
T-747-11262 | PS5-79-UR-7985C | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | To be completed |  | 24 | AUGUST
T-326-11263 | PS5-41-UR-7806C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-10-10 | PS5-61-02 | PS5 - Milestone B | 1.1 | Closed | 28 | 28 | OCTOBER
T-837-11264 | PS5-65-OB-7309A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-04-01 | PS5-01-06 | PS5 - Milestone B | 1.1 | Closed | 44 | 38 | APRIL
T-946-11265 | PS5-79-OB-8285D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone G | 6 | To be completed |  | 34 | AUGUST
T-769-11266 | PS5-93-IK-9105C | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone B | 1.1 | In progress |  | 42 | DECEMBER
T-463-11267 | PS5-34-UR-2954C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone F | 5 | In progress |  | 34 | SEPTEMBER
T-789-11268 | PS5-91-UR-6017C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-01-08 | PS5-01-08 | PS5 - Milestone I | 8 | Closed | 16 | 47 | JANUARY
T-529-11269 | PS5-51-OB-9472A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-04-28 | PS5-10-05 | PS5 - Milestone B | 1.1 | Closed | 10 | 26 | APRIL
T-432-11270 | PS5-78-OB-1154B | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | To be completed |  | 7 | DECEMBER
T-958-11271 | PS5-20-OB-9069D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | To be completed |  | 11 | DECEMBER
T-623-11272 | PS5-12-UR-2919D | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-08-14 | PS5-01-09 | PS5 - Milestone G | 6 | Closed | 23 | 25 | AUGUST
T-237-11273 | PS5-90-OB-7605D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | On hold |  | 22 | AUGUST
T-923-11274 | PS5-58-OB-6651C | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone G | 6 | To be completed |  | 15 | NOVEMBER
T-404-11275 | PS5-94-IK-5929B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone F | 5 | In progress |  | 38 | AUGUST
T-940-11276 | PS5-57-OB-8362B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone D | 3 | On hold |  | 44 | NOVEMBER
T-555-11277 | PS5-08-OB-5424B | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone I | 8 | To be completed |  | 14 | NOVEMBER
T-130-11278 | PS5-66-OB-8688C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-03-27 | PS5-01-09 | PS5 - Milestone C | 2 | Closed | 44 | 38 | MARCH
T-781-11279 | PS5-23-IK-1541B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone B | 1.1 | On hold |  | 43 | NOVEMBER
T-733-11280 | PS5-02-UR-6015D | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-01-23 | PS5-62-01 | PS5 - Milestone G | 6 | Closed | 22 | 28 | JANUARY
T-538-11281 | PS5-92-UR-7727B | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone G | 6 | To be completed |  | 23 | DECEMBER
T-441-11282 | PS5-83-IK-8481B | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone D | 3 | To be completed |  | 40 | OCTOBER
T-529-11283 | PS5-94-OB-1363C | CQM01 - Pump Installation | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone F | 5 | In progress |  | 18 | DECEMBER
T-183-11284 | PS5-60-OB-2640C | CQM01 - Pump Installation | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone D | 3 | To be completed |  | 13 | OCTOBER
T-961-11285 | PS5-60-OB-6977D | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | On hold |  | 21 | OCTOBER
T-019-11286 | PS5-65-OB-5014B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone G | 6 | In progress |  | 10 | SEPTEMBER
T-556-11287 | PS5-69-UR-1309A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-05-21 | PS5-11-03 | PS5 - Milestone D | 3 | Closed | 40 | 11 | MAY
T-639-11288 | PS5-36-IK-2424A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-09-08 | PS5-07-03 | PS5 - Milestone G | 6 | Closed | 13 | 20 | SEPTEMBER
T-110-11289 | PS5-48-OB-8442A | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone A | 1 | To be completed |  | 4 | AUGUST
T-494-11290 | PS5-23-UR-6923A | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone G | 6 | To be completed |  | 25 | OCTOBER
T-132-11291 | PS5-67-UR-5108C | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone A | 1 | In progress |  | 18 | AUGUST
T-103-11292 | PS5-83-UR-5511C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-06-05 | PS5-07-04 | PS5 - Milestone C | 2 | Closed | 28 | 33 | JUNE
T-510-11293 | PS5-71-UR-7413D | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone G | 6 | To be completed |  | 31 | OCTOBER
T-263-11294 | PS5-12-IK-5517C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone F | 5 | On hold |  | 20 | SEPTEMBER
T-269-11295 | PS5-34-OB-1240C | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-04-08 | PS5-09-02 | PS5 - Milestone E | 4 | Closed | 13 | 23 | APRIL
T-721-11296 | PS5-48-OB-4519B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | On hold |  | 4 | AUGUST
T-990-11297 | PS5-83-OB-5158C | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-10-04 | PS5-01-03 | PS5 - Milestone C | 2 | Closed | 11 | 35 | OCTOBER
T-844-11298 | PS5-53-OB-5358C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-09-20 | PS5-13-01 | PS5 - Milestone G | 6 | Closed | 37 | 33 | SEPTEMBER
T-582-11299 | PS5-02-OB-4997D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-06-03 | PS5-99-02 | PS5 - Milestone E | 4 | Closed | 46 | 26 | JUNE
T-720-11300 | PS5-13-OB-1154D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone H | 7 | In progress |  | 24 | SEPTEMBER
T-964-11301 | PS5-35-OB-6969D | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-12-08 | PS5-09-04 | PS5 - Milestone D | 3 | Closed | 28 | 15 | DECEMBER
T-084-11302 | PS5-87-IK-9241D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-09-10 | PS5-60-07 | PS5 - Milestone D | 3 | Closed | 26 | 41 | SEPTEMBER
T-163-11303 | PS5-31-UR-3637A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone E | 4 | In progress |  | 41 | DECEMBER
T-321-11304 | PS5-98-IK-6887A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-09-28 | PS5-07-04 | PS5 - Milestone I | 8 | Closed | 26 | 21 | SEPTEMBER
T-157-11305 | PS5-58-UR-8515A | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone D | 3 | To be completed |  | 30 | SEPTEMBER
T-077-11306 | PS5-50-IK-1793B | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone F | 5 | To be completed |  | 40 | OCTOBER
T-024-11307 | PS5-59-IK-9543D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-10-26 | PS5-61-01 | PS5 - Milestone D | 3 | Closed | 4 | 35 | OCTOBER
T-363-11308 | PS5-68-OB-6136D | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-01-16 | PS5-01-02 | PS5 - Milestone H | 7 | Closed | 31 | 25 | JANUARY
T-285-11309 | PS5-44-OB-5224C | CQP04 - Hydrotest | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-10-12 | PS5-03-03 | PS5 - Milestone D | 3 | Closed | 22 | 24 | OCTOBER
T-094-11310 | PS5-39-IK-8075C | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone C | 2 | In progress |  | 28 | NOVEMBER
T-712-11311 | PS5-50-IK-6639D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone C | 2 | In progress |  | 22 | OCTOBER
T-794-11312 | PS5-64-OB-3912B | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone F | 5 | To be completed |  | 42 | SEPTEMBER
T-402-11313 | PS5-64-OB-3342A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | To be completed |  | 11 | DECEMBER
T-800-11314 | PS5-18-IK-9921B | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-05-14 | PS5-01-08 | PS5 - Milestone F | 5 | Closed | 25 | 5 | MAY
T-273-11315 | PS5-32-IK-5017A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone H | 7 | To be completed |  | 25 | AUGUST
T-886-11316 | PS5-47-OB-2736D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-11-12 | PS5-62-01 | PS5 - Milestone A | 1 | Closed | 6 | 22 | NOVEMBER
T-414-11317 | PS5-73-IK-7456C | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-11-04 | PS5-02-03 | PS5 - Milestone A | 1 | Closed | 18 | 21 | NOVEMBER
T-560-11318 | PS5-76-IK-2052A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone H | 7 | On hold |  | 14 | DECEMBER
T-026-11319 | PS5-31-OB-4985A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone E | 4 | In progress |  | 10 | SEPTEMBER
T-277-11320 | PS5-10-OB-1835C | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone H | 7 | In progress |  | 41 | SEPTEMBER
T-820-11321 | PS5-47-IK-2483A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone D | 3 | In progress |  | 47 | NOVEMBER
T-177-11322 | PS5-65-OB-3832A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-08-13 | PS5-08-01 | PS5 - Milestone H | 7 | Closed | 35 | 36 | AUGUST
T-510-11323 | PS5-59-IK-1211A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone B | 1.1 | On hold |  | 29 | SEPTEMBER
T-459-11324 | PS5-55-OB-3755C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | In progress |  | 11 | OCTOBER
T-776-11325 | PS5-70-UR-2820A | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone D | 3 | In progress |  | 20 | DECEMBER
T-328-11326 | PS5-83-OB-7217B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-08-08 | PS5-09-02 | PS5 - Milestone A | 1 | Closed | 46 | 37 | AUGUST
T-856-11327 | PS5-19-IK-1920B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-07-18 | PS5-11-03 | PS5 - Milestone C | 2 | Closed | 34 | 9 | JULY
T-036-11328 | PS5-69-IK-1248D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-07-18 | PS5-01-08 | PS5 - Milestone B | 1.1 | Closed | 48 | 21 | JULY
T-989-11329 | PS5-52-UR-1908D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-03-01 | PS5-03-02 | PS5 - Milestone D | 3 | Closed | 24 | 46 | MARCH
T-214-11330 | PS5-85-IK-6359D | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone I | 8 | To be completed |  | 20 | OCTOBER
T-516-11331 | PS5-57-OB-8898A | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone C | 2 | To be completed |  | 28 | DECEMBER
T-024-11332 | PS5-34-OB-1990A | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-09-06 | PS5-05-02 | PS5 - Milestone A | 1 | Closed | 19 | 15 | SEPTEMBER
T-825-11333 | PS5-83-IK-3739C | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone I | 8 | On hold |  | 29 | DECEMBER
T-620-11334 | PS5-50-IK-5312C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone F | 5 | To be completed |  | 4 | DECEMBER
T-715-11335 | PS5-72-OB-3316B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone I | 8 | On hold |  | 37 | DECEMBER
T-918-11336 | PS5-17-OB-7054A | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-11-10 | PS5-04-03 | PS5 - Milestone H | 7 | Closed | 47 | 12 | NOVEMBER
T-133-11337 | PS5-38-IK-4813B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone E | 4 | To be completed |  | 18 | NOVEMBER
T-550-11338 | PS5-38-UR-5589A | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone G | 6 | In progress |  | 44 | OCTOBER
T-610-11339 | PS5-32-OB-9795B | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-11-12 | PS5-11-02 | PS5 - Milestone D | 3 | Closed | 23 | 46 | NOVEMBER
T-401-11340 | PS5-18-OB-4194D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-09-03 | PS5-10-06 | PS5 - Milestone C | 2 | Closed | 14 | 28 | SEPTEMBER
T-508-11341 | PS5-36-OB-9677B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone E | 4 | On hold |  | 39 | SEPTEMBER
T-227-11342 | PS5-79-OB-5483C | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone H | 7 | In progress |  | 7 | AUGUST
T-344-11343 | PS5-26-OB-6850A | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone H | 7 | To be completed |  | 38 | DECEMBER
T-324-11344 | PS5-25-UR-1612B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone A | 1 | In progress |  | 27 | OCTOBER
T-108-11345 | PS5-22-OB-8920D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-05-03 | PS5-10-01 | PS5 - Milestone F | 5 | Closed | 44 | 16 | MAY
T-514-11346 | PS5-33-IK-5777C | CQM04 - Vessel | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-07-13 | PS5-08-01 | PS5 - Milestone B | 1.1 | Closed | 24 | 21 | JULY
T-721-11347 | PS5-32-OB-1457D | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-06-05 | PS5-82-01 | PS5 - Milestone A | 1 | Closed | 42 | 38 | JUNE
T-923-11348 | PS5-55-OB-4912A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone A | 1 | In progress |  | 39 | AUGUST
T-931-11349 | PS5-37-OB-4950B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | On hold |  | 10 | DECEMBER
T-933-11350 | PS5-02-UR-2133D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone G | 6 | To be completed |  | 24 | OCTOBER
T-819-11351 | PS5-91-OB-3298B | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-03-11 | PS5-62-01 | PS5 - Milestone E | 4 | Closed | 17 | 38 | MARCH
T-701-11352 | PS5-19-OB-4501A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone B | 1.1 | On hold |  | 17 | OCTOBER
T-318-11353 | PS5-14-UR-4946C | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | To be completed |  | 48 | OCTOBER
T-134-11354 | PS5-21-UR-2648C | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | To be completed |  | 19 | OCTOBER
T-797-11355 | PS5-65-OB-8311A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-05-06 | PS5-07-01 | PS5 - Milestone H | 7 | Closed | 16 | 42 | MAY
T-149-11356 | PS5-72-OB-6389C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-20 | PS5-60-10 | PS5 - Milestone G | 6 | Closed | 20 | 18 | APRIL
T-110-11357 | PS5-61-IK-7943A | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone H | 7 | To be completed |  | 30 | AUGUST
T-602-11358 | PS5-45-OB-7032B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-08-09 | PS5-82-07 | PS5 - Milestone B | 1.1 | Closed | 33 | 6 | AUGUST
T-573-11359 | PS5-21-UR-3926A | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | On hold |  | 18 | AUGUST
T-880-11360 | PS5-19-OB-8241D | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone C | 2 | To be completed |  | 8 | SEPTEMBER
T-975-11361 | PS5-21-OB-2422B | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-07-24 | PS5-03-02 | PS5 - Milestone I | 8 | Closed | 47 | 19 | JULY
T-850-11362 | PS5-58-OB-1301C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone E | 4 | In progress |  | 6 | SEPTEMBER
T-049-11363 | PS5-95-OB-1010C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | In progress |  | 4 | DECEMBER
T-519-11364 | PS5-73-OB-1460A | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-08-23 | PS5-10-03 | PS5 - Milestone A | 1 | Closed | 13 | 37 | AUGUST
T-544-11365 | PS5-49-OB-6351A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | In progress |  | 21 | SEPTEMBER
T-889-11366 | PS5-33-IK-6745A | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone G | 6 | To be completed |  | 23 | OCTOBER
T-931-11367 | PS5-32-IK-3158B | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-03-28 | PS5-01-03 | PS5 - Milestone G | 6 | Closed | 48 | 5 | MARCH
T-735-11368 | PS5-48-UR-8157B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone D | 3 | To be completed |  | 34 | DECEMBER
T-011-11369 | PS5-26-OB-7147C | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-11-11 | PS5-12-02 | PS5 - Milestone E | 4 | Closed | 11 | 21 | NOVEMBER
T-907-11370 | PS5-33-IK-2891B | CQS01 - Fire Protection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-06-04 | PS5-10-01 | PS5 - Milestone C | 2 | Closed | 9 | 9 | JUNE
T-604-11371 | PS5-76-OB-8081C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone E | 4 | To be completed |  | 45 | AUGUST
T-263-11372 | PS5-48-OB-3049A | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone H | 7 | In progress |  | 10 | NOVEMBER
T-413-11373 | PS5-08-OB-4773D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | On hold |  | 27 | OCTOBER
T-008-11374 | PS5-82-IK-7067D | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | To be completed |  | 47 | AUGUST
T-736-11375 | PS5-95-IK-4057C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-10-16 | PS5-10-03 | PS5 - Milestone D | 3 | Closed | 22 | 24 | OCTOBER
T-206-11376 | PS5-90-OB-8760D | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone D | 3 | In progress |  | 44 | DECEMBER
T-393-11377 | PS5-47-OB-7472B | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone F | 5 | To be completed |  | 28 | AUGUST
T-131-11378 | PS5-14-IK-1527D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone G | 6 | To be completed |  | 9 | NOVEMBER
T-517-11379 | PS5-79-OB-7306A | CQM04 - Vessel | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone D | 3 | To be completed |  | 10 | NOVEMBER
T-126-11380 | PS5-42-OB-3038B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone A | 1 | To be completed |  | 13 | SEPTEMBER
T-552-11381 | PS5-15-UR-1733B | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-05-05 | PS5-01-06 | PS5 - Milestone H | 7 | Closed | 42 | 22 | MAY
T-183-11382 | PS5-53-OB-5577C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-07-05 | PS5-13-01 | PS5 - Milestone A | 1 | Closed | 48 | 8 | JULY
T-064-11383 | PS5-16-OB-4968D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | In progress |  | 35 | SEPTEMBER
T-920-11384 | PS5-32-OB-7580A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone I | 8 | To be completed |  | 8 | DECEMBER
T-669-11385 | PS5-85-OB-7308D | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone C | 2 | In progress |  | 41 | NOVEMBER
T-191-11386 | PS5-57-OB-7238B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone A | 1 | To be completed |  | 39 | DECEMBER
T-028-11387 | PS5-60-IK-7683B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-04-20 | PS5-03-02 | PS5 - Milestone E | 4 | Closed | 39 | 22 | APRIL
T-160-11388 | PS5-87-IK-5822C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | To be completed |  | 7 | NOVEMBER
T-863-11389 | PS5-56-OB-3208D | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-11-06 | PS5-05-01 | PS5 - Milestone F | 5 | Closed | 36 | 24 | NOVEMBER
T-107-11390 | PS5-37-UR-1899B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-01-22 | PS5-12-01 | PS5 - Milestone E | 4 | Closed | 4 | 8 | JANUARY
T-402-11391 | PS5-84-UR-2433D | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone B | 1.1 | To be completed |  | 21 | NOVEMBER
T-243-11392 | PS5-02-UR-7434D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | In progress |  | 21 | DECEMBER
T-198-11393 | PS5-40-OB-6851A | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone A | 1 | To be completed |  | 44 | NOVEMBER
T-965-11394 | PS5-30-UR-6328A | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone F | 5 | In progress |  | 48 | SEPTEMBER
T-248-11395 | PS5-80-OB-1057C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-07-07 | PS5-02-03 | PS5 - Milestone D | 3 | Closed | 34 | 27 | JULY
T-773-11396 | PS5-32-OB-3955B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | To be completed |  | 36 | NOVEMBER
T-203-11397 | PS5-81-OB-4028A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | In progress |  | 34 | DECEMBER
T-125-11398 | PS5-53-OB-3580A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-25 | PS5-60-07 | PS5 - Milestone A | 1 | Closed | 37 | 12 | APRIL
T-118-11399 | PS5-14-OB-8863A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone G | 6 | To be completed |  | 43 | DECEMBER
T-619-11400 | PS5-48-OB-8689C | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | In progress |  | 40 | SEPTEMBER
T-495-11401 | PS5-67-IK-1818D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-11-23 | PS5-09-02 | PS5 - Milestone C | 2 | Closed | 13 | 19 | NOVEMBER
T-912-11402 | PS5-93-UR-1080A | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-02-20 | PS5-11-03 | PS5 - Milestone C | 2 | Closed | 4 | 15 | FEBRUARY
T-702-11403 | PS5-36-OB-4904C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-09-09 | PS5-09-02 | PS5 - Milestone F | 5 | Closed | 23 | 22 | SEPTEMBER
T-628-11404 | PS5-71-IK-1307B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone F | 5 | On hold |  | 11 | DECEMBER
T-752-11405 | PS5-04-OB-2682A | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-02-24 | PS5-03-02 | PS5 - Milestone D | 3 | Closed | 25 | 41 | FEBRUARY
T-686-11406 | PS5-43-UR-9659B | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-07-23 | PS5-04-03 | PS5 - Milestone C | 2 | Closed | 31 | 8 | JULY
T-707-11407 | PS5-62-UR-1332D | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | To be completed |  | 26 | AUGUST
T-221-11408 | PS5-88-OB-8328B | CQE04 - Transformer | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-05-14 | PS5-99-01 | PS5 - Milestone B | 1.1 | Closed | 8 | 9 | MAY
T-571-11409 | PS5-14-OB-5633A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone C | 2 | In progress |  | 16 | SEPTEMBER
T-763-11410 | PS5-01-OB-5788C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-04-02 | PS5-62-01 | PS5 - Milestone F | 5 | Closed | 47 | 16 | APRIL
T-285-11411 | PS5-52-OB-2113A | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone C | 2 | On hold |  | 17 | AUGUST
T-659-11412 | PS5-95-IK-1142B | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone I | 8 | To be completed |  | 19 | DECEMBER
T-054-11413 | PS5-43-OB-2651A | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone E | 4 | To be completed |  | 18 | NOVEMBER
T-587-11414 | PS5-69-IK-4680D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone B | 1.1 | In progress |  | 17 | OCTOBER
T-900-11415 | PS5-80-IK-3228A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | On hold |  | 7 | SEPTEMBER
T-581-11416 | PS5-89-UR-6290B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | To be completed |  | 35 | SEPTEMBER
T-388-11417 | PS5-39-UR-2496A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone D | 3 | To be completed |  | 26 | DECEMBER
T-042-11418 | PS5-90-UR-4826A | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-11-02 | PS5-61-07 | PS5 - Milestone A | 1 | Closed | 35 | 30 | NOVEMBER
T-486-11419 | PS5-54-UR-2240B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-03-22 | PS5-06-01 | PS5 - Milestone F | 5 | Closed | 48 | 46 | MARCH
T-342-11420 | PS5-80-IK-3256C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-01-15 | PS5-09-01 | PS5 - Milestone H | 7 | Closed | 34 | 42 | JANUARY
T-987-11421 | PS5-21-OB-2474B | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone I | 8 | In progress |  | 32 | OCTOBER
T-918-11422 | PS5-86-UR-2156A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone G | 6 | On hold |  | 13 | NOVEMBER
T-453-11423 | PS5-55-IK-8141D | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone C | 2 | To be completed |  | 17 | SEPTEMBER
T-996-11424 | PS5-88-UR-9055B | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | In progress |  | 23 | OCTOBER
T-492-11425 | PS5-94-OB-3541B | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone G | 6 | To be completed |  | 6 | SEPTEMBER
T-163-11426 | PS5-27-OB-6474A | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-08-26 | PS5-11-02 | PS5 - Milestone I | 8 | Closed | 41 | 28 | AUGUST
T-243-11427 | PS5-15-IK-1361C | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | In progress |  | 29 | SEPTEMBER
T-423-11428 | PS5-22-IK-1051B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone I | 8 | In progress |  | 23 | AUGUST
T-114-11429 | PS5-05-OB-3196C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-04-14 | PS5-11-03 | PS5 - Milestone A | 1 | Closed | 45 | 48 | APRIL
T-877-11430 | PS5-58-UR-3072B | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-11-02 | PS5-07-03 | PS5 - Milestone D | 3 | Closed | 24 | 12 | NOVEMBER
T-488-11431 | PS5-62-OB-2102A | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone B | 1.1 | To be completed |  | 29 | DECEMBER
T-741-11432 | PS5-05-OB-2535B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-10-17 | PS5-06-02 | PS5 - Milestone F | 5 | Closed | 47 | 23 | OCTOBER
T-138-11433 | PS5-69-UR-4299D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone C | 2 | To be completed |  | 7 | DECEMBER
T-071-11434 | PS5-42-UR-2631A | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone F | 5 | In progress |  | 18 | AUGUST
T-047-11435 | PS5-91-OB-6698D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-09-09 | PS5-01-08 | PS5 - Milestone F | 5 | Closed | 40 | 46 | SEPTEMBER
T-100-11436 | PS5-83-IK-5704B | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-04-24 | PS5-01-09 | PS5 - Milestone C | 2 | Closed | 9 | 9 | APRIL
T-717-11437 | PS5-06-IK-5145D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone I | 8 | To be completed |  | 20 | OCTOBER
T-116-11438 | PS5-67-OB-3535D | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone G | 6 | On hold |  | 30 | NOVEMBER
T-764-11439 | PS5-14-OB-1326C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-05-27 | PS5-10-02 | PS5 - Milestone E | 4 | Closed | 34 | 41 | MAY
T-371-11440 | PS5-11-OB-4685D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-12-15 | PS5-07-02 | PS5 - Milestone A | 1 | Closed | 22 | 9 | DECEMBER
T-307-11441 | PS5-54-IK-5028D | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone G | 6 | In progress |  | 23 | SEPTEMBER
T-146-11442 | PS5-03-OB-6068C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | To be completed |  | 46 | AUGUST
T-170-11443 | PS5-24-UR-8149B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-08-28 | PS5-01-01 | PS5 - Milestone I | 8 | Closed | 13 | 41 | AUGUST
T-205-11444 | PS5-07-OB-6833B | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone A | 1 | To be completed |  | 6 | DECEMBER
T-787-11445 | PS5-37-UR-7420C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | In progress |  | 27 | OCTOBER
T-416-11446 | PS5-85-UR-7456A | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-06-25 | PS5-10-03 | PS5 - Milestone A | 1 | Closed | 33 | 19 | JUNE
T-309-11447 | PS5-49-UR-5591C | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | To be completed |  | 33 | NOVEMBER
T-846-11448 | PS5-69-UR-8561C | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | To be completed |  | 41 | SEPTEMBER
T-131-11449 | PS5-13-OB-4597C | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone C | 2 | To be completed |  | 21 | DECEMBER
T-877-11450 | PS5-32-OB-5335A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-02-05 | PS5-63-04 | PS5 - Milestone A | 1 | Closed | 28 | 35 | FEBRUARY
T-677-11451 | PS5-12-OB-3562B | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-01-27 | PS5-01-09 | PS5 - Milestone C | 2 | Closed | 17 | 33 | JANUARY
T-856-11452 | PS5-35-OB-1218D | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone E | 4 | To be completed |  | 21 | NOVEMBER
T-667-11453 | PS5-98-OB-3622B | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone H | 7 | To be completed |  | 20 | OCTOBER
T-262-11454 | PS5-47-IK-1273A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone A | 1 | On hold |  | 22 | DECEMBER
T-698-11455 | PS5-12-OB-1531B | CQP04 - Hydrotest | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-11-13 | PS5-01-03 | PS5 - Milestone I | 8 | Closed | 41 | 25 | NOVEMBER
T-856-11456 | PS5-18-OB-7743B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone B | 1.1 | To be completed |  | 46 | DECEMBER
T-926-11457 | PS5-38-IK-7011A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-08-17 | PS5-11-03 | PS5 - Milestone F | 5 | Closed | 5 | 10 | AUGUST
T-957-11458 | PS5-97-OB-4577D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | To be completed |  | 15 | NOVEMBER
T-898-11459 | PS5-37-UR-8030A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | To be completed |  | 40 | SEPTEMBER
T-462-11460 | PS5-67-IK-1382B | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone B | 1.1 | To be completed |  | 13 | NOVEMBER
T-050-11461 | PS5-82-OB-2352A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | In progress |  | 8 | OCTOBER
T-972-11462 | PS5-51-OB-8078C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone G | 6 | To be completed |  | 6 | AUGUST
T-992-11463 | PS5-21-OB-9830B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone H | 7 | To be completed |  | 22 | DECEMBER
T-102-11464 | PS5-06-OB-3941C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | In progress |  | 10 | NOVEMBER
T-706-11465 | PS5-91-OB-9067B | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-11-08 | PS5-01-07 | PS5 - Milestone A | 1 | Closed | 8 | 19 | NOVEMBER
T-722-11466 | PS5-93-IK-7418B | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-11-12 | PS5-10-05 | PS5 - Milestone I | 8 | Closed | 44 | 37 | NOVEMBER
T-894-11467 | PS5-16-OB-2947B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone A | 1 | To be completed |  | 38 | AUGUST
T-323-11468 | PS5-06-IK-3192A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone I | 8 | In progress |  | 47 | SEPTEMBER
T-147-11469 | PS5-90-OB-9097D | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-07-27 | PS5-10-04 | PS5 - Milestone A | 1 | Closed | 5 | 20 | JULY
T-601-11470 | PS5-02-OB-7506B | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-06-19 | PS5-01-01 | PS5 - Milestone F | 5 | Closed | 9 | 17 | JUNE
T-510-11471 | PS5-09-OB-9088B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone D | 3 | On hold |  | 6 | NOVEMBER
T-161-11472 | PS5-97-OB-6024C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone E | 4 | In progress |  | 11 | SEPTEMBER
T-371-11473 | PS5-37-UR-4318B | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-08-12 | PS5-09-03 | PS5 - Milestone A | 1 | Closed | 46 | 47 | AUGUST
T-707-11474 | PS5-86-OB-5190C | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-05-11 | PS5-10-05 | PS5 - Milestone F | 5 | Closed | 24 | 47 | MAY
T-115-11475 | PS5-23-OB-2722C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone F | 5 | To be completed |  | 47 | OCTOBER
T-722-11476 | PS5-59-IK-8986D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone H | 7 | To be completed |  | 4 | DECEMBER
T-387-11477 | PS5-57-UR-4595D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone I | 8 | On hold |  | 40 | DECEMBER
T-294-11478 | PS5-87-OB-8148C | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | To be completed |  | 45 | DECEMBER
T-959-11479 | PS5-18-OB-3213D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone B | 1.1 | To be completed |  | 13 | AUGUST
T-757-11480 | PS5-32-IK-5364A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone I | 8 | To be completed |  | 42 | SEPTEMBER
T-057-11481 | PS5-76-OB-6427D | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-04-12 | PS5-06-01 | PS5 - Milestone A | 1 | Closed | 48 | 21 | APRIL
T-881-11482 | PS5-26-OB-6678B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone I | 8 | In progress |  | 45 | OCTOBER
T-216-11483 | PS5-11-UR-2643A | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone H | 7 | On hold |  | 48 | AUGUST
T-353-11484 | PS5-67-OB-1631C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone C | 2 | To be completed |  | 20 | AUGUST
T-227-11485 | PS5-97-OB-5360D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone C | 2 | In progress |  | 30 | DECEMBER
T-890-11486 | PS5-67-UR-9744A | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone H | 7 | On hold |  | 20 | SEPTEMBER
T-575-11487 | PS5-53-UR-6752C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone I | 8 | On hold |  | 40 | OCTOBER
T-608-11488 | PS5-79-IK-6780C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-07-16 | PS5-04-03 | PS5 - Milestone F | 5 | Closed | 17 | 48 | JULY
T-772-11489 | PS5-11-UR-3736D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-05-07 | PS5-05-03 | PS5 - Milestone E | 4 | Closed | 27 | 30 | MAY
T-584-11490 | PS5-39-UR-5294B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone C | 2 | To be completed |  | 40 | OCTOBER
T-961-11491 | PS5-78-OB-2743C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | To be completed |  | 36 | OCTOBER
T-527-11492 | PS5-95-OB-6263D | CQS01 - Fire Protection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone I | 8 | To be completed |  | 21 | AUGUST
T-319-11493 | PS5-05-OB-7384B | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone H | 7 | To be completed |  | 37 | OCTOBER
T-355-11494 | PS5-50-OB-3478B | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone A | 1 | To be completed |  | 34 | SEPTEMBER
T-246-11495 | PS5-34-IK-7766C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-12-01 | PS5-02-03 | PS5 - Milestone F | 5 | Closed | 9 | 29 | DECEMBER
T-612-11496 | PS5-55-UR-6086C | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-10-27 | PS5-10-01 | PS5 - Milestone D | 3 | Closed | 30 | 26 | OCTOBER
T-443-11497 | PS5-01-OB-2680D | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone G | 6 | To be completed |  | 5 | NOVEMBER
T-789-11498 | PS5-43-OB-6923A | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone A | 1 | In progress |  | 12 | DECEMBER
T-229-11499 | PS5-48-OB-9682C | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone F | 5 | To be completed |  | 19 | NOVEMBER
T-573-11500 | PS5-39-OB-4233C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone F | 5 | In progress |  | 48 | OCTOBER
T-973-11501 | PS5-35-UR-6812B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone G | 6 | To be completed |  | 5 | OCTOBER
T-086-11502 | PS5-31-OB-4007C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-05-21 | PS5-12-01 | PS5 - Milestone B | 1.1 | Closed | 36 | 47 | MAY
T-548-11503 | PS5-80-OB-2893D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone G | 6 | On hold |  | 10 | OCTOBER
T-698-11504 | PS5-49-UR-9639A | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone C | 2 | To be completed |  | 6 | SEPTEMBER
T-756-11505 | PS5-72-IK-3040B | CQS02 - Gas Detection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | To be completed |  | 19 | NOVEMBER
T-431-11506 | PS5-86-UR-7299B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone D | 3 | To be completed |  | 38 | SEPTEMBER
T-419-11507 | PS5-18-IK-2230C | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-07-23 | PS5-01-04 | PS5 - Milestone A | 1 | Closed | 12 | 40 | JULY
T-627-11508 | PS5-68-IK-5934A | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | To be completed |  | 39 | AUGUST
T-244-11509 | PS5-51-OB-7550C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | In progress |  | 16 | OCTOBER
T-628-11510 | PS5-37-OB-5931B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-10-25 | PS5-01-03 | PS5 - Milestone C | 2 | Closed | 21 | 20 | OCTOBER
T-457-11511 | PS5-37-OB-5205C | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | To be completed |  | 31 | AUGUST
T-975-11512 | PS5-89-OB-6043C | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone D | 3 | To be completed |  | 4 | SEPTEMBER
T-708-11513 | PS5-53-OB-6233C | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-02-19 | PS5-08-01 | PS5 - Milestone I | 8 | Closed | 37 | 5 | FEBRUARY
T-732-11514 | PS5-90-OB-7548D | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | On hold |  | 32 | DECEMBER
T-352-11515 | PS5-02-OB-7305C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | To be completed |  | 25 | NOVEMBER
T-010-11516 | PS5-48-OB-3822C | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone C | 2 | On hold |  | 48 | AUGUST
T-779-11517 | PS5-66-OB-2532C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-04-23 | PS5-07-03 | PS5 - Milestone A | 1 | Closed | 32 | 8 | APRIL
T-327-11518 | PS5-22-OB-5629A | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone I | 8 | To be completed |  | 35 | NOVEMBER
T-065-11519 | PS5-16-UR-4224A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone H | 7 | On hold |  | 40 | NOVEMBER
T-799-11520 | PS5-55-OB-3982C | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-08-05 | PS5-05-01 | PS5 - Milestone G | 6 | Closed | 37 | 31 | AUGUST
T-263-11521 | PS5-24-OB-8049D | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone G | 6 | In progress |  | 47 | SEPTEMBER
T-899-11522 | PS5-48-OB-9666B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-01-12 | PS5-10-05 | PS5 - Milestone F | 5 | Closed | 46 | 27 | JANUARY
T-278-11523 | PS5-63-UR-9647B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-11-11 | PS5-04-03 | PS5 - Milestone E | 4 | Closed | 12 | 39 | NOVEMBER
T-094-11524 | PS5-52-OB-7320C | CQE01 - HV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone H | 7 | In progress |  | 48 | DECEMBER
T-842-11525 | PS5-43-IK-1725D | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-09-21 | PS5-99-01 | PS5 - Milestone H | 7 | Closed | 12 | 9 | SEPTEMBER
T-437-11526 | PS5-25-OB-5520B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone I | 8 | To be completed |  | 11 | SEPTEMBER
T-879-11527 | PS5-82-IK-6181B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | To be completed |  | 27 | NOVEMBER
T-830-11528 | PS5-52-OB-5931A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | To be completed |  | 37 | OCTOBER
T-315-11529 | PS5-01-IK-3574C | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-03-27 | PS5-04-01 | PS5 - Milestone F | 5 | Closed | 33 | 26 | MARCH
T-961-11530 | PS5-96-OB-3898D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-07-26 | PS5-10-03 | PS5 - Milestone G | 6 | Closed | 43 | 10 | JULY
T-626-11531 | PS5-36-IK-9695B | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-01-15 | PS5-07-04 | PS5 - Milestone A | 1 | Closed | 26 | 33 | JANUARY
T-127-11532 | PS5-54-UR-1591C | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-04-20 | PS5-03-02 | PS5 - Milestone C | 2 | Closed | 40 | 32 | APRIL
T-932-11533 | PS5-25-IK-4244D | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone G | 6 | To be completed |  | 35 | DECEMBER
T-264-11534 | PS5-03-IK-1759B | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | In progress |  | 40 | SEPTEMBER
T-810-11535 | PS5-09-IK-6840A | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-01-02 | PS5-62-01 | PS5 - Milestone E | 4 | Closed | 45 | 35 | JANUARY
T-409-11536 | PS5-82-UR-7676C | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone D | 3 | To be completed |  | 48 | AUGUST
T-183-11537 | PS5-26-UR-4705A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-01-16 | PS5-06-01 | PS5 - Milestone H | 7 | Closed | 37 | 34 | JANUARY
T-671-11538 | PS5-88-UR-8930D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-01-08 | PS5-10-02 | PS5 - Milestone E | 4 | Closed | 23 | 24 | JANUARY
T-695-11539 | PS5-91-IK-1237C | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-10-07 | PS5-05-02 | PS5 - Milestone E | 4 | Closed | 38 | 22 | OCTOBER
T-676-11540 | PS5-09-IK-6753D | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-02-21 | PS5-09-02 | PS5 - Milestone C | 2 | Closed | 14 | 46 | FEBRUARY
T-746-11541 | PS5-38-OB-6621D | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | To be completed |  | 8 | NOVEMBER
T-629-11542 | PS5-68-IK-6873C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone C | 2 | In progress |  | 12 | DECEMBER
T-998-11543 | PS5-94-UR-7702C | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone G | 6 | In progress |  | 16 | SEPTEMBER
T-908-11544 | PS5-63-UR-4148A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone A | 1 | To be completed |  | 23 | OCTOBER
T-705-11545 | PS5-64-IK-6361B | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone H | 7 | On hold |  | 15 | NOVEMBER
T-844-11546 | PS5-47-IK-3410C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone C | 2 | To be completed |  | 17 | OCTOBER
T-297-11547 | PS5-42-IK-4025D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone C | 2 | In progress |  | 11 | OCTOBER
T-925-11548 | PS5-15-OB-5809D | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-10-22 | PS5-06-02 | PS5 - Milestone H | 7 | Closed | 13 | 34 | OCTOBER
T-178-11549 | PS5-94-OB-4518A | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone A | 1 | On hold |  | 45 | OCTOBER
T-897-11550 | PS5-09-OB-3796A | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone C | 2 | To be completed |  | 27 | DECEMBER
T-697-11551 | PS5-68-OB-4848B | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-02-17 | PS5-04-03 | PS5 - Milestone H | 7 | Closed | 40 | 21 | FEBRUARY
T-758-11552 | PS5-26-IK-5818D | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone H | 7 | In progress |  | 16 | DECEMBER
T-834-11553 | PS5-68-IK-4426B | CQM01 - Pump Installation | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | On hold |  | 26 | AUGUST
T-518-11554 | PS5-09-OB-9971B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone A | 1 | On hold |  | 9 | AUGUST
T-686-11555 | PS5-65-OB-3978B | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-01-25 | PS5-05-03 | PS5 - Milestone E | 4 | Closed | 20 | 34 | JANUARY
T-648-11556 | PS5-02-UR-1563C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone C | 2 | In progress |  | 46 | NOVEMBER
T-214-11557 | PS5-57-OB-6309D | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-12-24 | PS5-61-02 | PS5 - Milestone D | 3 | Closed | 8 | 44 | DECEMBER
T-061-11558 | PS5-77-OB-2761A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone D | 3 | In progress |  | 33 | NOVEMBER
T-636-11559 | PS5-21-UR-1719B | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone A | 1 | To be completed |  | 30 | DECEMBER
T-259-11560 | PS5-73-OB-2416C | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-08-10 | PS5-06-01 | PS5 - Milestone B | 1.1 | Closed | 6 | 39 | AUGUST
T-770-11561 | PS5-80-OB-8169C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone I | 8 | In progress |  | 15 | AUGUST
T-238-11562 | PS5-56-OB-3959B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-10-06 | PS5-01-02 | PS5 - Milestone B | 1.1 | Closed | 6 | 34 | OCTOBER
T-968-11563 | PS5-03-OB-8276D | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-12-03 | PS5-04-02 | PS5 - Milestone F | 5 | Closed | 37 | 20 | DECEMBER
T-101-11564 | PS5-25-IK-9613D | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | On hold |  | 37 | NOVEMBER
T-452-11565 | PS5-67-OB-6767C | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-02-04 | PS5-09-04 | PS5 - Milestone D | 3 | Closed | 44 | 43 | FEBRUARY
T-986-11566 | PS5-61-IK-4815D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | To be completed |  | 14 | SEPTEMBER
T-578-11567 | PS5-44-OB-1900B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-11-11 | PS5-82-01 | PS5 - Milestone I | 8 | Closed | 20 | 7 | NOVEMBER
T-095-11568 | PS5-65-OB-3489C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone I | 8 | To be completed |  | 37 | NOVEMBER
T-566-11569 | PS5-70-OB-4760D | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone C | 2 | On hold |  | 31 | NOVEMBER
T-409-11570 | PS5-32-UR-6985D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-14 | PS5-60-01 | PS5 - Milestone B | 1.1 | Closed | 30 | 31 | JUNE
T-237-11571 | PS5-32-OB-8499A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone F | 5 | In progress |  | 20 | NOVEMBER
T-956-11572 | PS5-51-OB-7972D | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone F | 5 | To be completed |  | 33 | AUGUST
T-944-11573 | PS5-05-OB-6174D | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-07-14 | PS5-07-01 | PS5 - Milestone E | 4 | Closed | 23 | 28 | JULY
T-594-11574 | PS5-83-IK-7659C | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-07-20 | PS5-02-03 | PS5 - Milestone I | 8 | Closed | 36 | 17 | JULY
T-030-11575 | PS5-47-IK-1547D | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-12-23 | PS5-10-05 | PS5 - Milestone D | 3 | Closed | 23 | 43 | DECEMBER
T-023-11576 | PS5-85-OB-3538B | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone F | 5 | To be completed |  | 4 | SEPTEMBER
T-437-11577 | PS5-65-OB-1804A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone E | 4 | In progress |  | 6 | SEPTEMBER
T-069-11578 | PS5-88-OB-9990A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone F | 5 | In progress |  | 21 | OCTOBER
T-425-11579 | PS5-34-IK-8887C | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | To be completed |  | 7 | OCTOBER
T-614-11580 | PS5-76-IK-7364C | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-06-18 | PS5-06-03 | PS5 - Milestone B | 1.1 | Closed | 39 | 37 | JUNE
T-180-11581 | PS5-83-OB-6627C | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-11-17 | PS5-05-01 | PS5 - Milestone F | 5 | Closed | 45 | 10 | NOVEMBER
T-771-11582 | PS5-20-OB-7735C | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-01-21 | PS5-08-02 | PS5 - Milestone D | 3 | Closed | 35 | 23 | JANUARY
T-093-11583 | PS5-54-OB-2936C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-06-13 | PS5-13-01 | PS5 - Milestone H | 7 | Closed | 26 | 5 | JUNE
T-030-11584 | PS5-29-IK-8787A | CQM04 - Vessel | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone H | 7 | To be completed |  | 24 | AUGUST
T-162-11585 | PS5-43-OB-1479C | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-04-14 | PS5-99-03 | PS5 - Milestone G | 6 | Closed | 14 | 37 | APRIL
T-841-11586 | PS5-27-OB-6399C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-06-03 | PS5-10-01 | PS5 - Milestone E | 4 | Closed | 20 | 47 | JUNE
T-262-11587 | PS5-35-UR-2908D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-09-04 | PS5-99-02 | PS5 - Milestone A | 1 | Closed | 5 | 6 | SEPTEMBER
T-940-11588 | PS5-68-IK-5604B | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone I | 8 | To be completed |  | 47 | NOVEMBER
T-896-11589 | PS5-22-OB-6294D | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone A | 1 | To be completed |  | 47 | SEPTEMBER
T-703-11590 | PS5-42-IK-2566B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone D | 3 | To be completed |  | 7 | NOVEMBER
T-693-11591 | PS5-78-OB-2186D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-02-26 | PS5-09-02 | PS5 - Milestone A | 1 | Closed | 19 | 18 | FEBRUARY
T-435-11592 | PS5-63-UR-3269D | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone B | 1.1 | In progress |  | 41 | SEPTEMBER
T-473-11593 | PS5-70-OB-5127A | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone C | 2 | On hold |  | 39 | OCTOBER
T-726-11594 | PS5-63-UR-4202C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-12-12 | PS5-01-06 | PS5 - Milestone H | 7 | Closed | 40 | 45 | DECEMBER
T-521-11595 | PS5-02-OB-4126A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-03-04 | PS5-61-07 | PS5 - Milestone G | 6 | Closed | 48 | 42 | MARCH
T-963-11596 | PS5-59-IK-5244C | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-06-22 | PS5-07-01 | PS5 - Milestone H | 7 | Closed | 40 | 16 | JUNE
T-176-11597 | PS5-80-IK-4021D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone B | 1.1 | To be completed |  | 46 | AUGUST
T-260-11598 | PS5-94-UR-2921A | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-08-06 | PS5-09-01 | PS5 - Milestone A | 1 | Closed | 47 | 15 | AUGUST
T-847-11599 | PS5-59-OB-9283C | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-08-12 | PS5-01-02 | PS5 - Milestone E | 4 | Closed | 30 | 47 | AUGUST
T-638-11600 | PS5-85-OB-1105A | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone A | 1 | On hold |  | 15 | DECEMBER
T-636-11601 | PS5-46-UR-1526D | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-11-18 | PS5-60-04 | PS5 - Milestone A | 1 | Closed | 37 | 13 | NOVEMBER
T-015-11602 | PS5-13-IK-4842C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-03-27 | PS5-09-01 | PS5 - Milestone E | 4 | Closed | 20 | 36 | MARCH
T-861-11603 | PS5-64-OB-4674D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-01-01 | PS5-99-02 | PS5 - Milestone A | 1 | Closed | 18 | 35 | JANUARY
T-583-11604 | PS5-68-IK-9504D | CQE01 - HV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-04-13 | PS5-61-01 | PS5 - Milestone C | 2 | Closed | 29 | 25 | APRIL
T-356-11605 | PS5-72-OB-6481D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-07-14 | PS5-03-01 | PS5 - Milestone I | 8 | Closed | 16 | 32 | JULY
T-466-11606 | PS5-12-UR-6747B | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-03-16 | PS5-01-03 | PS5 - Milestone A | 1 | Closed | 43 | 27 | MARCH
T-292-11607 | PS5-14-UR-9114B | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone I | 8 | To be completed |  | 21 | AUGUST
T-396-11608 | PS5-80-OB-6389D | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone I | 8 | To be completed |  | 29 | DECEMBER
T-992-11609 | PS5-96-OB-4549B | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone F | 5 | To be completed |  | 40 | AUGUST
T-026-11610 | PS5-59-IK-6883A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-12-04 | PS5-02-01 | PS5 - Milestone I | 8 | Closed | 30 | 34 | DECEMBER
T-974-11611 | PS5-82-IK-1602B | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone F | 5 | To be completed |  | 16 | AUGUST
T-779-11612 | PS5-10-IK-2636B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-12-01 | PS5-01-07 | PS5 - Milestone I | 8 | Closed | 30 | 42 | DECEMBER
T-608-11613 | PS5-63-IK-6962D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | To be completed |  | 25 | AUGUST
T-564-11614 | PS5-04-OB-4744C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | To be completed |  | 18 | DECEMBER
T-758-11615 | PS5-92-IK-6292C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-09 | PS5-60-04 | PS5 - Milestone A | 1 | Closed | 26 | 12 | FEBRUARY
T-097-11616 | PS5-91-OB-7710A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-04-01 | PS5-61-01 | PS5 - Milestone C | 2 | Closed | 8 | 42 | APRIL
T-026-11617 | PS5-16-IK-4890B | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone G | 6 | On hold |  | 40 | NOVEMBER
T-050-11618 | PS5-66-UR-3792C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-09-21 | PS5-13-01 | PS5 - Milestone C | 2 | Closed | 28 | 8 | SEPTEMBER
T-046-11619 | PS5-40-IK-1391C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-09-18 | PS5-09-02 | PS5 - Milestone F | 5 | Closed | 10 | 13 | SEPTEMBER
T-918-11620 | PS5-32-UR-4708B | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-01-01 | PS5-03-01 | PS5 - Milestone B | 1.1 | Closed | 18 | 33 | JANUARY
T-540-11621 | PS5-61-IK-9689D | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone H | 7 | In progress |  | 45 | OCTOBER
T-160-11622 | PS5-78-OB-9037A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-08-28 | PS5-09-04 | PS5 - Milestone A | 1 | Closed | 24 | 7 | AUGUST
T-809-11623 | PS5-77-IK-7032C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | In progress |  | 10 | NOVEMBER
T-722-11624 | PS5-07-IK-7342D | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-01-21 | PS5-01-06 | PS5 - Milestone E | 4 | Closed | 5 | 41 | JANUARY
T-167-11625 | PS5-13-IK-8078B | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-02-08 | PS5-04-01 | PS5 - Milestone I | 8 | Closed | 23 | 14 | FEBRUARY
T-160-11626 | PS5-73-OB-9312A | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-01-27 | PS5-01-08 | PS5 - Milestone D | 3 | Closed | 22 | 19 | JANUARY
T-154-11627 | PS5-67-UR-9772B | CQX01 - Steel Structure | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone C | 2 | On hold |  | 21 | NOVEMBER
T-867-11628 | PS5-63-OB-6484D | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone E | 4 | In progress |  | 39 | AUGUST
T-573-11629 | PS5-71-OB-4329D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone H | 7 | On hold |  | 29 | AUGUST
T-921-11630 | PS5-85-OB-5260B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-12-25 | PS5-08-02 | PS5 - Milestone A | 1 | Closed | 18 | 24 | DECEMBER
T-242-11631 | PS5-10-OB-7609B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | To be completed |  | 28 | OCTOBER
T-959-11632 | PS5-05-IK-4689A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone E | 4 | In progress |  | 39 | DECEMBER
T-260-11633 | PS5-96-OB-4193B | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone D | 3 | To be completed |  | 20 | NOVEMBER
T-842-11634 | PS5-65-OB-4984D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-04-04 | PS5-04-03 | PS5 - Milestone F | 5 | Closed | 30 | 19 | APRIL
T-713-11635 | PS5-37-OB-4130B | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone H | 7 | In progress |  | 25 | DECEMBER
T-466-11636 | PS5-93-IK-6660C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone E | 4 | To be completed |  | 32 | AUGUST
T-477-11637 | PS5-73-OB-1615D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | To be completed |  | 42 | DECEMBER
T-305-11638 | PS5-39-OB-6033B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | To be completed |  | 31 | NOVEMBER
T-412-11639 | PS5-03-IK-3698B | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-04-05 | PS5-04-04 | PS5 - Milestone F | 5 | Closed | 4 | 10 | APRIL
T-771-11640 | PS5-79-OB-6816D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-06-22 | PS5-61-01 | PS5 - Milestone E | 4 | Closed | 7 | 14 | JUNE
T-439-11641 | PS5-45-UR-1348D | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone B | 1.1 | To be completed |  | 45 | DECEMBER
T-865-11642 | PS5-49-OB-7242B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone B | 1.1 | To be completed |  | 39 | NOVEMBER
T-428-11643 | PS5-08-OB-3752A | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone I | 8 | In progress |  | 36 | AUGUST
T-863-11644 | PS5-28-OB-7680D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone G | 6 | On hold |  | 34 | AUGUST
T-296-11645 | PS5-05-IK-2756C | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-06-26 | PS5-01-04 | PS5 - Milestone I | 8 | Closed | 5 | 35 | JUNE
T-274-11646 | PS5-75-OB-6240C | CQM03 - Heat Exchanger | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone A | 1 | To be completed |  | 44 | NOVEMBER
T-141-11647 | PS5-56-UR-8222A | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-01-04 | PS5-63-04 | PS5 - Milestone H | 7 | Closed | 10 | 45 | JANUARY
T-867-11648 | PS5-62-OB-1542B | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone H | 7 | To be completed |  | 47 | AUGUST
T-067-11649 | PS5-79-OB-7636C | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-02-09 | PS5-13-01 | PS5 - Milestone E | 4 | Closed | 44 | 31 | FEBRUARY
T-401-11650 | PS5-87-OB-4522D | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone C | 2 | In progress |  | 33 | DECEMBER
T-816-11651 | PS5-75-IK-2449D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-02-12 | PS5-01-06 | PS5 - Milestone H | 7 | Closed | 35 | 17 | FEBRUARY
T-798-11652 | PS5-51-OB-6834B | CQP05 - Insulation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-04-22 | PS5-04-04 | PS5 - Milestone B | 1.1 | Closed | 7 | 48 | APRIL
T-270-11653 | PS5-90-OB-8268D | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone E | 4 | To be completed |  | 33 | NOVEMBER
T-245-11654 | PS5-78-IK-1752C | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | In progress |  | 29 | SEPTEMBER
T-800-11655 | PS5-53-IK-1720A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | To be completed |  | 24 | AUGUST
T-225-11656 | PS5-94-OB-3722B | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone C | 2 | To be completed |  | 9 | SEPTEMBER
T-682-11657 | PS5-70-UR-3579B | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-05-02 | PS5-99-01 | PS5 - Milestone D | 3 | Closed | 47 | 42 | MAY
T-836-11658 | PS5-37-OB-6280D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-04-20 | PS5-05-01 | PS5 - Milestone E | 4 | Closed | 4 | 46 | APRIL
T-469-11659 | PS5-48-OB-2596B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-10-04 | PS5-05-02 | PS5 - Milestone G | 6 | Closed | 45 | 47 | OCTOBER
T-105-11660 | PS5-31-OB-9034A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone C | 2 | To be completed |  | 26 | OCTOBER
T-028-11661 | PS5-08-IK-7478A | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-01-20 | PS5-12-02 | PS5 - Milestone E | 4 | Closed | 28 | 48 | JANUARY
T-726-11662 | PS5-05-OB-4445D | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-08-26 | PS5-99-02 | PS5 - Milestone D | 3 | Closed | 7 | 46 | AUGUST
T-294-11663 | PS5-68-OB-9776B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone I | 8 | In progress |  | 46 | DECEMBER
T-595-11664 | PS5-18-UR-8328A | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-10-02 | PS5-03-02 | PS5 - Milestone F | 5 | Closed | 32 | 27 | OCTOBER
T-522-11665 | PS5-56-OB-8576B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | On hold |  | 16 | AUGUST
T-338-11666 | PS5-09-OB-2272C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone F | 5 | In progress |  | 9 | AUGUST
T-745-11667 | PS5-66-OB-7722B | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-11-21 | PS5-10-05 | PS5 - Milestone D | 3 | Closed | 30 | 17 | NOVEMBER
T-113-11668 | PS5-35-IK-2757C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone B | 1.1 | On hold |  | 45 | NOVEMBER
T-993-11669 | PS5-27-OB-5895A | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-09-03 | PS5-08-02 | PS5 - Milestone H | 7 | Closed | 37 | 11 | SEPTEMBER
T-862-11670 | PS5-42-OB-1890C | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone G | 6 | To be completed |  | 12 | DECEMBER
T-516-11671 | PS5-44-UR-3841B | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-01-12 | PS5-05-01 | PS5 - Milestone D | 3 | Closed | 32 | 44 | JANUARY
T-982-11672 | PS5-19-OB-4312A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-02-24 | PS5-10-06 | PS5 - Milestone E | 4 | Closed | 39 | 29 | FEBRUARY
T-231-11673 | PS5-55-IK-9066B | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone A | 1 | In progress |  | 24 | OCTOBER
T-882-11674 | PS5-75-OB-7369B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-09-13 | PS5-05-03 | PS5 - Milestone H | 7 | Closed | 9 | 36 | SEPTEMBER
T-828-11675 | PS5-43-OB-2554B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | To be completed |  | 16 | OCTOBER
T-333-11676 | PS5-14-UR-1165C | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone F | 5 | To be completed |  | 37 | SEPTEMBER
T-765-11677 | PS5-29-UR-3243A | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | To be completed |  | 35 | NOVEMBER
T-112-11678 | PS5-22-UR-9719C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone B | 1.1 | To be completed |  | 26 | SEPTEMBER
T-615-11679 | PS5-55-UR-6417A | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone B | 1.1 | To be completed |  | 41 | AUGUST
T-842-11680 | PS5-42-OB-2179D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-12-13 | PS5-12-01 | PS5 - Milestone E | 4 | Closed | 15 | 42 | DECEMBER
T-310-11681 | PS5-27-UR-8334A | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone D | 3 | On hold |  | 7 | SEPTEMBER
T-507-11682 | PS5-72-IK-2714B | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-03-21 | PS5-05-03 | PS5 - Milestone H | 7 | Closed | 24 | 30 | MARCH
T-358-11683 | PS5-50-IK-9369D | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone C | 2 | On hold |  | 31 | NOVEMBER
T-079-11684 | PS5-33-IK-8508B | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | In progress |  | 43 | NOVEMBER
T-110-11685 | PS5-77-OB-3177D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone D | 3 | To be completed |  | 6 | OCTOBER
T-501-11686 | PS5-37-OB-2877B | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone D | 3 | In progress |  | 36 | SEPTEMBER
T-516-11687 | PS5-06-UR-9129C | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone B | 1.1 | In progress |  | 23 | AUGUST
T-578-11688 | PS5-15-UR-1742A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-11-12 | PS5-12-01 | PS5 - Milestone G | 6 | Closed | 33 | 22 | NOVEMBER
T-025-11689 | PS5-66-UR-5570C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-03-05 | PS5-07-03 | PS5 - Milestone E | 4 | Closed | 13 | 16 | MARCH
T-764-11690 | PS5-28-UR-6295D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-01-09 | PS5-11-01 | PS5 - Milestone H | 7 | Closed | 5 | 39 | JANUARY
T-789-11691 | PS5-82-OB-1077A | CQX04 - Painting & Coating | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-10-10 | PS5-07-02 | PS5 - Milestone I | 8 | Closed | 13 | 9 | OCTOBER
T-409-11692 | PS5-20-OB-4561C | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-11-06 | PS5-10-05 | PS5 - Milestone G | 6 | Closed | 19 | 25 | NOVEMBER
T-623-11693 | PS5-74-OB-4834D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | To be completed |  | 21 | NOVEMBER
T-357-11694 | PS5-64-OB-8235A | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone G | 6 | To be completed |  | 48 | OCTOBER
T-673-11695 | PS5-20-OB-5589C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone B | 1.1 | To be completed |  | 4 | SEPTEMBER
T-495-11696 | PS5-27-OB-2546D | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone G | 6 | In progress |  | 14 | DECEMBER
T-876-11697 | PS5-42-UR-2527B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-04-16 | PS5-82-07 | PS5 - Milestone D | 3 | Closed | 44 | 12 | APRIL
T-477-11698 | PS5-03-OB-9759C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-08-04 | PS5-04-02 | PS5 - Milestone H | 7 | Closed | 6 | 27 | AUGUST
T-509-11699 | PS5-85-IK-4572B | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-05-16 | PS5-63-04 | PS5 - Milestone A | 1 | Closed | 38 | 20 | MAY
T-774-11700 | PS5-61-OB-4527A | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone D | 3 | On hold |  | 24 | NOVEMBER
T-227-11701 | PS5-58-OB-1403B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-10-01 | PS5-09-02 | PS5 - Milestone A | 1 | Closed | 30 | 15 | OCTOBER
T-763-11702 | PS5-64-OB-5149B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | To be completed |  | 31 | OCTOBER
T-309-11703 | PS5-58-OB-8537A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone F | 5 | To be completed |  | 14 | NOVEMBER
T-006-11704 | PS5-18-UR-2565A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-08-15 | PS5-04-02 | PS5 - Milestone H | 7 | Closed | 11 | 22 | AUGUST
T-696-11705 | PS5-66-OB-8663C | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone H | 7 | In progress |  | 38 | DECEMBER
T-958-11706 | PS5-95-UR-7000A | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-11-01 | PS5-05-03 | PS5 - Milestone D | 3 | Closed | 33 | 19 | NOVEMBER
T-029-11707 | PS5-17-OB-1918B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-03-28 | PS5-03-02 | PS5 - Milestone C | 2 | Closed | 27 | 47 | MARCH
T-628-11708 | PS5-38-UR-8260B | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone H | 7 | In progress |  | 34 | SEPTEMBER
T-275-11709 | PS5-68-OB-1628D | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone C | 2 | To be completed |  | 10 | DECEMBER
T-874-11710 | PS5-57-OB-7077A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-02-25 | PS5-99-02 | PS5 - Milestone I | 8 | Closed | 34 | 20 | FEBRUARY
T-773-11711 | PS5-06-OB-2609A | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-03-23 | PS5-01-03 | PS5 - Milestone G | 6 | Closed | 13 | 18 | MARCH
T-402-11712 | PS5-60-IK-1342C | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | In progress |  | 47 | NOVEMBER
T-315-11713 | PS5-31-OB-8553C | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | To be completed |  | 5 | AUGUST
T-591-11714 | PS5-31-OB-6920D | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone A | 1 | On hold |  | 46 | DECEMBER
T-537-11715 | PS5-28-OB-4872B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-08-13 | PS5-10-03 | PS5 - Milestone C | 2 | Closed | 25 | 34 | AUGUST
T-725-11716 | PS5-60-OB-1200A | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone B | 1.1 | On hold |  | 8 | NOVEMBER
T-918-11717 | PS5-23-IK-6963C | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | In progress |  | 17 | SEPTEMBER
T-265-11718 | PS5-82-OB-5925D | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone C | 2 | To be completed |  | 48 | DECEMBER
T-180-11719 | PS5-61-OB-3321B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | To be completed |  | 39 | SEPTEMBER
T-807-11720 | PS5-19-IK-3595A | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-06-27 | PS5-63-04 | PS5 - Milestone A | 1 | Closed | 14 | 10 | JUNE
T-514-11721 | PS5-45-UR-1788A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone C | 2 | To be completed |  | 28 | AUGUST
T-453-11722 | PS5-49-UR-6076D | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-03-20 | PS5-60-04 | PS5 - Milestone C | 2 | Closed | 4 | 34 | MARCH
T-602-11723 | PS5-49-OB-2062B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone F | 5 | To be completed |  | 43 | SEPTEMBER
T-730-11724 | PS5-22-UR-3608C | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-10-09 | PS5-60-07 | PS5 - Milestone B | 1.1 | Closed | 48 | 4 | OCTOBER
T-443-11725 | PS5-78-OB-5300B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone D | 3 | To be completed |  | 40 | DECEMBER
T-330-11726 | PS5-74-UR-4261C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone E | 4 | On hold |  | 11 | DECEMBER
T-751-11727 | PS5-37-UR-3281A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-07-11 | PS5-11-02 | PS5 - Milestone C | 2 | Closed | 32 | 37 | JULY
T-307-11728 | PS5-95-UR-6814A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-09-04 | PS5-02-01 | PS5 - Milestone G | 6 | Closed | 5 | 14 | SEPTEMBER
T-045-11729 | PS5-94-OB-9571B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-02-18 | PS5-02-01 | PS5 - Milestone G | 6 | Closed | 33 | 34 | FEBRUARY
T-610-11730 | PS5-25-OB-7756D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone D | 3 | In progress |  | 9 | AUGUST
T-560-11731 | PS5-97-IK-5203D | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-12-04 | PS5-01-06 | PS5 - Milestone H | 7 | Closed | 44 | 26 | DECEMBER
T-950-11732 | PS5-62-UR-1905B | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone E | 4 | To be completed |  | 41 | SEPTEMBER
T-728-11733 | PS5-50-UR-5867C | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-09-04 | PS5-10-01 | PS5 - Milestone D | 3 | Closed | 13 | 48 | SEPTEMBER
T-566-11734 | PS5-52-OB-5942D | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-12-01 | PS5-10-04 | PS5 - Milestone H | 7 | Closed | 48 | 6 | DECEMBER
T-750-11735 | PS5-66-OB-4970D | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-06-06 | PS5-04-04 | PS5 - Milestone B | 1.1 | Closed | 12 | 8 | JUNE
T-050-11736 | PS5-36-UR-6149C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone C | 2 | In progress |  | 45 | AUGUST
T-826-11737 | PS5-30-IK-6503D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone D | 3 | To be completed |  | 41 | AUGUST
T-279-11738 | PS5-88-UR-1230A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-04-05 | PS5-01-02 | PS5 - Milestone G | 6 | Closed | 40 | 8 | APRIL
T-775-11739 | PS5-45-OB-4290A | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-09-13 | PS5-82-02 | PS5 - Milestone A | 1 | Closed | 10 | 39 | SEPTEMBER
T-096-11740 | PS5-98-OB-5304B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-03-12 | PS5-03-03 | PS5 - Milestone H | 7 | Closed | 7 | 13 | MARCH
T-278-11741 | PS5-12-OB-5587D | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-11-09 | PS5-05-02 | PS5 - Milestone B | 1.1 | Closed | 9 | 25 | NOVEMBER
T-327-11742 | PS5-18-UR-7005D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone I | 8 | In progress |  | 36 | SEPTEMBER
T-515-11743 | PS5-55-OB-6383C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone G | 6 | To be completed |  | 39 | AUGUST
T-078-11744 | PS5-79-IK-6015B | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | To be completed |  | 45 | SEPTEMBER
T-271-11745 | PS5-34-IK-1369D | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone F | 5 | To be completed |  | 24 | NOVEMBER
T-410-11746 | PS5-62-OB-3546A | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone D | 3 | In progress |  | 16 | DECEMBER
T-849-11747 | PS5-86-IK-2687C | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-02-13 | PS5-01-03 | PS5 - Milestone A | 1 | Closed | 7 | 38 | FEBRUARY
T-568-11748 | PS5-66-OB-4292C | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone E | 4 | To be completed |  | 8 | AUGUST
T-489-11749 | PS5-47-UR-7044B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-01-06 | PS5-09-01 | PS5 - Milestone G | 6 | Closed | 35 | 35 | JANUARY
T-107-11750 | PS5-30-UR-7087A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | In progress |  | 27 | SEPTEMBER
T-567-11751 | PS5-42-UR-3639C | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone F | 5 | To be completed |  | 47 | AUGUST
T-990-11752 | PS5-07-OB-9485D | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-04-10 | PS5-63-04 | PS5 - Milestone E | 4 | Closed | 7 | 40 | APRIL
T-817-11753 | PS5-52-UR-6824B | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-07-18 | PS5-08-01 | PS5 - Milestone F | 5 | Closed | 30 | 31 | JULY
T-682-11754 | PS5-73-OB-6654A | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-10-01 | PS5-04-01 | PS5 - Milestone B | 1.1 | Closed | 42 | 5 | OCTOBER
T-179-11755 | PS5-99-UR-7563C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone F | 5 | On hold |  | 25 | DECEMBER
T-106-11756 | PS5-55-OB-8817A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone A | 1 | In progress |  | 46 | SEPTEMBER
T-305-11757 | PS5-18-UR-4265D | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone D | 3 | In progress |  | 7 | AUGUST
T-311-11758 | PS5-95-IK-7291A | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone D | 3 | To be completed |  | 14 | DECEMBER
T-573-11759 | PS5-22-UR-1814C | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-07-15 | PS5-60-01 | PS5 - Milestone E | 4 | Closed | 36 | 48 | JULY
T-755-11760 | PS5-31-IK-9712A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone H | 7 | On hold |  | 35 | AUGUST
T-906-11761 | PS5-88-OB-2449C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-11-12 | PS5-10-02 | PS5 - Milestone G | 6 | Closed | 12 | 32 | NOVEMBER
T-135-11762 | PS5-52-OB-2818D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone G | 6 | To be completed |  | 13 | NOVEMBER
T-547-11763 | PS5-41-IK-5944B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone F | 5 | To be completed |  | 5 | SEPTEMBER
T-157-11764 | PS5-62-OB-6846A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone A | 1 | In progress |  | 33 | DECEMBER
T-783-11765 | PS5-46-OB-3412D | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-07-14 | PS5-11-02 | PS5 - Milestone C | 2 | Closed | 6 | 35 | JULY
T-692-11766 | PS5-99-UR-8288A | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | To be completed |  | 27 | OCTOBER
T-267-11767 | PS5-68-IK-9664C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone E | 4 | On hold |  | 17 | OCTOBER
T-527-11768 | PS5-29-OB-9446A | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone B | 1.1 | To be completed |  | 37 | AUGUST
T-274-11769 | PS5-75-UR-6182D | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone D | 3 | On hold |  | 11 | SEPTEMBER
T-827-11770 | PS5-34-IK-4665A | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone D | 3 | To be completed |  | 45 | SEPTEMBER
T-712-11771 | PS5-57-IK-2900C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone C | 2 | To be completed |  | 9 | NOVEMBER
T-655-11772 | PS5-68-IK-1797D | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone E | 4 | To be completed |  | 22 | OCTOBER
T-065-11773 | PS5-70-IK-7200B | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-11-16 | PS5-03-02 | PS5 - Milestone F | 5 | Closed | 11 | 9 | NOVEMBER
T-612-11774 | PS5-10-IK-3202B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone G | 6 | To be completed |  | 31 | DECEMBER
T-914-11775 | PS5-89-OB-7474A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-23 | PS5-60-07 | PS5 - Milestone I | 8 | Closed | 5 | 26 | JULY
T-663-11776 | PS5-83-OB-1879D | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone A | 1 | In progress |  | 25 | SEPTEMBER
T-599-11777 | PS5-58-UR-9425B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | To be completed |  | 40 | NOVEMBER
T-300-11778 | PS5-54-IK-4904B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone B | 1.1 | In progress |  | 38 | OCTOBER
T-305-11779 | PS5-05-UR-8663C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-12-07 | PS5-61-07 | PS5 - Milestone G | 6 | Closed | 25 | 19 | DECEMBER
T-809-11780 | PS5-92-IK-9151C | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone D | 3 | To be completed |  | 13 | NOVEMBER
T-256-11781 | PS5-32-IK-2107D | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone B | 1.1 | To be completed |  | 19 | OCTOBER
T-799-11782 | PS5-55-UR-5934A | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone B | 1.1 | To be completed |  | 30 | AUGUST
T-346-11783 | PS5-88-OB-4017C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone C | 2 | To be completed |  | 20 | SEPTEMBER
T-247-11784 | PS5-03-IK-9979D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone B | 1.1 | In progress |  | 27 | NOVEMBER
T-650-11785 | PS5-81-UR-9501A | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone A | 1 | In progress |  | 34 | OCTOBER
T-400-11786 | PS5-10-OB-8980C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | In progress |  | 48 | AUGUST
T-752-11787 | PS5-76-UR-9361B | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-11-23 | PS5-01-06 | PS5 - Milestone E | 4 | Closed | 32 | 37 | NOVEMBER
T-297-11788 | PS5-16-IK-8850D | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-04-13 | PS5-03-01 | PS5 - Milestone D | 3 | Closed | 41 | 35 | APRIL
T-809-11789 | PS5-24-UR-1456C | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-08-26 | PS5-61-07 | PS5 - Milestone C | 2 | Closed | 12 | 14 | AUGUST
T-670-11790 | PS5-46-OB-2373B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | In progress |  | 18 | SEPTEMBER
T-336-11791 | PS5-01-UR-6583A | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-12-22 | PS5-60-04 | PS5 - Milestone A | 1 | Closed | 12 | 30 | DECEMBER
T-299-11792 | PS5-40-OB-2774B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone B | 1.1 | In progress |  | 21 | DECEMBER
T-219-11793 | PS5-38-OB-3948A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone C | 2 | To be completed |  | 22 | OCTOBER
T-805-11794 | PS5-91-OB-3311C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone H | 7 | On hold |  | 39 | NOVEMBER
T-031-11795 | PS5-95-OB-1351A | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone D | 3 | To be completed |  | 6 | NOVEMBER
T-565-11796 | PS5-82-OB-1836B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone E | 4 | To be completed |  | 8 | OCTOBER
T-054-11797 | PS5-80-IK-5630D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-05-19 | PS5-07-02 | PS5 - Milestone C | 2 | Closed | 24 | 14 | MAY
T-053-11798 | PS5-65-IK-6108A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone F | 5 | On hold |  | 46 | NOVEMBER
T-461-11799 | PS5-51-UR-5522C | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-06-01 | PS5-01-09 | PS5 - Milestone G | 6 | Closed | 43 | 30 | JUNE
T-353-11800 | PS5-67-IK-9212A | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone C | 2 | To be completed |  | 33 | NOVEMBER
T-695-11801 | PS5-32-OB-7841C | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-03-02 | PS5-09-01 | PS5 - Milestone B | 1.1 | Closed | 43 | 42 | MARCH
T-039-11802 | PS5-89-OB-9071C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone A | 1 | To be completed |  | 9 | NOVEMBER
T-395-11803 | PS5-90-UR-2997C | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-11 | PS5-60-04 | PS5 - Milestone B | 1.1 | Closed | 41 | 35 | MAY
T-680-11804 | PS5-95-OB-2394D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-05-26 | PS5-03-03 | PS5 - Milestone B | 1.1 | Closed | 46 | 18 | MAY
T-202-11805 | PS5-16-UR-2123B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-05-08 | PS5-04-04 | PS5 - Milestone F | 5 | Closed | 39 | 46 | MAY
T-246-11806 | PS5-32-OB-1686B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone B | 1.1 | To be completed |  | 9 | AUGUST
T-043-11807 | PS5-29-IK-9495C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-11-27 | PS5-99-02 | PS5 - Milestone C | 2 | Closed | 37 | 42 | NOVEMBER
T-727-11808 | PS5-71-UR-3724A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone B | 1.1 | To be completed |  | 44 | SEPTEMBER
T-945-11809 | PS5-86-OB-3334C | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-24 | PS5-60-04 | PS5 - Milestone E | 4 | Closed | 5 | 22 | JUNE
T-973-11810 | PS5-69-IK-2199B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-09-02 | PS5-61-02 | PS5 - Milestone F | 5 | Closed | 21 | 16 | SEPTEMBER
T-904-11811 | PS5-53-UR-9432B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-02-27 | PS5-04-03 | PS5 - Milestone B | 1.1 | Closed | 27 | 16 | FEBRUARY
T-143-11812 | PS5-07-OB-4131D | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone I | 8 | In progress |  | 14 | OCTOBER
T-992-11813 | PS5-99-IK-8137A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-01-18 | PS5-60-07 | PS5 - Milestone H | 7 | Closed | 7 | 6 | JANUARY
T-028-11814 | PS5-59-OB-6644A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | In progress |  | 44 | AUGUST
T-050-11815 | PS5-54-OB-5754D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone F | 5 | To be completed |  | 31 | DECEMBER
T-003-11816 | PS5-43-OB-1803D | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-12-10 | PS5-01-07 | PS5 - Milestone F | 5 | Closed | 14 | 27 | DECEMBER
T-072-11817 | PS5-83-UR-2549B | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone C | 2 | To be completed |  | 43 | OCTOBER
T-137-11818 | PS5-18-OB-2243B | CQP04 - Hydrotest | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-02-24 | PS5-09-01 | PS5 - Milestone A | 1 | Closed | 15 | 47 | FEBRUARY
T-318-11819 | PS5-33-UR-5122B | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone A | 1 | To be completed |  | 22 | OCTOBER
T-919-11820 | PS5-90-UR-4294A | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone C | 2 | To be completed |  | 15 | NOVEMBER
T-592-11821 | PS5-37-OB-3302C | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-11-08 | PS5-03-03 | PS5 - Milestone H | 7 | Closed | 4 | 29 | NOVEMBER
T-189-11822 | PS5-63-UR-7605A | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-03 | PS5-60-04 | PS5 - Milestone A | 1 | Closed | 22 | 19 | MAY
T-594-11823 | PS5-57-OB-6810C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-02-21 | PS5-02-01 | PS5 - Milestone I | 8 | Closed | 27 | 30 | FEBRUARY
T-006-11824 | PS5-23-OB-5771A | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone C | 2 | In progress |  | 31 | AUGUST
T-687-11825 | PS5-02-UR-7726C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-11-19 | PS5-01-01 | PS5 - Milestone I | 8 | Closed | 28 | 34 | NOVEMBER
T-344-11826 | PS5-36-OB-5042B | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone D | 3 | To be completed |  | 32 | SEPTEMBER
T-503-11827 | PS5-31-IK-8173D | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-01-07 | PS5-09-01 | PS5 - Milestone G | 6 | Closed | 15 | 14 | JANUARY
T-266-11828 | PS5-85-UR-7605B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-08-08 | PS5-01-05 | PS5 - Milestone D | 3 | Closed | 12 | 44 | AUGUST
T-396-11829 | PS5-45-OB-4058B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone I | 8 | In progress |  | 29 | DECEMBER
T-566-11830 | PS5-37-OB-8499A | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone C | 2 | In progress |  | 31 | SEPTEMBER
T-518-11831 | PS5-10-OB-2706A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone A | 1 | In progress |  | 16 | AUGUST
T-081-11832 | PS5-98-IK-3848A | CQP05 - Insulation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-04-22 | PS5-63-01 | PS5 - Milestone F | 5 | Closed | 11 | 38 | APRIL
T-697-11833 | PS5-60-OB-6377B | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone F | 5 | To be completed |  | 45 | DECEMBER
T-416-11834 | PS5-45-UR-1765B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | To be completed |  | 19 | DECEMBER
T-198-11835 | PS5-69-IK-2982D | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone A | 1 | To be completed |  | 24 | DECEMBER
T-344-11836 | PS5-92-IK-4905A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone H | 7 | To be completed |  | 33 | DECEMBER
T-357-11837 | PS5-78-IK-2411C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone A | 1 | On hold |  | 16 | DECEMBER
T-483-11838 | PS5-35-OB-9445C | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone F | 5 | To be completed |  | 35 | DECEMBER
T-036-11839 | PS5-24-OB-7441A | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-05-11 | PS5-04-01 | PS5 - Milestone G | 6 | Closed | 30 | 19 | MAY
T-625-11840 | PS5-98-UR-4362A | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | In progress |  | 36 | AUGUST
T-502-11841 | PS5-85-IK-2047D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-11-15 | PS5-04-01 | PS5 - Milestone A | 1 | Closed | 19 | 5 | NOVEMBER
T-539-11842 | PS5-46-IK-4799C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-01-04 | PS5-60-10 | PS5 - Milestone H | 7 | Closed | 46 | 29 | JANUARY
T-964-11843 | PS5-61-OB-5034C | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone H | 7 | In progress |  | 28 | NOVEMBER
T-061-11844 | PS5-10-UR-5662D | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-09-12 | PS5-63-01 | PS5 - Milestone G | 6 | Closed | 38 | 8 | SEPTEMBER
T-632-11845 | PS5-85-UR-9251D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-01-27 | PS5-99-01 | PS5 - Milestone G | 6 | Closed | 43 | 22 | JANUARY
T-091-11846 | PS5-73-IK-1449C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone A | 1 | To be completed |  | 24 | DECEMBER
T-003-11847 | PS5-56-OB-6372C | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone D | 3 | To be completed |  | 6 | DECEMBER
T-806-11848 | PS5-96-OB-8827C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone I | 8 | To be completed |  | 30 | SEPTEMBER
T-192-11849 | PS5-78-UR-2255C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone E | 4 | In progress |  | 19 | NOVEMBER
T-119-11850 | PS5-71-OB-7655A | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone B | 1.1 | To be completed |  | 32 | SEPTEMBER
T-952-11851 | PS5-23-IK-7563A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone E | 4 | To be completed |  | 17 | DECEMBER
T-602-11852 | PS5-55-OB-5212D | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-09-19 | PS5-09-03 | PS5 - Milestone C | 2 | Closed | 20 | 34 | SEPTEMBER
T-187-11853 | PS5-61-OB-9581C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone C | 2 | In progress |  | 47 | AUGUST
T-733-11854 | PS5-23-UR-4701A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | In progress |  | 23 | NOVEMBER
T-252-11855 | PS5-47-OB-8905A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone C | 2 | To be completed |  | 4 | SEPTEMBER
T-381-11856 | PS5-32-OB-9405C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | To be completed |  | 42 | DECEMBER
T-803-11857 | PS5-15-OB-6268C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-11-08 | PS5-08-01 | PS5 - Milestone D | 3 | Closed | 13 | 34 | NOVEMBER
T-250-11858 | PS5-90-OB-1998B | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-08-11 | PS5-07-02 | PS5 - Milestone C | 2 | Closed | 5 | 33 | AUGUST
T-200-11859 | PS5-88-UR-9022B | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-07-23 | PS5-06-02 | PS5 - Milestone C | 2 | Closed | 18 | 26 | JULY
T-535-11860 | PS5-90-OB-6961B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone C | 2 | To be completed |  | 39 | OCTOBER
T-502-11861 | PS5-89-IK-8690B | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-03-11 | PS5-09-03 | PS5 - Milestone C | 2 | Closed | 21 | 17 | MARCH
T-819-11862 | PS5-42-IK-4006C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-04-27 | PS5-02-01 | PS5 - Milestone B | 1.1 | Closed | 15 | 31 | APRIL
T-546-11863 | PS5-32-IK-3068B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | In progress |  | 27 | AUGUST
T-084-11864 | PS5-23-OB-2815C | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | On hold |  | 46 | SEPTEMBER
T-830-11865 | PS5-79-OB-8151A | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | To be completed |  | 19 | SEPTEMBER
T-370-11866 | PS5-96-OB-4114C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-04-23 | PS5-11-02 | PS5 - Milestone G | 6 | Closed | 22 | 6 | APRIL
T-805-11867 | PS5-94-UR-3477C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-05 | PS5-60-04 | PS5 - Milestone D | 3 | Closed | 44 | 35 | JULY
T-402-11868 | PS5-41-UR-6139C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-03-15 | PS5-10-05 | PS5 - Milestone E | 4 | Closed | 31 | 14 | MARCH
T-616-11869 | PS5-28-IK-2832A | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | In progress |  | 23 | AUGUST
T-726-11870 | PS5-73-OB-1050A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone H | 7 | On hold |  | 39 | OCTOBER
T-831-11871 | PS5-68-IK-1246C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone C | 2 | To be completed |  | 44 | OCTOBER
T-135-11872 | PS5-82-OB-7215D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-05-07 | PS5-62-02 | PS5 - Milestone E | 4 | Closed | 36 | 43 | MAY
T-647-11873 | PS5-38-OB-1385C | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone F | 5 | In progress |  | 34 | NOVEMBER
T-247-11874 | PS5-37-OB-1473D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone F | 5 | To be completed |  | 8 | OCTOBER
T-249-11875 | PS5-22-OB-5968C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | To be completed |  | 22 | SEPTEMBER
T-032-11876 | PS5-47-IK-6389A | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | To be completed |  | 41 | OCTOBER
T-245-11877 | PS5-66-IK-2914B | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-12-13 | PS5-02-01 | PS5 - Milestone G | 6 | Closed | 35 | 8 | DECEMBER
T-363-11878 | PS5-29-OB-7127D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-09-04 | PS5-09-02 | PS5 - Milestone I | 8 | Closed | 9 | 18 | SEPTEMBER
T-044-11879 | PS5-65-OB-8153C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-06-14 | PS5-01-02 | PS5 - Milestone B | 1.1 | Closed | 36 | 27 | JUNE
T-481-11880 | PS5-05-OB-5472A | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone E | 4 | To be completed |  | 27 | OCTOBER
T-511-11881 | PS5-52-UR-9737C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone H | 7 | In progress |  | 33 | DECEMBER
T-894-11882 | PS5-02-UR-3667C | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone D | 3 | In progress |  | 17 | SEPTEMBER
T-107-11883 | PS5-03-OB-6598B | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | In progress |  | 42 | DECEMBER
T-550-11884 | PS5-05-IK-1077D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone G | 6 | On hold |  | 32 | SEPTEMBER
T-567-11885 | PS5-93-UR-5251B | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone I | 8 | To be completed |  | 8 | NOVEMBER
T-708-11886 | PS5-82-IK-8613B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-12-10 | PS5-09-02 | PS5 - Milestone F | 5 | Closed | 44 | 36 | DECEMBER
T-520-11887 | PS5-50-UR-1391B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone E | 4 | On hold |  | 41 | AUGUST
T-862-11888 | PS5-63-IK-3333C | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | On hold |  | 30 | AUGUST
T-072-11889 | PS5-58-IK-4973B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | On hold |  | 46 | AUGUST
T-989-11890 | PS5-17-UR-1416B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone E | 4 | On hold |  | 14 | AUGUST
T-656-11891 | PS5-39-OB-7196B | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-11-18 | PS5-04-01 | PS5 - Milestone A | 1 | Closed | 18 | 18 | NOVEMBER
T-677-11892 | PS5-91-IK-4715C | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone D | 3 | To be completed |  | 10 | OCTOBER
T-834-11893 | PS5-14-OB-6033D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone G | 6 | To be completed |  | 43 | DECEMBER
T-614-11894 | PS5-91-OB-4002B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone I | 8 | On hold |  | 16 | OCTOBER
T-264-11895 | PS5-26-UR-4615A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone F | 5 | To be completed |  | 31 | AUGUST
T-398-11896 | PS5-62-UR-5622D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-01-22 | PS5-01-02 | PS5 - Milestone H | 7 | Closed | 30 | 20 | JANUARY
T-784-11897 | PS5-25-OB-8400A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone C | 2 | In progress |  | 48 | DECEMBER
T-836-11898 | PS5-61-UR-4243C | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-11-12 | PS5-60-01 | PS5 - Milestone I | 8 | Closed | 47 | 5 | NOVEMBER
T-242-11899 | PS5-58-UR-6114A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-01-06 | PS5-61-01 | PS5 - Milestone F | 5 | Closed | 44 | 15 | JANUARY
T-679-11900 | PS5-74-OB-2669A | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-09-09 | PS5-11-01 | PS5 - Milestone B | 1.1 | Closed | 20 | 36 | SEPTEMBER
T-170-11901 | PS5-32-UR-4809A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-07-14 | PS5-01-05 | PS5 - Milestone A | 1 | Closed | 4 | 38 | JULY
T-029-11902 | PS5-64-IK-8352D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-08-27 | PS5-05-01 | PS5 - Milestone H | 7 | Closed | 19 | 20 | AUGUST
T-133-11903 | PS5-34-UR-1829D | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone F | 5 | On hold |  | 7 | OCTOBER
T-418-11904 | PS5-36-UR-8603C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | To be completed |  | 24 | AUGUST
T-144-11905 | PS5-63-IK-5567C | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone I | 8 | In progress |  | 15 | NOVEMBER
T-871-11906 | PS5-15-UR-9276B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone B | 1.1 | In progress |  | 31 | AUGUST
T-018-11907 | PS5-18-OB-2411A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-11-09 | PS5-03-03 | PS5 - Milestone G | 6 | Closed | 25 | 22 | NOVEMBER
T-633-11908 | PS5-57-UR-3093D | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone H | 7 | On hold |  | 24 | SEPTEMBER
T-902-11909 | PS5-48-OB-7257C | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-01-18 | PS5-06-03 | PS5 - Milestone F | 5 | Closed | 30 | 24 | JANUARY
T-973-11910 | PS5-35-OB-3846D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-11-15 | PS5-12-02 | PS5 - Milestone D | 3 | Closed | 48 | 37 | NOVEMBER
T-967-11911 | PS5-53-IK-3339C | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | To be completed |  | 31 | NOVEMBER
T-834-11912 | PS5-44-UR-6193D | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone D | 3 | In progress |  | 29 | AUGUST
T-930-11913 | PS5-03-UR-6665C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone A | 1 | In progress |  | 16 | AUGUST
T-250-11914 | PS5-54-OB-8124A | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone E | 4 | To be completed |  | 47 | DECEMBER
T-431-11915 | PS5-64-OB-5765D | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-06-26 | PS5-09-03 | PS5 - Milestone E | 4 | Closed | 48 | 40 | JUNE
T-736-11916 | PS5-07-OB-9683A | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-04-17 | PS5-10-01 | PS5 - Milestone C | 2 | Closed | 28 | 42 | APRIL
T-640-11917 | PS5-02-OB-9677C | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-12-22 | PS5-06-03 | PS5 - Milestone E | 4 | Closed | 23 | 25 | DECEMBER
T-851-11918 | PS5-90-OB-7018A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone H | 7 | On hold |  | 8 | OCTOBER
T-534-11919 | PS5-20-UR-6149A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-05-05 | PS5-08-02 | PS5 - Milestone D | 3 | Closed | 47 | 27 | MAY
T-866-11920 | PS5-31-UR-8200B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone E | 4 | In progress |  | 19 | NOVEMBER
T-167-11921 | PS5-48-OB-3315C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone B | 1.1 | To be completed |  | 37 | OCTOBER
T-484-11922 | PS5-33-OB-8716B | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone F | 5 | To be completed |  | 21 | OCTOBER
T-941-11923 | PS5-29-UR-3063A | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone G | 6 | To be completed |  | 15 | OCTOBER
T-706-11924 | PS5-28-UR-1827B | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-08-27 | PS5-02-01 | PS5 - Milestone A | 1 | Closed | 14 | 45 | AUGUST
T-011-11925 | PS5-51-IK-7659D | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-04-05 | PS5-61-07 | PS5 - Milestone F | 5 | Closed | 41 | 37 | APRIL
T-869-11926 | PS5-67-UR-5933B | CQE03 - Earthing | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone F | 5 | To be completed |  | 36 | OCTOBER
T-754-11927 | PS5-80-OB-7254B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | On hold |  | 47 | OCTOBER
T-313-11928 | PS5-69-OB-6580B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone C | 2 | On hold |  | 16 | OCTOBER
T-403-11929 | PS5-40-UR-9080A | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone E | 4 | To be completed |  | 14 | SEPTEMBER
T-044-11930 | PS5-27-UR-1311C | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-03-05 | PS5-11-02 | PS5 - Milestone G | 6 | Closed | 4 | 24 | MARCH
T-835-11931 | PS5-60-OB-5229B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-09-23 | PS5-99-02 | PS5 - Milestone G | 6 | Closed | 16 | 35 | SEPTEMBER
T-659-11932 | PS5-66-OB-2908A | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone G | 6 | In progress |  | 16 | SEPTEMBER
T-309-11933 | PS5-87-UR-6171B | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-09-01 | PS5-03-23 | PS5 - Milestone D | 3 | Closed | 43 | 36 | SEPTEMBER
T-186-11934 | PS5-94-OB-3320C | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone E | 4 | In progress |  | 25 | AUGUST
T-918-11935 | PS5-44-IK-3379A | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone G | 6 | In progress |  | 18 | SEPTEMBER
T-374-11936 | PS5-22-UR-5659D | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone I | 8 | To be completed |  | 38 | OCTOBER
T-509-11937 | PS5-82-UR-7252A | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone E | 4 | In progress |  | 11 | SEPTEMBER
T-061-11938 | PS5-33-OB-2928C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-04-15 | PS5-01-01 | PS5 - Milestone A | 1 | Closed | 39 | 35 | APRIL
T-414-11939 | PS5-52-OB-6597C | CQI03 - Control Valve | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone C | 2 | To be completed |  | 47 | NOVEMBER
T-499-11940 | PS5-15-UR-5462B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone C | 2 | To be completed |  | 4 | SEPTEMBER
T-034-11941 | PS5-85-OB-5711C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone D | 3 | To be completed |  | 20 | DECEMBER
T-561-11942 | PS5-84-IK-7582C | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone A | 1 | To be completed |  | 12 | OCTOBER
T-830-11943 | PS5-95-IK-8388C | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone H | 7 | In progress |  | 28 | SEPTEMBER
T-213-11944 | PS5-97-OB-2757A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-02-09 | PS5-02-01 | PS5 - Milestone I | 8 | Closed | 6 | 34 | FEBRUARY
T-797-11945 | PS5-66-OB-1027C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone B | 1.1 | On hold |  | 43 | DECEMBER
T-968-11946 | PS5-50-UR-3926A | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-09-11 | PS5-61-01 | PS5 - Milestone E | 4 | Closed | 18 | 9 | SEPTEMBER
T-376-11947 | PS5-35-UR-2830D | CQP01 - Pipe Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone D | 3 | In progress |  | 15 | OCTOBER
T-655-11948 | PS5-06-OB-2096C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | In progress |  | 31 | DECEMBER
T-671-11949 | PS5-94-IK-4709D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone D | 3 | To be completed |  | 24 | AUGUST
T-306-11950 | PS5-17-UR-2915B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone E | 4 | To be completed |  | 12 | NOVEMBER
T-126-11951 | PS5-17-OB-2200C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | To be completed |  | 42 | NOVEMBER
T-568-11952 | PS5-86-OB-4482A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone C | 2 | To be completed |  | 24 | SEPTEMBER
T-103-11953 | PS5-60-UR-2119A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone G | 6 | On hold |  | 40 | AUGUST
T-096-11954 | PS5-32-IK-4913C | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-01-04 | PS5-07-03 | PS5 - Milestone A | 1 | Closed | 21 | 22 | JANUARY
T-780-11955 | PS5-15-IK-2993D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone I | 8 | In progress |  | 26 | DECEMBER
T-387-11956 | PS5-91-OB-5148B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-12-04 | PS5-63-01 | PS5 - Milestone B | 1.1 | Closed | 46 | 15 | DECEMBER
T-033-11957 | PS5-78-UR-1413A | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone G | 6 | To be completed |  | 32 | OCTOBER
T-793-11958 | PS5-37-UR-3910C | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone A | 1 | In progress |  | 48 | DECEMBER
T-022-11959 | PS5-81-OB-6976A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | To be completed |  | 46 | DECEMBER
T-386-11960 | PS5-17-UR-3312B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-11-06 | PS5-99-02 | PS5 - Milestone H | 7 | Closed | 17 | 11 | NOVEMBER
T-860-11961 | PS5-22-OB-9515C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone C | 2 | To be completed |  | 42 | AUGUST
T-568-11962 | PS5-53-UR-7718B | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone F | 5 | To be completed |  | 38 | NOVEMBER
T-363-11963 | PS5-73-UR-9314B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone I | 8 | In progress |  | 37 | SEPTEMBER
T-184-11964 | PS5-32-OB-9740A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | To be completed |  | 31 | SEPTEMBER
T-345-11965 | PS5-01-UR-4390B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone E | 4 | To be completed |  | 20 | DECEMBER
T-266-11966 | PS5-99-OB-2688B | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone E | 4 | To be completed |  | 28 | AUGUST
T-532-11967 | PS5-24-IK-9245D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-12-09 | PS5-04-03 | PS5 - Milestone C | 2 | Closed | 24 | 4 | DECEMBER
T-836-11968 | PS5-04-OB-3337B | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | To be completed |  | 28 | SEPTEMBER
T-823-11969 | PS5-20-UR-8573D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-10-03 | PS5-11-02 | PS5 - Milestone H | 7 | Closed | 28 | 10 | OCTOBER
T-973-11970 | PS5-50-OB-8619B | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-12-10 | PS5-01-01 | PS5 - Milestone I | 8 | Closed | 35 | 6 | DECEMBER
T-477-11971 | PS5-09-IK-7221B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone A | 1 | To be completed |  | 32 | DECEMBER
T-204-11972 | PS5-77-OB-4055A | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-12-09 | PS5-02-03 | PS5 - Milestone G | 6 | Closed | 33 | 16 | DECEMBER
T-211-11973 | PS5-99-OB-3061D | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-10-04 | PS5-09-02 | PS5 - Milestone C | 2 | Closed | 13 | 15 | OCTOBER
T-447-11974 | PS5-17-UR-9734B | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone A | 1 | To be completed |  | 19 | SEPTEMBER
T-673-11975 | PS5-49-OB-9651D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone F | 5 | In progress |  | 9 | NOVEMBER
T-203-11976 | PS5-62-OB-4051C | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone C | 2 | To be completed |  | 19 | SEPTEMBER
T-396-11977 | PS5-63-OB-9960A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone C | 2 | To be completed |  | 40 | AUGUST
T-894-11978 | PS5-87-UR-6183D | CQM01 - Pump Installation | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | In progress |  | 23 | SEPTEMBER
T-654-11979 | PS5-67-OB-5657B | CQM02 - Compressor | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone B | 1.1 | In progress |  | 39 | AUGUST
T-708-11980 | PS5-28-UR-7968A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | On hold |  | 20 | DECEMBER
T-118-11981 | PS5-78-IK-8726D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone H | 7 | In progress |  | 25 | SEPTEMBER
T-438-11982 | PS5-21-IK-4027A | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone B | 1.1 | To be completed |  | 47 | SEPTEMBER
T-470-11983 | PS5-01-IK-8790D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | On hold |  | 37 | OCTOBER
T-434-11984 | PS5-73-IK-4089D | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone H | 7 | To be completed |  | 48 | AUGUST
T-872-11985 | PS5-07-UR-4406C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone A | 1 | On hold |  | 9 | DECEMBER
T-792-11986 | PS5-53-OB-6789C | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-05-10 | PS5-06-03 | PS5 - Milestone A | 1 | Closed | 39 | 13 | MAY
T-704-11987 | PS5-07-OB-4331A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone I | 8 | To be completed |  | 34 | OCTOBER
T-633-11988 | PS5-74-OB-1496A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-01-26 | PS5-01-02 | PS5 - Milestone E | 4 | Closed | 6 | 21 | JANUARY
T-836-11989 | PS5-24-UR-1265C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone D | 3 | To be completed |  | 18 | AUGUST
T-791-11990 | PS5-96-OB-3851C | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-05-23 | PS5-05-01 | PS5 - Milestone H | 7 | Closed | 13 | 46 | MAY
T-324-11991 | PS5-96-IK-3652D | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-05-25 | PS5-09-03 | PS5 - Milestone C | 2 | Closed | 16 | 14 | MAY
T-534-11992 | PS5-32-UR-7045B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone G | 6 | In progress |  | 21 | OCTOBER
T-959-11993 | PS5-18-OB-5058A | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone I | 8 | In progress |  | 35 | NOVEMBER
T-647-11994 | PS5-59-OB-2686D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone B | 1.1 | To be completed |  | 27 | OCTOBER
T-039-11995 | PS5-07-OB-1203D | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-05-23 | PS5-99-03 | PS5 - Milestone H | 7 | Closed | 36 | 11 | MAY
T-323-11996 | PS5-84-OB-2979D | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | To be completed |  | 19 | SEPTEMBER
T-016-11997 | PS5-50-OB-4458C | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-03-11 | PS5-01-07 | PS5 - Milestone I | 8 | Closed | 28 | 47 | MARCH
T-049-11998 | PS5-47-UR-3085B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone C | 2 | In progress |  | 31 | SEPTEMBER
T-638-11999 | PS5-55-IK-8551D | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-12-10 | PS5-13-01 | PS5 - Milestone C | 2 | Closed | 26 | 46 | DECEMBER
T-327-12000 | PS5-42-OB-8977A | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | In progress |  | 47 | DECEMBER
T-866-12001 | PS5-34-OB-3422B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone B | 1.1 | In progress |  | 44 | AUGUST
T-207-12002 | PS5-18-OB-9870A | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | In progress |  | 23 | SEPTEMBER
T-230-12003 | PS5-56-IK-7333C | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-06-23 | PS5-05-02 | PS5 - Milestone A | 1 | Closed | 48 | 42 | JUNE
T-429-12004 | PS5-07-IK-4093C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone I | 8 | To be completed |  | 8 | SEPTEMBER
T-320-12005 | PS5-12-OB-5837C | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone C | 2 | To be completed |  | 28 | OCTOBER
T-500-12006 | PS5-53-OB-7229A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone F | 5 | In progress |  | 8 | DECEMBER
T-224-12007 | PS5-74-OB-5078B | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone E | 4 | To be completed |  | 17 | DECEMBER
T-276-12008 | PS5-84-OB-7605C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-08-20 | PS5-11-03 | PS5 - Milestone A | 1 | Closed | 40 | 19 | AUGUST
T-817-12009 | PS5-02-OB-8510B | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-03-12 | PS5-60-07 | PS5 - Milestone D | 3 | Closed | 8 | 25 | MARCH
T-312-12010 | PS5-87-IK-7947C | CQH02 - AHU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone C | 2 | In progress |  | 10 | SEPTEMBER
T-798-12011 | PS5-85-IK-9835C | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone D | 3 | On hold |  | 6 | NOVEMBER
T-143-12012 | PS5-21-OB-6448D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone A | 1 | In progress |  | 29 | DECEMBER
T-083-12013 | PS5-51-OB-7757D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone C | 2 | On hold |  | 16 | NOVEMBER
T-639-12014 | PS5-23-IK-4843A | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | In progress |  | 13 | DECEMBER
T-558-12015 | PS5-54-UR-1449A | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-12-21 | PS5-07-03 | PS5 - Milestone F | 5 | Closed | 18 | 12 | DECEMBER
T-441-12016 | PS5-71-UR-1102A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone E | 4 | To be completed |  | 14 | OCTOBER
T-131-12017 | PS5-75-IK-6009A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-10-18 | PS5-09-01 | PS5 - Milestone F | 5 | Closed | 10 | 35 | OCTOBER
T-272-12018 | PS5-20-OB-6151C | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone I | 8 | On hold |  | 19 | OCTOBER
T-631-12019 | PS5-36-UR-7348C | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-10-11 | PS5-13-01 | PS5 - Milestone I | 8 | Closed | 18 | 48 | OCTOBER
T-476-12020 | PS5-74-OB-8155C | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone E | 4 | On hold |  | 42 | DECEMBER
T-718-12021 | PS5-28-UR-1526B | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone G | 6 | To be completed |  | 24 | AUGUST
T-935-12022 | PS5-26-UR-6956C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone H | 7 | In progress |  | 7 | DECEMBER
T-540-12023 | PS5-02-OB-6004D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-06-20 | PS5-82-02 | PS5 - Milestone I | 8 | Closed | 8 | 40 | JUNE
T-521-12024 | PS5-72-OB-3190B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-07-18 | PS5-01-09 | PS5 - Milestone H | 7 | Closed | 46 | 6 | JULY
T-552-12025 | PS5-56-OB-4877B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone A | 1 | In progress |  | 46 | DECEMBER
T-858-12026 | PS5-85-OB-4483C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-07-05 | PS5-01-08 | PS5 - Milestone G | 6 | Closed | 42 | 13 | JULY
T-758-12027 | PS5-71-OB-1379A | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone B | 1.1 | To be completed |  | 20 | DECEMBER
T-107-12028 | PS5-29-OB-8123D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-03-21 | PS5-99-03 | PS5 - Milestone A | 1 | Closed | 30 | 38 | MARCH
T-704-12029 | PS5-59-UR-5291C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-01-16 | PS5-01-05 | PS5 - Milestone D | 3 | Closed | 5 | 18 | JANUARY
T-180-12030 | PS5-53-IK-7689B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone F | 5 | On hold |  | 40 | NOVEMBER
T-485-12031 | PS5-92-OB-9089D | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-12-21 | PS5-10-03 | PS5 - Milestone F | 5 | Closed | 35 | 40 | DECEMBER
T-407-12032 | PS5-96-UR-9354B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | To be completed |  | 38 | NOVEMBER
T-151-12033 | PS5-65-OB-9645D | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-05-03 | PS5-61-07 | PS5 - Milestone C | 2 | Closed | 16 | 31 | MAY
T-264-12034 | PS5-97-OB-7130D | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone B | 1.1 | In progress |  | 9 | AUGUST
T-498-12035 | PS5-30-UR-3037B | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone A | 1 | To be completed |  | 21 | NOVEMBER
T-252-12036 | PS5-57-IK-8499B | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone F | 5 | To be completed |  | 31 | OCTOBER
T-659-12037 | PS5-02-IK-9054B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-10-02 | PS5-61-01 | PS5 - Milestone F | 5 | Closed | 24 | 21 | OCTOBER
T-570-12038 | PS5-17-IK-7567C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone I | 8 | To be completed |  | 13 | DECEMBER
T-144-12039 | PS5-86-IK-4101A | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone G | 6 | To be completed |  | 46 | OCTOBER
T-444-12040 | PS5-40-OB-2806B | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-12-10 | PS5-10-03 | PS5 - Milestone D | 3 | Closed | 23 | 5 | DECEMBER
T-494-12041 | PS5-62-OB-4992B | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone B | 1.1 | To be completed |  | 20 | OCTOBER
T-937-12042 | PS5-53-UR-1576D | CQP04 - Hydrotest | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-06-10 | PS5-08-02 | PS5 - Milestone H | 7 | Closed | 13 | 31 | JUNE
T-134-12043 | PS5-33-OB-4798C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone I | 8 | To be completed |  | 9 | AUGUST
T-715-12044 | PS5-98-OB-4277B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-03-07 | PS5-99-01 | PS5 - Milestone G | 6 | Closed | 24 | 9 | MARCH
T-218-12045 | PS5-49-UR-5558B | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-06-02 | PS5-02-03 | PS5 - Milestone D | 3 | Closed | 18 | 38 | JUNE
T-162-12046 | PS5-31-IK-1115B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone F | 5 | In progress |  | 39 | DECEMBER
T-491-12047 | PS5-52-OB-7650B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone A | 1 | In progress |  | 45 | AUGUST
T-915-12048 | PS5-55-OB-5008B | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-11-28 | PS5-01-04 | PS5 - Milestone H | 7 | Closed | 5 | 44 | NOVEMBER
T-552-12049 | PS5-03-OB-9984B | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone C | 2 | On hold |  | 30 | DECEMBER
T-736-12050 | PS5-03-OB-6608A | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-09-24 | PS5-08-01 | PS5 - Milestone B | 1.1 | Closed | 14 | 14 | SEPTEMBER
T-101-12051 | PS5-07-UR-6473B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone H | 7 | To be completed |  | 11 | AUGUST
T-793-12052 | PS5-34-UR-2686C | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-04-16 | PS5-09-03 | PS5 - Milestone E | 4 | Closed | 35 | 7 | APRIL
T-687-12053 | PS5-24-IK-3365B | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-10-26 | PS5-61-07 | PS5 - Milestone D | 3 | Closed | 17 | 28 | OCTOBER
T-420-12054 | PS5-33-OB-2217D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone F | 5 | In progress |  | 17 | SEPTEMBER
T-571-12055 | PS5-07-IK-5782B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-06-19 | PS5-10-01 | PS5 - Milestone A | 1 | Closed | 44 | 39 | JUNE
T-256-12056 | PS5-58-IK-3575A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-01-02 | PS5-07-03 | PS5 - Milestone B | 1.1 | Closed | 45 | 32 | JANUARY
T-289-12057 | PS5-65-UR-4099C | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone F | 5 | In progress |  | 46 | DECEMBER
T-727-12058 | PS5-42-OB-7405A | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-09-11 | PS5-03-02 | PS5 - Milestone E | 4 | Closed | 23 | 47 | SEPTEMBER
T-628-12059 | PS5-73-OB-2946D | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone C | 2 | In progress |  | 41 | AUGUST
T-280-12060 | PS5-39-UR-2569A | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | To be completed |  | 23 | SEPTEMBER
T-170-12061 | PS5-43-UR-7156D | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone A | 1 | To be completed |  | 6 | NOVEMBER
T-326-12062 | PS5-91-IK-8834B | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone C | 2 | In progress |  | 45 | OCTOBER
T-395-12063 | PS5-92-UR-9042B | CQE01 - HV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone H | 7 | In progress |  | 48 | AUGUST
T-242-12064 | PS5-72-UR-8109B | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone A | 1 | In progress |  | 27 | DECEMBER
T-833-12065 | PS5-19-IK-1195A | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-04-26 | PS5-05-02 | PS5 - Milestone A | 1 | Closed | 41 | 6 | APRIL
T-157-12066 | PS5-93-IK-7672A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone I | 8 | On hold |  | 5 | OCTOBER
T-316-12067 | PS5-95-OB-2976A | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-05-27 | PS5-13-01 | PS5 - Milestone I | 8 | Closed | 7 | 27 | MAY
T-332-12068 | PS5-70-OB-1328D | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-08-11 | PS5-07-01 | PS5 - Milestone B | 1.1 | Closed | 34 | 36 | AUGUST
T-444-12069 | PS5-87-IK-4378C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone D | 3 | To be completed |  | 14 | AUGUST
T-726-12070 | PS5-08-IK-9787A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone G | 6 | To be completed |  | 11 | DECEMBER
T-005-12071 | PS5-67-IK-9102C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone G | 6 | In progress |  | 19 | SEPTEMBER
T-886-12072 | PS5-82-OB-8074C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-12-10 | PS5-02-02 | PS5 - Milestone D | 3 | Closed | 22 | 45 | DECEMBER
T-791-12073 | PS5-49-IK-9433C | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone B | 1.1 | In progress |  | 18 | SEPTEMBER
T-233-12074 | PS5-07-OB-4620D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-07-18 | PS5-02-02 | PS5 - Milestone F | 5 | Closed | 34 | 40 | JULY
T-758-12075 | PS5-51-OB-8568A | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone D | 3 | In progress |  | 31 | OCTOBER
T-767-12076 | PS5-65-UR-3446D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone F | 5 | On hold |  | 13 | AUGUST
T-313-12077 | PS5-68-IK-6158D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone F | 5 | In progress |  | 36 | AUGUST
T-874-12078 | PS5-44-UR-3083C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-09-22 | PS5-63-04 | PS5 - Milestone B | 1.1 | Closed | 18 | 14 | SEPTEMBER
T-591-12079 | PS5-94-OB-8530A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-03-05 | PS5-11-03 | PS5 - Milestone H | 7 | Closed | 39 | 39 | MARCH
T-258-12080 | PS5-80-OB-9162A | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-02-19 | PS5-01-06 | PS5 - Milestone C | 2 | Closed | 39 | 45 | FEBRUARY
T-300-12081 | PS5-40-UR-9470C | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone A | 1 | On hold |  | 36 | DECEMBER
T-863-12082 | PS5-53-IK-6974C | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone G | 6 | To be completed |  | 6 | SEPTEMBER
T-085-12083 | PS5-75-OB-1711C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-07-01 | PS5-60-01 | PS5 - Milestone F | 5 | Closed | 27 | 13 | JULY
T-286-12084 | PS5-27-UR-5573A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone B | 1.1 | On hold |  | 17 | DECEMBER
T-799-12085 | PS5-15-OB-3648B | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone C | 2 | In progress |  | 21 | AUGUST
T-392-12086 | PS5-99-OB-5622D | CQE03 - Earthing | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-02-16 | PS5-10-04 | PS5 - Milestone E | 4 | Closed | 4 | 16 | FEBRUARY
T-254-12087 | PS5-36-OB-9335B | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone F | 5 | On hold |  | 7 | DECEMBER
T-505-12088 | PS5-79-UR-2232A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-12-06 | PS5-62-02 | PS5 - Milestone E | 4 | Closed | 25 | 7 | DECEMBER
T-847-12089 | PS5-07-UR-5422A | CQE04 - Transformer | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | In progress |  | 15 | AUGUST
T-706-12090 | PS5-29-UR-9160A | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone G | 6 | To be completed |  | 4 | OCTOBER
T-085-12091 | PS5-32-UR-3461D | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone H | 7 | On hold |  | 20 | AUGUST
T-873-12092 | PS5-33-OB-3142B | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone B | 1.1 | To be completed |  | 12 | NOVEMBER
T-985-12093 | PS5-39-UR-3840C | CQM01 - Pump Installation | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-04-02 | PS5-03-03 | PS5 - Milestone C | 2 | Closed | 24 | 20 | APRIL
T-577-12094 | PS5-12-OB-9256B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-01-24 | PS5-01-07 | PS5 - Milestone G | 6 | Closed | 30 | 9 | JANUARY
T-122-12095 | PS5-65-IK-5911A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | To be completed |  | 23 | AUGUST
T-085-12096 | PS5-88-OB-1782D | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | To be completed |  | 13 | OCTOBER
T-966-12097 | PS5-50-OB-9684D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone G | 6 | To be completed |  | 14 | SEPTEMBER
T-659-12098 | PS5-80-OB-2787C | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-02-27 | PS5-09-01 | PS5 - Milestone G | 6 | Closed | 15 | 23 | FEBRUARY
T-035-12099 | PS5-42-OB-2850D | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone H | 7 | To be completed |  | 6 | OCTOBER
T-760-12100 | PS5-41-OB-4810A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-10-12 | PS5-82-01 | PS5 - Milestone E | 4 | Closed | 19 | 12 | OCTOBER
T-389-12101 | PS5-61-IK-4458C | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-05-17 | PS5-61-07 | PS5 - Milestone F | 5 | Closed | 26 | 23 | MAY
T-716-12102 | PS5-13-UR-4756A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-08-24 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 29 | 40 | AUGUST
T-816-12103 | PS5-26-OB-3527D | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-01-07 | PS5-60-10 | PS5 - Milestone A | 1 | Closed | 35 | 10 | JANUARY
T-186-12104 | PS5-48-OB-3942C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | To be completed |  | 34 | NOVEMBER
T-532-12105 | PS5-73-OB-6460B | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-07-24 | PS5-10-01 | PS5 - Milestone B | 1.1 | Closed | 40 | 39 | JULY
T-739-12106 | PS5-54-OB-4377C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-09-18 | PS5-01-06 | PS5 - Milestone E | 4 | Closed | 48 | 47 | SEPTEMBER
T-858-12107 | PS5-74-OB-4296A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone E | 4 | In progress |  | 44 | AUGUST
T-766-12108 | PS5-71-OB-3947C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone G | 6 | To be completed |  | 44 | AUGUST
T-279-12109 | PS5-12-UR-1306A | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-11-15 | PS5-11-02 | PS5 - Milestone B | 1.1 | Closed | 44 | 29 | NOVEMBER
T-191-12110 | PS5-41-UR-4623A | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone I | 8 | In progress |  | 34 | NOVEMBER
T-144-12111 | PS5-21-IK-1451B | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone G | 6 | To be completed |  | 30 | AUGUST
T-388-12112 | PS5-36-UR-9702B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | In progress |  | 9 | DECEMBER
T-618-12113 | PS5-36-IK-8772D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone F | 5 | To be completed |  | 41 | AUGUST
T-981-12114 | PS5-59-IK-1204B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone G | 6 | To be completed |  | 28 | OCTOBER
T-601-12115 | PS5-26-UR-7182D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone G | 6 | In progress |  | 20 | SEPTEMBER
T-807-12116 | PS5-55-OB-6527D | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone H | 7 | To be completed |  | 30 | AUGUST
T-688-12117 | PS5-21-OB-4661B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-04-27 | PS5-99-02 | PS5 - Milestone F | 5 | Closed | 46 | 39 | APRIL
T-308-12118 | PS5-16-OB-1229D | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-10-05 | PS5-10-06 | PS5 - Milestone H | 7 | Closed | 29 | 19 | OCTOBER
T-633-12119 | PS5-22-OB-2012D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone A | 1 | To be completed |  | 14 | DECEMBER
T-778-12120 | PS5-02-OB-9806A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-08-23 | PS5-09-02 | PS5 - Milestone I | 8 | Closed | 39 | 25 | AUGUST
T-622-12121 | PS5-07-OB-8496A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | On hold |  | 21 | OCTOBER
T-134-12122 | PS5-93-UR-9430C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone F | 5 | In progress |  | 25 | DECEMBER
T-950-12123 | PS5-07-IK-1024D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone G | 6 | In progress |  | 10 | DECEMBER
T-735-12124 | PS5-74-IK-9187A | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-01-23 | PS5-06-01 | PS5 - Milestone B | 1.1 | Closed | 39 | 26 | JANUARY
T-828-12125 | PS5-02-OB-3473A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone A | 1 | On hold |  | 13 | AUGUST
T-778-12126 | PS5-32-UR-5812D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-07-23 | PS5-99-03 | PS5 - Milestone B | 1.1 | Closed | 5 | 17 | JULY
T-147-12127 | PS5-73-OB-6393C | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone I | 8 | To be completed |  | 29 | OCTOBER
T-765-12128 | PS5-86-IK-1588B | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone I | 8 | To be completed |  | 16 | SEPTEMBER
T-117-12129 | PS5-49-OB-8809A | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone A | 1 | On hold |  | 10 | OCTOBER
T-586-12130 | PS5-91-OB-3564D | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone H | 7 | On hold |  | 17 | DECEMBER
T-952-12131 | PS5-36-UR-3012A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone H | 7 | On hold |  | 46 | NOVEMBER
T-328-12132 | PS5-17-OB-9361A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone E | 4 | To be completed |  | 45 | SEPTEMBER
T-333-12133 | PS5-26-OB-7317A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-02-15 | PS5-11-02 | PS5 - Milestone I | 8 | Closed | 20 | 12 | FEBRUARY
T-426-12134 | PS5-86-OB-2467B | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | In progress |  | 36 | DECEMBER
T-345-12135 | PS5-90-OB-1444C | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone C | 2 | To be completed |  | 17 | DECEMBER
T-452-12136 | PS5-28-IK-5900B | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-04-14 | PS5-02-02 | PS5 - Milestone H | 7 | Closed | 19 | 7 | APRIL
T-067-12137 | PS5-55-OB-1044C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | In progress |  | 15 | OCTOBER
T-045-12138 | PS5-07-OB-7277D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-03-02 | PS5-10-03 | PS5 - Milestone I | 8 | Closed | 5 | 25 | MARCH
T-814-12139 | PS5-98-OB-5487C | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone D | 3 | In progress |  | 24 | SEPTEMBER
T-998-12140 | PS5-55-UR-9476B | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | In progress |  | 44 | SEPTEMBER
T-154-12141 | PS5-08-IK-2901A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone F | 5 | To be completed |  | 28 | NOVEMBER
T-531-12142 | PS5-37-OB-1095A | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone A | 1 | To be completed |  | 35 | SEPTEMBER
T-579-12143 | PS5-50-IK-1629A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone H | 7 | On hold |  | 32 | DECEMBER
T-385-12144 | PS5-85-OB-4306A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-06-18 | PS5-05-01 | PS5 - Milestone E | 4 | Closed | 12 | 25 | JUNE
T-935-12145 | PS5-57-OB-6746A | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone G | 6 | To be completed |  | 16 | NOVEMBER
T-519-12146 | PS5-12-OB-7258D | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone I | 8 | To be completed |  | 39 | OCTOBER
T-829-12147 | PS5-03-IK-8079B | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-05-20 | PS5-82-07 | PS5 - Milestone G | 6 | Closed | 40 | 13 | MAY
T-698-12148 | PS5-57-OB-5023D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | In progress |  | 32 | SEPTEMBER
T-789-12149 | PS5-79-OB-1041B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone I | 8 | In progress |  | 4 | SEPTEMBER
T-787-12150 | PS5-43-UR-6738A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-02-21 | PS5-12-01 | PS5 - Milestone A | 1 | Closed | 27 | 16 | FEBRUARY
T-800-12151 | PS5-15-OB-2439C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-10-10 | PS5-05-03 | PS5 - Milestone E | 4 | Closed | 11 | 30 | OCTOBER
T-610-12152 | PS5-50-IK-8237A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone B | 1.1 | In progress |  | 31 | NOVEMBER
T-230-12153 | PS5-49-IK-5197C | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone B | 1.1 | In progress |  | 19 | OCTOBER
T-747-12154 | PS5-50-OB-6221D | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone G | 6 | To be completed |  | 16 | AUGUST
T-098-12155 | PS5-01-OB-9521A | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-04-26 | PS5-03-02 | PS5 - Milestone E | 4 | Closed | 42 | 43 | APRIL
T-133-12156 | PS5-09-IK-6333D | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-12-13 | PS5-07-03 | PS5 - Milestone B | 1.1 | Closed | 42 | 10 | DECEMBER
T-060-12157 | PS5-63-OB-4413A | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | To be completed |  | 39 | AUGUST
T-870-12158 | PS5-86-OB-3308D | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone D | 3 | To be completed |  | 40 | DECEMBER
T-061-12159 | PS5-01-IK-1716A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone I | 8 | In progress |  | 14 | NOVEMBER
T-451-12160 | PS5-43-UR-3127A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | To be completed |  | 36 | SEPTEMBER
T-301-12161 | PS5-58-IK-3151C | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone D | 3 | To be completed |  | 16 | OCTOBER
T-680-12162 | PS5-41-UR-2968D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone D | 3 | In progress |  | 36 | NOVEMBER
T-922-12163 | PS5-41-IK-3627C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-07-22 | PS5-10-05 | PS5 - Milestone F | 5 | Closed | 20 | 4 | JULY
T-629-12164 | PS5-70-OB-5007D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone A | 1 | On hold |  | 47 | OCTOBER
T-686-12165 | PS5-18-UR-6455D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-03-20 | PS5-10-02 | PS5 - Milestone G | 6 | Closed | 36 | 21 | MARCH
T-975-12166 | PS5-13-IK-6377A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone A | 1 | In progress |  | 13 | DECEMBER
T-106-12167 | PS5-12-OB-2373D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone G | 6 | To be completed |  | 29 | SEPTEMBER
T-717-12168 | PS5-70-OB-7883D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone A | 1 | On hold |  | 48 | DECEMBER
T-728-12169 | PS5-69-UR-1697A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | On hold |  | 26 | DECEMBER
T-704-12170 | PS5-11-OB-1177A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone C | 2 | To be completed |  | 11 | NOVEMBER
T-027-12171 | PS5-96-UR-3433D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | To be completed |  | 18 | OCTOBER
T-569-12172 | PS5-43-IK-4547A | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | On hold |  | 8 | SEPTEMBER
T-344-12173 | PS5-10-IK-7002B | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone H | 7 | To be completed |  | 45 | OCTOBER
T-924-12174 | PS5-88-OB-6156B | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone D | 3 | To be completed |  | 4 | AUGUST
T-236-12175 | PS5-01-UR-5874C | CQE01 - HV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-05-13 | PS5-04-04 | PS5 - Milestone A | 1 | Closed | 34 | 40 | MAY
T-857-12176 | PS5-74-IK-5869B | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone B | 1.1 | To be completed |  | 12 | NOVEMBER
T-960-12177 | PS5-13-IK-2064A | CQE02 - LV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-02-13 | PS5-11-01 | PS5 - Milestone H | 7 | Closed | 34 | 43 | FEBRUARY
T-122-12178 | PS5-35-IK-5497C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone H | 7 | On hold |  | 30 | OCTOBER
T-350-12179 | PS5-20-UR-3452D | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-05-03 | PS5-06-03 | PS5 - Milestone C | 2 | Closed | 25 | 7 | MAY
T-870-12180 | PS5-96-OB-1196A | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-09-08 | PS5-63-04 | PS5 - Milestone E | 4 | Closed | 15 | 43 | SEPTEMBER
T-445-12181 | PS5-37-UR-2388D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-07-07 | PS5-99-03 | PS5 - Milestone E | 4 | Closed | 16 | 40 | JULY
T-266-12182 | PS5-14-OB-2954C | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-01-27 | PS5-06-01 | PS5 - Milestone G | 6 | Closed | 9 | 10 | JANUARY
T-464-12183 | PS5-12-OB-3764A | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone G | 6 | On hold |  | 15 | AUGUST
T-692-12184 | PS5-03-OB-4417A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone C | 2 | To be completed |  | 14 | AUGUST
T-812-12185 | PS5-45-UR-5791C | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone F | 5 | In progress |  | 15 | OCTOBER
T-163-12186 | PS5-80-OB-8384C | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone C | 2 | To be completed |  | 12 | NOVEMBER
T-331-12187 | PS5-42-OB-3840C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone F | 5 | To be completed |  | 18 | SEPTEMBER
T-439-12188 | PS5-25-OB-7192B | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone A | 1 | To be completed |  | 27 | AUGUST
T-119-12189 | PS5-39-IK-5705B | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | In progress |  | 37 | OCTOBER
T-700-12190 | PS5-33-UR-9647D | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone C | 2 | To be completed |  | 22 | OCTOBER
T-153-12191 | PS5-67-UR-6992C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | To be completed |  | 38 | AUGUST
T-995-12192 | PS5-65-UR-9121B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | To be completed |  | 39 | AUGUST
T-972-12193 | PS5-51-OB-2865C | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone B | 1.1 | In progress |  | 13 | AUGUST
T-653-12194 | PS5-96-IK-6401D | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone B | 1.1 | To be completed |  | 8 | OCTOBER
T-247-12195 | PS5-46-OB-5689C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone C | 2 | To be completed |  | 6 | AUGUST
T-616-12196 | PS5-61-OB-5363A | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-06-02 | PS5-10-06 | PS5 - Milestone I | 8 | Closed | 34 | 32 | JUNE
T-593-12197 | PS5-37-OB-2238A | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone G | 6 | To be completed |  | 11 | AUGUST
T-018-12198 | PS5-21-OB-9696B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-09-23 | PS5-05-03 | PS5 - Milestone E | 4 | Closed | 17 | 30 | SEPTEMBER
T-745-12199 | PS5-90-OB-6854C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-05-21 | PS5-61-01 | PS5 - Milestone B | 1.1 | Closed | 34 | 7 | MAY
T-134-12200 | PS5-21-IK-3909B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone H | 7 | To be completed |  | 19 | DECEMBER
T-339-12201 | PS5-76-OB-1183B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone F | 5 | To be completed |  | 12 | SEPTEMBER
T-160-12202 | PS5-52-IK-8141C | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-03-20 | PS5-60-04 | PS5 - Milestone F | 5 | Closed | 33 | 21 | MARCH
T-372-12203 | PS5-84-UR-8890B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | To be completed |  | 28 | NOVEMBER
T-686-12204 | PS5-58-OB-7572C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone E | 4 | To be completed |  | 25 | OCTOBER
T-015-12205 | PS5-02-OB-2993D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-11-06 | PS5-13-01 | PS5 - Milestone A | 1 | Closed | 38 | 30 | NOVEMBER
T-132-12206 | PS5-99-UR-8337A | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-06-14 | PS5-01-03 | PS5 - Milestone G | 6 | Closed | 35 | 21 | JUNE
T-354-12207 | PS5-88-IK-6819C | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone C | 2 | On hold |  | 36 | NOVEMBER
T-445-12208 | PS5-02-UR-8072D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-09-26 | PS5-01-06 | PS5 - Milestone C | 2 | Closed | 37 | 31 | SEPTEMBER
T-890-12209 | PS5-89-OB-2055B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-06-21 | PS5-07-03 | PS5 - Milestone E | 4 | Closed | 37 | 32 | JUNE
T-740-12210 | PS5-63-OB-4928D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | To be completed |  | 15 | SEPTEMBER
T-718-12211 | PS5-22-UR-5692A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-08-28 | PS5-63-04 | PS5 - Milestone I | 8 | Closed | 5 | 33 | AUGUST
T-574-12212 | PS5-05-OB-4444B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone C | 2 | In progress |  | 47 | NOVEMBER
T-565-12213 | PS5-56-IK-4255D | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-05-25 | PS5-01-09 | PS5 - Milestone B | 1.1 | Closed | 19 | 48 | MAY
T-552-12214 | PS5-51-OB-5821C | CQT03 - PA/GA System | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone E | 4 | In progress |  | 28 | SEPTEMBER
T-713-12215 | PS5-70-OB-8149D | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-07-03 | PS5-07-01 | PS5 - Milestone G | 6 | Closed | 5 | 48 | JULY
T-267-12216 | PS5-09-IK-7219A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | To be completed |  | 8 | AUGUST
T-145-12217 | PS5-59-OB-9592D | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone I | 8 | In progress |  | 9 | OCTOBER
T-339-12218 | PS5-79-UR-2610C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone H | 7 | On hold |  | 23 | DECEMBER
T-525-12219 | PS5-90-OB-6412A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | In progress |  | 44 | OCTOBER
T-415-12220 | PS5-50-IK-2543C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | In progress |  | 41 | AUGUST
T-341-12221 | PS5-76-UR-2238C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | On hold |  | 6 | SEPTEMBER
T-756-12222 | PS5-29-UR-2600D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-01-06 | PS5-99-02 | PS5 - Milestone G | 6 | Closed | 46 | 25 | JANUARY
T-861-12223 | PS5-15-OB-9721B | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-25 | PS5-60-07 | PS5 - Milestone E | 4 | Closed | 39 | 4 | JULY
T-090-12224 | PS5-65-OB-8795B | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone G | 6 | In progress |  | 27 | OCTOBER
T-350-12225 | PS5-66-IK-1459C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-02-21 | PS5-63-01 | PS5 - Milestone A | 1 | Closed | 28 | 42 | FEBRUARY
T-782-12226 | PS5-31-IK-4915B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | To be completed |  | 13 | SEPTEMBER
T-545-12227 | PS5-16-UR-6478D | CQM03 - Heat Exchanger | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone H | 7 | On hold |  | 37 | OCTOBER
T-257-12228 | PS5-62-OB-3716A | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-02-17 | PS5-61-02 | PS5 - Milestone I | 8 | Closed | 36 | 15 | FEBRUARY
T-516-12229 | PS5-12-UR-2123D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-05-11 | PS5-01-09 | PS5 - Milestone I | 8 | Closed | 20 | 17 | MAY
T-443-12230 | PS5-12-UR-4921B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone H | 7 | To be completed |  | 20 | DECEMBER
T-639-12231 | PS5-44-OB-4919B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-12-28 | PS5-10-05 | PS5 - Milestone H | 7 | Closed | 17 | 21 | DECEMBER
T-297-12232 | PS5-76-IK-1184C | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone G | 6 | To be completed |  | 25 | AUGUST
T-158-12233 | PS5-99-OB-5350C | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone G | 6 | In progress |  | 10 | DECEMBER
T-082-12234 | PS5-43-UR-5801D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone B | 1.1 | In progress |  | 45 | DECEMBER
T-837-12235 | PS5-67-OB-2621B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | To be completed |  | 24 | DECEMBER
T-937-12236 | PS5-05-OB-3610B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-06-03 | PS5-82-02 | PS5 - Milestone I | 8 | Closed | 17 | 15 | JUNE
T-279-12237 | PS5-12-UR-8309A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-02-03 | PS5-07-01 | PS5 - Milestone F | 5 | Closed | 8 | 29 | FEBRUARY
T-751-12238 | PS5-09-OB-5833B | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone I | 8 | In progress |  | 15 | OCTOBER
T-265-12239 | PS5-08-UR-7157A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone B | 1.1 | In progress |  | 22 | AUGUST
T-129-12240 | PS5-02-OB-4685D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone F | 5 | In progress |  | 28 | SEPTEMBER
T-131-12241 | PS5-50-OB-2341A | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone E | 4 | In progress |  | 29 | AUGUST
T-862-12242 | PS5-35-OB-6668D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone D | 3 | In progress |  | 12 | SEPTEMBER
T-117-12243 | PS5-14-UR-1906D | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-11-11 | PS5-07-01 | PS5 - Milestone D | 3 | Closed | 13 | 13 | NOVEMBER
T-527-12244 | PS5-41-OB-3327A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-11-25 | PS5-09-02 | PS5 - Milestone A | 1 | Closed | 42 | 48 | NOVEMBER
T-871-12245 | PS5-44-OB-5795B | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone I | 8 | To be completed |  | 8 | OCTOBER
T-223-12246 | PS5-66-OB-9006C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-09-07 | PS5-09-02 | PS5 - Milestone E | 4 | Closed | 44 | 48 | SEPTEMBER
T-532-12247 | PS5-23-OB-6801B | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-12-11 | PS5-63-01 | PS5 - Milestone H | 7 | Closed | 15 | 18 | DECEMBER
T-973-12248 | PS5-84-UR-5731A | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone G | 6 | On hold |  | 22 | AUGUST
T-753-12249 | PS5-30-UR-9892D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone F | 5 | To be completed |  | 29 | AUGUST
T-867-12250 | PS5-42-OB-1379A | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone H | 7 | To be completed |  | 12 | NOVEMBER
T-559-12251 | PS5-64-IK-4742D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-01-23 | PS5-03-23 | PS5 - Milestone D | 3 | Closed | 15 | 31 | JANUARY
T-947-12252 | PS5-36-UR-3718B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-10-07 | PS5-03-02 | PS5 - Milestone H | 7 | Closed | 5 | 26 | OCTOBER
T-244-12253 | PS5-44-UR-6233A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone I | 8 | To be completed |  | 15 | SEPTEMBER
T-652-12254 | PS5-52-IK-9164B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone D | 3 | In progress |  | 19 | AUGUST
T-701-12255 | PS5-54-UR-9342C | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-04-18 | PS5-03-01 | PS5 - Milestone C | 2 | Closed | 48 | 37 | APRIL
T-521-12256 | PS5-39-OB-7433C | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-10-27 | PS5-07-01 | PS5 - Milestone I | 8 | Closed | 18 | 12 | OCTOBER
T-664-12257 | PS5-15-IK-5029A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-01-15 | PS5-06-03 | PS5 - Milestone A | 1 | Closed | 28 | 9 | JANUARY
T-960-12258 | PS5-96-IK-9281D | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone A | 1 | To be completed |  | 8 | OCTOBER
T-041-12259 | PS5-91-OB-8312D | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone G | 6 | To be completed |  | 19 | OCTOBER
T-698-12260 | PS5-03-OB-2694B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone A | 1 | In progress |  | 16 | AUGUST
T-298-12261 | PS5-31-UR-1710A | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone D | 3 | To be completed |  | 41 | NOVEMBER
T-767-12262 | PS5-38-OB-8973B | CQM02 - Compressor | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone B | 1.1 | On hold |  | 42 | DECEMBER
T-883-12263 | PS5-80-OB-7161A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone D | 3 | In progress |  | 29 | DECEMBER
T-066-12264 | PS5-33-UR-1854C | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-12-11 | PS5-04-03 | PS5 - Milestone D | 3 | Closed | 33 | 39 | DECEMBER
T-996-12265 | PS5-16-OB-8440C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-11-04 | PS5-11-02 | PS5 - Milestone E | 4 | Closed | 21 | 20 | NOVEMBER
T-300-12266 | PS5-91-OB-9829D | CQX04 - Painting & Coating | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone D | 3 | To be completed |  | 34 | OCTOBER
T-195-12267 | PS5-66-UR-2078A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone A | 1 | To be completed |  | 39 | SEPTEMBER
T-421-12268 | PS5-26-OB-4434B | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone E | 4 | To be completed |  | 30 | SEPTEMBER
T-325-12269 | PS5-15-IK-2572C | CQT02 - Fiber Optic | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-11-20 | PS5-60-04 | PS5 - Milestone G | 6 | Closed | 16 | 33 | NOVEMBER
T-945-12270 | PS5-40-OB-1882D | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone G | 6 | In progress |  | 9 | SEPTEMBER
T-833-12271 | PS5-69-OB-2012A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-06-02 | PS5-01-01 | PS5 - Milestone H | 7 | Closed | 9 | 13 | JUNE
T-787-12272 | PS5-75-IK-3268D | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-04-16 | PS5-01-02 | PS5 - Milestone A | 1 | Closed | 48 | 6 | APRIL
T-638-12273 | PS5-66-UR-7562A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-02-11 | PS5-11-02 | PS5 - Milestone F | 5 | Closed | 37 | 46 | FEBRUARY
T-126-12274 | PS5-10-IK-9858D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | To be completed |  | 13 | NOVEMBER
T-569-12275 | PS5-94-OB-4428B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-02-11 | PS5-82-07 | PS5 - Milestone G | 6 | Closed | 6 | 44 | FEBRUARY
T-756-12276 | PS5-20-IK-1515D | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-04-13 | PS5-82-07 | PS5 - Milestone H | 7 | Closed | 9 | 15 | APRIL
T-834-12277 | PS5-23-UR-8040A | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-10-26 | PS5-08-01 | PS5 - Milestone G | 6 | Closed | 27 | 44 | OCTOBER
T-612-12278 | PS5-03-OB-9657D | CQP01 - Pipe Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone B | 1.1 | To be completed |  | 44 | DECEMBER
T-474-12279 | PS5-46-OB-6216B | CQP01 - Pipe Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-05-10 | PS5-01-03 | PS5 - Milestone B | 1.1 | Closed | 20 | 22 | MAY
T-536-12280 | PS5-24-UR-7697D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone E | 4 | To be completed |  | 17 | SEPTEMBER
T-822-12281 | PS5-09-IK-2526C | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone B | 1.1 | To be completed |  | 37 | DECEMBER
T-880-12282 | PS5-07-IK-6849A | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone B | 1.1 | To be completed |  | 22 | SEPTEMBER
T-372-12283 | PS5-64-OB-9162A | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-08-25 | PS5-12-02 | PS5 - Milestone H | 7 | Closed | 30 | 28 | AUGUST
T-670-12284 | PS5-81-IK-5281C | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-06-22 | PS5-06-02 | PS5 - Milestone D | 3 | Closed | 7 | 17 | JUNE
T-834-12285 | PS5-19-UR-9202A | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-09-05 | PS5-08-01 | PS5 - Milestone E | 4 | Closed | 46 | 11 | SEPTEMBER
T-186-12286 | PS5-39-UR-9949D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-06-22 | PS5-07-03 | PS5 - Milestone B | 1.1 | Closed | 20 | 44 | JUNE
T-947-12287 | PS5-96-IK-7463B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone C | 2 | In progress |  | 20 | NOVEMBER
T-910-12288 | PS5-18-IK-5958A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-07-01 | PS5-07-02 | PS5 - Milestone D | 3 | Closed | 28 | 38 | JULY
T-053-12289 | PS5-82-OB-7808D | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone D | 3 | In progress |  | 18 | NOVEMBER
T-906-12290 | PS5-33-OB-8555D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone F | 5 | On hold |  | 48 | SEPTEMBER
T-640-12291 | PS5-90-OB-7367B | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-07-03 | PS5-10-06 | PS5 - Milestone A | 1 | Closed | 5 | 44 | JULY
T-015-12292 | PS5-97-IK-5171A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-02-16 | PS5-01-03 | PS5 - Milestone D | 3 | Closed | 4 | 7 | FEBRUARY
T-301-12293 | PS5-15-IK-3338A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-03-27 | PS5-11-03 | PS5 - Milestone I | 8 | Closed | 19 | 34 | MARCH
T-333-12294 | PS5-57-IK-7396B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone F | 5 | On hold |  | 19 | SEPTEMBER
T-254-12295 | PS5-34-UR-5842A | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | To be completed |  | 29 | AUGUST
T-478-12296 | PS5-85-IK-5128C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-02-22 | PS5-09-01 | PS5 - Milestone G | 6 | Closed | 21 | 46 | FEBRUARY
T-962-12297 | PS5-23-OB-5514A | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | To be completed |  | 35 | AUGUST
T-086-12298 | PS5-10-OB-7361D | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | On hold |  | 23 | AUGUST
T-864-12299 | PS5-68-IK-5875B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | To be completed |  | 46 | AUGUST
T-610-12300 | PS5-52-IK-6780C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone A | 1 | In progress |  | 22 | SEPTEMBER
T-403-12301 | PS5-17-OB-7750B | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone B | 1.1 | In progress |  | 24 | OCTOBER
T-953-12302 | PS5-86-OB-5248C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone C | 2 | To be completed |  | 44 | SEPTEMBER
T-582-12303 | PS5-18-IK-8275D | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone A | 1 | On hold |  | 6 | AUGUST
T-731-12304 | PS5-63-UR-9088D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | To be completed |  | 38 | AUGUST
T-195-12305 | PS5-56-OB-4344C | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-07-08 | PS5-06-02 | PS5 - Milestone E | 4 | Closed | 9 | 22 | JULY
T-220-12306 | PS5-06-OB-4565A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone H | 7 | In progress |  | 41 | AUGUST
T-393-12307 | PS5-62-OB-7084C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-05-23 | PS5-02-01 | PS5 - Milestone E | 4 | Closed | 13 | 4 | MAY
T-567-12308 | PS5-69-IK-3059A | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-03-20 | PS5-04-01 | PS5 - Milestone H | 7 | Closed | 8 | 40 | MARCH
T-237-12309 | PS5-82-UR-7878D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone F | 5 | On hold |  | 42 | DECEMBER
T-064-12310 | PS5-34-IK-5906A | CQH03 - FCU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone I | 8 | To be completed |  | 15 | DECEMBER
T-649-12311 | PS5-47-OB-7329A | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone E | 4 | In progress |  | 43 | AUGUST
T-579-12312 | PS5-94-OB-3951D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-01-20 | PS5-11-01 | PS5 - Milestone C | 2 | Closed | 17 | 4 | JANUARY
T-518-12313 | PS5-50-OB-7082D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone C | 2 | In progress |  | 15 | DECEMBER
T-480-12314 | PS5-55-UR-1643C | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone A | 1 | To be completed |  | 38 | DECEMBER
T-049-12315 | PS5-27-UR-5218C | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-03-02 | PS5-06-01 | PS5 - Milestone H | 7 | Closed | 25 | 41 | MARCH
T-604-12316 | PS5-18-UR-6133D | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone E | 4 | On hold |  | 44 | AUGUST
T-264-12317 | PS5-25-UR-1915C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-12-15 | PS5-60-07 | PS5 - Milestone I | 8 | Closed | 43 | 39 | DECEMBER
T-365-12318 | PS5-96-OB-6950D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-08-01 | PS5-13-01 | PS5 - Milestone B | 1.1 | Closed | 38 | 30 | AUGUST
T-548-12319 | PS5-54-OB-6675D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone C | 2 | On hold |  | 47 | OCTOBER
T-518-12320 | PS5-49-UR-1727B | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | To be completed |  | 46 | NOVEMBER
T-447-12321 | PS5-06-OB-2382B | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-18 | PS5-60-04 | PS5 - Milestone B | 1.1 | Closed | 25 | 8 | MAY
T-408-12322 | PS5-90-IK-9976D | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-12-14 | PS5-12-01 | PS5 - Milestone A | 1 | Closed | 16 | 39 | DECEMBER
T-857-12323 | PS5-47-OB-3634B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-06-21 | PS5-06-02 | PS5 - Milestone E | 4 | Closed | 28 | 39 | JUNE
T-263-12324 | PS5-30-OB-9140C | CQM04 - Vessel | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone D | 3 | To be completed |  | 48 | SEPTEMBER
T-622-12325 | PS5-74-OB-1759C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone C | 2 | In progress |  | 12 | NOVEMBER
T-631-12326 | PS5-62-UR-7380D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone C | 2 | To be completed |  | 32 | OCTOBER
T-918-12327 | PS5-41-IK-5264C | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone B | 1.1 | To be completed |  | 24 | NOVEMBER
T-119-12328 | PS5-09-IK-1730A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone I | 8 | In progress |  | 9 | AUGUST
T-360-12329 | PS5-96-IK-4620A | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-05-14 | PS5-03-01 | PS5 - Milestone C | 2 | Closed | 20 | 14 | MAY
T-501-12330 | PS5-30-OB-8535D | CQP03 - Flange Management | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-03-18 | PS5-01-02 | PS5 - Milestone B | 1.1 | Closed | 40 | 42 | MARCH
T-711-12331 | PS5-02-OB-1401C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone A | 1 | In progress |  | 4 | AUGUST
T-706-12332 | PS5-18-OB-1599C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone B | 1.1 | To be completed |  | 41 | OCTOBER
T-059-12333 | PS5-07-UR-8680C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone C | 2 | To be completed |  | 29 | DECEMBER
T-141-12334 | PS5-69-OB-3926B | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-12-26 | PS5-11-01 | PS5 - Milestone E | 4 | Closed | 35 | 46 | DECEMBER
T-832-12335 | PS5-30-IK-3715D | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone D | 3 | In progress |  | 10 | SEPTEMBER
T-869-12336 | PS5-26-IK-6215B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone A | 1 | To be completed |  | 17 | SEPTEMBER
T-191-12337 | PS5-64-UR-2157B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-03-03 | PS5-01-01 | PS5 - Milestone C | 2 | Closed | 10 | 21 | MARCH
T-212-12338 | PS5-89-OB-7470C | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone I | 8 | In progress |  | 28 | NOVEMBER
T-374-12339 | PS5-21-OB-2994D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | To be completed |  | 40 | DECEMBER
T-698-12340 | PS5-72-OB-7830C | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone F | 5 | To be completed |  | 12 | DECEMBER
T-570-12341 | PS5-71-OB-7345A | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-08-18 | PS5-06-03 | PS5 - Milestone D | 3 | Closed | 48 | 35 | AUGUST
T-685-12342 | PS5-09-OB-5145B | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone H | 7 | To be completed |  | 22 | AUGUST
T-330-12343 | PS5-76-IK-1611B | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-03-21 | PS5-06-02 | PS5 - Milestone C | 2 | Closed | 21 | 22 | MARCH
T-586-12344 | PS5-85-OB-7961C | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-11-19 | PS5-03-01 | PS5 - Milestone A | 1 | Closed | 42 | 14 | NOVEMBER
T-825-12345 | PS5-85-UR-1550A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone I | 8 | To be completed |  | 44 | OCTOBER
T-670-12346 | PS5-18-UR-9460B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone G | 6 | In progress |  | 18 | DECEMBER
T-468-12347 | PS5-78-IK-2277C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | In progress |  | 27 | OCTOBER
T-266-12348 | PS5-21-UR-2114D | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone D | 3 | To be completed |  | 20 | DECEMBER
T-513-12349 | PS5-35-IK-8754A | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone C | 2 | To be completed |  | 32 | DECEMBER
T-693-12350 | PS5-74-OB-1879D | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone E | 4 | To be completed |  | 5 | OCTOBER
T-255-12351 | PS5-26-UR-2315C | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone C | 2 | To be completed |  | 30 | AUGUST
T-391-12352 | PS5-28-OB-9013C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone C | 2 | To be completed |  | 11 | AUGUST
T-297-12353 | PS5-57-OB-8878C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone H | 7 | In progress |  | 12 | NOVEMBER
T-320-12354 | PS5-46-UR-5190C | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone F | 5 | To be completed |  | 14 | SEPTEMBER
T-253-12355 | PS5-92-OB-6445D | CQS04 - Foam System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone I | 8 | On hold |  | 4 | SEPTEMBER
T-417-12356 | PS5-81-OB-3274C | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | In progress |  | 46 | OCTOBER
T-229-12357 | PS5-14-UR-6791C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-09-04 | PS5-08-01 | PS5 - Milestone G | 6 | Closed | 5 | 4 | SEPTEMBER
T-436-12358 | PS5-34-OB-4727D | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone E | 4 | To be completed |  | 41 | AUGUST
T-551-12359 | PS5-56-OB-8784C | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone B | 1.1 | To be completed |  | 34 | NOVEMBER
T-649-12360 | PS5-80-OB-5873B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone E | 4 | In progress |  | 23 | AUGUST
T-873-12361 | PS5-38-OB-2349B | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone D | 3 | On hold |  | 38 | NOVEMBER
T-863-12362 | PS5-21-IK-6460B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-05-13 | PS5-07-04 | PS5 - Milestone E | 4 | Closed | 34 | 23 | MAY
T-968-12363 | PS5-95-UR-6451B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-08-04 | PS5-01-06 | PS5 - Milestone D | 3 | Closed | 23 | 37 | AUGUST
T-273-12364 | PS5-39-IK-1585A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-02-11 | PS5-09-02 | PS5 - Milestone E | 4 | Closed | 9 | 45 | FEBRUARY
T-607-12365 | PS5-44-UR-7000A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone E | 4 | In progress |  | 36 | OCTOBER
T-669-12366 | PS5-92-IK-1605D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | To be completed |  | 26 | NOVEMBER
T-997-12367 | PS5-61-UR-5563C | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-03-22 | PS5-02-01 | PS5 - Milestone F | 5 | Closed | 27 | 44 | MARCH
T-385-12368 | PS5-31-UR-4509C | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone E | 4 | To be completed |  | 18 | NOVEMBER
T-964-12369 | PS5-61-UR-3901B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | On hold |  | 10 | OCTOBER
T-515-12370 | PS5-06-IK-4561A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone H | 7 | To be completed |  | 33 | NOVEMBER
T-163-12371 | PS5-25-OB-1042C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone E | 4 | On hold |  | 28 | AUGUST
T-592-12372 | PS5-02-IK-7379B | CQM02 - Compressor | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-05-19 | PS5-60-10 | PS5 - Milestone E | 4 | Closed | 5 | 23 | MAY
T-755-12373 | PS5-67-OB-4232C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-02-02 | PS5-01-09 | PS5 - Milestone C | 2 | Closed | 27 | 43 | FEBRUARY
T-798-12374 | PS5-93-UR-5699C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-07-18 | PS5-08-02 | PS5 - Milestone B | 1.1 | Closed | 18 | 15 | JULY
T-550-12375 | PS5-39-IK-4819C | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-01-05 | PS5-61-02 | PS5 - Milestone C | 2 | Closed | 22 | 46 | JANUARY
T-127-12376 | PS5-59-OB-6955C | CQI01 - Instrument Tubing | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-08-19 | PS5-05-03 | PS5 - Milestone B | 1.1 | Closed | 35 | 40 | AUGUST
T-283-12377 | PS5-76-UR-1347D | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-02-08 | PS5-13-01 | PS5 - Milestone G | 6 | Closed | 32 | 8 | FEBRUARY
T-831-12378 | PS5-33-OB-2050D | CQS03 - Deluge System | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | To be completed |  | 35 | SEPTEMBER
T-244-12379 | PS5-08-UR-1335B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone F | 5 | In progress |  | 46 | NOVEMBER
T-680-12380 | PS5-05-IK-8871C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | On hold |  | 30 | SEPTEMBER
T-587-12381 | PS5-65-UR-2059C | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone B | 1.1 | To be completed |  | 6 | DECEMBER
T-017-12382 | PS5-01-IK-9352D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone B | 1.1 | In progress |  | 31 | AUGUST
T-525-12383 | PS5-44-UR-4941C | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-05-12 | PS5-03-01 | PS5 - Milestone D | 3 | Closed | 36 | 25 | MAY
T-164-12384 | PS5-57-IK-1214B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone A | 1 | In progress |  | 47 | SEPTEMBER
T-967-12385 | PS5-43-OB-5664D | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone D | 3 | To be completed |  | 36 | SEPTEMBER
T-664-12386 | PS5-54-OB-7336C | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone E | 4 | To be completed |  | 23 | DECEMBER
T-794-12387 | PS5-68-OB-7152A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-07-25 | PS5-10-01 | PS5 - Milestone D | 3 | Closed | 12 | 47 | JULY
T-764-12388 | PS5-35-IK-6851D | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone D | 3 | To be completed |  | 30 | DECEMBER
T-479-12389 | PS5-78-IK-9663A | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-05-07 | PS5-10-04 | PS5 - Milestone C | 2 | Closed | 27 | 30 | MAY
T-470-12390 | PS5-36-UR-3421D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-15 | PS5-60-07 | PS5 - Milestone H | 7 | Closed | 31 | 10 | APRIL
T-361-12391 | PS5-14-IK-9187C | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-04-10 | PS5-99-01 | PS5 - Milestone F | 5 | Closed | 36 | 47 | APRIL
T-881-12392 | PS5-80-OB-3011C | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-06-15 | PS5-07-01 | PS5 - Milestone I | 8 | Closed | 40 | 38 | JUNE
T-700-12393 | PS5-82-OB-2876A | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone D | 3 | In progress |  | 39 | DECEMBER
T-028-12394 | PS5-31-UR-9411D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone H | 7 | In progress |  | 48 | OCTOBER
T-094-12395 | PS5-55-IK-2521B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-12-28 | PS5-60-04 | PS5 - Milestone D | 3 | Closed | 21 | 6 | DECEMBER
T-351-12396 | PS5-46-OB-7872C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone G | 6 | In progress |  | 30 | NOVEMBER
T-728-12397 | PS5-23-OB-1094A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-02-20 | PS5-01-04 | PS5 - Milestone H | 7 | Closed | 31 | 45 | FEBRUARY
T-420-12398 | PS5-67-UR-4212C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | In progress |  | 44 | SEPTEMBER
T-757-12399 | PS5-43-OB-5763D | CQX03 - Architectural | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone A | 1 | To be completed |  | 15 | AUGUST
T-081-12400 | PS5-03-OB-5829D | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-02-21 | PS5-82-07 | PS5 - Milestone A | 1 | Closed | 42 | 32 | FEBRUARY
T-193-12401 | PS5-51-IK-9812D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone G | 6 | To be completed |  | 15 | OCTOBER
T-232-12402 | PS5-54-OB-7851C | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone C | 2 | To be completed |  | 47 | OCTOBER
T-807-12403 | PS5-60-OB-9887A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-09-06 | PS5-06-02 | PS5 - Milestone B | 1.1 | Closed | 29 | 43 | SEPTEMBER
T-080-12404 | PS5-40-IK-8833D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-08-07 | PS5-61-02 | PS5 - Milestone D | 3 | Closed | 43 | 9 | AUGUST
T-520-12405 | PS5-36-OB-3995B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone F | 5 | In progress |  | 42 | DECEMBER
T-052-12406 | PS5-39-OB-8184D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-01-25 | PS5-01-01 | PS5 - Milestone H | 7 | Closed | 29 | 45 | JANUARY
T-137-12407 | PS5-52-OB-3754A | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-07-21 | PS5-62-01 | PS5 - Milestone E | 4 | Closed | 27 | 32 | JULY
T-675-12408 | PS5-20-OB-9811B | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-12-07 | PS5-01-05 | PS5 - Milestone G | 6 | Closed | 42 | 48 | DECEMBER
T-827-12409 | PS5-74-OB-6734C | CQP04 - Hydrotest | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | To be completed |  | 25 | DECEMBER
T-757-12410 | PS5-73-UR-3201A | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-12-12 | PS5-12-01 | PS5 - Milestone F | 5 | Closed | 23 | 10 | DECEMBER
T-630-12411 | PS5-62-OB-9260A | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone I | 8 | To be completed |  | 48 | AUGUST
T-812-12412 | PS5-34-OB-9961B | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-03-13 | PS5-12-01 | PS5 - Milestone B | 1.1 | Closed | 10 | 15 | MARCH
T-508-12413 | PS5-56-IK-9546D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone F | 5 | To be completed |  | 45 | DECEMBER
T-757-12414 | PS5-09-OB-9261B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone B | 1.1 | To be completed |  | 4 | SEPTEMBER
T-037-12415 | PS5-23-UR-4982A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-07-25 | PS5-62-01 | PS5 - Milestone F | 5 | Closed | 7 | 40 | JULY
T-236-12416 | PS5-36-UR-1871B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-08-09 | PS5-82-02 | PS5 - Milestone I | 8 | Closed | 37 | 46 | AUGUST
T-177-12417 | PS5-84-OB-6661A | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone G | 6 | On hold |  | 31 | OCTOBER
T-439-12418 | PS5-71-OB-6946C | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | On hold |  | 18 | DECEMBER
T-184-12419 | PS5-88-OB-8134D | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-04-16 | PS5-01-03 | PS5 - Milestone H | 7 | Closed | 29 | 14 | APRIL
T-081-12420 | PS5-86-OB-6812C | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone D | 3 | In progress |  | 35 | AUGUST
T-597-12421 | PS5-07-OB-2849A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone C | 2 | To be completed |  | 7 | NOVEMBER
T-805-12422 | PS5-78-OB-3845C | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone A | 1 | In progress |  | 33 | SEPTEMBER
T-535-12423 | PS5-48-IK-5485C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-08-21 | PS5-04-04 | PS5 - Milestone B | 1.1 | Closed | 31 | 35 | AUGUST
T-397-12424 | PS5-34-OB-9043C | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone H | 7 | To be completed |  | 30 | AUGUST
T-967-12425 | PS5-21-OB-9029C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-02-01 | PS5-02-03 | PS5 - Milestone E | 4 | Closed | 22 | 39 | FEBRUARY
T-789-12426 | PS5-35-OB-3135B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone C | 2 | On hold |  | 40 | OCTOBER
T-114-12427 | PS5-08-OB-7057A | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-10-03 | PS5-05-03 | PS5 - Milestone G | 6 | Closed | 10 | 4 | OCTOBER
T-410-12428 | PS5-86-OB-3390B | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-09-19 | PS5-01-04 | PS5 - Milestone A | 1 | Closed | 47 | 48 | SEPTEMBER
T-680-12429 | PS5-72-UR-1310C | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone I | 8 | To be completed |  | 7 | NOVEMBER
T-109-12430 | PS5-47-OB-5284A | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-09-21 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 18 | 31 | SEPTEMBER
T-486-12431 | PS5-82-OB-2891D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-12-17 | PS5-04-04 | PS5 - Milestone E | 4 | Closed | 6 | 34 | DECEMBER
T-572-12432 | PS5-48-OB-5121D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-06-16 | PS5-99-03 | PS5 - Milestone F | 5 | Closed | 23 | 11 | JUNE
T-163-12433 | PS5-54-OB-9593C | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone H | 7 | To be completed |  | 21 | OCTOBER
T-698-12434 | PS5-73-IK-1871C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-09-10 | PS5-02-03 | PS5 - Milestone E | 4 | Closed | 38 | 18 | SEPTEMBER
T-435-12435 | PS5-22-UR-6345A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-04-07 | PS5-06-03 | PS5 - Milestone G | 6 | Closed | 6 | 46 | APRIL
T-052-12436 | PS5-39-UR-8714B | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone B | 1.1 | On hold |  | 12 | OCTOBER
T-495-12437 | PS5-81-UR-1889B | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | In progress |  | 9 | OCTOBER
T-986-12438 | PS5-73-OB-4709A | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-01-28 | PS5-06-03 | PS5 - Milestone G | 6 | Closed | 39 | 34 | JANUARY
T-767-12439 | PS5-95-OB-5683D | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | To be completed |  | 4 | OCTOBER
T-703-12440 | PS5-43-OB-8121D | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-03-08 | PS5-03-03 | PS5 - Milestone A | 1 | Closed | 24 | 20 | MARCH
T-373-12441 | PS5-87-OB-9323B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | In progress |  | 27 | OCTOBER
T-544-12442 | PS5-63-IK-2604C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-08-11 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 18 | 43 | AUGUST
T-563-12443 | PS5-83-UR-4842D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone C | 2 | To be completed |  | 28 | SEPTEMBER
T-972-12444 | PS5-41-IK-2074C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-09-09 | PS5-07-04 | PS5 - Milestone I | 8 | Closed | 38 | 25 | SEPTEMBER
T-400-12445 | PS5-20-OB-6095C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-03-08 | PS5-82-01 | PS5 - Milestone B | 1.1 | Closed | 10 | 39 | MARCH
T-183-12446 | PS5-70-UR-5312A | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-08-21 | PS5-02-01 | PS5 - Milestone B | 1.1 | Closed | 9 | 36 | AUGUST
T-095-12447 | PS5-29-IK-3468C | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-04-21 | PS5-03-01 | PS5 - Milestone G | 6 | Closed | 34 | 28 | APRIL
T-769-12448 | PS5-82-IK-8457C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone B | 1.1 | In progress |  | 22 | SEPTEMBER
T-038-12449 | PS5-71-UR-1342B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone C | 2 | To be completed |  | 36 | NOVEMBER
T-718-12450 | PS5-20-OB-3517A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone I | 8 | To be completed |  | 42 | NOVEMBER
T-872-12451 | PS5-34-OB-5579A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone A | 1 | To be completed |  | 10 | AUGUST
T-934-12452 | PS5-64-OB-7406B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-09-18 | PS5-07-02 | PS5 - Milestone A | 1 | Closed | 7 | 45 | SEPTEMBER
T-473-12453 | PS5-18-OB-5555C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-04-13 | PS5-99-01 | PS5 - Milestone I | 8 | Closed | 39 | 31 | APRIL
T-505-12454 | PS5-41-IK-3672B | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-04-08 | PS5-03-01 | PS5 - Milestone D | 3 | Closed | 26 | 9 | APRIL
T-630-12455 | PS5-72-OB-5501D | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | To be completed |  | 39 | DECEMBER
T-336-12456 | PS5-70-OB-8760D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-02-23 | PS5-08-02 | PS5 - Milestone F | 5 | Closed | 43 | 17 | FEBRUARY
T-670-12457 | PS5-16-OB-4683B | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | In progress |  | 43 | AUGUST
T-632-12458 | PS5-89-OB-7988B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone C | 2 | In progress |  | 24 | OCTOBER
T-445-12459 | PS5-92-IK-1640A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone H | 7 | To be completed |  | 12 | AUGUST
T-431-12460 | PS5-61-OB-6971D | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone E | 4 | On hold |  | 30 | DECEMBER
T-414-12461 | PS5-91-IK-1984B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone B | 1.1 | To be completed |  | 39 | DECEMBER
T-487-12462 | PS5-95-IK-6656C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone G | 6 | To be completed |  | 13 | SEPTEMBER
T-879-12463 | PS5-18-OB-9892B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone D | 3 | In progress |  | 31 | NOVEMBER
T-545-12464 | PS5-55-UR-1725B | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone B | 1.1 | To be completed |  | 46 | DECEMBER
T-079-12465 | PS5-53-UR-1194C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-02-08 | PS5-01-09 | PS5 - Milestone D | 3 | Closed | 43 | 34 | FEBRUARY
T-737-12466 | PS5-24-OB-6349C | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone D | 3 | To be completed |  | 8 | OCTOBER
T-813-12467 | PS5-42-OB-9125D | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-04-03 | PS5-82-07 | PS5 - Milestone A | 1 | Closed | 33 | 4 | APRIL
T-052-12468 | PS5-91-UR-8472A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone B | 1.1 | On hold |  | 7 | OCTOBER
T-855-12469 | PS5-58-UR-7033D | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-01-03 | PS5-82-07 | PS5 - Milestone B | 1.1 | Closed | 16 | 27 | JANUARY
T-676-12470 | PS5-72-IK-3627A | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | In progress |  | 44 | OCTOBER
T-022-12471 | PS5-26-OB-2809C | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | To be completed |  | 31 | SEPTEMBER
T-762-12472 | PS5-61-IK-5012D | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | To be completed |  | 35 | AUGUST
T-799-12473 | PS5-91-OB-2427C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-06-28 | PS5-82-01 | PS5 - Milestone G | 6 | Closed | 4 | 7 | JUNE
T-220-12474 | PS5-52-OB-8989D | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone G | 6 | To be completed |  | 21 | DECEMBER
T-820-12475 | PS5-79-IK-7390C | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | In progress |  | 10 | SEPTEMBER
T-490-12476 | PS5-35-OB-6123B | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone I | 8 | To be completed |  | 10 | AUGUST
T-572-12477 | PS5-72-UR-6978D | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone H | 7 | In progress |  | 33 | DECEMBER
T-058-12478 | PS5-98-IK-1507D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-08-07 | PS5-61-02 | PS5 - Milestone I | 8 | Closed | 23 | 25 | AUGUST
T-489-12479 | PS5-50-IK-7362B | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone F | 5 | To be completed |  | 14 | NOVEMBER
T-685-12480 | PS5-80-UR-9776B | CQT04 - CCTV Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | To be completed |  | 42 | SEPTEMBER
T-546-12481 | PS5-50-OB-7393A | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone E | 4 | To be completed |  | 45 | DECEMBER
T-609-12482 | PS5-70-UR-6965A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-10-28 | PS5-62-02 | PS5 - Milestone G | 6 | Closed | 45 | 22 | OCTOBER
T-659-12483 | PS5-67-IK-8515D | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone B | 1.1 | To be completed |  | 6 | DECEMBER
T-968-12484 | PS5-07-OB-4565B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-09-21 | PS5-01-07 | PS5 - Milestone A | 1 | Closed | 13 | 22 | SEPTEMBER
T-280-12485 | PS5-14-OB-6196A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone E | 4 | On hold |  | 23 | SEPTEMBER
T-199-12486 | PS5-19-IK-7255C | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone F | 5 | On hold |  | 40 | NOVEMBER
T-075-12487 | PS5-23-OB-9349D | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone I | 8 | In progress |  | 28 | NOVEMBER
T-472-12488 | PS5-04-IK-4403C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | To be completed |  | 11 | AUGUST
T-241-12489 | PS5-31-UR-2670C | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone D | 3 | To be completed |  | 41 | NOVEMBER
T-574-12490 | PS5-05-OB-2741B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone B | 1.1 | In progress |  | 34 | AUGUST
T-218-12491 | PS5-75-UR-4315B | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone H | 7 | To be completed |  | 45 | OCTOBER
T-924-12492 | PS5-19-UR-9428A | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone A | 1 | To be completed |  | 35 | DECEMBER
T-184-12493 | PS5-77-UR-4287D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone F | 5 | In progress |  | 48 | SEPTEMBER
T-961-12494 | PS5-49-UR-2324C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone I | 8 | To be completed |  | 48 | OCTOBER
T-090-12495 | PS5-89-UR-9697B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone A | 1 | In progress |  | 10 | AUGUST
T-462-12496 | PS5-84-OB-1410B | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | To be completed |  | 6 | OCTOBER
T-873-12497 | PS5-20-OB-9270D | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-10-18 | PS5-60-10 | PS5 - Milestone I | 8 | Closed | 31 | 13 | OCTOBER
T-088-12498 | PS5-18-IK-6155A | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone F | 5 | On hold |  | 17 | DECEMBER
T-328-12499 | PS5-40-OB-9679C | CQI03 - Control Valve | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone E | 4 | To be completed |  | 29 | NOVEMBER
T-681-12500 | PS5-45-OB-3188B | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone F | 5 | In progress |  | 23 | DECEMBER
T-457-12501 | PS5-43-IK-9951B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | To be completed |  | 7 | NOVEMBER
T-935-12502 | PS5-46-UR-9242A | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone I | 8 | To be completed |  | 8 | DECEMBER
T-604-12503 | PS5-46-IK-2450C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone H | 7 | To be completed |  | 45 | DECEMBER
T-141-12504 | PS5-85-OB-1187A | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone C | 2 | To be completed |  | 23 | AUGUST
T-216-12505 | PS5-77-IK-8620B | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone F | 5 | To be completed |  | 32 | OCTOBER
T-221-12506 | PS5-12-OB-9424A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone I | 8 | To be completed |  | 47 | NOVEMBER
T-049-12507 | PS5-97-OB-5102D | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | To be completed |  | 15 | SEPTEMBER
T-543-12508 | PS5-22-IK-2873C | CQH02 - AHU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone E | 4 | On hold |  | 30 | NOVEMBER
T-140-12509 | PS5-07-UR-8593A | CQP01 - Pipe Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | To be completed |  | 23 | AUGUST
T-293-12510 | PS5-65-IK-3789A | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone D | 3 | On hold |  | 31 | SEPTEMBER
T-503-12511 | PS5-85-OB-8870C | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone F | 5 | To be completed |  | 34 | OCTOBER
T-548-12512 | PS5-46-OB-4212C | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-03-12 | PS5-62-01 | PS5 - Milestone D | 3 | Closed | 21 | 36 | MARCH
T-164-12513 | PS5-01-OB-8527D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-08-21 | PS5-82-07 | PS5 - Milestone G | 6 | Closed | 21 | 26 | AUGUST
T-282-12514 | PS5-44-OB-5560D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone F | 5 | To be completed |  | 6 | AUGUST
T-633-12515 | PS5-58-OB-5713C | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone E | 4 | To be completed |  | 21 | AUGUST
T-261-12516 | PS5-11-OB-8041B | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-11-24 | PS5-07-01 | PS5 - Milestone E | 4 | Closed | 41 | 12 | NOVEMBER
T-666-12517 | PS5-84-IK-7037C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone A | 1 | To be completed |  | 46 | AUGUST
T-672-12518 | PS5-59-OB-2955D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-12-24 | PS5-03-02 | PS5 - Milestone I | 8 | Closed | 31 | 35 | DECEMBER
T-246-12519 | PS5-33-OB-7457B | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone I | 8 | To be completed |  | 4 | OCTOBER
T-747-12520 | PS5-15-OB-2778A | CQM03 - Heat Exchanger | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone G | 6 | In progress |  | 5 | NOVEMBER
T-480-12521 | PS5-22-OB-7590D | CQM05 - Rotating Equipment | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone F | 5 | To be completed |  | 6 | OCTOBER
T-458-12522 | PS5-82-OB-3310C | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-10-22 | PS5-01-06 | PS5 - Milestone A | 1 | Closed | 48 | 29 | OCTOBER
T-062-12523 | PS5-30-OB-8416D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-01-12 | PS5-04-01 | PS5 - Milestone H | 7 | Closed | 30 | 33 | JANUARY
T-896-12524 | PS5-40-UR-6510B | CQE04 - Transformer | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-08-06 | PS5-99-01 | PS5 - Milestone G | 6 | Closed | 12 | 39 | AUGUST
T-611-12525 | PS5-17-OB-6745B | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone E | 4 | To be completed |  | 19 | OCTOBER
T-147-12526 | PS5-04-IK-3327A | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-04-12 | PS5-04-04 | PS5 - Milestone G | 6 | Closed | 27 | 28 | APRIL
T-458-12527 | PS5-40-OB-2956B | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone H | 7 | On hold |  | 7 | DECEMBER
T-376-12528 | PS5-39-OB-2427D | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | To be completed |  | 38 | NOVEMBER
T-537-12529 | PS5-46-OB-4595C | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone I | 8 | In progress |  | 43 | SEPTEMBER
T-559-12530 | PS5-67-OB-9392A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | In progress |  | 22 | OCTOBER
T-078-12531 | PS5-58-IK-5853A | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone A | 1 | To be completed |  | 14 | SEPTEMBER
T-977-12532 | PS5-93-IK-4006B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-07-15 | PS5-08-02 | PS5 - Milestone G | 6 | Closed | 44 | 32 | JULY
T-908-12533 | PS5-81-UR-5253D | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone H | 7 | In progress |  | 25 | OCTOBER
T-547-12534 | PS5-54-UR-6335C | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-12-25 | PS5-02-03 | PS5 - Milestone C | 2 | Closed | 26 | 6 | DECEMBER
T-761-12535 | PS5-19-IK-3916A | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-07-07 | PS5-99-02 | PS5 - Milestone C | 2 | Closed | 21 | 37 | JULY
T-649-12536 | PS5-84-IK-2547D | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone F | 5 | To be completed |  | 21 | NOVEMBER
T-237-12537 | PS5-63-OB-4714B | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-11-19 | PS5-06-01 | PS5 - Milestone B | 1.1 | Closed | 22 | 35 | NOVEMBER
T-549-12538 | PS5-51-UR-9015C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | To be completed |  | 33 | AUGUST
T-580-12539 | PS5-26-OB-4647D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone G | 6 | On hold |  | 12 | NOVEMBER
T-781-12540 | PS5-62-OB-5274A | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-07-22 | PS5-99-03 | PS5 - Milestone E | 4 | Closed | 24 | 33 | JULY
T-282-12541 | PS5-47-OB-2101C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone H | 7 | To be completed |  | 8 | AUGUST
T-818-12542 | PS5-09-UR-7461C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-05-11 | PS5-10-02 | PS5 - Milestone F | 5 | Closed | 39 | 23 | MAY
T-399-12543 | PS5-85-UR-4352A | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-06-05 | PS5-13-01 | PS5 - Milestone H | 7 | Closed | 41 | 15 | JUNE
T-143-12544 | PS5-22-OB-3711A | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-01-15 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 37 | 45 | JANUARY
T-371-12545 | PS5-57-OB-4750B | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-10-15 | PS5-12-02 | PS5 - Milestone G | 6 | Closed | 45 | 17 | OCTOBER
T-647-12546 | PS5-05-IK-7545A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-11-12 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 48 | 12 | NOVEMBER
T-807-12547 | PS5-98-OB-5432B | CQM01 - Pump Installation | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-12-08 | PS5-04-02 | PS5 - Milestone C | 2 | Closed | 34 | 35 | DECEMBER
T-974-12548 | PS5-69-UR-1562B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone A | 1 | In progress |  | 38 | OCTOBER
T-537-12549 | PS5-50-OB-2580D | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-04-28 | PS5-07-01 | PS5 - Milestone F | 5 | Closed | 5 | 14 | APRIL
T-651-12550 | PS5-59-OB-2739D | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone B | 1.1 | In progress |  | 41 | AUGUST
T-821-12551 | PS5-01-OB-9779C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone D | 3 | To be completed |  | 46 | DECEMBER
T-601-12552 | PS5-84-IK-4939B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone G | 6 | In progress |  | 45 | NOVEMBER
T-734-12553 | PS5-58-OB-8683C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone A | 1 | In progress |  | 24 | OCTOBER
T-370-12554 | PS5-42-UR-4195C | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-12-18 | PS5-13-01 | PS5 - Milestone H | 7 | Closed | 21 | 44 | DECEMBER
T-373-12555 | PS5-85-IK-8939D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-12-12 | PS5-09-04 | PS5 - Milestone C | 2 | Closed | 23 | 47 | DECEMBER
T-100-12556 | PS5-93-UR-9094D | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | In progress |  | 4 | SEPTEMBER
T-174-12557 | PS5-52-IK-9572D | CQE01 - HV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone C | 2 | In progress |  | 6 | DECEMBER
T-161-12558 | PS5-11-OB-3175D | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-07-16 | PS5-99-02 | PS5 - Milestone F | 5 | Closed | 40 | 36 | JULY
T-803-12559 | PS5-18-OB-3638D | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-09-21 | PS5-07-04 | PS5 - Milestone I | 8 | Closed | 5 | 27 | SEPTEMBER
T-852-12560 | PS5-17-OB-6367D | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone I | 8 | In progress |  | 33 | OCTOBER
T-589-12561 | PS5-72-OB-1794D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone G | 6 | To be completed |  | 36 | AUGUST
T-710-12562 | PS5-24-IK-9048A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-08-20 | PS5-61-02 | PS5 - Milestone F | 5 | Closed | 7 | 29 | AUGUST
T-567-12563 | PS5-12-OB-2129A | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-11-18 | PS5-99-03 | PS5 - Milestone B | 1.1 | Closed | 36 | 24 | NOVEMBER
T-541-12564 | PS5-79-OB-3450A | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-01-05 | PS5-05-03 | PS5 - Milestone F | 5 | Closed | 34 | 46 | JANUARY
T-808-12565 | PS5-20-OB-4504D | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone B | 1.1 | To be completed |  | 22 | OCTOBER
T-502-12566 | PS5-46-IK-3743A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | To be completed |  | 30 | NOVEMBER
T-920-12567 | PS5-78-IK-4629A | CQM02 - Compressor | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone H | 7 | To be completed |  | 15 | SEPTEMBER
T-987-12568 | PS5-21-IK-6009B | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone B | 1.1 | In progress |  | 7 | OCTOBER
T-614-12569 | PS5-19-UR-1227D | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-08-16 | PS5-01-01 | PS5 - Milestone H | 7 | Closed | 37 | 22 | AUGUST
T-062-12570 | PS5-53-OB-3996B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-11-10 | PS5-05-02 | PS5 - Milestone D | 3 | Closed | 19 | 19 | NOVEMBER
T-281-12571 | PS5-41-UR-2605B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone G | 6 | To be completed |  | 9 | DECEMBER
T-608-12572 | PS5-40-IK-1379D | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone H | 7 | In progress |  | 11 | NOVEMBER
T-235-12573 | PS5-33-OB-5402A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-09-10 | PS5-11-02 | PS5 - Milestone E | 4 | Closed | 45 | 11 | SEPTEMBER
T-824-12574 | PS5-75-UR-3410D | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone A | 1 | To be completed |  | 25 | AUGUST
T-015-12575 | PS5-86-OB-2663C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-09-01 | PS5-04-04 | PS5 - Milestone I | 8 | Closed | 6 | 29 | SEPTEMBER
T-094-12576 | PS5-50-IK-9171B | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-02-09 | PS5-04-01 | PS5 - Milestone D | 3 | Closed | 11 | 8 | FEBRUARY
T-411-12577 | PS5-57-OB-8074B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-01-02 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 19 | 14 | JANUARY
T-584-12578 | PS5-16-OB-8182C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone G | 6 | To be completed |  | 43 | DECEMBER
T-806-12579 | PS5-10-UR-5551D | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone I | 8 | In progress |  | 47 | DECEMBER
T-201-12580 | PS5-17-OB-1753A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | On hold |  | 6 | DECEMBER
T-715-12581 | PS5-66-OB-6768B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-08-20 | PS5-62-02 | PS5 - Milestone B | 1.1 | Closed | 33 | 11 | AUGUST
T-257-12582 | PS5-64-OB-4764D | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-07-06 | PS5-61-02 | PS5 - Milestone D | 3 | Closed | 34 | 11 | JULY
T-941-12583 | PS5-94-OB-1408B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone I | 8 | To be completed |  | 12 | NOVEMBER
T-450-12584 | PS5-96-UR-4375D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone F | 5 | To be completed |  | 42 | DECEMBER
T-376-12585 | PS5-35-OB-9065C | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone G | 6 | In progress |  | 8 | NOVEMBER
T-124-12586 | PS5-50-IK-4859B | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | To be completed |  | 6 | AUGUST
T-396-12587 | PS5-88-OB-2229A | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | To be completed |  | 15 | SEPTEMBER
T-097-12588 | PS5-99-OB-7552A | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone I | 8 | In progress |  | 21 | AUGUST
T-304-12589 | PS5-91-IK-4244B | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-04-15 | PS5-11-01 | PS5 - Milestone C | 2 | Closed | 41 | 21 | APRIL
T-659-12590 | PS5-95-UR-6787D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone H | 7 | In progress |  | 26 | OCTOBER
T-582-12591 | PS5-44-UR-1088C | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | In progress |  | 28 | OCTOBER
T-185-12592 | PS5-34-OB-6238C | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-06-26 | PS5-99-01 | PS5 - Milestone D | 3 | Closed | 19 | 27 | JUNE
T-007-12593 | PS5-06-OB-8790C | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | To be completed |  | 24 | AUGUST
T-169-12594 | PS5-87-UR-8626B | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | On hold |  | 33 | SEPTEMBER
T-110-12595 | PS5-84-IK-5865D | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-08-04 | PS5-06-03 | PS5 - Milestone A | 1 | Closed | 8 | 34 | AUGUST
T-994-12596 | PS5-47-IK-3395A | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-07-20 | PS5-99-03 | PS5 - Milestone F | 5 | Closed | 42 | 38 | JULY
T-597-12597 | PS5-78-IK-1416B | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone F | 5 | On hold |  | 12 | SEPTEMBER
T-875-12598 | PS5-85-OB-8832B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-11-19 | PS5-09-02 | PS5 - Milestone H | 7 | Closed | 40 | 17 | NOVEMBER
T-978-12599 | PS5-50-UR-9983A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-02-19 | PS5-99-03 | PS5 - Milestone H | 7 | Closed | 30 | 43 | FEBRUARY
T-937-12600 | PS5-44-OB-6901D | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-03-27 | PS5-05-02 | PS5 - Milestone C | 2 | Closed | 31 | 11 | MARCH
T-493-12601 | PS5-74-UR-1201B | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | To be completed |  | 45 | AUGUST
T-809-12602 | PS5-40-UR-5999A | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-09-21 | PS5-13-01 | PS5 - Milestone I | 8 | Closed | 47 | 13 | SEPTEMBER
T-718-12603 | PS5-19-OB-8269C | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone H | 7 | To be completed |  | 11 | OCTOBER
T-163-12604 | PS5-13-UR-7458C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-05-10 | PS5-04-01 | PS5 - Milestone C | 2 | Closed | 45 | 16 | MAY
T-279-12605 | PS5-73-OB-9355A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone E | 4 | To be completed |  | 13 | NOVEMBER
T-790-12606 | PS5-47-IK-6131B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone D | 3 | To be completed |  | 24 | OCTOBER
T-117-12607 | PS5-91-IK-6859A | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | To be completed |  | 41 | DECEMBER
T-735-12608 | PS5-54-OB-7896A | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-04-09 | PS5-12-02 | PS5 - Milestone H | 7 | Closed | 48 | 47 | APRIL
T-041-12609 | PS5-76-OB-3722D | CQT04 - CCTV Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone G | 6 | To be completed |  | 6 | DECEMBER
T-681-12610 | PS5-25-OB-2068A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | To be completed |  | 14 | AUGUST
T-457-12611 | PS5-48-OB-7928D | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | To be completed |  | 20 | DECEMBER
T-889-12612 | PS5-66-IK-9226B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | To be completed |  | 44 | NOVEMBER
T-395-12613 | PS5-74-OB-3504C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone H | 7 | To be completed |  | 36 | SEPTEMBER
T-405-12614 | PS5-76-OB-3622A | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone B | 1.1 | In progress |  | 13 | OCTOBER
T-329-12615 | PS5-21-UR-1900A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone E | 4 | To be completed |  | 26 | SEPTEMBER
T-694-12616 | PS5-69-OB-8564C | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone D | 3 | To be completed |  | 40 | OCTOBER
T-110-12617 | PS5-30-OB-8204B | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-10-20 | PS5-02-02 | PS5 - Milestone C | 2 | Closed | 9 | 28 | OCTOBER
T-671-12618 | PS5-75-OB-8975D | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-07-15 | PS5-11-01 | PS5 - Milestone F | 5 | Closed | 40 | 8 | JULY
T-809-12619 | PS5-73-OB-1766A | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-01-18 | PS5-60-01 | PS5 - Milestone G | 6 | Closed | 12 | 12 | JANUARY
T-262-12620 | PS5-56-OB-3973B | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-04-21 | PS5-63-04 | PS5 - Milestone C | 2 | Closed | 9 | 33 | APRIL
T-123-12621 | PS5-14-UR-1025B | CQP04 - Hydrotest | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone I | 8 | To be completed |  | 7 | NOVEMBER
T-714-12622 | PS5-23-OB-8192C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone A | 1 | On hold |  | 19 | SEPTEMBER
T-148-12623 | PS5-45-IK-3115C | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-01-06 | PS5-07-02 | PS5 - Milestone H | 7 | Closed | 30 | 4 | JANUARY
T-476-12624 | PS5-04-OB-1157D | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone I | 8 | On hold |  | 18 | AUGUST
T-682-12625 | PS5-98-IK-1970B | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-09-04 | PS5-10-03 | PS5 - Milestone C | 2 | Closed | 48 | 45 | SEPTEMBER
T-155-12626 | PS5-96-OB-9251B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-09-10 | PS5-01-09 | PS5 - Milestone B | 1.1 | Closed | 48 | 19 | SEPTEMBER
T-192-12627 | PS5-11-OB-8979A | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone E | 4 | To be completed |  | 28 | OCTOBER
T-822-12628 | PS5-95-OB-1767D | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-07-28 | PS5-11-02 | PS5 - Milestone I | 8 | Closed | 9 | 16 | JULY
T-108-12629 | PS5-33-UR-8699B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone F | 5 | In progress |  | 13 | OCTOBER
T-503-12630 | PS5-16-IK-6825D | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone G | 6 | To be completed |  | 14 | SEPTEMBER
T-532-12631 | PS5-67-OB-7453B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-10-22 | PS5-07-02 | PS5 - Milestone A | 1 | Closed | 30 | 23 | OCTOBER
T-147-12632 | PS5-12-IK-2324D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone E | 4 | In progress |  | 31 | AUGUST
T-829-12633 | PS5-12-IK-9646A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-27 | PS5-60-01 | PS5 - Milestone H | 7 | Closed | 22 | 39 | JUNE
T-249-12634 | PS5-55-OB-8998C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-10-23 | PS5-07-03 | PS5 - Milestone G | 6 | Closed | 40 | 31 | OCTOBER
T-982-12635 | PS5-31-UR-6899B | CQE04 - Transformer | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone F | 5 | In progress |  | 39 | OCTOBER
T-724-12636 | PS5-83-UR-9879C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-02-02 | PS5-01-03 | PS5 - Milestone B | 1.1 | Closed | 30 | 14 | FEBRUARY
T-677-12637 | PS5-84-UR-5588B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone D | 3 | In progress |  | 37 | OCTOBER
T-844-12638 | PS5-56-OB-5872C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone B | 1.1 | In progress |  | 15 | SEPTEMBER
T-491-12639 | PS5-34-UR-6418A | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-01-22 | PS5-07-02 | PS5 - Milestone G | 6 | Closed | 30 | 48 | JANUARY
T-752-12640 | PS5-49-OB-4250A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone D | 3 | In progress |  | 12 | DECEMBER
T-021-12641 | PS5-41-UR-9530C | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone G | 6 | In progress |  | 26 | DECEMBER
T-747-12642 | PS5-63-OB-1435D | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-07-06 | PS5-11-02 | PS5 - Milestone H | 7 | Closed | 28 | 30 | JULY
T-510-12643 | PS5-18-IK-2546A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-02-24 | PS5-07-01 | PS5 - Milestone I | 8 | Closed | 19 | 17 | FEBRUARY
T-707-12644 | PS5-86-UR-2002B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-02-04 | PS5-62-01 | PS5 - Milestone E | 4 | Closed | 36 | 40 | FEBRUARY
T-076-12645 | PS5-32-OB-3762B | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone H | 7 | On hold |  | 4 | OCTOBER
T-787-12646 | PS5-53-OB-5521D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-06-03 | PS5-04-04 | PS5 - Milestone F | 5 | Closed | 12 | 18 | JUNE
T-257-12647 | PS5-22-UR-4189B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone G | 6 | In progress |  | 8 | SEPTEMBER
T-232-12648 | PS5-43-OB-4417A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-03-05 | PS5-07-03 | PS5 - Milestone D | 3 | Closed | 24 | 24 | MARCH
T-307-12649 | PS5-67-OB-4204C | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone C | 2 | In progress |  | 17 | SEPTEMBER
T-586-12650 | PS5-34-UR-9155A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-09-14 | PS5-06-01 | PS5 - Milestone D | 3 | Closed | 27 | 39 | SEPTEMBER
T-813-12651 | PS5-16-UR-1678A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | To be completed |  | 43 | SEPTEMBER
T-534-12652 | PS5-33-OB-9755B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-05-01 | PS5-01-07 | PS5 - Milestone F | 5 | Closed | 9 | 27 | MAY
T-120-12653 | PS5-04-IK-1458A | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone D | 3 | To be completed |  | 44 | AUGUST
T-858-12654 | PS5-29-OB-3433D | CQP02 - Valve Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone H | 7 | To be completed |  | 14 | AUGUST
T-554-12655 | PS5-18-IK-4355A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone I | 8 | To be completed |  | 6 | NOVEMBER
T-494-12656 | PS5-94-IK-1879C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone B | 1.1 | To be completed |  | 30 | AUGUST
T-766-12657 | PS5-70-OB-7233B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-01-09 | PS5-60-10 | PS5 - Milestone I | 8 | Closed | 39 | 27 | JANUARY
T-028-12658 | PS5-05-UR-9594D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone C | 2 | In progress |  | 12 | DECEMBER
T-581-12659 | PS5-41-OB-7158C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone A | 1 | In progress |  | 15 | AUGUST
T-657-12660 | PS5-41-OB-2143C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-06-04 | PS5-01-02 | PS5 - Milestone I | 8 | Closed | 40 | 37 | JUNE
T-921-12661 | PS5-46-UR-7627C | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone G | 6 | To be completed |  | 48 | AUGUST
T-069-12662 | PS5-78-OB-6600D | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone E | 4 | On hold |  | 4 | AUGUST
T-442-12663 | PS5-73-OB-1646D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone H | 7 | On hold |  | 23 | SEPTEMBER
T-066-12664 | PS5-42-OB-9867D | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-05-14 | PS5-07-03 | PS5 - Milestone B | 1.1 | Closed | 33 | 16 | MAY
T-085-12665 | PS5-35-OB-9799D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone C | 2 | In progress |  | 46 | AUGUST
T-942-12666 | PS5-85-UR-3603D | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone I | 8 | To be completed |  | 32 | AUGUST
T-163-12667 | PS5-07-IK-8943D | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | To be completed |  | 34 | DECEMBER
T-524-12668 | PS5-44-OB-2574B | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-08-11 | PS5-01-01 | PS5 - Milestone A | 1 | Closed | 10 | 31 | AUGUST
T-833-12669 | PS5-75-OB-8239D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone E | 4 | In progress |  | 27 | AUGUST
T-221-12670 | PS5-97-OB-2044A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | On hold |  | 26 | DECEMBER
T-641-12671 | PS5-36-UR-2239A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone D | 3 | To be completed |  | 21 | AUGUST
T-461-12672 | PS5-28-OB-4408D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | In progress |  | 45 | NOVEMBER
T-424-12673 | PS5-01-IK-8055A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-02-03 | PS5-09-03 | PS5 - Milestone H | 7 | Closed | 42 | 21 | FEBRUARY
T-373-12674 | PS5-20-OB-1192B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone D | 3 | On hold |  | 11 | NOVEMBER
T-149-12675 | PS5-41-OB-9327C | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone A | 1 | On hold |  | 34 | NOVEMBER
T-615-12676 | PS5-34-IK-6571D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | To be completed |  | 12 | OCTOBER
T-079-12677 | PS5-14-IK-6600D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone F | 5 | In progress |  | 34 | OCTOBER
T-257-12678 | PS5-10-OB-4497A | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-12-03 | PS5-05-01 | PS5 - Milestone A | 1 | Closed | 23 | 16 | DECEMBER
T-835-12679 | PS5-68-OB-1708D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone C | 2 | To be completed |  | 26 | DECEMBER
T-157-12680 | PS5-34-OB-9022A | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone D | 3 | In progress |  | 44 | OCTOBER
T-251-12681 | PS5-14-OB-7495C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | To be completed |  | 41 | AUGUST
T-786-12682 | PS5-37-OB-5174A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone H | 7 | To be completed |  | 7 | OCTOBER
T-423-12683 | PS5-11-OB-4098D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-01-01 | PS5-61-01 | PS5 - Milestone F | 5 | Closed | 45 | 6 | JANUARY
T-996-12684 | PS5-87-IK-8278C | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-08-21 | PS5-11-03 | PS5 - Milestone C | 2 | Closed | 47 | 18 | AUGUST
T-822-12685 | PS5-34-OB-6726D | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone G | 6 | To be completed |  | 32 | AUGUST
T-047-12686 | PS5-15-UR-1370A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone G | 6 | On hold |  | 11 | SEPTEMBER
T-103-12687 | PS5-95-OB-4616C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-03-15 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 38 | 39 | MARCH
T-734-12688 | PS5-08-OB-1299D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone F | 5 | In progress |  | 23 | AUGUST
T-754-12689 | PS5-60-UR-9227A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-07-16 | PS5-01-03 | PS5 - Milestone H | 7 | Closed | 16 | 21 | JULY
T-964-12690 | PS5-36-OB-4320B | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-06-02 | PS5-82-01 | PS5 - Milestone E | 4 | Closed | 48 | 31 | JUNE
T-330-12691 | PS5-53-OB-9269C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-01-26 | PS5-02-01 | PS5 - Milestone E | 4 | Closed | 21 | 20 | JANUARY
T-283-12692 | PS5-58-IK-9849C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone G | 6 | To be completed |  | 7 | NOVEMBER
T-754-12693 | PS5-88-OB-5798D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone H | 7 | On hold |  | 34 | AUGUST
T-593-12694 | PS5-76-UR-6570A | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-04-24 | PS5-63-01 | PS5 - Milestone C | 2 | Closed | 29 | 28 | APRIL
T-159-12695 | PS5-13-OB-3674B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-10-25 | PS5-62-02 | PS5 - Milestone F | 5 | Closed | 16 | 28 | OCTOBER
T-243-12696 | PS5-89-IK-1100D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-11-04 | PS5-61-01 | PS5 - Milestone C | 2 | Closed | 22 | 22 | NOVEMBER
T-954-12697 | PS5-86-IK-9901A | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone G | 6 | To be completed |  | 36 | OCTOBER
T-095-12698 | PS5-89-OB-6643B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone C | 2 | To be completed |  | 40 | AUGUST
T-036-12699 | PS5-76-OB-3881A | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-03-10 | PS5-01-02 | PS5 - Milestone G | 6 | Closed | 7 | 32 | MARCH
T-750-12700 | PS5-77-IK-5432B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | To be completed |  | 4 | DECEMBER
T-172-12701 | PS5-80-OB-9579D | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone A | 1 | To be completed |  | 38 | DECEMBER
T-986-12702 | PS5-18-IK-2834A | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone E | 4 | To be completed |  | 16 | AUGUST
T-040-12703 | PS5-02-OB-5035A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-04-28 | PS5-10-05 | PS5 - Milestone B | 1.1 | Closed | 26 | 39 | APRIL
T-295-12704 | PS5-23-IK-5345B | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone C | 2 | To be completed |  | 39 | DECEMBER
T-810-12705 | PS5-11-OB-5404A | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone H | 7 | To be completed |  | 19 | SEPTEMBER
T-856-12706 | PS5-34-OB-4510C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone F | 5 | On hold |  | 29 | SEPTEMBER
T-777-12707 | PS5-41-OB-9919B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone F | 5 | To be completed |  | 27 | SEPTEMBER
T-505-12708 | PS5-25-IK-9413D | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone C | 2 | To be completed |  | 41 | AUGUST
T-248-12709 | PS5-36-OB-1889B | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | On hold |  | 6 | DECEMBER
T-372-12710 | PS5-64-IK-6201B | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | To be completed |  | 25 | SEPTEMBER
T-886-12711 | PS5-87-OB-3194C | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone D | 3 | On hold |  | 8 | OCTOBER
T-050-12712 | PS5-95-OB-8929D | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone B | 1.1 | To be completed |  | 41 | AUGUST
T-088-12713 | PS5-22-OB-5316A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone B | 1.1 | To be completed |  | 31 | AUGUST
T-996-12714 | PS5-81-UR-4277D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone I | 8 | To be completed |  | 27 | AUGUST
T-003-12715 | PS5-07-OB-6464A | CQP03 - Flange Management | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone B | 1.1 | In progress |  | 41 | OCTOBER
T-705-12716 | PS5-56-OB-7357A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-09-01 | PS5-01-08 | PS5 - Milestone A | 1 | Closed | 14 | 27 | SEPTEMBER
T-162-12717 | PS5-75-UR-2917C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone G | 6 | To be completed |  | 12 | OCTOBER
T-149-12718 | PS5-88-OB-4265C | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | In progress |  | 43 | SEPTEMBER
T-009-12719 | PS5-79-OB-3642C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-05-03 | PS5-12-02 | PS5 - Milestone E | 4 | Closed | 23 | 48 | MAY
T-168-12720 | PS5-34-UR-9944D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone D | 3 | To be completed |  | 14 | DECEMBER
T-805-12721 | PS5-46-UR-4673C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-09-13 | PS5-02-03 | PS5 - Milestone B | 1.1 | Closed | 44 | 36 | SEPTEMBER
T-593-12722 | PS5-79-OB-3491D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-06-25 | PS5-82-01 | PS5 - Milestone B | 1.1 | Closed | 16 | 15 | JUNE
T-111-12723 | PS5-14-IK-2798D | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-04-05 | PS5-10-01 | PS5 - Milestone H | 7 | Closed | 4 | 10 | APRIL
T-318-12724 | PS5-68-OB-6206A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone E | 4 | In progress |  | 17 | AUGUST
T-739-12725 | PS5-79-OB-2131C | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-14 | PS5-60-04 | PS5 - Milestone F | 5 | Closed | 18 | 35 | FEBRUARY
T-106-12726 | PS5-24-OB-6441B | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-07-15 | PS5-99-01 | PS5 - Milestone D | 3 | Closed | 28 | 16 | JULY
T-707-12727 | PS5-29-IK-7142A | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-06-22 | PS5-05-01 | PS5 - Milestone D | 3 | Closed | 34 | 31 | JUNE
T-135-12728 | PS5-63-IK-9411B | CQM04 - Vessel | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone I | 8 | On hold |  | 32 | DECEMBER
T-511-12729 | PS5-26-IK-6732B | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-11-20 | PS5-10-04 | PS5 - Milestone H | 7 | Closed | 13 | 8 | NOVEMBER
T-421-12730 | PS5-57-OB-4572A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone F | 5 | In progress |  | 14 | SEPTEMBER
T-270-12731 | PS5-76-OB-7931B | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone H | 7 | In progress |  | 19 | SEPTEMBER
T-039-12732 | PS5-43-IK-5143C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-02-17 | PS5-03-01 | PS5 - Milestone H | 7 | Closed | 21 | 39 | FEBRUARY
T-666-12733 | PS5-55-IK-9155A | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-07-05 | PS5-82-07 | PS5 - Milestone G | 6 | Closed | 4 | 46 | JULY
T-286-12734 | PS5-80-UR-6291A | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone I | 8 | To be completed |  | 28 | NOVEMBER
T-480-12735 | PS5-87-OB-6086C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone C | 2 | In progress |  | 19 | SEPTEMBER
T-350-12736 | PS5-55-OB-6547A | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone G | 6 | To be completed |  | 44 | AUGUST
T-593-12737 | PS5-23-OB-7778B | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | In progress |  | 32 | NOVEMBER
T-209-12738 | PS5-29-OB-6071C | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-05-15 | PS5-11-03 | PS5 - Milestone B | 1.1 | Closed | 29 | 36 | MAY
T-319-12739 | PS5-33-OB-9292C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone G | 6 | To be completed |  | 5 | SEPTEMBER
T-410-12740 | PS5-12-OB-3561C | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-05-04 | PS5-10-01 | PS5 - Milestone B | 1.1 | Closed | 28 | 16 | MAY
T-029-12741 | PS5-79-UR-5624D | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone E | 4 | On hold |  | 21 | SEPTEMBER
T-928-12742 | PS5-39-OB-7019B | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone F | 5 | To be completed |  | 17 | SEPTEMBER
T-340-12743 | PS5-37-OB-8753D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone I | 8 | In progress |  | 15 | AUGUST
T-779-12744 | PS5-54-OB-5377C | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-08-01 | PS5-10-06 | PS5 - Milestone F | 5 | Closed | 12 | 38 | AUGUST
T-119-12745 | PS5-18-OB-5630D | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone H | 7 | To be completed |  | 7 | DECEMBER
T-916-12746 | PS5-07-OB-7932B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | To be completed |  | 30 | NOVEMBER
T-737-12747 | PS5-46-IK-1286D | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | In progress |  | 32 | AUGUST
T-234-12748 | PS5-94-OB-6487B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | To be completed |  | 31 | AUGUST
T-741-12749 | PS5-67-UR-3794A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone G | 6 | To be completed |  | 26 | OCTOBER
T-465-12750 | PS5-31-OB-3365B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone B | 1.1 | To be completed |  | 9 | DECEMBER
T-808-12751 | PS5-95-UR-4683B | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone B | 1.1 | To be completed |  | 39 | AUGUST
T-331-12752 | PS5-54-OB-9978B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-26 | PS5-60-07 | PS5 - Milestone B | 1.1 | Closed | 20 | 10 | JULY
T-731-12753 | PS5-93-IK-2414C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-08-18 | PS5-61-01 | PS5 - Milestone I | 8 | Closed | 4 | 13 | AUGUST
T-188-12754 | PS5-63-IK-4827B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | On hold |  | 34 | NOVEMBER
T-612-12755 | PS5-63-UR-8152B | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone E | 4 | In progress |  | 6 | OCTOBER
T-485-12756 | PS5-72-OB-6303C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone H | 7 | To be completed |  | 17 | AUGUST
T-291-12757 | PS5-15-OB-6578C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-05-06 | PS5-02-02 | PS5 - Milestone I | 8 | Closed | 35 | 6 | MAY
T-192-12758 | PS5-61-OB-8949B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-07-13 | PS5-61-02 | PS5 - Milestone E | 4 | Closed | 32 | 16 | JULY
T-424-12759 | PS5-99-OB-7587A | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-12-19 | PS5-10-06 | PS5 - Milestone C | 2 | Closed | 37 | 8 | DECEMBER
T-655-12760 | PS5-07-UR-6732C | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-03-03 | PS5-60-07 | PS5 - Milestone C | 2 | Closed | 5 | 24 | MARCH
T-876-12761 | PS5-12-OB-2960B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-05-14 | PS5-01-03 | PS5 - Milestone I | 8 | Closed | 26 | 15 | MAY
T-130-12762 | PS5-68-UR-9735D | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone G | 6 | In progress |  | 22 | SEPTEMBER
T-035-12763 | PS5-93-IK-4891C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-05-03 | PS5-06-01 | PS5 - Milestone E | 4 | Closed | 46 | 12 | MAY
T-988-12764 | PS5-38-IK-7054A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone A | 1 | On hold |  | 32 | NOVEMBER
T-404-12765 | PS5-76-OB-1808D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone D | 3 | In progress |  | 17 | SEPTEMBER
T-231-12766 | PS5-69-OB-7424B | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone E | 4 | To be completed |  | 35 | DECEMBER
T-483-12767 | PS5-02-OB-8478C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone F | 5 | In progress |  | 39 | NOVEMBER
T-542-12768 | PS5-38-OB-6819B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-07-04 | PS5-82-02 | PS5 - Milestone D | 3 | Closed | 19 | 33 | JULY
T-792-12769 | PS5-13-IK-9826A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | In progress |  | 37 | AUGUST
T-563-12770 | PS5-52-OB-4855C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-03-06 | PS5-02-02 | PS5 - Milestone G | 6 | Closed | 9 | 23 | MARCH
T-058-12771 | PS5-02-IK-4220A | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-07-25 | PS5-07-01 | PS5 - Milestone I | 8 | Closed | 8 | 28 | JULY
T-536-12772 | PS5-02-OB-6718C | CQM04 - Vessel | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-06-16 | PS5-10-04 | PS5 - Milestone A | 1 | Closed | 22 | 5 | JUNE
T-343-12773 | PS5-27-UR-3415A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone B | 1.1 | In progress |  | 19 | NOVEMBER
T-717-12774 | PS5-44-OB-2413D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone H | 7 | To be completed |  | 39 | DECEMBER
T-835-12775 | PS5-59-OB-3852C | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone D | 3 | In progress |  | 32 | NOVEMBER
T-843-12776 | PS5-78-OB-7425C | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-08-05 | PS5-82-07 | PS5 - Milestone D | 3 | Closed | 41 | 8 | AUGUST
T-026-12777 | PS5-13-UR-2206C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone F | 5 | On hold |  | 6 | OCTOBER
T-918-12778 | PS5-71-OB-8811A | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone D | 3 | In progress |  | 11 | SEPTEMBER
T-361-12779 | PS5-10-IK-2221D | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-09-19 | PS5-60-04 | PS5 - Milestone D | 3 | Closed | 39 | 6 | SEPTEMBER
T-987-12780 | PS5-34-IK-4208B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-12-17 | PS5-99-02 | PS5 - Milestone H | 7 | Closed | 39 | 11 | DECEMBER
T-296-12781 | PS5-58-UR-5779C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-03-15 | PS5-08-02 | PS5 - Milestone E | 4 | Closed | 43 | 6 | MARCH
T-309-12782 | PS5-93-OB-7200C | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-04-18 | PS5-01-07 | PS5 - Milestone A | 1 | Closed | 13 | 22 | APRIL
T-812-12783 | PS5-41-UR-6018B | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone I | 8 | On hold |  | 11 | OCTOBER
T-192-12784 | PS5-35-UR-1103B | CQE05 - Switchgear | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-07-12 | PS5-01-02 | PS5 - Milestone C | 2 | Closed | 28 | 35 | JULY
T-278-12785 | PS5-75-IK-7600B | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone D | 3 | To be completed |  | 16 | DECEMBER
T-437-12786 | PS5-22-UR-9598B | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-10-09 | PS5-61-02 | PS5 - Milestone G | 6 | Closed | 32 | 15 | OCTOBER
T-556-12787 | PS5-03-OB-3628D | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-10-25 | PS5-04-04 | PS5 - Milestone B | 1.1 | Closed | 15 | 39 | OCTOBER
T-933-12788 | PS5-78-UR-6163C | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-12-01 | PS5-63-01 | PS5 - Milestone D | 3 | Closed | 29 | 36 | DECEMBER
T-694-12789 | PS5-81-UR-5632D | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone H | 7 | In progress |  | 33 | OCTOBER
T-184-12790 | PS5-69-IK-7350C | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-09-04 | PS5-01-02 | PS5 - Milestone C | 2 | Closed | 5 | 14 | SEPTEMBER
T-036-12791 | PS5-69-UR-7727B | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone F | 5 | To be completed |  | 42 | OCTOBER
T-968-12792 | PS5-93-IK-2891C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-04-24 | PS5-02-01 | PS5 - Milestone E | 4 | Closed | 46 | 42 | APRIL
T-570-12793 | PS5-58-OB-6851C | CQI03 - Control Valve | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone G | 6 | To be completed |  | 5 | OCTOBER
T-431-12794 | PS5-55-IK-7690B | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-11-09 | PS5-12-01 | PS5 - Milestone B | 1.1 | Closed | 25 | 39 | NOVEMBER
T-823-12795 | PS5-97-OB-5198A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone D | 3 | In progress |  | 9 | OCTOBER
T-958-12796 | PS5-47-IK-4127A | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-11-28 | PS5-63-01 | PS5 - Milestone A | 1 | Closed | 32 | 17 | NOVEMBER
T-156-12797 | PS5-46-UR-4956C | CQM03 - Heat Exchanger | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | In progress |  | 6 | DECEMBER
T-446-12798 | PS5-55-IK-6936D | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-09-26 | PS5-07-03 | PS5 - Milestone F | 5 | Closed | 21 | 38 | SEPTEMBER
T-150-12799 | PS5-82-UR-4732D | CQM02 - Compressor | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone A | 1 | In progress |  | 26 | DECEMBER
T-895-12800 | PS5-49-OB-9789C | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone G | 6 | On hold |  | 48 | NOVEMBER
T-317-12801 | PS5-47-OB-6185A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | In progress |  | 30 | OCTOBER
T-588-12802 | PS5-23-IK-7303B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone H | 7 | In progress |  | 8 | AUGUST
T-448-12803 | PS5-36-IK-2595A | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-04-26 | PS5-09-01 | PS5 - Milestone D | 3 | Closed | 39 | 34 | APRIL
T-188-12804 | PS5-45-OB-7904C | CQX02 - Concrete Works | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone C | 2 | On hold |  | 31 | DECEMBER
T-502-12805 | PS5-33-IK-7730C | CQM05 - Rotating Equipment | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-10-02 | PS5-10-02 | PS5 - Milestone B | 1.1 | Closed | 17 | 4 | OCTOBER
T-429-12806 | PS5-62-UR-2790D | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone G | 6 | To be completed |  | 35 | OCTOBER
T-165-12807 | PS5-08-OB-6394A | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | To be completed |  | 7 | NOVEMBER
T-881-12808 | PS5-96-OB-3296A | CQE05 - Switchgear | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-04-05 | PS5-10-01 | PS5 - Milestone B | 1.1 | Closed | 31 | 41 | APRIL
T-025-12809 | PS5-80-OB-7055C | CQH04 - Insulation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone E | 4 | In progress |  | 5 | AUGUST
T-679-12810 | PS5-19-OB-7786B | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone D | 3 | On hold |  | 7 | SEPTEMBER
T-384-12811 | PS5-34-UR-1071B | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-09-16 | PS5-07-03 | PS5 - Milestone E | 4 | Closed | 17 | 48 | SEPTEMBER
T-227-12812 | PS5-87-OB-8959B | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone F | 5 | To be completed |  | 13 | OCTOBER
T-985-12813 | PS5-67-UR-8173B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-03-19 | PS5-07-03 | PS5 - Milestone B | 1.1 | Closed | 28 | 10 | MARCH
T-091-12814 | PS5-67-IK-4876A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-09-27 | PS5-03-23 | PS5 - Milestone H | 7 | Closed | 43 | 30 | SEPTEMBER
T-759-12815 | PS5-49-IK-6865A | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | To be completed |  | 28 | AUGUST
T-421-12816 | PS5-61-UR-7557D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-11-19 | PS5-01-09 | PS5 - Milestone F | 5 | Closed | 35 | 31 | NOVEMBER
T-956-12817 | PS5-07-IK-5747B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone G | 6 | In progress |  | 45 | NOVEMBER
T-859-12818 | PS5-30-OB-6409C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone E | 4 | In progress |  | 12 | AUGUST
T-930-12819 | PS5-12-UR-5605D | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone F | 5 | To be completed |  | 47 | SEPTEMBER
T-258-12820 | PS5-77-IK-2230B | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-04-26 | PS5-06-01 | PS5 - Milestone G | 6 | Closed | 26 | 33 | APRIL
T-581-12821 | PS5-63-OB-4231B | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone G | 6 | To be completed |  | 9 | DECEMBER
T-160-12822 | PS5-66-OB-2809B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-10-18 | PS5-10-02 | PS5 - Milestone H | 7 | Closed | 34 | 4 | OCTOBER
T-855-12823 | PS5-96-OB-2376B | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone G | 6 | In progress |  | 36 | SEPTEMBER
T-632-12824 | PS5-67-OB-4052C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-07-16 | PS5-01-06 | PS5 - Milestone C | 2 | Closed | 32 | 37 | JULY
T-797-12825 | PS5-24-UR-1563C | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone G | 6 | To be completed |  | 4 | SEPTEMBER
T-916-12826 | PS5-10-OB-4774B | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-02-05 | PS5-03-03 | PS5 - Milestone I | 8 | Closed | 24 | 48 | FEBRUARY
T-395-12827 | PS5-94-UR-8760A | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone I | 8 | On hold |  | 19 | SEPTEMBER
T-556-12828 | PS5-97-IK-4735D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-03-25 | PS5-04-01 | PS5 - Milestone B | 1.1 | Closed | 40 | 24 | MARCH
T-982-12829 | PS5-36-OB-5407D | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | On hold |  | 15 | OCTOBER
T-018-12830 | PS5-28-OB-5714C | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | On hold |  | 41 | NOVEMBER
T-817-12831 | PS5-64-OB-8985D | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone G | 6 | On hold |  | 32 | DECEMBER
T-050-12832 | PS5-62-OB-8490A | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-09-28 | PS5-60-07 | PS5 - Milestone E | 4 | Closed | 36 | 47 | SEPTEMBER
T-935-12833 | PS5-06-IK-6638A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone A | 1 | To be completed |  | 22 | NOVEMBER
T-720-12834 | PS5-56-IK-6403A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone D | 3 | On hold |  | 34 | AUGUST
T-882-12835 | PS5-33-UR-4382C | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone A | 1 | To be completed |  | 25 | SEPTEMBER
T-952-12836 | PS5-55-OB-3848C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | To be completed |  | 36 | AUGUST
T-363-12837 | PS5-22-OB-8405D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone A | 1 | To be completed |  | 20 | OCTOBER
T-953-12838 | PS5-67-IK-6870D | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone G | 6 | On hold |  | 38 | AUGUST
T-281-12839 | PS5-44-OB-8448C | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone C | 2 | To be completed |  | 22 | NOVEMBER
T-468-12840 | PS5-71-OB-6492C | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone C | 2 | On hold |  | 44 | SEPTEMBER
T-754-12841 | PS5-68-OB-9843D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | To be completed |  | 11 | AUGUST
T-585-12842 | PS5-35-OB-5190D | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone H | 7 | In progress |  | 15 | NOVEMBER
T-605-12843 | PS5-11-OB-1982C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone E | 4 | On hold |  | 44 | DECEMBER
T-229-12844 | PS5-18-OB-1831D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | In progress |  | 33 | DECEMBER
T-251-12845 | PS5-25-OB-7046C | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-04-16 | PS5-10-03 | PS5 - Milestone C | 2 | Closed | 9 | 33 | APRIL
T-037-12846 | PS5-79-IK-5763D | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone A | 1 | To be completed |  | 22 | NOVEMBER
T-511-12847 | PS5-47-OB-7707D | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone A | 1 | To be completed |  | 18 | DECEMBER
T-154-12848 | PS5-36-IK-6473A | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone C | 2 | To be completed |  | 16 | AUGUST
T-274-12849 | PS5-13-UR-5123D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone A | 1 | To be completed |  | 36 | SEPTEMBER
T-237-12850 | PS5-43-IK-5304D | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone B | 1.1 | On hold |  | 22 | SEPTEMBER
T-005-12851 | PS5-24-OB-5919A | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-08-20 | PS5-07-02 | PS5 - Milestone F | 5 | Closed | 24 | 35 | AUGUST
T-871-12852 | PS5-83-UR-3465D | CQT02 - Fiber Optic | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-12-01 | PS5-10-02 | PS5 - Milestone B | 1.1 | Closed | 5 | 44 | DECEMBER
T-181-12853 | PS5-35-OB-1977B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-04-14 | PS5-09-02 | PS5 - Milestone C | 2 | Closed | 33 | 27 | APRIL
T-935-12854 | PS5-63-UR-7024D | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone I | 8 | To be completed |  | 24 | DECEMBER
T-976-12855 | PS5-09-UR-2002A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone F | 5 | To be completed |  | 22 | AUGUST
T-211-12856 | PS5-32-OB-2410D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-07-02 | PS5-62-02 | PS5 - Milestone H | 7 | Closed | 45 | 45 | JULY
T-413-12857 | PS5-38-UR-2697A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone G | 6 | To be completed |  | 18 | AUGUST
T-538-12858 | PS5-63-OB-3719B | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone E | 4 | On hold |  | 26 | SEPTEMBER
T-040-12859 | PS5-44-IK-5820D | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-10-19 | PS5-60-04 | PS5 - Milestone A | 1 | Closed | 44 | 9 | OCTOBER
T-881-12860 | PS5-29-UR-1496B | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone H | 7 | To be completed |  | 11 | NOVEMBER
T-908-12861 | PS5-22-IK-6942B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-12-07 | PS5-60-07 | PS5 - Milestone G | 6 | Closed | 15 | 5 | DECEMBER
T-198-12862 | PS5-45-OB-2142B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone F | 5 | In progress |  | 23 | OCTOBER
T-269-12863 | PS5-27-OB-9645C | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-11-05 | PS5-01-08 | PS5 - Milestone F | 5 | Closed | 47 | 43 | NOVEMBER
T-374-12864 | PS5-90-UR-1263C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone C | 2 | On hold |  | 21 | NOVEMBER
T-129-12865 | PS5-55-UR-8556D | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone E | 4 | In progress |  | 33 | NOVEMBER
T-459-12866 | PS5-46-IK-2069B | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-12-23 | PS5-63-01 | PS5 - Milestone E | 4 | Closed | 45 | 37 | DECEMBER
T-718-12867 | PS5-70-IK-1565A | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-10-06 | PS5-60-01 | PS5 - Milestone C | 2 | Closed | 23 | 15 | OCTOBER
T-796-12868 | PS5-06-IK-1041B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone F | 5 | To be completed |  | 33 | AUGUST
T-020-12869 | PS5-58-IK-3068B | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone D | 3 | In progress |  | 9 | DECEMBER
T-880-12870 | PS5-78-IK-6163C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone C | 2 | To be completed |  | 28 | OCTOBER
T-087-12871 | PS5-43-UR-4040A | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-11-23 | PS5-09-03 | PS5 - Milestone H | 7 | Closed | 36 | 7 | NOVEMBER
T-372-12872 | PS5-96-IK-3383C | CQH01 - Ductwork | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone G | 6 | To be completed |  | 18 | SEPTEMBER
T-026-12873 | PS5-08-OB-2761D | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone I | 8 | To be completed |  | 5 | OCTOBER
T-554-12874 | PS5-81-IK-3286C | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | To be completed |  | 45 | DECEMBER
T-068-12875 | PS5-18-UR-8398D | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone F | 5 | To be completed |  | 35 | NOVEMBER
T-777-12876 | PS5-57-OB-7735C | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-08-16 | PS5-09-04 | PS5 - Milestone H | 7 | Closed | 17 | 31 | AUGUST
T-883-12877 | PS5-56-IK-9209C | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main | 2026-02-20 | PS5-62-01 | PS5 - Milestone B | 1.1 | Closed | 13 | 9 | FEBRUARY
T-087-12878 | PS5-10-OB-9657C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone F | 5 | In progress |  | 12 | NOVEMBER
T-056-12879 | PS5-95-OB-2298C | CQI01 - Instrument Tubing | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone C | 2 | To be completed |  | 32 | OCTOBER
T-334-12880 | PS5-89-OB-8344C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone C | 2 | To be completed |  | 19 | OCTOBER
T-538-12881 | PS5-19-UR-4012C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone D | 3 | In progress |  | 11 | SEPTEMBER
T-679-12882 | PS5-99-IK-9613C | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone E | 4 | In progress |  | 23 | AUGUST
T-149-12883 | PS5-31-IK-8392D | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone H | 7 | On hold |  | 4 | OCTOBER
T-595-12884 | PS5-05-OB-7827B | CQX04 - Painting & Coating | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-06-22 | PS5-01-01 | PS5 - Milestone F | 5 | Closed | 32 | 27 | JUNE
T-472-12885 | PS5-77-OB-2087C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone A | 1 | To be completed |  | 42 | DECEMBER
T-070-12886 | PS5-88-OB-4536A | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone B | 1.1 | In progress |  | 25 | SEPTEMBER
T-373-12887 | PS5-23-OB-7463D | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-10-17 | PS5-01-09 | PS5 - Milestone B | 1.1 | Closed | 46 | 23 | OCTOBER
T-968-12888 | PS5-26-IK-6478A | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone E | 4 | On hold |  | 39 | AUGUST
T-873-12889 | PS5-13-OB-5108B | CQM02 - Compressor | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-06 | PS5-60-04 | PS5 - Milestone G | 6 | Closed | 17 | 16 | JULY
T-895-12890 | PS5-17-UR-2253A | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone D | 3 | In progress |  | 27 | NOVEMBER
T-075-12891 | PS5-14-UR-8723A | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone D | 3 | To be completed |  | 28 | DECEMBER
T-525-12892 | PS5-24-OB-8626C | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone I | 8 | To be completed |  | 23 | NOVEMBER
T-247-12893 | PS5-57-IK-1455B | CQX04 - Painting & Coating | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone E | 4 | On hold |  | 23 | DECEMBER
T-080-12894 | PS5-24-IK-9595D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-05-07 | PS5-62-02 | PS5 - Milestone E | 4 | Closed | 43 | 43 | MAY
T-648-12895 | PS5-41-UR-4201A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone F | 5 | To be completed |  | 29 | NOVEMBER
T-060-12896 | PS5-26-OB-8001A | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-07-17 | PS5-99-03 | PS5 - Milestone C | 2 | Closed | 33 | 34 | JULY
T-498-12897 | PS5-85-OB-4149A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone G | 6 | On hold |  | 8 | NOVEMBER
T-253-12898 | PS5-81-OB-1993C | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-11-01 | PS5-04-03 | PS5 - Milestone E | 4 | Closed | 45 | 34 | NOVEMBER
T-678-12899 | PS5-40-OB-5673A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone I | 8 | To be completed |  | 34 | OCTOBER
T-560-12900 | PS5-86-IK-5238A | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-05-15 | PS5-82-07 | PS5 - Milestone D | 3 | Closed | 33 | 23 | MAY
T-710-12901 | PS5-82-OB-1161B | CQE02 - LV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone H | 7 | To be completed |  | 40 | SEPTEMBER
T-801-12902 | PS5-80-IK-6439D | CQP05 - Insulation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-12-06 | PS5-60-10 | PS5 - Milestone A | 1 | Closed | 18 | 25 | DECEMBER
T-055-12903 | PS5-13-IK-6912B | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone A | 1 | In progress |  | 28 | SEPTEMBER
T-245-12904 | PS5-70-UR-5142B | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone G | 6 | To be completed |  | 48 | SEPTEMBER
T-807-12905 | PS5-05-UR-8966C | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone I | 8 | On hold |  | 36 | NOVEMBER
T-646-12906 | PS5-91-OB-2464B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone F | 5 | On hold |  | 24 | AUGUST
T-204-12907 | PS5-69-OB-6347D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | On hold |  | 17 | SEPTEMBER
T-694-12908 | PS5-96-OB-4997A | CQS04 - Foam System | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-08-20 | PS5-63-04 | PS5 - Milestone I | 8 | Closed | 44 | 30 | AUGUST
T-752-12909 | PS5-66-UR-8461D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone H | 7 | On hold |  | 37 | SEPTEMBER
T-946-12910 | PS5-87-UR-8988A | CQX03 - Architectural | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone I | 8 | To be completed |  | 30 | SEPTEMBER
T-728-12911 | PS5-27-IK-3526A | CQP04 - Hydrotest | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone D | 3 | To be completed |  | 27 | NOVEMBER
T-288-12912 | PS5-90-OB-9937B | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone H | 7 | To be completed |  | 37 | NOVEMBER
T-763-12913 | PS5-04-IK-8237D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone E | 4 | To be completed |  | 36 | SEPTEMBER
T-051-12914 | PS5-68-IK-8013C | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-04-18 | PS5-63-01 | PS5 - Milestone D | 3 | Closed | 31 | 47 | APRIL
T-853-12915 | PS5-17-OB-6955D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone H | 7 | To be completed |  | 6 | DECEMBER
T-591-12916 | PS5-43-OB-9273B | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone C | 2 | In progress |  | 41 | DECEMBER
T-810-12917 | PS5-35-IK-6060A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone H | 7 | To be completed |  | 39 | SEPTEMBER
T-274-12918 | PS5-96-UR-4116B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone F | 5 | In progress |  | 20 | SEPTEMBER
T-193-12919 | PS5-32-OB-3556D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-03-03 | PS5-11-01 | PS5 - Milestone E | 4 | Closed | 8 | 12 | MARCH
T-070-12920 | PS5-32-IK-2534D | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-05-05 | PS5-09-01 | PS5 - Milestone B | 1.1 | Closed | 7 | 36 | MAY
T-663-12921 | PS5-37-OB-7734D | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-09-09 | PS5-01-04 | PS5 - Milestone G | 6 | Closed | 12 | 16 | SEPTEMBER
T-170-12922 | PS5-51-OB-8357D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-10-27 | PS5-05-03 | PS5 - Milestone H | 7 | Closed | 45 | 19 | OCTOBER
T-621-12923 | PS5-21-IK-6699C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone C | 2 | In progress |  | 16 | OCTOBER
T-909-12924 | PS5-31-IK-2312A | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone G | 6 | In progress |  | 47 | NOVEMBER
T-658-12925 | PS5-64-IK-2535C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-01-09 | PS5-03-01 | PS5 - Milestone C | 2 | Closed | 24 | 41 | JANUARY
T-919-12926 | PS5-29-OB-5272D | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-04-14 | PS5-05-02 | PS5 - Milestone I | 8 | Closed | 44 | 39 | APRIL
T-359-12927 | PS5-92-OB-8144D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone A | 1 | To be completed |  | 21 | AUGUST
T-731-12928 | PS5-26-OB-4816B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone B | 1.1 | To be completed |  | 37 | DECEMBER
T-692-12929 | PS5-47-IK-2969B | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-08-08 | PS5-10-06 | PS5 - Milestone I | 8 | Closed | 15 | 34 | AUGUST
T-590-12930 | PS5-52-OB-7452B | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-01-25 | PS5-01-04 | PS5 - Milestone H | 7 | Closed | 39 | 34 | JANUARY
T-886-12931 | PS5-53-OB-6683A | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone A | 1 | On hold |  | 10 | DECEMBER
T-995-12932 | PS5-87-OB-7986C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone A | 1 | In progress |  | 43 | SEPTEMBER
T-037-12933 | PS5-13-OB-2756A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building |  | PS5-11-03 | PS5 - Milestone E | 4 | In progress |  | 12 | AUGUST
T-955-12934 | PS5-31-UR-7704A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-07-10 | PS5-10-01 | PS5 - Milestone C | 2 | Closed | 15 | 20 | JULY
T-685-12935 | PS5-57-IK-9841B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone F | 5 | To be completed |  | 30 | SEPTEMBER
T-080-12936 | PS5-37-IK-9290A | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone F | 5 | To be completed |  | 16 | NOVEMBER
T-428-12937 | PS5-93-OB-2025A | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone F | 5 | On hold |  | 6 | NOVEMBER
T-036-12938 | PS5-42-OB-9022B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-02-07 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 6 | 33 | FEBRUARY
T-581-12939 | PS5-66-UR-6923C | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone G | 6 | In progress |  | 20 | DECEMBER
T-944-12940 | PS5-62-OB-7278A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone F | 5 | To be completed |  | 41 | DECEMBER
T-186-12941 | PS5-62-OB-6397D | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-06-01 | PS5-10-01 | PS5 - Milestone E | 4 | Closed | 33 | 11 | JUNE
T-299-12942 | PS5-11-OB-6250D | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone A | 1 | On hold |  | 23 | AUGUST
T-610-12943 | PS5-89-UR-2689D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone H | 7 | In progress |  | 14 | OCTOBER
T-675-12944 | PS5-92-UR-4065C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone B | 1.1 | To be completed |  | 26 | DECEMBER
T-943-12945 | PS5-03-IK-4961D | CQX03 - Architectural | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-01-23 | PS5-01-03 | PS5 - Milestone H | 7 | Closed | 17 | 39 | JANUARY
T-444-12946 | PS5-95-IK-3047D | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone C | 2 | To be completed |  | 20 | OCTOBER
T-957-12947 | PS5-24-IK-7087A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone A | 1 | On hold |  | 6 | SEPTEMBER
T-426-12948 | PS5-24-IK-1761D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone G | 6 | To be completed |  | 40 | NOVEMBER
T-105-12949 | PS5-03-OB-9999D | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-02-21 | PS5-63-04 | PS5 - Milestone D | 3 | Closed | 14 | 9 | FEBRUARY
T-530-12950 | PS5-05-OB-4969D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-10-03 | PS5-01-07 | PS5 - Milestone H | 7 | Closed | 4 | 33 | OCTOBER
T-126-12951 | PS5-71-OB-9071C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-06-10 | PS5-06-01 | PS5 - Milestone E | 4 | Closed | 44 | 34 | JUNE
T-641-12952 | PS5-95-UR-9867A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone I | 8 | To be completed |  | 7 | SEPTEMBER
T-125-12953 | PS5-99-OB-1273A | CQM04 - Vessel | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-02-11 | PS5-07-04 | PS5 - Milestone D | 3 | Closed | 15 | 16 | FEBRUARY
T-961-12954 | PS5-27-OB-9965B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-05-03 | PS5-12-02 | PS5 - Milestone B | 1.1 | Closed | 8 | 23 | MAY
T-398-12955 | PS5-84-IK-6864A | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone C | 2 | To be completed |  | 20 | NOVEMBER
T-474-12956 | PS5-88-OB-2836D | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone E | 4 | In progress |  | 7 | OCTOBER
T-025-12957 | PS5-43-OB-9354A | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone I | 8 | To be completed |  | 10 | SEPTEMBER
T-173-12958 | PS5-40-UR-7897B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone C | 2 | To be completed |  | 26 | DECEMBER
T-455-12959 | PS5-67-OB-2911B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-10-11 | PS5-03-03 | PS5 - Milestone E | 4 | Closed | 29 | 22 | OCTOBER
T-894-12960 | PS5-55-OB-5594D | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone A | 1 | To be completed |  | 17 | OCTOBER
T-800-12961 | PS5-55-OB-6306D | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone G | 6 | In progress |  | 19 | DECEMBER
T-623-12962 | PS5-50-IK-9330A | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone A | 1 | In progress |  | 22 | DECEMBER
T-814-12963 | PS5-78-UR-8103C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-04-15 | PS5-02-03 | PS5 - Milestone D | 3 | Closed | 40 | 21 | APRIL
T-060-12964 | PS5-87-OB-8272D | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone G | 6 | To be completed |  | 9 | SEPTEMBER
T-295-12965 | PS5-12-IK-8336A | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-08-16 | PS5-11-02 | PS5 - Milestone F | 5 | Closed | 16 | 15 | AUGUST
T-442-12966 | PS5-41-OB-1883D | CQI04 - Analyzer Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone D | 3 | In progress |  | 46 | AUGUST
T-029-12967 | PS5-91-OB-2563C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone G | 6 | On hold |  | 16 | AUGUST
T-822-12968 | PS5-38-OB-8962B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone I | 8 | To be completed |  | 7 | DECEMBER
T-770-12969 | PS5-80-OB-5837B | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | To be completed |  | 6 | DECEMBER
T-900-12970 | PS5-97-OB-9845D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone A | 1 | To be completed |  | 12 | SEPTEMBER
T-268-12971 | PS5-83-IK-6982D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-05-18 | PS5-02-02 | PS5 - Milestone C | 2 | Closed | 7 | 34 | MAY
T-065-12972 | PS5-19-IK-9905A | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone I | 8 | On hold |  | 8 | DECEMBER
T-893-12973 | PS5-19-OB-5141C | CQX04 - Painting & Coating | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone F | 5 | To be completed |  | 14 | AUGUST
T-047-12974 | PS5-47-IK-8086A | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone D | 3 | On hold |  | 35 | OCTOBER
T-109-12975 | PS5-73-OB-3102D | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone G | 6 | In progress |  | 36 | AUGUST
T-852-12976 | PS5-33-UR-8744A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone G | 6 | To be completed |  | 24 | NOVEMBER
T-165-12977 | PS5-71-OB-1945D | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone G | 6 | In progress |  | 12 | SEPTEMBER
T-900-12978 | PS5-46-OB-6277C | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone B | 1.1 | To be completed |  | 6 | AUGUST
T-379-12979 | PS5-16-UR-3149A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone H | 7 | In progress |  | 22 | NOVEMBER
T-378-12980 | PS5-68-OB-9660A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone G | 6 | In progress |  | 41 | NOVEMBER
T-639-12981 | PS5-97-UR-2733D | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone D | 3 | In progress |  | 9 | AUGUST
T-549-12982 | PS5-43-OB-3631C | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-10-10 | PS5-05-02 | PS5 - Milestone D | 3 | Closed | 28 | 18 | OCTOBER
T-080-12983 | PS5-05-UR-3691A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone E | 4 | To be completed |  | 13 | DECEMBER
T-012-12984 | PS5-89-UR-1096C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-06-16 | PS5-01-01 | PS5 - Milestone I | 8 | Closed | 12 | 11 | JUNE
T-414-12985 | PS5-76-OB-4956A | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-03-03 | PS5-02-01 | PS5 - Milestone H | 7 | Closed | 33 | 40 | MARCH
T-950-12986 | PS5-69-OB-8639C | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-09-17 | PS5-01-08 | PS5 - Milestone B | 1.1 | Closed | 48 | 47 | SEPTEMBER
T-373-12987 | PS5-48-IK-8932B | CQI02 - Transmitter Installation | COM - Commissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | In progress |  | 15 | OCTOBER
T-888-12988 | PS5-94-IK-8473D | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-03-19 | PS5-06-02 | PS5 - Milestone G | 6 | Closed | 27 | 45 | MARCH
T-702-12989 | PS5-54-OB-9697C | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-12-01 | PS5-12-01 | PS5 - Milestone G | 6 | Closed | 37 | 47 | DECEMBER
T-573-12990 | PS5-54-OB-4222D | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone A | 1 | To be completed |  | 24 | AUGUST
T-614-12991 | PS5-03-UR-3877A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-01-17 | PS5-03-23 | PS5 - Milestone I | 8 | Closed | 40 | 29 | JANUARY
T-753-12992 | PS5-93-OB-1169C | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-08-13 | PS5-01-06 | PS5 - Milestone F | 5 | Closed | 18 | 33 | AUGUST
T-652-12993 | PS5-46-OB-7279C | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone A | 1 | On hold |  | 33 | AUGUST
T-791-12994 | PS5-30-IK-9546A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-01-14 | PS5-01-01 | PS5 - Milestone E | 4 | Closed | 38 | 31 | JANUARY
T-378-12995 | PS5-92-OB-2176B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-12-01 | PS5-11-03 | PS5 - Milestone E | 4 | Closed | 35 | 4 | DECEMBER
T-868-12996 | PS5-95-IK-9598A | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone G | 6 | To be completed |  | 5 | NOVEMBER
T-328-12997 | PS5-36-OB-8536B | CQX03 - Architectural | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone I | 8 | To be completed |  | 37 | NOVEMBER
T-117-12998 | PS5-93-UR-6717D | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone I | 8 | In progress |  | 39 | NOVEMBER
T-510-12999 | PS5-64-OB-3584D | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone D | 3 | In progress |  | 22 | AUGUST
T-427-13000 | PS5-80-OB-9061C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone C | 2 | In progress |  | 44 | NOVEMBER
T-478-13001 | PS5-98-OB-4473B | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | In progress |  | 34 | SEPTEMBER
T-764-13002 | PS5-29-OB-6001D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-12-13 | PS5-13-01 | PS5 - Milestone B | 1.1 | Closed | 20 | 11 | DECEMBER
T-507-13003 | PS5-28-OB-2825B | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone A | 1 | To be completed |  | 48 | AUGUST
T-401-13004 | PS5-21-OB-6559C | CQP05 - Insulation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B | 2026-03-12 | PS5-11-02 | PS5 - Milestone F | 5 | Closed | 28 | 12 | MARCH
T-297-13005 | PS5-61-UR-6936A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone A | 1 | In progress |  | 17 | OCTOBER
T-713-13006 | PS5-95-IK-6123B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-08-01 | PS5-09-04 | PS5 - Milestone G | 6 | Closed | 10 | 40 | AUGUST
T-633-13007 | PS5-21-IK-3971D | CQM01 - Pump Installation | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone E | 4 | In progress |  | 47 | AUGUST
T-862-13008 | PS5-29-IK-7512A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone G | 6 | To be completed |  | 31 | NOVEMBER
T-726-13009 | PS5-36-OB-5494C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone H | 7 | To be completed |  | 12 | DECEMBER
T-183-13010 | PS5-74-OB-6361D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-09-18 | PS5-01-04 | PS5 - Milestone I | 8 | Closed | 24 | 40 | SEPTEMBER
T-907-13011 | PS5-66-OB-7226C | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone E | 4 | On hold |  | 40 | NOVEMBER
T-748-13012 | PS5-99-OB-3858B | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone A | 1 | To be completed |  | 21 | OCTOBER
T-639-13013 | PS5-59-UR-6319B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone D | 3 | In progress |  | 28 | AUGUST
T-506-13014 | PS5-02-OB-3858B | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone I | 8 | To be completed |  | 43 | NOVEMBER
T-014-13015 | PS5-25-UR-7072D | CQH01 - Ductwork | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-12-20 | PS5-05-01 | PS5 - Milestone I | 8 | Closed | 25 | 36 | DECEMBER
T-408-13016 | PS5-35-OB-2566C | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone E | 4 | To be completed |  | 32 | DECEMBER
T-730-13017 | PS5-50-OB-3423C | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | In progress |  | 24 | DECEMBER
T-405-13018 | PS5-08-OB-7787B | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone A | 1 | On hold |  | 26 | OCTOBER
T-467-13019 | PS5-88-UR-3093D | CQX03 - Architectural | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone G | 6 | To be completed |  | 47 | OCTOBER
T-658-13020 | PS5-86-IK-8178B | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-12-20 | PS5-04-02 | PS5 - Milestone B | 1.1 | Closed | 33 | 6 | DECEMBER
T-068-13021 | PS5-58-OB-4660D | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone B | 1.1 | In progress |  | 47 | AUGUST
T-899-13022 | PS5-40-OB-2087C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone E | 4 | In progress |  | 34 | AUGUST
T-896-13023 | PS5-99-UR-9094A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-06-01 | PS5-01-02 | PS5 - Milestone B | 1.1 | Closed | 8 | 23 | JUNE
T-629-13024 | PS5-09-IK-8964A | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-01-28 | PS5-01-08 | PS5 - Milestone A | 1 | Closed | 42 | 23 | JANUARY
T-536-13025 | PS5-39-IK-8611B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-09-15 | PS5-63-01 | PS5 - Milestone C | 2 | Closed | 18 | 21 | SEPTEMBER
T-576-13026 | PS5-66-OB-4819D | CQP04 - Hydrotest | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-03-16 | PS5-01-08 | PS5 - Milestone H | 7 | Closed | 22 | 15 | MARCH
T-295-13027 | PS5-71-UR-8060D | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone C | 2 | On hold |  | 21 | AUGUST
T-698-13028 | PS5-85-UR-4289D | CQI01 - Instrument Tubing | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone F | 5 | In progress |  | 13 | OCTOBER
T-405-13029 | PS5-33-UR-4343B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone D | 3 | To be completed |  | 13 | SEPTEMBER
T-364-13030 | PS5-71-UR-3725B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone A | 1 | To be completed |  | 23 | SEPTEMBER
T-410-13031 | PS5-80-UR-4434B | CQH01 - Ductwork | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone I | 8 | To be completed |  | 45 | SEPTEMBER
T-252-13032 | PS5-47-OB-7015A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone A | 1 | In progress |  | 18 | NOVEMBER
T-810-13033 | PS5-41-OB-5985D | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone B | 1.1 | To be completed |  | 9 | DECEMBER
T-960-13034 | PS5-39-OB-3963D | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone B | 1.1 | To be completed |  | 11 | SEPTEMBER
T-427-13035 | PS5-20-OB-5764D | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-10-01 | PS5-10-05 | PS5 - Milestone B | 1.1 | Closed | 33 | 32 | OCTOBER
T-941-13036 | PS5-18-UR-1466A | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone B | 1.1 | On hold |  | 40 | NOVEMBER
T-364-13037 | PS5-96-OB-6348A | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone F | 5 | To be completed |  | 15 | AUGUST
T-758-13038 | PS5-27-IK-1023C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-10-03 | PS5-04-03 | PS5 - Milestone B | 1.1 | Closed | 4 | 46 | OCTOBER
T-466-13039 | PS5-41-OB-8062D | CQE04 - Transformer | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-02-24 | PS5-07-02 | PS5 - Milestone B | 1.1 | Closed | 10 | 7 | FEBRUARY
T-187-13040 | PS5-59-OB-3598C | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone E | 4 | In progress |  | 32 | DECEMBER
T-132-13041 | PS5-43-IK-4580B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-07-28 | PS5-99-01 | PS5 - Milestone I | 8 | Closed | 34 | 46 | JULY
T-339-13042 | PS5-59-IK-6265D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone B | 1.1 | In progress |  | 21 | OCTOBER
T-736-13043 | PS5-04-OB-3002D | CQM04 - Vessel | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-06-07 | PS5-63-04 | PS5 - Milestone H | 7 | Closed | 47 | 10 | JUNE
T-049-13044 | PS5-36-IK-5459B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone F | 5 | To be completed |  | 20 | SEPTEMBER
T-456-13045 | PS5-05-OB-1555C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone E | 4 | To be completed |  | 40 | OCTOBER
T-332-13046 | PS5-59-OB-2343A | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-09-28 | PS5-06-02 | PS5 - Milestone F | 5 | Closed | 22 | 15 | SEPTEMBER
T-770-13047 | PS5-75-IK-7147D | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-02-22 | PS5-07-02 | PS5 - Milestone E | 4 | Closed | 43 | 38 | FEBRUARY
T-915-13048 | PS5-54-OB-5338A | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone D | 3 | To be completed |  | 9 | AUGUST
T-175-13049 | PS5-94-OB-2735B | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone F | 5 | To be completed |  | 21 | NOVEMBER
T-483-13050 | PS5-95-OB-8853C | CQM02 - Compressor | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | On hold |  | 8 | SEPTEMBER
T-373-13051 | PS5-66-OB-8772C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-07-08 | PS5-12-02 | PS5 - Milestone F | 5 | Closed | 14 | 9 | JULY
T-929-13052 | PS5-56-OB-7030A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone D | 3 | To be completed |  | 39 | SEPTEMBER
T-143-13053 | PS5-56-UR-2275B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-02-24 | PS5-08-02 | PS5 - Milestone F | 5 | Closed | 46 | 25 | FEBRUARY
T-396-13054 | PS5-61-IK-9204C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone A | 1 | To be completed |  | 25 | NOVEMBER
T-907-13055 | PS5-08-OB-9287A | CQM04 - Vessel | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone I | 8 | To be completed |  | 28 | AUGUST
T-099-13056 | PS5-93-OB-9970B | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-05-26 | PS5-03-23 | PS5 - Milestone F | 5 | Closed | 32 | 6 | MAY
T-816-13057 | PS5-27-UR-6013A | CQH01 - Ductwork | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-09-17 | PS5-02-03 | PS5 - Milestone B | 1.1 | Closed | 19 | 27 | SEPTEMBER
T-201-13058 | PS5-63-IK-9927D | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone D | 3 | In progress |  | 36 | DECEMBER
T-896-13059 | PS5-27-OB-7607B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone G | 6 | To be completed |  | 34 | AUGUST
T-011-13060 | PS5-22-UR-1070B | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-03-11 | PS5-10-02 | PS5 - Milestone B | 1.1 | Closed | 5 | 23 | MARCH
T-771-13061 | PS5-15-UR-1131D | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-04-26 | PS5-09-01 | PS5 - Milestone C | 2 | Closed | 24 | 28 | APRIL
T-949-13062 | PS5-74-OB-4883C | CQP02 - Valve Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone F | 5 | On hold |  | 30 | DECEMBER
T-686-13063 | PS5-60-IK-3283B | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone I | 8 | In progress |  | 39 | AUGUST
T-286-13064 | PS5-25-OB-7789C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-07-05 | PS5-09-02 | PS5 - Milestone E | 4 | Closed | 12 | 4 | JULY
T-269-13065 | PS5-76-IK-1355C | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone F | 5 | In progress |  | 48 | AUGUST
T-905-13066 | PS5-05-IK-1806C | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone E | 4 | To be completed |  | 18 | DECEMBER
T-774-13067 | PS5-47-IK-2015C | CQP05 - Insulation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-03-06 | PS5-09-02 | PS5 - Milestone F | 5 | Closed | 24 | 5 | MARCH
T-267-13068 | PS5-68-OB-6320C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System | 2026-06-24 | PS5-04-03 | PS5 - Milestone B | 1.1 | Closed | 6 | 16 | JUNE
T-228-13069 | PS5-63-OB-4228D | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-02-24 | PS5-63-04 | PS5 - Milestone F | 5 | Closed | 29 | 15 | FEBRUARY
T-071-13070 | PS5-05-OB-9545B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone B | 1.1 | In progress |  | 39 | AUGUST
T-894-13071 | PS5-21-OB-5929C | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone E | 4 | To be completed |  | 7 | OCTOBER
T-815-13072 | PS5-40-IK-8698D | CQE03 - Earthing | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone C | 2 | To be completed |  | 20 | NOVEMBER
T-262-13073 | PS5-73-UR-9748C | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-09-18 | PS5-12-01 | PS5 - Milestone B | 1.1 | Closed | 21 | 46 | SEPTEMBER
T-868-13074 | PS5-83-OB-1271B | CQH02 - AHU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV |  | PS5-09-01 | PS5 - Milestone I | 8 | To be completed |  | 44 | OCTOBER
T-229-13075 | PS5-61-OB-2241A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-10-12 | PS5-11-03 | PS5 - Milestone H | 7 | Closed | 13 | 5 | OCTOBER
T-114-13076 | PS5-97-OB-1916A | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | To be completed |  | 26 | OCTOBER
T-964-13077 | PS5-37-OB-6159A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-03-12 | PS5-03-02 | PS5 - Milestone E | 4 | Closed | 22 | 31 | MARCH
T-712-13078 | PS5-33-OB-6890D | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone E | 4 | To be completed |  | 4 | OCTOBER
T-847-13079 | PS5-89-OB-3896C | CQI02 - Transmitter Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-05-04 | PS5-03-01 | PS5 - Milestone E | 4 | Closed | 48 | 45 | MAY
T-967-13080 | PS5-85-OB-2281D | CQT03 - PA/GA System | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-03-27 | PS5-01-08 | PS5 - Milestone C | 2 | Closed | 37 | 41 | MARCH
T-326-13081 | PS5-56-OB-3340D | CQH01 - Ductwork | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone A | 1 | In progress |  | 43 | NOVEMBER
T-150-13082 | PS5-38-IK-6825C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-03-02 | PS5-04-04 | PS5 - Milestone C | 2 | Closed | 6 | 7 | MARCH
T-355-13083 | PS5-73-OB-1299C | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone F | 5 | On hold |  | 6 | OCTOBER
T-179-13084 | PS5-06-OB-8961B | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone G | 6 | To be completed |  | 30 | AUGUST
T-670-13085 | PS5-33-OB-3295B | CQX02 - Concrete Works | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-12-01 | PS5-04-02 | PS5 - Milestone G | 6 | Closed | 40 | 37 | DECEMBER
T-040-13086 | PS5-08-UR-7322B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-08-24 | PS5-13-01 | PS5 - Milestone B | 1.1 | Closed | 31 | 45 | AUGUST
T-130-13087 | PS5-91-OB-6808A | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | To be completed |  | 39 | AUGUST
T-848-13088 | PS5-64-UR-3244D | CQE04 - Transformer | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-12-26 | PS5-04-02 | PS5 - Milestone C | 2 | Closed | 17 | 11 | DECEMBER
T-472-13089 | PS5-19-UR-1324D | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | To be completed |  | 32 | AUGUST
T-495-13090 | PS5-41-OB-7647A | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone F | 5 | On hold |  | 38 | NOVEMBER
T-371-13091 | PS5-70-OB-6335D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone I | 8 | In progress |  | 29 | OCTOBER
T-663-13092 | PS5-81-OB-8362D | CQE02 - LV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone D | 3 | To be completed |  | 28 | NOVEMBER
T-249-13093 | PS5-90-UR-9377D | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone E | 4 | In progress |  | 26 | OCTOBER
T-877-13094 | PS5-03-UR-3133B | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-01-09 | PS5-01-07 | PS5 - Milestone E | 4 | Closed | 9 | 18 | JANUARY
T-009-13095 | PS5-25-OB-2744B | CQI03 - Control Valve | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone G | 6 | To be completed |  | 15 | OCTOBER
T-128-13096 | PS5-82-UR-2914B | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-08-19 | PS5-99-01 | PS5 - Milestone C | 2 | Closed | 10 | 23 | AUGUST
T-869-13097 | PS5-60-UR-5722B | CQM05 - Rotating Equipment | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone D | 3 | On hold |  | 43 | SEPTEMBER
T-366-13098 | PS5-50-OB-9696B | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone H | 7 | To be completed |  | 39 | AUGUST
T-863-13099 | PS5-08-OB-1496B | CQM04 - Vessel | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | On hold |  | 11 | AUGUST
T-569-13100 | PS5-45-OB-9453B | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone H | 7 | On hold |  | 38 | AUGUST
T-770-13101 | PS5-24-OB-5291A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-02-23 | PS5-02-01 | PS5 - Milestone H | 7 | Closed | 28 | 4 | FEBRUARY
T-633-13102 | PS5-10-OB-4124C | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-06-23 | PS5-12-01 | PS5 - Milestone B | 1.1 | Closed | 42 | 37 | JUNE
T-045-13103 | PS5-67-UR-2342C | CQS03 - Deluge System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-02-10 | PS5-05-02 | PS5 - Milestone I | 8 | Closed | 12 | 16 | FEBRUARY
T-083-13104 | PS5-24-OB-4224A | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone H | 7 | In progress |  | 43 | DECEMBER
T-173-13105 | PS5-79-UR-7992C | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-10-09 | PS5-61-01 | PS5 - Milestone G | 6 | Closed | 38 | 48 | OCTOBER
T-354-13106 | PS5-46-OB-9227D | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-09-22 | PS5-02-03 | PS5 - Milestone A | 1 | Closed | 37 | 7 | SEPTEMBER
T-404-13107 | PS5-06-OB-8994B | CQH04 - Insulation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System | 2026-10-23 | PS5-03-01 | PS5 - Milestone G | 6 | Closed | 17 | 48 | OCTOBER
T-723-13108 | PS5-33-IK-1307D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone E | 4 | In progress |  | 18 | NOVEMBER
T-201-13109 | PS5-45-OB-6152B | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone E | 4 | In progress |  | 33 | AUGUST
T-655-13110 | PS5-31-OB-2940D | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-07-25 | PS5-01-01 | PS5 - Milestone B | 1.1 | Closed | 48 | 20 | JULY
T-412-13111 | PS5-23-OB-3156D | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-05-28 | PS5-82-01 | PS5 - Milestone E | 4 | Closed | 40 | 26 | MAY
T-270-13112 | PS5-60-UR-5515B | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-12-04 | PS5-04-04 | PS5 - Milestone I | 8 | Closed | 5 | 40 | DECEMBER
T-809-13113 | PS5-20-OB-2954C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone D | 3 | On hold |  | 20 | NOVEMBER
T-753-13114 | PS5-65-UR-6348C | CQE05 - Switchgear | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone E | 4 | On hold |  | 24 | OCTOBER
T-057-13115 | PS5-79-UR-7337B | CQP03 - Flange Management | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone A | 1 | To be completed |  | 39 | AUGUST
T-468-13116 | PS5-82-OB-6278C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-06-23 | PS5-10-06 | PS5 - Milestone G | 6 | Closed | 36 | 41 | JUNE
T-463-13117 | PS5-34-OB-1403A | CQH02 - AHU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone C | 2 | In progress |  | 42 | SEPTEMBER
T-506-13118 | PS5-03-UR-7756C | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-07-09 | PS5-05-03 | PS5 - Milestone H | 7 | Closed | 44 | 32 | JULY
T-981-13119 | PS5-37-IK-7529A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone I | 8 | In progress |  | 22 | OCTOBER
T-765-13120 | PS5-96-UR-8222A | CQH03 - FCU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone D | 3 | To be completed |  | 20 | AUGUST
T-595-13121 | PS5-50-OB-3240B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-07-13 | PS5-06-03 | PS5 - Milestone E | 4 | Closed | 17 | 5 | JULY
T-727-13122 | PS5-82-OB-6552B | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-03-22 | PS5-03-02 | PS5 - Milestone G | 6 | Closed | 17 | 16 | MARCH
T-119-13123 | PS5-88-OB-1157C | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone E | 4 | To be completed |  | 11 | SEPTEMBER
T-591-13124 | PS5-52-OB-3486A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone A | 1 | In progress |  | 39 | DECEMBER
T-593-13125 | PS5-92-OB-9095C | CQM03 - Heat Exchanger | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone I | 8 | To be completed |  | 19 | SEPTEMBER
T-351-13126 | PS5-78-IK-5817C | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-12-23 | PS5-03-23 | PS5 - Milestone B | 1.1 | Closed | 47 | 42 | DECEMBER
T-513-13127 | PS5-16-OB-1529C | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone I | 8 | On hold |  | 40 | NOVEMBER
T-595-13128 | PS5-34-IK-9277B | CQX03 - Architectural | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-02-10 | PS5-13-01 | PS5 - Milestone A | 1 | Closed | 29 | 10 | FEBRUARY
T-218-13129 | PS5-92-OB-5056B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone D | 3 | In progress |  | 26 | AUGUST
T-777-13130 | PS5-26-IK-3749A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-09-12 | PS5-03-23 | PS5 - Milestone E | 4 | Closed | 7 | 20 | SEPTEMBER
T-914-13131 | PS5-50-OB-4250D | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-07-14 | PS5-12-01 | PS5 - Milestone C | 2 | Closed | 37 | 31 | JULY
T-343-13132 | PS5-68-OB-9583B | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-12-22 | PS5-08-01 | PS5 - Milestone B | 1.1 | Closed | 39 | 18 | DECEMBER
T-601-13133 | PS5-08-UR-2362A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-11-01 | PS5-09-04 | PS5 - Milestone C | 2 | Closed | 9 | 4 | NOVEMBER
T-156-13134 | PS5-95-OB-8775A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone C | 2 | To be completed |  | 19 | SEPTEMBER
T-388-13135 | PS5-59-OB-2845D | CQP02 - Valve Installation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-03-02 | PS5-01-03 | PS5 - Milestone C | 2 | Closed | 10 | 22 | MARCH
T-032-13136 | PS5-17-OB-8535A | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-07-26 | PS5-01-04 | PS5 - Milestone H | 7 | Closed | 19 | 29 | JULY
T-875-13137 | PS5-17-OB-6132A | CQX04 - Painting & Coating | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-02-18 | PS5-01-08 | PS5 - Milestone C | 2 | Closed | 27 | 15 | FEBRUARY
T-353-13138 | PS5-57-IK-1353D | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone C | 2 | To be completed |  | 41 | NOVEMBER
T-079-13139 | PS5-42-OB-4915B | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-10-21 | PS5-02-02 | PS5 - Milestone F | 5 | Closed | 44 | 42 | OCTOBER
T-123-13140 | PS5-41-UR-6695C | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-05-20 | PS5-10-03 | PS5 - Milestone A | 1 | Closed | 27 | 44 | MAY
T-422-13141 | PS5-65-OB-2552C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-10-03 | PS5-07-01 | PS5 - Milestone F | 5 | Closed | 45 | 47 | OCTOBER
T-701-13142 | PS5-98-OB-2826D | CQX01 - Steel Structure | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-09-05 | PS5-09-03 | PS5 - Milestone D | 3 | Closed | 37 | 19 | SEPTEMBER
T-062-13143 | PS5-39-IK-4739D | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone C | 2 | To be completed |  | 17 | AUGUST
T-232-13144 | PS5-43-OB-8556B | CQS01 - Fire Protection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-11-03 | PS5-10-02 | PS5 - Milestone D | 3 | Closed | 46 | 31 | NOVEMBER
T-057-13145 | PS5-59-IK-9979A | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone E | 4 | In progress |  | 8 | NOVEMBER
T-887-13146 | PS5-91-UR-1475D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-05-22 | PS5-82-02 | PS5 - Milestone A | 1 | Closed | 7 | 8 | MAY
T-092-13147 | PS5-31-OB-8534D | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-07-16 | PS5-06-03 | PS5 - Milestone G | 6 | Closed | 6 | 20 | JULY
T-106-13148 | PS5-17-IK-7676B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-12-18 | PS5-10-04 | PS5 - Milestone H | 7 | Closed | 36 | 15 | DECEMBER
T-984-13149 | PS5-09-OB-1342B | CQT01 - Cable Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone B | 1.1 | To be completed |  | 31 | SEPTEMBER
T-570-13150 | PS5-56-OB-8047D | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building | 2026-08-28 | PS5-06-01 | PS5 - Milestone A | 1 | Closed | 11 | 20 | AUGUST
T-329-13151 | PS5-73-OB-3830B | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone I | 8 | On hold |  | 18 | OCTOBER
T-278-13152 | PS5-83-OB-2626D | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone I | 8 | On hold |  | 25 | SEPTEMBER
T-855-13153 | PS5-58-OB-8063A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-11-14 | PS5-60-04 | PS5 - Milestone E | 4 | Closed | 17 | 47 | NOVEMBER
T-562-13154 | PS5-04-OB-1949A | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone E | 4 | In progress |  | 43 | SEPTEMBER
T-990-13155 | PS5-13-OB-2444B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-08-24 | PS5-08-01 | PS5 - Milestone E | 4 | Closed | 4 | 45 | AUGUST
T-166-13156 | PS5-93-IK-2741C | CQS04 - Foam System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone D | 3 | In progress |  | 9 | AUGUST
T-065-13157 | PS5-51-IK-9835D | CQE03 - Earthing | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System | 2026-09-25 | PS5-01-05 | PS5 - Milestone C | 2 | Closed | 47 | 18 | SEPTEMBER
T-492-13158 | PS5-04-OB-3587A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System |  | PS5-13-01 | PS5 - Milestone C | 2 | To be completed |  | 6 | OCTOBER
T-581-13159 | PS5-18-IK-4892A | CQP02 - Valve Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone I | 8 | To be completed |  | 46 | AUGUST
T-653-13160 | PS5-59-UR-1130B | CQT01 - Cable Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone B | 1.1 | To be completed |  | 42 | NOVEMBER
T-490-13161 | PS5-06-OB-2449B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-01-09 | PS5-11-01 | PS5 - Milestone C | 2 | Closed | 20 | 13 | JANUARY
T-140-13162 | PS5-81-OB-4907B | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-02-06 | PS5-05-01 | PS5 - Milestone A | 1 | Closed | 38 | 41 | FEBRUARY
T-195-13163 | PS5-73-IK-6067A | CQP03 - Flange Management | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone H | 7 | To be completed |  | 30 | NOVEMBER
T-270-13164 | PS5-75-OB-8734A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | In progress |  | 46 | DECEMBER
T-219-13165 | PS5-34-OB-3178A | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-11-09 | PS5-61-01 | PS5 - Milestone H | 7 | Closed | 33 | 14 | NOVEMBER
T-772-13166 | PS5-09-OB-8010C | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone F | 5 | In progress |  | 15 | AUGUST
T-251-13167 | PS5-84-OB-4996B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-10-03 | PS5-02-03 | PS5 - Milestone E | 4 | Closed | 18 | 25 | OCTOBER
T-318-13168 | PS5-69-OB-6579C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone G | 6 | To be completed |  | 26 | NOVEMBER
T-920-13169 | PS5-43-UR-2608C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-10-14 | PS5-07-01 | PS5 - Milestone A | 1 | Closed | 4 | 16 | OCTOBER
T-342-13170 | PS5-17-OB-7164C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-02-12 | PS5-01-02 | PS5 - Milestone I | 8 | Closed | 15 | 39 | FEBRUARY
T-776-13171 | PS5-25-OB-4287D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-02-14 | PS5-04-01 | PS5 - Milestone A | 1 | Closed | 38 | 6 | FEBRUARY
T-243-13172 | PS5-32-OB-1933C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone F | 5 | On hold |  | 27 | OCTOBER
T-444-13173 | PS5-47-IK-6401B | CQI02 - Transmitter Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone H | 7 | In progress |  | 26 | DECEMBER
T-381-13174 | PS5-46-UR-9357A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-12-10 | PS5-82-07 | PS5 - Milestone E | 4 | Closed | 39 | 15 | DECEMBER
T-021-13175 | PS5-18-OB-7257A | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone A | 1 | To be completed |  | 20 | SEPTEMBER
T-344-13176 | PS5-53-IK-1892C | CQX01 - Steel Structure | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-11-12 | PS5-06-02 | PS5 - Milestone D | 3 | Closed | 15 | 47 | NOVEMBER
T-205-13177 | PS5-64-OB-9723D | CQM02 - Compressor | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-01-17 | PS5-07-02 | PS5 - Milestone G | 6 | Closed | 37 | 36 | JANUARY
T-528-13178 | PS5-69-OB-7229C | CQH02 - AHU Installation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone A | 1 | To be completed |  | 33 | SEPTEMBER
T-197-13179 | PS5-54-OB-9746D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-06-26 | PS5-09-04 | PS5 - Milestone E | 4 | Closed | 38 | 16 | JUNE
T-144-13180 | PS5-03-UR-3352A | CQP03 - Flange Management | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-05-06 | PS5-09-02 | PS5 - Milestone I | 8 | Closed | 17 | 16 | MAY
T-584-13181 | PS5-53-OB-4314C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone E | 4 | On hold |  | 26 | SEPTEMBER
T-307-13182 | PS5-05-UR-8276B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone E | 4 | On hold |  | 25 | OCTOBER
T-427-13183 | PS5-74-OB-1788D | CQI03 - Control Valve | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-05-01 | PS5-99-01 | PS5 - Milestone E | 4 | Closed | 16 | 37 | MAY
T-118-13184 | PS5-97-IK-8442C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone H | 7 | In progress |  | 9 | NOVEMBER
T-937-13185 | PS5-12-OB-6674B | CQH04 - Insulation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone B | 1.1 | To be completed |  | 12 | AUGUST
T-817-13186 | PS5-47-UR-5106B | CQM04 - Vessel | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-10-24 | PS5-02-03 | PS5 - Milestone D | 3 | Closed | 6 | 47 | OCTOBER
T-553-13187 | PS5-44-IK-1577C | CQT01 - Cable Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone G | 6 | To be completed |  | 9 | NOVEMBER
T-403-13188 | PS5-63-OB-5033D | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone H | 7 | To be completed |  | 33 | OCTOBER
T-901-13189 | PS5-54-UR-1583B | CQS02 - Gas Detection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone G | 6 | In progress |  | 47 | NOVEMBER
T-145-13190 | PS5-91-OB-7251C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone H | 7 | To be completed |  | 9 | NOVEMBER
T-959-13191 | PS5-99-UR-1486C | CQP01 - Pipe Installation | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-03-17 | PS5-07-03 | PS5 - Milestone F | 5 | Closed | 26 | 44 | MARCH
T-999-13192 | PS5-39-OB-6457A | CQS03 - Deluge System | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone F | 5 | To be completed |  | 18 | OCTOBER
T-573-13193 | PS5-85-OB-3797D | CQM02 - Compressor | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System | 2026-06-18 | PS5-01-06 | PS5 - Milestone G | 6 | Closed | 21 | 22 | JUNE
T-864-13194 | PS5-96-OB-7759C | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | On hold |  | 5 | NOVEMBER
T-116-13195 | PS5-50-OB-3441C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone D | 3 | To be completed |  | 47 | AUGUST
T-229-13196 | PS5-71-IK-1622C | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone B | 1.1 | On hold |  | 17 | SEPTEMBER
T-711-13197 | PS5-73-IK-4205D | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone C | 2 | To be completed |  | 25 | NOVEMBER
T-188-13198 | PS5-81-OB-3858D | CQS04 - Foam System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone D | 3 | In progress |  | 28 | AUGUST
T-693-13199 | PS5-59-OB-5841A | CQH04 - Insulation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone F | 5 | To be completed |  | 4 | DECEMBER
T-680-13200 | PS5-21-OB-4405C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone F | 5 | To be completed |  | 5 | SEPTEMBER
T-294-13201 | PS5-66-OB-9815D | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone H | 7 | In progress |  | 21 | OCTOBER
T-826-13202 | PS5-31-IK-8184A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone C | 2 | To be completed |  | 16 | AUGUST
T-288-13203 | PS5-23-OB-4996C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone E | 4 | In progress |  | 16 | NOVEMBER
T-278-13204 | PS5-28-OB-7342B | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-09-28 | PS5-12-02 | PS5 - Milestone C | 2 | Closed | 27 | 8 | SEPTEMBER
T-162-13205 | PS5-49-OB-9641C | CQP05 - Insulation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-11-21 | PS5-63-01 | PS5 - Milestone C | 2 | Closed | 24 | 21 | NOVEMBER
T-545-13206 | PS5-63-OB-8454A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-03-12 | PS5-01-08 | PS5 - Milestone F | 5 | Closed | 36 | 46 | MARCH
T-848-13207 | PS5-94-OB-9680D | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone F | 5 | To be completed |  | 24 | SEPTEMBER
T-353-13208 | PS5-82-OB-8035B | CQX04 - Painting & Coating | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | To be completed |  | 47 | NOVEMBER
T-013-13209 | PS5-69-UR-7676A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | To be completed |  | 40 | NOVEMBER
T-820-13210 | PS5-18-IK-1493A | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-11-21 | PS5-07-04 | PS5 - Milestone H | 7 | Closed | 19 | 40 | NOVEMBER
T-433-13211 | PS5-31-UR-3604D | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard |  | PS5-09-04 | PS5 - Milestone E | 4 | In progress |  | 43 | DECEMBER
T-763-13212 | PS5-33-OB-8953C | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-06-26 | PS5-62-02 | PS5 - Milestone A | 1 | Closed | 4 | 38 | JUNE
T-841-13213 | PS5-50-OB-7591A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone I | 8 | To be completed |  | 39 | OCTOBER
T-608-13214 | PS5-81-UR-7210A | CQE05 - Switchgear | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-07-16 | PS5-09-03 | PS5 - Milestone B | 1.1 | Closed | 20 | 23 | JULY
T-670-13215 | PS5-08-OB-7293A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone H | 7 | In progress |  | 40 | SEPTEMBER
T-271-13216 | PS5-51-OB-7222D | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone F | 5 | To be completed |  | 12 | DECEMBER
T-557-13217 | PS5-09-UR-5418A | CQE04 - Transformer | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-06-02 | PS5-09-04 | PS5 - Milestone H | 7 | Closed | 21 | 21 | JUNE
T-598-13218 | PS5-74-OB-7196A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System | 2026-04-07 | PS5-10-06 | PS5 - Milestone F | 5 | Closed | 25 | 40 | APRIL
T-421-13219 | PS5-48-UR-2838D | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System |  | PS5-07-04 | PS5 - Milestone G | 6 | To be completed |  | 19 | AUGUST
T-944-13220 | PS5-63-OB-9220B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone I | 8 | On hold |  | 9 | OCTOBER
T-099-13221 | PS5-07-OB-4781A | CQP05 - Insulation | PCOM - Precommissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone A | 1 | On hold |  | 39 | SEPTEMBER
T-767-13222 | PS5-29-UR-3738A | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone G | 6 | To be completed |  | 15 | AUGUST
T-961-13223 | PS5-36-OB-1665A | CQH02 - AHU Installation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B | 2026-12-02 | PS5-82-02 | PS5 - Milestone G | 6 | Closed | 12 | 26 | DECEMBER
T-798-13224 | PS5-57-OB-3736A | CQI02 - Transmitter Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-03-03 | PS5-04-01 | PS5 - Milestone F | 5 | Closed | 45 | 27 | MARCH
T-543-13225 | PS5-40-OB-8405A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone H | 7 | On hold |  | 38 | NOVEMBER
T-820-13226 | PS5-35-UR-1051B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone G | 6 | In progress |  | 43 | AUGUST
T-079-13227 | PS5-39-UR-8315D | CQX03 - Architectural | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone C | 2 | To be completed |  | 42 | NOVEMBER
T-200-13228 | PS5-65-OB-1493A | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-07-06 | PS5-01-09 | PS5 - Milestone A | 1 | Closed | 32 | 20 | JULY
T-340-13229 | PS5-21-IK-8668C | CQS04 - Foam System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-08-26 | PS5-07-04 | PS5 - Milestone B | 1.1 | Closed | 37 | 38 | AUGUST
T-784-13230 | PS5-01-OB-3970D | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone B | 1.1 | In progress |  | 7 | DECEMBER
T-460-13231 | PS5-78-IK-8540C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone E | 4 | To be completed |  | 12 | DECEMBER
T-806-13232 | PS5-56-IK-7085B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone G | 6 | To be completed |  | 29 | SEPTEMBER
T-475-13233 | PS5-08-OB-7874D | CQH01 - Ductwork | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone A | 1 | To be completed |  | 42 | OCTOBER
T-217-13234 | PS5-78-OB-3228A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone F | 5 | On hold |  | 28 | NOVEMBER
T-978-13235 | PS5-25-IK-3939D | CQE03 - Earthing | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone G | 6 | To be completed |  | 36 | NOVEMBER
T-302-13236 | PS5-12-UR-6925A | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone D | 3 | To be completed |  | 12 | AUGUST
T-379-13237 | PS5-32-OB-4068A | CQX01 - Steel Structure | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-03-07 | PS5-62-02 | PS5 - Milestone D | 3 | Closed | 22 | 23 | MARCH
T-434-13238 | PS5-06-OB-6133B | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone I | 8 | In progress |  | 10 | DECEMBER
T-791-13239 | PS5-67-OB-9374C | CQT04 - CCTV Installation | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-06-01 | PS5-09-03 | PS5 - Milestone A | 1 | Closed | 37 | 6 | JUNE
T-714-13240 | PS5-89-OB-3147C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone G | 6 | To be completed |  | 20 | AUGUST
T-775-13241 | PS5-67-OB-4307D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone F | 5 | In progress |  | 33 | SEPTEMBER
T-491-13242 | PS5-65-OB-9375B | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-03-15 | PS5-82-01 | PS5 - Milestone F | 5 | Closed | 32 | 14 | MARCH
T-923-13243 | PS5-23-UR-3873D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-09-24 | PS5-02-01 | PS5 - Milestone G | 6 | Closed | 21 | 47 | SEPTEMBER
T-042-13244 | PS5-57-IK-7534B | CQT02 - Fiber Optic | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-08-05 | PS5-61-02 | PS5 - Milestone F | 5 | Closed | 25 | 9 | AUGUST
T-147-13245 | PS5-18-OB-4751A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone B | 1.1 | In progress |  | 29 | SEPTEMBER
T-706-13246 | PS5-56-UR-5238A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-05-09 | PS5-05-01 | PS5 - Milestone A | 1 | Closed | 48 | 7 | MAY
T-675-13247 | PS5-64-IK-2127B | CQE01 - HV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack | 2026-04-06 | PS5-10-02 | PS5 - Milestone F | 5 | Closed | 33 | 33 | APRIL
T-672-13248 | PS5-16-UR-2168B | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building |  | PS5-01-09 | PS5 - Milestone F | 5 | In progress |  | 23 | AUGUST
T-394-13249 | PS5-51-UR-7907C | CQM02 - Compressor | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-06-27 | PS5-12-02 | PS5 - Milestone C | 2 | Closed | 46 | 40 | JUNE
T-813-13250 | PS5-50-OB-3794A | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | To be completed |  | 27 | AUGUST
T-628-13251 | PS5-29-IK-3368A | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-13-01 - Flare System | 2026-10-16 | PS5-13-01 | PS5 - Milestone B | 1.1 | Closed | 36 | 9 | OCTOBER
T-309-13252 | PS5-84-UR-4781A | CQI03 - Control Valve | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone F | 5 | To be completed |  | 44 | NOVEMBER
T-139-13253 | PS5-94-UR-7692C | CQI03 - Control Valve | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | In progress |  | 44 | SEPTEMBER
T-757-13254 | PS5-54-OB-1634C | CQT04 - CCTV Installation | COM - Commissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | To be completed |  | 27 | OCTOBER
T-542-13255 | PS5-67-UR-5239D | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone G | 6 | In progress |  | 12 | SEPTEMBER
T-933-13256 | PS5-49-OB-3216D | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone H | 7 | On hold |  | 6 | DECEMBER
T-913-13257 | PS5-88-IK-3074C | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-12-22 | PS5-09-01 | PS5 - Milestone C | 2 | Closed | 15 | 19 | DECEMBER
T-386-13258 | PS5-54-OB-7390C | CQX04 - Painting & Coating | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone E | 4 | To be completed |  | 32 | AUGUST
T-375-13259 | PS5-88-OB-6314B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-09-16 | PS5-02-03 | PS5 - Milestone H | 7 | Closed | 21 | 8 | SEPTEMBER
T-770-13260 | PS5-17-OB-2788B | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone G | 6 | To be completed |  | 43 | OCTOBER
T-696-13261 | PS5-68-OB-7587A | CQM04 - Vessel | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone F | 5 | In progress |  | 5 | OCTOBER
T-959-13262 | PS5-81-OB-2272D | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone A | 1 | In progress |  | 10 | AUGUST
T-733-13263 | PS5-07-OB-4083D | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone B | 1.1 | To be completed |  | 34 | DECEMBER
T-865-13264 | PS5-48-UR-5858B | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | In progress |  | 24 | NOVEMBER
T-270-13265 | PS5-87-UR-4948D | CQM05 - Rotating Equipment | COM - Commissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-03-26 | PS5-60-01 | PS5 - Milestone D | 3 | Closed | 23 | 6 | MARCH
T-492-13266 | PS5-16-UR-2535C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment |  | PS5-12-02 | PS5 - Milestone F | 5 | In progress |  | 45 | NOVEMBER
T-969-13267 | PS5-30-OB-3868D | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection | 2026-08-03 | PS5-03-02 | PS5 - Milestone E | 4 | Closed | 47 | 5 | AUGUST
T-515-13268 | PS5-45-OB-3637C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack | 2026-04-02 | PS5-10-01 | PS5 - Milestone B | 1.1 | Closed | 20 | 34 | APRIL
T-479-13269 | PS5-82-OB-3183D | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone B | 1.1 | In progress |  | 27 | OCTOBER
T-400-13270 | PS5-09-UR-9091D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-05-24 | PS5-99-03 | PS5 - Milestone E | 4 | Closed | 45 | 46 | MAY
T-766-13271 | PS5-72-OB-2428C | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone E | 4 | To be completed |  | 43 | OCTOBER
T-572-13272 | PS5-55-OB-5136D | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-02 - Utility Pipe Rack |  | PS5-10-02 | PS5 - Milestone E | 4 | To be completed |  | 9 | AUGUST
T-303-13273 | PS5-62-UR-5856C | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone F | 5 | To be completed |  | 14 | OCTOBER
T-842-13274 | PS5-77-OB-5605B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone E | 4 | On hold |  | 33 | SEPTEMBER
T-082-13275 | PS5-88-OB-6963C | CQI03 - Control Valve | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-01 - AC UPS - EITS Building |  | PS5-06-01 | PS5 - Milestone F | 5 | To be completed |  | 40 | SEPTEMBER
T-956-13276 | PS5-62-OB-1274A | CQT04 - CCTV Installation | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-05-04 | PS5-11-03 | PS5 - Milestone G | 6 | Closed | 41 | 34 | MAY
T-079-13277 | PS5-60-OB-2287B | CQX01 - Steel Structure | COM - Commissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone H | 7 | To be completed |  | 20 | AUGUST
T-146-13278 | PS5-25-IK-5627B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-02-02 | PS5-04-01 | PS5 - Milestone H | 7 | Closed | 33 | 36 | FEBRUARY
T-030-13279 | PS5-41-UR-5307B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-03-28 | PS5-07-04 | PS5 - Milestone D | 3 | Closed | 4 | 17 | MARCH
T-294-13280 | PS5-81-UR-1517A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone D | 3 | In progress |  | 34 | DECEMBER
T-875-13281 | PS5-04-IK-8050B | CQM01 - Pump Installation | COM - Commissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone A | 1 | In progress |  | 19 | AUGUST
T-565-13282 | PS5-52-UR-1968A | CQE03 - Earthing | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-10-18 | PS5-06-03 | PS5 - Milestone D | 3 | Closed | 37 | 45 | OCTOBER
T-953-13283 | PS5-12-OB-8981A | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone A | 1 | In progress |  | 27 | DECEMBER
T-238-13284 | PS5-58-UR-3441A | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone C | 2 | To be completed |  | 16 | OCTOBER
T-031-13285 | PS5-81-OB-9270B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone B | 1.1 | In progress |  | 25 | AUGUST
T-050-13286 | PS5-64-OB-2326D | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone D | 3 | On hold |  | 35 | DECEMBER
T-614-13287 | PS5-52-OB-7310C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-01 - Cable Tray Main |  | PS5-62-01 | PS5 - Milestone H | 7 | In progress |  | 32 | NOVEMBER
T-581-13288 | PS5-89-OB-3632D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System | 2026-09-24 | PS5-08-01 | PS5 - Milestone A | 1 | Closed | 44 | 23 | SEPTEMBER
T-514-13289 | PS5-22-OB-5253B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network |  | PS5-05-01 | PS5 - Milestone G | 6 | To be completed |  | 33 | AUGUST
T-863-13290 | PS5-87-OB-4007C | CQE02 - LV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-21 | PS5-60-01 | PS5 - Milestone G | 6 | Closed | 18 | 25 | FEBRUARY
T-274-13291 | PS5-21-UR-2057B | CQH03 - FCU Installation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-04-02 | PS5-62-02 | PS5 - Milestone E | 4 | Closed | 30 | 7 | APRIL
T-425-13292 | PS5-10-OB-8107D | CQE05 - Switchgear | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone D | 3 | To be completed |  | 15 | SEPTEMBER
T-829-13293 | PS5-89-UR-2343B | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | To be completed |  | 38 | DECEMBER
T-838-13294 | PS5-13-OB-5287C | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone G | 6 | To be completed |  | 5 | AUGUST
T-820-13295 | PS5-80-IK-5409B | CQP05 - Insulation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-08-21 | PS5-01-02 | PS5 - Milestone C | 2 | Closed | 21 | 9 | AUGUST
T-454-13296 | PS5-80-UR-9859B | CQE04 - Transformer | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-01-22 | PS5-03-23 | PS5 - Milestone E | 4 | Closed | 45 | 45 | JANUARY
T-421-13297 | PS5-94-IK-4817D | CQS02 - Gas Detection | COM - Commissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-11-14 | PS5-11-01 | PS5 - Milestone E | 4 | Closed | 46 | 35 | NOVEMBER
T-890-13298 | PS5-99-UR-4430A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-04-10 | PS5-09-01 | PS5 - Milestone B | 1.1 | Closed | 7 | 10 | APRIL
T-590-13299 | PS5-46-UR-7580C | CQS03 - Deluge System | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-01-20 | PS5-11-03 | PS5 - Milestone H | 7 | Closed | 10 | 31 | JANUARY
T-254-13300 | PS5-28-IK-1736A | CQE03 - Earthing | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-12-01 | PS5-99-03 | PS5 - Milestone F | 5 | Closed | 17 | 32 | DECEMBER
T-846-13301 | PS5-38-OB-5517D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone F | 5 | In progress |  | 38 | NOVEMBER
T-180-13302 | PS5-77-UR-8759C | CQM04 - Vessel | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone C | 2 | On hold |  | 14 | DECEMBER
T-274-13303 | PS5-01-UR-3608B | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-08-27 | PS5-06-03 | PS5 - Milestone F | 5 | Closed | 36 | 22 | AUGUST
T-316-13304 | PS5-12-OB-8619D | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone A | 1 | To be completed |  | 40 | SEPTEMBER
T-934-13305 | PS5-76-OB-6157C | CQP02 - Valve Installation | COM - Commissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary | 2026-11-26 | PS5-62-02 | PS5 - Milestone C | 2 | Closed | 10 | 26 | NOVEMBER
T-943-13306 | PS5-98-OB-3369A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-11-22 | PS5-12-01 | PS5 - Milestone C | 2 | Closed | 35 | 43 | NOVEMBER
T-714-13307 | PS5-22-OB-3414A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-02-01 | PS5-01-08 | PS5 - Milestone F | 5 | Closed | 23 | 8 | FEBRUARY
T-965-13308 | PS5-32-UR-5848C | CQT01 - Cable Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-01-10 | PS5-02-02 | PS5 - Milestone G | 6 | Closed | 41 | 24 | JANUARY
T-204-13309 | PS5-57-OB-1176C | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-03-22 | PS5-07-01 | PS5 - Milestone I | 8 | Closed | 45 | 18 | MARCH
T-630-13310 | PS5-04-OB-9898C | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone E | 4 | On hold |  | 18 | SEPTEMBER
T-155-13311 | PS5-63-IK-4606A | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Inspection | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-10-17 | PS5-61-01 | PS5 - Milestone G | 6 | Closed | 7 | 24 | OCTOBER
T-917-13312 | PS5-96-OB-8946B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone D | 3 | To be completed |  | 24 | DECEMBER
T-370-13313 | PS5-53-OB-2185B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone I | 8 | To be completed |  | 7 | DECEMBER
T-133-13314 | PS5-41-OB-7200A | CQP04 - Hydrotest | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System | 2026-02-17 | PS5-01-07 | PS5 - Milestone H | 7 | Closed | 18 | 48 | FEBRUARY
T-753-13315 | PS5-72-UR-2346A | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-07-07 | PS5-03-23 | PS5 - Milestone E | 4 | Closed | 8 | 6 | JULY
T-614-13316 | PS5-29-OB-1065B | CQM04 - Vessel | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts |  | PS5-82-07 | PS5 - Milestone A | 1 | To be completed |  | 25 | SEPTEMBER
T-603-13317 | PS5-84-OB-2242B | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone A | 1 | In progress |  | 13 | OCTOBER
T-931-13318 | PS5-41-OB-2903A | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone A | 1 | To be completed |  | 18 | AUGUST
T-409-13319 | PS5-77-OB-6960D | CQI04 - Analyzer Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-10-28 | PS5-63-04 | PS5 - Milestone E | 4 | Closed | 44 | 27 | OCTOBER
T-347-13320 | PS5-49-UR-9007C | CQT02 - Fiber Optic | COM - Commissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone G | 6 | To be completed |  | 19 | OCTOBER
T-449-13321 | PS5-17-UR-3118A | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone H | 7 | To be completed |  | 6 | DECEMBER
T-641-13322 | PS5-59-OB-2315C | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone E | 4 | To be completed |  | 46 | AUGUST
T-161-13323 | PS5-50-OB-6573D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone D | 3 | To be completed |  | 10 | SEPTEMBER
T-855-13324 | PS5-39-UR-6625B | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System | 2026-10-16 | PS5-02-03 | PS5 - Milestone G | 6 | Closed | 12 | 11 | OCTOBER
T-068-13325 | PS5-24-OB-2917A | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-05-04 | PS5-63-04 | PS5 - Milestone B | 1.1 | Closed | 45 | 35 | MAY
T-870-13326 | PS5-91-IK-2827B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-10-18 | PS5-10-03 | PS5 - Milestone C | 2 | Closed | 11 | 47 | OCTOBER
T-005-13327 | PS5-89-OB-1279A | CQP01 - Pipe Installation | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone A | 1 | In progress |  | 30 | DECEMBER
T-655-13328 | PS5-46-OB-5050D | CQH03 - FCU Installation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-04-19 | PS5-04-01 | PS5 - Milestone C | 2 | Closed | 21 | 45 | APRIL
T-080-13329 | PS5-45-IK-7157C | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone B | 1.1 | In progress |  | 48 | AUGUST
T-877-13330 | PS5-61-IK-2653D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone G | 6 | On hold |  | 24 | OCTOBER
T-968-13331 | PS5-72-UR-1806A | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-03 - Fuel Gas System |  | PS5-02-03 | PS5 - Milestone E | 4 | To be completed |  | 9 | SEPTEMBER
T-916-13332 | PS5-47-UR-8176B | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-09-12 | PS5-60-07 | PS5 - Milestone G | 6 | Closed | 39 | 19 | SEPTEMBER
T-137-13333 | PS5-42-IK-8526D | CQH01 - Ductwork | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone D | 3 | To be completed |  | 6 | NOVEMBER
T-057-13334 | PS5-39-UR-8157A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-01 - Compressor Air System |  | PS5-08-01 | PS5 - Milestone B | 1.1 | To be completed |  | 9 | OCTOBER
T-571-13335 | PS5-08-OB-8582C | CQX03 - Architectural | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area | 2026-09-04 | PS5-99-01 | PS5 - Milestone G | 6 | Closed | 33 | 40 | SEPTEMBER
T-225-13336 | PS5-85-OB-7621D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone E | 4 | To be completed |  | 18 | SEPTEMBER
T-970-13337 | PS5-58-OB-1556D | CQH02 - AHU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone H | 7 | In progress |  | 48 | AUGUST
T-215-13338 | PS5-34-OB-7158D | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A |  | PS5-01-02 | PS5 - Milestone C | 2 | On hold |  | 13 | DECEMBER
T-234-13339 | PS5-13-OB-2056B | CQP04 - Hydrotest | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone C | 2 | To be completed |  | 15 | SEPTEMBER
T-062-13340 | PS5-25-OB-6460A | CQE01 - HV Cable Installation | COM - Commissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B | 2026-04-19 | PS5-01-03 | PS5 - Milestone F | 5 | Closed | 9 | 36 | APRIL
T-645-13341 | PS5-78-OB-6988B | CQT02 - Fiber Optic | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone E | 4 | To be completed |  | 6 | OCTOBER
T-585-13342 | PS5-20-UR-5960D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-11-10 | PS5-04-04 | PS5 - Milestone F | 5 | Closed | 6 | 46 | NOVEMBER
T-414-13343 | PS5-89-UR-6140D | CQH01 - Ductwork | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building |  | PS5-61-07 | PS5 - Milestone G | 6 | On hold |  | 46 | DECEMBER
T-561-13344 | PS5-05-OB-2661C | CQE02 - LV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A | 2026-12-27 | PS5-07-01 | PS5 - Milestone H | 7 | Closed | 36 | 28 | DECEMBER
T-514-13345 | PS5-70-OB-8414D | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | PS5 - Milestone C | 2 | To be completed |  | 10 | SEPTEMBER
T-059-13346 | PS5-49-IK-2076B | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump | 2026-12-12 | PS5-02-02 | PS5 - Milestone A | 1 | Closed | 13 | 16 | DECEMBER
T-096-13347 | PS5-55-OB-8358B | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone A | 1 | To be completed |  | 16 | DECEMBER
T-500-13348 | PS5-32-OB-5255C | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone G | 6 | In progress |  | 40 | NOVEMBER
T-976-13349 | PS5-11-OB-4271A | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-08-19 | PS5-61-07 | PS5 - Milestone I | 8 | Closed | 14 | 37 | AUGUST
T-704-13350 | PS5-42-IK-8337D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone A | 1 | In progress |  | 46 | AUGUST
T-579-13351 | PS5-37-OB-1871C | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone D | 3 | To be completed |  | 25 | AUGUST
T-458-13352 | PS5-74-OB-3661B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-11-11 | PS5-82-01 | PS5 - Milestone A | 1 | Closed | 45 | 39 | NOVEMBER
T-393-13353 | PS5-03-OB-4992A | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone E | 4 | To be completed |  | 14 | NOVEMBER
T-820-13354 | PS5-82-UR-4244A | CQE04 - Transformer | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-02 - Water Treatment | 2026-08-01 | PS5-12-02 | PS5 - Milestone E | 4 | Closed | 46 | 18 | AUGUST
T-365-13355 | PS5-09-UR-9536D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone B | 1.1 | In progress |  | 9 | AUGUST
T-953-13356 | PS5-72-OB-5882D | CQE03 - Earthing | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone F | 5 | To be completed |  | 22 | AUGUST
T-324-13357 | PS5-91-OB-5820C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone B | 1.1 | In progress |  | 27 | SEPTEMBER
T-063-13358 | PS5-70-UR-6925A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Walkdown | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-01-01 | PS5-99-02 | PS5 - Milestone E | 4 | Closed | 10 | 17 | JANUARY
T-449-13359 | PS5-49-IK-1448A | CQT01 - Cable Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-09-16 | PS5-82-01 | PS5 - Milestone G | 6 | Closed | 44 | 29 | SEPTEMBER
T-471-13360 | PS5-30-IK-7247C | CQE02 - LV Cable Installation | COM - Commissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone H | 7 | To be completed |  | 16 | AUGUST
T-317-13361 | PS5-05-OB-8675C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-01-16 | PS5-61-01 | PS5 - Milestone F | 5 | Closed | 14 | 9 | JANUARY
T-832-13362 | PS5-31-UR-9203D | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone I | 8 | On hold |  | 37 | SEPTEMBER
T-923-13363 | PS5-50-OB-7964C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-01-02 | PS5-60-10 | PS5 - Milestone H | 7 | Closed | 23 | 42 | JANUARY
T-706-13364 | PS5-97-OB-6870B | CQH04 - Insulation | COM - Commissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-07-19 | PS5-08-02 | PS5 - Milestone G | 6 | Closed | 47 | 20 | JULY
T-752-13365 | PS5-80-UR-3751C | CQS02 - Gas Detection | COM - Commissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone I | 8 | To be completed |  | 14 | NOVEMBER
T-389-13366 | PS5-17-IK-5785A | CQS04 - Foam System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building | 2026-12-24 | PS5-61-01 | PS5 - Milestone F | 5 | Closed | 8 | 25 | DECEMBER
T-676-13367 | PS5-23-IK-6664D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone D | 3 | To be completed |  | 43 | DECEMBER
T-168-13368 | PS5-12-IK-1538B | CQX02 - Concrete Works | COM - Commissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building | 2026-03-15 | PS5-63-04 | PS5 - Milestone I | 8 | Closed | 34 | 46 | MARCH
T-818-13369 | PS5-86-IK-5294D | CQI03 - Control Valve | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A | 2026-07-24 | PS5-82-01 | PS5 - Milestone D | 3 | Closed | 16 | 37 | JULY
T-326-13370 | PS5-34-OB-5570D | CQT03 - PA/GA System | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-10-12 | PS5-61-02 | PS5 - Milestone A | 1 | Closed | 48 | 9 | OCTOBER
T-776-13371 | PS5-87-UR-7545B | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone H | 7 | To be completed |  | 23 | SEPTEMBER
T-340-13372 | PS5-90-OB-3274C | CQI04 - Analyzer Installation | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone I | 8 | To be completed |  | 33 | DECEMBER
T-746-13373 | PS5-73-OB-5863B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-11-16 | PS5-08-02 | PS5 - Milestone D | 3 | Closed | 23 | 24 | NOVEMBER
T-897-13374 | PS5-54-OB-8688C | CQT03 - PA/GA System | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-05-02 | PS5-05-01 | PS5 - Milestone G | 6 | Closed | 38 | 35 | MAY
T-713-13375 | PS5-23-IK-8148A | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building |  | PS5-03-23 | PS5 - Milestone A | 1 | In progress |  | 9 | NOVEMBER
T-629-13376 | PS5-88-UR-8230D | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone G | 6 | To be completed |  | 39 | SEPTEMBER
T-868-13377 | PS5-33-IK-3141A | CQH01 - Ductwork | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone E | 4 | To be completed |  | 7 | OCTOBER
T-819-13378 | PS5-51-IK-1354D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-02-28 | PS5-10-03 | PS5 - Milestone F | 5 | Closed | 11 | 34 | FEBRUARY
T-019-13379 | PS5-73-OB-2091B | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-10-15 | PS5-02-01 | PS5 - Milestone B | 1.1 | Closed | 17 | 19 | OCTOBER
T-421-13380 | PS5-88-IK-8176C | CQE05 - Switchgear | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone F | 5 | To be completed |  | 36 | OCTOBER
T-203-13381 | PS5-20-UR-3512B | CQS01 - Fire Protection | COM - Commissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone G | 6 | On hold |  | 33 | DECEMBER
T-491-13382 | PS5-68-OB-6911C | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-06-11 | PS5-82-07 | PS5 - Milestone E | 4 | Closed | 16 | 28 | JUNE
T-699-13383 | PS5-15-OB-6502C | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North |  | PS5-61-02 | PS5 - Milestone E | 4 | In progress |  | 12 | OCTOBER
T-600-13384 | PS5-13-UR-8338C | CQT03 - PA/GA System | COM - Commissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2026-02-04 | PS5-03-23 | PS5 - Milestone G | 6 | Closed | 37 | 31 | FEBRUARY
T-151-13385 | PS5-81-IK-9303A | CQI01 - Instrument Tubing | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone B | 1.1 | In progress |  | 27 | SEPTEMBER
T-414-13386 | PS5-08-OB-3908C | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System | 2026-05-28 | PS5-04-01 | PS5 - Milestone G | 6 | Closed | 31 | 27 | MAY
T-367-13387 | PS5-69-OB-9892A | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone F | 5 | To be completed |  | 33 | DECEMBER
T-015-13388 | PS5-75-UR-5577A | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Conformity Check | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone G | 6 | In progress |  | 4 | NOVEMBER
T-239-13389 | PS5-83-IK-9194C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone A | 1 | In progress |  | 6 | AUGUST
T-895-13390 | PS5-92-OB-9245B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B | 2026-12-22 | PS5-10-04 | PS5 - Milestone I | 8 | Closed | 21 | 46 | DECEMBER
T-989-13391 | PS5-99-OB-7500C | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV | 2026-05-24 | PS5-09-02 | PS5 - Milestone C | 2 | Closed | 33 | 15 | MAY
T-056-13392 | PS5-75-OB-7604A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-12-02 | PS5-01-02 | PS5 - Milestone I | 8 | Closed | 7 | 6 | DECEMBER
T-766-13393 | PS5-65-IK-5206D | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | To be completed |  | 31 | AUGUST
T-363-13394 | PS5-59-OB-2996B | CQX02 - Concrete Works | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System | 2026-01-09 | PS5-05-03 | PS5 - Milestone A | 1 | Closed | 38 | 41 | JANUARY
T-150-13395 | PS5-28-IK-3653C | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone D | 3 | To be completed |  | 24 | DECEMBER
T-599-13396 | PS5-53-UR-1225C | CQP03 - Flange Management | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone F | 5 | In progress |  | 28 | DECEMBER
T-973-13397 | PS5-38-OB-8598B | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System |  | PS5-04-04 | PS5 - Milestone I | 8 | On hold |  | 8 | AUGUST
T-483-13398 | PS5-98-OB-4616C | CQS02 - Gas Detection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B |  | PS5-01-01 | PS5 - Milestone E | 4 | In progress |  | 13 | AUGUST
T-849-13399 | PS5-68-OB-7569C | CQI04 - Analyzer Installation | COM - Commissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B |  | PS5-07-02 | PS5 - Milestone A | 1 | In progress |  | 46 | OCTOBER
T-667-13400 | PS5-91-OB-1034B | CQE04 - Transformer | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-01 - Transformer 33kV/6.6kV | 2026-12-15 | PS5-09-01 | PS5 - Milestone G | 6 | Closed | 14 | 17 | DECEMBER
T-530-13401 | PS5-38-OB-6628B | CQP02 - Valve Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone G | 6 | On hold |  | 39 | DECEMBER
T-546-13402 | PS5-50-IK-8732C | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System |  | PS5-10-05 | PS5 - Milestone E | 4 | On hold |  | 36 | NOVEMBER
T-126-13403 | PS5-18-IK-8746A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Precommissioning | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-02 - 6.6kV Switchboard LLHT North | 2026-02-22 | PS5-61-02 | PS5 - Milestone H | 7 | Closed | 9 | 6 | FEBRUARY
T-243-13404 | PS5-45-IK-7292C | CQH01 - Ductwork | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone E | 4 | To be completed |  | 28 | DECEMBER
T-143-13405 | PS5-89-UR-1287B | CQX03 - Architectural | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone I | 8 | In progress |  | 48 | NOVEMBER
T-157-13406 | PS5-93-OB-2498C | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System |  | PS5-03-03 | PS5 - Milestone B | 1.1 | In progress |  | 15 | SEPTEMBER
T-892-13407 | PS5-48-IK-6337C | CQH03 - FCU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-07-25 | PS5-08-02 | PS5 - Milestone I | 8 | Closed | 17 | 41 | JULY
T-467-13408 | PS5-68-UR-1706B | CQE02 - LV Cable Installation | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-04 - Electrical Earthing EITS Building |  | PS5-63-04 | PS5 - Milestone B | 1.1 | To be completed |  | 24 | SEPTEMBER
T-474-13409 | PS5-44-OB-5706B | CQS02 - Gas Detection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System |  | PS5-01-08 | PS5 - Milestone G | 6 | In progress |  | 13 | AUGUST
T-731-13410 | PS5-95-OB-1871D | CQT03 - PA/GA System | PCOM - Precommissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone H | 7 | To be completed |  | 32 | NOVEMBER
T-335-13411 | PS5-15-IK-9756C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-07-20 | PS5-06-02 | PS5 - Milestone H | 7 | Closed | 43 | 45 | JULY
T-428-13412 | PS5-57-IK-3833D | CQS03 - Deluge System | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone C | 2 | To be completed |  | 13 | AUGUST
T-222-13413 | PS5-80-OB-8298A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone E | 4 | To be completed |  | 6 | SEPTEMBER
T-675-13414 | PS5-88-UR-7036B | CQP05 - Insulation | PCOM - Precommissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone B | 1.1 | To be completed |  | 19 | OCTOBER
T-157-13415 | PS5-25-OB-6684D | CQM01 - Pump Installation | COM - Commissioning | M | Walkdown | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-08 - Drencher System | 2026-07-12 | PS5-01-08 | PS5 - Milestone B | 1.1 | Closed | 4 | 35 | JULY
T-171-13416 | PS5-27-OB-1942A | CQH04 - Insulation | COM - Commissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone C | 2 | In progress |  | 35 | AUGUST
T-695-13417 | PS5-83-UR-3603B | CQP03 - Flange Management | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-62-02 - Cable Tray Secondary |  | PS5-62-02 | PS5 - Milestone C | 2 | In progress |  | 31 | DECEMBER
T-230-13418 | PS5-36-OB-3738A | CQS04 - Foam System | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone E | 4 | To be completed |  | 11 | SEPTEMBER
T-493-13419 | PS5-09-IK-2496B | CQP03 - Flange Management | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone E | 4 | To be completed |  | 21 | AUGUST
T-881-13420 | PS5-12-OB-5300B | CQH03 - FCU Installation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-03-11 | PS5-09-04 | PS5 - Milestone F | 5 | Closed | 45 | 36 | MARCH
T-271-13421 | PS5-55-OB-6181C | CQP02 - Valve Installation | COM - Commissioning | P | Precommissioning | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone D | 3 | To be completed |  | 41 | DECEMBER
T-925-13422 | PS5-87-OB-3743B | CQS01 - Fire Protection | COM - Commissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone G | 6 | To be completed |  | 6 | SEPTEMBER
T-268-13423 | PS5-86-OB-2021B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | PS5 - Milestone B | 1.1 | In progress |  | 20 | OCTOBER
T-798-13424 | PS5-95-UR-6775D | CQE02 - LV Cable Installation | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone D | 3 | To be completed |  | 17 | OCTOBER
T-935-13425 | PS5-39-OB-1662B | CQP05 - Insulation | PCOM - Precommissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-01-20 | PS5-09-03 | PS5 - Milestone E | 4 | Closed | 35 | 48 | JANUARY
T-470-13426 | PS5-47-OB-5863A | CQT04 - CCTV Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone B | 1.1 | On hold |  | 17 | DECEMBER
T-130-13427 | PS5-02-IK-3279C | CQE04 - Transformer | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone E | 4 | In progress |  | 25 | OCTOBER
T-051-13428 | PS5-63-OB-4339D | CQM05 - Rotating Equipment | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank | 2026-04-06 | PS5-02-01 | PS5 - Milestone F | 5 | Closed | 7 | 19 | APRIL
T-566-13429 | PS5-67-IK-2343C | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone C | 2 | To be completed |  | 16 | NOVEMBER
T-340-13430 | PS5-98-OB-5282B | CQM02 - Compressor | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A |  | PS5-10-03 | PS5 - Milestone I | 8 | On hold |  | 32 | DECEMBER
T-708-13431 | PS5-49-UR-3966B | CQS04 - Foam System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building | 2026-05-23 | PS5-06-02 | PS5 - Milestone I | 8 | Closed | 12 | 31 | MAY
T-228-13432 | PS5-88-IK-2926A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone I | 8 | To be completed |  | 17 | AUGUST
T-653-13433 | PS5-37-OB-7149D | CQE01 - HV Cable Installation | COM - Commissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone E | 4 | In progress |  | 25 | AUGUST
T-362-13434 | PS5-55-IK-9141B | CQT01 - Cable Installation | PCOM - Precommissioning | T | Conformity Check | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-08-05 | PS5-01-09 | PS5 - Milestone H | 7 | Closed | 32 | 44 | AUGUST
T-949-13435 | PS5-46-OB-5070A | CQM02 - Compressor | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | PS5 - Milestone D | 3 | In progress |  | 33 | SEPTEMBER
T-136-13436 | PS5-89-OB-7877B | CQE01 - HV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone H | 7 | On hold |  | 41 | SEPTEMBER
T-107-13437 | PS5-51-OB-5493B | CQM04 - Vessel | COM - Commissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-02-22 | PS5-09-03 | PS5 - Milestone I | 8 | Closed | 7 | 25 | FEBRUARY
T-972-13438 | PS5-17-OB-7148A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-02 - Transformer 6.6kV/0.4kV |  | PS5-09-02 | PS5 - Milestone D | 3 | To be completed |  | 22 | SEPTEMBER
T-931-13439 | PS5-56-IK-8885D | CQS04 - Foam System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-09 - Inergen for EITS Building | 2026-07-18 | PS5-01-09 | PS5 - Milestone E | 4 | Closed | 17 | 5 | JULY
T-797-13440 | PS5-71-OB-1190D | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone G | 6 | On hold |  | 30 | AUGUST
T-515-13441 | PS5-43-OB-9922D | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-08-21 | PS5-99-03 | PS5 - Milestone E | 4 | Closed | 47 | 21 | AUGUST
T-612-13442 | PS5-40-IK-5553B | CQX02 - Concrete Works | COM - Commissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone C | 2 | On hold |  | 42 | OCTOBER
T-257-13443 | PS5-76-OB-1087C | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone H | 7 | To be completed |  | 27 | SEPTEMBER
T-821-13444 | PS5-75-OB-3045C | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-01 - Diesel Storage Tank |  | PS5-02-01 | PS5 - Milestone A | 1 | In progress |  | 14 | SEPTEMBER
T-014-13445 | PS5-44-OB-1917B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area |  | PS5-99-02 | PS5 - Milestone A | 1 | To be completed |  | 5 | SEPTEMBER
T-603-13446 | PS5-98-OB-4820C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-02 - Chiller System B | 2026-05-10 | PS5-07-02 | PS5 - Milestone E | 4 | Closed | 44 | 22 | MAY
T-053-13447 | PS5-68-UR-4910D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-03-09 | PS5-60-01 | PS5 - Milestone A | 1 | Closed | 45 | 14 | MARCH
T-424-13448 | PS5-91-IK-6941D | CQI01 - Instrument Tubing | COM - Commissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-03 - CCTV System |  | PS5-05-03 | PS5 - Milestone B | 1.1 | In progress |  | 25 | SEPTEMBER
T-947-13449 | PS5-64-OB-7334C | CQM01 - Pump Installation | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-05 - Foam System |  | PS5-01-05 | PS5 - Milestone H | 7 | In progress |  | 8 | DECEMBER
T-480-13450 | PS5-03-IK-6902D | CQS03 - Deluge System | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main | 2026-01-08 | PS5-01-04 | PS5 - Milestone I | 8 | Closed | 22 | 7 | JANUARY
T-430-13451 | PS5-84-UR-3429A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Walkdown | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone B | 1.1 | To be completed |  | 35 | OCTOBER
T-182-13452 | PS5-38-OB-6474B | CQX01 - Steel Structure | PCOM - Precommissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System |  | PS5-05-02 | PS5 - Milestone E | 4 | To be completed |  | 19 | AUGUST
T-720-13453 | PS5-09-IK-2582B | CQI03 - Control Valve | PCOM - Precommissioning | I | Conformity Check | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone G | 6 | To be completed |  | 16 | NOVEMBER
T-081-13454 | PS5-71-OB-9923B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone D | 3 | On hold |  | 43 | OCTOBER
T-816-13455 | PS5-60-OB-8953A | CQT02 - Fiber Optic | PCOM - Precommissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone E | 4 | To be completed |  | 32 | AUGUST
T-845-13456 | PS5-61-OB-5008A | CQE05 - Switchgear | COM - Commissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-09-02 | PS5-10-03 | PS5 - Milestone E | 4 | Closed | 35 | 42 | SEPTEMBER
T-179-13457 | PS5-80-IK-7350A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area | 2026-02-21 | PS5-99-03 | PS5 - Milestone G | 6 | Closed | 14 | 44 | FEBRUARY
T-786-13458 | PS5-34-OB-2393B | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone E | 4 | To be completed |  | 43 | NOVEMBER
T-541-13459 | PS5-59-OB-3003A | CQH04 - Insulation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-08-10 | PS5-99-02 | PS5 - Milestone I | 8 | Closed | 41 | 8 | AUGUST
T-394-13460 | PS5-42-IK-8226D | CQE05 - Switchgear | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center |  | PS5-09-03 | PS5 - Milestone F | 5 | To be completed |  | 46 | SEPTEMBER
T-586-13461 | PS5-19-OB-7124B | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-03 - Area Completion Utilities Area |  | PS5-99-03 | PS5 - Milestone H | 7 | In progress |  | 11 | SEPTEMBER
T-514-13462 | PS5-89-OB-1818C | CQH03 - FCU Installation | COM - Commissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection | 2026-02-26 | PS5-06-03 | PS5 - Milestone D | 3 | Closed | 35 | 37 | FEBRUARY
T-915-13463 | PS5-61-IK-4044C | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-05 - Drain System | 2026-07-02 | PS5-10-05 | PS5 - Milestone F | 5 | Closed | 40 | 14 | JULY
T-971-13464 | PS5-63-UR-8690A | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone B | 1.1 | In progress |  | 4 | OCTOBER
T-630-13465 | PS5-78-OB-3844B | CQI04 - Analyzer Installation | COM - Commissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System |  | PS5-07-03 | PS5 - Milestone A | 1 | In progress |  | 7 | AUGUST
T-412-13466 | PS5-55-OB-4328A | CQX01 - Steel Structure | PCOM - Precommissioning | B | Test Pack | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System | 2026-08-19 | PS5-04-02 | PS5 - Milestone C | 2 | Closed | 8 | 41 | AUGUST
T-253-13467 | PS5-99-OB-8553A | CQX02 - Concrete Works | COM - Commissioning | B | Conformity Check | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-02 - SIS System |  | PS5-04-02 | PS5 - Milestone C | 2 | To be completed |  | 37 | NOVEMBER
T-108-13468 | PS5-18-UR-6901A | CQP04 - Hydrotest | COM - Commissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone A | 1 | In progress |  | 32 | SEPTEMBER
T-634-13469 | PS5-46-IK-9262C | CQS02 - Gas Detection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-06 - Deluge System |  | PS5-01-06 | PS5 - Milestone B | 1.1 | To be completed |  | 5 | OCTOBER
T-834-13470 | PS5-34-UR-9111D | CQH04 - Insulation | PCOM - Precommissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-02 - DC UPS - EITS Building |  | PS5-06-02 | PS5 - Milestone B | 1.1 | To be completed |  | 9 | AUGUST
T-558-13471 | PS5-62-OB-3464B | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-01 - Area Completion Building Area |  | PS5-99-01 | PS5 - Milestone A | 1 | To be completed |  | 20 | DECEMBER
T-985-13472 | PS5-49-UR-6381A | CQE05 - Switchgear | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-08-07 | PS5-07-04 | PS5 - Milestone A | 1 | Closed | 46 | 40 | AUGUST
T-388-13473 | PS5-12-OB-1039A | CQI02 - Transmitter Installation | COM - Commissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-07 - Guard Huts | 2026-05-18 | PS5-82-07 | PS5 - Milestone G | 6 | Closed | 12 | 10 | MAY
T-667-13474 | PS5-69-OB-4893D | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone I | 8 | To be completed |  | 15 | DECEMBER
T-648-13475 | PS5-68-OB-9681A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Test Pack | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-01 - Telecom Network | 2026-03-01 | PS5-05-01 | PS5 - Milestone A | 1 | Closed | 4 | 29 | MARCH
T-457-13476 | PS5-89-UR-7822A | CQX02 - Concrete Works | PCOM - Precommissioning | B | Inspection | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-01 - Fire Water Jockey Pump A/B | 2026-10-06 | PS5-01-01 | PS5 - Milestone A | 1 | Closed | 15 | 22 | OCTOBER
T-743-13477 | PS5-20-UR-4792B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-05-02 - PA/GA System | 2026-06-19 | PS5-05-02 | PS5 - Milestone C | 2 | Closed | 14 | 38 | JUNE
T-031-13478 | PS5-32-OB-4543C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Inspection | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator | 2026-02-26 | PS5-08-02 | PS5 - Milestone H | 7 | Closed | 44 | 30 | FEBRUARY
T-975-13479 | PS5-58-OB-4679A | CQX03 - Architectural | COM - Commissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-03 - AHU System | 2026-06-28 | PS5-07-03 | PS5 - Milestone A | 1 | Closed | 38 | 35 | JUNE
T-991-13480 | PS5-72-OB-3408C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Precommissioning | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-09-25 | PS5-11-01 | PS5 - Milestone F | 5 | Closed | 19 | 11 | SEPTEMBER
T-704-13481 | PS5-50-UR-2203D | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-05-25 | PS5-09-04 | PS5 - Milestone F | 5 | Closed | 45 | 44 | MAY
T-444-13482 | PS5-26-OB-6042B | CQI02 - Transmitter Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A | 2026-08-02 | PS5-11-01 | PS5 - Milestone D | 3 | Closed | 16 | 16 | AUGUST
T-088-13483 | PS5-64-IK-1703C | CQP03 - Flange Management | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | PS5 - Milestone A | 1 | To be completed |  | 31 | AUGUST
T-989-13484 | PS5-88-UR-6123B | CQP04 - Hydrotest | COM - Commissioning | P | Walkdown | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-03 - Flame Detector System | 2026-12-02 | PS5-03-03 | PS5 - Milestone H | 7 | Closed | 19 | 42 | DECEMBER
T-697-13485 | PS5-64-IK-5886B | CQE05 - Switchgear | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone E | 4 | To be completed |  | 22 | DECEMBER
T-137-13486 | PS5-39-IK-9375D | CQT01 - Cable Installation | COM - Commissioning | T | Inspection | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-06-03 - Lightning Protection |  | PS5-06-03 | PS5 - Milestone H | 7 | In progress |  | 33 | AUGUST
T-555-13487 | PS5-02-OB-7719C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-04 - Fire Water Ring Main |  | PS5-01-04 | PS5 - Milestone E | 4 | To be completed |  | 44 | NOVEMBER
T-950-13488 | PS5-74-IK-5111D | CQT01 - Cable Installation | COM - Commissioning | T | Test Pack | Telecom | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-02 - Guard Hut B |  | PS5-11-02 | PS5 - Milestone A | 1 | In progress |  | 19 | NOVEMBER
T-904-13489 | PS5-91-OB-8545C | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-04 - Process piping B |  | PS5-10-04 | PS5 - Milestone A | 1 | To be completed |  | 5 | DECEMBER
T-004-13490 | PS5-27-OB-4349A | CQI04 - Analyzer Installation | PCOM - Precommissioning | I | Inspection | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-06 - Vent System |  | PS5-10-06 | PS5 - Milestone C | 2 | In progress |  | 46 | SEPTEMBER
T-970-13491 | PS5-02-IK-7067A | CQM03 - Heat Exchanger | PCOM - Precommissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-04 - 0.4kV Switchboard | 2026-05-02 | PS5-09-04 | PS5 - Milestone A | 1 | Closed | 43 | 21 | MAY
T-950-13492 | PS5-71-UR-6355B | CQE02 - LV Cable Installation | PCOM - Precommissioning | E | Precommissioning | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-01 - ESD System |  | PS5-03-01 | PS5 - Milestone I | 8 | To be completed |  | 6 | DECEMBER
T-750-13493 | PS5-85-IK-5588B | CQM03 - Heat Exchanger | COM - Commissioning | M | Test Pack | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-03 - Fire Water Pump B |  | PS5-01-03 | PS5 - Milestone A | 1 | On hold |  | 41 | SEPTEMBER
T-089-13494 | PS5-88-OB-2214D | CQS01 - Fire Protection | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-01 - Main Pipe Rack |  | PS5-10-01 | PS5 - Milestone H | 7 | To be completed |  | 33 | OCTOBER
T-851-13495 | PS5-29-IK-5769A | CQH02 - AHU Installation | PCOM - Precommissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing | 2026-04-25 | PS5-63-01 | PS5 - Milestone D | 3 | Closed | 26 | 24 | APRIL
T-433-13496 | PS5-16-UR-8754C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Inspection | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-01 - Guard Hut A |  | PS5-11-01 | PS5 - Milestone E | 4 | To be completed |  | 42 | AUGUST
T-207-13497 | PS5-58-OB-8327B | CQH04 - Insulation | COM - Commissioning | H | Test Pack | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone G | 6 | On hold |  | 13 | NOVEMBER
T-776-13498 | PS5-97-IK-4266C | CQP02 - Valve Installation | COM - Commissioning | P | Inspection | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-03 - 33kV ICSS System |  | PS5-04-03 | PS5 - Milestone C | 2 | To be completed |  | 10 | OCTOBER
T-304-13499 | PS5-79-IK-4316A | CQH03 - FCU Installation | PCOM - Precommissioning | H | Walkdown | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-02 - Structural Steel B |  | PS5-82-02 | PS5 - Milestone H | 7 | To be completed |  | 30 | OCTOBER
T-353-13500 | PS5-32-OB-4191C | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-01 - DCS System |  | PS5-04-01 | PS5 - Milestone D | 3 | In progress |  | 18 | NOVEMBER
T-542-13501 | PS5-87-OB-1783D | CQX01 - Steel Structure | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower |  | PS5-12-01 | PS5 - Milestone I | 8 | To be completed |  | 45 | OCTOBER
T-336-13502 | PS5-29-OB-9770B | CQS03 - Deluge System | PCOM - Precommissioning | S | Conformity Check | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-82-01 - Structural Steel A |  | PS5-82-01 | PS5 - Milestone A | 1 | In progress |  | 8 | NOVEMBER
T-155-13503 | PS5-38-IK-7361D | CQH04 - Insulation | COM - Commissioning | H | Conformity Check | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-07 - 0.4kV Switchboard EITS Building | 2026-06-09 | PS5-61-07 | PS5 - Milestone G | 6 | Closed | 46 | 34 | JUNE
T-554-13504 | PS5-65-IK-5001C | CQE03 - Earthing | PCOM - Precommissioning | E | Test Pack | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone H | 7 | To be completed |  | 45 | SEPTEMBER
T-014-13505 | PS5-84-OB-6998A | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Precommissioning | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-02-02 - Diesel Transfer Pump |  | PS5-02-02 | PS5 - Milestone B | 1.1 | In progress |  | 23 | NOVEMBER
T-117-13506 | PS5-28-UR-1910A | CQS03 - Deluge System | PCOM - Precommissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-03-02 - Fire & Gas Detection |  | PS5-03-02 | PS5 - Milestone A | 1 | To be completed |  | 34 | DECEMBER
T-535-13507 | PS5-51-OB-3695C | CQS01 - Fire Protection | PCOM - Precommissioning | S | Walkdown | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-04-04 - 33kV PCS System | 2026-04-10 | PS5-04-04 | PS5 - Milestone H | 7 | Closed | 13 | 13 | APRIL
T-740-13508 | PS5-97-IK-8942A | CQS04 - Foam System | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-09-03 - Motor Control Center | 2026-04-04 | PS5-09-03 | PS5 - Milestone I | 8 | Closed | 22 | 33 | APRIL
T-113-13509 | PS5-56-IK-8358B | CQX04 - Painting & Coating | PCOM - Precommissioning | B | Walkdown | Building | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-11-03 - Admin Building | 2026-04-11 | PS5-11-03 | PS5 - Milestone G | 6 | Closed | 9 | 16 | APRIL
T-346-13510 | PS5-49-OB-7904D | CQP01 - Pipe Installation | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-04 - FCU System | 2026-07-08 | PS5-07-04 | PS5 - Milestone C | 2 | Closed | 24 | 10 | JULY
T-073-13511 | PS5-13-OB-7083D | CQP05 - Insulation | PCOM - Precommissioning | P | Conformity Check | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | PS5 - Milestone G | 6 | To be completed |  | 16 | OCTOBER
T-592-13512 | PS5-43-OB-1014A | CQP03 - Flange Management | PCOM - Precommissioning | P | Test Pack | Piping & Vessel | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-08-02 - Nitrogen Generator |  | PS5-08-02 | PS5 - Milestone A | 1 | To be completed |  | 12 | DECEMBER
T-618-13513 | PS5-95-IK-6066B | CQE03 - Earthing | PCOM - Precommissioning | E | Walkdown | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-10-03 - Process piping A | 2026-03-22 | PS5-10-03 | PS5 - Milestone I | 8 | Closed | 32 | 37 | MARCH
T-756-13514 | PS5-21-IK-2130D | CQM05 - Rotating Equipment | PCOM - Precommissioning | M | Precommissioning | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-12-01 - Cooling Tower | 2026-06-19 | PS5-12-01 | PS5 - Milestone G | 6 | Closed | 6 | 36 | JUNE
T-184-13515 | PS5-65-UR-7342C | CQH02 - AHU Installation | PCOM - Precommissioning | H | Precommissioning | HVAC | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-61-01 - 33kV Switchboard EITS Building |  | PS5-61-01 | PS5 - Milestone B | 1.1 | In progress |  | 41 | AUGUST
T-275-13516 | PS5-24-IK-8475B | CQE04 - Transformer | COM - Commissioning | E | Inspection | Electrical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-07-01 - Chiller System A |  | PS5-07-01 | PS5 - Milestone I | 8 | To be completed |  | 46 | DECEMBER
T-631-13517 | PS5-54-OB-3044D | CQI01 - Instrument Tubing | PCOM - Precommissioning | I | Precommissioning | Instrumentation | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-02 - Fire Water Pump A | 2026-06-22 | PS5-01-02 | PS5 - Milestone H | 7 | Closed | 48 | 19 | JUNE
T-723-13518 | PS5-77-OB-7969C | CQS01 - Fire Protection | COM - Commissioning | S | Test Pack | Safety | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-99-02 - Area Completion Process Area | 2026-01-14 | PS5-99-02 | PS5 - Milestone D | 3 | Closed | 13 | 22 | JANUARY
T-197-13519 | PS5-47-IK-4197B | CQM01 - Pump Installation | PCOM - Precommissioning | M | Conformity Check | Mechanical | CPP AGI | PS5 - TZA - PS5 - Tanzania | PS5-01-07 - Hydrant System |  | PS5-01-07 | PS5 - Milestone E | 4 | To be completed |  | 40 | SEPTEMBER