## Summary
PS-5 EIT TASK MANAGEMENT - SUMMARY DASHBOARD
1. TASK STATE OVERVIEW
Status | Open | Close | Total | Close %
To be completed | 8414 | 0 | 8414 | 0.0%
Started (not Completed) | 20 | 0 | 20 | 0.0%
Submitted | 17 | 0 | 17 | 0.0%
Completed (not Closed) | 6 | 0 | 6 | 0.0%
Closed | 0 | 1827 | 1827 | 100.0%
TOTAL | 8457 | 1827 | 10284 | 17.8%
2. DISCIPLINE BREAKDOWN
Discipline | Open | Close | Total | Close %
E | 3402 | 1207 | 4609 | 26.2%
I | 4016 | 581 | 4597 | 12.6%
T | 1039 | 39 | 1078 | 3.6%
TOTAL E+I+T | 8457 | 1827 | 10284 | 17.8%
3. CONFORMITY CHECK (Task Type)
Type | Open | Close | Total | Close %
Conformity Check | 5883 | 435 | 6318 | 6.9%
Other Types | 2574 | 1392 | 3966 | 35.1%
4. STATIC TEST (Task Type)
Type | Open | Close | Total | Close %
Static Test | 2574 | 1392 | 3966 | 35.1%
5. INSTALLATION & PULLING RFI
Status | Open | Close | Total | Close %
With RFI | 1734 | 1384 | 3118 | 44.4%
Without RFI | 6723 | 443 | 7166 | 6.2%
TOTAL | 8457 | 1827 | 10284 | 17.8%
6. TESTING RFI
Status | Open | Close | Total | Close %
With RFI | 1945 | 1618 | 3563 | 45.4%
Without RFI | 6512 | 209 | 6721 | 3.1%
TOTAL | 8457 | 1827 | 10284 | 17.8%
7. GLANDING & TERMINATION RFI
Status | Open | Close | Total | Close %
With RFI | 1 | 24 | 25 | 96.0%
TOTAL | 8457 | 1827 | 10284 | 17.8%
8. PUNCH ITEMS (A / B / C)
Category | Open | Close | Total | Close %
PUNCH A | 516 | 406 | 922 | 44.0%
PUNCH B | 1330 | 805 | 2135 | 37.7%
PUNCH C | 43 | 54 | 97 | 55.7%
TOTAL PUNCH | 1361 | 871 | 2232 | 39.0%
9. COLOR LEGEND
Color | Meaning
Yellow | Task State: To be completed
Orange | Task State: Started (not Completed)
Green (State) | Task State: Submitted
Light Blue (State) | Task State: Completed (not Closed)
Light Blue (RFI) | Has RFI Number
Red | Punch OPEN
Green (Punch) | Punch CLOSED

## PS-5 EIT TASK OPEN
PS-5 EIT TASK MANAGEMENT - OPEN TASKS
Task ID | Asset - Tag | Description | Discipline | Subsystem | Task State | INSTALLATION & PULLING | Testing | GLANDING & TERMINATION INSPECTION | PUNCH A | PUNCH B | PUNCH C
T-00018-0098 | PS5-61-ISR-0101 | CPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed
T-00018-0099 | PS5-61-ISR-0102 | CPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Started (not Completed)
T-00018-0100 | PS5-61-IU-0010 | CPX02 - Power transformer | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed
T-00018-0101 | PS5-61-IU-0011 | CPX02 - Power transformer | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed
T-00018-0103 | PS5-61-IV-0001B | CPX02 - Power transformer | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | To be completed | CPP-RFI-68-332-02-0395 | CPP-RFI-68-332-16-0396 |  | TZ-MID-68-WPR2-151112 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding [OPEN] ¦ TZ-MID-68-WPR2-151112 Transformer Grounding Not Complete [OPEN]
T-00018-0104 | PS5-63-IV-0010 | CPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed
T-00018-0105 | PS5-63-IV-0011 | CPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed
T-00018-0121 | PS5-61-IV-0002A | CPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-332-02-0395 | CPP-RFI-68-332-16-0396 |  | Doc.TZ-MID-68-WPR2-151112 - Missing Support by CPP1 [CLOSED] ¦ Doc.TZ-MID-68-WPR2-151112 - Cable Ladder not installed [CLOSED] ¦ TZ-MID-68-WPR2-151167 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding [OPEN] ¦ TZ-MID-68-WPR2-151167 Transformer Grounding Not Complete [OPEN] |  | Doc.TZ-MID-68-WPR2-151112 HV Trefoil Cable Clamp not installed [OPEN]
T-00018-0122 | PS5-61-IV-0002B | CPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-332-02-0395 | CPP-RFI-68-332-16-0396 |  | Doc.TZ-MID-68-WPR2-151112 - Missing Support by CPP1 [CLOSED] ¦ TZ-MID-68-WPR2-151167 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding [OPEN] ¦ TZ-MID-68-WPR2-151167 Transformer Grounding Not Complete [OPEN] |  | Doc.TZ-MID-68-WPR2-151112 HV Trefoil Cable Clamp not installed [OPEN]
T-00018-0123 | PS5-61-IV-0007A | CPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-332-02-0395 | CPP-RFI-68-332-16-0396 |  | TZ-MID-68-WPR2-151167 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding [OPEN] ¦ TZ-MID-68-WPR2-151167 Transformer Grounding Not Complete [OPEN] | Doc.TZ-MID-68-WPR2-151112 HV Trefoil Cable Clamp not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-151112 - Missing Support by CPP1 [CLOSED]
T-00018-0124 | PS5-61-IV-0007B | CPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-332-02-0395 | CPP-RFI-68-332-16-0396 |  | TZ-MID-68-WPR2-151167 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding [OPEN] ¦ TZ-MID-68-WPR2-151167 Transformer Grounding Not Complete [OPEN] | Doc.TZ-MID-68-WPR2-151112 HV Trefoil Cable Clamp not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-151112 - Missing Support by CPP1 [CLOSED]
T-00018-0192 | PS5-61-IU-0001A | CPX02 - Power transformer | E | PS5-60-01 - Power Generation Package A | To be completed
T-00018-0193 | PS5-61-IU-0001B | CPX02 - Power transformer | E | PS5-60-04 - Power Generation Package B | To be completed
T-00018-0194 | PS5-61-IU-0001C | CPX02 - Power transformer | E | PS5-60-07 - Power Generation Package C | To be completed
T-00018-0195 | PS5-61-IU-0001D | CPX02 - Power transformer | E | PS5-60-10 - Power Generation Package D | To be completed
T-00018-0196 | PS5-61-IU-0001E | CPX02 - Power transformer | E | PS5-60-13 - Power Generation Package E | To be completed
T-00018-0197 | PS5-61-IU-0001F | CPX02 - Power transformer | E | PS5-60-16 - Power Generation Package F | To be completed
T-00018-0198 | PS5-61-IU-0001G | CPX02 - Power transformer | E | PS5-60-19 - Power Generation Package G | To be completed
T-00018-0237 | PS5-79-IV-0001 | CPX02 - Power transformer | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00018-0238 | PS5-79-IV-0002 | CPX02 - Power transformer | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00018-0239 | PS5-79-IV-0003 | CPX02 - Power transformer | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00018-0240 | PS5-79-IV-0004 | CPX02 - Power transformer | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00018-0241 | PS5-79-IV-0005 | CPX02 - Power transformer | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00018-0242 | PS5-79-IV-0006 | CPX02 - Power transformer | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  | TZ-MID-68-WPR2-151117 Rectify concrete broken 1 pcs anchor bolt [OPEN] | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00018-0243 | PS5-79-IV-0007 | CPX02 - Power transformer | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00018-0244 | PS5-79-IV-0008 | CPX02 - Power transformer | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00018-0245 | PS5-79-IV-0009 | CPX02 - Power transformer | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00018-0246 | PS5-79-IV-0010 | CPX02 - Power transformer | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00018-0247 | PS5-79-IV-0011 | CPX02 - Power transformer | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151118 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00018-0248 | PS5-79-IV-0012 | CPX02 - Power transformer | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00018-0249 | PS5-87-IRF-0001 | CPX02 - Power transformer | E | PS5-53-01 - Utility Water / Storage Tank | To be completed
T-00018-0250 | PS5-87-IRF-0002 | CPX02 - Power transformer | E | PS5-71-04 - CFO Storage Tank | To be completed
T-00018-0251 | PS5-87-IRF-0003 | CPX02 - Power transformer | E | PS5-71-12 - CFO Service Tank | To be completed
T-00018-0252 | PS5-87-IRF-0004 | CPX02 - Power transformer | E | PS5-71-15 - Diesel Fuel Storage Tank | To be completed
T-00018-0294 | PS5-61-IV-0005A | CPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed
T-00018-0295 | PS5-61-IV-0005B | CPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed
T-00019-0035 | PS5-61-IK-0003 | CPX05 - LV switchboard | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/2-13-0402 | CPP-RFI-68-332-13-0424 |  | TZ-MID-68-WPR2-151166 Panel Grounding not yet connected to the grid [OPEN] ¦ TZ-MID-68-WPR2-151166 To perform the busbar contact resistance test (ductor test) [OPEN] |  | TZ-MID-68-WPR2-151166 To be cleanning internal and external of the panel [OPEN]
T-00019-0036 | PS5-61-IK-0006 | CPX05 - LV switchboard | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed
T-00022-3398 | PS5-61-IJ-0010-CH01 | CPX08 - HV Power Cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed | CPP-RFI-68-33/1-05-0198 | CPP-RFI-68-33/1-07-201
T-00022-3399 | PS5-61-IJ-0010-CH02 | CPX08 - HV Power Cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed | CPP-RFI-68-33/1-05-0198 | CPP-RFI-68-33/1-07-201
T-00022-3400 | PS5-61-IJ-0010-CH03 | CPX08 - HV Power Cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed | CPP-RFI-68-33/1-05-0198 | CPP-RFI-68-33/1-07-201
T-00022-3401 | PS5-61-IJ-0011-CH01 | CPX08 - HV Power Cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed | CPP-RFI-68-33/1-05-0198 | CPP-RFI-68-33/1-07-201
T-00022-3402 | PS5-61-IJ-0011-CH02 | CPX08 - HV Power Cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed | CPP-RFI-68-33/1-05-0198 | CPP-RFI-68-33/1-07-201
T-00022-3403 | PS5-61-IJ-0011-CH03 | CPX08 - HV Power Cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed | CPP-RFI-68-33/1-05-0198 | CPP-RFI-68-33/1-07-201
T-00022-3404 | PS5-61-ISR-0101-CH01 | CPX08 - HV Power Cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-33/1-05-0197
T-00022-3405 | PS5-61-ISR-0101-CH02 | CPX08 - HV Power Cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-200
T-00022-3406 | PS5-61-ISR-0101-CH03 | CPX08 - HV Power Cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-200
T-00022-3407 | PS5-61-ISR-0102-CH01 | CPX08 - HV Power Cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00022-3408 | PS5-61-ISR-0102-CH02 | CPX08 - HV Power Cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00022-3409 | PS5-61-ISR-0102-CH03 | CPX08 - HV Power Cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00022-3431 | PS5-61-IU-0010-CH01 | CPX08 - HV Power Cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-200
T-00022-3432 | PS5-61-IU-0010-CH02 | CPX08 - HV Power Cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-200
T-00022-3433 | PS5-61-IU-0010-CH03 | CPX08 - HV Power Cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-200
T-00022-3434 | PS5-61-IU-0011-CH01 | CPX08 - HV Power Cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-200
T-00022-3435 | PS5-61-IU-0011-CH02 | CPX08 - HV Power Cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-200
T-00022-3436 | PS5-61-IU-0011-CH03 | CPX08 - HV Power Cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-200
T-00022-3461 | PS5-61-IV-0005A-CH01 | CPX08 - HV Power Cable | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00022-3462 | PS5-61-IV-0005A-CH02 | CPX08 - HV Power Cable | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00022-3463 | PS5-61-IV-0005A-CH03 | CPX08 - HV Power Cable | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00022-3464 | PS5-61-IV-0005B-CH01 | CPX08 - HV Power Cable | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00022-3465 | PS5-61-IV-0005B-CH02 | CPX08 - HV Power Cable | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00022-3466 | PS5-61-IV-0005B-CH03 | CPX08 - HV Power Cable | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00022-3473 | PS5-61-NER-0010-CH01 | CPX08 - HV Power Cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151112 Cable ladder at transformer side not yet install PS5-61-IU-0010 [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete termination [OPEN] | TZ-MID-68-WPR2-151112 Cable Dressing to be done at both side [OPEN]
T-00022-3474 | PS5-61-NER-0011-CH01 | CPX08 - HV Power Cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151112 Cable ladder at transformer side not yet install PS5-61-IU-0011 [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete termination [OPEN] | TZ-MID-68-WPR2-151112 Cable Dressing to be done at both side [OPEN]
T-00022-3475 | PS5-63-IV-0010-CH01 | CPX08 - HV Power Cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00022-3476 | PS5-63-IV-0010-CH02 | CPX08 - HV Power Cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00022-3477 | PS5-63-IV-0010-CH03 | CPX08 - HV Power Cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00022-3478 | PS5-63-IV-0011-CH01 | CPX08 - HV Power Cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00022-3479 | PS5-63-IV-0011-CH02 | CPX08 - HV Power Cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00022-3480 | PS5-63-IV-0011-CH03 | CPX08 - HV Power Cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00022-3481 | PS5-63-NER-0010-CH01 | CPX08 - HV Power Cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0210 | CPP-RFI-68-331-07-0209 |  | TZ-MID-68-WPR2-151112 Cable ladder to be install at transformer side (PS5-88-LD-HV-6019) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench backfilled to be done (PS5-88-CU-HV-0031) [OPEN] | TZ-MID-68-WPR2-151112 Cable dressing to be done at both side [OPEN]
T-00022-3482 | PS5-63-NER-0011-CH01 | CPX08 - HV Power Cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0210 | CPP-RFI-68-331-07-0209 |  | TZ-MID-68-WPR2-151112 Cable ladder to be install at transformer side (PS5-88-LD-HV-6020) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench backfilled to be done (PS5-88-CU-HV-0030) [OPEN] | TZ-MID-68-WPR2-151112 Cable dressing to be done at both side [OPEN]
T-00022-3483 | PS5-79-BH-0001-CH01 | CPX08 - HV Power Cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation [OPEN]
T-00022-3484 | PS5-79-BH-0001-CH02 | CPX08 - HV Power Cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation [OPEN]
T-00022-3485 | PS5-79-BH-0001-CH03 | CPX08 - HV Power Cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation [OPEN]
T-00022-3486 | PS5-79-BH-0002-CH01 | CPX08 - HV Power Cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation [OPEN]
T-00022-3487 | PS5-79-BH-0002-CH02 | CPX08 - HV Power Cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation [OPEN]
T-00022-3488 | PS5-79-BH-0002-CH03 | CPX08 - HV Power Cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation [OPEN]
T-00023-10060 | PS5-62-IE-0001-CL02 | CPX09 - LV Power Cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00023-10061 | PS5-62-IE-0001-CL03 | CPX09 - LV Power Cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00023-10062 | PS5-62-IE-0001-CL05 | CPX09 - LV Power Cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00023-10063 | PS5-62-IE-0001-CL06 | CPX09 - LV Power Cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00023-10064 | PS5-62-IE-0001-CL07 | CPX09 - LV Power Cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00023-10065 | PS5-62-IE-0001-CL51 | CPX09 - LV Power Cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00023-10066 | PS5-62-IE-0001-CL52 | CPX09 - LV Power Cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00023-10067 | PS5-62-IE-0001-CL53 | CPX09 - LV Power Cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00023-10068 | PS5-62-IE-0001-CL54 | CPX09 - LV Power Cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00023-10069 | PS5-62-IE-0001-CL55 | CPX09 - LV Power Cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00023-10070 | PS5-62-IE-0001-CL56 | CPX09 - LV Power Cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00023-10071 | PS5-62-IE-0001-CL57 | CPX09 - LV Power Cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00023-10072 | PS5-62-IE-0001-CL58 | CPX09 - LV Power Cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00023-10073 | PS5-62-IE-0001-CL59 | CPX09 - LV Power Cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00023-10074 | PS5-62-IE-0002-CL02 | CPX09 - LV Power Cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00023-10075 | PS5-62-IE-0002-CL03 | CPX09 - LV Power Cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00023-10076 | PS5-62-IE-0002-CL04 | CPX09 - LV Power Cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00023-10077 | PS5-62-IE-0002-CL05 | CPX09 - LV Power Cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00023-10078 | PS5-62-IE-0002-CL06 | CPX09 - LV Power Cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00023-10079 | PS5-62-IE-0002-CL07 | CPX09 - LV Power Cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00023-10080 | PS5-62-IE-0002-CL52 | CPX09 - LV Power Cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00023-10081 | PS5-62-IE-0002-CL53 | CPX09 - LV Power Cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00023-10082 | PS5-62-IE-0002-CL54 | CPX09 - LV Power Cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00023-10083 | PS5-62-IE-0002-CL55 | CPX09 - LV Power Cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00023-10084 | PS5-62-IE-0002-CL56 | CPX09 - LV Power Cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00023-10085 | PS5-62-IE-0002-CL57 | CPX09 - LV Power Cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00023-10086 | PS5-62-IE-0002-CL58 | CPX09 - LV Power Cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00023-10087 | PS5-62-IE-0002-CL59 | CPX09 - LV Power Cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00023-10088 | PS5-62-IE-0002-CL60 | CPX09 - LV Power Cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00023-10535 | PS5-06-GB-0003-CG01 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed
T-00023-10536 | PS5-60-IN-0002A-CG01 | CPX09 - LV Power Cable | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed
T-00023-10537 | PS5-60-IN-0002B-CG01 | CPX09 - LV Power Cable | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed
T-00023-10538 | PS5-60-IN-0002C-CG01 | CPX09 - LV Power Cable | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00023-10539 | PS5-60-IN-0002D-CG01 | CPX09 - LV Power Cable | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00023-10540 | PS5-60-IN-0002E-CG01 | CPX09 - LV Power Cable | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00023-10541 | PS5-60-IN-0002F-CG01 | CPX09 - LV Power Cable | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00023-10542 | PS5-60-IN-0002G-CG01 | CPX09 - LV Power Cable | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00023-10584 | PS5-05-BE-0001-CG01 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet install at EDG side [OPEN] | TZ-MID-68-WPR2-151111 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151111 Dressing to be done at both end [OPEN]
T-00023-10585 | PS5-06-IG-0004A-CG01 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed
T-00023-10586 | PS5-06-IG-0004B-CG01 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed
T-00023-10587 | PS5-25-DM-3100A-CG01 | CPX09 - LV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable dressing to be done both side [OPEN]
T-00023-10588 | PS5-25-DM-3100A-CG02 | CPX09 - LV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable dressing to be done both side [OPEN]
T-00023-10589 | PS5-25-DM-3100B-CG01 | CPX09 - LV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Permanent cable tag to be install [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable actual laid in the HV Cable trench PS5-88-CU-HV-0002 in drawing mention PS5-88-CU-LV-0011 need to be RLMU drawing as per actual. (Dwg No.TZ-MID-68-WPR2-151114) [OPEN]
T-00023-10590 | PS5-25-DM-3100B-CG02 | CPX09 - LV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Permanent cable tag to be install [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable actual laid in the HV Cable trench PS5-88-CU-HV-0002 in drawing mention PS5-88-CU-LV-0011 need to be RLMU drawing as per actual. (Dwg No.TZ-MID-68-WPR2-151114) [OPEN]
T-00023-10591 | PS5-25-DM-3100C-CG01 | CPX09 - LV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Permanent cable tag to be install [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable actual laid in the HV Cable trench PS5-88-CU-HV-0001 in drawing mention PS5-88-CU-LV-0012 need to be RLMU drawing as per actual. (Dwg No.TZ-MID-68-WPR2-151114) [OPEN]
T-00023-10592 | PS5-25-DM-3100C-CG02 | CPX09 - LV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Permanent cable tag to be install [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable actual laid in the HV Cable trench PS5-88-CU-HV-0001 in drawing mention PS5-88-CU-LV-0012 need to be RLMU drawing as per actual. (Dwg No.TZ-MID-68-WPR2-151114) [OPEN]
T-00023-10593 | PS5-60-IH-0001A-CG01 | CPX09 - LV Power Cable | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | To be completed
T-00023-10594 | PS5-60-IH-0001B-CG01 | CPX09 - LV Power Cable | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | To be completed
T-00023-10595 | PS5-60-IH-0001C-CG01 | CPX09 - LV Power Cable | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | To be completed
T-00023-10596 | PS5-60-IH-0001D-CG01 | CPX09 - LV Power Cable | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | To be completed
T-00023-10597 | PS5-60-IH-0001E-CG01 | CPX09 - LV Power Cable | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed
T-00023-10598 | PS5-60-IH-0001F-CG01 | CPX09 - LV Power Cable | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00023-10599 | PS5-60-IH-0001G-CG01 | CPX09 - LV Power Cable | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed
T-00023-10600 | PS5-60-IH-0002-CG01 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-10601 | PS5-60-IH-0002-CG02 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-10602 | PS5-61-IH-0004-CG01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-10603 | PS5-61-IH-0004-CG02 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-10604 | PS5-61-IH-0004-CG03 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-10605 | PS5-61-IH-0004-CG04 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-10616 | PS5-61-IK-0003-CG07 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable Trench Not yet complete installation [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Dressing Cable Both Side to be done [OPEN] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Permanent Cable Tag Missing Both End [CLOSED]
T-00023-10886 | PS5-28-DM-31100-CL01 | CPX09 - LV Power Cable | E | PS5-28-10 - Oil Skimmer Package | To be completed
T-00023-10887 | PS5-60-BE-0007A-CL02 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN]
T-00023-10888 | PS5-60-BE-0007A-CL03 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN]
T-00023-10889 | PS5-60-BE-0007B-CL02 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN]
T-00023-10890 | PS5-60-BE-0007B-CL03 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN]
T-00023-10891 | PS5-60-BE-0007C-CL02 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed |  | CPP-RFI-68-33/1-07-0410
T-00023-10892 | PS5-60-BE-0007C-CL03 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed |  | CPP-RFI-68-33/1-07-0410
T-00023-10893 | PS5-60-BE-0007D-CL02 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151179, Cable Coiled in Control Panel Side, Not yet Reaching Final Destination [OPEN] | Doc. TZ-MID-68-WPR2-151179, Cable Tagging not yet installed at both side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179, Cable Dressing not yet done [OPEN]
T-00023-10894 | PS5-60-BE-0007D-CL03 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151179, Cable Coiled in Control Panel Side, Not yet Reaching Final Destination [OPEN] | Doc. TZ-MID-68-WPR2-151179, Cable Tagging not yet installed at both side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179, Cable dresing not yet done [OPEN]
T-00023-10895 | PS5-60-BE-0007E-CL02 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed |  | CPP-RFI-68-33/1-07-0410
T-00023-10896 | PS5-60-BE-0007E-CL03 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed |  | CPP-RFI-68-33/1-07-0410
T-00023-10897 | PS5-60-BE-0007F-CL02 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed |  | CPP-RFI-68-33/1-07-0410
T-00023-10898 | PS5-60-BE-0007F-CL03 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed |  | CPP-RFI-68-33/1-07-0410
T-00023-10899 | PS5-60-BE-0007G-CL02 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed |  | CPP-RFI-68-33/1-07-0410
T-00023-10900 | PS5-60-BE-0007G-CL03 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed |  | CPP-RFI-68-33/1-07-0410
T-00023-10901 | PS5-60-ISO-62800A-CL01 | CPX09 - LV Power Cable | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done [OPEN]
T-00023-10902 | PS5-60-ISO-62800C-CL01 | CPX09 - LV Power Cable | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-10903 | PS5-60-ISO-62800E-CL01 | CPX09 - LV Power Cable | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray not finished [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done [OPEN]
T-00023-10904 | PS5-60-ISO-62800G-CL01 | CPX09 - LV Power Cable | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-331-07-0423
T-00023-10965 | PS5-08-85CP-1201-CS01 | CPX09 - LV Power Cable | E | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00023-10966 | PS5-08-85CP-1202-CS01 | CPX09 - LV Power Cable | E | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00023-10967 | PS5-08-85CP-1601-CS01 | CPX09 - LV Power Cable | E | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00023-11058 | PS5-05-BE-0001-CL12 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  | TZ-MID-68-WPR2-151111, 151112, 151116 To be install vertical cable ladder at EDG Junction box side [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00023-11059 | PS5-09-DM-84500A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-11060 | PS5-09-DM-84500B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-11250 | PS5-71-BE-0001A-CL01 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11251 | PS5-71-BE-0001A-CL02 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11252 | PS5-71-BE-0001A-CL03 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11253 | PS5-71-BE-0001A-CL04 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11254 | PS5-71-BE-0001A-CL05 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11255 | PS5-71-BE-0001A-CL06 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11256 | PS5-71-BE-0001A-CL07 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11257 | PS5-71-BE-0001A-CL08 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11258 | PS5-71-BE-0001A-CL09 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11259 | PS5-71-BE-0001A-CL10 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11260 | PS5-71-BE-0001A-CL11 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11261 | PS5-71-BE-0001A-CL12 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11262 | PS5-71-BE-0001B-CL01 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | Started (not Completed)
T-00023-11263 | PS5-71-BE-0001B-CL02 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11264 | PS5-71-BE-0001B-CL03 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11265 | PS5-71-BE-0001B-CL04 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11266 | PS5-71-BE-0001B-CL05 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11267 | PS5-71-BE-0001B-CL06 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11268 | PS5-71-BE-0001B-CL07 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11269 | PS5-71-BE-0001B-CL08 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11270 | PS5-71-BE-0001B-CL09 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11271 | PS5-71-BE-0001B-CL10 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11272 | PS5-71-BE-0001B-CL11 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11273 | PS5-71-BE-0001B-CL12 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00023-11274 | PS5-71-BE-0005-CL01 | CPX09 - LV Power Cable | E | PS5-71-19 - Diesel Separator Module (UCP) | To be completed
T-00023-11275 | PS5-71-BE-0005-CL02 | CPX09 - LV Power Cable | E | PS5-71-19 - Diesel Separator Module (UCP) | To be completed
T-00023-11276 | PS5-71-BE-0005-CL03 | CPX09 - LV Power Cable | E | PS5-71-19 - Diesel Separator Module (UCP) | To be completed
T-00023-11277 | PS5-71-BE-0005-CL04 | CPX09 - LV Power Cable | E | PS5-71-19 - Diesel Separator Module (UCP) | To be completed
T-00023-4695 | PS5-01-BE-0001-CL01 | CPX09 - LV Power Cable | E | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  | TZ-MID-68-WPR2-151117 Need to Open trench at PS5-05-IG-0004 side (PS5-88-BU-LV-00165, PS5-88-BU-LV-00164). [OPEN] ¦ TZ-MID-68-WPR2-151117 Cable to be laid inside conduit at PS5-01-BE-0001 side. [OPEN] | TZ-MID-68-WPR2-151117 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151117 Cable dressing to be done both side [OPEN]
T-00023-4696 | PS5-01-FCV-0003A-CL01 | CPX09 - LV Power Cable | E | PS5-01-02 - Fire Water Pump A | Started (not Completed) | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely [OPEN]
T-00023-4697 | PS5-01-FCV-0003B-CL01 | CPX09 - LV Power Cable | E | PS5-01-03 - Fire Water Pump B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely [OPEN]
T-00023-4698 | PS5-01-FCV-0004A-CL01 | CPX09 - LV Power Cable | E | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed [CLOSED]
T-00023-4699 | PS5-01-FCV-0004B-CL01 | CPX09 - LV Power Cable | E | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed [CLOSED]
T-00023-4710 | PS5-01-IG-0001-CL01 | CPX09 - LV Power Cable | E | PS5-01-10 - Water Mist Package | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-4711 | PS5-01-LB-0004-CL01 | CPX09 - LV Power Cable | E | PS5-01-11 - Inergen for Power Gen Building | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00023-4712 | PS5-01-LB-0004-CL02 | CPX09 - LV Power Cable | E | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00023-4713 | PS5-01-LB-0004-CL03 | CPX09 - LV Power Cable | E | PS5-01-11 - Inergen for Power Gen Building | To be completed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  |  | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side [OPEN]
T-00023-4714 | PS5-01-MOV-8701-CL01 | CPX09 - LV Power Cable | E | PS5-01-05 - Foam Skid | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-4724 | PS5-03-SEA-0002-CL01 | CPX09 - LV Power Cable | E | PS5-03-22 - FZ-G1 - Guard House | To be completed
T-00023-4725 | PS5-03-SEA-0003-CL01 | CPX09 - LV Power Cable | E | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00023-4727 | PS5-05-BE-0001-CL01 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00023-4728 | PS5-05-BE-0001-CL02 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00023-4729 | PS5-05-BE-0001-CL03 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00023-4730 | PS5-05-BE-0001-CL04 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00023-4731 | PS5-05-BE-0001-CL05 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00023-4732 | PS5-05-BE-0001-CL06 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00023-4733 | PS5-05-BE-0001-CL07 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00023-4734 | PS5-05-BE-0001-CL08 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00023-4735 | PS5-05-BE-0001-CL09 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00023-4736 | PS5-05-BE-0001-CL10 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00023-4737 | PS5-05-BE-0001-CL11 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00023-4738 | PS5-05-IE-8100-CL01 | CPX09 - LV Power Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-4739 | PS5-05-IE-8100-CL02 | CPX09 - LV Power Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-4742 | PS5-05-IG-0009-CL01 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151167, 151116, 151112, 151111-SS Tag on both ends not installed [OPEN] ¦ TZ-MID-68-WPR2-151167, 151116, 151112, 151111-Cable dressing not yet done completely [OPEN]
T-00023-4743 | PS5-05-IG-0009-CL02 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151167, 151116, 151112, 151111-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151167, 151116, 151112, 151111-Cable dressing not yet done completely [OPEN]
T-00023-4744 | PS5-05-IG-0025-CL01 | CPX09 - LV Power Cable | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | To be completed | CPP-RFI-68-33/1-05-0309 | CPP-RFI-68-331-07-0310 |  | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable Reaching final Destination, But need to Install Cable Tray [OPEN] | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable Tagging Installaton not Yet Done at Both Side [OPEN] ¦ TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable Dressing not yet done [OPEN]
T-00023-4745 | PS5-05-IG-0026-CL01 | CPX09 - LV Power Cable | E | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | To be completed | CPP-RFI-68-33/1-05-0309 | CPP-RFI-68-331-07-0310 |  | TZ-MID-68-WPR2-151166, Cable Not Reaching Final Destination [OPEN] | TZ-MID-68-WPR2-151166, Cable Tagging Installation not Yet Done at Both Side [OPEN] ¦ TZ-MID-68-WPR2-151166, Cable Dressing not yet done [OPEN]
T-00023-4746 | PS5-06-GB-0003-CL01 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00023-4747 | PS5-06-GB-0003-CL02 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00023-4748 | PS5-06-GB-0003-CL03 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00023-4749 | PS5-06-GB-0003-CL04 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00023-4750 | PS5-06-GB-0003-CL05 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00023-4751 | PS5-06-GB-0003-CL06 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00023-4752 | PS5-06-GU-0003A-CL01 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00023-4753 | PS5-06-GU-0003B-CL01 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00023-4754 | PS5-06-GU-0003C-CL01 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00023-4756 | PS5-06-IG-0004A-CL01 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00023-4757 | PS5-06-IG-0004A-CL02 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00023-4758 | PS5-06-IG-0004A-CL03 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00023-4759 | PS5-06-IG-0004A-CL04 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00023-4761 | PS5-06-IG-0004B-CL01 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00023-4762 | PS5-06-IG-0004B-CL02 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00023-4763 | PS5-06-IG-0004B-CL03 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00023-4764 | PS5-06-IG-0004B-CL04 | CPX09 - LV Power Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00023-4808 | PS5-08-11CB-1501-CL01 | CPX09 - LV Power Cable | E | PS5-08-11 - Corporate LAN (SIE) | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-4809 | PS5-08-11CB-1901-CL01 | CPX09 - LV Power Cable | E | PS5-08-11 - Corporate LAN (SIE) | To be completed
T-00023-4810 | PS5-08-11CB-1901-CL02 | CPX09 - LV Power Cable | E | PS5-08-11 - Corporate LAN (SIE) | To be completed
T-00023-4811 | PS5-08-11CB-1901-CL03 | CPX09 - LV Power Cable | E | PS5-08-11 - Corporate LAN (SIE) | To be completed
T-00023-4878 | PS5-09-LB-0008-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-4879 | PS5-09-LB-0008-CL02 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-4882 | PS5-25-DM-3100A-CL01 | CPX09 - LV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0286 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00023-4883 | PS5-25-DM-3100A-CL02 | CPX09 - LV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0286 |  |  | TZ-MID-68-WPR2-151111, 151115, 151117, 151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151115, 151117, 151114-Cable dressing not yet done completely [OPEN]
T-00023-4886 | PS5-25-DM-3100B-CL01 | CPX09 - LV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0286 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00023-4887 | PS5-25-DM-3100B-CL02 | CPX09 - LV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0286 |  |  | TZ-MID-68-WPR2-151111, 151115, 151117, 151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151115, 151117, 151114-Cable dressing not yet done completely [OPEN]
T-00023-4890 | PS5-25-DM-3100C-CL01 | CPX09 - LV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0286 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00023-4891 | PS5-25-DM-3100C-CL02 | CPX09 - LV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0286 |  |  | TZ-MID-68-WPR2-151111, 151115, 151117, 151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151115, 151117, 151114-Cable dressing not yet done completely [OPEN]
T-00023-4904 | PS5-25-ESDV-0021-CL01 | CPX09 - LV Power Cable | E | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0042) [OPEN] | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN]
T-00023-4905 | PS5-25-ESDV-0023-CL01 | CPX09 - LV Power Cable | E | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0042) [OPEN] | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN]
T-00023-4906 | PS5-25-FCV-0003A-CL01 | CPX09 - LV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0042) [OPEN] | TZ-MID-68-WPR2-151117,151114 Permanent Cable tag not yet installed. [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN]
T-00023-4907 | PS5-25-FCV-0003B-CL01 | CPX09 - LV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0042) [OPEN] | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN]
T-00023-4908 | PS5-25-FCV-0003C-CL01 | CPX09 - LV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0043) [OPEN] | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN]
T-00023-4909 | PS5-25-FCV-0004-CL01 | CPX09 - LV Power Cable | E | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-4918 | PS5-25-MOV-0001-CL01 | CPX09 - LV Power Cable | E | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely [OPEN]
T-00023-4919 | PS5-25-MOV-0002-CL01 | CPX09 - LV Power Cable | E | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely [OPEN]
T-00023-4920 | PS5-25-MOV-0003-CL01 | CPX09 - LV Power Cable | E | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely [OPEN]
T-00023-4921 | PS5-25-MOV-0008-CL01 | CPX09 - LV Power Cable | E | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151114,151113 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. [OPEN] | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS cable tags to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable need to be dressing completely at both side [OPEN]
T-00023-4922 | PS5-25-MOV-0011-CL01 | CPX09 - LV Power Cable | E | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely [OPEN]
T-00023-4923 | PS5-25-MOV-0012-CL01 | CPX09 - LV Power Cable | E | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely [OPEN]
T-00023-4924 | PS5-25-MOV-0025-CL01 | CPX09 - LV Power Cable | E | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151114,151113 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0042. [OPEN] | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS cable tags to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable need to be dressing completely at both side [OPEN]
T-00023-4925 | PS5-25-MOV-0026-CL01 | CPX09 - LV Power Cable | E | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151114,151113 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0042. [OPEN] | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS cable tags to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable need to be dressing completely at both side [OPEN]
T-00023-4926 | PS5-25-MOV-0027-CL01 | CPX09 - LV Power Cable | E | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely [OPEN]
T-00023-4927 | PS5-25-MOV-0028-CL01 | CPX09 - LV Power Cable | E | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely [OPEN]
T-00023-4928 | PS5-25-SDV-0022-CL01 | CPX09 - LV Power Cable | E | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely [OPEN]
T-00023-4929 | PS5-25-SDV-0035A-CL01 | CPX09 - LV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely [OPEN]
T-00023-4930 | PS5-25-SDV-0035B-CL01 | CPX09 - LV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely [OPEN]
T-00023-4931 | PS5-25-SDV-0035C-CL01 | CPX09 - LV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely [OPEN]
T-00023-4932 | PS5-25-SDV-0036A-CL01 | CPX09 - LV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely [OPEN]
T-00023-4933 | PS5-25-SDV-0036B-CL01 | CPX09 - LV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely [OPEN]
T-00023-4934 | PS5-25-SDV-0036C-CL01 | CPX09 - LV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely [OPEN]
T-00023-4935 | PS5-25-SDV-0046-CL01 | CPX09 - LV Power Cable | E | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151114,151113 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. [OPEN] | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS cable tags to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable need to be dressing completely at both side [OPEN]
T-00023-4936 | PS5-25-SDV-0052-CL01 | CPX09 - LV Power Cable | E | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely [OPEN]
T-00023-4937 | PS5-25-SDV-0054A-CL01 | CPX09 - LV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0043) [OPEN] | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 Permanent Cable tag not yet installed. [CLOSED]
T-00023-4938 | PS5-25-SDV-0054B-CL01 | CPX09 - LV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0043) [OPEN] | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN]
T-00023-4939 | PS5-25-SDV-0054C-CL01 | CPX09 - LV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0043) [OPEN] | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN]
T-00023-4941 | PS5-25-XV-0053-CL01 | CPX09 - LV Power Cable | E | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed | CPP-RFI-68-331-05-0210 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151114,151113 Field run cable ladder to be installed [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 To be complete cable trench backfilled, protection tiles, and warning tape installation (PS5-88-BU-LV-00164) [OPEN] | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS cable tag to be installed at both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable dressing to be done at both side [OPEN]
T-00023-4942 | PS5-25-XV-0070-CL01 | CPX09 - LV Power Cable | E | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-4944 | PS5-28-BE-0002A-CL02 | CPX09 - LV Power Cable | E | PS5-28-17 - Reinjection Pump | To be completed | CPP-RFI-68-331-05-0238 | CPP-RFI-68-331-07-0253 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Vertical Cable Tray to be install at panel side PS5-61-IG-0007 [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Direct Buried Cable trench installation at panel side PS5-61-IG-0007 not complete yet [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Dressing to be done at both side [OPEN]
T-00023-4946 | PS5-28-BE-0002B-CL02 | CPX09 - LV Power Cable | E | PS5-28-17 - Reinjection Pump | To be completed | CPP-RFI-68-331-05-0238 | CPP-RFI-68-331-07-0253 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Vertical Cable Tray to be install at panel side PS5-61-IG-0007 [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Direct Buried Cable trench installation at panel side PS5-61-IG-0007 not complete yet [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Dressing to be done at both side [OPEN]
T-00023-4962 | PS5-28-HE-2100-CL02 | CPX09 - LV Power Cable | E | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed | CPP-RFI-68-331-05-0238 | CPP-RFI-68-331-07-0253 |  | TZ-MID-68-WPR2-151111,151115,151117,151114 Vertical Cable Tray & Direct Buried Cable trench installation at panel side PS5-61-IG-0007 not complete yet. [OPEN] | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Dressing to be done at both side [OPEN]
T-00023-4964 | PS5-28-HE-2200-CL02 | CPX09 - LV Power Cable | E | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151111,151115,151118-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151118-SS Tag on both ends not installed [CLOSED]
T-00023-4966 | PS5-28-LB-8200-CL01 | CPX09 - LV Power Cable | E | PS5-28-11 - Open Drain Interceptor | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151111-SS Tag on both ends not installed [OPEN]
T-00023-4967 | PS5-28-SDV-0045-CL01 | CPX09 - LV Power Cable | E | PS5-28-17 - Reinjection Pump | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-4968 | PS5-28-SDV-0053A-CL01 | CPX09 - LV Power Cable | E | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0043) [OPEN] | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN]
T-00023-4969 | PS5-28-SDV-0053B-CL01 | CPX09 - LV Power Cable | E | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed | CPP-RFI-68-331-05-0239 | CPP-RFI-68-331-07-0254 |  | TZ-MID-68-WPR2-151117,151114 Vertical cable ladder to be done installation at panel side (PS5-61-IG-0043) [OPEN] | TZ-MID-68-WPR2-151117,151114 Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114 Dressing to be done at both side [OPEN]
T-00023-4970 | PS5-28-SDV-0053C-CL01 | CPX09 - LV Power Cable | E | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed | CPP-RFI-68-331-05-0238 | CPP-RFI-68-331-07-0253 |  | TZ-MID-68-WPR2-151117,151114 Vertical field tray to be install at panel side PS5-61-IG-0043 [OPEN] | TZ-MID-68-WPR2-151117,151114 Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114 Dressing to be done at both side [OPEN]
T-00023-4978 | PS5-60-BE-0001-CL01 | CPX09 - LV Power Cable | E | PS5-60-27 - Compressed Air Starting Skid | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151116 To be install Field Run Cable Tray/Ladder [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done at both side [OPEN]
T-00023-4979 | PS5-60-BE-0001-CL02 | CPX09 - LV Power Cable | E | PS5-60-27 - Compressed Air Starting Skid | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151116 To be install Field Run Cable Tray/Ladder [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done at both side [OPEN]
T-00023-4981 | PS5-60-BE-0001-CL04 | CPX09 - LV Power Cable | E | PS5-60-27 - Compressed Air Starting Skid | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 To be install Field Run Cable Tray/Ladder [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN]
T-00023-4982 | PS5-60-BE-0002-CL01 | CPX09 - LV Power Cable | E | PS5-60-26 - Instrument Air Compressor Skid | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151116 To be install Field Run Cable Tray/Ladder [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done at both side [OPEN]
T-00023-4983 | PS5-60-BE-0002-CL02 | CPX09 - LV Power Cable | E | PS5-60-26 - Instrument Air Compressor Skid | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151116 To be install Field Run Cable Tray/Ladder [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done at both side [OPEN]
T-00023-4984 | PS5-60-BE-0002-CL03 | CPX09 - LV Power Cable | E | PS5-60-26 - Instrument Air Compressor Skid | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151116 To be install Field Run Cable Tray/Ladder [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done at both side [OPEN]
T-00023-4986 | PS5-60-BE-0002-CL05 | CPX09 - LV Power Cable | E | PS5-60-26 - Instrument Air Compressor Skid | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 To be install Field Run Cable Tray/Ladder [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN]
T-00023-4987 | PS5-60-BE-0003A-CL01 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-4988 | PS5-60-BE-0003B-CL01 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-4989 | PS5-60-BE-0003C-CL01 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-4990 | PS5-60-BE-0003D-CL01 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed
T-00023-4991 | PS5-60-BE-0003E-CL01 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-4992 | PS5-60-BE-0003F-CL01 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-4993 | PS5-60-BE-0003G-CL01 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0427
T-00023-4994 | PS5-60-BE-0004A-CL01 | CPX09 - LV Power Cable | E | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | To be completed
T-00023-4995 | PS5-60-BE-0004B-CL01 | CPX09 - LV Power Cable | E | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | To be completed
T-00023-4996 | PS5-60-BE-0004C-CL01 | CPX09 - LV Power Cable | E | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-4997 | PS5-60-BE-0004D-CL01 | CPX09 - LV Power Cable | E | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | To be completed
T-00023-4998 | PS5-60-BE-0004E-CL01 | CPX09 - LV Power Cable | E | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | To be completed
T-00023-4999 | PS5-60-BE-0004F-CL01 | CPX09 - LV Power Cable | E | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-5000 | PS5-60-BE-0004G-CL01 | CPX09 - LV Power Cable | E | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | To be completed |  | CPP-RFI-68-33/1-07-0427
T-00023-5001 | PS5-60-BE-0005A-CL01 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable not Reaching Final Destination (Incorrect Destination) [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5002 | PS5-60-BE-0005B-CL01 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Destination, but need to install cable ladder [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5003 | PS5-60-BE-0005C-CL01 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-5004 | PS5-60-BE-0005D-CL01 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5005 | PS5-60-BE-0005E-CL01 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-5006 | PS5-60-BE-0005F-CL01 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  | TZ-MID-68-WPR2-151167,151116,151179 Field run cable tray not finished [OPEN] | TZ-MID-68-WPR2-151167,151116,151179 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151116,151179 Cable Dressing not yet done [OPEN]
T-00023-5007 | PS5-60-BE-0005G-CL01 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-331-07-0423
T-00023-5008 | PS5-60-BE-0011A-CL01 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151116, 151118 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151116, 151118 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116, 151118 Cable to be dressing completely at both side [OPEN]
T-00023-5009 | PS5-60-BE-0011A-CL02 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151116, 151118 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151116, 151118 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116, 151118 Cable to be dressing completely at both side [OPEN]
T-00023-5010 | PS5-60-BE-0011A-CL03 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5011 | PS5-60-BE-0011A-CL04 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151116, 151118 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151116, 151118 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116, 151118 Cable to be dressing completely at both side [OPEN]
T-00023-5012 | PS5-60-BE-0011A-CL05 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5013 | PS5-60-BE-0011A-CL06 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5014 | PS5-60-BE-0011B-CL01 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5015 | PS5-60-BE-0011B-CL02 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5016 | PS5-60-BE-0011B-CL03 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5017 | PS5-60-BE-0011B-CL04 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5018 | PS5-60-BE-0011B-CL05 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5019 | PS5-60-BE-0011B-CL06 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5020 | PS5-60-BE-0012A-CL01 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5021 | PS5-60-BE-0012A-CL02 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5022 | PS5-60-BE-0012A-CL03 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5023 | PS5-60-BE-0012A-CL04 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5024 | PS5-60-BE-0012A-CL05 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5025 | PS5-60-BE-0012A-CL06 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5026 | PS5-60-BE-0012B-CL01 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5027 | PS5-60-BE-0012B-CL02 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5028 | PS5-60-BE-0012B-CL03 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5029 | PS5-60-BE-0012B-CL04 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5030 | PS5-60-BE-0012B-CL05 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5031 | PS5-60-BE-0012B-CL06 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, 151118, Cable Not Reaching to Final Destination (PS5-60-BE-0012B) Cooler Fan JB need to install Cable Ladder [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151118 -Cable Dressing not Yet Done [OPEN]
T-00023-5032 | PS5-60-BE-0013A-CL01 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed
T-00023-5033 | PS5-60-BE-0013A-CL02 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-33/1-07-0411
T-00023-5034 | PS5-60-BE-0013A-CL03 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-33/1-07-0411
T-00023-5035 | PS5-60-BE-0013A-CL04 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-33/1-07-0411
T-00023-5036 | PS5-60-BE-0013A-CL05 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-33/1-07-0411
T-00023-5037 | PS5-60-BE-0013A-CL06 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-33/1-07-0411
T-00023-5038 | PS5-60-BE-0013B-CL01 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-33/1-07-0411
T-00023-5039 | PS5-60-BE-0013B-CL02 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-33/1-07-0411
T-00023-5040 | PS5-60-BE-0013B-CL03 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-33/1-07-0411
T-00023-5041 | PS5-60-BE-0013B-CL04 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-33/1-07-0411
T-00023-5042 | PS5-60-BE-0013B-CL05 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-33/1-07-0411
T-00023-5043 | PS5-60-BE-0013B-CL06 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-33/1-07-0411
T-00023-5044 | PS5-60-BE-0014A-CL01 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0421
T-00023-5045 | PS5-60-BE-0014A-CL02 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5046 | PS5-60-BE-0014A-CL03 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5047 | PS5-60-BE-0014A-CL04 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5048 | PS5-60-BE-0014A-CL05 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5049 | PS5-60-BE-0014A-CL06 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5050 | PS5-60-BE-0014B-CL01 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5051 | PS5-60-BE-0014B-CL02 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5052 | PS5-60-BE-0014B-CL03 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5053 | PS5-60-BE-0014B-CL04 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5054 | PS5-60-BE-0014B-CL05 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5055 | PS5-60-BE-0014B-CL06 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5056 | PS5-60-BE-0015A-CL01 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5057 | PS5-60-BE-0015A-CL02 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5058 | PS5-60-BE-0015A-CL03 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5059 | PS5-60-BE-0015A-CL04 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5060 | PS5-60-BE-0015A-CL05 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5061 | PS5-60-BE-0015A-CL06 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5062 | PS5-60-BE-0015B-CL01 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5063 | PS5-60-BE-0015B-CL02 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-33/1-07-0421
T-00023-5064 | PS5-60-BE-0015B-CL03 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5065 | PS5-60-BE-0015B-CL04 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5066 | PS5-60-BE-0015B-CL05 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5067 | PS5-60-BE-0015B-CL06 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5068 | PS5-60-BE-0016A-CL01 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0411
T-00023-5069 | PS5-60-BE-0016A-CL02 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0411
T-00023-5070 | PS5-60-BE-0016A-CL03 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5071 | PS5-60-BE-0016A-CL04 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5072 | PS5-60-BE-0016A-CL05 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5073 | PS5-60-BE-0016A-CL06 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5074 | PS5-60-BE-0016B-CL01 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5075 | PS5-60-BE-0016B-CL02 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5076 | PS5-60-BE-0016B-CL03 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5077 | PS5-60-BE-0016B-CL04 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5078 | PS5-60-BE-0016B-CL05 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5079 | PS5-60-BE-0016B-CL06 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5080 | PS5-60-BE-0017A-CL01 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5081 | PS5-60-BE-0017A-CL02 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-5082 | PS5-60-BE-0017A-CL03 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5083 | PS5-60-BE-0017A-CL04 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed
T-00023-5084 | PS5-60-BE-0017A-CL05 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0416
T-00023-5085 | PS5-60-BE-0017A-CL06 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-5086 | PS5-60-BE-0017B-CL01 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5087 | PS5-60-BE-0017B-CL02 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5088 | PS5-60-BE-0017B-CL03 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5089 | PS5-60-BE-0017B-CL04 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-5090 | PS5-60-BE-0017B-CL05 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0421
T-00023-5091 | PS5-60-BE-0017B-CL06 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0421
T-00023-5092 | PS5-60-BE-0021A-CL01 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-RFI-68-33/1-05-0309 | CPP-RFI-68-331-07-0310 |  | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118, Cable Reaching Final Destination, but need to install cable tray [OPEN] | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118, Cable Tagging not yet done at both side [OPEN] ¦ TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118, Cable Dressing not yet done [OPEN]
T-00023-5093 | PS5-60-BE-0021B-CL01 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151116 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151116 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5094 | PS5-60-BE-0024A-CL01 | CPX09 - LV Power Cable | E | PS5-60-35 - Injector Tip Cooling Module A | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Final Destination, but need to install cable LADDER [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5095 | PS5-60-BE-0024A-CL02 | CPX09 - LV Power Cable | E | PS5-60-35 - Injector Tip Cooling Module A | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Destination, but need to install cable ladder [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5096 | PS5-60-BE-0024B-CL01 | CPX09 - LV Power Cable | E | PS5-60-36 - Injector Tip Cooling Module B | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Final Destination, but need to install cable LADDER [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5097 | PS5-60-BE-0024B-CL02 | CPX09 - LV Power Cable | E | PS5-60-36 - Injector Tip Cooling Module B | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Destination, But need to install Vertikal Cable Ladder [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5098 | PS5-60-BE-0024C-CL01 | CPX09 - LV Power Cable | E | PS5-60-37 - Injector Tip Cooling Module C | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray not finished [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done [OPEN]
T-00023-5099 | PS5-60-BE-0024C-CL02 | CPX09 - LV Power Cable | E | PS5-60-37 - Injector Tip Cooling Module C | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray not finished [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done [OPEN]
T-00023-5100 | PS5-60-BE-0024D-CL01 | CPX09 - LV Power Cable | E | PS5-60-38 - Injector Tip Cooling Module D | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable not Reaching Final Destination [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5101 | PS5-60-BE-0024D-CL02 | CPX09 - LV Power Cable | E | PS5-60-38 - Injector Tip Cooling Module D | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Destination, But need to install cable ladder [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5102 | PS5-60-BE-0024E-CL01 | CPX09 - LV Power Cable | E | PS5-60-39 - Injector Tip Cooling Module E | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-5103 | PS5-60-BE-0024E-CL02 | CPX09 - LV Power Cable | E | PS5-60-39 - Injector Tip Cooling Module E | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray not finished [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done [OPEN]
T-00023-5104 | PS5-60-BE-0024F-CL01 | CPX09 - LV Power Cable | E | PS5-60-40 - Injector Tip Cooling Module F | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-5105 | PS5-60-BE-0024F-CL02 | CPX09 - LV Power Cable | E | PS5-60-40 - Injector Tip Cooling Module F | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  | TZ-MID-68-WPR2-151116 Field run cable tray not finished [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable Dressing not yet done [OPEN]
T-00023-5106 | PS5-60-BE-0024G-CL01 | CPX09 - LV Power Cable | E | PS5-60-41 - Injector Tip Cooling Module G | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable Dressing not yet done [OPEN]
T-00023-5107 | PS5-60-BE-0024G-CL02 | CPX09 - LV Power Cable | E | PS5-60-41 - Injector Tip Cooling Module G | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00023-5108 | PS5-60-BE-0025A-CL01 | CPX09 - LV Power Cable | E | PS5-60-35 - Injector Tip Cooling Module A | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cable not Reaching final destination, coiled around 9 MTR to final Destination (Generator Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5109 | PS5-60-BE-0025B-CL01 | CPX09 - LV Power Cable | E | PS5-60-36 - Injector Tip Cooling Module B | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cable not Reaching final destination, coiled around 9 MTR to final Destination (Generator Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5110 | PS5-60-BE-0025C-CL01 | CPX09 - LV Power Cable | E | PS5-60-37 - Injector Tip Cooling Module C | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done [OPEN]
T-00023-5111 | PS5-60-BE-0025D-CL01 | CPX09 - LV Power Cable | E | PS5-60-38 - Injector Tip Cooling Module D | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151118,151116 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5112 | PS5-60-BE-0025E-CL01 | CPX09 - LV Power Cable | E | PS5-60-39 - Injector Tip Cooling Module E | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-5113 | PS5-60-BE-0025F-CL01 | CPX09 - LV Power Cable | E | PS5-60-40 - Injector Tip Cooling Module F | To be completed |  | CPP-RFI-68-331-07-0423
T-00023-5114 | PS5-60-BE-0025G-CL01 | CPX09 - LV Power Cable | E | PS5-60-41 - Injector Tip Cooling Module G | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable Dressing not yet done [OPEN]
T-00023-5115 | PS5-60-BE-0026A-CL01 | CPX09 - LV Power Cable | E | PS5-60-70 - Engine A Cooling system | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5116 | PS5-60-BE-0026A-CL02 | CPX09 - LV Power Cable | E | PS5-60-70 - Engine A Cooling system | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5117 | PS5-60-BE-0026B-CL01 | CPX09 - LV Power Cable | E | PS5-60-71 - Engine B Cooling system | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5118 | PS5-60-BE-0026B-CL02 | CPX09 - LV Power Cable | E | PS5-60-71 - Engine B Cooling system | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5119 | PS5-60-BE-0026C-CL01 | CPX09 - LV Power Cable | E | PS5-60-72 - Engine C Cooling system | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done [OPEN]
T-00023-5120 | PS5-60-BE-0026C-CL02 | CPX09 - LV Power Cable | E | PS5-60-72 - Engine C Cooling system | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5121 | PS5-60-BE-0026D-CL01 | CPX09 - LV Power Cable | E | PS5-60-73 - Engine D Cooling system | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done, Cable Not Reaching Final Destination [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5122 | PS5-60-BE-0026D-CL02 | CPX09 - LV Power Cable | E | PS5-60-73 - Engine D Cooling system | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Final Destination, but need to install cable LADDER [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5123 | PS5-60-BE-0026E-CL01 | CPX09 - LV Power Cable | E | PS5-60-74 - Engine E Cooling system | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-5124 | PS5-60-BE-0026E-CL02 | CPX09 - LV Power Cable | E | PS5-60-74 - Engine E Cooling system | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Final Destination, but need to install cable LADDER [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5125 | PS5-60-BE-0026F-CL01 | CPX09 - LV Power Cable | E | PS5-60-75 - Engine F Cooling system | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-5126 | PS5-60-BE-0026F-CL02 | CPX09 - LV Power Cable | E | PS5-60-75 - Engine F Cooling system | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Final Destination, but need to install cable LADDER [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00023-5127 | PS5-60-BE-0026G-CL01 | CPX09 - LV Power Cable | E | PS5-60-76 - Engine G Cooling system | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable Dressing not yet done [OPEN]
T-00023-5128 | PS5-60-BE-0026G-CL02 | CPX09 - LV Power Cable | E | PS5-60-76 - Engine G Cooling system | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5129 | PS5-60-BI-0005A-CL01 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable to be dressing completely at both side [OPEN]
T-00023-5130 | PS5-60-BI-0005B-CL01 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable to be dressing completely at both side [OPEN]
T-00023-5131 | PS5-60-BI-0005C-CL01 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable to be dressing completely at both side [OPEN]
T-00023-5132 | PS5-60-BI-0005D-CL01 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable to be dressing completely at both side [OPEN]
T-00023-5133 | PS5-60-BI-0005E-CL01 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable to be dressing completely at both side [OPEN]
T-00023-5134 | PS5-60-BI-0005F-CL01 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151116 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side [OPEN]
T-00023-5135 | PS5-60-BI-0005G-CL01 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151116 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side [OPEN]
T-00023-5136 | PS5-60-BI-0015A-CL01 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed
T-00023-5137 | PS5-60-BI-0015A-CL02 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cable Reaching final destination, coiled around 5 MTR to Final Destination [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5138 | PS5-60-BI-0015A-CL03 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5139 | PS5-60-BI-0015B-CL01 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed
T-00023-5140 | PS5-60-BI-0015B-CL02 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5141 | PS5-60-BI-0015B-CL03 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5142 | PS5-60-BI-0015C-CL01 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-5143 | PS5-60-BI-0015C-CL02 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-5144 | PS5-60-BI-0015C-CL03 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-5145 | PS5-60-BI-0015D-CL01 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed
T-00023-5146 | PS5-60-BI-0015D-CL02 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5147 | PS5-60-BI-0015D-CL03 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5148 | PS5-60-BI-0015E-CL01 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5149 | PS5-60-BI-0015E-CL02 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-5150 | PS5-60-BI-0015E-CL03 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-5151 | PS5-60-BI-0015F-CL01 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5152 | PS5-60-BI-0015F-CL02 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5153 | PS5-60-BI-0015F-CL03 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-5154 | PS5-60-BI-0015G-CL01 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed
T-00023-5155 | PS5-60-BI-0015G-CL02 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0410
T-00023-5156 | PS5-60-BI-0015G-CL03 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0410
T-00023-5157 | PS5-60-DD-62800A-CL01 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed
T-00023-5159 | PS5-60-DD-62800C-CL01 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed
T-00023-5161 | PS5-60-DD-62800E-CL01 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed
T-00023-5163 | PS5-60-DD-62800G-CL01 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed
T-00023-5166 | PS5-60-IE-0002A-CL01 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5167 | PS5-60-IE-0002A-CL02 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5168 | PS5-60-IE-0002A-CL03 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5169 | PS5-60-IE-0002B-CL01 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-33/1-05-0309 | CPP-RFI-68-331-07-0310 |  | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable not Reaching Final Destination [OPEN] | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable Tagging Installaton not Yet Done at Both Side [OPEN] ¦ TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable Dressing not yet done [OPEN]
T-00023-5170 | PS5-60-IE-0002B-CL02 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-331-05-0275 | CPP-RFI-68-331-07-0310 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable coiled 110Mtr at Electrical building side, to be laid in the ladder (PS5-88-LD-LV-9025, PS5-88-LD-LV-9087, PS5-88-LD-LV-3091, PS5-88-LD-LV-3090). [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag To be Install [OPEN]
T-00023-5171 | PS5-60-IE-0002B-CL03 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5172 | PS5-60-IE-0002C-CL01 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-331-07-0423
T-00023-5173 | PS5-60-IE-0002C-CL02 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151116,151179 Cable Dressing not yet done [OPEN]
T-00023-5174 | PS5-60-IE-0002C-CL03 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed |  | CPP-RFI-68-33/1-07-0421
T-00023-5175 | PS5-60-IE-0002D-CL01 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5176 | PS5-60-IE-0002D-CL02 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5177 | PS5-60-IE-0002D-CL03 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed
T-00023-5178 | PS5-60-IE-0002E-CL01 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151116,151179 Cable Dressing not yet done [OPEN]
T-00023-5179 | PS5-60-IE-0002E-CL02 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151116,151179 Cable Dressing not yet done [OPEN]
T-00023-5180 | PS5-60-IE-0002E-CL03 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed
T-00023-5181 | PS5-60-IE-0002F-CL01 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-5182 | PS5-60-IE-0002F-CL02 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0421
T-00023-5183 | PS5-60-IE-0002F-CL03 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed
T-00023-5184 | PS5-60-IE-0002G-CL01 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-5185 | PS5-60-IE-0002G-CL02 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0419
T-00023-5186 | PS5-60-IE-0002G-CL03 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed
T-00023-5187 | PS5-60-IE-0003A-CL01 | CPX09 - LV Power Cable | E | PS5-60-02 - Power Gen Package A (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not reaching final destinantion (Coiled not in Below of final Panel Location) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5188 | PS5-60-IE-0003A-CL02 | CPX09 - LV Power Cable | E | PS5-60-02 - Power Gen Package A (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not reaching final destinantion (Coiled not in Below of final Panel Location) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5189 | PS5-60-IE-0003B-CL01 | CPX09 - LV Power Cable | E | PS5-60-05 - Power Gen Package B (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not reaching final destinantion (Coiled not in Below of final Panel Location) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5190 | PS5-60-IE-0003B-CL02 | CPX09 - LV Power Cable | E | PS5-60-05 - Power Gen Package B (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not reaching final destinantion (Coiled not in Below of final Panel Location) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5191 | PS5-60-IE-0003C-CL01 | CPX09 - LV Power Cable | E | PS5-60-08 - Power Gen Package C (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0419
T-00023-5192 | PS5-60-IE-0003C-CL02 | CPX09 - LV Power Cable | E | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00023-5193 | PS5-60-IE-0003D-CL01 | CPX09 - LV Power Cable | E | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00023-5194 | PS5-60-IE-0003D-CL02 | CPX09 - LV Power Cable | E | PS5-60-11 - Power Gen Package D (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5195 | PS5-60-IE-0003E-CL01 | CPX09 - LV Power Cable | E | PS5-60-14 - Power Gen Package E (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0419
T-00023-5196 | PS5-60-IE-0003E-CL02 | CPX09 - LV Power Cable | E | PS5-60-14 - Power Gen Package E (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0419
T-00023-5197 | PS5-60-IE-0003F-CL01 | CPX09 - LV Power Cable | E | PS5-60-17 - Power Gen Package F (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0419
T-00023-5198 | PS5-60-IE-0003F-CL02 | CPX09 - LV Power Cable | E | PS5-60-17 - Power Gen Package F (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0419
T-00023-5199 | PS5-60-IE-0003G-CL01 | CPX09 - LV Power Cable | E | PS5-60-20 - Power Gen Package G (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0419
T-00023-5200 | PS5-60-IE-0003G-CL02 | CPX09 - LV Power Cable | E | PS5-60-20 - Power Gen Package G (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-5201 | PS5-60-IE-0004-CL01 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5202 | PS5-60-IE-0004-CL02 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5204 | PS5-60-IH-0001A-CL01 | CPX09 - LV Power Cable | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5205 | PS5-60-IH-0001A-CL02 | CPX09 - LV Power Cable | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5206 | PS5-60-IH-0001A-CL03 | CPX09 - LV Power Cable | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5207 | PS5-60-IH-0001A-CL04 | CPX09 - LV Power Cable | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5208 | PS5-60-IH-0001A-CL05 | CPX09 - LV Power Cable | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5209 | PS5-60-IH-0001A-CL06 | CPX09 - LV Power Cable | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching, Coiled around 2 MTR to final Panel (PS5-60-IH-0001A) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5211 | PS5-60-IH-0001B-CL01 | CPX09 - LV Power Cable | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5212 | PS5-60-IH-0001B-CL02 | CPX09 - LV Power Cable | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5213 | PS5-60-IH-0001B-CL03 | CPX09 - LV Power Cable | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5214 | PS5-60-IH-0001B-CL04 | CPX09 - LV Power Cable | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5215 | PS5-60-IH-0001B-CL05 | CPX09 - LV Power Cable | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5216 | PS5-60-IH-0001B-CL06 | CPX09 - LV Power Cable | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5218 | PS5-60-IH-0001C-CL01 | CPX09 - LV Power Cable | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable Dressing not yet done [OPEN]
T-00023-5219 | PS5-60-IH-0001C-CL02 | CPX09 - LV Power Cable | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable Dressing not yet done [OPEN]
T-00023-5220 | PS5-60-IH-0001C-CL03 | CPX09 - LV Power Cable | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable Dressing not yet done [OPEN]
T-00023-5221 | PS5-60-IH-0001C-CL04 | CPX09 - LV Power Cable | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable Dressing not yet done [OPEN]
T-00023-5222 | PS5-60-IH-0001C-CL05 | CPX09 - LV Power Cable | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-33/1-07-0427
T-00023-5223 | PS5-60-IH-0001C-CL06 | CPX09 - LV Power Cable | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-5225 | PS5-60-IH-0001D-CL01 | CPX09 - LV Power Cable | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-33/1-07-0411
T-00023-5226 | PS5-60-IH-0001D-CL02 | CPX09 - LV Power Cable | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-33/1-07-0411
T-00023-5227 | PS5-60-IH-0001D-CL03 | CPX09 - LV Power Cable | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-33/1-07-0411
T-00023-5228 | PS5-60-IH-0001D-CL04 | CPX09 - LV Power Cable | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-33/1-07-0411
T-00023-5229 | PS5-60-IH-0001D-CL05 | CPX09 - LV Power Cable | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5230 | PS5-60-IH-0001D-CL06 | CPX09 - LV Power Cable | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-5232 | PS5-60-IH-0001E-CL01 | CPX09 - LV Power Cable | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-5233 | PS5-60-IH-0001E-CL02 | CPX09 - LV Power Cable | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-5234 | PS5-60-IH-0001E-CL03 | CPX09 - LV Power Cable | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-5235 | PS5-60-IH-0001E-CL04 | CPX09 - LV Power Cable | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed
T-00023-5236 | PS5-60-IH-0001E-CL05 | CPX09 - LV Power Cable | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-5237 | PS5-60-IH-0001E-CL06 | CPX09 - LV Power Cable | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-5239 | PS5-60-IH-0001F-CL01 | CPX09 - LV Power Cable | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00023-5240 | PS5-60-IH-0001F-CL02 | CPX09 - LV Power Cable | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00023-5241 | PS5-60-IH-0001F-CL03 | CPX09 - LV Power Cable | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00023-5242 | PS5-60-IH-0001F-CL04 | CPX09 - LV Power Cable | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00023-5243 | PS5-60-IH-0001F-CL05 | CPX09 - LV Power Cable | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00023-5244 | PS5-60-IH-0001F-CL06 | CPX09 - LV Power Cable | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-5246 | PS5-60-IH-0001G-CL01 | CPX09 - LV Power Cable | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed
T-00023-5247 | PS5-60-IH-0001G-CL02 | CPX09 - LV Power Cable | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed
T-00023-5248 | PS5-60-IH-0001G-CL03 | CPX09 - LV Power Cable | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed
T-00023-5249 | PS5-60-IH-0001G-CL04 | CPX09 - LV Power Cable | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | Started (not Completed) | CPP-RFI-68-331-05-0407 | CPP-RFI-68-33/1-07-0410 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable Dressing not yet done [OPEN]
T-00023-5250 | PS5-60-IH-0001G-CL05 | CPX09 - LV Power Cable | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-5251 | PS5-60-IH-0001G-CL06 | CPX09 - LV Power Cable | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed
T-00023-5254 | PS5-60-IH-0002-CL01 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5255 | PS5-60-IH-0002-CL02 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5256 | PS5-60-IH-0002-CL03 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5257 | PS5-60-IH-0002-CL04 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5258 | PS5-60-IH-0002-CL05 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5259 | PS5-60-IH-0002-CL06 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5260 | PS5-60-IH-0002-CL07 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5261 | PS5-60-IH-0002-CL08 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5262 | PS5-60-IH-0002-CL09 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5263 | PS5-60-IH-0002-CL10 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5264 | PS5-60-IN-0001A-CL01 | CPX09 - LV Power Cable | E | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5265 | PS5-60-IN-0001B-CL01 | CPX09 - LV Power Cable | E | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5266 | PS5-60-IN-0001C-CL01 | CPX09 - LV Power Cable | E | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-5267 | PS5-60-IN-0001D-CL01 | CPX09 - LV Power Cable | E | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5268 | PS5-60-IN-0001E-CL01 | CPX09 - LV Power Cable | E | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-5269 | PS5-60-IN-0001F-CL01 | CPX09 - LV Power Cable | E | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-5270 | PS5-60-IN-0001G-CL01 | CPX09 - LV Power Cable | E | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-5271 | PS5-60-IN-0002A-CL01 | CPX09 - LV Power Cable | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151118,151116 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5272 | PS5-60-IN-0002A-CL02 | CPX09 - LV Power Cable | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN]
T-00023-5273 | PS5-60-IN-0002A-CL03 | CPX09 - LV Power Cable | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5274 | PS5-60-IN-0002B-CL01 | CPX09 - LV Power Cable | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151118,151116 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5275 | PS5-60-IN-0002B-CL02 | CPX09 - LV Power Cable | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5276 | PS5-60-IN-0002B-CL03 | CPX09 - LV Power Cable | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS cable tag to be install at both side [OPEN]
T-00023-5277 | PS5-60-IN-0002C-CL01 | CPX09 - LV Power Cable | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00023-5278 | PS5-60-IN-0002C-CL02 | CPX09 - LV Power Cable | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00023-5279 | PS5-60-IN-0002C-CL03 | CPX09 - LV Power Cable | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00023-5280 | PS5-60-IN-0002D-CL01 | CPX09 - LV Power Cable | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5281 | PS5-60-IN-0002D-CL02 | CPX09 - LV Power Cable | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Need to Install Vertical Cable ladder to provide support for cable installation (Generator Building Site) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5282 | PS5-60-IN-0002D-CL03 | CPX09 - LV Power Cable | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Need to Install Vertical Cable ladder to provide support for cable installation (Generator Building Site) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5283 | PS5-60-IN-0002E-CL01 | CPX09 - LV Power Cable | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00023-5284 | PS5-60-IN-0002E-CL02 | CPX09 - LV Power Cable | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5285 | PS5-60-IN-0002E-CL03 | CPX09 - LV Power Cable | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5286 | PS5-60-IN-0002F-CL01 | CPX09 - LV Power Cable | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00023-5287 | PS5-60-IN-0002F-CL02 | CPX09 - LV Power Cable | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5288 | PS5-60-IN-0002F-CL03 | CPX09 - LV Power Cable | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0421
T-00023-5289 | PS5-60-IN-0002G-CL01 | CPX09 - LV Power Cable | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00023-5290 | PS5-60-IN-0002G-CL02 | CPX09 - LV Power Cable | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0421
T-00023-5291 | PS5-60-IN-0002G-CL03 | CPX09 - LV Power Cable | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5292 | PS5-60-IWK-0001A-CL01 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed
T-00023-5293 | PS5-60-IWK-0001A-CL02 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed
T-00023-5294 | PS5-60-IWK-0001B-CL01 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching, Coiled around 3 MTR to final Panel (PS5-60-IWK-0001B) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5295 | PS5-60-IWK-0001B-CL02 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching, Coiled around 3 MTR to final Panel (PS5-60-IWK-0001B) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5296 | PS5-60-IWK-0001C-CL01 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching, Coiled around 5 MTR to final Panel (PS5-60-IWK-0001C) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5297 | PS5-60-IWK-0001C-CL02 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching, Coiled around 5 MTR to final Panel (PS5-60-IWK-0001C) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5298 | PS5-60-LA-0002A-CL01 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5299 | PS5-60-LA-0002A-CL02 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5300 | PS5-60-LA-0002B-CL01 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0419
T-00023-5301 | PS5-60-LA-0002B-CL02 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0419
T-00023-5302 | PS5-60-LA-0002C-CL01 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0419
T-00023-5303 | PS5-60-LA-0002C-CL02 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0419
T-00023-5304 | PS5-60-LA-0003-CL01 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN]
T-00023-5305 | PS5-60-LA-0003-CL02 | CPX09 - LV Power Cable | E | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN]
T-00023-5306 | PS5-60-MOV-0005-CL01 | CPX09 - LV Power Cable | E | PS5-71-12 - CFO Service Tank | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). [OPEN] ¦ TZ-MID-68-WPR2-151117,151118 Cable coiled around 90m, to be laid in ladder and reach equipment at field location. [CLOSED] | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side [OPEN]
T-00023-5307 | PS5-60-MOV-0006-CL01 | CPX09 - LV Power Cable | E | PS5-71-12 - CFO Service Tank | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). [OPEN] ¦ TZ-MID-68-WPR2-151117,151118 Cable coiled around 90m, to be laid in ladder and reach equipment at field location. [CLOSED] | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side [OPEN]
T-00023-5308 | PS5-60-MOV-0011-CL01 | CPX09 - LV Power Cable | E | PS5-71-12 - CFO Service Tank | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151118 Cable coiled around 80m, to be laid in ladder and reach equipment at field location. [CLOSED] ¦ TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). [OPEN] | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side [OPEN]
T-00023-5309 | PS5-60-MOV-0012-CL01 | CPX09 - LV Power Cable | E | PS5-71-12 - CFO Service Tank | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151118 Cable coiled around 80m, to be laid in ladder and reach equipment at field location. [CLOSED] ¦ TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). [OPEN] | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side [OPEN]
T-00023-5310 | PS5-60-SEA-0001-CL01 | CPX09 - LV Power Cable | E | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed |  | CPP-RFI-68-33/1-07-0419
T-00023-5311 | PS5-60-SEA-0001-CL02 | CPX09 - LV Power Cable | E | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed |  | CPP-RFI-68-33/1-07-0419
T-00023-5312 | PS5-60-VS-9100A-CL01 | CPX09 - LV Power Cable | E | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5313 | PS5-60-VS-9100B-CL01 | CPX09 - LV Power Cable | E | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5314 | PS5-60-VS-9100C-CL01 | CPX09 - LV Power Cable | E | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5315 | PS5-60-VS-9100D-CL01 | CPX09 - LV Power Cable | E | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-5316 | PS5-60-VS-9100E-CL01 | CPX09 - LV Power Cable | E | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray not finished [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done [OPEN]
T-00023-5317 | PS5-60-VS-9100F-CL01 | CPX09 - LV Power Cable | E | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-5318 | PS5-60-VS-9100G-CL01 | CPX09 - LV Power Cable | E | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-5319 | PS5-61-BI-0001-CL01 | CPX09 - LV Power Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0267 |  |  | TZ-MID-68-WPR2-151118,151116,151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151118,151116,151112-SS Tag on both ends not installed [CLOSED]
T-00023-5320 | PS5-61-BI-0002-CL01 | CPX09 - LV Power Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0267 |  |  | TZ-MID-68-WPR2-151118,151116,151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151118,151116,151112-SS Tag on both ends not installed [OPEN]
T-00023-5321 | PS5-61-BI-0003-CL01 | CPX09 - LV Power Cable | E | PS5-60-07 - Power Generation Package C | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151118,151116,151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151118,151116,151112-SS Tag on both ends not installed [CLOSED]
T-00023-5322 | PS5-61-BI-0004-CL01 | CPX09 - LV Power Cable | E | PS5-60-10 - Power Generation Package D | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151116,151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116,151112-SS Tag on both ends not installed [OPEN]
T-00023-5323 | PS5-61-BI-0005-CL01 | CPX09 - LV Power Cable | E | PS5-60-13 - Power Generation Package E | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151116,151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116,151112-SS Tag on both ends not installed [CLOSED]
T-00023-5324 | PS5-61-BI-0006-CL01 | CPX09 - LV Power Cable | E | PS5-60-16 - Power Generation Package F | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151116,151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116,151112-SS Tag on both ends not installed [OPEN]
T-00023-5325 | PS5-61-BI-0007-CL01 | CPX09 - LV Power Cable | E | PS5-60-19 - Power Generation Package G | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  | TZ-MID-68-WPR2-151116,151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0029, PS5-88-BU-HV-0017, PS5-88-BU-HV-0013, PS5-88-BU-HV-0014, PS5-88-BU-HV-0015, PS5-88-CU-HV-0024) [OPEN] | TZ-MID-68-WPR2-151116,151112 SS Cable tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151116,151112 Cable dressing to be done both side [OPEN]
T-00023-5335 | PS5-61-IG-0015-CL01 | CPX09 - LV Power Cable | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5336 | PS5-61-IG-0016-CL01 | CPX09 - LV Power Cable | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151116 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151116 Cable dressing to be done at both side [OPEN]
T-00023-5343 | PS5-61-IH-0004-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-5344 | PS5-61-IH-0004-CL02 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-5345 | PS5-61-IH-0004-CL03 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-5346 | PS5-61-IH-0004-CL04 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-5347 | PS5-61-IH-0004-CL05 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-5348 | PS5-61-IH-0004-CL06 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-5349 | PS5-61-IH-0004-CL07 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-5350 | PS5-61-IH-0004-CL08 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-5351 | PS5-61-IH-0004-CL09 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-5352 | PS5-61-IH-0004-CL10 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-5353 | PS5-61-IH-0004-CL11 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-5354 | PS5-61-IH-0004-CL12 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-5355 | PS5-61-IH-0004-CL13 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-5356 | PS5-61-IH-0004-CL14 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-5357 | PS5-61-IH-0004-CL15 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-5358 | PS5-61-IH-0004-CL16 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-5359 | PS5-61-IH-0004-CL17 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-5360 | PS5-61-IH-0004-CL18 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-5361 | PS5-61-IH-0004-CL19 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-5362 | PS5-61-IH-0004-CL20 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-5363 | PS5-61-IH-0004-CL21 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-5364 | PS5-61-IH-0004-CL22 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-5425 | PS5-61-IK-0003-CL01 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN]
T-00023-5426 | PS5-61-IK-0003-CL02 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN]
T-00023-5427 | PS5-61-IK-0003-CL03 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed
T-00023-5428 | PS5-61-IK-0003-CL04 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching final destination around 2 MTR (PS5-61-IK-0003) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done [OPEN]
T-00023-5429 | PS5-61-IK-0003-CL05 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching final destination around 2 MTR (PS5-61-IK-0003) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done [OPEN]
T-00023-5430 | PS5-61-IK-0003-CL06 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done [OPEN]
T-00023-5431 | PS5-61-IK-0003-CL07 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00023-5432 | PS5-61-IK-0003-CL08 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00023-5433 | PS5-61-IK-0003-CL09 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00023-5434 | PS5-61-IK-0003-CL10 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00023-5435 | PS5-61-IK-0003-CL11 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00023-5436 | PS5-61-IK-0003-CL12 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00023-5437 | PS5-61-IK-0003-CL13 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5438 | PS5-61-IK-0003-CL14 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5439 | PS5-61-IK-0003-CL15 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/1-05-0211 |  |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [CLOSED]
T-00023-5440 | PS5-61-IK-0003-CL16 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5441 | PS5-61-IK-0003-CL17 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5442 | PS5-61-IK-0003-CL18 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5443 | PS5-61-IK-0003-CL19 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5444 | PS5-61-IK-0003-CL20 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5445 | PS5-61-IK-0003-CL21 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5446 | PS5-61-IK-0003-CL22 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5447 | PS5-61-IK-0003-CL23 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5448 | PS5-61-IK-0003-CL24 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5449 | PS5-61-IK-0003-CL25 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0310 |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [CLOSED]
T-00023-5450 | PS5-61-IK-0003-CL26 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0310 |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [OPEN]
T-00023-5451 | PS5-61-IK-0003-CL27 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0310 |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [CLOSED]
T-00023-5452 | PS5-61-IK-0003-CL28 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0310 |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [CLOSED]
T-00023-5453 | PS5-61-IK-0003-CL29 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0310 |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [CLOSED]
T-00023-5454 | PS5-61-IK-0003-CL30 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5455 | PS5-61-IK-0003-CL31 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5456 | PS5-61-IK-0003-CL32 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5457 | PS5-61-IK-0003-CL33 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5458 | PS5-61-IK-0003-CL34 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5459 | PS5-61-IK-0003-CL35 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5460 | PS5-61-IK-0003-CL36 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5461 | PS5-61-IK-0003-CL37 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151116 Cable ladder to be install at trafo side (PS5-61-IV-0002A) [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0020, PS5-88-BU-LV-00160) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done both side [OPEN]
T-00023-5462 | PS5-61-IK-0003-CL38 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151116 Cable ladder to be install at trafo side (PS5-61-IV-0002A) [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0020, PS5-88-BU-LV-00160) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done both side [OPEN]
T-00023-5463 | PS5-61-IK-0003-CL39 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151116 Cable ladder to be install at trafo side (PS5-61-IV-0002A) [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0020, PS5-88-BU-LV-00160) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done both side [OPEN]
T-00023-5464 | PS5-61-IK-0003-CL40 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151116 Cable ladder to be install at trafo side (PS5-61-IV-0002A) [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0020, PS5-88-BU-LV-00160) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done both side [OPEN]
T-00023-5465 | PS5-61-IK-0003-CL41 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00023-5466 | PS5-61-IK-0003-CL42 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00023-5467 | PS5-61-IK-0003-CL43 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00023-5468 | PS5-61-IK-0003-CL44 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151111, 151112, 151116-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116-Cable dressing not yet done completely [OPEN]
T-00023-5469 | PS5-61-IK-0003-CL45 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00023-5470 | PS5-61-IK-0003-CL46 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00023-5471 | PS5-61-IK-0003-CL47 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00023-5472 | PS5-61-IK-0003-CL48 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00023-5473 | PS5-61-IK-0003-CL49 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00023-5474 | PS5-61-IK-0003-CL50 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00023-5475 | PS5-61-IK-0003-CL51 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00023-5476 | PS5-61-IK-0003-CL52 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00023-5477 | PS5-61-IK-0003-CL53 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00023-5478 | PS5-61-IK-0003-CL54 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00023-5479 | PS5-61-IK-0003-CL55 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0238 | CPP-RFI-68-331-07-0253 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable Trench to be complete installation [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Dressing to be done at both side [OPEN]
T-00023-5480 | PS5-61-IK-0003-CL56 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0238 | CPP-RFI-68-331-07-0253 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable Trench to be complete installation [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Dressing to be done at both side [OPEN]
T-00023-5481 | PS5-61-IK-0003-CL57 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151111, 151112, 151116-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116-Cable dressing not yet done completely [OPEN]
T-00023-5482 | PS5-61-IK-0003-CL58 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151111, 151112, 151116-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116-Cable dressing not yet done completely [OPEN]
T-00023-5483 | PS5-61-IK-0003-CL59 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151111, 151112, 151116-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116-Cable dressing not yet done completely [OPEN]
T-00023-5484 | PS5-61-IK-0003-CL60 | CPX09 - LV Power Cable | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151111, 151112, 151116-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116-Cable dressing not yet done completely [OPEN]
T-00023-5485 | PS5-61-IK-0003-CL61 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed |  | CPP-RFI-68-331-07-0310
T-00023-5486 | PS5-61-IK-0003-CL62 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done [OPEN]
T-00023-5487 | PS5-05-IG-0002-CL01 | CPX09 - LV Power Cable | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00023-5492 | PS5-61-IK-0006-CL01 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00023-5493 | PS5-61-IK-0006-CL02 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00023-5494 | PS5-61-IK-0006-CL03 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00023-5495 | PS5-61-IK-0006-CL04 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00023-5496 | PS5-61-IK-0006-CL05 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00023-5497 | PS5-61-IK-0006-CL06 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00023-5498 | PS5-61-IK-0006-CL07 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00023-5499 | PS5-61-IK-0006-CL08 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00023-5500 | PS5-61-IK-0006-CL09 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00023-5501 | PS5-61-IK-0006-CL10 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5502 | PS5-61-IK-0006-CL11 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5503 | PS5-61-IK-0006-CL12 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5504 | PS5-61-IK-0006-CL13 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5505 | PS5-61-IK-0006-CL14 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5506 | PS5-61-IK-0006-CL15 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5507 | PS5-61-IK-0006-CL16 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5508 | PS5-61-IK-0006-CL17 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5509 | PS5-61-IK-0006-CL18 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5510 | PS5-61-IK-0006-CL19 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151116 Cable Trench Installation to be complete at PS5-61-IV-0007B side [OPEN] | TZ-MID-68-WPR2-151116 Permanent Cable Tag Missing Both End [CLOSED] ¦ TZ-MID-68-WPR2-151116 Dressing Cable To be done at Generator Electrical Building side [OPEN]
T-00023-5511 | PS5-61-IK-0006-CL20 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151116 Cable Trench Installation to be complete at PS5-61-IV-0007B side [OPEN] | TZ-MID-68-WPR2-151116 Permanent Cable Tag Missing Both End [CLOSED] ¦ TZ-MID-68-WPR2-151116 Dressing Cable To be done at Generator Electrical Building side [OPEN]
T-00023-5512 | PS5-61-IK-0006-CL21 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151116 Cable Trench Installation to be complete at PS5-61-IV-0007B side [OPEN] | TZ-MID-68-WPR2-151116 Permanent Cable Tag Missing Both End [CLOSED] ¦ TZ-MID-68-WPR2-151116 Dressing Cable To be done at Generator Electrical Building side [OPEN]
T-00023-5513 | PS5-61-IK-0006-CL22 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151116 Cable Trench Installation to be complete at PS5-61-IV-0007B side [OPEN] | TZ-MID-68-WPR2-151116 Permanent Cable Tag Missing Both End [CLOSED] ¦ TZ-MID-68-WPR2-151116 Dressing Cable To be done at Generator Electrical Building side [OPEN]
T-00023-5514 | PS5-61-IK-0006-CL23 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [OPEN]
T-00023-5515 | PS5-61-IK-0006-CL24 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [OPEN]
T-00023-5516 | PS5-61-IK-0006-CL25 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [OPEN]
T-00023-5517 | PS5-61-IK-0006-CL26 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151112 Cable ladder/tray not yet install at trafo side (PPS5-61-IV-0007B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00157). [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00023-5518 | PS5-61-IK-0006-CL27 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151112 Cable ladder/tray not yet install at trafo side (PPS5-61-IV-0007B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00157). [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00023-5519 | PS5-61-IK-0006-CL28 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151112 Cable ladder/tray not yet install at trafo side (PPS5-61-IV-0007B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00157). [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00023-5520 | PS5-61-IK-0006-CL29 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00023-5521 | PS5-61-IK-0006-CL30 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed |  | CPP-RFI-68-33/1-07-0419
T-00023-5522 | PS5-61-IK-0006-CL31 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00023-5523 | PS5-61-IK-0006-CL32 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00023-5524 | PS5-61-IK-0006-CL33 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151116 Cable ladder at transformer side not yet install PS5-61-IV-0007A [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable trench not yet complete termination [OPEN] | TZ-MID-68-WPR2-151116 SS Permanent cable tag to be install [CLOSED] ¦ TZ-MID-68-WPR2-151116 Cable Dressing to be done at both side [OPEN]
T-00023-5525 | PS5-61-IK-0006-CL34 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151116 Cable ladder at transformer side not yet install PS5-61-IV-0007B [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable trench not yet complete termination [OPEN] | TZ-MID-68-WPR2-151116 SS Permanent cable tag to be install [CLOSED] ¦ TZ-MID-68-WPR2-151116 Cable Dressing to be done at both side [OPEN]
T-00023-5532 | PS5-61-IU-3100A-CL01 | CPX09 - LV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-33/1-05-0217
T-00023-5533 | PS5-61-IU-3100B-CL01 | CPX09 - LV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-33/1-05-0217
T-00023-5534 | PS5-61-IU-3100C-CL01 | CPX09 - LV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-33/1-05-0217
T-00023-5537 | PS5-61-IV-0002A-CL01 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done [OPEN]
T-00023-5538 | PS5-61-IV-0002B-CL01 | CPX09 - LV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done [OPEN]
T-00023-5542 | PS5-61-IV-0007A-CL01 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  |  | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5543 | PS5-61-IV-0007B-CL01 | CPX09 - LV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  |  | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00023-5546 | PS5-62-IE-0001-CL01 | CPX09 - LV Power Cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151111 To be install vertical cable ladder at both end [OPEN] | TZ-MID-68-WPR2-151111 Dressing to be done at both end [OPEN]
T-00023-5547 | PS5-62-IE-0002-CL01 | CPX09 - LV Power Cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117 Cable to be laid in the cable trench No. PS5-88-BU-LV-00162. [OPEN] | TZ-MID-68-WPR2-151117 Permanent SS cable tags to be install [OPEN] ¦ TZ-MID-68-WPR2-151117 Cable need to be dressing completely [OPEN]
T-00023-5561 | PS5-71-FCV-0018-CL01 | CPX09 - LV Power Cable | E | PS5-71-13 - CFO Service Pump A/B | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0307 |  |  | TZ-MID-68-WPR2-151115, TZ-MID-68-WPR2-151112 SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151115, TZ-MID-68-WPR2-151112 Cable Dressing at Both Ends [OPEN]
T-00023-5562 | PS5-71-FCV-0019-CL01 | CPX09 - LV Power Cable | E | PS5-71-21 - Diesel Transfer Pump A/B | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0267 |  |  | TZ-MID-68-WPR2-151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117-SS Tag on both ends not installed [CLOSED]
T-00023-5563 | PS5-71-FCV-0020-CL01 | CPX09 - LV Power Cable | E | PS5-71-05 - CFO Transfer Pump A/B | To be completed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151114,151115 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151115 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. [OPEN] | TZ-MID-68-WPR2-151117,151114,151115 Permanent SS cable tags to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151115 Cable need to be dressing completely at both side [OPEN]
T-00023-5567 | PS5-71-HE-2200-CL02 | CPX09 - LV Power Cable | E | PS5-71-12 - CFO Service Tank | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  | TZ-MID-68-WPR2-151117,151114,151115 Field run cable tray installation not yet complete. [OPEN] | TZ-MID-68-WPR2-151117,151114,151115 SS Cable tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151115 Cable dressing to be done both side [OPEN]
T-00023-5569 | PS5-71-HE-2300-CL02 | CPX09 - LV Power Cable | E | PS5-71-04 - CFO Storage Tank | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0307 |  |  | TZ-MID-68-WPR2-151117,151114,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151115-SS Tag on both ends not installed [CLOSED]
T-00023-5578 | PS5-71-IN-0001-CL01 | CPX09 - LV Power Cable | E | PS5-71-19 - Diesel Separator Module (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00023-5579 | PS5-71-IN-0001-CL02 | CPX09 - LV Power Cable | E | PS5-71-19 - Diesel Separator Module (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00023-5580 | PS5-71-IN-0001-CL03 | CPX09 - LV Power Cable | E | PS5-71-19 - Diesel Separator Module (UCP) | To be completed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151116 Cable trench backfiled, protection tiles, and warning tape installation to be done (PS5-88-BU-LV-00160) [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side [OPEN]
T-00023-5581 | PS5-71-IN-0002-CL01 | CPX09 - LV Power Cable | E | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-5582 | PS5-71-IN-0002-CL02 | CPX09 - LV Power Cable | E | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-5583 | PS5-71-IN-0002-CL03 | CPX09 - LV Power Cable | E | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-5584 | PS5-71-IN-0003-CL01 | CPX09 - LV Power Cable | E | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5585 | PS5-71-IN-0003-CL02 | CPX09 - LV Power Cable | E | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00023-5586 | PS5-71-IN-0003-CL03 | CPX09 - LV Power Cable | E | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed | CPP-RFI-68-33/1-05-0309 | CPP-RFI-68-331-07-0310 |  | TZ-MID-68-WPR2-151166, Cable not reaching final destination [OPEN] | TZ-MID-68-WPR2-151166, Cable Tagging Installation not Yet Done at Both Side [OPEN] ¦ TZ-MID-68-WPR2-151166, Cable Dressing not yet done [OPEN]
T-00023-5587 | PS5-71-IN-0004A-CL01 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable Dressing not yet done [OPEN]
T-00023-5588 | PS5-71-IN-0004A-CL02 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable Dressing not yet done [OPEN]
T-00023-5589 | PS5-71-IN-0004A-CL03 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151116 Cable trench backfiled, protection tiles, and warning tape installation to be done (PS5-88-BU-LV-00159) [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side [OPEN]
T-00023-5590 | PS5-71-IN-0004B-CL01 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-5591 | PS5-71-IN-0004B-CL02 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-5592 | PS5-71-IN-0004B-CL03 | CPX09 - LV Power Cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151116 Cable trench backfiled, protection tiles, and warning tape installation to be done (PS5-88-BU-LV-00159) [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side [OPEN]
T-00023-5593 | PS5-71-LCV-4101-CL01 | CPX09 - LV Power Cable | E | PS5-71-04 - CFO Storage Tank | To be completed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151114,151115 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151115 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. [OPEN] | TZ-MID-68-WPR2-151117,151114,151115 Permanent SS cable tags to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151115 Cable need to be dressing completely at both side [OPEN]
T-00023-5594 | PS5-71-MOV-0001-CL01 | CPX09 - LV Power Cable | E | PS5-71-08 - CFO Pre-Pressure Modules | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench [OPEN] | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed [CLOSED]
T-00023-5595 | PS5-71-MOV-0002-CL01 | CPX09 - LV Power Cable | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench [OPEN] | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed [CLOSED]
T-00023-5596 | PS5-71-MOV-0003-CL01 | CPX09 - LV Power Cable | E | PS5-71-08 - CFO Pre-Pressure Modules | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench [OPEN] | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed [CLOSED]
T-00023-5597 | PS5-71-MOV-0004-CL01 | CPX09 - LV Power Cable | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench [OPEN] | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed [CLOSED]
T-00023-5598 | PS5-71-MOV-0007-CL01 | CPX09 - LV Power Cable | E | PS5-71-04 - CFO Storage Tank | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151118 Cable coiled around 90m, to be laid in ladder and reach equipment at field location. [CLOSED] ¦ TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). [OPEN] | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side [OPEN]
T-00023-5599 | PS5-71-MOV-0008-CL01 | CPX09 - LV Power Cable | E | PS5-71-08 - CFO Pre-Pressure Modules | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151118 Cable coiled around 90m, to be laid in ladder and reach equipment at field location. [CLOSED] ¦ TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). [OPEN] | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side [OPEN]
T-00023-5600 | PS5-71-MOV-0009-CL01 | CPX09 - LV Power Cable | E | PS5-71-04 - CFO Storage Tank | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench [OPEN] | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed [CLOSED]
T-00023-5601 | PS5-71-MOV-0010-CL01 | CPX09 - LV Power Cable | E | PS5-71-08 - CFO Pre-Pressure Modules | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench [OPEN] | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed [CLOSED]
T-00023-5602 | PS5-71-SDV-0001-CL01 | CPX09 - LV Power Cable | E | PS5-71-20 - Diesel Fuel Day Tank | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0267 |  |  | TZ-MID-68-WPR2-151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117-SS Tag on both ends not installed [CLOSED]
T-00023-5603 | PS5-71-SDV-0022-CL01 | CPX09 - LV Power Cable | E | PS5-71-04 - CFO Storage Tank | To be completed
T-00023-5604 | PS5-71-SDV-0029-CL01 | CPX09 - LV Power Cable | E | PS5-71-15 - Diesel Fuel Storage Tank | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151117,151115,151111,151108,151107-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151107-SS Tag on both ends not installed [CLOSED]
T-00023-5605 | PS5-71-SDV-0039-CL01 | CPX09 - LV Power Cable | E | PS5-71-12 - CFO Service Tank | To be completed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151115 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151115 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. [OPEN] | TZ-MID-68-WPR2-151117,151115 Permanent SS cable tags to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151115 Cable need to be dressing completely at both side [OPEN]
T-00023-5606 | PS5-71-UZ-6200-CL01 | CPX09 - LV Power Cable | E | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112, 151111, 151108, 151107-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151111, 151108, 151107-SS Tag on both ends not installed [CLOSED]
T-00023-5607 | PS5-71-XV-0089-CL01 | CPX09 - LV Power Cable | E | PS5-71-04 - CFO Storage Tank | To be completed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151115 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151115 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. [OPEN] | TZ-MID-68-WPR2-151117,151115 Permanent SS cable tags to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151115 Cable need to be dressing completely at both side [OPEN]
T-00023-5608 | PS5-71-XV-0090-CL01 | CPX09 - LV Power Cable | E | PS5-71-12 - CFO Service Tank | To be completed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151115 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151115 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. [OPEN] | TZ-MID-68-WPR2-151117,151115 Permanent SS cable tags to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151115 Cable need to be dressing completely at both side [OPEN]
T-00023-5609 | PS5-71-XV-0091-CL01 | CPX09 - LV Power Cable | E | PS5-71-18 - Diesel Separator Module | To be completed
T-00023-5610 | PS5-71-XV-0092-CL01 | CPX09 - LV Power Cable | E | PS5-71-20 - Diesel Fuel Day Tank | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0267 |  |  | TZ-MID-68-WPR2-151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117-SS Tag on both ends not installed [CLOSED]
T-00023-5612 | PS5-74-LB-5101-CL01 | CPX09 - LV Power Cable | E | PS5-74-02 - N2 Generation Skid (UCP) | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  | TZ-MID-68-WPR2-151167,151116,151112,151111,151108 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0029, PS5-88-BU-HV-0017, PS5-88-DU-HV-0004, PS5-88-BU-HV-0013) [OPEN] | TZ-MID-68-WPR2-151167,151116,151112,151111,151108 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151116,151112,151111,151108 Cable dressing to be done both side [OPEN]
T-00023-5613 | PS5-74-LB-5101-CL02 | CPX09 - LV Power Cable | E | PS5-74-02 - N2 Generation Skid (UCP) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151167,151116,151112,151111,151108-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151167,151116,151112,151111,151108-SS Tag on both ends not installed [OPEN]
T-00023-5620 | PS5-75-MOV-0001-CL01 | CPX09 - LV Power Cable | E | PS5-28-07 - Open Drains (OD2) | To be completed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151117,151114,151113 Field run cable tray/ladder to be installed completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable trench backfiled, protection tiles, and warning tape installation to be done (PS5-88-BU-LV-00164) [OPEN] | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable to be dressing completely at both side [OPEN]
T-00023-5621 | PS5-75-UI-6200-CL01 | CPX09 - LV Power Cable | E | PS5-75-01 - DRA Injection Package | To be completed
T-00023-5622 | PS5-75-UI-6200-CL02 | CPX09 - LV Power Cable | E | PS5-75-01 - DRA Injection Package | To be completed
T-00023-5623 | PS5-78-JC-9100A-CL01 | CPX09 - LV Power Cable | E | PS5-78-01 - Lifting and handling equipment | To be completed
T-00023-5624 | PS5-78-JC-9100B-CL01 | CPX09 - LV Power Cable | E | PS5-78-01 - Lifting and handling equipment | To be completed |  | CPP-RFI-68-33/1-07-0427
T-00023-5625 | PS5-78-JC-9100C-CL01 | CPX09 - LV Power Cable | E | PS5-78-01 - Lifting and handling equipment | To be completed |  | CPP-RFI-68-33/1-07-0427
T-00023-5626 | PS5-78-JC-9100D-CL01 | CPX09 - LV Power Cable | E | PS5-78-01 - Lifting and handling equipment | To be completed |  | CPP-RFI-68-33/1-07-0427
T-00023-5640 | PS5-87-IRF-0001-CL01 | CPX09 - LV Power Cable | E | PS5-53-01 - Utility Water / Storage Tank | To be completed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151111,151108,151109 Field run cable tray to be install at both equipment side [OPEN] | TZ-MID-68-WPR2-151111,151108,151109 Permanent SS cable tags to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151111,151108,151109 Cable need to be dressing completely at both side [OPEN]
T-00023-5641 | PS5-87-IRF-0002-CL01 | CPX09 - LV Power Cable | E | PS5-71-04 - CFO Storage Tank | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  | TZ-MID-68-WPR2-151117,151115--Cable coiled, need to be laid in trench [OPEN] | TZ-MID-68-WPR2-151117,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151115-SS Tag on both ends not installed [CLOSED]
T-00023-5642 | PS5-87-IRF-0003-CL01 | CPX09 - LV Power Cable | E | PS5-71-12 - CFO Service Tank | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  | TZ-MID-68-WPR2-151117,151115--Cable coiled, need to be laid in trench [OPEN] | TZ-MID-68-WPR2-151117,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151115-SS Tag on both ends not installed [CLOSED]
T-00023-5643 | PS5-87-IRF-0004-CL01 | CPX09 - LV Power Cable | E | PS5-71-15 - Diesel Fuel Storage Tank | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151111,151108,151107-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151111,151108,151107-SS Tag on both ends not installed [CLOSED]
T-00023-8829 | PS5-79-IG-0001-CL01 | CPX09 - LV Power Cable | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00023-8830 | PS5-79-IG-0002-CL01 | CPX09 - LV Power Cable | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00023-8831 | PS5-79-IG-0003-CL01 | CPX09 - LV Power Cable | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00023-8832 | PS5-79-IG-0004-CL01 | CPX09 - LV Power Cable | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00023-8833 | PS5-79-IG-0005-CL01 | CPX09 - LV Power Cable | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00023-8834 | PS5-79-IG-0006-CL01 | CPX09 - LV Power Cable | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00023-8835 | PS5-79-IG-0007-CL01 | CPX09 - LV Power Cable | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00023-8836 | PS5-79-IG-0008-CL01 | CPX09 - LV Power Cable | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00023-8837 | PS5-79-IG-0009-CL01 | CPX09 - LV Power Cable | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00023-8838 | PS5-79-IG-0010-CL01 | CPX09 - LV Power Cable | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00023-8839 | PS5-79-IG-0011-CL01 | CPX09 - LV Power Cable | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00023-8840 | PS5-79-IG-0012-CL01 | CPX09 - LV Power Cable | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00023-9120 | PS5-02-SWSI-0001-CL01 | CPX09 - LV Power Cable | E | PS5-02-01 - Miscellaneous Safety equipment | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151111 TZ-MID-68-WPR2-151105, Cable Not Yet Reaching Final Destination, Coiled more than 10 MTR need to Open Trench to Finish installation & Reaching Final Destination (Illuminated Windshock) [OPEN] | Doc. TZ-MID-68-WPR2-151111 TZ-MID-68-WPR2-151105, Cable Tagging Not Yet installed at both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151111 TZ-MID-68-WPR2-151105, Cable Dressing not yet done [OPEN]
T-00023-9121 | PS5-02-SWSI-0003-CL01 | CPX09 - LV Power Cable | E | PS5-02-01 - Miscellaneous Safety equipment | To be completed |  | CPP-RFI-68-331-07-0423
T-00023-9122 | PS5-06-GU-0005-CL01 | CPX09 - LV Power Cable | E | PS5-06-04 - AC UPS - Guard House | To be completed
T-00023-9128 | PS5-09-LB-7001-CL01 | CPX09 - LV Power Cable | E | PS5-09-02 - HVAC for Guard House | To be completed
T-00023-9131 | PS5-60-BE-0007A-CL01 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN]
T-00023-9132 | PS5-60-BE-0007B-CL01 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN]
T-00023-9133 | PS5-60-BE-0007C-CL01 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed |  | CPP-RFI-68-33/1-07-0410
T-00023-9134 | PS5-60-BE-0007D-CL01 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed |  | CPP-RFI-68-33/1-07-0330 |  |  | TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00023-9135 | PS5-60-BE-0007E-CL01 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed |  | CPP-RFI-68-33/1-07-0410
T-00023-9136 | PS5-60-BE-0007F-CL01 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed |  | CPP-RFI-68-33/1-07-0410
T-00023-9137 | PS5-60-BE-0007G-CL01 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed |  | CPP-RFI-68-33/1-07-0410
T-00023-9138 | PS5-60-BE-0027A-CL01 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9139 | PS5-60-BE-0027B-CL01 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed
T-00023-9140 | PS5-60-BE-0027C-CL01 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00023-9141 | PS5-60-BE-0027D-CL01 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00023-9142 | PS5-60-BE-0027E-CL01 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00023-9143 | PS5-60-BE-0027F-CL01 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00023-9144 | PS5-60-BE-0027G-CL01 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00023-9145 | PS5-60-BE-0028A-CL01 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9146 | PS5-60-BE-0028B-CL01 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9147 | PS5-60-BE-0028C-CL01 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00023-9148 | PS5-60-BE-0028D-CL01 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00023-9149 | PS5-60-BE-0028E-CL01 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-9150 | PS5-60-BE-0028F-CL01 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-9151 | PS5-60-BE-0028G-CL01 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-9152 | PS5-60-BI-0006A-CL01 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9153 | PS5-60-BI-0006A-CL02 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  | TZ-MID-68-WPR2-151179 Field Run Cable Tray To be installed [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00023-9154 | PS5-60-BI-0006A-CL03 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9155 | PS5-60-BI-0006A-CL04 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9156 | PS5-60-BI-0006A-CL05 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9157 | PS5-60-BI-0006A-CL06 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9158 | PS5-60-BI-0006A-CL07 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9159 | PS5-60-BI-0006A-CL08 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9160 | PS5-60-BI-0006A-CL09 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9161 | PS5-60-BI-0006A-CL10 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9162 | PS5-60-BI-0006A-CL11 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9163 | PS5-60-BI-0006B-CL01 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9164 | PS5-60-BI-0006B-CL02 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9165 | PS5-60-BI-0006B-CL03 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9166 | PS5-60-BI-0006B-CL04 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9167 | PS5-60-BI-0006B-CL05 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9168 | PS5-60-BI-0006B-CL06 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9169 | PS5-60-BI-0006B-CL07 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9170 | PS5-60-BI-0006B-CL08 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9171 | PS5-60-BI-0006B-CL09 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9172 | PS5-60-BI-0006B-CL10 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9173 | PS5-60-BI-0006B-CL11 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9174 | PS5-60-BI-0006C-CL01 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00023-9175 | PS5-60-BI-0006C-CL02 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00023-9176 | PS5-60-BI-0006C-CL03 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-9177 | PS5-60-BI-0006C-CL04 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-9178 | PS5-60-BI-0006C-CL05 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-9179 | PS5-60-BI-0006C-CL06 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00023-9180 | PS5-60-BI-0006C-CL07 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00023-9181 | PS5-60-BI-0006C-CL08 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00023-9182 | PS5-60-BI-0006C-CL09 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00023-9183 | PS5-60-BI-0006C-CL10 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00023-9184 | PS5-60-BI-0006C-CL11 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00023-9185 | PS5-60-BI-0006D-CL01 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00023-9186 | PS5-60-BI-0006D-CL02 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00023-9187 | PS5-60-BI-0006D-CL03 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00023-9188 | PS5-60-BI-0006D-CL04 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00023-9189 | PS5-60-BI-0006D-CL05 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00023-9190 | PS5-60-BI-0006D-CL06 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00023-9191 | PS5-60-BI-0006D-CL07 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00023-9192 | PS5-60-BI-0006D-CL08 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00023-9193 | PS5-60-BI-0006D-CL09 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00023-9194 | PS5-60-BI-0006D-CL10 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00023-9195 | PS5-60-BI-0006D-CL11 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-9196 | PS5-60-BI-0006E-CL01 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00023-9197 | PS5-60-BI-0006E-CL02 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00023-9198 | PS5-60-BI-0006E-CL03 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed |  | CPP-RFI-68-33/1-07-0427
T-00023-9199 | PS5-60-BI-0006E-CL04 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00023-9200 | PS5-60-BI-0006E-CL05 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00023-9201 | PS5-60-BI-0006E-CL06 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00023-9202 | PS5-60-BI-0006E-CL07 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00023-9203 | PS5-60-BI-0006E-CL08 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed |  | CPP-RFI-68-33/1-07-0420
T-00023-9204 | PS5-60-BI-0006E-CL09 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00023-9205 | PS5-60-BI-0006E-CL10 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00023-9206 | PS5-60-BI-0006E-CL11 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-9207 | PS5-60-BI-0006F-CL01 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00023-9208 | PS5-60-BI-0006F-CL02 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00023-9209 | PS5-60-BI-0006F-CL03 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00023-9210 | PS5-60-BI-0006F-CL04 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-9211 | PS5-60-BI-0006F-CL05 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00023-9212 | PS5-60-BI-0006F-CL06 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00023-9213 | PS5-60-BI-0006F-CL07 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00023-9214 | PS5-60-BI-0006F-CL08 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00023-9215 | PS5-60-BI-0006F-CL09 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00023-9216 | PS5-60-BI-0006F-CL10 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00023-9217 | PS5-60-BI-0006F-CL11 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-9218 | PS5-60-BI-0006G-CL01 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00023-9219 | PS5-60-BI-0006G-CL02 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00023-9220 | PS5-60-BI-0006G-CL03 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00023-9221 | PS5-60-BI-0006G-CL04 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00023-9222 | PS5-60-BI-0006G-CL05 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00023-9223 | PS5-60-BI-0006G-CL06 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00023-9224 | PS5-60-BI-0006G-CL07 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00023-9225 | PS5-60-BI-0006G-CL08 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00023-9226 | PS5-60-BI-0006G-CL09 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00023-9227 | PS5-60-BI-0006G-CL10 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00023-9228 | PS5-60-BI-0006G-CL11 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-9229 | PS5-60-BI-0017A-CL01 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9230 | PS5-60-BI-0017B-CL01 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00023-9231 | PS5-60-BI-0017C-CL01 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-9232 | PS5-60-BI-0017D-CL01 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-9233 | PS5-60-BI-0017E-CL01 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-9234 | PS5-60-BI-0017F-CL01 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed |  | CPP-RFI-68-331-07-0422
T-00023-9235 | PS5-60-BI-0017G-CL01 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed |  | CPP-RFI-68-33/1-07-0412
T-00023-9236 | PS5-60-EA-2900A-CL01 | CPX09 - LV Power Cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed
T-00023-9237 | PS5-60-EA-2900B-CL01 | CPX09 - LV Power Cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed
T-00023-9238 | PS5-60-EA-2900C-CL01 | CPX09 - LV Power Cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00023-9239 | PS5-60-EA-2900D-CL01 | CPX09 - LV Power Cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00023-9240 | PS5-60-EA-2900E-CL01 | CPX09 - LV Power Cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00023-9241 | PS5-60-EA-2900F-CL01 | CPX09 - LV Power Cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00023-9242 | PS5-60-EA-2900G-CL01 | CPX09 - LV Power Cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00023-9243 | PS5-61-IK-0005-CL01 | CPX09 - LV Power Cable | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00023-9244 | PS5-71-BE-0004-CL01 | CPX09 - LV Power Cable | E | PS5-71-08 - CFO Pre-Pressure Modules | To be completed | CPP-RFI-68-331-05-0399 | CPP-RFI-68-331-07-0400 |  | TZ-MID-68-WPR2-151167, 151118, 151179 Field Run cable tray to be install [OPEN] | TZ-MID-68-WPR2-151167, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167, 151118, 151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables [OPEN]
T-00023-9245 | PS5-71-BE-0004-CL02 | CPX09 - LV Power Cable | E | PS5-71-08 - CFO Pre-Pressure Modules | To be completed
T-00023-9246 | PS5-71-BE-0004-CL03 | CPX09 - LV Power Cable | E | PS5-71-08 - CFO Pre-Pressure Modules | To be completed | CPP-RFI-68-331-05-0399 | CPP-RFI-68-331-07-0400 |  | TZ-MID-68-WPR2-151167, 151118, 151179 Field Run cable tray to be install [OPEN] | TZ-MID-68-WPR2-151167, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167, 151118, 151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables [OPEN]
T-00023-9247 | PS5-71-BI-0003-CL01 | CPX09 - LV Power Cable | E | PS5-71-08 - CFO Pre-Pressure Modules | To be completed | CPP-RFI-68-331-05-0399 | CPP-RFI-68-331-07-0400 |  | TZ-MID-68-WPR2-151167, 151118, 151179 Field Run cable tray to be install [OPEN] | TZ-MID-68-WPR2-151167, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167, 151118, 151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables [OPEN]
T-00023-9248 | PS5-71-BI-0003-CL02 | CPX09 - LV Power Cable | E | PS5-71-08 - CFO Pre-Pressure Modules | To be completed |  | CPP-RFI-68-33/1-07-0410
T-00023-9249 | PS5-71-BI-0003-CL03 | CPX09 - LV Power Cable | E | PS5-71-08 - CFO Pre-Pressure Modules | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-9250 | PS5-71-BI-0003-CL04 | CPX09 - LV Power Cable | E | PS5-71-08 - CFO Pre-Pressure Modules | To be completed |  | CPP-RFI-68-331-07-0409
T-00023-9251 | PS5-71-BI-0004-CL01 | CPX09 - LV Power Cable | E | PS5-71-08 - CFO Pre-Pressure Modules | To be completed |  | CPP-RFI-68-331-07-0423
T-00023-9252 | PS5-71-BI-0005-CL01 | CPX09 - LV Power Cable | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cables Dressing not yet done at both ends [OPEN]
T-00023-9253 | PS5-71-BI-0005-CL02 | CPX09 - LV Power Cable | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cables Dressing not yet done at both ends [OPEN]
T-00023-9254 | PS5-71-BI-0005-CL03 | CPX09 - LV Power Cable | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  | TZ-MID-68-WPR2-151167, 151118, 151179 Field Run Cable tray to be intall [OPEN] | TZ-MID-68-WPR2-151167, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00023-9255 | PS5-71-BI-0006-CL01 | CPX09 - LV Power Cable | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cables Dressing not yet done at both ends [OPEN]
T-00023-9680 | PS5-09-AHU-8111A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9681 | PS5-09-AHU-8111B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9682 | PS5-09-AHU-8211A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9683 | PS5-09-AHU-8211B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9684 | PS5-09-AHU-8311A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9685 | PS5-09-AHU-8311A-CL02 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9686 | PS5-09-AHU-8311B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9687 | PS5-09-AHU-8311B-CL02 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9688 | PS5-09-AHU-8321A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9689 | PS5-09-AHU-8321A-CL02 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9690 | PS5-09-AHU-8321B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9691 | PS5-09-AHU-8321B-CL02 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9692 | PS5-09-AHU-8331A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9693 | PS5-09-AHU-8331A-CL02 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9694 | PS5-09-AHU-8331B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9695 | PS5-09-AHU-8331B-CL02 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9696 | PS5-09-AHU-8341-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9697 | PS5-09-AHU-8341-CL02 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9698 | PS5-09-AHU-8411A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9699 | PS5-09-AHU-8411A-CL02 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9700 | PS5-09-AHU-8411B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9701 | PS5-09-AHU-8411B-CL02 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9702 | PS5-09-FCU-8442A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9703 | PS5-09-FCU-8442B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9704 | PS5-09-FCU-8442C-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9705 | PS5-09-FCU-8442D-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9706 | PS5-09-FCU-8442E-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9707 | PS5-09-FCU-8442F-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9708 | PS5-09-FCU-8442G-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9709 | PS5-09-FCU-8442H-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9710 | PS5-09-LB-0008-CL03 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9711 | PS5-09-PA-84500A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9712 | PS5-09-PA-84500B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9713 | PS5-09-QX-8451A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9714 | PS5-09-QX-8451A-CL02 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9715 | PS5-09-QX-8451B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9716 | PS5-09-QX-8451B-CL02 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9717 | PS5-09-RF-81200A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9718 | PS5-09-RF-81200B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9719 | PS5-09-RF-81200C-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9720 | PS5-09-RF-82200A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9721 | PS5-09-RF-82200B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9722 | PS5-09-RF-82200C-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9723 | PS5-09-RF-82200D-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9724 | PS5-09-RF-83500A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9725 | PS5-09-RF-83500B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9726 | PS5-09-RF-83500C-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9727 | PS5-09-RF-83500D-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9728 | PS5-09-RF-83500E-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9729 | PS5-09-RF-83500F-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9730 | PS5-09-RF-83500G-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9731 | PS5-09-RF-83500H-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9732 | PS5-09-RF-83500J-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9733 | PS5-09-RF-83500K-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9734 | PS5-09-RF-83500L-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9735 | PS5-09-RF-83500M-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9736 | PS5-09-RF-83500N-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9737 | PS5-09-RF-83500P-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9738 | PS5-09-RF-83600A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9739 | PS5-09-RF-83600B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9740 | PS5-09-RF-83600C-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9741 | PS5-09-RF-83600D-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9742 | PS5-09-RF-83600E-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9743 | PS5-09-RF-83600F-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9744 | PS5-09-RF-83600G-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9745 | PS5-09-RF-83600H-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9746 | PS5-09-RF-83600J-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9747 | PS5-09-RF-83600K-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9748 | PS5-09-RF-83600L-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9749 | PS5-09-RF-83600M-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9750 | PS5-09-RF-83600N-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9751 | PS5-09-RF-83600P-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9752 | PS5-09-RF-83700A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9753 | PS5-09-RF-83700B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9754 | PS5-09-RF-83700C-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9755 | PS5-09-RF-83700D-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9756 | PS5-09-RF-83700E-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9757 | PS5-09-RF-83700F-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9758 | PS5-09-RF-83700G-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9759 | PS5-09-RF-83700H-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9760 | PS5-09-RF-83700J-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9761 | PS5-09-RF-83700K-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9762 | PS5-09-RF-83700L-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9763 | PS5-09-RF-83700M-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9764 | PS5-09-RF-83700N-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9765 | PS5-09-RF-83700P-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9766 | PS5-09-RF-83800A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9767 | PS5-09-RF-83800B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9768 | PS5-09-RF-83800C-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9769 | PS5-09-RF-83800D-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9770 | PS5-09-RF-83800E-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9771 | PS5-09-RF-83800F-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9772 | PS5-09-RF-83800G-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9773 | PS5-09-RF-84200A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9774 | PS5-09-RF-84200B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9775 | PS5-09-UZ-84600-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9776 | PS5-61-IH-0004A-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9777 | PS5-61-IH-0004B-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9778 | PS5-61-IH-0004C-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00023-9779 | PS5-61-IH-0004D-CL01 | CPX09 - LV Power Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-2028 | PS5-05-IE-8100-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00024-2029 | PS5-05-IE-8100-CD02 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00024-2030 | PS5-05-IE-8100-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00024-2031 | PS5-05-IE-8100-CD04 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00024-2032 | PS5-05-IE-8100-CD05 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00024-2033 | PS5-05-IE-8100-CD06 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00024-2034 | PS5-05-IE-8100-CD07 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00024-2035 | PS5-05-IE-8100-CD08 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00024-2037 | PS5-05-IE-8100-CD10 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00024-2038 | PS5-05-IE-8100-CD11 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00024-2039 | PS5-05-IE-8100-CD12 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00024-2040 | PS5-05-IE-8100-CD13 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00024-2041 | PS5-05-IE-8100-CD14 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00024-2042 | PS5-05-IE-8100-CD15 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00024-2043 | PS5-05-IE-8100-CD16 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00024-2044 | PS5-05-IE-8100-CD17 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00024-2045 | PS5-05-IE-8100-CD18 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00024-2046 | PS5-05-IE-8100-CD19 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00024-2047 | PS5-05-IE-8100-CD20 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00024-2048 | PS5-05-IE-8100-CD21 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00024-2052 | PS5-05-IE-8100-CD25 | CPX10 - Multicore Electrical Control Cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  |  | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side [OPEN]
T-00024-2061 | PS5-25-DM-3100A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Trench Not yet complete installation both end [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Field Run Cable tray not yet complete installation both end. [OPEN] | TZ-MID-68-WPR2-151111,151115,151117,151114 Dressing Cable Both Side to be done [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Permanent Cable Tag Missing Both End [CLOSED]
T-00024-2062 | PS5-25-DM-3100B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Trench Not yet complete installation both end [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Field Run Cable tray not yet complete installation both end. [OPEN] | TZ-MID-68-WPR2-151111,151115,151117,151114 Dressing Cable Both Side to be done [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Permanent Cable Tag Missing Both End [CLOSED]
T-00024-2063 | PS5-25-DM-3100C-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Trench Not yet complete installation both end [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Field Run Cable tray not yet complete installation both end. [OPEN] | TZ-MID-68-WPR2-151111,151115,151117,151114 Dressing Cable Both Side to be done [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Permanent Cable Tag Missing Both End [CLOSED]
T-00024-2067 | PS5-25-IES-3100A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0287 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00024-2068 | PS5-25-IES-3100B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0287 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00024-2069 | PS5-25-IES-3100C-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0287 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00024-2097 | PS5-50-IE-0001-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-50-01 - Water Well Submersible Pumps (3100) | To be completed
T-00024-2098 | PS5-50-IE-0002-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-50-02 - Water Well Submersible Pumps (3200) | To be completed
T-00024-2101 | PS5-60-IE-0002A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN]
T-00024-2102 | PS5-60-IE-0002A-CD02 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN]
T-00024-2103 | PS5-60-IE-0002A-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN]
T-00024-2104 | PS5-60-IE-0002B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN]
T-00024-2105 | PS5-60-IE-0002B-CD02 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN]
T-00024-2106 | PS5-60-IE-0002B-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN]
T-00024-2107 | PS5-60-IE-0002C-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-07 - Power Generation Package C | To be completed | CPP-RFI-68-331-05-0399 | CPP-RFI-68-331-07-0400 |  | TZ-MID-68-WPR2-151179 Secondary cable tray to be install at both side [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables [OPEN]
T-00024-2108 | PS5-60-IE-0002C-CD02 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-07 - Power Generation Package C | To be completed | CPP-RFI-68-331-05-0399 | CPP-RFI-68-331-07-0400 |  | TZ-MID-68-WPR2-151179 Secondary cable tray to be install at both side [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables [OPEN]
T-00024-2109 | PS5-60-IE-0002C-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-07 - Power Generation Package C | To be completed | CPP-RFI-68-331-05-0399 | CPP-RFI-68-331-07-0400 |  | TZ-MID-68-WPR2-151179 Secondary cable tray to be install at both side [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables [OPEN]
T-00024-2110 | PS5-60-IE-0002D-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-10 - Power Generation Package D | To be completed | CPP-RFI-68-331-05-0399 | CPP-RFI-68-331-07-0400 |  | TZ-MID-68-WPR2-151179 Secondary cable tray to be install at both side [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables [OPEN]
T-00024-2111 | PS5-60-IE-0002D-CD02 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-10 - Power Generation Package D | To be completed | CPP-RFI-68-331-05-0399 | CPP-RFI-68-331-07-0400 |  | TZ-MID-68-WPR2-151179 Secondary cable tray to be install at both side [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables [OPEN]
T-00024-2112 | PS5-60-IE-0002D-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-331-07-0422
T-00024-2113 | PS5-60-IE-0002E-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-33/1-07-0421
T-00024-2114 | PS5-60-IE-0002E-CD02 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-33/1-07-0421
T-00024-2115 | PS5-60-IE-0002E-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-13 - Power Generation Package E | To be completed |  | CPP-RFI-68-33/1-07-0421
T-00024-2116 | PS5-60-IE-0002F-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00024-2117 | PS5-60-IE-0002F-CD02 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00024-2118 | PS5-60-IE-0002F-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00024-2119 | PS5-60-IE-0002G-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00024-2120 | PS5-60-IE-0002G-CD02 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00024-2121 | PS5-60-IE-0002G-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-33/1-07-0415
T-00024-2123 | PS5-60-IE-0003A-CD02 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00024-2124 | PS5-60-IE-0003A-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179,151116,151118,151167 Cable dressing to be done at both side [OPEN]
T-00024-2125 | PS5-60-IE-0003A-CD04 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00024-2126 | PS5-60-IE-0003A-CD05 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179,151116,151118,151167 Cable dressing to be done at both side [OPEN]
T-00024-2135 | PS5-60-IE-0003A-CD14 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179,151116,151118,151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179,151116,151118, 151167 Permanent SS cable tag to be install at both side [OPEN]
T-00024-2136 | PS5-60-IE-0003A-CD15 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN]
T-00024-2138 | PS5-60-IE-0003B-CD02 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179,151116,151118,151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179,151116,151118, 151167 Permanent SS cable tag to be install at both side [OPEN]
T-00024-2139 | PS5-60-IE-0003B-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179,151116,151118,151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179,151116,151118, 151167 Permanent SS cable tag to be install at both side [OPEN]
T-00024-2140 | PS5-60-IE-0003B-CD04 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN]
T-00024-2141 | PS5-60-IE-0003B-CD05 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-04 - Power Generation Package B | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00024-2150 | PS5-60-IE-0003B-CD14 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179,151116,151118, 151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179,151116,151118, 151167 Permanent SS cable tag to be install at both side [OPEN]
T-00024-2151 | PS5-60-IE-0003B-CD15 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN]
T-00024-2153 | PS5-60-IE-0003C-CD02 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-07 - Power Generation Package C | To be completed
T-00024-2154 | PS5-60-IE-0003C-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-07 - Power Generation Package C | To be completed
T-00024-2155 | PS5-60-IE-0003C-CD04 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-07 - Power Generation Package C | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00024-2156 | PS5-60-IE-0003C-CD05 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-07 - Power Generation Package C | To be completed
T-00024-2165 | PS5-60-IE-0003C-CD14 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-07 - Power Generation Package C | To be completed
T-00024-2166 | PS5-60-IE-0003C-CD15 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-07 - Power Generation Package C | To be completed
T-00024-2168 | PS5-60-IE-0003D-CD02 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-10 - Power Generation Package D | To be completed
T-00024-2169 | PS5-60-IE-0003D-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00024-2170 | PS5-60-IE-0003D-CD04 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00024-2171 | PS5-60-IE-0003D-CD05 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00024-2180 | PS5-60-IE-0003D-CD14 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00024-2181 | PS5-60-IE-0003D-CD15 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-10 - Power Generation Package D | To be completed
T-00024-2183 | PS5-60-IE-0003E-CD02 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-13 - Power Generation Package E | To be completed
T-00024-2184 | PS5-60-IE-0003E-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-13 - Power Generation Package E | To be completed
T-00024-2185 | PS5-60-IE-0003E-CD04 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-13 - Power Generation Package E | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00024-2186 | PS5-60-IE-0003E-CD05 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-13 - Power Generation Package E | To be completed
T-00024-2195 | PS5-60-IE-0003E-CD14 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-13 - Power Generation Package E | To be completed
T-00024-2196 | PS5-60-IE-0003E-CD15 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-13 - Power Generation Package E | To be completed
T-00024-2198 | PS5-60-IE-0003F-CD02 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-331-07-0423
T-00024-2199 | PS5-60-IE-0003F-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-331-07-0423
T-00024-2200 | PS5-60-IE-0003F-CD04 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-16 - Power Generation Package F | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00024-2201 | PS5-60-IE-0003F-CD05 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-16 - Power Generation Package F | To be completed
T-00024-2210 | PS5-60-IE-0003F-CD14 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-16 - Power Generation Package F | To be completed
T-00024-2211 | PS5-60-IE-0003F-CD15 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-16 - Power Generation Package F | To be completed |  | CPP-RFI-68-331-07-0423
T-00024-2213 | PS5-60-IE-0003G-CD02 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-331-07-0423
T-00024-2214 | PS5-60-IE-0003G-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-331-07-0423
T-00024-2215 | PS5-60-IE-0003G-CD04 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-19 - Power Generation Package G | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00024-2216 | PS5-60-IE-0003G-CD05 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-331-07-0423
T-00024-2225 | PS5-60-IE-0003G-CD14 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-331-07-0423
T-00024-2226 | PS5-60-IE-0003G-CD15 | CPX10 - Multicore Electrical Control Cable | E | PS5-60-19 - Power Generation Package G | To be completed |  | CPP-RFI-68-331-07-0423
T-00024-2233 | PS5-61-IDH-3100A-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-33/1-05-0217 |  |  |  | Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely [OPEN]
T-00024-2236 | PS5-61-IDH-3100B-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-33/1-05-0217 |  |  |  | Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely [OPEN]
T-00024-2239 | PS5-61-IDH-3100C-CD03 | CPX10 - Multicore Electrical Control Cable | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-33/1-05-0217 |  |  |  | Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely [OPEN]
T-00024-2288 | PS5-62-IE-0001-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151111 To be install vertical cable ladder at both end [OPEN] | TZ-MID-68-WPR2-151111 Dressing to be done at both end [OPEN]
T-00024-3288 | PS5-79-IG-0001-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00024-3289 | PS5-79-IG-0002-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00024-3290 | PS5-79-IG-0003-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00024-3291 | PS5-79-IG-0004-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00024-3292 | PS5-79-IG-0005-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00024-3293 | PS5-79-IG-0006-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00024-3294 | PS5-79-IG-0007-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00024-3295 | PS5-79-IG-0008-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00024-3296 | PS5-79-IG-0009-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00024-3297 | PS5-79-IG-0010-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00024-3298 | PS5-79-IG-0011-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00024-3299 | PS5-79-IG-0012-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00024-3399 | PS5-06-GU-0003A-CD02 | CPX10 - Multicore Electrical Control Cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  |  | TZ-MID-68-WPR2-151112, 151116, 151118 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be done at both side [OPEN]
T-00024-3634 | PS5-09-IES-8101A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3635 | PS5-09-IES-8101B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3636 | PS5-09-IES-8102A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3637 | PS5-09-IES-8102B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3638 | PS5-09-IES-8102C-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3639 | PS5-09-IES-8201A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3640 | PS5-09-IES-8201B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3641 | PS5-09-IES-8202A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3642 | PS5-09-IES-8202B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3643 | PS5-09-IES-8202C-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3644 | PS5-09-IES-8202D-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3645 | PS5-09-IES-8301A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3646 | PS5-09-IES-8301B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3647 | PS5-09-IES-8302A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3648 | PS5-09-IES-8302B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3649 | PS5-09-IES-8304A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3650 | PS5-09-IES-8304B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3651 | PS5-09-IES-8305A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3652 | PS5-09-IES-8305B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3653 | PS5-09-IES-8307A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3654 | PS5-09-IES-8307B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3655 | PS5-09-IES-8308A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3656 | PS5-09-IES-8308B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3657 | PS5-09-IES-8311A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3658 | PS5-09-IES-8311B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3659 | PS5-09-IES-8313-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3660 | PS5-09-IES-8314-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3661 | PS5-09-IES-8315-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3662 | PS5-09-IES-8316-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3663 | PS5-09-IES-8317-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3664 | PS5-09-IES-8318-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3665 | PS5-09-IES-8319-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3666 | PS5-09-IES-8321-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3667 | PS5-09-IES-8322-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3668 | PS5-09-IES-8323-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3669 | PS5-09-IES-8324-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3670 | PS5-09-IES-8325-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3671 | PS5-09-IES-8401A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3672 | PS5-09-IES-8401B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3673 | PS5-09-IES-8403A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3674 | PS5-09-IES-8403B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3675 | PS5-09-IES-8404A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3676 | PS5-09-IES-8404B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3677 | PS5-09-IES-8405A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3678 | PS5-09-IES-8405B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3679 | PS5-09-IES-8406A-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3680 | PS5-09-IES-8406B-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3681 | PS5-09-IES-8406C-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3682 | PS5-09-IES-8406D-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3683 | PS5-09-IES-8406E-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3684 | PS5-09-IES-8406F-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3685 | PS5-09-IES-8406G-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3686 | PS5-09-IES-8406H-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00024-3687 | PS5-09-IES-8407-CD01 | CPX10 - Multicore Electrical Control Cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00025-0013 | PS5-25-DM-3100A | CPX12 - HV Motor | E | PS5-25-02 - Crude Oil Export Pump A | To be completed |  | CPP-RFI-68-331-18-0364
T-00025-0014 | PS5-25-DM-3100B | CPX12 - HV Motor | E | PS5-25-03 - Crude Oil Export Pump B | To be completed |  | CPP-RFI-68-331-18-0364
T-00025-0015 | PS5-25-DM-3100C | CPX12 - HV Motor | E | PS5-25-04 - Crude Oil Export Pump C | To be completed |  | CPP-RFI-68-331-18-0364
T-00026-0155 | PS5-28-DM-3300 | CPX13 - LV Motor | E | PS5-28-06 - Relief Drum and Pump | To be completed
T-00026-0156 | PS5-28-DM-3400 | CPX13 - LV Motor | E | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00026-0157 | PS5-28-DM-3500 | CPX13 - LV Motor | E | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00026-0158 | PS5-28-DM-3600A | CPX13 - LV Motor | E | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00026-0159 | PS5-28-DM-3600B | CPX13 - LV Motor | E | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00026-0160 | PS5-28-DM-3700A | CPX13 - LV Motor | E | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00026-0161 | PS5-28-DM-3700B | CPX13 - LV Motor | E | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00026-0162 | PS5-28-DM-3800A | CPX13 - LV Motor | E | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00026-0163 | PS5-28-DM-3800B | CPX13 - LV Motor | E | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00026-0164 | PS5-28-DM-3800C | CPX13 - LV Motor | E | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00026-0165 | PS5-28-DM-3900A | CPX13 - LV Motor | E | PS5-28-17 - Reinjection Pump | To be completed
T-00026-0166 | PS5-28-DM-3900B | CPX13 - LV Motor | E | PS5-28-17 - Reinjection Pump | To be completed
T-00026-0167 | PS5-53-DM-3100A | CPX13 - LV Motor | E | PS5-53-02 - Water Distribution Pump A/B | To be completed
T-00026-0168 | PS5-53-DM-3100B | CPX13 - LV Motor | E | PS5-53-02 - Water Distribution Pump A/B | To be completed
T-00026-0169 | PS5-60-DM-3300 | CPX13 - LV Motor | E | PS5-60-24 - Cooling Water Tank & Pump | To be completed
T-00026-0170 | PS5-60-DM-3400 | CPX13 - LV Motor | E | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | To be completed
T-00026-0171 | PS5-71-DM-3100A | CPX13 - LV Motor | E | PS5-71-16 - Diesel Fuel Supply Pump A/B | To be completed
T-00026-0172 | PS5-71-DM-3100B | CPX13 - LV Motor | E | PS5-71-16 - Diesel Fuel Supply Pump A/B | To be completed
T-00026-0173 | PS5-71-DM-3200 | CPX13 - LV Motor | E | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | To be completed
T-00026-0174 | PS5-71-DM-3300A | CPX13 - LV Motor | E | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00026-0175 | PS5-71-DM-3300B | CPX13 - LV Motor | E | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00026-0176 | PS5-71-DM-3400A | CPX13 - LV Motor | E | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00026-0177 | PS5-71-DM-3400B | CPX13 - LV Motor | E | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00026-0178 | PS5-71-DM-3500A | CPX13 - LV Motor | E | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00026-0179 | PS5-71-DM-3500B | CPX13 - LV Motor | E | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00026-0286 | PS5-28-DM-31100 | CPX13 - LV Motor | E | PS5-28-10 - Oil Skimmer Package | To be completed
T-00028-0462 | PS5-01-IG-0001 | CPX15 - Distribution Board | E | PS5-01-10 - Water Mist Package | To be completed
T-00028-0463 | PS5-05-IG-0002 | CPX15 - Distribution Board | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00028-0464 | PS5-05-IG-0004 | CPX15 - Distribution Board | E | PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | To be completed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  | TZ-MID-68-WPR2-151117 Door glass has cracked to be rectify/replaced [OPEN] | TZ-MID-68-WPR2-151117 To be clean weld slag and touch up paint at the panel support. [OPEN] | TZ-MID-68-WPR2-151117 Perform cleanning internal and external of the panel [OPEN]
T-00028-0465 | PS5-05-IG-0006 | CPX15 - Distribution Board | E | PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | To be completed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  | TZ-MID-68-WPR2-151111 Isolation pad to be install at SS bracket and bolts since disimilar material. [OPEN] |  | TZ-MID-68-WPR2-151111 Perform cleanning internal and external of the panel [OPEN]
T-00028-0466 | PS5-05-IG-0007 | CPX15 - Distribution Board | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00028-0467 | PS5-05-IG-0025 | CPX15 - Distribution Board | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | To be completed
T-00028-0468 | PS5-05-IG-0026 | CPX15 - Distribution Board | E | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | To be completed
T-00028-0469 | PS5-06-IG-0004A | CPX15 - Distribution Board | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | [5 empty] | TZ-MID-60-RME2-150010 Cleanning internal and external of the panel [OPEN] ¦ TZ-MID-60-RME2-150010 The Panel Frame need to be touch up paint [OPEN]
T-00028-0470 | PS5-06-IG-0004B | CPX15 - Distribution Board | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | [5 empty] | TZ-MID-60-RME2-150010 Cleanning internal and external of the panel [OPEN] ¦ TZ-MID-60-RME2-150010 The Panel Frame need to be touch up paint [OPEN]
T-00028-0471 | PS5-61-IG-0006 | CPX15 - Distribution Board | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  |  | TZ-MID-68-WPR2-151117 To be clean weld slag and touch up paint at the panel support. [OPEN] | TZ-MID-68-WPR2-151117 Perform cleanning internal and external of the panel [OPEN]
T-00028-0472 | PS5-61-IG-0007 | CPX15 - Distribution Board | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | To be completed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  | TZ-MID-68-WPR2-151111 Isolation pad to be install at SS bracket and bolts since disimilar material. [OPEN] |  | TZ-MID-68-WPR2-151111 Perform cleanning internal and external of the panel [OPEN] ¦ TZ-MID-68-WPR2-151111 Body panel scratc to be touch up paint [OPEN]
T-00028-0473 | PS5-61-IG-0014 | CPX15 - Distribution Board | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  | TZ-MID-68-WPR2-151111 Isolation pad to be install at SS bracket and bolts since disimilar material. [OPEN] |  | TZ-MID-68-WPR2-151111 Perform cleanning internal and external of the panel [OPEN]
T-00028-0474 | PS5-61-IG-0015 | CPX15 - Distribution Board | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00028-0475 | PS5-61-IG-0016 | CPX15 - Distribution Board | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed
T-00028-0476 | PS5-61-IG-0042 | CPX15 - Distribution Board | E | PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-0042 | To be completed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  | TZ-MID-68-WPR2-151117 Door glass has cracked to be rectify/replaced [OPEN] | TZ-MID-68-WPR2-151117 To be clean weld slag and touch up paint at the panel support. [OPEN] | TZ-MID-68-WPR2-151117 Perform cleanning internal and external of the panel [OPEN]
T-00028-0477 | PS5-61-IG-0043 | CPX15 - Distribution Board | E | PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-0043 | To be completed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  |  | TZ-MID-68-WPR2-151117 To be clean weld slag and touch up paint at the panel support. [OPEN] | TZ-MID-68-WPR2-151117 Perform cleanning internal and external of the panel [OPEN]
T-00028-0478 | PS5-74-IG-5101 | CPX15 - Distribution Board | E | PS5-74-01 - N2 Generation Skid | To be completed
T-00028-0479 | PS5-79-IG-0001 | CPX15 - Distribution Board | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | Started (not Completed) | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151115 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00028-0480 | PS5-79-IG-0002 | CPX15 - Distribution Board | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151115 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00028-0481 | PS5-79-IG-0003 | CPX15 - Distribution Board | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00028-0482 | PS5-79-IG-0004 | CPX15 - Distribution Board | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00028-0483 | PS5-79-IG-0005 | CPX15 - Distribution Board | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug [OPEN] | TZ-MID-68-WPR2-151117 Need install seam plate to the gap between concrete foundation and frame support of DB Panel [OPEN] | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00028-0484 | PS5-79-IG-0006 | CPX15 - Distribution Board | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug [OPEN] | TZ-MID-68-WPR2-151117 Need install seam plate to the gap between concrete foundation and frame support of DB Panel [OPEN] | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00028-0485 | PS5-79-IG-0007 | CPX15 - Distribution Board | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00028-0486 | PS5-79-IG-0008 | CPX15 - Distribution Board | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00028-0487 | PS5-79-IG-0009 | CPX15 - Distribution Board | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00028-0488 | PS5-79-IG-0010 | CPX15 - Distribution Board | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00028-0489 | PS5-79-IG-0011 | CPX15 - Distribution Board | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151118 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151118 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00028-0490 | PS5-79-IG-0012 | CPX15 - Distribution Board | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00029-0234 | PS5-06-GU-0003A | CPX16 - Charger/Inverter | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed
T-00029-0235 | PS5-06-GU-0003B | CPX16 - Charger/Inverter | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed
T-00029-0236 | PS5-06-GU-0003C | CPX16 - Charger/Inverter | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed
T-00031-1264 |  | CPX18 - Lighting Circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00031-1265 |  | CPX18 - Lighting Circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00031-1266 |  | CPX18 - Lighting Circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00031-1267 |  | CPX18 - Lighting Circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00031-1268 |  | CPX18 - Lighting Circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00031-1269 |  | CPX18 - Lighting Circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00031-1270 |  | CPX18 - Lighting Circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00031-1271 |  | CPX18 - Lighting Circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00031-1272 |  | CPX18 - Lighting Circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00031-1273 |  | CPX18 - Lighting Circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00031-1274 |  | CPX18 - Lighting Circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00031-1275 |  | CPX18 - Lighting Circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00031-1277 |  | CPX18 - Lighting Circuits | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00031-1278 |  | CPX18 - Lighting Circuits | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00031-1279 |  | CPX18 - Lighting Circuits | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00031-1280 |  | CPX18 - Lighting Circuits | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00031-1281 |  | CPX18 - Lighting Circuits | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | To be completed
T-00031-1282 |  | CPX18 - Lighting Circuits | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | To be completed
T-00031-1283 |  | CPX18 - Lighting Circuits | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | To be completed
T-00031-1284 |  | CPX18 - Lighting Circuits | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | To be completed
T-00031-1285 |  | CPX18 - Lighting Circuits | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | To be completed
T-00031-1286 |  | CPX18 - Lighting Circuits | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | To be completed
T-00031-1287 |  | CPX18 - Lighting Circuits | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | To be completed
T-00031-1288 |  | CPX18 - Lighting Circuits | E | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | To be completed
T-00031-1289 |  | CPX18 - Lighting Circuits | E | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | To be completed
T-00031-1290 |  | CPX18 - Lighting Circuits | E | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | To be completed
T-00031-1291 |  | CPX18 - Lighting Circuits | E | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | To be completed
T-00031-1292 |  | CPX18 - Lighting Circuits | E | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | To be completed
T-00031-1294 |  | CPX18 - Lighting Circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00031-1295 |  | CPX18 - Lighting Circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00031-1296 |  | CPX18 - Lighting Circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00031-1297 |  | CPX18 - Lighting Circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00031-1298 |  | CPX18 - Lighting Circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00031-1299 |  | CPX18 - Lighting Circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00031-1300 |  | CPX18 - Lighting Circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00031-1301 |  | CPX18 - Lighting Circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00031-1302 |  | CPX18 - Lighting Circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00031-1303 |  | CPX18 - Lighting Circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00031-1304 |  | CPX18 - Lighting Circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | Started (not Completed)
T-00031-1305 |  | CPX18 - Lighting Circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00031-1306 |  | CPX18 - Lighting Circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00031-1307 |  | CPX18 - Lighting Circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00031-1308 |  | CPX18 - Lighting Circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00031-1309 |  | CPX18 - Lighting Circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00031-1310 |  | CPX18 - Lighting Circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00031-1311 |  | CPX18 - Lighting Circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00031-1312 |  | CPX18 - Lighting Circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00031-1313 |  | CPX18 - Lighting Circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00031-1314 |  | CPX18 - Lighting Circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00031-1315 |  | CPX18 - Lighting Circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | To be completed
T-00031-1318 |  | CPX18 - Lighting Circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | To be completed
T-00031-1320 |  | CPX18 - Lighting Circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | To be completed
T-00031-1322 |  | CPX18 - Lighting Circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | To be completed
T-00031-1323 |  | CPX18 - Lighting Circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | To be completed
T-00031-1325 |  | CPX18 - Lighting Circuits | E | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010 | To be completed
T-00031-1326 |  | CPX18 - Lighting Circuits | E | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010 | To be completed
T-00031-1327 |  | CPX18 - Lighting Circuits | E | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010 | To be completed
T-00031-1328 |  | CPX18 - Lighting Circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00031-1329 |  | CPX18 - Lighting Circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00031-1330 |  | CPX18 - Lighting Circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00031-1331 |  | CPX18 - Lighting Circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00031-1332 |  | CPX18 - Lighting Circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00031-1333 |  | CPX18 - Lighting Circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00031-1334 |  | CPX18 - Lighting Circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00031-1335 |  | CPX18 - Lighting Circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00031-1336 |  | CPX18 - Lighting Circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00031-1337 |  | CPX18 - Lighting Circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00031-1338 |  | CPX18 - Lighting Circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00031-1339 |  | CPX18 - Lighting Circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00031-1340 |  | CPX18 - Lighting Circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00031-1341 |  | CPX18 - Lighting Circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00031-1342 |  | CPX18 - Lighting Circuits | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed
T-00031-1343 |  | CPX18 - Lighting Circuits | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed
T-00031-1344 |  | CPX18 - Lighting Circuits | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed
T-00031-1345 |  | CPX18 - Lighting Circuits | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed
T-00031-1346 |  | CPX18 - Lighting Circuits | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed
T-00031-1347 |  | CPX18 - Lighting Circuits | E | PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111 | To be completed
T-00031-1348 |  | CPX18 - Lighting Circuits | E | PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112 | To be completed
T-00031-1349 |  | CPX18 - Lighting Circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00031-1350 |  | CPX18 - Lighting Circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00031-1351 |  | CPX18 - Lighting Circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00031-1352 |  | CPX18 - Lighting Circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00031-1353 |  | CPX18 - Lighting Circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00031-1354 |  | CPX18 - Lighting Circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00031-1355 |  | CPX18 - Lighting Circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00031-1356 |  | CPX18 - Lighting Circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00031-1357 |  | CPX18 - Lighting Circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00031-1358 |  | CPX18 - Lighting Circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00031-1359 |  | CPX18 - Lighting Circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00031-1360 |  | CPX18 - Lighting Circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00031-1361 |  | CPX18 - Lighting Circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00031-1362 |  | CPX18 - Lighting Circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00031-1363 |  | CPX18 - Lighting Circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00031-1364 |  | CPX18 - Lighting Circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00031-1365 |  | CPX18 - Lighting Circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00031-1366 |  | CPX18 - Lighting Circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00031-1367 |  | CPX18 - Lighting Circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00031-1368 |  | CPX18 - Lighting Circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00031-1369 |  | CPX18 - Lighting Circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00031-1370 |  | CPX18 - Lighting Circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00031-1371 |  | CPX18 - Lighting Circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00031-1372 |  | CPX18 - Lighting Circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00031-1373 |  | CPX18 - Lighting Circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00031-1374 |  | CPX18 - Lighting Circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00031-1375 |  | CPX18 - Lighting Circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00031-1376 |  | CPX18 - Lighting Circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00031-1377 |  | CPX18 - Lighting Circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00031-1378 |  | CPX18 - Lighting Circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00031-1379 |  | CPX18 - Lighting Circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00032-0165 | PS5-25-UD-3100A | CPX19 - Power Socket Outlet | E | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00032-0166 | PS5-28-ISO-2008 | CPX19 - Power Socket Outlet | E | PS5-28-10 - Oil Skimmer Package | To be completed
T-00032-0438 |  | CPX19 - Power Socket Outlet | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00032-0439 |  | CPX19 - Power Socket Outlet | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00032-0440 |  | CPX19 - Power Socket Outlet | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00032-0441 |  | CPX19 - Power Socket Outlet | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00032-0442 |  | CPX19 - Power Socket Outlet | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00032-0443 |  | CPX19 - Power Socket Outlet | E | PS5-06-05 - AC UPS - Workshop & Warehouse | To be completed
T-00032-0444 |  | CPX19 - Power Socket Outlet | E | PS5-06-05 - AC UPS - Workshop & Warehouse | To be completed
T-00032-0445 |  | CPX19 - Power Socket Outlet | E | PS5-06-05 - AC UPS - Workshop & Warehouse | To be completed
T-00032-0446 |  | CPX19 - Power Socket Outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00032-0447 |  | CPX19 - Power Socket Outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00032-0448 |  | CPX19 - Power Socket Outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00032-0449 |  | CPX19 - Power Socket Outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00032-0450 |  | CPX19 - Power Socket Outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00032-0451 |  | CPX19 - Power Socket Outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00032-0452 |  | CPX19 - Power Socket Outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00032-0453 |  | CPX19 - Power Socket Outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00032-0454 |  | CPX19 - Power Socket Outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00032-0455 |  | CPX19 - Power Socket Outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00032-0456 |  | CPX19 - Power Socket Outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00032-0457 |  | CPX19 - Power Socket Outlet | E | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010 | To be completed
T-00032-0458 |  | CPX19 - Power Socket Outlet | E | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010 | To be completed
T-00032-0459 |  | CPX19 - Power Socket Outlet | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed
T-00032-0460 |  | CPX19 - Power Socket Outlet | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed
T-00032-0461 |  | CPX19 - Power Socket Outlet | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed
T-00032-0462 |  | CPX19 - Power Socket Outlet | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed
T-00032-0463 |  | CPX19 - Power Socket Outlet | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed
T-00032-0464 |  | CPX19 - Power Socket Outlet | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed
T-00032-0465 |  | CPX19 - Power Socket Outlet | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed
T-00032-0466 |  | CPX19 - Power Socket Outlet | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed
T-00032-0467 |  | CPX19 - Power Socket Outlet | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00032-0468 |  | CPX19 - Power Socket Outlet | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00032-0469 |  | CPX19 - Power Socket Outlet | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00032-0470 |  | CPX19 - Power Socket Outlet | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed
T-00032-0471 |  | CPX19 - Power Socket Outlet | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed
T-00032-0472 |  | CPX19 - Power Socket Outlet | E | PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111 | To be completed
T-00032-0473 |  | CPX19 - Power Socket Outlet | E | PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111 | To be completed
T-00032-0474 |  | CPX19 - Power Socket Outlet | E | PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112 | To be completed
T-00032-0475 |  | CPX19 - Power Socket Outlet | E | PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112 | To be completed
T-00033-0044 | PS5-28-HE-2100 | CPX20 - Heater | E | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00033-0045 | PS5-28-HE-2200 | CPX20 - Heater | E | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00033-0046 | PS5-71-HE-2200 | CPX20 - Heater | E | PS5-71-12 - CFO Service Tank | To be completed
T-00033-0047 | PS5-71-HE-2300 | CPX20 - Heater | E | PS5-71-04 - CFO Storage Tank | To be completed
T-00033-0048 | PS5-71-HE-2400A | CPX20 - Heater | E | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00033-0049 | PS5-71-HE-2400B | CPX20 - Heater | E | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00033-0068 | PS5-25-HE-2100 | CPX20 - Heater | E | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00033-0069 | PS5-25-HE-2200 | CPX20 - Heater | E | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00033-0070 | PS5-25-HE-2300 | CPX20 - Heater | E | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00034-0041 | PS5-61-NER-0010 | CPX21 - Neutral Earthing Resistor | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed
T-00034-0042 | PS5-61-NER-0011 | CPX21 - Neutral Earthing Resistor | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed
T-00034-0043 | PS5-63-NER-0010 | CPX21 - Neutral Earthing Resistor | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed
T-00034-0044 | PS5-63-NER-0011 | CPX21 - Neutral Earthing Resistor | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed
T-00034-0059 | PS5-60-IJ-0001A | CPX21 - Neutral Earthing Resistor | E | PS5-60-01 - Power Generation Package A | To be completed
T-00034-0060 | PS5-60-IJ-0001B | CPX21 - Neutral Earthing Resistor | E | PS5-60-04 - Power Generation Package B | To be completed
T-00034-0061 | PS5-60-IJ-0001C | CPX21 - Neutral Earthing Resistor | E | PS5-60-07 - Power Generation Package C | To be completed
T-00034-0062 | PS5-60-IJ-0001D | CPX21 - Neutral Earthing Resistor | E | PS5-60-10 - Power Generation Package D | To be completed
T-00034-0063 | PS5-60-IJ-0001E | CPX21 - Neutral Earthing Resistor | E | PS5-60-13 - Power Generation Package E | To be completed
T-00034-0064 | PS5-60-IJ-0001F | CPX21 - Neutral Earthing Resistor | E | PS5-60-16 - Power Generation Package F | To be completed
T-00034-0065 | PS5-60-IJ-0001G | CPX21 - Neutral Earthing Resistor | E | PS5-60-19 - Power Generation Package G | To be completed
T-00035-1357 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1358 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1359 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1360 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1361 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1362 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1363 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1364 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1365 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1366 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1367 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1368 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1369 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1370 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1371 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1372 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1373 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1374 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1375 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1376 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1377 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1378 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1379 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1380 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1381 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1382 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1383 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1384 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1385 |  | CPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00035-1386 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1387 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1388 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1389 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1390 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1391 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1392 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1393 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1394 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1395 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1396 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1397 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1398 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1399 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1400 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1401 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1402 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1403 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1404 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1405 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1406 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1407 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1408 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1409 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1410 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1411 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1412 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1413 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1414 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1415 |  | CPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00035-1416 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1417 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1418 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1419 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1420 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1421 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1422 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1423 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1424 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1425 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1426 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1427 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1428 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1429 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1430 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1431 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1432 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1433 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1434 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1435 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1436 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1437 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1438 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1439 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1440 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1441 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1442 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1443 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1444 |  | CPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00035-1445 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1446 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1447 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1448 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1449 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1450 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1451 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1452 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1453 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1454 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1455 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1456 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1457 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1458 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1459 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1460 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1461 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1462 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1463 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1464 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1465 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1466 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1467 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1468 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1469 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1470 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1471 |  | CPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00035-1472 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1473 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1474 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1475 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1476 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1477 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1478 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1479 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1480 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1481 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1482 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1483 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1484 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1485 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1486 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1487 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1488 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1489 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1490 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1491 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1492 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1493 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1494 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1495 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1496 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1497 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1498 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1499 |  | CPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00035-1500 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1501 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1502 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1503 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1504 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1505 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1506 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1507 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1508 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1509 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1510 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1511 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1512 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1513 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1514 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1515 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1516 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1517 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1518 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1519 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1520 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1521 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1522 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1523 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1524 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1525 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1526 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1527 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1528 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1529 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1530 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1531 |  | CPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00035-1532 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1533 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1534 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1535 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1536 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1537 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1538 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1539 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1540 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1541 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1542 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1543 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1544 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1545 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1546 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1547 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1548 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1549 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1550 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1551 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1552 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1553 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1554 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1555 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1556 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1557 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1558 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1559 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1560 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1561 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1562 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1563 |  | CPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00035-1564 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1565 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1566 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1567 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1568 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1569 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1570 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1571 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1572 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1573 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1574 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1575 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1576 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1577 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1578 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1579 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1580 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1581 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1582 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1583 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1584 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1585 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1586 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1587 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1588 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1589 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1590 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1591 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1592 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1593 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1594 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1595 |  | CPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00035-1596 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1597 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1598 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1599 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1600 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1601 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1602 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1603 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1604 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1605 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1606 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1607 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1608 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1609 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1610 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1611 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1612 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1613 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1614 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1615 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1616 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1617 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1618 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1619 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1620 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1621 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1622 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1623 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1624 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1625 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1626 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1627 |  | CPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00035-1628 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1629 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1630 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1631 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1632 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1633 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1634 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1635 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1636 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1637 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1638 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1639 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1640 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1641 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1642 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1643 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1644 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1645 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1646 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1647 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1648 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1649 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1650 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1651 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1652 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1653 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1654 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1655 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1656 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1657 |  | CPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00035-1658 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1659 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1660 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1661 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1662 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1663 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1664 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1665 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1666 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1667 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1668 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1669 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1670 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1671 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1672 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1673 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1674 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1675 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1676 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1677 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1678 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1679 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1680 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1681 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1682 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1683 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1684 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1685 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1686 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1687 |  | CPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00035-1688 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1689 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1690 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1691 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1692 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1693 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1694 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1695 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1696 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1697 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1698 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1699 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1700 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1701 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1702 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1703 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1704 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1705 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1706 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1707 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1708 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1709 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1710 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1711 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1712 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1713 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1714 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1715 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1716 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1717 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1718 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1719 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1720 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1721 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00035-1722 |  | CPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00039-0283 | PS5 - CFO AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Submitted
T-00039-0284 | PS5 - CHEMICAL AND WASTE STORAGE AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Submitted
T-00039-0285 | PS5 - CLOSED DRAIN DRUM AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Submitted
T-00039-0286 | PS5 - DIESEL FUEL STORAGE AND PUMP AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Submitted
T-00039-0287 | PS5 - EXPORT PUMP VSD AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Submitted
T-00039-0288 | PS5 - EXPORT LOADING PUMP AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Submitted
T-00039-0289 | PS5 - FENCE EAST AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00039-0290 | PS5 - FENCE SOUTH WEST AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00039-0291 | PS5 - FENCE WEST AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Submitted
T-00039-0292 | PS5 - FENCE SOUTH EAST AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00039-0293 | PS5 - LAUNCHER/RECEIVER AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Submitted
T-00039-0294 | PS5 - OBSERVATION BASIN AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00039-0295 | PS5 - POWER DISTRIBUTION AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Submitted
T-00039-0296 | PS5 - POWER GENERATION BUILDING AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Submitted
T-00039-0297 | PS5 - POWER GENERATION COOLING TOWER AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Submitted
T-00039-0298 | PS5 - TURNSTILE GATE AND OFFICE BUILDING AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00039-0299 | PS5 - UTILITY AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Submitted
T-00039-0300 | PS5 - UTILITY/FIRE WATER STORAGE TANK AREA_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Submitted
T-00039-0301 | PS5-82-OB-0001_Earthing | CPX26 - Earthing system | E | PS5-63-02 - Electrical Earthing - Office and Facilities building | To be completed
T-00039-0302 | PS5-82-OB-0005_Earthing | CPX26 - Earthing system | E | PS5-63-06 - Electrical Earthing - Guard House | To be completed
T-00039-0303 | PS5-82-OB-0009A_Earthing | CPX26 - Earthing system | E | PS5-63-05 - Electrical Earthing - Guard Hut A & B | To be completed
T-00039-0304 | PS5-82-OB-0009B_Earthing | CPX26 - Earthing system | E | PS5-63-05 - Electrical Earthing - Guard Hut A & B | To be completed
T-00039-0306 | PS5-84-OB-0001_Earthing | CPX26 - Earthing system | E | PS5-63-07 - Electrical Earthing - Workshop & Warehouse | To be completed
T-00039-0307 | PS5-84-OB-0003_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Submitted
T-00039-0308 | PS5-84-OB-0004_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Submitted
T-00039-0309 | PS5-84-OB-0005_Earthing | CPX26 - Earthing system | E | PS5-63-03 - Electrical Earthing - Generator Building | To be completed
T-00039-0310 | PS5-84-OB-0006_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Started (not Completed)
T-00039-0311 | PS5-84-OB-0007_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Submitted
T-00039-0312 | PS5-86-OB-0001_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00039-0313 | PS5-86-OB-0002_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00039-0314 | PS5-86-OB-0003_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00039-0315 | PS5-86-OB-0004_Earthing | CPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00040-0052 | PS5 - RECEIVER AND LAUNCHER AREA_Lightning | CPX28 - Lightning protection system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00040-0053 | PS5-82-OB-0001_Lightning | CPX28 - Lightning protection system | E | PS5-63-02 - Electrical Earthing - Office and Facilities building | To be completed
T-00040-0054 | PS5-82-OB-0005_Lightning | CPX28 - Lightning protection system | E | PS5-63-06 - Electrical Earthing - Guard House | To be completed
T-00040-0055 | PS5-82-OB-0009A_Lightning | CPX28 - Lightning protection system | E | PS5-63-05 - Electrical Earthing - Guard Hut A & B | To be completed
T-00040-0056 | PS5-82-OB-0009B_Lightning | CPX28 - Lightning protection system | E | PS5-63-05 - Electrical Earthing - Guard Hut A & B | To be completed
T-00040-0057 | PS5-84-OB-0001_Lightning | CPX28 - Lightning protection system | E | PS5-63-07 - Electrical Earthing - Workshop & Warehouse | To be completed
T-00040-0058 | PS5-84-OB-0003_Lightning | CPX28 - Lightning protection system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00040-0059 | PS5-84-OB-0005_Lightning | CPX28 - Lightning protection system | E | PS5-63-03 - Electrical Earthing - Generator Building | To be completed
T-00040-0060 | PS5-84-OB-0006_Lightning | CPX28 - Lightning protection system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00040-0061 | PS5-84-OB-0007_Lightning | CPX28 - Lightning protection system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00040-0062 | PS5-86-OB-0001_Lightning | CPX28 - Lightning protection system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00040-0063 | PS5-86-OB-0002_Lightning | CPX28 - Lightning protection system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00040-0064 | PS5-86-OB-0003_Lightning | CPX28 - Lightning protection system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00040-0065 | PS5-86-OB-0004_Lightning | CPX28 - Lightning protection system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00041-0026 | PS5-82-OB-0001 | CPX29 - MCT cabling | E | PS5-82-05 - Office and Facilities building | To be completed
T-00041-0027 | PS5-82-OB-0005 | CPX29 - MCT cabling | E | PS5-82-06 - Guard House Building | To be completed
T-00041-0028 | PS5-84-OB-0005 | CPX29 - MCT cabling | E | PS5-84-01 - Generator Building | To be completed
T-00042-0142 | PS5_AREA_COMPLETION_FOR_BUILDING_AREA_-_NORTH | CPX30 - Cable tray / ladder | E | PS5-99-01 - Area Completion for Building area | To be completed
T-00042-0143 | PS5_AREA_COMPLETION_FOR_BUILDING_AREA_-_NORTH_WEST | CPX30 - Cable tray / ladder | E | PS5-99-01 - Area Completion for Building area | To be completed
T-00042-0144 | PS5_AREA_COMPLETION_FOR_CFO_AREA | CPX30 - Cable tray / ladder | E | PS5-99-05 - Area Completion for CFO area | To be completed
T-00042-0145 | PS5_AREA_COMPLETION_FOR_POWER_DISTRIBUTION_AREA | CPX30 - Cable tray / ladder | E | PS5-99-03 - Area Completion for Power Distribution area | To be completed
T-00042-0146 | PS5_AREA_COMPLETION_FOR_POWER_GENERATION_AREA | CPX30 - Cable tray / ladder | E | PS5-99-06 - Area Completion for Power Generation area | To be completed
T-00042-0147 | PS5_AREA_COMPLETION_FOR_PROCESS_AREA | CPX30 - Cable tray / ladder | E | PS5-99-04 - Area Completion for Process area | To be completed
T-00042-0148 | PS5_AREA_COMPLETION_FOR_PROCESS_AREA_-_NORTH | CPX30 - Cable tray / ladder | E | PS5-99-04 - Area Completion for Process area | To be completed
T-00042-0149 | PS5_AREA_COMPLETION_FOR_PROCESS_AREA_SOUTH | CPX30 - Cable tray / ladder | E | PS5-99-04 - Area Completion for Process area | To be completed
T-00042-0150 | PS5_AREA_COMPLETION_FOR_UTILITY_AREA | CPX30 - Cable tray / ladder | E | PS5-99-02 - Area Completion for Utility area | To be completed
T-00042-0167 | PS5-82-OB-0001 | CPX30 - Cable tray / ladder | E | PS5-82-05 - Office and Facilities building | To be completed
T-00042-0168 | PS5-82-OB-0005 | CPX30 - Cable tray / ladder | E | PS5-82-06 - Guard House Building | To be completed
T-00042-0169 | PS5-84-OB-0005 | CPX30 - Cable tray / ladder | E | PS5-84-01 - Generator Building | To be completed
T-00042-0208 | PS5-83-OB-0001_Installation | CPX30 - Cable tray / ladder | E | PS5-83-01 - EITS Building | Submitted
T-00043-0045 | PS5-79-BH-0001 | CPX31 - Junction and marshalling box | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed
T-00043-0046 | PS5-79-BH-0002 | CPX31 - Junction and marshalling box | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed
T-00043-0073 | PS5-05-BE-0001 | CPX31 - Junction and marshalling box | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed
T-00044-0090 | PS5-60-IE-0003A | CPX32 - Console / control panel | E | PS5-60-02 - Power Gen Package A (UCP) | To be completed
T-00044-0091 | PS5-60-IE-0003B | CPX32 - Console / control panel | E | PS5-60-05 - Power Gen Package B (UCP) | To be completed
T-00044-0092 | PS5-60-IE-0003C | CPX32 - Console / control panel | E | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00044-0093 | PS5-60-IE-0003D | CPX32 - Console / control panel | E | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00044-0094 | PS5-60-IE-0003E | CPX32 - Console / control panel | E | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00044-0095 | PS5-60-IE-0003F | CPX32 - Console / control panel | E | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00044-0096 | PS5-60-IE-0003G | CPX32 - Console / control panel | E | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00044-0097 | PS5-60-IE-0004 | CPX32 - Console / control panel | E | PS5-60-22 - Power Gen Master UCP | To be completed
T-00044-0098 | PS5-60-IH-0001A | CPX32 - Console / control panel | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-332-13-0424
T-00044-0099 | PS5-60-IH-0001B | CPX32 - Console / control panel | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-332-13-0424
T-00044-0100 | PS5-60-IH-0001C | CPX32 - Console / control panel | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-332-13-0424
T-00044-0101 | PS5-60-IH-0001D | CPX32 - Console / control panel | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-332-13-0424
T-00044-0102 | PS5-60-IH-0001E | CPX32 - Console / control panel | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-332-13-0424
T-00044-0103 | PS5-60-IH-0001F | CPX32 - Console / control panel | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-332-13-0424
T-00044-0104 | PS5-60-IH-0001G | CPX32 - Console / control panel | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-332-13-0424
T-00044-0105 | PS5-60-IH-0002 | CPX32 - Console / control panel | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-332-13-0424
T-00044-0106 | PS5-60-IE-0002A | CPX32 - Console / control panel | E | PS5-60-01 - Power Generation Package A | To be completed
T-00044-0107 | PS5-60-IE-0002B | CPX32 - Console / control panel | E | PS5-60-04 - Power Generation Package B | To be completed
T-00044-0108 | PS5-60-IE-0002C | CPX32 - Console / control panel | E | PS5-60-07 - Power Generation Package C | To be completed
T-00044-0109 | PS5-60-IE-0002D | CPX32 - Console / control panel | E | PS5-60-10 - Power Generation Package D | To be completed
T-00044-0110 | PS5-60-IE-0002E | CPX32 - Console / control panel | E | PS5-60-13 - Power Generation Package E | To be completed
T-00044-0111 | PS5-60-IE-0002F | CPX32 - Console / control panel | E | PS5-60-16 - Power Generation Package F | To be completed
T-00044-0112 | PS5-60-IE-0002G | CPX32 - Console / control panel | E | PS5-60-19 - Power Generation Package G | To be completed
T-00044-0175 | PS5-01-IE-0001A | CPX32 - Console / control panel | E | PS5-01-05 - Foam Skid | To be completed
T-00044-0176 | PS5-01-IE-0001B | CPX32 - Console / control panel | E | PS5-01-05 - Foam Skid | To be completed
T-00044-0177 | PS5-01-IE-0002A | CPX32 - Console / control panel | E | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00044-0178 | PS5-01-IE-0002B | CPX32 - Console / control panel | E | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00044-0179 | PS5-01-IE-0009A | CPX32 - Console / control panel | E | PS5-01-02 - Fire Water Pump A | To be completed
T-00044-0180 | PS5-01-IE-0009B | CPX32 - Console / control panel | E | PS5-01-03 - Fire Water Pump B | To be completed
T-00044-0183 | PS5-50-IE-0001 | CPX32 - Console / control panel | E | PS5-50-01 - Water Well Submersible Pumps (3100) | To be completed
T-00044-0184 | PS5-50-IE-0002 | CPX32 - Console / control panel | E | PS5-50-02 - Water Well Submersible Pumps (3200) | To be completed
T-00044-0185 | PS5-60-IN-0002A | CPX32 - Console / control panel | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed
T-00044-0186 | PS5-60-IN-0002B | CPX32 - Console / control panel | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed
T-00044-0187 | PS5-60-IN-0002C | CPX32 - Console / control panel | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00044-0188 | PS5-60-IN-0002D | CPX32 - Console / control panel | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00044-0189 | PS5-60-IN-0002E | CPX32 - Console / control panel | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00044-0190 | PS5-60-IN-0002F | CPX32 - Console / control panel | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00044-0191 | PS5-60-IN-0002G | CPX32 - Console / control panel | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00044-0192 | PS5-61-IH-0004 | CPX32 - Console / control panel | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00044-0193 | PS5-61-IH-0004A | CPX32 - Console / control panel | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00044-0194 | PS5-61-IH-0004B | CPX32 - Console / control panel | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00044-0197 | PS5-71-IN-0001 | CPX32 - Console / control panel | E | PS5-71-19 - Diesel Separator Module (UCP) | To be completed
T-00044-0198 | PS5-71-IN-0002 | CPX32 - Console / control panel | E | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | To be completed
T-00044-0199 | PS5-71-IN-0003 | CPX32 - Console / control panel | E | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed
T-00044-0200 | PS5-71-IN-0004A | CPX32 - Console / control panel | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00044-0201 | PS5-71-IN-0004B | CPX32 - Console / control panel | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00044-0267 | PS5-09-LB-0008 | CPX32 - Console / control panel | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00044-0268 | PS5-61-IH-0004C | CPX32 - Console / control panel | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00044-0269 | PS5-61-IH-0004D | CPX32 - Console / control panel | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00044-0279 | PS5-09-LB-7001 | CPX32 - Console / control panel | E | PS5-09-02 - HVAC for Guard House | To be completed
T-00045-0008 | PS5-53-TR-4100 | CPX33 - Cathodic protection | E | PS5-53-01 - Utility Water / Storage Tank | To be completed
T-00045-0009 | PS5-71-TR-4100 | CPX33 - Cathodic protection | E | PS5-71-04 - CFO Storage Tank | To be completed
T-00045-0010 | PS5-71-TR-4200 | CPX33 - Cathodic protection | E | PS5-71-12 - CFO Service Tank | To be completed
T-00045-0011 | PS5-71-TR-4400 | CPX33 - Cathodic protection | E | PS5-71-15 - Diesel Fuel Storage Tank | To be completed
T-00046-0013 | PS5-01-UK-6100 | CZX01E - Package | E | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | Started (not Completed)
T-00046-0014 | PS5-01-UV-8700 | CZX01E - Package | E | PS5-01-05 - Foam Skid | To be completed
T-00046-0295 | PS5-60-UR-8100E | CZX01E - Package | E | PS5-60-13 - Power Generation Package E | To be completed
T-00046-0296 | PS5-60-UR-8100F | CZX01E - Package | E | PS5-60-16 - Power Generation Package F | To be completed
T-00046-0297 | PS5-60-UR-8100G | CZX01E - Package | E | PS5-60-19 - Power Generation Package G | To be completed
T-00046-0298 | PS5-05-UR-8100 | CZX01E - Package | E | PS5-05-01 - Emergency Diesel Generator Package | To be completed
T-00046-0299 | PS5-71-UZ-6200 | CZX01E - Package | E | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | To be completed
T-00046-0305 | PS5-60-UO-81100E | CZX01E - Package | E | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | To be completed
T-00046-0306 | PS5-60-UO-81100F | CZX01E - Package | E | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | To be completed
T-00046-0307 | PS5-60-UO-81100G | CZX01E - Package | E | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | To be completed
T-00046-0312 | PS5-60-UZ-8200E | CZX01E - Package | E | PS5-60-39 - Injector Tip Cooling Module E | To be completed
T-00046-0313 | PS5-60-UZ-8200F | CZX01E - Package | E | PS5-60-40 - Injector Tip Cooling Module F | To be completed
T-00046-0318 | PS5-60-VS-9100E | CZX01E - Package | E | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | To be completed
T-00046-0319 | PS5-60-VS-9100F | CZX01E - Package | E | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | To be completed
T-00046-0320 | PS5-60-VS-9100G | CZX01E - Package | E | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | To be completed
T-00046-0324 | PS5-01-UZ-6900 | CZX01E - Package | E | PS5-01-10 - Water Mist Package | To be completed
T-00046-0325 | PS5-53-UT-8100 | CZX01E - Package | E | PS5-50-03 - Water Pre-Treatment Package | To be completed
T-00046-0326 | PS5-53-UT-8200 | CZX01E - Package | E | PS5-53-04 - Water Treatment Purification Package | To be completed
T-00046-0333 | PS5-60-EA-21100E | CZX01E - Package | E | PS5-60-13 - Power Generation Package E | To be completed
T-00046-0334 | PS5-60-EA-21100F | CZX01E - Package | E | PS5-60-16 - Power Generation Package F | To be completed
T-00046-0335 | PS5-60-EA-21100G | CZX01E - Package | E | PS5-60-19 - Power Generation Package G | To be completed
T-00046-0340 | PS5-60-EA-21200E | CZX01E - Package | E | PS5-60-13 - Power Generation Package E | To be completed
T-00046-0341 | PS5-60-EA-21200F | CZX01E - Package | E | PS5-60-16 - Power Generation Package F | To be completed
T-00046-0342 | PS5-60-EA-21200G | CZX01E - Package | E | PS5-60-19 - Power Generation Package G | To be completed
T-00046-0349 | PS5-60-EA-2500A | CZX01E - Package | E | PS5-60-74 - Engine E Cooling system | To be completed
T-00046-0350 | PS5-60-EA-2500B | CZX01E - Package | E | PS5-60-74 - Engine E Cooling system | To be completed
T-00046-0351 | PS5-60-EA-2600A | CZX01E - Package | E | PS5-60-75 - Engine F Cooling system | To be completed
T-00046-0352 | PS5-60-EA-2600B | CZX01E - Package | E | PS5-60-75 - Engine F Cooling system | To be completed
T-00046-0353 | PS5-60-EA-2700A | CZX01E - Package | E | PS5-60-76 - Engine G Cooling system | To be completed
T-00046-0354 | PS5-60-EA-2700B | CZX01E - Package | E | PS5-60-76 - Engine G Cooling system | To be completed
T-00046-0359 | PS5-60-EA-2800E | CZX01E - Package | E | PS5-60-39 - Injector Tip Cooling Module E | To be completed
T-00046-0360 | PS5-60-EA-2800F | CZX01E - Package | E | PS5-60-40 - Injector Tip Cooling Module F | To be completed
T-00046-0361 | PS5-60-EA-2800G | CZX01E - Package | E | PS5-60-41 - Injector Tip Cooling Module G | To be completed
T-00046-0366 | PS5-60-EA-2900E | CZX01E - Package | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00046-0367 | PS5-60-EA-2900F | CZX01E - Package | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00046-0368 | PS5-60-EA-2900G | CZX01E - Package | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00046-0372 | PS5-60-TCV-0001D | CZX01E - Package | E | PS5-60-73 - Engine D Cooling system | To be completed
T-00046-0373 | PS5-60-TCV-0001E | CZX01E - Package | E | PS5-60-74 - Engine E Cooling system | To be completed
T-00046-0374 | PS5-60-TCV-0001F | CZX01E - Package | E | PS5-60-75 - Engine F Cooling system | To be completed
T-00046-0375 | PS5-60-TCV-0001G | CZX01E - Package | E | PS5-60-76 - Engine G Cooling system | To be completed
T-00046-0376 | PS5-60-TCV-0002A | CZX01E - Package | E | PS5-60-70 - Engine A Cooling system | To be completed
T-00046-0377 | PS5-60-TCV-0002B | CZX01E - Package | E | PS5-60-71 - Engine B Cooling system | To be completed
T-00046-0378 | PS5-60-TCV-0002C | CZX01E - Package | E | PS5-60-72 - Engine C Cooling system | To be completed
T-00046-0379 | PS5-60-TCV-0002D | CZX01E - Package | E | PS5-60-73 - Engine D Cooling system | To be completed
T-00046-0380 | PS5-60-TCV-0002E | CZX01E - Package | E | PS5-60-74 - Engine E Cooling system | To be completed
T-00046-0381 | PS5-60-TCV-0002F | CZX01E - Package | E | PS5-60-75 - Engine F Cooling system | To be completed
T-00046-0382 | PS5-60-TCV-0002G | CZX01E - Package | E | PS5-60-76 - Engine G Cooling system | To be completed
T-00046-0383 | PS5-60-UA-5200 | CZX01E - Package | E | PS5-60-26 - Instrument Air Compressor Skid | To be completed
T-00046-0384 | PS5-60-UR-8200A | CZX01E - Package | E | PS5-60-01 - Power Generation Package A | To be completed
T-00046-0385 | PS5-60-UR-8200B | CZX01E - Package | E | PS5-60-04 - Power Generation Package B | To be completed
T-00046-0386 | PS5-60-UR-8200C | CZX01E - Package | E | PS5-60-07 - Power Generation Package C | To be completed
T-00046-0387 | PS5-60-UR-8200D | CZX01E - Package | E | PS5-60-10 - Power Generation Package D | To be completed
T-00046-0388 | PS5-60-UR-8200E | CZX01E - Package | E | PS5-60-13 - Power Generation Package E | To be completed
T-00046-0389 | PS5-60-UR-8200F | CZX01E - Package | E | PS5-60-16 - Power Generation Package F | To be completed
T-00046-0390 | PS5-60-UR-8200G | CZX01E - Package | E | PS5-60-19 - Power Generation Package G | To be completed
T-00046-0391 | PS5-60-UZ-8200G | CZX01E - Package | E | PS5-60-41 - Injector Tip Cooling Module G | To be completed
T-00046-0392 | PS5-60-UZ-8900A | CZX01E - Package | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed
T-00046-0393 | PS5-60-UZ-8900B | CZX01E - Package | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed
T-00046-0394 | PS5-60-UZ-8900C | CZX01E - Package | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00046-0395 | PS5-60-UZ-8900D | CZX01E - Package | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00046-0396 | PS5-60-UZ-8900E | CZX01E - Package | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00046-0397 | PS5-60-UZ-8900F | CZX01E - Package | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00046-0398 | PS5-60-UZ-8900G | CZX01E - Package | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00046-0399 | PS5-71-UN-7200 | CZX01E - Package | E | PS5-71-02 - CFO Allocation Metering Package | To be completed
T-00046-0400 | PS5-71-UZ-6400 | CZX01E - Package | E | PS5-71-08 - CFO Pre-Pressure Modules | To be completed
T-00046-0401 | PS5-71-UZ-6700 | CZX01E - Package | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed
T-00046-0402 | PS5-74-UB-5100 | CZX01E - Package | E | PS5-74-01 - N2 Generation Skid | To be completed
T-00046-0403 | PS5-75-UI-6100 | CZX01E - Package | E | PS5-75-02 - Biocide Injection Package | To be completed
T-00046-0404 | PS5-75-UI-6200 | CZX01E - Package | E | PS5-75-01 - DRA Injection Package | To be completed
T-00046-0405 | PS5-75-UI-6300 | CZX01E - Package | E | PS5-75-03 - Corrosion Inhibitor Injection Package | To be completed
T-00046-0406 | PS5-77-UZ-8200 | CZX01E - Package | E | PS5-53-03 - Water Softener Package | To be completed
T-00046-0407 | PS5-82-UZ-8100 | CZX01E - Package | E | PS5-82-02 - Sewage Treatment Plant Package | To be completed
T-00046-0542 | PS5-83-EHO-0001A | CZX01E - Package | E | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00046-0543 | PS5-83-EHO-0001B | CZX01E - Package | E | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00046-0544 | PS5-83-EHO-0001C | CZX01E - Package | E | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00046-0549 | PS5-01-UZ-610 | CZX01E - Package | E | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00046-0552 | PS5-60-UR-8300A | CZX01E - Package | E | PS5-60-35 - Injector Tip Cooling Module A | To be completed
T-00046-0553 | PS5-60-UR-8300B | CZX01E - Package | E | PS5-60-36 - Injector Tip Cooling Module B | To be completed
T-00046-0554 | PS5-60-UR-8300C | CZX01E - Package | E | PS5-60-37 - Injector Tip Cooling Module C | To be completed
T-00046-0555 | PS5-60-UR-8300D | CZX01E - Package | E | PS5-60-38 - Injector Tip Cooling Module D | To be completed
T-00046-0556 | PS5-60-UR-8300E | CZX01E - Package | E | PS5-60-39 - Injector Tip Cooling Module E | To be completed
T-00046-0557 | PS5-60-UR-8300F | CZX01E - Package | E | PS5-60-40 - Injector Tip Cooling Module F | To be completed
T-00046-0558 | PS5-60-UR-8300G | CZX01E - Package | E | PS5-60-41 - Injector Tip Cooling Module G | To be completed
T-00064-0412 | PS5-01-RAB-61001A | CJX00 - Miscellaneous | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00064-0413 | PS5-01-RAB-61001B | CJX00 - Miscellaneous | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00064-0414 | PS5-01-RAB-61002A | CJX00 - Miscellaneous | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00064-0415 | PS5-01-RAB-61002B | CJX00 - Miscellaneous | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00064-0416 | PS5-01-RAB-61003A | CJX00 - Miscellaneous | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00064-0417 | PS5-01-RAB-61003B | CJX00 - Miscellaneous | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00064-0418 | PS5-01-RAB-61004A | CJX00 - Miscellaneous | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00064-0419 | PS5-01-RAB-61004B | CJX00 - Miscellaneous | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00064-0437 | PS5-03-RAB-B402 | CJX00 - Miscellaneous | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00064-0438 | PS5-03-RAB-B902 | CJX00 - Miscellaneous | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00064-0439 | PS5-03-RAB-W502 | CJX00 - Miscellaneous | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00065-0115 | PS5-25-PSV-1103 | CJX03 - Relief valve | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00065-0116 | PS5-28-PSV-0064C | CJX03 - Relief valve | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00065-0117 | PS5-25-PSV-1203 | CJX03 - Relief valve | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00065-0118 | PS5-28-PRV-0047B | CJX03 - Relief valve | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00065-0119 | PS5-74-PSV-0003 | CJX03 - Relief valve | I | PS5-74-03 - Nitrogen Receiver | To be completed
T-00065-0120 | PS5-28-PRV-0040 | CJX03 - Relief valve | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00065-0121 | PS5-50-PSV-0004A | CJX03 - Relief valve | I | PS5-50-01 - Water Well Submersible Pumps (3100) | To be completed
T-00065-0122 | PS5-71-PSV-2403A | CJX03 - Relief valve | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00065-0123 | PS5-28-PSV-3901B | CJX03 - Relief valve | I | PS5-28-17 - Reinjection Pump | To be completed
T-00065-0124 | PS5-28-PRV-0047A | CJX03 - Relief valve | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00065-0125 | PS5-71-PVSV-4202 | CJX03 - Relief valve | I | PS5-71-12 - CFO Service Tank | To be completed
T-00065-0126 | PS5-71-PVSV-4102 | CJX03 - Relief valve | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00065-0127 | PS5-28-PRV-0046A | CJX03 - Relief valve | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00065-0128 | PS5-28-PRV-0008 | CJX03 - Relief valve | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00065-0129 | PS5-28-PSV-0064A | CJX03 - Relief valve | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00065-0130 | PS5-28-PRV-0054 | CJX03 - Relief valve | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00065-0131 | PS5-28-PSV-0044 | CJX03 - Relief valve | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00065-0132 | PS5-71-PRV-0016 | CJX03 - Relief valve | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00065-0133 | PS5-28-PRV-0046B | CJX03 - Relief valve | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00065-0134 | PS5-71-PRV-0015 | CJX03 - Relief valve | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00065-0135 | PS5-71-PRV-0018 | CJX03 - Relief valve | I | PS5-71-12 - CFO Service Tank | To be completed
T-00065-0136 | PS5-71-PRV-0041 | CJX03 - Relief valve | I | PS5-71-12 - CFO Service Tank | To be completed
T-00065-0137 | PS5-71-PSV-2403B | CJX03 - Relief valve | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00065-0138 | PS5-28-PRV-0046C | CJX03 - Relief valve | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00065-0139 | PS5-28-PRV-0047C | CJX03 - Relief valve | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00065-0140 | PS5-28-PRV-0055 | CJX03 - Relief valve | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00065-0141 | PS5-28-PSV-0061 | CJX03 - Relief valve | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00065-0142 | PS5-28-PSV-0064B | CJX03 - Relief valve | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00065-0143 | PS5-28-PSV-3901A | CJX03 - Relief valve | I | PS5-28-17 - Reinjection Pump | To be completed
T-00065-0144 | PS5-50-PSV-0004B | CJX03 - Relief valve | I | PS5-50-02 - Water Well Submersible Pumps (3200) | To be completed
T-00066-0059 | PS5-01-FCV-0004B | CJX06 - Tubing Hydraulic | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00066-0060 | PS5-25-FCV-0004 | CJX06 - Tubing Hydraulic | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00066-0061 | PS5-01-FCV-0003A | CJX06 - Tubing Hydraulic | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00066-0062 | PS5-01-FCV-0003B | CJX06 - Tubing Hydraulic | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00066-0063 | PS5-71-FCV-0018 | CJX06 - Tubing Hydraulic | I | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00066-0064 | PS5-25-FCV-0003B | CJX06 - Tubing Hydraulic | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00066-0065 | PS5-71-LCV-4101 | CJX06 - Tubing Hydraulic | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00066-0066 | PS5-71-FCV-0019 | CJX06 - Tubing Hydraulic | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00066-0067 | PS5-71-FCV-0020 | CJX06 - Tubing Hydraulic | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00066-0068 | PS5-01-FCV-0004A | CJX06 - Tubing Hydraulic | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00066-0069 | PS5-25-FCV-0003A | CJX06 - Tubing Hydraulic | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00066-0070 | PS5-25-FCV-0003C | CJX06 - Tubing Hydraulic | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00067-0072 | PS5-03-RMAC-0101 | CJX08 - Electrical instrument | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00067-0073 | PS5-03-RMAC-0102 | CJX08 - Electrical instrument | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00067-0074 | PS5-03-RMAC-0103 | CJX08 - Electrical instrument | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00067-0075 | PS5-03-RMAC-0120 | CJX08 - Electrical instrument | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00067-0076 | PS5-03-RMAC-0301 | CJX08 - Electrical instrument | I | PS5-03-03 - FZ-03 - Buildings Area | To be completed
T-00067-0077 | PS5-03-RMAC-0401 | CJX08 - Electrical instrument | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed
T-00067-0078 | PS5-03-RMAC-0402 | CJX08 - Electrical instrument | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed
T-00067-0079 | PS5-03-RMAC-0613 | CJX08 - Electrical instrument | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00067-0081 | PS5-03-RMAC-0827 | CJX08 - Electrical instrument | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00067-0640 | PS5-03-NMR-0801 | CJX08 - Electrical instrument | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00067-0641 | PS5-03-NMR-0802 | CJX08 - Electrical instrument | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00067-0642 | PS5-03-NMR-0803 | CJX08 - Electrical instrument | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00067-0643 | PS5-03-NMR-0804 | CJX08 - Electrical instrument | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00067-0652 | PS5-03-RMAC-0304 | CJX08 - Electrical instrument | I | PS5-03-03 - FZ-03 - Buildings Area | To be completed
T-00067-0653 | PS5-03-RMAC-0706 | CJX08 - Electrical instrument | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00067-0654 | PS5-03-RMAC-0707 | CJX08 - Electrical instrument | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00067-0655 | PS5-03-RMAC-0824 | CJX08 - Electrical instrument | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00067-0656 | PS5-03-RMAC-0825 | CJX08 - Electrical instrument | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00067-0657 | PS5-03-RMAC-0834 | CJX08 - Electrical instrument | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00067-0658 | PS5-03-RMAC-1301 | CJX08 - Electrical instrument | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | To be completed
T-00067-0659 | PS5-03-RMAC-1409 | CJX08 - Electrical instrument | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00067-0660 | PS5-03-RMAC-1410 | CJX08 - Electrical instrument | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00067-0661 | PS5-03-RMAC-1411 | CJX08 - Electrical instrument | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00067-2049 | PS5-25-ZIT-0001 | CJX08 - Electrical instrument | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00067-2050 | PS5-25-ZS-1101 | CJX08 - Electrical instrument | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00067-2051 | PS5-03-HS-7002 | CJX08 - Electrical instrument | I | PS5-03-03 - FZ-03 - Buildings Area | To be completed
T-00067-2052 | PS5-71-HZL-0059 | CJX08 - Electrical instrument | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00067-2053 | PS5-71-HZH-0059 | CJX08 - Electrical instrument | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00067-2054 | PS5-25-ZIT-0002 | CJX08 - Electrical instrument | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00067-2055 | PS5-25-ZS-1201 | CJX08 - Electrical instrument | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00067-2056 | PS5-25-FIT-0003B | CJX08 - Electrical instrument | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00067-2057 | PS5-71-FIT-0019 | CJX08 - Electrical instrument | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00067-2058 | PS5-71-FIT-0011B | CJX08 - Electrical instrument | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00067-2059 | PS5-50-FIT-0001 | CJX08 - Electrical instrument | I | PS5-50-03 - Water Pre-Treatment Package | To be completed
T-00067-2060 | PS5-01-FIT-0003B | CJX08 - Electrical instrument | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00067-2061 | PS5-25-FIT-0003A | CJX08 - Electrical instrument | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00067-2062 | PS5-71-FIT-0018 | CJX08 - Electrical instrument | I | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00067-2063 | PS5-01-FIT-0003A | CJX08 - Electrical instrument | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00067-2064 | PS5-71-FIT-0020 | CJX08 - Electrical instrument | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00067-2065 | PS5-25-FIT-0004 | CJX08 - Electrical instrument | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00067-2066 | PS5-25-FIT-0003C | CJX08 - Electrical instrument | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00067-2067 | PS5-25-FIT-0001 | CJX08 - Electrical instrument | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00067-2068 | PS5-71-FIT-0012 | CJX08 - Electrical instrument | I | PS5-71-17 - Diesel Fuel Distribution Header | To be completed
T-00067-2069 | PS5-71-FIT-0005 | CJX08 - Electrical instrument | I | PS5-71-17 - Diesel Fuel Distribution Header | To be completed
T-00067-2070 | PS5-71-FIT-0011A | CJX08 - Electrical instrument | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00067-2071 | PS5-01-FIT-0004A | CJX08 - Electrical instrument | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00067-2072 | PS5-01-FIT-0004B | CJX08 - Electrical instrument | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00067-2073 | PS5-71-LIT-1202 | CJX08 - Electrical instrument | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed
T-00067-2074 | PS5-71-LIT-4202 | CJX08 - Electrical instrument | I | PS5-71-12 - CFO Service Tank | To be completed
T-00067-2075 | PS5-01-LIT-4101B | CJX08 - Electrical instrument | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00067-2076 | PS5-28-LIT-1301A | CJX08 - Electrical instrument | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00067-2077 | PS5-28-LIT-1102 | CJX08 - Electrical instrument | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00067-2078 | PS5-50-LIT-0001 | CJX08 - Electrical instrument | I | PS5-50-01 - Water Well Submersible Pumps (3100) | To be completed
T-00067-2079 | PS5-28-LIT-1301B | CJX08 - Electrical instrument | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00067-2080 | PS5-71-LIT-4101 | CJX08 - Electrical instrument | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00067-2081 | PS5-60-LIT-4401 | CJX08 - Electrical instrument | I | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | To be completed
T-00067-2082 | PS5-71-LIT-4102 | CJX08 - Electrical instrument | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00067-2083 | PS5-71-LIT-4401 | CJX08 - Electrical instrument | I | PS5-71-15 - Diesel Fuel Storage Tank | To be completed
T-00067-2084 | PS5-28-LIT-1202 | CJX08 - Electrical instrument | I | PS5-28-06 - Relief Drum and Pump | To be completed
T-00067-2085 | PS5-28-LIT-0002 | CJX08 - Electrical instrument | I | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00067-2086 | PS5-53-LIT-4101 | CJX08 - Electrical instrument | I | PS5-53-01 - Utility Water / Storage Tank | To be completed
T-00067-2087 | PS5-28-LIT-1402 | CJX08 - Electrical instrument | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00067-2088 | PS5-71-LIT-4201 | CJX08 - Electrical instrument | I | PS5-71-12 - CFO Service Tank | To be completed
T-00067-2089 | PS5-28-LIT-1201 | CJX08 - Electrical instrument | I | PS5-28-06 - Relief Drum and Pump | To be completed
T-00067-2090 | PS5-60-LIT-4301 | CJX08 - Electrical instrument | I | PS5-60-24 - Cooling Water Tank & Pump | To be completed
T-00067-2091 | PS5-28-LIT-1301C | CJX08 - Electrical instrument | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00067-2092 | PS5-28-LIT-1101 | CJX08 - Electrical instrument | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00067-2093 | PS5-71-LIT-1201 | CJX08 - Electrical instrument | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed
T-00067-2094 | PS5-71-LIT-4402 | CJX08 - Electrical instrument | I | PS5-71-15 - Diesel Fuel Storage Tank | To be completed
T-00067-2095 | PS5-01-LIT-4101A | CJX08 - Electrical instrument | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00067-2096 | PS5-28-LIT-0008 | CJX08 - Electrical instrument | I | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00067-2097 | PS5-28-LIT-1401 | CJX08 - Electrical instrument | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00067-2098 | PS5-50-LIT-0002 | CJX08 - Electrical instrument | I | PS5-50-02 - Water Well Submersible Pumps (3200) | To be completed
T-00067-2099 | PS5-53-LIT-4102 | CJX08 - Electrical instrument | I | PS5-53-01 - Utility Water / Storage Tank | To be completed
T-00067-2100 | PS5-25-PDIT-0034A | CJX08 - Electrical instrument | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00067-2101 | PS5-25-PIT-0008C | CJX08 - Electrical instrument | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00067-2102 | PS5-01-PDIT-0012B | CJX08 - Electrical instrument | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00067-2103 | PS5-01-PIT-0010 | CJX08 - Electrical instrument | I | PS5-01-07 - Fire Water Ring Main & Distribution | To be completed
T-00067-2104 | PS5-25-PIT-0018 | CJX08 - Electrical instrument | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00067-2105 | PS5-01-PDIT-0011A | CJX08 - Electrical instrument | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00067-2106 | PS5-25-PDIT-0050 | CJX08 - Electrical instrument | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00067-2107 | PS5-28-PIT-0015 | CJX08 - Electrical instrument | I | PS5-28-17 - Reinjection Pump | To be completed
T-00067-2108 | PS5-28-PIT-0041 | CJX08 - Electrical instrument | I | PS5-28-17 - Reinjection Pump | To be completed
T-00067-2109 | PS5-25-PIT-0004C | CJX08 - Electrical instrument | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00067-2110 | PS5-25-PDIT-0034C | CJX08 - Electrical instrument | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00067-2111 | PS5-01-PIT-0016 | CJX08 - Electrical instrument | I | PS5-01-07 - Fire Water Ring Main & Distribution | To be completed
T-00067-2112 | PS5-71-PDIT-0030 | CJX08 - Electrical instrument | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00067-2113 | PS5-25-PIT-0071B | CJX08 - Electrical instrument | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00067-2114 | PS5-01-PDIT-0011B | CJX08 - Electrical instrument | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00067-2115 | PS5-25-PIT-0001 | CJX08 - Electrical instrument | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00067-2116 | PS5-71-PDIT-0056B | CJX08 - Electrical instrument | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00067-2117 | PS5-25-PIT-1202 | CJX08 - Electrical instrument | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00067-2118 | PS5-25-PIT-0005B | CJX08 - Electrical instrument | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00067-2119 | PS5-25-PIT-0004A | CJX08 - Electrical instrument | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00067-2120 | PS5-01-PIT-0015 | CJX08 - Electrical instrument | I | PS5-01-07 - Fire Water Ring Main & Distribution | To be completed
T-00067-2121 | PS5-71-PDIT-0056A | CJX08 - Electrical instrument | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00067-2122 | PS5-74-PIT-0002 | CJX08 - Electrical instrument | I | PS5-74-04 - Nitrogen Distribution Header | To be completed
T-00067-2123 | PS5-28-PIT-0033 | CJX08 - Electrical instrument | I | PS5-28-06 - Relief Drum and Pump | To be completed
T-00067-2124 | PS5-01-PIT-0017 | CJX08 - Electrical instrument | I | PS5-01-07 - Fire Water Ring Main & Distribution | To be completed
T-00067-2125 | PS5-25-PIT-1102 | CJX08 - Electrical instrument | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00067-2126 | PS5-25-PIT-0004B | CJX08 - Electrical instrument | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00067-2127 | PS5-25-PIT-0007B | CJX08 - Electrical instrument | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00067-2128 | PS5-01-PIT-0014 | CJX08 - Electrical instrument | I | PS5-01-07 - Fire Water Ring Main & Distribution | To be completed
T-00067-2129 | PS5-25-PIT-0071C | CJX08 - Electrical instrument | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00067-2130 | PS5-53-PIT-0005 | CJX08 - Electrical instrument | I | PS5-53-02 - Water Distribution Pump A/B | To be completed
T-00067-2131 | PS5-25-PIT-0007A | CJX08 - Electrical instrument | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00067-2132 | PS5-25-PIT-0005A | CJX08 - Electrical instrument | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00067-2133 | PS5-25-PIT-0071A | CJX08 - Electrical instrument | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00067-2134 | PS5-71-PIT-0014 | CJX08 - Electrical instrument | I | PS5-71-17 - Diesel Fuel Distribution Header | To be completed
T-00067-2135 | PS5-25-PIT-0013 | CJX08 - Electrical instrument | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00067-2136 | PS5-71-PIT-2402A | CJX08 - Electrical instrument | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00067-2137 | PS5-71-PIT-2402B | CJX08 - Electrical instrument | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00067-2138 | PS5-01-PDIT-0012A | CJX08 - Electrical instrument | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00067-2139 | PS5-01-PIT-0013 | CJX08 - Electrical instrument | I | PS5-01-07 - Fire Water Ring Main & Distribution | To be completed
T-00067-2140 | PS5-25-PDIT-0034B | CJX08 - Electrical instrument | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00067-2141 | PS5-25-PIT-0005C | CJX08 - Electrical instrument | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00067-2142 | PS5-25-PIT-0007C | CJX08 - Electrical instrument | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00067-2143 | PS5-25-PIT-0008A | CJX08 - Electrical instrument | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00067-2144 | PS5-25-PIT-0008B | CJX08 - Electrical instrument | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00067-2145 | PS5-71-TIT-0003 | CJX08 - Electrical instrument | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00067-2146 | PS5-71-TIT-0006 | CJX08 - Electrical instrument | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00067-2147 | PS5-71-TIT-4203 | CJX08 - Electrical instrument | I | PS5-71-12 - CFO Service Tank | To be completed
T-00067-2148 | PS5-28-TIT-1402 | CJX08 - Electrical instrument | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00067-2149 | PS5-25-TIT-0002B | CJX08 - Electrical instrument | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00067-2150 | PS5-25-TIT-1201 | CJX08 - Electrical instrument | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00067-2151 | PS5-25-TIT-0003B | CJX08 - Electrical instrument | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00067-2152 | PS5-28-TIT-1401 | CJX08 - Electrical instrument | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00067-2153 | PS5-25-TIT-0003A | CJX08 - Electrical instrument | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00067-2154 | PS5-71-TIT-0007 | CJX08 - Electrical instrument | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00067-2155 | PS5-28-TIT-1104 | CJX08 - Electrical instrument | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00067-2156 | PS5-71-TIT-0004 | CJX08 - Electrical instrument | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00067-2157 | PS5-71-TIT-4202 | CJX08 - Electrical instrument | I | PS5-71-12 - CFO Service Tank | To be completed
T-00067-2158 | PS5-25-TIT-0003C | CJX08 - Electrical instrument | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00067-2159 | PS5-25-TIT-1101 | CJX08 - Electrical instrument | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00067-2160 | PS5-28-TIT-1105 | CJX08 - Electrical instrument | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00067-2161 | PS5-71-TIT-4103 | CJX08 - Electrical instrument | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00067-2162 | PS5-25-TIT-0002C | CJX08 - Electrical instrument | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00067-2163 | PS5-71-TIT-4102 | CJX08 - Electrical instrument | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00067-2164 | PS5-25-TIT-0001 | CJX08 - Electrical instrument | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00067-2165 | PS5-25-TIT-0002A | CJX08 - Electrical instrument | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00067-2166 | PS5-25-TIT-0004 | CJX08 - Electrical instrument | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00067-2167 | PS5-28-TIT-1201 | CJX08 - Electrical instrument | I | PS5-28-06 - Relief Drum and Pump | To be completed
T-00067-2168 | PS5-71-HZL-0058 | CJX08 - Electrical instrument | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00067-2169 | PS5-71-HZH-0058 | CJX08 - Electrical instrument | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00067-2432 | PS5-25-IES-3200A | CJX08 - Electrical instrument | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00067-2433 | PS5-25-IES-3200B | CJX08 - Electrical instrument | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00067-2434 | PS5-25-IES-3300A | CJX08 - Electrical instrument | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00067-2435 | PS5-25-IES-3300B | CJX08 - Electrical instrument | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00067-2436 | PS5-25-IES-3400A | CJX08 - Electrical instrument | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00067-2437 | PS5-25-IES-3400B | CJX08 - Electrical instrument | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00067-2438 | PS5-25-IES-6400A | CJX08 - Electrical instrument | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00067-2439 | PS5-25-IES-6400B | CJX08 - Electrical instrument | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00067-2440 | PS5-25-IES-6500A | CJX08 - Electrical instrument | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00067-2441 | PS5-25-IES-6500B | CJX08 - Electrical instrument | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00067-2442 | PS5-25-IES-6600A | CJX08 - Electrical instrument | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00067-2443 | PS5-25-IES-6600B | CJX08 - Electrical instrument | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00067-2444 | PS5-28-IES-2008 | CJX08 - Electrical instrument | I | PS5-28-10 - Oil Skimmer Package | To be completed
T-00067-2445 | PS5-28-IES-3300 | CJX08 - Electrical instrument | I | PS5-28-06 - Relief Drum and Pump | To be completed
T-00067-2446 | PS5-28-IES-3400 | CJX08 - Electrical instrument | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00067-2447 | PS5-28-IES-3500 | CJX08 - Electrical instrument | I | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00067-2448 | PS5-28-IES-3600A | CJX08 - Electrical instrument | I | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00067-2449 | PS5-28-IES-3600B | CJX08 - Electrical instrument | I | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00067-2450 | PS5-28-IES-3700A | CJX08 - Electrical instrument | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00067-2451 | PS5-28-IES-3700B | CJX08 - Electrical instrument | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00067-2452 | PS5-28-IES-3800A | CJX08 - Electrical instrument | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00067-2453 | PS5-28-IES-3800B | CJX08 - Electrical instrument | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00067-2454 | PS5-28-IES-3800C | CJX08 - Electrical instrument | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00067-2455 | PS5-28-IES-3900A | CJX08 - Electrical instrument | I | PS5-28-17 - Reinjection Pump | To be completed
T-00067-2456 | PS5-28-IES-3900B | CJX08 - Electrical instrument | I | PS5-28-17 - Reinjection Pump | To be completed
T-00067-2457 | PS5-53-IES-3100A | CJX08 - Electrical instrument | I | PS5-53-02 - Water Distribution Pump A/B | To be completed
T-00067-2458 | PS5-53-IES-3100B | CJX08 - Electrical instrument | I | PS5-53-02 - Water Distribution Pump A/B | To be completed
T-00067-2459 | PS5-60-IES-3300 | CJX08 - Electrical instrument | I | PS5-60-24 - Cooling Water Tank & Pump | To be completed
T-00067-2460 | PS5-60-IES-3400 | CJX08 - Electrical instrument | I | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | To be completed
T-00067-2461 | PS5-71-IES-3100A | CJX08 - Electrical instrument | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | To be completed
T-00067-2462 | PS5-71-IES-3100B | CJX08 - Electrical instrument | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | To be completed
T-00067-2463 | PS5-71-IES-3200 | CJX08 - Electrical instrument | I | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | To be completed
T-00067-2464 | PS5-71-IES-3300A | CJX08 - Electrical instrument | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00067-2465 | PS5-71-IES-3300B | CJX08 - Electrical instrument | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00067-2466 | PS5-71-IES-3400A | CJX08 - Electrical instrument | I | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00067-2467 | PS5-71-IES-3400B | CJX08 - Electrical instrument | I | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00067-2468 | PS5-71-IES-3500A | CJX08 - Electrical instrument | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00067-2469 | PS5-71-IES-3500B | CJX08 - Electrical instrument | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00067-2560 | PS5-01-LB-6101A | CJX08 - Electrical instrument | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00067-2561 | PS5-01-LB-6102A | CJX08 - Electrical instrument | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00067-2562 | PS5-01-LB-6103A | CJX08 - Electrical instrument | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00067-2563 | PS5-01-LB-6104A | CJX08 - Electrical instrument | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00067-2643 | PS5-03-RMAC-B401 | CJX08 - Electrical instrument | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00067-2644 | PS5-03-RMAC-B901 | CJX08 - Electrical instrument | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00067-2645 | PS5-03-RMAC-W501 | CJX08 - Electrical instrument | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00067-2728 | PS5-09-AH-8401 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2729 | PS5-09-AH-8402 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2730 | PS5-09-AH-8403 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2731 | PS5-09-IES-8101A | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2732 | PS5-09-IES-8101B | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2733 | PS5-09-IES-8102A | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2734 | PS5-09-IES-8102B | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2735 | PS5-09-IES-8102C | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2736 | PS5-09-IES-8201A | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2737 | PS5-09-IES-8201B | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2738 | PS5-09-IES-8202A | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2739 | PS5-09-IES-8202B | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2740 | PS5-09-IES-8202C | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2741 | PS5-09-IES-8202D | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2742 | PS5-09-IES-8301A | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2743 | PS5-09-IES-8301B | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2744 | PS5-09-IES-8302A | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2745 | PS5-09-IES-8302B | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2746 | PS5-09-IES-8304A | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2747 | PS5-09-IES-8304B | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2748 | PS5-09-IES-8305A | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2749 | PS5-09-IES-8305B | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2750 | PS5-09-IES-8307A | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2751 | PS5-09-IES-8307B | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2752 | PS5-09-IES-8308A | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2753 | PS5-09-IES-8308B | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2754 | PS5-09-IES-8311A | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2755 | PS5-09-IES-8311B | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2756 | PS5-09-IES-8313 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2757 | PS5-09-IES-8314 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2758 | PS5-09-IES-8315 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2759 | PS5-09-IES-8316 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2760 | PS5-09-IES-8317 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2761 | PS5-09-IES-8318 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2762 | PS5-09-IES-8319 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2763 | PS5-09-IES-8321 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2764 | PS5-09-IES-8322 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2765 | PS5-09-IES-8323 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2766 | PS5-09-IES-8324 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2767 | PS5-09-IES-8325 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2768 | PS5-09-IES-8401A | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2769 | PS5-09-IES-8401B | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2770 | PS5-09-IES-8403A | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2771 | PS5-09-IES-8403B | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2772 | PS5-09-IES-8404A | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2773 | PS5-09-IES-8404B | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2774 | PS5-09-IES-8405A | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2775 | PS5-09-IES-8405B | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2776 | PS5-09-IES-8406A | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2777 | PS5-09-IES-8406B | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2778 | PS5-09-IES-8406C | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2779 | PS5-09-IES-8406D | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2780 | PS5-09-IES-8406E | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2781 | PS5-09-IES-8406F | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2782 | PS5-09-IES-8406G | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2783 | PS5-09-IES-8406H | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2784 | PS5-09-IES-8407 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2785 | PS5-09-PDIT-8207 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2786 | PS5-09-PDIT-8407 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2787 | PS5-09-PDIT-8408 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2788 | PS5-09-PDIT-8409 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2789 | PS5-09-PDIT-8411 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2790 | PS5-09-PIT-8401 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2791 | PS5-09-PIT-8402 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2792 | PS5-09-PIT-8403 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2793 | PS5-09-PIT-8404 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2794 | PS5-09-TIT-8101 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2795 | PS5-09-TIT-8201 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2796 | PS5-09-TIT-8301 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2797 | PS5-09-TIT-8302 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2798 | PS5-09-TIT-8303 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2799 | PS5-09-TIT-8304 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2800 | PS5-09-TIT-8401 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2801 | PS5-09-TIT-8402 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2802 | PS5-09-TIT-8403 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2803 | PS5-09-TIT-8404 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2804 | PS5-09-TIT-8405 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2805 | PS5-09-TIT-8406 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2806 | PS5-09-TIT-8407 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2807 | PS5-09-TIT-8408 | CJX08 - Electrical instrument | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00067-2929 | PS5-23-SPZM-0003A | CJX08 - Electrical instrument | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00067-2930 | PS5-23-SPZM-0003B | CJX08 - Electrical instrument | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00067-2931 | PS5-23-SPZM-0003C | CJX08 - Electrical instrument | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00067-2932 | PS5-23-SPZM-0003D | CJX08 - Electrical instrument | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00067-2933 | PS5-23-SPZM-0004A | CJX08 - Electrical instrument | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00067-2934 | PS5-23-SPZM-0004B | CJX08 - Electrical instrument | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00067-2935 | PS5-23-SPZM-0004C | CJX08 - Electrical instrument | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00067-2936 | PS5-23-SPZM-0004D | CJX08 - Electrical instrument | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00069-10850 | PS5-03-RAB-B402-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10851 | PS5-03-RAB-B902-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10852 | PS5-03-RAB-W502-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10853 | PS5-03-RDHR-W101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10854 | PS5-03-RDHR-W101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10855 | PS5-03-RDHR-W101C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10856 | PS5-03-RDHR-W101D-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10857 | PS5-03-RDHR-W101E-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10858 | PS5-03-RDHR-W101F-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10859 | PS5-03-RDHR-W101G-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10860 | PS5-03-RDHR-W101H-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10861 | PS5-03-RDHR-W101I-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10862 | PS5-03-RDHR-W601A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10863 | PS5-03-RDHR-W601B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10864 | PS5-03-RDHR-W601C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10865 | PS5-03-RDHR-W601D-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10866 | PS5-03-RDHR-W601E-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10867 | PS5-03-RDHR-W601F-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10868 | PS5-03-RDHR-W601G-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10869 | PS5-03-RDHR-W601H-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10870 | PS5-03-RDHR-W601I-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10871 | PS5-03-RDHR-W601J-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10872 | PS5-03-RDHR-W601K-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10873 | PS5-03-RDHR-W601L-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10874 | PS5-03-RDHR-W601M-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10875 | PS5-03-RDHR-W601N-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10876 | PS5-03-RDHR-W601O-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10877 | PS5-03-RDHR-W601P-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10878 | PS5-03-RDOS-B101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10879 | PS5-03-RDOS-B101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10880 | PS5-03-RDOS-B101C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10881 | PS5-03-RDOS-B101D-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10882 | PS5-03-RDOS-B201A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10883 | PS5-03-RDOS-B201B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10884 | PS5-03-RDOS-B201C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10885 | PS5-03-RDOS-B201D-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10886 | PS5-03-RDOS-B201E-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10887 | PS5-03-RDOS-B301A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10888 | PS5-03-RDOS-B301B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10889 | PS5-03-RDOS-B301C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10890 | PS5-03-RDOS-B301D-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10891 | PS5-03-RDOS-B401A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10892 | PS5-03-RDOS-B401B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10893 | PS5-03-RDOS-B401C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10894 | PS5-03-RDOS-B401D-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10895 | PS5-03-RDOS-B501A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10896 | PS5-03-RDOS-B601A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10897 | PS5-03-RDOS-B701A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10898 | PS5-03-RDOS-B701B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10899 | PS5-03-RDOS-B701C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10900 | PS5-03-RDOS-B701D-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10901 | PS5-03-RDOS-B701E-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10902 | PS5-03-RDOS-B701F-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10903 | PS5-03-RDOS-B701G-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10904 | PS5-03-RDOS-B701H-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10905 | PS5-03-RDOS-B701I-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10906 | PS5-03-RDOS-B801A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10907 | PS5-03-RDOS-B801B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10908 | PS5-03-RDOS-B901A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10909 | PS5-03-RDOS-B901B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10910 | PS5-03-RDOS-B901C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10911 | PS5-03-RDOS-B901D-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10912 | PS5-03-RDOS-B901E-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10913 | PS5-03-RDOS-W201A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10914 | PS5-03-RDOS-W201B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10915 | PS5-03-RDOS-W201C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10916 | PS5-03-RDOS-W201D-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10917 | PS5-03-RDOS-W301A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10918 | PS5-03-RDOS-W401A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10919 | PS5-03-RDOS-W501A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10920 | PS5-03-RDOS-W501B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10921 | PS5-03-RDOS-W501C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10922 | PS5-03-RDOS-W501D-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10923 | PS5-03-RDOS-W501E-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10924 | PS5-03-RDOS-W501F-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-10925 | PS5-03-RMAC-B401-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10926 | PS5-03-RMAC-B901-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00069-10927 | PS5-03-RMAC-W501-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00069-11574 | PS5-09-AH-8401-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11575 | PS5-09-AH-8401-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11576 | PS5-09-AH-8402-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11577 | PS5-09-AH-8402-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11578 | PS5-09-AH-8403-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11579 | PS5-09-AH-8403-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11580 | PS5-09-AS-8111A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11581 | PS5-09-AS-8111A-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11582 | PS5-09-AS-8111B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11583 | PS5-09-AS-8111B-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11584 | PS5-09-AS-8211A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11585 | PS5-09-AS-8211A-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11586 | PS5-09-AS-8211B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11587 | PS5-09-AS-8211B-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11588 | PS5-09-AS-8311A-A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11589 | PS5-09-AS-8311A-A-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11590 | PS5-09-AS-8311B-B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11591 | PS5-09-AS-8311B-B-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11592 | PS5-09-AS-8311C-A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11593 | PS5-09-AS-8311C-A-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11594 | PS5-09-AS-8311D-B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11595 | PS5-09-AS-8311D-B-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11596 | PS5-09-AS-8321A-A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11597 | PS5-09-AS-8321A-A-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11598 | PS5-09-AS-8321B-B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11599 | PS5-09-AS-8321B-B-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11600 | PS5-09-AS-8321C-A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11601 | PS5-09-AS-8321C-A-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11602 | PS5-09-AS-8321D-B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11603 | PS5-09-AS-8321D-B-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11604 | PS5-09-AS-8331A-A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11605 | PS5-09-AS-8331A-A-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11606 | PS5-09-AS-8331B-B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11607 | PS5-09-AS-8331B-B-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11608 | PS5-09-AS-8331C-A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11609 | PS5-09-AS-8331C-A-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11610 | PS5-09-AS-8331D-B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11611 | PS5-09-AS-8331D-B-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11612 | PS5-09-AS-8341A-A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11613 | PS5-09-AS-8341A-A-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11614 | PS5-09-AS-8341B-B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11615 | PS5-09-AS-8341B-B-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11616 | PS5-09-AS-8411A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11617 | PS5-09-AS-8411A-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11618 | PS5-09-AS-8411B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11619 | PS5-09-AS-8411B-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11620 | PS5-09-AS-8412A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11621 | PS5-09-AS-8412A-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11622 | PS5-09-AS-8412B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11623 | PS5-09-AS-8412B-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11624 | PS5-09-AS-8421A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11625 | PS5-09-AS-8421A-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11626 | PS5-09-AS-8421B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11627 | PS5-09-AS-8421B-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11628 | PS5-09-AS-8432A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11629 | PS5-09-AS-8432A-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11630 | PS5-09-AS-8432B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11631 | PS5-09-AS-8432B-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11632 | PS5-09-BI-8111A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11633 | PS5-09-BI-8111B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11634 | PS5-09-BI-8211A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11635 | PS5-09-BI-8211B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11636 | PS5-09-BI-8311A-A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11637 | PS5-09-BI-8311A-B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11638 | PS5-09-BI-8311B-A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11639 | PS5-09-BI-8311B-B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11640 | PS5-09-BI-8321A-A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11641 | PS5-09-BI-8321A-B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11642 | PS5-09-BI-8321B-A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11643 | PS5-09-BI-8321B-B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11644 | PS5-09-BI-8331A-A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11645 | PS5-09-BI-8331A-B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11646 | PS5-09-BI-8331B-A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11647 | PS5-09-BI-8331B-B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11648 | PS5-09-BI-8341A-A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11649 | PS5-09-BI-8341A-B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11650 | PS5-09-BI-8411A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11651 | PS5-09-BI-8411B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11652 | PS5-09-FCU-8442A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11653 | PS5-09-FCU-8442A-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11654 | PS5-09-FCU-8442B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11655 | PS5-09-FCU-8442B-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11656 | PS5-09-FCU-8442C-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11657 | PS5-09-FCU-8442C-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11658 | PS5-09-FCU-8442D-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11659 | PS5-09-FCU-8442D-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11660 | PS5-09-FCU-8442E-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11661 | PS5-09-FCU-8442E-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11662 | PS5-09-FCU-8442F-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11663 | PS5-09-FCU-8442F-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11664 | PS5-09-FCU-8442G-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11665 | PS5-09-FCU-8442G-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11666 | PS5-09-FCU-8442H-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11667 | PS5-09-FCU-8442H-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11668 | PS5-09-FD-0019-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11669 | PS5-09-FD-0019-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11670 | PS5-09-FD-0019-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11671 | PS5-09-FD-0021-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11672 | PS5-09-FD-0021-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11673 | PS5-09-FD-0021-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11674 | PS5-09-FD-0024-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11675 | PS5-09-FD-0024-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11676 | PS5-09-FD-0024-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11677 | PS5-09-FD-0025-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11678 | PS5-09-FD-0025-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11679 | PS5-09-FD-0025-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11680 | PS5-09-FD-0026-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11681 | PS5-09-FD-0026-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11682 | PS5-09-FD-0026-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11683 | PS5-09-FD-0027-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11684 | PS5-09-FD-0027-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11685 | PS5-09-FD-0027-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11686 | PS5-09-FD-0028-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11687 | PS5-09-FD-0028-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11688 | PS5-09-FD-0028-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11689 | PS5-09-FD-0029-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11690 | PS5-09-FD-0029-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11691 | PS5-09-FD-0029-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11692 | PS5-09-FD-0030-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11693 | PS5-09-FD-0030-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11694 | PS5-09-FD-0030-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11695 | PS5-09-FD-0031-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11696 | PS5-09-FD-0031-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11697 | PS5-09-FD-0031-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11698 | PS5-09-FD-0032-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11699 | PS5-09-FD-0032-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11700 | PS5-09-FD-0032-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11701 | PS5-09-FD-0033-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11702 | PS5-09-FD-0033-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11703 | PS5-09-FD-0033-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11704 | PS5-09-HE-8401A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11705 | PS5-09-HE-8401B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11706 | PS5-09-LB-8111A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11707 | PS5-09-LB-8111B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11708 | PS5-09-LB-8211A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11709 | PS5-09-LB-8211B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11710 | PS5-09-LB-8311A-A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11711 | PS5-09-LB-8311A-B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11712 | PS5-09-LB-8311B-A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11713 | PS5-09-LB-8311B-B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11714 | PS5-09-LB-8321A-A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11715 | PS5-09-LB-8321A-B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11716 | PS5-09-LB-8321B-A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11717 | PS5-09-LB-8321B-B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11718 | PS5-09-LB-8331A-A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11719 | PS5-09-LB-8331A-B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11720 | PS5-09-LB-8331B-A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11721 | PS5-09-LB-8331B-B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11722 | PS5-09-LB-8341A-A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11723 | PS5-09-LB-8341A-B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11724 | PS5-09-LB-8411A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11725 | PS5-09-LB-8411B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11726 | PS5-09-LB-8442A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11727 | PS5-09-LB-8442B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11728 | PS5-09-LB-8442C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11729 | PS5-09-LB-8442D-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11730 | PS5-09-LB-8442E-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11731 | PS5-09-LB-8442F-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11732 | PS5-09-LB-8442G-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11733 | PS5-09-LB-8442H-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11734 | PS5-09-LB-8451A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11735 | PS5-09-LB-8451A-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11736 | PS5-09-LB-8451B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11737 | PS5-09-LB-8451B-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11738 | PS5-09-PDIT-8207-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11739 | PS5-09-PDIT-8407-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11740 | PS5-09-PDIT-8408-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11741 | PS5-09-PDIT-8409-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11742 | PS5-09-PDIT-8411-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11743 | PS5-09-PIT-8401-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11744 | PS5-09-PIT-8402-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11745 | PS5-09-PIT-8403-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11746 | PS5-09-PIT-8404-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11747 | PS5-09-TCV-8401-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11748 | PS5-09-TCV-8401-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11749 | PS5-09-TCV-8402-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11750 | PS5-09-TCV-8402-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11751 | PS5-09-TIT-8101-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11752 | PS5-09-TIT-8201-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11753 | PS5-09-TIT-8301-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11754 | PS5-09-TIT-8302-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11755 | PS5-09-TIT-8303-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11756 | PS5-09-TIT-8304-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11757 | PS5-09-TIT-8401-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11758 | PS5-09-TIT-8402-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11759 | PS5-09-TIT-8403-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11760 | PS5-09-TIT-8404-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11761 | PS5-09-TIT-8405-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11762 | PS5-09-TIT-8406-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11763 | PS5-09-TIT-8407-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11764 | PS5-09-TIT-8408-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11765 | PS5-09-UZ-84600-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11766 | PS5-09-UZ-84600-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11767 | PS5-09-XV-8401-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11768 | PS5-09-XV-8401-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11769 | PS5-09-XV-8402-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11770 | PS5-09-XV-8402-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11771 | PS5-09-XV-8403-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11772 | PS5-09-XV-8403-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11773 | PS5-09-XV-8404-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11774 | PS5-09-XV-8404-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11775 | PS5-09-XV-8413-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11776 | PS5-09-XV-8413-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11777 | PS5-09-XV-8414-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11778 | PS5-09-XV-8414-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11779 | PS5-61-IH-0004A-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11780 | PS5-61-IH-0004A-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11781 | PS5-61-IH-0004A-CU03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11782 | PS5-61-IH-0004A-CU04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11783 | PS5-61-IH-0004B-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11784 | PS5-61-IH-0004B-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11785 | PS5-61-IH-0004B-CU03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11786 | PS5-61-IH-0004B-CU04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11787 | PS5-61-IH-0004C-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11788 | PS5-61-IH-0004C-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11789 | PS5-61-IH-0004C-CU03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11790 | PS5-61-IH-0004C-CU04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11791 | PS5-61-IH-0004-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11792 | PS5-61-IH-0004-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11793 | PS5-61-IH-0004-CU03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11794 | PS5-61-IH-0004-CU04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11795 | PS5-61-IH-0004-CU05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11796 | PS5-61-IH-0004-CU06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11797 | PS5-61-IH-0004-CU07 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11798 | PS5-61-IH-0004-CU08 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11799 | PS5-61-IH-0004-CU09 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11800 | PS5-61-IH-0004-CU10 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11801 | PS5-61-IH-0004-CU11 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11802 | PS5-61-IH-0004-CU12 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11803 | PS5-61-IH-0004-CU13 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11804 | PS5-61-IH-0004-CU14 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11805 | PS5-61-IH-0004-CU15 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11806 | PS5-61-IH-0004-CU16 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11807 | PS5-61-IH-0004-CU17 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11808 | PS5-61-IH-0004-CU18 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11809 | PS5-61-IH-0004-CU19 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11810 | PS5-61-IH-0004-CU20 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11811 | PS5-61-IH-0004-CU21 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11812 | PS5-61-IH-0004-CU22 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11813 | PS5-61-IH-0004-CU23 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11814 | PS5-61-IH-0004-CU24 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11815 | PS5-61-IH-0004-CU25 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11816 | PS5-61-IH-0004-CU26 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11817 | PS5-61-IH-0004-CU27 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11818 | PS5-61-IH-0004-CU28 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11819 | PS5-61-IH-0004-CU29 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11820 | PS5-61-IH-0004D-CU01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-11821 | PS5-61-IH-0004D-CU02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00069-12946 | PS5-03-RDH-1902-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | To be completed
T-00069-12947 | PS5-03-RDOS-1703-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3 | To be completed
T-00069-12948 | PS5-60-BI-0001A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00069-12949 | PS5-60-BI-0001B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00069-12950 | PS5-60-BI-0001C-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00069-12951 | PS5-60-BI-0001D-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00069-12952 | PS5-60-BI-0001E-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00069-12953 | PS5-60-BI-0001F-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00069-12954 | PS5-60-BI-0001G-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00069-12955 | PS5-60-BI-0003-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00069-12956 | PS5-60-IE-0002A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00069-12957 | PS5-60-IE-0002A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00069-12958 | PS5-60-IE-0002A-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00069-12959 | PS5-60-IE-0002B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00069-12960 | PS5-60-IE-0002B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00069-12961 | PS5-60-IE-0002B-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00069-12962 | PS5-60-IE-0002C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00069-12963 | PS5-60-IE-0002C-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00069-12964 | PS5-60-IE-0002C-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00069-12965 | PS5-60-IE-0002D-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00069-12966 | PS5-60-IE-0002D-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00069-12967 | PS5-60-IE-0002D-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00069-12968 | PS5-60-IE-0002E-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00069-12969 | PS5-60-IE-0002E-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00069-12970 | PS5-60-IE-0002E-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00069-12971 | PS5-60-IE-0002F-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00069-12972 | PS5-60-IE-0002F-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00069-12973 | PS5-60-IE-0002F-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00069-12974 | PS5-60-IE-0002G-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00069-12975 | PS5-60-IE-0002G-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00069-12976 | PS5-60-IE-0002G-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00069-12977 | PS5-60-IH-0001A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | To be completed
T-00069-12978 | PS5-60-IH-0001A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | To be completed
T-00069-12979 | PS5-60-IH-0001B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | To be completed
T-00069-12980 | PS5-60-IH-0001B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | To be completed
T-00069-12981 | PS5-60-IH-0001C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | To be completed
T-00069-12982 | PS5-60-IH-0001C-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | To be completed
T-00069-12983 | PS5-60-IH-0001D-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | To be completed
T-00069-12984 | PS5-60-IH-0001D-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | To be completed
T-00069-12985 | PS5-60-IH-0001E-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed
T-00069-12986 | PS5-60-IH-0001E-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed
T-00069-12987 | PS5-60-IH-0001F-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00069-12988 | PS5-60-IH-0001F-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00069-12989 | PS5-60-IH-0001G-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed
T-00069-12990 | PS5-60-IH-0001G-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed
T-00069-12991 | PS5-60-IH-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00069-12992 | PS5-60-IH-0002-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00069-12993 | PS5-60-LA-0003-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00069-12994 | PS5-60-LA-0003-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00069-12995 | PS5-60-PIT-8113A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed
T-00069-12996 | PS5-60-PIT-8113B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed
T-00069-12997 | PS5-60-PIT-8113C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00069-12998 | PS5-60-PIT-8113D-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00069-12999 | PS5-60-PIT-8113E-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00069-13000 | PS5-60-PIT-8113F-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00069-13001 | PS5-60-PIT-8113G-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00069-13002 | PS5-60-PIT-8114A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed
T-00069-13003 | PS5-60-PIT-8114B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed
T-00069-13004 | PS5-60-PIT-8114C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00069-13005 | PS5-60-PIT-8114D-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00069-13006 | PS5-60-PIT-8114E-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00069-13007 | PS5-60-PIT-8114F-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00069-13008 | PS5-60-PIT-8114G-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00069-13009 | PS5-71-IN-0004A-CC10 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00069-4210 | PS5-01-BI-0007-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4211 | PS5-01-BI-0008-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4212 | PS5-01-BI-0009-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4223 | PS5-01-FCV-0003A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00069-4224 | PS5-01-FCV-0003B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00069-4225 | PS5-01-FCV-0004A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00069-4226 | PS5-01-FCV-0004B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00069-4227 | PS5-01-FIT-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00069-4228 | PS5-01-FIT-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00069-4229 | PS5-01-FIT-0004A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00069-4230 | PS5-01-FIT-0004B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00069-4231 | PS5-01-FXS-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00069-4232 | PS5-01-FXS-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00069-4233 | PS5-01-FXS-0004A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00069-4234 | PS5-01-FXS-0004B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00069-4235 | PS5-01-FY-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00069-4236 | PS5-01-FY-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00069-4237 | PS5-01-FY-0004A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00069-4238 | PS5-01-FY-0004B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00069-4239 | PS5-01-HS-3108AB-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00069-4240 | PS5-01-HS-3108BB-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00069-4252 | PS5-01-LB-6101A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4253 | PS5-01-LB-6102A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4254 | PS5-01-LB-6103A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4255 | PS5-01-LB-6104A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4256 | PS5-01-LIT-4101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00069-4257 | PS5-01-LIT-4101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00069-4259 | PS5-01-NMR-61001-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4260 | PS5-01-NMR-61002-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4261 | PS5-01-NMR-61003-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4262 | PS5-01-NMR-61004-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4263 | PS5-01-NMRA-61001-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4264 | PS5-01-NMRA-61002-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4265 | PS5-01-NMRA-61003-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4266 | PS5-01-NMRA-61004-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4267 | PS5-01-PDIT-0011A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00069-4268 | PS5-01-PDIT-0011B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00069-4269 | PS5-01-PDIT-0012A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00069-4270 | PS5-01-PDIT-0012B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00069-4271 | PS5-01-PIT-0003AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00069-4272 | PS5-01-PIT-0003BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00069-4273 | PS5-01-PIT-0004AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00069-4274 | PS5-01-PIT-0004BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00069-4275 | PS5-01-PIT-0010-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-07 - Fire Water Ring Main & Distribution | To be completed | CPP-RFI-68-64-12-0061 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4276 | PS5-01-PIT-0013-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-07 - Fire Water Ring Main & Distribution | To be completed
T-00069-4281 | PS5-01-PIT-8101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00069-4282 | PS5-01-PIT-8101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00069-4283 | PS5-01-PIT-8101C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00069-4284 | PS5-01-PIT-8101D-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00069-4285 | PS5-01-PIT-8101E-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00069-4286 | PS5-01-PIT-8101F-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00069-4287 | PS5-01-PIT-8101G-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00069-4288 | PS5-01-PIT-8101H-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00069-4289 | PS5-01-RAB-61001A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4290 | PS5-01-RAB-61001B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4291 | PS5-01-RAB-61002A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4292 | PS5-01-RAB-61002B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4293 | PS5-01-RAB-61003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4294 | PS5-01-RAB-61003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4295 | PS5-01-RAB-61004A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4296 | PS5-01-RAB-61004B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00069-4297 | PS5-01-SY-8101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00069-4298 | PS5-01-SY-8101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00069-4299 | PS5-01-SY-8101C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00069-4300 | PS5-01-SY-8101D-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00069-4301 | PS5-01-SY-8101E-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00069-4302 | PS5-01-SY-8101F-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00069-4303 | PS5-01-SY-8101G-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00069-4304 | PS5-01-SY-8101H-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00069-4331 | PS5-03-GDIR-0901-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-4332 | PS5-03-GDIR-0902-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-4333 | PS5-03-GDIR-0903-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-4334 | PS5-03-GDIR-0904-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-4335 | PS5-03-GDIR-0906-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-4336 | PS5-03-GDIR-0907-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-4337 | PS5-03-GDIR-0908-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-4338 | PS5-03-GDIR-0909-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-4339 | PS5-03-GDIR-1001-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-4340 | PS5-03-GDIR-1002-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-4341 | PS5-03-GDIR-1003-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-4342 | PS5-03-GDIR-1004-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-4343 | PS5-03-GDIR-1006-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-4344 | PS5-03-GDIR-1007-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-4345 | PS5-03-GDIR-1008-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-4346 | PS5-03-GDIR-1009-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-4347 | PS5-03-GDIR-1101-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4348 | PS5-03-GDIR-1102-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4349 | PS5-03-GDIR-1103-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4350 | PS5-03-GDIR-1104-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4351 | PS5-03-GDIR-1106-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4352 | PS5-03-GDIR-1107-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4353 | PS5-03-GDIR-1108-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4354 | PS5-03-GDIR-1109-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4355 | PS5-03-GDIR-1201-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00069-4356 | PS5-03-GDIR-1202-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00069-4357 | PS5-03-GDIR-1203-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00069-4358 | PS5-03-GDIR-1204-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-4359 | PS5-03-GDLHP-0137-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0072
T-00069-4360 | PS5-03-GDLHP-0142-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0072
T-00069-4361 | PS5-03-GDLHP-0143-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0072
T-00069-4362 | PS5-03-GDLHP-0144-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0072
T-00069-4363 | PS5-03-GDLHP-0146-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0072
T-00069-4364 | PS5-03-GDLHP-0147-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4365 | PS5-03-GDLHP-0149-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4366 | PS5-03-GDLHP-0150-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4367 | PS5-03-GDLHP-0401-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4381 | PS5-03-RDH-0302-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-03 - FZ-03 - Buildings Area | To be completed
T-00069-4382 | PS5-03-RDH-0303-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-03 - FZ-03 - Buildings Area | To be completed
T-00069-4383 | PS5-03-RDH-0601-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00069-4384 | PS5-03-RDH-0602-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00069-4385 | PS5-03-RDH-0603-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00069-4386 | PS5-03-RDH-0604-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00069-4387 | PS5-03-RDH-0605-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00069-4388 | PS5-03-RDH-0606-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00069-4389 | PS5-03-RDH-0607-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00069-4390 | PS5-03-RDH-0608-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00069-4391 | PS5-03-RDH-0609-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00069-4392 | PS5-03-RDH-0610-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00069-4393 | PS5-03-RDH-0611-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00069-4394 | PS5-03-RDH-0612-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00069-4395 | PS5-03-RDH-0614-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4396 | PS5-03-RDH-0615-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4397 | PS5-03-RDH-0616-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4398 | PS5-03-RDH-0617-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00069-4399 | PS5-03-RDH-0618-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00069-4400 | PS5-03-RDH-0620-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00069-4401 | PS5-03-RDH-0828-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00069-4402 | PS5-03-RDH-0829-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00069-4403 | PS5-03-RDH-0830-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-4404 | PS5-03-RDH-0831-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-4405 | PS5-03-RDH-0901-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00069-4406 | PS5-03-RDH-0902-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00069-4407 | PS5-03-RDH-0903-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00069-4408 | PS5-03-RDH-0904-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00069-4409 | PS5-03-RDH-0905-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00069-4410 | PS5-03-RDH-0906-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00069-4411 | PS5-03-RDH-0909-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00069-4412 | PS5-03-RDH-0910-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00069-4413 | PS5-03-RDH-0911-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00069-4414 | PS5-03-RDH-0912-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00069-4415 | PS5-03-RDH-1001-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00069-4416 | PS5-03-RDH-1002-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00069-4417 | PS5-03-RDH-1003-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00069-4418 | PS5-03-RDH-1004-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00069-4419 | PS5-03-RDH-1005-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00069-4420 | PS5-03-RDH-1006-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00069-4421 | PS5-03-RDH-1009-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00069-4422 | PS5-03-RDH-1010-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00069-4423 | PS5-03-RDH-1011-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00069-4424 | PS5-03-RDH-1012-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00069-4425 | PS5-03-RDH-1101-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4426 | PS5-03-RDH-1102-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4427 | PS5-03-RDH-1103-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4428 | PS5-03-RDH-1104-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4429 | PS5-03-RDH-1105-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4430 | PS5-03-RDH-1106-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4431 | PS5-03-RDH-1109-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4432 | PS5-03-RDH-1110-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4433 | PS5-03-RDH-1111-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4434 | PS5-03-RDH-1112-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4435 | PS5-03-RDH-1201-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00069-4436 | PS5-03-RDH-1202-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00069-4437 | PS5-03-RDH-1203-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00069-4438 | PS5-03-RDH-1204-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00069-4439 | PS5-03-RDH-1205-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00069-4440 | PS5-03-RDH-1302-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | To be completed
T-00069-4441 | PS5-03-RDH-1303-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | To be completed
T-00069-4442 | PS5-03-RDH-1304-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | To be completed
T-00069-4443 | PS5-03-RDH-1901-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | To be completed
T-00069-4444 | PS5-03-RDH-1903-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | To be completed
T-00069-4445 | PS5-03-RDIR-0104-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0092
T-00069-4446 | PS5-03-RDIR-0105-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0092
T-00069-4447 | PS5-03-RDIR-0106-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0092
T-00069-4448 | PS5-03-RDIR-0107-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00069-4449 | PS5-03-RDIR-0108-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00069-4450 | PS5-03-RDIR-0109-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00069-4451 | PS5-03-RDIR-0110-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00069-4452 | PS5-03-RDIR-0111-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00069-4453 | PS5-03-RDIR-0112-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00069-4454 | PS5-03-RDIR-0113-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00069-4455 | PS5-03-RDIR-0114-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4456 | PS5-03-RDIR-0115-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4457 | PS5-03-RDIR-0116-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4458 | PS5-03-RDIR-0117-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4459 | PS5-03-RDIR-0118-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4460 | PS5-03-RDIR-0121-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-4461 | PS5-03-RDIR-0122-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-4462 | PS5-03-RDIR-0123-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-4463 | PS5-03-RDIR-0124-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00069-4464 | PS5-03-RDIR-0125-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-4465 | PS5-03-RDIR-0126-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-4466 | PS5-03-RDIR-0127-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-4467 | PS5-03-RDIR-0128-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00069-4468 | PS5-03-RDIR-0129-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00069-4469 | PS5-03-RDIR-0130-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00069-4470 | PS5-03-RDIR-0131-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00069-4471 | PS5-03-RDIR-0132-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00069-4472 | PS5-03-RDIR-0133-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00069-4473 | PS5-03-RDIR-0137-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0092 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00069-4474 | PS5-03-RDIR-0138-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00069-4475 | PS5-03-RDIR-0141-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0092
T-00069-4476 | PS5-03-RDIR-0142-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0092 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00069-4477 | PS5-03-RDIR-0403-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN]
T-00069-4478 | PS5-03-RDIR-0404-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0075
T-00069-4479 | PS5-03-RDIR-0405-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0092
T-00069-4480 | PS5-03-RDIR-0406-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed
T-00069-4481 | PS5-03-RDIR-0409-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0092
T-00069-4482 | PS5-03-RDIR-0411-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0075
T-00069-4483 | PS5-03-RDIR-0819-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4484 | PS5-03-RDIR-0820-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4485 | PS5-03-RDIR-0832-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4486 | PS5-03-RDIR-0833-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00069-4487 | PS5-03-RDOS-1401-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00069-4488 | PS5-03-RDOS-1402-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00069-4489 | PS5-03-RDOS-1403-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00069-4490 | PS5-03-RDOS-1404-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00069-4491 | PS5-03-RDOS-1405-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00069-4492 | PS5-03-RDOS-1406-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00069-4493 | PS5-03-RDOS-1407-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00069-4494 | PS5-03-RDOS-1408-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00069-4495 | PS5-03-RDOS-1501-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1 | To be completed
T-00069-4496 | PS5-03-RDOS-1502-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1 | To be completed
T-00069-4497 | PS5-03-RDOS-1503-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1 | To be completed
T-00069-4498 | PS5-03-RDOS-1601-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2 | To be completed
T-00069-4499 | PS5-03-RDOS-1602-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2 | To be completed
T-00069-4500 | PS5-03-RDOS-1603-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2 | To be completed
T-00069-4501 | PS5-03-RDOS-1701-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3 | To be completed
T-00069-4502 | PS5-03-RDOS-1702-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3 | To be completed
T-00069-4503 | PS5-03-RDOS-1801-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4 | To be completed
T-00069-4504 | PS5-03-RDOS-1802-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4 | To be completed
T-00069-4505 | PS5-03-RDOS-1803-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4 | To be completed
T-00069-4506 | PS5-03-RDOS-2101-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit | To be completed
T-00069-4507 | PS5-03-RDOS-2102-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit | To be completed
T-00069-4508 | PS5-03-RDOS-2103-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit | To be completed
T-00069-4509 | PS5-03-RDOS-G101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-22 - FZ-G1 - Guard House | To be completed
T-00069-4510 | PS5-03-RDOS-G101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-22 - FZ-G1 - Guard House | To be completed
T-00069-4511 | PS5-03-RDUIR-0701-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00069-4512 | PS5-03-RDUIR-0702-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00069-4513 | PS5-03-RDUIR-0703-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00069-4514 | PS5-03-RDUIR-0704-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00069-4515 | PS5-03-RDUIR-0705-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00069-4516 | PS5-03-RDUIR-0907-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00069-4517 | PS5-03-RDUIR-0908-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00069-4518 | PS5-03-RDUIR-1007-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00069-4519 | PS5-03-RDUIR-1008-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00069-4520 | PS5-03-RDUIR-1107-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4521 | PS5-03-RDUIR-1108-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00069-4522 | PS5-03-RDUIR-1207-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00069-4523 | PS5-03-RDUIR-1208-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00069-4524 | PS5-03-RMAC-0101-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4525 | PS5-03-RMAC-0102-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-4526 | PS5-03-RMAC-0103-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4528 | PS5-03-RMAC-0301-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-03 - FZ-03 - Buildings Area | To be completed
T-00069-4529 | PS5-03-RMAC-0304-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-03 - FZ-03 - Buildings Area | To be completed
T-00069-4530 | PS5-03-RMAC-0401-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-4531 | PS5-03-RMAC-0402-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4532 | PS5-03-RMAC-0613-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN]
T-00069-4533 | PS5-03-RMAC-0706-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00069-4534 | PS5-03-RMAC-0707-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00069-4536 | PS5-03-RMAC-0825-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00069-4537 | PS5-03-RMAC-0827-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00069-4538 | PS5-03-RMAC-0834-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00069-4539 | PS5-03-RMAC-1301-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | To be completed
T-00069-4540 | PS5-03-RMAC-1410-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00069-4541 | PS5-03-RMAC-1411-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00069-4542 | PS5-03-SEA-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-04-0049 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00069-4551 | PS5-05-BI-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00069-4552 | PS5-05-BI-0002-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00069-4553 | PS5-05-BI-0002-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-04-0049 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00069-4554 | PS5-05-BI-0002-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0043 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4555 | PS5-05-BI-0002-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0050 |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00069-4556 | PS5-05-BI-0002-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0050 |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00069-4559 | PS5-05-BI-0002-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00069-4560 | PS5-05-BI-0002-CJ02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00069-4561 | PS5-05-BI-0002-CJ03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00069-4562 | PS5-05-GC-8100-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0043 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4565 | PS5-05-IE-8101-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00069-4566 | PS5-05-IG-0009-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0043 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4567 | PS5-05-IG-0009-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0043 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4568 | PS5-05-IG-0009-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00069-4569 | PS5-05-LIT-4101-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00069-4570 | PS5-05-UH-8100-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0043 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4571 | PS5-05-UH-8100-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-04-0049 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00069-4611 | PS5-25-BI-1802A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00069-4613 | PS5-25-BI-1802B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00069-4615 | PS5-25-BI-1802C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00069-4642 | PS5-25-ESDV-0021-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4643 | PS5-25-ESDV-0021-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00069-4644 | PS5-25-ESDV-0021-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00069-4645 | PS5-25-ESDV-0023-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4646 | PS5-25-ESDV-0023-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00069-4647 | PS5-25-ESDV-0023-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00069-4648 | PS5-25-ESY-0021A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4649 | PS5-25-ESY-0021B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4650 | PS5-25-ESY-0023B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4651 | PS5-25-FCV-0003A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00069-4652 | PS5-25-FCV-0003B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00069-4653 | PS5-25-FCV-0003C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4654 | PS5-25-FCV-0004-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00069-4655 | PS5-25-FIT-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00069-4656 | PS5-25-FIT-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00069-4657 | PS5-25-FIT-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00069-4658 | PS5-25-FIT-0003C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4659 | PS5-25-FIT-0004-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4660 | PS5-25-FXS-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00069-4661 | PS5-25-FXS-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00069-4662 | PS5-25-FXS-0003C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4663 | PS5-25-FXS-0004-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00069-4664 | PS5-25-FY-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00069-4665 | PS5-25-FY-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00069-4666 | PS5-25-FY-0003C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4667 | PS5-25-FY-0004-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4668 | PS5-25-HS-8101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4669 | PS5-25-HS-8101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4670 | PS5-25-HS-8101C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4671 | PS5-25-HS-8102A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4672 | PS5-25-HS-8102B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4673 | PS5-25-HS-8102C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4674 | PS5-25-MOV-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00069-4675 | PS5-25-MOV-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4676 | PS5-25-MOV-0003-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4677 | PS5-25-MOV-0008-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00069-4678 | PS5-25-MOV-0011-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4679 | PS5-25-MOV-0012-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4680 | PS5-25-MOV-0025-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00069-4681 | PS5-25-MOV-0026-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4682 | PS5-25-MOV-0026-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094
T-00069-4683 | PS5-25-MOV-0027-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4684 | PS5-25-MOV-0027-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00069-4685 | PS5-25-MOV-0028-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00069-4686 | PS5-25-MXS-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00069-4687 | PS5-25-MXS-0008-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00069-4688 | PS5-25-MXS-0025-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00069-4689 | PS5-25-MXS-0028-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00069-4696 | PS5-25-PDIT-0034A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00069-4697 | PS5-25-PDIT-0034B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00069-4698 | PS5-25-PDIT-0034C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4699 | PS5-25-PDIT-0050-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00069-4700 | PS5-25-PI-1102B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00069-4701 | PS5-25-PI-1202B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00069-4702 | PS5-25-PIT-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094
T-00069-4703 | PS5-25-PIT-0003AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00069-4704 | PS5-25-PIT-0003BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00069-4705 | PS5-25-PIT-0003CA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4706 | PS5-25-PIT-0004AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00069-4707 | PS5-25-PIT-0004A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00069-4708 | PS5-25-PIT-0004B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00069-4709 | PS5-25-PIT-0004C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4710 | PS5-25-PIT-0005A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00069-4711 | PS5-25-PIT-0005B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00069-4712 | PS5-25-PIT-0005C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4713 | PS5-25-PIT-0007A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00069-4714 | PS5-25-PIT-0007B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00069-4715 | PS5-25-PIT-0007C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4716 | PS5-25-PIT-0008A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4717 | PS5-25-PIT-0008B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0072
T-00069-4718 | PS5-25-PIT-0008C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0072
T-00069-4719 | PS5-25-PIT-0013-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4720 | PS5-25-PIT-0018-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00069-4721 | PS5-25-PIT-0022-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4722 | PS5-25-PIT-0035A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00069-4723 | PS5-25-PIT-0035B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00069-4724 | PS5-25-PIT-0035C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4725 | PS5-25-PIT-0036A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00069-4726 | PS5-25-PIT-0036B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00069-4727 | PS5-25-PIT-0036C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4728 | PS5-25-PIT-0046-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed
T-00069-4730 | PS5-25-PIT-0053-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4731 | PS5-25-PIT-0054A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00069-4732 | PS5-25-PIT-0054B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00069-4733 | PS5-25-PIT-0054C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4734 | PS5-25-PIT-0070-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00069-4738 | PS5-25-PIT-1102-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00069-4739 | PS5-25-PIT-1202-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00069-4740 | PS5-25-SDV-0022-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4741 | PS5-25-SDV-0022-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00069-4742 | PS5-25-SDV-0035A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4743 | PS5-25-SDV-0035B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4744 | PS5-25-SDV-0035C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4745 | PS5-25-SDV-0036A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4746 | PS5-25-SDV-0036B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00069-4747 | PS5-25-SDV-0036C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4748 | PS5-25-SDV-0046-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4751 | PS5-25-SDV-0054A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4752 | PS5-25-SDV-0054B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4753 | PS5-25-SDV-0054C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4755 | PS5-25-SXS-0022-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00069-4756 | PS5-25-SXS-0035A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-4757 | PS5-25-SXS-0035B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-4758 | PS5-25-SXS-0035C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-4759 | PS5-25-SXS-0036A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-4760 | PS5-25-SXS-0036B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-4761 | PS5-25-SXS-0036C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-4762 | PS5-25-SXS-0046-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-4764 | PS5-25-SXS-0054A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00069-4765 | PS5-25-SXS-0054B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00069-4766 | PS5-25-SXS-0054C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4767 | PS5-25-SY-0022-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4768 | PS5-25-SY-0035AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4769 | PS5-25-SY-0035AB-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00069-4770 | PS5-25-SY-0035BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4771 | PS5-25-SY-0035BB-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00069-4772 | PS5-25-SY-0035CA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4773 | PS5-25-SY-0035CB-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4774 | PS5-25-SY-0036AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4775 | PS5-25-SY-0036AB-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00069-4776 | PS5-25-SY-0036BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00069-4777 | PS5-25-SY-0036BB-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00069-4778 | PS5-25-SY-0036CA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4779 | PS5-25-SY-0036CB-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4780 | PS5-25-SY-0046A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4781 | PS5-25-SY-0046B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4783 | PS5-25-SY-0052B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00069-4784 | PS5-25-SY-0054AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4785 | PS5-25-SY-0054AB-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4786 | PS5-25-SY-0054BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00069-4787 | PS5-25-SY-0054BB-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00069-4788 | PS5-25-SY-0054CA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4789 | PS5-25-SY-0054CB-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4790 | PS5-25-TIT-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00069-4791 | PS5-25-TIT-0002A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00069-4792 | PS5-25-TIT-0002B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00069-4793 | PS5-25-TIT-0002C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0072
T-00069-4794 | PS5-25-TIT-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00069-4795 | PS5-25-TIT-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00069-4796 | PS5-25-TIT-0003C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00069-4797 | PS5-25-TIT-0004-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094
T-00069-4798 | PS5-25-TIT-1101-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00069-4799 | PS5-25-TIT-1201-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00069-4800 | PS5-25-XV-0053-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed
T-00069-4801 | PS5-25-XV-0053-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed
T-00069-4802 | PS5-25-XV-0070-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed
T-00069-4803 | PS5-25-XXS-0053-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed
T-00069-4804 | PS5-25-XXS-0070-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed
T-00069-4805 | PS5-25-XY-0053-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4806 | PS5-25-XY-0070-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4807 | PS5-25-ZIT-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00069-4808 | PS5-25-ZIT-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00069-4809 | PS5-25-ZS-1101-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00069-4810 | PS5-25-ZS-1201-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00069-4818 | PS5-28-HXA-1402-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00069-4819 | PS5-28-HY-3901A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4820 | PS5-28-HY-3901B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4823 | PS5-28-LI-1101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4824 | PS5-28-LI-1101C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00069-4825 | PS5-28-LI-1402B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4826 | PS5-28-LIT-0002-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-08 - Open Drain Sump and Pumps | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4827 | PS5-28-LIT-0008-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-08 - Open Drain Sump and Pumps | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4828 | PS5-28-LIT-1101-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4829 | PS5-28-LIT-1102-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4830 | PS5-28-LIT-1201-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-06 - Relief Drum and Pump | To be completed
T-00069-4831 | PS5-28-LIT-1202-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-06 - Relief Drum and Pump | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4832 | PS5-28-LIT-1301A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00069-4833 | PS5-28-LIT-1301B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00069-4834 | PS5-28-LIT-1301C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00069-4835 | PS5-28-LIT-1401-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4836 | PS5-28-LIT-1402-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4837 | PS5-28-PIT-0015-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4838 | PS5-28-PIT-0033-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-06 - Relief Drum and Pump | To be completed
T-00069-4839 | PS5-28-PIT-0041-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4840 | PS5-28-PIT-0045-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4841 | PS5-28-PIT-0053A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00069-4842 | PS5-28-PIT-0053B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00069-4843 | PS5-28-PIT-0053C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00069-4844 | PS5-28-PIT-3901A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4845 | PS5-28-PIT-3901B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4846 | PS5-28-SDV-0045-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | To be completed
T-00069-4847 | PS5-28-SDV-0045-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | To be completed
T-00069-4848 | PS5-28-SDV-0053A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4849 | PS5-28-SDV-0053A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00069-4850 | PS5-28-SDV-0053B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00069-4851 | PS5-28-SDV-0053B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00069-4852 | PS5-28-SDV-0053C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00069-4853 | PS5-28-SDV-0053C-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00069-4854 | PS5-28-SXS-0045-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | To be completed
T-00069-4855 | PS5-28-SXS-0053A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed | CPP-RFI-68-64-04-0072
T-00069-4856 | PS5-28-SXS-0053B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed | CPP-RFI-68-64-04-0072
T-00069-4857 | PS5-28-SXS-0053C-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00069-4858 | PS5-28-SY-0045A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4859 | PS5-28-SY-0045B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4860 | PS5-28-SY-0053AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4861 | PS5-28-SY-0053AB-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00069-4862 | PS5-28-SY-0053BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4863 | PS5-28-SY-0053BB-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4864 | PS5-28-SY-0053CA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00069-4865 | PS5-28-SY-0053CB-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00069-4866 | PS5-28-TIT-1104-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4867 | PS5-28-TIT-1105-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4868 | PS5-28-TIT-1201-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-06 - Relief Drum and Pump | To be completed
T-00069-4869 | PS5-28-TIT-1401-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4870 | PS5-28-TIT-1402-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4871 | PS5-28-TIT-2101-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4872 | PS5-28-TIT-2201-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-4874 | PS5-50-FIT-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-50-03 - Water Pre-Treatment Package | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-4885 | PS5-53-LIT-4101-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-53-01 - Utility Water / Storage Tank | To be completed
T-00069-4886 | PS5-53-LIT-4102-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-53-01 - Utility Water / Storage Tank | To be completed
T-00069-4887 | PS5-53-PIT-0005-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-53-02 - Water Distribution Pump A/B | To be completed
T-00069-4888 | PS5-60-BE-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-27 - Compressed Air Starting Skid | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4889 | PS5-60-BE-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-26 - Instrument Air Compressor Skid | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4890 | PS5-60-BE-0004A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4891 | PS5-60-BE-0004B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4892 | PS5-60-BE-0004C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4893 | PS5-60-BE-0004D-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4894 | PS5-60-BE-0004E-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4895 | PS5-60-BE-0004F-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4896 | PS5-60-BE-0004G-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4897 | PS5-60-BI-0001A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4898 | PS5-60-BI-0001A-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4899 | PS5-60-BI-0001B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4900 | PS5-60-BI-0001B-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4901 | PS5-60-BI-0001C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4902 | PS5-60-BI-0001C-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4903 | PS5-60-BI-0001D-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4904 | PS5-60-BI-0001D-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4905 | PS5-60-BI-0001E-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4906 | PS5-60-BI-0001E-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4907 | PS5-60-BI-0001F-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4908 | PS5-60-BI-0001F-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4909 | PS5-60-BI-0001G-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4910 | PS5-60-BI-0001G-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-4911 | PS5-60-BI-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00069-4912 | PS5-60-BI-0002-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-4913 | PS5-60-BI-0002-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00069-4914 | PS5-60-BI-0002-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00069-4915 | PS5-60-BI-0003-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-4916 | PS5-60-BI-0003-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-4917 | PS5-60-BI-0004A-CCO1 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00069-4918 | PS5-60-BI-0004B-CCO1 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00069-4919 | PS5-60-BI-0004C-CCO1 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00069-4920 | PS5-60-BI-0004D-CCO1 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00069-4921 | PS5-60-BI-0004E-CCO1 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00069-4922 | PS5-60-BI-0004F-CCO1 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00069-4923 | PS5-60-BI-0004G-CCO1 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00069-4924 | PS5-60-BI-0005A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00069-4925 | PS5-60-BI-0005A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00069-4926 | PS5-60-BI-0005B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00069-4927 | PS5-60-BI-0005B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00069-4928 | PS5-60-BI-0005C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00069-4929 | PS5-60-BI-0005C-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00069-4930 | PS5-60-BI-0005D-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00069-4931 | PS5-60-BI-0005D-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00069-4932 | PS5-60-BI-0005E-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00069-4933 | PS5-60-BI-0005E-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00069-4934 | PS5-60-BI-0005F-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00069-4935 | PS5-60-BI-0005F-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00069-4936 | PS5-60-BI-0005G-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00069-4937 | PS5-60-BI-0005G-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00069-4938 | PS5-60-BI-0006A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-4939 | PS5-60-BI-0006A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed
T-00069-4940 | PS5-60-BI-0006A-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed
T-00069-4941 | PS5-60-BI-0006A-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed
T-00069-4942 | PS5-60-BI-0006A-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-4943 | PS5-60-BI-0006A-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed
T-00069-4944 | PS5-60-BI-0006B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-4945 | PS5-60-BI-0006B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00069-4946 | PS5-60-BI-0006B-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00069-4947 | PS5-60-BI-0006B-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00069-4948 | PS5-60-BI-0006B-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-4949 | PS5-60-BI-0006B-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00069-4950 | PS5-60-BI-0006C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-4951 | PS5-60-BI-0006C-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00069-4952 | PS5-60-BI-0006C-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00069-4953 | PS5-60-BI-0006C-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00069-4954 | PS5-60-BI-0006C-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-4955 | PS5-60-BI-0006C-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00069-4956 | PS5-60-BI-0006D-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-4957 | PS5-60-BI-0006D-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00069-4958 | PS5-60-BI-0006D-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00069-4959 | PS5-60-BI-0006D-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00069-4960 | PS5-60-BI-0006D-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-4961 | PS5-60-BI-0006D-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00069-4962 | PS5-60-BI-0006E-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-4963 | PS5-60-BI-0006E-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00069-4964 | PS5-60-BI-0006E-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00069-4965 | PS5-60-BI-0006E-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00069-4966 | PS5-60-BI-0006E-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-4967 | PS5-60-BI-0006E-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00069-4968 | PS5-60-BI-0006F-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-4969 | PS5-60-BI-0006F-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00069-4970 | PS5-60-BI-0006F-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00069-4971 | PS5-60-BI-0006F-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00069-4972 | PS5-60-BI-0006F-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-4973 | PS5-60-BI-0006F-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00069-4974 | PS5-60-BI-0006G-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-4975 | PS5-60-BI-0006G-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00069-4976 | PS5-60-BI-0006G-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00069-4977 | PS5-60-BI-0006G-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00069-4978 | PS5-60-BI-0006G-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-4979 | PS5-60-BI-0006G-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00069-4980 | PS5-60-BI-0008A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00069-4981 | PS5-60-BI-0008A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00069-4982 | PS5-60-BI-0008B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00069-4983 | PS5-60-BI-0008B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00069-4984 | PS5-60-BI-0009A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00069-4985 | PS5-60-BI-0009A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00069-4986 | PS5-60-BI-0009B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00069-4987 | PS5-60-BI-0009B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-4988 | PS5-60-BI-0010A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00069-4989 | PS5-60-BI-0010A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00069-4990 | PS5-60-BI-0010B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00069-4991 | PS5-60-BI-0010B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-4992 | PS5-60-BI-0011A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00069-4993 | PS5-60-BI-0011A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00069-4994 | PS5-60-BI-0011B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00069-4995 | PS5-60-BI-0011B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-4996 | PS5-60-BI-0012A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00069-4997 | PS5-60-BI-0012A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-4998 | PS5-60-BI-0012B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00069-4999 | PS5-60-BI-0012B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-5000 | PS5-60-BI-0013A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00069-5001 | PS5-60-BI-0013A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-5002 | PS5-60-BI-0013B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00069-5003 | PS5-60-BI-0013B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-5004 | PS5-60-BI-0014A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00069-5005 | PS5-60-BI-0014A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00069-5006 | PS5-60-BI-0014B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00069-5007 | PS5-60-BI-0014B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00069-5008 | PS5-60-BI-0016A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5009 | PS5-60-BI-0016A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-64-12-0102
T-00069-5010 | PS5-60-BI-0016A-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5011 | PS5-60-BI-0016A-CCO4 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00069-5012 | PS5-60-BI-0016B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5013 | PS5-60-BI-0016B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5014 | PS5-60-BI-0016B-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5015 | PS5-60-BI-0016B-CCO4 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00069-5016 | PS5-60-BI-0016C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5017 | PS5-60-BI-0016C-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00069-5018 | PS5-60-BI-0016C-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5019 | PS5-60-BI-0016C-CCO4 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00069-5020 | PS5-60-BI-0016D-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5021 | PS5-60-BI-0016D-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00069-5022 | PS5-60-BI-0016D-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5023 | PS5-60-BI-0016D-CCO4 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00069-5024 | PS5-60-BI-0016E-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5025 | PS5-60-BI-0016E-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00069-5026 | PS5-60-BI-0016E-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5027 | PS5-60-BI-0016E-CCO4 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00069-5028 | PS5-60-BI-0016F-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5029 | PS5-60-BI-0016F-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00069-5030 | PS5-60-BI-0016F-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5031 | PS5-60-BI-0016F-CCO4 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00069-5032 | PS5-60-BI-0016G-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5033 | PS5-60-BI-0016G-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00069-5034 | PS5-60-BI-0016G-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5035 | PS5-60-BI-0016G-CCO4 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00069-5036 | PS5-60-BI-0017A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed
T-00069-5037 | PS5-60-BI-0017B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed |  | CPP-RFI-68-64-12-0101
T-00069-5038 | PS5-60-BI-0017C-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00069-5039 | PS5-60-BI-0017D-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00069-5040 | PS5-60-BI-0017E-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00069-5041 | PS5-60-BI-0017F-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00069-5042 | PS5-60-BI-0017G-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00069-5043 | PS5-60-BI-0019A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5044 | PS5-60-BI-0019A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5045 | PS5-60-BI-0019B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5046 | PS5-60-BI-0019B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5047 | PS5-60-BI-0019C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5048 | PS5-60-BI-0019C-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5049 | PS5-60-BI-0019D-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5050 | PS5-60-BI-0019D-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5051 | PS5-60-BI-0019E-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5052 | PS5-60-BI-0019E-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5053 | PS5-60-BI-0019F-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00069-5054 | PS5-60-BI-0019F-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5055 | PS5-60-BI-0019G-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00069-5056 | PS5-60-BI-0019G-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5057 | PS5-60-IE-0002B-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00069-5058 | PS5-60-IE-0002C-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5059 | PS5-60-IE-0002D-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5060 | PS5-60-IE-0002E-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5061 | PS5-60-IE-0002F-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5062 | PS5-60-IE-0002G-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5063 | PS5-60-IE-0003A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5064 | PS5-60-IE-0003A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5065 | PS5-60-IE-0003A-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed
T-00069-5066 | PS5-60-IE-0003A-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed
T-00069-5067 | PS5-60-IE-0003A-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5068 | PS5-60-IE-0003A-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5069 | PS5-60-IE-0003A-CC07 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00069-5070 | PS5-60-IE-0003A-CC08 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5071 | PS5-60-IE-0003A-CC09 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5072 | PS5-60-IE-0003A-CC10 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed |  | CPP-RFI-68-64-12-0101
T-00069-5073 | PS5-60-IE-0003A-CC11 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed |  | CPP-RFI-68-64-12-0101
T-00069-5074 | PS5-60-IE-0003A-CC15 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5075 | PS5-60-IE-0003A-CC16 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5076 | PS5-60-IE-0003A-CC17 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5081 | PS5-60-IE-0003A-CC25 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5082 | PS5-60-IE-0003A-CC26 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5083 | PS5-60-IE-0003B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5084 | PS5-60-IE-0003B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5085 | PS5-60-IE-0003B-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5086 | PS5-60-IE-0003B-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00069-5087 | PS5-60-IE-0003B-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00069-5088 | PS5-60-IE-0003B-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00069-5089 | PS5-60-IE-0003B-CC07 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00069-5090 | PS5-60-IE-0003B-CC08 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5091 | PS5-60-IE-0003B-CC09 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5092 | PS5-60-IE-0003B-CC10 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed |  | CPP-RFI-68-64-12-0101
T-00069-5093 | PS5-60-IE-0003B-CC11 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed |  | CPP-RFI-68-64-12-0101
T-00069-5094 | PS5-60-IE-0003B-CC15 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5095 | PS5-60-IE-0003B-CC16 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5096 | PS5-60-IE-0003B-CC17 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5101 | PS5-60-IE-0003B-CC25 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5102 | PS5-60-IE-0003B-CC26 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5103 | PS5-60-IE-0003C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00069-5104 | PS5-60-IE-0003C-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00069-5105 | PS5-60-IE-0003C-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00069-5106 | PS5-60-IE-0003C-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00069-5107 | PS5-60-IE-0003C-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00069-5108 | PS5-60-IE-0003C-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00069-5109 | PS5-60-IE-0003C-CC07 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00069-5110 | PS5-60-IE-0003C-CC08 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5111 | PS5-60-IE-0003C-CC09 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5112 | PS5-60-IE-0003C-CC10 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00069-5113 | PS5-60-IE-0003C-CC11 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00069-5114 | PS5-60-IE-0003C-CC15 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00069-5115 | PS5-60-IE-0003C-CC16 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5116 | PS5-60-IE-0003C-CC17 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5121 | PS5-60-IE-0003C-CC25 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5122 | PS5-60-IE-0003C-CC26 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5123 | PS5-60-IE-0003D-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00069-5124 | PS5-60-IE-0003D-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00069-5125 | PS5-60-IE-0003D-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00069-5126 | PS5-60-IE-0003D-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00069-5127 | PS5-60-IE-0003D-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00069-5128 | PS5-60-IE-0003D-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00069-5129 | PS5-60-IE-0003D-CC07 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00069-5130 | PS5-60-IE-0003D-CC08 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5131 | PS5-60-IE-0003D-CC09 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5132 | PS5-60-IE-0003D-CC10 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00069-5133 | PS5-60-IE-0003D-CC11 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00069-5134 | PS5-60-IE-0003D-CC15 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00069-5135 | PS5-60-IE-0003D-CC16 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5136 | PS5-60-IE-0003D-CC17 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5141 | PS5-60-IE-0003D-CC25 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5142 | PS5-60-IE-0003D-CC26 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5143 | PS5-60-IE-0003E-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00069-5144 | PS5-60-IE-0003E-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00069-5145 | PS5-60-IE-0003E-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00069-5146 | PS5-60-IE-0003E-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00069-5147 | PS5-60-IE-0003E-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00069-5148 | PS5-60-IE-0003E-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5149 | PS5-60-IE-0003E-CC07 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00069-5150 | PS5-60-IE-0003E-CC08 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5151 | PS5-60-IE-0003E-CC09 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5152 | PS5-60-IE-0003E-CC10 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00069-5153 | PS5-60-IE-0003E-CC11 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00069-5154 | PS5-60-IE-0003E-CC15 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00069-5155 | PS5-60-IE-0003E-CC16 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5156 | PS5-60-IE-0003E-CC17 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5161 | PS5-60-IE-0003E-CC25 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5162 | PS5-60-IE-0003E-CC26 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5163 | PS5-60-IE-0003F-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00069-5164 | PS5-60-IE-0003F-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00069-5165 | PS5-60-IE-0003F-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00069-5166 | PS5-60-IE-0003F-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00069-5167 | PS5-60-IE-0003F-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00069-5168 | PS5-60-IE-0003F-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00069-5169 | PS5-60-IE-0003F-CC07 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00069-5170 | PS5-60-IE-0003F-CC08 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00069-5171 | PS5-60-IE-0003F-CC09 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00069-5172 | PS5-60-IE-0003F-CC10 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00069-5173 | PS5-60-IE-0003F-CC11 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00069-5174 | PS5-60-IE-0003F-CC15 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00069-5175 | PS5-60-IE-0003F-CC16 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5176 | PS5-60-IE-0003F-CC17 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5181 | PS5-60-IE-0003F-CC25 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5182 | PS5-60-IE-0003F-CC26 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5183 | PS5-60-IE-0003G-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00069-5184 | PS5-60-IE-0003G-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00069-5185 | PS5-60-IE-0003G-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5186 | PS5-60-IE-0003G-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00069-5187 | PS5-60-IE-0003G-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00069-5188 | PS5-60-IE-0003G-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00069-5189 | PS5-60-IE-0003G-CC07 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00069-5190 | PS5-60-IE-0003G-CC08 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00069-5191 | PS5-60-IE-0003G-CC09 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00069-5192 | PS5-60-IE-0003G-CC10 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00069-5193 | PS5-60-IE-0003G-CC11 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00069-5194 | PS5-60-IE-0003G-CC15 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00069-5195 | PS5-60-IE-0003G-CC16 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5196 | PS5-60-IE-0003G-CC17 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5201 | PS5-60-IE-0003G-CC25 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5202 | PS5-60-IE-0003G-CC26 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5203 | PS5-60-IE-0004-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00069-5204 | PS5-60-IE-0004-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00069-5205 | PS5-60-IE-0004-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00069-5206 | PS5-60-IE-0004-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00069-5207 | PS5-60-IE-0004-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00069-5208 | PS5-60-IE-0004-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00069-5209 | PS5-60-IE-0004-CC07 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00069-5213 | PS5-60-IN-0001A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5214 | PS5-60-IN-0001A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | To be completed
T-00069-5215 | PS5-60-IN-0001A-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5216 | PS5-60-IN-0001A-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5217 | PS5-60-IN-0001B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5218 | PS5-60-IN-0001B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | To be completed
T-00069-5219 | PS5-60-IN-0001B-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5220 | PS5-60-IN-0001B-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5221 | PS5-60-IN-0001C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5222 | PS5-60-IN-0001C-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5223 | PS5-60-IN-0001C-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5224 | PS5-60-IN-0001C-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5225 | PS5-60-IN-0001D-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5226 | PS5-60-IN-0001D-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5227 | PS5-60-IN-0001D-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5228 | PS5-60-IN-0001D-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5229 | PS5-60-IN-0001E-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5230 | PS5-60-IN-0001E-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5231 | PS5-60-IN-0001E-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5232 | PS5-60-IN-0001E-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5233 | PS5-60-IN-0001F-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5234 | PS5-60-IN-0001F-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5235 | PS5-60-IN-0001F-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5236 | PS5-60-IN-0001F-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5237 | PS5-60-IN-0001G-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5238 | PS5-60-IN-0001G-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5239 | PS5-60-IN-0001G-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5240 | PS5-60-IN-0001G-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5241 | PS5-60-IN-0002A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed |  | CPP-RFI-68-64-12-0099
T-00069-5242 | PS5-60-IN-0002A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed |  | CPP-RFI-68-64-12-0101
T-00069-5243 | PS5-60-IN-0002A-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed
T-00069-5244 | PS5-60-IN-0002A-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5245 | PS5-60-IN-0002A-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5246 | PS5-60-IN-0002A-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5247 | PS5-60-IN-0002B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5248 | PS5-60-IN-0002B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed |  | CPP-RFI-68-64-12-0101
T-00069-5249 | PS5-60-IN-0002B-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00069-5250 | PS5-60-IN-0002B-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5251 | PS5-60-IN-0002B-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00069-5252 | PS5-60-IN-0002B-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5253 | PS5-60-IN-0002C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5254 | PS5-60-IN-0002C-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00069-5255 | PS5-60-IN-0002C-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00069-5256 | PS5-60-IN-0002C-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5257 | PS5-60-IN-0002C-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00069-5258 | PS5-60-IN-0002C-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5259 | PS5-60-IN-0002D-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5260 | PS5-60-IN-0002D-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00069-5261 | PS5-60-IN-0002D-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00069-5262 | PS5-60-IN-0002D-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5263 | PS5-60-IN-0002D-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00069-5264 | PS5-60-IN-0002D-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5265 | PS5-60-IN-0002E-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5266 | PS5-60-IN-0002E-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00069-5267 | PS5-60-IN-0002E-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00069-5268 | PS5-60-IN-0002E-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5269 | PS5-60-IN-0002E-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00069-5270 | PS5-60-IN-0002E-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5271 | PS5-60-IN-0002F-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5272 | PS5-60-IN-0002F-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00069-5273 | PS5-60-IN-0002F-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00069-5274 | PS5-60-IN-0002F-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5275 | PS5-60-IN-0002F-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00069-5276 | PS5-60-IN-0002F-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5277 | PS5-60-IN-0002G-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5278 | PS5-60-IN-0002G-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00069-5279 | PS5-60-IN-0002G-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00069-5280 | PS5-60-IN-0002G-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5281 | PS5-60-IN-0002G-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00069-5282 | PS5-60-IN-0002G-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5283 | PS5-60-IN-0004A-CC11 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00069-5284 | PS5-60-LA-0002A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-64-12-0099
T-00069-5285 | PS5-60-LA-0002A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-64-12-0099
T-00069-5286 | PS5-60-LA-0002A-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-64-12-0099
T-00069-5287 | PS5-60-LA-0002A-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-64-12-0099
T-00069-5288 | PS5-60-LA-0002A-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-64-12-0099
T-00069-5289 | PS5-60-LA-0002A-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-64-12-0099
T-00069-5290 | PS5-60-LA-0002A-CC07 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-64-12-0101
T-00069-5291 | PS5-60-LA-0002A-CC08 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-64-12-0101
T-00069-5292 | PS5-60-LA-0002A-CC09 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-64-12-0101
T-00069-5293 | PS5-60-LA-0002B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-64-12-0101
T-00069-5294 | PS5-60-LA-0002B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-64-12-0101
T-00069-5295 | PS5-60-LA-0002B-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed |  | CPP-RFI-68-64-12-0101
T-00069-5296 | PS5-60-LA-0002B-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00069-5297 | PS5-60-LA-0002B-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00069-5298 | PS5-60-LA-0002B-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00069-5299 | PS5-60-LA-0002C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5300 | PS5-60-LA-0002C-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5301 | PS5-60-LA-0002C-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5302 | PS5-60-LA-0002C-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0080
T-00069-5303 | PS5-60-LA-0002C-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5304 | PS5-60-LA-0002C-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5305 | PS5-60-LA-0003-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00069-5306 | PS5-60-LIT-4301-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-24 - Cooling Water Tank & Pump | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5307 | PS5-60-LIT-4401-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5308 | PS5-60-MOV-0005-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5309 | PS5-60-MOV-0005-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5310 | PS5-60-MOV-0006-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5311 | PS5-60-MOV-0006-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5312 | PS5-60-MOV-0011-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5313 | PS5-60-MOV-0011-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5314 | PS5-60-MOV-0012-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5315 | PS5-60-MOV-0012-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5316 | PS5-60-SEA-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5317 | PS5-60-SEA-0001-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00069-5318 | PS5-60-SEA-0001-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5319 | PS5-60-SEA-0001-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5320 | PS5-60-SEA-0001-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5321 | PS5-60-SEA-0001-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5322 | PS5-60-SEA-0001-CC07 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5323 | PS5-60-SEA-0001-CC10 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5324 | PS5-60-SEA-0001-CC11 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0082
T-00069-5325 | PS5-60-SEA-0001-CC12 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0082
T-00069-5326 | PS5-60-SEA-0001-CC13 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00069-5327 | PS5-60-SEA-0001-CC14 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5328 | PS5-60-SEA-0001-CC15 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5329 | PS5-60-SEA-0001-CC16 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5330 | PS5-60-SEA-0001-CC17 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5332 | PS5-60-SY-0007-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-28 - Air Receiver A & Air Regulator A | To be completed
T-00069-5333 | PS5-60-SY-0008-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-29 - Air Receiver B & Air Regulator B | To be completed
T-00069-5334 | PS5-60-SY-0009-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-30 - Air Receiver C & Air Regulator C | To be completed
T-00069-5335 | PS5-60-SY-0010-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-31 - Air Receiver D & Air Regulator D | To be completed
T-00069-5336 | PS5-60-SY-0011-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-32 - Air Receiver E & Air Regulator E | To be completed
T-00069-5337 | PS5-60-SY-0012-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-33 - Air Receiver F & Air Regulator F | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5338 | PS5-60-SY-0013-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-34 - Air Receiver G & Air Regulator G | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5339 | PS5-60-VS-9101A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5340 | PS5-60-VS-9101B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5341 | PS5-60-VS-9101C-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5342 | PS5-60-VS-9101D-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5343 | PS5-60-VS-9101E-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5344 | PS5-60-VS-9101F-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5345 | PS5-60-VS-9101G-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5346 | PS5-61-BI-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (120 MTR) Cable tray not yet installed [OPEN]
T-00069-5347 | PS5-61-BI-0001-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (180 MTR) Cable tray not yet installed [OPEN]
T-00069-5348 | PS5-61-BI-0001-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-64-04-0071 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5349 | PS5-61-BI-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00069-5350 | PS5-61-BI-0002-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (180 MTR) Cable tray not yet installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5351 | PS5-61-BI-0002-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-64-04-0071 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5352 | PS5-61-BI-0003-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (100 MTR) Cable tray not yet installed [OPEN]
T-00069-5353 | PS5-61-BI-0003-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (100 MTR) Cable tray not yet installed [OPEN]
T-00069-5354 | PS5-61-BI-0003-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed | CPP-RFI-68-64-04-0071 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5355 | PS5-61-BI-0004-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (100 MTR) Cable tray not yet installed [OPEN]
T-00069-5356 | PS5-61-BI-0004-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (100 MTR) Cable tray not yet installed [OPEN]
T-00069-5357 | PS5-61-BI-0004-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed | CPP-RFI-68-64-04-0071 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5358 | PS5-61-BI-0005-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (55 MTR) Cable tray not yet installed [OPEN]
T-00069-5359 | PS5-61-BI-0005-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (100 MTR) Cable tray not yet installed [OPEN]
T-00069-5360 | PS5-61-BI-0005-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed | CPP-RFI-68-64-04-0071 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5361 | PS5-61-BI-0006-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (50 MTR) Cable tray not yet installed [OPEN]
T-00069-5362 | PS5-61-BI-0006-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (55 MTR) Cable tray not yet installed [OPEN]
T-00069-5363 | PS5-61-BI-0006-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-RFI-68-64-04-0071 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5364 | PS5-61-BI-0007-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (50 MTR) Cable tray not yet installed [OPEN]
T-00069-5365 | PS5-61-BI-0007-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (55 MTR) Cable tray not yet installed [OPEN]
T-00069-5366 | PS5-61-BI-0007-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed | CPP-RFI-68-64-04-0071 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00069-5376 | PS5-71-BAV-0058-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5377 | PS5-71-BAV-0059-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5378 | PS5-71-BI-0001A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00069-5379 | PS5-71-BI-0001B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00069-5381 | PS5-71-BI-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00069-5382 | PS5-71-BI-0003-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5383 | PS5-71-BI-0003-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed
T-00069-5384 | PS5-71-BI-0003-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed
T-00069-5385 | PS5-71-BI-0003-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed
T-00069-5386 | PS5-71-BI-0004-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed
T-00069-5387 | PS5-71-BI-0005-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed
T-00069-5388 | PS5-71-BI-0005-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5389 | PS5-71-BI-0006-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed
T-00069-5390 | PS5-71-BI-0008A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00069-5391 | PS5-71-BI-0008A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00069-5392 | PS5-71-BI-0008B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00069-5393 | PS5-71-BI-0008B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00069-5394 | PS5-71-BI-0009-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00069-5395 | PS5-71-BI-0009-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00069-5396 | PS5-71-BI-0009-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00069-5397 | PS5-71-BI-0009-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00069-5398 | PS5-71-BI-0010-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00069-5399 | PS5-71-BI-0011A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00069-5400 | PS5-71-BI-0011A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00069-5401 | PS5-71-BI-0011A-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00069-5402 | PS5-71-BI-0011A-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00069-5403 | PS5-71-BI-0011A-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00069-5404 | PS5-71-BI-0011B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00069-5405 | PS5-71-BI-0011B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00069-5406 | PS5-71-BI-0011B-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00069-5407 | PS5-71-BI-0011B-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00069-5408 | PS5-71-BI-0011B-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00069-5441 | PS5-71-FCV-0018-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00069-5442 | PS5-71-FCV-0019-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00069-5443 | PS5-71-FCV-0020-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00069-5444 | PS5-71-FIT-0005-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-17 - Diesel Fuel Distribution Header | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5445 | PS5-71-FIT-0011A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00069-5446 | PS5-71-FIT-0011B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00069-5447 | PS5-71-FIT-0012-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-17 - Diesel Fuel Distribution Header | To be completed
T-00069-5448 | PS5-71-FIT-0018-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00069-5449 | PS5-71-FIT-0019-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5450 | PS5-71-FIT-0020-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00069-5451 | PS5-71-FXS-0018-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5452 | PS5-71-FXS-0019-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5453 | PS5-71-FXS-0020-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5454 | PS5-71-FY-0018-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00069-5455 | PS5-71-FY-0019-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5456 | PS5-71-FY-0020-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5457 | PS5-71-IN-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-19 - Diesel Separator Module (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5458 | PS5-71-IN-0001-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-19 - Diesel Separator Module (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5459 | PS5-71-IN-0001-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-19 - Diesel Separator Module (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5460 | PS5-71-IN-0001-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-19 - Diesel Separator Module (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5461 | PS5-71-IN-0001-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-19 - Diesel Separator Module (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5462 | PS5-71-IN-0001-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-19 - Diesel Separator Module (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5463 | PS5-71-IN-0001-CC07 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-19 - Diesel Separator Module (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5467 | PS5-71-IN-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5468 | PS5-71-IN-0002-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | To be completed
T-00069-5469 | PS5-71-IN-0002-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5470 | PS5-71-IN-0002-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5474 | PS5-71-IN-0003-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5475 | PS5-71-IN-0003-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00069-5476 | PS5-71-IN-0003-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5477 | PS5-71-IN-0003-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5481 | PS5-71-IN-0004A-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00069-5482 | PS5-71-IN-0004A-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00069-5483 | PS5-71-IN-0004A-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00069-5484 | PS5-71-IN-0004A-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5485 | PS5-71-IN-0004A-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5486 | PS5-71-IN-0004A-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5487 | PS5-71-IN-0004A-CC07 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5490 | PS5-71-IN-0004A-CC11 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00069-5492 | PS5-71-IN-0004A-CC13 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00069-5493 | PS5-71-IN-0004B-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00069-5494 | PS5-71-IN-0004B-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00069-5495 | PS5-71-IN-0004B-CC03 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00069-5496 | PS5-71-IN-0004B-CC04 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5497 | PS5-71-IN-0004B-CC05 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00069-5498 | PS5-71-IN-0004B-CC06 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5499 | PS5-71-IN-0004B-CC07 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00069-5502 | PS5-71-IN-0004B-CC11 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00069-5504 | PS5-71-LCV-4101-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00069-5505 | PS5-71-LI-4201B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5506 | PS5-71-LIT-1201-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5507 | PS5-71-LIT-1202-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5508 | PS5-71-LIT-4101-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00069-5509 | PS5-71-LIT-4102-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00069-5510 | PS5-71-LIT-4201-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5511 | PS5-71-LIT-4202-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5512 | PS5-71-LIT-4401-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-15 - Diesel Fuel Storage Tank | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5513 | PS5-71-LIT-4402-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-15 - Diesel Fuel Storage Tank | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5514 | PS5-71-LXS-4101-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5515 | PS5-71-LY-4101-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00069-5516 | PS5-71-MOV-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed |  | CPP-RFI-68-64-12-0099
T-00069-5517 | PS5-71-MOV-0001-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed |  | CPP-RFI-68-64-12-0099
T-00069-5518 | PS5-71-MOV-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed |  | CPP-RFI-68-64-12-0099
T-00069-5519 | PS5-71-MOV-0002-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed |  | CPP-RFI-68-64-12-0099
T-00069-5520 | PS5-71-MOV-0003-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5521 | PS5-71-MOV-0003-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5522 | PS5-71-MOV-0004-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed |  | CPP-RFI-68-64-12-0099
T-00069-5523 | PS5-71-MOV-0004-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed |  | CPP-RFI-68-64-12-0099
T-00069-5524 | PS5-71-MOV-0007-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5525 | PS5-71-MOV-0007-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5526 | PS5-71-MOV-0008-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5527 | PS5-71-MOV-0008-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5528 | PS5-71-MOV-0009-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5529 | PS5-71-MOV-0009-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5530 | PS5-71-MOV-0010-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5531 | PS5-71-MOV-0010-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed |  | CPP-RFI-68-64-04-0100
T-00069-5532 | PS5-71-PDIT-0030-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00069-5533 | PS5-71-PDIT-0056A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00069-5534 | PS5-71-PDIT-0056B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00069-5535 | PS5-71-PIT-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5536 | PS5-71-PIT-0014-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-17 - Diesel Fuel Distribution Header | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5537 | PS5-71-PIT-0018A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00069-5538 | PS5-71-PIT-0019A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5539 | PS5-71-PIT-0020A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00069-5540 | PS5-71-PIT-0022-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5541 | PS5-71-PIT-0029-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-15 - Diesel Fuel Storage Tank | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5542 | PS5-71-PIT-0039-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5543 | PS5-71-PIT-0089-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00069-5544 | PS5-71-PIT-0090-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5545 | PS5-71-PIT-0091-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5546 | PS5-71-PIT-0092-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5547 | PS5-71-PIT-2402A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00069-5548 | PS5-71-PIT-2402B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00069-5549 | PS5-71-PIT-3301A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5550 | PS5-71-PIT-3301B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5551 | PS5-71-PIT-3302A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5552 | PS5-71-PIT-3302B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5553 | PS5-71-PIT-3401A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5554 | PS5-71-PIT-3401B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5555 | PS5-71-PIT-3402A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5556 | PS5-71-PIT-3402B-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5557 | PS5-71-PIT-4101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00069-5558 | PS5-71-SDV-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed |  | CPP-RFI-68-64-12-0099
T-00069-5559 | PS5-71-SDV-0001-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed
T-00069-5560 | PS5-71-SDV-0022-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00069-5561 | PS5-71-SDV-0022-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00069-5562 | PS5-71-SDV-0029-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-15 - Diesel Fuel Storage Tank | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5563 | PS5-71-SDV-0029-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-15 - Diesel Fuel Storage Tank | To be completed
T-00069-5564 | PS5-71-SDV-0039-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5565 | PS5-71-SDV-0039-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5566 | PS5-71-SXS-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed |  | CPP-RFI-68-64-12-0099
T-00069-5567 | PS5-71-SXS-0022-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5568 | PS5-71-SXS-0029-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-15 - Diesel Fuel Storage Tank | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5569 | PS5-71-SXS-0039-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5570 | PS5-71-SY-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed |  | CPP-RFI-68-64-12-0099
T-00069-5571 | PS5-71-SY-0022-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5572 | PS5-71-SY-0029-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-15 - Diesel Fuel Storage Tank | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5573 | PS5-71-SY-0039-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5574 | PS5-71-TIT-0003-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00069-5575 | PS5-71-TIT-0004-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00069-5576 | PS5-71-TIT-0006-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5577 | PS5-71-TIT-0007-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5578 | PS5-71-TIT-2204-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5579 | PS5-71-TIT-2301-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00069-5580 | PS5-71-TIT-2402AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5581 | PS5-71-TIT-2402BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5584 | PS5-71-TIT-4102-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00069-5585 | PS5-71-TIT-4103-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00069-5586 | PS5-71-TIT-4202-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5587 | PS5-71-TIT-4203-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5588 | PS5-71-XV-0089-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00069-5589 | PS5-71-XV-0089-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00069-5590 | PS5-71-XV-0090-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5591 | PS5-71-XV-0090-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00069-5592 | PS5-71-XV-0091-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5593 | PS5-71-XV-0091-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00069-5594 | PS5-71-XV-0092-CC01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5595 | PS5-71-XV-0092-CC02 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed
T-00069-5596 | PS5-71-XXS-0089-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5597 | PS5-71-XXS-0090-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5598 | PS5-71-XXS-0091-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5599 | PS5-71-XXS-0092-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5600 | PS5-71-XY-0089-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5601 | PS5-71-XY-0090-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00069-5602 | PS5-71-XY-0091-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5603 | PS5-71-XY-0092-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00069-5606 | PS5-74-PIT-0002-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-74-04 - Nitrogen Distribution Header | To be completed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00069-9408 | PS5-03-RMAC-1409-CJ01 | CJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00070-0051 | PS5-71-FO-0013B | CJX11 - Orifice plate | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | To be completed
T-00070-0052 | PS5-28-FO-0009A | CJX11 - Orifice plate | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00070-0053 | PS5-28-FO-0009B | CJX11 - Orifice plate | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00070-0054 | PS5-28-FO-0003 | CJX11 - Orifice plate | I | PS5-28-05 - HP Relief Header | To be completed
T-00070-0055 | PS5-50-FE-0001 | CJX11 - Orifice plate | I | PS5-50-03 - Water Pre-Treatment Package | To be completed
T-00070-0056 | PS5-60-FO-0002 | CJX11 - Orifice plate | I | PS5-60-24 - Cooling Water Tank & Pump | To be completed
T-00070-0057 | PS5-28-FO-0005 | CJX11 - Orifice plate | I | PS5-28-06 - Relief Drum and Pump | To be completed
T-00070-0058 | PS5-60-FO-0001 | CJX11 - Orifice plate | I | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | To be completed
T-00070-0059 | PS5-25-FO-0008 | CJX11 - Orifice plate | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed
T-00070-0060 | PS5-71-FO-0013A | CJX11 - Orifice plate | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | To be completed
T-00070-0061 | PS5-74-FO-0001 | CJX11 - Orifice plate | I | PS5-74-04 - Nitrogen Distribution Header | To be completed
T-00070-0062 | PS5-28-FO-0002A | CJX11 - Orifice plate | I | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00070-0063 | PS5-28-FO-0002B | CJX11 - Orifice plate | I | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00070-0064 | PS5-28-FO-0004 | CJX11 - Orifice plate | I | PS5-28-16 - LP Relief Header | To be completed
T-00070-0065 | PS5-28-FO-0006 | CJX11 - Orifice plate | I | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00070-0066 | PS5-28-FO-0007 | CJX11 - Orifice plate | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00071-0023 | PS5-09-LB-0006-CX01 | CJX12 - Optical fiber cable | I | PS5-09-01 - HVAC for Office and Facilities building | To be completed
T-00071-0024 | PS5-09-LB-0007-CX01 | CJX12 - Optical fiber cable | I | PS5-09-04 - HVAC for Workshop & Warehouse | To be completed | CPP-RFI-68-64-04-0043 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable coiled 155mtr,Cable to be laid in trench [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00071-0025 | PS5-09-LB-0008-CX01 | CJX12 - Optical fiber cable | I | PS5-09-03 - HVAC for Generator Building | To be completed | CPP-RFI-68-64-04-0054 |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00071-0026 | PS5-53-LA-0001-CX01 | CJX12 - Optical fiber cable | I | PS5-53-04 - Water Treatment Purification Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00071-0027 | PS5-60-IE-0004-CX03 | CJX12 - Optical fiber cable | I | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-RFI-68-64-04-0054 |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00071-0028 | PS5-60-IE-0004-CX04 | CJX12 - Optical fiber cable | I | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-RFI-68-64-04-0054 |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00071-0029 | PS5-60-LA-0003-CX01 | CJX12 - Optical fiber cable | I | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-68-64-04-0078
T-00071-0030 | PS5-74-LB-5101-CX01 | CJX12 - Optical fiber cable | I | PS5-74-02 - N2 Generation Skid (UCP) | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00071-0031 | PS5-82-LA-0001-CX01 | CJX12 - Optical fiber cable | I | PS5-82-03 - Sewage Treatment Plant Package (UCP) | To be completed | CPP-RFI-68-64-04-0037 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00071-0085 | PS5-75-LA-6200-CX01 | CJX12 - Optical fiber cable | I | PS5-75-01 - DRA Injection Package | To be completed | CPP-RFI-68-64-04-0049 |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00071-0090 | PS5-60-LA-0003-CX02 | CJX12 - Optical fiber cable | I | PS5-60-22 - Power Gen Master UCP | To be completed |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00072-0165 | PS5-60-TW-0006G | CJX13 - Thermowell | I | PS5-60-76 - Engine G Cooling system | To be completed
T-00072-0166 | PS5-71-TW-4203 | CJX13 - Thermowell | I | PS5-71-12 - CFO Service Tank | To be completed
T-00072-0167 | PS5-71-TW-0007 | CJX13 - Thermowell | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00072-0168 | PS5-71-TW-0003 | CJX13 - Thermowell | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00072-0169 | PS5-60-TW-0007C | CJX13 - Thermowell | I | PS5-60-72 - Engine C Cooling system | To be completed
T-00072-0170 | PS5-71-TW-0004 | CJX13 - Thermowell | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00072-0171 | PS5-60-TW-0005F | CJX13 - Thermowell | I | PS5-60-75 - Engine F Cooling system | To be completed
T-00072-0172 | PS5-28-TW-1201 | CJX13 - Thermowell | I | PS5-28-06 - Relief Drum and Pump | To be completed
T-00072-0173 | PS5-60-TW-0007B | CJX13 - Thermowell | I | PS5-60-71 - Engine B Cooling system | To be completed
T-00072-0174 | PS5-60-TW-0006C | CJX13 - Thermowell | I | PS5-60-72 - Engine C Cooling system | To be completed
T-00072-0175 | PS5-60-TW-0008A | CJX13 - Thermowell | I | PS5-60-70 - Engine A Cooling system | To be completed
T-00072-0176 | PS5-60-TW-0007D | CJX13 - Thermowell | I | PS5-60-73 - Engine D Cooling system | To be completed
T-00072-0177 | PS5-60-TW-0008C | CJX13 - Thermowell | I | PS5-60-72 - Engine C Cooling system | To be completed
T-00072-0178 | PS5-28-TW-1402 | CJX13 - Thermowell | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00072-0179 | PS5-60-TW-0005G | CJX13 - Thermowell | I | PS5-60-76 - Engine G Cooling system | To be completed
T-00072-0180 | PS5-28-TW-1104 | CJX13 - Thermowell | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00072-0181 | PS5-60-TW-0008E | CJX13 - Thermowell | I | PS5-60-74 - Engine E Cooling system | To be completed
T-00072-0182 | PS5-60-TW-0007A | CJX13 - Thermowell | I | PS5-60-70 - Engine A Cooling system | To be completed
T-00072-0183 | PS5-60-TW-0006D | CJX13 - Thermowell | I | PS5-60-73 - Engine D Cooling system | To be completed
T-00072-0184 | PS5-60-TW-0008B | CJX13 - Thermowell | I | PS5-60-71 - Engine B Cooling system | To be completed
T-00072-0185 | PS5-60-TW-0007E | CJX13 - Thermowell | I | PS5-60-74 - Engine E Cooling system | To be completed
T-00072-0186 | PS5-60-TW-0008D | CJX13 - Thermowell | I | PS5-60-73 - Engine D Cooling system | To be completed
T-00072-0187 | PS5-25-TW-0003B | CJX13 - Thermowell | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00072-0188 | PS5-71-TW-4202 | CJX13 - Thermowell | I | PS5-71-12 - CFO Service Tank | To be completed
T-00072-0189 | PS5-60-TW-0008F | CJX13 - Thermowell | I | PS5-60-75 - Engine F Cooling system | To be completed
T-00072-0190 | PS5-60-TW-0006E | CJX13 - Thermowell | I | PS5-60-74 - Engine E Cooling system | To be completed
T-00072-0191 | PS5-25-TW-0002A | CJX13 - Thermowell | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00072-0192 | PS5-25-TW-0003C | CJX13 - Thermowell | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00072-0193 | PS5-71-TW-0006 | CJX13 - Thermowell | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00072-0194 | PS5-60-TW-0006B | CJX13 - Thermowell | I | PS5-60-71 - Engine B Cooling system | To be completed
T-00072-0195 | PS5-25-TW-0003A | CJX13 - Thermowell | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00072-0196 | PS5-71-TW-4103 | CJX13 - Thermowell | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00072-0197 | PS5-28-TW-1105 | CJX13 - Thermowell | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00072-0198 | PS5-60-TW-0006A | CJX13 - Thermowell | I | PS5-60-70 - Engine A Cooling system | To be completed
T-00072-0199 | PS5-60-TW-0007F | CJX13 - Thermowell | I | PS5-60-75 - Engine F Cooling system | To be completed
T-00072-0200 | PS5-25-TW-0002B | CJX13 - Thermowell | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00072-0201 | PS5-25-TW-0001 | CJX13 - Thermowell | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00072-0202 | PS5-25-TW-0004 | CJX13 - Thermowell | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00072-0203 | PS5-25-TW-0002C | CJX13 - Thermowell | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00072-0204 | PS5-71-TW-4102 | CJX13 - Thermowell | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00072-0205 | PS5-74-TW-0001 | CJX13 - Thermowell | I | PS5-74-04 - Nitrogen Distribution Header | To be completed
T-00072-0206 | PS5-28-TW-1401 | CJX13 - Thermowell | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00072-0207 | PS5-60-TW-0005A | CJX13 - Thermowell | I | PS5-60-70 - Engine A Cooling system | To be completed
T-00072-0208 | PS5-60-TW-0005B | CJX13 - Thermowell | I | PS5-60-71 - Engine B Cooling system | To be completed
T-00072-0209 | PS5-60-TW-0005C | CJX13 - Thermowell | I | PS5-60-72 - Engine C Cooling system | To be completed
T-00072-0210 | PS5-60-TW-0005D | CJX13 - Thermowell | I | PS5-60-73 - Engine D Cooling system | To be completed
T-00072-0211 | PS5-60-TW-0005E | CJX13 - Thermowell | I | PS5-60-74 - Engine E Cooling system | To be completed
T-00072-0212 | PS5-60-TW-0006F | CJX13 - Thermowell | I | PS5-60-75 - Engine F Cooling system | To be completed
T-00072-0213 | PS5-60-TW-0007G | CJX13 - Thermowell | I | PS5-60-76 - Engine G Cooling system | To be completed
T-00072-0214 | PS5-60-TW-0008G | CJX13 - Thermowell | I | PS5-60-76 - Engine G Cooling system | To be completed
T-00075-0197 | PS5-25-PG-1101B | CJX16 - Local gauge / indicator | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00075-0198 | PS5-28-PG-0001 | CJX16 - Local gauge / indicator | I | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00075-0199 | PS5-28-PG-0071 | CJX16 - Local gauge / indicator | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00075-0200 | PS5-60-TG-0005C | CJX16 - Local gauge / indicator | I | PS5-60-72 - Engine C Cooling system | To be completed
T-00075-0201 | PS5-71-PG-0044 | CJX16 - Local gauge / indicator | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00075-0202 | PS5-60-TG-0006F | CJX16 - Local gauge / indicator | I | PS5-60-75 - Engine F Cooling system | To be completed
T-00075-0203 | PS5-28-PG-0067B | CJX16 - Local gauge / indicator | I | PS5-28-17 - Reinjection Pump | To be completed
T-00075-0204 | PS5-60-TG-0005E | CJX16 - Local gauge / indicator | I | PS5-60-74 - Engine E Cooling system | To be completed
T-00075-0205 | PS5-60-TG-0008D | CJX16 - Local gauge / indicator | I | PS5-60-73 - Engine D Cooling system | To be completed
T-00075-0206 | PS5-71-PG-0053B | CJX16 - Local gauge / indicator | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00075-0207 | PS5-71-PG-0053A | CJX16 - Local gauge / indicator | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00075-0208 | PS5-28-PG-0070C | CJX16 - Local gauge / indicator | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00075-0209 | PS5-71-PG-0050B | CJX16 - Local gauge / indicator | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00075-0210 | PS5-71-PG-0050A | CJX16 - Local gauge / indicator | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00075-0211 | PS5-60-TG-0005A | CJX16 - Local gauge / indicator | I | PS5-60-70 - Engine A Cooling system | To be completed
T-00075-0212 | PS5-28-PG-0007A | CJX16 - Local gauge / indicator | I | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00075-0213 | PS5-25-PG-1201A | CJX16 - Local gauge / indicator | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00075-0214 | PS5-60-PG-0002F | CJX16 - Local gauge / indicator | I | PS5-60-33 - Air Receiver F & Air Regulator F | To be completed
T-00075-0215 | PS5-60-TG-0007G | CJX16 - Local gauge / indicator | I | PS5-60-76 - Engine G Cooling system | To be completed
T-00075-0216 | PS5-60-TG-0005F | CJX16 - Local gauge / indicator | I | PS5-60-75 - Engine F Cooling system | To be completed
T-00075-0217 | PS5-60-TG-0006G | CJX16 - Local gauge / indicator | I | PS5-60-76 - Engine G Cooling system | To be completed
T-00075-0218 | PS5-60-TG-0008A | CJX16 - Local gauge / indicator | I | PS5-60-70 - Engine A Cooling system | To be completed
T-00075-0219 | PS5-25-PG-1101A | CJX16 - Local gauge / indicator | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00075-0220 | PS5-60-PG-0027 | CJX16 - Local gauge / indicator | I | PS5-60-24 - Cooling Water Tank & Pump | To be completed
T-00075-0221 | PS5-60-PG-0002A | CJX16 - Local gauge / indicator | I | PS5-60-28 - Air Receiver A & Air Regulator A | To be completed
T-00075-0222 | PS5-28-PG-1401 | CJX16 - Local gauge / indicator | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00075-0223 | PS5-53-PG-0022B | CJX16 - Local gauge / indicator | I | PS5-53-02 - Water Distribution Pump A/B | To be completed
T-00075-0224 | PS5-60-TG-0008C | CJX16 - Local gauge / indicator | I | PS5-60-72 - Engine C Cooling system | To be completed
T-00075-0225 | PS5-60-PG-0002C | CJX16 - Local gauge / indicator | I | PS5-60-30 - Air Receiver C & Air Regulator C | To be completed
T-00075-0226 | PS5-60-PG-0002E | CJX16 - Local gauge / indicator | I | PS5-60-32 - Air Receiver E & Air Regulator E | To be completed
T-00075-0227 | PS5-71-PDG-0043A | CJX16 - Local gauge / indicator | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | To be completed
T-00075-0228 | PS5-28-PG-0014A | CJX16 - Local gauge / indicator | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00075-0229 | PS5-60-TG-0007D | CJX16 - Local gauge / indicator | I | PS5-60-73 - Engine D Cooling system | To be completed
T-00075-0230 | PS5-74-TG-0001 | CJX16 - Local gauge / indicator | I | PS5-74-04 - Nitrogen Distribution Header | To be completed
T-00075-0231 | PS5-53-PG-0022A | CJX16 - Local gauge / indicator | I | PS5-53-02 - Water Distribution Pump A/B | To be completed
T-00075-0232 | PS5-60-PG-0002B | CJX16 - Local gauge / indicator | I | PS5-60-29 - Air Receiver B & Air Regulator B | To be completed
T-00075-0233 | PS5-60-LG-0001 | CJX16 - Local gauge / indicator | I | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | To be completed
T-00075-0234 | PS5-60-TG-0008E | CJX16 - Local gauge / indicator | I | PS5-60-74 - Engine E Cooling system | To be completed
T-00075-0235 | PS5-71-PDG-0043B | CJX16 - Local gauge / indicator | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | To be completed
T-00075-0236 | PS5-28-PG-1201 | CJX16 - Local gauge / indicator | I | PS5-28-06 - Relief Drum and Pump | To be completed
T-00075-0237 | PS5-60-PG-0002D | CJX16 - Local gauge / indicator | I | PS5-60-31 - Air Receiver D & Air Regulator D | To be completed
T-00075-0238 | PS5-74-PG-0001 | CJX16 - Local gauge / indicator | I | PS5-74-03 - Nitrogen Receiver | To be completed
T-00075-0239 | PS5-60-TG-0007A | CJX16 - Local gauge / indicator | I | PS5-60-70 - Engine A Cooling system | To be completed
T-00075-0240 | PS5-71-PG-0005 | CJX16 - Local gauge / indicator | I | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | To be completed
T-00075-0241 | PS5-71-PDG-0049A | CJX16 - Local gauge / indicator | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00075-0242 | PS5-60-TG-0008F | CJX16 - Local gauge / indicator | I | PS5-60-75 - Engine F Cooling system | To be completed
T-00075-0243 | PS5-25-PG-1201B | CJX16 - Local gauge / indicator | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00075-0244 | PS5-60-TG-0007C | CJX16 - Local gauge / indicator | I | PS5-60-72 - Engine C Cooling system | To be completed
T-00075-0245 | PS5-28-PG-0007B | CJX16 - Local gauge / indicator | I | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00075-0246 | PS5-71-PG-0059B | CJX16 - Local gauge / indicator | I | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00075-0247 | PS5-71-PG-0059A | CJX16 - Local gauge / indicator | I | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00075-0248 | PS5-28-PG-0014B | CJX16 - Local gauge / indicator | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00075-0249 | PS5-71-PG-0006A | CJX16 - Local gauge / indicator | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | To be completed
T-00075-0250 | PS5-60-TG-0005G | CJX16 - Local gauge / indicator | I | PS5-60-76 - Engine G Cooling system | To be completed
T-00075-0251 | PS5-60-TG-0006D | CJX16 - Local gauge / indicator | I | PS5-60-73 - Engine D Cooling system | To be completed
T-00075-0252 | PS5-60-TG-0007E | CJX16 - Local gauge / indicator | I | PS5-60-74 - Engine E Cooling system | To be completed
T-00075-0253 | PS5-71-PG-0045 | CJX16 - Local gauge / indicator | I | PS5-71-12 - CFO Service Tank | To be completed
T-00075-0254 | PS5-71-PG-0007 | CJX16 - Local gauge / indicator | I | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | To be completed
T-00075-0255 | PS5-71-PDG-0049B | CJX16 - Local gauge / indicator | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00075-0256 | PS5-71-PG-0006B | CJX16 - Local gauge / indicator | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | To be completed
T-00075-0257 | PS5-25-PG-0010 | CJX16 - Local gauge / indicator | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00075-0258 | PS5-25-PG-0019 | CJX16 - Local gauge / indicator | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00075-0259 | PS5-28-PG-0067A | CJX16 - Local gauge / indicator | I | PS5-28-17 - Reinjection Pump | To be completed
T-00075-0260 | PS5-28-PG-0070A | CJX16 - Local gauge / indicator | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00075-0261 | PS5-28-PG-0070B | CJX16 - Local gauge / indicator | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00075-0262 | PS5-28-PG-1101 | CJX16 - Local gauge / indicator | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00075-0263 | PS5-60-PG-0002G | CJX16 - Local gauge / indicator | I | PS5-60-34 - Air Receiver G & Air Regulator G | To be completed
T-00075-0264 | PS5-60-TG-0005D | CJX16 - Local gauge / indicator | I | PS5-60-73 - Engine D Cooling system | To be completed
T-00075-0265 | PS5-60-TG-0006A | CJX16 - Local gauge / indicator | I | PS5-60-70 - Engine A Cooling system | To be completed
T-00075-0266 | PS5-60-TG-0006C | CJX16 - Local gauge / indicator | I | PS5-60-72 - Engine C Cooling system | To be completed
T-00075-0267 | PS5-60-TG-0006E | CJX16 - Local gauge / indicator | I | PS5-60-74 - Engine E Cooling system | To be completed
T-00075-0268 | PS5-60-TG-0007F | CJX16 - Local gauge / indicator | I | PS5-60-75 - Engine F Cooling system | To be completed
T-00075-0269 | PS5-60-TG-0008G | CJX16 - Local gauge / indicator | I | PS5-60-76 - Engine G Cooling system | To be completed
T-00075-0270 | PS5-60-TG-0006B | CJX16 - Local gauge / indicator | I | PS5-60-71 - Engine B Cooling system | To be completed
T-00075-0271 | PS5-60-TG-0005B | CJX16 - Local gauge / indicator | I | PS5-60-71 - Engine B Cooling system | To be completed
T-00075-0272 | PS5-60-TG-0007B | CJX16 - Local gauge / indicator | I | PS5-60-71 - Engine B Cooling system | To be completed
T-00075-0273 | PS5-60-TG-0008B | CJX16 - Local gauge / indicator | I | PS5-60-71 - Engine B Cooling system | To be completed
T-00075-0376 | PS5-09-PI-8401 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0377 | PS5-09-PI-8402 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0378 | PS5-09-PI-8403 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0379 | PS5-09-PI-8404 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0380 | PS5-09-PI-8405 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0381 | PS5-09-PI-8406 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0382 | PS5-09-PI-8407 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0383 | PS5-09-PI-8408 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0384 | PS5-09-PI-8409 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0385 | PS5-09-PI-8411 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0386 | PS5-09-PI-8412 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0387 | PS5-09-PI-8413 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0388 | PS5-09-PI-8414 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0389 | PS5-09-PI-8415 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0390 | PS5-09-PI-8416 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0391 | PS5-09-TI-8401 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0392 | PS5-09-TI-8402 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0393 | PS5-09-TI-8403 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0394 | PS5-09-TI-8404 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0395 | PS5-09-TI-8405 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0396 | PS5-09-TI-8406 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0397 | PS5-09-TI-8407 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0398 | PS5-09-TI-8408 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0399 | PS5-09-TI-8409 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00075-0400 | PS5-09-TI-8411 | CJX16 - Local gauge / indicator | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00076-0013 | PS5-71-PSE-2401A | CJX20 - Bursting disc | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00076-0014 | PS5-71-PSE-2401B | CJX20 - Bursting disc | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00077-0236 | PS5-25-ESDV-0021 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00077-0237 | PS5-25-ESDV-0023 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00077-0238 | PS5-71-XV-0091 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00077-0239 | PS5-71-XV-0090 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-71-12 - CFO Service Tank | To be completed
T-00077-0240 | PS5-25-SDV-0052 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00077-0241 | PS5-25-SDV-0054A | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00077-0242 | PS5-28-SDV-0053B | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00077-0243 | PS5-71-SDV-0039 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-71-12 - CFO Service Tank | To be completed
T-00077-0244 | PS5-71-SDV-0029 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-71-15 - Diesel Fuel Storage Tank | To be completed
T-00077-0245 | PS5-25-SDV-0036A | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00077-0246 | PS5-25-SDV-0036C | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00077-0247 | PS5-25-SDV-0035B | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00077-0248 | PS5-71-SDV-0022 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00077-0249 | PS5-25-SDV-0054C | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00077-0250 | PS5-28-SDV-0053C | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00077-0251 | PS5-71-XV-0089 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00077-0252 | PS5-28-SDV-0045 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-28-17 - Reinjection Pump | To be completed
T-00077-0253 | PS5-25-XV-0053 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed
T-00077-0254 | PS5-71-XV-0092 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed
T-00077-0255 | PS5-28-SDV-0053A | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00077-0256 | PS5-71-SDV-0001 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed
T-00077-0257 | PS5-25-SDV-0022 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00077-0258 | PS5-25-SDV-0035A | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00077-0259 | PS5-25-SDV-0035C | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00077-0260 | PS5-25-SDV-0036B | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00077-0261 | PS5-25-SDV-0046 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed
T-00077-0262 | PS5-25-SDV-0054B | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00077-0263 | PS5-25-XV-0070 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed
T-00078-0131 | PS5-25-MOV-0001 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00078-0132 | PS5-25-MOV-0008 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00078-0133 | PS5-25-MOV-0025 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00078-0134 | PS5-25-MOV-0028 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00078-0137 | PS5-25-MOV-0026 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00078-0138 | PS5-25-MOV-0027 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00078-0139 | PS5-60-MOV-0012 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-71-12 - CFO Service Tank | To be completed
T-00078-0140 | PS5-71-MOV-0007 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed
T-00078-0141 | PS5-25-MOV-0003 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00078-0142 | PS5-75-MOV-0001 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-28-07 - Open Drains (OD2) | To be completed
T-00078-0143 | PS5-71-MOV-0010 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed
T-00078-0144 | PS5-71-MOV-0003 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed
T-00078-0145 | PS5-25-MOV-0011 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00078-0146 | PS5-60-MOV-0005 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-71-12 - CFO Service Tank | To be completed
T-00078-0147 | PS5-71-MOV-0004 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed
T-00078-0148 | PS5-25-MOV-0012 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00078-0149 | PS5-71-MOV-0001 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed
T-00078-0150 | PS5-60-MOV-0006 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-71-12 - CFO Service Tank | To be completed
T-00078-0151 | PS5-71-MOV-0002 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed
T-00078-0152 | PS5-71-MOV-0008 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed
T-00078-0153 | PS5-71-MOV-0009 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed
T-00078-0154 | PS5-25-MOV-0002 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00078-0155 | PS5-60-MOV-0011 | CJX24 - Actuated on/off valve - Electrical type | I | PS5-71-12 - CFO Service Tank | To be completed
T-00079-0062 | PS5-01-FCV-0004B | CJX27 - Control valve - Pneumatic / Hydraulic type | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00079-0063 | PS5-25-FCV-0004 | CJX27 - Control valve - Pneumatic / Hydraulic type | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00079-0064 | PS5-01-FCV-0003A | CJX27 - Control valve - Pneumatic / Hydraulic type | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00079-0065 | PS5-01-FCV-0003B | CJX27 - Control valve - Pneumatic / Hydraulic type | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00079-0066 | PS5-71-FCV-0018 | CJX27 - Control valve - Pneumatic / Hydraulic type | I | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00079-0067 | PS5-25-FCV-0003B | CJX27 - Control valve - Pneumatic / Hydraulic type | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00079-0068 | PS5-71-LCV-4101 | CJX27 - Control valve - Pneumatic / Hydraulic type | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00079-0069 | PS5-71-FCV-0019 | CJX27 - Control valve - Pneumatic / Hydraulic type | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00079-0070 | PS5-71-FCV-0020 | CJX27 - Control valve - Pneumatic / Hydraulic type | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00079-0071 | PS5-01-FCV-0004A | CJX27 - Control valve - Pneumatic / Hydraulic type | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00079-0072 | PS5-25-FCV-0003A | CJX27 - Control valve - Pneumatic / Hydraulic type | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00079-0073 | PS5-25-FCV-0003C | CJX27 - Control valve - Pneumatic / Hydraulic type | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00080-0003 | PS5-09-TCV-8401 | CJX28 - Control valve - Electrical type | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00080-0004 | PS5-09-TCV-8402 | CJX28 - Control valve - Electrical type | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00082-0459 | PS5-01-BI-0006 | CJX31 - Junction & marshalling box | I | PS5-01-05 - Foam Skid | To be completed | CPP-RFI-68-64-05-0076
T-00082-0482 | PS5-03-BI-2501 | CJX31 - Junction & marshalling box | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-05-0064
T-00082-0497 | PS5-09-BI-2501 | CJX31 - Junction & marshalling box | I | PS5-09-04 - HVAC for Workshop & Warehouse | To be completed
T-00082-0498 | PS5-09-BI-2502 | CJX31 - Junction & marshalling box | I | PS5-09-01 - HVAC for Office and Facilities building | To be completed
T-00082-0499 | PS5-09-BI-2503 | CJX31 - Junction & marshalling box | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00082-1230 | PS5-01-BI-0007 | CJX31 - Junction & marshalling box | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00082-1231 | PS5-01-BI-0008 | CJX31 - Junction & marshalling box | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00082-1232 | PS5-01-BI-0009 | CJX31 - Junction & marshalling box | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00082-1233 | PS5-01-NMR-61001 | CJX31 - Junction & marshalling box | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00082-1234 | PS5-01-NMR-61002 | CJX31 - Junction & marshalling box | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00082-1235 | PS5-01-NMR-61003 | CJX31 - Junction & marshalling box | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00082-1236 | PS5-01-NMR-61004 | CJX31 - Junction & marshalling box | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00082-1237 | PS5-01-NMRA-61001 | CJX31 - Junction & marshalling box | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00082-1238 | PS5-01-NMRA-61002 | CJX31 - Junction & marshalling box | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00082-1239 | PS5-01-NMRA-61003 | CJX31 - Junction & marshalling box | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00082-1240 | PS5-01-NMRA-61004 | CJX31 - Junction & marshalling box | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00083-0184 | PS5-03-GDLHP-0137 | CJX42 - Gas / smoke detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00083-0185 | PS5-03-GDLHP-0142 | CJX42 - Gas / smoke detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00083-0186 | PS5-03-GDLHP-0143 | CJX42 - Gas / smoke detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00083-0187 | PS5-03-GDLHP-0144 | CJX42 - Gas / smoke detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00083-0189 | PS5-03-GDLHP-0401 | CJX42 - Gas / smoke detector | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed
T-00083-0191 | PS5-03-RDH-0302 | CJX42 - Gas / smoke detector | I | PS5-03-03 - FZ-03 - Buildings Area | To be completed
T-00083-0192 | PS5-03-RDH-0303 | CJX42 - Gas / smoke detector | I | PS5-03-03 - FZ-03 - Buildings Area | To be completed
T-00083-0193 | PS5-03-RDH-0601 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0194 | PS5-03-RDH-0602 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0195 | PS5-03-RDH-0603 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0196 | PS5-03-RDH-0604 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0197 | PS5-03-RDH-0605 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0198 | PS5-03-RDH-0606 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0199 | PS5-03-RDH-0607 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0200 | PS5-03-RDH-0608 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0201 | PS5-03-RDH-0609 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0202 | PS5-03-RDH-0610 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0203 | PS5-03-RDH-0611 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0204 | PS5-03-RDH-0612 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0205 | PS5-03-RDH-0614 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0206 | PS5-03-RDH-0615 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0207 | PS5-03-RDH-0616 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0208 | PS5-03-RDH-0617 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0209 | PS5-03-RDH-0618 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0210 | PS5-03-RDH-0828 | CJX42 - Gas / smoke detector | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00083-0211 | PS5-03-RDH-0829 | CJX42 - Gas / smoke detector | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00083-0212 | PS5-03-RDH-0830 | CJX42 - Gas / smoke detector | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00083-0213 | PS5-03-RDH-0831 | CJX42 - Gas / smoke detector | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00083-0214 | PS5-03-RDH-0901 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0215 | PS5-03-RDH-0902 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0216 | PS5-03-RDH-0903 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0217 | PS5-03-RDH-0904 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0218 | PS5-03-RDH-0905 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0219 | PS5-03-RDH-0906 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0220 | PS5-03-RDH-0909 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0221 | PS5-03-RDH-0910 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0222 | PS5-03-RDH-0911 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0223 | PS5-03-RDH-0912 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0224 | PS5-03-RDH-1001 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0225 | PS5-03-RDH-1002 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0226 | PS5-03-RDH-1003 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0227 | PS5-03-RDH-1004 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0228 | PS5-03-RDH-1005 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0229 | PS5-03-RDH-1006 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0230 | PS5-03-RDH-1009 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0231 | PS5-03-RDH-1010 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0232 | PS5-03-RDH-1011 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0233 | PS5-03-RDH-1012 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0234 | PS5-03-RDH-1101 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0235 | PS5-03-RDH-1102 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0236 | PS5-03-RDH-1103 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0237 | PS5-03-RDH-1104 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0238 | PS5-03-RDH-1105 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0239 | PS5-03-RDH-1106 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0240 | PS5-03-RDH-1109 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0241 | PS5-03-RDH-1110 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0242 | PS5-03-RDH-1111 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0243 | PS5-03-RDH-1112 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0820 | PS5-03-GDIR-0901 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0821 | PS5-03-GDIR-0902 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0822 | PS5-03-GDIR-0903 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0823 | PS5-03-GDIR-0904 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0824 | PS5-03-GDIR-0906 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0825 | PS5-03-GDIR-0907 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0826 | PS5-03-GDIR-0908 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0827 | PS5-03-GDIR-0909 | CJX42 - Gas / smoke detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00083-0828 | PS5-03-GDIR-1001 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0829 | PS5-03-GDIR-1002 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0830 | PS5-03-GDIR-1003 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0831 | PS5-03-GDIR-1004 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0832 | PS5-03-GDIR-1006 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0833 | PS5-03-GDIR-1007 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0834 | PS5-03-GDIR-1008 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0835 | PS5-03-GDIR-1009 | CJX42 - Gas / smoke detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00083-0836 | PS5-03-GDIR-1101 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0837 | PS5-03-GDIR-1102 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0838 | PS5-03-GDIR-1103 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0839 | PS5-03-GDIR-1104 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0840 | PS5-03-GDIR-1106 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0841 | PS5-03-GDIR-1107 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0842 | PS5-03-GDIR-1108 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0843 | PS5-03-GDIR-1109 | CJX42 - Gas / smoke detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00083-0844 | PS5-03-GDIR-1201 | CJX42 - Gas / smoke detector | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00083-0845 | PS5-03-GDIR-1202 | CJX42 - Gas / smoke detector | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00083-0846 | PS5-03-GDIR-1203 | CJX42 - Gas / smoke detector | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00083-0847 | PS5-03-GDIR-1204 | CJX42 - Gas / smoke detector | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00083-0848 | PS5-03-GDLHP-0146 | CJX42 - Gas / smoke detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00083-0849 | PS5-03-GDLHP-0147 | CJX42 - Gas / smoke detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00083-0850 | PS5-03-GDLHP-0149 | CJX42 - Gas / smoke detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00083-0851 | PS5-03-GDLHP-0150 | CJX42 - Gas / smoke detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00083-0852 | PS5-03-RDH-0619 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0853 | PS5-03-RDH-0620 | CJX42 - Gas / smoke detector | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00083-0854 | PS5-03-RDH-1201 | CJX42 - Gas / smoke detector | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00083-0855 | PS5-03-RDH-1202 | CJX42 - Gas / smoke detector | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00083-0856 | PS5-03-RDH-1203 | CJX42 - Gas / smoke detector | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00083-0857 | PS5-03-RDH-1204 | CJX42 - Gas / smoke detector | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00083-0858 | PS5-03-RDH-1205 | CJX42 - Gas / smoke detector | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00083-0859 | PS5-03-RDH-1302 | CJX42 - Gas / smoke detector | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | To be completed
T-00083-0860 | PS5-03-RDH-1303 | CJX42 - Gas / smoke detector | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | To be completed
T-00083-0861 | PS5-03-RDH-1304 | CJX42 - Gas / smoke detector | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | To be completed
T-00083-0862 | PS5-03-RDH-1901 | CJX42 - Gas / smoke detector | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | To be completed
T-00083-0863 | PS5-03-RDH-1902 | CJX42 - Gas / smoke detector | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | To be completed
T-00083-0864 | PS5-03-RDH-1903 | CJX42 - Gas / smoke detector | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | To be completed
T-00083-0865 | PS5-03-RDOS-1401 | CJX42 - Gas / smoke detector | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00083-0866 | PS5-03-RDOS-1402 | CJX42 - Gas / smoke detector | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00083-0867 | PS5-03-RDOS-1403 | CJX42 - Gas / smoke detector | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00083-0868 | PS5-03-RDOS-1404 | CJX42 - Gas / smoke detector | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00083-0869 | PS5-03-RDOS-1405 | CJX42 - Gas / smoke detector | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00083-0870 | PS5-03-RDOS-1406 | CJX42 - Gas / smoke detector | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00083-0871 | PS5-03-RDOS-1407 | CJX42 - Gas / smoke detector | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00083-0872 | PS5-03-RDOS-1408 | CJX42 - Gas / smoke detector | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00083-0873 | PS5-03-RDOS-1501 | CJX42 - Gas / smoke detector | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1 | To be completed
T-00083-0874 | PS5-03-RDOS-1502 | CJX42 - Gas / smoke detector | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1 | To be completed
T-00083-0875 | PS5-03-RDOS-1503 | CJX42 - Gas / smoke detector | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1 | To be completed
T-00083-0876 | PS5-03-RDOS-1601 | CJX42 - Gas / smoke detector | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2 | To be completed
T-00083-0877 | PS5-03-RDOS-1602 | CJX42 - Gas / smoke detector | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2 | To be completed
T-00083-0878 | PS5-03-RDOS-1603 | CJX42 - Gas / smoke detector | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2 | To be completed
T-00083-0879 | PS5-03-RDOS-1701 | CJX42 - Gas / smoke detector | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3 | To be completed
T-00083-0880 | PS5-03-RDOS-1702 | CJX42 - Gas / smoke detector | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3 | To be completed
T-00083-0881 | PS5-03-RDOS-1703 | CJX42 - Gas / smoke detector | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3 | To be completed
T-00083-0882 | PS5-03-RDOS-1801 | CJX42 - Gas / smoke detector | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4 | To be completed
T-00083-0883 | PS5-03-RDOS-1802 | CJX42 - Gas / smoke detector | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4 | To be completed
T-00083-0884 | PS5-03-RDOS-1803 | CJX42 - Gas / smoke detector | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4 | To be completed
T-00083-0885 | PS5-03-RDOS-2101 | CJX42 - Gas / smoke detector | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit | To be completed
T-00083-0886 | PS5-03-RDOS-2102 | CJX42 - Gas / smoke detector | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit | To be completed
T-00083-0887 | PS5-03-RDOS-2103 | CJX42 - Gas / smoke detector | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit | To be completed
T-00083-0888 | PS5-03-RDOS-G101A | CJX42 - Gas / smoke detector | I | PS5-03-22 - FZ-G1 - Guard House | To be completed
T-00083-0889 | PS5-03-RDOS-G101B | CJX42 - Gas / smoke detector | I | PS5-03-22 - FZ-G1 - Guard House | To be completed
T-00083-1560 | PS5-03-RDHR-W101A | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1561 | PS5-03-RDHR-W101B | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1562 | PS5-03-RDHR-W101C | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1563 | PS5-03-RDHR-W101D | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1564 | PS5-03-RDHR-W101E | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1565 | PS5-03-RDHR-W101F | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1566 | PS5-03-RDHR-W101G | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1567 | PS5-03-RDHR-W101H | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1568 | PS5-03-RDHR-W101I | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1569 | PS5-03-RDHR-W601A | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1570 | PS5-03-RDHR-W601B | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1571 | PS5-03-RDHR-W601C | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1572 | PS5-03-RDHR-W601D | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1573 | PS5-03-RDHR-W601E | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1574 | PS5-03-RDHR-W601F | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1575 | PS5-03-RDHR-W601G | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1576 | PS5-03-RDHR-W601H | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1577 | PS5-03-RDHR-W601I | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1578 | PS5-03-RDHR-W601J | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1579 | PS5-03-RDHR-W601K | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1580 | PS5-03-RDHR-W601L | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1581 | PS5-03-RDHR-W601M | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1582 | PS5-03-RDHR-W601N | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1583 | PS5-03-RDHR-W601O | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1584 | PS5-03-RDHR-W601P | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1585 | PS5-03-RDOS-B101A | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1586 | PS5-03-RDOS-B101B | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1587 | PS5-03-RDOS-B101C | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1588 | PS5-03-RDOS-B101D | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1589 | PS5-03-RDOS-B201A | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1590 | PS5-03-RDOS-B201B | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1591 | PS5-03-RDOS-B201C | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1592 | PS5-03-RDOS-B201D | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1593 | PS5-03-RDOS-B201E | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1594 | PS5-03-RDOS-B301A | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1595 | PS5-03-RDOS-B301B | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1596 | PS5-03-RDOS-B301C | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1597 | PS5-03-RDOS-B301D | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1598 | PS5-03-RDOS-B401A | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1599 | PS5-03-RDOS-B401B | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1600 | PS5-03-RDOS-B401C | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1601 | PS5-03-RDOS-B401D | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1602 | PS5-03-RDOS-B501A | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1603 | PS5-03-RDOS-B601A | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1604 | PS5-03-RDOS-B701A | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1605 | PS5-03-RDOS-B701B | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1606 | PS5-03-RDOS-B701C | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1607 | PS5-03-RDOS-B701D | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1608 | PS5-03-RDOS-B701E | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1609 | PS5-03-RDOS-B701F | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1610 | PS5-03-RDOS-B701G | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1611 | PS5-03-RDOS-B701H | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1612 | PS5-03-RDOS-B701I | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1613 | PS5-03-RDOS-B801A | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1614 | PS5-03-RDOS-B801B | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1615 | PS5-03-RDOS-B901A | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1616 | PS5-03-RDOS-B901B | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1617 | PS5-03-RDOS-B901C | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1618 | PS5-03-RDOS-B901D | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1619 | PS5-03-RDOS-B901E | CJX42 - Gas / smoke detector | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00083-1620 | PS5-03-RDOS-W201A | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1621 | PS5-03-RDOS-W201B | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1622 | PS5-03-RDOS-W201C | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1623 | PS5-03-RDOS-W201D | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1624 | PS5-03-RDOS-W301A | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1625 | PS5-03-RDOS-W401A | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1626 | PS5-03-RDOS-W501A | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1627 | PS5-03-RDOS-W501B | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1628 | PS5-03-RDOS-W501C | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1629 | PS5-03-RDOS-W501D | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1630 | PS5-03-RDOS-W501E | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00083-1631 | PS5-03-RDOS-W501F | CJX42 - Gas / smoke detector | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00084-0277 | PS5-03-RDIR-0104 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0278 | PS5-03-RDIR-0105 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0279 | PS5-03-RDIR-0106 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0280 | PS5-03-RDIR-0107 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0281 | PS5-03-RDIR-0108 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0282 | PS5-03-RDIR-0109 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0283 | PS5-03-RDIR-0110 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0284 | PS5-03-RDIR-0111 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0285 | PS5-03-RDIR-0112 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0286 | PS5-03-RDIR-0113 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0287 | PS5-03-RDIR-0114 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0288 | PS5-03-RDIR-0115 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0289 | PS5-03-RDIR-0116 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0290 | PS5-03-RDIR-0117 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0291 | PS5-03-RDIR-0118 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0292 | PS5-03-RDIR-0121 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0293 | PS5-03-RDIR-0122 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0294 | PS5-03-RDIR-0123 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0295 | PS5-03-RDIR-0124 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0296 | PS5-03-RDIR-0125 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0297 | PS5-03-RDIR-0126 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0298 | PS5-03-RDIR-0127 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0299 | PS5-03-RDIR-0128 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0300 | PS5-03-RDIR-0129 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0301 | PS5-03-RDIR-0130 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0302 | PS5-03-RDIR-0131 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0303 | PS5-03-RDIR-0132 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0304 | PS5-03-RDIR-0133 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0305 | PS5-03-RDIR-0137 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0306 | PS5-03-RDIR-0138 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0309 | PS5-03-RDIR-0403 | CJX43 - Fire detector | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed
T-00084-0310 | PS5-03-RDIR-0404 | CJX43 - Fire detector | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed
T-00084-0311 | PS5-03-RDIR-0405 | CJX43 - Fire detector | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed
T-00084-0312 | PS5-03-RDIR-0406 | CJX43 - Fire detector | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed
T-00084-0313 | PS5-03-RDIR-0409 | CJX43 - Fire detector | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed
T-00084-0315 | PS5-03-RDIR-0411 | CJX43 - Fire detector | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed
T-00084-0320 | PS5-03-RDIR-0819 | CJX43 - Fire detector | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00084-0321 | PS5-03-RDIR-0820 | CJX43 - Fire detector | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00084-0322 | PS5-03-RDIR-0832 | CJX43 - Fire detector | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00084-0323 | PS5-03-RDIR-0833 | CJX43 - Fire detector | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00084-0324 | PS5-03-RDUIR-0701 | CJX43 - Fire detector | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00084-0325 | PS5-03-RDUIR-0702 | CJX43 - Fire detector | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00084-0326 | PS5-03-RDUIR-0703 | CJX43 - Fire detector | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00084-0327 | PS5-03-RDUIR-0704 | CJX43 - Fire detector | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00084-0328 | PS5-03-RDUIR-0705 | CJX43 - Fire detector | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00084-0329 | PS5-03-RDUIR-0907 | CJX43 - Fire detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00084-0330 | PS5-03-RDUIR-0908 | CJX43 - Fire detector | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00084-0331 | PS5-03-RDUIR-1007 | CJX43 - Fire detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00084-0332 | PS5-03-RDUIR-1008 | CJX43 - Fire detector | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00084-0333 | PS5-03-RDUIR-1107 | CJX43 - Fire detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00084-0334 | PS5-03-RDUIR-1108 | CJX43 - Fire detector | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00084-0349 | PS5-03-RDIR-0141 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0350 | PS5-03-RDIR-0142 | CJX43 - Fire detector | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00084-0351 | PS5-03-RDUIR-1207 | CJX43 - Fire detector | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00084-0352 | PS5-03-RDUIR-1208 | CJX43 - Fire detector | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00087-0102 | PS5-03-SEA-0002 | CJX48 - Indoor cabinet / panel | I | PS5-03-22 - FZ-G1 - Guard House | To be completed
T-00087-0103 | PS5-03-SEA-0003 | CJX48 - Indoor cabinet / panel | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00087-0105 | PS5-60-SEA-0001 | CJX48 - Indoor cabinet / panel | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00087-0315 | PS5-03-MTX-0001 | CJX48 - Indoor cabinet / panel | I | PS5-04-02 - Office Building SIS/FGS System | To be completed
T-00087-0492 | PS5-01-LB-0004 | CJX48 - Indoor cabinet / panel | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00087-0500 | PS5-60-LA-0002A | CJX48 - Indoor cabinet / panel | I | PS5-60-01 - Power Generation Package A | To be completed
T-00087-0516 | PS5-03-SEA-0005 | CJX48 - Indoor cabinet / panel | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00087-0517 | PS5-03-SEA-0006 | CJX48 - Indoor cabinet / panel | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00087-0528 | PS5-60-LA-0003 | CJX48 - Indoor cabinet / panel | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00090-0009 | PS5-01-UK-6100 | CZX01I - Package | I | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | To be completed
T-00090-0010 | PS5-01-UV-8700 | CZX01I - Package | I | PS5-01-05 - Foam Skid | To be completed
T-00090-0179 | PS5-60-UR-8100A | CZX01I - Package | I | PS5-60-01 - Power Generation Package A | To be completed
T-00090-0180 | PS5-60-UR-8100B | CZX01I - Package | I | PS5-60-04 - Power Generation Package B | To be completed
T-00090-0181 | PS5-60-UR-8100C | CZX01I - Package | I | PS5-60-07 - Power Generation Package C | To be completed
T-00090-0182 | PS5-60-UR-8100D | CZX01I - Package | I | PS5-60-10 - Power Generation Package D | To be completed
T-00090-0183 | PS5-60-UR-8100E | CZX01I - Package | I | PS5-60-13 - Power Generation Package E | To be completed
T-00090-0184 | PS5-60-UR-8100F | CZX01I - Package | I | PS5-60-16 - Power Generation Package F | To be completed
T-00090-0185 | PS5-60-UR-8100G | CZX01I - Package | I | PS5-60-19 - Power Generation Package G | To be completed
T-00090-0186 | PS5-05-UR-8100 | CZX01I - Package | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed
T-00090-0187 | PS5-71-UZ-6200 | CZX01I - Package | I | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | To be completed
T-00090-0188 | PS5-60-UA-5100 | CZX01I - Package | I | PS5-60-27 - Compressed Air Starting Skid | To be completed
T-00090-0189 | PS5-60-UO-81100A | CZX01I - Package | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | To be completed
T-00090-0190 | PS5-60-UO-81100B | CZX01I - Package | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | To be completed
T-00090-0191 | PS5-60-UO-81100C | CZX01I - Package | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | To be completed
T-00090-0192 | PS5-60-UO-81100D | CZX01I - Package | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | To be completed
T-00090-0193 | PS5-60-UO-81100E | CZX01I - Package | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | To be completed
T-00090-0194 | PS5-60-UO-81100F | CZX01I - Package | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | To be completed
T-00090-0195 | PS5-60-UO-81100G | CZX01I - Package | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | To be completed
T-00090-0196 | PS5-60-UZ-8200A | CZX01I - Package | I | PS5-60-35 - Injector Tip Cooling Module A | To be completed
T-00090-0197 | PS5-60-UZ-8200B | CZX01I - Package | I | PS5-60-36 - Injector Tip Cooling Module B | To be completed
T-00090-0198 | PS5-60-UZ-8200C | CZX01I - Package | I | PS5-60-37 - Injector Tip Cooling Module C | To be completed
T-00090-0199 | PS5-60-UZ-8200D | CZX01I - Package | I | PS5-60-38 - Injector Tip Cooling Module D | To be completed
T-00090-0200 | PS5-60-UZ-8200E | CZX01I - Package | I | PS5-60-39 - Injector Tip Cooling Module E | To be completed
T-00090-0201 | PS5-60-UZ-8200F | CZX01I - Package | I | PS5-60-40 - Injector Tip Cooling Module F | To be completed
T-00090-0202 | PS5-60-VS-9100A | CZX01I - Package | I | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | To be completed
T-00090-0203 | PS5-60-VS-9100B | CZX01I - Package | I | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | To be completed
T-00090-0204 | PS5-60-VS-9100C | CZX01I - Package | I | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | To be completed
T-00090-0205 | PS5-60-VS-9100D | CZX01I - Package | I | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | To be completed
T-00090-0206 | PS5-60-VS-9100E | CZX01I - Package | I | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | To be completed
T-00090-0207 | PS5-60-VS-9100F | CZX01I - Package | I | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | To be completed
T-00090-0208 | PS5-60-VS-9100G | CZX01I - Package | I | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | To be completed
T-00090-0209 | PS5-71-UZ-6500 | CZX01I - Package | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00090-0210 | PS5-71-UZ-6800A | CZX01I - Package | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00090-0211 | PS5-71-UZ-6800B | CZX01I - Package | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00090-0212 | PS5-01-UZ-6900 | CZX01I - Package | I | PS5-01-10 - Water Mist Package | To be completed
T-00090-0213 | PS5-53-UT-8100 | CZX01I - Package | I | PS5-50-03 - Water Pre-Treatment Package | To be completed
T-00090-0214 | PS5-53-UT-8200 | CZX01I - Package | I | PS5-53-04 - Water Treatment Purification Package | To be completed
T-00090-0215 | PS5-60-EA-2100A | CZX01I - Package | I | PS5-60-70 - Engine A Cooling system | To be completed
T-00090-0216 | PS5-60-EA-2100B | CZX01I - Package | I | PS5-60-70 - Engine A Cooling system | To be completed
T-00090-0217 | PS5-60-EA-21100A | CZX01I - Package | I | PS5-60-01 - Power Generation Package A | To be completed
T-00090-0218 | PS5-60-EA-21100B | CZX01I - Package | I | PS5-60-04 - Power Generation Package B | To be completed
T-00090-0219 | PS5-60-EA-21100C | CZX01I - Package | I | PS5-60-07 - Power Generation Package C | To be completed
T-00090-0220 | PS5-60-EA-21100D | CZX01I - Package | I | PS5-60-10 - Power Generation Package D | To be completed
T-00090-0221 | PS5-60-EA-21100E | CZX01I - Package | I | PS5-60-13 - Power Generation Package E | To be completed
T-00090-0222 | PS5-60-EA-21100F | CZX01I - Package | I | PS5-60-16 - Power Generation Package F | To be completed
T-00090-0223 | PS5-60-EA-21100G | CZX01I - Package | I | PS5-60-19 - Power Generation Package G | To be completed
T-00090-0224 | PS5-60-EA-21200A | CZX01I - Package | I | PS5-60-01 - Power Generation Package A | To be completed
T-00090-0225 | PS5-60-EA-21200B | CZX01I - Package | I | PS5-60-04 - Power Generation Package B | To be completed
T-00090-0226 | PS5-60-EA-21200C | CZX01I - Package | I | PS5-60-07 - Power Generation Package C | To be completed
T-00090-0227 | PS5-60-EA-21200D | CZX01I - Package | I | PS5-60-10 - Power Generation Package D | To be completed
T-00090-0228 | PS5-60-EA-21200E | CZX01I - Package | I | PS5-60-13 - Power Generation Package E | To be completed
T-00090-0229 | PS5-60-EA-21200F | CZX01I - Package | I | PS5-60-16 - Power Generation Package F | To be completed
T-00090-0230 | PS5-60-EA-21200G | CZX01I - Package | I | PS5-60-19 - Power Generation Package G | To be completed
T-00090-0231 | PS5-60-EA-2200A | CZX01I - Package | I | PS5-60-71 - Engine B Cooling system | To be completed
T-00090-0232 | PS5-60-EA-2200B | CZX01I - Package | I | PS5-60-71 - Engine B Cooling system | To be completed
T-00090-0233 | PS5-60-EA-2300A | CZX01I - Package | I | PS5-60-72 - Engine C Cooling system | To be completed
T-00090-0234 | PS5-60-EA-2300B | CZX01I - Package | I | PS5-60-72 - Engine C Cooling system | To be completed
T-00090-0235 | PS5-60-EA-2400A | CZX01I - Package | I | PS5-60-73 - Engine D Cooling system | To be completed
T-00090-0236 | PS5-60-EA-2400B | CZX01I - Package | I | PS5-60-73 - Engine D Cooling system | To be completed
T-00090-0237 | PS5-60-EA-2500A | CZX01I - Package | I | PS5-60-74 - Engine E Cooling system | To be completed
T-00090-0238 | PS5-60-EA-2500B | CZX01I - Package | I | PS5-60-74 - Engine E Cooling system | To be completed
T-00090-0239 | PS5-60-EA-2600A | CZX01I - Package | I | PS5-60-75 - Engine F Cooling system | To be completed
T-00090-0240 | PS5-60-EA-2600B | CZX01I - Package | I | PS5-60-75 - Engine F Cooling system | To be completed
T-00090-0241 | PS5-60-EA-2700A | CZX01I - Package | I | PS5-60-76 - Engine G Cooling system | To be completed
T-00090-0242 | PS5-60-EA-2700B | CZX01I - Package | I | PS5-60-76 - Engine G Cooling system | To be completed
T-00090-0243 | PS5-60-EA-2800A | CZX01I - Package | I | PS5-60-35 - Injector Tip Cooling Module A | To be completed
T-00090-0244 | PS5-60-EA-2800B | CZX01I - Package | I | PS5-60-36 - Injector Tip Cooling Module B | To be completed
T-00090-0245 | PS5-60-EA-2800C | CZX01I - Package | I | PS5-60-37 - Injector Tip Cooling Module C | To be completed
T-00090-0246 | PS5-60-EA-2800D | CZX01I - Package | I | PS5-60-38 - Injector Tip Cooling Module D | To be completed
T-00090-0247 | PS5-60-EA-2800E | CZX01I - Package | I | PS5-60-39 - Injector Tip Cooling Module E | To be completed
T-00090-0248 | PS5-60-EA-2800F | CZX01I - Package | I | PS5-60-40 - Injector Tip Cooling Module F | To be completed
T-00090-0249 | PS5-60-EA-2800G | CZX01I - Package | I | PS5-60-41 - Injector Tip Cooling Module G | To be completed
T-00090-0250 | PS5-60-EA-2900A | CZX01I - Package | I | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed
T-00090-0251 | PS5-60-EA-2900B | CZX01I - Package | I | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed
T-00090-0252 | PS5-60-EA-2900C | CZX01I - Package | I | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00090-0253 | PS5-60-EA-2900D | CZX01I - Package | I | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00090-0254 | PS5-60-EA-2900E | CZX01I - Package | I | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00090-0255 | PS5-60-EA-2900F | CZX01I - Package | I | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00090-0256 | PS5-60-EA-2900G | CZX01I - Package | I | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00090-0257 | PS5-60-TCV-0001A | CZX01I - Package | I | PS5-60-70 - Engine A Cooling system | To be completed
T-00090-0258 | PS5-60-TCV-0001B | CZX01I - Package | I | PS5-60-71 - Engine B Cooling system | To be completed
T-00090-0259 | PS5-60-TCV-0001C | CZX01I - Package | I | PS5-60-72 - Engine C Cooling system | To be completed
T-00090-0260 | PS5-60-TCV-0001D | CZX01I - Package | I | PS5-60-73 - Engine D Cooling system | To be completed
T-00090-0261 | PS5-60-TCV-0001E | CZX01I - Package | I | PS5-60-74 - Engine E Cooling system | To be completed
T-00090-0262 | PS5-60-TCV-0001F | CZX01I - Package | I | PS5-60-75 - Engine F Cooling system | To be completed
T-00090-0263 | PS5-60-TCV-0001G | CZX01I - Package | I | PS5-60-76 - Engine G Cooling system | To be completed
T-00090-0264 | PS5-60-TCV-0002A | CZX01I - Package | I | PS5-60-70 - Engine A Cooling system | To be completed
T-00090-0265 | PS5-60-TCV-0002B | CZX01I - Package | I | PS5-60-71 - Engine B Cooling system | To be completed
T-00090-0266 | PS5-60-TCV-0002C | CZX01I - Package | I | PS5-60-72 - Engine C Cooling system | To be completed
T-00090-0267 | PS5-60-TCV-0002D | CZX01I - Package | I | PS5-60-73 - Engine D Cooling system | To be completed
T-00090-0268 | PS5-60-TCV-0002E | CZX01I - Package | I | PS5-60-74 - Engine E Cooling system | To be completed
T-00090-0269 | PS5-60-TCV-0002F | CZX01I - Package | I | PS5-60-75 - Engine F Cooling system | To be completed
T-00090-0270 | PS5-60-TCV-0002G | CZX01I - Package | I | PS5-60-76 - Engine G Cooling system | To be completed
T-00090-0271 | PS5-60-UA-5200 | CZX01I - Package | I | PS5-60-26 - Instrument Air Compressor Skid | To be completed
T-00090-0272 | PS5-60-UR-8200A | CZX01I - Package | I | PS5-60-01 - Power Generation Package A | To be completed
T-00090-0273 | PS5-60-UR-8200B | CZX01I - Package | I | PS5-60-04 - Power Generation Package B | To be completed
T-00090-0274 | PS5-60-UR-8200C | CZX01I - Package | I | PS5-60-07 - Power Generation Package C | To be completed
T-00090-0275 | PS5-60-UR-8200D | CZX01I - Package | I | PS5-60-10 - Power Generation Package D | To be completed
T-00090-0276 | PS5-60-UR-8200E | CZX01I - Package | I | PS5-60-13 - Power Generation Package E | To be completed
T-00090-0277 | PS5-60-UR-8200F | CZX01I - Package | I | PS5-60-16 - Power Generation Package F | To be completed
T-00090-0278 | PS5-60-UR-8200G | CZX01I - Package | I | PS5-60-19 - Power Generation Package G | To be completed
T-00090-0279 | PS5-60-UZ-8200G | CZX01I - Package | I | PS5-60-41 - Injector Tip Cooling Module G | To be completed
T-00090-0280 | PS5-60-UZ-8900A | CZX01I - Package | I | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed
T-00090-0281 | PS5-60-UZ-8900B | CZX01I - Package | I | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed
T-00090-0282 | PS5-60-UZ-8900C | CZX01I - Package | I | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00090-0283 | PS5-60-UZ-8900D | CZX01I - Package | I | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00090-0284 | PS5-60-UZ-8900E | CZX01I - Package | I | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00090-0285 | PS5-60-UZ-8900F | CZX01I - Package | I | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00090-0286 | PS5-60-UZ-8900G | CZX01I - Package | I | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00090-0287 | PS5-71-UN-7200 | CZX01I - Package | I | PS5-71-02 - CFO Allocation Metering Package | To be completed
T-00090-0288 | PS5-71-UZ-6400 | CZX01I - Package | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed
T-00090-0289 | PS5-71-UZ-6700 | CZX01I - Package | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed
T-00090-0290 | PS5-74-UB-5100 | CZX01I - Package | I | PS5-74-01 - N2 Generation Skid | To be completed
T-00090-0291 | PS5-75-UI-6100 | CZX01I - Package | I | PS5-75-02 - Biocide Injection Package | To be completed
T-00090-0292 | PS5-75-UI-6200 | CZX01I - Package | I | PS5-75-01 - DRA Injection Package | To be completed
T-00090-0293 | PS5-75-UI-6300 | CZX01I - Package | I | PS5-75-03 - Corrosion Inhibitor Injection Package | To be completed
T-00090-0294 | PS5-77-UZ-8200 | CZX01I - Package | I | PS5-53-03 - Water Softener Package | To be completed
T-00090-0295 | PS5-82-UZ-8100 | CZX01I - Package | I | PS5-82-02 - Sewage Treatment Plant Package | To be completed
T-00090-0296 | PS5-60-PRV-0008A | CZX01I - Package | I | PS5-60-28 - Air Receiver A & Air Regulator A | To be completed
T-00090-0297 | PS5-60-PRV-0008B | CZX01I - Package | I | PS5-60-29 - Air Receiver B & Air Regulator B | To be completed
T-00090-0298 | PS5-60-PRV-0008C | CZX01I - Package | I | PS5-60-30 - Air Receiver C & Air Regulator C | To be completed
T-00090-0299 | PS5-60-PRV-0008D | CZX01I - Package | I | PS5-60-31 - Air Receiver D & Air Regulator D | To be completed
T-00090-0300 | PS5-60-PRV-0008E | CZX01I - Package | I | PS5-60-32 - Air Receiver E & Air Regulator E | To be completed
T-00090-0301 | PS5-60-PRV-0008F | CZX01I - Package | I | PS5-60-33 - Air Receiver F & Air Regulator F | To be completed
T-00090-0302 | PS5-60-PRV-0008G | CZX01I - Package | I | PS5-60-34 - Air Receiver G & Air Regulator G | To be completed
T-00090-0433 | PS5-01-UZ-610 | CZX01I - Package | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00090-0436 | PS5-60-UR-8300A | CZX01I - Package | I | PS5-60-35 - Injector Tip Cooling Module A | To be completed
T-00090-0437 | PS5-60-UR-8300B | CZX01I - Package | I | PS5-60-36 - Injector Tip Cooling Module B | To be completed
T-00090-0438 | PS5-60-UR-8300C | CZX01I - Package | I | PS5-60-37 - Injector Tip Cooling Module C | To be completed
T-00090-0439 | PS5-60-UR-8300D | CZX01I - Package | I | PS5-60-38 - Injector Tip Cooling Module D | To be completed
T-00090-0440 | PS5-60-UR-8300E | CZX01I - Package | I | PS5-60-39 - Injector Tip Cooling Module E | To be completed
T-00090-0441 | PS5-60-UR-8300F | CZX01I - Package | I | PS5-60-40 - Injector Tip Cooling Module F | To be completed
T-00090-0442 | PS5-60-UR-8300G | CZX01I - Package | I | PS5-60-41 - Injector Tip Cooling Module G | To be completed
T-00090-0455 | PS5-03-SEA-0001 | CZX01I - Package | I | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | To be completed
T-00171-4342 | PS5-60-IE-0003B-CA02 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-05 - Power Gen Package B (UCP) | To be completed
T-00171-4343 | PS5-60-IE-0003B-CA03 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-05 - Power Gen Package B (UCP) | To be completed
T-00171-4344 | PS5-60-IE-0003B-CA04 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-05 - Power Gen Package B (UCP) | To be completed
T-00171-4345 | PS5-60-IE-0003B-CA05 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-05 - Power Gen Package B (UCP) | To be completed
T-00171-4346 | PS5-60-IE-0003C-CA02 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00171-4347 | PS5-60-IE-0003C-CA03 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00171-4348 | PS5-60-IE-0003C-CA04 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00171-4349 | PS5-60-IE-0003C-CA05 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00171-4350 | PS5-60-IE-0003D-CA02 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00171-4351 | PS5-60-IE-0003D-CA03 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00171-4352 | PS5-60-IE-0003D-CA04 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00171-4353 | PS5-60-IE-0003D-CA05 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00171-4354 | PS5-60-IE-0003E-CA02 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00171-4355 | PS5-60-IE-0003E-CA03 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00171-4356 | PS5-60-IE-0003E-CA04 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00171-4357 | PS5-60-IE-0003E-CA05 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00171-4358 | PS5-60-IE-0003F-CA02 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00171-4359 | PS5-60-IE-0003F-CA03 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00171-4360 | PS5-60-IE-0003F-CA04 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00171-4361 | PS5-60-IE-0003F-CA05 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00171-4362 | PS5-60-IE-0003G-CA03 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00171-4363 | PS5-60-IE-0003G-CA04 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00171-4364 | PS5-60-IE-0003G-CA05 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00171-4365 | PS5-60-IE-0004-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-22 - Power Gen Master UCP | To be completed
T-00171-4366 | PS5-60-IE-0004-CA07 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-22 - Power Gen Master UCP | To be completed
T-00171-4367 | PS5-60-IE-0004-CA08 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-22 - Power Gen Master UCP | To be completed
T-00171-4368 | PS5-60-IE-0004-CA14 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-22 - Power Gen Master UCP | To be completed
T-00171-4369 | PS5-60-IE-0004-CA15 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-22 - Power Gen Master UCP | To be completed
T-00171-4370 | PS5-60-IE-0004-CA21 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-22 - Power Gen Master UCP | To be completed
T-00171-4371 | PS5-60-IH-0001A-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | To be completed
T-00171-4372 | PS5-60-IH-0001B-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | To be completed
T-00171-4373 | PS5-60-IH-0001C-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | To be completed
T-00171-4374 | PS5-60-IH-0001D-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | To be completed
T-00171-4375 | PS5-60-IH-0001E-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed
T-00171-4376 | PS5-60-IH-0001F-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00171-4377 | PS5-60-IH-0001G-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed
T-00171-4378 | PS5-60-IN-0001A-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | To be completed
T-00171-4379 | PS5-60-IN-0001B-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | To be completed
T-00171-4380 | PS5-60-IN-0001C-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | To be completed
T-00171-4381 | PS5-60-IN-0001D-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | To be completed
T-00171-4382 | PS5-60-IN-0001E-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | To be completed
T-00171-4383 | PS5-60-IN-0001F-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | To be completed
T-00171-4384 | PS5-60-IN-0001G-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | To be completed
T-00171-4385 | PS5-60-IN-0002A-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed
T-00171-4386 | PS5-60-IN-0002B-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed
T-00171-4387 | PS5-60-IN-0002C-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00171-4388 | PS5-60-IN-0002D-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00171-4389 | PS5-60-IN-0002E-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00171-4390 | PS5-60-IN-0002F-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00171-4391 | PS5-60-IN-0002G-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00171-4392 | PS5-60-LA-0002B-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-10 - Power Generation Package D | To be completed
T-00171-4393 | PS5-60-LA-0002B-CA02 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-10 - Power Generation Package D | To be completed
T-00171-4394 | PS5-60-LA-0002B-CA03 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-10 - Power Generation Package D | To be completed
T-00171-4395 | PS5-60-LA-0002B-CA04 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-10 - Power Generation Package D | To be completed
T-00171-4396 | PS5-60-LA-0002B-CA05 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-10 - Power Generation Package D | To be completed
T-00171-4397 | PS5-60-LA-0002B-CA06 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-10 - Power Generation Package D | To be completed
T-00171-4398 | PS5-60-LA-0002C-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-16 - Power Generation Package F | To be completed
T-00171-4399 | PS5-60-LA-0002C-CA02 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-16 - Power Generation Package F | To be completed
T-00171-4400 | PS5-60-LA-0002C-CA03 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-16 - Power Generation Package F | To be completed
T-00171-4401 | PS5-60-LA-0002C-CA04 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-16 - Power Generation Package F | To be completed
T-00171-4402 | PS5-60-LA-0002C-CA05 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-16 - Power Generation Package F | To be completed
T-00171-4403 | PS5-60-LA-0002C-CA06 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-60-16 - Power Generation Package F | To be completed
T-00171-4404 | PS5-60-SEA-0001-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00171-4405 | PS5-71-IN-0001-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-71-19 - Diesel Separator Module (UCP) | To be completed
T-00171-4406 | PS5-71-IN-0001-CA11 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-71-19 - Diesel Separator Module (UCP) | To be completed
T-00171-4407 | PS5-71-IN-0002-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | To be completed
T-00171-4408 | PS5-71-IN-0003-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed
T-00171-4409 | PS5-71-IN-0004A-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00171-4410 | PS5-71-IN-0004B-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00171-9468 | PS5-09-LB-8451A-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-09-03 - HVAC for Generator Building | To be completed
T-00171-9469 | PS5-09-LB-8451B-CA01 | CIX09 - Telecom cable power / Control / Multicore | T | PS5-09-03 - HVAC for Generator Building | To be completed
T-00227-0068 | PS5-61-ISR-0101 | TPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed
T-00227-0070 | PS5-61-IU-0010 | TPX02 - Power transformer | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed
T-00227-0071 | PS5-61-IU-0011 | TPX02 - Power transformer | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed
T-00227-0072 | PS5-63-IV-0010 | TPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed
T-00227-0073 | PS5-63-IV-0011 | TPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed
T-00227-0133 | PS5-61-IU-0001A | TPX02 - Power transformer | E | PS5-60-01 - Power Generation Package A | To be completed
T-00227-0134 | PS5-61-IU-0001B | TPX02 - Power transformer | E | PS5-60-04 - Power Generation Package B | To be completed
T-00227-0135 | PS5-61-IU-0001C | TPX02 - Power transformer | E | PS5-60-07 - Power Generation Package C | To be completed
T-00227-0136 | PS5-61-IU-0001D | TPX02 - Power transformer | E | PS5-60-10 - Power Generation Package D | To be completed
T-00227-0137 | PS5-61-IU-0001E | TPX02 - Power transformer | E | PS5-60-13 - Power Generation Package E | To be completed
T-00227-0138 | PS5-61-IU-0001F | TPX02 - Power transformer | E | PS5-60-16 - Power Generation Package F | To be completed
T-00227-0139 | PS5-61-IU-0001G | TPX02 - Power transformer | E | PS5-60-19 - Power Generation Package G | To be completed
T-00227-0175 | PS5-61-IV-0005A | TPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed
T-00227-0176 | PS5-61-IV-0005B | TPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed
T-00228-0107 | PS5-79-IV-0012 | TPX03 - LV transformer | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00228-0108 | PS5-87-IRF-0001 | TPX03 - LV transformer | E | PS5-53-01 - Utility Water / Storage Tank | To be completed
T-00228-0109 | PS5-87-IRF-0002 | TPX03 - LV transformer | E | PS5-71-04 - CFO Storage Tank | To be completed
T-00228-0110 | PS5-87-IRF-0003 | TPX03 - LV transformer | E | PS5-71-12 - CFO Service Tank | To be completed
T-00228-0111 | PS5-87-IRF-0004 | TPX03 - LV transformer | E | PS5-71-15 - Diesel Fuel Storage Tank | To be completed
T-00230-0035 | PS5-61-IK-0003 | TPX05 - LV switchboard | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/2-13-0402 | CPP-RFI-68-332-13-0424 |  | TZ-MID-68-WPR2-151166 Panel Grounding not yet connected to the grid [OPEN] ¦ TZ-MID-68-WPR2-151166 To perform the busbar contact resistance test (ductor test) [OPEN] |  | TZ-MID-68-WPR2-151166 To be cleanning internal and external of the panel [OPEN]
T-00230-0036 | PS5-61-IK-0006 | TPX05 - LV switchboard | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed
T-00232-1097 | PS5-61-IV-0005A-CH01 | TPX08 - HV power cable | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00232-1098 | PS5-61-IV-0005A-CH02 | TPX08 - HV power cable | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00232-1099 | PS5-61-IV-0005A-CH03 | TPX08 - HV power cable | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00232-1100 | PS5-61-IV-0005B-CH01 | TPX08 - HV power cable | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00232-1101 | PS5-61-IV-0005B-CH02 | TPX08 - HV power cable | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00232-1102 | PS5-61-IV-0005B-CH03 | TPX08 - HV power cable | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00232-1119 | PS5-79-BH-0001-CH01 | TPX08 - HV power cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | Completed (not Closed) | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation [OPEN]
T-00232-1120 | PS5-79-BH-0001-CH02 | TPX08 - HV power cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | Completed (not Closed) | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation [OPEN]
T-00232-1121 | PS5-79-BH-0001-CH03 | TPX08 - HV power cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | Completed (not Closed) | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation [OPEN]
T-00232-1122 | PS5-79-BH-0002-CH01 | TPX08 - HV power cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | Completed (not Closed) | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation [OPEN]
T-00232-1123 | PS5-79-BH-0002-CH02 | TPX08 - HV power cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | Completed (not Closed) | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation [OPEN]
T-00232-1124 | PS5-79-BH-0002-CH03 | TPX08 - HV power cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | Completed (not Closed) | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation [OPEN]
T-00233-10060 | PS5-62-IE-0001-CL02 | TPX09 - LV power cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00233-10061 | PS5-62-IE-0001-CL03 | TPX09 - LV power cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00233-10062 | PS5-62-IE-0001-CL05 | TPX09 - LV power cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00233-10063 | PS5-62-IE-0001-CL06 | TPX09 - LV power cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00233-10064 | PS5-62-IE-0001-CL07 | TPX09 - LV power cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00233-10065 | PS5-62-IE-0001-CL51 | TPX09 - LV power cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00233-10066 | PS5-62-IE-0001-CL52 | TPX09 - LV power cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00233-10067 | PS5-62-IE-0001-CL53 | TPX09 - LV power cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00233-10068 | PS5-62-IE-0001-CL54 | TPX09 - LV power cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00233-10069 | PS5-62-IE-0001-CL55 | TPX09 - LV power cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00233-10070 | PS5-62-IE-0001-CL56 | TPX09 - LV power cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00233-10071 | PS5-62-IE-0001-CL57 | TPX09 - LV power cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00233-10072 | PS5-62-IE-0001-CL58 | TPX09 - LV power cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00233-10073 | PS5-62-IE-0001-CL59 | TPX09 - LV power cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00233-10074 | PS5-62-IE-0002-CL02 | TPX09 - LV power cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00233-10075 | PS5-62-IE-0002-CL03 | TPX09 - LV power cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00233-10076 | PS5-62-IE-0002-CL04 | TPX09 - LV power cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00233-10077 | PS5-62-IE-0002-CL05 | TPX09 - LV power cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00233-10078 | PS5-62-IE-0002-CL06 | TPX09 - LV power cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00233-10079 | PS5-62-IE-0002-CL07 | TPX09 - LV power cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00233-10080 | PS5-62-IE-0002-CL52 | TPX09 - LV power cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00233-10081 | PS5-62-IE-0002-CL53 | TPX09 - LV power cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00233-10082 | PS5-62-IE-0002-CL54 | TPX09 - LV power cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00233-10083 | PS5-62-IE-0002-CL55 | TPX09 - LV power cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00233-10084 | PS5-62-IE-0002-CL56 | TPX09 - LV power cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00233-10085 | PS5-62-IE-0002-CL57 | TPX09 - LV power cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00233-10086 | PS5-62-IE-0002-CL58 | TPX09 - LV power cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00233-10087 | PS5-62-IE-0002-CL59 | TPX09 - LV power cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00233-10088 | PS5-62-IE-0002-CL60 | TPX09 - LV power cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00233-10535 | PS5-06-GB-0003-CG01 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed
T-00233-10536 | PS5-60-IN-0002A-CG01 | TPX09 - LV power cable | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed
T-00233-10537 | PS5-60-IN-0002B-CG01 | TPX09 - LV power cable | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed
T-00233-10538 | PS5-60-IN-0002C-CG01 | TPX09 - LV power cable | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00233-10539 | PS5-60-IN-0002D-CG01 | TPX09 - LV power cable | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00233-10540 | PS5-60-IN-0002E-CG01 | TPX09 - LV power cable | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00233-10541 | PS5-60-IN-0002F-CG01 | TPX09 - LV power cable | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00233-10542 | PS5-60-IN-0002G-CG01 | TPX09 - LV power cable | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00233-10585 | PS5-06-IG-0004A-CG01 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed
T-00233-10586 | PS5-06-IG-0004B-CG01 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed
T-00233-10593 | PS5-60-IH-0001A-CG01 | TPX09 - LV power cable | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | To be completed
T-00233-10594 | PS5-60-IH-0001B-CG01 | TPX09 - LV power cable | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | To be completed
T-00233-10595 | PS5-60-IH-0001C-CG01 | TPX09 - LV power cable | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | To be completed
T-00233-10596 | PS5-60-IH-0001D-CG01 | TPX09 - LV power cable | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | To be completed
T-00233-10597 | PS5-60-IH-0001E-CG01 | TPX09 - LV power cable | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed
T-00233-10598 | PS5-60-IH-0001F-CG01 | TPX09 - LV power cable | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00233-10599 | PS5-60-IH-0001G-CG01 | TPX09 - LV power cable | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed
T-00233-10602 | PS5-61-IH-0004-CG01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-10603 | PS5-61-IH-0004-CG02 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-10604 | PS5-61-IH-0004-CG03 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-10605 | PS5-61-IH-0004-CG04 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-10889 | PS5-28-DM-31100-CL01 | TPX09 - LV power cable | E | PS5-28-10 - Oil Skimmer Package | To be completed
T-00233-10968 | PS5-08-85CP-1201-CS01 | TPX09 - LV power cable | E | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00233-10969 | PS5-08-85CP-1202-CS01 | TPX09 - LV power cable | E | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00233-10970 | PS5-08-85CP-1601-CS01 | TPX09 - LV power cable | E | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00233-11062 | PS5-09-DM-84500A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-11063 | PS5-09-DM-84500B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-11253 | PS5-71-BE-0001A-CL01 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11254 | PS5-71-BE-0001A-CL02 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11255 | PS5-71-BE-0001A-CL03 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11256 | PS5-71-BE-0001A-CL04 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11257 | PS5-71-BE-0001A-CL05 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11258 | PS5-71-BE-0001A-CL06 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11259 | PS5-71-BE-0001A-CL07 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11260 | PS5-71-BE-0001A-CL08 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11261 | PS5-71-BE-0001A-CL09 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11262 | PS5-71-BE-0001A-CL10 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11263 | PS5-71-BE-0001A-CL11 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11264 | PS5-71-BE-0001A-CL12 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11265 | PS5-71-BE-0001B-CL01 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11266 | PS5-71-BE-0001B-CL02 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11267 | PS5-71-BE-0001B-CL03 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11268 | PS5-71-BE-0001B-CL04 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11269 | PS5-71-BE-0001B-CL05 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11270 | PS5-71-BE-0001B-CL06 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11271 | PS5-71-BE-0001B-CL07 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11272 | PS5-71-BE-0001B-CL08 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11273 | PS5-71-BE-0001B-CL09 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11274 | PS5-71-BE-0001B-CL10 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11275 | PS5-71-BE-0001B-CL11 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11276 | PS5-71-BE-0001B-CL12 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00233-11277 | PS5-71-BE-0005-CL01 | TPX09 - LV power cable | E | PS5-71-19 - Diesel Separator Module (UCP) | To be completed
T-00233-11278 | PS5-71-BE-0005-CL02 | TPX09 - LV power cable | E | PS5-71-19 - Diesel Separator Module (UCP) | To be completed
T-00233-11279 | PS5-71-BE-0005-CL03 | TPX09 - LV power cable | E | PS5-71-19 - Diesel Separator Module (UCP) | To be completed
T-00233-11280 | PS5-71-BE-0005-CL04 | TPX09 - LV power cable | E | PS5-71-19 - Diesel Separator Module (UCP) | To be completed
T-00233-4712 | PS5-01-LB-0004-CL02 | TPX09 - LV power cable | E | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00233-4724 | PS5-03-SEA-0002-CL01 | TPX09 - LV power cable | E | PS5-03-22 - FZ-G1 - Guard House | To be completed
T-00233-4725 | PS5-03-SEA-0003-CL01 | TPX09 - LV power cable | E | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00233-4809 | PS5-08-11CB-1901-CL01 | TPX09 - LV power cable | E | PS5-08-11 - Corporate LAN (SIE) | To be completed
T-00233-4810 | PS5-08-11CB-1901-CL02 | TPX09 - LV power cable | E | PS5-08-11 - Corporate LAN (SIE) | To be completed
T-00233-4811 | PS5-08-11CB-1901-CL03 | TPX09 - LV power cable | E | PS5-08-11 - Corporate LAN (SIE) | To be completed
T-00233-4878 | PS5-09-LB-0008-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-4879 | PS5-09-LB-0008-CL02 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-4990 | PS5-60-BE-0003D-CL01 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | To be completed
T-00233-4994 | PS5-60-BE-0004A-CL01 | TPX09 - LV power cable | E | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | To be completed
T-00233-4995 | PS5-60-BE-0004B-CL01 | TPX09 - LV power cable | E | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | To be completed
T-00233-4997 | PS5-60-BE-0004D-CL01 | TPX09 - LV power cable | E | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | To be completed
T-00233-5032 | PS5-60-BE-0013A-CL01 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | To be completed
T-00233-5136 | PS5-60-BI-0015A-CL01 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | To be completed
T-00233-5139 | PS5-60-BI-0015B-CL01 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | To be completed
T-00233-5145 | PS5-60-BI-0015D-CL01 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | To be completed
T-00233-5154 | PS5-60-BI-0015G-CL01 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | To be completed
T-00233-5157 | PS5-60-DD-62800A-CL01 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | To be completed
T-00233-5159 | PS5-60-DD-62800C-CL01 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | To be completed
T-00233-5161 | PS5-60-DD-62800E-CL01 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | To be completed
T-00233-5163 | PS5-60-DD-62800G-CL01 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | To be completed
T-00233-5177 | PS5-60-IE-0002D-CL03 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | To be completed
T-00233-5180 | PS5-60-IE-0002E-CL03 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | To be completed
T-00233-5183 | PS5-60-IE-0002F-CL03 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | To be completed
T-00233-5186 | PS5-60-IE-0002G-CL03 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | To be completed
T-00233-5192 | PS5-60-IE-0003C-CL02 | TPX09 - LV power cable | E | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00233-5193 | PS5-60-IE-0003D-CL01 | TPX09 - LV power cable | E | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00233-5235 | PS5-60-IH-0001E-CL04 | TPX09 - LV power cable | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed
T-00233-5239 | PS5-60-IH-0001F-CL01 | TPX09 - LV power cable | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00233-5240 | PS5-60-IH-0001F-CL02 | TPX09 - LV power cable | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00233-5241 | PS5-60-IH-0001F-CL03 | TPX09 - LV power cable | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00233-5242 | PS5-60-IH-0001F-CL04 | TPX09 - LV power cable | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00233-5243 | PS5-60-IH-0001F-CL05 | TPX09 - LV power cable | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00233-5246 | PS5-60-IH-0001G-CL01 | TPX09 - LV power cable | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed
T-00233-5247 | PS5-60-IH-0001G-CL02 | TPX09 - LV power cable | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed
T-00233-5248 | PS5-60-IH-0001G-CL03 | TPX09 - LV power cable | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed
T-00233-5251 | PS5-60-IH-0001G-CL06 | TPX09 - LV power cable | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed
T-00233-5277 | PS5-60-IN-0002C-CL01 | TPX09 - LV power cable | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00233-5278 | PS5-60-IN-0002C-CL02 | TPX09 - LV power cable | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00233-5279 | PS5-60-IN-0002C-CL03 | TPX09 - LV power cable | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00233-5283 | PS5-60-IN-0002E-CL01 | TPX09 - LV power cable | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00233-5286 | PS5-60-IN-0002F-CL01 | TPX09 - LV power cable | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00233-5289 | PS5-60-IN-0002G-CL01 | TPX09 - LV power cable | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00233-5292 | PS5-60-IWK-0001A-CL01 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | To be completed
T-00233-5293 | PS5-60-IWK-0001A-CL02 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | To be completed
T-00233-5357 | PS5-61-IH-0004-CL15 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-5358 | PS5-61-IH-0004-CL16 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-5360 | PS5-61-IH-0004-CL18 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-5361 | PS5-61-IH-0004-CL19 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-5362 | PS5-61-IH-0004-CL20 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-5363 | PS5-61-IH-0004-CL21 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-5427 | PS5-61-IK-0003-CL03 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed
T-00233-5487 | PS5-05-IG-0002-CL01 | TPX09 - LV power cable | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00233-5532 | PS5-61-IU-3100A-CL01 | TPX09 - LV power cable | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-33/1-05-0217
T-00233-5533 | PS5-61-IU-3100B-CL01 | TPX09 - LV power cable | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-33/1-05-0217
T-00233-5534 | PS5-61-IU-3100C-CL01 | TPX09 - LV power cable | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-33/1-05-0217
T-00233-5603 | PS5-71-SDV-0022-CL01 | TPX09 - LV power cable | E | PS5-71-04 - CFO Storage Tank | To be completed
T-00233-5609 | PS5-71-XV-0091-CL01 | TPX09 - LV power cable | E | PS5-71-18 - Diesel Separator Module | To be completed
T-00233-5621 | PS5-75-UI-6200-CL01 | TPX09 - LV power cable | E | PS5-75-01 - DRA Injection Package | To be completed
T-00233-5622 | PS5-75-UI-6200-CL02 | TPX09 - LV power cable | E | PS5-75-01 - DRA Injection Package | To be completed
T-00233-5623 | PS5-78-JC-9100A-CL01 | TPX09 - LV power cable | E | PS5-78-01 - Lifting and handling equipment | To be completed
T-00233-8829 | PS5-79-IG-0001-CL01 | TPX09 - LV power cable | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00233-8830 | PS5-79-IG-0002-CL01 | TPX09 - LV power cable | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00233-8831 | PS5-79-IG-0003-CL01 | TPX09 - LV power cable | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00233-8832 | PS5-79-IG-0004-CL01 | TPX09 - LV power cable | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00233-8833 | PS5-79-IG-0005-CL01 | TPX09 - LV power cable | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00233-8834 | PS5-79-IG-0006-CL01 | TPX09 - LV power cable | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00233-8835 | PS5-79-IG-0007-CL01 | TPX09 - LV power cable | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00233-8836 | PS5-79-IG-0008-CL01 | TPX09 - LV power cable | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00233-8837 | PS5-79-IG-0009-CL01 | TPX09 - LV power cable | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00233-8838 | PS5-79-IG-0010-CL01 | TPX09 - LV power cable | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00233-8839 | PS5-79-IG-0011-CL01 | TPX09 - LV power cable | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00233-8840 | PS5-79-IG-0012-CL01 | TPX09 - LV power cable | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00233-9122 | PS5-06-GU-0005-CL01 | TPX09 - LV power cable | E | PS5-06-04 - AC UPS - Guard House | To be completed
T-00233-9128 | PS5-09-LB-7001-CL01 | TPX09 - LV power cable | E | PS5-09-02 - HVAC for Guard House | To be completed
T-00233-9139 | PS5-60-BE-0027B-CL01 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed
T-00233-9140 | PS5-60-BE-0027C-CL01 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00233-9141 | PS5-60-BE-0027D-CL01 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00233-9142 | PS5-60-BE-0027E-CL01 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00233-9143 | PS5-60-BE-0027F-CL01 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00233-9144 | PS5-60-BE-0027G-CL01 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00233-9147 | PS5-60-BE-0028C-CL01 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00233-9148 | PS5-60-BE-0028D-CL01 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00233-9175 | PS5-60-BI-0006C-CL02 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00233-9184 | PS5-60-BI-0006C-CL11 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00233-9186 | PS5-60-BI-0006D-CL02 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00233-9197 | PS5-60-BI-0006E-CL02 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00233-9199 | PS5-60-BI-0006E-CL04 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00233-9200 | PS5-60-BI-0006E-CL05 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00233-9201 | PS5-60-BI-0006E-CL06 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00233-9202 | PS5-60-BI-0006E-CL07 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00233-9204 | PS5-60-BI-0006E-CL09 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00233-9205 | PS5-60-BI-0006E-CL10 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00233-9207 | PS5-60-BI-0006F-CL01 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00233-9208 | PS5-60-BI-0006F-CL02 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00233-9209 | PS5-60-BI-0006F-CL03 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00233-9211 | PS5-60-BI-0006F-CL05 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00233-9212 | PS5-60-BI-0006F-CL06 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00233-9213 | PS5-60-BI-0006F-CL07 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00233-9214 | PS5-60-BI-0006F-CL08 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00233-9215 | PS5-60-BI-0006F-CL09 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00233-9216 | PS5-60-BI-0006F-CL10 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00233-9218 | PS5-60-BI-0006G-CL01 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00233-9219 | PS5-60-BI-0006G-CL02 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00233-9220 | PS5-60-BI-0006G-CL03 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00233-9221 | PS5-60-BI-0006G-CL04 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00233-9222 | PS5-60-BI-0006G-CL05 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00233-9223 | PS5-60-BI-0006G-CL06 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00233-9224 | PS5-60-BI-0006G-CL07 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00233-9225 | PS5-60-BI-0006G-CL08 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00233-9226 | PS5-60-BI-0006G-CL09 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00233-9227 | PS5-60-BI-0006G-CL10 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00233-9236 | PS5-60-EA-2900A-CL01 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed
T-00233-9237 | PS5-60-EA-2900B-CL01 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed
T-00233-9243 | PS5-61-IK-0005-CL01 | TPX09 - LV power cable | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00233-9245 | PS5-71-BE-0004-CL02 | TPX09 - LV power cable | E | PS5-71-08 - CFO Pre-Pressure Modules | To be completed
T-00233-9680 | PS5-09-AHU-8111A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9681 | PS5-09-AHU-8111B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9682 | PS5-09-AHU-8211A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9683 | PS5-09-AHU-8211B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9684 | PS5-09-AHU-8311A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9685 | PS5-09-AHU-8311A-CL02 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9686 | PS5-09-AHU-8311B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9687 | PS5-09-AHU-8311B-CL02 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9688 | PS5-09-AHU-8321A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9689 | PS5-09-AHU-8321A-CL02 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9690 | PS5-09-AHU-8321B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9691 | PS5-09-AHU-8321B-CL02 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9692 | PS5-09-AHU-8331A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9693 | PS5-09-AHU-8331A-CL02 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9694 | PS5-09-AHU-8331B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9695 | PS5-09-AHU-8331B-CL02 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9696 | PS5-09-AHU-8341-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9697 | PS5-09-AHU-8341-CL02 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9698 | PS5-09-AHU-8411A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9699 | PS5-09-AHU-8411A-CL02 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9700 | PS5-09-AHU-8411B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9701 | PS5-09-AHU-8411B-CL02 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9702 | PS5-09-FCU-8442A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9703 | PS5-09-FCU-8442B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9704 | PS5-09-FCU-8442C-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9705 | PS5-09-FCU-8442D-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9706 | PS5-09-FCU-8442E-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9707 | PS5-09-FCU-8442F-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9708 | PS5-09-FCU-8442G-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9709 | PS5-09-FCU-8442H-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9710 | PS5-09-LB-0008-CL03 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9711 | PS5-09-PA-84500A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9712 | PS5-09-PA-84500B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9713 | PS5-09-QX-8451A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9714 | PS5-09-QX-8451A-CL02 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9715 | PS5-09-QX-8451B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9716 | PS5-09-QX-8451B-CL02 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9717 | PS5-09-RF-81200A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9718 | PS5-09-RF-81200B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9719 | PS5-09-RF-81200C-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9720 | PS5-09-RF-82200A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9721 | PS5-09-RF-82200B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9722 | PS5-09-RF-82200C-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9723 | PS5-09-RF-82200D-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9724 | PS5-09-RF-83500A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9725 | PS5-09-RF-83500B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9726 | PS5-09-RF-83500C-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9727 | PS5-09-RF-83500D-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9728 | PS5-09-RF-83500E-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9729 | PS5-09-RF-83500F-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9730 | PS5-09-RF-83500G-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9731 | PS5-09-RF-83500H-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9732 | PS5-09-RF-83500J-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9733 | PS5-09-RF-83500K-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9734 | PS5-09-RF-83500L-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9735 | PS5-09-RF-83500M-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9736 | PS5-09-RF-83500N-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9737 | PS5-09-RF-83500P-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9738 | PS5-09-RF-83600A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9739 | PS5-09-RF-83600B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9740 | PS5-09-RF-83600C-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9741 | PS5-09-RF-83600D-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9742 | PS5-09-RF-83600E-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9743 | PS5-09-RF-83600F-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9744 | PS5-09-RF-83600G-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9745 | PS5-09-RF-83600H-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9746 | PS5-09-RF-83600J-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9747 | PS5-09-RF-83600K-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9748 | PS5-09-RF-83600L-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9749 | PS5-09-RF-83600M-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9750 | PS5-09-RF-83600N-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9751 | PS5-09-RF-83600P-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9752 | PS5-09-RF-83700A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9753 | PS5-09-RF-83700B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9754 | PS5-09-RF-83700C-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9755 | PS5-09-RF-83700D-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9756 | PS5-09-RF-83700E-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9757 | PS5-09-RF-83700F-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9758 | PS5-09-RF-83700G-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9759 | PS5-09-RF-83700H-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9760 | PS5-09-RF-83700J-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9761 | PS5-09-RF-83700K-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9762 | PS5-09-RF-83700L-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9763 | PS5-09-RF-83700M-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9764 | PS5-09-RF-83700N-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9765 | PS5-09-RF-83700P-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9766 | PS5-09-RF-83800A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9767 | PS5-09-RF-83800B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9768 | PS5-09-RF-83800C-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9769 | PS5-09-RF-83800D-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9770 | PS5-09-RF-83800E-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9771 | PS5-09-RF-83800F-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9772 | PS5-09-RF-83800G-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9773 | PS5-09-RF-84200A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9774 | PS5-09-RF-84200B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9775 | PS5-09-UZ-84600-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9776 | PS5-61-IH-0004A-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9777 | PS5-61-IH-0004B-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9778 | PS5-61-IH-0004C-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00233-9779 | PS5-61-IH-0004D-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-2035 | PS5-05-IE-8100-CD08 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00234-2037 | PS5-05-IE-8100-CD10 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00234-2039 | PS5-05-IE-8100-CD12 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00234-2040 | PS5-05-IE-8100-CD13 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00234-2041 | PS5-05-IE-8100-CD14 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00234-2042 | PS5-05-IE-8100-CD15 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00234-2043 | PS5-05-IE-8100-CD16 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00234-2044 | PS5-05-IE-8100-CD17 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00234-2097 | PS5-50-IE-0001-CD01 | TPX10 - Multicore electrical control cable | E | PS5-50-01 - Water Well Submersible Pumps (3100) | To be completed
T-00234-2098 | PS5-50-IE-0002-CD01 | TPX10 - Multicore electrical control cable | E | PS5-50-02 - Water Well Submersible Pumps (3200) | To be completed
T-00234-2153 | PS5-60-IE-0003C-CD02 | TPX10 - Multicore electrical control cable | E | PS5-60-07 - Power Generation Package C | To be completed
T-00234-2154 | PS5-60-IE-0003C-CD03 | TPX10 - Multicore electrical control cable | E | PS5-60-07 - Power Generation Package C | To be completed
T-00234-2156 | PS5-60-IE-0003C-CD05 | TPX10 - Multicore electrical control cable | E | PS5-60-07 - Power Generation Package C | To be completed
T-00234-2165 | PS5-60-IE-0003C-CD14 | TPX10 - Multicore electrical control cable | E | PS5-60-07 - Power Generation Package C | To be completed
T-00234-2166 | PS5-60-IE-0003C-CD15 | TPX10 - Multicore electrical control cable | E | PS5-60-07 - Power Generation Package C | To be completed
T-00234-2168 | PS5-60-IE-0003D-CD02 | TPX10 - Multicore electrical control cable | E | PS5-60-10 - Power Generation Package D | To be completed
T-00234-2181 | PS5-60-IE-0003D-CD15 | TPX10 - Multicore electrical control cable | E | PS5-60-10 - Power Generation Package D | To be completed
T-00234-2183 | PS5-60-IE-0003E-CD02 | TPX10 - Multicore electrical control cable | E | PS5-60-13 - Power Generation Package E | To be completed
T-00234-2184 | PS5-60-IE-0003E-CD03 | TPX10 - Multicore electrical control cable | E | PS5-60-13 - Power Generation Package E | To be completed
T-00234-2186 | PS5-60-IE-0003E-CD05 | TPX10 - Multicore electrical control cable | E | PS5-60-13 - Power Generation Package E | To be completed
T-00234-2195 | PS5-60-IE-0003E-CD14 | TPX10 - Multicore electrical control cable | E | PS5-60-13 - Power Generation Package E | To be completed
T-00234-2196 | PS5-60-IE-0003E-CD15 | TPX10 - Multicore electrical control cable | E | PS5-60-13 - Power Generation Package E | To be completed
T-00234-2201 | PS5-60-IE-0003F-CD05 | TPX10 - Multicore electrical control cable | E | PS5-60-16 - Power Generation Package F | To be completed
T-00234-2210 | PS5-60-IE-0003F-CD14 | TPX10 - Multicore electrical control cable | E | PS5-60-16 - Power Generation Package F | To be completed
T-00234-3288 | PS5-79-IG-0001-CD01 | TPX10 - Multicore electrical control cable | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00234-3289 | PS5-79-IG-0002-CD01 | TPX10 - Multicore electrical control cable | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00234-3290 | PS5-79-IG-0003-CD01 | TPX10 - Multicore electrical control cable | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00234-3291 | PS5-79-IG-0004-CD01 | TPX10 - Multicore electrical control cable | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00234-3292 | PS5-79-IG-0005-CD01 | TPX10 - Multicore electrical control cable | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00234-3293 | PS5-79-IG-0006-CD01 | TPX10 - Multicore electrical control cable | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00234-3294 | PS5-79-IG-0007-CD01 | TPX10 - Multicore electrical control cable | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00234-3295 | PS5-79-IG-0008-CD01 | TPX10 - Multicore electrical control cable | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00234-3296 | PS5-79-IG-0009-CD01 | TPX10 - Multicore electrical control cable | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00234-3297 | PS5-79-IG-0010-CD01 | TPX10 - Multicore electrical control cable | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00234-3298 | PS5-79-IG-0011-CD01 | TPX10 - Multicore electrical control cable | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00234-3299 | PS5-79-IG-0012-CD01 | TPX10 - Multicore electrical control cable | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00234-3634 | PS5-09-IES-8101A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3635 | PS5-09-IES-8101B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3636 | PS5-09-IES-8102A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3637 | PS5-09-IES-8102B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3638 | PS5-09-IES-8102C-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3639 | PS5-09-IES-8201A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3640 | PS5-09-IES-8201B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3641 | PS5-09-IES-8202A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3642 | PS5-09-IES-8202B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3643 | PS5-09-IES-8202C-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3644 | PS5-09-IES-8202D-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3645 | PS5-09-IES-8301A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3646 | PS5-09-IES-8301B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3647 | PS5-09-IES-8302A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3648 | PS5-09-IES-8302B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3649 | PS5-09-IES-8304A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3650 | PS5-09-IES-8304B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3651 | PS5-09-IES-8305A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3652 | PS5-09-IES-8305B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3653 | PS5-09-IES-8307A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3654 | PS5-09-IES-8307B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3655 | PS5-09-IES-8308A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3656 | PS5-09-IES-8308B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3657 | PS5-09-IES-8311A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3658 | PS5-09-IES-8311B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3659 | PS5-09-IES-8313-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3660 | PS5-09-IES-8314-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3661 | PS5-09-IES-8315-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3662 | PS5-09-IES-8316-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3663 | PS5-09-IES-8317-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3664 | PS5-09-IES-8318-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3665 | PS5-09-IES-8319-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3666 | PS5-09-IES-8321-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3667 | PS5-09-IES-8322-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3668 | PS5-09-IES-8323-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3669 | PS5-09-IES-8324-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3670 | PS5-09-IES-8325-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3671 | PS5-09-IES-8401A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3672 | PS5-09-IES-8401B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3673 | PS5-09-IES-8403A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3674 | PS5-09-IES-8403B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3675 | PS5-09-IES-8404A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3676 | PS5-09-IES-8404B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3677 | PS5-09-IES-8405A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3678 | PS5-09-IES-8405B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3679 | PS5-09-IES-8406A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3680 | PS5-09-IES-8406B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3681 | PS5-09-IES-8406C-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3682 | PS5-09-IES-8406D-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3683 | PS5-09-IES-8406E-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3684 | PS5-09-IES-8406F-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3685 | PS5-09-IES-8406G-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3686 | PS5-09-IES-8406H-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00234-3687 | PS5-09-IES-8407-CD01 | TPX10 - Multicore electrical control cable | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00236-0155 | PS5-28-DM-3300 | TPX13 - Motor LV | E | PS5-28-06 - Relief Drum and Pump | To be completed
T-00236-0156 | PS5-28-DM-3400 | TPX13 - Motor LV | E | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00236-0157 | PS5-28-DM-3500 | TPX13 - Motor LV | E | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00236-0158 | PS5-28-DM-3600A | TPX13 - Motor LV | E | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00236-0159 | PS5-28-DM-3600B | TPX13 - Motor LV | E | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00236-0160 | PS5-28-DM-3700A | TPX13 - Motor LV | E | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00236-0161 | PS5-28-DM-3700B | TPX13 - Motor LV | E | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00236-0162 | PS5-28-DM-3800A | TPX13 - Motor LV | E | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00236-0163 | PS5-28-DM-3800B | TPX13 - Motor LV | E | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00236-0164 | PS5-28-DM-3800C | TPX13 - Motor LV | E | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00236-0165 | PS5-28-DM-3900A | TPX13 - Motor LV | E | PS5-28-17 - Reinjection Pump | To be completed
T-00236-0166 | PS5-28-DM-3900B | TPX13 - Motor LV | E | PS5-28-17 - Reinjection Pump | To be completed
T-00236-0167 | PS5-53-DM-3100A | TPX13 - Motor LV | E | PS5-53-02 - Water Distribution Pump A/B | To be completed
T-00236-0168 | PS5-53-DM-3100B | TPX13 - Motor LV | E | PS5-53-02 - Water Distribution Pump A/B | To be completed
T-00236-0169 | PS5-60-DM-3300 | TPX13 - Motor LV | E | PS5-60-24 - Cooling Water Tank & Pump | To be completed
T-00236-0170 | PS5-60-DM-3400 | TPX13 - Motor LV | E | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | To be completed
T-00236-0171 | PS5-71-DM-3100A | TPX13 - Motor LV | E | PS5-71-16 - Diesel Fuel Supply Pump A/B | To be completed
T-00236-0172 | PS5-71-DM-3100B | TPX13 - Motor LV | E | PS5-71-16 - Diesel Fuel Supply Pump A/B | To be completed
T-00236-0173 | PS5-71-DM-3200 | TPX13 - Motor LV | E | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | To be completed
T-00236-0174 | PS5-71-DM-3300A | TPX13 - Motor LV | E | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00236-0175 | PS5-71-DM-3300B | TPX13 - Motor LV | E | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00236-0176 | PS5-71-DM-3400A | TPX13 - Motor LV | E | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00236-0177 | PS5-71-DM-3400B | TPX13 - Motor LV | E | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00236-0178 | PS5-71-DM-3500A | TPX13 - Motor LV | E | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00236-0179 | PS5-71-DM-3500B | TPX13 - Motor LV | E | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00236-0286 | PS5-28-DM-31100 | TPX13 - Motor LV | E | PS5-28-10 - Oil Skimmer Package | To be completed
T-00238-0457 | PS5-60-IE-0003A | TPX15 - Distribution board/console/control panel | E | PS5-60-02 - Power Gen Package A (UCP) | To be completed
T-00238-0458 | PS5-60-IE-0003B | TPX15 - Distribution board/console/control panel | E | PS5-60-05 - Power Gen Package B (UCP) | To be completed
T-00238-0459 | PS5-60-IE-0003C | TPX15 - Distribution board/console/control panel | E | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00238-0460 | PS5-60-IE-0003D | TPX15 - Distribution board/console/control panel | E | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00238-0461 | PS5-60-IE-0003E | TPX15 - Distribution board/console/control panel | E | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00238-0462 | PS5-60-IE-0003F | TPX15 - Distribution board/console/control panel | E | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00238-0463 | PS5-60-IE-0003G | TPX15 - Distribution board/console/control panel | E | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00238-0464 | PS5-60-IE-0004 | TPX15 - Distribution board/console/control panel | E | PS5-60-22 - Power Gen Master UCP | To be completed
T-00238-0465 | PS5-60-IH-0001A | TPX15 - Distribution board/console/control panel | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | Started (not Completed) |  | CPP-RFI-68-332-13-0424
T-00238-0466 | PS5-60-IH-0001B | TPX15 - Distribution board/console/control panel | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-332-13-0424
T-00238-0467 | PS5-60-IH-0001C | TPX15 - Distribution board/console/control panel | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-332-13-0424
T-00238-0468 | PS5-60-IH-0001D | TPX15 - Distribution board/console/control panel | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-332-13-0424
T-00238-0469 | PS5-60-IH-0001E | TPX15 - Distribution board/console/control panel | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-332-13-0424
T-00238-0470 | PS5-60-IH-0001F | TPX15 - Distribution board/console/control panel | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-332-13-0424
T-00238-0471 | PS5-60-IH-0001G | TPX15 - Distribution board/console/control panel | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed |  | CPP-RFI-68-332-13-0424
T-00238-0472 | PS5-60-IH-0002 | TPX15 - Distribution board/console/control panel | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-332-13-0424
T-00238-0473 | PS5-60-IE-0002A | TPX15 - Distribution board/console/control panel | E | PS5-60-01 - Power Generation Package A | To be completed
T-00238-0474 | PS5-60-IE-0002B | TPX15 - Distribution board/console/control panel | E | PS5-60-04 - Power Generation Package B | To be completed
T-00238-0475 | PS5-60-IE-0002C | TPX15 - Distribution board/console/control panel | E | PS5-60-07 - Power Generation Package C | To be completed
T-00238-0476 | PS5-60-IE-0002D | TPX15 - Distribution board/console/control panel | E | PS5-60-10 - Power Generation Package D | To be completed
T-00238-0477 | PS5-60-IE-0002E | TPX15 - Distribution board/console/control panel | E | PS5-60-13 - Power Generation Package E | To be completed
T-00238-0478 | PS5-60-IE-0002F | TPX15 - Distribution board/console/control panel | E | PS5-60-16 - Power Generation Package F | To be completed
T-00238-0479 | PS5-60-IE-0002G | TPX15 - Distribution board/console/control panel | E | PS5-60-19 - Power Generation Package G | To be completed
T-00238-0542 | PS5-01-IE-0001A | TPX15 - Distribution board/console/control panel | E | PS5-01-05 - Foam Skid | To be completed
T-00238-0543 | PS5-01-IE-0001B | TPX15 - Distribution board/console/control panel | E | PS5-01-05 - Foam Skid | To be completed
T-00238-0544 | PS5-01-IE-0002A | TPX15 - Distribution board/console/control panel | E | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00238-0545 | PS5-01-IE-0002B | TPX15 - Distribution board/console/control panel | E | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00238-0546 | PS5-01-IE-0009A | TPX15 - Distribution board/console/control panel | E | PS5-01-02 - Fire Water Pump A | To be completed
T-00238-0547 | PS5-01-IE-0009B | TPX15 - Distribution board/console/control panel | E | PS5-01-03 - Fire Water Pump B | To be completed
T-00238-0549 | PS5-05-IE-8100 | TPX15 - Distribution board/console/control panel | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed |  |  |  |  | TZ-MID-60-UTR2-150005 IE bar not connected to earth grid [OPEN] | TZ-MID-60-UTR2-150005 Cleanning internal and external of the panel [OPEN] ¦ TZ-MID-60-UTR2-150005 The Panel Frame need to be touch up paint [OPEN]
T-00238-0550 | PS5-50-IE-0001 | TPX15 - Distribution board/console/control panel | E | PS5-50-01 - Water Well Submersible Pumps (3100) | To be completed
T-00238-0551 | PS5-50-IE-0002 | TPX15 - Distribution board/console/control panel | E | PS5-50-02 - Water Well Submersible Pumps (3200) | To be completed
T-00238-0552 | PS5-60-IN-0002A | TPX15 - Distribution board/console/control panel | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed
T-00238-0553 | PS5-60-IN-0002B | TPX15 - Distribution board/console/control panel | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed
T-00238-0554 | PS5-60-IN-0002C | TPX15 - Distribution board/console/control panel | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00238-0555 | PS5-60-IN-0002D | TPX15 - Distribution board/console/control panel | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00238-0556 | PS5-60-IN-0002E | TPX15 - Distribution board/console/control panel | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00238-0557 | PS5-60-IN-0002F | TPX15 - Distribution board/console/control panel | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00238-0558 | PS5-60-IN-0002G | TPX15 - Distribution board/console/control panel | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00238-0559 | PS5-61-IH-0004 | TPX15 - Distribution board/console/control panel | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00238-0560 | PS5-61-IH-0004A | TPX15 - Distribution board/console/control panel | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00238-0561 | PS5-61-IH-0004B | TPX15 - Distribution board/console/control panel | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00238-0564 | PS5-71-IN-0001 | TPX15 - Distribution board/console/control panel | E | PS5-71-19 - Diesel Separator Module (UCP) | To be completed
T-00238-0565 | PS5-71-IN-0002 | TPX15 - Distribution board/console/control panel | E | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | To be completed
T-00238-0566 | PS5-71-IN-0003 | TPX15 - Distribution board/console/control panel | E | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed
T-00238-0567 | PS5-71-IN-0004A | TPX15 - Distribution board/console/control panel | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00238-0568 | PS5-71-IN-0004B | TPX15 - Distribution board/console/control panel | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00238-0714 | PS5-01-IG-0001 | TPX15 - Distribution board/console/control panel | E | PS5-01-10 - Water Mist Package | To be completed
T-00238-0715 | PS5-05-IG-0002 | TPX15 - Distribution board/console/control panel | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00238-0718 | PS5-05-IG-0007 | TPX15 - Distribution board/console/control panel | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00238-0719 | PS5-05-IG-0025 | TPX15 - Distribution board/console/control panel | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | To be completed
T-00238-0720 | PS5-05-IG-0026 | TPX15 - Distribution board/console/control panel | E | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | To be completed
T-00238-0721 | PS5-06-IG-0004A | TPX15 - Distribution board/console/control panel | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | [5 empty] | TZ-MID-60-RME2-150010 Cleanning internal and external of the panel [OPEN] ¦ TZ-MID-60-RME2-150010 The Panel Frame need to be touch up paint [OPEN]
T-00238-0722 | PS5-06-IG-0004B | TPX15 - Distribution board/console/control panel | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | [5 empty] | TZ-MID-60-RME2-150010 Cleanning internal and external of the panel [OPEN] ¦ TZ-MID-60-RME2-150010 The Panel Frame need to be touch up paint [OPEN]
T-00238-0726 | PS5-61-IG-0015 | TPX15 - Distribution board/console/control panel | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00238-0727 | PS5-61-IG-0016 | TPX15 - Distribution board/console/control panel | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed
T-00238-0730 | PS5-74-IG-5101 | TPX15 - Distribution board/console/control panel | E | PS5-74-01 - N2 Generation Skid | To be completed
T-00238-0742 | PS5-79-IG-0012 | TPX15 - Distribution board/console/control panel | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00238-0819 | PS5-09-LB-0008 | TPX15 - Distribution board/console/control panel | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00238-0820 | PS5-61-IH-0004C | TPX15 - Distribution board/console/control panel | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00238-0821 | PS5-61-IH-0004D | TPX15 - Distribution board/console/control panel | E | PS5-09-03 - HVAC for Generator Building | To be completed
T-00238-0858 | PS5-09-LB-7001 | TPX15 - Distribution board/console/control panel | E | PS5-09-02 - HVAC for Guard House | To be completed
T-00239-0234 | PS5-06-GU-0003A | TPX16 - Charger / inverter | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed
T-00239-0235 | PS5-06-GU-0003B | TPX16 - Charger / inverter | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed
T-00239-0236 | PS5-06-GU-0003C | TPX16 - Charger / inverter | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed
T-00240-1264 |  | TPX18 - Lighting circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00240-1265 |  | TPX18 - Lighting circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00240-1266 |  | TPX18 - Lighting circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00240-1267 |  | TPX18 - Lighting circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00240-1268 |  | TPX18 - Lighting circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00240-1269 |  | TPX18 - Lighting circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00240-1270 |  | TPX18 - Lighting circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00240-1271 |  | TPX18 - Lighting circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00240-1272 |  | TPX18 - Lighting circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | Started (not Completed)
T-00240-1273 |  | TPX18 - Lighting circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00240-1274 |  | TPX18 - Lighting circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00240-1275 |  | TPX18 - Lighting circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00240-1276 |  | TPX18 - Lighting circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | To be completed
T-00240-1277 |  | TPX18 - Lighting circuits | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00240-1278 |  | TPX18 - Lighting circuits | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00240-1279 |  | TPX18 - Lighting circuits | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00240-1280 |  | TPX18 - Lighting circuits | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00240-1281 |  | TPX18 - Lighting circuits | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | To be completed
T-00240-1282 |  | TPX18 - Lighting circuits | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | To be completed
T-00240-1283 |  | TPX18 - Lighting circuits | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | To be completed
T-00240-1284 |  | TPX18 - Lighting circuits | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | To be completed
T-00240-1285 |  | TPX18 - Lighting circuits | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | To be completed
T-00240-1286 |  | TPX18 - Lighting circuits | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | To be completed
T-00240-1287 |  | TPX18 - Lighting circuits | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | Started (not Completed)
T-00240-1288 |  | TPX18 - Lighting circuits | E | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | To be completed
T-00240-1289 |  | TPX18 - Lighting circuits | E | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | To be completed
T-00240-1290 |  | TPX18 - Lighting circuits | E | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | To be completed
T-00240-1291 |  | TPX18 - Lighting circuits | E | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | To be completed
T-00240-1292 |  | TPX18 - Lighting circuits | E | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | To be completed
T-00240-1293 |  | TPX18 - Lighting circuits | E | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | To be completed
T-00240-1294 |  | TPX18 - Lighting circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00240-1295 |  | TPX18 - Lighting circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00240-1296 |  | TPX18 - Lighting circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00240-1297 |  | TPX18 - Lighting circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00240-1298 |  | TPX18 - Lighting circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00240-1299 |  | TPX18 - Lighting circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00240-1300 |  | TPX18 - Lighting circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00240-1301 |  | TPX18 - Lighting circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00240-1302 |  | TPX18 - Lighting circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00240-1303 |  | TPX18 - Lighting circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00240-1304 |  | TPX18 - Lighting circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00240-1305 |  | TPX18 - Lighting circuits | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00240-1306 |  | TPX18 - Lighting circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00240-1307 |  | TPX18 - Lighting circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00240-1308 |  | TPX18 - Lighting circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00240-1309 |  | TPX18 - Lighting circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00240-1310 |  | TPX18 - Lighting circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00240-1311 |  | TPX18 - Lighting circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00240-1312 |  | TPX18 - Lighting circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00240-1313 |  | TPX18 - Lighting circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00240-1314 |  | TPX18 - Lighting circuits | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed
T-00240-1315 |  | TPX18 - Lighting circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | To be completed
T-00240-1318 |  | TPX18 - Lighting circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | To be completed
T-00240-1320 |  | TPX18 - Lighting circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | To be completed
T-00240-1322 |  | TPX18 - Lighting circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | To be completed
T-00240-1323 |  | TPX18 - Lighting circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | To be completed
T-00240-1325 |  | TPX18 - Lighting circuits | E | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010 | To be completed
T-00240-1326 |  | TPX18 - Lighting circuits | E | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010 | To be completed
T-00240-1327 |  | TPX18 - Lighting circuits | E | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010 | To be completed
T-00240-1328 |  | TPX18 - Lighting circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00240-1329 |  | TPX18 - Lighting circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00240-1330 |  | TPX18 - Lighting circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00240-1331 |  | TPX18 - Lighting circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00240-1332 |  | TPX18 - Lighting circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00240-1333 |  | TPX18 - Lighting circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00240-1334 |  | TPX18 - Lighting circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00240-1335 |  | TPX18 - Lighting circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00240-1336 |  | TPX18 - Lighting circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00240-1337 |  | TPX18 - Lighting circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00240-1338 |  | TPX18 - Lighting circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00240-1339 |  | TPX18 - Lighting circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00240-1340 |  | TPX18 - Lighting circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00240-1341 |  | TPX18 - Lighting circuits | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00240-1342 |  | TPX18 - Lighting circuits | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed
T-00240-1343 |  | TPX18 - Lighting circuits | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed
T-00240-1344 |  | TPX18 - Lighting circuits | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed
T-00240-1345 |  | TPX18 - Lighting circuits | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed
T-00240-1346 |  | TPX18 - Lighting circuits | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed
T-00240-1347 |  | TPX18 - Lighting circuits | E | PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111 | To be completed
T-00240-1348 |  | TPX18 - Lighting circuits | E | PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112 | To be completed
T-00240-1349 |  | TPX18 - Lighting circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00240-1350 |  | TPX18 - Lighting circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00240-1351 |  | TPX18 - Lighting circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00240-1352 |  | TPX18 - Lighting circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00240-1353 |  | TPX18 - Lighting circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00240-1354 |  | TPX18 - Lighting circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00240-1355 |  | TPX18 - Lighting circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00240-1356 |  | TPX18 - Lighting circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00240-1357 |  | TPX18 - Lighting circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00240-1358 |  | TPX18 - Lighting circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00240-1359 |  | TPX18 - Lighting circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00240-1360 |  | TPX18 - Lighting circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00240-1361 |  | TPX18 - Lighting circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00240-1362 |  | TPX18 - Lighting circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00240-1363 |  | TPX18 - Lighting circuits | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | To be completed
T-00240-1364 |  | TPX18 - Lighting circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00240-1365 |  | TPX18 - Lighting circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00240-1366 |  | TPX18 - Lighting circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00240-1367 |  | TPX18 - Lighting circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00240-1368 |  | TPX18 - Lighting circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00240-1369 |  | TPX18 - Lighting circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00240-1370 |  | TPX18 - Lighting circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00240-1371 |  | TPX18 - Lighting circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00240-1372 |  | TPX18 - Lighting circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00240-1373 |  | TPX18 - Lighting circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00240-1374 |  | TPX18 - Lighting circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00240-1375 |  | TPX18 - Lighting circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00240-1376 |  | TPX18 - Lighting circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00240-1377 |  | TPX18 - Lighting circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00240-1378 |  | TPX18 - Lighting circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00240-1379 |  | TPX18 - Lighting circuits | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed
T-00241-0165 | PS5-25-UD-3100A | TPX19 - Power socket outlet | E | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00241-0166 | PS5-28-ISO-2008 | TPX19 - Power socket outlet | E | PS5-28-10 - Oil Skimmer Package | To be completed
T-00241-0438 |  | TPX19 - Power socket outlet | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00241-0439 |  | TPX19 - Power socket outlet | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00241-0440 |  | TPX19 - Power socket outlet | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00241-0441 |  | TPX19 - Power socket outlet | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00241-0442 |  | TPX19 - Power socket outlet | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | To be completed
T-00241-0443 |  | TPX19 - Power socket outlet | E | PS5-06-05 - AC UPS - Workshop & Warehouse | To be completed
T-00241-0444 |  | TPX19 - Power socket outlet | E | PS5-06-05 - AC UPS - Workshop & Warehouse | To be completed
T-00241-0445 |  | TPX19 - Power socket outlet | E | PS5-06-05 - AC UPS - Workshop & Warehouse | To be completed
T-00241-0446 |  | TPX19 - Power socket outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00241-0447 |  | TPX19 - Power socket outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00241-0448 |  | TPX19 - Power socket outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00241-0449 |  | TPX19 - Power socket outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00241-0450 |  | TPX19 - Power socket outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00241-0451 |  | TPX19 - Power socket outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00241-0452 |  | TPX19 - Power socket outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00241-0453 |  | TPX19 - Power socket outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00241-0454 |  | TPX19 - Power socket outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00241-0455 |  | TPX19 - Power socket outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00241-0456 |  | TPX19 - Power socket outlet | E | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | To be completed
T-00241-0457 |  | TPX19 - Power socket outlet | E | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010 | To be completed
T-00241-0458 |  | TPX19 - Power socket outlet | E | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010 | To be completed
T-00241-0459 |  | TPX19 - Power socket outlet | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed
T-00241-0460 |  | TPX19 - Power socket outlet | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed
T-00241-0461 |  | TPX19 - Power socket outlet | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed
T-00241-0462 |  | TPX19 - Power socket outlet | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed
T-00241-0463 |  | TPX19 - Power socket outlet | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed
T-00241-0464 |  | TPX19 - Power socket outlet | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed
T-00241-0465 |  | TPX19 - Power socket outlet | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed
T-00241-0466 |  | TPX19 - Power socket outlet | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed
T-00241-0467 |  | TPX19 - Power socket outlet | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00241-0468 |  | TPX19 - Power socket outlet | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00241-0469 |  | TPX19 - Power socket outlet | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed
T-00241-0470 |  | TPX19 - Power socket outlet | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed
T-00241-0471 |  | TPX19 - Power socket outlet | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed
T-00241-0472 |  | TPX19 - Power socket outlet | E | PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111 | To be completed
T-00241-0473 |  | TPX19 - Power socket outlet | E | PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111 | To be completed
T-00241-0474 |  | TPX19 - Power socket outlet | E | PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112 | To be completed
T-00241-0475 |  | TPX19 - Power socket outlet | E | PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112 | To be completed
T-00242-0044 | PS5-28-HE-2100 | TPX20 - Heater | E | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00242-0045 | PS5-28-HE-2200 | TPX20 - Heater | E | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00242-0046 | PS5-71-HE-2200 | TPX20 - Heater | E | PS5-71-12 - CFO Service Tank | To be completed
T-00242-0047 | PS5-71-HE-2300 | TPX20 - Heater | E | PS5-71-04 - CFO Storage Tank | To be completed
T-00242-0048 | PS5-71-HE-2400A | TPX20 - Heater | E | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00242-0049 | PS5-71-HE-2400B | TPX20 - Heater | E | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00242-0068 | PS5-25-HE-2100 | TPX20 - Heater | E | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00242-0069 | PS5-25-HE-2200 | TPX20 - Heater | E | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00242-0070 | PS5-25-HE-2300 | TPX20 - Heater | E | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00243-0041 | PS5-61-NER-0010 | TPX21 - Neutral earthing resistor | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed
T-00243-0042 | PS5-61-NER-0011 | TPX21 - Neutral earthing resistor | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed
T-00243-0043 | PS5-63-NER-0010 | TPX21 - Neutral earthing resistor | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed
T-00243-0044 | PS5-63-NER-0011 | TPX21 - Neutral earthing resistor | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed
T-00243-0059 | PS5-60-IJ-0001A | TPX21 - Neutral earthing resistor | E | PS5-60-01 - Power Generation Package A | To be completed
T-00243-0060 | PS5-60-IJ-0001B | TPX21 - Neutral earthing resistor | E | PS5-60-04 - Power Generation Package B | To be completed
T-00243-0061 | PS5-60-IJ-0001C | TPX21 - Neutral earthing resistor | E | PS5-60-07 - Power Generation Package C | To be completed
T-00243-0062 | PS5-60-IJ-0001D | TPX21 - Neutral earthing resistor | E | PS5-60-10 - Power Generation Package D | To be completed
T-00243-0063 | PS5-60-IJ-0001E | TPX21 - Neutral earthing resistor | E | PS5-60-13 - Power Generation Package E | To be completed
T-00243-0064 | PS5-60-IJ-0001F | TPX21 - Neutral earthing resistor | E | PS5-60-16 - Power Generation Package F | To be completed
T-00243-0065 | PS5-60-IJ-0001G | TPX21 - Neutral earthing resistor | E | PS5-60-19 - Power Generation Package G | To be completed
T-00244-1357 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1358 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1359 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1360 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1361 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1362 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1363 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1364 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1365 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1366 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1367 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1368 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1369 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1370 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1371 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1372 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1373 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1374 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1375 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1376 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1377 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1378 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1379 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1380 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1381 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1382 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1383 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1384 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1385 |  | TPX22 - Tape Trace Heating | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed
T-00244-1386 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1387 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1388 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1389 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1390 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1391 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1392 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1393 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1394 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1395 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1396 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1397 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1398 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1399 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1400 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1401 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1402 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1403 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1404 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1405 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1406 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1407 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1408 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1409 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1410 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1411 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1412 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1413 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1414 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1415 |  | TPX22 - Tape Trace Heating | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed
T-00244-1416 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1417 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1418 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1419 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1420 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1421 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1422 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1423 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1424 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1425 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1426 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1427 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1428 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1429 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1430 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1431 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1432 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1433 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1434 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1435 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1436 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1437 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1438 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1439 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1440 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1441 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1442 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1443 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1444 |  | TPX22 - Tape Trace Heating | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed
T-00244-1445 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1446 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1447 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1448 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1449 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1450 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1451 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1452 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1453 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1454 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1455 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1456 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1457 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1458 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1459 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1460 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1461 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1462 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1463 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1464 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1465 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1466 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1467 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1468 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1469 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1470 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1471 |  | TPX22 - Tape Trace Heating | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed
T-00244-1472 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1473 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1474 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1475 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1476 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1477 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1478 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1479 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1480 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1481 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1482 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1483 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1484 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1485 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1486 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1487 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1488 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1489 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1490 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1491 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1492 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1493 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1494 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1495 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1496 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1497 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1498 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1499 |  | TPX22 - Tape Trace Heating | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed
T-00244-1500 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1501 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1502 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1503 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1504 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1505 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1506 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1507 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1508 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1509 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1510 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1511 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1512 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1513 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1514 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1515 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1516 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1517 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1518 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1519 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1520 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1521 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1522 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1523 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1524 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1525 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1526 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1527 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1528 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1529 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1530 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1531 |  | TPX22 - Tape Trace Heating | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed
T-00244-1532 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1533 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1534 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1535 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1536 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1537 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1538 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1539 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1540 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1541 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1542 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1543 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1544 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1545 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1546 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | Started (not Completed)
T-00244-1547 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1548 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1549 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1550 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1551 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1552 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1553 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1554 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1555 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1556 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1557 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1558 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1559 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1560 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1561 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1562 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1563 |  | TPX22 - Tape Trace Heating | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed
T-00244-1564 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1565 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1566 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1567 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1568 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1569 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1570 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1571 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1572 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1573 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1574 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1575 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1576 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1577 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1578 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1579 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1580 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1581 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1582 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1583 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1584 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1585 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1586 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1587 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1588 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1589 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1590 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1591 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1592 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1593 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1594 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1595 |  | TPX22 - Tape Trace Heating | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed
T-00244-1596 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1597 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1598 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1599 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1600 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1601 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1602 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1603 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1604 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1605 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1606 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1607 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1608 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1609 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1610 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1611 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1612 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1613 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1614 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1615 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1616 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1617 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1618 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1619 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1620 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1621 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1622 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1623 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1624 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1625 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1626 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1627 |  | TPX22 - Tape Trace Heating | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed
T-00244-1628 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1629 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1630 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1631 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1632 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1633 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1634 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1635 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1636 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1637 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1638 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1639 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1640 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1641 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1642 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1643 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1644 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1645 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1646 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1647 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1648 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1649 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1650 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1651 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1652 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1653 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1654 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1655 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1656 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1657 |  | TPX22 - Tape Trace Heating | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed
T-00244-1658 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1659 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1660 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1661 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1662 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1663 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1664 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1665 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1666 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1667 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1668 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1669 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1670 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1671 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1672 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1673 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1674 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1675 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1676 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1677 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1678 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1679 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1680 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1681 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1682 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1683 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1684 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1685 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1686 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1687 |  | TPX22 - Tape Trace Heating | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed
T-00244-1688 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1689 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1690 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1691 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1692 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1693 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1694 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1695 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1696 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1697 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1698 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1699 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1700 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1701 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1702 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1703 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1704 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1705 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1706 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1707 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1708 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1709 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1710 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1711 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1712 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1713 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1714 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1715 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1716 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1717 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1718 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1719 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1720 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1721 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00244-1722 |  | TPX22 - Tape Trace Heating | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed
T-00247-0134 | PS5 - CFO AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0135 | PS5 - CHEMICAL AND WASTE STORAGE AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0136 | PS5 - CLOSED DRAIN DRUM AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0137 | PS5 - DIESEL FUEL STORAGE AND PUMP AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | Started (not Completed)
T-00247-0138 | PS5 - EXPORT PUMP VSD AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0139 | PS5 - EXPORT LOADING PUMP AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0140 | PS5 - FENCE EAST AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0141 | PS5 - FENCE SOUTH WEST AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0142 | PS5 - FENCE WEST AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0143 | PS5 - FENCE SOUTH EAST AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0144 | PS5 - LAUNCHER/RECEIVER AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0145 | PS5 - OBSERVATION BASIN AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0146 | PS5 - POWER DISTRIBUTION AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0147 | PS5 - POWER GENERATION BUILDING AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0148 | PS5 - POWER GENERATION COOLING TOWER AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0149 | PS5 - TURNSTILE GATE AND OFFICE BUILDING AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0150 | PS5 - UTILITY AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0151 | PS5 - UTILITY/FIRE WATER STORAGE TANK AREA_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0152 | PS5-82-OB-0001_Earthing | TPX26 - Earthing system | E | PS5-63-02 - Electrical Earthing - Office and Facilities building | To be completed
T-00247-0153 | PS5-82-OB-0005_Earthing | TPX26 - Earthing system | E | PS5-63-06 - Electrical Earthing - Guard House | To be completed
T-00247-0154 | PS5-82-OB-0009A_Earthing | TPX26 - Earthing system | E | PS5-63-05 - Electrical Earthing - Guard Hut A & B | To be completed
T-00247-0155 | PS5-82-OB-0009B_Earthing | TPX26 - Earthing system | E | PS5-63-05 - Electrical Earthing - Guard Hut A & B | To be completed
T-00247-0157 | PS5-84-OB-0001_Earthing | TPX26 - Earthing system | E | PS5-63-07 - Electrical Earthing - Workshop & Warehouse | To be completed
T-00247-0158 | PS5-84-OB-0003_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0159 | PS5-84-OB-0004_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0160 | PS5-84-OB-0005_Earthing | TPX26 - Earthing system | E | PS5-63-03 - Electrical Earthing - Generator Building | To be completed
T-00247-0161 | PS5-84-OB-0006_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0162 | PS5-84-OB-0007_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0163 | PS5-86-OB-0001_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0164 | PS5-86-OB-0002_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0165 | PS5-86-OB-0003_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00247-0166 | PS5-86-OB-0004_Earthing | TPX26 - Earthing system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00248-0052 | PS5 - RECEIVER AND LAUNCHER AREA_Lightning | TPX28 - Lightning protection system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00248-0053 | PS5-82-OB-0001_Lightning | TPX28 - Lightning protection system | E | PS5-63-02 - Electrical Earthing - Office and Facilities building | To be completed
T-00248-0054 | PS5-82-OB-0005_Lightning | TPX28 - Lightning protection system | E | PS5-63-06 - Electrical Earthing - Guard House | To be completed
T-00248-0055 | PS5-82-OB-0009A_Lightning | TPX28 - Lightning protection system | E | PS5-63-05 - Electrical Earthing - Guard Hut A & B | To be completed
T-00248-0056 | PS5-82-OB-0009B_Lightning | TPX28 - Lightning protection system | E | PS5-63-05 - Electrical Earthing - Guard Hut A & B | To be completed
T-00248-0057 | PS5-84-OB-0001_Lightning | TPX28 - Lightning protection system | E | PS5-63-07 - Electrical Earthing - Workshop & Warehouse | To be completed
T-00248-0058 | PS5-84-OB-0003_Lightning | TPX28 - Lightning protection system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00248-0059 | PS5-84-OB-0005_Lightning | TPX28 - Lightning protection system | E | PS5-63-03 - Electrical Earthing - Generator Building | To be completed
T-00248-0060 | PS5-84-OB-0006_Lightning | TPX28 - Lightning protection system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00248-0061 | PS5-84-OB-0007_Lightning | TPX28 - Lightning protection system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00248-0062 | PS5-86-OB-0001_Lightning | TPX28 - Lightning protection system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00248-0063 | PS5-86-OB-0002_Lightning | TPX28 - Lightning protection system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00248-0064 | PS5-86-OB-0003_Lightning | TPX28 - Lightning protection system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00248-0065 | PS5-86-OB-0004_Lightning | TPX28 - Lightning protection system | E | PS5-63-01 - Electrical Earthing | To be completed
T-00249-0008 | PS5-53-TR-4100 | TPX33 - Cathodic protection | E | PS5-53-01 - Utility Water / Storage Tank | To be completed
T-00249-0009 | PS5-71-TR-4100 | TPX33 - Cathodic protection | E | PS5-71-04 - CFO Storage Tank | To be completed
T-00249-0010 | PS5-71-TR-4200 | TPX33 - Cathodic protection | E | PS5-71-12 - CFO Service Tank | To be completed
T-00249-0011 | PS5-71-TR-4400 | TPX33 - Cathodic protection | E | PS5-71-15 - Diesel Fuel Storage Tank | To be completed
T-00251-0115 | PS5-25-PSV-1103 | TJX03 - Relief valve | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00251-0116 | PS5-28-PSV-0064C | TJX03 - Relief valve | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00251-0117 | PS5-25-PSV-1203 | TJX03 - Relief valve | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00251-0118 | PS5-28-PRV-0047B | TJX03 - Relief valve | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00251-0119 | PS5-74-PSV-0003 | TJX03 - Relief valve | I | PS5-74-03 - Nitrogen Receiver | To be completed
T-00251-0120 | PS5-28-PRV-0040 | TJX03 - Relief valve | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00251-0121 | PS5-50-PSV-0004A | TJX03 - Relief valve | I | PS5-50-01 - Water Well Submersible Pumps (3100) | To be completed
T-00251-0122 | PS5-71-PSV-2403A | TJX03 - Relief valve | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00251-0123 | PS5-28-PSV-3901B | TJX03 - Relief valve | I | PS5-28-17 - Reinjection Pump | To be completed
T-00251-0124 | PS5-28-PRV-0047A | TJX03 - Relief valve | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00251-0125 | PS5-71-PVSV-4202 | TJX03 - Relief valve | I | PS5-71-12 - CFO Service Tank | To be completed
T-00251-0126 | PS5-71-PVSV-4102 | TJX03 - Relief valve | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00251-0127 | PS5-28-PRV-0046A | TJX03 - Relief valve | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00251-0128 | PS5-28-PRV-0008 | TJX03 - Relief valve | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00251-0129 | PS5-28-PSV-0064A | TJX03 - Relief valve | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00251-0130 | PS5-28-PRV-0054 | TJX03 - Relief valve | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00251-0131 | PS5-28-PSV-0044 | TJX03 - Relief valve | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00251-0132 | PS5-71-PRV-0016 | TJX03 - Relief valve | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00251-0133 | PS5-28-PRV-0046B | TJX03 - Relief valve | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00251-0134 | PS5-71-PRV-0015 | TJX03 - Relief valve | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00251-0135 | PS5-71-PRV-0018 | TJX03 - Relief valve | I | PS5-71-12 - CFO Service Tank | To be completed
T-00251-0136 | PS5-71-PRV-0041 | TJX03 - Relief valve | I | PS5-71-12 - CFO Service Tank | To be completed
T-00251-0137 | PS5-71-PSV-2403B | TJX03 - Relief valve | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00251-0138 | PS5-28-PRV-0046C | TJX03 - Relief valve | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00251-0139 | PS5-28-PRV-0047C | TJX03 - Relief valve | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00251-0140 | PS5-28-PRV-0055 | TJX03 - Relief valve | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00251-0141 | PS5-28-PSV-0061 | TJX03 - Relief valve | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00251-0142 | PS5-28-PSV-0064B | TJX03 - Relief valve | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00251-0143 | PS5-28-PSV-3901A | TJX03 - Relief valve | I | PS5-28-17 - Reinjection Pump | To be completed
T-00251-0144 | PS5-50-PSV-0004B | TJX03 - Relief valve | I | PS5-50-02 - Water Well Submersible Pumps (3200) | To be completed
T-00254-10862 | PS5-03-RAB-B402-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10863 | PS5-03-RAB-B902-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10864 | PS5-03-RAB-W502-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10865 | PS5-03-RDHR-W101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10866 | PS5-03-RDHR-W101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10867 | PS5-03-RDHR-W101C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10868 | PS5-03-RDHR-W101D-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10869 | PS5-03-RDHR-W101E-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10870 | PS5-03-RDHR-W101F-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10871 | PS5-03-RDHR-W101G-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10872 | PS5-03-RDHR-W101H-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10873 | PS5-03-RDHR-W101I-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10874 | PS5-03-RDHR-W601A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10875 | PS5-03-RDHR-W601B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10876 | PS5-03-RDHR-W601C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10877 | PS5-03-RDHR-W601D-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10878 | PS5-03-RDHR-W601E-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10879 | PS5-03-RDHR-W601F-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10880 | PS5-03-RDHR-W601G-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10881 | PS5-03-RDHR-W601H-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10882 | PS5-03-RDHR-W601I-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10883 | PS5-03-RDHR-W601J-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10884 | PS5-03-RDHR-W601K-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10885 | PS5-03-RDHR-W601L-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10886 | PS5-03-RDHR-W601M-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10887 | PS5-03-RDHR-W601N-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10888 | PS5-03-RDHR-W601O-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10889 | PS5-03-RDHR-W601P-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10890 | PS5-03-RDOS-B101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10891 | PS5-03-RDOS-B101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10892 | PS5-03-RDOS-B101C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10893 | PS5-03-RDOS-B101D-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10894 | PS5-03-RDOS-B201A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10895 | PS5-03-RDOS-B201B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10896 | PS5-03-RDOS-B201C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10897 | PS5-03-RDOS-B201D-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10898 | PS5-03-RDOS-B201E-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10899 | PS5-03-RDOS-B301A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10900 | PS5-03-RDOS-B301B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10901 | PS5-03-RDOS-B301C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10902 | PS5-03-RDOS-B301D-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10903 | PS5-03-RDOS-B401A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10904 | PS5-03-RDOS-B401B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10905 | PS5-03-RDOS-B401C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10906 | PS5-03-RDOS-B401D-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10907 | PS5-03-RDOS-B501A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10908 | PS5-03-RDOS-B601A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10909 | PS5-03-RDOS-B701A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10910 | PS5-03-RDOS-B701B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10911 | PS5-03-RDOS-B701C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10912 | PS5-03-RDOS-B701D-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10913 | PS5-03-RDOS-B701E-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10914 | PS5-03-RDOS-B701F-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10915 | PS5-03-RDOS-B701G-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10916 | PS5-03-RDOS-B701H-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10917 | PS5-03-RDOS-B701I-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10918 | PS5-03-RDOS-B801A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10919 | PS5-03-RDOS-B801B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10920 | PS5-03-RDOS-B901A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10921 | PS5-03-RDOS-B901B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10922 | PS5-03-RDOS-B901C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10923 | PS5-03-RDOS-B901D-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10924 | PS5-03-RDOS-B901E-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10925 | PS5-03-RDOS-W201A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10926 | PS5-03-RDOS-W201B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10927 | PS5-03-RDOS-W201C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10928 | PS5-03-RDOS-W201D-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10929 | PS5-03-RDOS-W301A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10930 | PS5-03-RDOS-W401A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10931 | PS5-03-RDOS-W501A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10932 | PS5-03-RDOS-W501B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10933 | PS5-03-RDOS-W501C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10934 | PS5-03-RDOS-W501D-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10935 | PS5-03-RDOS-W501E-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10936 | PS5-03-RDOS-W501F-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-10937 | PS5-03-RMAC-B401-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10938 | PS5-03-RMAC-B901-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00254-10939 | PS5-03-RMAC-W501-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed
T-00254-11586 | PS5-09-AH-8401-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11587 | PS5-09-AH-8401-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11588 | PS5-09-AH-8402-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11589 | PS5-09-AH-8402-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11590 | PS5-09-AH-8403-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11591 | PS5-09-AH-8403-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11592 | PS5-09-AS-8111A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11593 | PS5-09-AS-8111A-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11594 | PS5-09-AS-8111B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11595 | PS5-09-AS-8111B-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11596 | PS5-09-AS-8211A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11597 | PS5-09-AS-8211A-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11598 | PS5-09-AS-8211B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11599 | PS5-09-AS-8211B-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11600 | PS5-09-AS-8311A-A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11601 | PS5-09-AS-8311A-A-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11602 | PS5-09-AS-8311B-B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11603 | PS5-09-AS-8311B-B-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11604 | PS5-09-AS-8311C-A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11605 | PS5-09-AS-8311C-A-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11606 | PS5-09-AS-8311D-B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11607 | PS5-09-AS-8311D-B-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11608 | PS5-09-AS-8321A-A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11609 | PS5-09-AS-8321A-A-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11610 | PS5-09-AS-8321B-B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11611 | PS5-09-AS-8321B-B-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11612 | PS5-09-AS-8321C-A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11613 | PS5-09-AS-8321C-A-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11614 | PS5-09-AS-8321D-B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11615 | PS5-09-AS-8321D-B-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11616 | PS5-09-AS-8331A-A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11617 | PS5-09-AS-8331A-A-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11618 | PS5-09-AS-8331B-B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11619 | PS5-09-AS-8331B-B-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11620 | PS5-09-AS-8331C-A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11621 | PS5-09-AS-8331C-A-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11622 | PS5-09-AS-8331D-B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11623 | PS5-09-AS-8331D-B-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11624 | PS5-09-AS-8341A-A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11625 | PS5-09-AS-8341A-A-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11626 | PS5-09-AS-8341B-B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11627 | PS5-09-AS-8341B-B-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11628 | PS5-09-AS-8411A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11629 | PS5-09-AS-8411A-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11630 | PS5-09-AS-8411B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11631 | PS5-09-AS-8411B-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11632 | PS5-09-AS-8412A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11633 | PS5-09-AS-8412A-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11634 | PS5-09-AS-8412B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11635 | PS5-09-AS-8412B-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11636 | PS5-09-AS-8421A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11637 | PS5-09-AS-8421A-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11638 | PS5-09-AS-8421B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11639 | PS5-09-AS-8421B-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11640 | PS5-09-AS-8432A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11641 | PS5-09-AS-8432A-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11642 | PS5-09-AS-8432B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11643 | PS5-09-AS-8432B-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11644 | PS5-09-BI-8111A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11645 | PS5-09-BI-8111B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11646 | PS5-09-BI-8211A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11647 | PS5-09-BI-8211B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11648 | PS5-09-BI-8311A-A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11649 | PS5-09-BI-8311A-B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11650 | PS5-09-BI-8311B-A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11651 | PS5-09-BI-8311B-B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11652 | PS5-09-BI-8321A-A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11653 | PS5-09-BI-8321A-B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11654 | PS5-09-BI-8321B-A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11655 | PS5-09-BI-8321B-B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11656 | PS5-09-BI-8331A-A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11657 | PS5-09-BI-8331A-B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11658 | PS5-09-BI-8331B-A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11659 | PS5-09-BI-8331B-B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11660 | PS5-09-BI-8341A-A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11661 | PS5-09-BI-8341A-B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11662 | PS5-09-BI-8411A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11663 | PS5-09-BI-8411B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11664 | PS5-09-FCU-8442A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11665 | PS5-09-FCU-8442A-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11666 | PS5-09-FCU-8442B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11667 | PS5-09-FCU-8442B-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11668 | PS5-09-FCU-8442C-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11669 | PS5-09-FCU-8442C-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11670 | PS5-09-FCU-8442D-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11671 | PS5-09-FCU-8442D-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11672 | PS5-09-FCU-8442E-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11673 | PS5-09-FCU-8442E-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11674 | PS5-09-FCU-8442F-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11675 | PS5-09-FCU-8442F-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11676 | PS5-09-FCU-8442G-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11677 | PS5-09-FCU-8442G-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11678 | PS5-09-FCU-8442H-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11679 | PS5-09-FCU-8442H-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11680 | PS5-09-FD-0019-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11681 | PS5-09-FD-0019-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11682 | PS5-09-FD-0019-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11683 | PS5-09-FD-0021-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11684 | PS5-09-FD-0021-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11685 | PS5-09-FD-0021-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11686 | PS5-09-FD-0024-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11687 | PS5-09-FD-0024-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11688 | PS5-09-FD-0024-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11689 | PS5-09-FD-0025-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11690 | PS5-09-FD-0025-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11691 | PS5-09-FD-0025-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11692 | PS5-09-FD-0026-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11693 | PS5-09-FD-0026-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11694 | PS5-09-FD-0026-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11695 | PS5-09-FD-0027-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11696 | PS5-09-FD-0027-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11697 | PS5-09-FD-0027-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11698 | PS5-09-FD-0028-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11699 | PS5-09-FD-0028-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11700 | PS5-09-FD-0028-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11701 | PS5-09-FD-0029-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11702 | PS5-09-FD-0029-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11703 | PS5-09-FD-0029-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11704 | PS5-09-FD-0030-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11705 | PS5-09-FD-0030-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11706 | PS5-09-FD-0030-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11707 | PS5-09-FD-0031-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11708 | PS5-09-FD-0031-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11709 | PS5-09-FD-0031-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11710 | PS5-09-FD-0032-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11711 | PS5-09-FD-0032-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11712 | PS5-09-FD-0032-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11713 | PS5-09-FD-0033-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11714 | PS5-09-FD-0033-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11715 | PS5-09-FD-0033-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11716 | PS5-09-HE-8401A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11717 | PS5-09-HE-8401B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11718 | PS5-09-LB-8111A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11719 | PS5-09-LB-8111B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11720 | PS5-09-LB-8211A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11721 | PS5-09-LB-8211B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11722 | PS5-09-LB-8311A-A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11723 | PS5-09-LB-8311A-B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11724 | PS5-09-LB-8311B-A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11725 | PS5-09-LB-8311B-B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11726 | PS5-09-LB-8321A-A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11727 | PS5-09-LB-8321A-B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11728 | PS5-09-LB-8321B-A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11729 | PS5-09-LB-8321B-B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11730 | PS5-09-LB-8331A-A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11731 | PS5-09-LB-8331A-B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11732 | PS5-09-LB-8331B-A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11733 | PS5-09-LB-8331B-B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11734 | PS5-09-LB-8341A-A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11735 | PS5-09-LB-8341A-B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11736 | PS5-09-LB-8411A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11737 | PS5-09-LB-8411B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11738 | PS5-09-LB-8442A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11739 | PS5-09-LB-8442B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11740 | PS5-09-LB-8442C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11741 | PS5-09-LB-8442D-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11742 | PS5-09-LB-8442E-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11743 | PS5-09-LB-8442F-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11744 | PS5-09-LB-8442G-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11745 | PS5-09-LB-8442H-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11746 | PS5-09-LB-8451A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11747 | PS5-09-LB-8451A-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11748 | PS5-09-LB-8451B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11749 | PS5-09-LB-8451B-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11750 | PS5-09-PDIT-8207-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11751 | PS5-09-PDIT-8407-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11752 | PS5-09-PDIT-8408-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11753 | PS5-09-PDIT-8409-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11754 | PS5-09-PDIT-8411-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11755 | PS5-09-PIT-8401-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11756 | PS5-09-PIT-8402-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11757 | PS5-09-PIT-8403-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11758 | PS5-09-PIT-8404-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11759 | PS5-09-TCV-8401-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11760 | PS5-09-TCV-8401-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11761 | PS5-09-TCV-8402-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11762 | PS5-09-TCV-8402-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11763 | PS5-09-TIT-8101-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11764 | PS5-09-TIT-8201-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11765 | PS5-09-TIT-8301-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11766 | PS5-09-TIT-8302-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11767 | PS5-09-TIT-8303-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11768 | PS5-09-TIT-8304-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11769 | PS5-09-TIT-8401-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11770 | PS5-09-TIT-8402-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11771 | PS5-09-TIT-8403-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11772 | PS5-09-TIT-8404-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11773 | PS5-09-TIT-8405-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11774 | PS5-09-TIT-8406-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11775 | PS5-09-TIT-8407-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11776 | PS5-09-TIT-8408-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11777 | PS5-09-UZ-84600-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11778 | PS5-09-UZ-84600-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11779 | PS5-09-XV-8401-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11780 | PS5-09-XV-8401-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11781 | PS5-09-XV-8402-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11782 | PS5-09-XV-8402-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11783 | PS5-09-XV-8403-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11784 | PS5-09-XV-8403-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11785 | PS5-09-XV-8404-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11786 | PS5-09-XV-8404-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11787 | PS5-09-XV-8413-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11788 | PS5-09-XV-8413-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11789 | PS5-09-XV-8414-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11790 | PS5-09-XV-8414-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11791 | PS5-61-IH-0004A-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11792 | PS5-61-IH-0004A-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11793 | PS5-61-IH-0004A-CU03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11794 | PS5-61-IH-0004A-CU04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11795 | PS5-61-IH-0004B-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11796 | PS5-61-IH-0004B-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11797 | PS5-61-IH-0004B-CU03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11798 | PS5-61-IH-0004B-CU04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11799 | PS5-61-IH-0004C-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11800 | PS5-61-IH-0004C-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11801 | PS5-61-IH-0004C-CU03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11802 | PS5-61-IH-0004C-CU04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11803 | PS5-61-IH-0004-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11804 | PS5-61-IH-0004-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11805 | PS5-61-IH-0004-CU03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11806 | PS5-61-IH-0004-CU04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11807 | PS5-61-IH-0004-CU05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11808 | PS5-61-IH-0004-CU06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11809 | PS5-61-IH-0004-CU07 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11810 | PS5-61-IH-0004-CU08 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11811 | PS5-61-IH-0004-CU09 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11812 | PS5-61-IH-0004-CU10 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11813 | PS5-61-IH-0004-CU11 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11814 | PS5-61-IH-0004-CU12 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11815 | PS5-61-IH-0004-CU13 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11816 | PS5-61-IH-0004-CU14 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11817 | PS5-61-IH-0004-CU15 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11818 | PS5-61-IH-0004-CU16 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11819 | PS5-61-IH-0004-CU17 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11820 | PS5-61-IH-0004-CU18 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11821 | PS5-61-IH-0004-CU19 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11822 | PS5-61-IH-0004-CU20 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11823 | PS5-61-IH-0004-CU21 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11824 | PS5-61-IH-0004-CU22 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11825 | PS5-61-IH-0004-CU23 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11826 | PS5-61-IH-0004-CU24 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11827 | PS5-61-IH-0004-CU25 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11828 | PS5-61-IH-0004-CU26 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11829 | PS5-61-IH-0004-CU27 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11830 | PS5-61-IH-0004-CU28 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11831 | PS5-61-IH-0004-CU29 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11832 | PS5-61-IH-0004D-CU01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-11833 | PS5-61-IH-0004D-CU02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00254-12958 | PS5-03-RDH-1902-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | To be completed
T-00254-12959 | PS5-03-RDOS-1703-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3 | To be completed
T-00254-12960 | PS5-60-BI-0001A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00254-12961 | PS5-60-BI-0001B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00254-12962 | PS5-60-BI-0001C-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00254-12963 | PS5-60-BI-0001D-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00254-12964 | PS5-60-BI-0001E-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00254-12965 | PS5-60-BI-0001F-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00254-12966 | PS5-60-BI-0001G-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00254-12967 | PS5-60-BI-0003-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00254-12968 | PS5-60-IE-0002A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00254-12969 | PS5-60-IE-0002A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00254-12970 | PS5-60-IE-0002A-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00254-12971 | PS5-60-IE-0002B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00254-12972 | PS5-60-IE-0002B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00254-12973 | PS5-60-IE-0002B-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00254-12974 | PS5-60-IE-0002C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00254-12975 | PS5-60-IE-0002C-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00254-12976 | PS5-60-IE-0002C-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00254-12977 | PS5-60-IE-0002D-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00254-12978 | PS5-60-IE-0002D-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00254-12979 | PS5-60-IE-0002D-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00254-12980 | PS5-60-IE-0002E-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00254-12981 | PS5-60-IE-0002E-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00254-12982 | PS5-60-IE-0002E-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00254-12983 | PS5-60-IE-0002F-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00254-12984 | PS5-60-IE-0002F-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00254-12985 | PS5-60-IE-0002F-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00254-12986 | PS5-60-IE-0002G-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00254-12987 | PS5-60-IE-0002G-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00254-12988 | PS5-60-IE-0002G-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00254-12989 | PS5-60-IH-0001A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | To be completed
T-00254-12990 | PS5-60-IH-0001A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | To be completed
T-00254-12991 | PS5-60-IH-0001B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | To be completed
T-00254-12992 | PS5-60-IH-0001B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | To be completed
T-00254-12993 | PS5-60-IH-0001C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | To be completed
T-00254-12994 | PS5-60-IH-0001C-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | To be completed
T-00254-12995 | PS5-60-IH-0001D-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | To be completed
T-00254-12996 | PS5-60-IH-0001D-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | To be completed
T-00254-12997 | PS5-60-IH-0001E-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed
T-00254-12998 | PS5-60-IH-0001E-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed
T-00254-12999 | PS5-60-IH-0001F-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00254-13000 | PS5-60-IH-0001F-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00254-13001 | PS5-60-IH-0001G-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed
T-00254-13002 | PS5-60-IH-0001G-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed
T-00254-13003 | PS5-60-IH-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00254-13004 | PS5-60-IH-0002-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00254-13005 | PS5-60-LA-0003-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00254-13006 | PS5-60-LA-0003-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00254-13007 | PS5-60-PIT-8113A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed
T-00254-13008 | PS5-60-PIT-8113B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed
T-00254-13009 | PS5-60-PIT-8113C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00254-13010 | PS5-60-PIT-8113D-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00254-13011 | PS5-60-PIT-8113E-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00254-13012 | PS5-60-PIT-8113F-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00254-13013 | PS5-60-PIT-8113G-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00254-13014 | PS5-60-PIT-8114A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed
T-00254-13015 | PS5-60-PIT-8114B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | To be completed
T-00254-13016 | PS5-60-PIT-8114C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00254-13017 | PS5-60-PIT-8114D-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00254-13018 | PS5-60-PIT-8114E-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00254-13019 | PS5-60-PIT-8114F-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00254-13020 | PS5-60-PIT-8114G-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00254-13021 | PS5-71-IN-0004A-CC10 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00254-4222 | PS5-01-BI-0007-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4223 | PS5-01-BI-0008-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4224 | PS5-01-BI-0009-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4235 | PS5-01-FCV-0003A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00254-4236 | PS5-01-FCV-0003B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00254-4237 | PS5-01-FCV-0004A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00254-4238 | PS5-01-FCV-0004B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00254-4239 | PS5-01-FIT-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00254-4240 | PS5-01-FIT-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00254-4241 | PS5-01-FIT-0004A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00254-4242 | PS5-01-FIT-0004B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00254-4243 | PS5-01-FXS-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00254-4244 | PS5-01-FXS-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00254-4245 | PS5-01-FXS-0004A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00254-4246 | PS5-01-FXS-0004B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00254-4247 | PS5-01-FY-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00254-4248 | PS5-01-FY-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00254-4249 | PS5-01-FY-0004A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00254-4250 | PS5-01-FY-0004B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00254-4251 | PS5-01-HS-3108AB-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00254-4252 | PS5-01-HS-3108BB-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00254-4264 | PS5-01-LB-6101A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4265 | PS5-01-LB-6102A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4266 | PS5-01-LB-6103A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4267 | PS5-01-LB-6104A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4268 | PS5-01-LIT-4101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00254-4269 | PS5-01-LIT-4101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00254-4271 | PS5-01-NMR-61001-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4272 | PS5-01-NMR-61002-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4273 | PS5-01-NMR-61003-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4274 | PS5-01-NMR-61004-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4275 | PS5-01-NMRA-61001-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4276 | PS5-01-NMRA-61002-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4277 | PS5-01-NMRA-61003-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4278 | PS5-01-NMRA-61004-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4279 | PS5-01-PDIT-0011A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00254-4280 | PS5-01-PDIT-0011B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00254-4281 | PS5-01-PDIT-0012A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00254-4282 | PS5-01-PDIT-0012B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00254-4283 | PS5-01-PIT-0003AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00254-4284 | PS5-01-PIT-0003BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00254-4285 | PS5-01-PIT-0004AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00254-4286 | PS5-01-PIT-0004BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00254-4288 | PS5-01-PIT-0013-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-07 - Fire Water Ring Main & Distribution | To be completed
T-00254-4293 | PS5-01-PIT-8101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00254-4294 | PS5-01-PIT-8101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00254-4295 | PS5-01-PIT-8101C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00254-4296 | PS5-01-PIT-8101D-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00254-4297 | PS5-01-PIT-8101E-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00254-4298 | PS5-01-PIT-8101F-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00254-4299 | PS5-01-PIT-8101G-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00254-4300 | PS5-01-PIT-8101H-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00254-4301 | PS5-01-RAB-61001A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4302 | PS5-01-RAB-61001B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4303 | PS5-01-RAB-61002A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4304 | PS5-01-RAB-61002B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4305 | PS5-01-RAB-61003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4306 | PS5-01-RAB-61003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4307 | PS5-01-RAB-61004A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4308 | PS5-01-RAB-61004B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-11 - Inergen for Power Gen Building | To be completed
T-00254-4309 | PS5-01-SY-8101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00254-4310 | PS5-01-SY-8101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00254-4311 | PS5-01-SY-8101C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00254-4312 | PS5-01-SY-8101D-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00254-4313 | PS5-01-SY-8101E-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00254-4314 | PS5-01-SY-8101F-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00254-4315 | PS5-01-SY-8101G-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00254-4316 | PS5-01-SY-8101H-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-10 - Water Mist Package | To be completed
T-00254-4343 | PS5-03-GDIR-0901-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-4344 | PS5-03-GDIR-0902-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-4345 | PS5-03-GDIR-0903-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-4346 | PS5-03-GDIR-0904-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-4347 | PS5-03-GDIR-0906-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-4348 | PS5-03-GDIR-0907-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-4349 | PS5-03-GDIR-0908-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-4350 | PS5-03-GDIR-0909-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-4351 | PS5-03-GDIR-1001-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-4352 | PS5-03-GDIR-1002-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-4353 | PS5-03-GDIR-1003-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-4354 | PS5-03-GDIR-1004-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-4355 | PS5-03-GDIR-1006-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-4356 | PS5-03-GDIR-1007-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-4357 | PS5-03-GDIR-1008-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-4358 | PS5-03-GDIR-1009-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-4359 | PS5-03-GDIR-1101-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4360 | PS5-03-GDIR-1102-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4361 | PS5-03-GDIR-1103-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4362 | PS5-03-GDIR-1104-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4363 | PS5-03-GDIR-1106-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4364 | PS5-03-GDIR-1107-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4365 | PS5-03-GDIR-1108-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4366 | PS5-03-GDIR-1109-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4367 | PS5-03-GDIR-1201-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00254-4368 | PS5-03-GDIR-1202-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00254-4369 | PS5-03-GDIR-1203-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00254-4370 | PS5-03-GDIR-1204-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-4371 | PS5-03-GDLHP-0137-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0072
T-00254-4372 | PS5-03-GDLHP-0142-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0072
T-00254-4373 | PS5-03-GDLHP-0143-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0072
T-00254-4374 | PS5-03-GDLHP-0144-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0072
T-00254-4375 | PS5-03-GDLHP-0146-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0072
T-00254-4393 | PS5-03-RDH-0302-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-03 - FZ-03 - Buildings Area | To be completed
T-00254-4394 | PS5-03-RDH-0303-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-03 - FZ-03 - Buildings Area | To be completed
T-00254-4404 | PS5-03-RDH-0610-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00254-4405 | PS5-03-RDH-0611-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00254-4406 | PS5-03-RDH-0612-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed
T-00254-4410 | PS5-03-RDH-0617-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00254-4411 | PS5-03-RDH-0618-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00254-4412 | PS5-03-RDH-0620-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00254-4413 | PS5-03-RDH-0828-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00254-4414 | PS5-03-RDH-0829-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00254-4417 | PS5-03-RDH-0901-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00254-4418 | PS5-03-RDH-0902-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00254-4419 | PS5-03-RDH-0903-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00254-4420 | PS5-03-RDH-0904-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00254-4421 | PS5-03-RDH-0905-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00254-4422 | PS5-03-RDH-0906-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00254-4423 | PS5-03-RDH-0909-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00254-4424 | PS5-03-RDH-0910-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00254-4425 | PS5-03-RDH-0911-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00254-4426 | PS5-03-RDH-0912-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00254-4427 | PS5-03-RDH-1001-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00254-4428 | PS5-03-RDH-1002-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00254-4429 | PS5-03-RDH-1003-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00254-4430 | PS5-03-RDH-1004-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00254-4431 | PS5-03-RDH-1005-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00254-4432 | PS5-03-RDH-1006-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00254-4433 | PS5-03-RDH-1009-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00254-4434 | PS5-03-RDH-1010-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00254-4435 | PS5-03-RDH-1011-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00254-4436 | PS5-03-RDH-1012-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00254-4437 | PS5-03-RDH-1101-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4438 | PS5-03-RDH-1102-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4439 | PS5-03-RDH-1103-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4440 | PS5-03-RDH-1104-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4441 | PS5-03-RDH-1105-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4442 | PS5-03-RDH-1106-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4443 | PS5-03-RDH-1109-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4444 | PS5-03-RDH-1110-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4445 | PS5-03-RDH-1111-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4446 | PS5-03-RDH-1112-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4447 | PS5-03-RDH-1201-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00254-4448 | PS5-03-RDH-1202-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00254-4449 | PS5-03-RDH-1203-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00254-4450 | PS5-03-RDH-1204-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00254-4451 | PS5-03-RDH-1205-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00254-4452 | PS5-03-RDH-1302-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | To be completed
T-00254-4453 | PS5-03-RDH-1303-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | To be completed
T-00254-4454 | PS5-03-RDH-1304-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | To be completed
T-00254-4455 | PS5-03-RDH-1901-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | To be completed
T-00254-4456 | PS5-03-RDH-1903-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | To be completed
T-00254-4460 | PS5-03-RDIR-0107-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00254-4475 | PS5-03-RDIR-0124-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00254-4479 | PS5-03-RDIR-0128-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00254-4480 | PS5-03-RDIR-0129-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00254-4481 | PS5-03-RDIR-0130-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00254-4482 | PS5-03-RDIR-0131-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00254-4483 | PS5-03-RDIR-0132-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00254-4484 | PS5-03-RDIR-0133-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | To be completed
T-00254-4492 | PS5-03-RDIR-0406-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed
T-00254-4498 | PS5-03-RDIR-0833-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00254-4499 | PS5-03-RDOS-1401-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00254-4500 | PS5-03-RDOS-1402-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00254-4501 | PS5-03-RDOS-1403-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00254-4502 | PS5-03-RDOS-1404-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00254-4503 | PS5-03-RDOS-1405-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00254-4504 | PS5-03-RDOS-1406-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00254-4505 | PS5-03-RDOS-1407-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00254-4506 | PS5-03-RDOS-1408-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00254-4507 | PS5-03-RDOS-1501-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1 | To be completed
T-00254-4508 | PS5-03-RDOS-1502-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1 | To be completed
T-00254-4509 | PS5-03-RDOS-1503-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1 | To be completed
T-00254-4510 | PS5-03-RDOS-1601-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2 | To be completed
T-00254-4511 | PS5-03-RDOS-1602-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2 | To be completed
T-00254-4512 | PS5-03-RDOS-1603-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2 | To be completed
T-00254-4513 | PS5-03-RDOS-1701-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3 | To be completed
T-00254-4514 | PS5-03-RDOS-1702-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3 | To be completed
T-00254-4515 | PS5-03-RDOS-1801-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4 | To be completed
T-00254-4516 | PS5-03-RDOS-1802-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4 | To be completed
T-00254-4517 | PS5-03-RDOS-1803-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4 | To be completed
T-00254-4518 | PS5-03-RDOS-2101-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit | To be completed
T-00254-4519 | PS5-03-RDOS-2102-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit | To be completed
T-00254-4520 | PS5-03-RDOS-2103-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit | To be completed
T-00254-4521 | PS5-03-RDOS-G101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-22 - FZ-G1 - Guard House | To be completed
T-00254-4522 | PS5-03-RDOS-G101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-22 - FZ-G1 - Guard House | To be completed
T-00254-4523 | PS5-03-RDUIR-0701-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00254-4524 | PS5-03-RDUIR-0702-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00254-4525 | PS5-03-RDUIR-0703-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00254-4526 | PS5-03-RDUIR-0704-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00254-4527 | PS5-03-RDUIR-0705-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00254-4528 | PS5-03-RDUIR-0907-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00254-4529 | PS5-03-RDUIR-0908-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed
T-00254-4530 | PS5-03-RDUIR-1007-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00254-4531 | PS5-03-RDUIR-1008-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed
T-00254-4532 | PS5-03-RDUIR-1107-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4533 | PS5-03-RDUIR-1108-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed
T-00254-4534 | PS5-03-RDUIR-1207-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00254-4535 | PS5-03-RDUIR-1208-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed
T-00254-4540 | PS5-03-RMAC-0301-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-03 - FZ-03 - Buildings Area | To be completed
T-00254-4541 | PS5-03-RMAC-0304-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-03 - FZ-03 - Buildings Area | To be completed
T-00254-4545 | PS5-03-RMAC-0706-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00254-4546 | PS5-03-RMAC-0707-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed
T-00254-4548 | PS5-03-RMAC-0825-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00254-4549 | PS5-03-RMAC-0827-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00254-4550 | PS5-03-RMAC-0834-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed
T-00254-4551 | PS5-03-RMAC-1301-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | To be completed
T-00254-4552 | PS5-03-RMAC-1410-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00254-4553 | PS5-03-RMAC-1411-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00254-4554 | PS5-03-SEA-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-04-0049 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00254-4563 | PS5-05-BI-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00254-4564 | PS5-05-BI-0002-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00254-4566 | PS5-05-BI-0002-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0043 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4567 | PS5-05-BI-0002-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0050 |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00254-4568 | PS5-05-BI-0002-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0050 |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00254-4571 | PS5-05-BI-0002-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00254-4572 | PS5-05-BI-0002-CJ02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00254-4573 | PS5-05-BI-0002-CJ03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00254-4574 | PS5-05-GC-8100-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0043 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4577 | PS5-05-IE-8101-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00254-4578 | PS5-05-IG-0009-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0043 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4579 | PS5-05-IG-0009-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0043 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4580 | PS5-05-IG-0009-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00254-4581 | PS5-05-LIT-4101-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00254-4582 | PS5-05-UH-8100-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0043 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4583 | PS5-05-UH-8100-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-04-0049 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00254-4623 | PS5-25-BI-1802A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00254-4625 | PS5-25-BI-1802B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00254-4627 | PS5-25-BI-1802C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00254-4655 | PS5-25-ESDV-0021-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00254-4656 | PS5-25-ESDV-0021-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00254-4658 | PS5-25-ESDV-0023-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00254-4659 | PS5-25-ESDV-0023-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00254-4663 | PS5-25-FCV-0003A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00254-4664 | PS5-25-FCV-0003B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00254-4665 | PS5-25-FCV-0003C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4666 | PS5-25-FCV-0004-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00254-4670 | PS5-25-FIT-0003C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4672 | PS5-25-FXS-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00254-4673 | PS5-25-FXS-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00254-4674 | PS5-25-FXS-0003C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4675 | PS5-25-FXS-0004-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00254-4678 | PS5-25-FY-0003C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4686 | PS5-25-MOV-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00254-4689 | PS5-25-MOV-0008-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00254-4692 | PS5-25-MOV-0025-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00254-4697 | PS5-25-MOV-0028-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00254-4698 | PS5-25-MXS-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00254-4699 | PS5-25-MXS-0008-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00254-4700 | PS5-25-MXS-0025-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00254-4701 | PS5-25-MXS-0028-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00254-4708 | PS5-25-PDIT-0034A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00254-4710 | PS5-25-PDIT-0034C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4711 | PS5-25-PDIT-0050-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00254-4717 | PS5-25-PIT-0003CA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4718 | PS5-25-PIT-0004AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00254-4719 | PS5-25-PIT-0004A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00254-4720 | PS5-25-PIT-0004B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00254-4721 | PS5-25-PIT-0004C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4724 | PS5-25-PIT-0005C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4727 | PS5-25-PIT-0007C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4729 | PS5-25-PIT-0008B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0072
T-00254-4730 | PS5-25-PIT-0008C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0072
T-00254-4734 | PS5-25-PIT-0035A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00254-4735 | PS5-25-PIT-0035B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00254-4736 | PS5-25-PIT-0035C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4737 | PS5-25-PIT-0036A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00254-4738 | PS5-25-PIT-0036B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00254-4739 | PS5-25-PIT-0036C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4740 | PS5-25-PIT-0046-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed
T-00254-4743 | PS5-25-PIT-0054A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00254-4744 | PS5-25-PIT-0054B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00254-4745 | PS5-25-PIT-0054C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4753 | PS5-25-SDV-0022-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00254-4756 | PS5-25-SDV-0035C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4758 | PS5-25-SDV-0036B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00254-4759 | PS5-25-SDV-0036C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4765 | PS5-25-SDV-0054C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4767 | PS5-25-SXS-0022-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00254-4776 | PS5-25-SXS-0054A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00254-4777 | PS5-25-SXS-0054B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00254-4778 | PS5-25-SXS-0054C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4781 | PS5-25-SY-0035AB-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00254-4783 | PS5-25-SY-0035BB-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00254-4784 | PS5-25-SY-0035CA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4785 | PS5-25-SY-0035CB-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4787 | PS5-25-SY-0036AB-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00254-4788 | PS5-25-SY-0036BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00254-4789 | PS5-25-SY-0036BB-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00254-4790 | PS5-25-SY-0036CA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4791 | PS5-25-SY-0036CB-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4795 | PS5-25-SY-0052B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00254-4798 | PS5-25-SY-0054BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00254-4799 | PS5-25-SY-0054BB-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00254-4800 | PS5-25-SY-0054CA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4801 | PS5-25-SY-0054CB-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4803 | PS5-25-TIT-0002A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00254-4804 | PS5-25-TIT-0002B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00254-4805 | PS5-25-TIT-0002C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0072
T-00254-4808 | PS5-25-TIT-0003C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00254-4812 | PS5-25-XV-0053-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed
T-00254-4813 | PS5-25-XV-0053-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed
T-00254-4814 | PS5-25-XV-0070-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed
T-00254-4815 | PS5-25-XXS-0053-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed
T-00254-4816 | PS5-25-XXS-0070-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed
T-00254-4819 | PS5-25-ZIT-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00254-4820 | PS5-25-ZIT-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00254-4821 | PS5-25-ZS-1101-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00254-4822 | PS5-25-ZS-1201-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed
T-00254-4830 | PS5-28-HXA-1402-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00254-4842 | PS5-28-LIT-1201-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-06 - Relief Drum and Pump | To be completed
T-00254-4846 | PS5-28-LIT-1301C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00254-4850 | PS5-28-PIT-0033-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-06 - Relief Drum and Pump | To be completed
T-00254-4853 | PS5-28-PIT-0053A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00254-4854 | PS5-28-PIT-0053B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00254-4855 | PS5-28-PIT-0053C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00254-4858 | PS5-28-SDV-0045-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | To be completed
T-00254-4859 | PS5-28-SDV-0045-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | To be completed
T-00254-4861 | PS5-28-SDV-0053A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00254-4862 | PS5-28-SDV-0053B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00254-4863 | PS5-28-SDV-0053B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed
T-00254-4864 | PS5-28-SDV-0053C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00254-4865 | PS5-28-SDV-0053C-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00254-4866 | PS5-28-SXS-0045-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | To be completed
T-00254-4867 | PS5-28-SXS-0053A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed | CPP-RFI-68-64-04-0072
T-00254-4868 | PS5-28-SXS-0053B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed | CPP-RFI-68-64-04-0072
T-00254-4869 | PS5-28-SXS-0053C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00254-4873 | PS5-28-SY-0053AB-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed
T-00254-4876 | PS5-28-SY-0053CA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00254-4877 | PS5-28-SY-0053CB-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed
T-00254-4880 | PS5-28-TIT-1201-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-06 - Relief Drum and Pump | To be completed
T-00254-4897 | PS5-53-LIT-4101-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-53-01 - Utility Water / Storage Tank | To be completed
T-00254-4898 | PS5-53-LIT-4102-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-53-01 - Utility Water / Storage Tank | To be completed
T-00254-4899 | PS5-53-PIT-0005-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-53-02 - Water Distribution Pump A/B | To be completed
T-00254-4923 | PS5-60-BI-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00254-4925 | PS5-60-BI-0002-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00254-4926 | PS5-60-BI-0002-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00254-4929 | PS5-60-BI-0004A-CCO1 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00254-4930 | PS5-60-BI-0004B-CCO1 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00254-4931 | PS5-60-BI-0004C-CCO1 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00254-4932 | PS5-60-BI-0004D-CCO1 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00254-4933 | PS5-60-BI-0004E-CCO1 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00254-4934 | PS5-60-BI-0004F-CCO1 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00254-4935 | PS5-60-BI-0004G-CCO1 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00254-4936 | PS5-60-BI-0005A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00254-4937 | PS5-60-BI-0005A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00254-4938 | PS5-60-BI-0005B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00254-4939 | PS5-60-BI-0005B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00254-4940 | PS5-60-BI-0005C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00254-4941 | PS5-60-BI-0005C-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00254-4942 | PS5-60-BI-0005D-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00254-4943 | PS5-60-BI-0005D-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00254-4944 | PS5-60-BI-0005E-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00254-4945 | PS5-60-BI-0005E-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00254-4946 | PS5-60-BI-0005F-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00254-4947 | PS5-60-BI-0005F-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00254-4948 | PS5-60-BI-0005G-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00254-4949 | PS5-60-BI-0005G-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00254-4951 | PS5-60-BI-0006A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed
T-00254-4952 | PS5-60-BI-0006A-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed
T-00254-4953 | PS5-60-BI-0006A-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed
T-00254-4955 | PS5-60-BI-0006A-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed
T-00254-4957 | PS5-60-BI-0006B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00254-4958 | PS5-60-BI-0006B-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00254-4959 | PS5-60-BI-0006B-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00254-4961 | PS5-60-BI-0006B-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00254-4963 | PS5-60-BI-0006C-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00254-4964 | PS5-60-BI-0006C-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00254-4965 | PS5-60-BI-0006C-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00254-4967 | PS5-60-BI-0006C-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00254-4969 | PS5-60-BI-0006D-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00254-4970 | PS5-60-BI-0006D-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00254-4971 | PS5-60-BI-0006D-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00254-4973 | PS5-60-BI-0006D-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00254-4975 | PS5-60-BI-0006E-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00254-4976 | PS5-60-BI-0006E-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00254-4977 | PS5-60-BI-0006E-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00254-4979 | PS5-60-BI-0006E-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00254-4981 | PS5-60-BI-0006F-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00254-4982 | PS5-60-BI-0006F-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00254-4983 | PS5-60-BI-0006F-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00254-4985 | PS5-60-BI-0006F-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00254-4987 | PS5-60-BI-0006G-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00254-4988 | PS5-60-BI-0006G-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00254-4989 | PS5-60-BI-0006G-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00254-4991 | PS5-60-BI-0006G-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00254-4992 | PS5-60-BI-0008A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00254-4993 | PS5-60-BI-0008A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00254-4994 | PS5-60-BI-0008B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00254-4995 | PS5-60-BI-0008B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00254-4996 | PS5-60-BI-0009A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00254-4997 | PS5-60-BI-0009A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00254-4998 | PS5-60-BI-0009B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00254-4999 | PS5-60-BI-0009B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-5000 | PS5-60-BI-0010A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00254-5001 | PS5-60-BI-0010A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00254-5002 | PS5-60-BI-0010B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00254-5003 | PS5-60-BI-0010B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-5004 | PS5-60-BI-0011A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00254-5005 | PS5-60-BI-0011A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00254-5006 | PS5-60-BI-0011B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00254-5007 | PS5-60-BI-0011B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-5008 | PS5-60-BI-0012A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00254-5009 | PS5-60-BI-0012A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-5010 | PS5-60-BI-0012B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00254-5011 | PS5-60-BI-0012B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-5012 | PS5-60-BI-0013A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00254-5013 | PS5-60-BI-0013A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-5014 | PS5-60-BI-0013B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00254-5015 | PS5-60-BI-0013B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-5016 | PS5-60-BI-0014A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00254-5017 | PS5-60-BI-0014A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed | CPP-68-64-04-0079 | CPP-68-64-12-0085
T-00254-5018 | PS5-60-BI-0014B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00254-5019 | PS5-60-BI-0014B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00254-5021 | PS5-60-BI-0016A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed |  | CPP-RFI-68-64-12-0102
T-00254-5023 | PS5-60-BI-0016A-CCO4 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed
T-00254-5027 | PS5-60-BI-0016B-CCO4 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00254-5029 | PS5-60-BI-0016C-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00254-5031 | PS5-60-BI-0016C-CCO4 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed
T-00254-5033 | PS5-60-BI-0016D-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00254-5035 | PS5-60-BI-0016D-CCO4 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00254-5037 | PS5-60-BI-0016E-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00254-5039 | PS5-60-BI-0016E-CCO4 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed
T-00254-5041 | PS5-60-BI-0016F-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00254-5043 | PS5-60-BI-0016F-CCO4 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00254-5045 | PS5-60-BI-0016G-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00254-5047 | PS5-60-BI-0016G-CCO4 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00254-5048 | PS5-60-BI-0017A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | To be completed
T-00254-5050 | PS5-60-BI-0017C-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | To be completed
T-00254-5051 | PS5-60-BI-0017D-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | To be completed
T-00254-5052 | PS5-60-BI-0017E-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | To be completed
T-00254-5053 | PS5-60-BI-0017F-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | To be completed
T-00254-5054 | PS5-60-BI-0017G-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | To be completed
T-00254-5055 | PS5-60-BI-0019A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5056 | PS5-60-BI-0019A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5057 | PS5-60-BI-0019B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5058 | PS5-60-BI-0019B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5059 | PS5-60-BI-0019C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5060 | PS5-60-BI-0019C-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5061 | PS5-60-BI-0019D-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5062 | PS5-60-BI-0019D-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5063 | PS5-60-BI-0019E-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5064 | PS5-60-BI-0019E-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5065 | PS5-60-BI-0019F-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed
T-00254-5066 | PS5-60-BI-0019F-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5067 | PS5-60-BI-0019G-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed
T-00254-5068 | PS5-60-BI-0019G-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5069 | PS5-60-IE-0002B-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed
T-00254-5077 | PS5-60-IE-0003A-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed
T-00254-5078 | PS5-60-IE-0003A-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed
T-00254-5080 | PS5-60-IE-0003A-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5081 | PS5-60-IE-0003A-CC07 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00254-5082 | PS5-60-IE-0003A-CC08 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5083 | PS5-60-IE-0003A-CC09 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5087 | PS5-60-IE-0003A-CC16 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5088 | PS5-60-IE-0003A-CC17 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5098 | PS5-60-IE-0003B-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00254-5099 | PS5-60-IE-0003B-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00254-5100 | PS5-60-IE-0003B-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00254-5101 | PS5-60-IE-0003B-CC07 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00254-5102 | PS5-60-IE-0003B-CC08 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5103 | PS5-60-IE-0003B-CC09 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5107 | PS5-60-IE-0003B-CC16 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5108 | PS5-60-IE-0003B-CC17 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5115 | PS5-60-IE-0003C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00254-5116 | PS5-60-IE-0003C-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00254-5117 | PS5-60-IE-0003C-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00254-5118 | PS5-60-IE-0003C-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00254-5119 | PS5-60-IE-0003C-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00254-5120 | PS5-60-IE-0003C-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00254-5121 | PS5-60-IE-0003C-CC07 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00254-5122 | PS5-60-IE-0003C-CC08 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5123 | PS5-60-IE-0003C-CC09 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5124 | PS5-60-IE-0003C-CC10 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00254-5125 | PS5-60-IE-0003C-CC11 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00254-5126 | PS5-60-IE-0003C-CC15 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00254-5127 | PS5-60-IE-0003C-CC16 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5128 | PS5-60-IE-0003C-CC17 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5135 | PS5-60-IE-0003D-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00254-5136 | PS5-60-IE-0003D-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00254-5137 | PS5-60-IE-0003D-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00254-5138 | PS5-60-IE-0003D-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00254-5139 | PS5-60-IE-0003D-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00254-5140 | PS5-60-IE-0003D-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00254-5141 | PS5-60-IE-0003D-CC07 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00254-5142 | PS5-60-IE-0003D-CC08 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5143 | PS5-60-IE-0003D-CC09 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5144 | PS5-60-IE-0003D-CC10 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00254-5145 | PS5-60-IE-0003D-CC11 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00254-5146 | PS5-60-IE-0003D-CC15 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00254-5147 | PS5-60-IE-0003D-CC16 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5148 | PS5-60-IE-0003D-CC17 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5155 | PS5-60-IE-0003E-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00254-5156 | PS5-60-IE-0003E-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00254-5157 | PS5-60-IE-0003E-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00254-5158 | PS5-60-IE-0003E-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00254-5159 | PS5-60-IE-0003E-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00254-5161 | PS5-60-IE-0003E-CC07 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00254-5162 | PS5-60-IE-0003E-CC08 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5163 | PS5-60-IE-0003E-CC09 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5164 | PS5-60-IE-0003E-CC10 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00254-5165 | PS5-60-IE-0003E-CC11 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00254-5166 | PS5-60-IE-0003E-CC15 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00254-5167 | PS5-60-IE-0003E-CC16 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5168 | PS5-60-IE-0003E-CC17 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5175 | PS5-60-IE-0003F-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00254-5176 | PS5-60-IE-0003F-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00254-5177 | PS5-60-IE-0003F-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00254-5178 | PS5-60-IE-0003F-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00254-5179 | PS5-60-IE-0003F-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00254-5180 | PS5-60-IE-0003F-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00254-5181 | PS5-60-IE-0003F-CC07 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00254-5182 | PS5-60-IE-0003F-CC08 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00254-5183 | PS5-60-IE-0003F-CC09 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00254-5184 | PS5-60-IE-0003F-CC10 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00254-5185 | PS5-60-IE-0003F-CC11 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00254-5186 | PS5-60-IE-0003F-CC15 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00254-5187 | PS5-60-IE-0003F-CC16 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5188 | PS5-60-IE-0003F-CC17 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5195 | PS5-60-IE-0003G-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00254-5196 | PS5-60-IE-0003G-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00254-5197 | PS5-60-IE-0003G-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5198 | PS5-60-IE-0003G-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00254-5199 | PS5-60-IE-0003G-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00254-5200 | PS5-60-IE-0003G-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00254-5201 | PS5-60-IE-0003G-CC07 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00254-5202 | PS5-60-IE-0003G-CC08 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00254-5203 | PS5-60-IE-0003G-CC09 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00254-5204 | PS5-60-IE-0003G-CC10 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00254-5205 | PS5-60-IE-0003G-CC11 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00254-5206 | PS5-60-IE-0003G-CC15 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00254-5207 | PS5-60-IE-0003G-CC16 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5208 | PS5-60-IE-0003G-CC17 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5215 | PS5-60-IE-0004-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00254-5216 | PS5-60-IE-0004-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00254-5217 | PS5-60-IE-0004-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00254-5218 | PS5-60-IE-0004-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00254-5219 | PS5-60-IE-0004-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00254-5220 | PS5-60-IE-0004-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00254-5221 | PS5-60-IE-0004-CC07 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00254-5226 | PS5-60-IN-0001A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | To be completed
T-00254-5230 | PS5-60-IN-0001B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | To be completed
T-00254-5255 | PS5-60-IN-0002A-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed
T-00254-5261 | PS5-60-IN-0002B-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00254-5263 | PS5-60-IN-0002B-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed |  | CPP-RFI-68-64-12-0102
T-00254-5266 | PS5-60-IN-0002C-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00254-5267 | PS5-60-IN-0002C-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00254-5269 | PS5-60-IN-0002C-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00254-5272 | PS5-60-IN-0002D-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00254-5273 | PS5-60-IN-0002D-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00254-5275 | PS5-60-IN-0002D-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00254-5278 | PS5-60-IN-0002E-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00254-5279 | PS5-60-IN-0002E-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00254-5281 | PS5-60-IN-0002E-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00254-5284 | PS5-60-IN-0002F-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00254-5285 | PS5-60-IN-0002F-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00254-5287 | PS5-60-IN-0002F-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00254-5290 | PS5-60-IN-0002G-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00254-5291 | PS5-60-IN-0002G-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00254-5293 | PS5-60-IN-0002G-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00254-5295 | PS5-60-IN-0004A-CC11 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00254-5308 | PS5-60-LA-0002B-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00254-5309 | PS5-60-LA-0002B-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00254-5310 | PS5-60-LA-0002B-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed
T-00254-5314 | PS5-60-LA-0002C-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-68-64-04-0080
T-00254-5317 | PS5-60-LA-0003-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | To be completed
T-00254-5320 | PS5-60-MOV-0005-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5321 | PS5-60-MOV-0005-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5322 | PS5-60-MOV-0006-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5323 | PS5-60-MOV-0006-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5324 | PS5-60-MOV-0011-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5325 | PS5-60-MOV-0011-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5326 | PS5-60-MOV-0012-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5327 | PS5-60-MOV-0012-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5329 | PS5-60-SEA-0001-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00254-5338 | PS5-60-SEA-0001-CC13 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00254-5344 | PS5-60-SY-0007-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-28 - Air Receiver A & Air Regulator A | To be completed
T-00254-5345 | PS5-60-SY-0008-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-29 - Air Receiver B & Air Regulator B | To be completed
T-00254-5346 | PS5-60-SY-0009-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-30 - Air Receiver C & Air Regulator C | To be completed
T-00254-5347 | PS5-60-SY-0010-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-31 - Air Receiver D & Air Regulator D | To be completed
T-00254-5348 | PS5-60-SY-0011-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-32 - Air Receiver E & Air Regulator E | To be completed
T-00254-5360 | PS5-61-BI-0001-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-64-04-0071 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5363 | PS5-61-BI-0002-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-64-04-0071 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5366 | PS5-61-BI-0003-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | To be completed | CPP-RFI-68-64-04-0071 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5369 | PS5-61-BI-0004-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | To be completed | CPP-RFI-68-64-04-0071 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5372 | PS5-61-BI-0005-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | To be completed | CPP-RFI-68-64-04-0071 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5375 | PS5-61-BI-0006-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | To be completed | CPP-RFI-68-64-04-0071 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5378 | PS5-61-BI-0007-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | To be completed | CPP-RFI-68-64-04-0071 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5390 | PS5-71-BI-0001A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00254-5391 | PS5-71-BI-0001B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00254-5393 | PS5-71-BI-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00254-5395 | PS5-71-BI-0003-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed
T-00254-5396 | PS5-71-BI-0003-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed
T-00254-5397 | PS5-71-BI-0003-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed
T-00254-5398 | PS5-71-BI-0004-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | To be completed
T-00254-5399 | PS5-71-BI-0005-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed
T-00254-5401 | PS5-71-BI-0006-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | To be completed
T-00254-5402 | PS5-71-BI-0008A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00254-5403 | PS5-71-BI-0008A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00254-5404 | PS5-71-BI-0008B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00254-5405 | PS5-71-BI-0008B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00254-5406 | PS5-71-BI-0009-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00254-5407 | PS5-71-BI-0009-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00254-5408 | PS5-71-BI-0009-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00254-5409 | PS5-71-BI-0009-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00254-5410 | PS5-71-BI-0010-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00254-5411 | PS5-71-BI-0011A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00254-5412 | PS5-71-BI-0011A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00254-5413 | PS5-71-BI-0011A-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00254-5414 | PS5-71-BI-0011A-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00254-5415 | PS5-71-BI-0011A-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00254-5416 | PS5-71-BI-0011B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00254-5417 | PS5-71-BI-0011B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00254-5418 | PS5-71-BI-0011B-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00254-5419 | PS5-71-BI-0011B-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00254-5420 | PS5-71-BI-0011B-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-06 - Crude Fuel Separation Module | To be completed
T-00254-5453 | PS5-71-FCV-0018-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00254-5454 | PS5-71-FCV-0019-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00254-5455 | PS5-71-FCV-0020-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00254-5457 | PS5-71-FIT-0011A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00254-5458 | PS5-71-FIT-0011B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00254-5459 | PS5-71-FIT-0012-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-17 - Diesel Fuel Distribution Header | To be completed
T-00254-5460 | PS5-71-FIT-0018-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00254-5462 | PS5-71-FIT-0020-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00254-5466 | PS5-71-FY-0018-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00254-5480 | PS5-71-IN-0002-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | To be completed
T-00254-5482 | PS5-71-IN-0002-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5488 | PS5-71-IN-0003-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5489 | PS5-71-IN-0003-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5493 | PS5-71-IN-0004A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00254-5494 | PS5-71-IN-0004A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00254-5498 | PS5-71-IN-0004A-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5499 | PS5-71-IN-0004A-CC07 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5502 | PS5-71-IN-0004A-CC11 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00254-5504 | PS5-71-IN-0004A-CC13 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00254-5505 | PS5-71-IN-0004B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00254-5506 | PS5-71-IN-0004B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00254-5507 | PS5-71-IN-0004B-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00254-5510 | PS5-71-IN-0004B-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5511 | PS5-71-IN-0004B-CC07 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-68-64-04-0081 | CPP-68-64-12-0085
T-00254-5514 | PS5-71-IN-0004B-CC11 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00254-5516 | PS5-71-LCV-4101-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00254-5517 | PS5-71-LI-4201B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5520 | PS5-71-LIT-4101-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00254-5521 | PS5-71-LIT-4102-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00254-5522 | PS5-71-LIT-4201-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5523 | PS5-71-LIT-4202-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5527 | PS5-71-LY-4101-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00254-5544 | PS5-71-PDIT-0030-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00254-5545 | PS5-71-PDIT-0056A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00254-5546 | PS5-71-PDIT-0056B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00254-5549 | PS5-71-PIT-0018A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00254-5551 | PS5-71-PIT-0020A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00254-5555 | PS5-71-PIT-0089-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00254-5556 | PS5-71-PIT-0090-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5559 | PS5-71-PIT-2402A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00254-5560 | PS5-71-PIT-2402B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00254-5569 | PS5-71-PIT-4101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00254-5571 | PS5-71-SDV-0001-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed
T-00254-5572 | PS5-71-SDV-0022-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00254-5573 | PS5-71-SDV-0022-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00254-5575 | PS5-71-SDV-0029-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-15 - Diesel Fuel Storage Tank | To be completed
T-00254-5576 | PS5-71-SDV-0039-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5577 | PS5-71-SDV-0039-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5586 | PS5-71-TIT-0003-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00254-5587 | PS5-71-TIT-0004-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00254-5590 | PS5-71-TIT-2204-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5591 | PS5-71-TIT-2301-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00254-5596 | PS5-71-TIT-4102-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00254-5597 | PS5-71-TIT-4103-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00254-5598 | PS5-71-TIT-4202-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5599 | PS5-71-TIT-4203-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5600 | PS5-71-XV-0089-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00254-5601 | PS5-71-XV-0089-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00254-5602 | PS5-71-XV-0090-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5603 | PS5-71-XV-0090-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | To be completed
T-00254-5605 | PS5-71-XV-0091-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | To be completed
T-00254-5607 | PS5-71-XV-0092-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed
T-00254-9420 | PS5-03-RMAC-1409-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00255-0051 | PS5-71-FO-0013B | TJX11 - Orifice plate | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | To be completed
T-00255-0052 | PS5-28-FO-0009A | TJX11 - Orifice plate | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00255-0053 | PS5-28-FO-0009B | TJX11 - Orifice plate | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00255-0054 | PS5-28-FO-0003 | TJX11 - Orifice plate | I | PS5-28-05 - HP Relief Header | To be completed
T-00255-0055 | PS5-50-FE-0001 | TJX11 - Orifice plate | I | PS5-50-03 - Water Pre-Treatment Package | To be completed
T-00255-0056 | PS5-60-FO-0002 | TJX11 - Orifice plate | I | PS5-60-24 - Cooling Water Tank & Pump | To be completed
T-00255-0057 | PS5-28-FO-0005 | TJX11 - Orifice plate | I | PS5-28-06 - Relief Drum and Pump | To be completed
T-00255-0058 | PS5-60-FO-0001 | TJX11 - Orifice plate | I | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | To be completed
T-00255-0059 | PS5-25-FO-0008 | TJX11 - Orifice plate | I | PS5-25-05 - Crude Oil Export Pumps Bypass | To be completed
T-00255-0060 | PS5-71-FO-0013A | TJX11 - Orifice plate | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | To be completed
T-00255-0061 | PS5-74-FO-0001 | TJX11 - Orifice plate | I | PS5-74-04 - Nitrogen Distribution Header | To be completed
T-00255-0062 | PS5-28-FO-0002A | TJX11 - Orifice plate | I | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00255-0063 | PS5-28-FO-0002B | TJX11 - Orifice plate | I | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00255-0064 | PS5-28-FO-0004 | TJX11 - Orifice plate | I | PS5-28-16 - LP Relief Header | To be completed
T-00255-0065 | PS5-28-FO-0006 | TJX11 - Orifice plate | I | PS5-28-08 - Open Drain Sump and Pumps | To be completed
T-00255-0066 | PS5-28-FO-0007 | TJX11 - Orifice plate | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00256-0023 | PS5-09-LB-0006-CX01 | TJX12 - Optical fiber cable | I | PS5-09-01 - HVAC for Office and Facilities building | To be completed
T-00256-0024 | PS5-09-LB-0007-CX01 | TJX12 - Optical fiber cable | I | PS5-09-04 - HVAC for Workshop & Warehouse | To be completed | CPP-RFI-68-64-04-0043 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable coiled 155mtr,Cable to be laid in trench [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00256-0025 | PS5-09-LB-0008-CX01 | TJX12 - Optical fiber cable | I | PS5-09-03 - HVAC for Generator Building | To be completed | CPP-RFI-68-64-04-0054 |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00256-0026 | PS5-53-LA-0001-CX01 | TJX12 - Optical fiber cable | I | PS5-53-04 - Water Treatment Purification Package | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00256-0027 | PS5-60-IE-0004-CX03 | TJX12 - Optical fiber cable | I | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-RFI-68-64-04-0054 |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00256-0028 | PS5-60-IE-0004-CX04 | TJX12 - Optical fiber cable | I | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-RFI-68-64-04-0054 |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00256-0029 | PS5-60-LA-0003-CX01 | TJX12 - Optical fiber cable | I | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-68-64-04-0078
T-00256-0030 | PS5-74-LB-5101-CX01 | TJX12 - Optical fiber cable | I | PS5-74-02 - N2 Generation Skid (UCP) | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00256-0031 | PS5-82-LA-0001-CX01 | TJX12 - Optical fiber cable | I | PS5-82-03 - Sewage Treatment Plant Package (UCP) | To be completed | CPP-RFI-68-64-04-0037 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00256-0085 | PS5-75-LA-6200-CX01 | TJX12 - Optical fiber cable | I | PS5-75-01 - DRA Injection Package | To be completed | CPP-RFI-68-64-04-0049 |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00256-0090 | PS5-60-LA-0003-CX02 | TJX12 - Optical fiber cable | I | PS5-60-22 - Power Gen Master UCP | To be completed |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00257-0165 | PS5-60-TW-0006G | TJX13 - Thermowell | I | PS5-60-76 - Engine G Cooling system | To be completed
T-00257-0166 | PS5-71-TW-4203 | TJX13 - Thermowell | I | PS5-71-12 - CFO Service Tank | To be completed
T-00257-0167 | PS5-71-TW-0007 | TJX13 - Thermowell | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00257-0168 | PS5-71-TW-0003 | TJX13 - Thermowell | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00257-0169 | PS5-60-TW-0007C | TJX13 - Thermowell | I | PS5-60-72 - Engine C Cooling system | To be completed
T-00257-0170 | PS5-71-TW-0004 | TJX13 - Thermowell | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00257-0171 | PS5-60-TW-0005F | TJX13 - Thermowell | I | PS5-60-75 - Engine F Cooling system | To be completed
T-00257-0172 | PS5-28-TW-1201 | TJX13 - Thermowell | I | PS5-28-06 - Relief Drum and Pump | To be completed
T-00257-0173 | PS5-60-TW-0007B | TJX13 - Thermowell | I | PS5-60-71 - Engine B Cooling system | To be completed
T-00257-0174 | PS5-60-TW-0006C | TJX13 - Thermowell | I | PS5-60-72 - Engine C Cooling system | To be completed
T-00257-0175 | PS5-60-TW-0008A | TJX13 - Thermowell | I | PS5-60-70 - Engine A Cooling system | To be completed
T-00257-0176 | PS5-60-TW-0007D | TJX13 - Thermowell | I | PS5-60-73 - Engine D Cooling system | To be completed
T-00257-0177 | PS5-60-TW-0008C | TJX13 - Thermowell | I | PS5-60-72 - Engine C Cooling system | To be completed
T-00257-0178 | PS5-28-TW-1402 | TJX13 - Thermowell | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00257-0179 | PS5-60-TW-0005G | TJX13 - Thermowell | I | PS5-60-76 - Engine G Cooling system | To be completed
T-00257-0180 | PS5-28-TW-1104 | TJX13 - Thermowell | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00257-0181 | PS5-60-TW-0008E | TJX13 - Thermowell | I | PS5-60-74 - Engine E Cooling system | To be completed
T-00257-0182 | PS5-60-TW-0007A | TJX13 - Thermowell | I | PS5-60-70 - Engine A Cooling system | To be completed
T-00257-0183 | PS5-60-TW-0006D | TJX13 - Thermowell | I | PS5-60-73 - Engine D Cooling system | To be completed
T-00257-0184 | PS5-60-TW-0008B | TJX13 - Thermowell | I | PS5-60-71 - Engine B Cooling system | To be completed
T-00257-0185 | PS5-60-TW-0007E | TJX13 - Thermowell | I | PS5-60-74 - Engine E Cooling system | To be completed
T-00257-0186 | PS5-60-TW-0008D | TJX13 - Thermowell | I | PS5-60-73 - Engine D Cooling system | To be completed
T-00257-0187 | PS5-25-TW-0003B | TJX13 - Thermowell | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00257-0188 | PS5-71-TW-4202 | TJX13 - Thermowell | I | PS5-71-12 - CFO Service Tank | To be completed
T-00257-0189 | PS5-60-TW-0008F | TJX13 - Thermowell | I | PS5-60-75 - Engine F Cooling system | To be completed
T-00257-0190 | PS5-60-TW-0006E | TJX13 - Thermowell | I | PS5-60-74 - Engine E Cooling system | To be completed
T-00257-0191 | PS5-25-TW-0002A | TJX13 - Thermowell | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00257-0192 | PS5-25-TW-0003C | TJX13 - Thermowell | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00257-0193 | PS5-71-TW-0006 | TJX13 - Thermowell | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00257-0194 | PS5-60-TW-0006B | TJX13 - Thermowell | I | PS5-60-71 - Engine B Cooling system | To be completed
T-00257-0195 | PS5-25-TW-0003A | TJX13 - Thermowell | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00257-0196 | PS5-71-TW-4103 | TJX13 - Thermowell | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00257-0197 | PS5-28-TW-1105 | TJX13 - Thermowell | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed
T-00257-0198 | PS5-60-TW-0006A | TJX13 - Thermowell | I | PS5-60-70 - Engine A Cooling system | To be completed
T-00257-0199 | PS5-60-TW-0007F | TJX13 - Thermowell | I | PS5-60-75 - Engine F Cooling system | To be completed
T-00257-0200 | PS5-25-TW-0002B | TJX13 - Thermowell | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00257-0201 | PS5-25-TW-0001 | TJX13 - Thermowell | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed
T-00257-0202 | PS5-25-TW-0004 | TJX13 - Thermowell | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00257-0203 | PS5-25-TW-0002C | TJX13 - Thermowell | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00257-0204 | PS5-71-TW-4102 | TJX13 - Thermowell | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00257-0205 | PS5-74-TW-0001 | TJX13 - Thermowell | I | PS5-74-04 - Nitrogen Distribution Header | To be completed
T-00257-0206 | PS5-28-TW-1401 | TJX13 - Thermowell | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed
T-00257-0207 | PS5-60-TW-0005A | TJX13 - Thermowell | I | PS5-60-70 - Engine A Cooling system | To be completed
T-00257-0208 | PS5-60-TW-0005B | TJX13 - Thermowell | I | PS5-60-71 - Engine B Cooling system | To be completed
T-00257-0209 | PS5-60-TW-0005C | TJX13 - Thermowell | I | PS5-60-72 - Engine C Cooling system | To be completed
T-00257-0210 | PS5-60-TW-0005D | TJX13 - Thermowell | I | PS5-60-73 - Engine D Cooling system | To be completed
T-00257-0211 | PS5-60-TW-0005E | TJX13 - Thermowell | I | PS5-60-74 - Engine E Cooling system | To be completed
T-00257-0212 | PS5-60-TW-0006F | TJX13 - Thermowell | I | PS5-60-75 - Engine F Cooling system | To be completed
T-00257-0213 | PS5-60-TW-0007G | TJX13 - Thermowell | I | PS5-60-76 - Engine G Cooling system | To be completed
T-00257-0214 | PS5-60-TW-0008G | TJX13 - Thermowell | I | PS5-60-76 - Engine G Cooling system | To be completed
T-00275-1945 | PS5-60-IE-0003B-CA02 | TIX01 - RJ45 Cable | T | PS5-60-05 - Power Gen Package B (UCP) | To be completed
T-00275-1946 | PS5-60-IE-0003B-CA03 | TIX01 - RJ45 Cable | T | PS5-60-05 - Power Gen Package B (UCP) | To be completed
T-00275-1947 | PS5-60-IE-0003B-CA04 | TIX01 - RJ45 Cable | T | PS5-60-05 - Power Gen Package B (UCP) | To be completed
T-00275-1948 | PS5-60-IE-0003B-CA05 | TIX01 - RJ45 Cable | T | PS5-60-05 - Power Gen Package B (UCP) | To be completed
T-00275-1949 | PS5-60-IE-0003C-CA02 | TIX01 - RJ45 Cable | T | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00275-1950 | PS5-60-IE-0003C-CA03 | TIX01 - RJ45 Cable | T | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00275-1951 | PS5-60-IE-0003C-CA04 | TIX01 - RJ45 Cable | T | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00275-1952 | PS5-60-IE-0003C-CA05 | TIX01 - RJ45 Cable | T | PS5-60-08 - Power Gen Package C (UCP) | To be completed
T-00275-1953 | PS5-60-IE-0003D-CA02 | TIX01 - RJ45 Cable | T | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00275-1954 | PS5-60-IE-0003D-CA03 | TIX01 - RJ45 Cable | T | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00275-1955 | PS5-60-IE-0003D-CA04 | TIX01 - RJ45 Cable | T | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00275-1956 | PS5-60-IE-0003D-CA05 | TIX01 - RJ45 Cable | T | PS5-60-11 - Power Gen Package D (UCP) | To be completed
T-00275-1957 | PS5-60-IE-0003E-CA02 | TIX01 - RJ45 Cable | T | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00275-1958 | PS5-60-IE-0003E-CA03 | TIX01 - RJ45 Cable | T | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00275-1959 | PS5-60-IE-0003E-CA04 | TIX01 - RJ45 Cable | T | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00275-1960 | PS5-60-IE-0003E-CA05 | TIX01 - RJ45 Cable | T | PS5-60-14 - Power Gen Package E (UCP) | To be completed
T-00275-1961 | PS5-60-IE-0003F-CA02 | TIX01 - RJ45 Cable | T | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00275-1962 | PS5-60-IE-0003F-CA03 | TIX01 - RJ45 Cable | T | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00275-1963 | PS5-60-IE-0003F-CA04 | TIX01 - RJ45 Cable | T | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00275-1964 | PS5-60-IE-0003F-CA05 | TIX01 - RJ45 Cable | T | PS5-60-17 - Power Gen Package F (UCP) | To be completed
T-00275-1965 | PS5-60-IE-0003G-CA03 | TIX01 - RJ45 Cable | T | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00275-1966 | PS5-60-IE-0003G-CA04 | TIX01 - RJ45 Cable | T | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00275-1967 | PS5-60-IE-0003G-CA05 | TIX01 - RJ45 Cable | T | PS5-60-20 - Power Gen Package G (UCP) | To be completed
T-00275-1968 | PS5-60-IE-0004-CA01 | TIX01 - RJ45 Cable | T | PS5-60-22 - Power Gen Master UCP | To be completed
T-00275-1969 | PS5-60-IE-0004-CA07 | TIX01 - RJ45 Cable | T | PS5-60-22 - Power Gen Master UCP | To be completed
T-00275-1970 | PS5-60-IE-0004-CA08 | TIX01 - RJ45 Cable | T | PS5-60-22 - Power Gen Master UCP | To be completed
T-00275-1971 | PS5-60-IE-0004-CA14 | TIX01 - RJ45 Cable | T | PS5-60-22 - Power Gen Master UCP | To be completed
T-00275-1972 | PS5-60-IE-0004-CA15 | TIX01 - RJ45 Cable | T | PS5-60-22 - Power Gen Master UCP | To be completed
T-00275-1973 | PS5-60-IE-0004-CA21 | TIX01 - RJ45 Cable | T | PS5-60-22 - Power Gen Master UCP | To be completed
T-00275-1974 | PS5-60-IH-0001A-CA01 | TIX01 - RJ45 Cable | T | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | To be completed
T-00275-1975 | PS5-60-IH-0001B-CA01 | TIX01 - RJ45 Cable | T | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | To be completed
T-00275-1976 | PS5-60-IH-0001C-CA01 | TIX01 - RJ45 Cable | T | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | To be completed
T-00275-1977 | PS5-60-IH-0001D-CA01 | TIX01 - RJ45 Cable | T | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | To be completed
T-00275-1978 | PS5-60-IH-0001E-CA01 | TIX01 - RJ45 Cable | T | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | To be completed
T-00275-1979 | PS5-60-IH-0001F-CA01 | TIX01 - RJ45 Cable | T | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | To be completed
T-00275-1980 | PS5-60-IH-0001G-CA01 | TIX01 - RJ45 Cable | T | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | To be completed
T-00275-1981 | PS5-60-IN-0001A-CA01 | TIX01 - RJ45 Cable | T | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | To be completed
T-00275-1982 | PS5-60-IN-0001B-CA01 | TIX01 - RJ45 Cable | T | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | To be completed
T-00275-1983 | PS5-60-IN-0001C-CA01 | TIX01 - RJ45 Cable | T | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | To be completed
T-00275-1984 | PS5-60-IN-0001D-CA01 | TIX01 - RJ45 Cable | T | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | To be completed
T-00275-1985 | PS5-60-IN-0001E-CA01 | TIX01 - RJ45 Cable | T | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | To be completed
T-00275-1986 | PS5-60-IN-0001F-CA01 | TIX01 - RJ45 Cable | T | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | To be completed
T-00275-1987 | PS5-60-IN-0001G-CA01 | TIX01 - RJ45 Cable | T | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | To be completed
T-00275-1988 | PS5-60-IN-0002A-CA01 | TIX01 - RJ45 Cable | T | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | To be completed
T-00275-1989 | PS5-60-IN-0002B-CA01 | TIX01 - RJ45 Cable | T | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | To be completed
T-00275-1990 | PS5-60-IN-0002C-CA01 | TIX01 - RJ45 Cable | T | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | To be completed
T-00275-1991 | PS5-60-IN-0002D-CA01 | TIX01 - RJ45 Cable | T | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | To be completed
T-00275-1992 | PS5-60-IN-0002E-CA01 | TIX01 - RJ45 Cable | T | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | To be completed
T-00275-1993 | PS5-60-IN-0002F-CA01 | TIX01 - RJ45 Cable | T | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | To be completed
T-00275-1994 | PS5-60-IN-0002G-CA01 | TIX01 - RJ45 Cable | T | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | To be completed
T-00275-1995 | PS5-60-LA-0002B-CA01 | TIX01 - RJ45 Cable | T | PS5-60-10 - Power Generation Package D | To be completed
T-00275-1996 | PS5-60-LA-0002B-CA02 | TIX01 - RJ45 Cable | T | PS5-60-10 - Power Generation Package D | To be completed
T-00275-1997 | PS5-60-LA-0002B-CA03 | TIX01 - RJ45 Cable | T | PS5-60-10 - Power Generation Package D | To be completed
T-00275-1998 | PS5-60-LA-0002B-CA04 | TIX01 - RJ45 Cable | T | PS5-60-10 - Power Generation Package D | To be completed
T-00275-1999 | PS5-60-LA-0002B-CA05 | TIX01 - RJ45 Cable | T | PS5-60-10 - Power Generation Package D | To be completed
T-00275-2000 | PS5-60-LA-0002B-CA06 | TIX01 - RJ45 Cable | T | PS5-60-10 - Power Generation Package D | To be completed
T-00275-2001 | PS5-60-LA-0002C-CA01 | TIX01 - RJ45 Cable | T | PS5-60-16 - Power Generation Package F | To be completed
T-00275-2002 | PS5-60-LA-0002C-CA02 | TIX01 - RJ45 Cable | T | PS5-60-16 - Power Generation Package F | To be completed
T-00275-2003 | PS5-60-LA-0002C-CA03 | TIX01 - RJ45 Cable | T | PS5-60-16 - Power Generation Package F | To be completed
T-00275-2004 | PS5-60-LA-0002C-CA04 | TIX01 - RJ45 Cable | T | PS5-60-16 - Power Generation Package F | To be completed
T-00275-2005 | PS5-60-LA-0002C-CA05 | TIX01 - RJ45 Cable | T | PS5-60-16 - Power Generation Package F | To be completed
T-00275-2006 | PS5-60-LA-0002C-CA06 | TIX01 - RJ45 Cable | T | PS5-60-16 - Power Generation Package F | To be completed
T-00275-2007 | PS5-60-SEA-0001-CA01 | TIX01 - RJ45 Cable | T | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed
T-00275-2008 | PS5-71-IN-0001-CA01 | TIX01 - RJ45 Cable | T | PS5-71-19 - Diesel Separator Module (UCP) | To be completed
T-00275-2009 | PS5-71-IN-0001-CA11 | TIX01 - RJ45 Cable | T | PS5-71-19 - Diesel Separator Module (UCP) | To be completed
T-00275-2010 | PS5-71-IN-0002-CA01 | TIX01 - RJ45 Cable | T | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | To be completed
T-00275-2011 | PS5-71-IN-0003-CA01 | TIX01 - RJ45 Cable | T | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed
T-00275-2012 | PS5-71-IN-0004A-CA01 | TIX01 - RJ45 Cable | T | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00275-2013 | PS5-71-IN-0004B-CA01 | TIX01 - RJ45 Cable | T | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed
T-00275-4202 | PS5-09-LB-8451A-CA01 | TIX01 - RJ45 Cable | T | PS5-09-03 - HVAC for Generator Building | To be completed
T-00275-4203 | PS5-09-LB-8451B-CA01 | TIX01 - RJ45 Cable | T | PS5-09-03 - HVAC for Generator Building | To be completed
T-00284-0085 | PS5-71-FIT-0019 | TJX06 - Tubing pressure test | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00284-0086 | PS5-50-FIT-0001 | TJX06 - Tubing pressure test | I | PS5-50-03 - Water Pre-Treatment Package | To be completed
T-00284-0087 | PS5-71-FIT-0018 | TJX06 - Tubing pressure test | I | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00284-0088 | PS5-71-FIT-0020 | TJX06 - Tubing pressure test | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00284-0089 | PS5-71-FIT-0012 | TJX06 - Tubing pressure test | I | PS5-71-17 - Diesel Fuel Distribution Header | To be completed
T-00284-0090 | PS5-71-FIT-0005 | TJX06 - Tubing pressure test | I | PS5-71-17 - Diesel Fuel Distribution Header | To be completed
T-00284-0091 | PS5-71-LIT-1202 | TJX06 - Tubing pressure test | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed
T-00284-0092 | PS5-60-LIT-4401 | TJX06 - Tubing pressure test | I | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | To be completed
T-00284-0093 | PS5-71-LIT-4401 | TJX06 - Tubing pressure test | I | PS5-71-15 - Diesel Fuel Storage Tank | To be completed
T-00284-0094 | PS5-53-LIT-4101 | TJX06 - Tubing pressure test | I | PS5-53-01 - Utility Water / Storage Tank | To be completed
T-00284-0095 | PS5-60-LIT-4301 | TJX06 - Tubing pressure test | I | PS5-60-24 - Cooling Water Tank & Pump | To be completed
T-00284-0096 | PS5-71-LIT-1201 | TJX06 - Tubing pressure test | I | PS5-71-20 - Diesel Fuel Day Tank | To be completed
T-00284-0097 | PS5-71-LIT-4402 | TJX06 - Tubing pressure test | I | PS5-71-15 - Diesel Fuel Storage Tank | To be completed
T-00284-0098 | PS5-53-LIT-4102 | TJX06 - Tubing pressure test | I | PS5-53-01 - Utility Water / Storage Tank | To be completed
T-00284-0099 | PS5-25-PDIT-0034A | TJX06 - Tubing pressure test | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00284-0100 | PS5-01-PDIT-0012B | TJX06 - Tubing pressure test | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00284-0101 | PS5-01-PDIT-0011A | TJX06 - Tubing pressure test | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00284-0102 | PS5-25-PDIT-0050 | TJX06 - Tubing pressure test | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00284-0103 | PS5-25-PDIT-0034C | TJX06 - Tubing pressure test | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00284-0104 | PS5-71-PDIT-0030 | TJX06 - Tubing pressure test | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed
T-00284-0105 | PS5-01-PDIT-0011B | TJX06 - Tubing pressure test | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00284-0106 | PS5-71-PDIT-0056B | TJX06 - Tubing pressure test | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00284-0107 | PS5-71-PDIT-0056A | TJX06 - Tubing pressure test | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00284-0108 | PS5-01-PDIT-0012A | TJX06 - Tubing pressure test | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00284-0109 | PS5-25-PDIT-0034B | TJX06 - Tubing pressure test | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00284-0179 | PS5-01-FCV-0004B | TJX06 - Tubing pressure test | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00284-0180 | PS5-25-FCV-0004 | TJX06 - Tubing pressure test | I | PS5-25-06 - Crude Oil Export Pumps Discharge | To be completed
T-00284-0181 | PS5-01-FCV-0003A | TJX06 - Tubing pressure test | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00284-0182 | PS5-01-FCV-0003B | TJX06 - Tubing pressure test | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00284-0183 | PS5-71-FCV-0018 | TJX06 - Tubing pressure test | I | PS5-71-13 - CFO Service Pump A/B | To be completed
T-00284-0184 | PS5-25-FCV-0003B | TJX06 - Tubing pressure test | I | PS5-25-03 - Crude Oil Export Pump B | To be completed
T-00284-0185 | PS5-71-LCV-4101 | TJX06 - Tubing pressure test | I | PS5-71-04 - CFO Storage Tank | To be completed
T-00284-0186 | PS5-71-FCV-0019 | TJX06 - Tubing pressure test | I | PS5-71-21 - Diesel Transfer Pump A/B | To be completed
T-00284-0187 | PS5-71-FCV-0020 | TJX06 - Tubing pressure test | I | PS5-71-05 - CFO Transfer Pump A/B | To be completed
T-00284-0188 | PS5-01-FCV-0004A | TJX06 - Tubing pressure test | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed
T-00284-0189 | PS5-25-FCV-0003A | TJX06 - Tubing pressure test | I | PS5-25-02 - Crude Oil Export Pump A | To be completed
T-00284-0190 | PS5-25-FCV-0003C | TJX06 - Tubing pressure test | I | PS5-25-04 - Crude Oil Export Pump C | To be completed
T-00284-0208 | PS5-09-PDIT-8207 | TJX06 - Tubing pressure test | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00284-0209 | PS5-09-PDIT-8407 | TJX06 - Tubing pressure test | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00284-0210 | PS5-09-PDIT-8408 | TJX06 - Tubing pressure test | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00284-0211 | PS5-09-PDIT-8409 | TJX06 - Tubing pressure test | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00284-0212 | PS5-09-PDIT-8411 | TJX06 - Tubing pressure test | I | PS5-09-03 - HVAC for Generator Building | To be completed
T-00604-0248 | PS5-61-IJ-0001-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-63-NER-0010) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00604-0249 | PS5-61-IJ-0001-CL02 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-63-NER-0011) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00604-0250 | PS5-61-IJ-0010-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0010) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00604-0251 | PS5-61-IJ-0011-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0011) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00604-0252 | PS5-61-IK-0001-CG01 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0240 | CPP-RFI-68-331-07-0255 |  | TZ-MID-68-WPR2-151112 Cable trench installation to be complete [OPEN] ¦ TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both side [OPEN]
T-00604-0253 | PS5-61-IK-0001-CG02 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0011) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [OPEN] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00604-0254 | PS5-61-IK-0001-CG03 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0011) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00604-0255 | PS5-61-IK-0001-CG04 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0011) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00604-0294 | PS5-61-ISR-0101-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0239 | CPP-RFI-68-331-07-0254 |  | TZ-MID-68-WPR2-151112 Vertical Cable ladder to be install at transformer side PS5-61-ISR-0101 [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench installation to be complete [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both side [OPEN]
T-00604-0295 | PS5-61-ISR-0102-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0239 | CPP-RFI-68-331-07-0254 |  | TZ-MID-68-WPR2-151112 Vertical Cable ladder to be install at transformer side PS5-61-ISR-0102 [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench installation to be complete [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both side [OPEN]
T-00604-0296 | PS5-61-IU-0010-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed | CPP-RFI-68-331-05-0239 | CPP-RFI-68-331-07-0254 |  | TZ-MID-68-WPR2-151112 Vertical Cable ladder to be install at transformer side PS5-61-IU-0010 [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench installation to be complete [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both side [OPEN]
T-00604-0297 | PS5-61-IU-0010-CL02 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0010) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00604-0298 | PS5-61-IU-0011-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed | CPP-RFI-68-331-05-0239 | CPP-RFI-68-331-07-0254 |  | TZ-MID-68-WPR2-151112 Vertical Cable ladder to be install at transformer side PS5-61-IU-0011 [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench installation to be complete [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both side [OPEN]
T-00604-0299 | PS5-61-IU-0011-CL02 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed | CPP-RFI-68-331-05-0239 | CPP-RFI-68-331-07-0254 |  | TZ-MID-68-WPR2-151112 Vertical Cable ladder to be install at transformer side PS5-61-IU-0011 [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench installation to be complete [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both side [OPEN]
T-00604-0302 | PS5-61-NER-0010-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed | CPP-RFI-68-331-05-0240 | CPP-RFI-68-331-07-0255 |  | TZ-MID-68-WPR2-151112 Cable trench installation to be complete [OPEN] ¦ TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both side [OPEN]
T-00604-0303 | PS5-61-NER-0011-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed | CPP-RFI-68-331-05-0240 | CPP-RFI-68-331-07-0255 |  | TZ-MID-68-WPR2-151112 Cable trench installation to be complete [OPEN] ¦ TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both side [OPEN]
T-00604-0304 | PS5-63-IV-0010-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0240 | CPP-RFI-68-331-07-0255 |  | TZ-MID-68-WPR2-151112 Cable trench installation to be complete [OPEN] ¦ TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both side [OPEN]
T-00604-0305 | PS5-63-IV-0011-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0240 | CPP-RFI-68-331-07-0255 |  | TZ-MID-68-WPR2-151112 Cable trench installation to be complete [OPEN] ¦ TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both side [OPEN]
T-00604-0306 | PS5-63-NER-0010-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0240 | CPP-RFI-68-331-07-0255 |  | TZ-MID-68-WPR2-151112 Cable trench installation to be complete [OPEN] ¦ TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both side [OPEN]
T-00604-0307 | PS5-63-NER-0011-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0240 | CPP-RFI-68-331-07-0255 |  | TZ-MID-68-WPR2-151112 Cable trench installation to be complete [OPEN] ¦ TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both side [OPEN]
T-00606-0065 | PS5-61-IE-0002-CD01 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0010) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00606-0066 | PS5-61-IE-0002-CD02 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-331-05-0243
T-00606-0067 | PS5-61-IE-0002-CD03 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0010) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00606-0068 | PS5-61-IE-0002-CD04 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0011) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00606-0069 | PS5-61-IE-0002-CD05 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0011) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00606-0070 | PS5-61-IE-0002-CD06 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151112 Cable ladder/tray not yet install at trafo side (PS5-61-IU-0011) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-HV-0016, PS5-88-BU-HV-0015, PS5-88-BU-HV-0019). [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00606-0071 | PS5-61-IJ-0001-CD01 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0010) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00606-0072 | PS5-61-IJ-0001-CD03 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Started (not Completed) | CPP-RFI-68-33/1-05-0211 |  |  |  | TZ-MID-68-WPR2-151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112-SS Tag on both ends not installed [CLOSED]
T-00606-0075 | PS5-61-IJ-0001-CD35 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0010) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00606-0077 | PS5-61-IJ-0001-CD37 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151112 Cable Reaching Final Destination, but need to install Cable Tray (at Transformers side) [OPEN] | Doc. TZ-MID-68-WPR2-151112 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00606-0078 | PS5-61-IJ-0001-CD38 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-ISR-0102) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00606-0079 | PS5-61-IJ-0001-CD39 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0010) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00606-0080 | PS5-61-IJ-0001-CD40 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0011) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00606-0082 | PS5-61-IJ-0001-CD42 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | To be completed
T-00608-0350 | PS5-01-FIT-0003A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-01-02 - Fire Water Pump A | To be completed | CPP-RFI-68-33/1-05-0219 |  |  |  | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely [OPEN]
T-00608-0351 | PS5-01-FIT-0003B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-01-03 - Fire Water Pump B | To be completed | CPP-RFI-68-33/1-05-0219 |  |  |  | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely [OPEN]
T-00608-0352 | PS5-01-FIT-0004A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed | CPP-RFI-68-33/1-05-0219 |  |  |  | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely [OPEN]
T-00608-0353 | PS5-01-FIT-0004B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed | CPP-RFI-68-33/1-05-0219 |  |  |  | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely [OPEN]
T-00608-0354 | PS5-01-IE-0001A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-01-05 - Foam Skid | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely [OPEN]
T-00608-0355 | PS5-01-IE-0001B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-01-05 - Foam Skid | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely [OPEN]
T-00608-0356 | PS5-01-IE-0002A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed | CPP-RFI-68-33/1-05-0219 |  |  |  | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely [OPEN]
T-00608-0357 | PS5-01-IE-0002B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed | CPP-RFI-68-33/1-05-0219 |  |  |  | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely [OPEN]
T-00608-0358 | PS5-01-IE-0009A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-01-02 - Fire Water Pump A | To be completed | CPP-RFI-68-33/1-05-0219 |  |  |  | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely [OPEN]
T-00608-0359 | PS5-01-IE-0009B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-01-03 - Fire Water Pump B | To be completed | CPP-RFI-68-33/1-05-0219 |  |  |  | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely [OPEN]
T-00608-0360 | PS5-03-GDLHP-0137-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151112, 151111, 151115-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151111, 151115-Cable dressing not yet done completely [OPEN]
T-00608-0361 | PS5-03-GDLHP-0142-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151112, 151111, 151115-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151111, 151115-Cable dressing not yet done completely [OPEN]
T-00608-0362 | PS5-03-GDLHP-0143-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-Cable dressing not yet done completely [OPEN]
T-00608-0363 | PS5-03-GDLHP-0144-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-Cable dressing not yet done completely [OPEN]
T-00608-0364 | PS5-03-GDLHP-0146-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114, 151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114, 151113-Cable dressing not yet done completely [OPEN]
T-00608-0365 | PS5-03-GDLHP-0147-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-Cable dressing not yet done completely [OPEN]
T-00608-0366 | PS5-03-GDLHP-0149-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-Cable dressing not yet done completely [OPEN]
T-00608-0367 | PS5-03-GDLHP-0150-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-Cable dressing not yet done completely [OPEN]
T-00608-0368 | PS5-03-GDLHP-0401-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151112, 151111, 151108, 151107-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151111, 151108, 151107-Cable dressing not yet done completely [OPEN]
T-00608-0369 | PS5-05-IG-0004-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | Started (not Completed) | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151111, 151115, 151117-SS Tag on both ends not installed [CLOSED]
T-00608-0370 | PS5-05-IG-0006-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151111-SS Tag on both ends not installed [OPEN]
T-00608-0371 | PS5-25-DM-3200A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0372 | PS5-25-DM-3200B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0373 | PS5-25-DM-3300A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0374 | PS5-25-DM-3300B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0375 | PS5-25-DM-3400A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0376 | PS5-25-DM-3400B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0377 | PS5-25-DM-6400A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0378 | PS5-25-DM-6400B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0379 | PS5-25-DM-6500A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0380 | PS5-25-DM-6500B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0381 | PS5-25-DM-6600A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0382 | PS5-25-DM-6600B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0383 | PS5-25-FIT-0001-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0384 | PS5-25-FIT-0003A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0385 | PS5-25-FIT-0003B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0386 | PS5-25-FIT-0003C-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0387 | PS5-25-FIT-0004-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-06 - Crude Oil Export Pumps Discharge | Started (not Completed) | CPP-RFI-68-331-05-0215 | CPP-RFI-68-33/1-07-0308 |  |  | TZ-MID-68-WPR2-151112,151111,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0388 | PS5-25-HE-2100-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0389 | PS5-25-HE-2200-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0287 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0390 | PS5-25-HE-2300-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0287 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0391 | PS5-25-UD-3100A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00608-0392 | PS5-28-BE-0002A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-17 - Reinjection Pump | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed [OPEN]
T-00608-0393 | PS5-28-BE-0002B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-17 - Reinjection Pump | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed [OPEN]
T-00608-0394 | PS5-28-DM-3300-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-06 - Relief Drum and Pump | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed [OPEN]
T-00608-0395 | PS5-28-DM-3400-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed | CPP-RFI-68-331-05-0238 | CPP-RFI-68-331-07-0253 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 To be laid the cable in field run cable tray [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Dressing to be done at both side [OPEN]
T-00608-0396 | PS5-28-DM-3500-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-08 - Open Drain Sump and Pumps | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed [CLOSED]
T-00608-0397 | PS5-28-DM-3600A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-08 - Open Drain Sump and Pumps | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed [OPEN]
T-00608-0398 | PS5-28-DM-3600A-CL02 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-08 - Open Drain Sump and Pumps | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0307 |  |  | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed [OPEN]
T-00608-0399 | PS5-28-DM-3600B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-08 - Open Drain Sump and Pumps | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed [OPEN]
T-00608-0400 | PS5-28-DM-3600B-CL02 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-08 - Open Drain Sump and Pumps | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed [CLOSED]
T-00608-0401 | PS5-28-DM-3700A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed | CPP-RFI-68-331-05-0240 | CPP-RFI-68-331-07-0255 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Field run cable tray to be install [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Dressing to be done at both side [OPEN]
T-00608-0402 | PS5-28-DM-3700B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151118-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151118-SS Tag on both ends not installed [CLOSED]
T-00608-0403 | PS5-28-DM-3800A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED]
T-00608-0404 | PS5-28-DM-3800B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [OPEN]
T-00608-0405 | PS5-28-DM-3800C-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED]
T-00608-0406 | PS5-28-DM-3900A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-17 - Reinjection Pump | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Cable Dressing to be done at both side [OPEN]
T-00608-0407 | PS5-28-DM-3900B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-17 - Reinjection Pump | To be completed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0307 |  |  | TZ-MID-68-WPR2-151113, TZ-MID-68-WPR2-151112 - Cable need to dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151113, TZ-MID-68-WPR2-151112 - SS tag at both ends Need to Install [CLOSED]
T-00608-0408 | PS5-28-HE-2100-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED]
T-00608-0409 | PS5-28-HE-2200-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151118-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151118-SS Tag on both ends not installed [CLOSED]
T-00608-0410 | PS5-28-ISO-2008-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-28-10 - Oil Skimmer Package | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed [OPEN]
T-00608-0411 | PS5-50-IE-0001-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-50-01 - Water Well Submersible Pumps (3100) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151119-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151119-SS Tag on both ends not installed [OPEN]
T-00608-0412 | PS5-50-IE-0002-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-50-02 - Water Well Submersible Pumps (3200) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112,151111,151108,151107,151105-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151108,151107,151105-SS Tag on both ends not installed [OPEN]
T-00608-0413 | PS5-53-DM-3100A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-53-02 - Water Distribution Pump A/B | To be completed | CPP-RFI-68-33/1-07-0220 |  |  |  | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely [OPEN]
T-00608-0414 | PS5-53-DM-3100B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-53-02 - Water Distribution Pump A/B | To be completed | CPP-RFI-68-33/1-07-0220 |  |  |  | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely [OPEN]
T-00608-0415 | PS5-53-IN-0001-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-53-04 - Water Treatment Purification Package | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0307 |  |  | TZ-MID-68-WPR2-151112,151111,151108,151109-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151108,151109-SS Tag on both ends not installed [OPEN]
T-00608-0416 | PS5-60-DM-3300-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-60-24 - Cooling Water Tank & Pump | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed [CLOSED]
T-00608-0417 | PS5-60-DM-3400-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | To be completed | CPP-RFI-68-331-05-0240 | CPP-RFI-68-331-07-0255 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Need to open cable trench at field side (PS5-88-BU-LV-00156) [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151118 To be laid into the conduit field side [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Dressing to be done at both side [OPEN]
T-00608-0418 | PS5-61-IDH-3100A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  |  | Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111 Cable Dressing to be done at both side [OPEN]
T-00608-0419 | PS5-61-IDH-3100B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  |  | Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111 SS Permanent cable tag to be install [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111 Cable Dressing to be done at both side [OPEN]
T-00608-0420 | PS5-61-IDH-3100C-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  |  | Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111 SS Permanent cable tag to be install [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111 Cable Dressing to be done at both side [OPEN]
T-00608-0421 | PS5-61-IG-0006-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151111, 151115, 151117-SS Tag on both ends not installed [OPEN]
T-00608-0422 | PS5-61-IG-0007-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed [OPEN]
T-00608-0423 | PS5-61-IG-0012A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely [OPEN]
T-00608-0424 | PS5-61-IG-0012B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely [OPEN]
T-00608-0425 | PS5-61-IG-0012C-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely [OPEN]
T-00608-0426 | PS5-61-IG-0014-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0307 |  |  | TZ-MID-68-WPR2-151112, 151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151111-SS Tag on both ends not installed [OPEN]
T-00608-0427 | PS5-61-IG-0042-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-0042 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151111, 151115, 151117-SS Tag on both ends not installed [CLOSED]
T-00608-0428 | PS5-61-IG-0043-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-0043 | To be completed | CPP-RFI-68-331-05-0239 | CPP-RFI-68-331-07-0254 |  | TZ-MID-68-WPR2-151112, 151111, 151115, 151117 Vertical cable ladder to be done installation at panel side (PS5-61-IG-0043) [OPEN] | TZ-MID-68-WPR2-151112, 151111, 151115, 151117 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151111, 151115, 151117 Dressing to be done at both side [OPEN]
T-00608-0429 | PS5-61-IK-0001-CL37 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Started (not Completed) | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed [CLOSED]
T-00608-0430 | PS5-61-IK-0001-CL38 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed [CLOSED]
T-00608-0431 | PS5-61-IK-0001-CL39 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed [CLOSED]
T-00608-0432 | PS5-61-IK-0001-CL40 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed [CLOSED]
T-00608-0433 | PS5-61-IK-0001-CL41 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed [CLOSED]
T-00608-0434 | PS5-61-IK-0001-CL42 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed [CLOSED]
T-00608-0435 | PS5-61-IK-0001-CL43 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed [CLOSED]
T-00608-0436 | PS5-61-IK-0003-CG01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed
T-00608-0437 | PS5-61-IK-0003-CG02 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed
T-00608-0438 | PS5-61-IK-0003-CG03 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed
T-00608-0439 | PS5-61-IK-0003-CG04 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed
T-00608-0440 | PS5-61-IK-0003-CG05 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed
T-00608-0441 | PS5-61-IK-0003-CG06 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed
T-00608-0442 | PS5-61-IK-0006-CG01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed
T-00608-0443 | PS5-61-IK-0006-CG02 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed
T-00608-0444 | PS5-61-IK-0006-CG03 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed
T-00608-0445 | PS5-61-IK-0006-CG04 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed
T-00608-0446 | PS5-61-IV-0006A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely [OPEN]
T-00608-0447 | PS5-61-IV-0006B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  |  | Doc. TZ-MID-68-WPR2-151112 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151112 - Cable Dressing at Both Side [OPEN]
T-00608-0448 | PS5-61-IV-0006C-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely [OPEN]
T-00608-0449 | PS5-71-DM-3100A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-16 - Diesel Fuel Supply Pump A/B | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151108,151107-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151108,151107-SS Tag on both ends not installed [CLOSED]
T-00608-0450 | PS5-71-DM-3100B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-16 - Diesel Fuel Supply Pump A/B | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151108,151107-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151108,151107-SS Tag on both ends not installed [CLOSED]
T-00608-0451 | PS5-71-DM-3200-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151108,151107-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151108,151107-SS Tag on both ends not installed [CLOSED]
T-00608-0452 | PS5-71-DM-3300A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-05 - CFO Transfer Pump A/B | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED]
T-00608-0453 | PS5-71-DM-3300B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-05 - CFO Transfer Pump A/B | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED]
T-00608-0454 | PS5-71-DM-3400A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-13 - CFO Service Pump A/B | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED]
T-00608-0455 | PS5-71-DM-3400B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-13 - CFO Service Pump A/B | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED]
T-00608-0456 | PS5-71-DM-3500A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-21 - Diesel Transfer Pump A/B | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed [CLOSED]
T-00608-0457 | PS5-71-DM-3500B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-21 - Diesel Transfer Pump A/B | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed [CLOSED]
T-00608-0458 | PS5-71-FIT-0011A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed | CPP-RFI-68-33/1-05-0211 |  |  |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED]
T-00608-0459 | PS5-71-FIT-0011B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED]
T-00608-0460 | PS5-71-HE-2200-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-12 - CFO Service Tank | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED]
T-00608-0461 | PS5-71-HE-2300-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-04 - CFO Storage Tank | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED]
T-00608-0462 | PS5-74-IG-5101-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-74-01 - N2 Generation Skid | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151112,151111,151108-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151108-SS Tag on both ends not installed [OPEN]
T-00608-0463 | PS5-75-DM-3100A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-75-03 - Corrosion Inhibitor Injection Package | To be completed | CPP-RFI-68-33/1-05-0211 |  |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed [OPEN]
T-00608-0464 | PS5-75-DM-3100B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-75-03 - Corrosion Inhibitor Injection Package | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed [OPEN]
T-00608-0465 | PS5-75-DM-3200A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-75-02 - Biocide Injection Package | To be completed | CPP-RFI-68-33/1-05-0211 |  |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed [OPEN]
T-00608-0466 | PS5-75-DM-3200B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-75-02 - Biocide Injection Package | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed [OPEN]
T-00608-0467 | PS5-75-ISO-0001-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-75-01 - DRA Injection Package | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114,151113-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114,151113-SS Tag on both ends not installed [CLOSED]
T-00608-0468 | PS5-75-ISO-0002-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-75-01 - DRA Injection Package | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114,151113-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114,151113-SS Tag on both ends not installed [CLOSED]
T-00608-0469 | PS5-79-IV-0001-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [OPEN]
T-00608-0470 | PS5-79-IV-0002-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [OPEN]
T-00608-0471 | PS5-79-IV-0003-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed [CLOSED]
T-00608-0472 | PS5-79-IV-0004-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed [CLOSED]
T-00608-0473 | PS5-79-IV-0005-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed [CLOSED]
T-00608-0474 | PS5-79-IV-0006-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed [OPEN]
T-00608-0475 | PS5-79-IV-0007-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed [OPEN]
T-00608-0476 | PS5-79-IV-0008-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed [CLOSED]
T-00608-0477 | PS5-79-IV-0009-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed [OPEN]
T-00608-0478 | PS5-79-IV-0010-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed [CLOSED]
T-00608-0479 | PS5-79-IV-0011-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed | CPP-RFI-68-331-05-0295 | CPP-RFI-68-331-07-0296 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Vertical Cable Ladder to be install at field side Heat Tracing Transformer PS5-79-IV-0011 [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Permanent SS tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Cable dressing to be complete at both side [OPEN]
T-00608-0480 | PS5-79-IV-0012-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed | CPP-RFI-68-331-05-0240 | CPP-RFI-68-331-07-0255 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Cable Trench PS5-88-BU-LV-00102 To be complete installation. [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Dressing to be done at both side [OPEN]
T-00608-0481 | PS5-82-IN-0001-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-82-02 - Sewage Treatment Plant Package | To be completed | CPP-RFI-68-33/1-05-0211 |  |  |  | TZ-MID-68-WPR2-151112,151111,151108,151107,151105-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151108,151107,151105-SS Tag on both ends not installed [CLOSED]
T-00608-0943 | PS5-53-IN-0001-CL02 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-53-04 - Water Treatment Purification Package | To be completed | CPP-RFI-68-331-05-0295 | CPP-RFI-68-331-07-0296 |  | TZ-MID-68-WPR2-151112,151111,151108,151109 Cable need to laid in the cable trench at field side Water Treatment Package MCC Panel. [OPEN] | TZ-MID-68-WPR2-151112,151111,151108,151109 Permanent SS tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151108,151109 Cable dressing to be complete at both side [OPEN]
T-00608-0944 | PS5-53-IN-0001-CL03 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-53-04 - Water Treatment Purification Package | To be completed | CPP-RFI-68-331-05-0295 | CPP-RFI-68-331-07-0296 |  | TZ-MID-68-WPR2-151112,151111,151108,151109 Cable need to laid in the cable trench at field side Water Treatment Package MCC Panel. [OPEN] | TZ-MID-68-WPR2-151112,151111,151108,151109 Permanent SS tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151108,151109 Cable dressing to be complete at both side [OPEN]
T-00608-1052 | PS5-71-HE-2400A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  |  | TZ-MID-68-WPR2-151112,151111,151115 Dressing Cable To be done both end [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115 Permanent Cable Tag Missing Both End [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115 Dressing Cable To be done both end [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115 Permanent Cable Tag Missing Both End [CLOSED]
T-00608-1053 | PS5-71-HE-2400A-CL02 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247
T-00608-1054 | PS5-71-HE-2400A-CL03 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED]
T-00608-1055 | PS5-71-HE-2400A-CL04 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED]
T-00608-1056 | PS5-71-HE-2400B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED]
T-00608-1057 | PS5-71-HE-2400B-CL02 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED]
T-00608-1058 | PS5-71-HE-2400B-CL03 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED]
T-00608-1059 | PS5-71-HE-2400B-CL04 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED]
T-00608-1068 | PS5-08-52BT-0131-CS01 | CPX09b - LV Power Cable (One end by HU CTR) | E | PS5-08-52 - Process & Security CCTV | To be completed | CPP-RFI-68-331-05-0275 | CPP-RFI-68-331-07-0276 |  | TZ-MID-68-WPR2-151112, 151111 Field run cable tray to be install [OPEN] | TZ-MID-68-WPR2-151112, 151111 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151111 Permanent SS Cable Tag To be Install [OPEN]
T-00610-0177 | PS5-05-IE-8100-CD09 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151112 151116 Cable trench not yet complete installation [OPEN] | TZ-MID-68-WPR2-151112 151116 Cable tag not yet install both end [CLOSED] ¦ TZ-MID-68-WPR2-151112 151116 Dressing to be done at both end [OPEN]
T-00610-0178 | PS5-05-IE-8100-CD22 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151112, 151116-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151116-Cable dressing not yet done completely [OPEN]
T-00610-0179 | PS5-05-IE-8100-CD24 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151112, 151116-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151116-Cable dressing not yet done completely [OPEN]
T-00610-0180 | PS5-05-IG-0004-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0307 |  |  | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151111, 151115, 151117-SS Tag on both ends not installed [CLOSED]
T-00610-0181 | PS5-05-IG-0006-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0307 |  |  | TZ-MID-68-WPR2-151112, 151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151111-SS Tag on both ends not installed [OPEN]
T-00610-0182 | PS5-05-IG-0025-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  | TZ-MID-68-WPR2-151112, 151116 Field run cable tray installation not yet complete at DB L&SP side (PS5-05-IG-0025). [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0012, PS5-88-BU-HV-0017, PS5-88-CU-HV-0039, PS5-88-CU-HV-0040). [OPEN] | TZ-MID-68-WPR2-151112, 151116 SS Cable tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151116 Cable dressing to be done both side [OPEN]
T-00610-0183 | PS5-05-IG-0026-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  | TZ-MID-68-WPR2-151112, 151116 Field run cable tray installation not yet complete at DB L&SP side (PS5-05-IG-0025). [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0029, PS5-88-BU-HV-0017, PS5-88-BU-HV-0013, PS5-88-BU-HV-0012). [OPEN] | TZ-MID-68-WPR2-151112, 151116 SS Cable tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151116 Cable dressing to be done both side [OPEN]
T-00610-0184 | PS5-06-GU-0003A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151112, 151116, 151118-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151116, 151118-Cable dressing not yet done completely [OPEN]
T-00610-0185 | PS5-06-GU-0003B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0286 |  |  | TZ-MID-68-WPR2-151112, 151116, 151118-SS Tag on both ends not installed [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118-Cable dressing not yet done completely [OPEN]
T-00610-0186 | PS5-06-IG-0004A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-331-05-0215 |  |  |  | TZ-MID-68-WPR2-151112, 151116, 151118-SS Tag on both ends not installed [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118-Cable dressing not yet done completely [OPEN]
T-00610-0187 | PS5-06-IG-0004B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151112, 151116, 151118 Cable Trench Not yet complete installation [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151118 Dressing Cable Both Side to be done [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Permanent Cable Tag Missing Both End [CLOSED]
T-00610-0188 | PS5-25-HE-2100-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00610-0189 | PS5-25-HE-2200-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0279 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00610-0190 | PS5-25-HE-2300-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0287 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00610-0203 | PS5-28-HE-2100-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED]
T-00610-0204 | PS5-28-HE-2200-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151112,151111,151115,151118 Field cable ladder not yet complete installation [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151118 SS Permanent cable tag to be install [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151118 Cable Dressing to be done at both side [OPEN]
T-00610-0205 | PS5-28-IES-2008-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-28-10 - Oil Skimmer Package | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed [OPEN]
T-00610-0206 | PS5-28-IES-3300-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-28-06 - Relief Drum and Pump | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed [OPEN]
T-00610-0207 | PS5-28-IES-3400-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED]
T-00610-0208 | PS5-28-IES-3500-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-28-08 - Open Drain Sump and Pumps | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed [CLOSED]
T-00610-0209 | PS5-28-IES-3600A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-28-08 - Open Drain Sump and Pumps | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  | TZ-MID-68-WPR2-151112,151108,151111 Field run cable tray installation to be install [OPEN] | TZ-MID-68-WPR2-151112,151108,151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112,151108,151111 Cable dressing to be done both side [OPEN]
T-00610-0210 | PS5-28-IES-3600B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-28-08 - Open Drain Sump and Pumps | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed [CLOSED]
T-00610-0211 | PS5-28-IES-3700A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed | CPP-RFI-68-331-05-0239 | CPP-RFI-68-331-07-0254 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Cable not yet laid in field run cable tray equipment side (PS5-28-IES-3700A) [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Dressing to be done at both side [OPEN]
T-00610-0212 | PS5-28-IES-3700B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0307 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151118-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151118-SS Tag on both ends not installed [CLOSED]
T-00610-0213 | PS5-28-IES-3800A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-28-13 - Seal Oil Drain Drum & Pump A | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED]
T-00610-0214 | PS5-28-IES-3800B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-28-14 - Seal Oil Drain Drum & Pump B | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED]
T-00610-0215 | PS5-28-IES-3800C-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-28-15 - Seal Oil Drain Drum & Pump C | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED]
T-00610-0217 | PS5-28-IES-3900B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-28-17 - Reinjection Pump | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed [CLOSED]
T-00610-0220 | PS5-60-IE-0003A-CD06 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0221 | PS5-60-IE-0003A-CD08 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0222 | PS5-60-IE-0003A-CD12 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-01 - Power Generation Package A | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0223 | PS5-60-IE-0003B-CD06 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0224 | PS5-60-IE-0003B-CD08 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0225 | PS5-60-IE-0003B-CD12 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-04 - Power Generation Package B | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0226 | PS5-60-IE-0003C-CD06 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-07 - Power Generation Package C | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0227 | PS5-60-IE-0003C-CD08 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-07 - Power Generation Package C | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0228 | PS5-60-IE-0003C-CD12 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-07 - Power Generation Package C | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0229 | PS5-60-IE-0003D-CD06 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-10 - Power Generation Package D | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0230 | PS5-60-IE-0003D-CD08 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-10 - Power Generation Package D | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0231 | PS5-60-IE-0003D-CD12 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-10 - Power Generation Package D | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0232 | PS5-60-IE-0003E-CD06 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-13 - Power Generation Package E | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  | TZ-MID-68-WPR2-151112, 151116, 151167 Field run cable tray installation to be install [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-HV-0012, PS5-88-BU-HV-0013, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151167 SS Cable tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done both side [OPEN]
T-00610-0233 | PS5-60-IE-0003E-CD08 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-13 - Power Generation Package E | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  | TZ-MID-68-WPR2-151112, 151116, 151167 Field run cable tray installation to be install [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-HV-0012, PS5-88-BU-HV-0013, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151167 SS Cable tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done both side [OPEN]
T-00610-0234 | PS5-60-IE-0003E-CD12 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-13 - Power Generation Package E | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0235 | PS5-60-IE-0003F-CD06 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-16 - Power Generation Package F | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0236 | PS5-60-IE-0003F-CD08 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-16 - Power Generation Package F | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0237 | PS5-60-IE-0003F-CD12 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-16 - Power Generation Package F | To be completed
T-00610-0238 | PS5-60-IE-0003G-CD06 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-19 - Power Generation Package G | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0307 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0239 | PS5-60-IE-0003G-CD08 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-19 - Power Generation Package G | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0240 | PS5-60-IE-0003G-CD12 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-19 - Power Generation Package G | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed [CLOSED]
T-00610-0241 | PS5-60-IE-0004-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed [CLOSED]
T-00610-0242 | PS5-60-IE-0004-CD02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed [CLOSED]
T-00610-0243 | PS5-60-IES-3300-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-24 - Cooling Water Tank & Pump | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed [CLOSED]
T-00610-0244 | PS5-60-IES-3400-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | To be completed | CPP-RFI-68-331-05-0240 | CPP-RFI-68-331-07-0255 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Need to open cable trench at field side (PS5-88-BU-LV-00156) [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151118 To be laid into the conduit field side [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Dressing to be done at both side [OPEN]
T-00610-0245 | PS5-61-IDH-3100A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely [OPEN]
T-00610-0246 | PS5-61-IDH-3100A-CD02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely [OPEN]
T-00610-0247 | PS5-61-IDH-3100B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely [OPEN]
T-00610-0248 | PS5-61-IDH-3100B-CD02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0239 | CPP-RFI-68-331-07-0254 |  |  | TZ-MID-68-WPR2-151112,151111 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111 Dressing to be done at both side [OPEN]
T-00610-0249 | PS5-61-IDH-3100C-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely [OPEN]
T-00610-0250 | PS5-61-IDH-3100C-CD02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely [OPEN]
T-00610-0251 | PS5-61-IE-0003-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-33/1-05-0211 |  |  |  | TZ-MID-68-WPR2-151105,151107,151108,151111,151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151105,151107,151108,151111,151112-SS Tag on both ends not installed [OPEN]
T-00610-0252 | PS5-61-IG-0006-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151111, 151115, 151117-SS Tag on both ends not installed [OPEN]
T-00610-0253 | PS5-61-IG-0007-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed [OPEN]
T-00610-0254 | PS5-61-IG-0014-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0307 |  |  | TZ-MID-68-WPR2-151112, 151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151111-SS Tag on both ends not installed [OPEN]
T-00610-0255 | PS5-61-IG-0015-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0307 |  |  | TZ-MID-68-WPR2-151112, 151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116-SS Tag on both ends not installed [OPEN]
T-00610-0256 | PS5-61-IG-0016-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | To be completed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151112, 151116 Cable ladder at DB siide to be complete (PS5-61-IG-0016). [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0012, PS5-88-BU-HV-0013, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029) [OPEN] | TZ-MID-68-WPR2-151112, 151116 SS Cable tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151116 Cable dressing to be done both side [OPEN]
T-00610-0257 | PS5-61-IG-0042-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-0042 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151111, 151115, 151117-SS Tag on both ends not installed [CLOSED]
T-00610-0258 | PS5-61-IG-0043-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-0043 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151111, 151115, 151117-SS Tag on both ends not installed [CLOSED]
T-00610-0259 | PS5-61-IJ-0001-CD04 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151167, 151116,151112 Cable Trench Installation not yet done [OPEN] | TZ-MID-68-WPR2-151167, 151116,151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151167, 151116,151112 Dressing to be done at both end [OPEN]
T-00610-0260 | PS5-61-IJ-0001-CD05 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  | TZ-MID-68-WPR2-151167, 151116,151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0029, PS5-88-BU-HV-0017, PS5-88-DU-HV-0004, PS5-88-BU-HV-0013, PS5-88-BU-HV-0012). [OPEN] | TZ-MID-68-WPR2-151167, 151116,151112 SS Cable tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151167, 151116,151112 Cable dressing to be done both side [OPEN]
T-00610-0261 | PS5-61-IJ-0001-CD06 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151116,151112 Cable trench installation to be done [OPEN] | TZ-MID-68-WPR2-151116,151112 Dressing to be done at both end [OPEN]
T-00610-0262 | PS5-61-IJ-0001-CD07 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151116,151112 Cable Trench Not yet complete installation [OPEN] | TZ-MID-68-WPR2-151116,151112 Dressing Cable Both Side to be done [OPEN] ¦ TZ-MID-68-WPR2-151116,151112 Permanent Cable Tag Missing Both End [CLOSED]
T-00610-0263 | PS5-61-IJ-0001-CD24 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151111,151112-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111,151112-Cable dressing not yet done completely [OPEN]
T-00610-0264 | PS5-61-IJ-0001-CD25 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151111,151112-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111,151112-Cable dressing not yet done completely [OPEN]
T-00610-0265 | PS5-61-IJ-0001-CD26 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151111,151112-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111,151112-Cable dressing not yet done completely [OPEN]
T-00610-0266 | PS5-61-IJ-0001-CD27 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151116, 151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116, 151112-SS Tag on both ends not installed [CLOSED]
T-00610-0267 | PS5-61-IJ-0001-CD28 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151116, 151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116, 151112-SS Tag on both ends not installed [CLOSED]
T-00610-0268 | PS5-61-IJ-0001-CD29 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151116, 151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116, 151112-SS Tag on both ends not installed [CLOSED]
T-00610-0269 | PS5-61-IJ-0001-CD30 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151116, 151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116, 151112-SS Tag on both ends not installed [CLOSED]
T-00610-0270 | PS5-61-IJ-0001-CD31 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00610-0271 | PS5-61-IJ-0001-CD32 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00610-0272 | PS5-61-IK-0005-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00610-0273 | PS5-61-IK-0005-CD02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | To be completed
T-00610-0274 | PS5-62-IE-0002-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0307 |  |  | TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed [OPEN]
T-00610-0275 | PS5-71-HE-2200-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-71-12 - CFO Service Tank | To be completed | CPP-RFI-68-331-05-0239 | CPP-RFI-68-331-07-0254 |  | TZ-MID-68-WPR2-151112,151111,151115 Field run cable tray not yet complete installation [OPEN] | TZ-MID-68-WPR2-151112,151111,151115 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115 Dressing to be done at both side [OPEN]
T-00610-0276 | PS5-71-HE-2300-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-71-04 - CFO Storage Tank | To be completed | CPP-RFI-68-33/1-05-0223 |  |  |  | TZ-MID-68-WPR2-151115, TZ-MID-68-WPR2-151112 SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151115, TZ-MID-68-WPR2-151112 Cable Dressing at Both Ends [OPEN]
T-00610-0283 | PS5-71-IES-3400B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-71-13 - CFO Service Pump A/B | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED]
T-00610-0286 | PS5-75-IES-3100A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-75-03 - Corrosion Inhibitor Injection Package | To be completed | CPP-RFI-68-33/1-05-0211 |  |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed [OPEN]
T-00610-0287 | PS5-75-IES-3100B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-75-03 - Corrosion Inhibitor Injection Package | To be completed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed [OPEN]
T-00610-0288 | PS5-75-IES-3200A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-75-02 - Biocide Injection Package | To be completed | CPP-RFI-68-33/1-05-0211 |  |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed [OPEN]
T-00610-0289 | PS5-75-IES-3200B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-75-02 - Biocide Injection Package | To be completed | CPP-RFI-68-33/1-05-0211 |  |  |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed [OPEN]
T-00610-0574 | PS5-60-IE-0004-CD14 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00610-0575 | PS5-60-IE-0004-CD15 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00610-0576 | PS5-60-IE-0004-CD16 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-60-22 - Power Gen Master UCP | To be completed |  | CPP-RFI-68-33/1-07-0405
T-00610-0577 | PS5-61-IE-0002-CD41 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-331-05-0295 | CPP-RFI-68-331-07-0296 |  | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench to be done backfilled, protection tiles, and warning tape installation. [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151167 Permanent SS tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be complete at both side [OPEN]
T-00610-0578 | PS5-61-IE-0002-CD42 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-331-05-0295 | CPP-RFI-68-331-07-0296 |  | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench to be done backfilled, protection tiles, and warning tape installation. [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151167 Permanent SS tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be complete at both side [OPEN]
T-00610-0579 | PS5-61-IE-0002-CD43 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-331-05-0275 | CPP-RFI-68-331-07-0276 |  | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side [OPEN]
T-00610-0580 | PS5-61-IE-0002-CD44 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-331-05-0275 | CPP-RFI-68-331-07-0276 |  | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side [OPEN]
T-00610-0581 | PS5-61-IE-0003-CD02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-331-05-0275 | CPP-RFI-68-331-07-0276 |  | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side [OPEN]
T-00610-0582 | PS5-61-IE-0003-CD03 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-331-05-0275 | CPP-RFI-68-331-07-0276 |  | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side [OPEN]
T-00610-0583 | PS5-61-IE-0003-CD04 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-331-05-0275 | CPP-RFI-68-331-07-0276 |  | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side [OPEN]
T-00610-0584 | PS5-61-IJ-0001-CD61 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0275 | CPP-RFI-68-331-07-0276 |  | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side [OPEN]
T-00610-0585 | PS5-61-IJ-0001-CD62 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0275 | CPP-RFI-68-331-07-0276 |  | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side [OPEN]
T-00610-0586 | PS5-61-IJ-0001-CD63 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0275 | CPP-RFI-68-331-07-0276 |  | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side [OPEN]
T-00610-0587 | PS5-61-IJ-0001-CD64 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0275 | CPP-RFI-68-331-07-0276 |  | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side [OPEN]
T-00610-0588 | PS5-61-IJ-0001-CD65 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0275 | CPP-RFI-68-331-07-0276 |  | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side [OPEN]
T-00610-0589 | PS5-61-IJ-0001-CD66 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0275 | CPP-RFI-68-331-07-0276 |  | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side [OPEN]
T-00610-0590 | PS5-61-IJ-0001-CD67 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | To be completed | CPP-RFI-68-331-05-0275 | CPP-RFI-68-331-07-0276 |  | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side [OPEN]
T-00610-0598 | PS5-61-IE-0002-CD45 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed
T-00610-0599 | PS5-61-IE-0002-CD46 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed
T-00610-0600 | PS5-61-IE-0002-CD47 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed
T-00610-0601 | PS5-61-IE-0002-CD48 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  | TZ-MID-68-WPR2-151112, 151116, 151118 Need additional cable ladder at EITS side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable Trench backfilled , red protection tiles , and warning tape installation not complete [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151118 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00610-0602 | PS5-61-IE-0002-CD49 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  | TZ-MID-68-WPR2-151112, 151116, 151118 Need additional cable ladder at EITS side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable Trench backfilled , red protection tiles , and warning tape installation not complete [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151118 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00610-0603 | PS5-61-IE-0002-CD50 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  | TZ-MID-68-WPR2-151112, 151116, 151118 Need additional cable ladder at EITS side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable Trench backfilled , red protection tiles , and warning tape installation not complete [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151118 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00610-0604 | PS5-61-IE-0002-CD51 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed
T-00610-0605 | PS5-61-IE-0002-CD52 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed
T-00610-0606 | PS5-61-IE-0002-CD53 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed
T-00610-0607 | PS5-61-IE-0002-CD54 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed
T-00610-0608 | PS5-61-IE-0002-CD55 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed
T-00610-0609 | PS5-61-IE-0003-CD11 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  | TZ-MID-68-WPR2-151112, 151116, 151118 Need additional cable ladder at EITS side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable Trench backfilled , red protection tiles , and warning tape installation not complete [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151118 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00610-0610 | PS5-61-IE-0003-CD12 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  | TZ-MID-68-WPR2-151112, 151116, 151118 Need additional cable ladder at EITS side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable Trench backfilled , red protection tiles , and warning tape installation not complete [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151118 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00610-0611 | PS5-61-IE-0003-CD13 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-61-08 - Electrical Control System | To be completed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  | TZ-MID-68-WPR2-151112, 151116, 151118 Need additional cable ladder at EITS side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable Trench backfilled , red protection tiles , and warning tape installation not complete [OPEN] | TZ-MID-68-WPR2-151112, 151116, 151118 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00614-0847 | PS5-01-BI-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-05 - Foam Skid | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0848 | PS5-01-BI-0002-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-10 - Water Mist Package | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  | Doc.TZ-MID-68-WPR2-161507- Cable coiled (135 mtr)Cable tray not yet Installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-0849 | PS5-01-BI-0003-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-10 - Water Mist Package | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  | Doc.TZ-MID-68-WPR2-161507- Cable coiled (135 mtr)Cable tray not yet Installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-0850 | PS5-01-BI-0004-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-10 - Water Mist Package | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0851 | PS5-01-BI-0005-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-05 - Foam Skid | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0852 | PS5-01-BI-0006-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-05 - Foam Skid | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0853 | PS5-01-BI-1117-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0854 | PS5-01-BI-1118-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0041 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-0855 | PS5-01-BI-1501-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-07 - Fire Water Ring Main & Distribution | To be completed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00614-0856 | PS5-01-BI-1515-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0857 | PS5-01-BI-1520-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-10 - Water Mist Package | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-0858 | PS5-01-BI-1571-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0859 | PS5-01-BI-2110-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0860 | PS5-01-BI-2520-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-10 - Water Mist Package | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  | Doc.TZ-MID-68-WPR2-161507- Cable coiled (125 mtr)Cable tray not yet Installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-0861 | PS5-01-BI-2571A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0862 | PS5-01-BI-2571B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-0863 | PS5-01-IE-0002A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-0864 | PS5-01-IE-0002A-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-0865 | PS5-01-IE-0002B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-0866 | PS5-01-IE-0002B-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-01 - Fire Water Jockey Pump A/B | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-0867 | PS5-01-IE-0009A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-02 - Fire Water Pump A | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-0868 | PS5-01-IE-0009A-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-02 - Fire Water Pump A | To be completed
T-00614-0869 | PS5-01-IE-0009B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-03 - Fire Water Pump B | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-0870 | PS5-01-IE-0009B-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-03 - Fire Water Pump B | To be completed
T-00614-0871 | PS5-01-LB-0004-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-11 - Inergen for Power Gen Building | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0872 | PS5-01-LB-0004-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-11 - Inergen for Power Gen Building | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0873 | PS5-01-LB-0004-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-11 - Inergen for Power Gen Building | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0874 | PS5-01-LIT-4201-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-10 - Water Mist Package | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  | Doc.TZ-MID-68-WPR2-161507- Cable coiled (135 mtr)Cable tray not yet Installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-0875 | PS5-01-PIT-0014-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-07 - Fire Water Ring Main & Distribution | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0876 | PS5-01-PIT-0015-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-07 - Fire Water Ring Main & Distribution | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  | Doc.TZ-MID-68-WPR2-161507- Cable coiled (155 mtr)Cable tray not yet Installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-0877 | PS5-01-PIT-0016-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-07 - Fire Water Ring Main & Distribution | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0878 | PS5-01-PIT-0017-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-01-07 - Fire Water Ring Main & Distribution | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0879 | PS5-03-BI-1502-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0880 | PS5-03-BI-1503-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed [OPEN]
T-00614-0881 | PS5-03-BI-1506-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0882 | PS5-03-BI-1507-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-0883 | PS5-03-BI-1508-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0885 | PS5-03-BI-1510-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0886 | PS5-03-BI-1511-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-07 - FZ-07 - Pretreatment Area | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  | Doc.TZ-MID-68-WPR2-161507- Cable coiled (155 mtr)Cable tray not yet Installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-0887 | PS5-03-BI-1512-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  | Doc.TZ-MID-68-WPR2-161507- Cable coiled (85 mtr)Cable tray not yet Installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-0888 | PS5-03-BI-1513-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-RFI-68-64-04-0054 |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-0889 | PS5-03-BI-1514-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed | CPP-RFI-68-64-04-0054 |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-0890 | PS5-03-BI-1516-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | To be completed | CPP-RFI-68-64-04-0049 |  |  | Doc.TZ-MID-68-WPR2-161507- Cable coiled (100 mtr)Cable tray not yet Installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-0891 | PS5-03-BI-2501-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-06 - FZ-06 - Transformer Area | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0894 | PS5-03-BI-2504-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0895 | PS5-03-BI-2505-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0896 | PS5-03-BI-2506-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-0897 | PS5-03-BI-2507-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0898 | PS5-03-BI-2508-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0899 | PS5-03-BI-2509-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0900 | PS5-03-BI-2510-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-03 - FZ-03 - Buildings Area | To be completed
T-00614-0902 | PS5-03-BI-2512-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed [OPEN]
T-00614-0903 | PS5-03-BI-2514-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0054 |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-0904 | PS5-03-BI-2515-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0905 | PS5-03-HS-7002-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-03 - FZ-03 - Buildings Area | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench [OPEN] | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0906 | PS5-03-MTX-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-04-02 - Office Building SIS/FGS System | To be completed
T-00614-0907 | PS5-03-MTX-0001-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-04-02 - Office Building SIS/FGS System | To be completed
T-00614-0908 | PS5-03-MTX-0001-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-04-02 - Office Building SIS/FGS System | To be completed
T-00614-0909 | PS5-03-MTX-0001-CC04 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-04-02 - Office Building SIS/FGS System | To be completed
T-00614-0910 | PS5-03-MTX-0001-CC05 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-04-02 - Office Building SIS/FGS System | To be completed
T-00614-0911 | PS5-03-MTX-0001-CC06 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-04-02 - Office Building SIS/FGS System | To be completed
T-00614-0912 | PS5-03-MTX-0001-CC07 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-04-02 - Office Building SIS/FGS System | To be completed
T-00614-0913 | PS5-03-MTX-0001-CC08 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-04-02 - Office Building SIS/FGS System | To be completed
T-00614-0914 | PS5-03-NMR-0801-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  | Doc.TZ-MID-68-WPR2-161507- Cable coiled (120 mtr)Cable tray not yet Installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-0915 | PS5-03-NMR-0802-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-0916 | PS5-03-NMR-0803-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  | Doc.TZ-MID-68-WPR2-161507- Cable coiled (95 mtr)Cable tray not yet Installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-0917 | PS5-03-NMR-0804-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  | Doc.TZ-MID-68-WPR2-161507- Cable coiled (75 mtr)Cable tray not yet Installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-0918 | PS5-03-RMAC-0120-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-01 - FZ-01 - Process Area | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0919 | PS5-03-RMAC-0824-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  | Doc.TZ-MID-68-WPR2-161507- Cable coiled (15 mtr)Cable tray not yet Installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-0920 | PS5-03-SEA-0002-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-22 - FZ-G1 - Guard House | To be completed | CPP-RFI-68-64-04-0043 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-0921 | PS5-03-SEA-0002-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-22 - FZ-G1 - Guard House | To be completed | CPP-RFI-68-64-04-0037 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0922 | PS5-03-SEA-0003-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  | Doc.TZ-MID-68-WPR2-161507- Cable coiled (270 mtr)Cable tray not yet Installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-0923 | PS5-03-SEA-0003-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0924 | PS5-03-SEA-0005-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00614-0925 | PS5-03-SEA-0005-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-24 - FZ - Office and Facilities Building | To be completed
T-00614-0926 | PS5-03-SEA-0006-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed | CPP-RFI-68-64-04-0043 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-0927 | PS5-03-SEA-0006-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-25 - FZ - Workshop & Warehouse | To be completed | CPP-RFI-68-64-04-0037 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0928 | PS5-05-BI-0002-CC11 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0929 | PS5-05-BI-0002-CC12 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0930 | PS5-05-IE-8100-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-64-04-0049 |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-0931 | PS5-05-IE-8100-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-05-02 - Emergency Diesel Generator Package (UCP) | To be completed | CPP-RFI-68-64-04-0036
T-00614-0932 | PS5-06-GU-0003A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable coiled, Cable tray need to be Installed [CLOSED]
T-00614-0933 | PS5-06-GU-0003B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-06-02 - AC UPS - Power Generator Building | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable coiled, Cable tray need to be Installed [CLOSED]
T-00614-0934 | PS5-09-BI-2501-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-04 - HVAC for Workshop & Warehouse | To be completed | CPP-RFI-68-64-04-0037 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0935 | PS5-09-BI-2502-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-01 - HVAC for Office and Facilities building | To be completed
T-00614-0936 | PS5-09-BI-2503-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-03 - HVAC for Generator Building | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-0937 | PS5-09-LB-0006-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-01 - HVAC for Office and Facilities building | To be completed
T-00614-0938 | PS5-09-LB-0006-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-01 - HVAC for Office and Facilities building | To be completed
T-00614-0939 | PS5-09-LB-0006-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-01 - HVAC for Office and Facilities building | To be completed
T-00614-0940 | PS5-09-LB-0006-CC04 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-01 - HVAC for Office and Facilities building | To be completed
T-00614-0941 | PS5-09-LB-0007-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-04 - HVAC for Workshop & Warehouse | To be completed | CPP-RFI-68-64-04-0037 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0942 | PS5-09-LB-0007-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-04 - HVAC for Workshop & Warehouse | To be completed | CPP-RFI-68-64-04-0043 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-0943 | PS5-09-LB-0007-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-04 - HVAC for Workshop & Warehouse | To be completed | CPP-RFI-68-64-04-0037 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0944 | PS5-09-LB-0007-CC04 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-04 - HVAC for Workshop & Warehouse | To be completed | CPP-RFI-68-64-04-0037 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0945 | PS5-09-LB-0008-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-03 - HVAC for Generator Building | To be completed | CPP-RFI-68-64-04-0043 |  |  | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 275 MTR,Cable tray not yet installed [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-0946 | PS5-09-LB-0008-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-03 - HVAC for Generator Building | To be completed | CPP-RFI-68-64-04-0043 |  |  | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 275 MTR ,Cable tray not yet installed [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-0947 | PS5-09-LB-0008-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-03 - HVAC for Generator Building | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-0948 | PS5-09-LB-0008-CC04 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-03 - HVAC for Generator Building | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0949 | PS5-09-LB-0008-CC05 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-03 - HVAC for Generator Building | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0950 | PS5-09-LB-0008-CC06 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-03 - HVAC for Generator Building | To be completed | CPP-RFI-68-64-04-0043 |  |  | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 260 MTR,Cable tray not yet installed [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-0951 | PS5-09-LB-0008-CC07 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-03 - HVAC for Generator Building | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0952 | PS5-09-LB-0008-CC08 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-03 - HVAC for Generator Building | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0953 | PS5-25-BI-1101-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0954 | PS5-25-BI-1102-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0041 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-0957 | PS5-25-BI-1115-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0958 | PS5-25-BI-1174A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0959 | PS5-25-BI-1174B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0960 | PS5-25-BI-1174C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-0961 | PS5-25-BI-1201-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0962 | PS5-25-BI-1274A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0963 | PS5-25-BI-1274B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0964 | PS5-25-BI-1274C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0965 | PS5-25-BI-1301-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0966 | PS5-25-BI-1302-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0967 | PS5-25-BI-1310-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | Started (not Completed) | CPP-RFI-68-64-04-0054 |  | CPP-RFI-68-64-11-0067 |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-0968 | PS5-25-BI-1801A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-0969 | PS5-25-BI-1801B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0970 | PS5-25-BI-1801C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0971 | PS5-25-BI-1802A-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0972 | PS5-25-BI-1802B-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0973 | PS5-25-BI-1802C-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0974 | PS5-25-BI-1803A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0975 | PS5-25-BI-1803A-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0976 | PS5-25-BI-1803B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0977 | PS5-25-BI-1803B-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0978 | PS5-25-BI-1803C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0979 | PS5-25-BI-1803C-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0980 | PS5-25-BI-2101-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0981 | PS5-25-BI-2102-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0982 | PS5-25-BI-2103-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0041 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-0983 | PS5-25-BI-2104-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0984 | PS5-25-BI-2105-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0985 | PS5-25-BI-2106-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0988 | PS5-25-BI-2201-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0989 | PS5-25-BI-2203-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0041 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-0990 | PS5-25-BI-2205-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-01 - Export Pipeline Pig Receiver | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0991 | PS5-25-BI-2301-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0992 | PS5-25-BI-2302-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0993 | PS5-25-BI-2305-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0048 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0995 | PS5-25-BI-2309-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0048 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0999 | PS5-25-MXS-3101AA-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1000 | PS5-25-MXS-3101AB-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1001 | PS5-25-MXS-3101BA-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1002 | PS5-25-MXS-3101BB-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1003 | PS5-25-MXS-3101CA-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1004 | PS5-25-MXS-3101CB-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1005 | PS5-25-PIT-0052-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1006 | PS5-25-PIT-0071A-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1007 | PS5-25-PIT-0071B-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1008 | PS5-25-PIT-0071C-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1009 | PS5-25-SDV-0052-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1010 | PS5-25-SDV-0052-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1011 | PS5-25-SHSR-0052-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1012 | PS5-25-SXS-0052-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1013 | PS5-25-SY-0052A-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-07 - Export Pipeline Pig Launcher | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1014 | PS5-28-BI-1105-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0041 | CPP-RFI-68-64-12-0048 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-1015 | PS5-28-BI-1106-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-28-06 - Relief Drum and Pump | To be completed | CPP-RFI-68-64-04-0037 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1016 | PS5-28-BI-1114-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-28-04 - Closed Drain Drum and Pump 02 | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  | Doc.TZ-MID-68-WPR2-161507- Cable coiled (155 mtr)Cable tray not yet Installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-1017 | PS5-28-BI-1303-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0048 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1018 | PS5-28-BI-1307-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0048 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1019 | PS5-28-BI-2304-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-28-17 - Reinjection Pump | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-1020 | PS5-28-HXA-1101-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-28-03 - Closed Drain Drum and Pump 01 | To be completed | CPP-RFI-68-64-04-0037 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1021 | PS5-28-LB-8200-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-28-11 - Open Drain Interceptor | To be completed | CPP-RFI-68-64-04-0037 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1022 | PS5-28-LB-8200-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-28-11 - Open Drain Interceptor | To be completed | CPP-RFI-68-64-04-0037 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1023 | PS5-50-BI-1107-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0048 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1024 | PS5-50-IE-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-50-01 - Water Well Submersible Pumps (3100) | To be completed | CPP-RFI-68-64-04-0037 | CPP-RFI-68-64-12-0073 |  | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1025 | PS5-50-IE-0001-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-50-01 - Water Well Submersible Pumps (3100) | To be completed | CPP-RFI-68-64-04-0037 | CPP-RFI-68-64-12-0073 |  | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1026 | PS5-50-IE-0002-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-50-02 - Water Well Submersible Pumps (3200) | To be completed | CPP-RFI-68-64-04-0043 | CPP-RFI-68-64-12-0055 |  | Doc.TZ-MID-68-WPR2-161500 - Cable coiled 550mtr,Cable to be laid in trench [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-1027 | PS5-50-IE-0002-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-50-02 - Water Well Submersible Pumps (3200) | To be completed | CPP-RFI-68-64-04-0043 | CPP-RFI-68-64-12-0055 |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable coiled 550mtr,Cable to be laid in trench [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1028 | PS5-50-LIT-0001-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-50-01 - Water Well Submersible Pumps (3100) | To be completed | CPP-RFI-68-64-04-0037
T-00614-1029 | PS5-50-LIT-0002-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-50-02 - Water Well Submersible Pumps (3200) | To be completed
T-00614-1030 | PS5-53-BI-1108-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0048 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1032 | PS5-53-LA-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-53-04 - Water Treatment Purification Package | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1033 | PS5-53-LA-0001-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-53-04 - Water Treatment Purification Package | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-1034 | PS5-60-IE-0003A-CC21 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1035 | PS5-60-IE-0003A-CC22 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1036 | PS5-60-IE-0003A-CC23 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1037 | PS5-60-IE-0003A-CC24 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-02 - Power Gen Package A (UCP) | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1038 | PS5-60-IE-0003B-CC21 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1039 | PS5-60-IE-0003B-CC22 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-1040 | PS5-60-IE-0003B-CC23 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-1041 | PS5-60-IE-0003B-CC24 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-05 - Power Gen Package B (UCP) | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1042 | PS5-60-IE-0003C-CC21 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed | CPP-RFI-68-64-04-0043 |  |  | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 95 MTR ,Cable tray not yet installed [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-1043 | PS5-60-IE-0003C-CC22 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed | CPP-RFI-68-64-04-0043 |  |  | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 95 MTR ,Cable tray not yet installed [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-1044 | PS5-60-IE-0003C-CC23 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-1045 | PS5-60-IE-0003C-CC24 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-08 - Power Gen Package C (UCP) | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-1046 | PS5-60-IE-0003D-CC21 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed | CPP-RFI-68-64-04-0043 |  |  | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 95 MTR ,Cable tray not yet installed [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-1047 | PS5-60-IE-0003D-CC22 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed | CPP-RFI-68-64-04-0043 |  |  | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 95 MTR ,Cable tray not yet installed [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-1048 | PS5-60-IE-0003D-CC23 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-1049 | PS5-60-IE-0003D-CC24 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-11 - Power Gen Package D (UCP) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-1050 | PS5-60-IE-0003E-CC21 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed | CPP-RFI-68-64-04-0043 |  |  | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 95 MTR ,Cable tray not yet installed [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-1051 | PS5-60-IE-0003E-CC22 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed | CPP-RFI-68-64-04-0049 |  |  | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 95 MTR ,Cable tray not yet installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507- Cable coiled (85 mtr)Cable tray not yet Installed [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-1052 | PS5-60-IE-0003E-CC23 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-1053 | PS5-60-IE-0003E-CC24 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-14 - Power Gen Package E (UCP) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1054 | PS5-60-IE-0003F-CC21 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed | CPP-RFI-68-64-04-0043 |  |  | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 95 MTR ,Cable tray not yet installed [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-1055 | PS5-60-IE-0003F-CC22 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1056 | PS5-60-IE-0003F-CC23 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1057 | PS5-60-IE-0003F-CC24 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-17 - Power Gen Package F (UCP) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-1058 | PS5-60-IE-0003G-CC21 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1059 | PS5-60-IE-0003G-CC22 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1060 | PS5-60-IE-0003G-CC23 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-1061 | PS5-60-IE-0003G-CC24 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-20 - Power Gen Package G (UCP) | To be completed | CPP-RFI-68-64-04-0036 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-1062 | PS5-60-IE-0004-CC08 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-RFI-68-64-04-0054 |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-1063 | PS5-60-IE-0004-CC11 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1064 | PS5-60-IE-0004-CC12 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-60-22 - Power Gen Master UCP | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1065 | PS5-60-SEA-0001-CC18 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1066 | PS5-61-IDH-3100A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1067 | PS5-61-IDH-3100A-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1068 | PS5-61-IDH-3100A-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1069 | PS5-61-IDH-3100B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1070 | PS5-61-IDH-3100B-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-1071 | PS5-61-IDH-3100B-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-1072 | PS5-61-IDH-3100C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-1073 | PS5-61-IDH-3100C-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00614-1074 | PS5-61-IDH-3100C-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0036
T-00614-1075 | PS5-71-BI-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-02 - CFO Allocation Metering Package | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1076 | PS5-71-BI-0021-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-02 - CFO Allocation Metering Package | To be completed | CPP-RFI-68-64-04-0036
T-00614-1077 | PS5-71-BI-0021-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-02 - CFO Allocation Metering Package | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-1078 | PS5-71-BI-1109-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0041 | CPP-RFI-68-64-12-0048 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1080 | PS5-71-BI-1111-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1081 | PS5-71-BI-1112-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-17 - Diesel Fuel Distribution Header | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-1082 | PS5-71-BI-1113-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1084 | PS5-71-BI-1117-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1086 | PS5-71-BI-1305-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0041 | CPP-RFI-68-64-12-0048 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-1088 | PS5-71-BI-1308-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-15 - Diesel Fuel Storage Tank | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed [OPEN]
T-00614-1089 | PS5-71-BI-2107-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0048 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1090 | PS5-71-BI-2113-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1091 | PS5-71-BI-2114-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1092 | PS5-71-BI-2115-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1093 | PS5-71-BI-2116-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1094 | PS5-71-BI-2118-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0043 | CPP-RFI-68-64-12-0055 |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 -Cable coiled (130 MTR ),Cable tray not yet installed [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-1095 | PS5-71-BI-2119-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0043 | CPP-RFI-68-64-12-0055 |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 -Cable coiled (100 MTR ),Cable tray not yet installed [OPEN] | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-1096 | PS5-71-BI-2120-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0043 | CPP-RFI-68-64-12-0055 |  | Doc.TZ-MID-68-WPR2-161500 -Cable coiled (180 MTR ),Cable tray not yet installed [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-1097 | PS5-71-BI-2121-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0043 | CPP-RFI-68-64-12-0055 |  | Doc.TZ-MID-68-WPR2-161500 - Cable coiled 155mtr,Cable tray not yet installed [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-1098 | PS5-71-BI-2122-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1099 | PS5-71-BI-2123-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1100 | PS5-71-BI-2124-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1101 | PS5-71-BI-2125-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1102 | PS5-71-BI-2306-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1103 | PS5-71-BI-2307-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-15 - Diesel Fuel Storage Tank | To be completed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed [OPEN]
T-00614-1104 | PS5-71-BI-2310-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | To be completed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1105 | PS5-71-BI-2313-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-15 - Diesel Fuel Storage Tank | To be completed |  |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed [OPEN]
T-00614-1108 | PS5-71-IN-0001-CC08 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-19 - Diesel Separator Module (UCP) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-1109 | PS5-71-IN-0001-CC09 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-19 - Diesel Separator Module (UCP) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1110 | PS5-71-IN-0001-CC10 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-19 - Diesel Separator Module (UCP) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1111 | PS5-71-IN-0002-CC05 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1112 | PS5-71-IN-0002-CC06 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1113 | PS5-71-IN-0002-CC07 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1114 | PS5-71-IN-0003-CC05 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1115 | PS5-71-IN-0003-CC06 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1116 | PS5-71-IN-0003-CC07 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1117 | PS5-71-IN-0004A-CC08 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1118 | PS5-71-IN-0004A-CC09 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1119 | PS5-71-IN-0004A-CC12 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1120 | PS5-71-IN-0004B-CC08 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1121 | PS5-71-IN-0004B-CC09 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1122 | PS5-71-IN-0004B-CC12 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-1123 | PS5-71-TIT-2403A-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1124 | PS5-71-TIT-2403B-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-01 - CFO Storage Tank Feed Heater | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1125 | PS5-74-LB-5101-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-74-02 - N2 Generation Skid (UCP) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1126 | PS5-74-LB-5101-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-74-02 - N2 Generation Skid (UCP) | To be completed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1127 | PS5-75-BI-1177-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-75-02 - Biocide Injection Package | To be completed | CPP-RFI-68-64-04-0037 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1128 | PS5-75-BI-1178-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-75-03 - Corrosion Inhibitor Injection Package | To be completed | CPP-RFI-68-64-04-0037 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1129 | PS5-75-BI-1371-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-75-02 - Biocide Injection Package | To be completed | CPP-RFI-68-64-04-0037 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1130 | PS5-75-BI-1372-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-75-03 - Corrosion Inhibitor Injection Package | To be completed | CPP-RFI-68-64-04-0037 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1131 | PS5-75-BI-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-75-01 - DRA Injection Package | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-1132 | PS5-75-BI-0002-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-75-01 - DRA Injection Package | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-1133 | PS5-75-BI-0002-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-75-01 - DRA Injection Package | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-1134 | PS5-75-BI-0002-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-75-01 - DRA Injection Package | To be completed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00614-1135 | PS5-75-MOV-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-28-07 - Open Drains (OD2) | To be completed | CPP-RFI-68-64-04-0037 | CPP-RFI-68-64-12-0073 |  | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1136 | PS5-75-MOV-0001-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-28-07 - Open Drains (OD2) | To be completed | CPP-RFI-68-64-04-0037 | CPP-RFI-68-64-12-0073 |  | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1137 | PS5-79-IG-0001-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1138 | PS5-79-IG-0002-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | To be completed | CPP-RFI-68-64-04-0038 |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1139 | PS5-79-IG-0003-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1140 | PS5-79-IG-0004-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1141 | PS5-79-IG-0005-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1142 | PS5-79-IG-0006-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1143 | PS5-79-IG-0007-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1144 | PS5-79-IG-0008-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1145 | PS5-79-IG-0009-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1146 | PS5-79-IG-0010-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1147 | PS5-79-IG-0011-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073
T-00614-1148 | PS5-79-IG-0012-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1149 | PS5-83-EHO-0001A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1150 | PS5-83-EHO-0001A-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-02 - Crude Oil Export Pump A | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1151 | PS5-83-EHO-0001B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1152 | PS5-83-EHO-0001B-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-03 - Crude Oil Export Pump B | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1153 | PS5-83-EHO-0001C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1154 | PS5-83-EHO-0001C-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-25-04 - Crude Oil Export Pump C | To be completed | CPP-RFI-68-64-04-0038 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-2626 | PS5-09-BI-2504-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-01 - HVAC for Office and Facilities building | To be completed
T-00614-2627 | PS5-09-LB-0006-CC05 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-09-01 - HVAC for Office and Facilities building | To be completed
T-00614-2628 | PS5-50-IE-0001-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-50-01 - Water Well Submersible Pumps (3100) | To be completed |  |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-2629 | PS5-50-IE-0002-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-50-02 - Water Well Submersible Pumps (3200) | To be completed |  |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable coiled 550mtr,Cable to be laid in trench [OPEN] | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-2630 | PS5-74-LB-5101-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-74-02 - N2 Generation Skid (UCP) | To be completed |  |  |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00618-0217 | PS5-08-11CB-1201-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-11 - Corporate LAN (SIE) | To be completed
T-00618-0218 | PS5-08-11CB-1501-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-11 - Corporate LAN (SIE) | To be completed | CPP-RFI-68-65-05-0036
T-00618-0219 | PS5-08-11CB-1601-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-11 - Corporate LAN (SIE) | To be completed
T-00618-0220 | PS5-08-11CB-1901-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-11 - Corporate LAN (SIE) | To be completed
T-00618-0221 | PS5-08-12BT-0001-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00618-0222 | PS5-08-12BT-0104-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed | CPP-RFI-68-65-05-0028
T-00618-0223 | PS5-08-12BT-0105-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00618-0224 | PS5-08-12BT-0106-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00618-0225 | PS5-08-12BT-0107-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed | CPP-RFI-68-65-05-0036 |  |  |  | Doc. TZ-MID-68-WPR2-151166,TZ-MID-68-WPR2-171120 Cable Need to Be Dressing at Both Ends [OPEN]
T-00618-0226 | PS5-08-12BT-0108-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed | CPP-RFI-68-65-05-0036 |  |  |  | Doc. TZ-MID-68-WPR2-151166,TZ-MID-68-WPR2-171120 Cable Need to Be Dressing at Both Ends [OPEN]
T-00618-0227 | PS5-08-12BT-0109-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00618-0228 | PS5-08-12BT-1903-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00618-0229 | PS5-08-12BT-1904-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00618-0230 | PS5-08-15CP-0001-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | To be completed
T-00618-0231 | PS5-08-15CP-0002-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | To be completed | CPP-RFI-68-65-05-0023
T-00618-0232 | PS5-08-15CP-0003-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | To be completed
T-00618-0233 | PS5-08-15CP-0004-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | To be completed
T-00618-0234 | PS5-08-15CP-0005-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | To be completed
T-00618-0235 | PS5-08-15CP-0005-CX02 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | To be completed
T-00618-0236 | PS5-08-15CP-0006-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | To be completed
T-00618-0237 | PS5-08-15CP-0007-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | To be completed
T-00618-0238 | PS5-08-15CP-0008-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | To be completed
T-00618-0239 | PS5-08-36SP-0101-CX02 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-36 - Pipeline FO Cable & EPRS | To be completed
T-00618-0240 | PS5-08-36SP-0102-CX02 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-36 - Pipeline FO Cable & EPRS | To be completed
T-00618-0241 | PS5-08-52CM-0131-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed | CPP-RFI-68-65-05-0027 |  |  |  | TZ-MID-68-WPR2-171143. Cable Tagging not yet Install, Both Ends (Below EITS & CCTV at VSD) [OPEN] ¦ TZ-MID-68-WPR2-171143. Cable need to be Dressing Both Ends, (Below EITS & CCTV at VSD) [OPEN]
T-00618-0242 | PS5-08-52CM-0132-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed |  |  |  | TZ-MID-68-WPR2-171143. Cable not yet finish to Their Final Destination (94 MTR - COILED near VSD) need open trench, sand bedding, laying the cables to final destination (CCTV), backfilling with clean sand, protection tiles, warning tape, backfilling again & compaction [OPEN] | TZ-MID-68-WPR2-171143. Cable Tagging not yet Install, Below EITS & CCTV at Observation area) [OPEN] ¦ TZ-MID-68-WPR2-171143. Cable need to be Dressing Both Ends, (Below EITS & CCTV at VSD) [OPEN]
T-00618-0243 | PS5-08-52CM-0133-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed | CPP-RFI-68-65-05-0036 |  |  |  | Doc. TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-171120, Cable Need to be Dressing at Both Ends [OPEN]
T-00618-0244 | PS5-08-52CM-0135-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00618-0245 | PS5-08-52CM-0136-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00618-0246 | PS5-08-52CM-0138-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00618-0247 | PS5-08-52CM-0139-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00618-0248 | PS5-08-83SP-0001-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-83 - Perimeter & Pipeline intrusion detection system | To be completed
T-00618-0249 | PS5-08-83SP-0001-CX02 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-83 - Perimeter & Pipeline intrusion detection system | To be completed
T-00618-0250 | PS5-08-85CP-0024-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00618-0251 | PS5-08-85CP-0024-CX02 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00618-0252 | PS5-08-85CP-0025-CX01 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00618-0253 | PS5-08-85CP-0025-CX02 | CIX55a - Fiber Optic Cable (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-2796 | PS5-08-01BT-0001-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2797 | PS5-08-01BT-0001-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2798 | PS5-08-01BT-0002-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2799 | PS5-08-01BT-0002-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2800 | PS5-08-01BT-0003-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2801 | PS5-08-01BT-0003-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2802 | PS5-08-01BT-0004-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2803 | PS5-08-01BT-0004-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2804 | PS5-08-01BT-1201-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2805 | PS5-08-01BT-1201-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed |  | CPP-RFI-68-65-20-0035
T-00621-2806 | PS5-08-01BT-1201-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2807 | PS5-08-01BT-1201-CR03 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2808 | PS5-08-01BT-1202-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2809 | PS5-08-01BT-1202-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed |  | CPP-RFI-68-65-20-0035
T-00621-2810 | PS5-08-01BT-1202-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed |  | CPP-RFI-68-65-20-0035
T-00621-2811 | PS5-08-01BT-1202-CR03 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2812 | PS5-08-01BT-1203-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2813 | PS5-08-01BT-1203-CJ02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed |  | CPP-RFI-68-65-20-0035
T-00621-2814 | PS5-08-01BT-1203-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2815 | PS5-08-01BT-1203-CN02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2816 | PS5-08-01BT-1501-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2817 | PS5-08-01BT-1501-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2818 | PS5-08-01BT-1502-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2819 | PS5-08-01BT-1502-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2820 | PS5-08-01BT-1503-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed |  | CPP-RFI-68-65-20-0035
T-00621-2821 | PS5-08-01BT-1503-CJ02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed |  | CPP-RFI-68-65-20-0035
T-00621-2822 | PS5-08-01BT-1503-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2823 | PS5-08-01BT-1503-CN02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2824 | PS5-08-01BT-1601-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2825 | PS5-08-01BT-1601-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed |  | CPP-RFI-68-65-20-0035
T-00621-2826 | PS5-08-01BT-1602-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2827 | PS5-08-01BT-1602-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed |  | CPP-RFI-68-65-20-0035
T-00621-2828 | PS5-08-01BT-1901-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2829 | PS5-08-01BT-1901-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0034 | CPP-RFI-68-65-20-0035 |  |  | Doc. TZ-MID-68-WPR2-171100, TZ-MID-68-WPR2-171166 - Cable Need to Be Dressing at Both Ends []
T-00621-2830 | PS5-08-01BT-1902-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2835 | PS5-08-01LS-0102-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Trench not yet complete from EITS to PS5-08-01LS-0102 [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2836 | PS5-08-01LS-0103-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2837 | PS5-08-01LS-0104-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2838 | PS5-08-01LS-0105-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2839 | PS5-08-01LS-0106-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2840 | PS5-08-01LS-0107-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2841 | PS5-08-01LS-0108-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2842 | PS5-08-01LS-0109-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2843 | PS5-08-01LS-0110-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end [OPEN] ¦ TZ-MID-68-WPR2-171173 Cable coiled, need to be la.id in trench at PS5-08-01LS-0110 side (Est. 20 Mtr) [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2844 | PS5-08-01LS-0110-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Cable coiled, need to be laid in trench at PS5-08-01LS-0110 side (Est. 20 Mtr) [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2846 | PS5-08-01LS-0202-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2847 | PS5-08-01LS-0203-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2848 | PS5-08-01LS-0204-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2849 | PS5-08-01LS-0205-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2850 | PS5-08-01LS-0206-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2851 | PS5-08-01LS-0207-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2852 | PS5-08-01LS-0208-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2853 | PS5-08-01LS-0209-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2854 | PS5-08-01LS-0210-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2855 | PS5-08-01LS-0211-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2856 | PS5-08-01LS-0211-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2857 | PS5-08-01LS-0301-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Cable Coil, Need to Open Trench at PS5-08-01LS-0301 side (Est. 20Mtr) [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2858 | PS5-08-01LS-0302-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Cable Coil, Need to Open Trench at PS5-08-01LS-0301 side (Est. 20Mtr). [OPEN] ¦ TZ-MID-68-WPR2-171173 Cable Coil, Need to Open Trench at PS5-08-01LS-0302 side (Est. 5Mtr). [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2859 | PS5-08-01LS-0303-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Cable Coil, Need to Open Trench at PS5-08-01LS-0302 side (Est. 5Mtr). [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2860 | PS5-08-01LS-0304-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2861 | PS5-08-01LS-0305-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2862 | PS5-08-01LS-0306-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2863 | PS5-08-01LS-0307-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0034 | CPP-RFI-68-65-20-0035 |  |  | Doc. TZ-MID-68-WPR2-171100 - Cable Need to Be Dressing at Both Ends []
T-00621-2864 | PS5-08-01LS-0308-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2865 | PS5-08-01LS-0309-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2866 | PS5-08-01LS-0310-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2867 | PS5-08-01LS-0310-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2868 | PS5-08-01LS-0318-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2871 | PS5-08-01LS-0403-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Cable Coil, Need to open cable trench est.60 mtr at PS5-08-01LS-0403 Side [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2872 | PS5-08-01LS-0404-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0034 | CPP-RFI-68-65-20-0035 |  |  | Doc. TZ-MID-68-WPR2-171100 - Cable Need to Be Dressing at Both Ends []
T-00621-2874 | PS5-08-01LS-0406-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2875 | PS5-08-01LS-0407-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2876 | PS5-08-01LS-0408-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2877 | PS5-08-01LS-0409-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2878 | PS5-08-01LS-0410-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2879 | PS5-08-01LS-0411-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2880 | PS5-08-01LS-0411-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  | TZ-MID-68-WPR2-171173 Cable trench installation outstanding [OPEN] | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2881 | PS5-08-01LS-0418-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2882 | PS5-08-01LS-0501-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2883 | PS5-08-01LS-0502-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2884 | PS5-08-01LS-0503-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2885 | PS5-08-01LS-0504-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2886 | PS5-08-01LS-0505-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2887 | PS5-08-01LS-0506-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2888 | PS5-08-01LS-0507-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2889 | PS5-08-01LS-0508-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2890 | PS5-08-01LS-0509-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2891 | PS5-08-01LS-0510-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2892 | PS5-08-01LS-0511-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2893 | PS5-08-01LS-0512-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2894 | PS5-08-01LS-0517-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2895 | PS5-08-01LS-0518-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2896 | PS5-08-01LS-0519-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2897 | PS5-08-01LS-0520-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2898 | PS5-08-01LS-0521-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2899 | PS5-08-01LS-0522-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2900 | PS5-08-01LS-0522-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2901 | PS5-08-01LS-0523-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2902 | PS5-08-01LS-0524-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2903 | PS5-08-01LS-0525-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2904 | PS5-08-01LS-0526-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2905 | PS5-08-01LS-0527-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2906 | PS5-08-01LS-0528-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2907 | PS5-08-01LS-0529-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2908 | PS5-08-01LS-0530-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2909 | PS5-08-01LS-0530-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2910 | PS5-08-01LS-0601-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2911 | PS5-08-01LS-0602-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2912 | PS5-08-01LS-0603-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2913 | PS5-08-01LS-0604-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2914 | PS5-08-01LS-0605-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2915 | PS5-08-01LS-0606-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2916 | PS5-08-01LS-0607-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2917 | PS5-08-01LS-0608-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2918 | PS5-08-01LS-0609-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2919 | PS5-08-01LS-0610-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2920 | PS5-08-01LS-0611-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2921 | PS5-08-01LS-0612-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2922 | PS5-08-01LS-0617-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2923 | PS5-08-01LS-0618-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2924 | PS5-08-01LS-0619-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2925 | PS5-08-01LS-0620-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2926 | PS5-08-01LS-0621-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2927 | PS5-08-01LS-0621-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2928 | PS5-08-01LS-0622-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2929 | PS5-08-01LS-0623-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2930 | PS5-08-01LS-0624-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2931 | PS5-08-01LS-0625-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2932 | PS5-08-01LS-0626-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2933 | PS5-08-01LS-0627-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2934 | PS5-08-01LS-0628-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2935 | PS5-08-01LS-0629-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2936 | PS5-08-01LS-0629-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2937 | PS5-08-01LS-0701-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2938 | PS5-08-01LS-0702-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2939 | PS5-08-01LS-0703-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2940 | PS5-08-01LS-0704-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2941 | PS5-08-01LS-0705-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2942 | PS5-08-01LS-0706-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2943 | PS5-08-01LS-0707-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2944 | PS5-08-01LS-0708-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2945 | PS5-08-01LS-0709-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2946 | PS5-08-01LS-0710-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2947 | PS5-08-01LS-0711-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2948 | PS5-08-01LS-0712-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2949 | PS5-08-01LS-0713-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2950 | PS5-08-01LS-0714-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2951 | PS5-08-01LS-0715-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2952 | PS5-08-01LS-0716-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2953 | PS5-08-01LS-0716-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2954 | PS5-08-01LS-0717-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2955 | PS5-08-01LS-0718-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2956 | PS5-08-01LS-0719-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2957 | PS5-08-01LS-0720-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2958 | PS5-08-01LS-0721-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2959 | PS5-08-01LS-0722-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2960 | PS5-08-01LS-0723-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2961 | PS5-08-01LS-0724-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2962 | PS5-08-01LS-0725-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2963 | PS5-08-01LS-0726-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2964 | PS5-08-01LS-0727-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2965 | PS5-08-01LS-0728-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2966 | PS5-08-01LS-0729-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2967 | PS5-08-01LS-0730-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2968 | PS5-08-01LS-0731-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2969 | PS5-08-01LS-0732-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2970 | PS5-08-01LS-0733-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2971 | PS5-08-01LS-0733-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2972 | PS5-08-01LS-0801-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2973 | PS5-08-01LS-0802-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2974 | PS5-08-01LS-0803-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2975 | PS5-08-01LS-0804-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2976 | PS5-08-01LS-0805-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2977 | PS5-08-01LS-0806-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2978 | PS5-08-01LS-0807-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2979 | PS5-08-01LS-0808-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2980 | PS5-08-01LS-0809-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2981 | PS5-08-01LS-0810-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2982 | PS5-08-01LS-0811-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2983 | PS5-08-01LS-0812-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2984 | PS5-08-01LS-0813-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2985 | PS5-08-01LS-0814-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2986 | PS5-08-01LS-0815-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2987 | PS5-08-01LS-0816-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2988 | PS5-08-01LS-0816-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2989 | PS5-08-01LS-0817-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2990 | PS5-08-01LS-0818-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2991 | PS5-08-01LS-0819-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2992 | PS5-08-01LS-0820-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2993 | PS5-08-01LS-0821-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2994 | PS5-08-01LS-0822-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2995 | PS5-08-01LS-0823-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2996 | PS5-08-01LS-0824-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2997 | PS5-08-01LS-0825-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2998 | PS5-08-01LS-0826-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-2999 | PS5-08-01LS-0827-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-3000 | PS5-08-01LS-0828-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-3001 | PS5-08-01LS-0829-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-3002 | PS5-08-01LS-0830-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-3003 | PS5-08-01LS-0831-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-3004 | PS5-08-01LS-0832-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-3005 | PS5-08-01LS-0833-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-3006 | PS5-08-01LS-0834-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-3007 | PS5-08-01LS-0834-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-3012 | PS5-08-01OC-0001-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed |  | CPP-RFI-68-65-20-0035
T-00621-3013 | PS5-08-01OC-0001-CJ02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed |  | CPP-RFI-68-65-20-0035
T-00621-3014 | PS5-08-01OC-0001-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed |  | CPP-RFI-68-65-20-0035
T-00621-3015 | PS5-08-01OC-0001-CN02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed |  | CPP-RFI-68-65-20-0035
T-00621-3016 | PS5-08-01OC-0002-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-3017 | PS5-08-01OC-0002-CJ02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-3018 | PS5-08-01OC-0002-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-3019 | PS5-08-01OC-0002-CN02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-3020 | PS5-08-01PA-1201-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-3021 | PS5-08-01PA-1201-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-3022 | PS5-08-01PA-1501-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-3023 | PS5-08-01PA-1501-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00621-3025 | PS5-08-03TP-0001-CJ02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | To be completed
T-00621-3026 | PS5-08-03TP-0002-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | To be completed
T-00621-3027 | PS5-08-03TP-0002-CJ02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | To be completed
T-00621-3028 | PS5-08-03TP-0003-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | To be completed
T-00621-3029 | PS5-08-03TP-0003-CJ02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | To be completed
T-00621-3030 | PS5-08-03TP-0004-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | To be completed
T-00621-3031 | PS5-08-03TP-0004-CJ02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | To be completed
T-00621-3032 | PS5-08-03TP-0101-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | To be completed
T-00621-3033 | PS5-08-03TP-0101-CJ02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | To be completed
T-00621-3034 | PS5-08-03TP-0102-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | To be completed
T-00621-3035 | PS5-08-03TP-0102-CJ02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | To be completed
T-00621-3037 | PS5-08-03TP-0103-CJ02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | To be completed
T-00621-3038 | PS5-08-03TP-1903-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | To be completed
T-00621-3039 | PS5-08-03TP-1903-CJ02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | To be completed
T-00621-3040 | PS5-08-03TP-1904-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | To be completed
T-00621-3041 | PS5-08-03TP-1904-CJ02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | To be completed
T-00621-3047 | PS5-08-12AP-0001-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00621-3048 | PS5-08-12AP-0002-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00621-3049 | PS5-08-12AP-0003-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00621-3050 | PS5-08-12AP-0101-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00621-3051 | PS5-08-12AP-0103-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00621-3052 | PS5-08-12AP-0104-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00621-3053 | PS5-08-12AP-0105-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00621-3054 | PS5-08-12AP-0106-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00621-3055 | PS5-08-12AP-0107-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00621-3056 | PS5-08-12AP-0108-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00621-3057 | PS5-08-12AP-0109-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00621-3058 | PS5-08-12AP-1903-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00621-3059 | PS5-08-12AP-1904-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00621-3060 | PS5-08-12BT-0002-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00621-3061 | PS5-08-12BT-0003-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00621-3062 | PS5-08-12BT-0101-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed | CPP-RFI-68-65-05-0036 |  |  | Doc. Doc. TZ-MID-68-WPR2-151166,TZ-MID-68-WPR2-171120, Field Run Cable Tray need to Install at Wap Junction Box Side [OPEN] | Doc. TZ-MID-68-WPR2-151166,TZ-MID-68-WPR2-171120 Cable Need to Be Dressing at Both Ends [OPEN]
T-00621-3063 | PS5-08-12BT-0103-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00621-3064 | PS5-08-13CB-1201-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | To be completed
T-00621-3065 | PS5-08-13CB-1201-CA02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | To be completed
T-00621-3066 | PS5-08-13CB-1201-CA03 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | To be completed
T-00621-3067 | PS5-08-13CB-1201-CA04 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | To be completed
T-00621-3068 | PS5-08-13CB-1201-CA05 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | To be completed
T-00621-3069 | PS5-08-13CB-1201-CA06 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | To be completed
T-00621-3070 | PS5-08-13CB-1201-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-93 - Telecom Monitoring System | To be completed
T-00621-3071 | PS5-08-13CB-1201-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | To be completed
T-00621-3072 | PS5-08-14CB-1201-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-14 - Industrial Data Network (SII SP1) | To be completed
T-00621-3073 | PS5-08-14CB-1201-CA02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-14 - Industrial Data Network (SII SP1) | To be completed
T-00621-3074 | PS5-08-14CB-1201-CA03 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-14 - Industrial Data Network (SII SP1) | To be completed
T-00621-3075 | PS5-08-14CB-1201-CA04 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-14 - Industrial Data Network (SII SP1) | To be completed
T-00621-3076 | PS5-08-14CB-1201-CA05 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-14 - Industrial Data Network (SII SP1) | To be completed
T-00621-3077 | PS5-08-14CB-1201-CA06 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-14 - Industrial Data Network (SII SP1) | To be completed
T-00621-3078 | PS5-08-23AN-0001-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-23 - VHF Trunk Radio System | To be completed
T-00621-3079 | PS5-08-23AN-0002-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-23 - VHF Trunk Radio System | To be completed
T-00621-3080 | PS5-08-23AN-0003-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-23 - VHF Trunk Radio System | To be completed
T-00621-3081 | PS5-08-23AN-0005-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-23 - VHF Trunk Radio System | To be completed
T-00621-3082 | PS5-08-23AN-0901-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-23 - VHF Trunk Radio System | To be completed
T-00621-3083 | PS5-08-23AN-1201-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-23 - VHF Trunk Radio System | To be completed
T-00621-3084 | PS5-08-23AN-1601-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-23 - VHF Trunk Radio System | To be completed
T-00621-3085 | PS5-08-23AN-1901-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-23 - VHF Trunk Radio System | To be completed
T-00621-3086 | PS5-08-23LA-1201-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-23 - VHF Trunk Radio System | To be completed
T-00621-3087 | PS5-08-23LA-1202-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-23 - VHF Trunk Radio System | To be completed
T-00621-3088 | PS5-08-23LA-1501-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-23 - VHF Trunk Radio System | To be completed
T-00621-3089 | PS5-08-34AN-0001-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-34 - Satphone | To be completed
T-00621-3090 | PS5-08-34AN-0002-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-34 - Satphone | To be completed
T-00621-3091 | PS5-08-34LA-1201-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-34 - Satphone | To be completed
T-00621-3092 | PS5-08-34LA-1501-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-34 - Satphone | To be completed
T-00621-3093 | PS5-08-51AN-0001-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3094 | PS5-08-51AN-0001-CV02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3095 | PS5-08-51AN-0001-CV03 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3096 | PS5-08-51AN-0001-CV04 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3097 | PS5-08-51LA-1201-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3098 | PS5-08-51LA-1202-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3099 | PS5-08-51LA-1203-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3100 | PS5-08-51LA-1204-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3101 | PS5-08-51SK-1201-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3102 | PS5-08-51SK-1202-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3103 | PS5-08-51SK-1203-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3104 | PS5-08-51SK-1204-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3105 | PS5-08-51SK-1205-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3106 | PS5-08-51SK-1206-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3107 | PS5-08-51SK-1207-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3108 | PS5-08-51SK-1208-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3109 | PS5-08-51SK-1209-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3110 | PS5-08-51SK-1210-CV01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-51 - Entertainment | To be completed
T-00621-3111 | PS5-08-52CM-0001-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3112 | PS5-08-52CM-0002-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3113 | PS5-08-52CM-0003-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3114 | PS5-08-52CM-0004-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3115 | PS5-08-52CM-0005-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3116 | PS5-08-52CM-0031-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3117 | PS5-08-52CM-0032-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3118 | PS5-08-52CM-0033-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3119 | PS5-08-52CM-0034-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3120 | PS5-08-52CM-0071-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3121 | PS5-08-52CM-0072-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3122 | PS5-08-52CM-0073-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3123 | PS5-08-52CM-0074-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3124 | PS5-08-52CM-0075-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3125 | PS5-08-52CM-0076-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3126 | PS5-08-52CM-0077-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3127 | PS5-08-52CM-0078-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3128 | PS5-08-52CM-0134-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3129 | PS5-08-52CM-0137-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3130 | PS5-08-52CM-0140-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3131 | PS5-08-52CM-0931-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3132 | PS5-08-52CM-1201-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3133 | PS5-08-52CM-1202-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3134 | PS5-08-52CM-1901-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3135 | PS5-08-52CM-1902-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3136 | PS5-08-52CM-1903-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3137 | PS5-08-52TK-0031-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3138 | PS5-08-52TK-0032-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3139 | PS5-08-52TK-0033-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3140 | PS5-08-52TK-0131-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3141 | PS5-08-52TK-0132-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3142 | PS5-08-52TK-0133-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3143 | PS5-08-52TK-0134-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3144 | PS5-08-52TK-0135-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3145 | PS5-08-52TK-0136-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3146 | PS5-08-52TK-0137-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3147 | PS5-08-52TK-0138-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3148 | PS5-08-52TK-0139-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3149 | PS5-08-52TK-0140-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3150 | PS5-08-52TK-0931-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00621-3151 | PS5-08-61BT-0001-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-61 - Meteocean | To be completed
T-00621-3152 | PS5-08-61BT-0001-CC02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-61 - Meteocean | To be completed
T-00621-3153 | PS5-08-61BT-0001-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-61 - Meteocean | To be completed
T-00621-3154 | PS5-08-61BT-0002-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-61 - Meteocean | To be completed
T-00621-3155 | PS5-08-61BT-0901-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-61 - Meteocean | To be completed
T-00621-3156 | PS5-08-61SN-0003-CZ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-61 - Meteocean | To be completed
T-00621-3157 | PS5-08-61SN-0004-CZ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-61 - Meteocean | To be completed
T-00621-3158 | PS5-08-61SN-0005-CZ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-61 - Meteocean | To be completed
T-00621-3159 | PS5-08-61SN-0005-CZ02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-61 - Meteocean | To be completed
T-00621-3160 | PS5-08-61SN-0901-CZ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-61 - Meteocean | To be completed
T-00621-3161 | PS5-08-71SK-1201-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3162 | PS5-08-71SK-1202-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3163 | PS5-08-71SK-1203-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3164 | PS5-08-71SK-1204-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3165 | PS5-08-71SK-1205-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3166 | PS5-08-71SK-1206A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3167 | PS5-08-71SK-1206B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3168 | PS5-08-71SK-1207-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3169 | PS5-08-71SK-1208-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3170 | PS5-08-71SK-1209-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3171 | PS5-08-71SK-1210-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3172 | PS5-08-71SK-1211-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3173 | PS5-08-71SK-1212A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3174 | PS5-08-71SK-1212B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3175 | PS5-08-71SK-1213-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3176 | PS5-08-71SK-1214A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3177 | PS5-08-71SK-1214B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3178 | PS5-08-71SK-1214C-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3179 | PS5-08-71SK-1214D-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3180 | PS5-08-71SK-1215A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3181 | PS5-08-71SK-1215B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3182 | PS5-08-71SK-1216A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3183 | PS5-08-71SK-1216B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3184 | PS5-08-71SK-1217A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3185 | PS5-08-71SK-1217B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3186 | PS5-08-71SK-1218A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3187 | PS5-08-71SK-1218B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3188 | PS5-08-71SK-1219A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3189 | PS5-08-71SK-1219B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3190 | PS5-08-71SK-1220A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3191 | PS5-08-71SK-1220B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3192 | PS5-08-71SK-1221A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3193 | PS5-08-71SK-1221B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3194 | PS5-08-71SK-1222A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3195 | PS5-08-71SK-1222B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3196 | PS5-08-71SK-1223A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3197 | PS5-08-71SK-1223B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3198 | PS5-08-71SK-1224A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3199 | PS5-08-71SK-1224B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3200 | PS5-08-71SK-1225A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3201 | PS5-08-71SK-1225B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3202 | PS5-08-71SK-1226A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3203 | PS5-08-71SK-1226B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3204 | PS5-08-71SK-1227A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3205 | PS5-08-71SK-1227B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3206 | PS5-08-71SK-1228A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3207 | PS5-08-71SK-1228B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3208 | PS5-08-71SK-1229-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3209 | PS5-08-71SK-1230A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3210 | PS5-08-71SK-1230B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3211 | PS5-08-71SK-1231-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3212 | PS5-08-71SK-1232A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3213 | PS5-08-71SK-1232B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3214 | PS5-08-71SK-1233A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3215 | PS5-08-71SK-1233B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3216 | PS5-08-71SK-1234-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3217 | PS5-08-71SK-1235-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3218 | PS5-08-71SK-1236A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3219 | PS5-08-71SK-1236B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3220 | PS5-08-71SK-1237-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3221 | PS5-08-71SK-1238-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3222 | PS5-08-71SK-1239-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3223 | PS5-08-71SK-1240-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3224 | PS5-08-71SK-1241A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3225 | PS5-08-71SK-1241B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3226 | PS5-08-71SK-1242A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3227 | PS5-08-71SK-1242B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3228 | PS5-08-71SK-1243A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3229 | PS5-08-71SK-1243B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3230 | PS5-08-71SK-1244A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3231 | PS5-08-71SK-1244B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3232 | PS5-08-71SK-1245A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3233 | PS5-08-71SK-1245B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3234 | PS5-08-71SK-1246A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3235 | PS5-08-71SK-1246B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3236 | PS5-08-71SK-1247-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3237 | PS5-08-71SK-1248-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3238 | PS5-08-71SK-1249A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3239 | PS5-08-71SK-1249B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3240 | PS5-08-71SK-1249C-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3241 | PS5-08-71SK-1249D-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3242 | PS5-08-71SK-1250A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3243 | PS5-08-71SK-1250B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3244 | PS5-08-71SK-1501A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3245 | PS5-08-71SK-1501B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3246 | PS5-08-71SK-1502A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3247 | PS5-08-71SK-1502B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3248 | PS5-08-71SK-1503A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3249 | PS5-08-71SK-1503B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3250 | PS5-08-71SK-1504A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3251 | PS5-08-71SK-1504B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3252 | PS5-08-71SK-1505-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3253 | PS5-08-71SK-1506-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3254 | PS5-08-71SK-1507-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3255 | PS5-08-71SK-1508-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3256 | PS5-08-71SK-1509-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3257 | PS5-08-71SK-1510A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3258 | PS5-08-71SK-1510B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3259 | PS5-08-71SK-1511A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3260 | PS5-08-71SK-1511B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3261 | PS5-08-71SK-1512-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3262 | PS5-08-71SK-1513-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3263 | PS5-08-71SK-1601A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3264 | PS5-08-71SK-1601B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3265 | PS5-08-71SK-1602A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3266 | PS5-08-71SK-1602B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3267 | PS5-08-71SK-1603A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3268 | PS5-08-71SK-1603B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3269 | PS5-08-71SK-1604A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3270 | PS5-08-71SK-1604B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3271 | PS5-08-71SK-1605A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3272 | PS5-08-71SK-1605B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3273 | PS5-08-71SK-1606-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3274 | PS5-08-71SK-1607-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3275 | PS5-08-71SK-1608-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3276 | PS5-08-71SK-1609-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3277 | PS5-08-71SK-1610-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3278 | PS5-08-71SK-1611-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3279 | PS5-08-71SK-1901-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3280 | PS5-08-71SK-1903A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3281 | PS5-08-71SK-1903B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3282 | PS5-08-71SK-1904A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3283 | PS5-08-71SK-1904B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3284 | PS5-08-71SK-1905A-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3285 | PS5-08-71SK-1905B-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00621-3286 | PS5-08-85BG-1201-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3287 | PS5-08-85BG-1202-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3288 | PS5-08-85BG-1203-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3289 | PS5-08-85BG-1204-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3290 | PS5-08-85BG-1501-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3291 | PS5-08-85BG-1601-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3292 | PS5-08-85BG-1602-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3293 | PS5-08-85BG-1603-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3294 | PS5-08-85BG-1604-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3295 | PS5-08-85BG-1605-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3296 | PS5-08-85BG-1901-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3297 | PS5-08-85BG-1902-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3306 | PS5-08-85BR-0009-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3307 | PS5-08-85BR-0010-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3308 | PS5-08-85BR-0011-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3309 | PS5-08-85BR-0012-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3310 | PS5-08-85BR-1201-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3311 | PS5-08-85BR-1202-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3312 | PS5-08-85BR-1203-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3313 | PS5-08-85BR-1204-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3314 | PS5-08-85BR-1205-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3315 | PS5-08-85BR-1206-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3316 | PS5-08-85BR-1501-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3317 | PS5-08-85BR-1502-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3318 | PS5-08-85BR-1601-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3319 | PS5-08-85BR-1602-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3320 | PS5-08-85BR-1603-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3321 | PS5-08-85BR-1604-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3322 | PS5-08-85BR-1605-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3323 | PS5-08-85BR-1901-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3324 | PS5-08-85BR-1902-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3325 | PS5-08-85BT-0001-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3328 | PS5-08-85BT-0004-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3329 | PS5-08-85BT-0005-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed | CPP-RFI-68-65-05-0011
T-00621-3330 | PS5-08-85BT-0006-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3331 | PS5-08-85BT-0007-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed | CPP-RFI-68-65-05-0011
T-00621-3332 | PS5-08-85BT-0008-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3333 | PS5-08-85BT-0009-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3334 | PS5-08-85BT-0010-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed | CPP-RFI-68-65-05-0013
T-00621-3335 | PS5-08-85BT-0011-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3336 | PS5-08-85BT-0012-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3337 | PS5-08-85BT-0013-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed | CPP-RFI-68-65-05-0015
T-00621-3338 | PS5-08-85BT-0014-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed | CPP-RFI-68-65-05-0023
T-00621-3339 | PS5-08-85BT-0015-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed | CPP-RFI-68-65-05-0015
T-00621-3340 | PS5-08-85BT-0016-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed | CPP-RFI-68-65-05-0034 | CPP-RFI-68-65-20-0035 |  | Doc. TZ-MID-68-WPR2-171100 - As Per Details Installation, Cable Tray need to be install (Junction Box Side) refer to Drawing UT-MID-60-WPR2-171204 [] | Doc. TZ-MID-68-WPR2-171100 - Cable Need to Be Dressing at Both Ends []
T-00621-3343 | PS5-08-85BT-0018-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3352 | PS5-08-85BT-0027-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3353 | PS5-08-85BT-0028-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3354 | PS5-08-85BT-1201-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3355 | PS5-08-85BT-1201-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3356 | PS5-08-85BT-1202-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3357 | PS5-08-85BT-1202-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3358 | PS5-08-85BT-1203-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3359 | PS5-08-85BT-1203-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3360 | PS5-08-85BT-1204-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3361 | PS5-08-85BT-1205-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3362 | PS5-08-85BT-1205-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3363 | PS5-08-85BT-1501-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3364 | PS5-08-85BT-1502-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3365 | PS5-08-85BT-1503-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3366 | PS5-08-85BT-1503-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3367 | PS5-08-85BT-1601-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3368 | PS5-08-85BT-1602-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3369 | PS5-08-85BT-1603-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3370 | PS5-08-85BT-1603-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3371 | PS5-08-85BT-1604-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3372 | PS5-08-85BT-1605-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3373 | PS5-08-85BT-1605-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3374 | PS5-08-85BT-1606-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3375 | PS5-08-85BT-1606-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3376 | PS5-08-85BT-1607-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3377 | PS5-08-85BT-1607-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3378 | PS5-08-85BT-1608-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3379 | PS5-08-85BT-1608-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3380 | PS5-08-85BT-1609-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3381 | PS5-08-85BT-1610-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3382 | PS5-08-85BT-1611-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3383 | PS5-08-85BT-1612-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3384 | PS5-08-85BT-1613-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3385 | PS5-08-85BT-1614-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3386 | PS5-08-85BT-1901-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3387 | PS5-08-85BT-1901-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3388 | PS5-08-85BT-1902-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3389 | PS5-08-85BT-1902-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3390 | PS5-08-85BT-1903-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3391 | PS5-08-85BT-1904-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3392 | PS5-08-85BT-1905-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3393 | PS5-08-85BT-1906-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3394 | PS5-08-85BT-1907-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3395 | PS5-08-85BT-1908-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3396 | PS5-08-85BT-1909-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3397 | PS5-08-85CP-1201-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3398 | PS5-08-85CP-1202-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3399 | PS5-08-85CP-1501-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3400 | PS5-08-85CP-1601-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3401 | PS5-08-85CP-1901-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3402 | PS5-08-85DC-0001-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3403 | PS5-08-85DC-0002-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3404 | PS5-08-85DC-0003-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3405 | PS5-08-85DC-0004-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3406 | PS5-08-85DC-0005-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3407 | PS5-08-85DC-0006-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3408 | PS5-08-85DC-0007-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3409 | PS5-08-85DC-0008-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3410 | PS5-08-85DC-0009-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3411 | PS5-08-85DC-0010-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3412 | PS5-08-85DC-0011-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3413 | PS5-08-85DC-0012-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3414 | PS5-08-85DC-0013-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3415 | PS5-08-85DC-0014-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3416 | PS5-08-85DC-0015-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3417 | PS5-08-85DC-0016-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3418 | PS5-08-85DC-0017-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3419 | PS5-08-85DC-0018-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3420 | PS5-08-85DC-0019-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3421 | PS5-08-85DC-0021-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3422 | PS5-08-85DC-0022-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3423 | PS5-08-85DC-0023-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3424 | PS5-08-85DC-0024-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3425 | PS5-08-85DC-0025-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3426 | PS5-08-85DC-0026-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3427 | PS5-08-85DC-0027-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3428 | PS5-08-85DC-0028-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3429 | PS5-08-85DC-1201-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3430 | PS5-08-85DC-1202-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3431 | PS5-08-85DC-1203-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3432 | PS5-08-85DC-1204-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3433 | PS5-08-85DC-1205-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3434 | PS5-08-85DC-1206-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3435 | PS5-08-85DC-1207-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3436 | PS5-08-85DC-1501-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3437 | PS5-08-85DC-1502-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3438 | PS5-08-85DC-1503-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3439 | PS5-08-85DC-1601-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3440 | PS5-08-85DC-1602-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3441 | PS5-08-85DC-1603-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3442 | PS5-08-85DC-1604-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3443 | PS5-08-85DC-1605-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3444 | PS5-08-85DC-1606-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3445 | PS5-08-85DC-1607-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3446 | PS5-08-85DC-1608-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3447 | PS5-08-85DC-1609-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3448 | PS5-08-85DC-1610-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3449 | PS5-08-85DC-1611-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3450 | PS5-08-85DC-1612-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3451 | PS5-08-85DC-1613-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3452 | PS5-08-85DC-1614-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3453 | PS5-08-85DC-1615-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3454 | PS5-08-85DC-1616-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3455 | PS5-08-85DC-1617-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3456 | PS5-08-85DC-1618-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3457 | PS5-08-85DC-1901-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3458 | PS5-08-85DC-1902-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3459 | PS5-08-85DC-1903-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3460 | PS5-08-85DC-1904-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3461 | PS5-08-85DC-1905-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3462 | PS5-08-85DC-1906-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3463 | PS5-08-85DC-1907-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3464 | PS5-08-85DC-1908-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3465 | PS5-08-85DC-1909-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3466 | PS5-08-85DC-1910-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3467 | PS5-08-85DC-1911-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3468 | PS5-08-85DC-1912-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3469 | PS5-08-85DC-1913-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3470 | PS5-08-85DC-1914-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3471 | PS5-08-85DC-1915-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3472 | PS5-08-85DC-1916-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3473 | PS5-08-85ML-0001-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3474 | PS5-08-85ML-1201-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3475 | PS5-08-85ML-1202-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3476 | PS5-08-85ML-1203-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3477 | PS5-08-85ML-1204-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3478 | PS5-08-85ML-1501-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3479 | PS5-08-85ML-1601-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3480 | PS5-08-85ML-1602-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3481 | PS5-08-85ML-1603-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3482 | PS5-08-85ML-1604-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3483 | PS5-08-85ML-1605-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3484 | PS5-08-85ML-1901-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3485 | PS5-08-85ML-1902-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3486 | PS5-08-85PB-0001-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3487 | PS5-08-85PB-1201-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3488 | PS5-08-85PB-1202-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3489 | PS5-08-85PB-1203-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3490 | PS5-08-85PB-1204-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3491 | PS5-08-85PB-1501-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3492 | PS5-08-85PB-1601-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3493 | PS5-08-85PB-1602-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3494 | PS5-08-85PB-1603-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3495 | PS5-08-85PB-1604-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3496 | PS5-08-85PB-1605-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3497 | PS5-08-85PB-1901-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3498 | PS5-08-85PB-1902-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3499 | PS5-82-MBA-0001-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3500 | PS5-82-MBA-0002-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3501 | PS5-82-MBA-0003-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3502 | PS5-82-MGV-0002-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-3503 | PS5-82-MTL-0001-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-5357 | PS5-08-13CB-1201-CX01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | To be completed
T-00621-5358 | PS5-08-14CB-1201-CX01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-14 - Industrial Data Network (SII SP1) | To be completed
T-00621-5359 | PS5-08-85AP-0001-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-5360 | PS5-08-85AP-0002-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-5361 | PS5-08-85AP-0003-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00621-5362 | PS5-08-85AP-0004-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00624-0767 | PS5-08-01PA-1201-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00624-0768 | PS5-08-01PA-1501-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-01 - PAGA | To be completed
T-00624-0769 | PS5-08-05IN-0001-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Started (not Completed) | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00624-0770 | PS5-08-05IN-0002-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00624-0771 | PS5-08-05IN-0003-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00624-0772 | PS5-08-05IN-0004-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00624-0773 | PS5-08-05IN-0005-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00624-0774 | PS5-08-12AP-0002-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00624-0775 | PS5-08-12AP-0003-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00624-0776 | PS5-08-12AP-0101-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00624-0777 | PS5-08-12AP-0103-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00624-0778 | PS5-08-12BT-0002-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00624-0779 | PS5-08-12BT-0003-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00624-0780 | PS5-08-12BT-0101-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | Started (not Completed) | CPP-RFI-68-65-05-0036 |  |  | Doc. Doc. TZ-MID-68-WPR2-151166,TZ-MID-68-WPR2-171120, Field Run Cable Tray need to Install at Wap Junction Box Side [OPEN] | Doc. TZ-MID-68-WPR2-151166,TZ-MID-68-WPR2-171120 Cable Need to Be Dressing at Both Ends [OPEN]
T-00624-0781 | PS5-08-12BT-0103-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-12 - Corporate Wireless LAN (SIE) | To be completed
T-00624-0782 | PS5-08-13CB-1201-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | To be completed
T-00624-0783 | PS5-08-13CB-1201-CA02 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | To be completed
T-00624-0784 | PS5-08-13CB-1201-CA03 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | To be completed
T-00624-0785 | PS5-08-13CB-1201-CA04 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | To be completed
T-00624-0786 | PS5-08-13CB-1201-CA05 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | To be completed
T-00624-0787 | PS5-08-13CB-1201-CA06 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | To be completed
T-00624-0788 | PS5-08-14CB-1201-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-14 - Industrial Data Network (SII SP1) | To be completed
T-00624-0789 | PS5-08-14CB-1201-CA02 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-14 - Industrial Data Network (SII SP1) | To be completed
T-00624-0790 | PS5-08-14CB-1201-CA03 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-14 - Industrial Data Network (SII SP1) | To be completed
T-00624-0791 | PS5-08-14CB-1201-CA04 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-14 - Industrial Data Network (SII SP1) | To be completed
T-00624-0792 | PS5-08-14CB-1201-CA05 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-14 - Industrial Data Network (SII SP1) | To be completed
T-00624-0793 | PS5-08-14CB-1201-CA06 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-14 - Industrial Data Network (SII SP1) | To be completed
T-00624-0794 | PS5-08-52CM-0001-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0795 | PS5-08-52CM-0002-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0796 | PS5-08-52CM-0003-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0797 | PS5-08-52CM-0004-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0798 | PS5-08-52CM-0005-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0799 | PS5-08-52CM-0031-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0800 | PS5-08-52CM-0032-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0801 | PS5-08-52CM-0033-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0802 | PS5-08-52CM-0034-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0803 | PS5-08-52CM-0071-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0804 | PS5-08-52CM-0072-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0805 | PS5-08-52CM-0073-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0806 | PS5-08-52CM-0074-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0807 | PS5-08-52CM-0075-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0808 | PS5-08-52CM-0076-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0809 | PS5-08-52CM-0077-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0810 | PS5-08-52CM-0078-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0811 | PS5-08-52CM-0134-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0812 | PS5-08-52CM-0137-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0813 | PS5-08-52CM-0140-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0814 | PS5-08-52CM-0931-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0815 | PS5-08-52CM-1201-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0816 | PS5-08-52CM-1202-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0817 | PS5-08-52CM-1901-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0818 | PS5-08-52CM-1902-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0819 | PS5-08-52CM-1903-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-52 - Process & Security CCTV | To be completed
T-00624-0820 | PS5-08-71SK-1201-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0821 | PS5-08-71SK-1202-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0822 | PS5-08-71SK-1203-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0823 | PS5-08-71SK-1204-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0824 | PS5-08-71SK-1205-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0825 | PS5-08-71SK-1206A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0826 | PS5-08-71SK-1206B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0827 | PS5-08-71SK-1207-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0828 | PS5-08-71SK-1208-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0829 | PS5-08-71SK-1209-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0830 | PS5-08-71SK-1210-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0831 | PS5-08-71SK-1211-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0832 | PS5-08-71SK-1212A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0833 | PS5-08-71SK-1212B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0834 | PS5-08-71SK-1213-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0835 | PS5-08-71SK-1214A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0836 | PS5-08-71SK-1214B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0837 | PS5-08-71SK-1214C-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0838 | PS5-08-71SK-1214D-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0839 | PS5-08-71SK-1215A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0840 | PS5-08-71SK-1215B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0841 | PS5-08-71SK-1216A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0842 | PS5-08-71SK-1216B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0843 | PS5-08-71SK-1217A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0844 | PS5-08-71SK-1217B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0845 | PS5-08-71SK-1218A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0846 | PS5-08-71SK-1218B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0847 | PS5-08-71SK-1219A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0848 | PS5-08-71SK-1219B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0849 | PS5-08-71SK-1220A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0850 | PS5-08-71SK-1220B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0851 | PS5-08-71SK-1221A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0852 | PS5-08-71SK-1221B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0853 | PS5-08-71SK-1222A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0854 | PS5-08-71SK-1222B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0855 | PS5-08-71SK-1223A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0856 | PS5-08-71SK-1223B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0857 | PS5-08-71SK-1224A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0858 | PS5-08-71SK-1224B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0859 | PS5-08-71SK-1225A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0860 | PS5-08-71SK-1225B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0861 | PS5-08-71SK-1226A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0862 | PS5-08-71SK-1226B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0863 | PS5-08-71SK-1227A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0864 | PS5-08-71SK-1227B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0865 | PS5-08-71SK-1228A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0866 | PS5-08-71SK-1228B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0867 | PS5-08-71SK-1229-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0868 | PS5-08-71SK-1230A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0869 | PS5-08-71SK-1230B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0870 | PS5-08-71SK-1231-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0871 | PS5-08-71SK-1232A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0872 | PS5-08-71SK-1232B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0873 | PS5-08-71SK-1233A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0874 | PS5-08-71SK-1233B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0875 | PS5-08-71SK-1234-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0876 | PS5-08-71SK-1235-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0877 | PS5-08-71SK-1236A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0878 | PS5-08-71SK-1236B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0879 | PS5-08-71SK-1237-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0880 | PS5-08-71SK-1238-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0881 | PS5-08-71SK-1239-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0882 | PS5-08-71SK-1240-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0883 | PS5-08-71SK-1241A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0884 | PS5-08-71SK-1241B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0885 | PS5-08-71SK-1242A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0886 | PS5-08-71SK-1242B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0887 | PS5-08-71SK-1243A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0888 | PS5-08-71SK-1243B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0889 | PS5-08-71SK-1244A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0890 | PS5-08-71SK-1244B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0891 | PS5-08-71SK-1245A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0892 | PS5-08-71SK-1245B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0893 | PS5-08-71SK-1246A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0894 | PS5-08-71SK-1246B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0895 | PS5-08-71SK-1247-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0896 | PS5-08-71SK-1248-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0897 | PS5-08-71SK-1249A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0898 | PS5-08-71SK-1249B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0899 | PS5-08-71SK-1249C-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0900 | PS5-08-71SK-1249D-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0901 | PS5-08-71SK-1250A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0902 | PS5-08-71SK-1250B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0903 | PS5-08-71SK-1501A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0904 | PS5-08-71SK-1501B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0905 | PS5-08-71SK-1502A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0906 | PS5-08-71SK-1502B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0907 | PS5-08-71SK-1503A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0908 | PS5-08-71SK-1503B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0909 | PS5-08-71SK-1504A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0910 | PS5-08-71SK-1504B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0911 | PS5-08-71SK-1505-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0912 | PS5-08-71SK-1506-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0913 | PS5-08-71SK-1507-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0914 | PS5-08-71SK-1508-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0915 | PS5-08-71SK-1509-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0916 | PS5-08-71SK-1510A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0917 | PS5-08-71SK-1510B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0918 | PS5-08-71SK-1511A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0919 | PS5-08-71SK-1511B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0920 | PS5-08-71SK-1512-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0921 | PS5-08-71SK-1513-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0922 | PS5-08-71SK-1601A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0923 | PS5-08-71SK-1601B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0924 | PS5-08-71SK-1602A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0925 | PS5-08-71SK-1602B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0926 | PS5-08-71SK-1603A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0927 | PS5-08-71SK-1603B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0928 | PS5-08-71SK-1604A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0929 | PS5-08-71SK-1604B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0930 | PS5-08-71SK-1605A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0931 | PS5-08-71SK-1605B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0932 | PS5-08-71SK-1606-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0933 | PS5-08-71SK-1607-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0934 | PS5-08-71SK-1608-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0935 | PS5-08-71SK-1609-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0936 | PS5-08-71SK-1610-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0937 | PS5-08-71SK-1611-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0938 | PS5-08-71SK-1901-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0939 | PS5-08-71SK-1903A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0940 | PS5-08-71SK-1903B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0941 | PS5-08-71SK-1904A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0942 | PS5-08-71SK-1904B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0943 | PS5-08-71SK-1905A-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0944 | PS5-08-71SK-1905B-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-71 - Structured Cabling (CAT6) | To be completed
T-00624-0945 | PS5-08-85BT-0027-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00624-0946 | PS5-08-85BT-0028-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00624-0947 | PS5-08-85CP-1201-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00624-0948 | PS5-08-85CP-1202-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00624-0949 | PS5-08-85CP-1501-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00624-0950 | PS5-08-85CP-1601-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed
T-00624-0951 | PS5-08-85CP-1901-CA01 | TIX01a - RJ45 Cable (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | To be completed

## PS-5 EIT TASK CLOSE
PS-5 EIT TASK MANAGEMENT - CLOSED TASKS
Task ID | Asset - Tag | Description | Discipline | Subsystem | Task State | INSTALLATION & PULLING | Testing | GLANDING & TERMINATION INSPECTION | PUNCH A | PUNCH B | PUNCH C
T-00018-0102 | PS5-61-IV-0001A | CPX02 - Power transformer | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-332-02-0331 | CPP-RFI-68-332-16-0332 |  |  | TZ-MID-68-WPR2-151112 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding [OPEN] | TZ-MID-68-WPR2-151112 Carry out cleanning body of the transformer and surrounding bay area [OPEN]
T-00018-0171 | PS5-61-IU-3100A | CPX02 - Power transformer | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-332-02-0304 | CPP-RFI-68-332-16-0326 |  |  |  | TZ-MID-68-WPR2-151111 Cleanning body transformer and areas [OPEN]
T-00018-0172 | PS5-61-IU-3100B | CPX02 - Power transformer | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-332-02-0304 | CPP-RFI-68-332-16-0326 |  |  |  | TZ-MID-68-WPR2-151111 Cleanning body transformer and areas [OPEN]
T-00018-0173 | PS5-61-IU-3100C | CPX02 - Power transformer | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-332-02-0304 | CPP-RFI-68-332-16-0326 |  |  |  | TZ-MID-68-WPR2-151111 Cleanning body transformer and areas [OPEN]
T-00022-3316 | PS5-25-DM-3100A-CH01 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3317 | PS5-25-DM-3100A-CH02 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3318 | PS5-25-DM-3100A-CH03 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3319 | PS5-25-DM-3100A-CH04 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3320 | PS5-25-DM-3100A-CH05 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3321 | PS5-25-DM-3100A-CH06 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3322 | PS5-25-DM-3100B-CH01 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3323 | PS5-25-DM-3100B-CH02 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3324 | PS5-25-DM-3100B-CH03 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3325 | PS5-25-DM-3100B-CH04 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3326 | PS5-25-DM-3100B-CH05 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3327 | PS5-25-DM-3100B-CH06 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3328 | PS5-25-DM-3100C-CH01 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3329 | PS5-25-DM-3100C-CH02 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3330 | PS5-25-DM-3100C-CH03 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3331 | PS5-25-DM-3100C-CH04 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3332 | PS5-25-DM-3100C-CH05 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3333 | PS5-25-DM-3100C-CH06 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00022-3334 | PS5-60-IJ-0001A-CH04 | CPX08 - HV Power Cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-168 | CPP-RFI-68-33/1-07-0175
T-00022-3335 | PS5-60-IJ-0001B-CH04 | CPX08 - HV Power Cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-168 | CPP-RFI-68-33/1-07-0175
T-00022-3336 | PS5-60-IJ-0001C-CH04 | CPX08 - HV Power Cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-33/1-05-168 | CPP-RFI-68-33/1-07-0175
T-00022-3337 | PS5-60-IJ-0001D-CH04 | CPX08 - HV Power Cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-33/1-05-168 | CPP-RFI-68-33/1-07-0175
T-00022-3338 | PS5-60-IJ-0001E-CH04 | CPX08 - HV Power Cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-33/1-05-168 | CPP-RFI-68-33/1-07-0175
T-00022-3339 | PS5-60-IJ-0001F-CH04 | CPX08 - HV Power Cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-33/1-05-168 | CPP-RFI-68-33/1-07-0175
T-00022-3340 | PS5-60-IJ-0001G-CH04 | CPX08 - HV Power Cable | E | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-33/1-05-168 | CPP-RFI-68-33/1-07-0175
T-00022-3341 | PS5-61-IDH-3100A-CH01 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3342 | PS5-61-IDH-3100A-CH02 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3343 | PS5-61-IDH-3100A-CH03 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3344 | PS5-61-IDH-3100A-CH04 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3345 | PS5-61-IDH-3100A-CH05 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3346 | PS5-61-IDH-3100A-CH06 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3347 | PS5-61-IDH-3100A-CH07 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3348 | PS5-61-IDH-3100A-CH08 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3349 | PS5-61-IDH-3100A-CH09 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3350 | PS5-61-IDH-3100A-CH10 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3351 | PS5-61-IDH-3100A-CH11 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3352 | PS5-61-IDH-3100A-CH12 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3353 | PS5-61-IDH-3100B-CH01 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3354 | PS5-61-IDH-3100B-CH02 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3355 | PS5-61-IDH-3100B-CH03 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3356 | PS5-61-IDH-3100B-CH04 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3357 | PS5-61-IDH-3100B-CH05 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3358 | PS5-61-IDH-3100B-CH06 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3359 | PS5-61-IDH-3100B-CH07 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3360 | PS5-61-IDH-3100B-CH08 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3361 | PS5-61-IDH-3100B-CH09 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3362 | PS5-61-IDH-3100B-CH10 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3363 | PS5-61-IDH-3100B-CH11 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3364 | PS5-61-IDH-3100B-CH12 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3365 | PS5-61-IDH-3100C-CH01 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3366 | PS5-61-IDH-3100C-CH02 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3367 | PS5-61-IDH-3100C-CH03 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3368 | PS5-61-IDH-3100C-CH04 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3369 | PS5-61-IDH-3100C-CH05 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3370 | PS5-61-IDH-3100C-CH06 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3371 | PS5-61-IDH-3100C-CH07 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3372 | PS5-61-IDH-3100C-CH08 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3373 | PS5-61-IDH-3100C-CH09 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3374 | PS5-61-IDH-3100C-CH10 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3375 | PS5-61-IDH-3100C-CH11 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3376 | PS5-61-IDH-3100C-CH12 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3377 | PS5-61-IJ-0001-CH01 | CPX08 - HV Power Cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3378 | PS5-61-IJ-0001-CH02 | CPX08 - HV Power Cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3379 | PS5-61-IJ-0001-CH03 | CPX08 - HV Power Cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3380 | PS5-61-IJ-0001-CH04 | CPX08 - HV Power Cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3381 | PS5-61-IJ-0001-CH05 | CPX08 - HV Power Cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3382 | PS5-61-IJ-0001-CH06 | CPX08 - HV Power Cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3383 | PS5-61-IJ-0001-CH07 | CPX08 - HV Power Cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3384 | PS5-61-IJ-0001-CH08 | CPX08 - HV Power Cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3385 | PS5-61-IJ-0001-CH09 | CPX08 - HV Power Cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3386 | PS5-61-IJ-0001-CH10 | CPX08 - HV Power Cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3387 | PS5-61-IJ-0001-CH11 | CPX08 - HV Power Cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3388 | PS5-61-IJ-0001-CH12 | CPX08 - HV Power Cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3389 | PS5-61-IJ-0001-CH13 | CPX08 - HV Power Cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3390 | PS5-61-IJ-0001-CH14 | CPX08 - HV Power Cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3391 | PS5-61-IJ-0001-CH15 | CPX08 - HV Power Cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3392 | PS5-61-IJ-0001-CH16 | CPX08 - HV Power Cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3393 | PS5-61-IJ-0001-CH17 | CPX08 - HV Power Cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3394 | PS5-61-IJ-0001-CH18 | CPX08 - HV Power Cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3395 | PS5-61-IJ-0001-CH19 | CPX08 - HV Power Cable | E | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3396 | PS5-61-IJ-0001-CH20 | CPX08 - HV Power Cable | E | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3397 | PS5-61-IJ-0001-CH21 | CPX08 - HV Power Cable | E | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00022-3410 | PS5-61-IU-0001A-CH01 | CPX08 - HV Power Cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3411 | PS5-61-IU-0001A-CH02 | CPX08 - HV Power Cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3412 | PS5-61-IU-0001A-CH03 | CPX08 - HV Power Cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3413 | PS5-61-IU-0001B-CH01 | CPX08 - HV Power Cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3414 | PS5-61-IU-0001B-CH02 | CPX08 - HV Power Cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3415 | PS5-61-IU-0001B-CH03 | CPX08 - HV Power Cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3416 | PS5-61-IU-0001C-CH01 | CPX08 - HV Power Cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3417 | PS5-61-IU-0001C-CH02 | CPX08 - HV Power Cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3418 | PS5-61-IU-0001C-CH03 | CPX08 - HV Power Cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3419 | PS5-61-IU-0001D-CH01 | CPX08 - HV Power Cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3420 | PS5-61-IU-0001D-CH02 | CPX08 - HV Power Cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3421 | PS5-61-IU-0001D-CH03 | CPX08 - HV Power Cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3422 | PS5-61-IU-0001E-CH01 | CPX08 - HV Power Cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3423 | PS5-61-IU-0001E-CH02 | CPX08 - HV Power Cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3424 | PS5-61-IU-0001E-CH03 | CPX08 - HV Power Cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3425 | PS5-61-IU-0001F-CH01 | CPX08 - HV Power Cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3426 | PS5-61-IU-0001F-CH02 | CPX08 - HV Power Cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3427 | PS5-61-IU-0001F-CH03 | CPX08 - HV Power Cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3428 | PS5-61-IU-0001G-CH01 | CPX08 - HV Power Cable | E | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3429 | PS5-61-IU-0001G-CH02 | CPX08 - HV Power Cable | E | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3430 | PS5-61-IU-0001G-CH03 | CPX08 - HV Power Cable | E | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00022-3437 | PS5-61-IU-3100A-CH01 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00022-3438 | PS5-61-IU-3100A-CH02 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00022-3439 | PS5-61-IU-3100A-CH03 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00022-3440 | PS5-61-IU-3100A-CH04 | CPX08 - HV Power Cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3441 | PS5-61-IU-3100B-CH01 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00022-3442 | PS5-61-IU-3100B-CH02 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00022-3443 | PS5-61-IU-3100B-CH03 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00022-3444 | PS5-61-IU-3100B-CH04 | CPX08 - HV Power Cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3445 | PS5-61-IU-3100C-CH01 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00022-3446 | PS5-61-IU-3100C-CH02 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00022-3447 | PS5-61-IU-3100C-CH03 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00022-3448 | PS5-61-IU-3100C-CH04 | CPX08 - HV Power Cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00022-3449 | PS5-61-IV-0001A-CH01 | CPX08 - HV Power Cable | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00022-3450 | PS5-61-IV-0001A-CH02 | CPX08 - HV Power Cable | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00022-3451 | PS5-61-IV-0001A-CH03 | CPX08 - HV Power Cable | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00022-3452 | PS5-61-IV-0001B-CH01 | CPX08 - HV Power Cable | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00022-3453 | PS5-61-IV-0001B-CH02 | CPX08 - HV Power Cable | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00022-3454 | PS5-61-IV-0001B-CH03 | CPX08 - HV Power Cable | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00022-3455 | PS5-61-IV-0002A-CH01 | CPX08 - HV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00022-3456 | PS5-61-IV-0002A-CH02 | CPX08 - HV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00022-3457 | PS5-61-IV-0002A-CH03 | CPX08 - HV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00022-3458 | PS5-61-IV-0002B-CH01 | CPX08 - HV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00022-3459 | PS5-61-IV-0002B-CH02 | CPX08 - HV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00022-3460 | PS5-61-IV-0002B-CH03 | CPX08 - HV Power Cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00022-3467 | PS5-61-IV-0007A-CH01 | CPX08 - HV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00022-3468 | PS5-61-IV-0007A-CH02 | CPX08 - HV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00022-3469 | PS5-61-IV-0007A-CH03 | CPX08 - HV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00022-3470 | PS5-61-IV-0007B-CH01 | CPX08 - HV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00022-3471 | PS5-61-IV-0007B-CH02 | CPX08 - HV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00022-3472 | PS5-61-IV-0007B-CH03 | CPX08 - HV Power Cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00031-1276 |  | CPX18 - Lighting Circuits | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | Closed
T-00031-1293 |  | CPX18 - Lighting Circuits | E | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | Closed
T-00031-1316 |  | CPX18 - Lighting Circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | Closed
T-00031-1317 |  | CPX18 - Lighting Circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | Closed
T-00031-1319 |  | CPX18 - Lighting Circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | Closed
T-00031-1321 |  | CPX18 - Lighting Circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | Closed
T-00031-1324 |  | CPX18 - Lighting Circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | Closed
T-00044-0182 | PS5-05-IE-8100 | CPX32 - Console / control panel | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | Closed |  |  |  |  | TZ-MID-60-UTR2-150005 IE bar not connected to earth grid [OPEN] | TZ-MID-60-UTR2-150005 Cleanning internal and external of the panel [OPEN] ¦ TZ-MID-60-UTR2-150005 The Panel Frame need to be touch up paint [OPEN]
T-00044-0195 | PS5-62-IE-0001 | CPX32 - Console / control panel | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | Closed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  | TZ-MID-68-WPR2-151111 Isolation pad to be install at SS bracket and bolts since disimilar material. [OPEN] |  | TZ-MID-68-WPR2-151111 Perform cleanning internal and external of the panel [OPEN]
T-00044-0196 | PS5-62-IE-0002 | CPX32 - Console / control panel | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | Closed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  |  | TZ-MID-68-WPR2-151117 To be clean weld slag and touch up paint at the panel support. [OPEN] | TZ-MID-68-WPR2-151117 Perform cleanning internal and external of the panel [OPEN]
T-00046-0291 | PS5-60-UR-8100A | CZX01E - Package | E | PS5-60-01 - Power Generation Package A | Closed
T-00046-0292 | PS5-60-UR-8100B | CZX01E - Package | E | PS5-60-04 - Power Generation Package B | Closed
T-00046-0293 | PS5-60-UR-8100C | CZX01E - Package | E | PS5-60-07 - Power Generation Package C | Closed
T-00046-0294 | PS5-60-UR-8100D | CZX01E - Package | E | PS5-60-10 - Power Generation Package D | Closed
T-00046-0300 | PS5-60-UA-5100 | CZX01E - Package | E | PS5-60-27 - Compressed Air Starting Skid | Closed
T-00046-0301 | PS5-60-UO-81100A | CZX01E - Package | E | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | Closed
T-00046-0302 | PS5-60-UO-81100B | CZX01E - Package | E | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | Closed
T-00046-0303 | PS5-60-UO-81100C | CZX01E - Package | E | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | Closed
T-00046-0304 | PS5-60-UO-81100D | CZX01E - Package | E | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | Closed
T-00046-0308 | PS5-60-UZ-8200A | CZX01E - Package | E | PS5-60-35 - Injector Tip Cooling Module A | Closed
T-00046-0309 | PS5-60-UZ-8200B | CZX01E - Package | E | PS5-60-36 - Injector Tip Cooling Module B | Closed
T-00046-0310 | PS5-60-UZ-8200C | CZX01E - Package | E | PS5-60-37 - Injector Tip Cooling Module C | Closed
T-00046-0311 | PS5-60-UZ-8200D | CZX01E - Package | E | PS5-60-38 - Injector Tip Cooling Module D | Closed
T-00046-0314 | PS5-60-VS-9100A | CZX01E - Package | E | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | Closed
T-00046-0315 | PS5-60-VS-9100B | CZX01E - Package | E | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | Closed
T-00046-0316 | PS5-60-VS-9100C | CZX01E - Package | E | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | Closed
T-00046-0317 | PS5-60-VS-9100D | CZX01E - Package | E | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | Closed
T-00046-0321 | PS5-71-UZ-6500 | CZX01E - Package | E | PS5-71-18 - Diesel Separator Module | Closed
T-00046-0322 | PS5-71-UZ-6800A | CZX01E - Package | E | PS5-71-06 - Crude Fuel Separation Module | Closed
T-00046-0323 | PS5-71-UZ-6800B | CZX01E - Package | E | PS5-71-06 - Crude Fuel Separation Module | Closed
T-00046-0327 | PS5-60-EA-2100A | CZX01E - Package | E | PS5-60-70 - Engine A Cooling system | Closed
T-00046-0328 | PS5-60-EA-2100B | CZX01E - Package | E | PS5-60-70 - Engine A Cooling system | Closed
T-00046-0329 | PS5-60-EA-21100A | CZX01E - Package | E | PS5-60-01 - Power Generation Package A | Closed
T-00046-0330 | PS5-60-EA-21100B | CZX01E - Package | E | PS5-60-04 - Power Generation Package B | Closed
T-00046-0331 | PS5-60-EA-21100C | CZX01E - Package | E | PS5-60-07 - Power Generation Package C | Closed
T-00046-0332 | PS5-60-EA-21100D | CZX01E - Package | E | PS5-60-10 - Power Generation Package D | Closed
T-00046-0336 | PS5-60-EA-21200A | CZX01E - Package | E | PS5-60-01 - Power Generation Package A | Closed
T-00046-0337 | PS5-60-EA-21200B | CZX01E - Package | E | PS5-60-04 - Power Generation Package B | Closed
T-00046-0338 | PS5-60-EA-21200C | CZX01E - Package | E | PS5-60-07 - Power Generation Package C | Closed
T-00046-0339 | PS5-60-EA-21200D | CZX01E - Package | E | PS5-60-10 - Power Generation Package D | Closed
T-00046-0343 | PS5-60-EA-2200A | CZX01E - Package | E | PS5-60-71 - Engine B Cooling system | Closed
T-00046-0344 | PS5-60-EA-2200B | CZX01E - Package | E | PS5-60-71 - Engine B Cooling system | Closed
T-00046-0345 | PS5-60-EA-2300A | CZX01E - Package | E | PS5-60-72 - Engine C Cooling system | Closed
T-00046-0346 | PS5-60-EA-2300B | CZX01E - Package | E | PS5-60-72 - Engine C Cooling system | Closed
T-00046-0347 | PS5-60-EA-2400A | CZX01E - Package | E | PS5-60-73 - Engine D Cooling system | Closed
T-00046-0348 | PS5-60-EA-2400B | CZX01E - Package | E | PS5-60-73 - Engine D Cooling system | Closed
T-00046-0355 | PS5-60-EA-2800A | CZX01E - Package | E | PS5-60-35 - Injector Tip Cooling Module A | Closed
T-00046-0356 | PS5-60-EA-2800B | CZX01E - Package | E | PS5-60-36 - Injector Tip Cooling Module B | Closed
T-00046-0357 | PS5-60-EA-2800C | CZX01E - Package | E | PS5-60-37 - Injector Tip Cooling Module C | Closed
T-00046-0358 | PS5-60-EA-2800D | CZX01E - Package | E | PS5-60-38 - Injector Tip Cooling Module D | Closed
T-00046-0362 | PS5-60-EA-2900A | CZX01E - Package | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed
T-00046-0363 | PS5-60-EA-2900B | CZX01E - Package | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed
T-00046-0364 | PS5-60-EA-2900C | CZX01E - Package | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | Closed
T-00046-0365 | PS5-60-EA-2900D | CZX01E - Package | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | Closed
T-00046-0369 | PS5-60-TCV-0001A | CZX01E - Package | E | PS5-60-70 - Engine A Cooling system | Closed
T-00046-0370 | PS5-60-TCV-0001B | CZX01E - Package | E | PS5-60-71 - Engine B Cooling system | Closed
T-00046-0371 | PS5-60-TCV-0001C | CZX01E - Package | E | PS5-60-72 - Engine C Cooling system | Closed
T-00082-0454 | PS5-01-BI-0001 | CJX31 - Junction & marshalling box | I | PS5-01-05 - Foam Skid | Closed | CPP-RFI-68-64-05-0076
T-00082-0455 | PS5-01-BI-0002 | CJX31 - Junction & marshalling box | I | PS5-01-10 - Water Mist Package | Closed | CPP-RFI-68-64-05-0076
T-00082-0456 | PS5-01-BI-0003 | CJX31 - Junction & marshalling box | I | PS5-01-10 - Water Mist Package | Closed | CPP-RFI-68-64-05-0076
T-00082-0457 | PS5-01-BI-0004 | CJX31 - Junction & marshalling box | I | PS5-01-10 - Water Mist Package | Closed | CPP-RFI-68-64-05-0076
T-00082-0458 | PS5-01-BI-0005 | CJX31 - Junction & marshalling box | I | PS5-01-05 - Foam Skid | Closed | CPP-RFI-68-64-05-0076
T-00082-0460 | PS5-01-BI-1117 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0461 | PS5-01-BI-1118 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0462 | PS5-01-BI-1501 | CJX31 - Junction & marshalling box | I | PS5-01-07 - Fire Water Ring Main & Distribution | Closed | CPP-RFI-68-64-05-0062
T-00082-0463 | PS5-01-BI-1515 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0464 | PS5-01-BI-1520 | CJX31 - Junction & marshalling box | I | PS5-01-10 - Water Mist Package | Closed | CPP-RFI-68-64-05-0053 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done [OPEN] ¦ Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done [CLOSED] ¦ Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed [CLOSED]
T-00082-0465 | PS5-01-BI-1571 | CJX31 - Junction & marshalling box | I | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | Closed | CPP-RFI-68-64-05-0076
T-00082-0466 | PS5-01-BI-2110 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0467 | PS5-01-BI-2520 | CJX31 - Junction & marshalling box | I | PS5-01-10 - Water Mist Package | Closed | CPP-RFI-68-64-05-0053 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done [OPEN] ¦ Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done [CLOSED] ¦ Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed [CLOSED] ¦ Doc.UT-MID-60-WPR2-160101 -Junction Box TAG to be installed [OPEN]
T-00082-0468 | PS5-01-BI-2571A | CJX31 - Junction & marshalling box | I | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | Closed | CPP-RFI-68-64-05-0076
T-00082-0469 | PS5-01-BI-2571B | CJX31 - Junction & marshalling box | I | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | Closed | CPP-RFI-68-64-05-0076
T-00082-0470 | PS5-03-BI-1502 | CJX31 - Junction & marshalling box | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | Closed | CPP-RFI-68-64-05-0062
T-00082-0471 | PS5-03-BI-1503 | CJX31 - Junction & marshalling box | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | Closed | CPP-RFI-68-64-05-0057
T-00082-0472 | PS5-03-BI-1506 | CJX31 - Junction & marshalling box | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-05-0051 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done [OPEN]
T-00082-0473 | PS5-03-BI-1507 | CJX31 - Junction & marshalling box | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-05-0062
T-00082-0474 | PS5-03-BI-1508 | CJX31 - Junction & marshalling box | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-05-0058
T-00082-0475 | PS5-03-BI-1509 | CJX31 - Junction & marshalling box | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-05-0053 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done [OPEN] ¦ Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done [CLOSED] ¦ Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed [CLOSED]
T-00082-0476 | PS5-03-BI-1510 | CJX31 - Junction & marshalling box | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | Closed | CPP-RFI-68-64-05-0062
T-00082-0477 | PS5-03-BI-1511 | CJX31 - Junction & marshalling box | I | PS5-03-07 - FZ-07 - Pretreatment Area | Closed | CPP-RFI-68-64-05-0062
T-00082-0478 | PS5-03-BI-1512 | CJX31 - Junction & marshalling box | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | Closed | CPP-RFI-68-64-05-0065 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed [OPEN]
T-00082-0479 | PS5-03-BI-1513 | CJX31 - Junction & marshalling box | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | Closed | CPP-RFI-68-64-05-0065 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed [OPEN]
T-00082-0480 | PS5-03-BI-1514 | CJX31 - Junction & marshalling box | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | Closed | CPP-RFI-68-64-05-0065 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed [OPEN]
T-00082-0481 | PS5-03-BI-1516 | CJX31 - Junction & marshalling box | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | Closed | CPP-RFI-68-64-05-0065 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed [OPEN] | Doc.UT-MID-60-WPR2-160101 -Junction Box TAG to be installed [OPEN]
T-00082-0483 | PS5-03-BI-2502 | CJX31 - Junction & marshalling box | I | PS5-03-06 - FZ-06 - Transformer Area | Closed | CPP-RFI-68-64-05-0064
T-00082-0484 | PS5-03-BI-2503 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0064
T-00082-0485 | PS5-03-BI-2504 | CJX31 - Junction & marshalling box | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-05-0058
T-00082-0486 | PS5-03-BI-2505 | CJX31 - Junction & marshalling box | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | Closed | CPP-RFI-68-64-05-0076 |  |  | Doc.UT-MID-60-WPR2-160101 - Loose connection Grounding cable to the enclosure [OPEN]
T-00082-0487 | PS5-03-BI-2506 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0065 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed [OPEN]
T-00082-0488 | PS5-03-BI-2507 | CJX31 - Junction & marshalling box | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | Closed | CPP-RFI-68-64-05-0065 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed [OPEN]
T-00082-0489 | PS5-03-BI-2508 | CJX31 - Junction & marshalling box | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | Closed | CPP-RFI-68-64-05-0065 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed [OPEN]
T-00082-0490 | PS5-03-BI-2509 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0491 | PS5-03-BI-2510 | CJX31 - Junction & marshalling box | I | PS5-03-03 - FZ-03 - Buildings Area | Closed | CPP-RFI-68-64-05-0065 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed [OPEN]
T-00082-0492 | PS5-03-BI-2511 | CJX31 - Junction & marshalling box | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-05-0057
T-00082-0493 | PS5-03-BI-2512 | CJX31 - Junction & marshalling box | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | Closed | CPP-RFI-68-64-05-0057
T-00082-0494 | PS5-03-BI-2514 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0065 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed [OPEN]
T-00082-0495 | PS5-03-BI-2515 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0496 | PS5-05-BI-0002 | CJX31 - Junction & marshalling box | I | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-64-05-0076
T-00082-0500 | PS5-25-BI-1101 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0501 | PS5-25-BI-1102 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0502 | PS5-25-BI-1103 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0058
T-00082-0503 | PS5-25-BI-1104 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0057
T-00082-0504 | PS5-25-BI-1115 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0058
T-00082-0505 | PS5-25-BI-1174A | CJX31 - Junction & marshalling box | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-05-0076
T-00082-0506 | PS5-25-BI-1174B | CJX31 - Junction & marshalling box | I | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-64-05-0076
T-00082-0507 | PS5-25-BI-1174C | CJX31 - Junction & marshalling box | I | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-64-05-0076
T-00082-0508 | PS5-25-BI-1201 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0058
T-00082-0509 | PS5-25-BI-1274A | CJX31 - Junction & marshalling box | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-05-0076
T-00082-0510 | PS5-25-BI-1274B | CJX31 - Junction & marshalling box | I | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-64-05-0076
T-00082-0511 | PS5-25-BI-1274C | CJX31 - Junction & marshalling box | I | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-64-05-0076
T-00082-0512 | PS5-25-BI-1301 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0058
T-00082-0513 | PS5-25-BI-1302 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0057
T-00082-0514 | PS5-25-BI-1310 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0057
T-00082-0515 | PS5-25-BI-2101 | CJX31 - Junction & marshalling box | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-05-0062
T-00082-0516 | PS5-25-BI-2102 | CJX31 - Junction & marshalling box | I | PS5-25-07 - Export Pipeline Pig Launcher | Closed | CPP-RFI-68-64-05-0062
T-00082-0517 | PS5-25-BI-2103 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0518 | PS5-25-BI-2104 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0076 |  |  | Doc.UT-MID-60-WPR2-160101 - Loose connection Grounding cable to the enclosure [OPEN]
T-00082-0519 | PS5-25-BI-2105 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0058
T-00082-0520 | PS5-25-BI-2106 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0053 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done [OPEN] ¦ Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done [CLOSED] ¦ Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed [CLOSED]
T-00082-0521 | PS5-25-BI-2108 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0057
T-00082-0522 | PS5-25-BI-2109 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0057
T-00082-0523 | PS5-25-BI-2201 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0051 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done [OPEN] ¦ Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done [CLOSED] ¦ Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed [CLOSED]
T-00082-0524 | PS5-25-BI-2203 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0051 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done [OPEN] ¦ Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done [CLOSED] ¦ Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed [CLOSED]
T-00082-0525 | PS5-25-BI-2205 | CJX31 - Junction & marshalling box | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-05-0051 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done [OPEN] ¦ Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done [CLOSED] ¦ Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed [CLOSED]
T-00082-0526 | PS5-25-BI-2301 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0058
T-00082-0527 | PS5-25-BI-2302 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0058
T-00082-0528 | PS5-25-BI-2305 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0057
T-00082-0529 | PS5-25-BI-2308 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0053 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done [OPEN] ¦ Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done [CLOSED] ¦ Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed [CLOSED]
T-00082-0530 | PS5-25-BI-2309 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0058
T-00082-0531 | PS5-25-BI-2312 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0057
T-00082-0532 | PS5-25-BI-2315 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0057
T-00082-0533 | PS5-25-BI-2316 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0057
T-00082-0534 | PS5-28-BI-1105 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0064
T-00082-0535 | PS5-28-BI-1106 | CJX31 - Junction & marshalling box | I | PS5-28-06 - Relief Drum and Pump | Closed | CPP-RFI-68-64-05-0062
T-00082-0536 | PS5-28-BI-1114 | CJX31 - Junction & marshalling box | I | PS5-28-04 - Closed Drain Drum and Pump 02 | Closed | CPP-RFI-68-64-05-0062
T-00082-0537 | PS5-28-BI-1303 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0538 | PS5-28-BI-1307 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0539 | PS5-28-BI-2304 | CJX31 - Junction & marshalling box | I | PS5-28-17 - Reinjection Pump | Closed | CPP-RFI-68-64-05-0062
T-00082-0540 | PS5-50-BI-1107 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0541 | PS5-53-BI-1108 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0076 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed [OPEN]
T-00082-0542 | PS5-53-BI-1304 | CJX31 - Junction & marshalling box | I | PS5-53-01 - Utility Water / Storage Tank | Closed | CPP-RFI-68-64-05-0064 |  |  |  | Doc.UT-MID-60-WPR2-160101 -Junction Box TAG to be installed [OPEN]
T-00082-0543 | PS5-71-BI-1109 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0051
T-00082-0544 | PS5-71-BI-1110 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0058
T-00082-0545 | PS5-71-BI-1111 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0057
T-00082-0546 | PS5-71-BI-1112 | CJX31 - Junction & marshalling box | I | PS5-71-17 - Diesel Fuel Distribution Header | Closed | CPP-RFI-68-64-05-0076
T-00082-0547 | PS5-71-BI-1113 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0057
T-00082-0548 | PS5-71-BI-1116 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0051 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done [OPEN]
T-00082-0549 | PS5-71-BI-1117 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0058
T-00082-0550 | PS5-71-BI-1305 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0051 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done [OPEN]
T-00082-0551 | PS5-71-BI-1306 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0051 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done [OPEN]
T-00082-0552 | PS5-71-BI-1308 | CJX31 - Junction & marshalling box | I | PS5-71-15 - Diesel Fuel Storage Tank | Closed | CPP-RFI-68-64-05-0057
T-00082-0553 | PS5-71-BI-2101 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0058
T-00082-0554 | PS5-71-BI-2107 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0058
T-00082-0555 | PS5-71-BI-2113 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0057
T-00082-0556 | PS5-71-BI-2114 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0057
T-00082-0557 | PS5-71-BI-2115 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0057
T-00082-0558 | PS5-71-BI-2116 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0559 | PS5-71-BI-2118 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0053 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done [OPEN] ¦ Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done [CLOSED] ¦ Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed [CLOSED]
T-00082-0560 | PS5-71-BI-2119 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0561 | PS5-71-BI-2120 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0562 | PS5-71-BI-2121 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0065 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed [OPEN]
T-00082-0563 | PS5-71-BI-2122 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0053 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done [OPEN] ¦ Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done [CLOSED] ¦ Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed [CLOSED] ¦ Doc.UT-MID-60-WPR2-160101 -Junction Box TAG to be Installed [OPEN]
T-00082-0564 | PS5-71-BI-2123 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0565 | PS5-71-BI-2124 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0566 | PS5-71-BI-2125 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0065 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed [OPEN]
T-00082-0567 | PS5-71-BI-2306 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0051 |  |  | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done [OPEN]
T-00082-0568 | PS5-71-BI-2307 | CJX31 - Junction & marshalling box | I | PS5-71-15 - Diesel Fuel Storage Tank | Closed | CPP-RFI-68-64-05-0057
T-00082-0569 | PS5-71-BI-2310 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0062
T-00082-0570 | PS5-71-BI-2313 | CJX31 - Junction & marshalling box | I | PS5-71-15 - Diesel Fuel Storage Tank | Closed | CPP-RFI-68-64-05-0057
T-00082-0571 | PS5-71-BI-2314 | CJX31 - Junction & marshalling box | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-05-0058
T-00082-0572 | PS5-71-BI-2317 | CJX31 - Junction & marshalling box | I | PS5-71-15 - Diesel Fuel Storage Tank | Closed | CPP-RFI-68-64-05-0057
T-00087-0501 | PS5-60-LA-0002B | CJX48 - Indoor cabinet / panel | I | PS5-60-10 - Power Generation Package D | Closed |  |  |  |  | TZ-MID-68-UTR1-150016 ISE bar not connected to isolated earth grid [OPEN] | TZ-MID-68-UTR1-150016 Cleanning internal and external of the panel [OPEN] ¦ TZ-MID-68-UTR1-150016 The Panel Frame need to be touch up paint and un-used hole to be closed [OPEN]
T-00087-0502 | PS5-60-LA-0002C | CJX48 - Indoor cabinet / panel | I | PS5-60-16 - Power Generation Package F | Closed |  |  |  |  | TZ-MID-68-UTR1-150016 ISE bar not connected to isolated earth grid [OPEN] | TZ-MID-68-UTR1-150016 Cleanning internal and external of the panel [OPEN] ¦ TZ-MID-68-UTR1-150016 The Panel Frame need to be touch up paint and un-used hole to be closed [OPEN]
T-00227-0112 | PS5-61-IU-3100A | TPX02 - Power transformer | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-332-02-0304 | CPP-RFI-68-332-16-0326 |  |  |  | TZ-MID-68-WPR2-151111 Cleanning body transformer and areas [OPEN]
T-00227-0113 | PS5-61-IU-3100B | TPX02 - Power transformer | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-332-02-0304 | CPP-RFI-68-332-16-0326 |  |  |  | TZ-MID-68-WPR2-151111 Cleanning body transformer and areas [OPEN]
T-00227-0114 | PS5-61-IU-3100C | TPX02 - Power transformer | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-332-02-0304 | CPP-RFI-68-332-16-0326 |  |  |  | TZ-MID-68-WPR2-151111 Cleanning body transformer and areas [OPEN]
T-00227-0152 | PS5-61-IV-0001A | TPX02 - Power transformer | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-332-02-0331 | CPP-RFI-68-332-16-0332 |  |  | TZ-MID-68-WPR2-151112 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding [OPEN] | TZ-MID-68-WPR2-151112 Carry out cleanning body of the transformer and surrounding bay area [OPEN]
T-00227-0153 | PS5-61-IV-0001B | TPX02 - Power transformer | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-332-02-0395 | CPP-RFI-68-332-16-0396 |  | TZ-MID-68-WPR2-151112 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding [OPEN] ¦ TZ-MID-68-WPR2-151112 Transformer Grounding Not Complete [OPEN]
T-00227-0162 | PS5-61-IV-0002A | TPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-332-02-0395 | CPP-RFI-68-332-16-0396 |  | Doc.TZ-MID-68-WPR2-151112 - Missing Support by CPP1 [CLOSED] ¦ Doc.TZ-MID-68-WPR2-151112 - Cable Ladder not installed [CLOSED] ¦ TZ-MID-68-WPR2-151167 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding [OPEN] ¦ TZ-MID-68-WPR2-151167 Transformer Grounding Not Complete [OPEN] |  | Doc.TZ-MID-68-WPR2-151112 HV Trefoil Cable Clamp not installed [OPEN]
T-00227-0163 | PS5-61-IV-0002B | TPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-332-02-0395 | CPP-RFI-68-332-16-0396 |  | Doc.TZ-MID-68-WPR2-151112 - Missing Support by CPP1 [CLOSED] ¦ TZ-MID-68-WPR2-151167 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding [OPEN] ¦ TZ-MID-68-WPR2-151167 Transformer Grounding Not Complete [OPEN] |  | Doc.TZ-MID-68-WPR2-151112 HV Trefoil Cable Clamp not installed [OPEN]
T-00227-0164 | PS5-61-IV-0007A | TPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-332-02-0395 | CPP-RFI-68-332-16-0396 |  | TZ-MID-68-WPR2-151167 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding [OPEN] ¦ TZ-MID-68-WPR2-151167 Transformer Grounding Not Complete [OPEN] | Doc.TZ-MID-68-WPR2-151112 HV Trefoil Cable Clamp not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-151112 - Missing Support by CPP1 [CLOSED]
T-00227-0165 | PS5-61-IV-0007B | TPX02 - Power transformer | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-332-02-0395 | CPP-RFI-68-332-16-0396 |  | TZ-MID-68-WPR2-151167 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding [OPEN] ¦ TZ-MID-68-WPR2-151167 Transformer Grounding Not Complete [OPEN] | Doc.TZ-MID-68-WPR2-151112 HV Trefoil Cable Clamp not installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-151112 - Missing Support by CPP1 [CLOSED]
T-00228-0096 | PS5-79-IV-0001 | TPX03 - LV transformer | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | Closed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00228-0097 | PS5-79-IV-0002 | TPX03 - LV transformer | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | Closed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00228-0098 | PS5-79-IV-0003 | TPX03 - LV transformer | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | Closed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00228-0099 | PS5-79-IV-0004 | TPX03 - LV transformer | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | Closed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00228-0100 | PS5-79-IV-0005 | TPX03 - LV transformer | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | Closed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00228-0101 | PS5-79-IV-0006 | TPX03 - LV transformer | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | Closed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  | TZ-MID-68-WPR2-151117 Rectify concrete broken 1 pcs anchor bolt [OPEN] | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00228-0102 | PS5-79-IV-0007 | TPX03 - LV transformer | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | Closed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00228-0103 | PS5-79-IV-0008 | TPX03 - LV transformer | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | Closed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00228-0104 | PS5-79-IV-0009 | TPX03 - LV transformer | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | Closed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00228-0105 | PS5-79-IV-0010 | TPX03 - LV transformer | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | Closed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00228-0106 | PS5-79-IV-0011 | TPX03 - LV transformer | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | Closed | CPP-RFI-68-33/2-02-0301 | CPP-RFI-68-33/2-16-0327 |  |  |  | TZ-MID-68-WPR2-151118 To perform cleanning for EHT Transformer body and surround area [OPEN]
T-00232-0952 | PS5-25-DM-3100A-CH01 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0953 | PS5-25-DM-3100A-CH02 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0954 | PS5-25-DM-3100A-CH03 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0955 | PS5-25-DM-3100A-CH04 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0956 | PS5-25-DM-3100A-CH05 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0957 | PS5-25-DM-3100A-CH06 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0958 | PS5-25-DM-3100B-CH01 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0959 | PS5-25-DM-3100B-CH02 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0960 | PS5-25-DM-3100B-CH03 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0961 | PS5-25-DM-3100B-CH04 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0962 | PS5-25-DM-3100B-CH05 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0963 | PS5-25-DM-3100B-CH06 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0964 | PS5-25-DM-3100C-CH01 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0965 | PS5-25-DM-3100C-CH02 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0966 | PS5-25-DM-3100C-CH03 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0967 | PS5-25-DM-3100C-CH04 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0968 | PS5-25-DM-3100C-CH05 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0969 | PS5-25-DM-3100C-CH06 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0216 | CPP-RFI-68-33/1-07-0208
T-00232-0970 | PS5-60-IJ-0001A-CH04 | TPX08 - HV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-168 | CPP-RFI-68-33/1-07-0175
T-00232-0971 | PS5-60-IJ-0001B-CH04 | TPX08 - HV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-168 | CPP-RFI-68-33/1-07-0175
T-00232-0972 | PS5-60-IJ-0001C-CH04 | TPX08 - HV power cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-33/1-05-168 | CPP-RFI-68-33/1-07-0175
T-00232-0973 | PS5-60-IJ-0001D-CH04 | TPX08 - HV power cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-33/1-05-168 | CPP-RFI-68-33/1-07-0175
T-00232-0974 | PS5-60-IJ-0001E-CH04 | TPX08 - HV power cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-33/1-05-168 | CPP-RFI-68-33/1-07-0175
T-00232-0975 | PS5-60-IJ-0001F-CH04 | TPX08 - HV power cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-33/1-05-168 | CPP-RFI-68-33/1-07-0175
T-00232-0976 | PS5-60-IJ-0001G-CH04 | TPX08 - HV power cable | E | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-33/1-05-168 | CPP-RFI-68-33/1-07-0175
T-00232-0977 | PS5-61-IDH-3100A-CH01 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0978 | PS5-61-IDH-3100A-CH02 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0979 | PS5-61-IDH-3100A-CH03 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0980 | PS5-61-IDH-3100A-CH04 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0981 | PS5-61-IDH-3100A-CH05 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0982 | PS5-61-IDH-3100A-CH06 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0983 | PS5-61-IDH-3100A-CH07 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0984 | PS5-61-IDH-3100A-CH08 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0985 | PS5-61-IDH-3100A-CH09 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0986 | PS5-61-IDH-3100A-CH10 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0987 | PS5-61-IDH-3100A-CH11 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0988 | PS5-61-IDH-3100A-CH12 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0989 | PS5-61-IDH-3100B-CH01 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0990 | PS5-61-IDH-3100B-CH02 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0991 | PS5-61-IDH-3100B-CH03 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0992 | PS5-61-IDH-3100B-CH04 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0993 | PS5-61-IDH-3100B-CH05 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0994 | PS5-61-IDH-3100B-CH06 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0995 | PS5-61-IDH-3100B-CH07 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0996 | PS5-61-IDH-3100B-CH08 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0997 | PS5-61-IDH-3100B-CH09 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0998 | PS5-61-IDH-3100B-CH10 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-0999 | PS5-61-IDH-3100B-CH11 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-1000 | PS5-61-IDH-3100B-CH12 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-1001 | PS5-61-IDH-3100C-CH01 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-1002 | PS5-61-IDH-3100C-CH02 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-1003 | PS5-61-IDH-3100C-CH03 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-1004 | PS5-61-IDH-3100C-CH04 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-1005 | PS5-61-IDH-3100C-CH05 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-1006 | PS5-61-IDH-3100C-CH06 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-1007 | PS5-61-IDH-3100C-CH07 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-1008 | PS5-61-IDH-3100C-CH08 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-1009 | PS5-61-IDH-3100C-CH09 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-1010 | PS5-61-IDH-3100C-CH10 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-1011 | PS5-61-IDH-3100C-CH11 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-1012 | PS5-61-IDH-3100C-CH12 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-1013 | PS5-61-IJ-0001-CH01 | TPX08 - HV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1014 | PS5-61-IJ-0001-CH02 | TPX08 - HV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1015 | PS5-61-IJ-0001-CH03 | TPX08 - HV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1016 | PS5-61-IJ-0001-CH04 | TPX08 - HV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1017 | PS5-61-IJ-0001-CH05 | TPX08 - HV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1018 | PS5-61-IJ-0001-CH06 | TPX08 - HV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1019 | PS5-61-IJ-0001-CH07 | TPX08 - HV power cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1020 | PS5-61-IJ-0001-CH08 | TPX08 - HV power cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1021 | PS5-61-IJ-0001-CH09 | TPX08 - HV power cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1022 | PS5-61-IJ-0001-CH10 | TPX08 - HV power cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1023 | PS5-61-IJ-0001-CH11 | TPX08 - HV power cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1024 | PS5-61-IJ-0001-CH12 | TPX08 - HV power cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1025 | PS5-61-IJ-0001-CH13 | TPX08 - HV power cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1026 | PS5-61-IJ-0001-CH14 | TPX08 - HV power cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1027 | PS5-61-IJ-0001-CH15 | TPX08 - HV power cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1028 | PS5-61-IJ-0001-CH16 | TPX08 - HV power cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1029 | PS5-61-IJ-0001-CH17 | TPX08 - HV power cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1030 | PS5-61-IJ-0001-CH18 | TPX08 - HV power cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1031 | PS5-61-IJ-0001-CH19 | TPX08 - HV power cable | E | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1032 | PS5-61-IJ-0001-CH20 | TPX08 - HV power cable | E | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1033 | PS5-61-IJ-0001-CH21 | TPX08 - HV power cable | E | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-33/1-05-0196 | CPP-RFI-68-33/1-07-0199
T-00232-1034 | PS5-61-IJ-0010-CH01 | TPX08 - HV power cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | Closed | CPP-RFI-68-33/1-05-0198 | CPP-RFI-68-33/1-07-201
T-00232-1035 | PS5-61-IJ-0010-CH02 | TPX08 - HV power cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | Closed | CPP-RFI-68-33/1-05-0198 | CPP-RFI-68-33/1-07-201
T-00232-1036 | PS5-61-IJ-0010-CH03 | TPX08 - HV power cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | Closed | CPP-RFI-68-33/1-05-0198 | CPP-RFI-68-33/1-07-201
T-00232-1037 | PS5-61-IJ-0011-CH01 | TPX08 - HV power cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | Closed | CPP-RFI-68-33/1-05-0198 | CPP-RFI-68-33/1-07-201
T-00232-1038 | PS5-61-IJ-0011-CH02 | TPX08 - HV power cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | Closed | CPP-RFI-68-33/1-05-0198 | CPP-RFI-68-33/1-07-201
T-00232-1039 | PS5-61-IJ-0011-CH03 | TPX08 - HV power cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | Closed | CPP-RFI-68-33/1-05-0198 | CPP-RFI-68-33/1-07-201
T-00232-1040 | PS5-61-ISR-0101-CH01 | TPX08 - HV power cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-33/1-05-0197
T-00232-1041 | PS5-61-ISR-0101-CH02 | TPX08 - HV power cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-200
T-00232-1042 | PS5-61-ISR-0101-CH03 | TPX08 - HV power cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-200
T-00232-1043 | PS5-61-ISR-0102-CH01 | TPX08 - HV power cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00232-1044 | PS5-61-ISR-0102-CH02 | TPX08 - HV power cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00232-1045 | PS5-61-ISR-0102-CH03 | TPX08 - HV power cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00232-1046 | PS5-61-IU-0001A-CH01 | TPX08 - HV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1047 | PS5-61-IU-0001A-CH02 | TPX08 - HV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1048 | PS5-61-IU-0001A-CH03 | TPX08 - HV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1049 | PS5-61-IU-0001B-CH01 | TPX08 - HV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1050 | PS5-61-IU-0001B-CH02 | TPX08 - HV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1051 | PS5-61-IU-0001B-CH03 | TPX08 - HV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1052 | PS5-61-IU-0001C-CH01 | TPX08 - HV power cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1053 | PS5-61-IU-0001C-CH02 | TPX08 - HV power cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1054 | PS5-61-IU-0001C-CH03 | TPX08 - HV power cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1055 | PS5-61-IU-0001D-CH01 | TPX08 - HV power cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1056 | PS5-61-IU-0001D-CH02 | TPX08 - HV power cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1057 | PS5-61-IU-0001D-CH03 | TPX08 - HV power cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1058 | PS5-61-IU-0001E-CH01 | TPX08 - HV power cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1059 | PS5-61-IU-0001E-CH02 | TPX08 - HV power cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1060 | PS5-61-IU-0001E-CH03 | TPX08 - HV power cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1061 | PS5-61-IU-0001F-CH01 | TPX08 - HV power cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1062 | PS5-61-IU-0001F-CH02 | TPX08 - HV power cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1063 | PS5-61-IU-0001F-CH03 | TPX08 - HV power cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1064 | PS5-61-IU-0001G-CH01 | TPX08 - HV power cable | E | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1065 | PS5-61-IU-0001G-CH02 | TPX08 - HV power cable | E | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1066 | PS5-61-IU-0001G-CH03 | TPX08 - HV power cable | E | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-33/1-05-161 | CPP-RFI-68-33/1-07-169
T-00232-1067 | PS5-61-IU-0010-CH01 | TPX08 - HV power cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-200
T-00232-1068 | PS5-61-IU-0010-CH02 | TPX08 - HV power cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-200
T-00232-1069 | PS5-61-IU-0010-CH03 | TPX08 - HV power cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-200
T-00232-1070 | PS5-61-IU-0011-CH01 | TPX08 - HV power cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-200
T-00232-1071 | PS5-61-IU-0011-CH02 | TPX08 - HV power cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-200
T-00232-1072 | PS5-61-IU-0011-CH03 | TPX08 - HV power cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-200
T-00232-1073 | PS5-61-IU-3100A-CH01 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00232-1074 | PS5-61-IU-3100A-CH02 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00232-1075 | PS5-61-IU-3100A-CH03 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00232-1076 | PS5-61-IU-3100A-CH04 | TPX08 - HV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-1077 | PS5-61-IU-3100B-CH01 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00232-1078 | PS5-61-IU-3100B-CH02 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00232-1079 | PS5-61-IU-3100B-CH03 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00232-1080 | PS5-61-IU-3100B-CH04 | TPX08 - HV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-1081 | PS5-61-IU-3100C-CH01 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00232-1082 | PS5-61-IU-3100C-CH02 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00232-1083 | PS5-61-IU-3100C-CH03 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-181 | CPP-RFI-68-33/1-07-0185
T-00232-1084 | PS5-61-IU-3100C-CH04 | TPX08 - HV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0192 | CPP-RFI-68-33/1-07-0195
T-00232-1085 | PS5-61-IV-0001A-CH01 | TPX08 - HV power cable | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00232-1086 | PS5-61-IV-0001A-CH02 | TPX08 - HV power cable | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00232-1087 | PS5-61-IV-0001A-CH03 | TPX08 - HV power cable | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00232-1088 | PS5-61-IV-0001B-CH01 | TPX08 - HV power cable | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00232-1089 | PS5-61-IV-0001B-CH02 | TPX08 - HV power cable | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00232-1090 | PS5-61-IV-0001B-CH03 | TPX08 - HV power cable | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00232-1091 | PS5-61-IV-0002A-CH01 | TPX08 - HV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00232-1092 | PS5-61-IV-0002A-CH02 | TPX08 - HV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00232-1093 | PS5-61-IV-0002A-CH03 | TPX08 - HV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00232-1094 | PS5-61-IV-0002B-CH01 | TPX08 - HV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00232-1095 | PS5-61-IV-0002B-CH02 | TPX08 - HV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00232-1096 | PS5-61-IV-0002B-CH03 | TPX08 - HV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00232-1103 | PS5-61-IV-0007A-CH01 | TPX08 - HV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00232-1104 | PS5-61-IV-0007A-CH02 | TPX08 - HV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00232-1105 | PS5-61-IV-0007A-CH03 | TPX08 - HV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00232-1106 | PS5-61-IV-0007B-CH01 | TPX08 - HV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00232-1107 | PS5-61-IV-0007B-CH02 | TPX08 - HV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00232-1108 | PS5-61-IV-0007B-CH03 | TPX08 - HV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0184 | CPP-RFI-68-33/1-07-0191 |  |  | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done [OPEN]
T-00232-1109 | PS5-61-NER-0010-CH01 | TPX08 - HV power cable | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | Closed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151112 Cable ladder at transformer side not yet install PS5-61-IU-0010 [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete termination [OPEN] | TZ-MID-68-WPR2-151112 Cable Dressing to be done at both side [OPEN]
T-00232-1110 | PS5-61-NER-0011-CH01 | TPX08 - HV power cable | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | Closed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151112 Cable ladder at transformer side not yet install PS5-61-IU-0011 [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete termination [OPEN] | TZ-MID-68-WPR2-151112 Cable Dressing to be done at both side [OPEN]
T-00232-1111 | PS5-63-IV-0010-CH01 | TPX08 - HV power cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00232-1112 | PS5-63-IV-0010-CH02 | TPX08 - HV power cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00232-1113 | PS5-63-IV-0010-CH03 | TPX08 - HV power cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00232-1114 | PS5-63-IV-0011-CH01 | TPX08 - HV power cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00232-1115 | PS5-63-IV-0011-CH02 | TPX08 - HV power cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00232-1116 | PS5-63-IV-0011-CH03 | TPX08 - HV power cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-33/1-05-0197 | CPP-RFI-68-33/1-07-0200
T-00232-1117 | PS5-63-NER-0010-CH01 | TPX08 - HV power cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-331-05-0210 | CPP-RFI-68-331-07-0209 |  | TZ-MID-68-WPR2-151112 Cable ladder to be install at transformer side (PS5-88-LD-HV-6019) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench backfilled to be done (PS5-88-CU-HV-0031) [OPEN] | TZ-MID-68-WPR2-151112 Cable dressing to be done at both side [OPEN]
T-00232-1118 | PS5-63-NER-0011-CH01 | TPX08 - HV power cable | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | Closed | CPP-RFI-68-331-05-0210 | CPP-RFI-68-331-07-0209 |  | TZ-MID-68-WPR2-151112 Cable ladder to be install at transformer side (PS5-88-LD-HV-6020) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench backfilled to be done (PS5-88-CU-HV-0030) [OPEN] | TZ-MID-68-WPR2-151112 Cable dressing to be done at both side [OPEN]
T-00233-10584 | PS5-05-BE-0001-CG01 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet install at EDG side [OPEN] | TZ-MID-68-WPR2-151111 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151111 Dressing to be done at both end [OPEN]
T-00233-10587 | PS5-25-DM-3100A-CG01 | TPX09 - LV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable dressing to be done both side [OPEN]
T-00233-10588 | PS5-25-DM-3100A-CG02 | TPX09 - LV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable dressing to be done both side [OPEN]
T-00233-10589 | PS5-25-DM-3100B-CG01 | TPX09 - LV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Permanent cable tag to be install [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable actual laid in the HV Cable trench PS5-88-CU-HV-0002 in drawing mention PS5-88-CU-LV-0011 need to be RLMU drawing as per actual. (Dwg No.TZ-MID-68-WPR2-151114) [OPEN]
T-00233-10590 | PS5-25-DM-3100B-CG02 | TPX09 - LV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Permanent cable tag to be install [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable actual laid in the HV Cable trench PS5-88-CU-HV-0002 in drawing mention PS5-88-CU-LV-0011 need to be RLMU drawing as per actual. (Dwg No.TZ-MID-68-WPR2-151114) [OPEN]
T-00233-10591 | PS5-25-DM-3100C-CG01 | TPX09 - LV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Permanent cable tag to be install [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable actual laid in the HV Cable trench PS5-88-CU-HV-0001 in drawing mention PS5-88-CU-LV-0012 need to be RLMU drawing as per actual. (Dwg No.TZ-MID-68-WPR2-151114) [OPEN]
T-00233-10592 | PS5-25-DM-3100C-CG02 | TPX09 - LV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Permanent cable tag to be install [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Cable actual laid in the HV Cable trench PS5-88-CU-HV-0001 in drawing mention PS5-88-CU-LV-0012 need to be RLMU drawing as per actual. (Dwg No.TZ-MID-68-WPR2-151114) [OPEN]
T-00233-10600 | PS5-60-IH-0002-CG01 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-10601 | PS5-60-IH-0002-CG02 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-10616 | PS5-61-IK-0003-CG07 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable Trench Not yet complete installation [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Dressing Cable Both Side to be done [OPEN] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Permanent Cable Tag Missing Both End [CLOSED]
T-00233-10890 | PS5-60-BE-0007A-CL02 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN]
T-00233-10891 | PS5-60-BE-0007A-CL03 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN]
T-00233-10892 | PS5-60-BE-0007B-CL02 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN]
T-00233-10893 | PS5-60-BE-0007B-CL03 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN]
T-00233-10894 | PS5-60-BE-0007C-CL02 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | Closed |  | CPP-RFI-68-33/1-07-0410
T-00233-10895 | PS5-60-BE-0007C-CL03 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | Closed |  | CPP-RFI-68-33/1-07-0410
T-00233-10896 | PS5-60-BE-0007D-CL02 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151179, Cable Coiled in Control Panel Side, Not yet Reaching Final Destination [OPEN] | Doc. TZ-MID-68-WPR2-151179, Cable Tagging not yet installed at both side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179, Cable Dressing not yet done [OPEN]
T-00233-10897 | PS5-60-BE-0007D-CL03 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151179, Cable Coiled in Control Panel Side, Not yet Reaching Final Destination [OPEN] | Doc. TZ-MID-68-WPR2-151179, Cable Tagging not yet installed at both side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179, Cable dresing not yet done [OPEN]
T-00233-10898 | PS5-60-BE-0007E-CL02 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | Closed |  | CPP-RFI-68-33/1-07-0410
T-00233-10899 | PS5-60-BE-0007E-CL03 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | Closed |  | CPP-RFI-68-33/1-07-0410
T-00233-10900 | PS5-60-BE-0007F-CL02 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | Closed |  | CPP-RFI-68-33/1-07-0410
T-00233-10901 | PS5-60-BE-0007F-CL03 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | Closed |  | CPP-RFI-68-33/1-07-0410
T-00233-10902 | PS5-60-BE-0007G-CL02 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | Closed |  | CPP-RFI-68-33/1-07-0410
T-00233-10903 | PS5-60-BE-0007G-CL03 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | Closed |  | CPP-RFI-68-33/1-07-0410
T-00233-10904 | PS5-60-ISO-62800A-CL01 | TPX09 - LV power cable | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done [OPEN]
T-00233-10905 | PS5-60-ISO-62800C-CL01 | TPX09 - LV power cable | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-10906 | PS5-60-ISO-62800E-CL01 | TPX09 - LV power cable | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray not finished [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done [OPEN]
T-00233-10907 | PS5-60-ISO-62800G-CL01 | TPX09 - LV power cable | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-331-07-0423
T-00233-11061 | PS5-05-BE-0001-CL12 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  | TZ-MID-68-WPR2-151111, 151112, 151116 To be install vertical cable ladder at EDG Junction box side [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00233-4695 | PS5-01-BE-0001-CL01 | TPX09 - LV power cable | E | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | Closed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  | TZ-MID-68-WPR2-151117 Need to Open trench at PS5-05-IG-0004 side (PS5-88-BU-LV-00165, PS5-88-BU-LV-00164). [OPEN] ¦ TZ-MID-68-WPR2-151117 Cable to be laid inside conduit at PS5-01-BE-0001 side. [OPEN] | TZ-MID-68-WPR2-151117 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151117 Cable dressing to be done both side [OPEN]
T-00233-4696 | PS5-01-FCV-0003A-CL01 | TPX09 - LV power cable | E | PS5-01-02 - Fire Water Pump A | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely [OPEN]
T-00233-4697 | PS5-01-FCV-0003B-CL01 | TPX09 - LV power cable | E | PS5-01-03 - Fire Water Pump B | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely [OPEN]
T-00233-4698 | PS5-01-FCV-0004A-CL01 | TPX09 - LV power cable | E | PS5-01-01 - Fire Water Jockey Pump A/B | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed [CLOSED]
T-00233-4699 | PS5-01-FCV-0004B-CL01 | TPX09 - LV power cable | E | PS5-01-01 - Fire Water Jockey Pump A/B | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed [CLOSED]
T-00233-4710 | PS5-01-IG-0001-CL01 | TPX09 - LV power cable | E | PS5-01-10 - Water Mist Package | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-4711 | PS5-01-LB-0004-CL01 | TPX09 - LV power cable | E | PS5-01-11 - Inergen for Power Gen Building | Closed |  | CPP-RFI-68-33/1-07-0405
T-00233-4713 | PS5-01-LB-0004-CL03 | TPX09 - LV power cable | E | PS5-01-11 - Inergen for Power Gen Building | Closed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  |  | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side [OPEN]
T-00233-4714 | PS5-01-MOV-8701-CL01 | TPX09 - LV power cable | E | PS5-01-05 - Foam Skid | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-4727 | PS5-05-BE-0001-CL01 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00233-4728 | PS5-05-BE-0001-CL02 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00233-4729 | PS5-05-BE-0001-CL03 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00233-4730 | PS5-05-BE-0001-CL04 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00233-4731 | PS5-05-BE-0001-CL05 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00233-4732 | PS5-05-BE-0001-CL06 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00233-4733 | PS5-05-BE-0001-CL07 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00233-4734 | PS5-05-BE-0001-CL08 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00233-4735 | PS5-05-BE-0001-CL09 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00233-4736 | PS5-05-BE-0001-CL10 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00233-4737 | PS5-05-BE-0001-CL11 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). [OPEN] | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151111 Cable dressing to be done both side [OPEN]
T-00233-4738 | PS5-05-IE-8100-CL01 | TPX09 - LV power cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-4739 | PS5-05-IE-8100-CL02 | TPX09 - LV power cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-4742 | PS5-05-IG-0009-CL01 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151167, 151116, 151112, 151111-SS Tag on both ends not installed [OPEN] ¦ TZ-MID-68-WPR2-151167, 151116, 151112, 151111-Cable dressing not yet done completely [OPEN]
T-00233-4743 | PS5-05-IG-0009-CL02 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0278 |  |  | TZ-MID-68-WPR2-151167, 151116, 151112, 151111-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151167, 151116, 151112, 151111-Cable dressing not yet done completely [OPEN]
T-00233-4744 | PS5-05-IG-0025-CL01 | TPX09 - LV power cable | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | Closed | CPP-RFI-68-33/1-05-0309 | CPP-RFI-68-331-07-0310 |  | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable Reaching final Destination, But need to Install Cable Tray [OPEN] | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable Tagging Installaton not Yet Done at Both Side [OPEN] ¦ TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable Dressing not yet done [OPEN]
T-00233-4745 | PS5-05-IG-0026-CL01 | TPX09 - LV power cable | E | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | Closed | CPP-RFI-68-33/1-05-0309 | CPP-RFI-68-331-07-0310 |  | TZ-MID-68-WPR2-151166, Cable Not Reaching Final Destination [OPEN] | TZ-MID-68-WPR2-151166, Cable Tagging Installation not Yet Done at Both Side [OPEN] ¦ TZ-MID-68-WPR2-151166, Cable Dressing not yet done [OPEN]
T-00233-4746 | PS5-06-GB-0003-CL01 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00233-4747 | PS5-06-GB-0003-CL02 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00233-4748 | PS5-06-GB-0003-CL03 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00233-4749 | PS5-06-GB-0003-CL04 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00233-4750 | PS5-06-GB-0003-CL05 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00233-4751 | PS5-06-GB-0003-CL06 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00233-4752 | PS5-06-GU-0003A-CL01 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00233-4753 | PS5-06-GU-0003B-CL01 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00233-4754 | PS5-06-GU-0003C-CL01 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00233-4756 | PS5-06-IG-0004A-CL01 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00233-4757 | PS5-06-IG-0004A-CL02 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00233-4758 | PS5-06-IG-0004A-CL03 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00233-4759 | PS5-06-IG-0004A-CL04 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00233-4761 | PS5-06-IG-0004B-CL01 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00233-4762 | PS5-06-IG-0004B-CL02 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00233-4763 | PS5-06-IG-0004B-CL03 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00233-4764 | PS5-06-IG-0004B-CL04 | TPX09 - LV power cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-33/1-05-0298 | CPP-RFI-68-33/1-07-0299 |  |  | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side [OPEN]
T-00233-4808 | PS5-08-11CB-1501-CL01 | TPX09 - LV power cable | E | PS5-08-11 - Corporate LAN (SIE) | Closed |  | CPP-RFI-68-331-07-0409
T-00233-4882 | PS5-25-DM-3100A-CL01 | TPX09 - LV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0286 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00233-4883 | PS5-25-DM-3100A-CL02 | TPX09 - LV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0286 |  |  | TZ-MID-68-WPR2-151111, 151115, 151117, 151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151115, 151117, 151114-Cable dressing not yet done completely [OPEN]
T-00233-4886 | PS5-25-DM-3100B-CL01 | TPX09 - LV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0286 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00233-4887 | PS5-25-DM-3100B-CL02 | TPX09 - LV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0286 |  |  | TZ-MID-68-WPR2-151111, 151115, 151117, 151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151115, 151117, 151114-Cable dressing not yet done completely [OPEN]
T-00233-4890 | PS5-25-DM-3100C-CL01 | TPX09 - LV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0286 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00233-4891 | PS5-25-DM-3100C-CL02 | TPX09 - LV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0286 |  |  | TZ-MID-68-WPR2-151111, 151115, 151117, 151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151115, 151117, 151114-Cable dressing not yet done completely [OPEN]
T-00233-4904 | PS5-25-ESDV-0021-CL01 | TPX09 - LV power cable | E | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0042) [OPEN] | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN]
T-00233-4905 | PS5-25-ESDV-0023-CL01 | TPX09 - LV power cable | E | PS5-25-07 - Export Pipeline Pig Launcher | Closed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0042) [OPEN] | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN]
T-00233-4906 | PS5-25-FCV-0003A-CL01 | TPX09 - LV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0042) [OPEN] | TZ-MID-68-WPR2-151117,151114 Permanent Cable tag not yet installed. [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN]
T-00233-4907 | PS5-25-FCV-0003B-CL01 | TPX09 - LV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0042) [OPEN] | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN]
T-00233-4908 | PS5-25-FCV-0003C-CL01 | TPX09 - LV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0043) [OPEN] | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN]
T-00233-4909 | PS5-25-FCV-0004-CL01 | TPX09 - LV power cable | E | PS5-25-06 - Crude Oil Export Pumps Discharge | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-4918 | PS5-25-MOV-0001-CL01 | TPX09 - LV power cable | E | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely [OPEN]
T-00233-4919 | PS5-25-MOV-0002-CL01 | TPX09 - LV power cable | E | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely [OPEN]
T-00233-4920 | PS5-25-MOV-0003-CL01 | TPX09 - LV power cable | E | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely [OPEN]
T-00233-4921 | PS5-25-MOV-0008-CL01 | TPX09 - LV power cable | E | PS5-25-07 - Export Pipeline Pig Launcher | Closed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151114,151113 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. [OPEN] | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS cable tags to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable need to be dressing completely at both side [OPEN]
T-00233-4922 | PS5-25-MOV-0011-CL01 | TPX09 - LV power cable | E | PS5-25-07 - Export Pipeline Pig Launcher | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely [OPEN]
T-00233-4923 | PS5-25-MOV-0012-CL01 | TPX09 - LV power cable | E | PS5-25-07 - Export Pipeline Pig Launcher | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely [OPEN]
T-00233-4924 | PS5-25-MOV-0025-CL01 | TPX09 - LV power cable | E | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151114,151113 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0042. [OPEN] | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS cable tags to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable need to be dressing completely at both side [OPEN]
T-00233-4925 | PS5-25-MOV-0026-CL01 | TPX09 - LV power cable | E | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151114,151113 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0042. [OPEN] | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS cable tags to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable need to be dressing completely at both side [OPEN]
T-00233-4926 | PS5-25-MOV-0027-CL01 | TPX09 - LV power cable | E | PS5-25-06 - Crude Oil Export Pumps Discharge | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely [OPEN]
T-00233-4927 | PS5-25-MOV-0028-CL01 | TPX09 - LV power cable | E | PS5-25-07 - Export Pipeline Pig Launcher | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely [OPEN]
T-00233-4928 | PS5-25-SDV-0022-CL01 | TPX09 - LV power cable | E | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely [OPEN]
T-00233-4929 | PS5-25-SDV-0035A-CL01 | TPX09 - LV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely [OPEN]
T-00233-4930 | PS5-25-SDV-0035B-CL01 | TPX09 - LV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely [OPEN]
T-00233-4931 | PS5-25-SDV-0035C-CL01 | TPX09 - LV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely [OPEN]
T-00233-4932 | PS5-25-SDV-0036A-CL01 | TPX09 - LV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely [OPEN]
T-00233-4933 | PS5-25-SDV-0036B-CL01 | TPX09 - LV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely [OPEN]
T-00233-4934 | PS5-25-SDV-0036C-CL01 | TPX09 - LV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 |  |  | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely [OPEN]
T-00233-4935 | PS5-25-SDV-0046-CL01 | TPX09 - LV power cable | E | PS5-25-05 - Crude Oil Export Pumps Bypass | Closed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151114,151113 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. [OPEN] | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS cable tags to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable need to be dressing completely at both side [OPEN]
T-00233-4936 | PS5-25-SDV-0052-CL01 | TPX09 - LV power cable | E | PS5-25-07 - Export Pipeline Pig Launcher | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely [OPEN]
T-00233-4937 | PS5-25-SDV-0054A-CL01 | TPX09 - LV power cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0043) [OPEN] | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 Permanent Cable tag not yet installed. [CLOSED]
T-00233-4938 | PS5-25-SDV-0054B-CL01 | TPX09 - LV power cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0043) [OPEN] | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN]
T-00233-4939 | PS5-25-SDV-0054C-CL01 | TPX09 - LV power cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0043) [OPEN] | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN]
T-00233-4941 | PS5-25-XV-0053-CL01 | TPX09 - LV power cable | E | PS5-25-05 - Crude Oil Export Pumps Bypass | Closed | CPP-RFI-68-331-05-0210 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151114,151113 Field run cable ladder to be installed [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 To be complete cable trench backfilled, protection tiles, and warning tape installation (PS5-88-BU-LV-00164) [OPEN] | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS cable tag to be installed at both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable dressing to be done at both side [OPEN]
T-00233-4942 | PS5-25-XV-0070-CL01 | TPX09 - LV power cable | E | PS5-25-05 - Crude Oil Export Pumps Bypass | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-4944 | PS5-28-BE-0002A-CL02 | TPX09 - LV power cable | E | PS5-28-17 - Reinjection Pump | Closed | CPP-RFI-68-331-05-0238 | CPP-RFI-68-331-07-0253 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Vertical Cable Tray to be install at panel side PS5-61-IG-0007 [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Direct Buried Cable trench installation at panel side PS5-61-IG-0007 not complete yet [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Dressing to be done at both side [OPEN]
T-00233-4946 | PS5-28-BE-0002B-CL02 | TPX09 - LV power cable | E | PS5-28-17 - Reinjection Pump | Closed | CPP-RFI-68-331-05-0238 | CPP-RFI-68-331-07-0253 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Vertical Cable Tray to be install at panel side PS5-61-IG-0007 [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Direct Buried Cable trench installation at panel side PS5-61-IG-0007 not complete yet [OPEN] | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Dressing to be done at both side [OPEN]
T-00233-4962 | PS5-28-HE-2100-CL02 | TPX09 - LV power cable | E | PS5-28-03 - Closed Drain Drum and Pump 01 | Closed | CPP-RFI-68-331-05-0238 | CPP-RFI-68-331-07-0253 |  | TZ-MID-68-WPR2-151111,151115,151117,151114 Vertical Cable Tray & Direct Buried Cable trench installation at panel side PS5-61-IG-0007 not complete yet. [OPEN] | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Dressing to be done at both side [OPEN]
T-00233-4964 | PS5-28-HE-2200-CL02 | TPX09 - LV power cable | E | PS5-28-04 - Closed Drain Drum and Pump 02 | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151111,151115,151118-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151118-SS Tag on both ends not installed [CLOSED]
T-00233-4966 | PS5-28-LB-8200-CL01 | TPX09 - LV power cable | E | PS5-28-11 - Open Drain Interceptor | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151111-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151111-SS Tag on both ends not installed [OPEN]
T-00233-4967 | PS5-28-SDV-0045-CL01 | TPX09 - LV power cable | E | PS5-28-17 - Reinjection Pump | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-4968 | PS5-28-SDV-0053A-CL01 | TPX09 - LV power cable | E | PS5-28-13 - Seal Oil Drain Drum & Pump A | Closed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray [OPEN] ¦ TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0043) [OPEN] | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end [OPEN]
T-00233-4969 | PS5-28-SDV-0053B-CL01 | TPX09 - LV power cable | E | PS5-28-14 - Seal Oil Drain Drum & Pump B | Closed | CPP-RFI-68-331-05-0239 | CPP-RFI-68-331-07-0254 |  | TZ-MID-68-WPR2-151117,151114 Vertical cable ladder to be done installation at panel side (PS5-61-IG-0043) [OPEN] | TZ-MID-68-WPR2-151117,151114 Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114 Dressing to be done at both side [OPEN]
T-00233-4970 | PS5-28-SDV-0053C-CL01 | TPX09 - LV power cable | E | PS5-28-15 - Seal Oil Drain Drum & Pump C | Closed | CPP-RFI-68-331-05-0238 | CPP-RFI-68-331-07-0253 |  | TZ-MID-68-WPR2-151117,151114 Vertical field tray to be install at panel side PS5-61-IG-0043 [OPEN] | TZ-MID-68-WPR2-151117,151114 Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114 Dressing to be done at both side [OPEN]
T-00233-4978 | PS5-60-BE-0001-CL01 | TPX09 - LV power cable | E | PS5-60-27 - Compressed Air Starting Skid | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151116 To be install Field Run Cable Tray/Ladder [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done at both side [OPEN]
T-00233-4979 | PS5-60-BE-0001-CL02 | TPX09 - LV power cable | E | PS5-60-27 - Compressed Air Starting Skid | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151116 To be install Field Run Cable Tray/Ladder [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done at both side [OPEN]
T-00233-4981 | PS5-60-BE-0001-CL04 | TPX09 - LV power cable | E | PS5-60-27 - Compressed Air Starting Skid | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 To be install Field Run Cable Tray/Ladder [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN]
T-00233-4982 | PS5-60-BE-0002-CL01 | TPX09 - LV power cable | E | PS5-60-26 - Instrument Air Compressor Skid | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151116 To be install Field Run Cable Tray/Ladder [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done at both side [OPEN]
T-00233-4983 | PS5-60-BE-0002-CL02 | TPX09 - LV power cable | E | PS5-60-26 - Instrument Air Compressor Skid | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151116 To be install Field Run Cable Tray/Ladder [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done at both side [OPEN]
T-00233-4984 | PS5-60-BE-0002-CL03 | TPX09 - LV power cable | E | PS5-60-26 - Instrument Air Compressor Skid | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151116 To be install Field Run Cable Tray/Ladder [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done at both side [OPEN]
T-00233-4986 | PS5-60-BE-0002-CL05 | TPX09 - LV power cable | E | PS5-60-26 - Instrument Air Compressor Skid | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 To be install Field Run Cable Tray/Ladder [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN]
T-00233-4987 | PS5-60-BE-0003A-CL01 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-4988 | PS5-60-BE-0003B-CL01 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-4989 | PS5-60-BE-0003C-CL01 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-331-07-0422
T-00233-4991 | PS5-60-BE-0003E-CL01 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-331-07-0422
T-00233-4992 | PS5-60-BE-0003F-CL01 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-331-07-0422
T-00233-4993 | PS5-60-BE-0003G-CL01 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0427
T-00233-4996 | PS5-60-BE-0004C-CL01 | TPX09 - LV power cable | E | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | Closed |  | CPP-RFI-68-331-07-0422
T-00233-4998 | PS5-60-BE-0004E-CL01 | TPX09 - LV power cable | E | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | Closed
T-00233-4999 | PS5-60-BE-0004F-CL01 | TPX09 - LV power cable | E | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | Closed |  | CPP-RFI-68-331-07-0422
T-00233-5000 | PS5-60-BE-0004G-CL01 | TPX09 - LV power cable | E | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | Closed |  | CPP-RFI-68-33/1-07-0427
T-00233-5001 | PS5-60-BE-0005A-CL01 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable not Reaching Final Destination (Incorrect Destination) [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5002 | PS5-60-BE-0005B-CL01 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Destination, but need to install cable ladder [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5003 | PS5-60-BE-0005C-CL01 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-331-07-0422
T-00233-5004 | PS5-60-BE-0005D-CL01 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5005 | PS5-60-BE-0005E-CL01 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-331-07-0422
T-00233-5006 | PS5-60-BE-0005F-CL01 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  | TZ-MID-68-WPR2-151167,151116,151179 Field run cable tray not finished [OPEN] | TZ-MID-68-WPR2-151167,151116,151179 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151116,151179 Cable Dressing not yet done [OPEN]
T-00233-5007 | PS5-60-BE-0005G-CL01 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-331-07-0423
T-00233-5008 | PS5-60-BE-0011A-CL01 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151116, 151118 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151116, 151118 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116, 151118 Cable to be dressing completely at both side [OPEN]
T-00233-5009 | PS5-60-BE-0011A-CL02 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151116, 151118 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151116, 151118 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116, 151118 Cable to be dressing completely at both side [OPEN]
T-00233-5010 | PS5-60-BE-0011A-CL03 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5011 | PS5-60-BE-0011A-CL04 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151116, 151118 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151116, 151118 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116, 151118 Cable to be dressing completely at both side [OPEN]
T-00233-5012 | PS5-60-BE-0011A-CL05 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5013 | PS5-60-BE-0011A-CL06 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5014 | PS5-60-BE-0011B-CL01 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5015 | PS5-60-BE-0011B-CL02 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5016 | PS5-60-BE-0011B-CL03 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5017 | PS5-60-BE-0011B-CL04 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5018 | PS5-60-BE-0011B-CL05 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5019 | PS5-60-BE-0011B-CL06 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5020 | PS5-60-BE-0012A-CL01 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5021 | PS5-60-BE-0012A-CL02 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5022 | PS5-60-BE-0012A-CL03 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5023 | PS5-60-BE-0012A-CL04 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5024 | PS5-60-BE-0012A-CL05 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5025 | PS5-60-BE-0012A-CL06 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5026 | PS5-60-BE-0012B-CL01 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5027 | PS5-60-BE-0012B-CL02 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5028 | PS5-60-BE-0012B-CL03 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5029 | PS5-60-BE-0012B-CL04 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5030 | PS5-60-BE-0012B-CL05 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination [CLOSED] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5031 | PS5-60-BE-0012B-CL06 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, 151118, Cable Not Reaching to Final Destination (PS5-60-BE-0012B) Cooler Fan JB need to install Cable Ladder [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151118 -Cable Dressing not Yet Done [OPEN]
T-00233-5033 | PS5-60-BE-0013A-CL02 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-33/1-07-0411
T-00233-5034 | PS5-60-BE-0013A-CL03 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-33/1-07-0411
T-00233-5035 | PS5-60-BE-0013A-CL04 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-33/1-07-0411
T-00233-5036 | PS5-60-BE-0013A-CL05 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-33/1-07-0411
T-00233-5037 | PS5-60-BE-0013A-CL06 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-33/1-07-0411
T-00233-5038 | PS5-60-BE-0013B-CL01 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-33/1-07-0411
T-00233-5039 | PS5-60-BE-0013B-CL02 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-33/1-07-0411
T-00233-5040 | PS5-60-BE-0013B-CL03 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-33/1-07-0411
T-00233-5041 | PS5-60-BE-0013B-CL04 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-33/1-07-0411
T-00233-5042 | PS5-60-BE-0013B-CL05 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-33/1-07-0411
T-00233-5043 | PS5-60-BE-0013B-CL06 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-33/1-07-0411
T-00233-5044 | PS5-60-BE-0014A-CL01 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0421
T-00233-5045 | PS5-60-BE-0014A-CL02 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5046 | PS5-60-BE-0014A-CL03 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5047 | PS5-60-BE-0014A-CL04 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5048 | PS5-60-BE-0014A-CL05 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5049 | PS5-60-BE-0014A-CL06 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5050 | PS5-60-BE-0014B-CL01 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5051 | PS5-60-BE-0014B-CL02 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5052 | PS5-60-BE-0014B-CL03 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5053 | PS5-60-BE-0014B-CL04 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5054 | PS5-60-BE-0014B-CL05 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5055 | PS5-60-BE-0014B-CL06 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5056 | PS5-60-BE-0015A-CL01 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5057 | PS5-60-BE-0015A-CL02 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5058 | PS5-60-BE-0015A-CL03 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5059 | PS5-60-BE-0015A-CL04 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5060 | PS5-60-BE-0015A-CL05 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5061 | PS5-60-BE-0015A-CL06 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5062 | PS5-60-BE-0015B-CL01 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5063 | PS5-60-BE-0015B-CL02 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-33/1-07-0421
T-00233-5064 | PS5-60-BE-0015B-CL03 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5065 | PS5-60-BE-0015B-CL04 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5066 | PS5-60-BE-0015B-CL05 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5067 | PS5-60-BE-0015B-CL06 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5068 | PS5-60-BE-0016A-CL01 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0411
T-00233-5069 | PS5-60-BE-0016A-CL02 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0411
T-00233-5070 | PS5-60-BE-0016A-CL03 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5071 | PS5-60-BE-0016A-CL04 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5072 | PS5-60-BE-0016A-CL05 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5073 | PS5-60-BE-0016A-CL06 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5074 | PS5-60-BE-0016B-CL01 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5075 | PS5-60-BE-0016B-CL02 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5076 | PS5-60-BE-0016B-CL03 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5077 | PS5-60-BE-0016B-CL04 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5078 | PS5-60-BE-0016B-CL05 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5079 | PS5-60-BE-0016B-CL06 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5080 | PS5-60-BE-0017A-CL01 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5081 | PS5-60-BE-0017A-CL02 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-5082 | PS5-60-BE-0017A-CL03 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5083 | PS5-60-BE-0017A-CL04 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed
T-00233-5084 | PS5-60-BE-0017A-CL05 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0416
T-00233-5085 | PS5-60-BE-0017A-CL06 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-5086 | PS5-60-BE-0017B-CL01 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5087 | PS5-60-BE-0017B-CL02 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5088 | PS5-60-BE-0017B-CL03 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5089 | PS5-60-BE-0017B-CL04 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-5090 | PS5-60-BE-0017B-CL05 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0421
T-00233-5091 | PS5-60-BE-0017B-CL06 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0421
T-00233-5092 | PS5-60-BE-0021A-CL01 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed | CPP-RFI-68-33/1-05-0309 | CPP-RFI-68-331-07-0310 |  | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118, Cable Reaching Final Destination, but need to install cable tray [OPEN] | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118, Cable Tagging not yet done at both side [OPEN] ¦ TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118, Cable Dressing not yet done [OPEN]
T-00233-5093 | PS5-60-BE-0021B-CL01 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151116 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151116 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5094 | PS5-60-BE-0024A-CL01 | TPX09 - LV power cable | E | PS5-60-35 - Injector Tip Cooling Module A | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Final Destination, but need to install cable LADDER [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5095 | PS5-60-BE-0024A-CL02 | TPX09 - LV power cable | E | PS5-60-35 - Injector Tip Cooling Module A | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Destination, but need to install cable ladder [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5096 | PS5-60-BE-0024B-CL01 | TPX09 - LV power cable | E | PS5-60-36 - Injector Tip Cooling Module B | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Final Destination, but need to install cable LADDER [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5097 | PS5-60-BE-0024B-CL02 | TPX09 - LV power cable | E | PS5-60-36 - Injector Tip Cooling Module B | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Destination, But need to install Vertikal Cable Ladder [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5098 | PS5-60-BE-0024C-CL01 | TPX09 - LV power cable | E | PS5-60-37 - Injector Tip Cooling Module C | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray not finished [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done [OPEN]
T-00233-5099 | PS5-60-BE-0024C-CL02 | TPX09 - LV power cable | E | PS5-60-37 - Injector Tip Cooling Module C | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray not finished [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done [OPEN]
T-00233-5100 | PS5-60-BE-0024D-CL01 | TPX09 - LV power cable | E | PS5-60-38 - Injector Tip Cooling Module D | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable not Reaching Final Destination [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5101 | PS5-60-BE-0024D-CL02 | TPX09 - LV power cable | E | PS5-60-38 - Injector Tip Cooling Module D | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Destination, But need to install cable ladder [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5102 | PS5-60-BE-0024E-CL01 | TPX09 - LV power cable | E | PS5-60-39 - Injector Tip Cooling Module E | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-5103 | PS5-60-BE-0024E-CL02 | TPX09 - LV power cable | E | PS5-60-39 - Injector Tip Cooling Module E | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray not finished [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done [OPEN]
T-00233-5104 | PS5-60-BE-0024F-CL01 | TPX09 - LV power cable | E | PS5-60-40 - Injector Tip Cooling Module F | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-5105 | PS5-60-BE-0024F-CL02 | TPX09 - LV power cable | E | PS5-60-40 - Injector Tip Cooling Module F | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  | TZ-MID-68-WPR2-151116 Field run cable tray not finished [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable Dressing not yet done [OPEN]
T-00233-5106 | PS5-60-BE-0024G-CL01 | TPX09 - LV power cable | E | PS5-60-41 - Injector Tip Cooling Module G | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable Dressing not yet done [OPEN]
T-00233-5107 | PS5-60-BE-0024G-CL02 | TPX09 - LV power cable | E | PS5-60-41 - Injector Tip Cooling Module G | Closed |  | CPP-RFI-68-33/1-07-0405
T-00233-5108 | PS5-60-BE-0025A-CL01 | TPX09 - LV power cable | E | PS5-60-35 - Injector Tip Cooling Module A | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cable not Reaching final destination, coiled around 9 MTR to final Destination (Generator Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5109 | PS5-60-BE-0025B-CL01 | TPX09 - LV power cable | E | PS5-60-36 - Injector Tip Cooling Module B | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cable not Reaching final destination, coiled around 9 MTR to final Destination (Generator Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5110 | PS5-60-BE-0025C-CL01 | TPX09 - LV power cable | E | PS5-60-37 - Injector Tip Cooling Module C | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done [OPEN]
T-00233-5111 | PS5-60-BE-0025D-CL01 | TPX09 - LV power cable | E | PS5-60-38 - Injector Tip Cooling Module D | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151118,151116 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5112 | PS5-60-BE-0025E-CL01 | TPX09 - LV power cable | E | PS5-60-39 - Injector Tip Cooling Module E | Closed |  | CPP-RFI-68-331-07-0422
T-00233-5113 | PS5-60-BE-0025F-CL01 | TPX09 - LV power cable | E | PS5-60-40 - Injector Tip Cooling Module F | Closed |  | CPP-RFI-68-331-07-0423
T-00233-5114 | PS5-60-BE-0025G-CL01 | TPX09 - LV power cable | E | PS5-60-41 - Injector Tip Cooling Module G | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable Dressing not yet done [OPEN]
T-00233-5115 | PS5-60-BE-0026A-CL01 | TPX09 - LV power cable | E | PS5-60-70 - Engine A Cooling system | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5116 | PS5-60-BE-0026A-CL02 | TPX09 - LV power cable | E | PS5-60-70 - Engine A Cooling system | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5117 | PS5-60-BE-0026B-CL01 | TPX09 - LV power cable | E | PS5-60-71 - Engine B Cooling system | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5118 | PS5-60-BE-0026B-CL02 | TPX09 - LV power cable | E | PS5-60-71 - Engine B Cooling system | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5119 | PS5-60-BE-0026C-CL01 | TPX09 - LV power cable | E | PS5-60-72 - Engine C Cooling system | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done [OPEN]
T-00233-5120 | PS5-60-BE-0026C-CL02 | TPX09 - LV power cable | E | PS5-60-72 - Engine C Cooling system | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5121 | PS5-60-BE-0026D-CL01 | TPX09 - LV power cable | E | PS5-60-73 - Engine D Cooling system | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done, Cable Not Reaching Final Destination [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5122 | PS5-60-BE-0026D-CL02 | TPX09 - LV power cable | E | PS5-60-73 - Engine D Cooling system | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Final Destination, but need to install cable LADDER [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5123 | PS5-60-BE-0026E-CL01 | TPX09 - LV power cable | E | PS5-60-74 - Engine E Cooling system | Closed |  | CPP-RFI-68-331-07-0422
T-00233-5124 | PS5-60-BE-0026E-CL02 | TPX09 - LV power cable | E | PS5-60-74 - Engine E Cooling system | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Final Destination, but need to install cable LADDER [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5125 | PS5-60-BE-0026F-CL01 | TPX09 - LV power cable | E | PS5-60-75 - Engine F Cooling system | Closed |  | CPP-RFI-68-331-07-0422
T-00233-5126 | PS5-60-BE-0026F-CL02 | TPX09 - LV power cable | E | PS5-60-75 - Engine F Cooling system | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Final Destination, but need to install cable LADDER [OPEN] | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done [OPEN]
T-00233-5127 | PS5-60-BE-0026G-CL01 | TPX09 - LV power cable | E | PS5-60-76 - Engine G Cooling system | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable Dressing not yet done [OPEN]
T-00233-5128 | PS5-60-BE-0026G-CL02 | TPX09 - LV power cable | E | PS5-60-76 - Engine G Cooling system | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5129 | PS5-60-BI-0005A-CL01 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable to be dressing completely at both side [OPEN]
T-00233-5130 | PS5-60-BI-0005B-CL01 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable to be dressing completely at both side [OPEN]
T-00233-5131 | PS5-60-BI-0005C-CL01 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable to be dressing completely at both side [OPEN]
T-00233-5132 | PS5-60-BI-0005D-CL01 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable to be dressing completely at both side [OPEN]
T-00233-5133 | PS5-60-BI-0005E-CL01 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable to be dressing completely at both side [OPEN]
T-00233-5134 | PS5-60-BI-0005F-CL01 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151116 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side [OPEN]
T-00233-5135 | PS5-60-BI-0005G-CL01 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151116 Field run cable tray/ladder to be installed completely [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side [OPEN]
T-00233-5137 | PS5-60-BI-0015A-CL02 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cable Reaching final destination, coiled around 5 MTR to Final Destination [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5138 | PS5-60-BI-0015A-CL03 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5140 | PS5-60-BI-0015B-CL02 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5141 | PS5-60-BI-0015B-CL03 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5142 | PS5-60-BI-0015C-CL01 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-331-07-0422
T-00233-5143 | PS5-60-BI-0015C-CL02 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-331-07-0422
T-00233-5144 | PS5-60-BI-0015C-CL03 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-331-07-0422
T-00233-5146 | PS5-60-BI-0015D-CL02 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5147 | PS5-60-BI-0015D-CL03 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5148 | PS5-60-BI-0015E-CL01 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5149 | PS5-60-BI-0015E-CL02 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-331-07-0422
T-00233-5150 | PS5-60-BI-0015E-CL03 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-331-07-0422
T-00233-5151 | PS5-60-BI-0015F-CL01 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5152 | PS5-60-BI-0015F-CL02 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5153 | PS5-60-BI-0015F-CL03 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-331-07-0422
T-00233-5155 | PS5-60-BI-0015G-CL02 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0410
T-00233-5156 | PS5-60-BI-0015G-CL03 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0410
T-00233-5166 | PS5-60-IE-0002A-CL01 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5167 | PS5-60-IE-0002A-CL02 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5168 | PS5-60-IE-0002A-CL03 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5169 | PS5-60-IE-0002B-CL01 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0309 | CPP-RFI-68-331-07-0310 |  | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable not Reaching Final Destination [OPEN] | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable Tagging Installaton not Yet Done at Both Side [OPEN] ¦ TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable Dressing not yet done [OPEN]
T-00233-5170 | PS5-60-IE-0002B-CL02 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-331-05-0275 | CPP-RFI-68-331-07-0310 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable coiled 110Mtr at Electrical building side, to be laid in the ladder (PS5-88-LD-LV-9025, PS5-88-LD-LV-9087, PS5-88-LD-LV-3091, PS5-88-LD-LV-3090). [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag To be Install [OPEN]
T-00233-5171 | PS5-60-IE-0002B-CL03 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5172 | PS5-60-IE-0002C-CL01 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-331-07-0423
T-00233-5173 | PS5-60-IE-0002C-CL02 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151116,151179 Cable Dressing not yet done [OPEN]
T-00233-5174 | PS5-60-IE-0002C-CL03 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed |  | CPP-RFI-68-33/1-07-0421
T-00233-5175 | PS5-60-IE-0002D-CL01 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5176 | PS5-60-IE-0002D-CL02 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5178 | PS5-60-IE-0002E-CL01 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151116,151179 Cable Dressing not yet done [OPEN]
T-00233-5179 | PS5-60-IE-0002E-CL02 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151116,151179 Cable Dressing not yet done [OPEN]
T-00233-5181 | PS5-60-IE-0002F-CL01 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-331-07-0409
T-00233-5182 | PS5-60-IE-0002F-CL02 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0421
T-00233-5184 | PS5-60-IE-0002G-CL01 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-331-07-0422
T-00233-5185 | PS5-60-IE-0002G-CL02 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0419
T-00233-5187 | PS5-60-IE-0003A-CL01 | TPX09 - LV power cable | E | PS5-60-02 - Power Gen Package A (UCP) | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not reaching final destinantion (Coiled not in Below of final Panel Location) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5188 | PS5-60-IE-0003A-CL02 | TPX09 - LV power cable | E | PS5-60-02 - Power Gen Package A (UCP) | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not reaching final destinantion (Coiled not in Below of final Panel Location) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5189 | PS5-60-IE-0003B-CL01 | TPX09 - LV power cable | E | PS5-60-05 - Power Gen Package B (UCP) | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not reaching final destinantion (Coiled not in Below of final Panel Location) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5190 | PS5-60-IE-0003B-CL02 | TPX09 - LV power cable | E | PS5-60-05 - Power Gen Package B (UCP) | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not reaching final destinantion (Coiled not in Below of final Panel Location) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5191 | PS5-60-IE-0003C-CL01 | TPX09 - LV power cable | E | PS5-60-08 - Power Gen Package C (UCP) | Closed |  | CPP-RFI-68-33/1-07-0419
T-00233-5194 | PS5-60-IE-0003D-CL02 | TPX09 - LV power cable | E | PS5-60-11 - Power Gen Package D (UCP) | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5195 | PS5-60-IE-0003E-CL01 | TPX09 - LV power cable | E | PS5-60-14 - Power Gen Package E (UCP) | Closed |  | CPP-RFI-68-33/1-07-0419
T-00233-5196 | PS5-60-IE-0003E-CL02 | TPX09 - LV power cable | E | PS5-60-14 - Power Gen Package E (UCP) | Closed |  | CPP-RFI-68-33/1-07-0419
T-00233-5197 | PS5-60-IE-0003F-CL01 | TPX09 - LV power cable | E | PS5-60-17 - Power Gen Package F (UCP) | Closed |  | CPP-RFI-68-33/1-07-0419
T-00233-5198 | PS5-60-IE-0003F-CL02 | TPX09 - LV power cable | E | PS5-60-17 - Power Gen Package F (UCP) | Closed |  | CPP-RFI-68-33/1-07-0419
T-00233-5199 | PS5-60-IE-0003G-CL01 | TPX09 - LV power cable | E | PS5-60-20 - Power Gen Package G (UCP) | Closed |  | CPP-RFI-68-33/1-07-0419
T-00233-5200 | PS5-60-IE-0003G-CL02 | TPX09 - LV power cable | E | PS5-60-20 - Power Gen Package G (UCP) | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-5201 | PS5-60-IE-0004-CL01 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5202 | PS5-60-IE-0004-CL02 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5204 | PS5-60-IH-0001A-CL01 | TPX09 - LV power cable | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5205 | PS5-60-IH-0001A-CL02 | TPX09 - LV power cable | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5206 | PS5-60-IH-0001A-CL03 | TPX09 - LV power cable | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5207 | PS5-60-IH-0001A-CL04 | TPX09 - LV power cable | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5208 | PS5-60-IH-0001A-CL05 | TPX09 - LV power cable | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5209 | PS5-60-IH-0001A-CL06 | TPX09 - LV power cable | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching, Coiled around 2 MTR to final Panel (PS5-60-IH-0001A) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5211 | PS5-60-IH-0001B-CL01 | TPX09 - LV power cable | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5212 | PS5-60-IH-0001B-CL02 | TPX09 - LV power cable | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5213 | PS5-60-IH-0001B-CL03 | TPX09 - LV power cable | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5214 | PS5-60-IH-0001B-CL04 | TPX09 - LV power cable | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5215 | PS5-60-IH-0001B-CL05 | TPX09 - LV power cable | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5216 | PS5-60-IH-0001B-CL06 | TPX09 - LV power cable | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5218 | PS5-60-IH-0001C-CL01 | TPX09 - LV power cable | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable Dressing not yet done [OPEN]
T-00233-5219 | PS5-60-IH-0001C-CL02 | TPX09 - LV power cable | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable Dressing not yet done [OPEN]
T-00233-5220 | PS5-60-IH-0001C-CL03 | TPX09 - LV power cable | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable Dressing not yet done [OPEN]
T-00233-5221 | PS5-60-IH-0001C-CL04 | TPX09 - LV power cable | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable Dressing not yet done [OPEN]
T-00233-5222 | PS5-60-IH-0001C-CL05 | TPX09 - LV power cable | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-33/1-07-0427
T-00233-5223 | PS5-60-IH-0001C-CL06 | TPX09 - LV power cable | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-331-07-0409
T-00233-5225 | PS5-60-IH-0001D-CL01 | TPX09 - LV power cable | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-33/1-07-0411
T-00233-5226 | PS5-60-IH-0001D-CL02 | TPX09 - LV power cable | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-33/1-07-0411
T-00233-5227 | PS5-60-IH-0001D-CL03 | TPX09 - LV power cable | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-33/1-07-0411
T-00233-5228 | PS5-60-IH-0001D-CL04 | TPX09 - LV power cable | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-33/1-07-0411
T-00233-5229 | PS5-60-IH-0001D-CL05 | TPX09 - LV power cable | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5230 | PS5-60-IH-0001D-CL06 | TPX09 - LV power cable | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-331-07-0409
T-00233-5232 | PS5-60-IH-0001E-CL01 | TPX09 - LV power cable | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-5233 | PS5-60-IH-0001E-CL02 | TPX09 - LV power cable | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-5234 | PS5-60-IH-0001E-CL03 | TPX09 - LV power cable | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-5236 | PS5-60-IH-0001E-CL05 | TPX09 - LV power cable | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-331-07-0409
T-00233-5237 | PS5-60-IH-0001E-CL06 | TPX09 - LV power cable | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-331-07-0409
T-00233-5244 | PS5-60-IH-0001F-CL06 | TPX09 - LV power cable | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-331-07-0409
T-00233-5249 | PS5-60-IH-0001G-CL04 | TPX09 - LV power cable | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-33/1-07-0410 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable Dressing not yet done [OPEN]
T-00233-5250 | PS5-60-IH-0001G-CL05 | TPX09 - LV power cable | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | Closed |  | CPP-RFI-68-331-07-0409
T-00233-5254 | PS5-60-IH-0002-CL01 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5255 | PS5-60-IH-0002-CL02 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5256 | PS5-60-IH-0002-CL03 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5257 | PS5-60-IH-0002-CL04 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5258 | PS5-60-IH-0002-CL05 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5259 | PS5-60-IH-0002-CL06 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5260 | PS5-60-IH-0002-CL07 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5261 | PS5-60-IH-0002-CL08 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5262 | PS5-60-IH-0002-CL09 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5263 | PS5-60-IH-0002-CL10 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5264 | PS5-60-IN-0001A-CL01 | TPX09 - LV power cable | E | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5265 | PS5-60-IN-0001B-CL01 | TPX09 - LV power cable | E | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5266 | PS5-60-IN-0001C-CL01 | TPX09 - LV power cable | E | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | Closed |  | CPP-RFI-68-331-07-0409
T-00233-5267 | PS5-60-IN-0001D-CL01 | TPX09 - LV power cable | E | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5268 | PS5-60-IN-0001E-CL01 | TPX09 - LV power cable | E | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | Closed |  | CPP-RFI-68-331-07-0409
T-00233-5269 | PS5-60-IN-0001F-CL01 | TPX09 - LV power cable | E | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | Closed |  | CPP-RFI-68-331-07-0409
T-00233-5270 | PS5-60-IN-0001G-CL01 | TPX09 - LV power cable | E | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | Closed |  | CPP-RFI-68-331-07-0409
T-00233-5271 | PS5-60-IN-0002A-CL01 | TPX09 - LV power cable | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151118,151116 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5272 | PS5-60-IN-0002A-CL02 | TPX09 - LV power cable | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN]
T-00233-5273 | PS5-60-IN-0002A-CL03 | TPX09 - LV power cable | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5274 | PS5-60-IN-0002B-CL01 | TPX09 - LV power cable | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151118,151116 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5275 | PS5-60-IN-0002B-CL02 | TPX09 - LV power cable | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5276 | PS5-60-IN-0002B-CL03 | TPX09 - LV power cable | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS cable tag to be install at both side [OPEN]
T-00233-5280 | PS5-60-IN-0002D-CL01 | TPX09 - LV power cable | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5281 | PS5-60-IN-0002D-CL02 | TPX09 - LV power cable | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Need to Install Vertical Cable ladder to provide support for cable installation (Generator Building Site) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5282 | PS5-60-IN-0002D-CL03 | TPX09 - LV power cable | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Need to Install Vertical Cable ladder to provide support for cable installation (Generator Building Site) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5284 | PS5-60-IN-0002E-CL02 | TPX09 - LV power cable | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5285 | PS5-60-IN-0002E-CL03 | TPX09 - LV power cable | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5287 | PS5-60-IN-0002F-CL02 | TPX09 - LV power cable | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5288 | PS5-60-IN-0002F-CL03 | TPX09 - LV power cable | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | Closed |  | CPP-RFI-68-33/1-07-0421
T-00233-5290 | PS5-60-IN-0002G-CL02 | TPX09 - LV power cable | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | Closed |  | CPP-RFI-68-33/1-07-0421
T-00233-5291 | PS5-60-IN-0002G-CL03 | TPX09 - LV power cable | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5294 | PS5-60-IWK-0001B-CL01 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching, Coiled around 3 MTR to final Panel (PS5-60-IWK-0001B) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5295 | PS5-60-IWK-0001B-CL02 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching, Coiled around 3 MTR to final Panel (PS5-60-IWK-0001B) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5296 | PS5-60-IWK-0001C-CL01 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching, Coiled around 5 MTR to final Panel (PS5-60-IWK-0001C) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5297 | PS5-60-IWK-0001C-CL02 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching, Coiled around 5 MTR to final Panel (PS5-60-IWK-0001C) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5298 | PS5-60-LA-0002A-CL01 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5299 | PS5-60-LA-0002A-CL02 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5300 | PS5-60-LA-0002B-CL01 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0419
T-00233-5301 | PS5-60-LA-0002B-CL02 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0419
T-00233-5302 | PS5-60-LA-0002C-CL01 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0419
T-00233-5303 | PS5-60-LA-0002C-CL02 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0419
T-00233-5304 | PS5-60-LA-0003-CL01 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN]
T-00233-5305 | PS5-60-LA-0003-CL02 | TPX09 - LV power cable | E | PS5-60-22 - Power Gen Master UCP | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN]
T-00233-5306 | PS5-60-MOV-0005-CL01 | TPX09 - LV power cable | E | PS5-71-12 - CFO Service Tank | Closed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). [OPEN] ¦ TZ-MID-68-WPR2-151117,151118 Cable coiled around 90m, to be laid in ladder and reach equipment at field location. [CLOSED] | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side [OPEN]
T-00233-5307 | PS5-60-MOV-0006-CL01 | TPX09 - LV power cable | E | PS5-71-12 - CFO Service Tank | Closed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). [OPEN] ¦ TZ-MID-68-WPR2-151117,151118 Cable coiled around 90m, to be laid in ladder and reach equipment at field location. [CLOSED] | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side [OPEN]
T-00233-5308 | PS5-60-MOV-0011-CL01 | TPX09 - LV power cable | E | PS5-71-12 - CFO Service Tank | Closed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151118 Cable coiled around 80m, to be laid in ladder and reach equipment at field location. [CLOSED] ¦ TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). [OPEN] | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side [OPEN]
T-00233-5309 | PS5-60-MOV-0012-CL01 | TPX09 - LV power cable | E | PS5-71-12 - CFO Service Tank | Closed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151118 Cable coiled around 80m, to be laid in ladder and reach equipment at field location. [CLOSED] ¦ TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). [OPEN] | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side [OPEN]
T-00233-5310 | PS5-60-SEA-0001-CL01 | TPX09 - LV power cable | E | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | Closed |  | CPP-RFI-68-33/1-07-0419
T-00233-5311 | PS5-60-SEA-0001-CL02 | TPX09 - LV power cable | E | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | Closed |  | CPP-RFI-68-33/1-07-0419
T-00233-5312 | PS5-60-VS-9100A-CL01 | TPX09 - LV power cable | E | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5313 | PS5-60-VS-9100B-CL01 | TPX09 - LV power cable | E | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5314 | PS5-60-VS-9100C-CL01 | TPX09 - LV power cable | E | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5315 | PS5-60-VS-9100D-CL01 | TPX09 - LV power cable | E | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-5316 | PS5-60-VS-9100E-CL01 | TPX09 - LV power cable | E | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  | TZ-MID-68-WPR2-151118,151116 Field run cable tray not finished [OPEN] | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done [OPEN]
T-00233-5317 | PS5-60-VS-9100F-CL01 | TPX09 - LV power cable | E | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-5318 | PS5-60-VS-9100G-CL01 | TPX09 - LV power cable | E | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-5319 | PS5-61-BI-0001-CL01 | TPX09 - LV power cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0267 |  |  | TZ-MID-68-WPR2-151118,151116,151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151118,151116,151112-SS Tag on both ends not installed [CLOSED]
T-00233-5320 | PS5-61-BI-0002-CL01 | TPX09 - LV power cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0267 |  |  | TZ-MID-68-WPR2-151118,151116,151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151118,151116,151112-SS Tag on both ends not installed [OPEN]
T-00233-5321 | PS5-61-BI-0003-CL01 | TPX09 - LV power cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151118,151116,151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151118,151116,151112-SS Tag on both ends not installed [CLOSED]
T-00233-5322 | PS5-61-BI-0004-CL01 | TPX09 - LV power cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151116,151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116,151112-SS Tag on both ends not installed [OPEN]
T-00233-5323 | PS5-61-BI-0005-CL01 | TPX09 - LV power cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151116,151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116,151112-SS Tag on both ends not installed [CLOSED]
T-00233-5324 | PS5-61-BI-0006-CL01 | TPX09 - LV power cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151116,151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116,151112-SS Tag on both ends not installed [OPEN]
T-00233-5325 | PS5-61-BI-0007-CL01 | TPX09 - LV power cable | E | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  | TZ-MID-68-WPR2-151116,151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0029, PS5-88-BU-HV-0017, PS5-88-BU-HV-0013, PS5-88-BU-HV-0014, PS5-88-BU-HV-0015, PS5-88-CU-HV-0024) [OPEN] | TZ-MID-68-WPR2-151116,151112 SS Cable tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151116,151112 Cable dressing to be done both side [OPEN]
T-00233-5335 | PS5-61-IG-0015-CL01 | TPX09 - LV power cable | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5336 | PS5-61-IG-0016-CL01 | TPX09 - LV power cable | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151116 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151116 Cable dressing to be done at both side [OPEN]
T-00233-5343 | PS5-61-IH-0004-CL01 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-5344 | PS5-61-IH-0004-CL02 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-5345 | PS5-61-IH-0004-CL03 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-5346 | PS5-61-IH-0004-CL04 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-5347 | PS5-61-IH-0004-CL05 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-5348 | PS5-61-IH-0004-CL06 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-5349 | PS5-61-IH-0004-CL07 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-5350 | PS5-61-IH-0004-CL08 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-5351 | PS5-61-IH-0004-CL09 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-5352 | PS5-61-IH-0004-CL10 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-5353 | PS5-61-IH-0004-CL11 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-5354 | PS5-61-IH-0004-CL12 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-5355 | PS5-61-IH-0004-CL13 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-5356 | PS5-61-IH-0004-CL14 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-5359 | PS5-61-IH-0004-CL17 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-5364 | PS5-61-IH-0004-CL22 | TPX09 - LV power cable | E | PS5-09-03 - HVAC for Generator Building | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-5425 | PS5-61-IK-0003-CL01 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN]
T-00233-5426 | PS5-61-IK-0003-CL02 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN]
T-00233-5428 | PS5-61-IK-0003-CL04 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching final destination around 2 MTR (PS5-61-IK-0003) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done [OPEN]
T-00233-5429 | PS5-61-IK-0003-CL05 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching final destination around 2 MTR (PS5-61-IK-0003) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done [OPEN]
T-00233-5430 | PS5-61-IK-0003-CL06 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done [OPEN]
T-00233-5431 | PS5-61-IK-0003-CL07 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00233-5432 | PS5-61-IK-0003-CL08 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00233-5433 | PS5-61-IK-0003-CL09 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00233-5434 | PS5-61-IK-0003-CL10 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00233-5435 | PS5-61-IK-0003-CL11 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00233-5436 | PS5-61-IK-0003-CL12 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00233-5437 | PS5-61-IK-0003-CL13 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5438 | PS5-61-IK-0003-CL14 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5439 | PS5-61-IK-0003-CL15 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0211 |  |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [CLOSED]
T-00233-5440 | PS5-61-IK-0003-CL16 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5441 | PS5-61-IK-0003-CL17 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5442 | PS5-61-IK-0003-CL18 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5443 | PS5-61-IK-0003-CL19 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5444 | PS5-61-IK-0003-CL20 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5445 | PS5-61-IK-0003-CL21 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5446 | PS5-61-IK-0003-CL22 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5447 | PS5-61-IK-0003-CL23 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5448 | PS5-61-IK-0003-CL24 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5449 | PS5-61-IK-0003-CL25 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0310 |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [CLOSED]
T-00233-5450 | PS5-61-IK-0003-CL26 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0310 |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [OPEN]
T-00233-5451 | PS5-61-IK-0003-CL27 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0310 |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [CLOSED]
T-00233-5452 | PS5-61-IK-0003-CL28 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0310 |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [CLOSED]
T-00233-5453 | PS5-61-IK-0003-CL29 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0310 |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [CLOSED]
T-00233-5454 | PS5-61-IK-0003-CL30 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5455 | PS5-61-IK-0003-CL31 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5456 | PS5-61-IK-0003-CL32 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5457 | PS5-61-IK-0003-CL33 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5458 | PS5-61-IK-0003-CL34 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5459 | PS5-61-IK-0003-CL35 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5460 | PS5-61-IK-0003-CL36 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5461 | PS5-61-IK-0003-CL37 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151116 Cable ladder to be install at trafo side (PS5-61-IV-0002A) [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0020, PS5-88-BU-LV-00160) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done both side [OPEN]
T-00233-5462 | PS5-61-IK-0003-CL38 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151116 Cable ladder to be install at trafo side (PS5-61-IV-0002A) [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0020, PS5-88-BU-LV-00160) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done both side [OPEN]
T-00233-5463 | PS5-61-IK-0003-CL39 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151116 Cable ladder to be install at trafo side (PS5-61-IV-0002A) [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0020, PS5-88-BU-LV-00160) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done both side [OPEN]
T-00233-5464 | PS5-61-IK-0003-CL40 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151116 Cable ladder to be install at trafo side (PS5-61-IV-0002A) [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0020, PS5-88-BU-LV-00160) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151116 Cable dressing to be done both side [OPEN]
T-00233-5465 | PS5-61-IK-0003-CL41 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00233-5466 | PS5-61-IK-0003-CL42 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00233-5467 | PS5-61-IK-0003-CL43 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00233-5468 | PS5-61-IK-0003-CL44 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151111, 151112, 151116-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116-Cable dressing not yet done completely [OPEN]
T-00233-5469 | PS5-61-IK-0003-CL45 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00233-5470 | PS5-61-IK-0003-CL46 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00233-5471 | PS5-61-IK-0003-CL47 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00233-5472 | PS5-61-IK-0003-CL48 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00233-5473 | PS5-61-IK-0003-CL49 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00233-5474 | PS5-61-IK-0003-CL50 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00233-5475 | PS5-61-IK-0003-CL51 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00233-5476 | PS5-61-IK-0003-CL52 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00233-5477 | PS5-61-IK-0003-CL53 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00233-5478 | PS5-61-IK-0003-CL54 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side [OPEN]
T-00233-5479 | PS5-61-IK-0003-CL55 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0238 | CPP-RFI-68-331-07-0253 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable Trench to be complete installation [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Dressing to be done at both side [OPEN]
T-00233-5480 | PS5-61-IK-0003-CL56 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0238 | CPP-RFI-68-331-07-0253 |  | TZ-MID-68-WPR2-151111, 151112, 151116 Cable Trench to be complete installation [OPEN] | TZ-MID-68-WPR2-151111, 151112, 151116 Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116 Dressing to be done at both side [OPEN]
T-00233-5481 | PS5-61-IK-0003-CL57 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151111, 151112, 151116-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116-Cable dressing not yet done completely [OPEN]
T-00233-5482 | PS5-61-IK-0003-CL58 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151111, 151112, 151116-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116-Cable dressing not yet done completely [OPEN]
T-00233-5483 | PS5-61-IK-0003-CL59 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151111, 151112, 151116-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116-Cable dressing not yet done completely [OPEN]
T-00233-5484 | PS5-61-IK-0003-CL60 | TPX09 - LV power cable | E | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0292 |  |  | TZ-MID-68-WPR2-151111, 151112, 151116-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111, 151112, 151116-Cable dressing not yet done completely [OPEN]
T-00233-5485 | PS5-61-IK-0003-CL61 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed |  | CPP-RFI-68-331-07-0310
T-00233-5486 | PS5-61-IK-0003-CL62 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done [OPEN]
T-00233-5492 | PS5-61-IK-0006-CL01 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00233-5493 | PS5-61-IK-0006-CL02 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00233-5494 | PS5-61-IK-0006-CL03 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00233-5495 | PS5-61-IK-0006-CL04 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00233-5496 | PS5-61-IK-0006-CL05 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00233-5497 | PS5-61-IK-0006-CL06 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00233-5498 | PS5-61-IK-0006-CL07 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00233-5499 | PS5-61-IK-0006-CL08 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00233-5500 | PS5-61-IK-0006-CL09 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends [OPEN] ¦ TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side [OPEN]
T-00233-5501 | PS5-61-IK-0006-CL10 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5502 | PS5-61-IK-0006-CL11 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5503 | PS5-61-IK-0006-CL12 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5504 | PS5-61-IK-0006-CL13 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5505 | PS5-61-IK-0006-CL14 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5506 | PS5-61-IK-0006-CL15 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5507 | PS5-61-IK-0006-CL16 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5508 | PS5-61-IK-0006-CL17 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5509 | PS5-61-IK-0006-CL18 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side [OPEN] | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5510 | PS5-61-IK-0006-CL19 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151116 Cable Trench Installation to be complete at PS5-61-IV-0007B side [OPEN] | TZ-MID-68-WPR2-151116 Permanent Cable Tag Missing Both End [CLOSED] ¦ TZ-MID-68-WPR2-151116 Dressing Cable To be done at Generator Electrical Building side [OPEN]
T-00233-5511 | PS5-61-IK-0006-CL20 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151116 Cable Trench Installation to be complete at PS5-61-IV-0007B side [OPEN] | TZ-MID-68-WPR2-151116 Permanent Cable Tag Missing Both End [CLOSED] ¦ TZ-MID-68-WPR2-151116 Dressing Cable To be done at Generator Electrical Building side [OPEN]
T-00233-5512 | PS5-61-IK-0006-CL21 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151116 Cable Trench Installation to be complete at PS5-61-IV-0007B side [OPEN] | TZ-MID-68-WPR2-151116 Permanent Cable Tag Missing Both End [CLOSED] ¦ TZ-MID-68-WPR2-151116 Dressing Cable To be done at Generator Electrical Building side [OPEN]
T-00233-5513 | PS5-61-IK-0006-CL22 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151116 Cable Trench Installation to be complete at PS5-61-IV-0007B side [OPEN] | TZ-MID-68-WPR2-151116 Permanent Cable Tag Missing Both End [CLOSED] ¦ TZ-MID-68-WPR2-151116 Dressing Cable To be done at Generator Electrical Building side [OPEN]
T-00233-5514 | PS5-61-IK-0006-CL23 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [OPEN]
T-00233-5515 | PS5-61-IK-0006-CL24 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [OPEN]
T-00233-5516 | PS5-61-IK-0006-CL25 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151116-SS Tag on both ends not installed [OPEN]
T-00233-5517 | PS5-61-IK-0006-CL26 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151112 Cable ladder/tray not yet install at trafo side (PPS5-61-IV-0007B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00157). [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00233-5518 | PS5-61-IK-0006-CL27 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151112 Cable ladder/tray not yet install at trafo side (PPS5-61-IV-0007B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00157). [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00233-5519 | PS5-61-IK-0006-CL28 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151112 Cable ladder/tray not yet install at trafo side (PPS5-61-IV-0007B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00157). [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00233-5520 | PS5-61-IK-0006-CL29 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed |  | CPP-RFI-68-33/1-07-0405
T-00233-5521 | PS5-61-IK-0006-CL30 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed |  | CPP-RFI-68-33/1-07-0419
T-00233-5522 | PS5-61-IK-0006-CL31 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed |  | CPP-RFI-68-33/1-07-0405
T-00233-5523 | PS5-61-IK-0006-CL32 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed |  | CPP-RFI-68-33/1-07-0405
T-00233-5524 | PS5-61-IK-0006-CL33 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151116 Cable ladder at transformer side not yet install PS5-61-IV-0007A [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable trench not yet complete termination [OPEN] | TZ-MID-68-WPR2-151116 SS Permanent cable tag to be install [CLOSED] ¦ TZ-MID-68-WPR2-151116 Cable Dressing to be done at both side [OPEN]
T-00233-5525 | PS5-61-IK-0006-CL34 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0244 | CPP-RFI-68-331-07-0249 |  | TZ-MID-68-WPR2-151116 Cable ladder at transformer side not yet install PS5-61-IV-0007B [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable trench not yet complete termination [OPEN] | TZ-MID-68-WPR2-151116 SS Permanent cable tag to be install [CLOSED] ¦ TZ-MID-68-WPR2-151116 Cable Dressing to be done at both side [OPEN]
T-00233-5537 | PS5-61-IV-0002A-CL01 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done [OPEN]
T-00233-5538 | PS5-61-IV-0002B-CL01 | TPX09 - LV power cable | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done [OPEN]
T-00233-5542 | PS5-61-IV-0007A-CL01 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  |  | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5543 | PS5-61-IV-0007B-CL01 | TPX09 - LV power cable | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  |  | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side [OPEN]
T-00233-5546 | PS5-62-IE-0001-CL01 | TPX09 - LV power cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | Closed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151111 To be install vertical cable ladder at both end [OPEN] | TZ-MID-68-WPR2-151111 Dressing to be done at both end [OPEN]
T-00233-5547 | PS5-62-IE-0002-CL01 | TPX09 - LV power cable | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | Closed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117 Cable to be laid in the cable trench No. PS5-88-BU-LV-00162. [OPEN] | TZ-MID-68-WPR2-151117 Permanent SS cable tags to be install [OPEN] ¦ TZ-MID-68-WPR2-151117 Cable need to be dressing completely [OPEN]
T-00233-5561 | PS5-71-FCV-0018-CL01 | TPX09 - LV power cable | E | PS5-71-13 - CFO Service Pump A/B | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0307 |  |  | TZ-MID-68-WPR2-151115, TZ-MID-68-WPR2-151112 SS Cable Tags need to Install at Both Ends [CLOSED] ¦ TZ-MID-68-WPR2-151115, TZ-MID-68-WPR2-151112 Cable Dressing at Both Ends [OPEN]
T-00233-5562 | PS5-71-FCV-0019-CL01 | TPX09 - LV power cable | E | PS5-71-21 - Diesel Transfer Pump A/B | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0267 |  |  | TZ-MID-68-WPR2-151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117-SS Tag on both ends not installed [CLOSED]
T-00233-5563 | PS5-71-FCV-0020-CL01 | TPX09 - LV power cable | E | PS5-71-05 - CFO Transfer Pump A/B | Closed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151114,151115 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151115 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. [OPEN] | TZ-MID-68-WPR2-151117,151114,151115 Permanent SS cable tags to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151115 Cable need to be dressing completely at both side [OPEN]
T-00233-5567 | PS5-71-HE-2200-CL02 | TPX09 - LV power cable | E | PS5-71-12 - CFO Service Tank | Closed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  | TZ-MID-68-WPR2-151117,151114,151115 Field run cable tray installation not yet complete. [OPEN] | TZ-MID-68-WPR2-151117,151114,151115 SS Cable tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151114,151115 Cable dressing to be done both side [OPEN]
T-00233-5569 | PS5-71-HE-2300-CL02 | TPX09 - LV power cable | E | PS5-71-04 - CFO Storage Tank | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0307 |  |  | TZ-MID-68-WPR2-151117,151114,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151115-SS Tag on both ends not installed [CLOSED]
T-00233-5578 | PS5-71-IN-0001-CL01 | TPX09 - LV power cable | E | PS5-71-19 - Diesel Separator Module (UCP) | Closed |  | CPP-RFI-68-33/1-07-0405
T-00233-5579 | PS5-71-IN-0001-CL02 | TPX09 - LV power cable | E | PS5-71-19 - Diesel Separator Module (UCP) | Closed |  | CPP-RFI-68-33/1-07-0405
T-00233-5580 | PS5-71-IN-0001-CL03 | TPX09 - LV power cable | E | PS5-71-19 - Diesel Separator Module (UCP) | Closed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151116 Cable trench backfiled, protection tiles, and warning tape installation to be done (PS5-88-BU-LV-00160) [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side [OPEN]
T-00233-5581 | PS5-71-IN-0002-CL01 | TPX09 - LV power cable | E | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | Closed |  | CPP-RFI-68-331-07-0409
T-00233-5582 | PS5-71-IN-0002-CL02 | TPX09 - LV power cable | E | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | Closed |  | CPP-RFI-68-331-07-0409
T-00233-5583 | PS5-71-IN-0002-CL03 | TPX09 - LV power cable | E | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-5584 | PS5-71-IN-0003-CL01 | TPX09 - LV power cable | E | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5585 | PS5-71-IN-0003-CL02 | TPX09 - LV power cable | E | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done [OPEN]
T-00233-5586 | PS5-71-IN-0003-CL03 | TPX09 - LV power cable | E | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | Closed | CPP-RFI-68-33/1-05-0309 | CPP-RFI-68-331-07-0310 |  | TZ-MID-68-WPR2-151166, Cable not reaching final destination [OPEN] | TZ-MID-68-WPR2-151166, Cable Tagging Installation not Yet Done at Both Side [OPEN] ¦ TZ-MID-68-WPR2-151166, Cable Dressing not yet done [OPEN]
T-00233-5587 | PS5-71-IN-0004A-CL01 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable Dressing not yet done [OPEN]
T-00233-5588 | PS5-71-IN-0004A-CL02 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | Closed | CPP-RFI-68-331-05-0407 | CPP-RFI-68-331-07-0408 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable Dressing not yet done [OPEN]
T-00233-5589 | PS5-71-IN-0004A-CL03 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | Closed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151116 Cable trench backfiled, protection tiles, and warning tape installation to be done (PS5-88-BU-LV-00159) [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side [OPEN]
T-00233-5590 | PS5-71-IN-0004B-CL01 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | Closed |  | CPP-RFI-68-331-07-0409
T-00233-5591 | PS5-71-IN-0004B-CL02 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | Closed |  | CPP-RFI-68-331-07-0409
T-00233-5592 | PS5-71-IN-0004B-CL03 | TPX09 - LV power cable | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | Closed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151116 Cable trench backfiled, protection tiles, and warning tape installation to be done (PS5-88-BU-LV-00159) [OPEN] | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side [OPEN]
T-00233-5593 | PS5-71-LCV-4101-CL01 | TPX09 - LV power cable | E | PS5-71-04 - CFO Storage Tank | Closed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151114,151115 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151115 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. [OPEN] | TZ-MID-68-WPR2-151117,151114,151115 Permanent SS cable tags to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151115 Cable need to be dressing completely at both side [OPEN]
T-00233-5594 | PS5-71-MOV-0001-CL01 | TPX09 - LV power cable | E | PS5-71-08 - CFO Pre-Pressure Modules | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench [OPEN] | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed [CLOSED]
T-00233-5595 | PS5-71-MOV-0002-CL01 | TPX09 - LV power cable | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench [OPEN] | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed [CLOSED]
T-00233-5596 | PS5-71-MOV-0003-CL01 | TPX09 - LV power cable | E | PS5-71-08 - CFO Pre-Pressure Modules | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench [OPEN] | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed [CLOSED]
T-00233-5597 | PS5-71-MOV-0004-CL01 | TPX09 - LV power cable | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench [OPEN] | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed [CLOSED]
T-00233-5598 | PS5-71-MOV-0007-CL01 | TPX09 - LV power cable | E | PS5-71-04 - CFO Storage Tank | Closed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151118 Cable coiled around 90m, to be laid in ladder and reach equipment at field location. [CLOSED] ¦ TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). [OPEN] | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side [OPEN]
T-00233-5599 | PS5-71-MOV-0008-CL01 | TPX09 - LV power cable | E | PS5-71-08 - CFO Pre-Pressure Modules | Closed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-33/1-07-0308 |  | TZ-MID-68-WPR2-151117,151118 Cable coiled around 90m, to be laid in ladder and reach equipment at field location. [CLOSED] ¦ TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). [OPEN] | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side [OPEN]
T-00233-5600 | PS5-71-MOV-0009-CL01 | TPX09 - LV power cable | E | PS5-71-04 - CFO Storage Tank | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench [OPEN] | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed [CLOSED]
T-00233-5601 | PS5-71-MOV-0010-CL01 | TPX09 - LV power cable | E | PS5-71-08 - CFO Pre-Pressure Modules | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench [OPEN] | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed [CLOSED]
T-00233-5602 | PS5-71-SDV-0001-CL01 | TPX09 - LV power cable | E | PS5-71-20 - Diesel Fuel Day Tank | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0267 |  |  | TZ-MID-68-WPR2-151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117-SS Tag on both ends not installed [CLOSED]
T-00233-5604 | PS5-71-SDV-0029-CL01 | TPX09 - LV power cable | E | PS5-71-15 - Diesel Fuel Storage Tank | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151117,151115,151111,151108,151107-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151115,151111,151108,151107-SS Tag on both ends not installed [CLOSED]
T-00233-5605 | PS5-71-SDV-0039-CL01 | TPX09 - LV power cable | E | PS5-71-12 - CFO Service Tank | Closed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151115 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151115 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. [OPEN] | TZ-MID-68-WPR2-151117,151115 Permanent SS cable tags to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151115 Cable need to be dressing completely at both side [OPEN]
T-00233-5606 | PS5-71-UZ-6200-CL01 | TPX09 - LV power cable | E | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151112, 151111, 151108, 151107-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112, 151111, 151108, 151107-SS Tag on both ends not installed [CLOSED]
T-00233-5607 | PS5-71-XV-0089-CL01 | TPX09 - LV power cable | E | PS5-71-04 - CFO Storage Tank | Closed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151115 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151115 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. [OPEN] | TZ-MID-68-WPR2-151117,151115 Permanent SS cable tags to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151117,151115 Cable need to be dressing completely at both side [OPEN]
T-00233-5608 | PS5-71-XV-0090-CL01 | TPX09 - LV power cable | E | PS5-71-12 - CFO Service Tank | Closed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151117,151115 Field run cable tray to be complete installation at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151115 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. [OPEN] | TZ-MID-68-WPR2-151117,151115 Permanent SS cable tags to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151115 Cable need to be dressing completely at both side [OPEN]
T-00233-5610 | PS5-71-XV-0092-CL01 | TPX09 - LV power cable | E | PS5-71-20 - Diesel Fuel Day Tank | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-331-07-0267 |  |  | TZ-MID-68-WPR2-151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117-SS Tag on both ends not installed [CLOSED]
T-00233-5612 | PS5-74-LB-5101-CL01 | TPX09 - LV power cable | E | PS5-74-02 - N2 Generation Skid (UCP) | Closed | CPP-RFI-68-331-05-0260 | CPP-RFI-68-331-07-0261 |  | TZ-MID-68-WPR2-151167,151116,151112,151111,151108 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0029, PS5-88-BU-HV-0017, PS5-88-DU-HV-0004, PS5-88-BU-HV-0013) [OPEN] | TZ-MID-68-WPR2-151167,151116,151112,151111,151108 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167,151116,151112,151111,151108 Cable dressing to be done both side [OPEN]
T-00233-5613 | PS5-74-LB-5101-CL02 | TPX09 - LV power cable | E | PS5-74-02 - N2 Generation Skid (UCP) | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0303 |  |  | TZ-MID-68-WPR2-151167,151116,151112,151111,151108-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151167,151116,151112,151111,151108-SS Tag on both ends not installed [OPEN]
T-00233-5620 | PS5-75-MOV-0001-CL01 | TPX09 - LV power cable | E | PS5-28-07 - Open Drains (OD2) | Closed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  | TZ-MID-68-WPR2-151117,151114,151113 Field run cable tray/ladder to be installed completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable trench backfiled, protection tiles, and warning tape installation to be done (PS5-88-BU-LV-00164) [OPEN] | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151117,151114,151113 Cable to be dressing completely at both side [OPEN]
T-00233-5624 | PS5-78-JC-9100B-CL01 | TPX09 - LV power cable | E | PS5-78-01 - Lifting and handling equipment | Closed |  | CPP-RFI-68-33/1-07-0427
T-00233-5625 | PS5-78-JC-9100C-CL01 | TPX09 - LV power cable | E | PS5-78-01 - Lifting and handling equipment | Closed |  | CPP-RFI-68-33/1-07-0427
T-00233-5626 | PS5-78-JC-9100D-CL01 | TPX09 - LV power cable | E | PS5-78-01 - Lifting and handling equipment | Closed |  | CPP-RFI-68-33/1-07-0427
T-00233-5640 | PS5-87-IRF-0001-CL01 | TPX09 - LV power cable | E | PS5-53-01 - Utility Water / Storage Tank | Closed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151111,151108,151109 Field run cable tray to be install at both equipment side [OPEN] | TZ-MID-68-WPR2-151111,151108,151109 Permanent SS cable tags to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151111,151108,151109 Cable need to be dressing completely at both side [OPEN]
T-00233-5641 | PS5-87-IRF-0002-CL01 | TPX09 - LV power cable | E | PS5-71-04 - CFO Storage Tank | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  | TZ-MID-68-WPR2-151117,151115--Cable coiled, need to be laid in trench [OPEN] | TZ-MID-68-WPR2-151117,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151115-SS Tag on both ends not installed [CLOSED]
T-00233-5642 | PS5-87-IRF-0003-CL01 | TPX09 - LV power cable | E | PS5-71-12 - CFO Service Tank | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  | TZ-MID-68-WPR2-151117,151115--Cable coiled, need to be laid in trench [OPEN] | TZ-MID-68-WPR2-151117,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151117,151115-SS Tag on both ends not installed [CLOSED]
T-00233-5643 | PS5-87-IRF-0004-CL01 | TPX09 - LV power cable | E | PS5-71-15 - Diesel Fuel Storage Tank | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 |  |  | TZ-MID-68-WPR2-151111,151108,151107-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151111,151108,151107-SS Tag on both ends not installed [CLOSED]
T-00233-9120 | PS5-02-SWSI-0001-CL01 | TPX09 - LV power cable | E | PS5-02-01 - Miscellaneous Safety equipment | Closed | CPP-RFI-68-33/1-05-0329 | CPP-RFI-68-33/1-07-0321 |  | Doc. TZ-MID-68-WPR2-151111 TZ-MID-68-WPR2-151105, Cable Not Yet Reaching Final Destination, Coiled more than 10 MTR need to Open Trench to Finish installation & Reaching Final Destination (Illuminated Windshock) [OPEN] | Doc. TZ-MID-68-WPR2-151111 TZ-MID-68-WPR2-151105, Cable Tagging Not Yet installed at both Side [OPEN] ¦ Doc. TZ-MID-68-WPR2-151111 TZ-MID-68-WPR2-151105, Cable Dressing not yet done [OPEN]
T-00233-9121 | PS5-02-SWSI-0003-CL01 | TPX09 - LV power cable | E | PS5-02-01 - Miscellaneous Safety equipment | Closed |  | CPP-RFI-68-331-07-0423
T-00233-9131 | PS5-60-BE-0007A-CL01 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN]
T-00233-9132 | PS5-60-BE-0007B-CL01 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN]
T-00233-9133 | PS5-60-BE-0007C-CL01 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | Closed |  | CPP-RFI-68-33/1-07-0410
T-00233-9134 | PS5-60-BE-0007D-CL01 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | Closed |  | CPP-RFI-68-33/1-07-0330 |  |  | TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00233-9135 | PS5-60-BE-0007E-CL01 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | Closed |  | CPP-RFI-68-33/1-07-0410
T-00233-9136 | PS5-60-BE-0007F-CL01 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | Closed |  | CPP-RFI-68-33/1-07-0410
T-00233-9137 | PS5-60-BE-0007G-CL01 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | Closed |  | CPP-RFI-68-33/1-07-0410
T-00233-9138 | PS5-60-BE-0027A-CL01 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9145 | PS5-60-BE-0028A-CL01 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9146 | PS5-60-BE-0028B-CL01 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9149 | PS5-60-BE-0028E-CL01 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-9150 | PS5-60-BE-0028F-CL01 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-9151 | PS5-60-BE-0028G-CL01 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-9152 | PS5-60-BI-0006A-CL01 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9153 | PS5-60-BI-0006A-CL02 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  | TZ-MID-68-WPR2-151179 Field Run Cable Tray To be installed [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00233-9154 | PS5-60-BI-0006A-CL03 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9155 | PS5-60-BI-0006A-CL04 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9156 | PS5-60-BI-0006A-CL05 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9157 | PS5-60-BI-0006A-CL06 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9158 | PS5-60-BI-0006A-CL07 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9159 | PS5-60-BI-0006A-CL08 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9160 | PS5-60-BI-0006A-CL09 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9161 | PS5-60-BI-0006A-CL10 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9162 | PS5-60-BI-0006A-CL11 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9163 | PS5-60-BI-0006B-CL01 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9164 | PS5-60-BI-0006B-CL02 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9165 | PS5-60-BI-0006B-CL03 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9166 | PS5-60-BI-0006B-CL04 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9167 | PS5-60-BI-0006B-CL05 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9168 | PS5-60-BI-0006B-CL06 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9169 | PS5-60-BI-0006B-CL07 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9170 | PS5-60-BI-0006B-CL08 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9171 | PS5-60-BI-0006B-CL09 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9172 | PS5-60-BI-0006B-CL10 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9173 | PS5-60-BI-0006B-CL11 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9174 | PS5-60-BI-0006C-CL01 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | Closed |  | CPP-RFI-68-33/1-07-0405
T-00233-9176 | PS5-60-BI-0006C-CL03 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-9177 | PS5-60-BI-0006C-CL04 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-9178 | PS5-60-BI-0006C-CL05 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-9179 | PS5-60-BI-0006C-CL06 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | Closed
T-00233-9180 | PS5-60-BI-0006C-CL07 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | Closed
T-00233-9181 | PS5-60-BI-0006C-CL08 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | Closed
T-00233-9182 | PS5-60-BI-0006C-CL09 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | Closed
T-00233-9183 | PS5-60-BI-0006C-CL10 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | Closed
T-00233-9185 | PS5-60-BI-0006D-CL01 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | Closed |  | CPP-RFI-68-33/1-07-0405
T-00233-9187 | PS5-60-BI-0006D-CL03 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | Closed
T-00233-9188 | PS5-60-BI-0006D-CL04 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | Closed
T-00233-9189 | PS5-60-BI-0006D-CL05 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | Closed
T-00233-9190 | PS5-60-BI-0006D-CL06 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | Closed
T-00233-9191 | PS5-60-BI-0006D-CL07 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | Closed
T-00233-9192 | PS5-60-BI-0006D-CL08 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | Closed
T-00233-9193 | PS5-60-BI-0006D-CL09 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | Closed
T-00233-9194 | PS5-60-BI-0006D-CL10 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | Closed
T-00233-9195 | PS5-60-BI-0006D-CL11 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-9196 | PS5-60-BI-0006E-CL01 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | Closed |  | CPP-RFI-68-33/1-07-0405
T-00233-9198 | PS5-60-BI-0006E-CL03 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | Closed |  | CPP-RFI-68-33/1-07-0427
T-00233-9203 | PS5-60-BI-0006E-CL08 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | Closed |  | CPP-RFI-68-33/1-07-0420
T-00233-9206 | PS5-60-BI-0006E-CL11 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-9210 | PS5-60-BI-0006F-CL04 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-9217 | PS5-60-BI-0006F-CL11 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-9228 | PS5-60-BI-0006G-CL11 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | Closed |  | CPP-RFI-68-331-07-0422
T-00233-9229 | PS5-60-BI-0017A-CL01 | TPX09 - LV power cable | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9230 | PS5-60-BI-0017B-CL01 | TPX09 - LV power cable | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install [OPEN] | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends [OPEN]
T-00233-9231 | PS5-60-BI-0017C-CL01 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | Closed |  | CPP-RFI-68-331-07-0422
T-00233-9232 | PS5-60-BI-0017D-CL01 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | Closed |  | CPP-RFI-68-331-07-0422
T-00233-9233 | PS5-60-BI-0017E-CL01 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | Closed |  | CPP-RFI-68-331-07-0422
T-00233-9234 | PS5-60-BI-0017F-CL01 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | Closed |  | CPP-RFI-68-331-07-0422
T-00233-9235 | PS5-60-BI-0017G-CL01 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | Closed |  | CPP-RFI-68-33/1-07-0412
T-00233-9238 | PS5-60-EA-2900C-CL01 | TPX09 - LV power cable | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | Closed |  | CPP-RFI-68-33/1-07-0405
T-00233-9239 | PS5-60-EA-2900D-CL01 | TPX09 - LV power cable | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | Closed |  | CPP-RFI-68-33/1-07-0405
T-00233-9240 | PS5-60-EA-2900E-CL01 | TPX09 - LV power cable | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | Closed |  | CPP-RFI-68-33/1-07-0405
T-00233-9241 | PS5-60-EA-2900F-CL01 | TPX09 - LV power cable | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | Closed |  | CPP-RFI-68-33/1-07-0405
T-00233-9242 | PS5-60-EA-2900G-CL01 | TPX09 - LV power cable | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | Closed |  | CPP-RFI-68-33/1-07-0415
T-00233-9244 | PS5-71-BE-0004-CL01 | TPX09 - LV power cable | E | PS5-71-08 - CFO Pre-Pressure Modules | Closed | CPP-RFI-68-331-05-0399 | CPP-RFI-68-331-07-0400 |  | TZ-MID-68-WPR2-151167, 151118, 151179 Field Run cable tray to be install [OPEN] | TZ-MID-68-WPR2-151167, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167, 151118, 151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables [OPEN]
T-00233-9246 | PS5-71-BE-0004-CL03 | TPX09 - LV power cable | E | PS5-71-08 - CFO Pre-Pressure Modules | Closed | CPP-RFI-68-331-05-0399 | CPP-RFI-68-331-07-0400 |  | TZ-MID-68-WPR2-151167, 151118, 151179 Field Run cable tray to be install [OPEN] | TZ-MID-68-WPR2-151167, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167, 151118, 151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables [OPEN]
T-00233-9247 | PS5-71-BI-0003-CL01 | TPX09 - LV power cable | E | PS5-71-08 - CFO Pre-Pressure Modules | Closed | CPP-RFI-68-331-05-0399 | CPP-RFI-68-331-07-0400 |  | TZ-MID-68-WPR2-151167, 151118, 151179 Field Run cable tray to be install [OPEN] | TZ-MID-68-WPR2-151167, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167, 151118, 151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables [OPEN]
T-00233-9248 | PS5-71-BI-0003-CL02 | TPX09 - LV power cable | E | PS5-71-08 - CFO Pre-Pressure Modules | Closed |  | CPP-RFI-68-33/1-07-0410
T-00233-9249 | PS5-71-BI-0003-CL03 | TPX09 - LV power cable | E | PS5-71-08 - CFO Pre-Pressure Modules | Closed |  | CPP-RFI-68-331-07-0409
T-00233-9250 | PS5-71-BI-0003-CL04 | TPX09 - LV power cable | E | PS5-71-08 - CFO Pre-Pressure Modules | Closed |  | CPP-RFI-68-331-07-0409
T-00233-9251 | PS5-71-BI-0004-CL01 | TPX09 - LV power cable | E | PS5-71-08 - CFO Pre-Pressure Modules | Closed |  | CPP-RFI-68-331-07-0423
T-00233-9252 | PS5-71-BI-0005-CL01 | TPX09 - LV power cable | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cables Dressing not yet done at both ends [OPEN]
T-00233-9253 | PS5-71-BI-0005-CL02 | TPX09 - LV power cable | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cables Dressing not yet done at both ends [OPEN]
T-00233-9254 | PS5-71-BI-0005-CL03 | TPX09 - LV power cable | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  | TZ-MID-68-WPR2-151167, 151118, 151179 Field Run Cable tray to be intall [OPEN] | TZ-MID-68-WPR2-151167, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00233-9255 | PS5-71-BI-0006-CL01 | TPX09 - LV power cable | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | Closed | CPP-RFI-68-33/1-05-0377 | CPP-RFI-68-33/1-07-0378 |  |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends [OPEN] ¦ Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cables Dressing not yet done at both ends [OPEN]
T-00234-2028 | PS5-05-IE-8100-CD01 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00234-2029 | PS5-05-IE-8100-CD02 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00234-2030 | PS5-05-IE-8100-CD03 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00234-2031 | PS5-05-IE-8100-CD04 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00234-2032 | PS5-05-IE-8100-CD05 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00234-2033 | PS5-05-IE-8100-CD06 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00234-2034 | PS5-05-IE-8100-CD07 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00234-2038 | PS5-05-IE-8100-CD11 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00234-2045 | PS5-05-IE-8100-CD18 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00234-2046 | PS5-05-IE-8100-CD19 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00234-2047 | PS5-05-IE-8100-CD20 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00234-2048 | PS5-05-IE-8100-CD21 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | Closed | CPP-RFI-68-331-05-0391 | CPP-RFI-68-33/1-07-0392 |  |  | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. [OPEN]
T-00234-2052 | PS5-05-IE-8100-CD25 | TPX10 - Multicore electrical control cable | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | Closed | CPP-RFI-68-331-05-0312 | CPP-RFI-68-331-07-0313 |  |  | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side [OPEN]
T-00234-2061 | PS5-25-DM-3100A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Trench Not yet complete installation both end [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Field Run Cable tray not yet complete installation both end. [OPEN] | TZ-MID-68-WPR2-151111,151115,151117,151114 Dressing Cable Both Side to be done [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Permanent Cable Tag Missing Both End [CLOSED]
T-00234-2062 | PS5-25-DM-3100B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Trench Not yet complete installation both end [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Field Run Cable tray not yet complete installation both end. [OPEN] | TZ-MID-68-WPR2-151111,151115,151117,151114 Dressing Cable Both Side to be done [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Permanent Cable Tag Missing Both End [CLOSED]
T-00234-2063 | PS5-25-DM-3100C-CD01 | TPX10 - Multicore electrical control cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-331-05-0225 | CPP-RFI-68-331-07-0247 |  | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Trench Not yet complete installation both end [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Field Run Cable tray not yet complete installation both end. [OPEN] | TZ-MID-68-WPR2-151111,151115,151117,151114 Dressing Cable Both Side to be done [OPEN] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114 Permanent Cable Tag Missing Both End [CLOSED]
T-00234-2067 | PS5-25-IES-3100A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0287 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00234-2068 | PS5-25-IES-3100B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0287 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00234-2069 | PS5-25-IES-3100C-CD01 | TPX10 - Multicore electrical control cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0287 |  |  | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely [OPEN]
T-00234-2101 | PS5-60-IE-0002A-CD01 | TPX10 - Multicore electrical control cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN]
T-00234-2102 | PS5-60-IE-0002A-CD02 | TPX10 - Multicore electrical control cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN]
T-00234-2103 | PS5-60-IE-0002A-CD03 | TPX10 - Multicore electrical control cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN]
T-00234-2104 | PS5-60-IE-0002B-CD01 | TPX10 - Multicore electrical control cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN]
T-00234-2105 | PS5-60-IE-0002B-CD02 | TPX10 - Multicore electrical control cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN]
T-00234-2106 | PS5-60-IE-0002B-CD03 | TPX10 - Multicore electrical control cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN]
T-00234-2107 | PS5-60-IE-0002C-CD01 | TPX10 - Multicore electrical control cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-331-05-0399 | CPP-RFI-68-331-07-0400 |  | TZ-MID-68-WPR2-151179 Secondary cable tray to be install at both side [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables [OPEN]
T-00234-2108 | PS5-60-IE-0002C-CD02 | TPX10 - Multicore electrical control cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-331-05-0399 | CPP-RFI-68-331-07-0400 |  | TZ-MID-68-WPR2-151179 Secondary cable tray to be install at both side [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables [OPEN]
T-00234-2109 | PS5-60-IE-0002C-CD03 | TPX10 - Multicore electrical control cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-331-05-0399 | CPP-RFI-68-331-07-0400 |  | TZ-MID-68-WPR2-151179 Secondary cable tray to be install at both side [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables [OPEN]
T-00234-2110 | PS5-60-IE-0002D-CD01 | TPX10 - Multicore electrical control cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-331-05-0399 | CPP-RFI-68-331-07-0400 |  | TZ-MID-68-WPR2-151179 Secondary cable tray to be install at both side [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables [OPEN]
T-00234-2111 | PS5-60-IE-0002D-CD02 | TPX10 - Multicore electrical control cable | E | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-331-05-0399 | CPP-RFI-68-331-07-0400 |  | TZ-MID-68-WPR2-151179 Secondary cable tray to be install at both side [OPEN] | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables [OPEN]
T-00234-2112 | PS5-60-IE-0002D-CD03 | TPX10 - Multicore electrical control cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-331-07-0422
T-00234-2113 | PS5-60-IE-0002E-CD01 | TPX10 - Multicore electrical control cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-33/1-07-0421
T-00234-2114 | PS5-60-IE-0002E-CD02 | TPX10 - Multicore electrical control cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-33/1-07-0421
T-00234-2115 | PS5-60-IE-0002E-CD03 | TPX10 - Multicore electrical control cable | E | PS5-60-13 - Power Generation Package E | Closed |  | CPP-RFI-68-33/1-07-0421
T-00234-2116 | PS5-60-IE-0002F-CD01 | TPX10 - Multicore electrical control cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0415
T-00234-2117 | PS5-60-IE-0002F-CD02 | TPX10 - Multicore electrical control cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0415
T-00234-2118 | PS5-60-IE-0002F-CD03 | TPX10 - Multicore electrical control cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-33/1-07-0415
T-00234-2119 | PS5-60-IE-0002G-CD01 | TPX10 - Multicore electrical control cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0415
T-00234-2120 | PS5-60-IE-0002G-CD02 | TPX10 - Multicore electrical control cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0415
T-00234-2121 | PS5-60-IE-0002G-CD03 | TPX10 - Multicore electrical control cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-33/1-07-0415
T-00234-2123 | PS5-60-IE-0003A-CD02 | TPX10 - Multicore electrical control cable | E | PS5-60-01 - Power Generation Package A | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00234-2124 | PS5-60-IE-0003A-CD03 | TPX10 - Multicore electrical control cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179,151116,151118,151167 Cable dressing to be done at both side [OPEN]
T-00234-2125 | PS5-60-IE-0003A-CD04 | TPX10 - Multicore electrical control cable | E | PS5-60-01 - Power Generation Package A | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00234-2126 | PS5-60-IE-0003A-CD05 | TPX10 - Multicore electrical control cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179,151116,151118,151167 Cable dressing to be done at both side [OPEN]
T-00234-2135 | PS5-60-IE-0003A-CD14 | TPX10 - Multicore electrical control cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179,151116,151118,151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179,151116,151118, 151167 Permanent SS cable tag to be install at both side [OPEN]
T-00234-2136 | PS5-60-IE-0003A-CD15 | TPX10 - Multicore electrical control cable | E | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN]
T-00234-2138 | PS5-60-IE-0003B-CD02 | TPX10 - Multicore electrical control cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179,151116,151118,151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179,151116,151118, 151167 Permanent SS cable tag to be install at both side [OPEN]
T-00234-2139 | PS5-60-IE-0003B-CD03 | TPX10 - Multicore electrical control cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179,151116,151118,151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179,151116,151118, 151167 Permanent SS cable tag to be install at both side [OPEN]
T-00234-2140 | PS5-60-IE-0003B-CD04 | TPX10 - Multicore electrical control cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN]
T-00234-2141 | PS5-60-IE-0003B-CD05 | TPX10 - Multicore electrical control cable | E | PS5-60-04 - Power Generation Package B | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00234-2150 | PS5-60-IE-0003B-CD14 | TPX10 - Multicore electrical control cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-331-05-0347 | CPP-RFI-68-331-07-0348 |  | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely [OPEN] | TZ-MID-68-WPR2-151179,151116,151118, 151167 Cable dressing to be done at both side [OPEN] ¦ TZ-MID-68-WPR2-151179,151116,151118, 151167 Permanent SS cable tag to be install at both side [OPEN]
T-00234-2151 | PS5-60-IE-0003B-CD15 | TPX10 - Multicore electrical control cable | E | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  |  | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151167 Cable dressing to be done at both side [OPEN]
T-00234-2155 | PS5-60-IE-0003C-CD04 | TPX10 - Multicore electrical control cable | E | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00234-2169 | PS5-60-IE-0003D-CD03 | TPX10 - Multicore electrical control cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00234-2170 | PS5-60-IE-0003D-CD04 | TPX10 - Multicore electrical control cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00234-2171 | PS5-60-IE-0003D-CD05 | TPX10 - Multicore electrical control cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00234-2180 | PS5-60-IE-0003D-CD14 | TPX10 - Multicore electrical control cable | E | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-33/1-07-0330 |  | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) [OPEN] | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done [OPEN]
T-00234-2185 | PS5-60-IE-0003E-CD04 | TPX10 - Multicore electrical control cable | E | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00234-2198 | PS5-60-IE-0003F-CD02 | TPX10 - Multicore electrical control cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-331-07-0423
T-00234-2199 | PS5-60-IE-0003F-CD03 | TPX10 - Multicore electrical control cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-331-07-0423
T-00234-2200 | PS5-60-IE-0003F-CD04 | TPX10 - Multicore electrical control cable | E | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00234-2211 | PS5-60-IE-0003F-CD15 | TPX10 - Multicore electrical control cable | E | PS5-60-16 - Power Generation Package F | Closed |  | CPP-RFI-68-331-07-0423
T-00234-2213 | PS5-60-IE-0003G-CD02 | TPX10 - Multicore electrical control cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-331-07-0423
T-00234-2214 | PS5-60-IE-0003G-CD03 | TPX10 - Multicore electrical control cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-331-07-0423
T-00234-2215 | PS5-60-IE-0003G-CD04 | TPX10 - Multicore electrical control cable | E | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-33/1-05-0387 | CPP-RFI-68-33/1-07-0388 |  |  | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Permanent SS cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. [OPEN]
T-00234-2216 | PS5-60-IE-0003G-CD05 | TPX10 - Multicore electrical control cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-331-07-0423
T-00234-2225 | PS5-60-IE-0003G-CD14 | TPX10 - Multicore electrical control cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-331-07-0423
T-00234-2226 | PS5-60-IE-0003G-CD15 | TPX10 - Multicore electrical control cable | E | PS5-60-19 - Power Generation Package G | Closed |  | CPP-RFI-68-331-07-0423
T-00234-2233 | PS5-61-IDH-3100A-CD03 | TPX10 - Multicore electrical control cable | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-33/1-05-0217 |  |  |  | Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely [OPEN]
T-00234-2236 | PS5-61-IDH-3100B-CD03 | TPX10 - Multicore electrical control cable | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-33/1-05-0217 |  |  |  | Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely [OPEN]
T-00234-2239 | PS5-61-IDH-3100C-CD03 | TPX10 - Multicore electrical control cable | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-33/1-05-0217 |  |  |  | Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely [OPEN]
T-00234-2288 | PS5-62-IE-0001-CD01 | TPX10 - Multicore electrical control cable | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | Closed | CPP-RFI-68-331-05-0226 | CPP-RFI-68-331-07-0248 |  | TZ-MID-68-WPR2-151111 To be install vertical cable ladder at both end [OPEN] | TZ-MID-68-WPR2-151111 Dressing to be done at both end [OPEN]
T-00234-3399 | PS5-06-GU-0003A-CD02 | TPX10 - Multicore electrical control cable | E | PS5-06-02 - AC UPS - Power Generator Building | Closed | CPP-RFI-68-331-05-0368 | CPP-RFI-68-331-07-0369 |  |  | TZ-MID-68-WPR2-151112, 151116, 151118 Permanent SS Cable Tag to be Installed at both side [OPEN] ¦ TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be done at both side [OPEN]
T-00235-0013 | PS5-25-DM-3100A | TPX12 - Motor HV | E | PS5-25-02 - Crude Oil Export Pump A | Closed |  | CPP-RFI-68-331-18-0364
T-00235-0014 | PS5-25-DM-3100B | TPX12 - Motor HV | E | PS5-25-03 - Crude Oil Export Pump B | Closed |  | CPP-RFI-68-331-18-0364
T-00235-0015 | PS5-25-DM-3100C | TPX12 - Motor HV | E | PS5-25-04 - Crude Oil Export Pump C | Closed |  | CPP-RFI-68-331-18-0364
T-00238-0562 | PS5-62-IE-0001 | TPX15 - Distribution board/console/control panel | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | Closed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  | TZ-MID-68-WPR2-151111 Isolation pad to be install at SS bracket and bolts since disimilar material. [OPEN] |  | TZ-MID-68-WPR2-151111 Perform cleanning internal and external of the panel [OPEN]
T-00238-0563 | PS5-62-IE-0002 | TPX15 - Distribution board/console/control panel | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | Closed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  |  | TZ-MID-68-WPR2-151117 To be clean weld slag and touch up paint at the panel support. [OPEN] | TZ-MID-68-WPR2-151117 Perform cleanning internal and external of the panel [OPEN]
T-00238-0716 | PS5-05-IG-0004 | TPX15 - Distribution board/console/control panel | E | PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | Closed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  | TZ-MID-68-WPR2-151117 Door glass has cracked to be rectify/replaced [OPEN] | TZ-MID-68-WPR2-151117 To be clean weld slag and touch up paint at the panel support. [OPEN] | TZ-MID-68-WPR2-151117 Perform cleanning internal and external of the panel [OPEN]
T-00238-0717 | PS5-05-IG-0006 | TPX15 - Distribution board/console/control panel | E | PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | Closed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  | TZ-MID-68-WPR2-151111 Isolation pad to be install at SS bracket and bolts since disimilar material. [OPEN] |  | TZ-MID-68-WPR2-151111 Perform cleanning internal and external of the panel [OPEN]
T-00238-0723 | PS5-61-IG-0006 | TPX15 - Distribution board/console/control panel | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | Closed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  |  | TZ-MID-68-WPR2-151117 To be clean weld slag and touch up paint at the panel support. [OPEN] | TZ-MID-68-WPR2-151117 Perform cleanning internal and external of the panel [OPEN]
T-00238-0724 | PS5-61-IG-0007 | TPX15 - Distribution board/console/control panel | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | Closed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  | TZ-MID-68-WPR2-151111 Isolation pad to be install at SS bracket and bolts since disimilar material. [OPEN] |  | TZ-MID-68-WPR2-151111 Perform cleanning internal and external of the panel [OPEN] ¦ TZ-MID-68-WPR2-151111 Body panel scratc to be touch up paint [OPEN]
T-00238-0725 | PS5-61-IG-0014 | TPX15 - Distribution board/console/control panel | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | Closed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  | TZ-MID-68-WPR2-151111 Isolation pad to be install at SS bracket and bolts since disimilar material. [OPEN] |  | TZ-MID-68-WPR2-151111 Perform cleanning internal and external of the panel [OPEN]
T-00238-0728 | PS5-61-IG-0042 | TPX15 - Distribution board/console/control panel | E | PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-0042 | Closed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  | TZ-MID-68-WPR2-151117 Door glass has cracked to be rectify/replaced [OPEN] | TZ-MID-68-WPR2-151117 To be clean weld slag and touch up paint at the panel support. [OPEN] | TZ-MID-68-WPR2-151117 Perform cleanning internal and external of the panel [OPEN]
T-00238-0729 | PS5-61-IG-0043 | TPX15 - Distribution board/console/control panel | E | PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-0043 | Closed | CPP-RFI-68-332-03-0341 | CPP-RFI-68-332-17-0342 |  |  | TZ-MID-68-WPR2-151117 To be clean weld slag and touch up paint at the panel support. [OPEN] | TZ-MID-68-WPR2-151117 Perform cleanning internal and external of the panel [OPEN]
T-00238-0731 | PS5-79-IG-0001 | TPX15 - Distribution board/console/control panel | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | Closed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151115 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00238-0732 | PS5-79-IG-0002 | TPX15 - Distribution board/console/control panel | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | Closed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151115 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00238-0733 | PS5-79-IG-0003 | TPX15 - Distribution board/console/control panel | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | Closed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00238-0734 | PS5-79-IG-0004 | TPX15 - Distribution board/console/control panel | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | Closed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00238-0735 | PS5-79-IG-0005 | TPX15 - Distribution board/console/control panel | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | Closed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug [OPEN] | TZ-MID-68-WPR2-151117 Need install seam plate to the gap between concrete foundation and frame support of DB Panel [OPEN] | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00238-0736 | PS5-79-IG-0006 | TPX15 - Distribution board/console/control panel | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | Closed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug [OPEN] | TZ-MID-68-WPR2-151117 Need install seam plate to the gap between concrete foundation and frame support of DB Panel [OPEN] | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00238-0737 | PS5-79-IG-0007 | TPX15 - Distribution board/console/control panel | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | Closed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00238-0738 | PS5-79-IG-0008 | TPX15 - Distribution board/console/control panel | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | Closed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00238-0739 | PS5-79-IG-0009 | TPX15 - Distribution board/console/control panel | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | Closed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00238-0740 | PS5-79-IG-0010 | TPX15 - Distribution board/console/control panel | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | Closed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00238-0741 | PS5-79-IG-0011 | TPX15 - Distribution board/console/control panel | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | Closed | CPP-RFI-68-33/2-03-0302 | CPP-RFI-68-332-17-0335 |  | TZ-MID-68-WPR2-151118 Un-used cable entries to be install dummy plug [OPEN] |  | TZ-MID-68-WPR2-151118 To perform cleanning for EHT Distribution board body and surround area [OPEN]
T-00240-1316 |  | TPX18 - Lighting circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | Closed
T-00240-1317 |  | TPX18 - Lighting circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | Closed
T-00240-1319 |  | TPX18 - Lighting circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | Closed
T-00240-1321 |  | TPX18 - Lighting circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | Closed
T-00240-1324 |  | TPX18 - Lighting circuits | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | Closed
T-00254-4287 | PS5-01-PIT-0010-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-01-07 - Fire Water Ring Main & Distribution | Closed | CPP-RFI-68-64-12-0061 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4376 | PS5-03-GDLHP-0147-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4377 | PS5-03-GDLHP-0149-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4378 | PS5-03-GDLHP-0150-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4379 | PS5-03-GDLHP-0401-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4395 | PS5-03-RDH-0601-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | Closed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00254-4396 | PS5-03-RDH-0602-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | Closed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00254-4397 | PS5-03-RDH-0603-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | Closed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00254-4398 | PS5-03-RDH-0604-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | Closed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00254-4399 | PS5-03-RDH-0605-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | Closed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00254-4400 | PS5-03-RDH-0606-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | Closed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00254-4401 | PS5-03-RDH-0607-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | Closed
T-00254-4402 | PS5-03-RDH-0608-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | Closed
T-00254-4403 | PS5-03-RDH-0609-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | Closed
T-00254-4407 | PS5-03-RDH-0614-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4408 | PS5-03-RDH-0615-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4409 | PS5-03-RDH-0616-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4415 | PS5-03-RDH-0830-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-4416 | PS5-03-RDH-0831-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-4457 | PS5-03-RDIR-0104-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0092
T-00254-4458 | PS5-03-RDIR-0105-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0092
T-00254-4459 | PS5-03-RDIR-0106-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0092
T-00254-4461 | PS5-03-RDIR-0108-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00254-4462 | PS5-03-RDIR-0109-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00254-4463 | PS5-03-RDIR-0110-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00254-4464 | PS5-03-RDIR-0111-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00254-4465 | PS5-03-RDIR-0112-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00254-4466 | PS5-03-RDIR-0113-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00254-4467 | PS5-03-RDIR-0114-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4468 | PS5-03-RDIR-0115-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4469 | PS5-03-RDIR-0116-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4470 | PS5-03-RDIR-0117-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4471 | PS5-03-RDIR-0118-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4472 | PS5-03-RDIR-0121-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-4473 | PS5-03-RDIR-0122-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-4474 | PS5-03-RDIR-0123-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-4476 | PS5-03-RDIR-0125-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-4477 | PS5-03-RDIR-0126-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-4478 | PS5-03-RDIR-0127-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-4485 | PS5-03-RDIR-0137-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0092 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00254-4486 | PS5-03-RDIR-0138-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-4-0089 | CPP-RFI-68-64-12-0090
T-00254-4487 | PS5-03-RDIR-0141-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0092
T-00254-4488 | PS5-03-RDIR-0142-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0092 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00254-4489 | PS5-03-RDIR-0403-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN]
T-00254-4490 | PS5-03-RDIR-0404-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | Closed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0075
T-00254-4491 | PS5-03-RDIR-0405-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | Closed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0092
T-00254-4493 | PS5-03-RDIR-0409-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | Closed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0092
T-00254-4494 | PS5-03-RDIR-0411-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | Closed | CPP-RFI-68-64-4-0091 | CPP-RFI-68-64-12-0075
T-00254-4495 | PS5-03-RDIR-0819-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4496 | PS5-03-RDIR-0820-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4497 | PS5-03-RDIR-0832-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4536 | PS5-03-RMAC-0101-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4537 | PS5-03-RMAC-0102-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-4538 | PS5-03-RMAC-0103-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4542 | PS5-03-RMAC-0401-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-4543 | PS5-03-RMAC-0402-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4544 | PS5-03-RMAC-0613-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-06 - FZ-06 - Transformer Area | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN]
T-00254-4565 | PS5-05-BI-0002-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-05-01 - Emergency Diesel Generator Package | Closed | CPP-RFI-68-64-04-0049 | CPP-RFI-68-64-04-0049 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side [OPEN]
T-00254-4654 | PS5-25-ESDV-0021-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4657 | PS5-25-ESDV-0023-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4660 | PS5-25-ESY-0021A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4661 | PS5-25-ESY-0021B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4662 | PS5-25-ESY-0023B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4667 | PS5-25-FIT-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00254-4668 | PS5-25-FIT-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00254-4669 | PS5-25-FIT-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00254-4671 | PS5-25-FIT-0004-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4676 | PS5-25-FY-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00254-4677 | PS5-25-FY-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00254-4679 | PS5-25-FY-0004-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4680 | PS5-25-HS-8101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4681 | PS5-25-HS-8101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4682 | PS5-25-HS-8101C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4683 | PS5-25-HS-8102A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4684 | PS5-25-HS-8102B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4685 | PS5-25-HS-8102C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4687 | PS5-25-MOV-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4688 | PS5-25-MOV-0003-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4690 | PS5-25-MOV-0011-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4691 | PS5-25-MOV-0012-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4693 | PS5-25-MOV-0026-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4694 | PS5-25-MOV-0026-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094
T-00254-4695 | PS5-25-MOV-0027-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4696 | PS5-25-MOV-0027-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | Closed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00254-4709 | PS5-25-PDIT-0034B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00254-4712 | PS5-25-PI-1102B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00254-4713 | PS5-25-PI-1202B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | Closed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00254-4714 | PS5-25-PIT-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094
T-00254-4715 | PS5-25-PIT-0003AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00254-4716 | PS5-25-PIT-0003BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00254-4722 | PS5-25-PIT-0005A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00254-4723 | PS5-25-PIT-0005B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00254-4725 | PS5-25-PIT-0007A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00254-4726 | PS5-25-PIT-0007B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00254-4728 | PS5-25-PIT-0008A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4731 | PS5-25-PIT-0013-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4732 | PS5-25-PIT-0018-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00254-4733 | PS5-25-PIT-0022-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4742 | PS5-25-PIT-0053-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4746 | PS5-25-PIT-0070-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | Closed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00254-4750 | PS5-25-PIT-1102-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00254-4751 | PS5-25-PIT-1202-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | Closed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00254-4752 | PS5-25-SDV-0022-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4754 | PS5-25-SDV-0035A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4755 | PS5-25-SDV-0035B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4757 | PS5-25-SDV-0036A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4760 | PS5-25-SDV-0046-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4763 | PS5-25-SDV-0054A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4764 | PS5-25-SDV-0054B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4768 | PS5-25-SXS-0035A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-4769 | PS5-25-SXS-0035B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-4770 | PS5-25-SXS-0035C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-4771 | PS5-25-SXS-0036A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-4772 | PS5-25-SXS-0036B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-4773 | PS5-25-SXS-0036C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-4774 | PS5-25-SXS-0046-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-4779 | PS5-25-SY-0022-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4780 | PS5-25-SY-0035AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4782 | PS5-25-SY-0035BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4786 | PS5-25-SY-0036AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4792 | PS5-25-SY-0046A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4793 | PS5-25-SY-0046B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4796 | PS5-25-SY-0054AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4797 | PS5-25-SY-0054AB-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4802 | PS5-25-TIT-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00254-4806 | PS5-25-TIT-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00254-4807 | PS5-25-TIT-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00254-4809 | PS5-25-TIT-0004-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-06 - Crude Oil Export Pumps Discharge | Closed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094
T-00254-4810 | PS5-25-TIT-1101-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-01 - Export Pipeline Pig Receiver | Closed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00254-4811 | PS5-25-TIT-1201-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-07 - Export Pipeline Pig Launcher | Closed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00254-4817 | PS5-25-XY-0053-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4818 | PS5-25-XY-0070-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-25-05 - Crude Oil Export Pumps Bypass | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4831 | PS5-28-HY-3901A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4832 | PS5-28-HY-3901B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4835 | PS5-28-LI-1101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-03 - Closed Drain Drum and Pump 01 | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4836 | PS5-28-LI-1101C-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-03 - Closed Drain Drum and Pump 01 | Closed | CPP-RFI-68-64-04-0093 | CPP-RFI-68-64-12-0094 |  |  | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side [OPEN]
T-00254-4837 | PS5-28-LI-1402B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-04 - Closed Drain Drum and Pump 02 | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4838 | PS5-28-LIT-0002-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-08 - Open Drain Sump and Pumps | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4839 | PS5-28-LIT-0008-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-08 - Open Drain Sump and Pumps | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4840 | PS5-28-LIT-1101-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-03 - Closed Drain Drum and Pump 01 | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4841 | PS5-28-LIT-1102-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-03 - Closed Drain Drum and Pump 01 | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4843 | PS5-28-LIT-1202-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-06 - Relief Drum and Pump | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4844 | PS5-28-LIT-1301A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | Closed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00254-4845 | PS5-28-LIT-1301B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | Closed | CPP-RFI-68-64-04-0097 | CPP-RFI-68-64-12-0098
T-00254-4847 | PS5-28-LIT-1401-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-04 - Closed Drain Drum and Pump 02 | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4848 | PS5-28-LIT-1402-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-04 - Closed Drain Drum and Pump 02 | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4849 | PS5-28-PIT-0015-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4851 | PS5-28-PIT-0041-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4852 | PS5-28-PIT-0045-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4856 | PS5-28-PIT-3901A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4857 | PS5-28-PIT-3901B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4860 | PS5-28-SDV-0053A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4870 | PS5-28-SY-0045A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4871 | PS5-28-SY-0045B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-17 - Reinjection Pump | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4872 | PS5-28-SY-0053AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4874 | PS5-28-SY-0053BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4875 | PS5-28-SY-0053BB-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4878 | PS5-28-TIT-1104-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-03 - Closed Drain Drum and Pump 01 | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4879 | PS5-28-TIT-1105-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-03 - Closed Drain Drum and Pump 01 | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4881 | PS5-28-TIT-1401-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-04 - Closed Drain Drum and Pump 02 | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4882 | PS5-28-TIT-1402-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-04 - Closed Drain Drum and Pump 02 | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4883 | PS5-28-TIT-2101-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-03 - Closed Drain Drum and Pump 01 | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4884 | PS5-28-TIT-2201-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-28-04 - Closed Drain Drum and Pump 02 | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-4886 | PS5-50-FIT-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-50-03 - Water Pre-Treatment Package | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00254-4900 | PS5-60-BE-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-27 - Compressed Air Starting Skid | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4901 | PS5-60-BE-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-26 - Instrument Air Compressor Skid | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4902 | PS5-60-BE-0004A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4903 | PS5-60-BE-0004B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4904 | PS5-60-BE-0004C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4905 | PS5-60-BE-0004D-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4906 | PS5-60-BE-0004E-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4907 | PS5-60-BE-0004F-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4908 | PS5-60-BE-0004G-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4909 | PS5-60-BI-0001A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4910 | PS5-60-BI-0001A-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4911 | PS5-60-BI-0001B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4912 | PS5-60-BI-0001B-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4913 | PS5-60-BI-0001C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4914 | PS5-60-BI-0001C-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4915 | PS5-60-BI-0001D-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4916 | PS5-60-BI-0001D-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4917 | PS5-60-BI-0001E-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4918 | PS5-60-BI-0001E-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4919 | PS5-60-BI-0001F-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4920 | PS5-60-BI-0001F-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4921 | PS5-60-BI-0001G-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4922 | PS5-60-BI-0001G-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-4924 | PS5-60-BI-0002-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-4927 | PS5-60-BI-0003-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-4928 | PS5-60-BI-0003-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-22 - Power Gen Master UCP | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-4950 | PS5-60-BI-0006A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-4954 | PS5-60-BI-0006A-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-4956 | PS5-60-BI-0006B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-4960 | PS5-60-BI-0006B-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-4962 | PS5-60-BI-0006C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-4966 | PS5-60-BI-0006C-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-4968 | PS5-60-BI-0006D-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-4972 | PS5-60-BI-0006D-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-4974 | PS5-60-BI-0006E-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-4978 | PS5-60-BI-0006E-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-4980 | PS5-60-BI-0006F-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-4984 | PS5-60-BI-0006F-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-4986 | PS5-60-BI-0006G-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-4990 | PS5-60-BI-0006G-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5020 | PS5-60-BI-0016A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5022 | PS5-60-BI-0016A-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5024 | PS5-60-BI-0016B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5025 | PS5-60-BI-0016B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5026 | PS5-60-BI-0016B-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5028 | PS5-60-BI-0016C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5030 | PS5-60-BI-0016C-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5032 | PS5-60-BI-0016D-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5034 | PS5-60-BI-0016D-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5036 | PS5-60-BI-0016E-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5038 | PS5-60-BI-0016E-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5040 | PS5-60-BI-0016F-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5042 | PS5-60-BI-0016F-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5044 | PS5-60-BI-0016G-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5046 | PS5-60-BI-0016G-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5049 | PS5-60-BI-0017B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | Closed |  | CPP-RFI-68-64-12-0101
T-00254-5070 | PS5-60-IE-0002C-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5071 | PS5-60-IE-0002D-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5072 | PS5-60-IE-0002E-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5073 | PS5-60-IE-0002F-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5074 | PS5-60-IE-0002G-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5075 | PS5-60-IE-0003A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5076 | PS5-60-IE-0003A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5079 | PS5-60-IE-0003A-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5084 | PS5-60-IE-0003A-CC10 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | Closed |  | CPP-RFI-68-64-12-0101
T-00254-5085 | PS5-60-IE-0003A-CC11 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | Closed |  | CPP-RFI-68-64-12-0101
T-00254-5086 | PS5-60-IE-0003A-CC15 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5093 | PS5-60-IE-0003A-CC25 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5094 | PS5-60-IE-0003A-CC26 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-02 - Power Gen Package A (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5095 | PS5-60-IE-0003B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5096 | PS5-60-IE-0003B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5097 | PS5-60-IE-0003B-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5104 | PS5-60-IE-0003B-CC10 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | Closed |  | CPP-RFI-68-64-12-0101
T-00254-5105 | PS5-60-IE-0003B-CC11 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | Closed |  | CPP-RFI-68-64-12-0101
T-00254-5106 | PS5-60-IE-0003B-CC15 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5113 | PS5-60-IE-0003B-CC25 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5114 | PS5-60-IE-0003B-CC26 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-05 - Power Gen Package B (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5133 | PS5-60-IE-0003C-CC25 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5134 | PS5-60-IE-0003C-CC26 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-08 - Power Gen Package C (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5153 | PS5-60-IE-0003D-CC25 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5154 | PS5-60-IE-0003D-CC26 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-11 - Power Gen Package D (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5160 | PS5-60-IE-0003E-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5173 | PS5-60-IE-0003E-CC25 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5174 | PS5-60-IE-0003E-CC26 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-14 - Power Gen Package E (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5193 | PS5-60-IE-0003F-CC25 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5194 | PS5-60-IE-0003F-CC26 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-17 - Power Gen Package F (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5213 | PS5-60-IE-0003G-CC25 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5214 | PS5-60-IE-0003G-CC26 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-20 - Power Gen Package G (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5225 | PS5-60-IN-0001A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5227 | PS5-60-IN-0001A-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5228 | PS5-60-IN-0001A-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5229 | PS5-60-IN-0001B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5231 | PS5-60-IN-0001B-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5232 | PS5-60-IN-0001B-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5233 | PS5-60-IN-0001C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5234 | PS5-60-IN-0001C-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5235 | PS5-60-IN-0001C-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5236 | PS5-60-IN-0001C-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5237 | PS5-60-IN-0001D-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5238 | PS5-60-IN-0001D-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5239 | PS5-60-IN-0001D-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5240 | PS5-60-IN-0001D-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5241 | PS5-60-IN-0001E-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5242 | PS5-60-IN-0001E-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5243 | PS5-60-IN-0001E-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5244 | PS5-60-IN-0001E-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5245 | PS5-60-IN-0001F-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5246 | PS5-60-IN-0001F-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5247 | PS5-60-IN-0001F-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5248 | PS5-60-IN-0001F-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5249 | PS5-60-IN-0001G-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5250 | PS5-60-IN-0001G-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5251 | PS5-60-IN-0001G-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5252 | PS5-60-IN-0001G-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | Closed | CPP-RFI-68-64-04-0071 | CPP-RFI-68-64-12-0074 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5253 | PS5-60-IN-0002A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | Closed |  | CPP-RFI-68-64-12-0099
T-00254-5254 | PS5-60-IN-0002A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | Closed |  | CPP-RFI-68-64-12-0101
T-00254-5256 | PS5-60-IN-0002A-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5257 | PS5-60-IN-0002A-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5258 | PS5-60-IN-0002A-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5259 | PS5-60-IN-0002B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5260 | PS5-60-IN-0002B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | Closed |  | CPP-RFI-68-64-12-0101
T-00254-5262 | PS5-60-IN-0002B-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5264 | PS5-60-IN-0002B-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5265 | PS5-60-IN-0002C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5268 | PS5-60-IN-0002C-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5270 | PS5-60-IN-0002C-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5271 | PS5-60-IN-0002D-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5274 | PS5-60-IN-0002D-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5276 | PS5-60-IN-0002D-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5277 | PS5-60-IN-0002E-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5280 | PS5-60-IN-0002E-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5282 | PS5-60-IN-0002E-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5283 | PS5-60-IN-0002F-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5286 | PS5-60-IN-0002F-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5288 | PS5-60-IN-0002F-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5289 | PS5-60-IN-0002G-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5292 | PS5-60-IN-0002G-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5294 | PS5-60-IN-0002G-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5296 | PS5-60-LA-0002A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | Closed |  | CPP-RFI-68-64-12-0099
T-00254-5297 | PS5-60-LA-0002A-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | Closed |  | CPP-RFI-68-64-12-0099
T-00254-5298 | PS5-60-LA-0002A-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | Closed |  | CPP-RFI-68-64-12-0099
T-00254-5299 | PS5-60-LA-0002A-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | Closed |  | CPP-RFI-68-64-12-0099
T-00254-5300 | PS5-60-LA-0002A-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | Closed |  | CPP-RFI-68-64-12-0099
T-00254-5301 | PS5-60-LA-0002A-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | Closed |  | CPP-RFI-68-64-12-0099
T-00254-5302 | PS5-60-LA-0002A-CC07 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | Closed |  | CPP-RFI-68-64-12-0101
T-00254-5303 | PS5-60-LA-0002A-CC08 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | Closed |  | CPP-RFI-68-64-12-0101
T-00254-5304 | PS5-60-LA-0002A-CC09 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | Closed |  | CPP-RFI-68-64-12-0101
T-00254-5305 | PS5-60-LA-0002B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-64-12-0101
T-00254-5306 | PS5-60-LA-0002B-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-64-12-0101
T-00254-5307 | PS5-60-LA-0002B-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | Closed |  | CPP-RFI-68-64-12-0101
T-00254-5311 | PS5-60-LA-0002C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5312 | PS5-60-LA-0002C-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5313 | PS5-60-LA-0002C-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5315 | PS5-60-LA-0002C-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5316 | PS5-60-LA-0002C-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5318 | PS5-60-LIT-4301-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-24 - Cooling Water Tank & Pump | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5319 | PS5-60-LIT-4401-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5328 | PS5-60-SEA-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5330 | PS5-60-SEA-0001-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5331 | PS5-60-SEA-0001-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5332 | PS5-60-SEA-0001-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5333 | PS5-60-SEA-0001-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5334 | PS5-60-SEA-0001-CC07 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5335 | PS5-60-SEA-0001-CC10 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5336 | PS5-60-SEA-0001-CC11 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0082
T-00254-5337 | PS5-60-SEA-0001-CC12 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0082
T-00254-5339 | PS5-60-SEA-0001-CC14 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5340 | PS5-60-SEA-0001-CC15 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5341 | PS5-60-SEA-0001-CC16 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5342 | PS5-60-SEA-0001-CC17 | TJX10 - Multi/Single-core instrument control cable | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5349 | PS5-60-SY-0012-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-33 - Air Receiver F & Air Regulator F | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5350 | PS5-60-SY-0013-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-34 - Air Receiver G & Air Regulator G | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5351 | PS5-60-VS-9101A-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5352 | PS5-60-VS-9101B-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5353 | PS5-60-VS-9101C-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5354 | PS5-60-VS-9101D-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5355 | PS5-60-VS-9101E-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5356 | PS5-60-VS-9101F-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5357 | PS5-60-VS-9101G-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5358 | PS5-61-BI-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (120 MTR) Cable tray not yet installed [OPEN]
T-00254-5359 | PS5-61-BI-0001-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-01 - Power Generation Package A | Closed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (180 MTR) Cable tray not yet installed [OPEN]
T-00254-5361 | PS5-61-BI-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN]
T-00254-5362 | PS5-61-BI-0002-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-04 - Power Generation Package B | Closed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed [OPEN] | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (180 MTR) Cable tray not yet installed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side [OPEN]
T-00254-5364 | PS5-61-BI-0003-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (100 MTR) Cable tray not yet installed [OPEN]
T-00254-5365 | PS5-61-BI-0003-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-07 - Power Generation Package C | Closed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (100 MTR) Cable tray not yet installed [OPEN]
T-00254-5367 | PS5-61-BI-0004-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (100 MTR) Cable tray not yet installed [OPEN]
T-00254-5368 | PS5-61-BI-0004-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-10 - Power Generation Package D | Closed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (100 MTR) Cable tray not yet installed [OPEN]
T-00254-5370 | PS5-61-BI-0005-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (55 MTR) Cable tray not yet installed [OPEN]
T-00254-5371 | PS5-61-BI-0005-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-13 - Power Generation Package E | Closed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (100 MTR) Cable tray not yet installed [OPEN]
T-00254-5373 | PS5-61-BI-0006-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (50 MTR) Cable tray not yet installed [OPEN]
T-00254-5374 | PS5-61-BI-0006-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-16 - Power Generation Package F | Closed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (55 MTR) Cable tray not yet installed [OPEN]
T-00254-5376 | PS5-61-BI-0007-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (50 MTR) Cable tray not yet installed [OPEN]
T-00254-5377 | PS5-61-BI-0007-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-60-19 - Power Generation Package G | Closed | CPP-RFI-68-64-04-0050 | CPP-RFI-68-64-12-0056 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (55 MTR) Cable tray not yet installed [OPEN]
T-00254-5388 | PS5-71-BAV-0058-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-21 - Diesel Transfer Pump A/B | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5389 | PS5-71-BAV-0059-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5394 | PS5-71-BI-0003-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5400 | PS5-71-BI-0005-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5456 | PS5-71-FIT-0005-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-17 - Diesel Fuel Distribution Header | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5461 | PS5-71-FIT-0019-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-21 - Diesel Transfer Pump A/B | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5463 | PS5-71-FXS-0018-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5464 | PS5-71-FXS-0019-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-21 - Diesel Transfer Pump A/B | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5465 | PS5-71-FXS-0020-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5467 | PS5-71-FY-0019-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-21 - Diesel Transfer Pump A/B | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5468 | PS5-71-FY-0020-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5469 | PS5-71-IN-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-19 - Diesel Separator Module (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5470 | PS5-71-IN-0001-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-19 - Diesel Separator Module (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5471 | PS5-71-IN-0001-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-19 - Diesel Separator Module (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5472 | PS5-71-IN-0001-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-19 - Diesel Separator Module (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5473 | PS5-71-IN-0001-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-19 - Diesel Separator Module (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5474 | PS5-71-IN-0001-CC06 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-19 - Diesel Separator Module (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5475 | PS5-71-IN-0001-CC07 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-19 - Diesel Separator Module (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5479 | PS5-71-IN-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5481 | PS5-71-IN-0002-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5486 | PS5-71-IN-0003-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5487 | PS5-71-IN-0003-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | Closed | CPP-68-64-04-0080 | CPP-68-64-12-0084
T-00254-5495 | PS5-71-IN-0004A-CC03 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | Closed | CPP-68-64-04-0079 | CPP-68-64-12-0083
T-00254-5496 | PS5-71-IN-0004A-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5497 | PS5-71-IN-0004A-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5508 | PS5-71-IN-0004B-CC04 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5509 | PS5-71-IN-0004B-CC05 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | Closed | CPP-68-64-04-0078 | CPP-68-64-12-0082
T-00254-5518 | PS5-71-LIT-1201-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5519 | PS5-71-LIT-1202-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5524 | PS5-71-LIT-4401-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-15 - Diesel Fuel Storage Tank | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5525 | PS5-71-LIT-4402-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-15 - Diesel Fuel Storage Tank | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5526 | PS5-71-LXS-4101-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5528 | PS5-71-MOV-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | Closed |  | CPP-RFI-68-64-12-0099
T-00254-5529 | PS5-71-MOV-0001-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | Closed |  | CPP-RFI-68-64-12-0099
T-00254-5530 | PS5-71-MOV-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | Closed |  | CPP-RFI-68-64-12-0099
T-00254-5531 | PS5-71-MOV-0002-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | Closed |  | CPP-RFI-68-64-12-0099
T-00254-5532 | PS5-71-MOV-0003-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5533 | PS5-71-MOV-0003-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5534 | PS5-71-MOV-0004-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | Closed |  | CPP-RFI-68-64-12-0099
T-00254-5535 | PS5-71-MOV-0004-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | Closed |  | CPP-RFI-68-64-12-0099
T-00254-5536 | PS5-71-MOV-0007-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5537 | PS5-71-MOV-0007-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5538 | PS5-71-MOV-0008-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5539 | PS5-71-MOV-0008-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5540 | PS5-71-MOV-0009-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5541 | PS5-71-MOV-0009-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-08 - CFO Pre-Pressure Modules | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5542 | PS5-71-MOV-0010-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5543 | PS5-71-MOV-0010-CC02 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | Closed |  | CPP-RFI-68-64-04-0100
T-00254-5547 | PS5-71-PIT-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5548 | PS5-71-PIT-0014-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-17 - Diesel Fuel Distribution Header | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5550 | PS5-71-PIT-0019A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-21 - Diesel Transfer Pump A/B | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5552 | PS5-71-PIT-0022-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5553 | PS5-71-PIT-0029-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-15 - Diesel Fuel Storage Tank | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5554 | PS5-71-PIT-0039-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5557 | PS5-71-PIT-0091-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5558 | PS5-71-PIT-0092-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5561 | PS5-71-PIT-3301A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5562 | PS5-71-PIT-3301B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5563 | PS5-71-PIT-3302A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5564 | PS5-71-PIT-3302B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-05 - CFO Transfer Pump A/B | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5565 | PS5-71-PIT-3401A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5566 | PS5-71-PIT-3401B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5567 | PS5-71-PIT-3402A-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5568 | PS5-71-PIT-3402B-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-13 - CFO Service Pump A/B | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5570 | PS5-71-SDV-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | Closed |  | CPP-RFI-68-64-12-0099
T-00254-5574 | PS5-71-SDV-0029-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-15 - Diesel Fuel Storage Tank | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5578 | PS5-71-SXS-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | Closed |  | CPP-RFI-68-64-12-0099
T-00254-5579 | PS5-71-SXS-0022-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5580 | PS5-71-SXS-0029-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-15 - Diesel Fuel Storage Tank | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5581 | PS5-71-SXS-0039-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5582 | PS5-71-SY-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | Closed |  | CPP-RFI-68-64-12-0099
T-00254-5583 | PS5-71-SY-0022-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5584 | PS5-71-SY-0029-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-15 - Diesel Fuel Storage Tank | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5585 | PS5-71-SY-0039-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5588 | PS5-71-TIT-0006-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5589 | PS5-71-TIT-0007-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5592 | PS5-71-TIT-2402AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5593 | PS5-71-TIT-2402BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-01 - CFO Storage Tank Feed Heater | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5604 | PS5-71-XV-0091-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5606 | PS5-71-XV-0092-CC01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5608 | PS5-71-XXS-0089-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5609 | PS5-71-XXS-0090-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5610 | PS5-71-XXS-0091-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5611 | PS5-71-XXS-0092-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5612 | PS5-71-XY-0089-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-04 - CFO Storage Tank | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5613 | PS5-71-XY-0090-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-12 - CFO Service Tank | Closed | CPP-RFI-68-64-04-0052 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED]
T-00254-5614 | PS5-71-XY-0091-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-18 - Diesel Separator Module | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5615 | PS5-71-XY-0092-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-71-20 - Diesel Fuel Day Tank | Closed | CPP-RFI-68-64-04-0072 | CPP-RFI-68-64-12-0075
T-00254-5618 | PS5-74-PIT-0002-CJ01 | TJX10 - Multi/Single-core instrument control cable | I | PS5-74-04 - Nitrogen Distribution Header | Closed | CPP-RFI-68-64-04-0060 | CPP-RFI-68-64-12-0061 |  |  | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00604-0256 | PS5-61-IK-0001-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED] ¦ TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side [OPEN]
T-00604-0257 | PS5-61-IK-0001-CL02 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED] ¦ TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side [OPEN]
T-00604-0258 | PS5-61-IK-0001-CL03 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED] ¦ TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side [OPEN]
T-00604-0259 | PS5-61-IK-0001-CL04 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED] ¦ TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side [OPEN]
T-00604-0260 | PS5-61-IK-0001-CL05 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED] ¦ TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side [OPEN]
T-00604-0261 | PS5-61-IK-0001-CL06 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED] ¦ TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side [OPEN]
T-00604-0262 | PS5-61-IK-0001-CL07 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED] ¦ TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side [OPEN]
T-00604-0263 | PS5-61-IK-0001-CL08 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED] ¦ TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side [OPEN]
T-00604-0264 | PS5-61-IK-0001-CL09 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 |  |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED] ¦ TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side [OPEN]
T-00604-0265 | PS5-61-IK-0001-CL10 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED]
T-00604-0266 | PS5-61-IK-0001-CL11 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED]
T-00604-0267 | PS5-61-IK-0001-CL12 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED]
T-00604-0268 | PS5-61-IK-0001-CL13 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED]
T-00604-0269 | PS5-61-IK-0001-CL14 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED]
T-00604-0270 | PS5-61-IK-0001-CL15 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED]
T-00604-0271 | PS5-61-IK-0001-CL16 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED]
T-00604-0272 | PS5-61-IK-0001-CL17 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED] ¦ TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side [OPEN]
T-00604-0273 | PS5-61-IK-0001-CL18 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0223 | CPP-RFI-68-33/1-07-0257 |  |  | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends [OPEN] ¦ TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends [CLOSED] ¦ TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side [OPEN]
T-00604-0274 | PS5-61-IK-0001-CL19 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00604-0275 | PS5-61-IK-0001-CL20 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00604-0276 | PS5-61-IK-0001-CL21 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00604-0277 | PS5-61-IK-0001-CL22 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00604-0278 | PS5-61-IK-0001-CL23 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00604-0279 | PS5-61-IK-0001-CL24 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00604-0280 | PS5-61-IK-0001-CL25 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00604-0281 | PS5-61-IK-0001-CL26 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00604-0282 | PS5-61-IK-0001-CL27 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00604-0283 | PS5-61-IK-0001-CL28 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00604-0284 | PS5-61-IK-0001-CL29 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00604-0285 | PS5-61-IK-0001-CL30 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0250 | CPP-RFI-68-331-07-0251 |  | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00604-0286 | PS5-61-IK-0001-CL31 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112-SS Tag on both ends not installed [CLOSED]
T-00604-0287 | PS5-61-IK-0001-CL32 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112-SS Tag on both ends not installed [CLOSED]
T-00604-0288 | PS5-61-IK-0001-CL33 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0240 | CPP-RFI-68-331-07-0255 |  | TZ-MID-68-WPR2-151112 Cable trench installation to be complete [OPEN] ¦ TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both side [OPEN]
T-00604-0289 | PS5-61-IK-0001-CL34 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0240 | CPP-RFI-68-331-07-0255 |  | TZ-MID-68-WPR2-151112 Cable trench installation to be complete [OPEN] ¦ TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both side [OPEN]
T-00604-0290 | PS5-61-IK-0001-CL35 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151112 Cable ladder/tray not yet install at trafo side (PS5-61-IV-0001B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, and backfilled. ( PS5-88-CU-LV-0022). [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00604-0291 | PS5-61-IK-0001-CL36 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0264 | CPP-RFI-68-331-07-0268 |  | TZ-MID-68-WPR2-151112 Cable ladder/tray not yet install at trafo side (PS5-61-IV-0001B) [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, and backfilled. ( PS5-88-CU-LV-0022). [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install at both side [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable dressing to be done both side [OPEN]
T-00604-0292 | PS5-61-IK-0001-CL44 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0266 | CPP-RFI-68-331-07-0267 |  | TZ-MID-68-WPR2-151112 Cable trench backfilled to be complete PS5-88-CU-LV-0021 [OPEN] | TZ-MID-68-WPR2-151112 Permanent SS cable tags to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Cable need to be dressing completely at both side [OPEN]
T-00604-0293 | PS5-61-IK-0001-CL45 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0240 | CPP-RFI-68-331-07-0255 |  | TZ-MID-68-WPR2-151112 Cable trench installation to be complete [OPEN] ¦ TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both side [OPEN]
T-00604-0300 | PS5-61-IV-0001A-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  |  | Doc. TZ-MID-68-WPR2-151112 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151112 - Cable Dressing at Both Side [OPEN]
T-00604-0301 | PS5-61-IV-0001B-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0228 | CPP-RFI-68-33/1-07-0265 |  |  | Doc. TZ-MID-68-WPR2-151112 - Installation of SS Cable Tag at Both Ends of Cable [CLOSED] ¦ Doc. TZ-MID-68-WPR2-151112 - Cable Dressing at Both Side [OPEN]
T-00606-0073 | PS5-61-IJ-0001-CD33 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0240 | CPP-RFI-68-331-07-0255 |  | TZ-MID-68-WPR2-151112 Cable trench installation to be complete [OPEN] ¦ TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install [OPEN] | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side [OPEN] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both side [OPEN]
T-00606-0074 | PS5-61-IJ-0001-CD34 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | Closed | CPP-RFI-68-331-05-0243 | CPP-RFI-68-331-07-0256 |  | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done [OPEN] ¦ TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IV-0001B) [OPEN] | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side [CLOSED] ¦ TZ-MID-68-WPR2-151112 Dressing to be done at both end [OPEN]
T-00606-0076 | PS5-61-IJ-0001-CD36 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112-SS Tag on both ends not installed [CLOSED]
T-00606-0081 | PS5-61-IJ-0001-CD41 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0271 |  |  | TZ-MID-68-WPR2-151112-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112-SS Tag on both ends not installed [CLOSED]
T-00610-0191 | PS5-25-IES-3200A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0287 | CPP-RFI-68-33/1-06-0360 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151114 Cable gland earting not yet installed [OPEN] ¦ TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly [OPEN]
T-00610-0192 | PS5-25-IES-3200B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0287 | CPP-RFI-68-33/1-06-0360 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151114 Cable gland earting not yet installed [OPEN] ¦ TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly [OPEN]
T-00610-0193 | PS5-25-IES-3300A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0287 | CPP-RFI-68-33/1-06-0360 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151114 Cable gland earting not yet installed [OPEN] ¦ TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly [OPEN]
T-00610-0194 | PS5-25-IES-3300B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0287 | CPP-RFI-68-33/1-06-0360 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151114 Cable gland earting not yet installed [OPEN] ¦ TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly [OPEN]
T-00610-0195 | PS5-25-IES-3400A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0287 | CPP-RFI-68-33/1-06-0360 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151114 Cable gland earting not yet installed [OPEN] ¦ TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly [OPEN]
T-00610-0196 | PS5-25-IES-3400B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0287 | CPP-RFI-68-33/1-06-0360 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151114 Cable gland earting not yet installed [OPEN] ¦ TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly [OPEN]
T-00610-0197 | PS5-25-IES-6400A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0287 | CPP-RFI-68-33/1-06-0360 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151114 Cable gland earting not yet installed [OPEN] ¦ TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly [OPEN]
T-00610-0198 | PS5-25-IES-6400B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-02 - Crude Oil Export Pump A | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0287 | CPP-RFI-68-33/1-06-0360 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151114 Cable gland earting not yet installed [OPEN] ¦ TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly [OPEN]
T-00610-0199 | PS5-25-IES-6500A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 | CPP-RFI-68-33/1-06-0360 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151114 Cable gland earting not yet installed [OPEN] ¦ TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly [OPEN]
T-00610-0200 | PS5-25-IES-6500B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-03 - Crude Oil Export Pump B | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 | CPP-RFI-68-33/1-06-0360 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151114 Cable gland earting not yet installed [OPEN] ¦ TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly [OPEN]
T-00610-0201 | PS5-25-IES-6600A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 | CPP-RFI-68-33/1-06-0360 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151114 Cable gland earting not yet installed [OPEN] ¦ TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly [OPEN]
T-00610-0202 | PS5-25-IES-6600B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-25-04 - Crude Oil Export Pump C | Closed | CPP-RFI-68-331-05-0215 | CPP-RFI-68-331-07-0291 | CPP-RFI-68-33/1-06-0360 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151114 Cable gland earting not yet installed [OPEN] ¦ TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly [OPEN]
T-00610-0216 | PS5-28-IES-3900A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-28-17 - Reinjection Pump | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 | CPP-RFI-68-331-06-0379 |  | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-150101 Cable gland earting not yet installed [OPEN]
T-00610-0218 | PS5-53-IES-3100A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-53-02 - Water Distribution Pump A/B | Closed | CPP-RFI-68-33/1-07-0220 |  | CPP-RFI-68-331-06-0379 |  | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-150101 Cable gland earting not yet installed [OPEN]
T-00610-0219 | PS5-53-IES-3100B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-53-02 - Water Distribution Pump A/B | Closed | CPP-RFI-68-33/1-07-0220 |  | CPP-RFI-68-331-06-0379 |  | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-150101 Cable gland earting not yet installed [OPEN]
T-00610-0277 | PS5-71-IES-3100A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-71-16 - Diesel Fuel Supply Pump A/B | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 | CPP-RFI-68-331-06-0379 |  | TZ-MID-68-WPR2-151112,151111,151108.151107-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151108.151107-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-150101 Cable gland earting not yet installed [OPEN]
T-00610-0278 | PS5-71-IES-3100B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-71-16 - Diesel Fuel Supply Pump A/B | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 | CPP-RFI-68-331-06-0379 |  | TZ-MID-68-WPR2-151112,151111,151108.151107-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151108.151107-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-150101 Cable gland earting not yet installed [OPEN]
T-00610-0279 | PS5-71-IES-3200-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 | CPP-RFI-68-331-06-0379 |  | TZ-MID-68-WPR2-151112,151111,151108,151107-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151108,151107-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-150101 Cable gland earting not yet installed [OPEN]
T-00610-0280 | PS5-71-IES-3300A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-71-05 - CFO Transfer Pump A/B | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 | CPP-RFI-68-331-06-0379 |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-150101 Cable gland earting not yet installed [OPEN]
T-00610-0281 | PS5-71-IES-3300B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-71-05 - CFO Transfer Pump A/B | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 | CPP-RFI-68-331-06-0379 |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-150101 Cable gland earting not yet installed [OPEN]
T-00610-0282 | PS5-71-IES-3400A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-71-13 - CFO Service Pump A/B | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 | CPP-RFI-68-331-06-0379 |  | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-150101 Cable gland earting not yet installed [OPEN]
T-00610-0284 | PS5-71-IES-3500A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-71-21 - Diesel Transfer Pump A/B | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 | CPP-RFI-68-331-06-0379 |  | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-150101 Cable gland earting not yet installed [OPEN]
T-00610-0285 | PS5-71-IES-3500B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | E | PS5-71-21 - Diesel Transfer Pump A/B | Closed | CPP-RFI-68-33/1-05-0211 | CPP-RFI-68-33/1-07-0290 | CPP-RFI-68-331-06-0379 |  | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely [OPEN] ¦ TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed [CLOSED] ¦ TZ-MID-68-WPR2-150101 Cable gland earting not yet installed [OPEN]
T-00614-0884 | PS5-03-BI-1509-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0036/ CPP-RFI-68-64-11-0067 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-0892 | PS5-03-BI-2502-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-06 - FZ-06 - Transformer Area | Closed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0055 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed [OPEN]
T-00614-0893 | PS5-03-BI-2503-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed [OPEN]
T-00614-0901 | PS5-03-BI-2511-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-03-01 - FZ-01 - Process Area | Closed | CPP-RFI-68-64-04-0035/ CPP-RFI-68-64-11-0067 | CPP-RFI-68-64-12-0073 |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [OPEN]
T-00614-0955 | PS5-25-BI-1103-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed [OPEN]
T-00614-0956 | PS5-25-BI-1104-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0045 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0986 | PS5-25-BI-2108-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-0987 | PS5-25-BI-2109-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-04-0041 | CPP-RFI-68-64-12-0046 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-0994 | PS5-25-BI-2308-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-04-0041 | CPP-RFI-68-64-12-0048 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-0996 | PS5-25-BI-2312-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-04-0041 | CPP-RFI-68-64-12-0048 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-0997 | PS5-25-BI-2315-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-04-0041 | CPP-RFI-68-64-12-0048 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end [OPEN]
T-00614-0998 | PS5-25-BI-2316-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0048 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1031 | PS5-53-BI-1304-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-53-01 - Utility Water / Storage Tank | Closed |  | CPP-RFI-68-64-12-0073 | CPP-RFI-68-64-11-0068 |  |  | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed [OPEN]
T-00614-1079 | PS5-71-BI-1110-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0048 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1083 | PS5-71-BI-1116-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0048 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1085 | PS5-71-BI-2101-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | Closed |  |  |  |  | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED]
T-00614-1087 | PS5-71-BI-1306-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-04-0036 | CPP-RFI-68-64-12-0048 |  |  | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN]
T-00614-1106 | PS5-71-BI-2314-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-91-01 - Multicore cables & JB | Closed | CPP-RFI-68-64-04-0035 | CPP-RFI-68-64-12-0045 |  | UT-MID-60-WPR2-160101 Black Heat shrink sleeves not installed properly [OPEN] | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely [OPEN] ¦ Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed [OPEN]
T-00614-1107 | PS5-71-BI-2317-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | I | PS5-71-15 - Diesel Fuel Storage Tank | Closed | CPP-RFI-68-64-04-0054 | CPP-RFI-68-64-12-0063 |  |  | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side [CLOSED] ¦ Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed [OPEN] | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed [OPEN]
T-00621-2831 | PS5-08-01BT-1902-CR02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | Closed | CPP-RFI-68-65-05-0036 | CPP-RFI-68-65-20-0035 |  |  | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-171100, Cable Need to Be Dressing at Both Ends [OPEN]
T-00621-2832 | PS5-08-01BT-1903-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | Closed | CPP-RFI-68-65-05-0036 | CPP-RFI-68-65-20-0035 |  |  | Doc. TZ-MID-68-WPR2-171127, TZ-MID-68-WPR2-171100 - Cable Need to be Dressing at Both Ends [OPEN]
T-00621-2833 | PS5-08-01BT-1904-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | Closed | CPP-RFI-68-65-05-0036 | CPP-RFI-68-65-20-0035 |  |  | Doc. TZ-MID-68-WPR2-171127, TZ-MID-68-WPR2-171100 - Cable Need to be Dressing at Both Ends [OPEN]
T-00621-2834 | PS5-08-01LS-0101-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | Closed | CPP-RFI-68-65-05-0036 | CPP-RFI-68-65-20-0035 |  |  | Doc. TZ-MID-68-WPR2-171120 - Cable Need to be Dressing at Both Ends [OPEN]
T-00621-2845 | PS5-08-01LS-0201-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | Closed | CPP-RFI-68-65-05-0036 | CPP-RFI-68-65-20-0035 |  |  | Doc. TZ-MID-68-WPR2-171120 - Cable Need to be Dressing at Both Ends [OPEN]
T-00621-2869 | PS5-08-01LS-0401-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | Closed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  |  | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2870 | PS5-08-01LS-0402-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | Closed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  |  | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-2873 | PS5-08-01LS-0405-CR01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | Closed | CPP-RFI-68-65-05-0024 | CPP-RFI-68-65-20-0031 |  |  | TZ-MID-68-WPR2-171173 Cable Dressing at Both End [OPEN]
T-00621-3008 | PS5-08-01MP-0001-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | Closed | CPP-RFI-68-65-05-0036 |  |  |  | Doc. TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-171100 - Cable Need to be Dressing at Both Ends [OPEN]
T-00621-3009 | PS5-08-01MP-0001-CC02 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | Closed | CPP-RFI-68-65-05-0036 |  |  |  | Doc. TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-171120, Cable Need to be Dressing at Both Ends [OPEN]
T-00621-3010 | PS5-08-01MP-0001-CC03 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | Closed | CPP-RFI-68-65-05-0036 |  |  |  | Doc. TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-171100 - Cable Need to be Dressing at Both Ends [OPEN]
T-00621-3011 | PS5-08-01MP-0001-CC04 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-01 - PAGA | Closed | CPP-RFI-68-65-05-0036 |  |  |  | Doc. TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-171120, Cable Need to be Dressing at Both Ends [OPEN]
T-00621-3024 | PS5-08-03TP-0001-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | Closed | CPP-RFI-68-65-05-0036 |  |  |  | Doc. TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-171100 - Cable Need to be Dressing at Both Ends [OPEN] ¦ Doc. TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-171100 - Cable Need to Install Cable Tagging at EITS Sisde [OPEN]
T-00621-3036 | PS5-08-03TP-0103-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-03 - Telephone | Closed | CPP-RFI-68-65-05-0029
T-00621-3042 | PS5-08-05IN-0001-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3043 | PS5-08-05IN-0002-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3044 | PS5-08-05IN-0003-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3045 | PS5-08-05IN-0004-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3046 | PS5-08-05IN-0005-CA01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3298 | PS5-08-85BR-0001-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) [OPEN] | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3299 | PS5-08-85BR-0002-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) [OPEN] | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3300 | PS5-08-85BR-0003-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) [OPEN] | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3301 | PS5-08-85BR-0004-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) [OPEN] | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3302 | PS5-08-85BR-0005-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) [OPEN] | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3303 | PS5-08-85BR-0006-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) [OPEN] | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3304 | PS5-08-85BR-0007-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) [OPEN] | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3305 | PS5-08-85BR-0008-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) [OPEN] | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3326 | PS5-08-85BT-0002-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN] ¦ Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, as per details Installation, Vertikal Cable Tray Need to Install (ACS JB - Field Side), {refer to details ACS EQUIPMENT INSTALLATION DETAILS - UT-MID-60-WPR2-171204} [OPEN]
T-00621-3327 | PS5-08-85BT-0003-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN] ¦ Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, as per details Installation, Vertikal Cable Tray Need to Install (ACS JB - Field Side), {refer to details ACS EQUIPMENT INSTALLATION DETAILS - UT-MID-60-WPR2-171204} [OPEN]
T-00621-3341 | PS5-08-85BT-0017-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) [OPEN] | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3342 | PS5-08-85BT-0017-CN01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN] ¦ Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, as per details Installation, Vertikal Cable Tray Need to Install (ACS JB - Field Side), {refer to details ACS EQUIPMENT INSTALLATION DETAILS - UT-MID-60-WPR2-171204} [OPEN]
T-00621-3344 | PS5-08-85BT-0019-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) [OPEN] | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3345 | PS5-08-85BT-0020-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) [OPEN] | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3346 | PS5-08-85BT-0021-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) [OPEN] | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3347 | PS5-08-85BT-0022-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) [OPEN] | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3348 | PS5-08-85BT-0023-CC01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) [OPEN] | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN]
T-00621-3349 | PS5-08-85BT-0024-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN] ¦ Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, as per details Installation, Vertikal Cable Tray Need to Install (ACS JB - Field Side), {refer to details ACS EQUIPMENT INSTALLATION DETAILS - UT-MID-60-WPR2-171204} [OPEN]
T-00621-3350 | PS5-08-85BT-0025-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN] ¦ Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, as per details Installation, Vertikal Cable Tray Need to Install (ACS JB - Field Side), {refer to details ACS EQUIPMENT INSTALLATION DETAILS - UT-MID-60-WPR2-171204} [OPEN]
T-00621-3351 | PS5-08-85BT-0026-CJ01 | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | T | PS5-08-85 - Access Control, POB & e-Mustering | Closed | CPP-RFI-68-65-05-0032 | CPP-RFI-68-65-20-0033 |  |  | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done [OPEN] ¦ Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, as per details Installation, Vertikal Cable Tray Need to Install (ACS JB - Field Side), {refer to details ACS EQUIPMENT INSTALLATION DETAILS - UT-MID-60-WPR2-171204} [OPEN]