## MP Register
EACOP PIPELINE PROJECT
[5 empty] | EIT MASTER PUNCHLIST ITEM REGISTER - PS5 | [18 empty] | 3906 | 4016
[5 empty] | Date: | 2026-10-07 | [10 empty] | Report Date: 10-07-2026 | [6 empty] | CLOSE | 966
MPL No. | PL ID | CHECK_VLOOKUP | RFI Number | CPP SCOPE | Subsystem No/Description | Area | TAG No. | Punch Description | Cat. | Discipline Code | Raised By |  |  | Action By | Cleared and Signed Off by |  |  |  | Remarks | Status
[7 empty] | [Test Pack] |  | [A/B/C/0] |  | Contractor /Company | Name | Date |  | Contractor |  | Company
[10 empty] | [A ~ Z] |  |  |  |  | Name | Date | Name | Date
1 | PL-PS5-00001 | #N/A | CPP-RFI-68-33/1-03-0148 | PS5 | Electrical Cable Ladder/Tray Installation | From utility /Fire Water tank area to Diesel Fuel Storage | N/A | Doc. TZ-MID-68-WPR2-151107,TZ-MID-68-WPR2-151108,TZ-MID-68-WPR2-1511079 - Earth jumper not installed completely | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-01-31 | CPP EIT | Gao Chong |  |  |  |  | Open
2 | PL-PS5-00002 | #N/A | CPP-RFI-68-33/1-03-0148 | PS5 | Electrical Cable Ladder/Tray Installation | From utility /Fire Water tank area to Diesel Fuel Storage | N/A | Doc. TZ-MID-68-WPR2-151107,TZ-MID-68-WPR2-151108,TZ-MID-68-WPR2-1511079- Hold down Clamp not Installed yet | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-01-31 | CPP EIT | Gao Chong |  |  |  |  | Open
3 | PL-PS5-00003 | #N/A | CPP-RFI-68-33/1-03-0148 | PS5 | Electrical Cable Ladder/Tray Installation | From utility /Fire Water tank area to Diesel Fuel Storage | N/A | Doc. TZ-MID-68-WPR2-151107,TZ-MID-68-WPR2-151108,TZ-MID-68-WPR2-1511079 - Cover not installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-01-31 | CPP EIT | Gao Chong |  |  |  |  | Open
4 | PL-PS5-00004 | #N/A | CPP-RFI-68-33/1-03-0148 | PS5 | Electrical Cable Ladder/Tray Installation | From utility /Fire Water tank area to Diesel Fuel Storage | N/A | Doc. TZ-MID-68-WPR2-151107,TZ-MID-68-WPR2-151108,TZ-MID-68-WPR2-1511079 - Cover not installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-01-31 | CPP EIT | Gao Chong |  |  |  |  | Open
5 | PL-PS5-00005 | #N/A | CPP-RFI-68-64-03-0020 | PS5 | Instrument Cable Ladder/Tray Installation | From utility /Fire Water tank area to Diesel Fuel Storage | N/A | Doc.TZ-MID-68-WPR2-161500 - Earth jumper not installed completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-02-09 | CPP EIT | Gao Chong |  |  |  |  | Open
6 | PL-PS5-00006 | #N/A | CPP-RFI-68-64-03-0020 | PS5 | Instrument Cable Ladder/Tray Installation | From utility /Fire Water tank area to Diesel Fuel Storage | N/A | Doc.TZ-MID-68-WPR2-161500 - Hold down Clamp not Installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-02-09 | CPP EIT | Gao Chong |  |  |  |  | Open
7 | PL-PS5-00007 | #N/A | CPP-RFI-68-64-03-0020 | PS5 | Instrument Cable Ladder/Tray Installation | From utility /Fire Water tank area to Diesel Fuel Storage | N/A | Doc.TZ-MID-68-WPR2-161500 - Cover not installed | C | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-02-09 | CPP EIT | Gao Chong |  |  |  |  | Open
8 | PL-PS5-00008 | #N/A | CPP-RFI-68-64-03-0020 | PS5 | Instrument Cable Ladder/Tray Installation | From utility /Fire Water tank area to Diesel Fuel Storage | N/A | Doc.TZ-MID-68-WPR2-161500 - Corrosion need to be removed | C | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-02-09 | CPP EIT | Gao Chong |  |  |  |  | Open
9 | PL-PS5-00009 | #N/A | CPP-RFI-68-65-02-0016 | PS5 | Telecom Cable Ladder/Tray Installation | From utility /Fire Water tank area to Diesel Fuel Storage | N/A | Doc.TZ-MID-68-WPR2-171143 - Earth jumper not installed completely | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-02-09 | CPP EIT | Gao Chong |  |  |  |  | Open
10 | PL-PS5-00010 | #N/A | CPP-RFI-68-65-02-0016 | PS5 | Telecom Cable Ladder/Tray Installation | From utility /Fire Water tank area to Diesel Fuel Storage | N/A | Doc.TZ-MID-68-WPR2-171143- Hold down Clamp not Installed | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-02-09 | CPP EIT | Gao Chong |  |  |  |  | Open
11 | PL-PS5-00011 | #N/A | CPP-RFI-68-65-02-0016 | PS5 | Telecom Cable Ladder/Tray Installation | From utility /Fire Water tank area to Diesel Fuel Storage | N/A | Doc.TZ-MID-68-WPR2-171143 - Cover not installed | C | Telecom | CPY | Konstantin Ovchinnikov | 2026-02-09 | CPP EIT | Gao Chong |  |  |  |  | Open
12 | PL-PS5-00012 | #N/A | CPP-RFI-68-65-02-0016 | PS5 | Telecom Cable Ladder/Tray Installation | From utility /Fire Water tank area to Diesel Fuel Storage | N/A | Doc.TZ-MID-68-WPR2-171143 - Corrosion need to be removed | C | Telecom | CPY | Konstantin Ovchinnikov | 2026-02-09 | CPP EIT | Gao Chong |  |  |  |  | Open
13 | PL-PS5-00013 | #N/A | CPP-RFI-68-64-03-0023 | PS5 | Instrument Cable Ladder/Tray Installation | From utility /Fire Water tank area to Diesel Fuel Storage | N/A | Doc.TZ-MID-68-WPR2-161500 - Earth jumper not installed completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-02-21 | CPP EIT | Gao Chong |  |  |  |  | Open
14 | PL-PS5-00014 | #N/A | CPP-RFI-68-64-03-0023 | PS5 | Instrument Cable Ladder/Tray Installation | From utility /Fire Water tank area to Diesel Fuel Storage | N/A | Doc.TZ-MID-68-WPR2-161500 - Hold down Clamp not Installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-02-21 | CPP EIT | Gao Chong |  |  |  |  | Open
15 | PL-PS5-00015 | #N/A | CPP-RFI-68-64-03-0023 | PS5 | Instrument Cable Ladder/Tray Installation | From utility /Fire Water tank area to Diesel Fuel Storage | N/A | Doc.TZ-MID-68-WPR2-161500 - Cover not installed | C | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-02-21 | CPP EIT | Gao Chong |  |  |  |  | Open
16 | PL-PS5-00016 | #N/A | CPP-RFI-68-64-03-0023 | PS5 | Instrument Cable Ladder/Tray Installation | From utility /Fire Water tank area to Diesel Fuel Storage | N/A | Doc.TZ-MID-68-WPR2-161500 - Corrosion need to be removed | C | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-02-21 | CPP EIT | Gao Chong |  |  |  |  | Open
17 | PL-PS5-00017 | #N/A | CPP-RFI-68-33/1-05-0161 | PS5 | Electrical Cable Installation | From Power Generator Building Area to Power Distribution Area (Transformers) | N/A | Doc TZ-MID-68-WPR2-151112, TZ-MID-68-WPR2-151116 - Sand Bedding not done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-02-22 | CPP EIT | Gao Chong |  |  |  |  | Open
18 | PL-PS5-00018 | #N/A | CPP-RFI-68-33/1-05-0161 | PS5 | Electrical Cable Installation | From Power Generator Building Area to Power Distribution Area (Transformers) | N/A | Doc TZ-MID-68-WPR2-151112, TZ-MID-68-WPR2-151116 -Cable Route Marker not Installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-02-22 | CPP EIT | Gao Chong |  |  |  |  | Open
19 | PL-PS5-00019 | #N/A | CPP-RFI-68-33/2-10-0166 | PS5 | Busbar Installation | Power Distribution Area & Generator Building Area | N/A | Doc TZ-MID-68-WPR2-151148,TZ-MID-68-WPR2-151181 -No Tagging against drawing | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-04 | CPP EIT | Gao Chong |  |  |  |  | Open
20 | PL-PS5-00020 | #N/A | CPP-RFI-68-33/1-05-0168 | PS5 | Electrical Cable Installation | From Power Generator Building Area to Power Distribution Area (Transformers) | N/A | Doc TZ-MID-68-WPR2-151112, TZ-MID-68-WPR2-151116 - SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-06 | CPP EIT | Gao Chong |  |  |  |  | Open
21 | PL-PS5-00021 | #N/A | CPP-RFI-68-64-03-0027 | PS5 | Instrument Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-161500 - Earth jumper not installed completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
22 | PL-PS5-00022 | #N/A | CPP-RFI-68-64-03-0027 | PS5 | Instrument Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-161500 - Hold down Clamp not Installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
23 | PL-PS5-00023 | #N/A | CPP-RFI-68-64-03-0027 | PS5 | Instrument Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-161500 - Cover not installed | C | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
24 | PL-PS5-00024 | #N/A | CPP-RFI-68-64-03-0027 | PS5 | Instrument Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-161500 - Corrosion need to be removed | C | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
25 | PL-PS5-00025 | #N/A | CPP-RFI-68-64-03-0027 | PS5 | Instrument Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-161500 - Grommets for Cable Ladders not installed | C | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
26 | PL-PS5-00026 | #N/A | CPP-RFI-68-64-03-0027 | PS5 | Instrument Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-161500 - Bolts tightening on connection plates to be completed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
27 | PL-PS5-00027 | #N/A | CPP-RFI-68-33/1-03-0173 | PS5 | Electrical Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-151108, TZ-MID-68-WPR2-151111,.TZ-MID-68-WPR2-151114,.TZ-MID-68-WPR2-151115,.TZ-MID-68-WPR2-151117 - Corrosion need to be removed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
28 | PL-PS5-00028 | #N/A | CPP-RFI-68-33/1-03-0173 | PS5 | Electrical Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-151108, TZ-MID-68-WPR2-151111,.TZ-MID-68-WPR2-151114,.TZ-MID-68-WPR2-151115,.TZ-MID-68-WPR2-151117 Bolts tightening on connection plates to be completed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
29 | PL-PS5-00029 | #N/A | CPP-RFI-68-33/1-03-0173 | PS5 | Electrical Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-151108, TZ-MID-68-WPR2-151111,.TZ-MID-68-WPR2-151114,.TZ-MID-68-WPR2-151115,.TZ-MID-68-WPR2-151117- Hold down Clamp not Installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
30 | PL-PS5-00030 | #N/A | CPP-RFI-68-33/1-03-0173 | PS5 | Electrical Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-151108, TZ-MID-68-WPR2-151111,.TZ-MID-68-WPR2-151114,.TZ-MID-68-WPR2-151115,.TZ-MID-68-WPR2-151117 Earth jumper not installed completely | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
31 | PL-PS5-00031 | #N/A | CPP-RFI-68-33/1-03-0173 | PS5 | Electrical Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-151108, TZ-MID-68-WPR2-151111,.TZ-MID-68-WPR2-151114,.TZ-MID-68-WPR2-151115,.TZ-MID-68-WPR2-151117 Grommets not installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
32 | PL-PS5-00032 | #N/A | CPP-RFI-68-33/1-03-0173 | PS5 | Electrical Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-151108, TZ-MID-68-WPR2-151111,.TZ-MID-68-WPR2-151114,.TZ-MID-68-WPR2-151115,.TZ-MID-68-WPR2-151117 Cover not installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
33 | PL-PS5-00033 | #N/A | CPP-RFI-68-65-02-0020 | PS5 | Telecom Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-171143 Corrosion need to be removed | C | Telecom | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
34 | PL-PS5-00034 | #N/A | CPP-RFI-68-65-02-0020 | PS5 | Telecom Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-171143 Bolts tightening on connection plates to be completed | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
35 | PL-PS5-00035 | #N/A | CPP-RFI-68-65-02-0020 | PS5 | Telecom Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-171143 - Hold down Clamp not Installed | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
36 | PL-PS5-00036 | #N/A | CPP-RFI-68-65-02-0020 | PS5 | Telecom Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-171143 - Earth jumper not installed completely | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
37 | PL-PS5-00037 | #N/A | CPP-RFI-68-65-02-0020 | PS5 | Telecom Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-171143 - Grommets not installed | C | Telecom | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
38 | PL-PS5-00038 | #N/A | CPP-RFI-68-65-02-0020 | PS5 | Telecom Cable Ladder/Tray Installation | Utility Area, Export Pump VSD Area, Power Distribution Area, CFO Area, Closed Drain Drum Area, Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-171143 - Cover not installed | C | Telecom | CPY | Konstantin Ovchinnikov | 2026-03-11 | CPP EIT | Gao Chong |  |  |  |  | Open
39 | PL-PS5-00039 | #N/A | CPP-RFI-68-33/1-03-0178 | PS5 | Electrical Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-151114,.TZ-MID-68-WPR2-151117 - Corrosion need to be removed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
40 | PL-PS5-00040 | #N/A | CPP-RFI-68-33/1-03-0178 | PS5 | Electrical Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-151114,TZ-MID-68-WPR2-151117 Bolts tightening on connection plates to be completed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
41 | PL-PS5-00041 | #N/A | CPP-RFI-68-33/1-03-0178 | PS5 | Electrical Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-151114,.TZ-MID-68-WPR2-151117- Hold down Clamp not Installed yet | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
42 | PL-PS5-00042 | #N/A | CPP-RFI-68-33/1-03-0178 | PS5 | Electrical Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-151114,TZ-MID-68-WPR2-151117 Earth jumper not installed completely | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
43 | PL-PS5-00043 | #N/A | CPP-RFI-68-33/1-03-0178 | PS5 | Electrical Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-151114,.TZ-MID-68-WPR2-151117 Grommets not installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
44 | PL-PS5-00044 | #N/A | CPP-RFI-68-33/1-03-0178 | PS5 | Electrical Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-151114,TZ-MID-68-WPR2-151117 Cover not installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
45 | PL-PS5-00045 | #N/A | CPP-RFI-68-64-03-0031 | PS5 | Instrument Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-161500 - Earth jumper not installed completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
46 | PL-PS5-00046 | #N/A | CPP-RFI-68-64-03-0031 | PS5 | Instrument Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-161500 - Hold down Clamp not Installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
47 | PL-PS5-00047 | #N/A | CPP-RFI-68-64-03-0031 | PS5 | Instrument Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-161500 - Cover not installed | C | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
48 | PL-PS5-00048 | #N/A | CPP-RFI-68-64-03-0031 | PS5 | Instrument Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-161500 - Corrosion need to be removed | C | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
49 | PL-PS5-00049 | #N/A | CPP-RFI-68-64-03-0031 | PS5 | Instrument Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-161500 - Grommets for Cable Ladders not installed | C | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
50 | PL-PS5-00050 | #N/A | CPP-RFI-68-64-03-0031 | PS5 | Instrument Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-161500 - Bolts tightening on connection plates to be completed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
51 | PL-PS5-00051 | #N/A | CPP-RFI-68-65-02-0022 | PS5 | Telecom Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-171143 Corrosion need to be removed | C | Telecom | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
52 | PL-PS5-00052 | #N/A | CPP-RFI-68-65-02-0022 | PS5 | Telecom Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-171143 Bolts tightening on connection plates to be completed | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
53 | PL-PS5-00053 | #N/A | CPP-RFI-68-65-02-0022 | PS5 | Telecom Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-171143 - Hold down Clamp not Installed | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
54 | PL-PS5-00054 | #N/A | CPP-RFI-68-65-02-0022 | PS5 | Telecom Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-171143 - Earth jumper not installed completely | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
55 | PL-PS5-00055 | #N/A | CPP-RFI-68-65-02-0022 | PS5 | Telecom Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-171143 - Grommets not installed | C | Telecom | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
56 | PL-PS5-00056 | #N/A | CPP-RFI-68-65-02-0022 | PS5 | Telecom Cable Ladder/Tray Installation | Closed Drain Drum Area and Export Loading Pump Area | N/A | Doc.TZ-MID-68-WPR2-171143 - Cover not installed | C | Telecom | CPY | Konstantin Ovchinnikov | 2026-03-16 | CPP EIT | Gao Chong |  |  |  |  | Open
57 | PL-PS5-00057 | #N/A | CPP-RFI-68-33/1-05-0181 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS) & Export Pump VSD area | N/A | Doc TZ-MID-68-WPR2-151112, TZ-MID-68-WPR2-151116 -Missing support by CPP1 for Cable Tagging / REJECTED RFI | B | Electrical | CPY | Rustam Battalov | 2026-03-21 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
58 | PL-PS5-00058 | #N/A | CPP-RFI-68-33/1-05-0181 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS) & Export Pump VSD area | N/A | Doc TZ-MID-68-WPR2-151112, TZ-MID-68-WPR2-151116 - Cable Route Marker not yet installed / REJECTED RFI | C | Electrical | CPY | Rustam Battalov | 2026-03-21 | CPP EIT | Gao Chong |  |  |  |  | Open
59 | PL-PS5-00059 | #N/A | CPP-RFI-68-33/1-05-0181 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS) & Export Pump VSD area | N/A | Doc TZ-MID-68-WPR2-151112, TZ-MID-68-WPR2-151116 - Dressing & HV Trefoil Cable Clamp not installed / REJECTED RFI | B | Electrical | CPY | Rustam Battalov | 2026-03-21 | CPP EIT | Gao Chong |  |  |  |  | Open
60 | PL-PS5-00060 | #N/A | CPP-RFI-68-33/1-03-0182 | PS5 | Electrical Cable Ladder/Tray Installation | Launcher&Receiver Area, CFO Area and Closed drain drum Area | N/A | Doc.TZ-MID-68-WPR2-151113,TZ-MID-68-WPR2-151115 - Corrosion need to be removed | C | Electrical | CPY | Rustam Battalov | 2026-03-21 | CPP EIT | Gao Chong |  |  |  |  | Open
61 | PL-PS5-00061 | #N/A | CPP-RFI-68-33/1-03-0182 | PS5 | Electrical Cable Ladder/Tray Installation | Launcher&Receiver Area, CFO Area and Closed drain drum Area | N/A | Doc.TZ-MID-68-WPR2-151113,TZ-MID-68-WPR2-151115 - Bolts tightening on connection plates to be completed | B | Electrical | CPY | Rustam Battalov | 2026-03-21 | CPP EIT | Gao Chong |  |  |  |  | Open
62 | PL-PS5-00062 | #N/A | CPP-RFI-68-33/1-03-0182 | PS5 | Electrical Cable Ladder/Tray Installation | Launcher&Receiver Area, CFO Area and Closed drain drum Area | N/A | Doc.TZ-MID-68-WPR2-151113,TZ-MID-68-WPR2-151115- Hold down Clamp not Installed yet | B | Electrical | CPY | Rustam Battalov | 2026-03-21 | CPP EIT | Gao Chong |  |  |  |  | Open
63 | PL-PS5-00063 | #N/A | CPP-RFI-68-33/1-03-0182 | PS5 | Electrical Cable Ladder/Tray Installation | Launcher&Receiver Area, CFO Area and Closed drain drum Area | N/A | Doc.TZ-MID-68-WPR2-151113,TZ-MID-68-WPR2-151115 Earth jumper not installed completely | B | Electrical | CPY | Rustam Battalov | 2026-03-21 | CPP EIT | Gao Chong |  |  |  |  | Open
64 | PL-PS5-00064 | #N/A | CPP-RFI-68-33/1-03-0182 | PS5 | Electrical Cable Ladder/Tray Installation | Launcher&Receiver Area, CFO Area and Closed drain drum Area | N/A | Doc.TZ-MID-68-WPR2-151113,TZ-MID-68-WPR2-151115 Grommets not installed | C | Electrical | CPY | Rustam Battalov | 2026-03-21 | CPP EIT | Gao Chong |  |  |  |  | Open
65 | PL-PS5-00065 | #N/A | CPP-RFI-68-33/1-03-0182 | PS5 | Electrical Cable Ladder/Tray Installation | Launcher&Receiver Area, CFO Area and Closed drain drum Area | N/A | Doc.TZ-MID-68-WPR2-151113,TZ-MID-68-WPR2-151115 Cover not installed | C | Electrical | CPY | Rustam Battalov | 2026-03-21 | CPP EIT | Gao Chong |  |  |  |  | Open
66 | PL-PS5-00066 | #N/A | CPP-RFI-68-64-03-0033 | PS5 | Instrument Cable Ladder/Tray Installation | Launcher&Receiver Area, CFO Area and Closed drain drum Area | N/A | Doc.TZ-MID-68-WPR2-161500 - Corrosion need to be removed | C | Electrical | CPY | Rustam Battalov | 2026-03-21 | CPP EIT | Gao Chong |  |  |  |  | Open
67 | PL-PS5-00067 | #N/A | CPP-RFI-68-64-03-0033 | PS5 | Instrument Cable Ladder/Tray Installation | Launcher&Receiver Area, CFO Area and Closed drain drum Area | N/A | Doc.TZ-MID-68-WPR2-161500 - Bolts tightening on connection plates to be completed | B | Electrical | CPY | Rustam Battalov | 2026-03-21 | CPP EIT | Gao Chong |  |  |  |  | Open
68 | PL-PS5-00068 | #N/A | CPP-RFI-68-64-03-0033 | PS5 | Instrument Cable Ladder/Tray Installation | Launcher&Receiver Area, CFO Area and Closed drain drum Area | N/A | Doc.TZ-MID-68-WPR2-161500 - Hold down Clamp not Installed yet | B | Electrical | CPY | Rustam Battalov | 2026-03-21 | CPP EIT | Gao Chong |  |  |  |  | Open
69 | PL-PS5-00069 | #N/A | CPP-RFI-68-64-03-0033 | PS5 | Instrument Cable Ladder/Tray Installation | Launcher&Receiver Area, CFO Area and Closed drain drum Area | N/A | Doc.TZ-MID-68-WPR2-161500 - Earth jumper not installed completely | B | Electrical | CPY | Rustam Battalov | 2026-03-21 | CPP EIT | Gao Chong |  |  |  |  | Open
70 | PL-PS5-00070 | #N/A | CPP-RFI-68-64-03-0033 | PS5 | Instrument Cable Ladder/Tray Installation | Launcher&Receiver Area, CFO Area and Closed drain drum Area | N/A | Doc.TZ-MID-68-WPR2-161500 Grommets not installed | C | Electrical | CPY | Rustam Battalov | 2026-03-21 | CPP EIT | Gao Chong |  |  |  |  | Open
71 | PL-PS5-00071 | #N/A | CPP-RFI-68-64-03-0033 | PS5 | Instrument Cable Ladder/Tray Installation | Launcher&Receiver Area, CFO Area and Closed drain drum Area | N/A | Doc.TZ-MID-68-WPR2-161500 Cover not installed | C | Electrical | CPY | Rustam Battalov | 2026-03-21 | CPP EIT | Gao Chong |  |  |  |  | Open
72 | PL-PS5-00072 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-88-BU-HV-0013/0017 | Doc.TZ-MID-68-WPR2-151112 Cable Route Marker not yet done | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-20 | CPP EIT | Gao Chong |  |  |  |  | Open
73 | PL-PS5-00073 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0002A | Doc.TZ-MID-68-WPR2-151112 HV Trefoil Cable Clamp not installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-02 | CPP EIT | Gao Chong |  |  |  |  | Open
74 | PL-PS5-00074 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0002A | Doc.TZ-MID-68-WPR2-151112 - Missing Support by CPP1 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-02 | CPP1 | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
75 | PL-PS5-00075 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0002A-CH01 | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-02 | CPP EIT | Gao Chong |  |  |  |  | Open
76 | PL-PS5-00076 | #N/A | CPP-RFI-68-33/1-05-0181 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS) & Export Pump VSD area | N/A | Doc TZ-MID-68-WPR2-151112, TZ-MID-68-WPR2-151116 - Cable Ladder for Supporting Cable Installation (Transformers Side) not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-02 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
77 | PL-PS5-00077 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Tagging not yet install for tag number : PS5-61-IJ-0001-CH01, PS5-61-IJ-0001-CH02, PS5-61-IJ-0001-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-02 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
78 | PL-PS5-00078 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Tagging not yet install for tag number : PS5-61-IJ-0001-CH04, PS5-61-IJ-0001-CH05, PS5-61-IJ-0001-CH06 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-02 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
79 | PL-PS5-00079 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Tagging not yet install for tag number : PS5-61-IJ-0001-CH07, PS5-61-IJ-0001-CH08, PS5-61-IJ-0001-CH09 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-02 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
80 | PL-PS5-00080 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Tagging not yet install for tag number : PS5-61-IJ-0001-CH10, PS5-61-IJ-0001-CH11, PS5-61-IJ-0001-CH12 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-02 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
81 | PL-PS5-00081 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Tagging not yet install for tag number : PS5-61-ISR-0102-CH01, PS5-61-ISR-0102-CH02, PS5-61-ISR-0102-CH03 | C | Electrical | CPY | Rustam Battalov | 02-April-2026 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
82 | PL-PS5-00082 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Tagging not yet install for tag number : PS5-61-ISR-0101-CH01, PS5-61-ISR-0101-CH02, PS5-61-ISR-0101-CH03 | C | Electrical | CPY | Rustam Battalov | 02-April-2026 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
83 | PL-PS5-00083 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Tagging not yet install for tag number : PS5-61-IU-0011-CH01, PS5-61-IU-0011-CH02, PS5-61-IU-0011-CH03 | B | Electrical | CPY | Rustam Battalov | 02-April-2026 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
84 | PL-PS5-00084 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Tagging not yet install for tag number : PS5-61-IU-0010-CH01, PS5-61-IU-0010-CH02, PS5-61-IU-0010-CH03 | C | Electrical | CPY | Rustam Battalov | 02-April-2026 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
85 | PL-PS5-00085 | #N/A | CPP-RFI-68-33/1-03-0182 | PS5 | Electrical Cable Ladder/Tray Installation | Launcher&Receiver Area, CFO Area and Closed drain drum Area | N/A | Doc.TZ-MID-68-WPR2-151113,TZ-MID-68-WPR2-151115- Expansion splice Plate not Installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-06 | CPP EIT | Gao Chong |  |  |  |  | Open
86 | PL-PS5-00086 | #N/A | CPP-RFI-68-64-03-0033 | PS5 | Electrical Cable Ladder/Tray Installation | Launcher&Receiver Area, CFO Area and Closed drain drum Area | N/A | Doc.TZ-MID-68-WPR2-161500- Expansion splice Plate not Installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-04-06 | CPP EIT | Gao Chong |  |  |  |  | Open
87 | PL-PS5-00087 | #N/A | CPP-RFI-68-33/1-03-0213 | PS5 | Electrical Cable Ladder/Tray Installation | Closed Drain Drum Area and Power generation Cooling tower area | N/A | Doc.TZ-MID-68-WPR2-151117,TZ-MID-68-WPR2-151118 - Corrosion need to be removed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-10 | CPP EIT | Gao Chong |  |  |  |  | Open
88 | PL-PS5-00088 | #N/A | CPP-RFI-68-33/1-03-0213 | PS5 | Electrical Cable Ladder/Tray Installation | Closed Drain Drum Area and Power generation Cooling tower area | N/A | Doc.TZ-MID-68-WPR2-151117,TZ-MID-68-WPR2-151118 - Bolts tightening on connection plates to be completed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-10 | CPP EIT | Gao Chong |  |  |  |  | Open
89 | PL-PS5-00089 | #N/A | CPP-RFI-68-33/1-03-0213 | PS5 | Electrical Cable Ladder/Tray Installation | Closed Drain Drum Area and Power generation Cooling tower area | N/A | Doc.TZ-MID-68-WPR2-151117,TZ-MID-68-WPR2-151118- Hold down Clamp not Installed yet | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-10 | CPP EIT | Gao Chong |  |  |  |  | Open
90 | PL-PS5-00090 | #N/A | CPP-RFI-68-33/1-03-0213 | PS5 | Electrical Cable Ladder/Tray Installation | Closed Drain Drum Area and Power generation Cooling tower area | N/A | Doc.TZ-MID-68-WPR2-151117,TZ-MID-68-WPR2-151118 Earth jumper not installed completely | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-10 | CPP EIT | Gao Chong |  |  |  |  | Open
91 | PL-PS5-00091 | #N/A | CPP-RFI-68-33/1-03-0213 | PS5 | Electrical Cable Ladder/Tray Installation | Closed Drain Drum Area and Power generation Cooling tower area | N/A | Doc.TZ-MID-68-WPR2-151117,TZ-MID-68-WPR2-151118 Cover not installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-10 | CPP EIT | Gao Chong |  |  |  |  | Open
92 | PL-PS5-00092 | #N/A | CPP-RFI-68-33/1-03-0213 | PS5 | Electrical Cable Ladder/Tray Installation | Closed Drain Drum Area and Power generation Cooling tower area | N/A | Doc.TZ-MID-68-WPR2-151117,TZ-MID-68-WPR2-151119 Earth strap not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-10 | CPP EIT | Gao Chong |  |  |  |  | Open
93 | PL-PS5-00093 | #N/A | CPP-RFI-68-64-03-0034 | PS5 | Instrument Cable Ladder/Tray Installation | Closed Drain Drum Area and Power generation Cooling tower area | N/A | Doc.TZ-MID-68-WPR2-161500 - Corrosion need to be removed | C | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-04-10 | CPP EIT | Gao Chong |  |  |  |  | Open
94 | PL-PS5-00094 | #N/A | CPP-RFI-68-64-03-0034 | PS5 | Instrument Cable Ladder/Tray Installation | Closed Drain Drum Area and Power generation Cooling tower area | N/A | Doc.TZ-MID-68-WPR2-161500 - Bolts tightening on connection plates to be completed | C | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-04-10 | CPP EIT | Gao Chong |  |  |  |  | Open
95 | PL-PS5-00095 | #N/A | CPP-RFI-68-64-03-0034 | PS5 | Instrument Cable Ladder/Tray Installation | Closed Drain Drum Area and Power generation Cooling tower area | N/A | Doc.TZ-MID-68-WPR2-161500 - Hold down Clamp not Installed yet | B | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-04-10 | CPP EIT | Gao Chong |  |  |  |  | Open
96 | PL-PS5-00096 | #N/A | CPP-RFI-68-64-03-0034 | PS5 | Instrument Cable Ladder/Tray Installation | Closed Drain Drum Area and Power generation Cooling tower area | N/A | Doc.TZ-MID-68-WPR2-161500 - Earth jumper not installed completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-04-10 | CPP EIT | Gao Chong |  |  |  |  | Open
97 | PL-PS5-00097 | #N/A | CPP-RFI-68-64-03-0034 | PS5 | Instrument Cable Ladder/Tray Installation | Closed Drain Drum Area and Power generation Cooling tower area | N/A | Doc.TZ-MID-68-WPR2-161500 Cover not installed | C | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-04-10 | CPP EIT | Gao Chong |  |  |  |  | Open
98 | PL-PS5-00098 | #N/A | CPP-RFI-68-33/1-05-0181 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS) & Export Pump VSD area | N/A | Doc TZ-MID-68-WPR2-151112, TZ-MID-68-WPR2-151116 - Cable Ladder not Installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-10 | CPP1 | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
99 | PL-PS5-00099 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0002A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder not installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-10 | CPP EIT | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
100 | PL-PS5-00100 | #N/A | CPP-RFI-68-64-03-0034 | PS5 | Instrument Cable Ladder/Tray Installation | Closed Drain Drum Area and Power generation Cooling tower area | N/A | Doc.TZ-MID-68-WPR2-161500 sharp edge protection grommet to be installed | C | Instrumentation | CPY | Konstantin Ovchinnikov | 2026-04-10 | CPP EIT | Gao Chong |  |  |  |  | Open
101 | PL-PS5-00101 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Tagging not yet install for tag number : PS5-61-IJ-0001-CH13, PS5-61-IJ-0001-CH14, PS5-61-IJ-0001-CH15 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
102 | PL-PS5-00102 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Tagging not yet install for tag number : PS5-61-IJ-0001-CH16, PS5-61-IJ-0001-CH17, PS5-61-IJ-0001-CH18 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
103 | PL-PS5-00103 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Tagging not yet install for tag number : PS5-61-IJ-0001-CH19, PS5-61-IJ-0001-CH20, PS5-61-IJ-0001-CH21 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
104 | PL-PS5-00104 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Trefoil Cable Cleats not yet install for tag number : PS5-61-IJ-0001-CH01, PS5-61-IJ-0001-CH02, PS5-61-IJ-0001-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong |  |  |  |  | Open
105 | PL-PS5-00105 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Trefoil Cable Cleats not yet install for tag number : PS5-61-IJ-0001-CH04, PS5-61-IJ-0001-CH05, PS5-61-IJ-0001-CH06 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong |  |  |  |  | Open
106 | PL-PS5-00106 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Trefoil Cable Cleats not yet install for tag number : PS5-61-IJ-0001-CH07, PS5-61-IJ-0001-CH08, PS5-61-IJ-0001-CH09 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong |  |  |  |  | Open
107 | PL-PS5-00107 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Trefoil Cable Cleats not yet install for tag number : PS5-61-IJ-0001-CH10, PS5-61-IJ-0001-CH11, PS5-61-IJ-0001-CH12 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong |  |  |  |  | Open
108 | PL-PS5-00108 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Trefoil Cable Cleats not yet install for tag number : PS5-61-IJ-0001-CH13, PS5-61-IJ-0001-CH14, PS5-61-IJ-0001-CH15 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong |  |  |  |  | Open
109 | PL-PS5-00109 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Trefoil Cable Cleats not yet install for tag number : PS5-61-IJ-0001-CH16, PS5-61-IJ-0001-CH17, PS5-61-IJ-0001-CH18 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong |  |  |  |  | Open
110 | PL-PS5-00110 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Trefoil Cable Cleats not yet install for tag number : PS5-61-IJ-0001-CH19, PS5-61-IJ-0001-CH20, PS5-61-IJ-0001-CH21 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong |  |  |  |  | Open
111 | PL-PS5-00111 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Dressing not yet done for tagging number : PS5-61-IJ-0001-CH01, PS5-61-IJ-0001-CH02, PS5-61-IJ-0001-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong |  |  |  |  | Open
112 | PL-PS5-00112 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Dressing not yet done for tagging number : PS5-61-IJ-0001-CH04, PS5-61-IJ-0001-CH05, PS5-61-IJ-0001-CH06 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong |  |  |  |  | Open
113 | PL-PS5-00113 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Dressing not yet done for tagging number : PS5-61-IJ-0001-CH07, PS5-61-IJ-0001-CH08, PS5-61-IJ-0001-CH09 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong |  |  |  |  | Open
114 | PL-PS5-00114 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Dressing not yet done for tagging number : PS5-61-IJ-0001-CH10, PS5-61-IJ-0001-CH11, PS5-61-IJ-0001-CH12 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong |  |  |  |  | Open
115 | PL-PS5-00115 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Dressing not yet done for tagging number : PS5-61-IJ-0001-CH13, PS5-61-IJ-0001-CH14, PS5-61-IJ-0001-CH15 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong |  |  |  |  | Open
116 | PL-PS5-00116 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Dressing not yet done for tagging number : PS5-61-IJ-0001-CH16, PS5-61-IJ-0001-CH17, PS5-61-IJ-0001-CH18 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong |  |  |  |  | Open
117 | PL-PS5-00117 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Dressing not yet done for tagging number : PS5-61-IJ-0001-CH19, PS5-61-IJ-0001-CH20, PS5-61-IJ-0001-CH21 | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong |  |  |  |  | Open
118 | PL-PS5-00118 | #N/A | CPP-RFI-68-33/1-05-0196 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Route Marker not yet install at trench number : PS5-88-BU-HV-0015 | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-03-31 | CPP EIT | Gao Chong |  |  |  |  | Open
119 | PL-PS5-00118 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Tagging not yet install for tag number : PS5-63-IV-0010-CH01, PS5-63-IV-0010-CH02, PS5-63-IV-0010-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
120 | PL-PS5-00119 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Tagging not yet install for tag number : PS5-63-IV-0011-CH01, PS5-63-IV-0011-CH02, PS5-63-IV-0011-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
121 | PL-PS5-00120 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Tagging not yet install for tag number : PS5-61-IV-0001B-CH01, PS5-61-IV-0001B-CH02, PS5-61-IV-0001B-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
122 | PL-PS5-00121 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Tagging not yet install for tag number : PS5-61-IV-0001A-CH01, PS5-61-IV-0001A-CH02, PS5-61-IV-0001A-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
123 | PL-PS5-00122 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Trefoil Cable Cleats not yet install for tag number : PS5-61-ISR-0102-CH01, PS5-61-ISR-0102-CH02, PS5-61-ISR-0102-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
124 | PL-PS5-00123 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Trefoil Cable Cleats not yet install for tag number : PS5-61-ISR-0101-CH01, PS5-61-ISR-0101-CH02, PS5-61-ISR-0101-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
125 | PL-PS5-00124 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Trefoil Cable Cleats not yet install for tag number : PS5-61-IU-0011-CH01, PS5-61-IU-0011-CH02, PS5-61-IU-0011-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
126 | PL-PS5-00125 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Trefoil Cable Cleats not yet install for tag number : PS5-61-IU-0010-CH01, PS5-61-IU-0010-CH02, PS5-61-IU-0010-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
127 | PL-PS5-00126 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Trefoil Cable Cleats not yet install for tag number : PS5-63-IV-0010-CH01, PS5-63-IV-0010-CH02, PS5-63-IV-0010-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
128 | PL-PS5-00127 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Trefoil Cable Cleats not yet install for tag number : PS5-63-IV-0011-CH01, PS5-63-IV-0011-CH02, PS5-63-IV-0011-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
129 | PL-PS5-00128 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Trefoil Cable Cleats not yet install for tag number : PS5-61-IV-0001B-CH01, PS5-61-IV-0001B-CH02, PS5-61-IV-0001B-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
130 | PL-PS5-00129 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Trefoil Cable Cleats not yet install for tag number : PS5-61-IV-0001A-CH01, PS5-61-IV-0001A-CH02, PS5-61-IV-0001A-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
131 | PL-PS5-00130 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Dressing not yet done for tagging number : PS5-61-ISR-0102-CH01, PS5-61-ISR-0102-CH02, PS5-61-ISR-0102-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
132 | PL-PS5-00131 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Dressing not yet done for tagging number : PS5-61-ISR-0101-CH01, PS5-61-ISR-0101-CH02, PS5-61-ISR-0101-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
133 | PL-PS5-00132 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Dressing not yet done for tagging number : PS5-61-IU-0011-CH01, PS5-61-IU-0011-CH02, PS5-61-IU-0011-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
134 | PL-PS5-00133 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Dressing not yet done for tagging number : PS5-61-IU-0010-CH01, PS5-61-IU-0010-CH02, PS5-61-IU-0010-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
135 | PL-PS5-00134 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Dressing not yet done for tagging number : PS5-63-IV-0010-CH01, PS5-63-IV-0010-CH02, PS5-63-IV-0010-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
136 | PL-PS5-00135 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Dressing not yet done for tagging number : PS5-63-IV-0011-CH01, PS5-63-IV-0011-CH02, PS5-63-IV-0011-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
137 | PL-PS5-00136 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Dressing not yet done for tagging number : PS5-61-IV-0001B-CH01, PS5-61-IV-0001B-CH02, PS5-61-IV-0001B-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
138 | PL-PS5-00137 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Dressing not yet done for tagging number : PS5-61-IV-0001A-CH01, PS5-61-IV-0001A-CH02, PS5-61-IV-0001A-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
139 | PL-PS5-00138 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Route Marker not yet install at trench number PS5-88-BU-HV-0015 | C | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
140 | PL-PS5-00139 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder Support not yet install for Transformers PS5-61-ISR-0102 | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP1 | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
141 | PL-PS5-00140 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder Support not yet install for Transformers PS5-61-ISR-0101 | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP1 | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
142 | PL-PS5-00141 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder Support not yet install for Transformers PS5-61-IU-0011 | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP1 | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
143 | PL-PS5-00142 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder Support not yet install for Transformers PS5-61-IU-0010 | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP1 | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
144 | PL-PS5-00143 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder Support not yet install for Transformers PS5-63-IV-0010 | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP1 | Gao Chong |  |  |  |  | Open
145 | PL-PS5-00144 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder Support not yet install for Transforners PS5-63-IV-0011 | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP1 | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
146 | PL-PS5-00145 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder Support not yet install for Transformers PS5-61-IV-0001B | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP1 | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
147 | PL-PS5-00146 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder Support not yet install for Transformers PS5-61-IV-0001A | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP1 | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
148 | PL-PS5-00148 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder not yet install for Transformers PS5-61-ISR-0102 | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP1 | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
149 | PL-PS5-00149 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder not yet install for Transformers PS5-61-ISR-0101 | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
150 | PL-PS5-00150 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder not yet install for Transformers PS5-61-IU-0011 | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
151 | PL-PS5-00151 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder not yet install for Transformers PS5-61-IU-0010 | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
152 | PL-PS5-00152 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder not yet install for Transformers PS5-63-IV-0010 | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
153 | PL-PS5-00153 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder not yet install for Transformers PS5-63-IV-0011 | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
154 | PL-PS5-00154 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder not yet install for Transformers PS5-61-IV-0001B | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
155 | PL-PS5-00155 | #N/A | CPP-RFI-68-33/1-05-0197 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder not yet install for Transformers PS5-61-IV-0001A | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
156 | PL-PS5-00156 | #N/A | CPP-RFI-68-33/1-05-0198 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Tagging not yet install for tag number : PS5-61-IJ-0011-CH01, PS5-61-IJ-0011-CH02, PS5-61-IJ-0011-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
157 | PL-PS5-00157 | #N/A | CPP-RFI-68-33/1-05-0198 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Tagging not yet install for tag number : PS5-61-IJ-0010-CH01, PS5-61-IJ-0010-CH02, PS5-61-IJ-0010-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
158 | PL-PS5-00158 | #N/A | CPP-RFI-68-33/1-05-0198 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Trefoil Cable Cleats not yet install for tag number : PS5-61-IJ-0011-CH01, PS5-61-IJ-0011-CH02, PS5-61-IJ-0011-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
159 | PL-PS5-00159 | #N/A | CPP-RFI-68-33/1-05-0198 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Trefoil Cable Cleats not yet install for tag number : PS5-61-IJ-0010-CH01, PS5-61-IJ-0010-CH02, PS5-61-IJ-0010-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
160 | PL-PS5-00160 | #N/A | CPP-RFI-68-33/1-05-0198 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Dressing not yet done for tagging number : PS5-61-IJ-0011-CH01, PS5-61-IJ-0011-CH02, PS5-61-IJ-0011-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
161 | PL-PS5-00161 | #N/A | CPP-RFI-68-33/1-05-0198 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112, TZ-MID-68-SSF1-240000 - Cable Dressing not yet done for tagging number : PS5-61-IJ-0010-CH01, PS5-61-IJ-0010-CH02, PS5-61-IJ-0010-CH03 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
162 | PL-PS5-00162 | #N/A | CPP-RFI-68-33/1-05-0198 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder Support not yet install for Transformers : PS5-61-IU-0011 | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP1 | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
163 | PL-PS5-00163 | #N/A | CPP-RFI-68-33/1-05-0198 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder Support not yet install for Transformers : PS5-61-IU-0010 | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP1 | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
164 | PL-PS5-00164 | #N/A | CPP-RFI-68-33/1-05-0198 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder not yet install for Transformers : PS5-61-IU-0011 | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
165 | PL-PS5-00165 | #N/A | CPP-RFI-68-33/1-05-0198 | PS5 | Electrical Cable Installation | Power Distribution Area | N/A | Doc.TZ-MID-68-WPR2-151112 - Cable Ladder not yet install for Transformers : PS5-61-IU-0010 | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
166 | PL-PS5-00166 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100A | Doc.TZ-MID-68-WPR2-151111 - HV Trefoil Cable Clamp not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
167 | PL-PS5-00167 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | N/A | Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
168 | PL-PS5-00168 | #N/A | CPP-RFI-68-33/1-05-0216 | PS5 | Electrical Cable Installation | Export Pump VSD area & Export Pump Loading area | PS5-25-04 | Doc.TZ-MID-68-WPR2-151111 & TZ-MID-68-WPR2-151114 - HV Trefoil Cable Clamp not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
169 | PL-PS5-00169 | #N/A | CPP-RFI-68-33/1-05-0217 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100A-CD03 | Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
170 | PL-PS5-00170 | #N/A | CPP-RFI-68-33/1-05-0219 | PS5 | Electrical Cable Installation | Utility/Fire Water Tank Area and Power distribution area | PS5-01-FIT-0003A-CL01 | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
171 | PL-PS5-00171 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0002A-CH02 | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
172 | PL-PS5-00172 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0002A-CH03 | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done | C | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
173 | PL-PS5-00173 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0002B | Doc.TZ-MID-68-WPR2-151112 HV Trefoil Cable Clamp not installed | C | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
174 | PL-PS5-00174 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0002B | Doc.TZ-MID-68-WPR2-151112 - Missing Support by CPP1 | A | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP1 | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
175 | PL-PS5-00175 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0002B-CH01 | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
176 | PL-PS5-00176 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0002B-CH02 | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
177 | PL-PS5-00177 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0002B-CH03 | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
178 | PL-PS5-00178 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0007A | Doc.TZ-MID-68-WPR2-151112 HV Trefoil Cable Clamp not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
179 | PL-PS5-00179 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0007A | Doc.TZ-MID-68-WPR2-151112 - Missing Support by CPP1 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
180 | PL-PS5-00180 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0007A-CH01 | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
181 | PL-PS5-00181 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0007A-CH02 | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
182 | PL-PS5-00182 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0007A-CH03 | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
183 | PL-PS5-00183 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0007B | Doc.TZ-MID-68-WPR2-151112 HV Trefoil Cable Clamp not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
184 | PL-PS5-00184 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0007B | Doc.TZ-MID-68-WPR2-151112 - Missing Support by CPP1 | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
185 | PL-PS5-00185 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0007B-CH01 | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
186 | PL-PS5-00186 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0007B-CH02 | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
187 | PL-PS5-00187 | #N/A | CPP-RFI-68-33/1-05-0184 | PS5 | Electrical Cable Installation | Power Distribution Area (EITS), Generator Electrical Building | PS5-61-IV-0007B-CH03 | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
188 | PL-PS5-00188 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100B | Doc.TZ-MID-68-WPR2-151111 - HV Trefoil Cable Clamp not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
189 | PL-PS5-00189 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100A-CH01, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
190 | PL-PS5-00190 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100A-CH02, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
191 | PL-PS5-00191 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100A-CH03, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
192 | PL-PS5-00192 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100A-CH04, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
193 | PL-PS5-00193 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100A-CH05, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
194 | PL-PS5-00194 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100A-CH06, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
195 | PL-PS5-00195 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100A-CH07, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
196 | PL-PS5-00196 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100A-CH08, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
197 | PL-PS5-00197 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100A-CH09, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
198 | PL-PS5-00198 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100A-CH10, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
199 | PL-PS5-00199 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100A-CH11, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
200 | PL-PS5-00200 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100A-CH12, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
201 | PL-PS5-00201 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IU-3100A-CH04, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
202 | PL-PS5-00202 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100B-CH01, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
203 | PL-PS5-00203 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100B-CH02, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
204 | PL-PS5-00204 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100B-CH03, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
205 | PL-PS5-00205 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100B-CH04, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
206 | PL-PS5-00206 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100B-CH05, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
207 | PL-PS5-00207 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100B-CH06, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
208 | PL-PS5-00208 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100B-CH07, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
209 | PL-PS5-00209 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100B-CH08, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
210 | PL-PS5-00210 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100B-CH09, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
211 | PL-PS5-00211 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100B-CH10, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
212 | PL-PS5-00212 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100B-CH11, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
213 | PL-PS5-00213 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100B-CH12, | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
214 | PL-PS5-00214 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IU-3100B-CH04, | Doc.TZ-MID-68-WPR2-151113 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
215 | PL-PS5-00215 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100C | Doc.TZ-MID-68-WPR2-151111 - HV Trefoil Cable Clamp not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
216 | PL-PS5-00216 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100C-CH01, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
217 | PL-PS5-00217 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100C-CH02, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
218 | PL-PS5-00218 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100C-CH03, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
219 | PL-PS5-00219 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100C-CH04, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
220 | PL-PS5-00220 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100C-CH05, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
221 | PL-PS5-00221 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100C-CH06, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
222 | PL-PS5-00222 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100C-CH07, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
223 | PL-PS5-00223 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100C-CH08, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
224 | PL-PS5-00224 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100C-CH09, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
225 | PL-PS5-00225 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100C-CH10, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
226 | PL-PS5-00226 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100C-CH11, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
227 | PL-PS5-00227 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100C-CH12, | Doc.TZ-MID-68-WPR2-151111 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
228 | PL-PS5-00228 | #N/A | CPP-RFI-68-33/1-05-0192 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IU-3100C-CH04, | Doc.TZ-MID-68-WPR2-151112 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
229 | PL-PS5-00229 | #N/A | CPP-RFI-68-33/1-05-0216 | PS5 | Electrical Cable Installation | Export Pump VSD area & Export Pump Loading area | PS5-25-02 | Doc.TZ-MID-68-WPR2-151111 & TZ-MID-68-WPR2-151114 - HV Trefoil Cable Clamp not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
230 | PL-PS5-00230 | #N/A | CPP-RFI-68-33/1-05-0216 | PS5 | Electrical Cable Installation | Export Pump VSD area & Export Pump Loading area | PS5-25-03 | Doc.TZ-MID-68-WPR2-151111 & TZ-MID-68-WPR2-151115 - HV Trefoil Cable Clamp not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | OPEN
231 | PL-PS5-00231 | #N/A | CPP-RFI-68-33/1-05-0216 | PS5 | Electrical Cable Installation | Export Pump VSD area & Export Pump Loading area | PS5-25-04 | Doc.TZ-MID-68-WPR2-151111 & TZ-MID-68-WPR2-151116 - HV Trefoil Cable Clamp not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | OPEN
232 | PL-PS5-00232 | #N/A | CPP-RFI-68-33/1-05-0217 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100A-CD03 | Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | OPEN
233 | PL-PS5-00233 | #N/A | CPP-RFI-68-33/1-05-0217 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100A-CL01 | Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | OPEN
234 | PL-PS5-00234 | #N/A | CPP-RFI-68-33/1-05-0217 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100B-CD03 | Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | OPEN
235 | PL-PS5-00235 | #N/A | CPP-RFI-68-33/1-05-0217 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100B-CL01 | Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | OPEN
236 | PL-PS5-00236 | #N/A | CPP-RFI-68-33/1-05-0217 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100C-CD03 | Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | OPEN
237 | PL-PS5-00237 | #N/A | CPP-RFI-68-33/1-05-0217 | PS5 | Electrical Cable Installation | Export Pump VSD area | PS5-61-IDH-3100C-CL01 | Doc.TZ-MID-68-WPR2-151111 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 02-April-2026 | CPP EIT | Gao Chong |  |  |  |  | OPEN
238 | PL-PS5-00238 | #N/A | CPP-RFI-68-33/1-05-0219 | PS5 | Electrical Cable Installation | Utility/Fire Water Tank Area and Power distribution area | PS5-01-FIT-0003A-CL01 | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
239 | PL-PS5-00239 | #N/A | CPP-RFI-68-33/1-05-0219 | PS5 | Electrical Cable Installation | Utility/Fire Water Tank Area and Power distribution area | PS5-01-FIT-0003B-CL01 | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
240 | PL-PS5-00240 | #N/A | CPP-RFI-68-33/1-05-0219 | PS5 | Electrical Cable Installation | Utility/Fire Water Tank Area and Power distribution area | PS5-01-FIT-0004A-CL01 | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
241 | PL-PS5-00241 | #N/A | CPP-RFI-68-33/1-05-0219 | PS5 | Electrical Cable Installation | Utility/Fire Water Tank Area and Power distribution area | PS5-01-FIT-0004B-CL01 | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
242 | PL-PS5-00242 | #N/A | CPP-RFI-68-33/1-05-0219 | PS5 | Electrical Cable Installation | Utility/Fire Water Tank Area and Power distribution area | PS5-01-IE-0002A-CL01 | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
243 | PL-PS5-00243 | #N/A | CPP-RFI-68-33/1-05-0219 | PS5 | Electrical Cable Installation | Utility/Fire Water Tank Area and Power distribution area | PS5-01-IE-0002B-CL01 | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
244 | PL-PS5-00244 | #N/A | CPP-RFI-68-33/1-05-0219 | PS5 | Electrical Cable Installation | Utility/Fire Water Tank Area and Power distribution area | PS5-01-IE-0009A-CL01 | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
245 | PL-PS5-00245 | #N/A | CPP-RFI-68-33/1-05-0219 | PS5 | Electrical Cable Installation | Utility/Fire Water Tank Area and Power distribution area | PS5-01-IE-0009B-CL01 | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
246 | PL-PS5-00246 | #N/A | CPP-RFI-68-33/1-05-0219 | PS5 | Electrical Cable Installation | Utility/Fire Water Tank Area and Power distribution area | PS5-53-DM-3100A-CL01 | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
247 | PL-PS5-00247 | #N/A | CPP-RFI-68-33/1-05-0219 | PS5 | Electrical Cable Installation | Utility/Fire Water Tank Area and Power distribution area | PS5-53-DM-3100B-CL01 | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
248 | PL-PS5-00248 | #N/A | CPP-RFI-68-33/1-05-0219 | PS5 | Electrical Cable Installation | Utility/Fire Water Tank Area and Power distribution area | PS5-53-IES-3100A-CD01 | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
249 | PL-PS5-00249 | #N/A | CPP-RFI-68-33/1-05-0219 | PS5 | Electrical Cable Installation | Utility/Fire Water Tank Area and Power distribution area | PS5-53-IES-3100B-CD01 | Doc.TZ-MID-68-WPR2-151109 &TZ-MID-68-WPR2-151112 - Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
250 | PL-PS5-00250 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-1117-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
251 | PL-PS5-00251 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-1515-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
252 | PL-PS5-00252 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-2110-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
253 | PL-PS5-00253 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2509-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
254 | PL-PS5-00254 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1115-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
255 | PL-PS5-00255 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1201-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
256 | PL-PS5-00256 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1301-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
257 | PL-PS5-00257 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2105-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
258 | PL-PS5-00258 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2106-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
259 | PL-PS5-00259 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2201-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
260 | PL-PS5-00260 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2301-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
261 | PL-PS5-00261 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2302-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
262 | PL-PS5-00262 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2305-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
263 | PL-PS5-00263 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2309-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
264 | PL-PS5-00264 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-28-BI-1307-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
265 | PL-PS5-00265 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-50-BI-1107-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
266 | PL-PS5-00266 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-53-BI-1108-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
267 | PL-PS5-00267 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1110-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
268 | PL-PS5-00268 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1111-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
269 | PL-PS5-00269 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1306-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
270 | PL-PS5-00270 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2515-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
271 | PL-PS5-00271 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1101-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
272 | PL-PS5-00272 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1103-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
273 | PL-PS5-00273 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1104-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
274 | PL-PS5-00274 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1302-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
275 | PL-PS5-00275 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2104-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
276 | PL-PS5-00276 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2108-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
277 | PL-PS5-00277 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2316-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
278 | PL-PS5-00278 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-28-BI-1303-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
279 | PL-PS5-00279 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1109-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
280 | PL-PS5-00280 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1113-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
281 | PL-PS5-00281 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1116-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
282 | PL-PS5-00282 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1117-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
283 | PL-PS5-00283 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2107-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
284 | PL-PS5-00284 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2113-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
285 | PL-PS5-00285 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2114-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
286 | PL-PS5-00286 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2115-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
287 | PL-PS5-00287 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2116-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
288 | PL-PS5-00288 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2122-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
289 | PL-PS5-00289 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2123-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
290 | PL-PS5-00290 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2124-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
291 | PL-PS5-00291 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2125-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
292 | PL-PS5-00292 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2306-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
293 | PL-PS5-00293 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2314-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
294 | PL-PS5-00294 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-1117-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
295 | PL-PS5-00295 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-1515-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
296 | PL-PS5-00296 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-2110-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
297 | PL-PS5-00297 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2509-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
298 | PL-PS5-00298 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1115-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
299 | PL-PS5-00299 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1201-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
300 | PL-PS5-00300 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1301-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
301 | PL-PS5-00301 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2105-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
302 | PL-PS5-00302 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2106-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
303 | PL-PS5-00303 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2201-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
304 | PL-PS5-00304 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2301-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
305 | PL-PS5-00305 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2302-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
306 | PL-PS5-00306 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2305-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
307 | PL-PS5-00307 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2309-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
308 | PL-PS5-00308 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-28-BI-1307-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
309 | PL-PS5-00309 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-50-BI-1107-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
310 | PL-PS5-00310 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-53-BI-1108-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
311 | PL-PS5-00311 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1110-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
312 | PL-PS5-00312 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1111-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
313 | PL-PS5-00313 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1306-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
314 | PL-PS5-00314 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2515-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
315 | PL-PS5-00315 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1101-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
316 | PL-PS5-00316 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1103-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
317 | PL-PS5-00317 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1104-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
318 | PL-PS5-00318 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1302-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
319 | PL-PS5-00319 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2104-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
320 | PL-PS5-00320 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2108-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
321 | PL-PS5-00321 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2316-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
322 | PL-PS5-00322 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-28-BI-1303-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
323 | PL-PS5-00323 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1109-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
324 | PL-PS5-00324 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1113-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
325 | PL-PS5-00325 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1116-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
326 | PL-PS5-00326 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1117-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
327 | PL-PS5-00327 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2107-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
328 | PL-PS5-00328 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2113-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
329 | PL-PS5-00329 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2114-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
330 | PL-PS5-00330 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2115-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
331 | PL-PS5-00331 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2116-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
332 | PL-PS5-00332 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2122-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
333 | PL-PS5-00333 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2123-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
334 | PL-PS5-00334 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2124-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
335 | PL-PS5-00335 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2125-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
336 | PL-PS5-00336 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2306-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
337 | PL-PS5-00337 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2314-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
338 | PL-PS5-00338 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-1117-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
339 | PL-PS5-00339 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-1515-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
340 | PL-PS5-00340 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-2110-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
341 | PL-PS5-00341 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2509-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
342 | PL-PS5-00342 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1115-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
343 | PL-PS5-00343 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1201-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
344 | PL-PS5-00344 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1301-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
345 | PL-PS5-00345 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2105-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
346 | PL-PS5-00346 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2106-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
347 | PL-PS5-00347 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2201-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
348 | PL-PS5-00348 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2301-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
349 | PL-PS5-00349 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2302-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
350 | PL-PS5-00350 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2305-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
351 | PL-PS5-00351 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2309-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
352 | PL-PS5-00352 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-28-BI-1307-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
353 | PL-PS5-00353 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-50-BI-1107-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
354 | PL-PS5-00354 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-53-BI-1108-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
355 | PL-PS5-00355 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1110-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
356 | PL-PS5-00356 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1111-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
357 | PL-PS5-00357 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1306-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
358 | PL-PS5-00358 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2515-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
359 | PL-PS5-00359 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1101-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
360 | PL-PS5-00360 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1103-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
361 | PL-PS5-00361 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1104-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
362 | PL-PS5-00362 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1302-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
363 | PL-PS5-00363 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2104-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
364 | PL-PS5-00364 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2108-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
365 | PL-PS5-00365 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2316-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
366 | PL-PS5-00366 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-28-BI-1303-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
367 | PL-PS5-00367 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1109-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
368 | PL-PS5-00368 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1113-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
369 | PL-PS5-00369 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1116-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
370 | PL-PS5-00370 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1117-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
371 | PL-PS5-00371 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2107-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
372 | PL-PS5-00372 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2113-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
373 | PL-PS5-00373 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2114-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
374 | PL-PS5-00374 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2115-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
375 | PL-PS5-00375 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2116-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
376 | PL-PS5-00376 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2122-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
377 | PL-PS5-00377 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2123-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
378 | PL-PS5-00378 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2124-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
379 | PL-PS5-00379 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2125-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
380 | PL-PS5-00380 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2306-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
381 | PL-PS5-00381 | #N/A | CPP-RFI-68-64-04-0035 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2310-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
382 | PL-PS5-00382 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-74-LB-5101-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
383 | PL-PS5-00383 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-0005-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
384 | PL-PS5-00384 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-1571-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
385 | PL-PS5-00385 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-2571A-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
386 | PL-PS5-00386 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-1502-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED |  |  | CLOSED
387 | PL-PS5-00387 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-1510-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
388 | PL-PS5-00388 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2501-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
389 | PL-PS5-00389 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2502-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
390 | PL-PS5-00390 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-53-LA-0001-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
391 | PL-PS5-00391 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-53-LA-0001-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
392 | PL-PS5-00392 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1112-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
393 | PL-PS5-00393 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-74-LB-5101-CX01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
394 | PL-PS5-00394 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-53-LA-0001-CX01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
395 | PL-PS5-00395 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-74-LB-5101-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
396 | PL-PS5-00396 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-0001-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
397 | PL-PS5-00397 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-0004-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
398 | PL-PS5-00398 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-0006-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
399 | PL-PS5-00399 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-LB-0004-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
400 | PL-PS5-00400 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-LB-0004-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
401 | PL-PS5-00401 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-LB-0004-CC03 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
402 | PL-PS5-00402 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-PIT-0014-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
403 | PL-PS5-00403 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-PIT-0016-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
404 | PL-PS5-00404 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-PIT-0017-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
405 | PL-PS5-00405 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2505-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
406 | PL-PS5-00406 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2507-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
407 | PL-PS5-00407 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2508-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
408 | PL-PS5-00408 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-SEA-0003-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
409 | PL-PS5-00409 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-06-GU-0003A-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
410 | PL-PS5-00410 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-06-GU-0003B-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
411 | PL-PS5-00411 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-LB-0008-CC04 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
412 | PL-PS5-00412 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-LB-0008-CC05 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
413 | PL-PS5-00413 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-LB-0008-CC07 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
414 | PL-PS5-00414 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-LB-0008-CC08 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
415 | PL-PS5-00415 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003A-CC21 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
416 | PL-PS5-00416 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003A-CC22 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
417 | PL-PS5-00417 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003A-CC23 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
418 | PL-PS5-00418 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003A-CC24 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
419 | PL-PS5-00419 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003B-CC21 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
420 | PL-PS5-00420 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003B-CC22 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
421 | PL-PS5-00421 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003B-CC23 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
422 | PL-PS5-00422 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003B-CC24 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
423 | PL-PS5-00423 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003C-CC23 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
424 | PL-PS5-00424 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003C-CC24 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
425 | PL-PS5-00425 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003D-CC23 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
426 | PL-PS5-00426 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003D-CC24 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
427 | PL-PS5-00427 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003E-CC23 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
428 | PL-PS5-00428 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003E-CC24 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
429 | PL-PS5-00429 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003F-CC21 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
430 | PL-PS5-00430 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003F-CC22 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
431 | PL-PS5-00431 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003F-CC23 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
432 | PL-PS5-00432 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003F-CC24 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
433 | PL-PS5-00433 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003G-CC21 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
434 | PL-PS5-00434 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003G-CC22 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
435 | PL-PS5-00435 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003G-CC23 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
436 | PL-PS5-00436 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003G-CC24 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
437 | PL-PS5-00437 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0004-CC11 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
438 | PL-PS5-00438 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0004-CC12 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
439 | PL-PS5-00439 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-SEA-0001-CC18 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
440 | PL-PS5-00440 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0001-CC08 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
441 | PL-PS5-00441 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0001-CC09 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
442 | PL-PS5-00442 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0001-CC10 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
443 | PL-PS5-00443 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0003-CC05 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
444 | PL-PS5-00444 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0003-CC06 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
445 | PL-PS5-00445 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0003-CC07 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
446 | PL-PS5-00446 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-BI-0002-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
447 | PL-PS5-00447 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-BI-0002-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
448 | PL-PS5-00448 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-IE-8101-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
449 | PL-PS5-00449 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-BI-0002-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
450 | PL-PS5-00450 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-BI-0002-CJ02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
451 | PL-PS5-00451 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-LIT-4101-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
452 | PL-PS5-00452 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-BI-0002-CJ03 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
453 | PL-PS5-00453 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-IG-0009-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
454 | PL-PS5-00454 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-BI-0002-CC11 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
455 | PL-PS5-00455 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-BI-0002-CC12 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
456 | PL-PS5-00456 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-IE-8104-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
457 | PL-PS5-00457 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-74-LB-5101-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
458 | PL-PS5-00458 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-0005-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
459 | PL-PS5-00459 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-1571-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
460 | PL-PS5-00460 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-2571A-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
461 | PL-PS5-00461 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-1502-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
462 | PL-PS5-00462 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-1510-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
463 | PL-PS5-00463 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2501-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
464 | PL-PS5-00464 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2502-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
465 | PL-PS5-00465 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-53-LA-0001-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
466 | PL-PS5-00466 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-53-LA-0001-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
467 | PL-PS5-00467 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-1112-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
468 | PL-PS5-00468 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-74-LB-5101-CX01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
469 | PL-PS5-00469 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-53-LA-0001-CX01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
470 | PL-PS5-00470 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-74-LB-5101-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
471 | PL-PS5-00471 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-0001-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
472 | PL-PS5-00472 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-0004-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
473 | PL-PS5-00473 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-BI-0006-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
474 | PL-PS5-00474 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-LB-0004-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
475 | PL-PS5-00475 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-LB-0004-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
476 | PL-PS5-00476 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-LB-0004-CC03 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
477 | PL-PS5-00477 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-PIT-0014-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
478 | PL-PS5-00478 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-PIT-0016-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
479 | PL-PS5-00479 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-PIT-0017-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
480 | PL-PS5-00480 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2505-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
481 | PL-PS5-00481 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2507-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
482 | PL-PS5-00482 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2508-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
483 | PL-PS5-00483 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-SEA-0003-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
484 | PL-PS5-00484 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-06-GU-0003A-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, Cable tray need to be Installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
485 | PL-PS5-00485 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-06-GU-0003B-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, Cable tray need to be Installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
486 | PL-PS5-00486 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-LB-0008-CC04 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
487 | PL-PS5-00487 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-LB-0008-CC05 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
488 | PL-PS5-00488 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-LB-0008-CC07 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
489 | PL-PS5-00489 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-LB-0008-CC08 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
490 | PL-PS5-00490 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003A-CC21 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
491 | PL-PS5-00491 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003A-CC22 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
492 | PL-PS5-00492 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003A-CC23 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
493 | PL-PS5-00493 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003A-CC24 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
494 | PL-PS5-00494 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003B-CC21 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
495 | PL-PS5-00495 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003B-CC22 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
496 | PL-PS5-00496 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003B-CC23 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
497 | PL-PS5-00497 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003B-CC24 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
498 | PL-PS5-00498 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003C-CC23 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
499 | PL-PS5-00499 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003C-CC24 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
500 | PL-PS5-00500 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003D-CC23 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
501 | PL-PS5-00501 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003D-CC24 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
502 | PL-PS5-00502 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003E-CC23 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
503 | PL-PS5-00503 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003E-CC24 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
504 | PL-PS5-00504 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003F-CC21 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
505 | PL-PS5-00505 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003F-CC22 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
506 | PL-PS5-00506 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003F-CC23 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
507 | PL-PS5-00507 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003F-CC24 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
508 | PL-PS5-00508 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003G-CC21 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
509 | PL-PS5-00509 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003G-CC22 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
510 | PL-PS5-00510 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003G-CC23 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
511 | PL-PS5-00511 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0003G-CC24 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
512 | PL-PS5-00512 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0004-CC11 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
513 | PL-PS5-00513 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-IE-0004-CC12 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
514 | PL-PS5-00514 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-60-SEA-0001-CC18 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
515 | PL-PS5-00515 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0001-CC08 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
516 | PL-PS5-00516 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0001-CC09 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
517 | PL-PS5-00517 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0001-CC10 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
518 | PL-PS5-00518 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0003-CC05 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
519 | PL-PS5-00519 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0003-CC06 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
520 | PL-PS5-00520 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0003-CC07 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
521 | PL-PS5-00521 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-BI-0002-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
522 | PL-PS5-00522 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-BI-0002-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
523 | PL-PS5-00523 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-IE-8101-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
524 | PL-PS5-00524 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-BI-0002-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
525 | PL-PS5-00525 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-BI-0002-CJ02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
526 | PL-PS5-00526 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-LIT-4101-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
527 | PL-PS5-00527 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-BI-0002-CJ03 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
528 | PL-PS5-00528 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-IG-0009-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
529 | PL-PS5-00529 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-BI-0002-CC11 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
530 | PL-PS5-00530 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-BI-0002-CC12 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
531 | PL-PS5-00531 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-05-IE-8104-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
532 | PL-PS5-00532 | #N/A | CPP-RFI-68-64-04-0036 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-01-PIT-0014-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench | A | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
533 | PL-PS5-00533 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-28-BI-1106-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
534 | PL-PS5-00534 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-50-IE-0001-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
535 | PL-PS5-00535 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-75-BI-1177-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
536 | PL-PS5-00536 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-75-BI-1178-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
537 | PL-PS5-00537 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-75-BI-1371-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
538 | PL-PS5-00538 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-75-BI-1372-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
539 | PL-PS5-00539 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-75-MOV-0001-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
540 | PL-PS5-00540 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-SEA-0002-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
541 | PL-PS5-00541 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-SEA-0006-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
542 | PL-PS5-00542 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-BI-2501-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
543 | PL-PS5-00543 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-LB-0007-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
544 | PL-PS5-00544 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-LB-0007-CC03 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
545 | PL-PS5-00545 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-LB-0007-CC04 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
546 | PL-PS5-00546 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-28-HXA-1101-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
547 | PL-PS5-00547 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-28-LB-8200-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
548 | PL-PS5-00548 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-28-LB-8200-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
549 | PL-PS5-00549 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-50-IE-0001-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
550 | PL-PS5-00550 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-50-IE-0001-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
551 | PL-PS5-00551 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-75-MOV-0001-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
552 | PL-PS5-00552 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-82-LA-0001-CX01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
553 | PL-PS5-00553 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-28-BI-1106-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
554 | PL-PS5-00554 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-50-IE-0001-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
555 | PL-PS5-00555 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-75-BI-1177-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
556 | PL-PS5-00556 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-75-BI-1178-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
557 | PL-PS5-00557 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-75-BI-1371-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
558 | PL-PS5-00558 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-75-BI-1372-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
559 | PL-PS5-00559 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-75-MOV-0001-CC02 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
560 | PL-PS5-00560 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-SEA-0002-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
561 | PL-PS5-00561 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-SEA-0006-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
562 | PL-PS5-00562 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-BI-2501-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
563 | PL-PS5-00563 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-LB-0007-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
564 | PL-PS5-00564 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-LB-0007-CC03 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
565 | PL-PS5-00565 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-LB-0007-CC04 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
566 | PL-PS5-00566 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-28-HXA-1101-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
567 | PL-PS5-00567 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-28-LB-8200-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
568 | PL-PS5-00568 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-28-LB-8200-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
569 | PL-PS5-00569 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-50-IE-0001-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
570 | PL-PS5-00570 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-50-IE-0001-CC02 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
571 | PL-PS5-00571 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-75-MOV-0001-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
572 | PL-PS5-00572 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-82-LA-0001-CX01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
573 | PL-PS5-00573 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-50-IE-0001-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench | A | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
574 | PL-PS5-00574 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-50-IE-0001-CC02 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench | A | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
575 | PL-PS5-00575 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-75-MOV-0001-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench | A | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
576 | PL-PS5-00576 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-28-HXA-1101-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench | A | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
577 | PL-PS5-00577 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-75-MOV-0001-CC02 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench | A | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
578 | PL-PS5-00578 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-LB-0007-CC04 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench | A | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
579 | PL-PS5-00579 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-SEA-0002-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench | A | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
580 | PL-PS5-00580 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-SEA-0006-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench | A | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
581 | PL-PS5-00581 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-BI-2501-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench | A | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
582 | PL-PS5-00582 | #N/A | CPP-RFI-68-64-04-0037 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-09-LB-0007-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench | A | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
583 | PL-PS5-00583 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-HS-7002-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled, need to be laid in trench | A | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
584 | PL-PS5-00584 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-1509-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
585 | PL-PS5-00585 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2511-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
586 | PL-PS5-00586 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2205-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
587 | PL-PS5-00587 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-SHSR-0052-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
588 | PL-PS5-00588 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-28-BI-2304-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
589 | PL-PS5-00589 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0001-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
590 | PL-PS5-00590 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0002-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
591 | PL-PS5-00591 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0003-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
592 | PL-PS5-00592 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0004-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
593 | PL-PS5-00593 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0005-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
594 | PL-PS5-00594 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0006-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
595 | PL-PS5-00595 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0007-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
596 | PL-PS5-00596 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0008-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
597 | PL-PS5-00597 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0009-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
598 | PL-PS5-00598 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0010-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
599 | PL-PS5-00599 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0012-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
600 | PL-PS5-00600 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-TIT-2403A-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
601 | PL-PS5-00601 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-TIT-2403B-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
602 | PL-PS5-00602 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1174A-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
603 | PL-PS5-00603 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1174B-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
604 | PL-PS5-00604 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1274B-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
605 | PL-PS5-00605 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-MXS-3101AA-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
606 | PL-PS5-00606 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-MXS-3101BA-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
607 | PL-PS5-00607 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-MXS-3101CA-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
608 | PL-PS5-00608 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-83-EHO-0001A-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
609 | PL-PS5-00609 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-83-EHO-0001B-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
610 | PL-PS5-00610 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-83-EHO-0001C-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
611 | PL-PS5-00611 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-83-EHO-0001A-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
612 | PL-PS5-00612 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-83-EHO-0001B-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
613 | PL-PS5-00613 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-83-EHO-0001C-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
614 | PL-PS5-00614 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1802A-CC02 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
615 | PL-PS5-00615 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1803A-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
616 | PL-PS5-00616 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1803A-CC02 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
617 | PL-PS5-00617 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1801B-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
618 | PL-PS5-00618 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1802B-CC02 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
619 | PL-PS5-00619 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1803B-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
620 | PL-PS5-00620 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1803B-CC02 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
621 | PL-PS5-00621 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1801C-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
622 | PL-PS5-00622 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1802C-CC02 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
623 | PL-PS5-00623 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1803C-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
624 | PL-PS5-00624 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1803C-CC02 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
625 | PL-PS5-00625 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-MXS-3101AB-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
626 | PL-PS5-00626 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-MXS-3101BB-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
627 | PL-PS5-00627 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-MXS-3101CB-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
628 | PL-PS5-00628 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-PIT-0052-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
629 | PL-PS5-00629 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-PIT-0071A-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
630 | PL-PS5-00630 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-PIT-0071B-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
631 | PL-PS5-00631 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-PIT-0071C-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
632 | PL-PS5-00632 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-SDV-0052-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
633 | PL-PS5-00633 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-SXS-0052-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
634 | PL-PS5-00634 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-SY-0052A-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
635 | PL-PS5-00635 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-1506-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
636 | PL-PS5-00636 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-1508-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
637 | PL-PS5-00637 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2504-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
638 | PL-PS5-00638 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-HS-7002-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
639 | PL-PS5-00639 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-RMAC-0120-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
640 | PL-PS5-00640 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2101-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
641 | PL-PS5-00641 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2102-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
642 | PL-PS5-00642 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2101-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
643 | PL-PS5-00643 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0002-CC05 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
644 | PL-PS5-00644 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0002-CC06 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
645 | PL-PS5-00645 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0002-CC07 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
646 | PL-PS5-00646 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0004A-CC08 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
647 | PL-PS5-00647 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0004A-CC09 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
648 | PL-PS5-00648 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0004A-CC12 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
649 | PL-PS5-00649 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0004B-CC08 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
650 | PL-PS5-00650 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0004B-CC09 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
651 | PL-PS5-00651 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0004B-CC12 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
652 | PL-PS5-00652 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1274A-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
653 | PL-PS5-00653 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1274C-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
654 | PL-PS5-00654 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-61-IDH-3100A-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
655 | PL-PS5-00655 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-61-IDH-3100A-CC02 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
656 | PL-PS5-00656 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-61-IDH-3100A-CC03 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
657 | PL-PS5-00657 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-61-IDH-3100B-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
658 | PL-PS5-00658 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1802A-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
659 | PL-PS5-00659 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1802B-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
660 | PL-PS5-00660 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1802C-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
661 | PL-PS5-00661 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-0001-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
662 | PL-PS5-00662 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-0021-CC02 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
663 | PL-PS5-00663 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-SDV-0052-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable dressing not yet done completely | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
664 | PL-PS5-00664 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-1509-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
665 | PL-PS5-00665 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2511-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
666 | PL-PS5-00666 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2205-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
667 | PL-PS5-00667 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-SHSR-0052-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
668 | PL-PS5-00668 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-28-BI-2304-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
669 | PL-PS5-00669 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0001-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
670 | PL-PS5-00670 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0002-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
671 | PL-PS5-00671 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0003-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
672 | PL-PS5-00672 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0004-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
673 | PL-PS5-00673 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0005-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
674 | PL-PS5-00674 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0006-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
675 | PL-PS5-00675 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0007-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
676 | PL-PS5-00676 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0008-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
677 | PL-PS5-00677 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0009-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
678 | PL-PS5-00678 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0010-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
679 | PL-PS5-00679 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-79-IG-0012-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
680 | PL-PS5-00680 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-TIT-2403A-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
681 | PL-PS5-00681 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-TIT-2403B-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
682 | PL-PS5-00682 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1174A-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
683 | PL-PS5-00683 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1174B-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
684 | PL-PS5-00684 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1274B-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
685 | PL-PS5-00685 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-MXS-3101AA-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
686 | PL-PS5-00686 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-MXS-3101BA-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
687 | PL-PS5-00687 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-MXS-3101CA-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
688 | PL-PS5-00688 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-83-EHO-0001A-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
689 | PL-PS5-00689 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-83-EHO-0001B-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
690 | PL-PS5-00690 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-83-EHO-0001C-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
691 | PL-PS5-00691 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-83-EHO-0001A-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
692 | PL-PS5-00692 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-83-EHO-0001B-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
693 | PL-PS5-00693 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-83-EHO-0001C-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
694 | PL-PS5-00694 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1802A-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
695 | PL-PS5-00695 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1803A-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
696 | PL-PS5-00696 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1803A-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
697 | PL-PS5-00697 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1801B-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
698 | PL-PS5-00698 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1802B-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
699 | PL-PS5-00699 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1803B-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
700 | PL-PS5-00700 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1803B-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
701 | PL-PS5-00701 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1801C-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
702 | PL-PS5-00702 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1802C-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
703 | PL-PS5-00703 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1803C-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
704 | PL-PS5-00704 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1803C-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
705 | PL-PS5-00705 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-MXS-3101AB-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
706 | PL-PS5-00706 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-MXS-3101BB-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
707 | PL-PS5-00707 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-MXS-3101CB-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
708 | PL-PS5-00708 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-PIT-0052-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
709 | PL-PS5-00709 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-PIT-0071A-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
710 | PL-PS5-00710 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-PIT-0071B-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
711 | PL-PS5-00711 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-PIT-0071C-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
712 | PL-PS5-00712 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-SDV-0052-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
713 | PL-PS5-00713 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-SXS-0052-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
714 | PL-PS5-00714 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-SY-0052A-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
715 | PL-PS5-00715 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-1506-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
716 | PL-PS5-00716 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-1508-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
717 | PL-PS5-00717 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-BI-2504-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
718 | PL-PS5-00718 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-HS-7002-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
719 | PL-PS5-00719 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-03-RMAC-0120-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
720 | PL-PS5-00720 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2101-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
721 | PL-PS5-00721 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-2102-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
722 | PL-PS5-00722 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-2101-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
723 | PL-PS5-00723 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0002-CC05 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
724 | PL-PS5-00724 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0002-CC06 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
725 | PL-PS5-00725 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0002-CC07 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
726 | PL-PS5-00726 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0004A-CC08 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
727 | PL-PS5-00727 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0004A-CC09 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
728 | PL-PS5-00728 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0004A-CC12 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
729 | PL-PS5-00729 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0004B-CC08 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
730 | PL-PS5-00730 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0004B-CC09 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
731 | PL-PS5-00731 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-IN-0004B-CC12 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
732 | PL-PS5-00732 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1274A-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
733 | PL-PS5-00733 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1274C-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
734 | PL-PS5-00734 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-61-IDH-3100A-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
735 | PL-PS5-00735 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-61-IDH-3100A-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
736 | PL-PS5-00736 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-61-IDH-3100A-CC03 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
737 | PL-PS5-00737 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-61-IDH-3100B-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
738 | PL-PS5-00738 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1802A-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
739 | PL-PS5-00739 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1802B-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
740 | PL-PS5-00740 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-BI-1802C-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
741 | PL-PS5-00741 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-0001-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
742 | PL-PS5-00742 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-71-BI-0021-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
743 | PL-PS5-00743 | #N/A | CPP-RFI-68-64-04-0038 | PS5 | Instrument Cable Installation | Power Distribution Area (EITS Building ) | PS5-25-SDV-0052-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrumentation | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
744 | PL-PS5-00744 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-01-FCV-0003A-CL01 | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
745 | PL-PS5-00745 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-01-FCV-0003B-CL01 | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
746 | PL-PS5-00746 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-01-FCV-0004A-CL01 | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
747 | PL-PS5-00747 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-01-FCV-0004B-CL01 | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
748 | PL-PS5-00748 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-01-IE-0001A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
749 | PL-PS5-00749 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-01-IE-0001B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
750 | PL-PS5-00750 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0137-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
751 | PL-PS5-00751 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0142-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
752 | PL-PS5-00752 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0143-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
753 | PL-PS5-00753 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0144-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
754 | PL-PS5-00754 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0146-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114, 151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
755 | PL-PS5-00755 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0147-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
756 | PL-PS5-00756 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0149-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
757 | PL-PS5-00757 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0150-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
758 | PL-PS5-00758 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0401-CL01 | TZ-MID-68-WPR2-151112, 151111, 151108, 151107-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
759 | PL-PS5-00759 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-05-IE-8100-CD22 | TZ-MID-68-WPR2-151112, 151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
760 | PL-PS5-00760 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-05-IE-8100-CD24 | TZ-MID-68-WPR2-151112, 151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
761 | PL-PS5-00761 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IG-0009-CL01 | TZ-MID-68-WPR2-151167, 151116, 151112, 151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
762 | PL-PS5-00762 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IG-0009-CL02 | TZ-MID-68-WPR2-151167, 151116, 151112, 151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
763 | PL-PS5-00763 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-06-GU-0003A-CD01 | TZ-MID-68-WPR2-151112, 151116, 151118-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
764 | PL-PS5-00764 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-06-GU-0003B-CD01 | TZ-MID-68-WPR2-151112, 151116, 151118-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
765 | PL-PS5-00765 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-06-IG-0004A-CD01 | TZ-MID-68-WPR2-151112, 151116, 151118-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
766 | PL-PS5-00766 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-01FB-0901-CS01 | TZ-MID-68-WPR2-151112, 151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
767 | PL-PS5-00767 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-01FB-1001-CS01 | TZ-MID-68-WPR2-151112, 151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
768 | PL-PS5-00768 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-03FB-0001-CS01 | TZ-MID-68-WPR2-151112, 151111, 151108-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
769 | PL-PS5-00769 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-03FB-0002-CS01 | TZ-MID-68-WPR2-151112, 151111, 151108, 151105-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
770 | PL-PS5-00770 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-03FB-0103-CS01 | TZ-MID-68-WPR2-151112, 151111, 151108, 151107, 151110-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
771 | PL-PS5-00771 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Office Building | PS5-08-12BT-0001-CS01 | TZ-MID-68-WPR2-151106, 151108, 151107, 151105-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
772 | PL-PS5-00772 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-12BT-0104-CS01 | TZ-MID-68-WPR2-151112, 151111, 151108, 151107-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
773 | PL-PS5-00773 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-12BT-0105-CS01 | TZ-MID-68-WPR2-151112, 151111, 151108-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
774 | PL-PS5-00774 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-12BT-0106-CS01 | TZ-MID-68-WPR2-151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
775 | PL-PS5-00775 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-15CP-0002-CS01 | TZ-MID-68-WPR2-151119,151107, 151108, 151111, 151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
776 | PL-PS5-00776 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-52BT-0132-CS01 | TZ-MID-68-WPR2-151112, 151111, 151108, 151110-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
777 | PL-PS5-00777 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-52BT-0133-CS01 | TZ-MID-68-WPR2-151112, 151111, 151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
778 | PL-PS5-00778 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-52BT-0139-CS01 | TZ-MID-68-WPR2-151112, 151120, 151122, 151121-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
779 | PL-PS5-00779 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-85CP-0024-CS01 | TZ-MID-68-WPR2-151112, 151120, 151122-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
780 | PL-PS5-00780 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-85CP-0025-CS01 | TZ-MID-68-WPR2-151112, 151120, 151122-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
781 | PL-PS5-00781 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-25-DM-3100A-CL01 | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
782 | PL-PS5-00782 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near EITS | PS5-25-DM-3100A-CL02 | TZ-MID-68-WPR2-151111, 151115, 151117, 151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
783 | PL-PS5-00783 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-25-DM-3100B-CL01 | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
784 | PL-PS5-00784 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near EITS | PS5-25-DM-3100B-CL02 | TZ-MID-68-WPR2-151111, 151115, 151117, 151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
785 | PL-PS5-00785 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-25-DM-3100C-CL01 | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
786 | PL-PS5-00786 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near EITS | PS5-25-DM-3100C-CL02 | TZ-MID-68-WPR2-151111, 151115, 151117, 151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
787 | PL-PS5-00787 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-3200A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
788 | PL-PS5-00788 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-3200B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
789 | PL-PS5-00789 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-3300A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
790 | PL-PS5-00790 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-3300B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
791 | PL-PS5-00791 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-3400A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
792 | PL-PS5-00792 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-3400B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
793 | PL-PS5-00793 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-6400A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
794 | PL-PS5-00794 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-6400B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
795 | PL-PS5-00795 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-6500A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
796 | PL-PS5-00796 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-6500B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
797 | PL-PS5-00797 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-6600A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
798 | PL-PS5-00798 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-6600B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
799 | PL-PS5-00799 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-FIT-0001-CL01 | TZ-MID-68-WPR2-151112,151111,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
800 | PL-PS5-00800 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-FIT-0003A-CL01 | TZ-MID-68-WPR2-151112,151111,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
801 | PL-PS5-00801 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-FIT-0003B-CL01 | TZ-MID-68-WPR2-151112,151111,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
802 | PL-PS5-00802 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-FIT-0003C-CL01 | TZ-MID-68-WPR2-151112,151111,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
803 | PL-PS5-00803 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-FIT-0004-CL01 | TZ-MID-68-WPR2-151112,151111,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
804 | PL-PS5-00804 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-HE-2100-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
805 | PL-PS5-00805 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-HE-2100-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
806 | PL-PS5-00806 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-HE-2200-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
807 | PL-PS5-00807 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-HE-2200-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
808 | PL-PS5-00808 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-HE-2300-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
809 | PL-PS5-00809 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-HE-2300-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
810 | PL-PS5-00810 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-25-IES-3100A-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
811 | PL-PS5-00811 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-25-IES-3100B-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
812 | PL-PS5-00812 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-25-IES-3100C-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
813 | PL-PS5-00813 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-3200A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
814 | PL-PS5-00814 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-3200B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
815 | PL-PS5-00815 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-3300A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
816 | PL-PS5-00816 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-3300B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
817 | PL-PS5-00817 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-3400A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
818 | PL-PS5-00818 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-3400B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
819 | PL-PS5-00819 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-6400A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
820 | PL-PS5-00820 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-6400B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
821 | PL-PS5-00821 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-6500A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
822 | PL-PS5-00822 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-6500B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
823 | PL-PS5-00823 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-6600A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
824 | PL-PS5-00824 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-6600B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
825 | PL-PS5-00825 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-MOV-0001-CL01 | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
826 | PL-PS5-00826 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-MOV-0002-CL01 | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
827 | PL-PS5-00827 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-MOV-0003-CL01 | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
828 | PL-PS5-00828 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-MOV-0011-CL01 | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
829 | PL-PS5-00829 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-MOV-0012-CL01 | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
830 | PL-PS5-00830 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-MOV-0027-CL01 | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
831 | PL-PS5-00831 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-MOV-0028-CL01 | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
832 | PL-PS5-00832 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-SDV-0022-CL01 | TZ-MID-68-WPR2-151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
833 | PL-PS5-00833 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-SDV-0035A-CL01 | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
834 | PL-PS5-00834 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-SDV-0035B-CL01 | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
835 | PL-PS5-00835 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-SDV-0035C-CL01 | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
836 | PL-PS5-00836 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-SDV-0036A-CL01 | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
837 | PL-PS5-00837 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-SDV-0036B-CL01 | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
838 | PL-PS5-00838 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-SDV-0036C-CL01 | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
839 | PL-PS5-00839 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-SDV-0052-CL01 | TZ-MID-68-WPR2-151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
840 | PL-PS5-00840 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-UD-3100A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
841 | PL-PS5-00841 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IDH-3100A-CD01 | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
842 | PL-PS5-00842 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IDH-3100A-CD02 | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
843 | PL-PS5-00843 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IDH-3100B-CD01 | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
844 | PL-PS5-00844 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IDH-3100C-CD01 | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
845 | PL-PS5-00845 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IDH-3100C-CD02 | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
846 | PL-PS5-00846 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IG-0012A-CL01 | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
847 | PL-PS5-00847 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IG-0012B-CL01 | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
848 | PL-PS5-00848 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IG-0012C-CL01 | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
849 | PL-PS5-00849 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-61-IJ-0001-CD24 | TZ-MID-68-WPR2-151111,151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
850 | PL-PS5-00850 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-61-IJ-0001-CD25 | TZ-MID-68-WPR2-151111,151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
851 | PL-PS5-00851 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-61-IJ-0001-CD26 | TZ-MID-68-WPR2-151111,151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
852 | PL-PS5-00852 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near EDG | PS5-61-IK-0003-CL44 | TZ-MID-68-WPR2-151111, 151112, 151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
853 | PL-PS5-00853 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near EDG | PS5-61-IK-0003-CL57 | TZ-MID-68-WPR2-151111, 151112, 151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
854 | PL-PS5-00854 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near EDG | PS5-61-IK-0003-CL58 | TZ-MID-68-WPR2-151111, 151112, 151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
855 | PL-PS5-00855 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near EDG | PS5-61-IK-0003-CL59 | TZ-MID-68-WPR2-151111, 151112, 151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
856 | PL-PS5-00856 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near EDG | PS5-61-IK-0003-CL60 | TZ-MID-68-WPR2-151111, 151112, 151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
857 | PL-PS5-00857 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IV-0006A-CL01 | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
858 | PL-PS5-00858 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IV-0006C-CL01 | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
859 | PL-PS5-00859 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-01-FCV-0003A-CL01 | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
860 | PL-PS5-00860 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-01-FCV-0003B-CL01 | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
861 | PL-PS5-00861 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-01-FCV-0004A-CL01 | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
862 | PL-PS5-00862 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-01-FCV-0004B-CL01 | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
863 | PL-PS5-00863 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-01-IE-0001A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
864 | PL-PS5-00864 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-01-IE-0001B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
865 | PL-PS5-00865 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0137-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
866 | PL-PS5-00866 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0142-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
867 | PL-PS5-00867 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0143-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
868 | PL-PS5-00868 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0144-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
869 | PL-PS5-00869 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0146-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114, 151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
870 | PL-PS5-00870 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0147-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
871 | PL-PS5-00871 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0149-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
872 | PL-PS5-00872 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0150-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
873 | PL-PS5-00873 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-03-GDLHP-0401-CL01 | TZ-MID-68-WPR2-151112, 151111, 151108, 151107-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
874 | PL-PS5-00874 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-05-IE-8100-CD22 | TZ-MID-68-WPR2-151112, 151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
875 | PL-PS5-00875 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-05-IE-8100-CD24 | TZ-MID-68-WPR2-151112, 151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
876 | PL-PS5-00876 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IG-0009-CL01 | TZ-MID-68-WPR2-151167, 151116, 151112, 151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
877 | PL-PS5-00877 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IG-0009-CL02 | TZ-MID-68-WPR2-151167, 151116, 151112, 151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
878 | PL-PS5-00878 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-06-GU-0003A-CD01 | TZ-MID-68-WPR2-151112, 151116, 151118-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
879 | PL-PS5-00879 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-06-GU-0003B-CD01 | TZ-MID-68-WPR2-151112, 151116, 151118-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
880 | PL-PS5-00880 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-06-IG-0004A-CD01 | TZ-MID-68-WPR2-151112, 151116, 151118-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
881 | PL-PS5-00881 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-01FB-0901-CS01 | TZ-MID-68-WPR2-151112, 151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
882 | PL-PS5-00882 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-01FB-1001-CS01 | TZ-MID-68-WPR2-151112, 151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
883 | PL-PS5-00883 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-03FB-0001-CS01 | TZ-MID-68-WPR2-151112, 151111, 151108-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
884 | PL-PS5-00884 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-03FB-0002-CS01 | TZ-MID-68-WPR2-151112, 151111, 151108, 151105-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
885 | PL-PS5-00885 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-03FB-0103-CS01 | TZ-MID-68-WPR2-151112, 151111, 151108, 151107, 151110-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
886 | PL-PS5-00886 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Office Building | PS5-08-12BT-0001-CS01 | TZ-MID-68-WPR2-151106, 151108, 151107, 151105-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
887 | PL-PS5-00887 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-12BT-0104-CS01 | TZ-MID-68-WPR2-151112, 151111, 151108, 151107-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
888 | PL-PS5-00888 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-12BT-0105-CS01 | TZ-MID-68-WPR2-151112, 151111, 151108-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
889 | PL-PS5-00889 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-12BT-0106-CS01 | TZ-MID-68-WPR2-151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
890 | PL-PS5-00890 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-15CP-0002-CS01 | TZ-MID-68-WPR2-151119,151107, 151108, 151111, 151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
891 | PL-PS5-00891 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-52BT-0132-CS01 | TZ-MID-68-WPR2-151112, 151111, 151108, 151110-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
892 | PL-PS5-00892 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-52BT-0133-CS01 | TZ-MID-68-WPR2-151112, 151111, 151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
893 | PL-PS5-00893 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-52BT-0139-CS01 | TZ-MID-68-WPR2-151112, 151120, 151122, 151121-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
894 | PL-PS5-00894 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-85CP-0024-CS01 | TZ-MID-68-WPR2-151112, 151120, 151122-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
895 | PL-PS5-00895 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-08-85CP-0025-CS01 | TZ-MID-68-WPR2-151112, 151120, 151122-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
896 | PL-PS5-00896 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-25-DM-3100A-CL01 | TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
897 | PL-PS5-00897 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near EITS | PS5-25-DM-3100A-CL02 | TZ-MID-68-WPR2-151111, 151115, 151117, 151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
898 | PL-PS5-00898 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-25-DM-3100B-CL01 | TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
899 | PL-PS5-00899 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near EITS | PS5-25-DM-3100B-CL02 | TZ-MID-68-WPR2-151111, 151115, 151117, 151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
900 | PL-PS5-00900 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-25-DM-3100C-CL01 | TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
901 | PL-PS5-00901 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near EITS | PS5-25-DM-3100C-CL02 | TZ-MID-68-WPR2-151111, 151115, 151117, 151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
902 | PL-PS5-00902 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-3200A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
903 | PL-PS5-00903 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-3200B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
904 | PL-PS5-00904 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-3300A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
905 | PL-PS5-00905 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-3300B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
906 | PL-PS5-00906 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-3400A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
907 | PL-PS5-00907 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-3400B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
908 | PL-PS5-00908 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-6400A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
909 | PL-PS5-00909 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-6400B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
910 | PL-PS5-00910 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-6500A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
911 | PL-PS5-00911 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-6500B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
912 | PL-PS5-00912 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-6600A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
913 | PL-PS5-00913 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-DM-6600B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
914 | PL-PS5-00914 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-FIT-0001-CL01 | TZ-MID-68-WPR2-151112,151111,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
915 | PL-PS5-00915 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-FIT-0003A-CL01 | TZ-MID-68-WPR2-151112,151111,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
916 | PL-PS5-00916 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-FIT-0003B-CL01 | TZ-MID-68-WPR2-151112,151111,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
917 | PL-PS5-00917 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-FIT-0003C-CL01 | TZ-MID-68-WPR2-151112,151111,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
918 | PL-PS5-00918 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-FIT-0004-CL01 | TZ-MID-68-WPR2-151112,151111,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
919 | PL-PS5-00919 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-HE-2100-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
920 | PL-PS5-00920 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-HE-2100-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
921 | PL-PS5-00921 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-HE-2200-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
922 | PL-PS5-00922 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-HE-2200-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
923 | PL-PS5-00923 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-HE-2300-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
924 | PL-PS5-00924 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-HE-2300-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
925 | PL-PS5-00925 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-25-IES-3100A-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
926 | PL-PS5-00926 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-25-IES-3100B-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
927 | PL-PS5-00927 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-25-IES-3100C-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
928 | PL-PS5-00928 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-3200A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
929 | PL-PS5-00929 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-3200B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
930 | PL-PS5-00930 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-3300A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
931 | PL-PS5-00931 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-3300B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
932 | PL-PS5-00932 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-3400A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
933 | PL-PS5-00933 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-3400B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
934 | PL-PS5-00934 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-6400A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
935 | PL-PS5-00935 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-6400B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
936 | PL-PS5-00936 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-6500A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
937 | PL-PS5-00937 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-6500B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
938 | PL-PS5-00938 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-6600A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
939 | PL-PS5-00939 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-IES-6600B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
940 | PL-PS5-00940 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-MOV-0001-CL01 | TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
941 | PL-PS5-00941 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-MOV-0002-CL01 | TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
942 | PL-PS5-00942 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-MOV-0003-CL01 | TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
943 | PL-PS5-00943 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-MOV-0011-CL01 | TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
944 | PL-PS5-00944 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-MOV-0012-CL01 | TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
945 | PL-PS5-00945 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-MOV-0027-CL01 | TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
946 | PL-PS5-00946 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-MOV-0028-CL01 | TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
947 | PL-PS5-00947 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-SDV-0022-CL01 | TZ-MID-68-WPR2-151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
948 | PL-PS5-00948 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-SDV-0035A-CL01 | TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
949 | PL-PS5-00949 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-SDV-0035B-CL01 | TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
950 | PL-PS5-00950 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-SDV-0035C-CL01 | TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
951 | PL-PS5-00951 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-SDV-0036A-CL01 | TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
952 | PL-PS5-00952 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-SDV-0036B-CL01 | TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
953 | PL-PS5-00953 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-SDV-0036C-CL01 | TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
954 | PL-PS5-00954 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-25-SDV-0052-CL01 | TZ-MID-68-WPR2-151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
955 | PL-PS5-00955 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-25-UD-3100A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
956 | PL-PS5-00956 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IDH-3100A-CD01 | TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
957 | PL-PS5-00957 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IDH-3100A-CD02 | TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
958 | PL-PS5-00958 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IDH-3100B-CD01 | TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
959 | PL-PS5-00959 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IDH-3100C-CD01 | TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
960 | PL-PS5-00960 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IDH-3100C-CD02 | TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
961 | PL-PS5-00961 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IG-0012A-CL01 | TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
962 | PL-PS5-00962 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IG-0012B-CL01 | TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
963 | PL-PS5-00963 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IG-0012C-CL01 | TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
964 | PL-PS5-00964 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-61-IJ-0001-CD24 | TZ-MID-68-WPR2-151111,151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
965 | PL-PS5-00965 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-61-IJ-0001-CD25 | TZ-MID-68-WPR2-151111,151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
966 | PL-PS5-00966 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | VSD E-house | PS5-61-IJ-0001-CD26 | TZ-MID-68-WPR2-151111,151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
967 | PL-PS5-00967 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near EDG | PS5-61-IK-0003-CL44 | TZ-MID-68-WPR2-151111, 151112, 151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
968 | PL-PS5-00968 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near EDG | PS5-61-IK-0003-CL57 | TZ-MID-68-WPR2-151111, 151112, 151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
969 | PL-PS5-00969 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near EDG | PS5-61-IK-0003-CL58 | TZ-MID-68-WPR2-151111, 151112, 151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
970 | PL-PS5-00970 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near EDG | PS5-61-IK-0003-CL59 | TZ-MID-68-WPR2-151111, 151112, 151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
971 | PL-PS5-00971 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | Near EDG | PS5-61-IK-0003-CL60 | TZ-MID-68-WPR2-151111, 151112, 151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
972 | PL-PS5-00972 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IV-0006A-CL01 | TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
973 | PL-PS5-00973 | #N/A | CPP-RFI-68-33/1-05-0215 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IV-0006C-CL01 | TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
974 | PL-PS5-00974 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | FIRE WATER PUMP AREA | PS5-01-FCV-0004A-CL01 | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
975 | PL-PS5-00975 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | FIRE WATER PUMP AREA | PS5-01-FCV-0004B-CL01 | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
976 | PL-PS5-00976 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-05-IG-0004-CD01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
977 | PL-PS5-00977 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-05-IG-0004-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
978 | PL-PS5-00978 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near EDG package | PS5-05-IG-0006-CD01 | TZ-MID-68-WPR2-151112, 151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
979 | PL-PS5-00979 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near EDG package | PS5-05-IG-0006-CL01 | TZ-MID-68-WPR2-151112, 151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
980 | PL-PS5-00980 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Reinjection Pump | PS5-28-BE-0002A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
981 | PL-PS5-00981 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Reinjection Pump | PS5-28-BE-0002B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
982 | PL-PS5-00982 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Relief Drum Area | PS5-28-DM-3300-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
983 | PL-PS5-00983 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Oily Water Sump Pump Area | PS5-28-DM-3500-CL01 | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
984 | PL-PS5-00984 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Oily Water Sump Pump Area | PS5-28-DM-3600A-CL01 | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
985 | PL-PS5-00985 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Oily Water Sump Pump Area | PS5-28-DM-3600A-CL02 | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
986 | PL-PS5-00986 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Oily Water Sump Pump Area | PS5-28-DM-3600B-CL01 | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
987 | PL-PS5-00987 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Oily Water Sump Pump Area | PS5-28-DM-3600B-CL02 | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
988 | PL-PS5-00988 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-DM-3700B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
989 | PL-PS5-00989 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Export pump area | PS5-28-DM-3800A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
990 | PL-PS5-00990 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Export pump area | PS5-28-DM-3800B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
991 | PL-PS5-00991 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Export pump area | PS5-28-DM-3800C-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
992 | PL-PS5-00992 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-HE-2100-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
993 | PL-PS5-00993 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-HE-2100-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
994 | PL-PS5-00994 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-HE-2200-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151118-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
995 | PL-PS5-00995 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-HE-2200-CL02 | TZ-MID-68-WPR2-151111,151115,151118-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
996 | PL-PS5-00996 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Oil skimmer package | PS5-28-IES-2008-CD01 | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
997 | PL-PS5-00997 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Relief Drum Area | PS5-28-IES-3300-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
998 | PL-PS5-00998 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-IES-3400-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
999 | PL-PS5-00999 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Oily Water Area | PS5-28-IES-3500-CD01 | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1000 | PL-PS5-01000 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Oily Water Area | PS5-28-IES-3600B-CD01 | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1001 | PL-PS5-01001 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-IES-3700B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1002 | PL-PS5-01002 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Export pump area | PS5-28-IES-3800A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1003 | PL-PS5-01003 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Export pump area | PS5-28-IES-3800B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1004 | PL-PS5-01004 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Export pump area | PS5-28-IES-3800C-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1005 | PL-PS5-01005 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-IES-3900A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1006 | PL-PS5-01006 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-IES-3900B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1007 | PL-PS5-01007 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Observation Basin | PS5-28-ISO-2008-CL01 | TZ-MID-68-WPR2-151112,151108,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1008 | PL-PS5-01008 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | OPERATION AND MAINTENANCE AREA | PS5-28-LB-8200-CL01 | TZ-MID-68-WPR2-151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1009 | PL-PS5-01009 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Submerssiblre pump | PS5-50-IE-0001-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151119-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1010 | PL-PS5-01010 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Submerssiblre pump | PS5-50-IE-0002-CL01 | TZ-MID-68-WPR2-151112,151111,151108,151107,151105-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1011 | PL-PS5-01011 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Water Treatment Pre Package | PS5-53-IN-0001-CL01 | TZ-MID-68-WPR2-151112,151111,151108,151109-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1012 | PL-PS5-01012 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Deluge skid Area | PS5-60-DM-3300-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1013 | PL-PS5-01013 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CD06 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1014 | PL-PS5-01014 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CD08 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1015 | PL-PS5-01015 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CD12 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1016 | PL-PS5-01016 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD06 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1017 | PL-PS5-01017 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD08 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1018 | PL-PS5-01018 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD12 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1019 | PL-PS5-01019 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003C-CD06 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1020 | PL-PS5-01020 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003C-CD08 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1021 | PL-PS5-01021 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003C-CD12 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1022 | PL-PS5-01022 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003D-CD06 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1023 | PL-PS5-01023 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003D-CD08 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1024 | PL-PS5-01024 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003D-CD12 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1025 | PL-PS5-01025 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003E-CD12 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1026 | PL-PS5-01026 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003F-CD06 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1027 | PL-PS5-01027 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003F-CD08 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1028 | PL-PS5-01028 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003G-CD06 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1029 | PL-PS5-01029 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003G-CD08 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1030 | PL-PS5-01030 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003G-CD12 | TZ-MID-68-WPR2-151112, 151116, 151167-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1031 | PL-PS5-01031 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0004-CD01 | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1032 | PL-PS5-01032 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0004-CD02 | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1033 | PL-PS5-01033 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Deluge skid Area | PS5-60-IES-3300-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1034 | PL-PS5-01034 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-BI-0001-CL01 | TZ-MID-68-WPR2-151118,151116,151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1035 | PL-PS5-01035 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-BI-0002-CL01 | TZ-MID-68-WPR2-151118,151116,151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1036 | PL-PS5-01036 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-BI-0003-CL01 | TZ-MID-68-WPR2-151118,151116,151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1037 | PL-PS5-01037 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-BI-0004-CL01 | TZ-MID-68-WPR2-151116,151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1038 | PL-PS5-01038 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-BI-0005-CL01 | TZ-MID-68-WPR2-151116,151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1039 | PL-PS5-01039 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-BI-0006-CL01 | TZ-MID-68-WPR2-151116,151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1040 | PL-PS5-01040 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD01 | TZ-MID-68-WPR2-151105,151107,151108,151111,151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1041 | PL-PS5-01041 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Export pump area | PS5-61-IG-0006-CD01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1042 | PL-PS5-01042 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Export pump area | PS5-61-IG-0006-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1043 | PL-PS5-01043 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near EDG package | PS5-61-IG-0007-CD01 | TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1044 | PL-PS5-01044 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near EDG package | PS5-61-IG-0007-CL01 | TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1045 | PL-PS5-01045 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near EITS | PS5-61-IG-0014-CD01 | TZ-MID-68-WPR2-151112, 151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1046 | PL-PS5-01046 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near EITS | PS5-61-IG-0014-CL01 | TZ-MID-68-WPR2-151112, 151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1047 | PL-PS5-01047 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-IG-0015-CD01 | TZ-MID-68-WPR2-151112, 151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1048 | PL-PS5-01048 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-61-IG-0042-CD01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1049 | PL-PS5-01049 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-61-IG-0042-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1050 | PL-PS5-01050 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-61-IG-0043-CD01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1051 | PL-PS5-01051 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD03 | TZ-MID-68-WPR2-151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1052 | PL-PS5-01052 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD27 | TZ-MID-68-WPR2-151116, 151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1053 | PL-PS5-01053 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD28 | TZ-MID-68-WPR2-151116, 151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1054 | PL-PS5-01054 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD29 | TZ-MID-68-WPR2-151116, 151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1055 | PL-PS5-01055 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD30 | TZ-MID-68-WPR2-151116, 151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1056 | PL-PS5-01056 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD36 | TZ-MID-68-WPR2-151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1057 | PL-PS5-01057 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD41 | TZ-MID-68-WPR2-151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1058 | PL-PS5-01058 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL31 | TZ-MID-68-WPR2-151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1059 | PL-PS5-01059 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL32 | TZ-MID-68-WPR2-151112-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1060 | PL-PS5-01060 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL37 | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1061 | PL-PS5-01061 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL38 | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1062 | PL-PS5-01062 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL39 | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1063 | PL-PS5-01063 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL40 | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1064 | PL-PS5-01064 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL41 | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1065 | PL-PS5-01065 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL42 | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1066 | PL-PS5-01066 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL43 | TZ-MID-68-WPR2-151112,151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1067 | PL-PS5-01067 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL15 | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1068 | PL-PS5-01068 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL25 | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1069 | PL-PS5-01069 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL26 | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1070 | PL-PS5-01070 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL27 | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1071 | PL-PS5-01071 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL28 | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1072 | PL-PS5-01072 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL29 | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1073 | PL-PS5-01073 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL23 | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1074 | PL-PS5-01074 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL24 | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1075 | PL-PS5-01075 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL25 | TZ-MID-68-WPR2-151116-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1076 | PL-PS5-01076 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near EDG package | PS5-62-IE-0002-CD01 | TZ-MID-68-WPR2-151112,151111-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1077 | PL-PS5-01077 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Fuel Pump Area | PS5-71-DM-3100A-CL01 | TZ-MID-68-WPR2-151112,151111,151108,151107-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1078 | PL-PS5-01078 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Fuel Pump Area | PS5-71-DM-3100B-CL01 | TZ-MID-68-WPR2-151112,151111,151108,151107-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1079 | PL-PS5-01079 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Fuel Pump Area | PS5-71-DM-3200-CL01 | TZ-MID-68-WPR2-151112,151111,151108,151107-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1080 | PL-PS5-01080 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Pump Area | PS5-71-DM-3300A-CL01 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1081 | PL-PS5-01081 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Pump Area | PS5-71-DM-3300B-CL01 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1082 | PL-PS5-01082 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Pump Area | PS5-71-DM-3400A-CL01 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1083 | PL-PS5-01083 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Pump Area | PS5-71-DM-3400B-CL01 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1084 | PL-PS5-01084 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Day Fuel Day Drum Area | PS5-71-DM-3500A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1085 | PL-PS5-01085 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Day Fuel Day Drum Area | PS5-71-DM-3500B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1086 | PL-PS5-01086 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | DIESEL FUEL DAY DRUM | PS5-71-FCV-0019-CL01 | TZ-MID-68-WPR2-151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1087 | PL-PS5-01087 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO STORAGE TANK AREA | PS5-71-FIT-0011A-CL01 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1088 | PL-PS5-01088 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO STORAGE TANK AREA | PS5-71-FIT-0011B-CL01 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1089 | PL-PS5-01089 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Service tank area | PS5-71-HE-2200-CL01 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1090 | PL-PS5-01090 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2300-CL01 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1091 | PL-PS5-01091 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2300-CL02 | TZ-MID-68-WPR2-151117,151114,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1092 | PL-PS5-01092 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2400A-CL03 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1093 | PL-PS5-01093 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2400A-CL04 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1094 | PL-PS5-01094 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2400B-CL01 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1095 | PL-PS5-01095 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2400B-CL02 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1096 | PL-PS5-01096 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2400B-CL03 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1097 | PL-PS5-01097 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2400B-CL04 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1098 | PL-PS5-01098 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Fuel Pump Area | PS5-71-IES-3100A-CD01 | TZ-MID-68-WPR2-151112,151111,151108.151107-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1099 | PL-PS5-01099 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Fuel Pump Area | PS5-71-IES-3100B-CD01 | TZ-MID-68-WPR2-151112,151111,151108.151107-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1100 | PL-PS5-01100 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Fuel Pump Area | PS5-71-IES-3200-CD01 | TZ-MID-68-WPR2-151112,151111,151108,151107-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1101 | PL-PS5-01101 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Pump Area | PS5-71-IES-3300A-CD01 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1102 | PL-PS5-01102 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Pump Area | PS5-71-IES-3300B-CD01 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1103 | PL-PS5-01103 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Pump Area | PS5-71-IES-3400A-CD01 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1104 | PL-PS5-01104 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Pump Area | PS5-71-IES-3400B-CD01 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1105 | PL-PS5-01105 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel fuel day drum area | PS5-71-IES-3500A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1106 | PL-PS5-01106 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel fuel day drum area | PS5-71-IES-3500B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1107 | PL-PS5-01107 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0001-CL01 | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1108 | PL-PS5-01108 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0002-CL01 | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1109 | PL-PS5-01109 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0003-CL01 | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1110 | PL-PS5-01110 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0004-CL01 | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1111 | PL-PS5-01111 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0009-CL01 | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1112 | PL-PS5-01112 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0010-CL01 | TZ-MID-68-WPR2-151117,151118-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1113 | PL-PS5-01113 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | DIESEL FUEL DAY DRUM | PS5-71-SDV-0001-CL01 | TZ-MID-68-WPR2-151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1114 | PL-PS5-01114 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | DIESEL FUEL STORAGE AREA | PS5-71-SDV-0029-CL01 | TZ-MID-68-WPR2-151117,151115,151111,151108,151107-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1115 | PL-PS5-01115 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Fuel Dispenser Station | PS5-71-UZ-6200-CL01 | TZ-MID-68-WPR2-151112, 151111, 151108, 151107-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1116 | PL-PS5-01116 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | DIESEL FUEL DAY DRUM ARE | PS5-71-XV-0092-CL01 | TZ-MID-68-WPR2-151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1117 | PL-PS5-01117 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Nitrogen Generation Skid | PS5-74-IG-5101-CL01 | TZ-MID-68-WPR2-151112,151111,151108-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1118 | PL-PS5-01118 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Nitrogen Generation Skid | PS5-74-LB-5101-CL02 | TZ-MID-68-WPR2-151167,151116,151112,151111,151108-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1119 | PL-PS5-01119 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near DRA injection package | PS5-75-DM-3100A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1120 | PL-PS5-01120 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near DRA injection package | PS5-75-DM-3100B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1121 | PL-PS5-01121 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near DRA injection package | PS5-75-DM-3200A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1122 | PL-PS5-01122 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near DRA injection package | PS5-75-DM-3200B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1123 | PL-PS5-01123 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near DRA injection package | PS5-75-IES-3100A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1124 | PL-PS5-01124 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near DRA injection package | PS5-75-IES-3100B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1125 | PL-PS5-01125 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near DRA injection package | PS5-75-IES-3200A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1126 | PL-PS5-01126 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near DRA injection package | PS5-75-IES-3200B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1127 | PL-PS5-01127 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Field_DRA injection package | PS5-75-ISO-0001-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1128 | PL-PS5-01128 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Field_DRA injection package | PS5-75-ISO-0002-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114,151113-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1129 | PL-PS5-01129 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near CFO Service Pump area | PS5-79-IV-0001-CL01 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1130 | PL-PS5-01130 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near CFO Service Pump area | PS5-79-IV-0002-CL01 | TZ-MID-68-WPR2-151112,151111,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1131 | PL-PS5-01131 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Diesel Fuel Day Tank Area | PS5-79-IV-0003-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1132 | PL-PS5-01132 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Diesel Fuel Day Tank Area | PS5-79-IV-0004-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1133 | PL-PS5-01133 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Diesel Fuel Day Tank Area | PS5-79-IV-0005-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1134 | PL-PS5-01134 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export Pump Area | PS5-79-IV-0006-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1135 | PL-PS5-01135 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export Pump Area | PS5-79-IV-0007-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1136 | PL-PS5-01136 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export Pump Area | PS5-79-IV-0008-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1137 | PL-PS5-01137 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export Pump Area | PS5-79-IV-0009-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1138 | PL-PS5-01138 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export Pump Area | PS5-79-IV-0010-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1139 | PL-PS5-01139 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Sewage Treatment Pkge -North w | PS5-82-IN-0001-CL01 | TZ-MID-68-WPR2-151112,151111,151108,151107,151105-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1140 | PL-PS5-01140 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Area | PS5-87-IRF-0002-CL01 | TZ-MID-68-WPR2-151117,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1141 | PL-PS5-01141 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Area | PS5-87-IRF-0003-CL01 | TZ-MID-68-WPR2-151117,151115-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1142 | PL-PS5-01142 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel fuel tank Area | PS5-87-IRF-0004-CL01 | TZ-MID-68-WPR2-151111,151108,151107-Cable dressing not yet done completely | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1143 | PL-PS5-01143 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | FIRE WATER PUMP AREA | PS5-01-FCV-0004A-CL01 | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2026 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1144 | PL-PS5-01144 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | FIRE WATER PUMP AREA | PS5-01-FCV-0004B-CL01 | TZ-MID-68-WPR2-151117,151115,151111,151108,151109-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2026 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1145 | PL-PS5-01145 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-05-IG-0004-CD01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1146 | PL-PS5-01146 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-05-IG-0004-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1147 | PL-PS5-01147 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near EDG package | PS5-05-IG-0006-CD01 | TZ-MID-68-WPR2-151112, 151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1148 | PL-PS5-01148 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near EDG package | PS5-05-IG-0006-CL01 | TZ-MID-68-WPR2-151112, 151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1149 | PL-PS5-01149 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Reinjection Pump | PS5-28-BE-0002A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1150 | PL-PS5-01150 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Reinjection Pump | PS5-28-BE-0002B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1151 | PL-PS5-01151 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Relief Drum Area | PS5-28-DM-3300-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1152 | PL-PS5-01152 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Oily Water Sump Pump Area | PS5-28-DM-3500-CL01 | TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1153 | PL-PS5-01153 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Oily Water Sump Pump Area | PS5-28-DM-3600A-CL01 | TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1154 | PL-PS5-01154 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Oily Water Sump Pump Area | PS5-28-DM-3600A-CL02 | TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1155 | PL-PS5-01155 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Oily Water Sump Pump Area | PS5-28-DM-3600B-CL01 | TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1156 | PL-PS5-01156 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Oily Water Sump Pump Area | PS5-28-DM-3600B-CL02 | TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1157 | PL-PS5-01157 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-DM-3700B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1158 | PL-PS5-01158 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Export pump area | PS5-28-DM-3800A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1159 | PL-PS5-01159 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Export pump area | PS5-28-DM-3800B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1160 | PL-PS5-01160 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Export pump area | PS5-28-DM-3800C-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1161 | PL-PS5-01161 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-HE-2100-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2027 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1162 | PL-PS5-01162 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-HE-2100-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2028 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1163 | PL-PS5-01163 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-HE-2200-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151118-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1164 | PL-PS5-01164 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-HE-2200-CL02 | TZ-MID-68-WPR2-151111,151115,151118-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2029 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1165 | PL-PS5-01165 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Oil skimmer package | PS5-28-IES-2008-CD01 | TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1166 | PL-PS5-01166 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Relief Drum Area | PS5-28-IES-3300-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1167 | PL-PS5-01167 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-IES-3400-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2030 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1168 | PL-PS5-01168 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Oily Water Area | PS5-28-IES-3500-CD01 | TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1169 | PL-PS5-01169 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Oily Water Area | PS5-28-IES-3600B-CD01 | TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1170 | PL-PS5-01170 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-IES-3700B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1171 | PL-PS5-01171 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Export pump area | PS5-28-IES-3800A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1172 | PL-PS5-01172 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Export pump area | PS5-28-IES-3800B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1173 | PL-PS5-01173 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Export pump area | PS5-28-IES-3800C-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1174 | PL-PS5-01174 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-IES-3900A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1175 | PL-PS5-01175 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-IES-3900B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1176 | PL-PS5-01176 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Observation Basin | PS5-28-ISO-2008-CL01 | TZ-MID-68-WPR2-151112,151108,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1177 | PL-PS5-01177 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | OPERATION AND MAINTENANCE AREA | PS5-28-LB-8200-CL01 | TZ-MID-68-WPR2-151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1178 | PL-PS5-01178 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Submerssiblre pump | PS5-50-IE-0001-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151119-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1179 | PL-PS5-01179 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Submerssiblre pump | PS5-50-IE-0002-CL01 | TZ-MID-68-WPR2-151112,151111,151108,151107,151105-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1180 | PL-PS5-01180 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Water Treatment Pre Package | PS5-53-IN-0001-CL01 | TZ-MID-68-WPR2-151112,151111,151108,151109-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1181 | PL-PS5-01181 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Deluge skid Area | PS5-60-DM-3300-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2031 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1182 | PL-PS5-01182 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CD06 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1183 | PL-PS5-01183 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CD08 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1184 | PL-PS5-01184 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CD12 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1185 | PL-PS5-01185 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD06 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1186 | PL-PS5-01186 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD08 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1187 | PL-PS5-01187 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD12 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1188 | PL-PS5-01188 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003C-CD06 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1189 | PL-PS5-01189 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003C-CD08 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1190 | PL-PS5-01190 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003C-CD12 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1191 | PL-PS5-01191 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003D-CD06 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1192 | PL-PS5-01192 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003D-CD08 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1193 | PL-PS5-01193 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003D-CD12 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1194 | PL-PS5-01194 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003E-CD12 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1195 | PL-PS5-01195 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003F-CD06 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1196 | PL-PS5-01196 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003F-CD08 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1197 | PL-PS5-01197 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003G-CD06 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1198 | PL-PS5-01198 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003G-CD08 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1199 | PL-PS5-01199 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003G-CD12 | TZ-MID-68-WPR2-151112, 151116, 151167-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1200 | PL-PS5-01200 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0004-CD01 | TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1201 | PL-PS5-01201 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0004-CD02 | TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1202 | PL-PS5-01202 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Deluge skid Area | PS5-60-IES-3300-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2032 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1203 | PL-PS5-01203 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-BI-0001-CL01 | TZ-MID-68-WPR2-151118,151116,151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1204 | PL-PS5-01204 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-BI-0002-CL01 | TZ-MID-68-WPR2-151118,151116,151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1205 | PL-PS5-01205 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-BI-0003-CL01 | TZ-MID-68-WPR2-151118,151116,151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1206 | PL-PS5-01206 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-BI-0004-CL01 | TZ-MID-68-WPR2-151116,151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1207 | PL-PS5-01207 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-BI-0005-CL01 | TZ-MID-68-WPR2-151116,151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1208 | PL-PS5-01208 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-BI-0006-CL01 | TZ-MID-68-WPR2-151116,151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1209 | PL-PS5-01209 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD01 | TZ-MID-68-WPR2-151105,151107,151108,151111,151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1210 | PL-PS5-01210 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Export pump area | PS5-61-IG-0006-CD01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1211 | PL-PS5-01211 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Export pump area | PS5-61-IG-0006-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1212 | PL-PS5-01212 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near EDG package | PS5-61-IG-0007-CD01 | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1213 | PL-PS5-01213 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near EDG package | PS5-61-IG-0007-CL01 | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1214 | PL-PS5-01214 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near EITS | PS5-61-IG-0014-CD01 | TZ-MID-68-WPR2-151112, 151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1215 | PL-PS5-01215 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near EITS | PS5-61-IG-0014-CL01 | TZ-MID-68-WPR2-151112, 151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1216 | PL-PS5-01216 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-IG-0015-CD01 | TZ-MID-68-WPR2-151112, 151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1217 | PL-PS5-01217 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-61-IG-0042-CD01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1218 | PL-PS5-01218 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-61-IG-0042-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1219 | PL-PS5-01219 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-61-IG-0043-CD01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1220 | PL-PS5-01220 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD03 | TZ-MID-68-WPR2-151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2033 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1221 | PL-PS5-01221 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD27 | TZ-MID-68-WPR2-151116, 151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1222 | PL-PS5-01222 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD28 | TZ-MID-68-WPR2-151116, 151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1223 | PL-PS5-01223 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD29 | TZ-MID-68-WPR2-151116, 151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1224 | PL-PS5-01224 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD30 | TZ-MID-68-WPR2-151116, 151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1225 | PL-PS5-01225 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD36 | TZ-MID-68-WPR2-151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1226 | PL-PS5-01226 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD41 | TZ-MID-68-WPR2-151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1227 | PL-PS5-01227 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL31 | TZ-MID-68-WPR2-151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1228 | PL-PS5-01228 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL32 | TZ-MID-68-WPR2-151112-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1229 | PL-PS5-01229 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL37 | TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1230 | PL-PS5-01230 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL38 | TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1231 | PL-PS5-01231 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL39 | TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1232 | PL-PS5-01232 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL40 | TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1233 | PL-PS5-01233 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL41 | TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1234 | PL-PS5-01234 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL42 | TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1235 | PL-PS5-01235 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL43 | TZ-MID-68-WPR2-151112,151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1236 | PL-PS5-01236 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL15 | TZ-MID-68-WPR2-151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1237 | PL-PS5-01237 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL25 | TZ-MID-68-WPR2-151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1238 | PL-PS5-01238 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL26 | TZ-MID-68-WPR2-151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1239 | PL-PS5-01239 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL27 | TZ-MID-68-WPR2-151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1240 | PL-PS5-01240 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL28 | TZ-MID-68-WPR2-151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1241 | PL-PS5-01241 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL29 | TZ-MID-68-WPR2-151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1242 | PL-PS5-01242 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL23 | TZ-MID-68-WPR2-151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1243 | PL-PS5-01243 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL24 | TZ-MID-68-WPR2-151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1244 | PL-PS5-01244 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL25 | TZ-MID-68-WPR2-151116-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1245 | PL-PS5-01245 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near EDG package | PS5-62-IE-0002-CD01 | TZ-MID-68-WPR2-151112,151111-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1246 | PL-PS5-01246 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Fuel Pump Area | PS5-71-DM-3100A-CL01 | TZ-MID-68-WPR2-151112,151111,151108,151107-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2034 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1247 | PL-PS5-01247 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Fuel Pump Area | PS5-71-DM-3100B-CL01 | TZ-MID-68-WPR2-151112,151111,151108,151107-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2035 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1248 | PL-PS5-01248 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Fuel Pump Area | PS5-71-DM-3200-CL01 | TZ-MID-68-WPR2-151112,151111,151108,151107-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2036 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1249 | PL-PS5-01249 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Pump Area | PS5-71-DM-3300A-CL01 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1250 | PL-PS5-01250 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Pump Area | PS5-71-DM-3300B-CL01 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1251 | PL-PS5-01251 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Pump Area | PS5-71-DM-3400A-CL01 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1252 | PL-PS5-01252 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Pump Area | PS5-71-DM-3400B-CL01 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1253 | PL-PS5-01253 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Day Fuel Day Drum Area | PS5-71-DM-3500A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1254 | PL-PS5-01254 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Day Fuel Day Drum Area | PS5-71-DM-3500B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1255 | PL-PS5-01255 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | DIESEL FUEL DAY DRUM | PS5-71-FCV-0019-CL01 | TZ-MID-68-WPR2-151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2037 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1256 | PL-PS5-01256 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO STORAGE TANK AREA | PS5-71-FIT-0011A-CL01 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1257 | PL-PS5-01257 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO STORAGE TANK AREA | PS5-71-FIT-0011B-CL01 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1258 | PL-PS5-01258 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Service tank area | PS5-71-HE-2200-CL01 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1259 | PL-PS5-01259 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2300-CL01 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1260 | PL-PS5-01260 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2300-CL02 | TZ-MID-68-WPR2-151117,151114,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1261 | PL-PS5-01261 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2400A-CL03 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1262 | PL-PS5-01262 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2400A-CL04 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1263 | PL-PS5-01263 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2400B-CL01 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1264 | PL-PS5-01264 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2400B-CL02 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1265 | PL-PS5-01265 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2400B-CL03 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1266 | PL-PS5-01266 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2400B-CL04 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1267 | PL-PS5-01267 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Fuel Pump Area | PS5-71-IES-3100A-CD01 | TZ-MID-68-WPR2-151112,151111,151108.151107-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2038 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1268 | PL-PS5-01268 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Fuel Pump Area | PS5-71-IES-3100B-CD01 | TZ-MID-68-WPR2-151112,151111,151108.151107-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2039 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1269 | PL-PS5-01269 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Fuel Pump Area | PS5-71-IES-3200-CD01 | TZ-MID-68-WPR2-151112,151111,151108,151107-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2040 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1270 | PL-PS5-01270 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Pump Area | PS5-71-IES-3300A-CD01 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1271 | PL-PS5-01271 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Pump Area | PS5-71-IES-3300B-CD01 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1272 | PL-PS5-01272 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Pump Area | PS5-71-IES-3400A-CD01 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1273 | PL-PS5-01273 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | CFO Pump Area | PS5-71-IES-3400B-CD01 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1274 | PL-PS5-01274 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel fuel day drum area | PS5-71-IES-3500A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1275 | PL-PS5-01275 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel fuel day drum area | PS5-71-IES-3500B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1276 | PL-PS5-01276 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0001-CL01 | TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2041 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1277 | PL-PS5-01277 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0002-CL01 | TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2042 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1278 | PL-PS5-01278 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0003-CL01 | TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2043 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1279 | PL-PS5-01279 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0004-CL01 | TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2044 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1280 | PL-PS5-01280 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0009-CL01 | TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2045 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1281 | PL-PS5-01281 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0010-CL01 | TZ-MID-68-WPR2-151117,151118-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2046 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1282 | PL-PS5-01282 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | DIESEL FUEL DAY DRUM | PS5-71-SDV-0001-CL01 | TZ-MID-68-WPR2-151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1283 | PL-PS5-01283 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | DIESEL FUEL STORAGE AREA | PS5-71-SDV-0029-CL01 | TZ-MID-68-WPR2-151117,151115,151111,151108,151107-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1284 | PL-PS5-01284 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel Fuel Dispenser Station | PS5-71-UZ-6200-CL01 | TZ-MID-68-WPR2-151112, 151111, 151108, 151107-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1285 | PL-PS5-01285 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | DIESEL FUEL DAY DRUM ARE | PS5-71-XV-0092-CL01 | TZ-MID-68-WPR2-151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1286 | PL-PS5-01286 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Nitrogen Generation Skid | PS5-74-IG-5101-CL01 | TZ-MID-68-WPR2-151112,151111,151108-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1287 | PL-PS5-01287 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Nitrogen Generation Skid | PS5-74-LB-5101-CL02 | TZ-MID-68-WPR2-151167,151116,151112,151111,151108-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1288 | PL-PS5-01288 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near DRA injection package | PS5-75-DM-3100A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1289 | PL-PS5-01289 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near DRA injection package | PS5-75-DM-3100B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1290 | PL-PS5-01290 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near DRA injection package | PS5-75-DM-3200A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1291 | PL-PS5-01291 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near DRA injection package | PS5-75-DM-3200B-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1292 | PL-PS5-01292 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near DRA injection package | PS5-75-IES-3100A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1293 | PL-PS5-01293 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near DRA injection package | PS5-75-IES-3100B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1294 | PL-PS5-01294 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near DRA injection package | PS5-75-IES-3200A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1295 | PL-PS5-01295 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near DRA injection package | PS5-75-IES-3200B-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1296 | PL-PS5-01296 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Field_DRA injection package | PS5-75-ISO-0001-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1297 | PL-PS5-01297 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Field_DRA injection package | PS5-75-ISO-0002-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117, 151114,151113-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1298 | PL-PS5-01298 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near CFO Service Pump area | PS5-79-IV-0001-CL01 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1299 | PL-PS5-01299 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near CFO Service Pump area | PS5-79-IV-0002-CL01 | TZ-MID-68-WPR2-151112,151111,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1300 | PL-PS5-01300 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Diesel Fuel Day Tank Area | PS5-79-IV-0003-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1301 | PL-PS5-01301 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Diesel Fuel Day Tank Area | PS5-79-IV-0004-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1302 | PL-PS5-01302 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Diesel Fuel Day Tank Area | PS5-79-IV-0005-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1303 | PL-PS5-01303 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export Pump Area | PS5-79-IV-0006-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1304 | PL-PS5-01304 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export Pump Area | PS5-79-IV-0007-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1305 | PL-PS5-01305 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export Pump Area | PS5-79-IV-0008-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1306 | PL-PS5-01306 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export Pump Area | PS5-79-IV-0009-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1307 | PL-PS5-01307 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Near Export Pump Area | PS5-79-IV-0010-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1308 | PL-PS5-01308 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Sewage Treatment Pkge -North w | PS5-82-IN-0001-CL01 | TZ-MID-68-WPR2-151112,151111,151108,151107,151105-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1309 | PL-PS5-01309 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-87-IRF-0002-CL01 | TZ-MID-68-WPR2-151117,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2047 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1310 | PL-PS5-01310 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-87-IRF-0003-CL01 | TZ-MID-68-WPR2-151117,151115-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 16-06-2048 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1311 | PL-PS5-01311 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Diesel fuel tank Area | PS5-87-IRF-0004-CL01 | TZ-MID-68-WPR2-151111,151108,151107-SS Tag on both ends not installed | B | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
1312 | PL-PS5-01312 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0001-CL01 | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench | A | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1313 | PL-PS5-01313 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0002-CL01 | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench | A | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1314 | PL-PS5-01314 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0003-CL01 | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench | A | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1315 | PL-PS5-01315 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0004-CL01 | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench | A | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1316 | PL-PS5-01316 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0009-CL01 | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench | A | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1317 | PL-PS5-01317 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-71-MOV-0010-CL01 | TZ-MID-68-WPR2-151117,151118-Cable coiled, need to be laid in trench | A | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1318 | PL-PS5-01318 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-87-IRF-0002-CL01 | TZ-MID-68-WPR2-151117,151115--Cable coiled, need to be laid in trench | A | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1319 | PL-PS5-01319 | #N/A | CPP-RFI-68-33/1-05-0211 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-87-IRF-0003-CL01 | TZ-MID-68-WPR2-151117,151115--Cable coiled, need to be laid in trench | A | Electrical | CPY | Konstantin Ovchinnikov | 14-April-2026 | CPP EIT | Gao Chong |  |  |  |  | Open
1320 | PL-PS5-01320 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Launcher Receivier Area, Power Distribution Area | PS5-28-DM-3900B-CL01 | TZ-MID-68-WPR2-151113, TZ-MID-68-WPR2-151112 - Cable need to dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1321 | PL-PS5-01321 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Launcher Receivier Area, Power Distribution Area | PS5-28-DM-3900B-CL01 | TZ-MID-68-WPR2-151113, TZ-MID-68-WPR2-151112 - SS tag at both ends Need to Install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1322 | PL-PS5-01322 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL01 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1323 | PL-PS5-01323 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL02 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1324 | PL-PS5-01324 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL03 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1325 | PL-PS5-01325 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL04 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1326 | PL-PS5-01326 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL05 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1327 | PL-PS5-01327 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL06 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1328 | PL-PS5-01328 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL07 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1329 | PL-PS5-01329 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL08 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1330 | PL-PS5-01330 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL09 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1331 | PL-PS5-01331 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL10 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1332 | PL-PS5-01332 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL11 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1333 | PL-PS5-01333 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL12 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1334 | PL-PS5-01334 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL13 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1335 | PL-PS5-01335 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL14 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1336 | PL-PS5-01336 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL15 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1337 | PL-PS5-01337 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL16 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1338 | PL-PS5-01338 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL17 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1339 | PL-PS5-01339 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL18 | TZ-MID-68-WPR2-151112 - Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1340 | PL-PS5-01340 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL01 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1341 | PL-PS5-01341 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL02 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1342 | PL-PS5-01342 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL03 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1343 | PL-PS5-01343 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL04 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1344 | PL-PS5-01344 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL05 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1345 | PL-PS5-01345 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL06 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1346 | PL-PS5-01346 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL07 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1347 | PL-PS5-01347 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL08 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1348 | PL-PS5-01348 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL09 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1349 | PL-PS5-01349 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL10 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1350 | PL-PS5-01350 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL11 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1351 | PL-PS5-01351 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL12 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1352 | PL-PS5-01352 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL13 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1353 | PL-PS5-01353 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL14 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1354 | PL-PS5-01354 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL15 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1355 | PL-PS5-01355 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL16 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1356 | PL-PS5-01356 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL17 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1357 | PL-PS5-01357 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL18 | TZ-MID-68-WPR2-151112 - SS Cable Tag need to Install both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1358 | PL-PS5-01358 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL01 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1359 | PL-PS5-01359 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL02 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1360 | PL-PS5-01360 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL03 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1361 | PL-PS5-01361 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL04 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1362 | PL-PS5-01362 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL05 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1363 | PL-PS5-01363 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL06 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1364 | PL-PS5-01364 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL07 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1365 | PL-PS5-01365 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL08 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1366 | PL-PS5-01366 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL09 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1367 | PL-PS5-01367 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL010 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1368 | PL-PS5-01368 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL011 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1369 | PL-PS5-01369 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL012 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1370 | PL-PS5-01370 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL013 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1371 | PL-PS5-01371 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL014 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1372 | PL-PS5-01372 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL015 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1373 | PL-PS5-01373 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL016 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1374 | PL-PS5-01374 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL17 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1375 | PL-PS5-01375 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IK-0001-CL18 | TZ-MID-68-WPR2-151112 - Trench Backfilled, Red Protection Tiles & Warning Tape at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1376 | PL-PS5-01376 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL07 | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1377 | PL-PS5-01377 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL08 | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1378 | PL-PS5-01378 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL09 | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1379 | PL-PS5-01379 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL10 | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1380 | PL-PS5-01380 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL11 | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1381 | PL-PS5-01381 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL12 | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1382 | PL-PS5-01382 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL07 | TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1383 | PL-PS5-01383 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL08 | TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1384 | PL-PS5-01384 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL09 | TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1385 | PL-PS5-01385 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL10 | TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1386 | PL-PS5-01386 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL11 | TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1387 | PL-PS5-01387 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL12 | TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1388 | PL-PS5-01388 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL07 | TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1389 | PL-PS5-01389 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL08 | TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1390 | PL-PS5-01390 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL09 | TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1391 | PL-PS5-01391 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL10 | TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1392 | PL-PS5-01392 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL11 | TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1393 | PL-PS5-01393 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL12 | TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1394 | PL-PS5-01394 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL41 | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1395 | PL-PS5-01395 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL42 | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1396 | PL-PS5-01396 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL41 | TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 16-06-2049 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1397 | PL-PS5-01397 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL42 | TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1398 | PL-PS5-01398 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL41 | TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1399 | PL-PS5-01399 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL42 | TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1400 | PL-PS5-01400 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL01 | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1401 | PL-PS5-01401 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL02 | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1402 | PL-PS5-01402 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL03 | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1403 | PL-PS5-01403 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL04 | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1404 | PL-PS5-01404 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL05 | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1405 | PL-PS5-01405 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL06 | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1406 | PL-PS5-01406 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL07 | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1407 | PL-PS5-01407 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL08 | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1408 | PL-PS5-01408 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL09 | TZ-MID-68-WPR2-151167 - Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1409 | PL-PS5-01409 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL01 | TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1410 | PL-PS5-01410 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL02 | TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1411 | PL-PS5-01411 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL03 | TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1412 | PL-PS5-01412 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL04 | TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1413 | PL-PS5-01413 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL05 | TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1414 | PL-PS5-01414 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL06 | TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1415 | PL-PS5-01415 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL07 | TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1416 | PL-PS5-01416 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL08 | TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1417 | PL-PS5-01417 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL09 | TZ-MID-68-WPR2-151167 - SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1418 | PL-PS5-01418 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL01 | TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1419 | PL-PS5-01419 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL02 | TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1420 | PL-PS5-01420 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL03 | TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1421 | PL-PS5-01421 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL04 | TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1422 | PL-PS5-01422 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL05 | TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1423 | PL-PS5-01423 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL06 | TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1424 | PL-PS5-01424 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL07 | TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1425 | PL-PS5-01425 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL08 | TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1426 | PL-PS5-01426 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL09 | TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles & Warning Tapes at Transformers side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1427 | PL-PS5-01427 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | CFO & Power Distribution Area | PS5-71-FCV-0018-CL01 | TZ-MID-68-WPR2-151115, TZ-MID-68-WPR2-151112 SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1428 | PL-PS5-01428 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | CFO & Power Distribution Area | PS5-71-FCV-0018-CL01 | TZ-MID-68-WPR2-151115, TZ-MID-68-WPR2-151112 Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1429 | PL-PS5-01429 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | CFO & Power Distribution Area | PS5-71-HE-2300-CD01 | TZ-MID-68-WPR2-151115, TZ-MID-68-WPR2-151112 SS Cable Tags need to Install at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1430 | PL-PS5-01430 | #N/A | CPP-RFI-68-33/1-05-0223 | PS5 | Electrical Cable Installation | CFO & Power Distribution Area | PS5-71-HE-2300-CD01 | TZ-MID-68-WPR2-151115, TZ-MID-68-WPR2-151112 Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-22 | CPP EIT | Gao Chong |  |  |  |  | Open
1431 | PL-PS5-01431 | #N/A | CPP-RFI-68-33/1-03-0224 | PS5 | Electrical Cable Ladder/Tray Installation | Power Distribution Area | N/A | TZ-MID-68-WPR2-151112 - Hold On Clamp need to Install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1432 | PL-PS5-01432 | #N/A | CPP-RFI-68-33/1-03-0224 | PS5 | Electrical Cable Ladder/Tray Installation | Power Distribution Area | N/A | TZ-MID-68-WPR2-151112 - Earthing Straps Need to Complete Installlation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1433 | PL-PS5-01433 | #N/A | CPP-RFI-68-33/1-03-0224 | PS5 | Electrical Cable Ladder/Tray Installation | Power Distribution Area | N/A | TZ-MID-68-WPR2-151112 - Bolt need to Tighten | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1434 | PL-PS5-01434 | #N/A | CPP-RFI-68-33/1-03-0224 | PS5 | Electrical Cable Ladder/Tray Installation | Power Distribution Area | N/A | TZ-MID-68-WPR2-151112 - Corrosion need to Remove by Apply Zinc Spray | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1435 | PL-PS5-01435 | #N/A | CPP-RFI-68-33/1-03-0224 | PS5 | Electrical Cable Ladder/Tray Installation | Power Distribution Area | N/A | TZ-MID-68-WPR2-151112 - Bonding Jumper Ladder to Ladder Need to Install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1436 | PL-PS5-01436 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0102-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1437 | PL-PS5-01437 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0102-CR01 | TZ-MID-68-WPR2-171173 Trench not yet complete from EITS to PS5-08-01LS-0102 | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1438 | PL-PS5-01438 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0105-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1439 | PL-PS5-01439 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0105-CR01 | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1440 | PL-PS5-01440 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0106-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1441 | PL-PS5-01441 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0106-CR01 | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1442 | PL-PS5-01442 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0107-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1443 | PL-PS5-01443 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0107-CR01 | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1444 | PL-PS5-01444 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0108-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1445 | PL-PS5-01445 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0108-CR01 | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1446 | PL-PS5-01446 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0109-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1447 | PL-PS5-01447 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0109-CR01 | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1448 | PL-PS5-01448 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0110-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1449 | PL-PS5-01449 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0110-CR01 | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1450 | PL-PS5-01450 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0110-CR01 | TZ-MID-68-WPR2-171173 Cable coiled, need to be la.id in trench at PS5-08-01LS-0110 side (Est. 20 Mtr) | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1451 | PL-PS5-01451 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0110-CR02 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1452 | PL-PS5-01452 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0110-CR02 | TZ-MID-68-WPR2-171173 Cable coiled, need to be laid in trench at PS5-08-01LS-0110 side (Est. 20 Mtr) | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1453 | PL-PS5-01453 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0204-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1454 | PL-PS5-01454 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0204-CR01 | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1455 | PL-PS5-01455 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0205-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1456 | PL-PS5-01456 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0205-CR01 | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1457 | PL-PS5-01457 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0206-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1458 | PL-PS5-01458 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0206-CR01 | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1459 | PL-PS5-01459 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0207-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1460 | PL-PS5-01460 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0207-CR01 | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1461 | PL-PS5-01461 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0208-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1462 | PL-PS5-01462 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0208-CR01 | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1463 | PL-PS5-01463 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0209-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1464 | PL-PS5-01464 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0209-CR01 | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1465 | PL-PS5-01465 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0210-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1466 | PL-PS5-01466 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0210-CR01 | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1467 | PL-PS5-01467 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0211-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1468 | PL-PS5-01468 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0211-CR01 | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1469 | PL-PS5-01469 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0211-CR02 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1470 | PL-PS5-01470 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0211-CR02 | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1471 | PL-PS5-01471 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0301-CR01 | TZ-MID-68-WPR2-171173 Cable Coil, Need to Open Trench at PS5-08-01LS-0301 side (Est. 20Mtr) | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1472 | PL-PS5-01472 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0301-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1473 | PL-PS5-01473 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0302-CR01 | TZ-MID-68-WPR2-171173 Cable Coil, Need to Open Trench at PS5-08-01LS-0301 side (Est. 20Mtr). | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1474 | PL-PS5-01474 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0302-CR01 | TZ-MID-68-WPR2-171173 Cable Coil, Need to Open Trench at PS5-08-01LS-0302 side (Est. 5Mtr). | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1475 | PL-PS5-01475 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0302-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1476 | PL-PS5-01476 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0303-CR01 | TZ-MID-68-WPR2-171173 Cable Coil, Need to Open Trench at PS5-08-01LS-0302 side (Est. 5Mtr). | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1477 | PL-PS5-01477 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0303-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1478 | PL-PS5-01478 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0306-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1479 | PL-PS5-01479 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0306-CR01 | TZ-MID-68-WPR2-171173 Field run vertical cable tray shall be install at both end | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1480 | PL-PS5-01480 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0401-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1481 | PL-PS5-01481 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0402-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1482 | PL-PS5-01482 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0403-CR01 | TZ-MID-68-WPR2-171173 Cable Coil, Need to open cable trench est.60 mtr at PS5-08-01LS-0403 Side | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1483 | PL-PS5-01483 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0403-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1484 | PL-PS5-01484 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0405-CR01 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1485 | PL-PS5-01485 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0411-CR02 | TZ-MID-68-WPR2-171173 Cable Dressing at Both End | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1486 | PL-PS5-01486 | #N/A | CPP-RFI-68-65-05-0024 | PS5 | Telecom Cable Installation | FIELD | PS5-08-01LS-0411-CR02 | TZ-MID-68-WPR2-171173 Cable trench installation outstanding | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-04-23 | CPP EIT | Gao Chong |  |  |  |  | Open
1487 | PL-PS5-01487 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004B-CD01 | TZ-MID-68-WPR2-151112, 151116, 151118 Dressing Cable Both Side to be done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1488 | PL-PS5-01488 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004B-CD01 | TZ-MID-68-WPR2-151112, 151116, 151118 Permanent Cable Tag Missing Both End | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1489 | PL-PS5-01489 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004B-CD01 | TZ-MID-68-WPR2-151112, 151116, 151118 Cable Trench Not yet complete installation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1490 | PL-PS5-01490 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100A-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114 Dressing Cable Both Side to be done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1491 | PL-PS5-01491 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100A-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114 Permanent Cable Tag Missing Both End | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1492 | PL-PS5-01492 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100A-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Trench Not yet complete installation both end | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1493 | PL-PS5-01493 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100A-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114 Field Run Cable tray not yet complete installation both end. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1494 | PL-PS5-01494 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100B-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114 Dressing Cable Both Side to be done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1495 | PL-PS5-01495 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100B-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114 Permanent Cable Tag Missing Both End | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1496 | PL-PS5-01496 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100B-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Trench Not yet complete installation both end | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1497 | PL-PS5-01497 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100B-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114 Field Run Cable tray not yet complete installation both end. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1498 | PL-PS5-01498 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100C-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114 Dressing Cable Both Side to be done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1499 | PL-PS5-01499 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100C-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114 Permanent Cable Tag Missing Both End | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1500 | PL-PS5-01500 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100C-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Trench Not yet complete installation both end | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1501 | PL-PS5-01501 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100C-CD01 | TZ-MID-68-WPR2-151111,151115,151117,151114 Field Run Cable tray not yet complete installation both end. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1502 | PL-PS5-01502 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IJ-0001-CD07 | TZ-MID-68-WPR2-151116,151112 Dressing Cable Both Side to be done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1503 | PL-PS5-01503 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IJ-0001-CD07 | TZ-MID-68-WPR2-151116,151112 Permanent Cable Tag Missing Both End | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1504 | PL-PS5-01504 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IJ-0001-CD07 | TZ-MID-68-WPR2-151116,151112 Cable Trench Not yet complete installation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1505 | PL-PS5-01505 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CG07 | TZ-MID-68-WPR2-151111, 151112, 151116 Dressing Cable Both Side to be done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1506 | PL-PS5-01506 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CG07 | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent Cable Tag Missing Both End | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1507 | PL-PS5-01507 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CG07 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable Trench Not yet complete installation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1508 | PL-PS5-01508 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL19 | TZ-MID-68-WPR2-151116 Permanent Cable Tag Missing Both End | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1509 | PL-PS5-01509 | #N/A | CPP-RFI-68-33/1-05-0225 | PS6 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL19 | TZ-MID-68-WPR2-151116 Dressing Cable To be done at Generator Electrical Building side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1510 | PL-PS5-01510 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL19 | TZ-MID-68-WPR2-151116 Cable Trench Installation to be complete at PS5-61-IV-0007B side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1511 | PL-PS5-01511 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL20 | TZ-MID-68-WPR2-151116 Permanent Cable Tag Missing Both End | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1512 | PL-PS5-01512 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL20 | TZ-MID-68-WPR2-151116 Dressing Cable To be done at Generator Electrical Building side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1513 | PL-PS5-01513 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL20 | TZ-MID-68-WPR2-151116 Cable Trench Installation to be complete at PS5-61-IV-0007B side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1514 | PL-PS5-01514 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL21 | TZ-MID-68-WPR2-151116 Permanent Cable Tag Missing Both End | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1515 | PL-PS5-01515 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL21 | TZ-MID-68-WPR2-151116 Dressing Cable To be done at Generator Electrical Building side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1516 | PL-PS5-01516 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL21 | TZ-MID-68-WPR2-151116 Cable Trench Installation to be complete at PS5-61-IV-0007B side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1517 | PL-PS5-01517 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL22 | TZ-MID-68-WPR2-151116 Permanent Cable Tag Missing Both End | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1518 | PL-PS5-01518 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL22 | TZ-MID-68-WPR2-151116 Dressing Cable To be done at Generator Electrical Building side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1519 | PL-PS5-01519 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL22 | TZ-MID-68-WPR2-151116 Cable Trench Installation to be complete at PS5-61-IV-0007B side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1520 | PL-PS5-01520 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2400A-CL01 | TZ-MID-68-WPR2-151112,151111,151115 Dressing Cable To be done both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1521 | PL-PS5-01521 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2400A-CL01 | TZ-MID-68-WPR2-151112,151111,151115 Permanent Cable Tag Missing Both End | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1522 | PL-PS5-01522 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2400A-CL01 | TZ-MID-68-WPR2-151112,151111,151115 Dressing Cable To be done both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong |  |  |  |  | Open
1523 | PL-PS5-01523 | #N/A | CPP-RFI-68-33/1-05-0225 | PS5 | Electrical Cable Installation | CFO Stroage tank area | PS5-71-HE-2400A-CL01 | TZ-MID-68-WPR2-151112,151111,151115 Permanent Cable Tag Missing Both End | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-25 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1524 | PL-PS5-01524 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD09 | TZ-MID-68-WPR2-151112 151116 Cable trench not yet complete installation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1525 | PL-PS5-01525 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD09 | TZ-MID-68-WPR2-151112 151116 Cable tag not yet install both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1526 | PL-PS5-01526 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD09 | TZ-MID-68-WPR2-151112 151116 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1527 | PL-PS5-01527 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-52BT-0135-CS01 | TZ-MID-68-WPR2-151116 Cable trench not yet complete installation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1528 | PL-PS5-01528 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-52BT-0135-CS01 | TZ-MID-68-WPR2-151116 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1529 | PL-PS5-01529 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-52BT-0140-CS01 | TZ-MID-68-WPR2-151116 Cable trench not yet complete installation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1530 | PL-PS5-01530 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-52BT-0140-CS01 | TZ-MID-68-WPR2-151116 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1531 | PL-PS5-01531 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-ESDV-0021-CL01 | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1532 | PL-PS5-01532 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-ESDV-0021-CL01 | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1533 | PL-PS5-01533 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-ESDV-0021-CL01 | TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0042) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1534 | PL-PS5-01534 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-ESDV-0023-CL01 | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1535 | PL-PS5-01535 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-ESDV-0023-CL01 | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1536 | PL-PS5-01536 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-ESDV-0023-CL01 | TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0042) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1537 | PL-PS5-01537 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-FCV-0003A-CL01 | TZ-MID-68-WPR2-151117,151114 Permanent Cable tag not yet installed. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1538 | PL-PS5-01538 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-FCV-0003A-CL01 | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1539 | PL-PS5-01539 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-FCV-0003A-CL01 | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1540 | PL-PS5-01540 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-FCV-0003A-CL01 | TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0042) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1541 | PL-PS5-01541 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-FCV-0003B-CL01 | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1542 | PL-PS5-01542 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-FCV-0003B-CL01 | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1543 | PL-PS5-01543 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-FCV-0003B-CL01 | TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0042) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1544 | PL-PS5-01544 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-FCV-0003C-CL01 | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1545 | PL-PS5-01545 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-FCV-0003C-CL01 | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1546 | PL-PS5-01546 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-FCV-0003C-CL01 | TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0043) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1547 | PL-PS5-01547 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-SDV-0054A-CL01 | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1548 | PL-PS5-01548 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-SDV-0054A-CL01 | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1549 | PL-PS5-01549 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-SDV-0054A-CL01 | TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0043) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1550 | PL-PS5-01550 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-SDV-0054A-CL01 | TZ-MID-68-WPR2-151117,151114 Permanent Cable tag not yet installed. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1551 | PL-PS5-01551 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-SDV-0054B-CL01 | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1552 | PL-PS5-01552 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-SDV-0054B-CL01 | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1553 | PL-PS5-01553 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-SDV-0054B-CL01 | TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0043) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1554 | PL-PS5-01554 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-SDV-0054C-CL01 | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1555 | PL-PS5-01555 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-SDV-0054C-CL01 | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1556 | PL-PS5-01556 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-25-SDV-0054C-CL01 | TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0043) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1557 | PL-PS5-01557 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-28-SDV-0053A-CL01 | TZ-MID-68-WPR2-151117,151114 Cable not yet laid in the installed field side cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1558 | PL-PS5-01558 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-28-SDV-0053A-CL01 | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1559 | PL-PS5-01559 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-28-SDV-0053A-CL01 | TZ-MID-68-WPR2-151117,151114 To be install vertical tray at panel side (PS5-61-IG-0043) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1560 | PL-PS5-01560 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IJ-0001-CD06 | TZ-MID-68-WPR2-151116,151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1561 | PL-PS5-01561 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IJ-0001-CD06 | TZ-MID-68-WPR2-151116,151112 Cable trench installation to be done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1562 | PL-PS5-01562 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-62-IE-0001-CD01 | TZ-MID-68-WPR2-151111 To be install vertical cable ladder at both end | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1563 | PL-PS5-01563 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-62-IE-0001-CD01 | TZ-MID-68-WPR2-151111 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1564 | PL-PS5-01564 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-62-IE-0001-CL01 | TZ-MID-68-WPR2-151111 To be install vertical cable ladder at both end | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1565 | PL-PS5-01565 | #N/A | CPP-RFI-68-33/1-05-0226 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-62-IE-0001-CL01 | TZ-MID-68-WPR2-151111 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-26 | CPP EIT | Gao Chong |  |  |  |  | Open
1566 | PL-PS5-01566 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-01-BI-1118-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
1567 | PL-PS5-01567 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-25-BI-1102-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1568 | PL-PS5-01568 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-25-BI-2203-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1569 | PL-PS5-01569 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-25-BI-2312-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
1570 | PL-PS5-01570 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-28-BI-1105-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
1571 | PL-PS5-01571 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-71-BI-1305-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
1572 | PL-PS5-01572 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-25-BI-2103-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
1573 | PL-PS5-01573 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-25-BI-2109-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
1574 | PL-PS5-01574 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-25-BI-2308-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
1575 | PL-PS5-01575 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-25-BI-2315-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-24 | Konstantin | 2026-05-25 |  | CLOSED
1576 | PL-PS5-01576 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-71-BI-1109-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
1577 | PL-PS5-01577 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-71-BI-2310-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1578 | PL-PS5-01578 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-01-BI-1118-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1579 | PL-PS5-01579 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-25-BI-1102-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1580 | PL-PS5-01580 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-25-BI-2203-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1581 | PL-PS5-01581 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-25-BI-2312-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1582 | PL-PS5-01582 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-28-BI-1105-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1583 | PL-PS5-01583 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-71-BI-1305-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1584 | PL-PS5-01584 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-25-BI-2103-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1585 | PL-PS5-01585 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-25-BI-2109-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1586 | PL-PS5-01586 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-25-BI-2308-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1587 | PL-PS5-01587 | #N/A | CPP-RFI-68-64-04-0041 | PS5 | Instrument Cable installation | Power Distribution area | PS5-25-BI-2315-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1588 | PL-PS5-01588 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL13 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1589 | PL-PS5-01589 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL14 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1590 | PL-PS5-01590 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL16 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1591 | PL-PS5-01591 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL17 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1592 | PL-PS5-01592 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL18 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1593 | PL-PS5-01593 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL19 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1594 | PL-PS5-01594 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL20 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1595 | PL-PS5-01595 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL21 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1596 | PL-PS5-01596 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL22 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1597 | PL-PS5-01597 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL23 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1598 | PL-PS5-01598 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL24 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1599 | PL-PS5-01599 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL30 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1600 | PL-PS5-01600 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL31 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1601 | PL-PS5-01601 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL32 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1602 | PL-PS5-01602 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL33 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1603 | PL-PS5-01603 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL34 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1604 | PL-PS5-01604 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL35 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1605 | PL-PS5-01605 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL36 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1606 | PL-PS5-01606 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL10 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1607 | PL-PS5-01607 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL11 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1608 | PL-PS5-01608 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL12 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1609 | PL-PS5-01609 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL13 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1610 | PL-PS5-01610 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL14 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1611 | PL-PS5-01611 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL15 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1612 | PL-PS5-01612 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL16 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1613 | PL-PS5-01613 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL17 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1614 | PL-PS5-01614 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL18 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1615 | PL-PS5-01615 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IV-0007A-CL01 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 16-06-2050 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1616 | PL-PS5-01616 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IV-0007B-CL01 | Doc. TZ-MID-68-WPR2-151167 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1617 | PL-PS5-01617 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Power Distribution area | PS5-61-IV-0001A-CL01 | Doc. TZ-MID-68-WPR2-151112 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1618 | PL-PS5-01618 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Power Distribution area | PS5-61-IV-0001B-CL01 | Doc. TZ-MID-68-WPR2-151112 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1619 | PL-PS5-01619 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Power Distribution area | PS5-61-IV-0006B-CL01 | Doc. TZ-MID-68-WPR2-151112 - Installation of SS Cable Tag at Both Ends of Cable | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong | 16-06-2051 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1620 | PL-PS5-01620 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL13 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1621 | PL-PS5-01621 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL14 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1622 | PL-PS5-01622 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL16 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1623 | PL-PS5-01623 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL17 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1624 | PL-PS5-01624 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL18 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1625 | PL-PS5-01625 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL19 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1626 | PL-PS5-01626 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL20 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1627 | PL-PS5-01627 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL21 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1628 | PL-PS5-01628 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL22 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1629 | PL-PS5-01629 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL23 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1630 | PL-PS5-01630 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL24 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1631 | PL-PS5-01631 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL30 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1632 | PL-PS5-01632 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL31 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1633 | PL-PS5-01633 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL32 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1634 | PL-PS5-01634 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL33 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1635 | PL-PS5-01635 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL34 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1636 | PL-PS5-01636 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL35 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1637 | PL-PS5-01637 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL36 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1638 | PL-PS5-01638 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL10 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1639 | PL-PS5-01639 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL11 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1640 | PL-PS5-01640 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL12 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1641 | PL-PS5-01641 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL13 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1642 | PL-PS5-01642 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL14 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1643 | PL-PS5-01643 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL15 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1644 | PL-PS5-01644 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL16 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1645 | PL-PS5-01645 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL17 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1646 | PL-PS5-01646 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL18 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1647 | PL-PS5-01647 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IV-0007A-CL01 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1648 | PL-PS5-01648 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IV-0007B-CL01 | Doc. TZ-MID-68-WPR2-151167 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1649 | PL-PS5-01649 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Power Distribution area | PS5-61-IV-0001A-CL01 | Doc. TZ-MID-68-WPR2-151112 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1650 | PL-PS5-01650 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Power Distribution area | PS5-61-IV-0001B-CL01 | Doc. TZ-MID-68-WPR2-151112 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1651 | PL-PS5-01651 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Power Distribution area | PS5-61-IV-0006B-CL01 | Doc. TZ-MID-68-WPR2-151112 - Cable Dressing at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1652 | PL-PS5-01652 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL13 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1653 | PL-PS5-01653 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL14 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1654 | PL-PS5-01654 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL16 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1655 | PL-PS5-01655 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL17 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1656 | PL-PS5-01656 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL18 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1657 | PL-PS5-01657 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL19 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1658 | PL-PS5-01658 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL20 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1659 | PL-PS5-01659 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL21 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1660 | PL-PS5-01660 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL22 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1661 | PL-PS5-01661 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL23 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1662 | PL-PS5-01662 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL24 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1663 | PL-PS5-01663 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL30 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1664 | PL-PS5-01664 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL31 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1665 | PL-PS5-01665 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL32 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1666 | PL-PS5-01666 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL33 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1667 | PL-PS5-01667 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL34 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1668 | PL-PS5-01668 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL35 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1669 | PL-PS5-01669 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL36 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1670 | PL-PS5-01670 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL10 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1671 | PL-PS5-01671 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL11 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1672 | PL-PS5-01672 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL12 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1673 | PL-PS5-01673 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL13 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1674 | PL-PS5-01674 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL14 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1675 | PL-PS5-01675 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL15 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1676 | PL-PS5-01676 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL16 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1677 | PL-PS5-01677 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL17 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1678 | PL-PS5-01678 | #N/A | CPP-RFI-68-33/1-05-0228 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0006-CL18 | Doc. TZ-MID-68-WPR2-151167 - Trench Backfilled, Red Protection Tiles at Transformers side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-27 | CPP EIT | Gao Chong |  |  |  |  | Open
1679 | PL-PS5-01679 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-08-52BT-0134-CS01 | TZ-MID-68-WPR2-151116 Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1680 | PL-PS5-01680 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-08-52BT-0134-CS01 | TZ-MID-68-WPR2-151116 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1681 | PL-PS5-01681 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-08-52BT-0134-CS01 | TZ-MID-68-WPR2-151116 Need to open cable trench and complete the installation of the trench | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1682 | PL-PS5-01682 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | Reinjection Pump | PS5-28-BE-0002A-CL02 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1683 | PL-PS5-01683 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | Reinjection Pump | PS5-28-BE-0002A-CL02 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1684 | PL-PS5-01684 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | Reinjection Pump | PS5-28-BE-0002A-CL02 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Vertical Cable Tray to be install at panel side PS5-61-IG-0007 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1685 | PL-PS5-01685 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | Reinjection Pump | PS5-28-BE-0002A-CL02 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Direct Buried Cable trench installation at panel side PS5-61-IG-0007 not complete yet | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1686 | PL-PS5-01686 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | Reinjection Pump | PS5-28-BE-0002B-CL02 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1687 | PL-PS5-01687 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | Reinjection Pump | PS5-28-BE-0002B-CL02 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1688 | PL-PS5-01688 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | Reinjection Pump | PS5-28-BE-0002B-CL02 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Vertical Cable Tray to be install at panel side PS5-61-IG-0007 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1689 | PL-PS5-01689 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | Reinjection Pump | PS5-28-BE-0002B-CL02 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Direct Buried Cable trench installation at panel side PS5-61-IG-0007 not complete yet | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1690 | PL-PS5-01690 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-DM-3400-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1691 | PL-PS5-01691 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-DM-3400-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1692 | PL-PS5-01692 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-DM-3400-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 To be laid the cable in field run cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1693 | PL-PS5-01693 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | Closed Drain Drum 01 Heater | PS5-28-HE-2100-CL02 | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1694 | PL-PS5-01694 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | Closed Drain Drum 01 Heater | PS5-28-HE-2100-CL02 | TZ-MID-68-WPR2-151111,151115,151117,151114 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1695 | PL-PS5-01695 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | Closed Drain Drum 01 Heater | PS5-28-HE-2100-CL02 | TZ-MID-68-WPR2-151111,151115,151117,151114 Vertical Cable Tray & Direct Buried Cable trench installation at panel side PS5-61-IG-0007 not complete yet. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1696 | PL-PS5-01696 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-28-SDV-0053C-CL01 | TZ-MID-68-WPR2-151117,151114 Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1697 | PL-PS5-01697 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-28-SDV-0053C-CL01 | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1698 | PL-PS5-01698 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-28-SDV-0053C-CL01 | TZ-MID-68-WPR2-151117,151114 Vertical field tray to be install at panel side PS5-61-IG-0043 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1699 | PL-PS5-01699 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL55 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1700 | PL-PS5-01700 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL55 | TZ-MID-68-WPR2-151111, 151112, 151116 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1701 | PL-PS5-01701 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL55 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable Trench to be complete installation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1702 | PL-PS5-01702 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL56 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1703 | PL-PS5-01703 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL56 | TZ-MID-68-WPR2-151111, 151112, 151116 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1704 | PL-PS5-01704 | #N/A | CPP-RFI-68-33/1-05-0238 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL56 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable Trench to be complete installation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1705 | PL-PS5-01705 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Guard House Bldg FACP | PS5-03-SEA-0002-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
1706 | PL-PS5-01706 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Warehouse Bldg FACP | PS5-03-SEA-0006-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
1707 | PL-PS5-01707 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Warehouse Bldg HCP | PS5-09-LB-0007-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
1708 | PL-PS5-01708 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Generator Control Bldg HCP | PS5-09-LB-0008-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
1709 | PL-PS5-01709 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Generator Control Bldg HCP | PS5-09-LB-0008-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1710 | PL-PS5-01710 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Generator Control Bldg HCP | PS5-09-LB-0008-CC06 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1711 | PL-PS5-01711 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-50-IE-0002-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
1712 | PL-PS5-01712 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-50-IE-0002-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
1713 | PL-PS5-01713 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-50-IE-0002-CJ01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1714 | PL-PS5-01714 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003C-CC21 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
1715 | PL-PS5-01715 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003C-CC22 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
1716 | PL-PS5-01716 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003D-CC21 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
1717 | PL-PS5-01717 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003D-CC22 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
1718 | PL-PS5-01718 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003E-CC21 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-26 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
1719 | PL-PS5-01719 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003E-CC22 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 13-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
1720 | PL-PS5-01720 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003F-CC21 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1721 | PL-PS5-01721 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-71-BI-2118-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1722 | PL-PS5-01722 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-71-BI-2119-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1723 | PL-PS5-01723 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-71-BI-2120-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-25 | Konstantin | 2026-05-26 |  | CLOSED
1724 | PL-PS5-01724 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-71-BI-2121-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
1725 | PL-PS5-01725 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-05-GC-8100-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
1726 | PL-PS5-01726 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-05-UH-8100-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
1727 | PL-PS5-01727 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-05-BI-0002-CC04 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
1728 | PL-PS5-01728 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-05-IG-0009-CC01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
1729 | PL-PS5-01729 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-05-IG-0009-CC02 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
1730 | PL-PS5-01730 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Warehouse Bldg HCP | PS5-09-LB-0007-CX01 | Doc.TZ-MID-68-WPR2-161500 - SS Tag on both ends not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
1731 | PL-PS5-01731 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Guard House Bldg FACP | PS5-03-SEA-0002-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1732 | PL-PS5-01732 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Warehouse Bldg FACP | PS5-03-SEA-0006-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1733 | PL-PS5-01733 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Warehouse Bldg HCP | PS5-09-LB-0007-CC02 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1734 | PL-PS5-01734 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Generator Control Bldg HCP | PS5-09-LB-0008-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1735 | PL-PS5-01735 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Generator Control Bldg HCP | PS5-09-LB-0008-CC02 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1736 | PL-PS5-01736 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Generator Control Bldg HCP | PS5-09-LB-0008-CC06 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1737 | PL-PS5-01737 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-50-IE-0002-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1738 | PL-PS5-01738 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-50-IE-0002-CC02 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1739 | PL-PS5-01739 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-50-IE-0002-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1740 | PL-PS5-01740 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003C-CC21 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1741 | PL-PS5-01741 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003C-CC22 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1742 | PL-PS5-01742 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003D-CC21 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1743 | PL-PS5-01743 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003D-CC22 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1744 | PL-PS5-01744 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003E-CC21 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1745 | PL-PS5-01745 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003E-CC22 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1746 | PL-PS5-01746 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003F-CC21 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1747 | PL-PS5-01747 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-71-BI-2118-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1748 | PL-PS5-01748 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-71-BI-2119-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1749 | PL-PS5-01749 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-71-BI-2120-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1750 | PL-PS5-01750 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-71-BI-2121-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1751 | PL-PS5-01751 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-05-GC-8100-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1752 | PL-PS5-01752 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-05-UH-8100-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1753 | PL-PS5-01753 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-05-BI-0002-CC04 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1754 | PL-PS5-01754 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-05-IG-0009-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1755 | PL-PS5-01755 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | EITS Building | PS5-05-IG-0009-CC02 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1756 | PL-PS5-01756 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Warehouse Bldg HCP | PS5-09-LB-0007-CX01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1757 | PL-PS5-01757 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Generator Control Bldg HCP | PS5-09-LB-0008-CC01 | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 275 MTR,Cable tray not yet installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1758 | PL-PS5-01758 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Generator Control Bldg HCP | PS5-09-LB-0008-CC02 | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 275 MTR ,Cable tray not yet installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1759 | PL-PS5-01759 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Generator Control Bldg HCP | PS5-09-LB-0008-CC06 | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 260 MTR,Cable tray not yet installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-03 | CPP EIT | Gao Chong |  |  |  |  | Open
1760 | PL-PS5-01760 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003C-CC21 | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 95 MTR ,Cable tray not yet installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1761 | PL-PS5-01761 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003C-CC22 | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 95 MTR ,Cable tray not yet installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | Open
1762 | PL-PS5-01762 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003D-CC21 | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 95 MTR ,Cable tray not yet installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
1763 | PL-PS5-01763 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003D-CC22 | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 95 MTR ,Cable tray not yet installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
1764 | PL-PS5-01764 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003E-CC21 | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 95 MTR ,Cable tray not yet installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-08 | CPP EIT | Gao Chong |  |  |  |  | Open
1765 | PL-PS5-01765 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003E-CC22 | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 95 MTR ,Cable tray not yet installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-09 | CPP EIT | Gao Chong |  |  |  |  | Open
1766 | PL-PS5-01766 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | GCP | PS5-60-IE-0003F-CC21 | Doc.TZ-MID-68-WPR2-161500 -Cable coiled 95 MTR ,Cable tray not yet installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
1767 | PL-PS5-01767 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-52BT-0136-CS01 | TZ-MID-68-WPR2-151116 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1768 | PL-PS5-01768 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-52BT-0136-CS01 | TZ-MID-68-WPR2-151116 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1769 | PL-PS5-01769 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-52BT-0136-CS01 | TZ-MID-68-WPR2-151116 Cable Trench to be complete installation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1770 | PL-PS5-01770 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Near CRO Gen Area | PS5-28-IES-3700A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1771 | PL-PS5-01771 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Near CRO Gen Area | PS5-28-IES-3700A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1772 | PL-PS5-01772 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Near CRO Gen Area | PS5-28-IES-3700A-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Cable not yet laid in field run cable tray equipment side (PS5-28-IES-3700A) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1773 | PL-PS5-01773 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-28-SDV-0053B-CL01 | TZ-MID-68-WPR2-151117,151114 Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1774 | PL-PS5-01774 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-28-SDV-0053B-CL01 | TZ-MID-68-WPR2-151117,151114 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1775 | PL-PS5-01775 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | EXPORT PUMP AREA | PS5-28-SDV-0053B-CL01 | TZ-MID-68-WPR2-151117,151114 Vertical cable ladder to be done installation at panel side (PS5-61-IG-0043) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1776 | PL-PS5-01776 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | VSD E-house | PS5-61-IDH-3100B-CD02 | TZ-MID-68-WPR2-151112,151111 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong | 16-06-2052 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1777 | PL-PS5-01777 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | VSD E-house | PS5-61-IDH-3100B-CD02 | TZ-MID-68-WPR2-151112,151111 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1778 | PL-PS5-01778 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-61-IG-0043-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1779 | PL-PS5-01779 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-61-IG-0043-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1780 | PL-PS5-01780 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-61-IG-0043-CL01 | TZ-MID-68-WPR2-151112, 151111, 151115, 151117 Vertical cable ladder to be done installation at panel side (PS5-61-IG-0043) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1781 | PL-PS5-01781 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-ISR-0101-CL01 | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1782 | PL-PS5-01782 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-ISR-0101-CL01 | TZ-MID-68-WPR2-151112 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1783 | PL-PS5-01783 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-ISR-0101-CL01 | TZ-MID-68-WPR2-151112 Vertical Cable ladder to be install at transformer side PS5-61-ISR-0101 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1784 | PL-PS5-01784 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-ISR-0101-CL01 | TZ-MID-68-WPR2-151112 Cable trench installation to be complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1785 | PL-PS5-01785 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-ISR-0102-CL01 | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1786 | PL-PS5-01786 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-ISR-0102-CL01 | TZ-MID-68-WPR2-151112 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1787 | PL-PS5-01787 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-ISR-0102-CL01 | TZ-MID-68-WPR2-151112 Vertical Cable ladder to be install at transformer side PS5-61-ISR-0102 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1788 | PL-PS5-01788 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-ISR-0102-CL01 | TZ-MID-68-WPR2-151112 Cable trench installation to be complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1789 | PL-PS5-01789 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-IU-0010-CL01 | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1790 | PL-PS5-01790 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-IU-0010-CL01 | TZ-MID-68-WPR2-151112 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1791 | PL-PS5-01791 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-IU-0010-CL01 | TZ-MID-68-WPR2-151112 Vertical Cable ladder to be install at transformer side PS5-61-IU-0010 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1792 | PL-PS5-01792 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-IU-0010-CL01 | TZ-MID-68-WPR2-151112 Cable trench installation to be complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1793 | PL-PS5-01793 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-IU-0011-CL01 | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1794 | PL-PS5-01794 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-IU-0011-CL01 | TZ-MID-68-WPR2-151112 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1795 | PL-PS5-01795 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-IU-0011-CL01 | TZ-MID-68-WPR2-151112 Vertical Cable ladder to be install at transformer side PS5-61-IU-0011 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1796 | PL-PS5-01796 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-IU-0011-CL01 | TZ-MID-68-WPR2-151112 Cable trench installation to be complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1797 | PL-PS5-01797 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-IU-0011-CL02 | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1798 | PL-PS5-01798 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-IU-0011-CL02 | TZ-MID-68-WPR2-151112 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1799 | PL-PS5-01799 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-IU-0011-CL02 | TZ-MID-68-WPR2-151112 Vertical Cable ladder to be install at transformer side PS5-61-IU-0011 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1800 | PL-PS5-01800 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | Transformer area | PS5-61-IU-0011-CL02 | TZ-MID-68-WPR2-151112 Cable trench installation to be complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1801 | PL-PS5-01801 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | CFO Service tank area | PS5-71-HE-2200-CD01 | TZ-MID-68-WPR2-151112,151111,151115 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1802 | PL-PS5-01802 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | CFO Service tank area | PS5-71-HE-2200-CD01 | TZ-MID-68-WPR2-151112,151111,151115 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1803 | PL-PS5-01803 | #N/A | CPP-RFI-68-331-05-0239 | PS5 | Electrical Cable Installation | CFO Service tank area | PS5-71-HE-2200-CD01 | TZ-MID-68-WPR2-151112,151111,151115 Field run cable tray not yet complete installation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-01 | CPP EIT | Gao Chong |  |  |  |  | Open
1804 | PL-PS5-01804 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Generator building | PS5-71-BI-2118-CC01 | Doc.TZ-MID-68-WPR2-161500 -Cable coiled (130 MTR ),Cable tray not yet installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1805 | PL-PS5-01805 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Generator building | PS5-71-BI-2119-CC01 | Doc.TZ-MID-68-WPR2-161500 -Cable coiled (100 MTR ),Cable tray not yet installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1806 | PL-PS5-01806 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Generator building | PS5-71-BI-2120-CC01 | Doc.TZ-MID-68-WPR2-161500 -Cable coiled (180 MTR ),Cable tray not yet installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1807 | PL-PS5-01807 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Generator building | PS5-71-BI-2121-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled 155mtr,Cable tray not yet installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1808 | PL-PS5-01808 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | LP | PS5-50-IE-0002-CC01 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled 550mtr,Cable to be laid in trench | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1809 | PL-PS5-01809 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | LP | PS5-50-IE-0002-CC02 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled 550mtr,Cable to be laid in trench | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1810 | PL-PS5-01810 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | LP | PS5-50-IE-0002-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled 550mtr,Cable to be laid in trench | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1811 | PL-PS5-01811 | #N/A | CPP-RFI-68-64-04-0043 | PS5 | Instrument Cable installation | Warehouse Bldg HCP | PS5-09-LB-0007-CX01 | Doc.TZ-MID-68-WPR2-161500 - Cable coiled 155mtr,Cable to be laid in trench | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-04-30 | CPP EIT | Gao Chong |  |  |  |  | Open
1812 | PL-PS5-01812 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Near CRO Gen Area | PS5-28-DM-3700A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1813 | PL-PS5-01813 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Near CRO Gen Area | PS5-28-DM-3700A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1814 | PL-PS5-01814 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Near CRO Gen Area | PS5-28-DM-3700A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Field run cable tray to be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1815 | PL-PS5-01815 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Closed Drain Drum Power Gen | PS5-60-DM-3400-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1816 | PL-PS5-01816 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Closed Drain Drum Power Gen | PS5-60-DM-3400-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1817 | PL-PS5-01817 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Closed Drain Drum Power Gen | PS5-60-DM-3400-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Need to open cable trench at field side (PS5-88-BU-LV-00156) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1818 | PL-PS5-01818 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Closed Drain Drum Power Gen | PS5-60-DM-3400-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 To be laid into the conduit field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1819 | PL-PS5-01819 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Closed Drain Drum Power Gen | PS5-60-IES-3400-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1820 | PL-PS5-01820 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Closed Drain Drum Power Gen | PS5-60-IES-3400-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1821 | PL-PS5-01821 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Closed Drain Drum Power Gen | PS5-60-IES-3400-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Need to open cable trench at field side (PS5-88-BU-LV-00156) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1822 | PL-PS5-01822 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Closed Drain Drum Power Gen | PS5-60-IES-3400-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 To be laid into the conduit field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1823 | PL-PS5-01823 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IJ-0001-CD33 | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1824 | PL-PS5-01824 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IJ-0001-CD33 | TZ-MID-68-WPR2-151112 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1825 | PL-PS5-01825 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IJ-0001-CD33 | TZ-MID-68-WPR2-151112 Cable trench installation to be complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1826 | PL-PS5-01826 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IJ-0001-CD33 | TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1827 | PL-PS5-01827 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IK-0001-CG01 | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1828 | PL-PS5-01828 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IK-0001-CG01 | TZ-MID-68-WPR2-151112 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1829 | PL-PS5-01829 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IK-0001-CG01 | TZ-MID-68-WPR2-151112 Cable trench installation to be complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1830 | PL-PS5-01830 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IK-0001-CG01 | TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1831 | PL-PS5-01831 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IK-0001-CL33 | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1832 | PL-PS5-01832 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IK-0001-CL33 | TZ-MID-68-WPR2-151112 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1833 | PL-PS5-01833 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IK-0001-CL33 | TZ-MID-68-WPR2-151112 Cable trench installation to be complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1834 | PL-PS5-01834 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IK-0001-CL33 | TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1835 | PL-PS5-01835 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IK-0001-CL34 | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1836 | PL-PS5-01836 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IK-0001-CL34 | TZ-MID-68-WPR2-151112 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1837 | PL-PS5-01837 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IK-0001-CL34 | TZ-MID-68-WPR2-151112 Cable trench installation to be complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1838 | PL-PS5-01838 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IK-0001-CL34 | TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1839 | PL-PS5-01839 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IK-0001-CL45 | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1840 | PL-PS5-01840 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IK-0001-CL45 | TZ-MID-68-WPR2-151112 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1841 | PL-PS5-01841 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IK-0001-CL45 | TZ-MID-68-WPR2-151112 Cable trench installation to be complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1842 | PL-PS5-01842 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-IK-0001-CL45 | TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1843 | PL-PS5-01843 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-NER-0010-CL01 | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
1844 | PL-PS5-01844 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-NER-0010-CL01 | TZ-MID-68-WPR2-151112 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1845 | PL-PS5-01845 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-NER-0010-CL01 | TZ-MID-68-WPR2-151112 Cable trench installation to be complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1846 | PL-PS5-01846 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-NER-0010-CL01 | TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1847 | PL-PS5-01847 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-NER-0011-CL01 | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1848 | PL-PS5-01848 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-NER-0011-CL01 | TZ-MID-68-WPR2-151112 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1849 | PL-PS5-01849 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-NER-0011-CL01 | TZ-MID-68-WPR2-151112 Cable trench installation to be complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1850 | PL-PS5-01850 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-61-NER-0011-CL01 | TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1851 | PL-PS5-01851 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-63-IV-0010-CL01 | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1852 | PL-PS5-01852 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-63-IV-0010-CL01 | TZ-MID-68-WPR2-151112 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1853 | PL-PS5-01853 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-63-IV-0010-CL01 | TZ-MID-68-WPR2-151112 Cable trench installation to be complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1854 | PL-PS5-01854 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-63-IV-0010-CL01 | TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1855 | PL-PS5-01855 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-63-IV-0011-CL01 | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1856 | PL-PS5-01856 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-63-IV-0011-CL01 | TZ-MID-68-WPR2-151112 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1857 | PL-PS5-01857 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-63-IV-0011-CL01 | TZ-MID-68-WPR2-151112 Cable trench installation to be complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1858 | PL-PS5-01858 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-63-IV-0011-CL01 | TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1859 | PL-PS5-01859 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-63-NER-0010-CL01 | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1860 | PL-PS5-01860 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-63-NER-0010-CL01 | TZ-MID-68-WPR2-151112 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1861 | PL-PS5-01861 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-63-NER-0010-CL01 | TZ-MID-68-WPR2-151112 Cable trench installation to be complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1862 | PL-PS5-01862 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-63-NER-0010-CL01 | TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1863 | PL-PS5-01863 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-63-NER-0011-CL01 | TZ-MID-68-WPR2-151112 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1864 | PL-PS5-01864 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-63-NER-0011-CL01 | TZ-MID-68-WPR2-151112 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1865 | PL-PS5-01865 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-63-NER-0011-CL01 | TZ-MID-68-WPR2-151112 Cable trench installation to be complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1866 | PL-PS5-01866 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | Transformer Near EITS | PS5-63-NER-0011-CL01 | TZ-MID-68-WPR2-151112 Vertical cable ladder at trafo side not yet install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1867 | PL-PS5-01867 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-IV-0012-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1868 | PL-PS5-01868 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-IV-0012-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1869 | PL-PS5-01869 | #N/A | CPP-RFI-68-331-05-0240 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-IV-0012-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Cable Trench PS5-88-BU-LV-00102 To be complete installation. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-02 | CPP EIT | Gao Chong |  |  |  |  | Open
1870 | PL-PS5-01870 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CG01 | TZ-MID-68-WPR2-151111 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 16-06-2053 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
1871 | PL-PS5-01871 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CG01 | TZ-MID-68-WPR2-151111 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1872 | PL-PS5-01872 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CG01 | TZ-MID-68-WPR2-151111 Cable ladder not yet install at EDG side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1873 | PL-PS5-01873 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IE-0002-CD01 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1874 | PL-PS5-01874 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IE-0002-CD01 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1875 | PL-PS5-01875 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IE-0002-CD01 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1876 | PL-PS5-01876 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IE-0002-CD01 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0010) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1877 | PL-PS5-01877 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IJ-0001-CD04 | TZ-MID-68-WPR2-151167, 151116,151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1878 | PL-PS5-01878 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IJ-0001-CD04 | TZ-MID-68-WPR2-151167, 151116,151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1879 | PL-PS5-01879 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IJ-0001-CD04 | TZ-MID-68-WPR2-151167, 151116,151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1880 | PL-PS5-01880 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD35 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1881 | PL-PS5-01881 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD35 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1882 | PL-PS5-01882 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD35 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1883 | PL-PS5-01883 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD35 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0010) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1884 | PL-PS5-01884 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0010-CL01 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1885 | PL-PS5-01885 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0010-CL01 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1886 | PL-PS5-01886 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0010-CL01 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1887 | PL-PS5-01887 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0010-CL01 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0010) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1888 | PL-PS5-01888 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0011-CL01 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1889 | PL-PS5-01889 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0011-CL01 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1890 | PL-PS5-01890 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0011-CL01 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1891 | PL-PS5-01891 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0011-CL01 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0011) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1892 | PL-PS5-01892 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IK-0001-CG02 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1893 | PL-PS5-01893 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IK-0001-CG02 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1894 | PL-PS5-01894 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IK-0001-CG02 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1895 | PL-PS5-01895 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IK-0001-CG02 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0011) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1896 | PL-PS5-01896 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IK-0001-CG03 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1897 | PL-PS5-01897 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IK-0001-CG03 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1898 | PL-PS5-01898 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IK-0001-CG03 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1899 | PL-PS5-01899 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IK-0001-CG03 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0011) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1900 | PL-PS5-01900 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IK-0001-CG04 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-23 | Konstantin | 2026-05-24 |  | CLOSED
1901 | PL-PS5-01901 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IK-0001-CG04 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1902 | PL-PS5-01902 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IK-0001-CG04 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1903 | PL-PS5-01903 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IK-0001-CG04 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0011) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1904 | PL-PS5-01904 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IU-0010-CL02 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1905 | PL-PS5-01905 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IU-0010-CL02 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1906 | PL-PS5-01906 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IU-0010-CL02 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1907 | PL-PS5-01907 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IU-0010-CL02 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0010) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1908 | PL-PS5-01908 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IE-0002-CD05 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1909 | PL-PS5-01909 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IE-0002-CD05 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1910 | PL-PS5-01910 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IE-0002-CD05 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1911 | PL-PS5-01911 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IE-0002-CD05 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0011) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1912 | PL-PS5-01912 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD01 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1913 | PL-PS5-01913 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD01 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1914 | PL-PS5-01914 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD01 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1915 | PL-PS5-01915 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD01 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0010) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1916 | PL-PS5-01916 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD34 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1917 | PL-PS5-01917 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD34 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1918 | PL-PS5-01918 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD34 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1919 | PL-PS5-01919 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD34 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IV-0001B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1920 | PL-PS5-01920 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD38 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1921 | PL-PS5-01921 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD38 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1922 | PL-PS5-01922 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD38 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1923 | PL-PS5-01923 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD38 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-ISR-0102) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1924 | PL-PS5-01924 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CL01 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1925 | PL-PS5-01925 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CL01 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1926 | PL-PS5-01926 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CL01 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1927 | PL-PS5-01927 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CL01 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-63-NER-0010) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1928 | PL-PS5-01928 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CL02 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1929 | PL-PS5-01929 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CL02 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1930 | PL-PS5-01930 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CL02 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1931 | PL-PS5-01931 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CL02 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-63-NER-0011) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1932 | PL-PS5-01932 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IE-0002-CD04 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1933 | PL-PS5-01933 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IE-0002-CD04 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1934 | PL-PS5-01934 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IE-0002-CD04 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1935 | PL-PS5-01935 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IE-0002-CD04 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0011) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1936 | PL-PS5-01936 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD39 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1937 | PL-PS5-01937 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD39 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1938 | PL-PS5-01938 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD39 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1939 | PL-PS5-01939 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD39 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0010) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1940 | PL-PS5-01940 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD40 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1941 | PL-PS5-01941 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD40 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1942 | PL-PS5-01942 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD40 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1943 | PL-PS5-01943 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IJ-0001-CD40 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0011) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1944 | PL-PS5-01944 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IE-0002-CD03 | TZ-MID-68-WPR2-151112 SS Permanent Cable Tag Not Yet Install Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1945 | PL-PS5-01945 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IE-0002-CD03 | TZ-MID-68-WPR2-151112 Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1946 | PL-PS5-01946 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IE-0002-CD03 | TZ-MID-68-WPR2-151112 Cable Trench Installation not yet done | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-04 | CPP EIT | Gao Chong |  |  |  |  | Open
1947 | PL-PS5-01947 | #N/A | CPP-RFI-68-331-05-0243 | PS5 | Electrical Cable Installation | Transformer area Outside EITS | PS5-61-IE-0002-CD03 | TZ-MID-68-WPR2-151112 Cable ladder not yet install at Trafo side (PS5-61-IU-0010) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | Open
1948 | PL-PS5-01948 | #N/A | CPP-RFI-68-64-03-0044 | PS5 | Instrument Cable Ladder Installation | Utility/Fire water Tank and Export pump VSD area | N/A | Doc.TZ-MID-68-WPR2-161500 - Earth jumper not installed completely | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | Open
1949 | PL-PS5-01949 | #N/A | CPP-RFI-68-64-03-0044 | PS5 | Instrument Cable Ladder Installation | Utility/Fire water Tank and Export pump VSD area | N/A | Doc.TZ-MID-68-WPR2-161500 - Hold down Clamp not Installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | Open
1950 | PL-PS5-01950 | #N/A | CPP-RFI-68-64-03-0044 | PS5 | Instrument Cable Ladder Installation | Utility/Fire water Tank and Export pump VSD area | N/A | Doc.TZ-MID-68-WPR2-161500 - Cover not installed | C | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | Open
1951 | PL-PS5-01951 | #N/A | CPP-RFI-68-64-03-0044 | PS5 | Instrument Cable Ladder Installation | Utility/Fire water Tank and Export pump VSD area | N/A | Doc.TZ-MID-68-WPR2-161500 - Corrosion need to be removed | C | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | Open
1952 | PL-PS5-01952 | #N/A | CPP-RFI-68-64-03-0044 | PS5 | Instrument Cable Ladder Installation | Utility/Fire water Tank and Export pump VSD area | N/A | Doc.TZ-MID-68-WPR2-161500 - Bolts tightening on connection plates to be completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | Open
1953 | PL-PS5-01953 | #N/A | CPP-RFI-68-64-03-0044 | PS5 | Instrument Cable Ladder Installation | Utility/Fire water Tank and Export pump VSD area | N/A | Doc.TZ-MID-68-WPR2-161500 - Grommets not installed | C | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | Open
1954 | PL-PS5-01954 | #N/A | CPP-RFI-68-33/1-03-0245 | PS5 | Electrical cable ladder/Tray installation | Utility/Fire water Tank and Export pump VSD area and CFO area | N/A | Doc.TZ-MID-68-WPR2-151108,TZ-MID-68-WPR2-151111,TZ-MID-68-WPR2-151115 - Corrosion need to be removed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | Open
1955 | PL-PS5-01955 | #N/A | CPP-RFI-68-33/1-03-0245 | PS5 | Electrical cable ladder/Tray installation | Utility/Fire water Tank and Export pump VSD area and CFO area | N/A | Doc.TZ-MID-68-WPR2-151108,TZ-MID-68-WPR2-151111,TZ-MID-68-WPR2-151115 - Bolts tightening on connection plates to be completed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | Open
1956 | PL-PS5-01956 | #N/A | CPP-RFI-68-33/1-03-0245 | PS5 | Electrical cable ladder/Tray installation | Utility/Fire water Tank and Export pump VSD area and CFO area | N/A | Doc.TZ-MID-68-WPR2-151109,TZ-MID-68-WPR2-151111,TZ-MID-68-WPR2-151115- Hold down Clamp not Installed yet | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | Open
1957 | PL-PS5-01957 | #N/A | CPP-RFI-68-33/1-03-0245 | PS5 | Electrical cable ladder/Tray installation | Utility/Fire water Tank and Export pump VSD area and CFO area | N/A | Doc.TZ-MID-68-WPR2-151109,TZ-MID-68-WPR2-151111,TZ-MID-68-WPR2-151115 Earth jumper not installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | Open
1958 | PL-PS5-01958 | #N/A | CPP-RFI-68-33/1-03-0245 | PS5 | Electrical cable ladder/Tray installation | Utility/Fire water Tank and Export pump VSD area and CFO area | N/A | Doc.TZ-MID-68-WPR2-151109,TZ-MID-68-WPR2-151111,TZ-MID-68-WPR2-151115 Cover not installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | Open
1959 | PL-PS5-01959 | #N/A | CPP-RFI-68-33/1-03-0245 | PS5 | Electrical cable ladder/Tray installation | Utility/Fire water Tank and Export pump VSD area and CFO area | N/A | Doc.TZ-MID-68-WPR2-151109,TZ-MID-68-WPR2-151111,TZ-MID-68-WPR2-151115 Earth strap not installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | Open
1960 | PL-PS5-01960 | #N/A | CPP-RFI-68-33/1-03-0245 | PS5 | Electrical cable ladder/Tray installation | Utility/Fire water Tank and Export pump VSD area and CFO area | N/A | Doc.TZ-MID-68-WPR2-151109,TZ-MID-68-WPR2-151111,TZ-MID-68-WPR2-151115 Grommets not installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1961 | PL-PS5-01961 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Diesel fuel Storage and Pump area | PS5-62-IA-0403-12SW-CL01 | Doc.TZ-MID-68-WPR2-151125 Cable dressing not completed | c | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | Open
1962 | PL-PS5-01962 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Utility area | PS5-62-IB-0401-12SW-CL01 | Doc.TZ-MID-68-WPR2-151126, Cable dressing not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1963 | PL-PS5-01963 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Utility area | PS5-62-IB-0402-12SW-CL01 | Doc.TZ-MID-68-WPR2-151126, Cable dressing not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1964 | PL-PS5-01964 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Export Pump VSD area | PS5-62-BE-0704-09KA-CL01 | Doc. TZ-MID-68-WPR2-151129 Cable dressing not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1965 | PL-PS5-01965 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Utility area | PS5-62-BE-0701-03KA-CL01 | Doc.TZ-MID-68-WPR2-151126 Cable dressing not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1966 | PL-PS5-01966 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Export Pump VSD area | PS5-62-BE-0703-10KA-CL01 | Doc.TZ-MID-68-WPR2-151129 Cable dressing not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1967 | PL-PS5-01967 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Export Pump VSD area | PS5-62-BE-0707-01KA-CL01 | Doc.TZ-MID-68-WPR2-151129 Cable dressing not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1968 | PL-PS5-01968 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Export Loading Pump area | PS5-62-BE-0602-08KA-CL01 | Doc.TZ-MID-68-WPR2-151132 Cable dressing not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1969 | PL-PS5-01969 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Utility/Fire Water Storage tank | PS5-62-BE-0604-07KA-CL01 | Doc.TZ-MID-68-WPR2-151127 Cable dressing not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1970 | PL-PS5-01970 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Fence west area | PS5-62-BE-0701-01KB-CL01 | Doc.TZ-MID-68-WPR2-151137 Cable dressing not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1971 | PL-PS5-01971 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Utility area | PS5-62-BE-0405-06-CL01 | Doc.TZ-MID-68-WPR2-151129 Cable dressing not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1972 | PL-PS5-01972 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Chemical and waste Storage area | PS5-62-BE-0701-02KA-CL01 | Doc.TZ-MID-68-WPR2-151123 Cable dressing not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1973 | PL-PS5-01973 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Chemical and waste Storage area | PS5-62-BE-0702-02KA-CL01 | Doc.TZ-MID-68-WPR2-151123 Cable dressing not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1974 | PL-PS5-01974 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Export Pump VSD area | PS5-62-BE-0704-09KA-CL01 | TZ-MID-68-WPR2-151129 Cable tagging not completed |  | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1975 | PL-PS5-01975 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Diesel fuel Storage and Pump area | PS5-62-IA-0403-12SW-CL01 | Doc.TZ-MID-68-WPR2-151125 Cable tagging not completed | c | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1976 | PL-PS5-01976 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Utility area | PS5-62-IB-0401-12SW-CL01 | Doc.TZ-MID-68-WPR2-151126, Cable tagging not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1977 | PL-PS5-01977 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Utility area | PS5-62-IB-0402-12SW-CL01 | Doc.TZ-MID-68-WPR2-151126, Cable tagging not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1978 | PL-PS5-01978 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Export Pump VSD area | PS5-62-BE-0704-09KA-CL01 | Doc. TZ-MID-68-WPR2-151129 Cable tagging not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1979 | PL-PS5-01979 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Utility area | PS5-62-BE-0701-03KA-CL01 | Doc.TZ-MID-68-WPR2-151126 Cable tagging not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1980 | PL-PS5-01980 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Export Pump VSD area | PS5-62-BE-0703-10KA-CL01 | Doc.TZ-MID-68-WPR2-151129 Cable tagging not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1981 | PL-PS5-01981 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Export Pump VSD area | PS5-62-BE-0707-01KA-CL01 | Doc.TZ-MID-68-WPR2-151129 Cable tagging not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1982 | PL-PS5-01982 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Export Loading Pump area | PS5-62-BE-0602-08KA-CL01 | Doc.TZ-MID-68-WPR2-151132 Cable tagging not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1983 | PL-PS5-01983 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Utility/Fire Water Storage tank | PS5-62-BE-0604-07KA-CL01 | Doc.TZ-MID-68-WPR2-151127 Cable tagging not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1984 | PL-PS5-01984 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Fence west area | PS5-62-BE-0701-01KB-CL01 | Doc.TZ-MID-68-WPR2-151137 Cable tagging not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1985 | PL-PS5-01985 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Utility area | PS5-62-BE-0405-06-CL01 | Doc.TZ-MID-68-WPR2-151129 Cable tagging not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1986 | PL-PS5-01986 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Chemical and waste Storage area | PS5-62-BE-0701-02KA-CL01 | Doc.TZ-MID-68-WPR2-151123 Cable tagging not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1987 | PL-PS5-01987 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Chemical and waste Storage area | PS5-62-BE-0702-02KA-CL01 | Doc.TZ-MID-68-WPR2-151123 Cable tagging not completed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
1988 | PL-PS5-01988 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100B-CG01 | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Permanent cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
1989 | PL-PS5-01989 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100B-CG01 | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
1990 | PL-PS5-01990 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100B-CG01 | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable actual laid in the HV Cable trench PS5-88-CU-HV-0002 in drawing mention PS5-88-CU-LV-0011 need to be RLMU drawing as per actual. (Dwg No.TZ-MID-68-WPR2-151114) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
1991 | PL-PS5-01991 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100B-CG02 | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Permanent cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1992 | PL-PS5-01992 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100B-CG02 | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
1993 | PL-PS5-01993 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100B-CG02 | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable actual laid in the HV Cable trench PS5-88-CU-HV-0002 in drawing mention PS5-88-CU-LV-0011 need to be RLMU drawing as per actual. (Dwg No.TZ-MID-68-WPR2-151114) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
1994 | PL-PS5-01994 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100C-CG01 | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Permanent cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1995 | PL-PS5-01995 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100C-CG01 | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
1996 | PL-PS5-01996 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100C-CG01 | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable actual laid in the HV Cable trench PS5-88-CU-HV-0001 in drawing mention PS5-88-CU-LV-0012 need to be RLMU drawing as per actual. (Dwg No.TZ-MID-68-WPR2-151114) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
1997 | PL-PS5-01997 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100C-CG02 | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Permanent cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
1998 | PL-PS5-01998 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100C-CG02 | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
1999 | PL-PS5-01999 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100C-CG02 | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable actual laid in the HV Cable trench PS5-88-CU-HV-0001 in drawing mention PS5-88-CU-LV-0012 need to be RLMU drawing as per actual. (Dwg No.TZ-MID-68-WPR2-151114) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2000 | PL-PS5-02000 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Reinjection Pump A | PS5-28-DM-3900A-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114,151113 Cable Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2001 | PL-PS5-02001 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-HE-2200-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151118 SS Permanent cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong | 2026-05-20 | Konstantin | 2026-05-24 |  | CLOSED
2002 | PL-PS5-02002 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-HE-2200-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151118 Cable Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2003 | PL-PS5-02003 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Closed Drain Drum Area | PS5-28-HE-2200-CD01 | TZ-MID-68-WPR2-151112,151111,151115,151118 Field cable ladder not yet complete installation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2004 | PL-PS5-02004 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | VSD E-house | PS5-61-IDH-3100A-CL01 | TZ-MID-68-WPR2-151112,151111 Cable Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2005 | PL-PS5-02005 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | VSD E-house | PS5-61-IDH-3100B-CL01 | TZ-MID-68-WPR2-151112,151111 SS Permanent cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
2006 | PL-PS5-02006 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | VSD E-house | PS5-61-IDH-3100B-CL01 | TZ-MID-68-WPR2-151112,151111 Cable Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2007 | PL-PS5-02007 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | VSD E-house | PS5-61-IDH-3100C-CL01 | TZ-MID-68-WPR2-151112,151111 SS Permanent cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
2008 | PL-PS5-02008 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | VSD E-house | PS5-61-IDH-3100C-CL01 | TZ-MID-68-WPR2-151112,151111 Cable Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2009 | PL-PS5-02009 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL33 | TZ-MID-68-WPR2-151116 SS Permanent cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2010 | PL-PS5-02010 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL33 | TZ-MID-68-WPR2-151116 Cable Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2011 | PL-PS5-02011 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL33 | TZ-MID-68-WPR2-151116 Cable ladder at transformer side not yet install PS5-61-IV-0007A | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2012 | PL-PS5-02012 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL33 | TZ-MID-68-WPR2-151116 Cable trench not yet complete termination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2013 | PL-PS5-02013 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL34 | TZ-MID-68-WPR2-151116 SS Permanent cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2014 | PL-PS5-02014 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL34 | TZ-MID-68-WPR2-151116 Cable Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2015 | PL-PS5-02015 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL34 | TZ-MID-68-WPR2-151116 Cable ladder at transformer side not yet install PS5-61-IV-0007B | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2016 | PL-PS5-02016 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Gen Electrical Building | PS5-61-IK-0006-CL34 | TZ-MID-68-WPR2-151116 Cable trench not yet complete termination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2017 | PL-PS5-02017 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-NER-0010-CH01 | TZ-MID-68-WPR2-151112 Cable Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2018 | PL-PS5-02018 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-NER-0010-CH01 | TZ-MID-68-WPR2-151112 Cable ladder at transformer side not yet install PS5-61-IU-0010 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2019 | PL-PS5-02019 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-NER-0010-CH01 | TZ-MID-68-WPR2-151112 Cable trench not yet complete termination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2020 | PL-PS5-02020 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-NER-0011-CH01 | TZ-MID-68-WPR2-151112 Cable Dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2021 | PL-PS5-02021 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-NER-0011-CH01 | TZ-MID-68-WPR2-151112 Cable ladder at transformer side not yet install PS5-61-IU-0011 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2022 | PL-PS5-02022 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-NER-0011-CH01 | TZ-MID-68-WPR2-151112 Cable trench not yet complete termination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2023 | PL-PS5-02023 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0001-CH01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2024 | PL-PS5-02024 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0001-CH01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2025 | PL-PS5-02025 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0001-CH01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2026 | PL-PS5-02026 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0001-CH02 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2027 | PL-PS5-02027 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0001-CH02 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2028 | PL-PS5-02028 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0001-CH02 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2029 | PL-PS5-02029 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0001-CH03 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2030 | PL-PS5-02030 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0001-CH03 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2031 | PL-PS5-02031 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0001-CH03 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2032 | PL-PS5-02032 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0002-CH01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2033 | PL-PS5-02033 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0002-CH01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2034 | PL-PS5-02034 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0002-CH01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2035 | PL-PS5-02035 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0002-CH02 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2036 | PL-PS5-02036 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0002-CH02 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2037 | PL-PS5-02037 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0002-CH02 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2038 | PL-PS5-02038 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0002-CH03 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Cable Dressing to be done at both side with trefoil formation | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2039 | PL-PS5-02039 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0002-CH03 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Field run cable tray PS5-88-LD-HV-4501 not yet complete installation. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2040 | PL-PS5-02040 | #N/A | CPP-RFI-68-331-05-0244 | PS5 | Electrical Cable Installation | Near export pump area | PS5-79-BH-0002-CH03 | TZ-MID-68-WPR2-151112,151111,151115,151117,151114 Need to open Field run cable trench PS5-88-BU-HV-0008. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-06 | CPP EIT | Gao Chong |  |  |  |  | Open
2041 | PL-PS5-02041 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Utility area | PS5-62-IB-0401-12SW-CL01 | Doc.TZ-MID-68-WPR2-151126, Backfilling not yet completed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
2042 | PL-PS5-02042 | #N/A | CPP-RFI-68-33/1-05-0241 | PS5 | Lighting Cable Installation | Utility area | PS5-62-IB-0402-12SW-CL01 | Doc.TZ-MID-68-WPR2-151126, Backfilling not yet completed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-05 | CPP EIT | Gao Chong |  |  |  |  | OPEN
2043 | PL-PS5-02043 | #N/A | CPP-RFI-68-33/1-03-0252 | PS5 | Electrical cable ladder/Tray installation | Generator Electrical Building | N/A | Doc.TZ-MID-68-WPR2-151167 Bolts tightening on connection plates to be completed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | OPEN
2044 | PL-PS5-02044 | #N/A | CPP-RFI-68-33/1-03-0252 | PS5 | Electrical cable ladder/Tray installation | Generator Electrical Building | N/A | Doc.TZ-MID-68-WPR2-151167 Hold down Clamp not Installed yet | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | OPEN
2045 | PL-PS5-02045 | #N/A | CPP-RFI-68-33/1-03-0252 | PS5 | Electrical cable ladder/Tray installation | Generator Electrical Building | N/A | Doc.TZ-MID-68-WPR2-151167 Earth jumper not installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | OPEN
2046 | PL-PS5-02046 | #N/A | CPP-RFI-68-33/1-03-0252 | PS5 | Electrical cable ladder/Tray installation | Generator Electrical Building | N/A | Doc.TZ-MID-68-WPR2-151167 TZ-MID-68-WPR2-151115 Cover not installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | OPEN
2047 | PL-PS5-02047 | #N/A | CPP-RFI-68-33/1-03-0252 | PS5 | Electrical cable ladder/Tray installation | Generator Electrical Building | N/A | Doc.TZ-MID-68-WPR2-151167 Earth strap not installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | OPEN
2048 | PL-PS5-02048 | #N/A | CPP-RFI-68-33/1-03-0252 | PS5 | Electrical cable ladder/Tray installation | Generator Electrical Building | N/A | Doc.TZ-MID-68-WPR2-151167 Grommets not installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | OPEN
2049 | PL-PS5-02049 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL19 | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
2050 | PL-PS5-02050 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL19 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2051 | PL-PS5-02051 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL19 | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2052 | PL-PS5-02052 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL19 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2053 | PL-PS5-02053 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL20 | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
2054 | PL-PS5-02054 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL20 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2055 | PL-PS5-02055 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL20 | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2056 | PL-PS5-02056 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL20 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2057 | PL-PS5-02057 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL21 | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
2058 | PL-PS5-02058 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL21 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2059 | PL-PS5-02059 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL21 | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2060 | PL-PS5-02060 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL21 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2061 | PL-PS5-02061 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL22 | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
2062 | PL-PS5-02062 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL22 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2063 | PL-PS5-02063 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL22 | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2064 | PL-PS5-02064 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL22 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2065 | PL-PS5-02065 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL23 | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
2066 | PL-PS5-02066 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL23 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2067 | PL-PS5-02067 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL23 | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2068 | PL-PS5-02068 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL23 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2069 | PL-PS5-02069 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL24 | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
2070 | PL-PS5-02070 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL24 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2071 | PL-PS5-02071 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL24 | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2072 | PL-PS5-02072 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL24 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2073 | PL-PS5-02073 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL25 | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
2074 | PL-PS5-02074 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL25 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2075 | PL-PS5-02075 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL25 | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2076 | PL-PS5-02076 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL25 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2077 | PL-PS5-02077 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL26 | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
2078 | PL-PS5-02078 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL26 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2079 | PL-PS5-02079 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL26 | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2080 | PL-PS5-02080 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL26 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2081 | PL-PS5-02081 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL27 | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
2082 | PL-PS5-02082 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL27 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2083 | PL-PS5-02083 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL27 | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2084 | PL-PS5-02084 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL27 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2085 | PL-PS5-02085 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL28 | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
2086 | PL-PS5-02086 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL28 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2087 | PL-PS5-02087 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL28 | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2088 | PL-PS5-02088 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL28 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2089 | PL-PS5-02089 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL29 | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2090 | PL-PS5-02090 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL29 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2091 | PL-PS5-02091 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL29 | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2092 | PL-PS5-02092 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL29 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2093 | PL-PS5-02093 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL30 | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2094 | PL-PS5-02094 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL30 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2095 | PL-PS5-02095 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL30 | TZ-MID-68-WPR2-151112 Cable ladder to be install at trafo side (PS5-61-IV-0001B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2096 | PL-PS5-02096 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Transformer Area Outside EITS | PS5-61-IK-0001-CL30 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0022) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2097 | PL-PS5-02097 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL37 | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2098 | PL-PS5-02098 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL37 | TZ-MID-68-WPR2-151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2099 | PL-PS5-02099 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL37 | TZ-MID-68-WPR2-151116 Cable ladder to be install at trafo side (PS5-61-IV-0002A) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2100 | PL-PS5-02100 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL37 | TZ-MID-68-WPR2-151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0020, PS5-88-BU-LV-00160) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2101 | PL-PS5-02101 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL38 | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2102 | PL-PS5-02102 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL38 | TZ-MID-68-WPR2-151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2103 | PL-PS5-02103 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL38 | TZ-MID-68-WPR2-151116 Cable ladder to be install at trafo side (PS5-61-IV-0002A) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2104 | PL-PS5-02104 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL38 | TZ-MID-68-WPR2-151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0020, PS5-88-BU-LV-00160) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2105 | PL-PS5-02105 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL39 | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2106 | PL-PS5-02106 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL39 | TZ-MID-68-WPR2-151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2107 | PL-PS5-02107 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL39 | TZ-MID-68-WPR2-151116 Cable ladder to be install at trafo side (PS5-61-IV-0002A) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2108 | PL-PS5-02108 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL39 | TZ-MID-68-WPR2-151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0020, PS5-88-BU-LV-00160) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2109 | PL-PS5-02109 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL40 | TZ-MID-68-WPR2-151112 Permanent SS Cable Tag Not Yet Install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2110 | PL-PS5-02110 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL40 | TZ-MID-68-WPR2-151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2111 | PL-PS5-02111 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL40 | TZ-MID-68-WPR2-151116 Cable ladder to be install at trafo side (PS5-61-IV-0002A) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2112 | PL-PS5-02112 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL40 | TZ-MID-68-WPR2-151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-LV-0020, PS5-88-BU-LV-00160) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2113 | PL-PS5-02113 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL43 | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2114 | PL-PS5-02114 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL43 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2115 | PL-PS5-02115 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL43 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2116 | PL-PS5-02116 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL45 | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2117 | PL-PS5-02117 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL45 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2118 | PL-PS5-02118 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL45 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2119 | PL-PS5-02119 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL46 | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2120 | PL-PS5-02120 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL46 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2121 | PL-PS5-02121 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL46 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2122 | PL-PS5-02122 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL47 | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2123 | PL-PS5-02123 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL47 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2124 | PL-PS5-02124 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL47 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2125 | PL-PS5-02125 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL48 | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2126 | PL-PS5-02126 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL48 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2127 | PL-PS5-02127 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL48 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2128 | PL-PS5-02128 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL49 | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2129 | PL-PS5-02129 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL49 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2130 | PL-PS5-02130 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL49 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2131 | PL-PS5-02131 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL50 | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2132 | PL-PS5-02132 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL50 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2133 | PL-PS5-02133 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL50 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2134 | PL-PS5-02134 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL51 | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2135 | PL-PS5-02135 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL51 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2136 | PL-PS5-02136 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL51 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2137 | PL-PS5-02137 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL52 | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2138 | PL-PS5-02138 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL52 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2139 | PL-PS5-02139 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL52 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2140 | PL-PS5-02140 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL53 | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-19 | Konstantin | 2026-05-24 |  | CLOSED
2141 | PL-PS5-02141 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL53 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2142 | PL-PS5-02142 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL53 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2143 | PL-PS5-02143 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL54 | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS Cable tag not yet install at both end and every 30 meter at the underground cable trench. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong | 2026-05-22 | Konstantin | 2026-05-24 |  | CLOSED
2144 | PL-PS5-02144 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL54 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2145 | PL-PS5-02145 | #N/A | CPP-RFI-68-33/1-05-0250 | PS5 | Electrical Cable Installation | EDG Power JB | PS5-61-IK-0003-CL54 | TZ-MID-68-WPR2-151111, 151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-LV-0002, PS5-88-BU-HV-0013, PS5-88-DU-HV-0004, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-07 | CPP EIT | Gao Chong |  |  |  |  | Open
2146 | PL-PS5-02146 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Near Deluge skid | PS5-01-BE-0001-CL01 | TZ-MID-68-WPR2-151117 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2147 | PL-PS5-02147 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Near Deluge skid | PS5-01-BE-0001-CL01 | TZ-MID-68-WPR2-151117 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2148 | PL-PS5-02148 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Near Deluge skid | PS5-01-BE-0001-CL01 | TZ-MID-68-WPR2-151117 Need to Open trench at PS5-05-IG-0004 side (PS5-88-BU-LV-00165, PS5-88-BU-LV-00164). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2149 | PL-PS5-02149 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Near Deluge skid | PS5-01-BE-0001-CL01 | TZ-MID-68-WPR2-151117 Cable to be laid inside conduit at PS5-01-BE-0001 side. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2150 | PL-PS5-02150 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator Building | PS5-05-IG-0025-CD01 | TZ-MID-68-WPR2-151112, 151116 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 16-06-2054 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
2151 | PL-PS5-02151 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator Building | PS5-05-IG-0025-CD01 | TZ-MID-68-WPR2-151112, 151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2152 | PL-PS5-02152 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator Building | PS5-05-IG-0025-CD01 | TZ-MID-68-WPR2-151112, 151116 Field run cable tray installation not yet complete at DB L&SP side (PS5-05-IG-0025). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2153 | PL-PS5-02153 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator Building | PS5-05-IG-0025-CD01 | TZ-MID-68-WPR2-151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0012, PS5-88-BU-HV-0017, PS5-88-CU-HV-0039, PS5-88-CU-HV-0040). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2154 | PL-PS5-02154 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator Building | PS5-05-IG-0026-CD01 | TZ-MID-68-WPR2-151112, 151116 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 16-06-2055 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
2155 | PL-PS5-02155 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator Building | PS5-05-IG-0026-CD01 | TZ-MID-68-WPR2-151112, 151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2156 | PL-PS5-02156 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator Building | PS5-05-IG-0026-CD01 | TZ-MID-68-WPR2-151112, 151116 Field run cable tray installation not yet complete at DB L&SP side (PS5-05-IG-0025). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2157 | PL-PS5-02157 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator Building | PS5-05-IG-0026-CD01 | TZ-MID-68-WPR2-151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0029, PS5-88-BU-HV-0017, PS5-88-BU-HV-0013, PS5-88-BU-HV-0012). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2158 | PL-PS5-02158 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-0913-CS02 | TZ-MID-68-WPR2-151116, 151112 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 16-06-2056 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
2159 | PL-PS5-02159 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-0913-CS02 | TZ-MID-68-WPR2-151116, 151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2160 | PL-PS5-02160 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-0913-CS02 | TZ-MID-68-WPR2-151116, 151112 Field run cable tray installation not yet complete at field side (PS5-08-01FB-0913). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2161 | PL-PS5-02161 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-0913-CS02 | TZ-MID-68-WPR2-151116, 151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-HV-0039, PS5-88-BU-HV-0017, PS5-88-DU-HV-0004, PS5-88-BU-HV-0013, PS5-88-BU-HV-0012). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2162 | PL-PS5-02162 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-1013-CS02 | TZ-MID-68-WPR2-151116, 151112 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 16-06-2057 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
2163 | PL-PS5-02163 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-1013-CS02 | TZ-MID-68-WPR2-151116, 151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2164 | PL-PS5-02164 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-1013-CS02 | TZ-MID-68-WPR2-151116, 151112 Field run cable tray installation not yet complete at field side (PS5-08-01FB-1013). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2165 | PL-PS5-02165 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-1013-CS02 | TZ-MID-68-WPR2-151116, 151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-CU-HV-0040, PS5-88-CU-HV-0039, PS5-88-BU-HV-0017, PS5-88-BU-HV-0013, PS5-88-BU-HV-0012). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2166 | PL-PS5-02166 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-1101-CS01 | TZ-MID-68-WPR2-151112, 151116 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 16-06-2058 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
2167 | PL-PS5-02167 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-1101-CS01 | TZ-MID-68-WPR2-151112, 151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2168 | PL-PS5-02168 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-1101-CS01 | TZ-MID-68-WPR2-151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0012, PS5-88-BU-HV-0013, PS5-88-BU-HV-0017, PS5-88-CU-HV-0039, PS5-88-CU-HV-0041). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2169 | PL-PS5-02169 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-52BT-0138-CS01 | TZ-MID-68-WPR2-151112, 151120, 151122 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 16-06-2059 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
2170 | PL-PS5-02170 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-52BT-0138-CS01 | TZ-MID-68-WPR2-151112, 151120, 151122 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2171 | PL-PS5-02171 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-52BT-0138-CS01 | TZ-MID-68-WPR2-151112, 151120, 151122 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0001, PS5-88-BU-HV-0041, PS5-88-BU-HV-0006, PS5-88-BU-LV-0069, PS5-88-BU-LV-0060, PS5-88-BU-LV-0059, PS5-88-BU-LV-0067). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2172 | PL-PS5-02172 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100A-CG01 | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2173 | PL-PS5-02173 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100A-CG01 | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2174 | PL-PS5-02174 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100A-CG02 | TZ-MID-68-WPR2-151111,151115,151117,151114 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2175 | PL-PS5-02175 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Export Pump area | PS5-25-DM-3100A-CG02 | TZ-MID-68-WPR2-151111,151115,151117,151114 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2176 | PL-PS5-02176 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Oily Water Area | PS5-28-IES-3600A-CD01 | TZ-MID-68-WPR2-151112,151108,151111 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2177 | PL-PS5-02177 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Oily Water Area | PS5-28-IES-3600A-CD01 | TZ-MID-68-WPR2-151112,151108,151111 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2178 | PL-PS5-02178 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Oily Water Area | PS5-28-IES-3600A-CD01 | TZ-MID-68-WPR2-151112,151108,151111 Field run cable tray installation to be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2179 | PL-PS5-02179 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator control panel for generator set- 5 (E) | PS5-60-IE-0003E-CD06 | TZ-MID-68-WPR2-151112, 151116, 151167 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 16-06-2060 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
2180 | PL-PS5-02180 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator control panel for generator set- 5 (E) | PS5-60-IE-0003E-CD06 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2181 | PL-PS5-02181 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator control panel for generator set- 5 (E) | PS5-60-IE-0003E-CD06 | TZ-MID-68-WPR2-151112, 151116, 151167 Field run cable tray installation to be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2182 | PL-PS5-02182 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator control panel for generator set- 5 (E) | PS5-60-IE-0003E-CD06 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-HV-0012, PS5-88-BU-HV-0013, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2183 | PL-PS5-02183 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator control panel for generator set- 5 (E) | PS5-60-IE-0003E-CD08 | TZ-MID-68-WPR2-151112, 151116, 151167 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 16-06-2061 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
2184 | PL-PS5-02184 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator control panel for generator set- 5 (E) | PS5-60-IE-0003E-CD08 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2185 | PL-PS5-02185 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator control panel for generator set- 5 (E) | PS5-60-IE-0003E-CD08 | TZ-MID-68-WPR2-151112, 151116, 151167 Field run cable tray installation to be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2186 | PL-PS5-02186 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator control panel for generator set- 5 (E) | PS5-60-IE-0003E-CD08 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-HV-0012, PS5-88-BU-HV-0013, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2187 | PL-PS5-02187 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-60-MOV-0005-CL01 | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 16-06-2062 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
2188 | PL-PS5-02188 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-60-MOV-0005-CL01 | TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2189 | PL-PS5-02189 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-60-MOV-0005-CL01 | TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2190 | PL-PS5-02190 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-60-MOV-0005-CL01 | TZ-MID-68-WPR2-151117,151118 Cable coiled around 90m, to be laid in ladder and reach equipment at field location. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2191 | PL-PS5-02191 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-60-MOV-0006-CL01 | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2192 | PL-PS5-02192 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-60-MOV-0006-CL01 | TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2193 | PL-PS5-02193 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-60-MOV-0006-CL01 | TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2194 | PL-PS5-02194 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-60-MOV-0006-CL01 | TZ-MID-68-WPR2-151117,151118 Cable coiled around 90m, to be laid in ladder and reach equipment at field location. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2195 | PL-PS5-02195 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-60-MOV-0011-CL01 | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2196 | PL-PS5-02196 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-60-MOV-0011-CL01 | TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2197 | PL-PS5-02197 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-60-MOV-0011-CL01 | TZ-MID-68-WPR2-151117,151118 Cable coiled around 80m, to be laid in ladder and reach equipment at field location. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2198 | PL-PS5-02198 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-60-MOV-0011-CL01 | TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2199 | PL-PS5-02199 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-60-MOV-0012-CL01 | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2200 | PL-PS5-02200 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-60-MOV-0012-CL01 | TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2201 | PL-PS5-02201 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-60-MOV-0012-CL01 | TZ-MID-68-WPR2-151117,151118 Cable coiled around 80m, to be laid in ladder and reach equipment at field location. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2202 | PL-PS5-02202 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-MOV-0012-CL01 | TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2203 | PL-PS5-02203 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-BI-0007-CL01 | TZ-MID-68-WPR2-151116,151112 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 16-06-2063 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
2204 | PL-PS5-02204 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-BI-0007-CL01 | TZ-MID-68-WPR2-151116,151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2205 | PL-PS5-02205 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-BI-0007-CL01 | TZ-MID-68-WPR2-151116,151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0029, PS5-88-BU-HV-0017, PS5-88-BU-HV-0013, PS5-88-BU-HV-0014, PS5-88-BU-HV-0015, PS5-88-CU-HV-0024) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2206 | PL-PS5-02206 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-IJ-0001-CD05 | TZ-MID-68-WPR2-151167, 151116,151112 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 16-06-2064 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
2207 | PL-PS5-02207 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-IJ-0001-CD05 | TZ-MID-68-WPR2-151167, 151116,151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2208 | PL-PS5-02208 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Generator Building | PS5-61-IJ-0001-CD05 | TZ-MID-68-WPR2-151167, 151116,151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0029, PS5-88-BU-HV-0017, PS5-88-DU-HV-0004, PS5-88-BU-HV-0013, PS5-88-BU-HV-0012). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2209 | PL-PS5-02209 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | CFO Service tank area | PS5-71-HE-2200-CL02 | TZ-MID-68-WPR2-151117,151114,151115 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
2210 | PL-PS5-02210 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | CFO Service tank area | PS5-71-HE-2200-CL02 | TZ-MID-68-WPR2-151117,151114,151115 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2211 | PL-PS5-02211 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | CFO Service tank area | PS5-71-HE-2200-CL02 | TZ-MID-68-WPR2-151117,151114,151115 Field run cable tray installation not yet complete. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2212 | PL-PS5-02212 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-71-MOV-0007-CL01 | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
2213 | PL-PS5-02213 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-71-MOV-0007-CL01 | TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2214 | PL-PS5-02214 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-71-MOV-0007-CL01 | TZ-MID-68-WPR2-151117,151118 Cable coiled around 90m, to be laid in ladder and reach equipment at field location. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2215 | PL-PS5-02215 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-71-MOV-0007-CL01 | TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2216 | PL-PS5-02216 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-71-MOV-0008-CL01 | TZ-MID-68-WPR2-151117,151118 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
2217 | PL-PS5-02217 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-71-MOV-0008-CL01 | TZ-MID-68-WPR2-151117,151118 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2218 | PL-PS5-02218 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-71-MOV-0008-CL01 | TZ-MID-68-WPR2-151117,151118 Cable coiled around 90m, to be laid in ladder and reach equipment at field location. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong | 2026-06-02 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2219 | PL-PS5-02219 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Power generator building area | PS5-71-MOV-0008-CL01 | TZ-MID-68-WPR2-151117,151118 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00164). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2220 | PL-PS5-02220 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Nitrogen Generation Skid | PS5-74-LB-5101-CL01 | TZ-MID-68-WPR2-151167,151116,151112,151111,151108 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2221 | PL-PS5-02221 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Nitrogen Generation Skid | PS5-74-LB-5101-CL01 | TZ-MID-68-WPR2-151167,151116,151112,151111,151108 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2222 | PL-PS5-02222 | #N/A | CPP-RFI-68-33/1-05-0260 | PS5 | Electrical Cable Installation | Nitrogen Generation Skid | PS5-74-LB-5101-CL01 | TZ-MID-68-WPR2-151167,151116,151112,151111,151108 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0029, PS5-88-BU-HV-0017, PS5-88-DU-HV-0004, PS5-88-BU-HV-0013) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-10 | CPP EIT | Gao Chong |  |  |  |  | Open
2223 | PL-PS5-02223 | #N/A | CPP-RFI-68-65-05-0027 | PS5 | Telecom Cable Installation | Below EITS Building & VSD | PS5-08-52CM-0131-CX01 | TZ-MID-68-WPR2-171143. Cable Tagging not yet Install, Both Ends (Below EITS & CCTV at VSD) | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2224 | PL-PS5-02224 | #N/A | CPP-RFI-68-65-05-0027 | PS5 | Telecom Cable Installation | Below EITS Building & VSD | PS5-08-52CM-0131-CX01 | TZ-MID-68-WPR2-171143. Cable need to be Dressing Both Ends, (Below EITS & CCTV at VSD) | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2225 | PL-PS5-02225 | #N/A | CPP-RFI-68-65-05-0027 | PS5 | Telecom Cable Installation | Below EITS Building & Observation Basin | PS5-08-52CM-0132-CX01 | TZ-MID-68-WPR2-171143. Cable Tagging not yet Install, Below EITS & CCTV at Observation area) | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2226 | PL-PS5-02226 | #N/A | CPP-RFI-68-65-05-0027 | PS5 | Telecom Cable Installation | Below EITS Building & Observation Basin | PS5-08-52CM-0132-CX01 | TZ-MID-68-WPR2-171143. Cable need to be Dressing Both Ends, (Below EITS & CCTV at VSD) | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2227 | PL-PS5-02227 | #N/A | CPP-RFI-68-65-05-0027 | PS5 | Telecom Cable Installation | Below EITS Building & Observation Basin | PS5-08-52CM-0132-CX01 | TZ-MID-68-WPR2-171143. Cable not yet finish to Their Final Destination (94 MTR - COILED near VSD) need open trench, sand bedding, laying the cables to final destination (CCTV), backfilling with clean sand, protection tiles, warning tape, backfilling again & compaction | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2228 | PL-PS5-02228 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL01 | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2229 | PL-PS5-02229 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL01 | TZ-MID-68-WPR2-151111 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2230 | PL-PS5-02230 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL01 | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2231 | PL-PS5-02231 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL02 | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2232 | PL-PS5-02232 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL02 | TZ-MID-68-WPR2-151111 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2233 | PL-PS5-02233 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL02 | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2234 | PL-PS5-02234 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL03 | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2235 | PL-PS5-02235 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL03 | TZ-MID-68-WPR2-151111 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2236 | PL-PS5-02236 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL03 | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2237 | PL-PS5-02237 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL04 | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2238 | PL-PS5-02238 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL04 | TZ-MID-68-WPR2-151111 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2239 | PL-PS5-02239 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL04 | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2240 | PL-PS5-02240 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL05 | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2241 | PL-PS5-02241 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL05 | TZ-MID-68-WPR2-151111 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2242 | PL-PS5-02242 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL05 | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2243 | PL-PS5-02243 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL06 | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2244 | PL-PS5-02244 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL06 | TZ-MID-68-WPR2-151111 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2245 | PL-PS5-02245 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL06 | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2246 | PL-PS5-02246 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL07 | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2247 | PL-PS5-02247 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL07 | TZ-MID-68-WPR2-151111 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2248 | PL-PS5-02248 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL07 | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2249 | PL-PS5-02249 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL08 | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2250 | PL-PS5-02250 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL08 | TZ-MID-68-WPR2-151111 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2251 | PL-PS5-02251 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL08 | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2252 | PL-PS5-02252 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL09 | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2253 | PL-PS5-02253 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL09 | TZ-MID-68-WPR2-151111 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2254 | PL-PS5-02254 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL09 | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2255 | PL-PS5-02255 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL10 | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2256 | PL-PS5-02256 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL10 | TZ-MID-68-WPR2-151111 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2257 | PL-PS5-02257 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL10 | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2258 | PL-PS5-02258 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL11 | TZ-MID-68-WPR2-151111 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2259 | PL-PS5-02259 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL11 | TZ-MID-68-WPR2-151111 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2260 | PL-PS5-02260 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | EDG Package | PS5-05-BE-0001-CL11 | TZ-MID-68-WPR2-151111 Cable ladder not yet installed (PS5-88-LD-LV-9043). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2261 | PL-PS5-02261 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Power Gen Area | PS5-08-01FB-1106-CS02 | TZ-MID-68-WPR2-151116, 151112 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong | 16-06-2065 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
2262 | PL-PS5-02262 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Power Gen Area | PS5-08-01FB-1106-CS02 | TZ-MID-68-WPR2-151116, 151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2263 | PL-PS5-02263 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Power Gen Area | PS5-08-01FB-1106-CS02 | TZ-MID-68-WPR2-151116, 151112 Field run cable tray instrument side to be installed (PS5-08-01FB-1106) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2264 | PL-PS5-02264 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Power Gen Area | PS5-08-01FB-1106-CS02 | TZ-MID-68-WPR2-151116, 151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0029, PS5-88-BU-HV-0017, PS5-88-DU-HV-0004, PS5-88-BU-HV-0013, PS5-88-BU-HV-0012) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2265 | PL-PS5-02265 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IE-0002-CD06 | TZ-MID-68-WPR2-151112 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2266 | PL-PS5-02266 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IE-0002-CD06 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2267 | PL-PS5-02267 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IE-0002-CD06 | TZ-MID-68-WPR2-151112 Cable ladder/tray not yet install at trafo side (PS5-61-IU-0011) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2268 | PL-PS5-02268 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IE-0002-CD06 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-HV-0016, PS5-88-BU-HV-0015, PS5-88-BU-HV-0019). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2269 | PL-PS5-02269 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IG-0016-CD01 | TZ-MID-68-WPR2-151112, 151116 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong | 16-06-2066 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
2270 | PL-PS5-02270 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IG-0016-CD01 | TZ-MID-68-WPR2-151112, 151116 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2271 | PL-PS5-02271 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IG-0016-CD01 | TZ-MID-68-WPR2-151112, 151116 Cable ladder at DB siide to be complete (PS5-61-IG-0016). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2272 | PL-PS5-02272 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IG-0016-CD01 | TZ-MID-68-WPR2-151112, 151116 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0012, PS5-88-BU-HV-0013, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2273 | PL-PS5-02273 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0001-CL35 | TZ-MID-68-WPR2-151112 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2274 | PL-PS5-02274 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0001-CL35 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2275 | PL-PS5-02275 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0001-CL35 | TZ-MID-68-WPR2-151112 Cable ladder/tray not yet install at trafo side (PS5-61-IV-0001B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2276 | PL-PS5-02276 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0001-CL35 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, and backfilled. ( PS5-88-CU-LV-0022). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2277 | PL-PS5-02277 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0001-CL36 | TZ-MID-68-WPR2-151112 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2278 | PL-PS5-02278 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0001-CL36 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2279 | PL-PS5-02279 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0001-CL36 | TZ-MID-68-WPR2-151112 Cable ladder/tray not yet install at trafo side (PS5-61-IV-0001B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2280 | PL-PS5-02280 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0001-CL36 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, and backfilled. ( PS5-88-CU-LV-0022). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2281 | PL-PS5-02281 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0006-CL26 | TZ-MID-68-WPR2-151112 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2282 | PL-PS5-02282 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0006-CL26 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2283 | PL-PS5-02283 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0006-CL26 | TZ-MID-68-WPR2-151112 Cable ladder/tray not yet install at trafo side (PPS5-61-IV-0007B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2284 | PL-PS5-02284 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0006-CL26 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00157). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2285 | PL-PS5-02285 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0006-CL27 | TZ-MID-68-WPR2-151112 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2286 | PL-PS5-02286 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0006-CL27 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2287 | PL-PS5-02287 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0006-CL27 | TZ-MID-68-WPR2-151112 Cable ladder/tray not yet install at trafo side (PPS5-61-IV-0007B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2288 | PL-PS5-02288 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0006-CL27 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00157). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2289 | PL-PS5-02289 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0006-CL28 | TZ-MID-68-WPR2-151112 SS Cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2290 | PL-PS5-02290 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0006-CL28 | TZ-MID-68-WPR2-151112 Cable dressing to be done both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2291 | PL-PS5-02291 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0006-CL28 | TZ-MID-68-WPR2-151112 Cable ladder/tray not yet install at trafo side (PPS5-61-IV-0007B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2292 | PL-PS5-02292 | #N/A | CPP-RFI-68-33/1-05-0264 | PS5 | Electrical Cable Installation | Trafo Area | PS5-61-IK-0006-CL28 | TZ-MID-68-WPR2-151112 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. ( PS5-88-BU-LV-00157). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-12 | CPP EIT | Gao Chong |  |  |  |  | Open
2293 | PL-PS5-02293 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-62-IE-0002-CL01 | TZ-MID-68-WPR2-151117 Permanent SS cable tags to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2294 | PL-PS5-02294 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-62-IE-0002-CL01 | TZ-MID-68-WPR2-151117 Cable need to be dressing completely | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2295 | PL-PS5-02295 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | Near Export pump area | PS5-62-IE-0002-CL01 | TZ-MID-68-WPR2-151117 Cable to be laid in the cable trench No. PS5-88-BU-LV-00162. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2296 | PL-PS5-02296 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | CFO STORAGE TANKS AREA | PS5-71-XV-0089-CL01 | TZ-MID-68-WPR2-151117,151115 Permanent SS cable tags to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
2297 | PL-PS5-02297 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | CFO STORAGE TANKS AREA | PS5-71-XV-0089-CL01 | TZ-MID-68-WPR2-151117,151115 Cable need to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2298 | PL-PS5-02298 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | CFO STORAGE TANKS AREA | PS5-71-XV-0089-CL01 | TZ-MID-68-WPR2-151117,151115 Field run cable tray to be complete installation at both side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2299 | PL-PS5-02299 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | CFO STORAGE TANKS AREA | PS5-71-XV-0089-CL01 | TZ-MID-68-WPR2-151117,151115 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2300 | PL-PS5-02300 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | CFO STORAGE TANKS AREA | PS5-71-XV-0090-CL01 | TZ-MID-68-WPR2-151117,151115 Permanent SS cable tags to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2301 | PL-PS5-02301 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | CFO STORAGE TANKS AREA | PS5-71-XV-0090-CL01 | TZ-MID-68-WPR2-151117,151115 Cable need to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2302 | PL-PS5-02302 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | CFO STORAGE TANKS AREA | PS5-71-XV-0090-CL01 | TZ-MID-68-WPR2-151117,151115 Field run cable tray to be complete installation at both side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2303 | PL-PS5-02303 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | CFO STORAGE TANKS AREA | PS5-71-XV-0090-CL01 | TZ-MID-68-WPR2-151117,151115 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2304 | PL-PS5-02304 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-MOV-0008-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS cable tags to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2305 | PL-PS5-02305 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-MOV-0008-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Cable need to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2306 | PL-PS5-02306 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-MOV-0008-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Field run cable tray to be complete installation at both side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2307 | PL-PS5-02307 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-MOV-0008-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2308 | PL-PS5-02308 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-MOV-0025-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS cable tags to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2309 | PL-PS5-02309 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-MOV-0025-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Cable need to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2310 | PL-PS5-02310 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-MOV-0025-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Field run cable tray to be complete installation at both side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2311 | PL-PS5-02311 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-MOV-0025-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0042. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2312 | PL-PS5-02312 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-MOV-0026-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS cable tags to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2313 | PL-PS5-02313 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-MOV-0026-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Cable need to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2314 | PL-PS5-02314 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-MOV-0026-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Field run cable tray to be complete installation at both side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2315 | PL-PS5-02315 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-MOV-0026-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0042. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2316 | PL-PS5-02316 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-SDV-0046-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS cable tags to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2317 | PL-PS5-02317 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-SDV-0046-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Cable need to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2318 | PL-PS5-02318 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-SDV-0046-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Field run cable tray to be complete installation at both side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2319 | PL-PS5-02319 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-SDV-0046-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2320 | PL-PS5-02320 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | Field_CFO STORAGE TANK AREA | PS5-71-LCV-4101-CL01 | TZ-MID-68-WPR2-151117,151114,151115 Permanent SS cable tags to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2321 | PL-PS5-02321 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | Field_CFO STORAGE TANK AREA | PS5-71-LCV-4101-CL01 | TZ-MID-68-WPR2-151117,151114,151115 Cable need to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2322 | PL-PS5-02322 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | Field_CFO STORAGE TANK AREA | PS5-71-LCV-4101-CL01 | TZ-MID-68-WPR2-151117,151114,151115 Field run cable tray to be complete installation at both side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2323 | PL-PS5-02323 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | Field_CFO STORAGE TANK AREA | PS5-71-LCV-4101-CL01 | TZ-MID-68-WPR2-151117,151114,151115 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2324 | PL-PS5-02324 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | CFO STORAGE TANK AREA | PS5-71-FCV-0020-CL01 | TZ-MID-68-WPR2-151117,151114,151115 Permanent SS cable tags to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2325 | PL-PS5-02325 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | CFO STORAGE TANK AREA | PS5-71-FCV-0020-CL01 | TZ-MID-68-WPR2-151117,151114,151115 Cable need to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2326 | PL-PS5-02326 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | CFO STORAGE TANK AREA | PS5-71-FCV-0020-CL01 | TZ-MID-68-WPR2-151117,151114,151115 Field run cable tray to be complete installation at both side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2327 | PL-PS5-02327 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | CFO STORAGE TANK AREA | PS5-71-FCV-0020-CL01 | TZ-MID-68-WPR2-151117,151114,151115 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2328 | PL-PS5-02328 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | CFO STORAGE TANK AREA | PS5-71-SDV-0039-CL01 | TZ-MID-68-WPR2-151117,151115 Permanent SS cable tags to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong | 16-06-2067 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
2329 | PL-PS5-02329 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | CFO STORAGE TANK AREA | PS5-71-SDV-0039-CL01 | TZ-MID-68-WPR2-151117,151115 Cable need to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2330 | PL-PS5-02330 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | CFO STORAGE TANK AREA | PS5-71-SDV-0039-CL01 | TZ-MID-68-WPR2-151117,151115 Field run cable tray to be complete installation at both side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2331 | PL-PS5-02331 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | CFO STORAGE TANK AREA | PS5-71-SDV-0039-CL01 | TZ-MID-68-WPR2-151117,151115 Cable to be laid in the trench and backfiled (PS5-88-BU-LV-00164) at MOV DB side PS5-61-IG-0043. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2332 | PL-PS5-02332 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL44 | TZ-MID-68-WPR2-151112 Permanent SS cable tags to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong | 16-06-2068 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
2333 | PL-PS5-02333 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL44 | TZ-MID-68-WPR2-151112 Cable need to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2334 | PL-PS5-02334 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IK-0001-CL44 | TZ-MID-68-WPR2-151112 Cable trench backfilled to be complete PS5-88-CU-LV-0021 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2335 | PL-PS5-02335 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | Fire water storage Tank area | PS5-87-IRF-0001-CL01 | TZ-MID-68-WPR2-151111,151108,151109 Permanent SS cable tags to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2336 | PL-PS5-02336 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | Fire water storage Tank area | PS5-87-IRF-0001-CL01 | TZ-MID-68-WPR2-151111,151108,151109 Cable need to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2337 | PL-PS5-02337 | #N/A | CPP-RFI-68-33/1-05-0266 | PS5 | Electrical Cable Installation | Fire water storage Tank area | PS5-87-IRF-0001-CL01 | TZ-MID-68-WPR2-151111,151108,151109 Field run cable tray to be install at both equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-15 | CPP EIT | Gao Chong |  |  |  |  | Open
2338 | PL-PS5-02338 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-71-BE-0363-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2339 | PL-PS5-02339 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0304-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2340 | PL-PS5-02340 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0325-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2341 | PL-PS5-02341 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0311-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2342 | PL-PS5-02342 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0312-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2343 | PL-PS5-02343 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0355-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2344 | PL-PS5-02344 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0354-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2345 | PL-PS5-02345 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0172-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2346 | PL-PS5-02346 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0180-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2347 | PL-PS5-02347 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0191-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2348 | PL-PS5-02348 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0192-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2349 | PL-PS5-02349 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0193-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2350 | PL-PS5-02350 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0179-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2351 | PL-PS5-02351 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0326-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2352 | PL-PS5-02352 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0174-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2353 | PL-PS5-02353 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0305-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2354 | PL-PS5-02354 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0322-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2355 | PL-PS5-02355 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0346-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2356 | PL-PS5-02356 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0325-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2357 | PL-PS5-02357 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0311-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2358 | PL-PS5-02358 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0312-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2359 | PL-PS5-02359 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0355-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2360 | PL-PS5-02360 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0354-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2361 | PL-PS5-02361 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0172-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2362 | PL-PS5-02362 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0180-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2363 | PL-PS5-02363 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0191-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2364 | PL-PS5-02364 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0192-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2365 | PL-PS5-02365 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0193-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2366 | PL-PS5-02366 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0179-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2367 | PL-PS5-02367 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0326-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2368 | PL-PS5-02368 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0174-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2369 | PL-PS5-02369 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0305-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2370 | PL-PS5-02370 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0322-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2371 | PL-PS5-02371 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0346-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2372 | PL-PS5-02372 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-71-BE-0363-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2373 | PL-PS5-02373 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0304-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2374 | PL-PS5-02374 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0325-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2375 | PL-PS5-02375 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0311-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2376 | PL-PS5-02376 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0312-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2377 | PL-PS5-02377 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0355-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2378 | PL-PS5-02378 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0354-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2379 | PL-PS5-02379 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0172-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2380 | PL-PS5-02380 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0180-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2381 | PL-PS5-02381 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0191-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2382 | PL-PS5-02382 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0192-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2383 | PL-PS5-02383 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0193-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2384 | PL-PS5-02384 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0179-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2385 | PL-PS5-02385 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0326-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2386 | PL-PS5-02386 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0174-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2387 | PL-PS5-02387 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0305-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2388 | PL-PS5-02388 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0322-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2389 | PL-PS5-02389 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0346-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2390 | PL-PS5-02390 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0325-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2391 | PL-PS5-02391 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0311-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2392 | PL-PS5-02392 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0312-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2393 | PL-PS5-02393 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0355-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2394 | PL-PS5-02394 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0354-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2395 | PL-PS5-02395 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0172-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2396 | PL-PS5-02396 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0180-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2397 | PL-PS5-02397 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0191-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2398 | PL-PS5-02398 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0192-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2399 | PL-PS5-02399 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0193-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2400 | PL-PS5-02400 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0179-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2401 | PL-PS5-02401 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0326-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2402 | PL-PS5-02402 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0174-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2403 | PL-PS5-02403 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0305-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2404 | PL-PS5-02404 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0322-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2405 | PL-PS5-02405 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0346-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2406 | PL-PS5-02406 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-71-BE-0363-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2407 | PL-PS5-02407 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0304-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2408 | PL-PS5-02408 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0325-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2409 | PL-PS5-02409 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0311-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2410 | PL-PS5-02410 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0312-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2411 | PL-PS5-02411 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0355-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2412 | PL-PS5-02412 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0354-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2413 | PL-PS5-02413 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0172-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2414 | PL-PS5-02414 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0180-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2415 | PL-PS5-02415 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0191-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2416 | PL-PS5-02416 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0192-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2417 | PL-PS5-02417 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0193-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2418 | PL-PS5-02418 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0179-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2419 | PL-PS5-02419 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0326-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2420 | PL-PS5-02420 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0174-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2421 | PL-PS5-02421 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0305-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2422 | PL-PS5-02422 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0322-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2423 | PL-PS5-02423 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0346-CL01 | TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2424 | PL-PS5-02424 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0325-CD01 | TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2425 | PL-PS5-02425 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0311-CD01 | TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2426 | PL-PS5-02426 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0312-CD01 | TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2427 | PL-PS5-02427 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0355-CD01 | TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2428 | PL-PS5-02428 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0354-CD01 | TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2429 | PL-PS5-02429 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0172-CD01 | TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2430 | PL-PS5-02430 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0180-CD01 | TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2431 | PL-PS5-02431 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0191-CD01 | TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2432 | PL-PS5-02432 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0192-CD01 | TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2433 | PL-PS5-02433 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0193-CD01 | TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2434 | PL-PS5-02434 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0179-CD01 | TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2435 | PL-PS5-02435 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0326-CD01 | TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2436 | PL-PS5-02436 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0174-CD01 | TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2437 | PL-PS5-02437 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0305-CD01 | TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2438 | PL-PS5-02438 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0322-CD01 | TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2439 | PL-PS5-02439 | #N/A | CPP-RFI-68-33/1-05-0269 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0346-CD01 | TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2440 | PL-PS5-02440 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0123-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2441 | PL-PS5-02441 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0309-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2442 | PL-PS5-02442 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0018-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2443 | PL-PS5-02443 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0130-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2444 | PL-PS5-02444 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0015-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2445 | PL-PS5-02445 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0133-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2446 | PL-PS5-02446 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0298-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2447 | PL-PS5-02447 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0026-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2448 | PL-PS5-02448 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0309-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2449 | PL-PS5-02449 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0018-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2450 | PL-PS5-02450 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0130-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2451 | PL-PS5-02451 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0251-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2452 | PL-PS5-02452 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0297-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2453 | PL-PS5-02453 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0296-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2454 | PL-PS5-02454 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0258-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2455 | PL-PS5-02455 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0098-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2456 | PL-PS5-02456 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0300-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2457 | PL-PS5-02457 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0248-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2458 | PL-PS5-02458 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0013-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2459 | PL-PS5-02459 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0251-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2460 | PL-PS5-02460 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0297-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2461 | PL-PS5-02461 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0296-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2462 | PL-PS5-02462 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0258-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2463 | PL-PS5-02463 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0098-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2464 | PL-PS5-02464 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0300-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2465 | PL-PS5-02465 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0123-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2466 | PL-PS5-02466 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0248-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2467 | PL-PS5-02467 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0013-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2468 | PL-PS5-02468 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0015-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2469 | PL-PS5-02469 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0133-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2470 | PL-PS5-02470 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0298-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2471 | PL-PS5-02471 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0026-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong | 2026-06-04 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2472 | PL-PS5-02472 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0123-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2473 | PL-PS5-02473 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0309-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2474 | PL-PS5-02474 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0018-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2475 | PL-PS5-02475 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0130-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2476 | PL-PS5-02476 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0015-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2477 | PL-PS5-02477 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0133-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2478 | PL-PS5-02478 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0298-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2479 | PL-PS5-02479 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0026-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2480 | PL-PS5-02480 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0309-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2481 | PL-PS5-02481 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0018-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2482 | PL-PS5-02482 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0130-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2483 | PL-PS5-02483 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0251-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2484 | PL-PS5-02484 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0297-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2485 | PL-PS5-02485 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0296-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2486 | PL-PS5-02486 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0258-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2487 | PL-PS5-02487 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0098-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2488 | PL-PS5-02488 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0300-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2489 | PL-PS5-02489 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0248-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2490 | PL-PS5-02490 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0013-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2491 | PL-PS5-02491 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0251-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2492 | PL-PS5-02492 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0297-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2493 | PL-PS5-02493 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0296-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2494 | PL-PS5-02494 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0258-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2495 | PL-PS5-02495 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0098-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2496 | PL-PS5-02496 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0300-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2497 | PL-PS5-02497 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0123-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2498 | PL-PS5-02498 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0248-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2499 | PL-PS5-02499 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0013-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2500 | PL-PS5-02500 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0015-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2501 | PL-PS5-02501 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0133-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2502 | PL-PS5-02502 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0298-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2503 | PL-PS5-02503 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0026-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2504 | PL-PS5-02504 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0123-CL01 | TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2505 | PL-PS5-02505 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0309-CL01 | TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2506 | PL-PS5-02506 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0018-CL01 | TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2507 | PL-PS5-02507 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0130-CL01 | TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2508 | PL-PS5-02508 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0015-CL01 | TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2509 | PL-PS5-02509 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0133-CL01 | TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2510 | PL-PS5-02510 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0298-CL01 | TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2511 | PL-PS5-02511 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0026-CL01 | TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2512 | PL-PS5-02512 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0309-CD01 | TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2513 | PL-PS5-02513 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0018-CD01 | TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2514 | PL-PS5-02514 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0130-CD01 | TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2515 | PL-PS5-02515 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0251-CL01 | TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2516 | PL-PS5-02516 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0297-CL01 | TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2517 | PL-PS5-02517 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0296-CL01 | TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2518 | PL-PS5-02518 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0258-CL01 | TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2519 | PL-PS5-02519 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0098-CL01 | TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2520 | PL-PS5-02520 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0300-CL01 | TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2521 | PL-PS5-02521 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0248-CL01 | TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2522 | PL-PS5-02522 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0013-CL01 | TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2523 | PL-PS5-02523 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0251-CD01 | TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2524 | PL-PS5-02524 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0297-CD01 | TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2525 | PL-PS5-02525 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0296-CD01 | TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2526 | PL-PS5-02526 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0258-CD01 | TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2527 | PL-PS5-02527 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0098-CD01 | TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2528 | PL-PS5-02528 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0300-CD01 | TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2529 | PL-PS5-02529 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0123-CD01 | TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2530 | PL-PS5-02530 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0248-CD01 | TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2531 | PL-PS5-02531 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0013-CD01 | TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2532 | PL-PS5-02532 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0015-CD01 | TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2533 | PL-PS5-02533 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0133-CD01 | TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2534 | PL-PS5-02534 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0298-CD01 | TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2535 | PL-PS5-02535 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-TE-0026-CD01 | TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2536 | PL-PS5-02536 | #N/A | CPP-RFI-68-33/1-05-0274 | PS5 | EHT Power Cable Installation | Field | PS5-79-BE-0013-CL01 | TZ-MID-68-NVS1-150359 Cable shortage at field side coiled only 2 Meter | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-16 | CPP EIT | Gao Chong |  |  |  |  | Open
2537 | PL-PS5-02537 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | Field | PS5-08-52BT-0131-CS01 | TZ-MID-68-WPR2-151112, 151111 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2538 | PL-PS5-02538 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002B-CL02 | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2539 | PL-PS5-02539 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0002-CD43 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2540 | PL-PS5-02540 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0002-CD44 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2541 | PL-PS5-02541 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD61 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2542 | PL-PS5-02542 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD62 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2543 | PL-PS5-02543 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD63 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2544 | PL-PS5-02544 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD64 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2545 | PL-PS5-02545 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD65 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2546 | PL-PS5-02546 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD67 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2547 | PL-PS5-02547 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD02 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2548 | PL-PS5-02548 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD03 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2549 | PL-PS5-02549 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD04 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2550 | PL-PS5-02550 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD66 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2551 | PL-PS5-02551 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | Field | PS5-08-52BT-0131-CS01 | TZ-MID-68-WPR2-151112, 151111 Field run cable tray to be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2552 | PL-PS5-02552 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | Field | PS5-08-52BT-0131-CS01 | TZ-MID-68-WPR2-151112, 151111 Permanent SS Cable Tag To be Install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2553 | PL-PS5-02553 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002B-CL02 | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag To be Install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2554 | PL-PS5-02554 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002B-CL02 | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable coiled 110Mtr at Electrical building side, to be laid in the ladder (PS5-88-LD-LV-9025, PS5-88-LD-LV-9087, PS5-88-LD-LV-3091, PS5-88-LD-LV-3090). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2555 | PL-PS5-02555 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0002-CD43 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2556 | PL-PS5-02556 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0002-CD44 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2557 | PL-PS5-02557 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD61 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2558 | PL-PS5-02558 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD62 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2559 | PL-PS5-02559 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD63 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2560 | PL-PS5-02560 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD64 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2561 | PL-PS5-02561 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD65 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2562 | PL-PS5-02562 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD67 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2563 | PL-PS5-02563 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD02 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2564 | PL-PS5-02564 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD03 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2565 | PL-PS5-02565 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD04 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2566 | PL-PS5-02566 | #N/A | CPP-RFI-68-33/1-05-0275 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IJ-0001-CD66 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench not yet complete installation of protection tiles, warning tape, and backfilled. (PS5-88-BU-HV-0013, PS5-88-BU-HV-0014) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-19 | CPP EIT | Gao Chong |  |  |  |  | Open
2567 | PL-PS5-02567 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-01-BI-0002-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2568 | PL-PS5-02568 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-01-BI-0003-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2569 | PL-PS5-02569 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-01-BI-2520-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2570 | PL-PS5-02570 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-01-LIT-4201-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2571 | PL-PS5-02571 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-01-PIT-0015-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2572 | PL-PS5-02572 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-BI-1511-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2573 | PL-PS5-02573 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-BI-1512-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2574 | PL-PS5-02574 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-BI-1516-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2575 | PL-PS5-02575 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-NMR-0801-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2576 | PL-PS5-02576 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-NMR-0803-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2577 | PL-PS5-02577 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-NMR-0804-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2578 | PL-PS5-02578 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-RMAC-0824-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2579 | PL-PS5-02579 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-SEA-0003-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2580 | PL-PS5-02580 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-09-BI-2503-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2581 | PL-PS5-02581 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-09-LB-0008-CC03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2582 | PL-PS5-02582 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-28-BI-1114-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2583 | PL-PS5-02583 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-60-IE-0003E-CC22 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2584 | PL-PS5-02584 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Package Skid | PS5-75-BI-0002-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2585 | PL-PS5-02585 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Package Skid | PS5-75-BI-0002-CC03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2586 | PL-PS5-02586 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-05-BI-0002-CC03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2587 | PL-PS5-02587 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | Generator Bldg to EDG | PS5-05-UH-8100-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2588 | PL-PS5-02588 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | Generator Bldg to EDG | PS5-03-SEA-0001-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2589 | PL-PS5-02589 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-05-IE-8100-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2590 | PL-PS5-02590 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Package Skid | PS5-75-BI-0001-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2591 | PL-PS5-02591 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Package Skid | PS5-75-BI-0002-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2592 | PL-PS5-02592 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Package Skid | PS5-75-LA-6200-CX01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2593 | PL-PS5-02593 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-01-BI-0002-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2594 | PL-PS5-02594 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-01-BI-0003-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2595 | PL-PS5-02595 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-01-BI-2520-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2596 | PL-PS5-02596 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-01-LIT-4201-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2597 | PL-PS5-02597 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-01-PIT-0015-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2598 | PL-PS5-02598 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-BI-1511-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2599 | PL-PS5-02599 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-BI-1512-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2600 | PL-PS5-02600 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-BI-1516-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2601 | PL-PS5-02601 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-NMR-0801-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2602 | PL-PS5-02602 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-NMR-0803-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2603 | PL-PS5-02603 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-NMR-0804-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2604 | PL-PS5-02604 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-RMAC-0824-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2605 | PL-PS5-02605 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-SEA-0003-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2606 | PL-PS5-02606 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-09-BI-2503-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2607 | PL-PS5-02607 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-09-LB-0008-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2608 | PL-PS5-02608 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-28-BI-1114-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2609 | PL-PS5-02609 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-60-IE-0003E-CC22 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2610 | PL-PS5-02610 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-75-BI-0002-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2611 | PL-PS5-02611 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Package Skid | PS5-75-BI-0002-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2612 | PL-PS5-02612 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-05-BI-0002-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2613 | PL-PS5-02613 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | Generator Bldg to EDG | PS5-05-UH-8100-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2614 | PL-PS5-02614 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | Generator Bldg to EDG | PS5-03-SEA-0001-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2615 | PL-PS5-02615 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-05-IE-8100-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed on EITS side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2616 | PL-PS5-02616 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-01-BI-0002-CC01 | Doc.TZ-MID-68-WPR2-161507- Cable coiled (135 mtr)Cable tray not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2617 | PL-PS5-02617 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-01-BI-0003-CC01 | Doc.TZ-MID-68-WPR2-161507- Cable coiled (135 mtr)Cable tray not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2618 | PL-PS5-02618 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-01-BI-2520-CC01 | Doc.TZ-MID-68-WPR2-161507- Cable coiled (125 mtr)Cable tray not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2619 | PL-PS5-02619 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-01-LIT-4201-CJ01 | Doc.TZ-MID-68-WPR2-161507- Cable coiled (135 mtr)Cable tray not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2620 | PL-PS5-02620 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-01-PIT-0015-CJ01 | Doc.TZ-MID-68-WPR2-161507- Cable coiled (155 mtr)Cable tray not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2621 | PL-PS5-02621 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-BI-1511-CC01 | Doc.TZ-MID-68-WPR2-161507- Cable coiled (155 mtr)Cable tray not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2622 | PL-PS5-02622 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-BI-1512-CC01 | Doc.TZ-MID-68-WPR2-161507- Cable coiled (85 mtr)Cable tray not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2623 | PL-PS5-02623 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-BI-1516-CC01 | Doc.TZ-MID-68-WPR2-161507- Cable coiled (100 mtr)Cable tray not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2624 | PL-PS5-02624 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-NMR-0801-CJ01 | Doc.TZ-MID-68-WPR2-161507- Cable coiled (120 mtr)Cable tray not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2625 | PL-PS5-02625 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-NMR-0803-CJ01 | Doc.TZ-MID-68-WPR2-161507- Cable coiled (95 mtr)Cable tray not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2626 | PL-PS5-02626 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-NMR-0804-CJ01 | Doc.TZ-MID-68-WPR2-161507- Cable coiled (75 mtr)Cable tray not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2627 | PL-PS5-02627 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-RMAC-0824-CJ01 | Doc.TZ-MID-68-WPR2-161507- Cable coiled (15 mtr)Cable tray not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2628 | PL-PS5-02628 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-03-SEA-0003-CC01 | Doc.TZ-MID-68-WPR2-161507- Cable coiled (270 mtr)Cable tray not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2629 | PL-PS5-02629 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-28-BI-1114-CC01 | Doc.TZ-MID-68-WPR2-161507- Cable coiled (155 mtr)Cable tray not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2630 | PL-PS5-02630 | #N/A | CPP-RFI-68-64-04-0049 | PS5 | Instrument Cable Installation | EITS Building to Generator Bldg | PS5-60-IE-0003E-CC22 | Doc.TZ-MID-68-WPR2-161507- Cable coiled (85 mtr)Cable tray not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2631 | PL-PS5-02631 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | EDG to Generator Blgd | PS5-05-BI-0002-CC05 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2632 | PL-PS5-02632 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | EDG to Generator Blgd | PS5-05-BI-0002-CC06 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2633 | PL-PS5-02633 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0001-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2634 | PL-PS5-02634 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0002-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2635 | PL-PS5-02635 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0003-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2636 | PL-PS5-02636 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0004-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2637 | PL-PS5-02637 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0005-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2638 | PL-PS5-02638 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0006-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2639 | PL-PS5-02639 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0007-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2640 | PL-PS5-02640 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0001-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2641 | PL-PS5-02641 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0003-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2642 | PL-PS5-02642 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0004-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2643 | PL-PS5-02643 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0005-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2644 | PL-PS5-02644 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0006-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2645 | PL-PS5-02645 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0007-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2646 | PL-PS5-02646 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | EDG to Generator Blgd | PS5-05-BI-0002-CC05 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2647 | PL-PS5-02647 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | EDG to Generator Blgd | PS5-05-BI-0002-CC06 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2648 | PL-PS5-02648 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0001-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2649 | PL-PS5-02649 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0002-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2650 | PL-PS5-02650 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0003-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2651 | PL-PS5-02651 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0004-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2652 | PL-PS5-02652 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0005-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2653 | PL-PS5-02653 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0006-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2654 | PL-PS5-02654 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0007-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2655 | PL-PS5-02655 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0001-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2656 | PL-PS5-02656 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0003-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2657 | PL-PS5-02657 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0004-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2658 | PL-PS5-02658 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0005-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2659 | PL-PS5-02659 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0006-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2660 | PL-PS5-02660 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0007-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2661 | PL-PS5-02661 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0001-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (180 MTR) Cable tray not yet installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2662 | PL-PS5-02662 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0002-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (180 MTR) Cable tray not yet installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2663 | PL-PS5-02663 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0003-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (100 MTR) Cable tray not yet installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2664 | PL-PS5-02664 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0004-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (100 MTR) Cable tray not yet installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2665 | PL-PS5-02665 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0005-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (100 MTR) Cable tray not yet installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2666 | PL-PS5-02666 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0006-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (55 MTR) Cable tray not yet installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2667 | PL-PS5-02667 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0007-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (55 MTR) Cable tray not yet installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2668 | PL-PS5-02668 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0001-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (120 MTR) Cable tray not yet installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2669 | PL-PS5-02669 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0003-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (100 MTR) Cable tray not yet installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2670 | PL-PS5-02670 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0004-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (100 MTR) Cable tray not yet installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2671 | PL-PS5-02671 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0005-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (55 MTR) Cable tray not yet installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2672 | PL-PS5-02672 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0006-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (50 MTR) Cable tray not yet installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2673 | PL-PS5-02673 | #N/A | CPP-RFI-68-64-04-0050 | PS5 | Instrument Cable Installation | Powergen Bldg | PS5-61-BI-0007-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable Coiled (50 MTR) Cable tray not yet installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2674 | PL-PS5-02674 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | Diesel Fuel Storage & Pump area | PS5-03-RDIR-0403-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2675 | PL-PS5-02675 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RDIR-0122-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
2676 | PL-PS5-02676 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RDIR-0123-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2677 | PL-PS5-02677 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RDIR-0121-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
2678 | PL-PS5-02678 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RDIR-0125-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2679 | PL-PS5-02679 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RDIR-0126-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2680 | PL-PS5-02680 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RDIR-0127-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2681 | PL-PS5-02681 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RMAC-0613-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2682 | PL-PS5-02682 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RDH-0830-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2683 | PL-PS5-02683 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RDH-0831-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2684 | PL-PS5-02684 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | Launcher& Receiver | PS5-03-RMAC-0102-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2685 | PL-PS5-02685 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | UTILITY | PS5-03-RMAC-0401-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2686 | PL-PS5-02686 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | EXPORT | PS5-25-SXS-0035A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2687 | PL-PS5-02687 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | EXPORT | PS5-25-SXS-0035B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2688 | PL-PS5-02688 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | EXPORT | PS5-25-SXS-0036A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2689 | PL-PS5-02689 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | EXPORT | PS5-25-SXS-0035C-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2690 | PL-PS5-02690 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | EXPORT | PS5-25-SXS-0036B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2691 | PL-PS5-02691 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | EXPORT | PS5-25-SXS-0036C-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2692 | PL-PS5-02692 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | EXPORT | PS5-25-SXS-0046-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2693 | PL-PS5-02693 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-FIT-0019-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
2694 | PL-PS5-02694 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-3302A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
2695 | PL-PS5-02695 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-3302B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2696 | PL-PS5-02696 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-3402A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2697 | PL-PS5-02697 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-3402B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2698 | PL-PS5-02698 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-FY-0020-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
2699 | PL-PS5-02699 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-XY-0089-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2700 | PL-PS5-02700 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-XY-0090-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2701 | PL-PS5-02701 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-0022-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
2702 | PL-PS5-02702 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-TIT-0006-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
2703 | PL-PS5-02703 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-TIT-2402AA-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
2704 | PL-PS5-02704 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-TIT-2402BA-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
2705 | PL-PS5-02705 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-0039-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2706 | PL-PS5-02706 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-TIT-0007-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
2707 | PL-PS5-02707 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-3301A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
2708 | PL-PS5-02708 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-3301B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2709 | PL-PS5-02709 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-3401A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2710 | PL-PS5-02710 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-3401B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2711 | PL-PS5-02711 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-LXS-4101-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2712 | PL-PS5-02712 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-FXS-0020-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-27 | Konstantin Ovchinnikov | 2026-06-15 |  | CLOSED
2713 | PL-PS5-02713 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-FXS-0018-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2714 | PL-PS5-02714 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-XXS-0089-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2715 | PL-PS5-02715 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-XXS-0090-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2716 | PL-PS5-02716 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-SY-0039-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2717 | PL-PS5-02717 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-SY-0022-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2718 | PL-PS5-02718 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-SXS-0022-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2719 | PL-PS5-02719 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-SXS-0039-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2720 | PL-PS5-02720 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | Diesel Fuel Storage & Pump area | PS5-03-RDIR-0403-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2721 | PL-PS5-02721 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RDIR-0122-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2722 | PL-PS5-02722 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RDIR-0123-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2723 | PL-PS5-02723 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RDIR-0121-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2724 | PL-PS5-02724 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RDIR-0125-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2725 | PL-PS5-02725 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RDIR-0126-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2726 | PL-PS5-02726 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RDIR-0127-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2727 | PL-PS5-02727 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RMAC-0613-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong |  |  |  |  | Open
2728 | PL-PS5-02728 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RDH-0830-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2729 | PL-PS5-02729 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-03-RDH-0831-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2730 | PL-PS5-02730 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | Launcher& Receiver | PS5-03-RMAC-0102-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2731 | PL-PS5-02731 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | UTILITY | PS5-03-RMAC-0401-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2732 | PL-PS5-02732 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | EXPORT | PS5-25-SXS-0035A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2733 | PL-PS5-02733 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | EXPORT | PS5-25-SXS-0035B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2734 | PL-PS5-02734 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | EXPORT | PS5-25-SXS-0036A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2735 | PL-PS5-02735 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | EXPORT | PS5-25-SXS-0035C-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2736 | PL-PS5-02736 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | EXPORT | PS5-25-SXS-0036B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2737 | PL-PS5-02737 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | EXPORT | PS5-25-SXS-0036C-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2738 | PL-PS5-02738 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | EXPORT | PS5-25-SXS-0046-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2739 | PL-PS5-02739 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-FIT-0019-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2740 | PL-PS5-02740 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-3302A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2741 | PL-PS5-02741 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-3302B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2742 | PL-PS5-02742 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-3402A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2743 | PL-PS5-02743 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-3402B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2744 | PL-PS5-02744 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-FY-0020-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2745 | PL-PS5-02745 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-XY-0089-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2746 | PL-PS5-02746 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-XY-0090-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2747 | PL-PS5-02747 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-0022-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2748 | PL-PS5-02748 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-TIT-0006-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2749 | PL-PS5-02749 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-TIT-2402AA-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2750 | PL-PS5-02750 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-TIT-2402BA-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2751 | PL-PS5-02751 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-0039-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2752 | PL-PS5-02752 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-TIT-0007-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2753 | PL-PS5-02753 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-3301A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2754 | PL-PS5-02754 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-3301B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2755 | PL-PS5-02755 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-3401A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2756 | PL-PS5-02756 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-PIT-3401B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2757 | PL-PS5-02757 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-LXS-4101-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2758 | PL-PS5-02758 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-FXS-0020-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2759 | PL-PS5-02759 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-FXS-0018-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2760 | PL-PS5-02760 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-XXS-0089-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2761 | PL-PS5-02761 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-XXS-0090-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2762 | PL-PS5-02762 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-SY-0039-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2763 | PL-PS5-02763 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-SY-0022-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2764 | PL-PS5-02764 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-SXS-0022-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2765 | PL-PS5-02765 | #N/A | CPP-RFI-68-64-04-0052 | PS5 | Instrument Cable Installation | CFO | PS5-71-SXS-0039-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-20 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2766 | PL-PS5-02766 | #N/A | CPP-RFI-68-64-05-0051 | PS5 | Junction Box Installation | Launcher& Receiver | PS5-25-BI-2205 | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-23 | CPP EIT | Gao Chong |  |  |  |  | Open
2767 | PL-PS5-02767 | #N/A | CPP-RFI-68-64-05-0051 | PS5 | Junction Box Installation | Launcher& Receiver | PS5-25-BI-2203 | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-23 | CPP EIT | Gao Chong |  |  |  |  | Open
2768 | PL-PS5-02768 | #N/A | CPP-RFI-68-64-05-0051 | PS5 | Junction Box Installation | Launcher& Receiver | PS5-25-BI-2201 | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-23 | CPP EIT | Gao Chong |  |  |  |  | Open
2769 | PL-PS5-02769 | #N/A | CPP-RFI-68-64-05-0051 | PS5 | Junction Box Installation | CFO | PS5-03-BI-1506 | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-23 | CPP EIT | Gao Chong |  |  |  |  | Open
2770 | PL-PS5-02770 | #N/A | CPP-RFI-68-64-05-0051 | PS5 | Junction Box Installation | CFO | PS5-71-BI-1305 | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-23 | CPP EIT | Gao Chong |  |  |  |  | Open
2771 | PL-PS5-02771 | #N/A | CPP-RFI-68-64-05-0051 | PS5 | Junction Box Installation | CFO | PS5-71-BI-1109, | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-23 | CPP EIT | Gao Chong |  |  |  |  | Open
2772 | PL-PS5-02772 | #N/A | CPP-RFI-68-64-05-0051 | PS5 | Junction Box Installation | CFO | PS5-71-BI-2306 | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-23 | CPP EIT | Gao Chong | 2026-06-01 |  |  |  | OPEN
2773 | PL-PS5-02773 | #N/A | CPP-RFI-68-64-05-0051 | PS5 | Junction Box Installation | CFO | PS5-71-BI-1306 | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-23 | CPP EIT | Gao Chong | 2026-06-01 |  |  |  | OPEN
2774 | PL-PS5-02774 | #N/A | CPP-RFI-68-64-05-0051 | PS5 | Junction Box Installation | CFO | PS5-71-BI-1116 | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-23 | CPP EIT | Gao Chong | 2026-06-01 |  |  |  | OPEN
2775 | PL-PS5-02775 | #N/A | CPP-RFI-68-64-05-0051 | PS5 | Junction Box Installation | Launcher& Receiver | PS5-25-BI-2205 | Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-23 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2776 | PL-PS5-02776 | #N/A | CPP-RFI-68-64-05-0051 | PS5 | Junction Box Installation | Launcher& Receiver | PS5-25-BI-2203 | Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-23 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2777 | PL-PS5-02777 | #N/A | CPP-RFI-68-64-05-0051 | PS5 | Junction Box Installation | Launcher& Receiver | PS5-25-BI-2201 | Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-23 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2778 | PL-PS5-02778 | #N/A | CPP-RFI-68-64-05-0051 | PS5 | Junction Box Installation | Launcher& Receiver | PS5-25-BI-2205 | Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-23 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2779 | PL-PS5-02779 | #N/A | CPP-RFI-68-64-05-0051 | PS5 | Junction Box Installation | Launcher& Receiver | PS5-25-BI-2203 | Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-23 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2780 | PL-PS5-02780 | #N/A | CPP-RFI-68-64-05-0051 | PS5 | Junction Box Installation | Launcher& Receiver | PS5-25-BI-2201 | Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-23 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2781 | PL-PS5-02781 | #N/A | CPP-RFI-68-331-05-0295 | PS5 | Electrical Cable Installation | From EITS Buillding to Water Treatment Pre Package | PS5-53-IN-0001-CL02 | TZ-MID-68-WPR2-151112,151111,151108,151109 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2782 | PL-PS5-02782 | #N/A | CPP-RFI-68-331-05-0295 | PS5 | Electrical Cable Installation | From EITS Buillding to Water Treatment Pre Package | PS5-53-IN-0001-CL02 | TZ-MID-68-WPR2-151112,151111,151108,151109 Cable dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2783 | PL-PS5-02783 | #N/A | CPP-RFI-68-331-05-0295 | PS5 | Electrical Cable Installation | From EITS Buillding to Water Treatment Pre Package | PS5-53-IN-0001-CL02 | TZ-MID-68-WPR2-151112,151111,151108,151109 Cable need to laid in the cable trench at field side Water Treatment Package MCC Panel. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2784 | PL-PS5-02784 | #N/A | CPP-RFI-68-331-05-0295 | PS5 | Electrical Cable Installation | From EITS Buillding to Water Treatment Pre Package | PS5-53-IN-0001-CL03 | TZ-MID-68-WPR2-151112,151111,151108,151109 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
2785 | PL-PS5-02785 | #N/A | CPP-RFI-68-331-05-0295 | PS5 | Electrical Cable Installation | From EITS Buillding to Water Treatment Pre Package | PS5-53-IN-0001-CL03 | TZ-MID-68-WPR2-151112,151111,151108,151109 Cable dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2786 | PL-PS5-02786 | #N/A | CPP-RFI-68-331-05-0295 | PS5 | Electrical Cable Installation | From EITS Buillding to Water Treatment Pre Package | PS5-53-IN-0001-CL03 | TZ-MID-68-WPR2-151112,151111,151108,151109 Cable need to laid in the cable trench at field side Water Treatment Package MCC Panel. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2787 | PL-PS5-02787 | #N/A | CPP-RFI-68-331-05-0295 | PS5 | Electrical Cable Installation | From Generator Electrical Building to EITS Building | PS5-61-IE-0002-CD41 | TZ-MID-68-WPR2-151112, 151116, 151167 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
2788 | PL-PS5-02788 | #N/A | CPP-RFI-68-331-05-0295 | PS5 | Electrical Cable Installation | From Generator Electrical Building to EITS Building | PS5-61-IE-0002-CD41 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2789 | PL-PS5-02789 | #N/A | CPP-RFI-68-331-05-0295 | PS5 | Electrical Cable Installation | From Generator Electrical Building to EITS Building | PS5-61-IE-0002-CD41 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench to be done backfilled, protection tiles, and warning tape installation. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2790 | PL-PS5-02790 | #N/A | CPP-RFI-68-331-05-0295 | PS5 | Electrical Cable Installation | From Generator Electrical Building to EITS Building | PS5-61-IE-0002-CD42 | TZ-MID-68-WPR2-151112, 151116, 151167 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-06-03 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
2791 | PL-PS5-02791 | #N/A | CPP-RFI-68-331-05-0295 | PS5 | Electrical Cable Installation | From Generator Electrical Building to EITS Building | PS5-61-IE-0002-CD42 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2792 | PL-PS5-02792 | #N/A | CPP-RFI-68-331-05-0295 | PS5 | Electrical Cable Installation | From Generator Electrical Building to EITS Building | PS5-61-IE-0002-CD42 | TZ-MID-68-WPR2-151112, 151116, 151167 Cable trench to be done backfilled, protection tiles, and warning tape installation. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2793 | PL-PS5-02793 | #N/A | CPP-RFI-68-331-05-0295 | PS5 | Electrical Cable Installation | From EITS Buillding to Power generator building area | PS5-79-IV-0011-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2794 | PL-PS5-02794 | #N/A | CPP-RFI-68-331-05-0295 | PS5 | Electrical Cable Installation | From EITS Buillding to Power generator building area | PS5-79-IV-0011-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Cable dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2795 | PL-PS5-02795 | #N/A | CPP-RFI-68-331-05-0295 | PS5 | Electrical Cable Installation | From EITS Buillding to Power generator building area | PS5-79-IV-0011-CL01 | TZ-MID-68-WPR2-151112,151111,151115,151117,151118 Vertical Cable Ladder to be install at field side Heat Tracing Transformer PS5-79-IV-0011 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2796 | PL-PS5-02796 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-74-LB-5101-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2797 | PL-PS5-02797 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-01-BI-1520-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2798 | PL-PS5-02798 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-01-BI-2571B-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2799 | PL-PS5-02799 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-01-IE-0002A-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2800 | PL-PS5-02800 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-01-IE-0002A-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2801 | PL-PS5-02801 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-01-IE-0002B-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2802 | PL-PS5-02802 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-01-IE-0002B-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2803 | PL-PS5-02803 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-01-IE-0009A-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2804 | PL-PS5-02804 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-01-IE-0009B-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-28 | Konstantin Ovchinnikov | 2026-05-29 |  | CLOSED
2805 | PL-PS5-02805 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-BI-1503-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2806 | PL-PS5-02806 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-BI-1507-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2807 | PL-PS5-02807 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-BI-1513-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2808 | PL-PS5-02808 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-BI-1514-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2809 | PL-PS5-02809 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-BI-2503-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2810 | PL-PS5-02810 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-BI-2506-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2811 | PL-PS5-02811 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-BI-2512-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2812 | PL-PS5-02812 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-BI-2514-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2813 | PL-PS5-02813 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-NMR-0802-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
2814 | PL-PS5-02814 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-25-BI-1310-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2815 | PL-PS5-02815 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-60-IE-0004-CC08 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2816 | PL-PS5-02816 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-71-BI-1308-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
2817 | PL-PS5-02817 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-71-BI-2307-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
2818 | PL-PS5-02818 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-71-BI-2313-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
2819 | PL-PS5-02819 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-71-BI-2314-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
2820 | PL-PS5-02820 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-71-BI-2317-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
2821 | PL-PS5-02821 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-25-BI-1174C-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
2822 | PL-PS5-02822 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-61-IDH-3100B-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2823 | PL-PS5-02823 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-61-IDH-3100B-CC03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2824 | PL-PS5-02824 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-61-IDH-3100C-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2825 | PL-PS5-02825 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-61-IDH-3100C-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-05-29 | Konstantin Ovchinnikov | 2026-05-31 |  | CLOSED
2826 | PL-PS5-02826 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-25-BI-1801A-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
2827 | PL-PS5-02827 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-09-LB-0008-CX01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2828 | PL-PS5-02828 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-60-IE-0004-CX03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2829 | PL-PS5-02829 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-60-IE-0004-CX04 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
2830 | PL-PS5-02830 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-61-BI-0002-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong | 2026-06-01 | Konstantin Ovchinnikov | 2026-06-14 |  | CLOSED
2831 | PL-PS5-02831 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-74-LB-5101-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2832 | PL-PS5-02832 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-01-BI-1520-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2833 | PL-PS5-02833 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-01-BI-2571B-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2834 | PL-PS5-02834 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-01-IE-0002A-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2835 | PL-PS5-02835 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-01-IE-0002A-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2836 | PL-PS5-02836 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-01-IE-0002B-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2837 | PL-PS5-02837 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-01-IE-0002B-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2838 | PL-PS5-02838 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-01-IE-0009A-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2839 | PL-PS5-02839 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-01-IE-0009B-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2840 | PL-PS5-02840 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-BI-1503-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2841 | PL-PS5-02841 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-BI-1507-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2842 | PL-PS5-02842 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-BI-1513-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2843 | PL-PS5-02843 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-BI-1514-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2844 | PL-PS5-02844 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-BI-2503-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2845 | PL-PS5-02845 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-BI-2506-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2846 | PL-PS5-02846 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-BI-2512-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2847 | PL-PS5-02847 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-BI-2514-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2848 | PL-PS5-02848 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-03-NMR-0802-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2849 | PL-PS5-02849 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-25-BI-1310-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2850 | PL-PS5-02850 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-60-IE-0004-CC08 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2851 | PL-PS5-02851 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-71-BI-1308-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2852 | PL-PS5-02852 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-71-BI-2307-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2853 | PL-PS5-02853 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-71-BI-2313-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2854 | PL-PS5-02854 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-71-BI-2314-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2855 | PL-PS5-02855 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-71-BI-2317-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2856 | PL-PS5-02856 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-25-BI-1174C-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2857 | PL-PS5-02857 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-61-IDH-3100B-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2858 | PL-PS5-02858 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-61-IDH-3100B-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2859 | PL-PS5-02859 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-61-IDH-3100C-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2860 | PL-PS5-02860 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-61-IDH-3100C-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2861 | PL-PS5-02861 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-25-BI-1801A-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2862 | PL-PS5-02862 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-09-LB-0008-CX01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2863 | PL-PS5-02863 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-60-IE-0004-CX03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2864 | PL-PS5-02864 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-60-IE-0004-CX04 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | Open
2865 | PL-PS5-02865 | #N/A | CPP-RFI-68-64-04-0054 | PS5 | Instrument Cable Installation | EITS Building | PS5-61-BI-0002-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing not yet completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-24 | CPP EIT | Gao Chong |  |  |  |  | OPEN
2866 | PL-PS5-02866 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0196-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2867 | PL-PS5-02867 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0238-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2868 | PL-PS5-02868 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0244-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2869 | PL-PS5-02869 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0189-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2870 | PL-PS5-02870 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0186-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2871 | PL-PS5-02871 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0348-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2872 | PL-PS5-02872 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0352-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2873 | PL-PS5-02873 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0243-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2874 | PL-PS5-02874 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0196-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2875 | PL-PS5-02875 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0238-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2876 | PL-PS5-02876 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0244-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2877 | PL-PS5-02877 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0189-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2878 | PL-PS5-02878 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0186-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2879 | PL-PS5-02879 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0348-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2880 | PL-PS5-02880 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0352-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2881 | PL-PS5-02881 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0243-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2882 | PL-PS5-02882 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0092-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2883 | PL-PS5-02883 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0216-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2884 | PL-PS5-02884 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0092-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2885 | PL-PS5-02885 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0064-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2886 | PL-PS5-02886 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0084-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2887 | PL-PS5-02887 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0161-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2888 | PL-PS5-02888 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0162-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2889 | PL-PS5-02889 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0074-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2890 | PL-PS5-02890 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0077-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2891 | PL-PS5-02891 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0070-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2892 | PL-PS5-02892 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0108-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2893 | PL-PS5-02893 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0111-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2894 | PL-PS5-02894 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0062-CL01 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2895 | PL-PS5-02895 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0161-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2896 | PL-PS5-02896 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0162-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2897 | PL-PS5-02897 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0074-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2898 | PL-PS5-02898 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0077-CD01 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2899 | PL-PS5-02899 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0196-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2900 | PL-PS5-02900 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0238-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2901 | PL-PS5-02901 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0244-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2902 | PL-PS5-02902 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0189-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2903 | PL-PS5-02903 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0186-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2904 | PL-PS5-02904 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0348-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2905 | PL-PS5-02905 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0352-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2906 | PL-PS5-02906 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0243-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2907 | PL-PS5-02907 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0196-CD01 | TZ-MID-68-NVS1-150360 To be complete cable dressing at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2908 | PL-PS5-02908 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0238-CD01 | TZ-MID-68-NVS1-150360 To be complete cable dressing at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2909 | PL-PS5-02909 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0244-CD01 | TZ-MID-68-NVS1-150360 To be complete cable dressing at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2910 | PL-PS5-02910 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0189-CD01 | TZ-MID-68-NVS1-150360 To be complete cable dressing at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2911 | PL-PS5-02911 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0186-CD01 | TZ-MID-68-NVS1-150360 To be complete cable dressing at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2912 | PL-PS5-02912 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0348-CD01 | TZ-MID-68-NVS1-150360 To be complete cable dressing at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2913 | PL-PS5-02913 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0352-CD01 | TZ-MID-68-NVS1-150360 To be complete cable dressing at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2914 | PL-PS5-02914 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0243-CD01 | TZ-MID-68-NVS1-150360 To be complete cable dressing at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2915 | PL-PS5-02915 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0092-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2916 | PL-PS5-02916 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0216-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2917 | PL-PS5-02917 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0092-CD01 | TZ-MID-68-NVS1-150360 To be complete cable dressing at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2918 | PL-PS5-02918 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0064-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2919 | PL-PS5-02919 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0084-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2920 | PL-PS5-02920 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0161-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2921 | PL-PS5-02921 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0162-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2922 | PL-PS5-02922 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0074-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2923 | PL-PS5-02923 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0077-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2924 | PL-PS5-02924 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0070-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2925 | PL-PS5-02925 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0108-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2926 | PL-PS5-02926 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0111-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2927 | PL-PS5-02927 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0062-CL01 | TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2928 | PL-PS5-02928 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0161-CD01 | TZ-MID-68-NVS1-150360 To be complete cable dressing at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2929 | PL-PS5-02929 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0162-CD01 | TZ-MID-68-NVS1-150360 To be complete cable dressing at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2930 | PL-PS5-02930 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0074-CD01 | TZ-MID-68-NVS1-150360 To be complete cable dressing at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2931 | PL-PS5-02931 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0077-CD01 | TZ-MID-68-NVS1-150360 To be complete cable dressing at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2932 | PL-PS5-02932 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0196-CL01 | TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2933 | PL-PS5-02933 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0238-CL01 | TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2934 | PL-PS5-02934 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0244-CL01 | TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2935 | PL-PS5-02935 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0189-CL01 | TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2936 | PL-PS5-02936 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0186-CL01 | TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2937 | PL-PS5-02937 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0348-CL01 | TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2938 | PL-PS5-02938 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0352-CL01 | TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2939 | PL-PS5-02939 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0243-CL01 | TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2940 | PL-PS5-02940 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0196-CD01 | TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2941 | PL-PS5-02941 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0238-CD01 | TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2942 | PL-PS5-02942 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0244-CD01 | TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2943 | PL-PS5-02943 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0189-CD01 | TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2944 | PL-PS5-02944 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0186-CD01 | TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2945 | PL-PS5-02945 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0348-CD01 | TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2946 | PL-PS5-02946 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0352-CD01 | TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2947 | PL-PS5-02947 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0243-CD01 | TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2948 | PL-PS5-02948 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0092-CL01 | TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2949 | PL-PS5-02949 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0216-CL01 | TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2950 | PL-PS5-02950 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0092-CD01 | TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2951 | PL-PS5-02951 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0196-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2952 | PL-PS5-02952 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0238-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2953 | PL-PS5-02953 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0244-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2954 | PL-PS5-02954 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0189-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2955 | PL-PS5-02955 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0186-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2956 | PL-PS5-02956 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0348-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2957 | PL-PS5-02957 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0352-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2958 | PL-PS5-02958 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0243-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2959 | PL-PS5-02959 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0196-CD01 | TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2960 | PL-PS5-02960 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0238-CD01 | TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2961 | PL-PS5-02961 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0244-CD01 | TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2962 | PL-PS5-02962 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0189-CD01 | TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2963 | PL-PS5-02963 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0186-CD01 | TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2964 | PL-PS5-02964 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0348-CD01 | TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2965 | PL-PS5-02965 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0352-CD01 | TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2966 | PL-PS5-02966 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0243-CD01 | TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2967 | PL-PS5-02967 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0092-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2968 | PL-PS5-02968 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-BE-0216-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2969 | PL-PS5-02969 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Closed Drain Drum Area | PS5-79-TE-0092-CD01 | TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2970 | PL-PS5-02970 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0064-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2971 | PL-PS5-02971 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0084-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2972 | PL-PS5-02972 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0161-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2973 | PL-PS5-02973 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0162-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2974 | PL-PS5-02974 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0074-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2975 | PL-PS5-02975 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0077-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2976 | PL-PS5-02976 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0070-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2977 | PL-PS5-02977 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0108-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2978 | PL-PS5-02978 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0111-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2979 | PL-PS5-02979 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0062-CL01 | TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2980 | PL-PS5-02980 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0161-CD01 | TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2981 | PL-PS5-02981 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0162-CD01 | TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2982 | PL-PS5-02982 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0074-CD01 | TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2983 | PL-PS5-02983 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0077-CD01 | TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2984 | PL-PS5-02984 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0064-CL01 | TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0006 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2985 | PL-PS5-02985 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0084-CL01 | TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0007 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2986 | PL-PS5-02986 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0161-CL01 | TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2987 | PL-PS5-02987 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0162-CL01 | TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2988 | PL-PS5-02988 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0074-CL01 | TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2989 | PL-PS5-02989 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0077-CL01 | TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2990 | PL-PS5-02990 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0070-CL01 | TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2991 | PL-PS5-02991 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0108-CL01 | TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2992 | PL-PS5-02992 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0111-CL01 | TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2993 | PL-PS5-02993 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0062-CL01 | TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2994 | PL-PS5-02994 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0161-CD01 | TZ-MID-68-NVS1-150360To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2995 | PL-PS5-02995 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0162-CD01 | TZ-MID-68-NVS1-150360To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2996 | PL-PS5-02996 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0074-CD01 | TZ-MID-68-NVS1-150360To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2997 | PL-PS5-02997 | #N/A | CPP-RFI-68-331-05-0277 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0077-CD01 | TZ-MID-68-NVS1-150360To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008 | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-25 | CPP EIT | Gao Chong |  |  |  |  | Open
2998 | PL-PS5-02998 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0241-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
2999 | PL-PS5-02999 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0208-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3000 | PL-PS5-03000 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0292-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3001 | PL-PS5-03001 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0140-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3002 | PL-PS5-03002 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0004-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3003 | PL-PS5-03003 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0007-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3004 | PL-PS5-03004 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0139-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3005 | PL-PS5-03005 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0142-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3006 | PL-PS5-03006 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0053-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3007 | PL-PS5-03007 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0158-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3008 | PL-PS5-03008 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0060-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3009 | PL-PS5-03009 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0115-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3010 | PL-PS5-03010 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0141-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3011 | PL-PS5-03011 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0207-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3012 | PL-PS5-03012 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0205-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3013 | PL-PS5-03013 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0044-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3014 | PL-PS5-03014 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0045-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3015 | PL-PS5-03015 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0261-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3016 | PL-PS5-03016 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0209-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3017 | PL-PS5-03017 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0241-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3018 | PL-PS5-03018 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0208-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3019 | PL-PS5-03019 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0292-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3020 | PL-PS5-03020 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0140-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3021 | PL-PS5-03021 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0004-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3022 | PL-PS5-03022 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0007-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3023 | PL-PS5-03023 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0139-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3024 | PL-PS5-03024 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0142-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3025 | PL-PS5-03025 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0053-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3026 | PL-PS5-03026 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0158-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3027 | PL-PS5-03027 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0060-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3028 | PL-PS5-03028 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0115-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3029 | PL-PS5-03029 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0141-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3030 | PL-PS5-03030 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0207-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3031 | PL-PS5-03031 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0205-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3032 | PL-PS5-03032 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0044-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3033 | PL-PS5-03033 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0045-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3034 | PL-PS5-03034 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0261-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3035 | PL-PS5-03035 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0241-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3036 | PL-PS5-03036 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0208-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3037 | PL-PS5-03037 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0292-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3038 | PL-PS5-03038 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0140-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3039 | PL-PS5-03039 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0004-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3040 | PL-PS5-03040 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0007-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3041 | PL-PS5-03041 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0139-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3042 | PL-PS5-03042 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0142-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3043 | PL-PS5-03043 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0053-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3044 | PL-PS5-03044 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0158-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3045 | PL-PS5-03045 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0060-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3046 | PL-PS5-03046 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0115-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3047 | PL-PS5-03047 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0141-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3048 | PL-PS5-03048 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0207-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3049 | PL-PS5-03049 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0205-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3050 | PL-PS5-03050 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0044-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3051 | PL-PS5-03051 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0045-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3052 | PL-PS5-03052 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0261-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3053 | PL-PS5-03053 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0209-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3054 | PL-PS5-03054 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0241-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3055 | PL-PS5-03055 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0208-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3056 | PL-PS5-03056 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0292-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3057 | PL-PS5-03057 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0140-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3058 | PL-PS5-03058 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0004-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3059 | PL-PS5-03059 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0007-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3060 | PL-PS5-03060 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0139-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3061 | PL-PS5-03061 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0142-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3062 | PL-PS5-03062 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0053-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3063 | PL-PS5-03063 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0158-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3064 | PL-PS5-03064 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0060-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3065 | PL-PS5-03065 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0115-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3066 | PL-PS5-03066 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0141-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3067 | PL-PS5-03067 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0207-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3068 | PL-PS5-03068 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0205-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3069 | PL-PS5-03069 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0044-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3070 | PL-PS5-03070 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0045-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3071 | PL-PS5-03071 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0261-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3072 | PL-PS5-03072 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0241-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3073 | PL-PS5-03073 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0208-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3074 | PL-PS5-03074 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0292-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3075 | PL-PS5-03075 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0140-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3076 | PL-PS5-03076 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0004-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3077 | PL-PS5-03077 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0007-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3078 | PL-PS5-03078 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0139-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3079 | PL-PS5-03079 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0142-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3080 | PL-PS5-03080 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0053-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3081 | PL-PS5-03081 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0158-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3082 | PL-PS5-03082 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0060-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3083 | PL-PS5-03083 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0115-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3084 | PL-PS5-03084 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0141-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3085 | PL-PS5-03085 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0207-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3086 | PL-PS5-03086 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0205-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3087 | PL-PS5-03087 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0044-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3088 | PL-PS5-03088 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0045-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3089 | PL-PS5-03089 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0261-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3090 | PL-PS5-03090 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0209-CL01 | TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3091 | PL-PS5-03091 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0241-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3092 | PL-PS5-03092 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0208-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3093 | PL-PS5-03093 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0292-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3094 | PL-PS5-03094 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0140-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3095 | PL-PS5-03095 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0004-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3096 | PL-PS5-03096 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0007-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3097 | PL-PS5-03097 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0139-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3098 | PL-PS5-03098 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0142-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3099 | PL-PS5-03099 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0053-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3100 | PL-PS5-03100 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0158-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3101 | PL-PS5-03101 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0060-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3102 | PL-PS5-03102 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0115-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3103 | PL-PS5-03103 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0141-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3104 | PL-PS5-03104 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0207-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3105 | PL-PS5-03105 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0205-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3106 | PL-PS5-03106 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0044-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3107 | PL-PS5-03107 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0045-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3108 | PL-PS5-03108 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0261-CD01 | TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3109 | PL-PS5-03109 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0241-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3110 | PL-PS5-03110 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0208-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3111 | PL-PS5-03111 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0292-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3112 | PL-PS5-03112 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0140-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3113 | PL-PS5-03113 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0004-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3114 | PL-PS5-03114 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0007-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3115 | PL-PS5-03115 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0139-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3116 | PL-PS5-03116 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0142-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3117 | PL-PS5-03117 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0053-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3118 | PL-PS5-03118 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0158-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3119 | PL-PS5-03119 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0060-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3120 | PL-PS5-03120 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0115-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3121 | PL-PS5-03121 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0141-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3122 | PL-PS5-03122 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0207-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3123 | PL-PS5-03123 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0205-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3124 | PL-PS5-03124 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0044-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3125 | PL-PS5-03125 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0045-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3126 | PL-PS5-03126 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0261-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3127 | PL-PS5-03127 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0209-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3128 | PL-PS5-03128 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0241-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3129 | PL-PS5-03129 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0208-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3130 | PL-PS5-03130 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0292-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3131 | PL-PS5-03131 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0140-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3132 | PL-PS5-03132 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0004-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3133 | PL-PS5-03133 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0007-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3134 | PL-PS5-03134 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0139-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3135 | PL-PS5-03135 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0142-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3136 | PL-PS5-03136 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0053-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3137 | PL-PS5-03137 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0158-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3138 | PL-PS5-03138 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0060-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3139 | PL-PS5-03139 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0115-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3140 | PL-PS5-03140 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0141-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3141 | PL-PS5-03141 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0207-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3142 | PL-PS5-03142 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0205-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3143 | PL-PS5-03143 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0044-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3144 | PL-PS5-03144 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0045-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3145 | PL-PS5-03145 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0261-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3146 | PL-PS5-03146 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0241-CL01 | TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3147 | PL-PS5-03147 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0292-CL01 | TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3148 | PL-PS5-03148 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0140-CL01 | TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3149 | PL-PS5-03149 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0004-CL01 | TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3150 | PL-PS5-03150 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0007-CL01 | TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3151 | PL-PS5-03151 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0139-CL01 | TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3152 | PL-PS5-03152 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0142-CL01 | TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3153 | PL-PS5-03153 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-BE-0141-CL01 | TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3154 | PL-PS5-03154 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0241-CD01 | TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3155 | PL-PS5-03155 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0292-CD01 | TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3156 | PL-PS5-03156 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0140-CD01 | TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3157 | PL-PS5-03157 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0004-CD01 | TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3158 | PL-PS5-03158 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0007-CD01 | TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3159 | PL-PS5-03159 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0139-CD01 | TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3160 | PL-PS5-03160 | #N/A | CPP-RFI-68-33/1-05-0280 | PS5 | EHT Power Cable Installation | Export pump area | PS5-79-TE-0142-CD01 | TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-27 | CPP EIT | Gao Chong |  |  |  |  | Open
3161 | PL-PS5-03161 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0214-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3162 | PL-PS5-03162 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0215-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3163 | PL-PS5-03163 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0099-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3164 | PL-PS5-03164 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0171-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3165 | PL-PS5-03165 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0281-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3166 | PL-PS5-03166 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0284-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3167 | PL-PS5-03167 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0134-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3168 | PL-PS5-03168 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0063-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3169 | PL-PS5-03169 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0005-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3170 | PL-PS5-03170 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0041-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3171 | PL-PS5-03171 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0135-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3172 | PL-PS5-03172 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0214-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3173 | PL-PS5-03173 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0216-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3174 | PL-PS5-03174 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0215-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3175 | PL-PS5-03175 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0099-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3176 | PL-PS5-03176 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0171-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3177 | PL-PS5-03177 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0281-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3178 | PL-PS5-03178 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0284-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3179 | PL-PS5-03179 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Launcher/Receiver Area | PS5-79-TE-0084-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3180 | PL-PS5-03180 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Launcher/Receiver Area | PS5-79-TE-0020-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3181 | PL-PS5-03181 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0134-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3182 | PL-PS5-03182 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0063-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3183 | PL-PS5-03183 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0005-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3184 | PL-PS5-03184 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0041-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3185 | PL-PS5-03185 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0135-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3186 | PL-PS5-03186 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0214-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3187 | PL-PS5-03187 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0215-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3188 | PL-PS5-03188 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0099-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3189 | PL-PS5-03189 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0171-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3190 | PL-PS5-03190 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0281-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3191 | PL-PS5-03191 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0284-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3192 | PL-PS5-03192 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0134-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3193 | PL-PS5-03193 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0063-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3194 | PL-PS5-03194 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0005-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3195 | PL-PS5-03195 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0041-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3196 | PL-PS5-03196 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0135-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3197 | PL-PS5-03197 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0214-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3198 | PL-PS5-03198 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0216-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3199 | PL-PS5-03199 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0215-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3200 | PL-PS5-03200 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0099-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3201 | PL-PS5-03201 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0171-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3202 | PL-PS5-03202 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0281-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3203 | PL-PS5-03203 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0284-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3204 | PL-PS5-03204 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Launcher/Receiver Area | PS5-79-TE-0084-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3205 | PL-PS5-03205 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Launcher/Receiver Area | PS5-79-TE-0020-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3206 | PL-PS5-03206 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0134-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3207 | PL-PS5-03207 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0063-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3208 | PL-PS5-03208 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0005-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3209 | PL-PS5-03209 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0041-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3210 | PL-PS5-03210 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0135-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3211 | PL-PS5-03211 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0214-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3212 | PL-PS5-03212 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0215-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3213 | PL-PS5-03213 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0099-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3214 | PL-PS5-03214 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0171-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3215 | PL-PS5-03215 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0281-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3216 | PL-PS5-03216 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0284-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3217 | PL-PS5-03217 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0134-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3218 | PL-PS5-03218 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0063-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3219 | PL-PS5-03219 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0005-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3220 | PL-PS5-03220 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0041-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3221 | PL-PS5-03221 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0135-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3222 | PL-PS5-03222 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0214-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3223 | PL-PS5-03223 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0216-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3224 | PL-PS5-03224 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0215-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3225 | PL-PS5-03225 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0099-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3226 | PL-PS5-03226 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0171-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3227 | PL-PS5-03227 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0281-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3228 | PL-PS5-03228 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0284-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3229 | PL-PS5-03229 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Launcher/Receiver Area | PS5-79-TE-0084-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3230 | PL-PS5-03230 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Launcher/Receiver Area | PS5-79-TE-0020-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3231 | PL-PS5-03231 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0134-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3232 | PL-PS5-03232 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0063-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3233 | PL-PS5-03233 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0005-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3234 | PL-PS5-03234 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0041-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3235 | PL-PS5-03235 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0135-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray shall be install | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3236 | PL-PS5-03236 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0214-CL01 | TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3237 | PL-PS5-03237 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0215-CL01 | TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3238 | PL-PS5-03238 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0099-CL01 | TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3239 | PL-PS5-03239 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0171-CL01 | TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3240 | PL-PS5-03240 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0281-CL01 | TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3241 | PL-PS5-03241 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-BE-0284-CL01 | TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3242 | PL-PS5-03242 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0214-CD01 | TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3243 | PL-PS5-03243 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0216-CD01 | TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3244 | PL-PS5-03244 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0215-CD01 | TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3245 | PL-PS5-03245 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0099-CD01 | TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3246 | PL-PS5-03246 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0171-CD01 | TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3247 | PL-PS5-03247 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0281-CD01 | TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3248 | PL-PS5-03248 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Field/Close drain drum area | PS5-79-TE-0284-CD01 | TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3249 | PL-PS5-03249 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0134-CL01 | TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3250 | PL-PS5-03250 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0063-CL01 | TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3251 | PL-PS5-03251 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0005-CL01 | TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3252 | PL-PS5-03252 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0041-CL01 | TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3253 | PL-PS5-03253 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0135-CL01 | TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3254 | PL-PS5-03254 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Launcher/Receiver Area | PS5-79-TE-0084-CD01 | TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3255 | PL-PS5-03255 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Launcher/Receiver Area | PS5-79-TE-0020-CD01 | TZ-MID-68-NVS1-150360 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0007) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3256 | PL-PS5-03256 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0134-CD01 | TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3257 | PL-PS5-03257 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0063-CD01 | TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3258 | PL-PS5-03258 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0005-CD01 | TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3259 | PL-PS5-03259 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0041-CD01 | TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3260 | PL-PS5-03260 | #N/A | CPP-RFI-68-33/1-05-0281 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0135-CD01 | TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3261 | PL-PS5-03261 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | PGB | PS5-01-BI-1520 | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3262 | PL-PS5-03262 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | PGB | PS5-01-BI-2520 | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3263 | PL-PS5-03263 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | PGB | PS5-71-BI-2118 | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3264 | PL-PS5-03264 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | PGB | PS5-71-BI-2122 | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3265 | PL-PS5-03265 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | Export Pump Area | PS5-03-BI-1509 | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3266 | PL-PS5-03266 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | Export Pump Area | PS5-25-BI-2308 | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3267 | PL-PS5-03267 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | Export Pump Area | PS5-25-BI-2106 | Doc.UT-MID-60-WPR2-160101 - Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3268 | PL-PS5-03268 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | PGB | PS5-01-BI-1520 | Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
3269 | PL-PS5-03269 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | PGB | PS5-01-BI-2520 | Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
3270 | PL-PS5-03270 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | PGB | PS5-71-BI-2118 | Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
3271 | PL-PS5-03271 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | PGB | PS5-71-BI-2122 | Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
3272 | PL-PS5-03272 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | Export Pump Area | PS5-03-BI-1509 | Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong | 2026-06-05 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
3273 | PL-PS5-03273 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | Export Pump Area | PS5-25-BI-2308 | Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong | 2026-06-05 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
3274 | PL-PS5-03274 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | Export Pump Area | PS5-25-BI-2106 | Doc.UT-MID-60-WPR2-160101 - touch up to the drillied holes in Jb support frame not done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong | 2026-06-05 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
3275 | PL-PS5-03275 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | PGB | PS5-01-BI-1520 | Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
3276 | PL-PS5-03276 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | PGB | PS5-01-BI-2520 | Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
3277 | PL-PS5-03277 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | PGB | PS5-71-BI-2118 | Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
3278 | PL-PS5-03278 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | PGB | PS5-71-BI-2122 | Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong | 2026-05-30 | Konstantin Ovchinnikov | 14-06-2026 |  | CLOSED
3279 | PL-PS5-03279 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | Export Pump Area | PS5-03-BI-1509 | Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong | 2026-06-05 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
3280 | PL-PS5-03280 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | Export Pump Area | PS5-25-BI-2308 | Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong | 2026-06-05 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
3281 | PL-PS5-03281 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | Export Pump Area | PS5-25-BI-2106 | Doc.UT-MID-60-WPR2-160101 -Isolation Pad not yet Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong | 2026-06-05 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
3282 | PL-PS5-03282 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | PGB | PS5-01-BI-2520 | Doc.UT-MID-60-WPR2-160101 -Junction Box TAG to be installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3283 | PL-PS5-03283 | #N/A | CPP-RFI-68-64-05-0053 | PS5 | Junction Box Installation | PGB | PS5-71-BI-2122 | Doc.UT-MID-60-WPR2-160101 -Junction Box TAG to be Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-05-28 | CPP EIT | Gao Chong |  |  |  |  | Open
3284 | PL-PS5-03284 | #N/A | CPP-RFI-68-33/2-02-0301 | PS5 | EHT Power Transformer | CFO Area | PS5-79-IV-0001 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Transformer body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3285 | PL-PS5-03285 | #N/A | CPP-RFI-68-33/2-02-0301 | PS5 | EHT Power Transformer | CFO Area | PS5-79-IV-0002 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Transformer body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3286 | PL-PS5-03286 | #N/A | CPP-RFI-68-33/2-02-0301 | PS5 | EHT Power Transformer | Close Drain Drum Area | PS5-79-IV-0003 | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3287 | PL-PS5-03287 | #N/A | CPP-RFI-68-33/2-02-0301 | PS5 | EHT Power Transformer | Close Drain Drum Area | PS5-79-IV-0004 | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3288 | PL-PS5-03288 | #N/A | CPP-RFI-68-33/2-02-0301 | PS5 | EHT Power Transformer | Close Drain Drum Area | PS5-79-IV-0005 | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3289 | PL-PS5-03289 | #N/A | CPP-RFI-68-33/2-02-0301 | PS5 | EHT Power Transformer | Export Pump Area | PS5-79-IV-0006 | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3290 | PL-PS5-03290 | #N/A | CPP-RFI-68-33/2-02-0301 | PS5 | EHT Power Transformer | Export Pump Area | PS5-79-IV-0006 | TZ-MID-68-WPR2-151117 Rectify concrete broken 1 pcs anchor bolt | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3291 | PL-PS5-03291 | #N/A | CPP-RFI-68-33/2-02-0301 | PS5 | EHT Power Transformer | Export Pump Area | PS5-79-IV-0007 | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3292 | PL-PS5-03292 | #N/A | CPP-RFI-68-33/2-02-0301 | PS5 | EHT Power Transformer | Export Pump Area | PS5-79-IV-0008 | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3293 | PL-PS5-03293 | #N/A | CPP-RFI-68-33/2-02-0301 | PS5 | EHT Power Transformer | Export Pump Area | PS5-79-IV-0009 | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3294 | PL-PS5-03294 | #N/A | CPP-RFI-68-33/2-02-0301 | PS5 | EHT Power Transformer | Export Pump Area | PS5-79-IV-0010 | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Transformer body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3295 | PL-PS5-03295 | #N/A | CPP-RFI-68-33/2-02-0301 | PS5 | EHT Power Transformer | POWER GENERATION COOLING TOWER AREA | PS5-79-IV-0011 | TZ-MID-68-WPR2-151118 To perform cleanning for EHT Transformer body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3296 | PL-PS5-03296 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | CFO Area | PS5-79-IG-0001 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3297 | PL-PS5-03297 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | CFO Area | PS5-79-IG-0002 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3298 | PL-PS5-03298 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Close Drain Drum Area | PS5-79-IG-0003 | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3299 | PL-PS5-03299 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Close Drain Drum Area | PS5-79-IG-0004 | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3300 | PL-PS5-03300 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Close Drain Drum Area | PS5-79-IG-0005 | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3301 | PL-PS5-03301 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Export Pump Area | PS5-79-IG-0006 | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3302 | PL-PS5-03302 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Export Pump Area | PS5-79-IG-0007 | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3303 | PL-PS5-03303 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Export Pump Area | PS5-79-IG-0008 | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3304 | PL-PS5-03304 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Export Pump Area | PS5-79-IG-0009 | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3305 | PL-PS5-03305 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Export Pump Area | PS5-79-IG-0010 | TZ-MID-68-WPR2-151117 To perform cleanning for EHT Distribution board body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3306 | PL-PS5-03306 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | POWER GENERATION COOLING TOWER AREA | PS5-79-IG-0011 | TZ-MID-68-WPR2-151118 To perform cleanning for EHT Distribution board body and surround area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3307 | PL-PS5-03307 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | CFO Area | PS5-79-IG-0001 | TZ-MID-68-WPR2-151115 Un-used cable entries to be install dummy plug | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3308 | PL-PS5-03308 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | CFO Area | PS5-79-IG-0002 | TZ-MID-68-WPR2-151115 Un-used cable entries to be install dummy plug | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3309 | PL-PS5-03309 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Close Drain Drum Area | PS5-79-IG-0003 | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3310 | PL-PS5-03310 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Close Drain Drum Area | PS5-79-IG-0004 | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3311 | PL-PS5-03311 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Close Drain Drum Area | PS5-79-IG-0005 | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3312 | PL-PS5-03312 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Export Pump Area | PS5-79-IG-0006 | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3313 | PL-PS5-03313 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Export Pump Area | PS5-79-IG-0007 | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3314 | PL-PS5-03314 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Export Pump Area | PS5-79-IG-0008 | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3315 | PL-PS5-03315 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Export Pump Area | PS5-79-IG-0009 | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3316 | PL-PS5-03316 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Export Pump Area | PS5-79-IG-0010 | TZ-MID-68-WPR2-151117 Un-used cable entries to be install dummy plug | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3317 | PL-PS5-03317 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | POWER GENERATION COOLING TOWER AREA | PS5-79-IG-0011 | TZ-MID-68-WPR2-151118 Un-used cable entries to be install dummy plug | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3318 | PL-PS5-03318 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Close Drain Drum Area | PS5-79-IG-0005 | TZ-MID-68-WPR2-151117 Need install seam plate to the gap between concrete foundation and frame support of DB Panel | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3319 | PL-PS5-03319 | #N/A | CPP-RFI-68-33/2-03-0302 | PS5 | EHT Distribution Board | Export Pump Area | PS5-79-IG-0006 | TZ-MID-68-WPR2-151117 Need install seam plate to the gap between concrete foundation and frame support of DB Panel | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3320 | PL-PS5-03320 | #N/A | CPP-RFI-68-33/2-02-0304 | PS5 | VFD Power Transformer | VSD Area | PS5-61-IU-3100A | TZ-MID-68-WPR2-151111 Cleanning body transformer and areas | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3321 | PL-PS5-03321 | #N/A | CPP-RFI-68-33/2-02-0304 | PS5 | VFD Power Transformer | VSD Area | PS5-61-IU-3100B | TZ-MID-68-WPR2-151111 Cleanning body transformer and areas | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3322 | PL-PS5-03322 | #N/A | CPP-RFI-68-33/2-02-0304 | PS5 | VFD Power Transformer | VSD Area | PS5-61-IU-3100C | TZ-MID-68-WPR2-151111 Cleanning body transformer and areas | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3323 | PL-PS5-03323 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GB-0003-CL01 | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong | 15-06-2026 | Konstantin Ovchinnikov | 2026-06-16 |  | CLOSED
3324 | PL-PS5-03324 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GB-0003-CL02 | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3325 | PL-PS5-03325 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GB-0003-CL03 | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3326 | PL-PS5-03326 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GB-0003-CL04 | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3327 | PL-PS5-03327 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GB-0003-CL05 | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3328 | PL-PS5-03328 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GB-0003-CL06 | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3329 | PL-PS5-03329 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GU-0003A-CL01 | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3330 | PL-PS5-03330 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GU-0003B-CL01 | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3331 | PL-PS5-03331 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GU-0003C-CL01 | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3332 | PL-PS5-03332 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004A-CL01 | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3333 | PL-PS5-03333 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004A-CL02 | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3334 | PL-PS5-03334 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004A-CL03 | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3335 | PL-PS5-03335 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004A-CL04 | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3336 | PL-PS5-03336 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004B-CL01 | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3337 | PL-PS5-03337 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004B-CL02 | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3338 | PL-PS5-03338 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004B-CL03 | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3339 | PL-PS5-03339 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004B-CL04 | Doc. TZ-MID-68-WPR2-151166 - SS Cable Tag not install yet at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3340 | PL-PS5-03340 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GB-0003-CL01 | Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3341 | PL-PS5-03341 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GB-0003-CL02 | Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3342 | PL-PS5-03342 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GB-0003-CL03 | Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3343 | PL-PS5-03343 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GB-0003-CL04 | Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3344 | PL-PS5-03344 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GB-0003-CL05 | Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3345 | PL-PS5-03345 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GB-0003-CL06 | Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3346 | PL-PS5-03346 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GU-0003A-CL01 | Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3347 | PL-PS5-03347 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GU-0003B-CL01 | Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3348 | PL-PS5-03348 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GU-0003C-CL01 | Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3349 | PL-PS5-03349 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004A-CL01 | Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3350 | PL-PS5-03350 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004A-CL02 | Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3351 | PL-PS5-03351 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004A-CL03 | Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3352 | PL-PS5-03352 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004A-CL04 | Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3353 | PL-PS5-03353 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004B-CL01 | Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3354 | PL-PS5-03354 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004B-CL02 | Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3355 | PL-PS5-03355 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004B-CL03 | Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3356 | PL-PS5-03356 | #N/A | CPP-RFI-68-33/1-05-0298 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-IG-0004B-CL04 | Doc. TZ-MID-68-WPR2-151166 - Cable need to be Dressing Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-05-29 | CPP EIT | Gao Chong |  |  |  |  | Open
3357 | PL-PS5-03357 | #N/A | CPP-RFI-68-33/1-05-0210 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-0913-CS01 | TZ-MID-68-WPR2-151116 Permanent SS cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-03 | CPP EIT | Gao Chong |  |  |  |  | Open
3358 | PL-PS5-03358 | #N/A | CPP-RFI-68-33/1-05-0210 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-0913-CS01 | TZ-MID-68-WPR2-151116 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-03 | CPP EIT | Gao Chong |  |  |  |  | Open
3359 | PL-PS5-03359 | #N/A | CPP-RFI-68-33/1-05-0210 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-0913-CS01 | TZ-MID-68-WPR2-151116 Cable Trench to done backfilled (PS5-88-CU-HV-0040, PS5-88-CU-HV-0039) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-03 | CPP EIT | Gao Chong |  |  |  |  | Open
3360 | PL-PS5-03360 | #N/A | CPP-RFI-68-33/1-05-0210 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-XV-0053-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-03 | CPP EIT | Gao Chong | 16-06-2069 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
3361 | PL-PS5-03361 | #N/A | CPP-RFI-68-33/1-05-0210 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-XV-0053-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-03 | CPP EIT | Gao Chong |  |  |  |  | Open
3362 | PL-PS5-03362 | #N/A | CPP-RFI-68-33/1-05-0210 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-XV-0053-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Field run cable ladder to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-03 | CPP EIT | Gao Chong |  |  |  |  | Open
3363 | PL-PS5-03363 | #N/A | CPP-RFI-68-33/1-05-0210 | PS5 | Electrical Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-XV-0053-CL01 | TZ-MID-68-WPR2-151117,151114,151113 To be complete cable trench backfilled, protection tiles, and warning tape installation (PS5-88-BU-LV-00164) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-03 | CPP EIT | Gao Chong |  |  |  |  | Open
3364 | PL-PS5-03364 | #N/A | CPP-RFI-68-33/1-05-0210 | PS5 | Electrical Cable Installation | EITS Building (Outdoors) Trafo Area | PS5-63-NER-0010-CH01 | TZ-MID-68-WPR2-151112 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-03 | CPP EIT | Gao Chong |  |  |  |  | Open
3365 | PL-PS5-03365 | #N/A | CPP-RFI-68-33/1-05-0210 | PS5 | Electrical Cable Installation | EITS Building (Outdoors) Trafo Area | PS5-63-NER-0010-CH01 | TZ-MID-68-WPR2-151112 Cable ladder to be install at transformer side (PS5-88-LD-HV-6019) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-03 | CPP EIT | Gao Chong |  |  |  |  | Open
3366 | PL-PS5-03366 | #N/A | CPP-RFI-68-33/1-05-0210 | PS5 | Electrical Cable Installation | EITS Building (Outdoors) Trafo Area | PS5-63-NER-0010-CH01 | TZ-MID-68-WPR2-151112 Cable trench backfilled to be done (PS5-88-CU-HV-0031) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-03 | CPP EIT | Gao Chong |  |  |  |  | Open
3367 | PL-PS5-03367 | #N/A | CPP-RFI-68-33/1-05-0210 | PS5 | Electrical Cable Installation | EITS Building (Outdoors) Trafo Area | PS5-63-NER-0011-CH01 | TZ-MID-68-WPR2-151112 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-03 | CPP EIT | Gao Chong |  |  |  |  | Open
3368 | PL-PS5-03368 | #N/A | CPP-RFI-68-33/1-05-0210 | PS5 | Electrical Cable Installation | EITS Building (Outdoors) Trafo Area | PS5-63-NER-0011-CH01 | TZ-MID-68-WPR2-151112 Cable ladder to be install at transformer side (PS5-88-LD-HV-6020) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-03 | CPP EIT | Gao Chong |  |  |  |  | Open
3369 | PL-PS5-03369 | #N/A | CPP-RFI-68-33/1-05-0210 | PS5 | Electrical Cable Installation | EITS Building (Outdoors) Trafo Area | PS5-63-NER-0011-CH01 | TZ-MID-68-WPR2-151112 Cable trench backfilled to be done (PS5-88-CU-HV-0030) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-03 | CPP EIT | Gao Chong |  |  |  |  | Open
3370 | PL-PS5-03370 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-01-LB-0004-CL03 | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3371 | PL-PS5-03371 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD25 | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3372 | PL-PS5-03372 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-0902-CS01 | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong | 16-06-2070 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
3373 | PL-PS5-03373 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-0904-CS01 | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3374 | PL-PS5-03374 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-1007-CS01 | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong | 16-06-2071 | Konstantin Ovchinnikov | 2026-06-18 |  | CLOSED
3375 | PL-PS5-03375 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-1010-CS01 | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3376 | PL-PS5-03376 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Field | PS5-08-01FB-1105-CS01 | TZ-MID-68-WPR2-151116, 151118 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3377 | PL-PS5-03377 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Near Generator Building | PS5-60-BE-0011A-CL01 | TZ-MID-68-WPR2-151116, 151118 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3378 | PL-PS5-03378 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Near Generator Building | PS5-60-BE-0011A-CL02 | TZ-MID-68-WPR2-151116, 151118 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3379 | PL-PS5-03379 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Near Generator Building | PS5-60-BE-0011A-CL04 | TZ-MID-68-WPR2-151116, 151118 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3380 | PL-PS5-03380 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005A-CL01 | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3381 | PL-PS5-03381 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005B-CL01 | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3382 | PL-PS5-03382 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005C-CL01 | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3383 | PL-PS5-03383 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005D-CL01 | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3384 | PL-PS5-03384 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005E-CL01 | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3385 | PL-PS5-03385 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005F-CL01 | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3386 | PL-PS5-03386 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005G-CL01 | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3387 | PL-PS5-03387 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-71-IN-0001-CL03 | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3388 | PL-PS5-03388 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-71-IN-0004A-CL03 | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3389 | PL-PS5-03389 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-71-IN-0004B-CL03 | TZ-MID-68-WPR2-151116 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3390 | PL-PS5-03390 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | DRA Injection Package | PS5-75-MOV-0001-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Permanent SS Cable tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3391 | PL-PS5-03391 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-01-LB-0004-CL03 | TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3392 | PL-PS5-03392 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD25 | TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3393 | PL-PS5-03393 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-0902-CS01 | TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3394 | PL-PS5-03394 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-0904-CS01 | TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3395 | PL-PS5-03395 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-1007-CS01 | TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3396 | PL-PS5-03396 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-1010-CS01 | TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3397 | PL-PS5-03397 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Field | PS5-08-01FB-1105-CS01 | TZ-MID-68-WPR2-151116, 151118 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3398 | PL-PS5-03398 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Near Generator Building | PS5-60-BE-0011A-CL01 | TZ-MID-68-WPR2-151116, 151118 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3399 | PL-PS5-03399 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Near Generator Building | PS5-60-BE-0011A-CL02 | TZ-MID-68-WPR2-151116, 151118 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3400 | PL-PS5-03400 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Near Generator Building | PS5-60-BE-0011A-CL04 | TZ-MID-68-WPR2-151116, 151118 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3401 | PL-PS5-03401 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005A-CL01 | TZ-MID-68-WPR2-151118,151116 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3402 | PL-PS5-03402 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005B-CL01 | TZ-MID-68-WPR2-151118,151116 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3403 | PL-PS5-03403 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005C-CL01 | TZ-MID-68-WPR2-151118,151116 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3404 | PL-PS5-03404 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005D-CL01 | TZ-MID-68-WPR2-151118,151116 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3405 | PL-PS5-03405 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005E-CL01 | TZ-MID-68-WPR2-151118,151116 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3406 | PL-PS5-03406 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005F-CL01 | TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3407 | PL-PS5-03407 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005G-CL01 | TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3408 | PL-PS5-03408 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-71-IN-0001-CL03 | TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3409 | PL-PS5-03409 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-71-IN-0004A-CL03 | TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3410 | PL-PS5-03410 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-71-IN-0004B-CL03 | TZ-MID-68-WPR2-151116 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3411 | PL-PS5-03411 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | DRA Injection Package | PS5-75-MOV-0001-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3412 | PL-PS5-03412 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-0902-CS01 | TZ-MID-68-WPR2-151116 Field run cable tray/ladder to be installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3413 | PL-PS5-03413 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-0904-CS01 | TZ-MID-68-WPR2-151116 Field run cable tray/ladder to be installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3414 | PL-PS5-03414 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-1007-CS01 | TZ-MID-68-WPR2-151116 Field run cable tray/ladder to be installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3415 | PL-PS5-03415 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-1010-CS01 | TZ-MID-68-WPR2-151116 Field run cable tray/ladder to be installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3416 | PL-PS5-03416 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Field | PS5-08-01FB-1105-CS01 | TZ-MID-68-WPR2-151116, 151118 Field run cable tray/ladder to be installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3417 | PL-PS5-03417 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Near Generator Building | PS5-60-BE-0011A-CL01 | TZ-MID-68-WPR2-151116, 151118 Field run cable tray/ladder to be installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3418 | PL-PS5-03418 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Near Generator Building | PS5-60-BE-0011A-CL02 | TZ-MID-68-WPR2-151116, 151118 Field run cable tray/ladder to be installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3419 | PL-PS5-03419 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Near Generator Building | PS5-60-BE-0011A-CL04 | TZ-MID-68-WPR2-151116, 151118 Field run cable tray/ladder to be installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3420 | PL-PS5-03420 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005A-CL01 | TZ-MID-68-WPR2-151118,151116 Field run cable tray/ladder to be installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3421 | PL-PS5-03421 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005B-CL01 | TZ-MID-68-WPR2-151118,151116 Field run cable tray/ladder to be installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3422 | PL-PS5-03422 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005C-CL01 | TZ-MID-68-WPR2-151118,151116 Field run cable tray/ladder to be installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3423 | PL-PS5-03423 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005D-CL01 | TZ-MID-68-WPR2-151118,151116 Field run cable tray/ladder to be installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3424 | PL-PS5-03424 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005E-CL01 | TZ-MID-68-WPR2-151118,151116 Field run cable tray/ladder to be installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3425 | PL-PS5-03425 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005F-CL01 | TZ-MID-68-WPR2-151116 Field run cable tray/ladder to be installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3426 | PL-PS5-03426 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0005G-CL01 | TZ-MID-68-WPR2-151116 Field run cable tray/ladder to be installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3427 | PL-PS5-03427 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | DRA Injection Package | PS5-75-MOV-0001-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Field run cable tray/ladder to be installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3428 | PL-PS5-03428 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-0902-CS01 | TZ-MID-68-WPR2-151116 Cable trench backfilled to be done ( PS5-88-CU-HV-0039, PS5-88-CU-HV-0041, PS5-88-CU-HV-0043, PS5-88-CU-HV-0045) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3429 | PL-PS5-03429 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-0904-CS01 | TZ-MID-68-WPR2-151116 Cable trench backfilled to be done (PS5-88-CU-HV-0052, PS5-88-CU-HV-0051, PS5-88-CU-HV-0050) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3430 | PL-PS5-03430 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Field | PS5-08-01FB-1105-CS01 | TZ-MID-68-WPR2-151116, 151118 Cable trench backfilled to be done (PS5-88-CU-HV-0049, PS5-88-CU-HV-0051, PS5-88-CU-HV-0052) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3431 | PL-PS5-03431 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-71-IN-0001-CL03 | TZ-MID-68-WPR2-151116 Cable trench backfiled, protection tiles, and warning tape installation to be done (PS5-88-BU-LV-00160) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3432 | PL-PS5-03432 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-71-IN-0004A-CL03 | TZ-MID-68-WPR2-151116 Cable trench backfiled, protection tiles, and warning tape installation to be done (PS5-88-BU-LV-00159) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3433 | PL-PS5-03433 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-71-IN-0004B-CL03 | TZ-MID-68-WPR2-151116 Cable trench backfiled, protection tiles, and warning tape installation to be done (PS5-88-BU-LV-00159) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3434 | PL-PS5-03434 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | DRA Injection Package | PS5-75-MOV-0001-CL01 | TZ-MID-68-WPR2-151117,151114,151113 Cable trench backfiled, protection tiles, and warning tape installation to be done (PS5-88-BU-LV-00164) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3435 | PL-PS5-03435 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-1007-CS01 | TZ-MID-68-WPR2-151116 Cable coiled 20MTR to be laid in the ladder | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3436 | PL-PS5-03436 | #N/A | CPP-RFI-68-331-05-0312 | PS5 | Electrical Cable Installation | Power generator building area | PS5-08-01FB-1010-CS01 | TZ-MID-68-WPR2-151116 Cable coiled 20MTR to be laid in the ladder | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | Open
3437 | PL-PS5-03437 | #N/A | CPP-RFI-68-331-05-0314 | PS5 | Electrical cable ladder/Tray installation | Power generator building area | N/A | Doc.TZ-MID-68-WPR2-151118,TZ-MID-68-WPR2-151179 Bolts tightening on connection plates to be completed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3438 | PL-PS5-03438 | #N/A | CPP-RFI-68-331-05-0314 | PS5 | Electrical cable ladder/Tray installation | Power generator building area | N/A | Doc.TZ-MID-68-WPR2-151118,TZ-MID-68-WPR2-151179 Earth jumper not installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3439 | PL-PS5-03439 | #N/A | CPP-RFI-68-331-05-0314 | PS5 | Electrical cable ladder/Tray installation | Power generator building area | N/A | Doc.TZ-MID-68-WPR2-151118,TZ-MID-68-WPR2-151179 Cover not installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3440 | PL-PS5-03440 | #N/A | CPP-RFI-68-331-05-0314 | PS5 | Electrical cable ladder/Tray installation | Power generator building area | N/A | Doc.TZ-MID-68-WPR2-151118,TZ-MID-68-WPR2-151179 Earth strap not installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3441 | PL-PS5-03441 | #N/A | CPP-RFI-68-331-05-0314 | PS5 | Electrical cable ladder/Tray installation | Power generator building area | N/A | Doc.TZ-MID-68-WPR2-151118,TZ-MID-68-WPR2-151179 Grommets not installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3442 | PL-PS5-03442 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-01-PIT-0010-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3443 | PL-PS5-03443 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-03-RDIR-0114-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3444 | PL-PS5-03444 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-03-RDIR-0115-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3445 | PL-PS5-03445 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-03-RDIR-0116-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3446 | PL-PS5-03446 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-03-RDIR-0117-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3447 | PL-PS5-03447 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-03-RDIR-0118-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3448 | PL-PS5-03448 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-03-RMAC-0101-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3449 | PL-PS5-03449 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-03-RMAC-0103-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3450 | PL-PS5-03450 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-03-GDLHP-0147-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3451 | PL-PS5-03451 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-03-GDLHP-0149-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3452 | PL-PS5-03452 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-03-GDLHP-0150-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3453 | PL-PS5-03453 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-25-PIT-0008A-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3454 | PL-PS5-03454 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-25-PIT-0022-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3455 | PL-PS5-03455 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-25-MOV-0002-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3456 | PL-PS5-03456 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-25-MOV-0003-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3457 | PL-PS5-03457 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-25-MOV-0012-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3458 | PL-PS5-03458 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-25-MOV-0011-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3459 | PL-PS5-03459 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-25-MOV-0026-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3460 | PL-PS5-03460 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-25-MOV-0027-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3461 | PL-PS5-03461 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-28-SY-0053BB-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3462 | PL-PS5-03462 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-SY-0054AB-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3463 | PL-PS5-03463 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-28-SY-0045B-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3464 | PL-PS5-03464 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-SY-0046B-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3465 | PL-PS5-03465 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-XY-0053-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3466 | PL-PS5-03466 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-XY-0070-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3467 | PL-PS5-03467 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-25-ESY-0021A-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3468 | PL-PS5-03468 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-SDV-0035A-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3469 | PL-PS5-03469 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-SDV-0035B-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3470 | PL-PS5-03470 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-SDV-0036A-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3471 | PL-PS5-03471 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-SDV-0046-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3472 | PL-PS5-03472 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-SDV-0054A-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3473 | PL-PS5-03473 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-SDV-0054B-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3474 | PL-PS5-03474 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-SDV-0022-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3475 | PL-PS5-03475 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-28-SDV-0053A-CC01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3476 | PL-PS5-03476 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-HS-8101A-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3477 | PL-PS5-03477 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-HS-8101B-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3478 | PL-PS5-03478 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-HS-8101C-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3479 | PL-PS5-03479 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-HS-8102A-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3480 | PL-PS5-03480 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-HS-8102B-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3481 | PL-PS5-03481 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-HS-8102C-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3482 | PL-PS5-03482 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-SY-0035AA-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3483 | PL-PS5-03483 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-SY-0035BA-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3484 | PL-PS5-03484 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-SY-0036AA-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3485 | PL-PS5-03485 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-SY-0046A-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3486 | PL-PS5-03486 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-SY-0054AA-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3487 | PL-PS5-03487 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-25-SY-0022-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3488 | PL-PS5-03488 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-28-SY-0053AA-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3489 | PL-PS5-03489 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Export Pump area | PS5-28-SY-0053BA-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3490 | PL-PS5-03490 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-28-LIT-1102-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3491 | PL-PS5-03491 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-28-LIT-1202-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3492 | PL-PS5-03492 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-28-PIT-0041-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3493 | PL-PS5-03493 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-28-PIT-0045-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3494 | PL-PS5-03494 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-28-TIT-1105-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3495 | PL-PS5-03495 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-28-PIT-3901A-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3496 | PL-PS5-03496 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Launcher & Receiver area | PS5-28-PIT-3901B-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3497 | PL-PS5-03497 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Utility area | PS5-28-LIT-0002-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3498 | PL-PS5-03498 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Utility area | PS5-50-FIT-0001-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3499 | PL-PS5-03499 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Utility area | PS5-28-LIT-0008-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3500 | PL-PS5-03500 | #N/A | CPP-RFI-68-64-04-0060 | PS5 | Instrument Cable Installation | Utility area | PS5-74-PIT-0002-CJ01 | Doc.TZ-MID-68-WPR2-161500 - Dressing to be done at both end | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-04 | CPP EIT | Gao Chong |  |  |  |  | OPEN
3501 | PL-PS5-03501 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0112-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3502 | PL-PS5-03502 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0068-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3503 | PL-PS5-03503 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0042-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3504 | PL-PS5-03504 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0121-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3505 | PL-PS5-03505 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0116-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3506 | PL-PS5-03506 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0155-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3507 | PL-PS5-03507 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0083-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3508 | PL-PS5-03508 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0291-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3509 | PL-PS5-03509 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0003-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3510 | PL-PS5-03510 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0143-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3511 | PL-PS5-03511 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0059-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3512 | PL-PS5-03512 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0006-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3513 | PL-PS5-03513 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0240-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3514 | PL-PS5-03514 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0156-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3515 | PL-PS5-03515 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0068-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3516 | PL-PS5-03516 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0042-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3517 | PL-PS5-03517 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0121-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3518 | PL-PS5-03518 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0116-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3519 | PL-PS5-03519 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0291-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3520 | PL-PS5-03520 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0003-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3521 | PL-PS5-03521 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0143-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3522 | PL-PS5-03522 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0059-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3523 | PL-PS5-03523 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0006-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3524 | PL-PS5-03524 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0240-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3525 | PL-PS5-03525 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0112-CL01 | TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3526 | PL-PS5-03526 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0068-CL01 | TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3527 | PL-PS5-03527 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0042-CL01 | TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3528 | PL-PS5-03528 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0121-CL01 | TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3529 | PL-PS5-03529 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0116-CL01 | TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3530 | PL-PS5-03530 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0155-CL01 | TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3531 | PL-PS5-03531 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0083-CL01 | TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3532 | PL-PS5-03532 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0291-CL01 | TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3533 | PL-PS5-03533 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0003-CL01 | TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3534 | PL-PS5-03534 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0143-CL01 | TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3535 | PL-PS5-03535 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0059-CL01 | TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3536 | PL-PS5-03536 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0006-CL01 | TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3537 | PL-PS5-03537 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0240-CL01 | TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3538 | PL-PS5-03538 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0156-CD01 | TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3539 | PL-PS5-03539 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0068-CD01 | TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3540 | PL-PS5-03540 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0042-CD01 | TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3541 | PL-PS5-03541 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0121-CD01 | TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3542 | PL-PS5-03542 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0116-CD01 | TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3543 | PL-PS5-03543 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0291-CD01 | TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3544 | PL-PS5-03544 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0003-CD01 | TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3545 | PL-PS5-03545 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0143-CD01 | TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3546 | PL-PS5-03546 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0059-CD01 | TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3547 | PL-PS5-03547 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0006-CD01 | TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3548 | PL-PS5-03548 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0240-CD01 | TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3549 | PL-PS5-03549 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0112-CL01 | TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3550 | PL-PS5-03550 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0068-CL01 | TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3551 | PL-PS5-03551 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0042-CL01 | TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3552 | PL-PS5-03552 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0121-CL01 | TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3553 | PL-PS5-03553 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0116-CL01 | TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3554 | PL-PS5-03554 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0155-CL01 | TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3555 | PL-PS5-03555 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0083-CL01 | TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3556 | PL-PS5-03556 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0291-CL01 | TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3557 | PL-PS5-03557 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0003-CL01 | TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3558 | PL-PS5-03558 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0143-CL01 | TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3559 | PL-PS5-03559 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0059-CL01 | TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3560 | PL-PS5-03560 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0006-CL01 | TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3561 | PL-PS5-03561 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-BE-0240-CL01 | TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3562 | PL-PS5-03562 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0156-CD01 | TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3563 | PL-PS5-03563 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0068-CD01 | TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3564 | PL-PS5-03564 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0042-CD01 | TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3565 | PL-PS5-03565 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0121-CD01 | TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3566 | PL-PS5-03566 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0116-CD01 | TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3567 | PL-PS5-03567 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0291-CD01 | TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3568 | PL-PS5-03568 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0003-CD01 | TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3569 | PL-PS5-03569 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0143-CD01 | TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3570 | PL-PS5-03570 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0059-CD01 | TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3571 | PL-PS5-03571 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0006-CD01 | TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3572 | PL-PS5-03572 | #N/A | CPP-RFI-68-33/1-05-0315 | PS5 | EHT Power Cable Installation | Export Pump Area | PS5-79-TE-0240-CD01 | TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-05 | CPP EIT | Gao Chong |  |  |  |  | Open
3573 | PL-PS5-03573 | #N/A | CPP-RFI-68-33/1-05-0309 | PS5 | Electrical Cable installation | Power Generation Building Area | PS5-05-IG-0025-CL01 | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable Tagging Installaton not Yet Done at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3574 | PL-PS5-03574 | #N/A | CPP-RFI-68-33/1-05-0309 | PS5 | Electrical Cable installation | Power Generation Building Area | PS5-05-IG-0026-CL01 | TZ-MID-68-WPR2-151166, Cable Tagging Installation not Yet Done at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3575 | PL-PS5-03575 | #N/A | CPP-RFI-68-33/1-05-0309 | PS5 | Electrical Cable installation | Power Generation Building Area | PS5-60-BE-0021A-CL01 | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118, Cable Tagging not yet done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3576 | PL-PS5-03576 | #N/A | CPP-RFI-68-33/1-05-0309 | PS5 | Electrical Cable installation | Power Generation Building Area | PS5-60-IE-0002B-CL01 | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable Tagging Installaton not Yet Done at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3577 | PL-PS5-03577 | #N/A | CPP-RFI-68-33/1-05-0309 | PS5 | Electrical Cable installation | Power Generation Building Area | PS5-71-IN-0003-CL03 | TZ-MID-68-WPR2-151166, Cable Tagging Installation not Yet Done at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3578 | PL-PS5-03578 | #N/A | CPP-RFI-68-33/1-05-0309 | PS5 | Electrical Cable installation | Power Generation Building Area | PS5-05-IG-0025-CL01 | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3579 | PL-PS5-03579 | #N/A | CPP-RFI-68-33/1-05-0309 | PS5 | Electrical Cable installation | Power Generation Building Area | PS5-05-IG-0026-CL01 | TZ-MID-68-WPR2-151166, Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3580 | PL-PS5-03580 | #N/A | CPP-RFI-68-33/1-05-0309 | PS5 | Electrical Cable installation | Power Generation Building Area | PS5-60-BE-0021A-CL01 | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118, Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3581 | PL-PS5-03581 | #N/A | CPP-RFI-68-33/1-05-0309 | PS5 | Electrical Cable installation | Power Generation Building Area | PS5-60-IE-0002B-CL01 | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3582 | PL-PS5-03582 | #N/A | CPP-RFI-68-33/1-05-0309 | PS5 | Electrical Cable installation | Power Generation Building Area | PS5-71-IN-0003-CL03 | TZ-MID-68-WPR2-151166, Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3583 | PL-PS5-03583 | #N/A | CPP-RFI-68-33/1-05-0309 | PS5 | Electrical Cable installation | Power Generation Building Area | PS5-05-IG-0025-CL01 | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable Reaching final Destination, But need to Install Cable Tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3584 | PL-PS5-03584 | #N/A | CPP-RFI-68-33/1-05-0309 | PS5 | Electrical Cable installation | Power Generation Building Area | PS5-05-IG-0026-CL01 | TZ-MID-68-WPR2-151166, Cable Not Reaching Final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3585 | PL-PS5-03585 | #N/A | CPP-RFI-68-33/1-05-0309 | PS5 | Electrical Cable installation | Power Generation Building Area | PS5-60-BE-0021A-CL01 | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118, Cable Reaching Final Destination, but need to install cable tray | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3586 | PL-PS5-03586 | #N/A | CPP-RFI-68-33/1-05-0309 | PS5 | Electrical Cable installation | Power Generation Building Area | PS5-60-IE-0002B-CL01 | TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151179, Cable not Reaching Final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3587 | PL-PS5-03587 | #N/A | CPP-RFI-68-33/1-05-0309 | PS5 | Electrical Cable installation | Power Generation Building Area | PS5-71-IN-0003-CL03 | TZ-MID-68-WPR2-151166, Cable not reaching final destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3588 | PL-PS5-03588 | #N/A | CPP-RFI-68-64-03-0059 | PS5 | Instrument cable ladder/Tray installation | Power generation cooling tower area & CFO area | N/A | Doc.TZ-MID-68-WPR2-161500 Bolts tightening on connection plates to be completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-11 | CPP EIT | Gao Chong |  |  |  |  | Open
3589 | PL-PS5-03589 | #N/A | CPP-RFI-68-64-03-0059 | PS5 | Instrument cable ladder/Tray installation | Power generation cooling tower area & CFO area | N/A | Doc.TZ-MID-68-WPR2-161500 Earth jumper not installed completely | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-12 | CPP EIT | Gao Chong |  |  |  |  | Open
3590 | PL-PS5-03590 | #N/A | CPP-RFI-68-64-03-0059 | PS5 | Instrument cable ladder/Tray installation | Power generation cooling tower area & CFO area | N/A | Doc.TZ-MID-68-WPR2-161500 Cover not installed | C | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-13 | CPP EIT | Gao Chong |  |  |  |  | Open
3591 | PL-PS5-03591 | #N/A | CPP-RFI-68-64-03-0059 | PS5 | Instrument cable ladder/Tray installation | Power generation cooling tower area & CFO area | N/A | Doc.TZ-MID-68-WPR2-161500 Earth strap not installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-14 | CPP EIT | Gao Chong |  |  |  |  | Open
3592 | PL-PS5-03592 | #N/A | CPP-RFI-68-64-03-0059 | PS5 | Instrument cable ladder/Tray installation | Power generation cooling tower area & CFO area | N/A | Doc.TZ-MID-68-WPR2-161500 Grommets not installed | C | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3593 | PL-PS5-03593 | #N/A | CPP-RFI-68-332-02-0331 | PS5 | Electrical Equipment Installation | Power Distribution Area | PS5-61-IV-0001A | TZ-MID-68-WPR2-151112 Carry out cleanning body of the transformer and surrounding bay area | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3594 | PL-PS5-03594 | #N/A | CPP-RFI-68-332-02-0331 | PS5 | Electrical Equipment Installation | Power Distribution Area | PS5-61-IV-0001A | TZ-MID-68-WPR2-151112 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3595 | PL-PS5-03595 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Export Pump VSD Area & Chemical and Waste Storage Area | PS5-02-SWSI-0001-CL01 | Doc. TZ-MID-68-WPR2-151111 TZ-MID-68-WPR2-151105, Cable Tagging Not Yet installed at both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3596 | PL-PS5-03596 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generator Building | PS5-08-52BT-0137-CS01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-171127, Cable Tagging Not Yet Installed at Both Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3597 | PL-PS5-03597 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BE-0007D-CL02 | Doc. TZ-MID-68-WPR2-151179, Cable Tagging not yet installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3598 | PL-PS5-03598 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BE-0007D-CL03 | Doc. TZ-MID-68-WPR2-151179, Cable Tagging not yet installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3599 | PL-PS5-03599 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011A-CL03 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3600 | PL-PS5-03600 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011A-CL05 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3601 | PL-PS5-03601 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011A-CL06 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3602 | PL-PS5-03602 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3603 | PL-PS5-03603 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3604 | PL-PS5-03604 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL03 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3605 | PL-PS5-03605 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL04 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3606 | PL-PS5-03606 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL05 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3607 | PL-PS5-03607 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL06 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3608 | PL-PS5-03608 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3609 | PL-PS5-03609 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3610 | PL-PS5-03610 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL03 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3611 | PL-PS5-03611 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL04 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3612 | PL-PS5-03612 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL05 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3613 | PL-PS5-03613 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL06 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3614 | PL-PS5-03614 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012B-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3615 | PL-PS5-03615 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012B-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3616 | PL-PS5-03616 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012B-CL03 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3617 | PL-PS5-03617 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012B-CL04 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3618 | PL-PS5-03618 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012B-CL05 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3619 | PL-PS5-03619 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024B-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3620 | PL-PS5-03620 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024D-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3621 | PL-PS5-03621 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0005A-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3622 | PL-PS5-03622 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0005B-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3623 | PL-PS5-03623 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024A-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3624 | PL-PS5-03624 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024D-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3625 | PL-PS5-03625 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0026D-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3626 | PL-PS5-03626 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0026D-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3627 | PL-PS5-03627 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0026E-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3628 | PL-PS5-03628 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0026F-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3629 | PL-PS5-03629 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024A-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3630 | PL-PS5-03630 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024B-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3631 | PL-PS5-03631 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IJ-0001-CD37 | Doc. TZ-MID-68-WPR2-151112 Cable Tagging not yet install at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3632 | PL-PS5-03632 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Export Pump VSD Area & Chemical and Waste Storage Area | PS5-02-SWSI-0001-CL01 | Doc. TZ-MID-68-WPR2-151111 TZ-MID-68-WPR2-151105, Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3633 | PL-PS5-03633 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generator Building | PS5-08-52BT-0137-CS01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-171127, Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3634 | PL-PS5-03634 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BE-0007D-CL02 | Doc. TZ-MID-68-WPR2-151179, Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3635 | PL-PS5-03635 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BE-0007D-CL03 | Doc. TZ-MID-68-WPR2-151179, Cable dresing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3636 | PL-PS5-03636 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011A-CL03 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3637 | PL-PS5-03637 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011A-CL05 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3638 | PL-PS5-03638 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011A-CL06 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3639 | PL-PS5-03639 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3640 | PL-PS5-03640 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3641 | PL-PS5-03641 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL03 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3642 | PL-PS5-03642 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL04 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3643 | PL-PS5-03643 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL05 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3644 | PL-PS5-03644 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL06 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3645 | PL-PS5-03645 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3646 | PL-PS5-03646 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3647 | PL-PS5-03647 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL03 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3648 | PL-PS5-03648 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL04 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3649 | PL-PS5-03649 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL05 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3650 | PL-PS5-03650 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL06 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3651 | PL-PS5-03651 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012B-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3652 | PL-PS5-03652 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012B-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3653 | PL-PS5-03653 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012B-CL03 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3654 | PL-PS5-03654 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012B-CL04 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3655 | PL-PS5-03655 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012B-CL05 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3656 | PL-PS5-03656 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024B-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3657 | PL-PS5-03657 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024D-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3658 | PL-PS5-03658 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0005A-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3659 | PL-PS5-03659 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0005B-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3660 | PL-PS5-03660 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024A-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3661 | PL-PS5-03661 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024D-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3662 | PL-PS5-03662 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0026D-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3663 | PL-PS5-03663 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0026D-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3664 | PL-PS5-03664 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0026E-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3665 | PL-PS5-03665 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0026F-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3666 | PL-PS5-03666 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024A-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3667 | PL-PS5-03667 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024B-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3668 | PL-PS5-03668 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IJ-0001-CD37 | Doc. TZ-MID-68-WPR2-151112 Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3669 | PL-PS5-03669 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Export Pump VSD Area & Chemical and Waste Storage Area | PS5-02-SWSI-0001-CL01 | Doc. TZ-MID-68-WPR2-151111 TZ-MID-68-WPR2-151105, Cable Not Yet Reaching Final Destination, Coiled more than 10 MTR need to Open Trench to Finish installation & Reaching Final Destination (Illuminated Windshock) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3670 | PL-PS5-03670 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generator Building | PS5-08-52BT-0137-CS01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-171127, Cable not reaching final destination, coiled 5 MTR from Final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3671 | PL-PS5-03671 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BE-0007D-CL02 | Doc. TZ-MID-68-WPR2-151179, Cable Coiled in Control Panel Side, Not yet Reaching Final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3672 | PL-PS5-03672 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BE-0007D-CL03 | Doc. TZ-MID-68-WPR2-151179, Cable Coiled in Control Panel Side, Not yet Reaching Final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3673 | PL-PS5-03673 | PL-PS5-03673 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011A-CL03 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3674 | PL-PS5-03674 | PL-PS5-03674 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011A-CL05 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3675 | PL-PS5-03675 | PL-PS5-03675 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011A-CL06 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3676 | PL-PS5-03676 | PL-PS5-03676 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3677 | PL-PS5-03677 | PL-PS5-03677 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3678 | PL-PS5-03678 | PL-PS5-03678 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL03 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3679 | PL-PS5-03679 | PL-PS5-03679 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL04 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3680 | PL-PS5-03680 | PL-PS5-03680 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL05 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3681 | PL-PS5-03681 | PL-PS5-03681 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0011B-CL06 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3682 | PL-PS5-03682 | PL-PS5-03682 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3683 | PL-PS5-03683 | PL-PS5-03683 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3684 | PL-PS5-03684 | PL-PS5-03684 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL03 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3685 | PL-PS5-03685 | PL-PS5-03685 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL04 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3686 | PL-PS5-03686 | PL-PS5-03686 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL05 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3687 | PL-PS5-03687 | PL-PS5-03687 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012A-CL06 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3688 | PL-PS5-03688 | PL-PS5-03688 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012B-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3689 | PL-PS5-03689 | PL-PS5-03689 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012B-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3690 | PL-PS5-03690 | PL-PS5-03690 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012B-CL03 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3691 | PL-PS5-03691 | PL-PS5-03691 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012B-CL04 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3692 | PL-PS5-03692 | PL-PS5-03692 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0012B-CL05 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Coiled front below the Cooler, Install Cable Ladder to reaching final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3693 | PL-PS5-03693 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024B-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Destination, But need to install Vertikal Cable Ladder | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3694 | PL-PS5-03694 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024D-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Destination, But need to install cable ladder | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3695 | PL-PS5-03695 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0005A-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable not Reaching Final Destination (Incorrect Destination) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3696 | PL-PS5-03696 | PL-PS5-03696 | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0005B-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Destination, but need to install cable ladder | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong | 2026-04-07 | Rustam BATTALOV | 2026-11-07 |  | CLOSED
3697 | PL-PS5-03697 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024A-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Destination, but need to install cable ladder | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3698 | PL-PS5-03698 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024D-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable not Reaching Final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3699 | PL-PS5-03699 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0026D-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Dressing not yet done, Cable Not Reaching Final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3700 | PL-PS5-03700 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0026D-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Final Destination, but need to install cable LADDER | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3701 | PL-PS5-03701 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0026E-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Final Destination, but need to install cable LADDER | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3702 | PL-PS5-03702 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0026F-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Final Destination, but need to install cable LADDER | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3703 | PL-PS5-03703 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024A-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Final Destination, but need to install cable LADDER | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3704 | PL-PS5-03704 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Generator Electrical Building & Power Generation Cooling Tower Area | PS5-60-BE-0024B-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151118 Cable Reaching Final Destination, but need to install cable LADDER | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3705 | PL-PS5-03705 | #N/A | CPP-RFI-68-33/1-05-0329 | PS5 | Electrical Cable Installation | Power Distribution Area | PS5-61-IJ-0001-CD37 | Doc. TZ-MID-68-WPR2-151112 Cable Reaching Final Destination, but need to install Cable Tray (at Transformers side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-10 | CPP EIT | Gao Chong |  |  |  |  | Open
3706 | PL-PS5-03706 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0401-11 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-13 | CPP EIT | Gao Chong |  |  |  |  | Open
3707 | PL-PS5-03707 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0402-11 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-13 | CPP EIT | Gao Chong |  |  |  |  | Open
3708 | PL-PS5-03708 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0403-11 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-13 | CPP EIT | Gao Chong |  |  |  |  | Open
3709 | PL-PS5-03709 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0404-11 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-13 | CPP EIT | Gao Chong |  |  |  |  | Open
3710 | PL-PS5-03710 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0405-11 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-13 | CPP EIT | Gao Chong |  |  |  |  | Open
3711 | PL-PS5-03711 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0406-11 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-13 | CPP EIT | Gao Chong |  |  |  |  | Open
3712 | PL-PS5-03712 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0407-11 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-13 | CPP EIT | Gao Chong |  |  |  |  | Open
3713 | PL-PS5-03713 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0408-11 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-13 | CPP EIT | Gao Chong |  |  |  |  | Open
3714 | PL-PS5-03714 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0409-11 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-13 | CPP EIT | Gao Chong |  |  |  |  | Open
3715 | PL-PS5-03715 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near Export Pump Area | PS5-62-IE-0002 | TZ-MID-68-WPR2-151117 Perform cleanning internal and external of the panel | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3716 | PL-PS5-03716 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near Export Pump Area | PS5-05-IG-0004 | TZ-MID-68-WPR2-151117 Perform cleanning internal and external of the panel | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3717 | PL-PS5-03717 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near Export Pump Area | PS5-61-IG-0006 | TZ-MID-68-WPR2-151117 Perform cleanning internal and external of the panel | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3718 | PL-PS5-03718 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near Export Pump Area | PS5-61-IG-0042 | TZ-MID-68-WPR2-151117 Perform cleanning internal and external of the panel | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3719 | PL-PS5-03719 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near Export Pump Area | PS5-61-IG-0043 | TZ-MID-68-WPR2-151117 Perform cleanning internal and external of the panel | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3720 | PL-PS5-03720 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near VSD Area | PS5-62-IE-0001 | TZ-MID-68-WPR2-151111 Perform cleanning internal and external of the panel | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3721 | PL-PS5-03721 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near VSD Area | PS5-05-IG-0006 | TZ-MID-68-WPR2-151111 Perform cleanning internal and external of the panel | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3722 | PL-PS5-03722 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near VSD Area | PS5-61-IG-0007 | TZ-MID-68-WPR2-151111 Perform cleanning internal and external of the panel | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3723 | PL-PS5-03723 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near VSD Area | PS5-61-IG-0014 | TZ-MID-68-WPR2-151111 Perform cleanning internal and external of the panel | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3724 | PL-PS5-03724 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near Export Pump Area | PS5-62-IE-0002 | TZ-MID-68-WPR2-151117 To be clean weld slag and touch up paint at the panel support. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3725 | PL-PS5-03725 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near Export Pump Area | PS5-05-IG-0004 | TZ-MID-68-WPR2-151117 To be clean weld slag and touch up paint at the panel support. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3726 | PL-PS5-03726 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near Export Pump Area | PS5-61-IG-0006 | TZ-MID-68-WPR2-151117 To be clean weld slag and touch up paint at the panel support. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3727 | PL-PS5-03727 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near Export Pump Area | PS5-61-IG-0042 | TZ-MID-68-WPR2-151117 To be clean weld slag and touch up paint at the panel support. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3728 | PL-PS5-03728 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near Export Pump Area | PS5-61-IG-0043 | TZ-MID-68-WPR2-151117 To be clean weld slag and touch up paint at the panel support. | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3729 | PL-PS5-03729 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near VSD Area | PS5-62-IE-0001 | TZ-MID-68-WPR2-151111 Isolation pad to be install at SS bracket and bolts since disimilar material. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3730 | PL-PS5-03730 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near VSD Area | PS5-05-IG-0006 | TZ-MID-68-WPR2-151111 Isolation pad to be install at SS bracket and bolts since disimilar material. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3731 | PL-PS5-03731 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near VSD Area | PS5-61-IG-0007 | TZ-MID-68-WPR2-151111 Isolation pad to be install at SS bracket and bolts since disimilar material. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3732 | PL-PS5-03732 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near VSD Area | PS5-61-IG-0014 | TZ-MID-68-WPR2-151111 Isolation pad to be install at SS bracket and bolts since disimilar material. | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3733 | PL-PS5-03733 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near Export Pump Area | PS5-61-IG-0042 | TZ-MID-68-WPR2-151117 Door glass has cracked to be rectify/replaced | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3734 | PL-PS5-03734 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near Export Pump Area | PS5-05-IG-0004 | TZ-MID-68-WPR2-151117 Door glass has cracked to be rectify/replaced | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3735 | PL-PS5-03735 | #N/A | CPP-RFI-68-332-03-0341 | PS5 | Electrical Equipment Installation | Near VSD Area | PS5-61-IG-0007 | TZ-MID-68-WPR2-151111 Body panel scratc to be touch up paint | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-15 | CPP EIT | Gao Chong |  |  |  |  | Open
3736 | PL-PS5-03736 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0401-09 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-16 | CPP EIT | Gao Chong |  |  |  |  | Open
3737 | PL-PS5-03737 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0402-09 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-16 | CPP EIT | Gao Chong |  |  |  |  | Open
3738 | PL-PS5-03738 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0403-09 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-16 | CPP EIT | Gao Chong |  |  |  |  | Open
3739 | PL-PS5-03739 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0404-09 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-16 | CPP EIT | Gao Chong |  |  |  |  | Open
3740 | PL-PS5-03740 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0405-09 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-16 | CPP EIT | Gao Chong |  |  |  |  | Open
3741 | PL-PS5-03741 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0406-09 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-16 | CPP EIT | Gao Chong |  |  |  |  | Open
3742 | PL-PS5-03742 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0407-09 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-16 | CPP EIT | Gao Chong |  |  |  |  | Open
3743 | PL-PS5-03743 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0408-09 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-16 | CPP EIT | Gao Chong |  |  |  |  | Open
3744 | PL-PS5-03744 | #N/A | CPP-RFI-68-33/2-04-0337 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0409-09 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-16 | CPP EIT | Gao Chong |  |  |  |  | Open
3745 | PL-PS5-03745 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0002-CG01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3746 | PL-PS5-03746 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0002-CG02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3747 | PL-PS5-03747 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0002-CL03 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3748 | PL-PS5-03748 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0002-CL04 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3749 | PL-PS5-03749 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0002-CL05 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3750 | PL-PS5-03750 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0002-CL06 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3751 | PL-PS5-03751 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0002-CL07 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3752 | PL-PS5-03752 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0002-CL08 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3753 | PL-PS5-03753 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0002-CL09 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3754 | PL-PS5-03754 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0002-CL10 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3755 | PL-PS5-03755 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IG-0015-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3756 | PL-PS5-03756 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0002D-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3757 | PL-PS5-03757 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0002D-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3758 | PL-PS5-03758 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3759 | PL-PS5-03759 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3760 | PL-PS5-03760 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3761 | PL-PS5-03761 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3762 | PL-PS5-03762 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003D-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3763 | PL-PS5-03763 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0004-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3764 | PL-PS5-03764 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0004-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3765 | PL-PS5-03765 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001A-CL06 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3766 | PL-PS5-03766 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001B-CL05 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3767 | PL-PS5-03767 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001B-CL06 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3768 | PL-PS5-03768 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001D-CL05 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3769 | PL-PS5-03769 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0002-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3770 | PL-PS5-03770 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0002-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3771 | PL-PS5-03771 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002D-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3772 | PL-PS5-03772 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002D-CL03 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3773 | PL-PS5-03773 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IWK-0001B-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3774 | PL-PS5-03774 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IWK-0001B-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3775 | PL-PS5-03775 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IWK-0001C-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3776 | PL-PS5-03776 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IWK-0001C-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3777 | PL-PS5-03777 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-LA-0002A-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3778 | PL-PS5-03778 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-LA-0002A-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3779 | PL-PS5-03779 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-71-IN-0003-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3780 | PL-PS5-03780 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-71-IN-0003-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167 - Cable Dressing not yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3781 | PL-PS5-03781 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-IE-0003A-CD02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3782 | PL-PS5-03782 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-IE-0003B-CD05 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3783 | PL-PS5-03783 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-IE-0003D-CD03 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3784 | PL-PS5-03784 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-IE-0003D-CD05 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3785 | PL-PS5-03785 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-61-IK-0003-CL62 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3786 | PL-PS5-03786 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BE-0003A-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3787 | PL-PS5-03787 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BE-0003B-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3788 | PL-PS5-03788 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BE-0005D-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3789 | PL-PS5-03789 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BE-0012B-CL06 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151118 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3790 | PL-PS5-03790 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BE-0025A-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3791 | PL-PS5-03791 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BE-0025B-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3792 | PL-PS5-03792 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BE-0026A-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3793 | PL-PS5-03793 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BE-0026A-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3794 | PL-PS5-03794 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BE-0026B-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3795 | PL-PS5-03795 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BE-0026B-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3796 | PL-PS5-03796 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BE-0026C-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3797 | PL-PS5-03797 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BE-0026G-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3798 | PL-PS5-03798 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BI-0015A-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3799 | PL-PS5-03799 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BI-0015A-CL03 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3800 | PL-PS5-03800 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BI-0015B-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3801 | PL-PS5-03801 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BI-0015B-CL03 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3802 | PL-PS5-03802 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BI-0015D-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3803 | PL-PS5-03803 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BI-0015D-CL03 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3804 | PL-PS5-03804 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-IN-0001A-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3805 | PL-PS5-03805 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-IN-0001B-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3806 | PL-PS5-03806 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-IN-0001D-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3807 | PL-PS5-03807 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-IN-0002D-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3808 | PL-PS5-03808 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-VS-9100A-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3809 | PL-PS5-03809 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-VS-9100B-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3810 | PL-PS5-03810 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-VS-9100D-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3811 | PL-PS5-03811 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL04 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3812 | PL-PS5-03812 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL05 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3813 | PL-PS5-03813 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL06 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3814 | PL-PS5-03814 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IV-0002A-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3815 | PL-PS5-03815 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IV-0002B-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable Dressing not yet done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3816 | PL-PS5-03816 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-IE-0003D-CD14 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3817 | PL-PS5-03817 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-IE-0003A-CD04 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3818 | PL-PS5-03818 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-IE-0003D-CD04 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3819 | PL-PS5-03819 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-BE-0007D-CL01 | TZ-MID-68-WPR2-151179 -Cable Dressing not Yet Done | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3820 | PL-PS5-03820 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-61-IG-0015-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3821 | PL-PS5-03821 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-IE-0002D-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3822 | PL-PS5-03822 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building & Generator Building | PS5-60-IE-0002D-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3823 | PL-PS5-03823 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not reaching final destinantion (Coiled not in Below of final Panel Location) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3824 | PL-PS5-03824 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not reaching final destinantion (Coiled not in Below of final Panel Location) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3825 | PL-PS5-03825 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not reaching final destinantion (Coiled not in Below of final Panel Location) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3826 | PL-PS5-03826 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not reaching final destinantion (Coiled not in Below of final Panel Location) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3827 | PL-PS5-03827 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IH-0001A-CL06 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching, Coiled around 2 MTR to final Panel (PS5-60-IH-0001A) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3828 | PL-PS5-03828 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IN-0002D-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Need to Install Vertical Cable ladder to provide support for cable installation (Generator Building Site) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3829 | PL-PS5-03829 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IN-0002D-CL03 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Need to Install Vertical Cable ladder to provide support for cable installation (Generator Building Site) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3830 | PL-PS5-03830 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IWK-0001B-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching, Coiled around 3 MTR to final Panel (PS5-60-IWK-0001B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3831 | PL-PS5-03831 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IWK-0001B-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching, Coiled around 3 MTR to final Panel (PS5-60-IWK-0001B) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3832 | PL-PS5-03832 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IWK-0001C-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching, Coiled around 5 MTR to final Panel (PS5-60-IWK-0001C) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3833 | PL-PS5-03833 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IWK-0001C-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching, Coiled around 5 MTR to final Panel (PS5-60-IWK-0001C) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3834 | PL-PS5-03834 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IE-0003A-CD02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3835 | PL-PS5-03835 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IE-0003B-CD05 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3836 | PL-PS5-03836 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IE-0003D-CD03 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3837 | PL-PS5-03837 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IE-0003D-CD05 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3838 | PL-PS5-03838 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BE-0003A-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3839 | PL-PS5-03839 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BE-0003B-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3840 | PL-PS5-03840 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BE-0005D-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3841 | PL-PS5-03841 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BE-0012B-CL06 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, 151118, Cable Not Reaching to Final Destination (PS5-60-BE-0012B) Cooler Fan JB need to install Cable Ladder | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3842 | PL-PS5-03842 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BE-0025A-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cable not Reaching final destination, coiled around 9 MTR to final Destination (Generator Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3843 | PL-PS5-03843 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BE-0025B-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cable not Reaching final destination, coiled around 9 MTR to final Destination (Generator Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3844 | PL-PS5-03844 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BE-0026A-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3845 | PL-PS5-03845 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BE-0026A-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3846 | PL-PS5-03846 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BE-0026B-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3847 | PL-PS5-03847 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BE-0026B-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3848 | PL-PS5-03848 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BE-0026C-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3849 | PL-PS5-03849 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BE-0026G-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3850 | PL-PS5-03850 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BI-0015A-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cable Reaching final destination, coiled around 5 MTR to Final Destination | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3851 | PL-PS5-03851 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BI-0015A-CL03 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3852 | PL-PS5-03852 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BI-0015B-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3853 | PL-PS5-03853 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BI-0015B-CL03 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3854 | PL-PS5-03854 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BI-0015D-CL02 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3855 | PL-PS5-03855 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-BI-0015D-CL03 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3856 | PL-PS5-03856 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IN-0001A-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3857 | PL-PS5-03857 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IN-0001B-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3858 | PL-PS5-03858 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IN-0001D-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3859 | PL-PS5-03859 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IN-0002D-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3860 | PL-PS5-03860 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-VS-9100A-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3861 | PL-PS5-03861 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-VS-9100B-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3862 | PL-PS5-03862 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-VS-9100D-CL01 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3863 | PL-PS5-03863 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-61-IK-0003-CL04 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching final destination around 2 MTR (PS5-61-IK-0003) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3864 | PL-PS5-03864 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-61-IK-0003-CL05 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, Cable not Reaching final destination around 2 MTR (PS5-61-IK-0003) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3865 | PL-PS5-03865 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IE-0003D-CD14 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3866 | PL-PS5-03866 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IE-0003A-CD04 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3867 | PL-PS5-03867 | #N/A | CPP-RFI-68-33/1-05-0346 | PS5 | Electrical Cable Installation |  | PS5-60-IE-0003D-CD04 | Doc. TZ.MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 -, need to install Vertical & Horizontal Cable ladder to provide support for cable installation (Generator Building Side) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3868 | PL-PS5-03868 | #N/A | CPP-RFI-68-64-05-0064 | PS5 | Junction Box Installation | FIRE WATER AREA | PS5-53-BI-1304 | Doc.UT-MID-60-WPR2-160101 -Junction Box TAG to be installed | B | instrument | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3869 | PL-PS5-03869 | #N/A | CPP-RFI-68-64-05-0065 | PS5 | Junction Box Installation | PGB | PS5-03-BI-1516 | Doc.UT-MID-60-WPR2-160101 -Junction Box TAG to be installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3870 | PL-PS5-03870 | #N/A | CPP-RFI-68-64-05-0065 | PS5 | Junction Box Installation | PGB | PS5-03-BI-1512 | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3871 | PL-PS5-03871 | #N/A | CPP-RFI-68-64-05-0065 | PS5 | Junction Box Installation | PGB | PS5-03-BI-1513 | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3872 | PL-PS5-03872 | #N/A | CPP-RFI-68-64-05-0065 | PS5 | Junction Box Installation | PGB | PS5-03-BI-1514 | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3873 | PL-PS5-03873 | #N/A | CPP-RFI-68-64-05-0065 | PS5 | Junction Box Installation | PGB | PS5-03-BI-1516 | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3874 | PL-PS5-03874 | #N/A | CPP-RFI-68-64-05-0065 | PS5 | Junction Box Installation | PGB | PS5-03-BI-2506 | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3875 | PL-PS5-03875 | #N/A | CPP-RFI-68-64-05-0065 | PS5 | Junction Box Installation | PGB | PS5-03-BI-2507 | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3876 | PL-PS5-03876 | #N/A | CPP-RFI-68-64-05-0065 | PS5 | Junction Box Installation | PGB | PS5-03-BI-2508 | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3877 | PL-PS5-03877 | #N/A | CPP-RFI-68-64-05-0065 | PS5 | Junction Box Installation | PGB | PS5-03-BI-2510 | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3878 | PL-PS5-03878 | #N/A | CPP-RFI-68-64-05-0065 | PS5 | Junction Box Installation | PGB | PS5-03-BI-2514 | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3879 | PL-PS5-03879 | #N/A | CPP-RFI-68-64-05-0065 | PS5 | Junction Box Installation | PGB | PS5-71-BI-2121 | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3880 | PL-PS5-03880 | #N/A | CPP-RFI-68-64-05-0065 | PS5 | Junction Box Installation | PGB | PS5-71-BI-2125 | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
3881 | PL-PS5-03881 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0316-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3882 | PL-PS5-03882 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0315-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3883 | PL-PS5-03883 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0168-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3884 | PL-PS5-03884 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0170-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3885 | PL-PS5-03885 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0163-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3886 | PL-PS5-03886 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0167-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3887 | PL-PS5-03887 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0169-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3888 | PL-PS5-03888 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0159-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3889 | PL-PS5-03889 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0151-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3890 | PL-PS5-03890 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0356-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3891 | PL-PS5-03891 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0206-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3892 | PL-PS5-03892 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0148-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3893 | PL-PS5-03893 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0314-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3894 | PL-PS5-03894 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0149-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3895 | PL-PS5-03895 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0234-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3896 | PL-PS5-03896 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0114-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3897 | PL-PS5-03897 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0165-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3898 | PL-PS5-03898 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0166-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3899 | PL-PS5-03899 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0157-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3900 | PL-PS5-03900 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0153-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3901 | PL-PS5-03901 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0313-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3902 | PL-PS5-03902 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0188-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3903 | PL-PS5-03903 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0202-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3904 | PL-PS5-03904 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0103-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3905 | PL-PS5-03905 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0317-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3906 | PL-PS5-03906 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0306-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3907 | PL-PS5-03907 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-71-BE-0361-CL01 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3908 | PL-PS5-03908 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0316-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3909 | PL-PS5-03909 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0315-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3910 | PL-PS5-03910 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0168-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3911 | PL-PS5-03911 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0170-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3912 | PL-PS5-03912 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0163-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3913 | PL-PS5-03913 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0167-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3914 | PL-PS5-03914 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0169-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3915 | PL-PS5-03915 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0159-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3916 | PL-PS5-03916 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0151-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3917 | PL-PS5-03917 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0356-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3918 | PL-PS5-03918 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0206-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3919 | PL-PS5-03919 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0148-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3920 | PL-PS5-03920 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0314-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3921 | PL-PS5-03921 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0149-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3922 | PL-PS5-03922 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0234-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3923 | PL-PS5-03923 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0114-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3924 | PL-PS5-03924 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0166-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3925 | PL-PS5-03925 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0157-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3926 | PL-PS5-03926 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0153-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3927 | PL-PS5-03927 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0313-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3928 | PL-PS5-03928 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0188-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3929 | PL-PS5-03929 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0202-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3930 | PL-PS5-03930 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0103-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3931 | PL-PS5-03931 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0317-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3932 | PL-PS5-03932 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0306-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3933 | PL-PS5-03933 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0197-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3934 | PL-PS5-03934 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-71-TE-0361-CD01 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3935 | PL-PS5-03935 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0316-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3936 | PL-PS5-03936 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0315-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3937 | PL-PS5-03937 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0168-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3938 | PL-PS5-03938 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0170-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3939 | PL-PS5-03939 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0163-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3940 | PL-PS5-03940 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0167-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3941 | PL-PS5-03941 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0169-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3942 | PL-PS5-03942 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0159-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3943 | PL-PS5-03943 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0151-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3944 | PL-PS5-03944 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0356-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3945 | PL-PS5-03945 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0206-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3946 | PL-PS5-03946 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0148-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3947 | PL-PS5-03947 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0314-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3948 | PL-PS5-03948 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0149-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3949 | PL-PS5-03949 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0234-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3950 | PL-PS5-03950 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0114-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3951 | PL-PS5-03951 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0165-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3952 | PL-PS5-03952 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0166-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3953 | PL-PS5-03953 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0157-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3954 | PL-PS5-03954 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0153-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3955 | PL-PS5-03955 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0313-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3956 | PL-PS5-03956 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0188-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3957 | PL-PS5-03957 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0202-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3958 | PL-PS5-03958 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0103-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3959 | PL-PS5-03959 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0317-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3960 | PL-PS5-03960 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0306-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3961 | PL-PS5-03961 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-71-BE-0361-CL01 | TZ-MID-68-NVS1-150359 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3962 | PL-PS5-03962 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0316-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3963 | PL-PS5-03963 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0315-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3964 | PL-PS5-03964 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0168-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3965 | PL-PS5-03965 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0170-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3966 | PL-PS5-03966 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0163-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3967 | PL-PS5-03967 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0167-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3968 | PL-PS5-03968 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0169-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3969 | PL-PS5-03969 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0159-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3970 | PL-PS5-03970 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0151-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3971 | PL-PS5-03971 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0356-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3972 | PL-PS5-03972 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0206-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3973 | PL-PS5-03973 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0148-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3974 | PL-PS5-03974 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0314-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3975 | PL-PS5-03975 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0149-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3976 | PL-PS5-03976 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0234-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3977 | PL-PS5-03977 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0114-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3978 | PL-PS5-03978 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0166-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3979 | PL-PS5-03979 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0157-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3980 | PL-PS5-03980 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0153-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3981 | PL-PS5-03981 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0313-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3982 | PL-PS5-03982 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0188-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3983 | PL-PS5-03983 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0202-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3984 | PL-PS5-03984 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0103-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3985 | PL-PS5-03985 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0317-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3986 | PL-PS5-03986 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0306-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3987 | PL-PS5-03987 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0197-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3988 | PL-PS5-03988 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-71-TE-0361-CD01 | TZ-MID-68-NVS1-150360 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3989 | PL-PS5-03989 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0168-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3990 | PL-PS5-03990 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0170-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3991 | PL-PS5-03991 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0163-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3992 | PL-PS5-03992 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0159-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3993 | PL-PS5-03993 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0151-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3994 | PL-PS5-03994 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0206-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3995 | PL-PS5-03995 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0165-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3996 | PL-PS5-03996 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0166-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3997 | PL-PS5-03997 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0157-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3998 | PL-PS5-03998 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0188-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
3999 | PL-PS5-03999 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0103-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4000 | PL-PS5-04000 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0317-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4001 | PL-PS5-04001 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-BE-0306-CL01 | TZ-MID-68-NVS1-150359 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4002 | PL-PS5-04002 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0168-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4003 | PL-PS5-04003 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0170-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4004 | PL-PS5-04004 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0163-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4005 | PL-PS5-04005 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0151-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4006 | PL-PS5-04006 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0206-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4007 | PL-PS5-04007 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0234-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4008 | PL-PS5-04008 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0157-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4009 | PL-PS5-04009 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0153-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4010 | PL-PS5-04010 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0188-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4011 | PL-PS5-04011 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0103-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4012 | PL-PS5-04012 | #N/A | CPP-RFI-68-33/1-05-0322 | PS5 | EHT Power Cable Installation | CFO Area | PS5-79-TE-0306-CD01 | TZ-MID-68-NVS1-150360 Field run cable tray not yet complete | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4013 | PL-PS5-04013 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-08-01FB-1102-CS01 | TZ-MID-68-WPR2-151116 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4014 | PL-PS5-04014 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-08-01FB-1103-CS01 | TZ-MID-68-WPR2-151116 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4015 | PL-PS5-04015 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-08-01FB-1104-CS01 | TZ-MID-68-WPR2-151116, 151112 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4016 | PL-PS5-04016 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-08-01FB-1106-CS01 | TZ-MID-68-WPR2-151118 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4017 | PL-PS5-04017 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-08-03FB-1903-CS01 | TZ-MID-68-WPR2-151116 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4018 | PL-PS5-04018 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0021B-CL01 | TZ-MID-68-WPR2-151116 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4019 | PL-PS5-04019 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0025D-CL01 | TZ-MID-68-WPR2-151118,151116 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4020 | PL-PS5-04020 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CD01 | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4021 | PL-PS5-04021 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CD02 | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4022 | PL-PS5-04022 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CD03 | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4023 | PL-PS5-04023 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CL01 | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4024 | PL-PS5-04024 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CL02 | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4025 | PL-PS5-04025 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CL03 | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4026 | PL-PS5-04026 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002B-CD01 | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4027 | PL-PS5-04027 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002B-CD02 | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4028 | PL-PS5-04028 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002B-CD03 | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4029 | PL-PS5-04029 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002B-CL03 | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4030 | PL-PS5-04030 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CD03 | TZ-MID-68-WPR2-151179,151116,151118,151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4031 | PL-PS5-04031 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CD05 | TZ-MID-68-WPR2-151179,151116,151118,151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4032 | PL-PS5-04032 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CD14 | TZ-MID-68-WPR2-151179,151116,151118,151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4033 | PL-PS5-04033 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD02 | TZ-MID-68-WPR2-151179,151116,151118,151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4034 | PL-PS5-04034 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD03 | TZ-MID-68-WPR2-151179,151116,151118,151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4035 | PL-PS5-04035 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD04 | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4036 | PL-PS5-04036 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD14 | TZ-MID-68-WPR2-151179,151116,151118, 151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4037 | PL-PS5-04037 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001A-CL01 | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4038 | PL-PS5-04038 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001A-CL02 | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4039 | PL-PS5-04039 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001A-CL03 | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4040 | PL-PS5-04040 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001A-CL04 | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4041 | PL-PS5-04041 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001A-CL05 | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4042 | PL-PS5-04042 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001B-CL01 | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4043 | PL-PS5-04043 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001B-CL02 | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4044 | PL-PS5-04044 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001B-CL03 | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4045 | PL-PS5-04045 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001B-CL04 | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4046 | PL-PS5-04046 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002A-CL01 | TZ-MID-68-WPR2-151118,151116 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4047 | PL-PS5-04047 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002A-CL02 | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4048 | PL-PS5-04048 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002A-CL03 | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4049 | PL-PS5-04049 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002B-CL01 | TZ-MID-68-WPR2-151118,151116 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4050 | PL-PS5-04050 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002B-CL02 | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4051 | PL-PS5-04051 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002B-CL03 | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4052 | PL-PS5-04052 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-LA-0003-CL01 | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4053 | PL-PS5-04053 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-LA-0003-CL02 | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4054 | PL-PS5-04054 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IG-0016-CL01 | TZ-MID-68-WPR2-151116 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4055 | PL-PS5-04055 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-08-01FB-1102-CS01 | TZ-MID-68-WPR2-151116 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4056 | PL-PS5-04056 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-08-01FB-1103-CS01 | TZ-MID-68-WPR2-151116 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4057 | PL-PS5-04057 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-08-01FB-1104-CS01 | TZ-MID-68-WPR2-151116, 151112 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4058 | PL-PS5-04058 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-08-01FB-1106-CS01 | TZ-MID-68-WPR2-151118 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4059 | PL-PS5-04059 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-08-03FB-1903-CS01 | TZ-MID-68-WPR2-151116 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4060 | PL-PS5-04060 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0021B-CL01 | TZ-MID-68-WPR2-151116 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4061 | PL-PS5-04061 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0025D-CL01 | TZ-MID-68-WPR2-151118,151116 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4062 | PL-PS5-04062 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CD01 | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4063 | PL-PS5-04063 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CD02 | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4064 | PL-PS5-04064 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CD03 | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4065 | PL-PS5-04065 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CL01 | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4066 | PL-PS5-04066 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CL02 | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4067 | PL-PS5-04067 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CL03 | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4068 | PL-PS5-04068 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002B-CD01 | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4069 | PL-PS5-04069 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002B-CD02 | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4070 | PL-PS5-04070 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002B-CD03 | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4071 | PL-PS5-04071 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002B-CL03 | TZ-MID-68-WPR2-151179 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4072 | PL-PS5-04072 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CD03 | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4073 | PL-PS5-04073 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CD05 | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4074 | PL-PS5-04074 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CD14 | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4075 | PL-PS5-04075 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD02 | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4076 | PL-PS5-04076 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD03 | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4077 | PL-PS5-04077 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD04 | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4078 | PL-PS5-04078 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD14 | TZ-MID-68-WPR2-151179,151116,151118,151167 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4079 | PL-PS5-04079 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001A-CL01 | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4080 | PL-PS5-04080 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001A-CL02 | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4081 | PL-PS5-04081 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001A-CL03 | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4082 | PL-PS5-04082 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001A-CL04 | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4083 | PL-PS5-04083 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001A-CL05 | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4084 | PL-PS5-04084 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001B-CL01 | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4085 | PL-PS5-04085 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001B-CL02 | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4086 | PL-PS5-04086 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001B-CL03 | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4087 | PL-PS5-04087 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001B-CL04 | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4088 | PL-PS5-04088 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002A-CL01 | TZ-MID-68-WPR2-151118,151116 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4089 | PL-PS5-04089 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002A-CL02 | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4090 | PL-PS5-04090 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002A-CL03 | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4091 | PL-PS5-04091 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002B-CL01 | TZ-MID-68-WPR2-151118,151116 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4092 | PL-PS5-04092 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002B-CL02 | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4093 | PL-PS5-04093 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002B-CL03 | TZ-MID-68-WPR2-151167,151118,151116,151179 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4094 | PL-PS5-04094 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-LA-0003-CL01 | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4095 | PL-PS5-04095 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-LA-0003-CL02 | TZ-MID-68-WPR2-151167 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4096 | PL-PS5-04096 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IG-0016-CL01 | TZ-MID-68-WPR2-151116 Field run cable tray/secondary tray to be install completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4097 | PL-PS5-04097 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-08-03FB-1903-CS01 | TZ-MID-68-WPR2-151116 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4098 | PL-PS5-04098 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0021B-CL01 | TZ-MID-68-WPR2-151116 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4099 | PL-PS5-04099 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0025D-CL01 | TZ-MID-68-WPR2-151118,151116 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4100 | PL-PS5-04100 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CD01 | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4101 | PL-PS5-04101 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CD02 | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4102 | PL-PS5-04102 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CD03 | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4103 | PL-PS5-04103 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CL01 | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4104 | PL-PS5-04104 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CL02 | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4105 | PL-PS5-04105 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002A-CL03 | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4106 | PL-PS5-04106 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002B-CD01 | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4107 | PL-PS5-04107 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002B-CD02 | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4108 | PL-PS5-04108 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002B-CD03 | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4109 | PL-PS5-04109 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002B-CL03 | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4110 | PL-PS5-04110 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CD14 | TZ-MID-68-WPR2-151179,151116,151118, 151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4111 | PL-PS5-04111 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD02 | TZ-MID-68-WPR2-151179,151116,151118, 151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4112 | PL-PS5-04112 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD03 | TZ-MID-68-WPR2-151179,151116,151118, 151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4113 | PL-PS5-04113 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD04 | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4114 | PL-PS5-04114 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD14 | TZ-MID-68-WPR2-151179,151116,151118, 151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4115 | PL-PS5-04115 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001A-CL01 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4116 | PL-PS5-04116 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001A-CL02 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4117 | PL-PS5-04117 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001A-CL03 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4118 | PL-PS5-04118 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001A-CL04 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4119 | PL-PS5-04119 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001A-CL05 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4120 | PL-PS5-04120 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001B-CL01 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4121 | PL-PS5-04121 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001B-CL02 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4122 | PL-PS5-04122 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001B-CL03 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4123 | PL-PS5-04123 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001B-CL04 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4124 | PL-PS5-04124 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002A-CL01 | TZ-MID-68-WPR2-151118,151116 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4125 | PL-PS5-04125 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002A-CL03 | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4126 | PL-PS5-04126 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002B-CL01 | TZ-MID-68-WPR2-151118,151116 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4127 | PL-PS5-04127 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002B-CL02 | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4128 | PL-PS5-04128 | #N/A | CPP-RFI-68-33/1-05-0347 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IN-0002B-CL03 | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4129 | PL-PS5-04129 | #N/A | PS5-08-01FB-1102-CS01 | PS6 | Electrical Cable Installation | Generator Electrical Building | PS5-08-01FB-1102-CS01 | TZ-MID-68-WPR2-151116 Cable trench sand bedding, protection tiles and backfilled shall be done (PS5-88-CU-HV-0041, PS5-88-CU-HV-0039, PS5-88-BU-HV-0017, PS5-88-BU-HV-0029, PS5-88-BU-LV-00152). | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4130 | PL-PS5-04130 | #N/A | PS5-08-01FB-1103-CS01 | PS7 | Electrical Cable Installation | Generator Electrical Building | PS5-08-01FB-1103-CS01 | TZ-MID-68-WPR2-151116 Cable trench sand bedding, protection tiles and backfilled shall be done (PS5-88-BU-LV-00152) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4131 | PL-PS5-04131 | #N/A | PS5-08-03FB-1903-CS01 | PS8 | Electrical Cable Installation | Generator Electrical Building | PS5-08-03FB-1903-CS01 | TZ-MID-68-WPR2-151116 Cable trench sand bedding, protection tiles and backfilled shall be done (PS5-88-BU-HV-0029, PS5-88-BU-HV-0017, PS5-88-CU-HV-0039) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-17 | CPP EIT | Gao Chong |  |  |  |  | Open
4132 | PL-PS5-04132 | #N/A | CPP-RFI-68-33/2-04-0357 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0401-13 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4133 | PL-PS5-04133 | #N/A | CPP-RFI-68-33/2-04-0357 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0402-13 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4134 | PL-PS5-04134 | #N/A | CPP-RFI-68-33/2-04-0357 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0403-13 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4135 | PL-PS5-04135 | #N/A | CPP-RFI-68-33/2-04-0357 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0404-13 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4136 | PL-PS5-04136 | #N/A | CPP-RFI-68-33/2-04-0357 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0405-13 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4137 | PL-PS5-04137 | #N/A | CPP-RFI-68-33/2-04-0357 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0406-13 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4138 | PL-PS5-04138 | #N/A | CPP-RFI-68-33/2-04-0357 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0407-13 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4139 | PL-PS5-04139 | #N/A | CPP-RFI-68-33/2-04-0357 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0408-13 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4140 | PL-PS5-04140 | #N/A | CPP-RFI-68-33/2-04-0357 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0409-13 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4141 | PL-PS5-04141 | #N/A | CPP-RFI-68-33/2-04-0357 | PS5 | Junction Box Installation | Trnsformer area | PS5-62-BE-0411-13 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4142 | PL-PS5-04142 | #N/A | CPP-RFI-68-33/1-03-0363 | PS5 | Electrical Cable Ladder Installation | PGB | N/A | Doc.TZ-MID-68-WPR2-151118,TZ-MID-68-WPR2-151167 Bolts tightening on connection plates to be completed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4143 | PL-PS5-04143 | #N/A | CPP-RFI-68-33/1-03-0363 | PS5 | Electrical Cable Ladder Installation | PGB | N/A | Doc.TZ-MID-68-WPR2-151118,TZ-MID-68-WPR2-151167 Earth jumper not installed completely | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4144 | PL-PS5-04144 | #N/A | CPP-RFI-68-33/1-03-0363 | PS5 | Electrical Cable Ladder Installation | PGB | N/A | Doc.TZ-MID-68-WPR2-151118,TZ-MID-68-WPR2-151167 Cover not installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4145 | PL-PS5-04145 | #N/A | CPP-RFI-68-33/1-03-0363 | PS5 | Electrical Cable Ladder Installation | PGB | N/A | Doc.TZ-MID-68-WPR2-151118,TZ-MID-68-WPR2-151167 Grommets not installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4146 | PL-PS5-04146 | #N/A | CPP-RFI-68-64-03-0066 | PS5 | Instument Cable Ladder Installation | PGB | N/A | Doc. TZ-MID-68-WPR2-161500 Bolts tightening on connection plates to be completed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4147 | PL-PS5-04147 | #N/A | CPP-RFI-68-64-03-0066 | PS5 | Instument Cable Ladder Installation | PGB | N/A | Doc.TZ-MID-68-WPR2-161500 Earth jumper not installed completely | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4148 | PL-PS5-04148 | #N/A | CPP-RFI-68-64-03-0066 | PS5 | Instument Cable Ladder Installation | PGB | N/A | Doc.TZ-MID-68-WPR2-161500 Cover not installed | C | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4149 | PL-PS5-04149 | #N/A | CPP-RFI-68-64-03-0066 | PS5 | Instument Cable Ladder Installation | PGB | N/A | Doc.TZ-MID-68-WPR2-161500 Grommets not installed | C | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4150 | PL-PS5-04150 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-3200A-CD01 | TZ-MID-68-WPR2-151114 Cable gland earting not yet installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4151 | PL-PS5-04151 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-3200B-CD01 | TZ-MID-68-WPR2-151114 Cable gland earting not yet installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4152 | PL-PS5-04152 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-3300A-CD01 | TZ-MID-68-WPR2-151114 Cable gland earting not yet installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4153 | PL-PS5-04153 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-3300B-CD01 | TZ-MID-68-WPR2-151114 Cable gland earting not yet installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4154 | PL-PS5-04154 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-3400A-CD01 | TZ-MID-68-WPR2-151114 Cable gland earting not yet installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4155 | PL-PS5-04155 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-3400B-CD01 | TZ-MID-68-WPR2-151114 Cable gland earting not yet installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4156 | PL-PS5-04156 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-6400A-CD01 | TZ-MID-68-WPR2-151114 Cable gland earting not yet installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4157 | PL-PS5-04157 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-6400B-CD01 | TZ-MID-68-WPR2-151114 Cable gland earting not yet installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4158 | PL-PS5-04158 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-6500A-CD01 | TZ-MID-68-WPR2-151114 Cable gland earting not yet installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4159 | PL-PS5-04159 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-6500B-CD01 | TZ-MID-68-WPR2-151114 Cable gland earting not yet installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4160 | PL-PS5-04160 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-6600A-CD01 | TZ-MID-68-WPR2-151114 Cable gland earting not yet installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4161 | PL-PS5-04161 | #N/A | CPP-RFI-68-331-06-0360 | PS6 | Cable Gland and Termination | Export Pump area | PS5-25-IES-6600B-CD01 | TZ-MID-68-WPR2-151114 Cable gland earting not yet installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4162 | PL-PS5-04162 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-3200A-CD01 | TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4163 | PL-PS5-04163 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-3200B-CD01 | TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4164 | PL-PS5-04164 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-3300A-CD01 | TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4165 | PL-PS5-04165 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-3300B-CD01 | TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4166 | PL-PS5-04166 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-3400A-CD01 | TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4167 | PL-PS5-04167 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-3400B-CD01 | TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4168 | PL-PS5-04168 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-6400A-CD01 | TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4169 | PL-PS5-04169 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-6400B-CD01 | TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4170 | PL-PS5-04170 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-6500A-CD01 | TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4171 | PL-PS5-04171 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-6500B-CD01 | TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4172 | PL-PS5-04172 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-6600A-CD01 | TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4173 | PL-PS5-04173 | #N/A | CPP-RFI-68-331-06-0360 | PS5 | Cable Gland and Termination | Export Pump area | PS5-25-IES-6600B-CD01 | TZ-MID-68-WPR2-151114 Wire Dressing inside LCS not yet done properly | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4174 | PL-PS5-04174 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-05IN-0001-CA01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4175 | PL-PS5-04175 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-05IN-0002-CA01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4176 | PL-PS5-04176 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-05IN-0003-CA01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4177 | PL-PS5-04177 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-05IN-0004-CA01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4178 | PL-PS5-04178 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-05IN-0005-CA01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4179 | PL-PS5-04179 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0017-CN01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4180 | PL-PS5-04180 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BR-0001-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4181 | PL-PS5-04181 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BR-0002-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4182 | PL-PS5-04182 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BR-0003-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4183 | PL-PS5-04183 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BR-0004-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4184 | PL-PS5-04184 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BR-0005-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4185 | PL-PS5-04185 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BR-0006-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4186 | PL-PS5-04186 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BR-0007-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4187 | PL-PS5-04187 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BR-0008-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4188 | PL-PS5-04188 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0002-CJ01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4189 | PL-PS5-04189 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0003-CJ01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4190 | PL-PS5-04190 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0017-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4191 | PL-PS5-04191 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0019-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4192 | PL-PS5-04192 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0020-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4193 | PL-PS5-04193 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0021-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4194 | PL-PS5-04194 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0022-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4195 | PL-PS5-04195 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0023-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4196 | PL-PS5-04196 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0024-CJ01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4197 | PL-PS5-04197 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0025-CJ01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4198 | PL-PS5-04198 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0026-CJ01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Dressing not yet Done | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4199 | PL-PS5-04199 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0017-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4200 | PL-PS5-04200 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0019-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4201 | PL-PS5-04201 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0021-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4202 | PL-PS5-04202 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BR-0005-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4203 | PL-PS5-04203 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BR-0006-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4204 | PL-PS5-04204 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0022-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4205 | PL-PS5-04205 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BR-0003-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4206 | PL-PS5-04206 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BR-0004-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4207 | PL-PS5-04207 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0020-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4208 | PL-PS5-04208 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BR-0001-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4209 | PL-PS5-04209 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BR-0002-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4210 | PL-PS5-04210 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0023-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4211 | PL-PS5-04211 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BR-0007-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4212 | PL-PS5-04212 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BR-0008-CC01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable Tray need to Install to reaching Control Panel at Guard House, Panel Tagging (PS5-08-85CP-1501) | A | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4213 | PL-PS5-04213 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0017-CN01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, as per details Installation, Vertikal Cable Tray Need to Install (ACS JB - Field Side), {refer to details ACS EQUIPMENT INSTALLATION DETAILS - UT-MID-60-WPR2-171204} | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4214 | PL-PS5-04214 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0002-CJ01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, as per details Installation, Vertikal Cable Tray Need to Install (ACS JB - Field Side), {refer to details ACS EQUIPMENT INSTALLATION DETAILS - UT-MID-60-WPR2-171204} | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4215 | PL-PS5-04215 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0003-CJ01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, as per details Installation, Vertikal Cable Tray Need to Install (ACS JB - Field Side), {refer to details ACS EQUIPMENT INSTALLATION DETAILS - UT-MID-60-WPR2-171204} | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4216 | PL-PS5-04216 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0024-CJ01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, as per details Installation, Vertikal Cable Tray Need to Install (ACS JB - Field Side), {refer to details ACS EQUIPMENT INSTALLATION DETAILS - UT-MID-60-WPR2-171204} | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4217 | PL-PS5-04217 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0025-CJ01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, as per details Installation, Vertikal Cable Tray Need to Install (ACS JB - Field Side), {refer to details ACS EQUIPMENT INSTALLATION DETAILS - UT-MID-60-WPR2-171204} | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4218 | PL-PS5-04218 | #N/A | CPP-RFI-68-65-05-0032 | PS5 | Telecom Cables Installation | Guard House Area | PS5-08-85BT-0026-CJ01 | Doc. TZ-MID-68-WPR2-171143, TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, as per details Installation, Vertikal Cable Tray Need to Install (ACS JB - Field Side), {refer to details ACS EQUIPMENT INSTALLATION DETAILS - UT-MID-60-WPR2-171204} | B | Telecom | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4219 | PL-PS5-04219 | #N/A | CPP-RFI-68-33/1-08-0361 | PS5 | EHT SR cable installation | CDD Shelter | PS5-79-BE-0343-CT01 | Doc.TZ-MID-68-NVS1-150399 Ss Tag to be installed on both side | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4220 | PL-PS5-04220 | #N/A | CPP-RFI-68-33/1-08-0361 | PS5 | EHT SR cable installation | CDD Shelter | PS5-79-BE-0343 | Doc.TZ-MID-68-NVS1-150399 Ss Tag to be installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4221 | PL-PS5-04221 | #N/A | CPP-RFI-68-33/1-08-0361 | PS5 | EHT SR cable installation | CDD Shelter | PS5-79-TE-0343 | Doc.TZ-MID-68-NVS1-150399 Ss Tag to be installed | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4222 | PL-PS5-04222 | #N/A | CPP-RFI-68-33/2-07-0367 | PS5 | Socket Outlet Installation | Trnsformer area | PS5-62-ISO-0501-01 | Doc.TZ-MID-68-WPR2-151130 -Socket Outlets TAG to be Installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4223 | PL-PS5-04223 | #N/A | CPP-RFI-68-33/2-07-0367 | PS5 | Socket Outlet Installation | Trnsformer area | PS5-62-ISO-0502-01 | Doc.TZ-MID-68-WPR2-151130 -Socket Outlets TAG to be Installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4224 | PL-PS5-04224 | #N/A | CPP-RFI-68-33/2-07-0367 | PS5 | Socket Outlet Installation | Trnsformer area | PS5-62-ISO-0503-01 | Doc.TZ-MID-68-WPR2-151130 -Socket Outlets TAG to be Installed | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-20 | CPP EIT | Gao Chong |  |  |  |  | Open
4225 | PL-PS5-04225 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GU-0003A-CD02 | TZ-MID-68-WPR2-151112, 151116, 151118 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4226 | PL-PS5-04226 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0001-CL01 | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4227 | PL-PS5-04227 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0001-CL02 | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4228 | PL-PS5-04228 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0001-CL04 | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4229 | PL-PS5-04229 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0002-CL01 | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4230 | PL-PS5-04230 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0002-CL02 | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4231 | PL-PS5-04231 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0002-CL03 | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4232 | PL-PS5-04232 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0002-CL05 | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4233 | PL-PS5-04233 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0007A-CL01 | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4234 | PL-PS5-04234 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0007A-CL02 | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4235 | PL-PS5-04235 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0007A-CL03 | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4236 | PL-PS5-04236 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0007B-CL01 | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4237 | PL-PS5-04237 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0007B-CL02 | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4238 | PL-PS5-04238 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0007B-CL03 | TZ-MID-68-WPR2-151179 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4239 | PL-PS5-04239 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CD15 | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4240 | PL-PS5-04240 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD15 | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4241 | PL-PS5-04241 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL01 | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4242 | PL-PS5-04242 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL02 | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag to be Installed at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4243 | PL-PS5-04243 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-06-GU-0003A-CD02 | TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4244 | PL-PS5-04244 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0001-CL01 | TZ-MID-68-WPR2-151116 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4245 | PL-PS5-04245 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0001-CL02 | TZ-MID-68-WPR2-151116 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4246 | PL-PS5-04246 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0001-CL04 | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4247 | PL-PS5-04247 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0002-CL01 | TZ-MID-68-WPR2-151116 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4248 | PL-PS5-04248 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0002-CL02 | TZ-MID-68-WPR2-151116 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4249 | PL-PS5-04249 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0002-CL03 | TZ-MID-68-WPR2-151116 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4250 | PL-PS5-04250 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0002-CL05 | TZ-MID-68-WPR2-151167,151118,151116,151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4251 | PL-PS5-04251 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0007A-CL01 | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4252 | PL-PS5-04252 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0007A-CL02 | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4253 | PL-PS5-04253 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0007A-CL03 | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4254 | PL-PS5-04254 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0007B-CL01 | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4255 | PL-PS5-04255 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0007B-CL02 | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4256 | PL-PS5-04256 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0007B-CL03 | TZ-MID-68-WPR2-151179 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4257 | PL-PS5-04257 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003A-CD15 | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4258 | PL-PS5-04258 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003B-CD15 | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4259 | PL-PS5-04259 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL01 | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4260 | PL-PS5-04260 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-61-IK-0003-CL02 | TZ-MID-68-WPR2-151167 Cable dressing to be done at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4261 | PL-PS5-04261 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0001-CL01 | TZ-MID-68-WPR2-151116 To be install Field Run Cable Tray/Ladder | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4262 | PL-PS5-04262 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0001-CL02 | TZ-MID-68-WPR2-151116 To be install Field Run Cable Tray/Ladder | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4263 | PL-PS5-04263 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0001-CL04 | TZ-MID-68-WPR2-151167,151118,151116,151179 To be install Field Run Cable Tray/Ladder | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4264 | PL-PS5-04264 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0002-CL01 | TZ-MID-68-WPR2-151116 To be install Field Run Cable Tray/Ladder | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4265 | PL-PS5-04265 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0002-CL02 | TZ-MID-68-WPR2-151116 To be install Field Run Cable Tray/Ladder | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4266 | PL-PS5-04266 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0002-CL03 | TZ-MID-68-WPR2-151116 To be install Field Run Cable Tray/Ladder | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4267 | PL-PS5-04267 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0002-CL05 | TZ-MID-68-WPR2-151167,151118,151116,151179 To be install Field Run Cable Tray/Ladder | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4268 | PL-PS5-04268 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-BE-0007A-CL01 | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4269 | PL-PS5-04269 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-BE-0007A-CL02 | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4270 | PL-PS5-04270 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-BE-0007A-CL03 | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4271 | PL-PS5-04271 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-BE-0007B-CL01 | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4272 | PL-PS5-04272 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-BE-0007B-CL02 | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4273 | PL-PS5-04273 | #N/A | CPP-RFI-68-331-05-0368 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-BE-0007B-CL03 | TZ-MID-68-WPR2-151179 Cable Ladder not yet complete installation | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4274 | PL-PS5-04274 | #N/A | CPP-RFI-68-64-05-0068 | PS5 | Cable Gland and Termination | transfo side | PS5-03-BI-2502-CC01 | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed | C | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-22 | CPP EIT | Gao Chong |  |  |  |  | Open
4275 | PL-PS5-04275 | #N/A | CPP-RFI-68-64-05-0068 | PS5 | Cable Gland and Termination | transfo side | PS5-03-BI-2503-CC01 | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed | C | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-23 | CPP EIT | Gao Chong |  |  |  |  | Open
4276 | PL-PS5-04276 | #N/A | CPP-RFI-68-64-05-0068 | PS5 | Cable Gland and Termination | Fire water area | PS5-53-BI-1304-CC01 | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed | C | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4277 | PL-PS5-04277 | #N/A | CPP-RFI-68-64-05-0068 | PS5 | Cable Gland and Termination | CFO area | PS5-71-BI-2317-CC01 | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed | C | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-25 | CPP EIT | Gao Chong |  |  |  |  | Open
4278 | PL-PS5-04278 | #N/A | CPP-RFI-68-64-05-0068 | PS5 | Cable Gland and Termination | CFO area | PS5-25-BI-1103-CC01 | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed | C | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-26 | CPP EIT | Gao Chong |  |  |  |  | Open
4279 | PL-PS5-04279 | #N/A | CPP-RFI-68-64-05-0068 | PS5 | Cable Gland and Termination | CFO area | PS5-71-BI-2314-CC01 | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed | C | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4280 | PL-PS5-04280 | #N/A | CPP-RFI-68-64-05-0068 | PS5 | Cable Gland and Termination | CFO area | PS5-71-BI-2314-CC01 | UT-MID-60-WPR2-160101 Black Heat shrink sleeves not installed properly | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-06-28 | CPP EIT | Gao Chong |  |  |  |  | Open
4281 | PL-PS5-04281 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0012-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4282 | PL-PS5-04282 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0259-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4283 | PL-PS5-04283 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0257-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4284 | PL-PS5-04284 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0254-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4285 | PL-PS5-04285 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0310-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4286 | PL-PS5-04286 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0263-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4287 | PL-PS5-04287 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0122-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4288 | PL-PS5-04288 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0110-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4289 | PL-PS5-04289 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0256-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4290 | PL-PS5-04290 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0320-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4291 | PL-PS5-04291 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0255-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4292 | PL-PS5-04292 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0017-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4293 | PL-PS5-04293 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0250-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4294 | PL-PS5-04294 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0249-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4295 | PL-PS5-04295 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0318-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4296 | PL-PS5-04296 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0299-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4297 | PL-PS5-04297 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0308-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4298 | PL-PS5-04298 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0138-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4299 | PL-PS5-04299 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-BE-0364-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4300 | PL-PS5-04300 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0012-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4301 | PL-PS5-04301 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0259-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4302 | PL-PS5-04302 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0257-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4303 | PL-PS5-04303 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0254-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4304 | PL-PS5-04304 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0310-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4305 | PL-PS5-04305 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0263-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4306 | PL-PS5-04306 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0122-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4307 | PL-PS5-04307 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0110-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4308 | PL-PS5-04308 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0256-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4309 | PL-PS5-04309 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0320-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4310 | PL-PS5-04310 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0255-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4311 | PL-PS5-04311 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0017-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4312 | PL-PS5-04312 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0250-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4313 | PL-PS5-04313 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0249-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4314 | PL-PS5-04314 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0318-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4315 | PL-PS5-04315 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0299-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4316 | PL-PS5-04316 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0308-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4317 | PL-PS5-04317 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0138-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4318 | PL-PS5-04318 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-TE-0364-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4319 | PL-PS5-04319 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0012-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4320 | PL-PS5-04320 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0259-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4321 | PL-PS5-04321 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0257-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4322 | PL-PS5-04322 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0254-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4323 | PL-PS5-04323 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0310-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4324 | PL-PS5-04324 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0263-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4325 | PL-PS5-04325 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0122-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4326 | PL-PS5-04326 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0110-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4327 | PL-PS5-04327 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0256-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4328 | PL-PS5-04328 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0320-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4329 | PL-PS5-04329 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0255-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4330 | PL-PS5-04330 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0017-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4331 | PL-PS5-04331 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0250-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4332 | PL-PS5-04332 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0249-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4333 | PL-PS5-04333 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0318-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4334 | PL-PS5-04334 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0299-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4335 | PL-PS5-04335 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0308-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4336 | PL-PS5-04336 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0138-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4337 | PL-PS5-04337 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-BE-0364-CL01 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4338 | PL-PS5-04338 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0012-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4339 | PL-PS5-04339 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0259-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4340 | PL-PS5-04340 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0257-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4341 | PL-PS5-04341 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0254-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4342 | PL-PS5-04342 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0310-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4343 | PL-PS5-04343 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0263-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4344 | PL-PS5-04344 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0122-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4345 | PL-PS5-04345 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0110-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4346 | PL-PS5-04346 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0256-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4347 | PL-PS5-04347 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0320-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4348 | PL-PS5-04348 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0255-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4349 | PL-PS5-04349 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0017-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4350 | PL-PS5-04350 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0250-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4351 | PL-PS5-04351 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0249-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4352 | PL-PS5-04352 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0318-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4353 | PL-PS5-04353 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0299-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4354 | PL-PS5-04354 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0308-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4355 | PL-PS5-04355 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0138-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4356 | PL-PS5-04356 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-25-TE-0364-CD01 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4357 | PL-PS5-04357 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0012-CL01 | TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4358 | PL-PS5-04358 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0257-CL01 | TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4359 | PL-PS5-04359 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0263-CL01 | TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4360 | PL-PS5-04360 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0256-CL01 | TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4361 | PL-PS5-04361 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0320-CL01 | TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4362 | PL-PS5-04362 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0250-CL01 | TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4363 | PL-PS5-04363 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0249-CL01 | TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4364 | PL-PS5-04364 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0318-CL01 | TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4365 | PL-PS5-04365 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0299-CL01 | TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4366 | PL-PS5-04366 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0138-CL01 | TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4367 | PL-PS5-04367 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0012-CD01 | TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4368 | PL-PS5-04368 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0257-CD01 | TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4369 | PL-PS5-04369 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0254-CD01 | TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4370 | PL-PS5-04370 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0263-CD01 | TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4371 | PL-PS5-04371 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0256-CD01 | TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4372 | PL-PS5-04372 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0320-CD01 | TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4373 | PL-PS5-04373 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0250-CD01 | TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4374 | PL-PS5-04374 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0318-CD01 | TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4375 | PL-PS5-04375 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0299-CD01 | TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4376 | PL-PS5-04376 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-TE-0138-CD01 | TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4377 | PL-PS5-04377 | #N/A | CPP-RFI-68-33/2-04-0376 | PS5 | Junction Box Installation | VSD Trnsformer area | PS5-62-BE-0401-16 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-22 | CPP EIT | Gao Chong |  |  |  |  | Open
4378 | PL-PS5-04378 | #N/A | CPP-RFI-68-33/2-04-0376 | PS5 | Junction Box Installation | VSD Trnsformer area | PS5-62-BE-0402-16 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-22 | CPP EIT | Gao Chong |  |  |  |  | Open
4379 | PL-PS5-04379 | #N/A | CPP-RFI-68-33/2-04-0376 | PS5 | Junction Box Installation | VSD Trnsformer area | PS5-62-BE-0401-20 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-22 | CPP EIT | Gao Chong |  |  |  |  | Open
4380 | PL-PS5-04380 | #N/A | CPP-RFI-68-33/2-04-0376 | PS5 | Junction Box Installation | VSD Trnsformer area | PS5-62-BE-0402-20 | Doc.TZ-MID-68-WPR2-151130 -Junction Box TAG to be Installed , normal lighting jb | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-22 | CPP EIT | Gao Chong |  |  |  |  | Open
4381 | PL-PS5-04381 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL01 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4382 | PL-PS5-04382 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL03 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4383 | PL-PS5-04383 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL04 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4384 | PL-PS5-04384 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL05 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4385 | PL-PS5-04385 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL06 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4386 | PL-PS5-04386 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL07 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4387 | PL-PS5-04387 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL08 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4388 | PL-PS5-04388 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL09 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4389 | PL-PS5-04389 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL10 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4390 | PL-PS5-04390 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL11 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4391 | PL-PS5-04391 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0017A-CL01 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4392 | PL-PS5-04392 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BE-0027A-CL01 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4393 | PL-PS5-04393 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BE-0028A-CL01 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4394 | PL-PS5-04394 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL01 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4395 | PL-PS5-04395 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL02 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4396 | PL-PS5-04396 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL03 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4397 | PL-PS5-04397 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL04 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4398 | PL-PS5-04398 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL05 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4399 | PL-PS5-04399 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL06 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4400 | PL-PS5-04400 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL07 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4401 | PL-PS5-04401 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL08 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4402 | PL-PS5-04402 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL09 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4403 | PL-PS5-04403 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL10 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4404 | PL-PS5-04404 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL11 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4405 | PL-PS5-04405 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0017B-CL01 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4406 | PL-PS5-04406 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BE-0028B-CL01 | Doc. TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4407 | PL-PS5-04407 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building & Electrical Generator Building | PS5-71-BI-0005-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4408 | PL-PS5-04408 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building & Electrical Generator Building | PS5-71-BI-0005-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4409 | PL-PS5-04409 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building & Electrical Generator Building | PS5-71-BI-0006-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179 - SS Cables Tagging not yet install at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4410 | PL-PS5-04410 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL01 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4411 | PL-PS5-04411 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL03 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4412 | PL-PS5-04412 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL04 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4413 | PL-PS5-04413 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL05 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4414 | PL-PS5-04414 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL06 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4415 | PL-PS5-04415 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL07 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4416 | PL-PS5-04416 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL08 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4417 | PL-PS5-04417 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL09 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4418 | PL-PS5-04418 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL10 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4419 | PL-PS5-04419 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL11 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4420 | PL-PS5-04420 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0017A-CL01 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4421 | PL-PS5-04421 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BE-0027A-CL01 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4422 | PL-PS5-04422 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BE-0028A-CL01 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4423 | PL-PS5-04423 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL01 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4424 | PL-PS5-04424 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL02 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4425 | PL-PS5-04425 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL03 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4426 | PL-PS5-04426 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL04 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4427 | PL-PS5-04427 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL05 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4428 | PL-PS5-04428 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL06 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4429 | PL-PS5-04429 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL07 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4430 | PL-PS5-04430 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL08 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4431 | PL-PS5-04431 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL09 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4432 | PL-PS5-04432 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL10 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4433 | PL-PS5-04433 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL11 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4434 | PL-PS5-04434 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0017B-CL01 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4435 | PL-PS5-04435 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BE-0028B-CL01 | Doc. TZ-MID-68-WPR2-151179 - Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4436 | PL-PS5-04436 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building & Electrical Generator Building | PS5-71-BI-0005-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4437 | PL-PS5-04437 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building & Electrical Generator Building | PS5-71-BI-0005-CL02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4438 | PL-PS5-04438 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building & Electrical Generator Building | PS5-71-BI-0006-CL01 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-151167, TZ-MID-68-WPR2-151179, Cables Dressing not yet done at both ends | B | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4439 | PL-PS5-04439 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL01 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4440 | PL-PS5-04440 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL03 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4441 | PL-PS5-04441 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL04 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4442 | PL-PS5-04442 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL05 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4443 | PL-PS5-04443 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL06 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4444 | PL-PS5-04444 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL07 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4445 | PL-PS5-04445 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL08 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4446 | PL-PS5-04446 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL09 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4447 | PL-PS5-04447 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL10 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4448 | PL-PS5-04448 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006A-CL11 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4449 | PL-PS5-04449 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0017A-CL01 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4450 | PL-PS5-04450 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BE-0027A-CL01 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4451 | PL-PS5-04451 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BE-0028A-CL01 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4452 | PL-PS5-04452 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL01 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4453 | PL-PS5-04453 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL02 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4454 | PL-PS5-04454 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL03 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4455 | PL-PS5-04455 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL04 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4456 | PL-PS5-04456 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL05 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4457 | PL-PS5-04457 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL06 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4458 | PL-PS5-04458 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL07 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4459 | PL-PS5-04459 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL08 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4460 | PL-PS5-04460 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL09 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4461 | PL-PS5-04461 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL10 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4462 | PL-PS5-04462 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0006B-CL11 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4463 | PL-PS5-04463 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BI-0017B-CL01 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4464 | PL-PS5-04464 | #N/A | CPP-RFI-68-33/1-05-0377 | PS5 | Electrical Cable Installation | Power Generator Building | PS5-60-BE-0028B-CL01 | Doc. TZ-MID-68-WPR2-151179, Vertical & Horizontal Cable Ladder need to be install | A | Electrical | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4465 | PL-PS5-04465 | #N/A | CPP-RFI-68-64-11-0070 | PS5 | Cable Gland and Termination | Diesel storage tank area | PS5-03-BI-1503-CC01 | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed | C | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4466 | PL-PS5-04466 | #N/A | CPP-RFI-68-64-11-0070 | PS5 | Cable Gland and Termination | Diesel storage tank area | PS5-03-BI-2512-CC01 | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed | C | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4467 | PL-PS5-04467 | #N/A | CPP-RFI-68-64-11-0070 | PS5 | Cable Gland and Termination | Diesel storage tank area | PS5-71-BI-1308-CC01 | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed | C | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4468 | PL-PS5-04468 | #N/A | CPP-RFI-68-64-11-0070 | PS5 | Cable Gland and Termination | Diesel storage tank area | PS5-71-BI-2307-CC01 | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed | C | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4469 | PL-PS5-04469 | #N/A | CPP-RFI-68-64-11-0070 | PS5 | Cable Gland and Termination | Diesel storage tank area | PS5-71-BI-2313-CC01 | UT-MID-60-WPR2-160101 Grounding between Gland to Gland not yet Installed | C | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4470 | PL-PS5-04470 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-01-BI-1501-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4471 | PL-PS5-04471 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001C-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4472 | PL-PS5-04472 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001D-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4473 | PL-PS5-04473 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001E-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4474 | PL-PS5-04474 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001F-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4475 | PL-PS5-04475 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001G-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4476 | PL-PS5-04476 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001A-CC04 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4477 | PL-PS5-04477 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001B-CC04 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4478 | PL-PS5-04478 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001C-CC04 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4479 | PL-PS5-04479 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001D-CC04 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4480 | PL-PS5-04480 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001E-CC04 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4481 | PL-PS5-04481 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001F-CC04 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4482 | PL-PS5-04482 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001G-CC04 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4483 | PL-PS5-04483 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0001-CC03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4484 | PL-PS5-04484 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0002-CC03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4485 | PL-PS5-04485 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0003-CC03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4486 | PL-PS5-04486 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0004-CC03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4487 | PL-PS5-04487 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0005-CC03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4488 | PL-PS5-04488 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0006-CC03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4489 | PL-PS5-04489 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0007-CC03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4490 | PL-PS5-04490 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-BI-0016A-CC03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4491 | PL-PS5-04491 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-BI-0016B-CC03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4492 | PL-PS5-04492 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-BI-0016C-CC03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4493 | PL-PS5-04493 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-BI-0016D-CC03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4494 | PL-PS5-04494 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-BI-0016E-CC03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4495 | PL-PS5-04495 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-BI-0016G-CC03 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4496 | PL-PS5-04496 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0002-CC02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4497 | PL-PS5-04497 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-LA-0003-CX02 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4498 | PL-PS5-04498 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-01-BI-1501-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4499 | PL-PS5-04499 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001C-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4500 | PL-PS5-04500 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001D-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4501 | PL-PS5-04501 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001E-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4502 | PL-PS5-04502 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001F-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4503 | PL-PS5-04503 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001G-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4504 | PL-PS5-04504 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001A-CC04 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4505 | PL-PS5-04505 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001B-CC04 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4506 | PL-PS5-04506 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001C-CC04 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4507 | PL-PS5-04507 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001D-CC04 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4508 | PL-PS5-04508 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001E-CC04 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4509 | PL-PS5-04509 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001F-CC04 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4510 | PL-PS5-04510 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-60-IN-0001G-CC04 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4511 | PL-PS5-04511 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0001-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4512 | PL-PS5-04512 | #N/A | CPP-RFI-68-64-04-0071 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0002-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4513 | PL-PS5-04513 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0003-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4514 | PL-PS5-04514 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0004-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4515 | PL-PS5-04515 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0005-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4516 | PL-PS5-04516 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0006-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4517 | PL-PS5-04517 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0007-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4518 | PL-PS5-04518 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-60-BI-0016A-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4519 | PL-PS5-04519 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-60-BI-0016B-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4520 | PL-PS5-04520 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-60-BI-0016C-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4521 | PL-PS5-04521 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-60-BI-0016D-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4522 | PL-PS5-04522 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-60-BI-0016E-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4523 | PL-PS5-04523 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-60-BI-0016G-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4524 | PL-PS5-04524 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0002-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4525 | PL-PS5-04525 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-60-LA-0003-CX02 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side | B | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4526 | PL-PS5-04526 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0001-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed | A | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4527 | PL-PS5-04527 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0002-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed | A | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4528 | PL-PS5-04528 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0003-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed | A | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4529 | PL-PS5-04529 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0004-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed | A | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4530 | PL-PS5-04530 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0005-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed | A | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4531 | PL-PS5-04531 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0006-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed | A | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4532 | PL-PS5-04532 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0007-CC03 | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed | A | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4533 | PL-PS5-04533 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-61-BI-0002-CC02 | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed | A | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4534 | PL-PS5-04534 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | PGB | PS5-60-LA-0003-CX02 | Doc.TZ-MID-68-WPR2-161507 - Cable coiled on Generator side Cable tray to be installed | A | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4535 | PL-PS5-04535 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-01-PIT-0010-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  | Instrument | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4536 | PL-PS5-04536 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0404-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4537 | PL-PS5-04537 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0411-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4538 | PL-PS5-04538 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0138-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4539 | PL-PS5-04539 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0114-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4540 | PL-PS5-04540 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0115-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4541 | PL-PS5-04541 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0116-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4542 | PL-PS5-04542 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0117-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4543 | PL-PS5-04543 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0118-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4544 | PL-PS5-04544 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0819-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4545 | PL-PS5-04545 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0820-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4546 | PL-PS5-04546 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0832-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4547 | PL-PS5-04547 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDH-0614-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4548 | PL-PS5-04548 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDH-0615-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4549 | PL-PS5-04549 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDH-0616-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4550 | PL-PS5-04550 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RMAC-0101-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4551 | PL-PS5-04551 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RMAC-0103-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4552 | PL-PS5-04552 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RMAC-0402-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4553 | PL-PS5-04553 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-GDLHP-0137-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4554 | PL-PS5-04554 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-GDLHP-0142-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4555 | PL-PS5-04555 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-GDLHP-0143-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4556 | PL-PS5-04556 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-GDLHP-0144-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4557 | PL-PS5-04557 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-GDLHP-0146-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4558 | PL-PS5-04558 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-GDLHP-0401-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4559 | PL-PS5-04559 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-PIT-0013-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4560 | PL-PS5-04560 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-FIT-0004-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4561 | PL-PS5-04561 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-FY-0004-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4562 | PL-PS5-04562 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-PIT-0053-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4563 | PL-PS5-04563 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-ESDV-0021-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4564 | PL-PS5-04564 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-ESDV-0023-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4565 | PL-PS5-04565 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-PIT-0008A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4566 | PL-PS5-04566 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-PIT-0022-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4567 | PL-PS5-04567 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-PIT-0008C-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4568 | PL-PS5-04568 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-TIT-0002C-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4569 | PL-PS5-04569 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-PIT-0008B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4570 | PL-PS5-04570 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-MOV-0002-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4571 | PL-PS5-04571 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-MOV-0003-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4572 | PL-PS5-04572 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-MOV-0012-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4573 | PL-PS5-04573 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-MOV-0011-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4574 | PL-PS5-04574 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-MOV-0026-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4575 | PL-PS5-04575 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-MOV-0027-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4576 | PL-PS5-04576 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-SXS-0035A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4577 | PL-PS5-04577 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-SXS-0035B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4578 | PL-PS5-04578 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-SXS-0036A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4579 | PL-PS5-04579 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-SXS-0053A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4580 | PL-PS5-04580 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-SXS-0053B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4581 | PL-PS5-04581 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-HS-8102C-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4582 | PL-PS5-04582 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-ESY-0021B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4583 | PL-PS5-04583 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-ESY-0023B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4584 | PL-PS5-04584 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-SY-0045A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4585 | PL-PS5-04585 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-SXS-0035C-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4586 | PL-PS5-04586 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-SXS-0036B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4587 | PL-PS5-04587 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-SXS-0036C-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4588 | PL-PS5-04588 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0012-CL02 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4589 | PL-PS5-04589 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0259-CL02 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4590 | PL-PS5-04590 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0257-CL02 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4591 | PL-PS5-04591 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0254-CL02 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4592 | PL-PS5-04592 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0310-CL02 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4593 | PL-PS5-04593 | #N/A | CPP-RFI-68-331-05-0370 | PS5 | EHT Power Cable Installation | LAUNCHER/RECEIVER AREA | PS5-79-BE-0263-CL02 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-06-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4594 | PL-PS5-04594 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-TIT-1401-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4595 | PL-PS5-04595 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-LIT-1402-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4596 | PL-PS5-04596 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-LIT-1102-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4597 | PL-PS5-04597 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-LIT-1202-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4598 | PL-PS5-04598 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-PIT-0041-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4599 | PL-PS5-04599 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-PIT-0045-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4600 | PL-PS5-04600 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-TIT-1105-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4601 | PL-PS5-04601 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-TIT-2101-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4602 | PL-PS5-04602 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-PIT-3901A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4603 | PL-PS5-04603 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-PIT-3901B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4604 | PL-PS5-04604 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-TIT-1402-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4605 | PL-PS5-04605 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-LIT-1401-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4606 | PL-PS5-04606 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-TIT-2201-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4607 | PL-PS5-04607 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-LIT-1202-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4608 | PL-PS5-04608 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-PIT-0001-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4609 | PL-PS5-04609 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-LIT-0002-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4610 | PL-PS5-04610 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-50-FIT-0001-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4611 | PL-PS5-04611 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-LIT-0008-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4612 | PL-PS5-04612 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-74-PIT-0002-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4613 | PL-PS5-04613 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-FIT-0005-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4614 | PL-PS5-04614 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-LIT-4401-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4615 | PL-PS5-04615 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-PIT-0014-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4616 | PL-PS5-04616 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-FY-0019-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4617 | PL-PS5-04617 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-PIT-0019A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4618 | PL-PS5-04618 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-LIT-1201-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4619 | PL-PS5-04619 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-PIT-0091-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4620 | PL-PS5-04620 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-PIT-0092-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4621 | PL-PS5-04621 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-60-LIT-4301-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4622 | PL-PS5-04622 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-60-LIT-4401-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4623 | PL-PS5-04623 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-TIT-2402AA-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4624 | PL-PS5-04624 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-TIT-2402BA-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4625 | PL-PS5-04625 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-LIT-4402-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4626 | PL-PS5-04626 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-PIT-0029-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4627 | PL-PS5-04627 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-XV-0091-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4628 | PL-PS5-04628 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-XV-0092-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4629 | PL-PS5-04629 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-BAV-0059-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4630 | PL-PS5-04630 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-BAV-0058-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4631 | PL-PS5-04631 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-XXS-0091-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4632 | PL-PS5-04632 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-XXS-0092-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4633 | PL-PS5-04633 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-FXS-0019-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4634 | PL-PS5-04634 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-XY-0091-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4635 | PL-PS5-04635 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-XY-0092-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4636 | PL-PS5-04636 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-SDV-0029-CC01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4637 | PL-PS5-04637 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-SXS-0029-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4638 | PL-PS5-04638 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-SY-0029-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4639 | PL-PS5-04639 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-LI-1101B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4640 | PL-PS5-04640 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-LI-1402B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Cable dressing to be completed on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4641 | PL-PS5-04641 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-01-PIT-0010-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4642 | PL-PS5-04642 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0404-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4643 | PL-PS5-04643 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0411-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4644 | PL-PS5-04644 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0138-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4645 | PL-PS5-04645 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0114-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4646 | PL-PS5-04646 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0115-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4647 | PL-PS5-04647 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0116-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4648 | PL-PS5-04648 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0117-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4649 | PL-PS5-04649 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0118-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4650 | PL-PS5-04650 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0819-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4651 | PL-PS5-04651 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0820-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4652 | PL-PS5-04652 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDIR-0832-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4653 | PL-PS5-04653 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDH-0614-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4654 | PL-PS5-04654 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDH-0615-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4655 | PL-PS5-04655 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RDH-0616-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4656 | PL-PS5-04656 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RMAC-0101-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4657 | PL-PS5-04657 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RMAC-0103-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4658 | PL-PS5-04658 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-RMAC-0402-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4659 | PL-PS5-04659 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-GDLHP-0137-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4660 | PL-PS5-04660 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-GDLHP-0142-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4661 | PL-PS5-04661 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-GDLHP-0143-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4662 | PL-PS5-04662 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-GDLHP-0144-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4663 | PL-PS5-04663 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-GDLHP-0146-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4664 | PL-PS5-04664 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-03-GDLHP-0401-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4665 | PL-PS5-04665 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-PIT-0013-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4666 | PL-PS5-04666 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-FIT-0004-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4667 | PL-PS5-04667 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-FY-0004-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4668 | PL-PS5-04668 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-PIT-0053-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4669 | PL-PS5-04669 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-ESDV-0021-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4670 | PL-PS5-04670 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-ESDV-0023-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4671 | PL-PS5-04671 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-PIT-0008A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4672 | PL-PS5-04672 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-PIT-0022-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4673 | PL-PS5-04673 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-PIT-0008C-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4674 | PL-PS5-04674 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-TIT-0002C-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4675 | PL-PS5-04675 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-PIT-0008B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4676 | PL-PS5-04676 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-MOV-0002-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4677 | PL-PS5-04677 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-MOV-0003-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4678 | PL-PS5-04678 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-MOV-0012-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4679 | PL-PS5-04679 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-MOV-0011-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4680 | PL-PS5-04680 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-MOV-0026-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4681 | PL-PS5-04681 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-MOV-0027-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4682 | PL-PS5-04682 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-SXS-0035A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4683 | PL-PS5-04683 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-SXS-0035B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4684 | PL-PS5-04684 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-SXS-0036A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4685 | PL-PS5-04685 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-SXS-0053A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4686 | PL-PS5-04686 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-SXS-0053B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4687 | PL-PS5-04687 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-HS-8102C-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4688 | PL-PS5-04688 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-ESY-0021B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4689 | PL-PS5-04689 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-ESY-0023B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4690 | PL-PS5-04690 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-SY-0045A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4691 | PL-PS5-04691 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-SXS-0035C-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4692 | PL-PS5-04692 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-SXS-0036B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4693 | PL-PS5-04693 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-SXS-0036C-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4694 | PL-PS5-04694 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-25-SXS-0046-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4695 | PL-PS5-04695 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-PIT-0015-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4696 | PL-PS5-04696 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-LIT-1101-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4697 | PL-PS5-04697 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-TIT-1104-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4698 | PL-PS5-04698 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-HY-3901A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4699 | PL-PS5-04699 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-HY-3901B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4700 | PL-PS5-04700 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-TIT-1401-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4701 | PL-PS5-04701 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-LIT-1402-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4702 | PL-PS5-04702 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-LIT-1102-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4703 | PL-PS5-04703 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-LIT-1202-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4704 | PL-PS5-04704 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-PIT-0041-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4705 | PL-PS5-04705 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-PIT-0045-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4706 | PL-PS5-04706 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-TIT-1105-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4707 | PL-PS5-04707 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-TIT-2101-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4708 | PL-PS5-04708 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-PIT-3901A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4709 | PL-PS5-04709 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-PIT-3901B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4710 | PL-PS5-04710 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-TIT-1402-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4711 | PL-PS5-04711 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-LIT-1401-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4712 | PL-PS5-04712 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-TIT-2201-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4713 | PL-PS5-04713 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-LIT-1202-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4714 | PL-PS5-04714 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-PIT-0001-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4715 | PL-PS5-04715 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-LIT-0002-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4716 | PL-PS5-04716 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-50-FIT-0001-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4717 | PL-PS5-04717 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-LIT-0008-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4718 | PL-PS5-04718 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-74-PIT-0002-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4719 | PL-PS5-04719 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-FIT-0005-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4720 | PL-PS5-04720 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-LIT-4401-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4721 | PL-PS5-04721 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-PIT-0014-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4722 | PL-PS5-04722 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-FY-0019-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4723 | PL-PS5-04723 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-PIT-0019A-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4724 | PL-PS5-04724 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-LIT-1201-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4725 | PL-PS5-04725 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-PIT-0091-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4726 | PL-PS5-04726 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-PIT-0092-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4727 | PL-PS5-04727 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-60-LIT-4301-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4728 | PL-PS5-04728 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-60-LIT-4401-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4729 | PL-PS5-04729 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-TIT-2402AA-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4730 | PL-PS5-04730 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-TIT-2402BA-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4731 | PL-PS5-04731 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-LIT-4402-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4732 | PL-PS5-04732 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-PIT-0029-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4733 | PL-PS5-04733 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-XV-0091-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4734 | PL-PS5-04734 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-XV-0092-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4735 | PL-PS5-04735 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-BAV-0059-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4736 | PL-PS5-04736 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-BAV-0058-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4737 | PL-PS5-04737 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-XXS-0091-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4738 | PL-PS5-04738 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-XXS-0092-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4739 | PL-PS5-04739 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-FXS-0019-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4740 | PL-PS5-04740 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-XY-0091-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4741 | PL-PS5-04741 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-XY-0092-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4742 | PL-PS5-04742 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-SDV-0029-CC01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4743 | PL-PS5-04743 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-SXS-0029-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4744 | PL-PS5-04744 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-71-SY-0029-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4745 | PL-PS5-04745 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-LI-1101B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4746 | PL-PS5-04746 | #N/A | CPP-RFI-68-64-04-0072 | PS5 | Instrument Cable Installation | Process Area | PS5-28-LI-1402B-CJ01 | Doc.TZ-MID-68-WPR2-161507 - Permanet SS Tag not intalled on both side |  |  | CPY | Rustam Battalov | 2026-06-24 | CPP EIT | Gao Chong |  |  |  |  | Open
4747 | PL-PS5-04747 | #N/A | CPP-RFI-68-331-06-0379 | PS5 | Cable Gland and Termination | Closed Drain Drum Area | PS5-28-IES-3900A-CD01 | TZ-MID-68-WPR2-150101 Cable gland earting not yet installed | B | Electrical | CPY | Rustam Battalov | 2026-06-25 | CPP EIT | Gao Chong |  |  |  |  | Open
4748 | PL-PS5-04748 | #N/A | CPP-RFI-68-331-06-0379 | PS5 | Cable Gland and Termination | Water Treatment Package Area | PS5-53-IES-3100A-CD01 | TZ-MID-68-WPR2-150101 Cable gland earting not yet installed | B | Electrical | CPY | Rustam Battalov | 2026-06-25 | CPP EIT | Gao Chong |  |  |  |  | Open
4749 | PL-PS5-04749 | #N/A | CPP-RFI-68-331-06-0379 | PS5 | Cable Gland and Termination | Water Treatment Package Area | PS5-53-IES-3100B-CD01 | TZ-MID-68-WPR2-150101 Cable gland earting not yet installed | B | Electrical | CPY | Rustam Battalov | 2026-06-25 | CPP EIT | Gao Chong |  |  |  |  | Open
4750 | PL-PS5-04750 | #N/A | CPP-RFI-68-331-06-0379 | PS5 | Cable Gland and Termination | Diesel Fuel Pump Area | PS5-71-IES-3100A-CD01 | TZ-MID-68-WPR2-150101 Cable gland earting not yet installed | B | Electrical | CPY | Rustam Battalov | 2026-06-25 | CPP EIT | Gao Chong |  |  |  |  | Open
4751 | PL-PS5-04751 | #N/A | CPP-RFI-68-331-06-0379 | PS5 | Cable Gland and Termination | Diesel Fuel Pump Area | PS5-71-IES-3100B-CD01 | TZ-MID-68-WPR2-150101 Cable gland earting not yet installed | B | Electrical | CPY | Rustam Battalov | 2026-06-25 | CPP EIT | Gao Chong |  |  |  |  | Open
4752 | PL-PS5-04752 | #N/A | CPP-RFI-68-331-06-0379 | PS5 | Cable Gland and Termination | Diesel Fuel Pump Area | PS5-71-IES-3200-CD01 | TZ-MID-68-WPR2-150101 Cable gland earting not yet installed | B | Electrical | CPY | Rustam Battalov | 2026-06-25 | CPP EIT | Gao Chong |  |  |  |  | Open
4753 | PL-PS5-04753 | #N/A | CPP-RFI-68-331-06-0379 | PS5 | Cable Gland and Termination | CFO Pump Area | PS5-71-IES-3300A-CD01 | TZ-MID-68-WPR2-150101 Cable gland earting not yet installed | B | Electrical | CPY | Rustam Battalov | 2026-06-25 | CPP EIT | Gao Chong |  |  |  |  | Open
4754 | PL-PS5-04754 | #N/A | CPP-RFI-68-331-06-0379 | PS5 | Cable Gland and Termination | CFO Pump Area | PS5-71-IES-3300B-CD01 | TZ-MID-68-WPR2-150101 Cable gland earting not yet installed | B | Electrical | CPY | Rustam Battalov | 2026-06-25 | CPP EIT | Gao Chong |  |  |  |  | Open
4755 | PL-PS5-04755 | #N/A | CPP-RFI-68-331-06-0379 | PS5 | Cable Gland and Termination | CFO Pump Area | PS5-71-IES-3400A-CD01 | TZ-MID-68-WPR2-150101 Cable gland earting not yet installed | B | Electrical | CPY | Rustam Battalov | 2026-06-25 | CPP EIT | Gao Chong |  |  |  |  | Open
4756 | PL-PS5-04756 | #N/A | CPP-RFI-68-331-06-0379 | PS5 | Cable Gland and Termination | Diesel fuel day drum area | PS5-71-IES-3500A-CD01 | TZ-MID-68-WPR2-150101 Cable gland earting not yet installed | B | Electrical | CPY | Rustam Battalov | 2026-06-25 | CPP EIT | Gao Chong |  |  |  |  | Open
4757 | PL-PS5-04757 | #N/A | CPP-RFI-68-331-06-0379 | PS5 | Cable Gland and Termination | Diesel fuel day drum area | PS5-71-IES-3500B-CD01 | TZ-MID-68-WPR2-150101 Cable gland earting not yet installed | B | Electrical | CPY | Rustam Battalov | 2026-06-25 | CPP EIT | Gao Chong |  |  |  |  | Open
4758 | PL-PS5-04758 | #N/A | CPP-RFI-68-331-05-0389 | PS5 | Small power Cable Installation | Launcher Receivier Area, Power Distribution Area | PS5-62-BE-0501-03-CL01 | TZ-MID-68-WPR2-151415 SS tag at both ends Need to Install | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4759 | PL-PS5-04759 | #N/A | CPP-RFI-68-331-05-0389 | PS5 | Small power Cable Installation | Launcher Receivier Area, Power Distribution Area | PS5-62-ISO-0501-03-CL01 | TZ-MID-68-WPR2-151415 SS tag at both ends Need to Install | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4760 | PL-PS5-04760 | #N/A | CPP-RFI-68-331-05-0389 | PS5 | Small power Cable Installation | Launcher Receivier Area, Power Distribution Area | PS5-62-ISO-0502-03-CL01 | TZ-MID-68-WPR2-151415 SS tag at both ends Need to Install | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4761 | PL-PS5-04761 | #N/A | CPP-RFI-68-331-05-0389 | PS5 | Small power Cable Installation | Launcher Receivier Area, Power Distribution Area | PS5-62-ISO-0503-03-CL01 | TZ-MID-68-WPR2-151415 SS tag at both ends Need to Install | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4762 | PL-PS5-04762 | #N/A | CPP-RFI-68-331-05-0389 | PS5 | Small power Cable Installation | Launcher Receivier Area, Power Distribution Area | PS5-62-ISO-0504-03-CL01 | TZ-MID-68-WPR2-151415 SS tag at both ends Need to Install | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4763 | PL-PS5-04763 | #N/A | CPP-RFI-68-331-05-0389 | PS5 | Small power Cable Installation | VSD , Near VSD fance Area,fire watertank fance | PS5-62-BE-0501-04-CL01 | TZ-MID-68-WPR2-151415 SS tag at both ends Need to Install | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4764 | PL-PS5-04764 | #N/A | CPP-RFI-68-331-05-0389 | PS5 | Small power Cable Installation | VSD , Near VSD fance Area,fire watertank fance | PS5-62-ISO-0501-04-CL01 | TZ-MID-68-WPR2-151415 SS tag at both ends Need to Install | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4765 | PL-PS5-04765 | #N/A | CPP-RFI-68-331-05-0389 | PS5 | Small power Cable Installation | VSD , Near VSD fance Area,fire watertank fance | PS5-62-ISO-0502-04-CL01 | TZ-MID-68-WPR2-151415 SS tag at both ends Need to Install | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4766 | PL-PS5-04766 | #N/A | CPP-RFI-68-331-05-0389 | PS5 | Small power Cable Installation | VSD , Near VSD fance Area,fire watertank fance | PS5-62-ISO-0503-04-CL01 | TZ-MID-68-WPR2-151415 SS tag at both ends Need to Install | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4767 | PL-PS5-04767 | #N/A | CPP-RFI-68-331-05-0389 | PS5 | Small power Cable Installation | VSD , Near VSD fance Area,fire watertank fance | PS5-62-ISO-0504-04-CL01 | TZ-MID-68-WPR2-151415 SS tag at both ends Need to Install | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4768 | PL-PS5-04768 | #N/A | CPP-RFI-68-331-05-0389 | PS5 | Small power Cable Installation | VSD , Near VSD fance Area,fire watertank fance | PS5-62-BE-0505-04-CL01 | TZ-MID-68-WPR2-151415 SS tag at both ends Need to Install | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4769 | PL-PS5-04769 | #N/A | CPP-RFI-68-331-05-0389 | PS5 | Small power Cable Installation | VSD , Near VSD fance Area,fire watertank fance | PS5-62-ISO-0506-04-CL01 | TZ-MID-68-WPR2-151415 SS tag at both ends Need to Install | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4770 | PL-PS5-04770 | #N/A | CPP-RFI-68-331-05-0389 | PS5 | Small power Cable Installation | VSD , Near VSD fance Area,fire watertank fance | PS5-62-ISO-0507-04-CL01 | TZ-MID-68-WPR2-151415 SS tag at both ends Need to Install | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4771 | PL-PS5-04771 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003C-CD04 | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4772 | PL-PS5-04772 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003E-CD04 | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4773 | PL-PS5-04773 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003F-CD04 | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4774 | PL-PS5-04774 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003G-CD04 | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4775 | PL-PS5-04775 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0002-CD48 | TZ-MID-68-WPR2-151112, 151116, 151118 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4776 | PL-PS5-04776 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0002-CD49 | TZ-MID-68-WPR2-151112, 151116, 151118 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4777 | PL-PS5-04777 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0002-CD50 | TZ-MID-68-WPR2-151112, 151116, 151118 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4778 | PL-PS5-04778 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD11 | TZ-MID-68-WPR2-151112, 151116, 151118 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4779 | PL-PS5-04779 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD12 | TZ-MID-68-WPR2-151112, 151116, 151118 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4780 | PL-PS5-04780 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD13 | TZ-MID-68-WPR2-151112, 151116, 151118 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4781 | PL-PS5-04781 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Building | PS5-71-BI-0005-CL03 | TZ-MID-68-WPR2-151167, 151118, 151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4782 | PL-PS5-04782 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Near EDG | PS5-05-BE-0001-CL12 | TZ-MID-68-WPR2-151111, 151112, 151116 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4783 | PL-PS5-04783 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD01 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4784 | PL-PS5-04784 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD02 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4785 | PL-PS5-04785 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD03 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4786 | PL-PS5-04786 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD04 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4787 | PL-PS5-04787 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD05 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4788 | PL-PS5-04788 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD06 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4789 | PL-PS5-04789 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD07 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4790 | PL-PS5-04790 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD11 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4791 | PL-PS5-04791 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD18 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4792 | PL-PS5-04792 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD19 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4793 | PL-PS5-04793 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD20 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4794 | PL-PS5-04794 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0006A-CL02 | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4795 | PL-PS5-04795 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003C-CD04 | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4796 | PL-PS5-04796 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003E-CD04 | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4797 | PL-PS5-04797 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003F-CD04 | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4798 | PL-PS5-04798 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IE-0003G-CD04 | TZ-MID-68-WPR2-151167, 151116, 151118, 151179 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4799 | PL-PS5-04799 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0002-CD48 | TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4800 | PL-PS5-04800 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0002-CD49 | TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4801 | PL-PS5-04801 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0002-CD50 | TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4802 | PL-PS5-04802 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD11 | TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4803 | PL-PS5-04803 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD12 | TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4804 | PL-PS5-04804 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD13 | TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4805 | PL-PS5-04805 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Building | PS5-71-BI-0005-CL03 | TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4806 | PL-PS5-04806 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Near EDG | PS5-05-BE-0001-CL12 | TZ-MID-68-WPR2-151112, 151116, 151118 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4807 | PL-PS5-04807 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD01 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4808 | PL-PS5-04808 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD02 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4809 | PL-PS5-04809 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD03 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4810 | PL-PS5-04810 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD04 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4811 | PL-PS5-04811 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD05 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4812 | PL-PS5-04812 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD06 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4813 | PL-PS5-04813 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD07 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4814 | PL-PS5-04814 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD11 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4815 | PL-PS5-04815 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD18 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4816 | PL-PS5-04816 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD19 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4817 | PL-PS5-04817 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD20 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4818 | PL-PS5-04818 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0006A-CL02 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 24/48VDC and 110/230/400VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4819 | PL-PS5-04819 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0002-CD48 | TZ-MID-68-WPR2-151112, 151116, 151118 Need additional cable ladder at EITS side | A | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4820 | PL-PS5-04820 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0002-CD49 | TZ-MID-68-WPR2-151112, 151116, 151118 Need additional cable ladder at EITS side | A | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4821 | PL-PS5-04821 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0002-CD50 | TZ-MID-68-WPR2-151112, 151116, 151118 Need additional cable ladder at EITS side | A | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4822 | PL-PS5-04822 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD11 | TZ-MID-68-WPR2-151112, 151116, 151118 Need additional cable ladder at EITS side | A | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4823 | PL-PS5-04823 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD12 | TZ-MID-68-WPR2-151112, 151116, 151118 Need additional cable ladder at EITS side | A | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4824 | PL-PS5-04824 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD13 | TZ-MID-68-WPR2-151112, 151116, 151118 Need additional cable ladder at EITS side | A | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4825 | PL-PS5-04825 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0002-CD48 | TZ-MID-68-WPR2-151112, 151116, 151118 Cable Trench backfilled , red protection tiles , and warning tape installation not complete | A | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4826 | PL-PS5-04826 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0002-CD49 | TZ-MID-68-WPR2-151112, 151116, 151118 Cable Trench backfilled , red protection tiles , and warning tape installation not complete | A | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4827 | PL-PS5-04827 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0002-CD50 | TZ-MID-68-WPR2-151112, 151116, 151118 Cable Trench backfilled , red protection tiles , and warning tape installation not complete | A | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4828 | PL-PS5-04828 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD11 | TZ-MID-68-WPR2-151112, 151116, 151118 Cable Trench backfilled , red protection tiles , and warning tape installation not complete | A | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4829 | PL-PS5-04829 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD12 | TZ-MID-68-WPR2-151112, 151116, 151118 Cable Trench backfilled , red protection tiles , and warning tape installation not complete | A | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4830 | PL-PS5-04830 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | EITS Building | PS5-61-IE-0003-CD13 | TZ-MID-68-WPR2-151112, 151116, 151118 Cable Trench backfilled , red protection tiles , and warning tape installation not complete | A | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4831 | PL-PS5-04831 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Building | PS5-71-BI-0005-CL03 | TZ-MID-68-WPR2-151167, 151118, 151179 Field Run Cable tray to be intall | A | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4832 | PL-PS5-04832 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Near EDG | PS5-05-BE-0001-CL12 | TZ-MID-68-WPR2-151111, 151112, 151116 To be install vertical cable ladder at EDG Junction box side | A | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4833 | PL-PS5-04833 | #N/A | CPP-RFI-68-33/1-05-0387 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BI-0006A-CL02 | TZ-MID-68-WPR2-151179 Field Run Cable Tray To be installed | A | Electrical | CPY | Rustam Battalov | 2026-06-27 | CPP EIT | Gao Chong |  |  |  |  | Open
4834 | PL-PS5-04834 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD08 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4835 | PL-PS5-04835 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD10 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4836 | PL-PS5-04836 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD12 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4837 | PL-PS5-04837 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD13 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4838 | PL-PS5-04838 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD14 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4839 | PL-PS5-04839 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD15 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4840 | PL-PS5-04840 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD16 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4841 | PL-PS5-04841 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD17 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4842 | PL-PS5-04842 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD21 | TZ-MID-68-WPR2-151167 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4843 | PL-PS5-04843 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD08 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4844 | PL-PS5-04844 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD10 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4845 | PL-PS5-04845 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD12 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4846 | PL-PS5-04846 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD13 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4847 | PL-PS5-04847 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD14 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4848 | PL-PS5-04848 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD15 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4849 | PL-PS5-04849 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD16 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4850 | PL-PS5-04850 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD17 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4851 | PL-PS5-04851 | #N/A | CPP-RFI-68-33/1-05-0391 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-05-IE-8100-CD21 | TZ-MID-68-WPR2-151167 Cable dressing to be complete at both side and in ELE tray not provided the segregation between 48VDC and 230VAC. | B | Electrical | CPY | Rustam Battalov | 2026-06-29 | CPP EIT | Gao Chong |  |  |  |  | Open
4852 | PL-PS5-04852 | #N/A | CPP-RFI-68-64-05-0076 | PS5 | Junction Box installation | Utility area | PS5-53-BI-1108 | Doc.UT-MID-60-WPR2-160101 - Grounding need to be Installed | A | Instrument | CPY | Rustam Battalov | 2026-06-26 | CPP EIT | Gao Chong |  |  |  |  | Open
4853 | PL-PS5-04853 | #N/A | CPP-RFI-68-64-05-0076 | PS5 | Junction Box installation | Launcher Receivier Area | PS5-25-BI-2104 | Doc.UT-MID-60-WPR2-160101 - Loose connection Grounding cable to the enclosure | A | Instrument | CPY | Rustam Battalov | 2026-06-26 | CPP EIT | Gao Chong |  |  |  |  | Open
4854 | PL-PS5-04854 | #N/A | CPP-RFI-68-64-05-0076 | PS5 | Junction Box installation | PGB area | PS5-03-BI-2505 | Doc.UT-MID-60-WPR2-160101 - Loose connection Grounding cable to the enclosure | A | Instrument | CPY | Rustam Battalov | 2026-06-26 | CPP EIT | Gao Chong |  |  |  |  | Open
4855 | PL-PS5-04855 | #N/A | CPP-RFI-68-65-05-0034 | PS5 | Telecom Cable Instalation | FIELD | PS5-08-85BT-0016-CJ01 | Doc. TZ-MID-68-WPR2-171100 - Cable Need to Be Dressing at Both Ends | B | Telecom Cables
4856 | PL-PS5-04856 | #N/A | CPP-RFI-68-65-05-0034 | PS5 | Telecom Cable Instalation | VSD & EITS BUILDING | PS5-61-IG-0012A-CX01 | Doc. TZ-MID-68-SSF1-240000 - Cable Need to Be Dressing at Both Ends | B | Telecom Cables
4857 | PL-PS5-04857 | #N/A | CPP-RFI-68-65-05-0034 | PS5 | Telecom Cable Instalation | VSD & EITS BUILDING | PS5-61-IG-0012B-CX01 | Doc. TZ-MID-68-SSF1-240000 - Cable Need to Be Dressing at Both Ends | B | Telecom Cables
4858 | PL-PS5-04858 | #N/A | CPP-RFI-68-65-05-0034 | PS5 | Telecom Cable Instalation | VSD & EITS BUILDING | PS5-61-IG-0012C-CX01 | Doc. TZ-MID-68-SSF1-240000 - Cable Need to Be Dressing at Both Ends | B | Telecom Cables
4859 | PL-PS5-04859 | #N/A | CPP-RFI-68-65-05-0034 | PS5 | Telecom Cable Instalation | Electrical Generator Building & EITS BUILDING | PS5-60-IE-0004-CX02 | TZ-MID-68-WPR2-151166, TZ-MID-68-SSF1-240000 - Cable Need to Be Dressing at Both Ends | B | Telecom Cables
4860 | PL-PS5-04860 | #N/A | CPP-RFI-68-65-05-0034 | PS5 | Telecom Cable Instalation | Electrical Generator Building & EITS BUILDING | PS5-60-IE-0004-CX01 | TZ-MID-68-WPR2-151166, TZ-MID-68-SSF1-240000 - Cable Need to Be Dressing at Both Ends | B | Telecom Cables
4861 | PL-PS5-04861 | #N/A | CPP-RFI-68-65-05-0034 | PS5 | Telecom Cable Instalation | Electrical Generator Building & EITS BUILDING | PS5-61-IK-0003-CX01 | TZ-MID-68-WPR2-151166, TZ-MID-68-SSF1-240000 - Cable Need to Be Dressing at Both Ends | B | Telecom Cables
4862 | PL-PS5-04862 | #N/A | CPP-RFI-68-65-05-0034 | PS5 | Telecom Cable Instalation | Electrical Generator Building & EITS BUILDING | PS5-61-IK-0006-CX01 | TZ-MID-68-WPR2-151166, TZ-MID-68-SSF1-240000 - Cable Need to Be Dressing at Both Ends | B | Telecom Cables
4863 | PL-PS5-04863 | #N/A | CPP-RFI-68-65-05-0034 | PS5 | Telecom Cable Instalation | FIELD | PS5-08-01LS-0307-CR01 | Doc. TZ-MID-68-WPR2-171100 - Cable Need to Be Dressing at Both Ends | B | Telecom Cables
4864 | PL-PS5-04864 | #N/A | CPP-RFI-68-65-05-0034 | PS5 | Telecom Cable Instalation | FIELD | PS5-08-01LS-0404-CR01 | Doc. TZ-MID-68-WPR2-171100 - Cable Need to Be Dressing at Both Ends | B | Telecom Cables
4865 | PL-PS5-04865 | #N/A | CPP-RFI-68-65-05-0034 | PS5 | Telecom Cable Instalation | Electrical Generator Building & FIELD | PS5-08-01BT-1901-CR02 | Doc. TZ-MID-68-WPR2-171100, TZ-MID-68-WPR2-171166 - Cable Need to Be Dressing at Both Ends | B | Telecom Cables
4866 | PL-PS5-04866 | #N/A | CPP-RFI-68-65-05-0034 | PS5 | Telecom Cable Instalation | field | PS5-08-85BT-0016-CJ01 | Doc. TZ-MID-68-WPR2-171100 - As Per Details Installation, Cable Tray need to be install (Junction Box Side) refer to Drawing UT-MID-60-WPR2-171204 | A | Telecom Cables
4867 | PL-PS5-04867 |  | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002C-CD01 | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4868 | PL-PS5-04868 |  | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002C-CD02 | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4869 | PL-PS5-04869 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002C-CD03 | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4870 | PL-PS5-04870 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002D-CD01 | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4871 | PL-PS5-04871 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002D-CD02 | TZ-MID-68-WPR2-151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4872 | PL-PS5-04872 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-71-BE-0004-CL01 | TZ-MID-68-WPR2-151167, 151118, 151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4873 | PL-PS5-04873 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-71-BE-0004-CL03 | TZ-MID-68-WPR2-151167, 151118, 151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4874 | PL-PS5-04874 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-71-BI-0003-CL01 | TZ-MID-68-WPR2-151167, 151118, 151179 Permanent SS cable tag to be install at both side | B | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4875 | PL-PS5-04875 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002C-CD01 | TZ-MID-68-WPR2-151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables | B | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4876 | PL-PS5-04876 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002C-CD02 | TZ-MID-68-WPR2-151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables | B | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4877 | PL-PS5-04877 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002C-CD03 | TZ-MID-68-WPR2-151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables | B | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4878 | PL-PS5-04878 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002D-CD01 | TZ-MID-68-WPR2-151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables | B | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4879 | PL-PS5-04879 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002D-CD02 | TZ-MID-68-WPR2-151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables | B | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4880 | PL-PS5-04880 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-71-BE-0004-CL01 | TZ-MID-68-WPR2-151167, 151118, 151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables | B | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4881 | PL-PS5-04881 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-71-BE-0004-CL03 | TZ-MID-68-WPR2-151167, 151118, 151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables | B | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4882 | PL-PS5-04882 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-71-BI-0003-CL01 | TZ-MID-68-WPR2-151167, 151118, 151179 Cable dressing to be complete at both side and maintain segregation between VDC and VAC Cables | B | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4883 | PL-PS5-04883 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002C-CD01 | TZ-MID-68-WPR2-151179 Secondary cable tray to be install at both side | A | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4884 | PL-PS5-04884 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002C-CD02 | TZ-MID-68-WPR2-151179 Secondary cable tray to be install at both side | A | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4885 | PL-PS5-04885 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002C-CD03 | TZ-MID-68-WPR2-151179 Secondary cable tray to be install at both side | A | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4886 | PL-PS5-04886 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002D-CD01 | TZ-MID-68-WPR2-151179 Secondary cable tray to be install at both side | A | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4887 | PL-PS5-04887 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002D-CD02 | TZ-MID-68-WPR2-151179 Secondary cable tray to be install at both side | A | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4888 | PL-PS5-04888 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-71-BE-0004-CL01 | TZ-MID-68-WPR2-151167, 151118, 151179 Field Run cable tray to be install | A | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4889 | PL-PS5-04889 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-71-BE-0004-CL03 | TZ-MID-68-WPR2-151167, 151118, 151179 Field Run cable tray to be install | A | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4890 | PL-PS5-04890 | #N/A | CPP-RFI-68-33/1-05-0399 | PS5 | Electrical Cable Installation | Generator Building | PS5-71-BI-0003-CL01 | TZ-MID-68-WPR2-151167, 151118, 151179 Field Run cable tray to be install | A | Electrical | CPY | Rustam Battalov | 2026-07-02 | CPP EIT | Gao Chong |  |  |  |  | Open
4891 | PL-PS5-04891 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation | EITS & Field | PS5-08-03TP-0001-CJ01 | Doc. TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-171100 - Cable Need to be Dressing at Both Ends | B | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4892 | PL-PS5-04892 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation |  | PS5-08-01MP-0001-CC01 | Doc. TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-171100 - Cable Need to be Dressing at Both Ends | B | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4893 | PL-PS5-04893 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation | EITS & Field | PS5-08-01MP-0001-CC02 | Doc. TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-171120, Cable Need to be Dressing at Both Ends | B | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4894 | PL-PS5-04894 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation | EITS & Field | PS5-08-01MP-0001-CC03 | Doc. TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-171100 - Cable Need to be Dressing at Both Ends | B | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4895 | PL-PS5-04895 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation | EITS & Field | PS5-08-01MP-0001-CC04 | Doc. TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-171120, Cable Need to be Dressing at Both Ends | B | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4896 | PL-PS5-04896 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation | FIELD | PS5-08-01LS-0101-CR01 | Doc. TZ-MID-68-WPR2-171120 - Cable Need to be Dressing at Both Ends | B | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4897 | PL-PS5-04897 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation | FIELD | PS5-08-01LS-0201-CR01 | Doc. TZ-MID-68-WPR2-171120 - Cable Need to be Dressing at Both Ends | B | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4898 | PL-PS5-04898 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation | Power Generator & Field | PS5-08-01BT-1903-CR01 | Doc. TZ-MID-68-WPR2-171127, TZ-MID-68-WPR2-171100 - Cable Need to be Dressing at Both Ends | B | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4899 | PL-PS5-04899 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation | Power Generator & Field | PS5-08-01BT-1904-CR01 | Doc. TZ-MID-68-WPR2-171127, TZ-MID-68-WPR2-171100 - Cable Need to be Dressing at Both Ends | B | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4900 | PL-PS5-04900 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation | Generator Electrical Building & Field | PS5-08-01BT-1902-CR02 | Doc. TZ-MID-68-WPR2-151166, TZ-MID-68-WPR2-171100, Cable Need to Be Dressing at Both Ends | B | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4901 | PL-PS5-04901 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation | Guard House & Field | PS5-08-85IN-0005-CA01 | TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, Cable need to be dressing at both ends | B | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4902 | PL-PS5-04902 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation | EITS & Field | PS5-08-52CM-0133-CX01 | Doc. TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-171120, Cable Need to be Dressing at Both Ends | B | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4903 | PL-PS5-04903 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation | Generator Electrical Building & Field | PS5-08-12BT-0101-CA01 | Doc. TZ-MID-68-WPR2-151166,TZ-MID-68-WPR2-171120 Cable Need to Be Dressing at Both Ends | B | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4904 | PL-PS5-04904 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation | Generator Electrical Building & Field | PS5-08-12BT-0107-CX01 | Doc. TZ-MID-68-WPR2-151166,TZ-MID-68-WPR2-171120 Cable Need to Be Dressing at Both Ends | B | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4905 | PL-PS5-04905 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation | Generator Electrical Building & Field | PS5-08-12BT-0108-CX01 | Doc. TZ-MID-68-WPR2-151166,TZ-MID-68-WPR2-171120 Cable Need to Be Dressing at Both Ends | B | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4906 | PL-PS5-04906 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation | EITS Building & Field | PS5-08-03TP-0001-CJ01 | Doc. TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-171100 - Cable Need to Install Cable Tagging at EITS Sisde | B | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4907 | PL-PS5-04907 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation | Guard House & Field | PS5-08-85IN-0005-CA01 | Doc. TZ-MID-68-WPR2-171120, TZ-MID-68-WPR2-171100, in correct Cable Tagging Address at Intercom Side | B | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4908 | PL-PS5-04908 | #N/A | CPP-RFI-68-65-05-0036 | PS5 | Telecom Cable Instalation | Generator Electrical Building & Field | PS5-08-12BT-0101-CA01 | Doc. Doc. TZ-MID-68-WPR2-151166,TZ-MID-68-WPR2-171120, Field Run Cable Tray need to Install at Wap Junction Box Side | A | Telecom Cables | CPY | Rustam Battalov | 2026-07-06 | CPP EIT | Gao Chong |  |  |  |  | Open
4909 | PL-PS5-04909 |  | CPP-RFI-68-332-03-0406 | PS5 | Unit Control Panel for Emergency Diesel Generator | Gen. Electrical Building | PS5-05-IE-8100 | TZ-MID-60-UTR2-150005 Cleanning internal and external of the panel | C | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4910 | PL-PS5-04910 |  | CPP-RFI-68-332-03-0406 | PS5 | UPS A DB | Gen. Electrical Building | PS5-06-IG-0004A | TZ-MID-60-RME2-150010 Cleanning internal and external of the panel | C | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4911 | PL-PS5-04911 |  | CPP-RFI-68-332-03-0406 | PS5 | UPS B DB | Gen. Electrical Building | PS5-06-IG-0004B | TZ-MID-60-RME2-150010 Cleanning internal and external of the panel | C | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4912 | PL-PS5-04912 |  | CPP-RFI-68-332-03-0406 | PS5 | VTMS CABINET B | Gen. Electrical Building | PS5-60-LA-0002B | TZ-MID-68-UTR1-150016 Cleanning internal and external of the panel | C | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4913 | PL-PS5-04913 |  | CPP-RFI-68-332-03-0406 | PS5 | VTMS CABINET C | Gen. Electrical Building | PS5-60-LA-0002C | TZ-MID-68-UTR1-150016 Cleanning internal and external of the panel | C | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4914 | PL-PS5-04914 |  | CPP-RFI-68-332-03-0406 | PS5 | Unit Control Panel for Emergency Diesel Generator | Gen. Electrical Building | PS5-05-IE-8100 | TZ-MID-60-UTR2-150005 The Panel Frame need to be touch up paint | C | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4915 | PL-PS5-04915 |  | CPP-RFI-68-332-03-0406 | PS5 | UPS A DB | Gen. Electrical Building | PS5-06-IG-0004A | TZ-MID-60-RME2-150010 The Panel Frame need to be touch up paint | C | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4916 | PL-PS5-04916 |  | CPP-RFI-68-332-03-0406 | PS5 | UPS B DB | Gen. Electrical Building | PS5-06-IG-0004B | TZ-MID-60-RME2-150010 The Panel Frame need to be touch up paint | C | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4917 | PL-PS5-04917 |  | CPP-RFI-68-332-03-0406 | PS5 | VTMS CABINET B | Gen. Electrical Building | PS5-60-LA-0002B | TZ-MID-68-UTR1-150016 The Panel Frame need to be touch up paint and un-used hole to be closed | C | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4918 | PL-PS5-04918 |  | CPP-RFI-68-332-03-0406 | PS5 | VTMS CABINET C | Gen. Electrical Building | PS5-60-LA-0002C | TZ-MID-68-UTR1-150016 The Panel Frame need to be touch up paint and un-used hole to be closed | C | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4919 | PL-PS5-04919 |  | CPP-RFI-68-332-03-0406 | PS5 | Unit Control Panel for Emergency Diesel Generator | Gen. Electrical Building | PS5-05-IE-8100 | TZ-MID-60-UTR2-150005 IE bar not connected to earth grid | B | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4920 | PL-PS5-04920 |  | CPP-RFI-68-332-03-0406 | PS5 | VTMS CABINET B | Gen. Electrical Building | PS5-60-LA-0002B | TZ-MID-68-UTR1-150016 ISE bar not connected to isolated earth grid | B | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4921 | PL-PS5-04921 |  | CPP-RFI-68-332-03-0406 | PS5 | VTMS CABINET C | Gen. Electrical Building | PS5-60-LA-0002C | TZ-MID-68-UTR1-150016 ISE bar not connected to isolated earth grid | B | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4922 | PL-PS5-04922 |  | CPP-RFI-68-332-16-0396 | PS5 | Distribution Transformer | Gen. Electrical Building | PS5-61-IV-0001B | TZ-MID-68-WPR2-151112 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding | A | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4923 | PL-PS5-04923 |  | CPP-RFI-68-332-16-0396 | PS5 | Distribution Transformer | Gen. Electrical Building | PS5-61-IV-0002A | TZ-MID-68-WPR2-151167 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding | A | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4924 | PL-PS5-04924 |  | CPP-RFI-68-332-16-0396 | PS5 | Distribution Transformer | Gen. Electrical Building | PS5-61-IV-0002B | TZ-MID-68-WPR2-151167 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding | A | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4925 | PL-PS5-04925 |  | CPP-RFI-68-332-16-0396 | PS5 | Distribution Transformer | Gen. Electrical Building | PS5-61-IV-0007A | TZ-MID-68-WPR2-151167 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding | A | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4926 | PL-PS5-04926 |  | CPP-RFI-68-332-16-0396 | PS5 | Distribution Transformer | Gen. Electrical Building | PS5-61-IV-0007B | TZ-MID-68-WPR2-151167 Cable tray of gorunding cable needs to be lifted up 300mm for gravel bedding | A | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4927 | PL-PS5-04927 | #N/A | CPP-RFI-68-332-16-0396 | PS5 | Distribution Transformer | Gen. Electrical Building | PS5-61-IV-0001B | TZ-MID-68-WPR2-151112 Transformer Grounding Not Complete | A | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4928 | PL-PS5-04928 | #N/A | CPP-RFI-68-332-16-0396 | PS5 | Distribution Transformer | Gen. Electrical Building | PS5-61-IV-0002A | TZ-MID-68-WPR2-151167 Transformer Grounding Not Complete | A | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4929 | PL-PS5-04929 | #N/A | CPP-RFI-68-332-16-0396 | PS5 | Distribution Transformer | Gen. Electrical Building | PS5-61-IV-0002B | TZ-MID-68-WPR2-151167 Transformer Grounding Not Complete | A | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4930 | PL-PS5-04930 | #N/A | CPP-RFI-68-332-16-0396 | PS5 | Distribution Transformer | Gen. Electrical Building | PS5-61-IV-0007A | TZ-MID-68-WPR2-151167 Transformer Grounding Not Complete | A | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4931 | PL-PS5-04931 | #N/A | CPP-RFI-68-332-16-0396 | PS5 | Distribution Transformer | Gen. Electrical Building | PS5-61-IV-0007B | TZ-MID-68-WPR2-151167 Transformer Grounding Not Complete | A | Electrical | CPY | Rustam Battalov | 2026-07-08 | CPP EIT | Gao Chong |  |  |  |  | Open
4932 | PL-PS5-04932 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0005F-CL01 | TZ-MID-68-WPR2-151167,151116,151179 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4933 | PL-PS5-04933 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0024C-CL01 | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4934 | PL-PS5-04934 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0024C-CL02 | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4935 | PL-PS5-04935 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0024E-CL02 | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4936 | PL-PS5-04936 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0024F-CL02 | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4937 | PL-PS5-04937 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0024G-CL01 | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4938 | PL-PS5-04938 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0025C-CL01 | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4939 | PL-PS5-04939 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0025G-CL01 | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4940 | PL-PS5-04940 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0026C-CL01 | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4941 | PL-PS5-04941 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0026G-CL01 | TZ-MID-68-WPR2-151116 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4942 | PL-PS5-04942 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002C-CL02 | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4943 | PL-PS5-04943 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002E-CL01 | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4944 | PL-PS5-04944 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002E-CL02 | TZ-MID-68-WPR2-151167,151118,151116,151179 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4945 | PL-PS5-04945 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001C-CL01 | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4946 | PL-PS5-04946 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001C-CL02 | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4947 | PL-PS5-04947 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001C-CL03 | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4948 | PL-PS5-04948 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001C-CL04 | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4949 | PL-PS5-04949 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001G-CL04 | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4950 | PL-PS5-04950 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Inside Power Gen. Building | PS5-60-ISO-62800A-CL01 | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4951 | PL-PS5-04951 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Inside Power Gen. Building | PS5-60-ISO-62800E-CL01 | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4952 | PL-PS5-04952 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-VS-9100E-CL01 | TZ-MID-68-WPR2-151118,151116 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4953 | PL-PS5-04953 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-71-IN-0004A-CL01 | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4954 | PL-PS5-04954 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-71-IN-0004A-CL02 | TZ-MID-68-WPR2-151167 Permanent SS Cable Tag To be Installed at Both side | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4955 | PL-PS5-04955 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0005F-CL01 | TZ-MID-68-WPR2-151167,151116,151179 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4956 | PL-PS5-04956 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0024C-CL01 | TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4957 | PL-PS5-04957 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0024C-CL02 | TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4958 | PL-PS5-04958 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0024E-CL02 | TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4959 | PL-PS5-04959 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0024F-CL02 | TZ-MID-68-WPR2-151116 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4960 | PL-PS5-04960 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0024G-CL01 | TZ-MID-68-WPR2-151116 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4961 | PL-PS5-04961 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0025C-CL01 | TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4962 | PL-PS5-04962 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0025G-CL01 | TZ-MID-68-WPR2-151116 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4963 | PL-PS5-04963 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0026C-CL01 | TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4964 | PL-PS5-04964 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0026G-CL01 | TZ-MID-68-WPR2-151116 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4965 | PL-PS5-04965 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002C-CL02 | TZ-MID-68-WPR2-151167,151116,151179 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4966 | PL-PS5-04966 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002E-CL01 | TZ-MID-68-WPR2-151167,151116,151179 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4967 | PL-PS5-04967 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-IE-0002E-CL02 | TZ-MID-68-WPR2-151167,151116,151179 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4968 | PL-PS5-04968 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001C-CL01 | TZ-MID-68-WPR2-151167 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4969 | PL-PS5-04969 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001C-CL02 | TZ-MID-68-WPR2-151167 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4970 | PL-PS5-04970 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001C-CL03 | TZ-MID-68-WPR2-151167 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4971 | PL-PS5-04971 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001C-CL04 | TZ-MID-68-WPR2-151167 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4972 | PL-PS5-04972 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IH-0001G-CL04 | TZ-MID-68-WPR2-151167 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4973 | PL-PS5-04973 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Inside Power Gen. Building | PS5-60-ISO-62800A-CL01 | TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4974 | PL-PS5-04974 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Inside Power Gen. Building | PS5-60-ISO-62800E-CL01 | TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4975 | PL-PS5-04975 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-VS-9100E-CL01 | TZ-MID-68-WPR2-151118,151116 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4976 | PL-PS5-04976 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-71-IN-0004A-CL01 | TZ-MID-68-WPR2-151167 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4977 | PL-PS5-04977 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-71-IN-0004A-CL02 | TZ-MID-68-WPR2-151167 Cable Dressing not yet done | B | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4978 | PL-PS5-04978 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0005F-CL01 | TZ-MID-68-WPR2-151167,151116,151179 Field run cable tray not finished | A | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4979 | PL-PS5-04979 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0024C-CL01 | TZ-MID-68-WPR2-151118,151116 Field run cable tray not finished | A | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4980 | PL-PS5-04980 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0024C-CL02 | TZ-MID-68-WPR2-151118,151116 Field run cable tray not finished | A | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4981 | PL-PS5-04981 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0024E-CL02 | TZ-MID-68-WPR2-151118,151116 Field run cable tray not finished | A | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4982 | PL-PS5-04982 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-BE-0024F-CL02 | TZ-MID-68-WPR2-151116 Field run cable tray not finished | A | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4983 | PL-PS5-04983 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Inside Power Gen. Building | PS5-60-ISO-62800E-CL01 | TZ-MID-68-WPR2-151118,151116 Field run cable tray not finished | A | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4984 | PL-PS5-04984 | #N/A | CPP-RFI-68-33/1-05-0407 | PS5 | Electrical Cable Installation | Generator Building | PS5-60-VS-9100E-CL01 | TZ-MID-68-WPR2-151118,151116 Field run cable tray not finished | A | Electrical | CPY | Rustam Battalov | 2026-07-09 | CPP EIT | Gao Chong |  |  |  |  | Open
4985 | PL-PS5-04985 | #N/A | CPP-RFI-68-64-4-0091 | PS5 | Instrument Cable Installation | Launcher Receivier Area / Road near | PS5-03-RDIR-0137-CJ01 | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side | B | Instrument | CPY | Rustam Battalov | 2026-07-10 | CPP EIT | Gao Chong |  |  |  |  | Open
4986 | PL-PS5-04986 | #N/A | CPP-RFI-68-64-4-0091 | PS5 | Instrument Cable Installation | near Closed drain drum area | PS5-03-RDIR-0142-CJ01 | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side | B | Instrument | CPY | Rustam Battalov | 2026-07-10 | CPP EIT | Gao Chong |  |  |  |  | Open
4987 | PL-PS5-04987 | #N/A | CPP-RFI-68-64-4-0093 | PS5 | Instrument Cable Installation | Launcher Receivier Area | PS5-25-FIT-0001-CJ01 | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side | B | Instrument | CPY | Rustam Battalov | 2026-07-13 | CPP EIT | Gao Chong |  |  |  |  | Open
4988 | PL-PS5-04988 | #N/A | CPP-RFI-68-64-4-0093 | PS5 | Instrument Cable Installation | Launcher Receivier Area | PS5-25-PIT-1102-CJ01 | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side | B | Instrument | CPY | Rustam Battalov | 2026-07-13 | CPP EIT | Gao Chong |  |  |  |  | Open
4989 | PL-PS5-04989 | #N/A | CPP-RFI-68-64-4-0093 | PS5 | Instrument Cable Installation | Launcher Receivier Area | PS5-25-PIT-1202-CJ01 | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side | B | Instrument | CPY | Rustam Battalov | 2026-07-13 | CPP EIT | Gao Chong |  |  |  |  | Open
4990 | PL-PS5-04990 | #N/A | CPP-RFI-68-64-4-0093 | PS5 | Instrument Cable Installation | Launcher Receivier Area | PS5-25-TIT-0001-CJ01 | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side | B | Instrument | CPY | Rustam Battalov | 2026-07-13 | CPP EIT | Gao Chong |  |  |  |  | Open
4991 | PL-PS5-04991 | #N/A | CPP-RFI-68-64-4-0093 | PS5 | Instrument Cable Installation | Launcher Receivier Area | PS5-25-TIT-1101-CJ01 | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side | B | Instrument | CPY | Rustam Battalov | 2026-07-13 | CPP EIT | Gao Chong |  |  |  |  | Open
4992 | PL-PS5-04992 | #N/A | CPP-RFI-68-64-4-0093 | PS5 | Instrument Cable Installation | Launcher Receivier Area | PS5-25-TIT-1201-CJ01 | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side | B | Instrument | CPY | Rustam Battalov | 2026-07-13 | CPP EIT | Gao Chong |  |  |  |  | Open
4993 | PL-PS5-04993 | #N/A | CPP-RFI-68-64-4-0093 | PS5 | Instrument Cable Installation | Launcher Receivier Area | PS5-25-MOV-0027-CC02 | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side | B | Instrument | CPY | Rustam Battalov | 2026-07-13 | CPP EIT | Gao Chong |  |  |  |  | Open
4994 | PL-PS5-04994 | #N/A | CPP-RFI-68-64-4-0093 | PS5 | Instrument Cable Installation | Launcher Receivier Area | PS5-28-LI-1101C-CJ01 | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side | B | Instrument | CPY | Rustam Battalov | 2026-07-13 | CPP EIT | Gao Chong |  |  |  |  | Open
4995 | PL-PS5-04995 | #VALUE! | CPP-RFI-68-64-4-0093 | PS5 | Instrument Cable Installation | Launcher Receivier Area | PS5-25-PI-1102B-CJ01 | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side | B | Instrument | CPY | Rustam Battalov | 2026-07-13 | CPP EIT | Gao Chong |  |  |  |  | Open
4996 | PL-PS5-04996 | #VALUE! | CPP-RFI-68-64-4-0093 | PS5 | Instrument Cable Installation | Launcher Receivier Area | PS5-25-PI-1202B-CJ01 | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side | B | Instrument | CPY | Rustam Battalov | 2026-07-13 | CPP EIT | Gao Chong |  |  |  |  | Open
4997 | PL-PS5-04997 | #VALUE! | CPP-RFI-68-33-2-13-0402 | PS5 | Electrical Equipment Installation | Generator Electrical Building | PS5-61-IK-0003 | TZ-MID-68-WPR2-151166 To be cleanning internal and external of the panel | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4998 | PL-PS5-04998 | #VALUE! | CPP-RFI-68-33-2-13-0402 | PS5 | Electrical Equipment Installation | Generator Electrical Building | PS5-61-IK-0003 | TZ-MID-68-WPR2-151166 All Un-Used cables entries to be plugged with suitable dummy plug | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-21 | CPP EIT | Gao Chong |  |  |  |  | Open
4999 | PL-PS5-04999 | #VALUE! | CPP-RFI-68-33-2-13-0402 | PS5 | Electrical Equipment Installation | Generator Electrical Building | PS5-61-IK-0003 | TZ-MID-68-WPR2-151166 Foundation frame to be touch up paint | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-21 | CPP EIT | Gao Chong |  |  |  |  | Open
5000 | PL-PS5-05000 | #VALUE! | CPP-RFI-68-64-4-0097 | PS5 | Instrument Cable Installation | EXPORT PUMP AREA | PS5-25-PIT-0005A-CJ01 | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side | B | Instrument | CPY | Rustam Battalov | 2026-07-16 | CPP EIT | Gao Chong |  |  |  |  | Open
5001 | PL-PS5-05001 | #VALUE! | CPP-RFI-68-64-4-0097 | PS5 | Instrument Cable Installation | EXPORT PUMP AREA | PS5-25-FY-0003B-CJ01 | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side | B | Instrument | CPY | Rustam Battalov | 2026-07-16 | CPP EIT | Gao Chong |  |  |  |  | Open
5002 | PL-PS5-05002 | #VALUE! | CPP-RFI-68-64-4-0097 | PS5 | Instrument Cable Installation | EXPORT PUMP AREA | PS5-25-PIT-0070-CJ01 | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side | B | Instrument | CPY | Rustam Battalov | 2026-07-16 | CPP EIT | Gao Chong |  |  |  |  | Open
5003 | PL-PS5-05003 | #VALUE! | CPP-RFI-68-64-4-0109 | PS5 | Instrument Cable Installation | EXPORT PUMP AREA | PS5-25-FY-0003C-CJ01 | TZ-MID-68-WPR2-160500 Field run cable tray not finished | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-22 | CPP EIT | Gao Chong |  |  |  |  | Open
5004 | PL-PS5-05004 | #VALUE! | CPP-RFI-68-64-4-0109 | PS5 | Instrument Cable Installation | EXPORT PUMP AREA | PS5-25-PIT-0005C-CJ01 | TZ-MID-68-WPR2-160500 Field run cable tray not finished | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-22 | CPP EIT | Gao Chong |  |  |  |  | Open
5005 | PL-PS5-05005 | #VALUE! | CPP-RFI-68-64-4-0109 | PS5 | Instrument Cable Installation | EXPORT PUMP AREA | PS5-25-TIT-0003C-CJ01 | TZ-MID-68-WPR2-160500 Field run cable tray not finished | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-22 | CPP EIT | Gao Chong |  |  |  |  | Open
5006 | PL-PS5-05006 | #VALUE! | CPP-RFI-68-64-4-0109 | PS5 | Instrument Cable Installation | EXPORT PUMP AREA | PS5-28-LIT-1301C-CJ01 | TZ-MID-68-WPR2-160500 Field run cable tray not finished | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-22 | CPP EIT | Gao Chong |  |  |  |  | Open
5007 | PL-PS5-05007 | #VALUE! | CPP-RFI-68-64-4-0109 | PS5 | Instrument Cable Installation | EXPORT PUMP AREA | PS5-25-PIT-0003CA-CJ01 | TZ-MID-68-WPR2-160500 Field run cable tray not finished | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-22 | CPP EIT | Gao Chong |  |  |  |  | Open
5008 | PL-PS5-05008 | #VALUE! | CPP-RFI-68-64-4-0109 | PS5 | Instrument Cable Installation | EXPORT PUMP AREA | PS5-25-PIT-0003CA-CJ01 | TZ-MID-68-WPR2-160500 Permanent SS Cable Tag To be Installed at instrument side | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-22 | CPP EIT | Gao Chong |  |  |  |  | Open
5009 | PL-PS5-05009 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0011A-CL01 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5010 | PL-PS5-05010 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0011A-CL02 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5011 | PL-PS5-05011 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0011A-CL03 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5012 | PL-PS5-05012 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0011A-CL04 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5013 | PL-PS5-05013 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0011A-CL05 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5014 | PL-PS5-05014 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0011A-CL06 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5015 | PL-PS5-05015 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0011B-CL01 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5016 | PL-PS5-05016 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0011B-CL02 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5017 | PL-PS5-05017 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0011B-CL03 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5018 | PL-PS5-05018 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0011B-CL04 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5019 | PL-PS5-05019 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0011B-CL05 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5020 | PL-PS5-05020 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0011B-CL06 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5021 | PL-PS5-05021 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0012A-CL01 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5022 | PL-PS5-05022 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0012A-CL02 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5023 | PL-PS5-05023 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0012A-CL03 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5024 | PL-PS5-05024 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0012A-CL04 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5025 | PL-PS5-05025 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0012A-CL05 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5026 | PL-PS5-05026 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0012A-CL06 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5027 | PL-PS5-05027 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0012B-CL01 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5028 | PL-PS5-05028 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0012B-CL02 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5029 | PL-PS5-05029 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0012B-CL03 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5030 | PL-PS5-05030 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0012B-CL04 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5031 | PL-PS5-05031 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0012B-CL05 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5032 | PL-PS5-05032 | #VALUE! | CPP-RFI-68-331-06-0433 | PS5 | Gland & Termination | Gen. Electrical Building and CRO | PS5-60-BE-0012B-CL06 | TZ-MID-68-WPR2-151167 Earthing Tag to be bond to the earth stud at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-23 | CPP EIT | Gao Chong |  |  |  |  | Open
5033 | PL-PS5-05033 | #VALUE! | CPP-RFI-68-64-07-0113 | PS5 | Instrument installation | Gen. Electrical Building A and B | PS5-60-TG-0007A | TZ-MID-68-WPR2-161502 Permanent tags and hanging tags to be installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5034 | PL-PS5-05034 | #VALUE! | CPP-RFI-68-64-07-0113 | PS5 | Instrument installation | Gen. Electrical Building A and B | PS5-60-TG-0007B | TZ-MID-68-WPR2-161502 Permanent tags and hanging tags to be installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5035 | PL-PS5-05035 | #VALUE! | CPP-RFI-68-64-07-0113 | PS5 | Instrument installation | Gen. Electrical Building A and B | PS5-60-TG-0008A | TZ-MID-68-WPR2-161502 Permanent tags and hanging tags to be installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5036 | PL-PS5-05036 | #VALUE! | CPP-RFI-68-64-07-0113 | PS5 | Instrument installation | Gen. Electrical Building A and B | PS5-60-TG-0008B | TZ-MID-68-WPR2-161502 Permanent tags and hanging tags to be installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5037 | PL-PS5-05037 | #VALUE! | CPP-RFI-68-64-07-0113 | PS5 | Instrument installation | Gen. Electrical Building A and B | PS5-60-TG-0006A | TZ-MID-68-WPR2-161502 Permanent tags and hanging tags to be installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5038 | PL-PS5-05038 | #VALUE! | CPP-RFI-68-64-07-0113 | PS5 | Instrument installation | Gen. Electrical Building A and B | PS5-60-TG-0006B | TZ-MID-68-WPR2-161502 Permanent tags and hanging tags to be installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5039 | PL-PS5-05039 | #VALUE! | CPP-RFI-68-64-07-0113 | PS5 | Instrument installation | Gen. Electrical Building A and B | PS5-60-TG-0005A | TZ-MID-68-WPR2-161502 Permanent tags and hanging tags to be installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5040 | PL-PS5-05040 | #VALUE! | CPP-RFI-68-64-07-0113 | PS5 | Electrical Cable Installation | Gen. Electrical Building A and B | PS5-60-TG-0005B | TZ-MID-68-WPR2-161502 Permanent tags and hanging tags to be installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5041 | PL-PS5-05041 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL01 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5042 | PL-PS5-05042 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL03 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5043 | PL-PS5-05043 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL04 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5044 | PL-PS5-05044 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL05 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5045 | PL-PS5-05045 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL06 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5046 | PL-PS5-05046 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL07 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5047 | PL-PS5-05047 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL08 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5048 | PL-PS5-05048 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL09 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5049 | PL-PS5-05049 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL10 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5050 | PL-PS5-05050 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL11 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5051 | PL-PS5-05051 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0017A-CL01 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5052 | PL-PS5-05052 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL01 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5053 | PL-PS5-05053 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL02 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5054 | PL-PS5-05054 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL03 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5055 | PL-PS5-05055 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL04 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5056 | PL-PS5-05056 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL05 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5057 | PL-PS5-05057 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL06 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5058 | PL-PS5-05058 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL07 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5059 | PL-PS5-05059 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL08 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5060 | PL-PS5-05060 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL09 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5061 | PL-PS5-05061 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL10 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5062 | PL-PS5-05062 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL11 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5063 | PL-PS5-05063 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0017B-CL01 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5064 | PL-PS5-05064 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL01 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5065 | PL-PS5-05065 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL03 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5066 | PL-PS5-05066 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL04 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5067 | PL-PS5-05067 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL05 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5068 | PL-PS5-05068 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL06 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5069 | PL-PS5-05069 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL07 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5070 | PL-PS5-05070 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL08 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5071 | PL-PS5-05071 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL09 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5072 | PL-PS5-05072 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL10 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5073 | PL-PS5-05073 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL11 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5074 | PL-PS5-05074 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0017A-CL01 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5075 | PL-PS5-05075 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL01 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5076 | PL-PS5-05076 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL02 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5077 | PL-PS5-05077 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL03 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5078 | PL-PS5-05078 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL04 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5079 | PL-PS5-05079 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL05 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5080 | PL-PS5-05080 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL06 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5081 | PL-PS5-05081 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL07 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5082 | PL-PS5-05082 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL08 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5083 | PL-PS5-05083 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL09 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5084 | PL-PS5-05084 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL10 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5085 | PL-PS5-05085 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL11 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5086 | PL-PS5-05086 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0017B-CL01 | TZ-MID-68-WPR2-151187, SS Cables Tags not yet Install (From Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5087 | PL-PS5-05087 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL01 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5088 | PL-PS5-05088 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL03 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5089 | PL-PS5-05089 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL04 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5090 | PL-PS5-05090 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL05 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5091 | PL-PS5-05091 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL06 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5092 | PL-PS5-05092 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL07 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5093 | PL-PS5-05093 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL08 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5094 | PL-PS5-05094 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL09 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5095 | PL-PS5-05095 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL10 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5096 | PL-PS5-05096 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL11 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5097 | PL-PS5-05097 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0017A-CL01 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5098 | PL-PS5-05098 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL01 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5099 | PL-PS5-05099 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL02 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5100 | PL-PS5-05100 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL03 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5101 | PL-PS5-05101 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL04 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5102 | PL-PS5-05102 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL05 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5103 | PL-PS5-05103 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL06 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5104 | PL-PS5-05104 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL07 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5105 | PL-PS5-05105 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL08 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5106 | PL-PS5-05106 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL09 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5107 | PL-PS5-05107 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL10 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5108 | PL-PS5-05108 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL11 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5109 | PL-PS5-05109 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0017B-CL01 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5110 | PL-PS5-05110 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL01 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5111 | PL-PS5-05111 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL03 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5112 | PL-PS5-05112 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL04 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5113 | PL-PS5-05113 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL05 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5114 | PL-PS5-05114 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL06 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5115 | PL-PS5-05115 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL07 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5116 | PL-PS5-05116 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL08 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5117 | PL-PS5-05117 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL09 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5118 | PL-PS5-05118 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL10 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5119 | PL-PS5-05119 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006A-CL11 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5120 | PL-PS5-05120 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0017A-CL01 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5121 | PL-PS5-05121 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL01 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5122 | PL-PS5-05122 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL02 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5123 | PL-PS5-05123 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL03 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5124 | PL-PS5-05124 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL04 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5125 | PL-PS5-05125 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL05 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5126 | PL-PS5-05126 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL06 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5127 | PL-PS5-05127 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL07 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5128 | PL-PS5-05128 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL08 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5129 | PL-PS5-05129 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL09 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5130 | PL-PS5-05130 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL10 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5131 | PL-PS5-05131 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0006B-CL11 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5132 | PL-PS5-05132 | #VALUE! | CPP-RFI-68-33/1-05-0432 | PS5 | Electrical Cable Installation | Generator A & B | PS5-60-BI-0017B-CL01 | TZ-MID-68-WPR2-151187, Horizontal Cable Tray for Fuel Conditioning Control Panel need to be install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-24 | CPP EIT | Gao Chong |  |  |  |  | Open
5133 | PL-PS5-05133 | #VALUE! | CPP-RFI-68-33/1-08-0428 | PS5 | EHT SR cable Installaation | RDD Shelter to CDD shelter | PS5-79-BE-0262-CT01 | TZ-MID-68-NVS1-150280 ;SS Cables Tags not yet Install (both Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-25 | CPP EIT | Gao Chong |  |  |  |  | Open
5134 | PL-PS5-05134 | #VALUE! | CPP-RFI-68-33/1-08-0428 | PS5 | EHT SR cable Installaation | RDD Shelter to CDD shelter | PS5-79-BE-0263-CT02 | TZ-MID-68-NVS1-150281 ;SS Cables Tags not yet Install (both Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-25 | CPP EIT | Gao Chong |  |  |  |  | Open
5135 | PL-PS5-05135 | #VALUE! | CPP-RFI-68-33/1-08-0428 | PS5 | EHT SR cable Installaation | RDD Shelter to CDD shelter | PS5-79-BE-0012-CT01 | TZ-MID-68-NVS1-150030 ;SS Cables Tags not yet Install (both Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-25 | CPP EIT | Gao Chong |  |  |  |  | Open
5136 | PL-PS5-05136 | #VALUE! | CPP-RFI-68-33/1-08-0428 | PS5 | EHT SR cable Installaation | RDD Shelter to CDD shelter | PS5-79-BE-0012-CT02 | TZ-MID-68-NVS1-150030 ;SS Cables Tags not yet Install (both Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-25 | CPP EIT | Gao Chong |  |  |  |  | Open
5137 | PL-PS5-05137 | #VALUE! | CPP-RFI-68-33/1-08-0428 | PS5 | EHT SR cable Installaation | Process area | PS5-79-BE-0263-CT01 | TZ-MID-68-NVS1-150281 ;SS Cables Tags not yet Install (both Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-25 | CPP EIT | Gao Chong |  |  |  |  | Open
5138 | PL-PS5-05138 | #VALUE! | CPP-RFI-68-33/1-08-0428 | PS5 | EHT SR cable Installaation | Process area | PS5-79-BE-0262-CT02 | TZ-MID-68-NVS1-150280 ;SS Cables Tags not yet Install (both Side) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-25 | CPP EIT | Gao Chong |  |  |  |  | Open
5139 | PL-PS5-05139 | #VALUE! | CPP-RFI-68-33/1-08-0428 | PS5 | EHT SR cable Installaation | RDD Shelter to CDD shelter | PS5-79-TE-0013 | TZ-MID-68-NVS1-150030 ;SS Cables Tags not yet Install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-25 | CPP EIT | Gao Chong |  |  |  |  | Open
5140 | PL-PS5-05140 | #VALUE! | CPP-RFI-68-33/1-08-0428 | PS5 | EHT SR cable Installaation | RDD Shelter to CDD shelter | PS5-79-BE-0013 | TZ-MID-68-NVS1-150030 ;SS Cables Tags not yet Install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-25 | CPP EIT | Gao Chong |  |  |  |  | Open
5141 | PL-PS5-05141 | #VALUE! | CPP-RFI-68-33/1-08-0428 | PS5 | EHT SR cable Installaation | RDD Shelter to CDD shelter | PS5-79-BE-0012 | TZ-MID-68-NVS1-150030 ;SS Cables Tags not yet Install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-25 | CPP EIT | Gao Chong |  |  |  |  | Open
5142 | PL-PS5-05142 | #VALUE! | CPP-RFI-68-33/1-08-0428 | PS5 | EHT SR cable Installaation | RDD Shelter to CDD shelter | PS5-79-TE-0012 | TZ-MID-68-NVS1-150030 ;SS Cables Tags not yet Install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-25 | CPP EIT | Gao Chong |  |  |  |  | Open
5143 | PL-PS5-05143 | #VALUE! | CPP-RFI-68-33/1-08-0428 | PS5 | EHT SR cable Installaation | Process area | PS5-79-BE-00262 | TZ-MID-68-NVS1-150280 ;SS Cables Tags not yet Install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-25 | CPP EIT | Gao Chong |  |  |  |  | Open
5144 | PL-PS5-05144 | #VALUE! | CPP-RFI-68-33/1-08-0428 | PS5 | EHT SR cable Installaation | Process area | PS5-79-TE-00262 | TZ-MID-68-NVS1-150280 ;SS Cables Tags not yet Install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-25 | CPP EIT | Gao Chong |  |  |  |  | Open
5145 | PL-PS5-05145 | #VALUE! | CPP-RFI-68-33/1-08-0428 | PS5 | EHT SR cable Installaation | Process area | PS5-79-BE-00263 | TZ-MID-68-NVS1-150281 ;SS Cables Tags not yet Install | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-25 | CPP EIT | Gao Chong |  |  |  |  | Open
5146 | PL-PS5-05146 | #VALUE! | CPP-RFI-68-33/1-08-0428 | PS5 | EHT SR cable Installaation | Process area | PS5-79-TE-00263 | TZ-MID-68-NVS1-150281 ;SS Cables Tags not yet Install | B | Instrument | CPY | Konstantin Ovchinnikov | [7 empty] | Open
5147 | PL-PS5-05147 | #VALUE! | CPP-RFI-68-64-04-0117 | PS5 | INSTRUEMNT CABLE INSTALLATION | GCP A PGB ELEC BLDG - GEN A ENGING | PS5-60-IE-0003A-CC02 | TZ-MID-68-WPR2-160102 SS Cables Tags not yet Install BOTH SIDE | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-27 | CPP EIT | Gao Chong |  |  |  |  | Open
5148 | PL-PS5-05148 | #VALUE! | CPP-RFI-68-64-04-0117 | PS5 | INSTRUEMNT CABLE INSTALLATION | GCP A PGB ELEC BLDG - GEN A ENGING | PS5-60-IE-0003A-CC15 | TZ-MID-68-WPR2-160102 SS Cables Tags not yet Install BOTH SIDE | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-27 | CPP EIT | Gao Chong |  |  |  |  | Open
5149 | PL-PS5-05149 | #VALUE! | CPP-RFI-68-64-04-0117 | PS5 | INSTRUEMNT CABLE INSTALLATION | GCP A PGB ELEC BLDG - GEN A ENGING | PS5-60-IE-0003A-CC03 | TZ-MID-68-WPR2-160102 SS Cables Tags not yet Install BOTH SIDE | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-27 | CPP EIT | Gao Chong |  |  |  |  | Open
5150 | PL-PS5-05150 | #VALUE! | CPP-RFI-68-64-04-0117 | PS5 | INSTRUEMNT CABLE INSTALLATION | GCP A PGB ELEC BLDG - GEN A ENGING | PS5-60-IE-0003A-CC04 | TZ-MID-68-WPR2-160102 SS Cables Tags not yet Install BOTH SIDE | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-27 | CPP EIT | Gao Chong |  |  |  |  | Open
5151 | PL-PS5-05151 | #VALUE! | CPP-RFI-68-64-04-0117 | PS5 | INSTRUEMNT CABLE INSTALLATION | GCP A PGB ELEC BLDG - GEN A ENGING | PS5-60-BI-0016A-CC02 | TZ-MID-68-WPR2-160102 SS Cables Tags not yet Install BOTH SIDE | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-27 | CPP EIT | Gao Chong |  |  |  |  | Open
5152 | PL-PS5-05152 | #VALUE! | CPP-RFI-68-64-11-0118 | PS5 | INSTRUEMNT CABLE INSTALLATION | GCP A PGB ELEC BLDG - GEN A ENGING | PS5-60-IE-0003A-CC02 | -PANEL PS5-60-IE-0001A and PS5-60-IE-0003A internal Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-27 | CPP EIT | Gao Chong |  |  |  |  | Open
5153 | PL-PS5-05153 | #VALUE! | CPP-RFI-68-64-11-0118 | PS5 | INSTRUEMNT CABLE INSTALLATION | GCP A PGB ELEC BLDG - GEN A ENGING | PS5-60-IE-0003A-CC15 | -PANEL PS5-60-IE-0002A and PS5-60-IE-0003A internal Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-27 | CPP EIT | Gao Chong |  |  |  |  | Open
5154 | PL-PS5-05154 | #VALUE! | CPP-RFI-68-64-11-0118 | PS5 | INSTRUEMNT CABLE INSTALLATION | GCP A PGB ELEC BLDG - GEN A ENGING | PS5-60-IE-0003A-CC03 | -PANEL PS5-60-IE-0001A and PS5-60-IE-0003A internal Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-27 | CPP EIT | Gao Chong |  |  |  |  | Open
5155 | PL-PS5-05155 | #VALUE! | CPP-RFI-68-64-11-0118 | PS5 | INSTRUEMNT CABLE INSTALLATION | GCP A PGB ELEC BLDG - GEN A ENGING | PS5-60-IE-0003A-CC04 | -PANEL PS5-60-IE-0001A and PS5-60-IE-0003A internal Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-27 | CPP EIT | Gao Chong |  |  |  |  | Open
5156 | PL-PS5-05156 | #VALUE! | CPP-RFI-68-64-11-0118 | PS5 | INSTRUEMNT CABLE INSTALLATION | GCP A PGB ELEC BLDG - GEN A ENGING | PS5-60-BI-0016A-CC02 | -PANEL JB - PS5-60-BI-0016A and PS5-60-IE-0003A internal Grounding not yet Done | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-27 | CPP EIT | Gao Chong |  |  |  |  | Open
5157 | PL-PS5-05157 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | EITS BUILDING - GENERATOR ELECTRICAL BUILDING | PS5-60-IE-0004-CD14 | TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-151166, Cable Tagging not yet done Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5158 | PL-PS5-05158 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | EITS BUILDING - GENERATOR ELECTRICAL BUILDING | PS5-60-IE-0004-CD15 | TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-151166, Cable Tagging not yet done Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5159 | PL-PS5-05159 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | EITS BUILDING - GENERATOR ELECTRICAL BUILDING | PS5-60-IE-0004-CD16 | TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-151166, Cable Tagging not yet done Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5160 | PL-PS5-05160 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IWK-0001A-CL01 | TZ-MID-68-WPR2-151166, Cable Tagging not yet done both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5161 | PL-PS5-05161 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IWK-0001A-CL02 | TZ-MID-68-WPR2-151166, Cable Tagging not yet done both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5162 | PL-PS5-05162 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | Outdoor Transformers PS5-61-IV-0002A to Generator Electrical Building | PS5-61-IK-0003-CL61 | TZ-MID-68-WPR2-151167, Cable Tagging not yet done both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5163 | PL-PS5-05163 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | EITS BUILDING - GENERATOR ELECTRICAL BUILDING | PS5-60-IE-0004-CD14 | TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-151166, Cable Dressing at Both Ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5164 | PL-PS5-05164 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | EITS BUILDING - GENERATOR ELECTRICAL BUILDING | PS5-60-IE-0004-CD15 | TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-151166, Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5165 | PL-PS5-05165 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | EITS BUILDING - GENERATOR ELECTRICAL BUILDING | PS5-60-IE-0004-CD16 | TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-151166, Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5166 | PL-PS5-05166 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IWK-0001A-CL01 | TZ-MID-68-WPR2-151166, Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5167 | PL-PS5-05167 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IWK-0001A-CL02 | TZ-MID-68-WPR2-151166, Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5168 | PL-PS5-05168 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | Outdoor Transformers PS5-61-IV-0002A to Generator Electrical Building | PS5-61-IK-0003-CL61 | TZ-MID-68-WPR2-151167, Cable Dressing at both ends | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5169 | PL-PS5-05169 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | EITS BUILDING - GENERATOR ELECTRICAL BUILDING | PS5-60-IE-0004-CD14 | TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-151166, Cable not reaching to final destination (Both Ends) | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5170 | PL-PS5-05170 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | EITS BUILDING - GENERATOR ELECTRICAL BUILDING | PS5-60-IE-0004-CD15 | TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-151166, Cable not reaching to final destination (Both Ends) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5171 | PL-PS5-05171 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | EITS BUILDING - GENERATOR ELECTRICAL BUILDING | PS5-60-IE-0004-CD16 | TZ-MID-68-SSF1-240000, TZ-MID-68-WPR2-151166, Cable not reaching to final destination (Both Ends) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5172 | PL-PS5-05172 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IWK-0001A-CL01 | TZ-MID-68-WPR2-151166, Cable not reaching to final destination (Both ends) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5173 | PL-PS5-05173 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | Generator Electrical Building | PS5-60-IWK-0001A-CL02 | TZ-MID-68-WPR2-151166, Cable not reaching to final destination (Both Ends) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5174 | PL-PS5-05174 | #VALUE! | CPP-RFI-68-33/1-05-0438 | PS5 | Electrical Cable Installation | Outdoor Transformers PS5-61-IV-0002A to Generator Electrical Building | PS5-61-IK-0003-CL61 | TZ-MID-68-WPR2-151167, Cable Not Reaching to final destination (Both Ends) | A | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-28 | CPP EIT | Gao Chong |  |  |  |  | Open
5175 | PL-PS5-05175 | #VALUE! | CPP-RFI-68-331-06-0435 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IH-0001A-CL01 | TZ-MID-68-WPR2-151166 Earthing Tag of the cable gland shall be connected to the earthing stud/bar at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5176 | PL-PS5-05176 | #VALUE! | CPP-RFI-68-331-06-0435 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IH-0001A-CL02 | TZ-MID-68-WPR2-151166 Earthing Tag of the cable gland shall be connected to the earthing stud/bar at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5177 | PL-PS5-05177 | #VALUE! | CPP-RFI-68-331-06-0435 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IH-0001A-CL03 | TZ-MID-68-WPR2-151166 Earthing Tag of the cable gland shall be connected to the earthing stud/bar at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5178 | PL-PS5-05178 | #VALUE! | CPP-RFI-68-331-06-0435 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IH-0001A-CL04 | TZ-MID-68-WPR2-151166 Earthing Tag of the cable gland shall be connected to the earthing stud/bar at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5179 | PL-PS5-05179 | #VALUE! | CPP-RFI-68-331-06-0435 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IH-0001B-CL01 | TZ-MID-68-WPR2-151166 Earthing Tag of the cable gland shall be connected to the earthing stud/bar at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5180 | PL-PS5-05180 | #VALUE! | CPP-RFI-68-331-06-0435 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IH-0001B-CL02 | TZ-MID-68-WPR2-151166 Earthing Tag of the cable gland shall be connected to the earthing stud/bar at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5181 | PL-PS5-05181 | #VALUE! | CPP-RFI-68-331-06-0435 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IH-0001B-CL03 | TZ-MID-68-WPR2-151166 Earthing Tag of the cable gland shall be connected to the earthing stud/bar at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5182 | PL-PS5-05182 | #VALUE! | CPP-RFI-68-331-06-0435 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IH-0001B-CL04 | TZ-MID-68-WPR2-151166 Earthing Tag of the cable gland shall be connected to the earthing stud/bar at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5183 | PL-PS5-05183 | #VALUE! | CPP-RFI-68-331-06-0435 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IH-0001A-CL01 | TZ-MID-68-WPR2-151166 Core marking to be installed at both side | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5184 | PL-PS5-05184 | #VALUE! | CPP-RFI-68-331-06-0435 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IH-0001A-CL02 | TZ-MID-68-WPR2-151166 Core marking to be installed at both side | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5185 | PL-PS5-05185 | #VALUE! | CPP-RFI-68-331-06-0435 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IH-0001A-CL03 | TZ-MID-68-WPR2-151166 Core marking to be installed at both side | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5186 | PL-PS5-05186 | #VALUE! | CPP-RFI-68-331-06-0435 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IH-0001A-CL04 | TZ-MID-68-WPR2-151166 Core marking to be installed at both side | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5187 | PL-PS5-05187 | #VALUE! | CPP-RFI-68-331-06-0435 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IH-0001B-CL01 | TZ-MID-68-WPR2-151166 Core marking to be installed at both side | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5188 | PL-PS5-05188 | #VALUE! | CPP-RFI-68-331-06-0435 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IH-0001B-CL02 | TZ-MID-68-WPR2-151166 Core marking to be installed at both side | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5189 | PL-PS5-05189 | #VALUE! | CPP-RFI-68-331-06-0435 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IH-0001B-CL03 | TZ-MID-68-WPR2-151166 Core marking to be installed at both side | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5190 | PL-PS5-05190 | #VALUE! | CPP-RFI-68-331-06-0435 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IH-0001B-CL04 | TZ-MID-68-WPR2-151166 Core marking to be installed at both side | C | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5191 | PL-PS5-05191 | #VALUE! | CPP-RFI-68-64-07-0127 | PS5 | Instrument installation | Gen. Electrical Building A and B | PS5-60-PG-0002A | TZ-MID-68-WPR2-161502 Permanent tags and hanging tags to be installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5192 | PL-PS5-05192 | #VALUE! | CPP-RFI-68-64-07-0127 | PS5 | Instrument installation | Gen. Electrical Building A and B | PS5-60-PG-0002B | TZ-MID-68-WPR2-161502 Permanent tags and hanging tags to be installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5193 | PL-PS5-05193 | #VALUE! | CPP-RFI-68-33/1-08-0442 | PS5 | EHT SR cable Installaation | PGB | PS5-79-TE-0264 | SS tag to be installed in all Accessories | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5194 | PL-PS5-05194 | #VALUE! | CPP-RFI-68-33/1-08-0442 | PS5 | EHT SR cable Installaation | PGB | PS5-79-BE-0264 | SS tag to be installed in all Accessories | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open | PL-PS5-05195 | #VALUE!
5195 | PL-PS5-05195 | #VALUE! | CPP-RFI-68-33/1-08-0442 | PS5 | EHT SR cable Installaation | PGB | PS5-79-BE-0265 | SS tag to be installed in all Accessories | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5196 | PL-PS5-05196 | #VALUE! | CPP-RFI-68-33/1-08-0442 | PS5 | EHT SR cable Installaation | PGB | PS5-79-TE-0265 | SS tag to be installed in all Accessories | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5197 | PL-PS5-05197 | #VALUE! | CPP-RFI-68-33/1-08-0442 | PS5 | EHT SR cable Installaation | PGB | PS5-79-BE-0266 | SS tag to be installed in all Accessories | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5198 | PL-PS5-05198 | #VALUE! | CPP-RFI-68-33/1-08-0442 | PS5 | EHT SR cable Installaation | PGB | PS5-79-TE-0266 | SS tag to be installed in all Accessories | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5199 | PL-PS5-05199 | #VALUE! | CPP-RFI-68-33/1-08-0442 | PS5 | EHT SR cable Installaation | PGB | PS5-79-BE-0267 | SS tag to be installed in all Accessories | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5200 | PL-PS5-05200 | #VALUE! | CPP-RFI-68-33/1-08-0442 | PS5 | EHT SR cable Installaation | PGB | PS5-79-TE-0267 | SS tag to be installed in all Accessories | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5201 | PL-PS5-05201 | #VALUE! | CPP-RFI-68-33/1-08-0442 | PS5 | EHT SR cable Installaation | PGB | PS5-79-BE-0327 | SS tag to be installed in all Accessories | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5202 | PL-PS5-05202 | #VALUE! | CPP-RFI-68-33/1-08-0442 | PS5 | EHT SR cable Installaation | PGB | PS5-79-TE-0327 | SS tag to be installed in all Accessories | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5203 | PL-PS5-05203 | #VALUE! | CPP-RFI-68-33/1-08-0442 | PS5 | EHT SR cable Installaation | PGB | PS5-79-BE-0330 | SS tag to be installed in all Accessories | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5204 | PL-PS5-05204 | #VALUE! | CPP-RFI-68-33/1-08-0442 | PS5 | EHT SR cable Installaation | PGB | PS5-79-TE-0330 | SS tag to be installed in all Accessories | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5205 | PL-PS5-05205 | #VALUE! | CPP-RFI-68-64-03-0120 | PS5 | Instrument Cable Ladder Installation | PGB-Radiator | N/A | Doc.TZ-MID-68-WPR2-161500 Bolts tightening on connection plates to be completed | C | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5206 | PL-PS5-05206 | #VALUE! | CPP-RFI-68-64-03-0120 | PS5 | Instrument Cable Ladder Installation | PGB-Radiator | N/A | Doc.TZ-MID-68-WPR2-161500 Earth jumper not installed completely | A | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5207 | PL-PS5-05207 | #VALUE! | CPP-RFI-68-64-03-0120 | PS5 | Instrument Cable Ladder Installation | PGB-Radiator | N/A | Doc.TZ-MID-68-WPR2-161500 Cover not installed | B | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5208 | PL-PS5-05208 | #VALUE! | CPP-RFI-68-64-03-0120 | PS5 | Instrument Cable Ladder Installation | PGB-Radiator | N/A | DocTZ-MID-68-WPR2-161500 Grommets not installed | C | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5209 | PL-PS5-05209 | #VALUE! | CPP-RFI-68-64-03-0120 | PS5 | Instrument Cable Ladder Installation | PGB-Radiator | N/A | TZ-MID-68-WPR2-161500 Kick Plate to be Installed | C | Instrument | CPY | Konstantin Ovchinnikov | 2026-07-29 | CPP EIT | Gao Chong |  |  |  |  | Open
5210 | PL-PS5-05210 | #VALUE! | CPP-RFI-68-33/1-08-0447 | PS5 | EHT SR cable Installaation |  | PS5-79-TE-0260 | SS tag to be installed in all Accessories | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-30 | CPP EIT | Gao Chong |  |  |  |  | Open
5211 | PL-PS5-05211 | #VALUE! | CPP-RFI-68-33/1-08-0447 | PS5 | EHT SR cable Installaation |  | PS5-79-BE-0260 | SS tag to be installed in all Accessories | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-30 | CPP EIT | Gao Chong |  |  |  |  | Open
5212 | PL-PS5-05212 | #VALUE! | CPP-RFI-68-33/1-08-0447 | PS5 | EHT SR cable Installaation |  | PS5-79-BE-0261 | SS tag to be installed in all Accessories | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-30 | CPP EIT | Gao Chong |  |  |  |  | Open
5213 | PL-PS5-05213 | #VALUE! | CPP-RFI-68-33/1-08-0447 | PS5 | EHT SR cable Installaation |  | PS5-79-TE-0261 | SS tag to be installed in all Accessories | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-07-30 | CPP EIT | Gao Chong |  |  |  |  | Open
5214 | PL-PS5-05214 | #VALUE! | CPP-RFI-68-33/1-06-0452 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IE-0003A-CD02 | TZ-MID-68-WPR2-151166 Earthing Tag of the cable gland shall be connected to the earthing stud/bar at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-08-01 | CPP EIT | Gao Chong |  |  |  |  | Open
5215 | PL-PS5-05215 | #VALUE! | CPP-RFI-68-33/1-06-0452 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IE-0003A-CD03 | TZ-MID-68-WPR2-151166 Earthing Tag of the cable gland shall be connected to the earthing stud/bar at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-08-01 | CPP EIT | Gao Chong |  |  |  |  | Open
5216 | PL-PS5-05216 | #VALUE! | CPP-RFI-68-33/1-06-0452 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IE-0003A-CD05 | TZ-MID-68-WPR2-151166 Earthing Tag of the cable gland shall be connected to the earthing stud/bar at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-08-01 | CPP EIT | Gao Chong |  |  |  |  | Open
5217 | PL-PS5-05217 | #VALUE! | CPP-RFI-68-33/1-06-0452 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IE-0003A-CD06 | TZ-MID-68-WPR2-151166 Earthing Tag of the cable gland shall be connected to the earthing stud/bar at GCP-A Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-08-01 | CPP EIT | Gao Chong |  |  |  |  | Open
5218 | PL-PS5-05218 | #VALUE! | CPP-RFI-68-33/1-06-0452 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IE-0003A-CD08 | TZ-MID-68-WPR2-151166 Earthing Tag of the cable gland shall be connected to the earthing stud/bar at GCP-A Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-08-01 | CPP EIT | Gao Chong |  |  |  |  | Open
5219 | PL-PS5-05219 | #VALUE! | CPP-RFI-68-33/1-06-0452 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IE-0003A-CD12 | TZ-MID-68-WPR2-151166 Earthing Tag of the cable gland shall be connected to the earthing stud/bar at GCP-A Side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-08-01 | CPP EIT | Gao Chong |  |  |  |  | Open
5220 | PL-PS5-05220 | #VALUE! | CPP-RFI-68-33/1-06-0452 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-60-IE-0003A-CD14 | TZ-MID-68-WPR2-151166 Earthing Tag of the cable gland shall be connected to the earthing stud/bar at both side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-08-01 | CPP EIT | Gao Chong |  |  |  |  | Open
5221 | PL-PS5-05221 | #VALUE! | CPP-RFI-68-33/1-06-0452 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-71-DM-3500A-CL01 | TZ-MID-68-WPR2-151166 Earthing stud of motor not connected to earthing boss at field side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-08-01 | CPP EIT | Gao Chong |  |  |  |  | Open
5222 | PL-PS5-05222 | #VALUE! | CPP-RFI-68-33/1-06-0452 | PS5 | Electrical Cable Gland and Termination | Generator Electrical Building | PS5-71-DM-3500B-CL01 | TZ-MID-68-WPR2-151166 Earthing stud of motor not connected to earthing boss at field side | B | Electrical | CPY | Konstantin Ovchinnikov | 2026-08-01 | CPP EIT | Gao Chong |  |  |  |  | Open
5223 | PL-PS5-05223 | #VALUE! | CPP-RFI-68-64-12-0132 | PS5 | Instrument installation | Gen. Electrical Building C and D | PS5-60-TG-0008C | TZ-MID-68-WPR2-161502 Permanent tags and hanging tags to be installed | B
5224 | PL-PS5-05224 | #VALUE! | CPP-RFI-68-64-12-0132 | PS5 | Instrument installation | Gen. Electrical Building C and D | PS5-60-TG-0007C | TZ-MID-68-WPR2-161502 Permanent tags and hanging tags to be installed | B
5225 | PL-PS5-05225 | #VALUE! | CPP-RFI-68-64-12-0132 | PS5 | Instrument installation | Gen. Electrical Building C and D | PS5-60-TG-0006C | TZ-MID-68-WPR2-161502 Permanent tags and hanging tags to be installed | B
5226 | PL-PS5-05226 | #VALUE! | CPP-RFI-68-64-12-0132 | PS5 | Instrument installation | Gen. Electrical Building C and D | PS5-60-TG-0005C | TZ-MID-68-WPR2-161502 Permanent tags and hanging tags to be installed | B
5227 | PL-PS5-05227 | #VALUE! | CPP-RFI-68-64-12-0132 | PS5 | Instrument installation | Gen. Electrical Building C and D | PS5-60-PG-0002C | TZ-MID-68-WPR2-161502 Permanent tags and hanging tags to be installed | B
5228 | PL-PS5-05228 | #VALUE! | CPP-RFI-68-64-12-0132 | PS5 | Instrument installation | Gen. Electrical Building C and D | PS5-60-PG-0002D | TZ-MID-68-WPR2-161502 Permanent tags and hanging tags to be installed | B
| PL-PS5-05229 | #VALUE!

## SUM
OVERALL PUNCHLIST STATUS
TOTAL PL | 4982
OPEN | 4016
CLOSED | 966 | Paste PL No. Here To Check In MP Register
PL-PS5-03673
PL-PS5-03674
PL-PS5-03675
PL-PS5-03676
PL-PS5-03677
PL-PS5-03678
PL-PS5-03679
PL-PS5-03680
PL-PS5-03681
PL-PS5-03682
PL-PS5-03683
PL-PS5-03684
PL-PS5-03685
PL-PS5-03686
PL-PS5-03687
PL-PS5-03688
PL-PS5-03689
PL-PS5-03690
PL-PS5-03691
PL-PS5-03692
PL-PS5-03696